## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 133307281 | 132226122 | 136428741 | 136375040 | -92500 | 136081028 | 2.915% | 94.74% | 3048213 | 2.305% | 3121461 | 2.342% | 5200 | 1234 | 23.73% | 497 | 9.558% | 83 | 1.596% | 437 | 8.404% | 5720 | 10% | 7507 | 7312 | 5581 | 7.327% | 78.95%
| District Let | 328681947 | 327163070 | 331523786 | 332496116 | 941500 | 335300771 | 2.487% | 100% | 2109575 | 0.6448% | 2841837 | 0.8646% | 7315 | 1169 | 15.98% | 595 | 8.134% | 67 | 0.9159% | 171 | 2.338% | 7553 | 3.254% | 9252 | 8630 | 6866 | -6.138% | 90.48%
| All Contracts | 461989228 | 459389192 | 467952527 | 468871156 | 849000 | 471381799 | 2.611% | 97.5% | 5157788 | 1.123% | 5963298 | 1.291% | 12515 | 2403 | 19.2% | 1092 | 8.726% | 150 | 1.199% | 608 | 4.858% | 13273 | 6.057% | 16759 | 15942 | 12447 | -0.5433% | 85%
2 | Central Let | 455361878 | 451959098 | 506749318 | 521172416 | 0 | 522110186 | 15.52% | 83.33% | 52196463 | 11.55% | 51387438 | 11.28% | 13284 | 4421 | 33.28% | 2137 | 16.09% | 1600 | 12.04% | 3744 | 28.18% | 18628 | 40.23% | 23804 | 23123 | 16565 | 24.7% | 61.9%
| District Let | 51508550 | 50988315 | 66671266 | 67764611 | 0 | 67752714 | 32.88% | 66.67% | 15361906 | 30.13% | 15162716 | 29.44% | 2939 | 777 | 26.44% | 407 | 13.85% | 503 | 17.11% | 711 | 24.19% | 4153 | 41.31% | 4964 | 4952 | 3768 | 28.21% | 50%
| All Contracts | 506870428 | 502947413 | 573420584 | 588937027 | 0 | 589862900 | 17.28% | 81.25% | 67558369 | 13.43% | 66550154 | 13.13% | 16223 | 5198 | 32.04% | 2544 | 15.68% | 2103 | 12.96% | 4455 | 27.46% | 22781 | 40.42% | 28768 | 28075 | 20333 | 25.33% | 60.42%
3 | Central Let | 158613858 | 157039319 | 165197106 | 169374174 | 0 | 171433148 | 9.166% | 77.27% | 7089348 | 4.514% | 6583248 | 4.15% | 7169 | 2479 | 34.58% | 1175 | 16.39% | 1442 | 20.11% | 1006 | 14.03% | 9617 | 34.15% | 12788 | 12768 | 9114 | 27.13% | 50%
| District Let | 80955525 | 79794923 | 81446973 | 81952414 | 0 | 81025988 | 1.543% | 100% | 583804 | 0.7316% | 491449 | 0.6071% | 4812 | 1402 | 29.14% | 869 | 18.06% | 1299 | 27% | 357 | 7.419% | 6468 | 34.41% | 8300 | 8269 | 5998 | 24.65% | 65.22%
| All Contracts | 239569383 | 236834242 | 246644079 | 251326588 | 0 | 252459136 | 6.597% | 88.89% | 7673152 | 3.24% | 7074697 | 2.953% | 11981 | 3881 | 32.39% | 2044 | 17.06% | 2741 | 22.88% | 1363 | 11.38% | 16085 | 34.25% | 21088 | 21037 | 15112 | 26.13% | 57.78%
4 | Central Let | 154197905 | 152450738 | 157168851 | 154814028 | 0 | 155055685 | 1.709% | 100% | 2490780 | 1.634% | 3491674 | 2.264% | 7879 | 1757 | 22.3% | 668 | 8.478% | 324 | 4.112% | 241 | 3.059% | 8444 | 7.171% | 10735 | 10382 | 7957 | 0.99% | 95.65%
| District Let | 256546225 | 255271563 | 286712853 | 285724638 | 56000 | 285031498 | 11.66% | 90% | 30061765 | 11.78% | 30124498 | 11.74% | 6515 | 1513 | 23.22% | 603 | 9.256% | 1199 | 18.4% | 615 | 9.44% | 8329 | 27.84% | 10295 | 9996 | 7880 | 20.95% | 90%
| All Contracts | 410744130 | 407722301 | 443881704 | 440538666 | 56000 | 440087183 | 7.938% | 95.35% | 32552545 | 7.984% | 33616172 | 8.184% | 14394 | 3270 | 22.72% | 1271 | 8.83% | 1523 | 10.58% | 856 | 5.947% | 16773 | 16.53% | 21030 | 20378 | 15837 | 10.03% | 93.02%
5 | Central Let | 287406286 | 284930480 | 298797461 | 299816316 | 0 | 299674140 | 5.174% | 96.43% | 11632167 | 4.082% | 11960908 | 4.162% | 10090 | 2585 | 25.62% | 2247 | 22.27% | 32 | 0.3171% | 1153 | 11.43% | 11275 | 11.74% | 16001 | 15793 | 10961 | 8.632% | 82.14%
| District Let | 387190388 | 385490512 | 403528005 | 403808310 | 25000 | 404353226 | 4.893% | 100% | 16789497 | 4.355% | 16337617 | 4.22% | 7407 | 1624 | 21.93% | 2010 | 27.14% | 0 | 0% | 576 | 7.776% | 7983 | 7.776% | 11609 | 11493 | 7859 | 6.102% | 92%
| All Contracts | 674596674 | 670420992 | 702325466 | 703624626 | 25000 | 704027366 | 5.013% | 98.11% | 28421664 | 4.239% | 28298525 | 4.195% | 17497 | 4209 | 24.06% | 4257 | 24.33% | 32 | 0.1829% | 1729 | 9.882% | 19258 | 10.06% | 27610 | 27286 | 18820 | 7.561% | 86.79%
6 | Central Let | 124589477 | 123233123 | 126870666 | 124575886 | 3200000 | 124301702 | 0.8671% | 100% | 2451571 | 1.989% | 2281188 | 1.831% | 6041 | 729 | 12.07% | 406 | 6.721% | 22 | 0.3642% | 105 | 1.738% | 6168 | 2.102% | 7303 | 6542 | 5407 | -10.49% | 100%
| District Let | 156162912 | 155460924 | 160212048 | 157966777 | 3640000 | 149475670 | -3.85% | 100% | 3987153 | 2.565% | 4049136 | 2.593% | 4618 | 505 | 10.94% | 354 | 7.666% | 0 | 0% | 410 | 8.878% | 5028 | 8.878% | 6027 | 5786 | 4927 | 6.691% | 87.5%
| All Contracts | 280752389 | 278694047 | 287082714 | 282542663 | 6840000 | 273777372 | -1.764% | 100% | 6438724 | 2.31% | 6330324 | 2.255% | 10659 | 1234 | 11.58% | 760 | 7.13% | 22 | 0.2064% | 515 | 4.832% | 11196 | 5.038% | 13330 | 12328 | 10334 | -3.049% | 96.15%
7 | Central Let | 234588365 | 233024203 | 247526356 | 250572236 | 865160 | 249519272 | 7.079% | 88.24% | 10092876 | 4.331% | 12937989 | 5.515% | 5908 | 1140 | 19.3% | 491 | 8.311% | 163 | 2.759% | 196 | 3.318% | 6267 | 6.077% | 7743 | 7318 | 5687 | -3.741% | 94.12%
| District Let | 254992451 | 253744072 | 271272236 | 271228263 | 1450000 | 271356770 | 6.941% | 93.75% | 13003282 | 5.125% | 16279786 | 6.384% | 6254 | 1138 | 18.2% | 525 | 8.395% | 266 | 4.253% | 586 | 9.37% | 7106 | 13.62% | 8509 | 8048 | 6385 | 2.095% | 100%
| All Contracts | 489580816 | 486768275 | 518798592 | 521800499 | 2315160 | 520876042 | 7.007% | 90.91% | 23096158 | 4.745% | 29217775 | 5.968% | 12162 | 2278 | 18.73% | 1016 | 8.354% | 429 | 3.527% | 782 | 6.43% | 13373 | 9.957% | 16252 | 15366 | 12072 | -0.74% | 96.97%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 234788022 | 233425250 | 250834937 | 249408424 | 4781946 | 247229288 | 5.914% | 92.86% | 16367446 | 7.012% | 16046914 | 6.835% | 6794 | 910 | 13.39% | 688 | 10.13% | 137 | 2.016% | 195 | 2.87% | 7126 | 4.887% | 8620 | 7653 | 6055 | -10.88% | #VALUE!
| All Contracts | 234788022 | 233425250 | 250834937 | 249408424 | 4781946 | 247229288 | 5.914% | 92.86% | 16367446 | 7.012% | 16046914 | 6.835% | 6794 | 910 | 13.39% | 688 | 10.13% | 137 | 2.016% | 195 | 2.87% | 7126 | 4.887% | 8620 | 7653 | 6055 | -10.88% | 100%
Totals This Qtr | Central Let | 1548065050 | 1534863083 | 1638738499 | 1656700096 | 3972660 | 1658175161 | 8.034% | 90.53% | 89001418 | 5.799% | 91763906 | 5.928% | 55571 | 14345 | 25.81% | 7621 | 13.71% | 3666 | 6.597% | 6882 | 12.38% | 66119 | 18.98% | 85881 | 83238 | 61272 | 10.26% | 77.51%
| District Let | 1750826020 | 1741338629 | 1852202104 | 1850349553 | 10894446 | 1841525925 | 5.753% | 95.49% | 98264428 | 5.643% | 101333953 | 5.788% | 46654 | 9038 | 19.37% | 6051 | 12.97% | 3471 | 7.44% | 3621 | 7.761% | 53746 | 15.2% | 67576 | 64827 | 49738 | 6.61% | 86.47%
| All Contracts | 3298891070 | 3276201712 | 3490940603 | 3507049649 | 14867106 | 3499701086 | 6.822% | 92.72% | 187265846 | 5.716% | 193097859 | 5.853% | 102225 | 23383 | 22.87% | 13672 | 13.37% | 7137 | 6.982% | 10503 | 10.27% | 119865 | 17.26% | 153457 | 148065 | 111010 | 8.594% | 81.46%
Totals Previous Quarter | Central Let | 918828742 | 910894764 | 951249983 | 962059795 | 1842660 | 960152134 | 5.408% | 91.26% | 31146991 | 3.419% | 32421236 | 3.529% | 32299 | 8657 | 26.8% | 4610 | 14.27% | 1995 | 6.177% | 2826 | 8.749% | 37120 | 14.93% | 49226 | 47737 | 34470 | 6.722% | 80.58%
| District Let | 1013381397 | 1007214349 | 1081863455 | 1081278396 | 3612398 | 1075205834 | 6.75% | 94.51% | 65555095 | 6.509% | 68439925 | 6.754% | 29589 | 6115 | 20.67% | 4418 | 14.93% | 1564 | 5.286% | 2593 | 8.763% | 33746 | 14.05% | 43431 | 41870 | 31337 | 5.908% | 87.91%
| All Contracts | 1932210139 | 1918109113 | 2033113438 | 2043338191 | 5455058 | 2035357968 | 6.113% | 92.78% | 96702086 | 5.042% | 100861161 | 5.22% | 61888 | 14772 | 23.87% | 9028 | 14.59% | 3559 | 5.751% | 5419 | 8.756% | 70866 | 14.51% | 92657 | 89607 | 65807 | 6.332% | 84.02%
Totals Fiscal Year 2024/2025 | Central Let | 1279648903 | 1266221414 | 1312978963 | 1321473742 | 2536230 | 1326167192 | 4.734% | 90.72% | 35949687 | 2.839% | 33549474 | 2.622% | 54906 | 16687 | 30.39% | 7064 | 12.87% | 4509 | 8.212% | 6770 | 12.33% | 66185 | 20.54% | 86228 | 84771 | 61020 | 11.14% | 80.93%
| District Let | 1318833837 | 1310154031 | 1361025980 | 1368896349 | 5751239 | 1365653292 | 4.236% | 92.91% | 42375966 | 3.234% | 42720355 | 3.239% | 43619 | 9909 | 22.72% | 5114 | 11.72% | 2675 | 6.133% | 2106 | 4.828% | 48400 | 10.96% | 62882 | 61439 | 46416 | 6.412% | 89.76%
| All Contracts | 2598482740 | 2576375445 | 2674004943 | 2690370091 | 8287469 | 2691820484 | 4.481% | 91.59% | 78325653 | 3.04% | 76269829 | 2.935% | 98525 | 26596 | 26.99% | 12178 | 12.36% | 7184 | 7.292% | 8876 | 9.009% | 114585 | 16.3% | 149110 | 146210 | 107436 | 9.044% | 84.42%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1754 | 41924345201 | 2020-06-10 | QTR4 | 19/20 | 1 | 8 | 1300 | 1542 | 1316 | 82.62% | 1 | 226 | 0 | 0 | 242 | 0 | 44711727 | 150000 | 44561727 | 45332170 | 44869139 | 0 | 0 | 0 | 44869139 | 45508351 | 102.1% | 1 | 2409623 | 620443 | 176 | 66 | 0 | 0 | 75074 | 0 | 0 | 0 | 369025 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65721 | 0 | 0 | 0 | 2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656851 | 70927 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2024-04-12 | QTR4 | 23/24 | 118 | 49671695.98
| 01 | T1801 | 43355055201 | 2022-02-23 | QTR3 | 21/22 | 4 | 11 | 450 | 785 | 785 | 145.6% | 0 | 0 | 0 | 0 | 157 | 178 | 9943982 | 61935 | 9882047 | 10795145 | 10516274 | 0 | 0 | 0 | 10516274 | 10451415 | 105.8% | 1 | 22951 | 851163 | 75 | 55 | 0 | 10 | 59915 | 0 | 14 | 35 | 107389 | 65872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 0 | 0 | 60900 | 0 | 0 | 0 | 314 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 15101 | 0 | 0 | 0 | 0 | 0 | 10 | 133 | 534836 | 45203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 178 | 784204 | 111075 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2026-01-26 | QTR3 | 25/26 |  | 2024-12-23 | QTR2 | 24/25 | 115 | 8613987.04
| 01 | T1807 | 44464115201 | 2023-05-24 | QTR4 | 22/23 | 2 | 8 | 250 | 356 | 355 | 112.4% | 1 | 1 | 0 | 0 | 95 | 11 | 5486544 | 50000 | 5436544 | 5582663 | 5697293 | -30000 | 0 | -30000 | 5667293 | 5634025 | 103.6% | 1 | -212 | 96120 | 56 | 18 | 21 | 11 | 58440 | 0 | 0 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 1490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 11 | 77189 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-18 | QTR3 | 25/26 |  | 2025-04-21 | QTR4 | 24/25 | 118 | 4275732.4
| 01 | T1833 | 44634515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 300 | 472 | 471 | 99.67% | 1 | 1 | 0 | 0 | 172 | 0 | 16756829 | 150000 | 16606829 | 16756829 | 16918647 | 0 | -70500 | -70500 | 16848147 | 16748453 | 100.9% | 1 | -99694 | 0 | 136 | 36 | 0 | 0 | 23670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2023-12-05 | QTR2 | 23/24 | 106 | 17387334.58
| 01 | T1843 | 43695525201 | 2022-07-27 | QTR1 | 22/23 | 1 | 6 | 225 | 443 | 443 | 107.6% | 1 | 0 | 0 | 0 | 201 | 17 | 4165582 | 50000 | 4115582 | 4197230 | 4319692 | 0 | 0 | 0 | 4319692 | 4254744 | 103.4% | 1 | -56953 | 31648 | 155 | 46 | 0 | 17 | 23652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 23652 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-08-27 | QTR1 | 25/26 |  | 2025-01-17 | QTR3 | 24/25 | 113 | 3563244.72
| 01 | T1850 | 43944115201 | 2024-04-24 | QTR4 | 23/24 | 1 | 4 | 400 | 457 | 457 | 100% | 1 | 0 | 0 | 0 | 57 | 0 | 5279314 | 0 | 5279314 | 5778359 | 5716286 | 0 | 0 | 0 | 5716286 | 5630083 | 106.6% | 1 | -2290 | 499045 | 41 | 16 | 0 | 0 | 149726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349371 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-10-28 | QTR2 | 25/26 | 108 | 7929522.13
| 01 | T1852 | 44787215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 0 | 175 | 207 | 204 | 98.29% | 1 | 3 | 0 | 0 | 32 | 0 | 3084175 | 50000 | 3034175 | 3084175 | 3074445 | 0 | 0 | 0 | 3074445 | 3073651 | 101.3% | 1 | -795 | 0 | 14 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 115 | 2364265.94
| 01 | T1854 | 44480735201 | 2024-03-27 | QTR3 | 23/24 | 1 | 1 | 125 | 192 | 182 | 108% | 1 | 10 | 0 | 0 | 47 | 20 | 1273662 | 46380 | 1227282 | 1300460 | 1232804 | 0 | -22000 | -22000 | 1210804 | 1210162 | 98.61% | 1 | -642 | 26799 | 27 | 20 | 0 | 20 | 26799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 26799 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 115 | 1109604.92
| 01 | T1855 | 44547315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 5 | 300 | 577 | 607 | 143.7% | 0 | -30 | 30 | 0 | 176 | 101 | 11238774 | 116686 | 11122088 | 11323365 | 11568463 | -143070 | 0 | -143070 | 11425393 | 11375607 | 102.3% | 1 | -39102 | 84591 | 129 | 47 | 0 | 0 | 107185 | 0 | 0 | 101 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 114493 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 118 | 12534705.29
| 01 | T1866 | 43903215201 | 2023-11-15 | QTR2 | 23/24 | 2 | 4 | 225 | 301 | 330 | 117.8% | 1 | -29 | 29 | 0 | 65 | 11 | 3945642 | 68014 | 3877628 | 4078353 | 4013289 | -76850 | 0 | -76850 | 3936439 | 3832582 | 98.84% | 1 | -14467 | 132711 | 40 | 25 | 0 | 9 | 43321 | 0 | 0 | 2 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 45054 | 0 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-03-20 | QTR3 | 24/25 | 118 | 5005578.39
| 01 | T1867 | 44546715201 | 2024-01-31 | QTR3 | 23/24 | 2 | 4 | 250 | 361 | 352 | 120.4% | 0 | 9 | 0 | 0 | 83 | 28 | 7502026 | 73856 | 7428170 | 8082796 | 8181304 | 0 | 0 | 0 | 8181304 | 8176865 | 110.1% | 0 | -4440 | 580770 | 30 | 21 | 3 | 9 | 370939 | 0 | 3 | 0 | 23365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 201258 | 0 | 0 | 0 | 12662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 28 | 608224 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-02-11 | QTR3 | 25/26 |  | 2025-11-21 | QTR2 | 25/26 | 108 | 7936833.12
| 01 | T1868 | 44740215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 2 | 100 | 207 | 206 | 128% | 0 | 1 | 0 | 0 | 107 | 0 | 1036497 | 45938 | 990559 | 1074999 | 1074468 | 0 | 0 | 0 | 1074468 | 1035967 | 104.6% | 1 | 0 | 38502 | 57 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 115 | 1164568.56
| 01 | T1873 | 44788015201 | 2024-02-28 | QTR3 | 23/24 | 2 | 3 | 200 | 287 | 285 | 99% | 1 | 2 | 0 | 0 | 87 | 0 | 2902791 | 50000 | 2852791 | 2941983 | 2705963 | 0 | 0 | 0 | 2705963 | 2704866 | 94.81% | 1 | -1098 | 39192 | 78 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 65279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65279 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-02-02 | QTR3 | 25/26 |  | 2025-11-07 | QTR2 | 25/26 | 113 | 2895926.83
| 01 | T1881 | 43802715201 | 2023-11-15 | QTR2 | 23/24 | 2 | 1 | 200 | 310 | 310 | 108% | 1 | 0 | 0 | 0 | 94 | 16 | 6196035 | 68350 | 6127685 | 6206737 | 6556044 | 0 | 0 | 0 | 6556044 | 6524950 | 106.5% | 1 | -31093 | 10701 | 70 | 24 | 0 | 16 | 12210 | 0 | 0 | 0 | 19772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 31982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-04-02 | QTR4 | 24/25 | 108 | 6886950.71
| 01 | T1889 | 44431315201 | 2024-03-27 | QTR3 | 23/24 | 2 | 1 | 200 | 346 | 346 | 115% | 1 | 0 | 0 | 0 | 116 | 0 | 2636284 | 50000 | 2586284 | 2666046 | 2714680 | -3800 | 0 | -3800 | 2710880 | 2705941 | 104.6% | 1 | -4939 | 29762 | 88 | 28 | 0 | 0 | 6254 | 0 | 0 | 0 | 60445 | 15459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66698 | 15459 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-27 | QTR3 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 108 | 3253356.71
| 01 | T1891 | 44743625201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 175 | 235 | 235 | 112% | 1 | 0 | 0 | 0 | 39 | 21 | 4742624 | 50000 | 4692624 | 4787027 | 4779994 | 0 | 0 | 0 | 4779994 | 4777172 | 101.8% | 1 | -2822 | 44403 | 18 | 21 | 0 | 0 | 0 | 0 | 0 | 21 | 50051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -585 | 0 | 0 | 0 | 13168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 62635 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-10 | QTR2 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 108 | 4605369.8
| 01 | T1895 | 44656015201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 125 | 169 | 169 | 119.2% | 1 | 0 | 0 | 0 | 20 | 24 | 1414901 | 0 | 1414901 | 1450512 | 1460078 | 0 | 0 | 0 | 1460078 | 1460017 | 103.2% | 1 | -61 | 35611 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-07-28 | QTR1 | 25/26 | 108 | 1992638.1
| 01 | T1905 | 44645215201 | 2025-01-29 | QTR3 | 24/25 | 1 | 1 | 100 | 144 | 144 | 110% | 1 | 0 | 0 | 0 | 34 | 10 | 574929 | 0 | 574929 | 574929 | 554144 | 0 | 0 | 0 | 554144 | 554144 | 96.38% | 1 | 0 | 0 | 28 | 6 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-02-02 | QTR3 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 108 | 670642.47
| 01 | T1927 | 44477325201 | 2025-07-30 | QTR1 | 25/26 | 1 | 0 | 100 | 116 | 115 | 99% | 1 | 1 | 0 | 0 | 16 | 0 | 414963 | 0 | 414963 | 414963 | 422033 | 0 | 0 | 0 | 422033 | 422033 | 101.7% | 1 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2026-02-12 | QTR3 | 25/26 | 118 | 496784.63
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 19 | 31 | 64 | 5200 | 7507 | 7312 | 78.95% | 15 | 195 | 59 | 0 | 1840 | 437 | 133307281 | 1081159 | 132226122 | 136428741 | 136375040 | -253720 | -92500 | -346220 | 136028820 | 136081028 | 94.74% | 18 | 2173966 | 3121461 | 1234 | 497 | 24 | 92 | 957185 | 0 | 17 | 193 | 746479 | 187869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 29 | 19 | 535939 | 0 | 0 | 0 | 108747 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 159279 | 0 | 0 | 0 | 0 | 0 | 10 | 133 | 534836 | 45203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 437 | 3048213 | 233072
| 01 | E1R76 | 20121535201 | 2020-05-29 | QTR4 | 19/20 | 1 | 5 | 1050 | 1489 | 1488 | 107% | 1 | 1 | 0 | 0 | 365 | 74 | 70460520 | 150000 | 70310520 | 71635236 | 71638136 | -100000 | 0 | -100000 | 71538136 | 74769243 | 106.3% | 1 | 5571562 | 1174716 | 264 | 101 | 0 | 0 | 60435 | 0 | 0 | 74 | 916285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 314762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 74 | 1301779 | 0 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-10-20 | QTR2 | 25/26 |  | 2024-09-12 | QTR1 | 24/25 | 108 | 57230747.75 | Y | DESIGN/BUILD PROJECT
| 01 | E1R87 | 20103255201 | 2020-11-20 | QTR2 | 20/21 | 3 | 19 | 1400 | 1699 | 1699 | 100% | 1 | 0 | 0 | 0 | 265 | 34 | 143923300 | 150000 | 143773300 | 144607218 | 144885088 | -40000 | 0 | -40000 | 144845088 | 145590108 | 101.3% | 1 | 12782288 | 683918 | 199 | 100 | 0 | 0 | 857947 | 17389 | 0 | 0 | 113457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1718413 | 0 | 0 | 0 | 24827 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 569484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -46196 | 0 | 0 | 16 | -192910 | 17389 | F843374080 | AJAX-LEWARE JV | N/A | N/A | N/A | N/A | 2026-01-23 | QTR3 | 25/26 |  | 2025-10-25 | QTR2 | 25/26 | 106 | 132713200.45 | B11:B7:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - A+B/BONUS:ACC - DESIGN/BUILD - MAJOR
| 01 | E1V08 | 19602265201 | 2023-11-02 | QTR2 | 23/24 | 2 | 3 | 350 | 424 | 375 | 86% | 1 | 49 | 0 | 0 | 74 | 0 | 6226258 | 61298 | 6164960 | 6296806 | 6274547 | 0 | 0 | 0 | 6274547 | 6215664 | 100.8% | 1 | -10506 | 70548 | 51 | 23 | 0 | 0 | 45061 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48763 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 115 | 7418503.78
| 01 | E1V09 | 44743215201 | 2024-02-15 | QTR3 | 23/24 | 2 | 0 | 190 | 250 | 249 | 99.47% | 1 | 1 | 0 | 0 | 60 | 0 | 3665572 | 50000 | 3615572 | 3665572 | 3704260 | 0 | 0 | 0 | 3704260 | 3693129 | 102.1% | 1 | -11132 | 0 | 44 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 12979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 11006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24749 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 108 | 4198565.92
| 01 | E1V10 | 44155015201 | 2023-02-16 | QTR3 | 22/23 | 1 | 5 | 300 | 551 | 561 | 110.3% | 1 | -10 | 10 | 0 | 205 | 46 | 14609258 | 150000 | 14459258 | 14044029 | 14088333 | -3245 | 0 | -3245 | 14085087 | 13929541 | 96.34% | 1 | -126080 | -565229 | 188 | 42 | 0 | 0 | -627778 | 0 | 0 | 21 | 85849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -541929 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-19 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 115 | 14926349.94
| 01 | E1V13 | 44893915201 | 2024-09-19 | QTR1 | 24/25 | 1 | 1 | 150 | 195 | 194 | 111.3% | 1 | 1 | 0 | 0 | 45 | 0 | 5289078 | 65023 | 5224055 | 5392842 | 5545592 | 0 | 0 | 0 | 5545592 | 5545735 | 106.2% | 1 | 143 | 103763 | 8 | 19 | 0 | 0 | 103763 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 103763 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-25 | QTR1 | 25/26 |  | 2025-06-07 | QTR4 | 24/25 | 118 | 5760651.93
| 01 | E1V22 | 44620615201 | 2023-07-20 | QTR1 | 23/24 | 1 | 3 | 180 | 227 | 220 | 96.11% | 1 | 7 | 0 | 0 | 47 | 0 | 5142423 | 50000 | 5092423 | 5047658 | 5138834 | 0 | 0 | 0 | 5138834 | 5099867 | 100.1% | 1 | -1029 | -94765 | 25 | 22 | 0 | 0 | 44761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -132703 | 0 | 0 | 0 | -87943 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-05 | QTR3 | 24/25 | 118 | 4496918.22
| 01 | E1V23 | 44743415201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 225 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 53 | 0 | 5558710 | 57494 | 5501216 | 5552034 | 5723019 | 0 | 0 | 0 | 5723019 | 5723218 | 104% | 1 | 199 | -6676 | 44 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | -6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4873 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-01 | QTR1 | 25/26 |  | 2024-10-23 | QTR2 | 24/25 | 108 | 5765208.01
| 01 | E1V51 | 44743715201 | 2022-08-02 | QTR1 | 22/23 | 3 | 3 | 650 | 763 | 763 | 100% | 1 | 0 | 0 | 0 | 113 | 0 | 23141400 | 150000 | 22991400 | 23931467 | 24545579 | 0 | 0 | 0 | 24545579 | 24060306 | 104.6% | 1 | -480611 | 790067 | 61 | 52 | 0 | 0 | 53994 | 0 | 0 | 0 | 770405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824400 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-21 | QTR1 | 25/26 |  | 2024-11-12 | QTR2 | 24/25 | 108 | 26691037.4 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1V60 | 44901515201 | 2023-06-06 | QTR4 | 22/23 | 1 | 4 | 975 | 1035 | 559 | 51.18% | 1 | 476 | 0 | 0 | 60 | 0 | 24655000 | 150000 | 24505000 | 24840707 | 24676932 | 0 | 941500 | 941500 | 25618432 | 24522979 | 100.1% | 1 | -950274 | 185707 | 17 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 40527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51851 | 0 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2025-02-18 | QTR3 | 24/25 | 113 | 27242569.81 | B2:B5:Y | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:DESIGN/BUILD PROJECT
| 01 | E1W13 | 44594215201 | 2024-02-15 | QTR3 | 23/24 | 1 | 10 | 200 | 292 | 317 | 125.5% | 0 | -25 | 25 | 0 | 66 | 26 | 2428636 | 0 | 2428636 | 2626766 | 2708707 | -66250 | 0 | -66250 | 2642457 | 2624968 | 108.1% | 1 | -22 | 198130 | 44 | 22 | 0 | 26 | 115608 | 0 | 0 | 0 | 65054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 180662 | 0 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-04-22 | QTR4 | 24/25 | 115 | 3681296.02
| 01 | E1W16 | 44738015201 | 2023-09-21 | QTR1 | 23/24 | 1 | 5 | 200 | 302 | 296 | 97% | 1 | 6 | 0 | 0 | 58 | 44 | 2844972 | 50000 | 2794972 | 2870813 | 2826404 | 0 | 0 | 0 | 2826404 | 2806626 | 100.4% | 1 | -7691 | 25841 | 81 | 21 | 0 | 0 | 8709 | 0 | 0 | 0 | 5045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13754 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2026-03-18 | QTR3 | 25/26 |  | 2025-01-21 | QTR3 | 24/25 | 115 | 2548367.85
| 01 | E1W18 | 44743115201 | 2024-04-18 | QTR4 | 23/24 | 1 | 1 | 170 | 195 | 171 | 85.88% | 1 | 24 | 0 | 0 | 25 | 0 | 2506911 | 50000 | 2456911 | 2530764 | 2550717 | 0 | 0 | 0 | 2550717 | 2546483 | 103.6% | 1 | -4233 | 23853 | 8 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 |  | 2025-04-30 | QTR4 | 24/25 | 108 | 2727222.68
| 01 | E1W50 | 45279215201 | 2024-03-26 | QTR3 | 23/24 | 1 | 0 | 450 | 511 | 495 | 97.33% | 1 | 16 | 0 | 0 | 57 | 4 | 2283584 | 50000 | 2233584 | 2283584 | 2253806 | 0 | 0 | 0 | 2253806 | 2253543 | 100.9% | 1 | -264 | 0 | 24 | 33 | 0 | 4 | 25861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25861 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 |  | 2025-09-29 | QTR1 | 25/26 | 118 | 2780605.35 | Y | DESIGN/BUILD PROJECT
| 01 | E1W75 | 44923315201 | 2024-07-18 | QTR1 | 24/25 | 1 | 0 | 115 | 150 | 150 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 2560003 | 50000 | 2510003 | 2560003 | 2586788 | 0 | 0 | 0 | 2586788 | 2586788 | 103.1% | 1 | 0 | 0 | 32 | 3 | 0 | 0 | 29053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29053 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 |  | 2025-06-04 | QTR4 | 24/25 | 108 | 3481659.24
| 01 | E1W76 | 44897215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 0 | 140 | 166 | 150 | 88.57% | 1 | 16 | 0 | 0 | 26 | 0 | 3352588 | 50000 | 3302588 | 3352588 | 3378389 | 0 | 0 | 0 | 3378389 | 3377632 | 102.3% | 1 | -757 | 0 | 9 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-04-10 | QTR4 | 24/25 | 118 | 4285958.2
| 01 | E1W78 | 44927215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 1 | 100 | 127 | 110 | 83% | 1 | 17 | 0 | 0 | 27 | 0 | 1562427 | 50000 | 1512427 | 1562023 | 1597413 | 0 | 0 | 0 | 1597413 | 1597413 | 105.6% | 1 | 0 | -404 | 10 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 108 | 1884401.65
| 01 | E1W79 | 44023015201 | 2024-09-19 | QTR1 | 24/25 | 1 | 2 | 140 | 150 | 124 | 81.43% | 1 | 26 | 0 | 0 | 10 | 0 | 1118465 | 40273 | 1078192 | 1118465 | 854089 | 0 | 0 | 0 | 854089 | 854089 | 79.21% | 1 | -1 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-09-11 | QTR1 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 118 | 991704.32
| 01 | E1W85 | 44893115201 | 2024-11-07 | QTR2 | 24/25 | 2 | 3 | 150 | 180 | 160 | 86.67% | 1 | 20 | 0 | 0 | 30 | 0 | 4458291 | 54289 | 4404002 | 4710660 | 4720609 | 0 | 0 | 0 | 4720609 | 4719730 | 107.2% | 1 | -879 | 252368 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-09-04 | QTR1 | 25/26 | 113 | 5001199.26
| 01 | E1W94 | 44917815201 | 2025-02-20 | QTR3 | 24/25 | 1 | 0 | 80 | 147 | 156 | 148.8% | 0 | -9 | 9 | 0 | 37 | 30 | 830702 | 40500 | 790202 | 830702 | 826937 | -15165 | 0 | -15165 | 811772 | 811772 | 102.7% | 1 | 0 | 0 | 29 | 8 | 0 | 0 | 0 | 0 | 0 | 30 | 17515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 17515 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-01-30 | QTR3 | 25/26 |  | 2025-12-10 | QTR2 | 25/26 | 108 | 1048586.14
| 01 | E1X68 | 44895715201 | 2025-07-17 | QTR1 | 25/26 | 1 | 0 | 100 | 121 | 115 | 94% | 1 | 6 | 0 | 0 | 21 | 0 | 2063849 | 50000 | 2013849 | 2063849 | 1971937 | 0 | 0 | 0 | 1971937 | 1971937 | 97.92% | 1 | 0 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 8496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8496 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 |  | 2026-02-10 | QTR3 | 25/26 | 113 | 2136352.43
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 21 | 28 | 66 | 7315 | 9252 | 8630 | 90.48% | 19 | 622 | 44 | 0 | 1679 | 258 | 328681947 | 1518877 | 327163070 | 331523786 | 332496116 | -224660 | 941500 | 716840 | 333212955 | 335300771 | 100% | 21 | 16760713 | 2841837 | 1169 | 595 | 0 | 30 | 717414 | 17389 | 3 | 125 | 2315369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1706591 | 0 | 15 | 0 | 37636 | 0 | 0 | 0 | 0 | 0 | 49 | 16 | 894810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29838 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | -178899 | 0 | 67 | 171 | 2109575 | 41242
| District 01 Totals |  |  |  |  | 40 | 59 | 130 | 12515 | 16759 | 15942 | 85% | 34 | 817 | 103 | 0 | 3519 | 695 | 461989228 | 2600036 | 459389192 | 467952527 | 468871156 | -478380 | 849000 | 370620 | 469241775 | 471381799 | 97.5% | 39 | 18934679 | 5963298 | 2403 | 1092 | 24 | 122 | 1674599 | 17389 | 20 | 318 | 3061848 | 187869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 29 | 19 | -1170652 | 0 | 15 | 0 | 146383 | 0 | 0 | 0 | 0 | 0 | 52 | 16 | 1054089 | 0 | 0 | 0 | 0 | 0 | 10 | 133 | 564674 | 69056 | 0 | 0 | 0 | 0 | 0 | 0 | -178899 | 0 | 150 | 608 | 5157788 | 274314
| 02 | T2591 | 42886515201 | 2015-10-14 | QTR2 | 15/16 | 5 | 58 | 1200 | 3229 | 3229 | 220.2% | 0 | 0 | 0 | 0 | 905 | 1124 | 65973116 | 149995 | 65823121 | 108070596 | 111419612 | 0 | 0 | 0 | 111419612 | 112415734 | 170.8% | 0 | 1746230 | 42097480 | 322 | 264 | 133 | 66 | 1773148 | 375907 | 118 | 671 | 33362908 | 7141422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 335 | 4964601 | 3035499 | 0 | 0 | 325801 | 0 | 0 | 0 | 0 | 0 | 117 | 0 | 343725 | 2306 | 0 | 0 | 1388728 | 620012 | 0 | 52 | 1119347 | 685768 | 0 | 0 | 0 | 0 | 0 | 0 | -1139535 | 0 | 436 | 1124 | 42138723 | 11860914 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-03-23 | QTR3 | 25/26 |  | 2024-12-31 | QTR2 | 24/25 | 208 | 76779378.1
| 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 127.2% | 0 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 109.4% | 1 | 329791 | 87098 | 104 | 52 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6
| 02 | T2790 | 43616815201 | 2021-01-27 | QTR3 | 20/21 | 1 | 4 | 730 | 1441 | 1441 | 117.3% | 1 | 0 | 0 | 0 | 711 | 0 | 15444874 | 116066 | 15328808 | 18490817 | 18458945 | 0 | 0 | 0 | 18458945 | 18501533 | 120.7% | 0 | 251365 | 3045943 | 306 | 279 | 0 | 0 | 677453 | 0 | 0 | 0 | 61510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1981123 | 14607 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 2720087 | 14607 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2025-12-05 | QTR2 | 25/26 |  | 2025-05-07 | QTR4 | 24/25 | 216 | 11733776.57
| 02 | T2839 | 44342115201 | 2022-02-09 | QTR3 | 21/22 | 3 | 0 | 480 | 785 | 783 | 100% | 1 | 2 | 0 | 0 | 185 | 120 | 31969186 | 150000 | 31819186 | 31969186 | 32489212 | 0 | 0 | 0 | 32489212 | 33982240 | 106.8% | 1 | 1493028 | 0 | 244 | 59 | 0 | 2 | 18542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 18542 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-14 | QTR1 | 25/26 |  | 2024-06-14 | QTR4 | 23/24 | 209 | 35449756.12
| 02 | T2844 | 43935615201 | 2022-06-15 | QTR4 | 21/22 | 3 | 6 | 479 | 915 | 913 | 136.1% | 0 | 2 | 0 | 0 | 311 | 125 | 19892956 | 180993 | 19711963 | 20310363 | 20717832 | 0 | 0 | 0 | 20717832 | 20350044 | 103.2% | 1 | -345380 | 417407 | 191 | 70 | 50 | 92 | 143934 | 0 | 0 | 15 | 291019 | 3470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681 | 0 | 0 | 18 | 42558 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 125 | 516682 | 3470 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-07-16 | QTR1 | 25/26 | 208 | 16227519.23
| 02 | T2854 | 44554515201 | 2022-06-08 | QTR4 | 21/22 | 2 | 1 | 210 | 817 | 817 | 177.1% | 0 | 0 | 0 | 0 | 355 | 252 | 10095026 | 91284 | 10003741 | 10267526 | 10526210 | 0 | 0 | 0 | 10526210 | 10195263 | 101.9% | 1 | -330946 | 172500 | 390 | 55 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 110 | 172500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 252 | 172500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 209 | 10655889.17
| 02 | T2863 | 43744115201 | 2022-01-12 | QTR3 | 21/22 | 3 | 6 | 550 | 1127 | 1125 | 175.3% | 0 | 2 | 0 | 0 | 161 | 416 | 14032373 | 165047 | 13867326 | 15901285 | 16261074 | 0 | 0 | 0 | 16261074 | 16278606 | 117.4% | 0 | 24575 | 1868912 | 57 | 104 | 0 | 416 | 1783542 | 0 | 0 | 0 | 59192 | 4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20176 | 0 | 0 | 0 | 38915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 1906703 | 4208 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 208 | 15021660.86
| 02 | T2865 | 44351715201 | 2022-11-16 | QTR2 | 22/23 | 1 | 6 | 400 | 682 | 681 | 141% | 0 | 1 | 0 | 0 | 162 | 120 | 7663000 | 71865 | 7591135 | 8470199 | 9163770 | 0 | 0 | 0 | 9163770 | 9149657 | 120.5% | 0 | -14114 | 807199 | 68 | 49 | 45 | 91 | 723003 | 0 | 0 | 29 | 122914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 120 | 871252 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 208 | 7014633.18
| 02 | T2889 | 43575615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 5 | 280 | 638 | 638 | 156.8% | 0 | 0 | 0 | 0 | 199 | 159 | 3832776 | 50000 | 3782776 | 4315395 | 4383212 | 0 | 0 | 0 | 4383212 | 4383212 | 115.9% | 0 | 0 | 482619 | 107 | 92 | 0 | 24 | 38374 | 0 | 0 | 135 | 462409 | 134882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 500784 | 134882 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2025-06-06 | QTR4 | 24/25 | 208 | 4521037.25
| 02 | T2890 | 44554715201 | 2022-10-26 | QTR2 | 22/23 | 3 | 3 | 350 | 924 | 924 | 163.7% | 0 | 0 | 0 | 0 | 261 | 313 | 25595410 | 150000 | 25445410 | 25761158 | 26450421 | 0 | 0 | 0 | 26450421 | 25953030 | 102% | 1 | -497390 | 165747 | 280 | 71 | 0 | 213 | 120000 | 0 | 0 | 2 | 33247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 57500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 270747 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-09-17 | QTR1 | 25/26 | 209 | 25708227.9
| 02 | T2894 | 44540215201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 575 | 575 | 106.7% | 1 | 0 | 0 | 0 | 196 | 139 | 12471547 | 114486 | 12357061 | 12747539 | 13553931 | 0 | 0 | 0 | 13553931 | 13363147 | 108.1% | 1 | -190784 | 275992 | 290 | 29 | 0 | 57 | 256470 | 0 | 0 | 2 | 107104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 139 | 363574 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2024-09-11 | QTR1 | 24/25 | 209 | 11980864.41
| 02 | T2910 | 44535215201 | 2023-06-14 | QTR4 | 22/23 | 3 | 5 | 330 | 543 | 543 | 118.2% | 1 | 0 | 0 | 0 | 153 | 60 | 5895675 | 59623 | 5836052 | 5981679 | 6100547 | 0 | 0 | 0 | 6100547 | 6061260 | 103.9% | 1 | -3283 | 86004 | 101 | 52 | 0 | 20 | 48625 | 0 | 0 | 40 | 55572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 104197 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 |  | 2025-05-29 | QTR4 | 24/25 | 208 | 6680440.38
| 02 | T2913 | 44707815201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 150 | 420 | 412 | 206.7% | 0 | 8 | 0 | 0 | 102 | 168 | 4420617 | 50000 | 4370617 | 4518180 | 4416217 | 0 | 0 | 0 | 4416217 | 4412247 | 101% | 1 | -3971 | 97563 | 72 | 30 | 0 | 30 | 0 | 0 | 0 | 138 | 97563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 97563 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 |  | 2025-06-23 | QTR4 | 24/25 | 209 | 4807508.45
| 02 | T2915 | 44718015201 | 2023-03-29 | QTR3 | 22/23 | 1 | 1 | 300 | 660 | 659 | 104.3% | 1 | 1 | 0 | 0 | 346 | 14 | 11703806 | 89802 | 11614004 | 11742594 | 12389230 | 0 | 0 | 0 | 12389230 | 12372017 | 106.5% | 1 | -17213 | 38788 | 301 | 45 | 0 | 14 | 14951 | 0 | 0 | 0 | 38788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14 | 53739 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-20 | QTR2 | 25/26 |  | 2025-06-26 | QTR4 | 24/25 | 208 | 10416036.13
| 02 | T2916 | 43993715201 | 2023-04-26 | QTR4 | 22/23 | 2 | 0 | 425 | 610 | 605 | 98.82% | 1 | 5 | 0 | 0 | 185 | 0 | 10398707 | 246 | 10398461 | 10398707 | 10268067 | 0 | 0 | 0 | 10268067 | 10264507 | 98.71% | 1 | -3560 | 0 | 137 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 209 | 8834993.85
| 02 | T2917 | 44330415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 2 | 330 | 604 | 604 | 130.3% | 0 | 0 | 0 | 0 | 174 | 100 | 23947969 | 150000 | 23797969 | 24055659 | 25032603 | 0 | 0 | 0 | 25032603 | 25026994 | 105.2% | 1 | -5609 | 107690 | 101 | 73 | 0 | 66 | 177659 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 180877 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 208 | 21934859.67
| 02 | T2924 | 20930185201 | 2023-04-26 | QTR4 | 22/23 | 1 | 2 | 300 | 751 | 751 | 127.7% | 0 | 0 | 0 | 0 | 250 | 201 | 19358596 | 150000 | 19208596 | 19523393 | 20332171 | 0 | 0 | 0 | 20332171 | 20313549 | 105.8% | 1 | -18621 | 164797 | 300 | 68 | 0 | 0 | 49110 | 0 | 27 | 51 | 133896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17832 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 9270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 201 | 210108 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-02-20 | QTR3 | 25/26 |  | 2025-10-27 | QTR2 | 25/26 | 208 | 19142187.33
| 02 | T2934 | 44331015201 | 2022-12-07 | QTR2 | 22/23 | 2 | 5 | 450 | 714 | 711 | 123.1% | 0 | 3 | 0 | 0 | 264 | 0 | 26057502 | 150000 | 25907502 | 26443445 | 27980036 | 0 | 0 | 0 | 27980036 | 27874372 | 107.6% | 1 | -105664 | 385943 | 91 | 66 | 86 | 0 | 261787 | 11998 | 21 | 0 | 157751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 462296 | 11998 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-03-13 | QTR3 | 24/25 | 208 | 24163399.99
| 02 | T2945 | 44542715201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 300 | 503 | 501 | 129.3% | 0 | 2 | 0 | 0 | 113 | 90 | 6853255 | 73995 | 6779259 | 6853255 | 6989283 | 0 | 0 | 0 | 6989283 | 6981891 | 103% | 1 | -7392 | 0 | 72 | 41 | 0 | 10 | 13022 | 0 | 0 | 20 | 29941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 46335 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-08-12 | QTR1 | 25/26 | 208 | 7614578.02
| 02 | T2948 | 44712315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 300 | 431 | 414 | 94.33% | 1 | 17 | 0 | 0 | 71 | 60 | 5794236 | 50808 | 5743428 | 5794236 | 5977965 | 0 | 0 | 0 | 5977965 | 5956561 | 103.7% | 1 | -21404 | 0 | 93 | 38 | 0 | 0 | 14179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14179 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-12 | QTR2 | 25/26 |  | 2025-07-10 | QTR1 | 25/26 | 208 | 5749684.61
| 02 | T2949 | 20969745201 | 2023-11-15 | QTR2 | 23/24 | 1 | 2 | 270 | 360 | 323 | 92.59% | 1 | 37 | 0 | 0 | 73 | 17 | 1865813 | 50000 | 1815813 | 1939049 | 1961474 | 0 | 0 | 0 | 1961474 | 1960364 | 108% | 1 | -1110 | 73235 | 44 | 29 | 0 | 16 | 39150 | 0 | 0 | 1 | 39471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 78621 | 0 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2025-11-07 | QTR2 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 208 | 2230663.64
| 02 | T2954 | 44542015201 | 2023-12-06 | QTR2 | 23/24 | 2 | 0 | 270 | 373 | 372 | 99.63% | 1 | 1 | 0 | 0 | 103 | 0 | 3819110 | 50000 | 3769110 | 3819110 | 3735111 | 0 | 0 | 0 | 3735111 | 3733457 | 99.05% | 1 | -1654 | 0 | 67 | 36 | 0 | 0 | 702 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 208 | 5040191.6
| 02 | T2961 | 43633015201 | 2023-12-06 | QTR2 | 23/24 | 3 | 3 | 400 | 450 | 393 | 87.5% | 1 | 57 | 0 | 0 | 50 | 0 | 3521000 | 246 | 3520754 | 3558326 | 3560864 | 0 | 0 | 0 | 3560864 | 3553846 | 100.9% | 1 | -957 | 37326 | 19 | 24 | 7 | 0 | 31265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 31265 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-03-19 | QTR3 | 24/25 | 209 | 3765540.75
| 02 | T2962 | 44796215201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 180 | 370 | 370 | 130.6% | 0 | 0 | 0 | 0 | 160 | 30 | 7958218 | 85629 | 7872589 | 7958218 | 7882304 | 0 | 0 | 0 | 7882304 | 7877534 | 100.1% | 1 | -4770 | 0 | 79 | 56 | 0 | 30 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 30 | 1672 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 214 | 8827613.66
| 02 | T2966 | 21086555201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 120 | 236 | 232 | 146.7% | 0 | 4 | 0 | 0 | 56 | 60 | 2921783 | 50000 | 2871783 | 2921783 | 2938946 | 0 | 0 | 0 | 2938946 | 2938946 | 102.3% | 1 | 0 | 0 | 34 | 22 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-04-14 | QTR4 | 24/25 | 209 | 3224885.25
| 02 | T2969 | 44703615201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 300 | 408 | 406 | 118.7% | 1 | 2 | 0 | 0 | 50 | 58 | 10923210 | 112286 | 10810924 | 10892472 | 11424138 | 0 | 0 | 0 | 11424138 | 11378255 | 105.2% | 1 | -45883 | -30738 | 23 | 27 | 0 | 0 | 0 | 0 | 0 | 28 | 69752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | -30738 | 0 | 0 | 58 | 39014 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-24 | QTR2 | 25/26 |  | 2025-08-18 | QTR1 | 25/26 | 214 | 10802904.04
| 02 | T2970 | 44712815201 | 2024-02-28 | QTR3 | 23/24 | 3 | 5 | 180 | 392 | 392 | 140% | 0 | 0 | 0 | 0 | 140 | 72 | 6497196 | 70342 | 6426853 | 6705393 | 7314719 | 0 | 0 | 0 | 7314719 | 7267283 | 113.1% | 0 | -20654 | 208197 | 91 | 49 | 0 | 72 | 171277 | 99710 | 0 | 0 | 19849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 187461 | 99710 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 208 | 6729211.88
| 02 | T2974 | 44720415201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 300 | 461 | 461 | 102% | 1 | 0 | 0 | 0 | 155 | 6 | 18339896 | 150000 | 18189896 | 18339896 | 18394467 | 0 | 0 | 0 | 18394467 | 18347088 | 100.9% | 1 | -47379 | 0 | 113 | 42 | 0 | 3 | 40787 | 0 | 0 | 3 | 5308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 6 | 46094 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-10-11 | QTR2 | 25/26 | 214 | 19102224.25
| 02 | T2976 | 44755715201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 360 | 428 | 296 | 63.89% | 1 | 132 | 0 | 0 | 66 | 2 | 25893810 | 150000 | 25743810 | 26291007 | 27924429 | 0 | 0 | 0 | 27924429 | 27880284 | 108.3% | 1 | -44146 | 397198 | 39 | 27 | 0 | 0 | 417380 | 0 | 0 | 2 | 20401 | 3792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 437781 | 3792 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-21 | QTR2 | 25/26 |  | 2025-02-10 | QTR3 | 24/25 | 208 | 21206563.14
| 02 | T2981 | 45220125201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 275 | 345 | 286 | 78.55% | 1 | 59 | 0 | 0 | 70 | 0 | 2914229 | 50000 | 2864229 | 2914229 | 2917184 | 0 | 0 | 0 | 2917184 | 2917184 | 101.8% | 1 | 0 | 0 | 34 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-02-13 | QTR3 | 24/25 | 214 | 4244875.9
| 02 | T2985 | 43761415201 | 2023-11-15 | QTR2 | 23/24 | 1 | 0 | 270 | 405 | 405 | 116.7% | 1 | 0 | 0 | 0 | 119 | 16 | 7308506 | 69947 | 7238559 | 7308506 | 7304574 | 0 | 0 | 0 | 7304574 | 7285470 | 100.6% | 1 | -19104 | 0 | 59 | 31 | 0 | 2 | 31262 | 0 | 0 | 14 | 18461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 16 | 49723 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 208 | 8026688.02
| 02 | T2988 | 44721135201 | 2024-04-24 | QTR4 | 23/24 | 1 | 1 | 180 | 225 | 95 | 27.78% | 1 | 130 | 0 | 0 | 45 | 0 | 1562105 | 50000 | 1512105 | 1737694 | 1710662 | 0 | 0 | 0 | 1710662 | 1710435 | 113.1% | 0 | -227 | 175589 | 41 | 4 | 0 | 0 | 175589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175589 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 |  | 2024-10-17 | QTR2 | 24/25 | 208 | 1572771.91
| 02 | T2997 | 44984425201 | 2024-09-25 | QTR1 | 24/25 | 1 | 2 | 180 | 214 | 214 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 2499454 | 50000 | 2449454 | 2573884 | 2437559 | 0 | 0 | 0 | 2437559 | 2436488 | 99.47% | 1 | -1071 | 74430 | 20 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 24430 | 24430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61993 | 24430 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 214 | 2231402.67
| 02 | T2A02 | 43431825201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 180 | 188 | 171 | 90.56% | 1 | 17 | 0 | 0 | 8 | 0 | 7419960 | 87264 | 7332696 | 7419960 | 7285721 | 0 | 0 | 0 | 7285721 | 7282630 | 99.32% | 1 | -3091 | 0 | 4 | 4 | 0 | 0 | 46438 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61171 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 214 | 8775588.25
| 02 | T2A05 | 20944145201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 150 | 194 | 192 | 100.7% | 1 | 2 | 0 | 0 | 41 | 3 | 2487602 | 50000 | 2437602 | 2535510 | 2431426 | 0 | 0 | 0 | 2431426 | 2431081 | 99.73% | 1 | -345 | 47909 | 17 | 24 | 0 | 3 | 47909 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 49559 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2026-02-27 | QTR3 | 25/26 |  | 2025-11-24 | QTR2 | 25/26 | 208 | 3542854
| 02 | T2A06 | 21003025201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 300 | 343 | 305 | 87.33% | 1 | 38 | 0 | 0 | 43 | 0 | 6571980 | 67485 | 6504495 | 6571980 | 6862070 | 0 | 0 | 0 | 6862070 | 6863371 | 105.5% | 1 | 1301 | 0 | 17 | 26 | 0 | 0 | 13750 | 0 | 0 | 0 | 15770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29520 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-11 | QTR3 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 216 | 6362364.64
| 02 | T2A09 | 21022385201 | 2024-12-04 | QTR2 | 24/25 | 1 | 0 | 180 | 234 | 233 | 105% | 1 | 1 | 0 | 0 | 44 | 10 | 4685902 | 61983 | 4623919 | 4685902 | 4940814 | 0 | 0 | 0 | 4940814 | 4942704 | 106.9% | 1 | 1890 | 0 | 24 | 20 | 0 | 10 | 9787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9787 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2026-01-16 | QTR3 | 25/26 | 216 | 5665701.92
| 02 | T2A12 | 21071155201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 120 | 214 | 212 | 105.8% | 1 | 2 | 0 | 0 | 85 | 9 | 4071019 | 50000 | 4021019 | 4106006 | 4039787 | 0 | 0 | 0 | 4039787 | 4039787 | 100.5% | 1 | 0 | 34986 | 61 | 24 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 |  | 2025-06-24 | QTR4 | 24/25 | 208 | 4204426.35
| 02 | T9037 | 44627925214 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 300 | 323 | 260 | 79% | 1 | 63 | 0 | 0 | 23 | 0 | 755793 | 0 | 755793 | 799963 | 782324 | 0 | 0 | 0 | 782324 | 782311 | 103.5% | 1 | -13 | 44170 | 2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 216 | 588437.99
| 02 | T9039 | 44532025214 | 2024-05-22 | QTR4 | 23/24 | 1 | 2 | 400 | 433 | 375 | 85.5% | 1 | 58 | 0 | 0 | 33 | 0 | 2629396 | 0 | 2629396 | 2652851 | 2657516 | 0 | 0 | 0 | 2657516 | 2657516 | 101.1% | 1 | 0 | 23454 | 1 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 23454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23454 | 0 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2026-02-03 | QTR3 | 25/26 |  | 2025-12-01 | QTR2 | 25/26 | 208 | 2484683.43
| 02 | T9041 | 44628015215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 45 | 48 | 47 | 97.78% | 1 | 1 | 0 | 0 | 3 | 0 | 211688 | 9600 | 202088 | 211688 | 200166 | 0 | 0 | 0 | 200166 | 200166 | 99.05% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-02-21 | QTR3 | 24/25 | 208 | 233429.76
| 02 | T9044 | 44628025216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 120 | 126 | 92 | 71.67% | 1 | 34 | 0 | 0 | 6 | 0 | 393754 | 22100 | 371654 | 393754 | 371540 | 0 | 0 | 0 | 371540 | 371540 | 99.97% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 208 | 505500
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 42 | 65 | 128 | 13284 | 23804 | 23123 | 61.9% | 26 | 681 | 0 | 0 | 6776 | 3744 | 455361878 | 3402776 | 451959098 | 506749318 | 521172416 | 0 | 0 | 0 | 521172416 | 522110186 | 83.33% | 35 | 2092445 | 51387438 | 4421 | 2137 | 341 | 1367 | 7175142 | 487615 | 166 | 1194 | 35404099 | 7325752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 335 | 7079469 | 3050106 | 155 | 150 | 593525 | 67137 | 0 | 0 | 0 | 0 | 756 | 498 | 606426 | 3178 | 0 | 0 | 1388728 | 620012 | 0 | 52 | 1119347 | 685768 | 89 | 148 | 0 | 0 | 0 | 0 | -1170273 | 0 | 1600 | 3744 | 52196463 | 12239567
| 02 | E200W | 44572615201 | 2024-04-17 | QTR4 | 23/24 | 1 | 0 | 180 | 256 | 256 | 113.9% | 1 | 0 | 0 | 0 | 51 | 25 | 2930266 | 50000 | 2880266 | 2930266 | 2970891 | 0 | 0 | 0 | 2970891 | 2968577 | 103.1% | 1 | -2313 | 0 | 28 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17954 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18944 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-06-29 | QTR4 | 24/25 | 209 | 2593407.4
| 02 | E20S2 | 21054545201 | 2022-06-01 | QTR4 | 21/22 | 1 | 0 | 609 | 992 | 992 | 127.9% | 0 | 0 | 0 | 0 | 123 | 260 | 8601469 | 80882 | 8520588 | 8601469 | 8734394 | 0 | 0 | 0 | 8734394 | 8453915 | 99.22% | 1 | -280479 | 0 | 136 | 77 | 0 | 90 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 209 | 8397276.42 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E20T6 | 44278015201 | 2023-02-15 | QTR3 | 22/23 | 1 | 2 | 280 | 645 | 645 | 151.1% | 0 | 0 | 0 | 0 | 119 | 246 | 1676236 | 50000 | 1626236 | 1744958 | 1814629 | 0 | 0 | 0 | 1814629 | 1814629 | 111.6% | 0 | 0 | 68722 | 137 | 85 | 0 | 2 | 81415 | 0 | 0 | 141 | 31490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 112905 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 208 | 2494427.5
| 02 | E20X8 | 20840265201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 550 | 717 | 717 | 116.4% | 1 | 0 | 0 | 0 | 167 | 0 | 9409691 | 88302 | 9321389 | 9409691 | 9709502 | 0 | 0 | 0 | 9709502 | 9670685 | 103.7% | 1 | -38817 | 0 | 27 | 50 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-05-22 | QTR4 | 24/25 | 209 | 8868810.45 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E20X9 | 44707615201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 490 | 785 | 780 | 103.3% | 1 | 5 | 0 | 0 | 205 | 90 | 11213775 | 111419 | 11102356 | 11213775 | 11321495 | 0 | 0 | 0 | 11321495 | 11257290 | 101.4% | 1 | -64205 | 0 | 208 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 180 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 209 | 11190658.02 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E2Z53 | 43035245201 | 2020-02-20 | QTR3 | 19/20 | 2 | 15 | 830 | 1569 | 1562 | 146.4% | 0 | 7 | 0 | 0 | 739 | 0 | 17677113 | 139633 | 17537480 | 32771107 | 33213700 | 0 | 0 | 0 | 33213700 | 33587618 | 191.5% | 0 | 498724 | 15093994 | 241 | 106 | 29 | 0 | 182603 | 0 | 56 | 0 | 402438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 14608377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 15230057 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 214 | 14339167
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 6 | 7 | 17 | 2939 | 4964 | 4952 | 50% | 3 | 12 | 0 | 0 | 1404 | 621 | 51508550 | 520236 | 50988315 | 66671266 | 67764611 | 0 | 0 | 0 | 67764611 | 67752714 | 66.67% | 4 | 112910 | 15162716 | 777 | 407 | 29 | 92 | 264018 | 0 | 146 | 221 | 434918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 0 | 14608377 | 0 | 0 | 0 | 17954 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503 | 711 | 15361906 | 0
| District 02 Totals |  |  |  |  | 48 | 72 | 145 | 16223 | 28768 | 28075 | 60.42% | 29 | 693 | 0 | 0 | 8180 | 4365 | 506870428 | 3923012 | 502947413 | 573420584 | 588937027 | 0 | 0 | 0 | 588937027 | 589862900 | 81.25% | 39 | 2205355 | 66550154 | 5198 | 2544 | 370 | 1459 | 7439160 | 487615 | 312 | 1415 | 35839017 | 7325752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421 | 335 | 21687846 | 3050106 | 155 | 150 | 611479 | 67137 | 0 | 0 | 0 | 0 | 756 | 896 | 643065 | 3178 | 0 | 0 | 1388728 | 620012 | 0 | 52 | 1119347 | 685768 | 89 | 148 | 0 | 0 | 0 | 0 | -1170273 | 0 | 2103 | 4455 | 67558369 | 12239567
| 03 | T3618 | 21790935201 | 2020-05-20 | QTR4 | 19/20 | 1 | 25 | 1000 | 1915 | 1912 | 154.4% | 0 | 3 | 0 | 0 | 401 | 514 | 27170428 | 150000 | 27020428 | 30592621 | 31419600 | 0 | 0 | 0 | 31419600 | 32973116 | 122% | 0 | 1578565 | 3422193 | 242 | 126 | 0 | 106 | 96310 | 0 | 33 | 171 | 1524911 | 17782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 1824610 | 66674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 77645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 514 | 3523475 | 84456 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 313 | 35258008.48
| 03 | T3705 | 43581615201 | 2021-06-09 | QTR4 | 20/21 | 3 | 7 | 1150 | 1341 | 1299 | 96.35% | 1 | 42 | 0 | 0 | 191 | 0 | 21786584 | 150000 | 21636584 | 24287618 | 24447463 | 0 | 0 | 0 | 24447463 | 24458859 | 113% | 0 | 417101 | 2501033 | 111 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 1856044 | 1818253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2538824 | 1818253 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-07-24 | QTR1 | 25/26 | 308 | 31799900.02
| 03 | T3722 | 41098185201 | 2022-06-15 | QTR4 | 21/22 | 1 | 6 | 600 | 878 | 1063 | 147% | 0 | -185 | 185 | 0 | 197 | 81 | 16220760 | 150000 | 16070760 | 16260965 | 16485438 | -1083175 | 0 | -1083175 | 15402263 | 16125524 | 100.3% | 1 | 723261 | 40205 | 122 | 59 | 0 | 81 | -39105 | 0 | 16 | 0 | 102671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81 | 77715 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-10-24 | QTR2 | 25/26 | 314 | 24461056.7
| 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 2 | 365 | 689 | 689 | 117.8% | 1 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6169465 | 6682488 | 0 | 0 | 0 | 6682488 | 7794860 | 128.1% | 0 | 1176465 | 3017 | 170 | 89 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 21 | 70800 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-26 | QTR3 | 25/26 |  | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29
| 03 | T3789 | 43813315201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 50 | 230 | 226 | 168% | 0 | 4 | 0 | 0 | 142 | 38 | 383899 | 19912 | 363987 | 397919 | 393163 | -35910 | 0 | -35910 | 357253 | 329110 | 90.42% | 1 | -28143 | 14020 | 115 | 27 | 0 | 0 | 0 | 0 | 0 | 38 | 14020 | 917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 38 | 14020 | 917 | F473361483 | T & T CIVIL CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2026-03-26 | QTR3 | 25/26 |  | 2023-01-27 | QTR3 | 22/23 | 314 | 424157.75
| 03 | T3790 | 43748915201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 255 | 343 | 339 | 98.43% | 1 | 4 | 0 | 0 | 88 | 0 | 3547402 | 0 | 3547402 | 3547402 | 3587891 | 0 | 0 | 0 | 3587891 | 3586665 | 101.1% | 1 | -1225 | 0 | 66 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 313 | 4578761.95
| 03 | T3804 | 42697315201 | 2022-04-27 | QTR4 | 21/22 | 2 | 4 | 200 | 679 | 679 | 177.5% | 0 | 0 | 0 | 0 | 404 | 75 | 6212045 | 50000 | 6162045 | 6299150 | 6924822 | 0 | 0 | 0 | 6924822 | 6889613 | 111.8% | 0 | -35209 | 87105 | 260 | 64 | 161 | 0 | 0 | 0 | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 87105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 75 | 87105 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 313 | 5759918.26
| 03 | T3835 | 44563315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 2 | 435 | 712 | 712 | 117% | 1 | 0 | 0 | 0 | 265 | 12 | 10919335 | 105921 | 10813414 | 11003378 | 11511158 | 0 | 0 | 0 | 11511158 | 11473007 | 106.1% | 1 | -38151 | 84043 | 130 | 73 | 10 | 0 | 22048 | 0 | 52 | 12 | 94616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 12 | 116664 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-09-08 | QTR1 | 25/26 | 314 | 11459373.75
| 03 | T3837 | 22259365201 | 2022-12-07 | QTR2 | 22/23 | 2 | 3 | 425 | 608 | 608 | 109.6% | 1 | 0 | 0 | 0 | 146 | 37 | 11772258 | 136099 | 11636159 | 11871253 | 11834603 | 0 | 0 | 0 | 11834603 | 11821261 | 101.6% | 1 | -13342 | 98995 | 72 | 70 | 0 | 3 | 2170 | 0 | 4 | 12 | 33069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 130287 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37 | 165526 | 579 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-16 | QTR1 | 25/26 |  | 2025-02-07 | QTR3 | 24/25 | 321 | 13447557.24
| 03 | T3843 | 43736615201 | 2023-02-22 | QTR3 | 22/23 | 3 | 3 | 450 | 880 | 880 | 128% | 0 | 0 | 0 | 0 | 397 | 33 | 14976878 | 150000 | 14826878 | 15770067 | 16545874 | 0 | 0 | 0 | 16545874 | 16474250 | 111.1% | 0 | -71624 | 793189 | 199 | 105 | 0 | 17 | 182706 | 0 | 90 | 14 | 676082 | 8918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 2 | 8973 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 33 | 867761 | 8918 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-09-30 | QTR1 | 25/26 | 308 | 17116856.14
| 03 | T3844 | 44581515201 | 2023-04-26 | QTR4 | 22/23 | 2 | 1 | 325 | 796 | 793 | 159.1% | 0 | 3 | 0 | 0 | 471 | 0 | 16815829 | 150000 | 16665829 | 16829871 | 17633297 | 0 | 0 | 0 | 17633297 | 17609681 | 105.7% | 1 | -23615 | 14042 | 181 | 95 | 0 | 0 | 0 | 0 | 195 | 0 | 14042 | 11490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 14042 | 11490 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-09-12 | QTR1 | 25/26 | 306 | 15773894.2
| 03 | T3851 | 44292015201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 290 | 517 | 514 | 126.9% | 0 | 3 | 0 | 0 | 227 | 0 | 3185384 | 0 | 3185384 | 3188684 | 3129056 | 0 | 0 | 0 | 3129056 | 3127773 | 98.19% | 1 | -1283 | 3300 | 108 | 38 | 0 | 0 | 0 | 0 | 10 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-10-16 | QTR2 | 25/26 | 306 | 3413369.7
| 03 | T3855 | 44401915201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 140 | 482 | 482 | 194.3% | 0 | 0 | 0 | 0 | 342 | 0 | 958894 | 50000 | 908894 | 958894 | 885299 | 0 | 0 | 0 | 885299 | 885298 | 97.4% | 1 | -1 | 0 | 159 | 51 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2025-05-27 | QTR4 | 24/25 | 308 | 1271778.2
| 03 | T3862 | 43977415201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 220 | 395 | 370 | 120.5% | 0 | 25 | 0 | 0 | 105 | 70 | 3433760 | 50000 | 3383760 | 3478528 | 3538382 | 0 | 0 | 0 | 3538382 | 3534775 | 104.5% | 1 | -3607 | 44768 | 61 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 44768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 44768 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 |  | 2025-10-20 | QTR2 | 25/26 | 313 | 3773823.76
| 03 | T3868 | 41344925201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 90 | 421 | 420 | 396.7% | 0 | 1 | 0 | 0 | 213 | 118 | 1298401 | 50000 | 1248401 | 1321412 | 1234071 | 0 | 0 | 0 | 1234071 | 1234071 | 98.85% | 1 | 0 | 23011 | 20 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-24 | QTR4 | 24/25 | 313 | 1300164.1
| 03 | T3871 | 42695025201 | 2024-06-12 | QTR4 | 23/24 | 2 | 1 | 260 | 335 | 326 | 96.54% | 1 | 9 | 0 | 0 | 75 | 0 | 3111541 | 50000 | 3061541 | 2493770 | 2535278 | 0 | 0 | 0 | 2535278 | 2534712 | 82.79% | 1 | -566 | -617771 | 28 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -617771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -617771 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-09-25 | QTR1 | 25/26 | 314 | 4093773.7
| 03 | T3874 | 44188015201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 74 | 447 | 447 | 181.1% | 0 | 0 | 0 | 0 | 373 | 0 | 988409 | 46367 | 942042 | 988409 | 938135 | 0 | 0 | 0 | 938135 | 938135 | 99.59% | 1 | 0 | 0 | 262 | 51 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 314 | 990878.67
| 03 | T3891 | 43467815201 | 2024-01-31 | QTR3 | 23/24 | 2 | 2 | 200 | 288 | 288 | 100% | 1 | 0 | 0 | 0 | 88 | 0 | 2823614 | 50000 | 2773614 | 2855298 | 2780904 | 0 | 0 | 0 | 2780904 | 2780236 | 100.2% | 1 | -668 | 31684 | 50 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 308 | 3805809.9
| 03 | T3901 | 41342535201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 205 | 261 | 254 | 97.56% | 1 | 7 | 0 | 0 | 54 | 2 | 3608291 | 50000 | 3558291 | 3609941 | 3619668 | 0 | 0 | 0 | 3619668 | 3616057 | 101.6% | 1 | -3611 | 1650 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 2 | 1650 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19319 | 1500 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-07-28 | QTR1 | 25/26 | 321 | 3187529.04
| 03 | T3913 | 21934625201 | 2024-08-28 | QTR1 | 24/25 | 2 | 1 | 165 | 248 | 221 | 83.64% | 1 | 27 | 0 | 0 | 83 | 0 | 2531784 | 50000 | 2481784 | 2570548 | 2574902 | 0 | 0 | 0 | 2574902 | 2573463 | 103.7% | 1 | -1439 | 38764 | 59 | 24 | 0 | 0 | 61379 | 16559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61379 | 16559 | F592990776 | AMERICAN SAND & X-CAVATION INC. DBA AMERICAN SAND & ASPHALT | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 314 | 3011928.8
| 03 | T9043 | 44628415215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 90 | 124 | 124 | 110% | 1 | 0 | 0 | 0 | 34 | 0 | 189979 | 10000 | 179979 | 189979 | 177334 | 0 | 0 | 0 | 177334 | 177334 | 98.53% | 1 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-05-09 | QTR4 | 24/25 | 308 | 237358.31
| 03 | T9045 | 44628425216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 180 | 199 | 122 | 60% | 1 | 77 | 0 | 0 | 14 | 5 | 511934 | 22600 | 489334 | 511934 | 495348 | 0 | 0 | 0 | 495348 | 495348 | 101.2% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | F592320406 | BILL SMITH ELECTRIC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-11-05 | QTR2 | 25/26 | 308 | 509928.23
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 22 | 34 | 62 | 7169 | 12788 | 12768 | 50% | 11 | 20 | 185 | 0 | 4613 | 1006 | 158613858 | 1574539 | 157039319 | 165197106 | 169374174 | -1119085 | 0 | -1119085 | 168255089 | 171433148 | 77.27% | 17 | 3672908 | 6583248 | 2479 | 1175 | 307 | 207 | 325508 | 16559 | 529 | 299 | 4352089 | 1858860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 472 | 2257351 | 67253 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 28 | 154402 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 1006 | 7089348 | 1942672
| 03 | E3U65 | 44188515201 | 2022-11-17 | QTR2 | 22/23 | 1 | 0 | 250 | 680 | 695 | 166.8% | 0 | -15 | 15 | 0 | 430 | 0 | 3672487 | 50000 | 3622487 | 3672487 | 3781493 | -38880 | 0 | -38880 | 3742613 | 3778340 | 104.3% | 1 | 35727 | 0 | 186 | 92 | 0 | 0 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 308 | 3629576.67
| 03 | E3V54 | 44554115201 | 2023-02-09 | QTR3 | 22/23 | 3 | 4 | 310 | 751 | 749 | 177.7% | 0 | 2 | 0 | 0 | 275 | 169 | 9981474 | 90589 | 9890885 | 10203672 | 10678123 | 0 | 0 | 0 | 10678123 | 10639564 | 107.6% | 1 | -38559 | 222198 | 136 | 62 | 0 | 51 | 147417 | 0 | 77 | 3 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 44650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 169 | 219567 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2025-05-27 | QTR4 | 24/25 | 314 | 10144016.25
| 03 | E3V77 | 40919375201 | 2023-10-12 | QTR2 | 23/24 | 1 | 0 | 333 | 516 | 511 | 106.9% | 1 | 5 | 0 | 0 | 183 | 0 | 3075367 | 50000 | 3025367 | 3075367 | 2907496 | 0 | 0 | 0 | 2907496 | 2907496 | 96.1% | 1 | 0 | 0 | 87 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-06-13 | QTR4 | 24/25 | 313 | 4067368.66
| 03 | E3V81 | 44563415201 | 2023-06-08 | QTR4 | 22/23 | 3 | 1 | 385 | 538 | 538 | 106.5% | 1 | 0 | 0 | 0 | 144 | 9 | 7280451 | 56951 | 7223500 | 7422322 | 7437743 | 0 | 0 | 0 | 7437743 | 7440600 | 103% | 1 | 2857 | 141871 | 76 | 52 | 0 | 5 | 141871 | 0 | 0 | 0 | 2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 0 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9 | 159630 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-03-03 | QTR3 | 24/25 | 321 | 6184892.36
| 03 | E3W01 | 44559115201 | 2022-09-08 | QTR1 | 22/23 | 2 | 6 | 365 | 866 | 968 | 196.7% | 0 | -102 | 102 | 0 | 443 | 58 | 7469384 | 92731 | 7376653 | 7480930 | 7424797 | -374814 | 0 | -374814 | 7049983 | 6812783 | 92.36% | 1 | -211775 | 11546 | 143 | 107 | 0 | 3 | 8874 | 0 | 198 | 12 | 18933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 38 | 42680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 53 | 47234 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 308 | 9544565.57
| 03 | E3W12 | 44643355201 | 2024-08-08 | QTR1 | 24/25 | 2 | 1 | 170 | 220 | 220 | 120% | 1 | 0 | 0 | 0 | 16 | 34 | 2949285 | 50000 | 2899285 | 2625347 | 2604415 | 0 | 0 | 0 | 2604415 | 2604415 | 89.83% | 1 | 0 | -323937 | 5 | 11 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | -323937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | -323937 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-22 | QTR1 | 25/26 | 321 | 3480038
| 03 | E3W30 | 44759615201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 365 | 665 | 665 | 154.8% | 0 | 0 | 0 | 0 | 220 | 110 | 4167167 | 50000 | 4117167 | 4263313 | 3906647 | 0 | 0 | 0 | 3906647 | 3906647 | 94.89% | 1 | 0 | 96146 | 18 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 306 | 4722891.55
| 03 | E3W31 | 44554215201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 385 | 696 | 694 | 132.7% | 0 | 2 | 0 | 0 | 311 | 0 | 12495664 | 115497 | 12380167 | 12574093 | 13184954 | 0 | 0 | 0 | 13184954 | 13181542 | 106.5% | 1 | -3412 | 78429 | 133 | 50 | 8 | 0 | 78429 | 78429 | 30 | 0 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 85479 | 78429 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-10-24 | QTR2 | 25/26 | 314 | 11633200.16
| 03 | E3W40 | 44374425201 | 2023-05-11 | QTR4 | 22/23 | 2 | 1 | 240 | 529 | 547 | 127.5% | 0 | -18 | 18 | 0 | 286 | 3 | 6286877 | 58278 | 6228599 | 6497112 | 6613095 | -68148 | 0 | -68148 | 6544947 | 6545243 | 105.1% | 1 | 297 | 210235 | 157 | 84 | 0 | 1 | 7085 | 0 | 45 | 2 | 211204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 3 | 218289 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 308 | 5983264.86
| 03 | E3W42 | 44559015201 | 2023-05-11 | QTR4 | 22/23 | 1 | 1 | 195 | 345 | 394 | 126.7% | 0 | -49 | 49 | 0 | 147 | 3 | 6987787 | 100654 | 6887133 | 6987787 | 7253303 | -185514 | 0 | -185514 | 7067789 | 7068223 | 102.6% | 1 | 435 | 0 | 104 | 43 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 3 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2024-10-15 | QTR2 | 24/25 | 308 | 10217706.9
| 03 | E3W68 | 45102815201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 60 | 65 | 52 | 78.33% | 1 | 13 | 0 | 0 | 5 | 0 | 112106 | 8466 | 103639 | 112106 | 103639 | 0 | 0 | 0 | 103639 | 103639 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-06-12 | QTR4 | 24/25 | 314 | 174993.22
| 03 | E3W69 | 42696125201 | 2023-11-09 | QTR2 | 23/24 | 2 | 1 | 274 | 451 | 451 | 100% | 1 | 0 | 0 | 0 | 177 | 0 | 4685111 | 59134 | 4625977 | 4688658 | 4492681 | 0 | 0 | 0 | 4492681 | 4485331 | 96.96% | 1 | -7350 | 3547 | 133 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 3547 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 3547 | 1539 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-06-18 | QTR4 | 24/25 | 321 | 5910727.48
| 03 | E3W79 | 45109915201 | 2024-04-11 | QTR4 | 23/24 | 1 | 0 | 90 | 143 | 142 | 98.89% | 1 | 1 | 0 | 0 | 53 | 0 | 485265 | 30756 | 454509 | 485265 | 487819 | 0 | 0 | 0 | 487819 | 487819 | 107.3% | 1 | 0 | 0 | 34 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-02-04 | QTR3 | 24/25 | 321 | 555113.46
| 03 | E3X01 | 40619455201 | 2024-10-24 | QTR2 | 24/25 | 1 | 0 | 120 | 159 | 153 | 120% | 1 | 6 | 0 | 0 | 39 | 0 | 328567 | 17193 | 311374 | 328567 | 291720 | 0 | 0 | 0 | 291720 | 291720 | 93.69% | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-10-09 | QTR2 | 25/26 | 313 | 364798.17
| 03 | E3X03 | 40619635201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 90 | 112 | 86 | 71.11% | 1 | 26 | 0 | 0 | 22 | 0 | 169075 | 11395 | 157679 | 169075 | 154095 | 0 | 0 | 0 | 154095 | 154095 | 97.73% | 1 | 0 | 0 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 313 | 240133.12
| 03 | E3X08 | 45103115201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 225 | 303 | 223 | 64.44% | 1 | 80 | 0 | 0 | 78 | 0 | 1112248 | 50000 | 1062248 | 1112248 | 1077908 | 0 | 0 | 0 | 1077908 | 1077908 | 101.5% | 1 | 0 | 0 | 44 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-22 | QTR4 | 24/25 | 313 | 1273505.15
| 03 | E3X17 | 44758915201 | 2024-06-13 | QTR4 | 23/24 | 2 | 1 | 175 | 283 | 282 | 102.3% | 1 | 1 | 0 | 0 | 103 | 5 | 2342678 | 50000 | 2292678 | 2369603 | 2340433 | 0 | 0 | 0 | 2340433 | 2340369 | 102.1% | 1 | -64 | 26925 | 78 | 25 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-26 | QTR1 | 25/26 | 308 | 2975754.37
| 03 | E3X52 | 43078225201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 150 | 208 | 208 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 4271650 | 50000 | 4221650 | 4271650 | 4371998 | 0 | 0 | 0 | 4371998 | 4360199 | 103.3% | 1 | -11799 | 0 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 314 | 4754953.2
| 03 | E3X72 | 22020225201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 150 | 200 | 155 | 90% | 1 | 45 | 0 | 0 | 50 | 0 | 647631 | 42452 | 605180 | 647631 | 536583 | 0 | 0 | 0 | 536583 | 536583 | 88.67% | 1 | 0 | 0 | 9 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2025-09-29 | QTR1 | 25/26 | 313 | 900232.57
| 03 | E3X87 | 45268615201 | 2024-09-12 | QTR1 | 24/25 | 1 | 1 | 120 | 179 | 178 | 132.5% | 0 | 1 | 0 | 0 | 58 | 1 | 1172775 | 50000 | 1122775 | 1197264 | 1124063 | 0 | 0 | 0 | 1124063 | 1124063 | 100.1% | 1 | 0 | 24489 | 12 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 24489 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 321 | 1445110
| 03 | E3Y07 | 43937125201 | 2025-01-30 | QTR3 | 24/25 | 1 | 0 | 120 | 128 | 115 | 89.17% | 1 | 13 | 0 | 0 | 8 | 0 | 493247 | 26670 | 466577 | 493247 | 468786 | 0 | 0 | 0 | 468786 | 468786 | 100.5% | 1 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 321 | 566683.49
| 03 | E3Y25 | 45431115201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 120 | 138 | 136 | 98.33% | 1 | 2 | 0 | 0 | 18 | 0 | 430052 | 29999 | 400053 | 430052 | 391859 | 0 | 0 | 0 | 391859 | 391859 | 97.95% | 1 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 321 | 619869.69
| 03 | E3Y28 | 45443415201 | 2025-04-10 | QTR4 | 24/25 | 1 | 0 | 120 | 125 | 107 | 85% | 1 | 18 | 0 | 0 | 5 | 0 | 339177 | 19836 | 319341 | 339177 | 318764 | 0 | 0 | 0 | 318764 | 318764 | 99.82% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-11-03 | QTR2 | 25/26 | 308 | 393848.24
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 23 | 32 | 19 | 4812 | 8300 | 8269 | 65.22% | 15 | 31 | 184 | 0 | 3129 | 392 | 80955525 | 1160601 | 79794923 | 81446973 | 81952414 | -667356 | 0 | -667356 | 81285058 | 81025988 | 100% | 23 | -233643 | 491449 | 1402 | 869 | 8 | 80 | 383676 | 78429 | 502 | 22 | 298123 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247 | 213 | -150190 | 0 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 436 | 38 | 42680 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1299 | 357 | 583804 | 79968
| District 03 Totals |  |  |  |  | 45 | 66 | 81 | 11981 | 21088 | 21037 | 57.78% | 26 | 51 | 369 | 0 | 7742 | 1398 | 239569383 | 2735140 | 236834242 | 246644079 | 251326588 | -1786441 | 0 | -1786441 | 249540147 | 252459136 | 88.89% | 40 | 3439265 | 7074697 | 3881 | 2044 | 315 | 287 | 709184 | 94988 | 1031 | 321 | 4650212 | 1860399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 685 | 2107161 | 67253 | 71 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 727 | 66 | 197082 | 0 | 0 | 0 | 0 | 0 | 169 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2741 | 1363 | 7673152 | 2022640
| 04 | T4560 | 44004315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 482 | 552 | 551 | 99.79% | 1 | 1 | 0 | 0 | 70 | 0 | 2472960 | 50000 | 2422960 | 2472960 | 2454293 | 0 | 0 | 0 | 2454293 | 2461065 | 101.6% | 1 | 134358 | 0 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 19903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21118 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2025-09-22 | QTR1 | 25/26 |  | 2023-02-03 | QTR3 | 22/23 | 409 | 2686957.88
| 04 | T4580 | 43992915201 | 2021-05-26 | QTR4 | 20/21 | 5 | 8 | 739 | 1080 | 1080 | 110% | 1 | 0 | 0 | 0 | 321 | 20 | 18014663 | 150000 | 17864663 | 17978017 | 17209306 | 0 | 0 | 0 | 17209306 | 17705907 | 99.11% | 1 | 548358 | -36647 | 213 | 54 | 26 | 0 | 52717 | 0 | 28 | 0 | 96396 | 32818 | 0 | 0 | 0 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10479 | 0 | 0 | 0 | 8503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51758 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 19502 | 19502 | 0 | 0 | 0 | 0 | 0 | 0 | -63378 | 0 | 54 | 20 | 30554 | 52320 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 409 | 22960743.25
| 04 | T4627 | 44384615201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 353 | 497 | 497 | 108.5% | 1 | 0 | 0 | 0 | 114 | 30 | 1831417 | 50000 | 1781417 | 1831417 | 1800868 | 0 | 0 | 0 | 1800868 | 1800868 | 101.1% | 1 | 0 | 0 | 84 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 412 | 2390409.32
| 04 | T4638 | 43580855201 | 2023-07-26 | QTR1 | 23/24 | 4 | 4 | 345 | 512 | 512 | 108.7% | 1 | 0 | 0 | 0 | 137 | 30 | 8148235 | 82702 | 8065534 | 8411133 | 8179681 | 0 | 0 | 0 | 8179681 | 8160560 | 101.2% | 1 | -3998 | 262898 | 110 | 27 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2025-12-02 | QTR2 | 25/26 |  | 2025-07-23 | QTR1 | 25/26 | 412 | 8255267.22
| 04 | T4641 | 43984515201 | 2023-04-26 | QTR4 | 22/23 | 4 | 5 | 721 | 810 | 789 | 97.09% | 1 | 21 | 0 | 0 | 89 | 0 | 11705000 | 114314 | 11590686 | 12054276 | 11872830 | 0 | 0 | 0 | 11872830 | 11832340 | 102.1% | 1 | -11097 | 349276 | 32 | 57 | 0 | 0 | 211859 | 0 | 0 | 0 | 163474 | 18545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386900 | 18545 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-16 | QTR3 | 25/26 |  | 2025-09-05 | QTR1 | 25/26 | 409 | 11870989.01
| 04 | T4643 | 44637415201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 542 | 602 | 566 | 93.36% | 1 | 36 | 0 | 0 | 60 | 0 | 17748021 | 150000 | 17598021 | 18627265 | 18943576 | 0 | 0 | 0 | 18943576 | 18916878 | 107.5% | 1 | -25540 | 879244 | 29 | 31 | 0 | 0 | 886738 | 22797 | 0 | 0 | 7449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911403 | 22797 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-11-17 | QTR2 | 25/26 | 409 | 24914785.02
| 04 | T4645 | 44610215201 | 2023-05-24 | QTR4 | 22/23 | 2 | 4 | 430 | 560 | 558 | 104.4% | 1 | 2 | 0 | 0 | 130 | 0 | 12833449 | 133704 | 12699745 | 12956058 | 12287948 | 0 | 0 | 0 | 12287948 | 12282375 | 96.71% | 1 | 2250 | 122609 | 65 | 44 | 0 | 0 | 35147 | 0 | 21 | 0 | 79638 | 29413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114786 | 29413 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-31 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 409 | 14351247.26
| 04 | T4649 | 44839715201 | 2023-06-14 | QTR4 | 22/23 | 1 | 5 | 254 | 482 | 482 | 163.4% | 0 | 0 | 0 | 0 | 67 | 161 | 4835155 | 50000 | 4785155 | 5082020 | 5106645 | 0 | 0 | 0 | 5106645 | 5105846 | 106.7% | 1 | -798 | 246865 | 59 | 8 | 0 | 0 | 41171 | 0 | 0 | 0 | 40694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 246865 | 0 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 408 | 6110749.35
| 04 | T4651 | 44407915201 | 2023-10-25 | QTR2 | 23/24 | 3 | 6 | 473 | 492 | 347 | 64.27% | 1 | 145 | 0 | 0 | 43 | -24 | 7152200 | 65917 | 7086283 | 7526530 | 7413084 | 0 | 0 | 0 | 7413084 | 7393759 | 104.3% | 1 | -14849 | 529392 | 20 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 28959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28959 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 409 | 6673207.01
| 04 | T4652 | 44616915201 | 2023-11-15 | QTR2 | 23/24 | 2 | 3 | 259 | 447 | 447 | 118.1% | 1 | 0 | 0 | 0 | 188 | 0 | 5424973 | 53119 | 5371854 | 5477905 | 5676734 | 0 | 0 | 0 | 5676734 | 5654422 | 105.3% | 1 | -8426 | 52932 | 107 | 34 | 0 | 0 | 4345 | 0 | 30 | 0 | 53665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 58010 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-10 | QTR3 | 25/26 |  | 2025-08-14 | QTR1 | 25/26 | 408 | 5383942.21
| 04 | T4654 | 44952015201 | 2024-01-31 | QTR3 | 23/24 | 2 | 8 | 289 | 471 | 469 | 109.7% | 1 | 2 | 0 | 0 | 182 | 0 | 5626066 | 61166 | 5564900 | 5715669 | 5782761 | 0 | 0 | 0 | 5782761 | 5777248 | 103.8% | 1 | -91 | 89603 | 124 | 28 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 4409 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2026-01-12 | QTR3 | 25/26 |  | 2025-11-13 | QTR2 | 25/26 | 412 | 6458891.07
| 04 | T4661 | 44620015201 | 2024-03-27 | QTR3 | 23/24 | 4 | 4 | 422 | 432 | 352 | 75.59% | 1 | 80 | 0 | 0 | 33 | -46 | 9458464 | 113124 | 9345340 | 9790787 | 9649312 | 0 | 0 | 0 | 9649312 | 9617817 | 102.9% | 1 | -18533 | 566686 | 18 | 15 | 0 | 0 | 108078 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109406 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 |  | 2025-08-20 | QTR1 | 25/26 | 412 | 11108027.65
| 04 | T4662 | 44001515201 | 2023-12-06 | QTR2 | 23/24 | 1 | 3 | 182 | 353 | 351 | 111.5% | 1 | 2 | 0 | 0 | 171 | 0 | 2710165 | 50000 | 2660165 | 2699856 | 2568771 | 0 | 0 | 0 | 2568771 | 2567076 | 96.5% | 1 | -16 | -10309 | 123 | 25 | 0 | 0 | 811 | 0 | 23 | 0 | -6653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | -5843 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 409 | 3354139.5
| 04 | T4663 | 44764715201 | 2023-12-06 | QTR2 | 23/24 | 2 | 3 | 245 | 397 | 395 | 99.18% | 1 | 2 | 0 | 0 | 152 | 0 | 11192757 | 116425 | 11076332 | 11220679 | 11200266 | 0 | 0 | 0 | 11200266 | 11159153 | 100.7% | 1 | -30470 | 27922 | 125 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 17915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17915 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 408 | 11705908.23
| 04 | T4664 | 44699715201 | 2023-09-13 | QTR1 | 23/24 | 3 | 0 | 210 | 395 | 394 | 99.52% | 1 | 1 | 0 | 0 | 185 | 0 | 1247247 | 50000 | 1197247 | 1247247 | 1175544 | 0 | 0 | 0 | 1175544 | 1174544 | 98.1% | 1 | -1000 | 0 | 157 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-05-12 | QTR4 | 24/25 | 412 | 1347694.58
| 04 | T4665 | 44619515201 | 2024-02-28 | QTR3 | 23/24 | 6 | 2 | 240 | 367 | 367 | 100% | 1 | 0 | 0 | 0 | 127 | 0 | 5489802 | 58699 | 5431104 | 5499093 | 5514945 | 0 | 0 | 0 | 5514945 | 5496131 | 101.2% | 1 | -18814 | 9291 | 101 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 9291 | 9291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9291 | 9291 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-07 | QTR3 | 25/26 |  | 2025-10-08 | QTR2 | 25/26 | 412 | 5906510.04
| 04 | T4667 | 44764615201 | 2024-03-27 | QTR3 | 23/24 | 2 | 3 | 271 | 331 | 331 | 100.7% | 1 | 0 | 0 | 0 | 60 | 0 | 5722729 | 58760 | 5663969 | 5878728 | 5826172 | 0 | 0 | 0 | 5826172 | 5808077 | 102.5% | 1 | -12396 | 155998 | 38 | 20 | 0 | 0 | 1638 | 0 | 2 | 0 | 150300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 151938 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-05 | QTR3 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 408 | 5723687.91
| 04 | T4677 | 44767915201 | 2024-05-22 | QTR4 | 23/24 | 4 | 3 | 276 | 298 | 271 | 85.14% | 1 | 27 | 0 | 0 | 36 | -28 | 7765433 | 82562 | 7682871 | 7871392 | 7668837 | 0 | 0 | 0 | 7668837 | 7663134 | 99.74% | 1 | -5703 | 211917 | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 15171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24680 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2025-08-01 | QTR1 | 25/26 | 412 | 8421050.52
| 04 | T4679 | 44619615201 | 2024-01-31 | QTR3 | 23/24 | 3 | 0 | 244 | 337 | 336 | 99.59% | 1 | 1 | 0 | 0 | 93 | 0 | 5469442 | 56677 | 5412765 | 5469442 | 5544372 | 0 | 0 | 0 | 5544372 | 5542177 | 102.4% | 1 | -2195 | 0 | 70 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-12-12 | QTR2 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 412 | 5971108.66
| 04 | T4686 | 42957695201 | 2024-04-24 | QTR4 | 23/24 | 2 | 0 | 244 | 488 | 488 | 118.4% | 1 | 0 | 0 | 0 | 244 | 0 | 3298227 | 50000 | 3248227 | 3298227 | 3079319 | 0 | 0 | 0 | 3079319 | 3078260 | 94.77% | 1 | -1060 | 0 | 148 | 51 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2026-02-23 | QTR3 | 25/26 |  | 2026-01-09 | QTR3 | 25/26 | 412 | 3509812.2
| 04 | T4687 | 45222715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 167 | 237 | 237 | 117.4% | 1 | 0 | 0 | 0 | 70 | 0 | 1600545 | 50000 | 1550545 | 1600545 | 1508063 | 0 | 0 | 0 | 1508063 | 1508063 | 97.26% | 1 | 0 | 0 | 22 | 19 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 408 | 2128846.17
| 04 | T4694 | 44767115201 | 2024-07-31 | QTR1 | 24/25 | 3 | 2 | 291 | 358 | 351 | 97.59% | 1 | 7 | 0 | 0 | 67 | -15 | 3150955 | 50000 | 3100955 | 3159605 | 3107001 | 0 | 0 | 0 | 3107001 | 3106285 | 100.2% | 1 | -716 | 33997 | 45 | 22 | 0 | 0 | 27775 | 0 | 0 | 0 | 21950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49724 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 |  | 2026-01-14 | QTR3 | 25/26 | 409 | 3340322.06
| 04 | T4708 | 44754315201 | 2024-07-31 | QTR1 | 24/25 | 1 | 0 | 200 | 237 | 211 | 87% | 1 | 26 | 0 | 0 | 37 | 0 | 1300000 | 50000 | 1250000 | 1300000 | 1243700 | 0 | 0 | 0 | 1243700 | 1243700 | 99.5% | 1 | 0 | 0 | 22 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2025-08-05 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 412 | 1369377.1
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 23 | 59 | 66 | 7879 | 10735 | 10382 | 95.65% | 22 | 353 | 0 | 0 | 2676 | 128 | 154197905 | 1747169 | 152450738 | 157168851 | 154814028 | 0 | 0 | 0 | 154814028 | 155055685 | 100% | 23 | 529264 | 3491674 | 1757 | 668 | 26 | 0 | 1370279 | 22797 | 208 | 60 | 1030145 | 219664 | 0 | 0 | 0 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24397 | 0 | 17 | 0 | 38501 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 51758 | 0 | 0 | 161 | 165000 | 0 | 0 | 20 | 19502 | 19502 | 0 | 0 | 0 | 0 | 0 | 0 | -63378 | 0 | 324 | 241 | 2490780 | 261963
| 04 | E4Q32 | 43310845201 | 2015-04-27 | QTR4 | 14/15 | 2 | 51 | 1450 | 3156 | 3156 | 177% | 0 | 0 | 0 | 0 | 1179 | 527 | 148749800 | 150000 | 148599800 | 174962816 | 175180045 | 0 | 56000 | 56000 | 175236045 | 174744522 | 117.6% | 0 | -41128 | 26213016 | 414 | 176 | 0 | 0 | 1494952 | 0 | 0 | 0 | 142046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517 | 527 | 21512637 | 3321562 | 0 | 0 | 2751791 | 53052 | 0 | 0 | 0 | 0 | 186 | 0 | 468030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -204577 | 0 | 703 | 527 | 26164878 | 3374614 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2026-02-26 | QTR3 | 25/26 |  | 2024-05-24 | QTR4 | 23/24 | 412 | 122897181 | B10:B5:B8:::Y | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| 04 | E4U48 | 44146615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 281 | 416 | 416 | 110.7% | 1 | 0 | 0 | 0 | 135 | 0 | 2126000 | 50000 | 2076000 | 2132929 | 1513603 | 0 | 0 | 0 | 1513603 | 1506673 | 72.58% | 1 | 0 | 6930 | 77 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-08-04 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 409 | 2622051.6
| 04 | E4U88 | 43999925201 | 2023-04-07 | QTR4 | 22/23 | 1 | 3 | 764 | 860 | 713 | 80.76% | 1 | 147 | 0 | 0 | 96 | 0 | 10631541 | 85557 | 10545984 | 10738131 | 11100934 | 0 | 0 | 0 | 11100934 | 11070252 | 105% | 1 | -1518 | 106590 | 57 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 408 | 10492574.81
| 04 | E4V62 | 43695815201 | 2022-08-18 | QTR1 | 22/23 | 2 | 10 | 622 | 706 | 649 | 90.84% | 1 | 57 | 0 | 0 | 84 | 0 | 31058595 | 150000 | 30908595 | 33155117 | 32699199 | 0 | 0 | 0 | 32699199 | 32554410 | 105.3% | 1 | -144790 | 1946522 | 57 | 27 | 0 | 0 | 1746 | 0 | 0 | 0 | 1779105 | 8878 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239103 | 0 | 0 | 0 | 79175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -118750 | 0 | 0 | 0 | 1989203 | 8878 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2024-10-18 | QTR2 | 24/25 | 412 | 29695111.36
| 04 | E4W05 | 44047315201 | 2022-12-02 | QTR2 | 22/23 | 2 | 11 | 324 | 551 | 550 | 114.5% | 1 | 1 | 0 | 0 | 179 | 48 | 3993841 | 50000 | 3943841 | 4453325 | 4438530 | 0 | 0 | 0 | 4438530 | 4429433 | 112.3% | 0 | -6049 | 459484 | 135 | 44 | 0 | 0 | 14920 | 0 | 0 | 48 | 317478 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 48 | 425398 | 258 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-03-21 | QTR3 | 24/25 | 408 | 4033616.25
| 04 | E4W54 | 44618515201 | 2023-05-05 | QTR4 | 22/23 | 2 | 5 | 241 | 466 | 466 | 100% | 1 | 0 | 0 | 0 | 225 | 0 | 8153790 | 72216 | 8081573 | 8619435 | 8570644 | 0 | 0 | 0 | 8570644 | 8567270 | 106% | 1 | 0 | 469019 | 175 | 50 | 0 | 0 | 121843 | 1201843 | 0 | 0 | 314395 | 24985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3335 | 3335 | 0 | 0 | 22700 | 22700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462272 | 1252862 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-02-14 | QTR3 | 24/25 | 412 | 7653131.2
| 04 | E4W61 | 44610415201 | 2023-08-04 | QTR1 | 23/24 | 1 | 1 | 287 | 408 | 408 | 109.8% | 1 | 0 | 0 | 0 | 121 | 0 | 5369226 | 50000 | 5319226 | 5369226 | 5576786 | 0 | 0 | 0 | 5576786 | 5571433 | 104.7% | 1 | -5352 | 104495 | 64 | 29 | 28 | 0 | 31492 | 0 | 0 | 0 | 7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 38981 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 |  | 2025-04-09 | QTR4 | 24/25 | 409 | 4627615.06
| 04 | E4W65 | 44617415201 | 2024-01-05 | QTR3 | 23/24 | 3 | 0 | 163 | 241 | 241 | 111% | 1 | 0 | 0 | 0 | 78 | 0 | 4920477 | 50000 | 4870477 | 4920477 | 4833727 | 0 | 0 | 0 | 4833727 | 4832964 | 99.23% | 1 | -763 | 0 | 39 | 21 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-15 | QTR1 | 25/26 |  | 2025-06-11 | QTR4 | 24/25 | 409 | 4972817.95
| 04 | E4W71 | 44974015201 | 2023-05-05 | QTR4 | 22/23 | 1 | 0 | 82 | 523 | 522 | 550% | 0 | 1 | 0 | 0 | 441 | 0 | 827827 | 45348 | 782479 | 827827 | 848976 | 0 | 0 | 0 | 848976 | 848976 | 108.5% | 1 | 0 | 0 | 38 | 33 | 310 | 0 | 0 | 0 | 0 | 0 | 13151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 0 | 13151 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 412 | 1076147.07
| 04 | E4W72 | 44617015201 | 2023-11-03 | QTR2 | 23/24 | 3 | 5 | 182 | 306 | 303 | 108.8% | 1 | 3 | 0 | 0 | 105 | 19 | 4285836 | 50000 | 4235836 | 4430549 | 4413846 | 0 | 0 | 0 | 4413846 | 4401052 | 103.9% | 1 | -9192 | 144713 | 79 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 85267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 55844 | 55844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 145465 | 55844 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-30 | QTR2 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 408 | 4697027.08
| 04 | E4W82 | 44610515201 | 2024-01-05 | QTR3 | 23/24 | 2 | 2 | 274 | 356 | 355 | 109.1% | 1 | 1 | 0 | 0 | 82 | 0 | 4881711 | 57650 | 4824061 | 4893014 | 4759434 | 0 | 0 | 0 | 4759434 | 4740765 | 98.27% | 1 | -5116 | 11303 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 23092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 23092 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-04-17 | QTR4 | 24/25 | 409 | 5716819.1
| 04 | E4W88 | 44765415201 | 2024-02-02 | QTR3 | 23/24 | 3 | 3 | 233 | 271 | 240 | 79.4% | 1 | 31 | 0 | 0 | 55 | -17 | 6226524 | 63037 | 6163487 | 6395874 | 6393098 | 0 | 0 | 0 | 6393098 | 6379878 | 103.5% | 1 | -5542 | 169350 | 38 | 17 | 0 | 0 | 103394 | 103394 | 0 | 0 | 59105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162498 | 103394 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-04-09 | QTR4 | 24/25 | 412 | 6625403.9
| 04 | E4W89 | 44767415201 | 2024-07-12 | QTR1 | 24/25 | 1 | 1 | 180 | 262 | 260 | 98.89% | 1 | 2 | 0 | 0 | 82 | 0 | 3966137 | 50000 | 3916137 | 3985889 | 3958991 | 0 | 0 | 0 | 3958991 | 3953275 | 100.9% | 1 | -5716 | 19752 | 60 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 412 | 4276093.35
| 04 | E4W93 | 44764815201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 185 | 224 | 215 | 95.14% | 1 | 9 | 0 | 0 | 39 | 0 | 3198987 | 50000 | 3148987 | 3198987 | 3046918 | 0 | 0 | 0 | 3046918 | 3045966 | 96.73% | 1 | -952 | 0 | 18 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-18 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 408 | 3443705
| 04 | E4X14 | 44932315201 | 2024-04-05 | QTR4 | 23/24 | 1 | 5 | 209 | 308 | 298 | 107.7% | 1 | 10 | 0 | 0 | 78 | 21 | 3689059 | 50000 | 3639059 | 3733032 | 3801506 | 0 | 0 | 0 | 3801506 | 3800583 | 104.4% | 1 | -923 | 43973 | 65 | 8 | 5 | 0 | 0 | 0 | 0 | 21 | 74766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 21 | 74766 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-12 | QTR3 | 25/26 |  | 2025-10-30 | QTR2 | 25/26 | 408 | 2884956.63
| 04 | E4X17 | 44655115201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 132 | 174 | 174 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 1849000 | 50000 | 1799000 | 1870772 | 1768167 | 0 | 0 | 0 | 1768167 | 1768167 | 98.29% | 1 | 0 | 21772 | 38 | 4 | 0 | 0 | 4117 | 0 | 0 | 0 | 22787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26904 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-12 | QTR1 | 25/26 |  | 2025-07-02 | QTR1 | 25/26 | 409 | 2011837.24
| 04 | E4X24 | 44931815201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 222 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 3983900 | 50853 | 3933047 | 4183008 | 4262893 | 0 | 0 | 0 | 4262893 | 4262893 | 108.4% | 1 | 0 | 199108 | 48 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199108 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 409 | 5126069.11
| 04 | E4X33 | 44359525201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 262 | 309 | 294 | 94.27% | 1 | 15 | 0 | 0 | 47 | 0 | 2579048 | 50000 | 2529048 | 2787519 | 2747199 | 0 | 0 | 0 | 2747199 | 2747177 | 108.6% | 1 | -22 | 208471 | 38 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218168 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-11-13 | QTR2 | 25/26 | 408 | 3891911.4
| 04 | E4X39 | 44768115201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 170 | 193 | 193 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 2519093 | 50000 | 2469093 | 2519093 | 2422842 | 0 | 0 | 0 | 2422842 | 2420995 | 98.05% | 1 | -1848 | 0 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 412 | 2812112.37
| 04 | E4X51 | 44765815201 | 2024-08-02 | QTR1 | 24/25 | 3 | 1 | 252 | 287 | 265 | 91.27% | 1 | 22 | 0 | 0 | 35 | 0 | 3535833 | 50000 | 3485833 | 3535833 | 3387300 | 0 | 0 | 0 | 3387300 | 3384814 | 97.1% | 1 | -2487 | 0 | 14 | 21 | 0 | 0 | 13204 | 0 | 0 | 0 | 7499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20703 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 |  | 2025-09-03 | QTR1 | 25/26 | 409 | 3764178.43
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 20 | 34 | 104 | 6515 | 10295 | 9996 | 90% | 18 | 299 | 0 | 0 | 3182 | 598 | 256546225 | 1274661 | 255271563 | 286712853 | 285724638 | 0 | 56000 | 56000 | 285780638 | 285031498 | 90% | 18 | -231398 | 30124498 | 1513 | 603 | 391 | 0 | 1785668 | 1305237 | 0 | 69 | 2875629 | 34121 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517 | 527 | 21936429 | 3324897 | 0 | 0 | 2931092 | 75752 | 0 | 0 | 0 | 0 | 205 | 0 | 468030 | 0 | 0 | 0 | 323579 | 0 | 60 | 19 | 55844 | 55844 | 26 | 0 | 0 | 0 | 0 | 0 | -323327 | 0 | 1199 | 615 | 30061765 | 4795850
| District 04 Totals |  |  |  |  | 43 | 93 | 170 | 14394 | 21030 | 20378 | 93.02% | 40 | 652 | 0 | 0 | 5858 | 726 | 410744130 | 3021830 | 407722301 | 443881704 | 440538666 | 0 | 56000 | 56000 | 440594666 | 440087183 | 95.35% | 41 | 297866 | 33616172 | 3270 | 1271 | 417 | 0 | 3155947 | 1328034 | 208 | 129 | 3905774 | 253785 | 0 | 0 | 8824 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 0 | 0 | 517 | 527 | 21960826 | 3324897 | 17 | 0 | 2969593 | 75752 | 0 | 0 | 0 | 0 | 278 | 0 | 519788 | 0 | 0 | 161 | 488579 | 0 | 60 | 39 | 75346 | 75346 | 26 | 0 | 0 | 0 | 0 | 0 | -386705 | 0 | 1523 | 856 | 32552545 | 5057813
| 05 | T5650 | 23839555201 | 2020-03-11 | QTR3 | 19/20 | 7 | 12 | 1030 | 1956 | 1956 | 120.9% | 0 | 0 | 0 | 0 | 711 | 215 | 44960000 | 248112 | 44711888 | 46736451 | 46188504 | 0 | 0 | 0 | 46188504 | 47704062 | 106.7% | 1 | 1586115 | 1776451 | 295 | 416 | 0 | 57 | 769813 | 208395 | 0 | 169 | 1007439 | 1180290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63867 | 0 | 0 | 0 | 48656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 1889774 | 1388685 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-02-05 | QTR3 | 25/26 |  | 2025-12-03 | QTR2 | 25/26 | 515 | 45602807.97
| 05 | T5706 | 42955615201 | 2020-03-25 | QTR3 | 19/20 | 6 | 12 | 1100 | 1761 | 1761 | 109.3% | 1 | 0 | 0 | 0 | 559 | 102 | 44888403 | 150000 | 44738403 | 47699589 | 48432679 | 0 | 0 | 0 | 48432679 | 48287387 | 107.9% | 1 | 2317108 | 2811186 | 343 | 216 | 0 | 0 | 1647033 | 0 | 0 | 102 | 784469 | 30264 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26536 | 0 | 0 | 0 | 12848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 2823138 | 30264 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 513 | 37019154.5
| 05 | T5718 | 43763415201 | 2021-04-28 | QTR4 | 20/21 | 7 | 17 | 690 | 1399 | 1340 | 96.52% | 1 | 59 | 0 | 0 | 674 | 35 | 11250000 | 233500 | 11016500 | 12978309 | 13223828 | 0 | 0 | 0 | 13223828 | 13314228 | 120.9% | 0 | 155455 | 1728309 | 360 | 314 | 0 | 25 | 527918 | 11401 | 0 | 0 | 912863 | 0 | 0 | 10 | 40741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56556 | 0 | 0 | 0 | 355913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1901807 | 11401 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-10-23 | QTR2 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 507 | 10799982.79
| 05 | T5747 | 43366115201 | 2022-05-25 | QTR4 | 21/22 | 5 | 7 | 280 | 568 | 568 | 147.1% | 0 | 0 | 0 | 0 | 156 | 132 | 6696978 | 50000 | 6646978 | 7142732 | 7032054 | 0 | 0 | 0 | 7032054 | 7019736 | 105.6% | 1 | 0 | 445755 | 106 | 50 | 0 | 4 | 88147 | 0 | 0 | 5 | 26731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318 | 0 | 0 | 125 | 296588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 425240 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 |  | 2024-10-22 | QTR2 | 24/25 | 512 | 5918166.26
| 05 | T5759 | 44586715201 | 2023-04-26 | QTR4 | 22/23 | 5 | 6 | 170 | 600 | 588 | 92.94% | 1 | 12 | 0 | 0 | 430 | 0 | 3865830 | 50000 | 3815830 | 3991018 | 3937381 | 0 | 0 | 0 | 3937381 | 3936003 | 103.1% | 1 | -1378 | 125188 | 128 | 302 | 0 | 0 | -12273 | 0 | 0 | 0 | -103071 | 39310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251410 | 185032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136067 | 224342 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-08-13 | QTR1 | 25/26 | 514 | 3318268.57
| 05 | T5760 | 44114515201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 320 | 519 | 515 | 108.1% | 1 | 4 | 0 | 0 | 199 | 0 | 9020145 | 60000 | 8960145 | 9091224 | 9371724 | 0 | 0 | 0 | 9371724 | 9358265 | 104.4% | 1 | -1051 | 71079 | 39 | 130 | 0 | 0 | 58672 | 0 | 0 | 0 | 4020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62692 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2025-06-27 | QTR4 | 24/25 | 509 | 8000814.19
| 05 | T5777 | 44042425201 | 2023-01-25 | QTR3 | 22/23 | 3 | 5 | 650 | 704 | 611 | 81.23% | 1 | 93 | 0 | 0 | 86 | -32 | 22896706 | 150000 | 22746706 | 23663870 | 23767312 | 0 | 0 | 0 | 23767312 | 22921260 | 100.8% | 1 | -826558 | 767164 | 32 | 51 | 0 | 0 | 12008 | 0 | 0 | 0 | 246258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282497 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 28387049.83 | B10 | ACC - BONUS/INCENT/DISINCENT
| 05 | T5778 | 44569215201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 250 | 396 | 395 | 99.6% | 1 | 1 | 0 | 0 | 146 | 0 | 1617324 | 47000 | 1570324 | 1637324 | 1467772 | 0 | 0 | 0 | 1467772 | 1467140 | 93.43% | 1 | -632 | 20000 | 119 | 27 | 0 | 0 | 34331 | 0 | 0 | 0 | 28098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62429 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-01-30 | QTR3 | 24/25 | 509 | 1625738.6
| 05 | T5786 | 44521715201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 410 | 545 | 545 | 100% | 1 | 0 | 0 | 0 | 135 | 0 | 10986719 | 117744 | 10868975 | 11011859 | 11062198 | 0 | 0 | 0 | 11062198 | 11032701 | 101.5% | 1 | -4358 | 25139 | 80 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-28 | QTR2 | 25/26 |  | 2025-04-10 | QTR4 | 24/25 | 512 | 14985674.13
| 05 | T5789 | 43547125201 | 2023-05-24 | QTR4 | 22/23 | 3 | 3 | 360 | 467 | 467 | 104.2% | 1 | 0 | 0 | 0 | 92 | 15 | 8448064 | 70000 | 8378064 | 8800372 | 8800513 | 0 | 0 | 0 | 8800513 | 8740511 | 104.3% | 1 | 855 | 352308 | 69 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 93573 | 14238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 221451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 318271 | 14238 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 515 | 8153514.72
| 05 | T5792 | 41025135201 | 2023-06-14 | QTR4 | 22/23 | 3 | 9 | 610 | 822 | 816 | 104.3% | 1 | 6 | 0 | 0 | 180 | 32 | 15097285 | 150000 | 14947285 | 15626114 | 15519395 | 0 | 0 | 0 | 15519395 | 15475580 | 103.5% | 1 | -7963 | 1098563 | 116 | 64 | 0 | 0 | 64465 | 0 | 0 | 32 | 474785 | 8321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592234 | 0 | 0 | 0 | 1431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1132914 | 8321 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-13 | QTR3 | 25/26 |  | 2025-12-08 | QTR2 | 25/26 | 513 | 25813007.18
| 05 | T5795 | 24259285201 | 2023-06-14 | QTR4 | 22/23 | 3 | 4 | 380 | 531 | 523 | 113.4% | 1 | 8 | 0 | 0 | 92 | 59 | 8347803 | 60000 | 8287803 | 8496009 | 8830863 | 0 | 0 | 0 | 8830863 | 8791083 | 106.1% | 1 | -490 | 148206 | 43 | 49 | 0 | 59 | 0 | 0 | 0 | 0 | 139202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 145982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 507 | 8013785.1
| 05 | T5796 | 42617915201 | 2023-07-26 | QTR1 | 23/24 | 4 | 3 | 280 | 563 | 562 | 118.6% | 1 | 1 | 0 | 0 | 230 | 53 | 3346229 | 50000 | 3296229 | 3547942 | 3223459 | 0 | 0 | 0 | 3223459 | 3212971 | 97.47% | 1 | -31 | 201713 | 97 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 191255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 191255 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2026-01-07 | QTR3 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 512 | 4393698.6
| 05 | T5797 | 44568915201 | 2023-07-26 | QTR1 | 23/24 | 3 | 3 | 250 | 490 | 490 | 175.2% | 0 | 0 | 0 | 0 | 52 | 188 | 6209544 | 50000 | 6159544 | 6295030 | 5955348 | 0 | 0 | 0 | 5955348 | 5947678 | 96.56% | 1 | -685 | 85486 | 29 | 23 | 0 | 188 | 78501 | 61993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 78501 | 61993 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-01-14 | QTR3 | 25/26 |  | 2025-06-04 | QTR4 | 24/25 | 514 | 5653228.56
| 05 | T5799 | 44571615201 | 2023-10-25 | QTR2 | 23/24 | 3 | 7 | 330 | 445 | 445 | 104.2% | 1 | 0 | 0 | 0 | 101 | 14 | 7000000 | 71000 | 6929000 | 7423497 | 7482575 | 0 | 0 | 0 | 7482575 | 7419445 | 107.1% | 1 | -33657 | 423497 | 66 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 220409 | 72070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156171 | 0 | 0 | 0 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378650 | 72070 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 513 | 8074701.25
| 05 | T5800 | 44585515201 | 2023-07-26 | QTR1 | 23/24 | 3 | 5 | 230 | 409 | 491 | 173% | 0 | -82 | 82 | 0 | 93 | 86 | 3679712 | 50000 | 3629712 | 3851805 | 3808215 | 0 | 0 | 0 | 3808215 | 3802526 | 104.8% | 1 | -69 | 172092 | 61 | 32 | 0 | 84 | 71357 | 36514 | 0 | 9 | 67803 | 17258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 29703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 174435 | 53772 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 |  | 2025-06-05 | QTR4 | 24/25 | 514 | 2818721.96
| 05 | T5801 | 44521915201 | 2023-09-27 | QTR1 | 23/24 | 3 | 1 | 370 | 513 | 509 | 98.92% | 1 | 4 | 0 | 0 | 143 | 0 | 15286323 | 100000 | 15186323 | 15295366 | 15592805 | 0 | 0 | 0 | 15592805 | 15522129 | 102.2% | 1 | -61634 | 9043 | 97 | 46 | 0 | 0 | 33061 | 0 | 0 | 0 | 46645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79706 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 513 | 20005006.42
| 05 | T5804 | 43757515201 | 2024-05-22 | QTR4 | 23/24 | 1 | 2 | 160 | 223 | 223 | 100% | 1 | 0 | 0 | 0 | 63 | 0 | 3278993 | 50000 | 3228993 | 3308018 | 3163264 | 0 | 0 | 0 | 3163264 | 3163188 | 97.96% | 1 | -76 | 29025 | 59 | 4 | 0 | 0 | -17884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17884 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-01-14 | QTR3 | 25/26 |  | 2025-08-23 | QTR1 | 25/26 | 509 | 3131835.47
| 05 | T5805 | 44709215201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 280 | 334 | 332 | 99.29% | 1 | 2 | 0 | 0 | 54 | 0 | 3271306 | 50000 | 3221306 | 3287930 | 3244926 | 0 | 0 | 0 | 3244926 | 3224506 | 100.1% | 1 | -20420 | 16623 | 41 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2024-11-26 | QTR2 | 24/25 | 514 | 4597690.87
| 05 | T5806 | 44709815201 | 2023-09-27 | QTR1 | 23/24 | 3 | 3 | 300 | 435 | 431 | 98.67% | 1 | 4 | 0 | 0 | 135 | 0 | 9892142 | 110000 | 9782142 | 9938977 | 10455307 | 0 | 0 | 0 | 10455307 | 10363664 | 105.9% | 1 | -58186 | 46835 | 73 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 515 | 11922850
| 05 | T5809 | 43915615201 | 2023-09-27 | QTR1 | 23/24 | 4 | 2 | 420 | 517 | 481 | 91.43% | 1 | 36 | 0 | 0 | 97 | 0 | 19059007 | 150000 | 18909007 | 19456279 | 20132774 | 0 | 0 | 0 | 20132774 | 19987244 | 105.7% | 1 | -74410 | 397272 | 63 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-10-06 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 513 | 20470643.27
| 05 | T5811 | 43233215201 | 2023-10-25 | QTR2 | 23/24 | 6 | 6 | 250 | 541 | 540 | 149.6% | 0 | 1 | 0 | 0 | 176 | 115 | 15324226 | 150000 | 15174226 | 16443632 | 16758792 | 0 | 0 | 0 | 16758792 | 16617261 | 109.5% | 1 | -118108 | 1119406 | 124 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 614667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51362 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 62034 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 380350 | 643594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 115 | 1108414 | 643594 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-08-04 | QTR1 | 25/26 | 515 | 22228374.21
| 05 | T5826 | 45222915201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 200 | 276 | 273 | 98.5% | 1 | 3 | 0 | 0 | 76 | 0 | 1180815 | 50000 | 1130815 | 1180815 | 979467 | 0 | 0 | 0 | 979467 | 979467 | 86.62% | 1 | 0 | 0 | 71 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-07-08 | QTR1 | 25/26 | 507 | 1609251.1
| 05 | T5833 | 44708915201 | 2024-09-25 | QTR1 | 24/25 | 2 | 0 | 180 | 241 | 241 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 2100000 | 50000 | 2050000 | 2100000 | 2001416 | 0 | 0 | 0 | 2001416 | 2001416 | 97.63% | 1 | 0 | 0 | 8 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 513 | 2701146.14
| 05 | T5835 | 44873915201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 160 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 3081418 | 50000 | 3031418 | 3081418 | 3111059 | 0 | 0 | 0 | 3111059 | 3112003 | 102.7% | 1 | 944 | 0 | 37 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-02 | QTR1 | 25/26 | 515 | 3300432.25
| 05 | T5857 | 45613715201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 40 | 40 | 10 | 25% | 1 | 30 | 0 | 0 | 0 | 0 | 117123 | 7000 | 110123 | 113191 | 103346 | 0 | 0 | 0 | 103346 | 103346 | 93.85% | 1 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-17 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 513 | 180485.52
| 05 | T5858 | 45616815201 | 2025-03-26 | QTR3 | 24/25 | 5 | 3 | 120 | 130 | 105 | 79.17% | 1 | 25 | 0 | 0 | 10 | 0 | 948635 | 47500 | 901135 | 993577 | 604185 | 0 | 0 | 0 | 604185 | 604185 | 67.05% | 1 | 0 | 44942 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 44942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44942 | 0 | F850531344 | PREMIER PAVING LLC | N/A | N/A | N/A | N/A | 2026-01-09 | QTR3 | 25/26 |  | 2025-09-16 | QTR1 | 25/26 | 514 | 1621409.55
| 05 | T9030 | 44199035223 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 270 | 367 | 366 | 107.8% | 1 | 1 | 0 | 0 | 97 | 0 | 5555556 | 53950 | 5501606 | 5605113 | 5565155 | 0 | 0 | 0 | 5565155 | 5565155 | 101.2% | 1 | 0 | 49558 | 26 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-05-05 | QTR4 | 24/25 | 513 | 5529999.88
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 28 | 94 | 118 | 10090 | 16001 | 15793 | 82.14% | 23 | 208 | 82 | 0 | 4897 | 1014 | 287406286 | 2475806 | 284930480 | 298797461 | 299816316 | 0 | 0 | 0 | 299816316 | 299674140 | 96.43% | 27 | 2850771 | 11960908 | 2585 | 2247 | 0 | 417 | 3355149 | 318303 | 0 | 317 | 4952040 | 1361751 | 0 | 10 | 50192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 79 | 1290983 | 201655 | 0 | 4 | 94074 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 557071 | 0 | 0 | 125 | 701157 | 0 | 0 | 201 | 631504 | 643594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1153 | 11632167 | 2525303
| 05 | E50B8 | 44521515201 | 2023-06-06 | QTR4 | 22/23 | 4 | 6 | 410 | 645 | 641 | 118.8% | 1 | 4 | 0 | 0 | 154 | 81 | 11282143 | 100000 | 11182143 | 11851012 | 12077791 | 0 | 0 | 0 | 12077791 | 12077791 | 108% | 1 | 0 | 568869 | 109 | 45 | 0 | 6 | 419002 | 23191 | 0 | 37 | 361551 | 8287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 56263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -235426 | 0 | 0 | 84 | 601391 | 31478 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-03-02 | QTR3 | 25/26 |  | 2025-09-05 | QTR1 | 25/26 | 514 | 10131956.15
| 05 | E50F1 | 44656815201 | 2024-02-06 | QTR3 | 23/24 | 1 | 0 | 127 | 172 | 172 | 101.6% | 1 | 0 | 0 | 0 | 43 | 2 | 1104118 | 42000 | 1062118 | 1104118 | 1062935 | 0 | 0 | 0 | 1062935 | 1062929 | 100.1% | 1 | -6 | 0 | 25 | 18 | 0 | 0 | 3237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3237 | 0 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 509 | 1174163.5
| 05 | E50F5 | 44316915201 | 2024-01-04 | QTR3 | 23/24 | 1 | 1 | 290 | 430 | 429 | 123.4% | 0 | 1 | 0 | 0 | 71 | 69 | 5036336 | 50000 | 4986336 | 5073420 | 4545253 | 0 | 0 | 0 | 4545253 | 4525803 | 90.76% | 1 | -19451 | 37085 | 45 | 26 | 0 | 0 | 0 | 0 | 0 | 69 | 62085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 62085 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-06-05 | QTR4 | 24/25 | 514 | 5619045.42
| 05 | E51F2 | 44768815201 | 2024-04-02 | QTR4 | 23/24 | 2 | 1 | 150 | 239 | 238 | 110.7% | 1 | 1 | 0 | 0 | 72 | 17 | 1504656 | 50000 | 1454656 | 1506430 | 1447570 | 0 | 0 | 0 | 1447570 | 1445324 | 99.36% | 1 | -472 | 1774 | 46 | 26 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-21 | QTR4 | 24/25 | 514 | 1590260.07
| 05 | E51F6 | 43923415201 | 2024-03-05 | QTR3 | 23/24 | 3 | 3 | 350 | 458 | 457 | 99.71% | 1 | 1 | 0 | 0 | 108 | 0 | 16652098 | 150000 | 16502098 | 16895551 | 16781249 | 0 | 0 | 0 | 16781249 | 16753875 | 101.5% | 1 | -23602 | 243453 | 50 | 58 | 0 | 0 | 254263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254263 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-12-04 | QTR2 | 25/26 | 512 | 16309344.71
| 05 | E51F7 | 44530215201 | 2024-03-05 | QTR3 | 23/24 | 3 | 5 | 250 | 400 | 400 | 108% | 1 | 0 | 0 | 0 | 130 | 20 | 5562121 | 50000 | 5512121 | 5724310 | 5880473 | 0 | 0 | 0 | 5880473 | 5842942 | 106% | 1 | -14889 | 162189 | 89 | 41 | 0 | 0 | 29317 | 0 | 0 | 20 | 112422 | 22050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 141739 | 22050 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 |  | 2025-10-01 | QTR2 | 25/26 | 512 | 6330177.48
| 05 | E51F9 | 43912415201 | 2024-04-02 | QTR4 | 23/24 | 2 | 2 | 260 | 347 | 320 | 95.38% | 1 | 27 | 0 | 0 | 72 | 15 | 4408516 | 58000 | 4350516 | 4442576 | 4279968 | 0 | 0 | 0 | 4279968 | 4272484 | 98.21% | 1 | 0 | 34060 | 38 | 34 | 0 | 0 | 3850 | 0 | 0 | 0 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30938 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-19 | QTR4 | 24/25 | 513 | 6688704.65
| 05 | E52F4 | 45293215201 | 2024-06-04 | QTR4 | 23/24 | 1 | 0 | 160 | 367 | 366 | 106.9% | 1 | 1 | 0 | 0 | 195 | 12 | 1554510 | 50000 | 1504510 | 1554510 | 1576041 | 0 | 0 | 0 | 1576041 | 1575969 | 104.7% | 1 | -72 | 0 | 154 | 41 | 0 | 0 | 3946 | 0 | 0 | 7 | 16349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 36911 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-02-24 | QTR3 | 25/26 |  | 2026-01-06 | QTR3 | 25/26 | 507 | 1518095.5
| 05 | E53F2 | 44879115201 | 2024-10-01 | QTR2 | 24/25 | 1 | 3 | 170 | 268 | 268 | 102.9% | 1 | 0 | 0 | 0 | 93 | 5 | 7065614 | 86000 | 6979614 | 7183452 | 7253477 | 0 | 0 | 0 | 7253477 | 7256561 | 104% | 1 | 3084 | 117838 | 75 | 18 | 0 | 5 | 62000 | 0 | 0 | 0 | 47838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 109838 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 514 | 8985393.39
| 05 | E53F6 | 44880115201 | 2024-08-08 | QTR1 | 24/25 | 1 | 0 | 270 | 372 | 353 | 98.15% | 1 | 19 | 0 | 0 | 88 | 14 | 5664533 | 50000 | 5614533 | 5664533 | 5824248 | 0 | 0 | 0 | 5824248 | 5821719 | 103.7% | 1 | -2529 | 0 | 50 | 38 | 0 | 0 | 6765 | 0 | 0 | 0 | 12871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19636 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2026-02-24 | QTR3 | 25/26 |  | 2025-11-25 | QTR2 | 25/26 | 509 | 5574707.4
| 05 | E53F7 | 44984515201 | 2024-12-03 | QTR2 | 24/25 | 1 | 0 | 130 | 255 | 255 | 100% | 1 | 0 | 0 | 0 | 125 | 0 | 925088 | 40024 | 885064 | 925088 | 953719 | 0 | 0 | 0 | 953719 | 953719 | 107.8% | 1 | 0 | 0 | 115 | 10 | 0 | 0 | 2525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2525 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-01-13 | QTR3 | 25/26 |  | 2025-11-18 | QTR2 | 25/26 | 507 | 845921.65
| 05 | E53F8 | 45022745201 | 2024-06-04 | QTR4 | 23/24 | 1 | 1 | 160 | 259 | 257 | 111.9% | 1 | 2 | 0 | 0 | 78 | 21 | 1498164 | 50000 | 1448164 | 1498164 | 1468694 | 0 | 0 | 0 | 1468694 | 1468694 | 101.4% | 1 | 0 | 0 | 12 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 24155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24155 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 513 | 1507974.75
| 05 | E54B3 | 44521415201 | 2023-10-03 | QTR2 | 23/24 | 3 | 3 | 270 | 366 | 366 | 100% | 1 | 0 | 0 | 0 | 96 | 0 | 6964127 | 72500 | 6891627 | 7171619 | 7043664 | 0 | 0 | 0 | 7043664 | 6984590 | 101.3% | 1 | -45651 | 207492 | 59 | 37 | 0 | 0 | 167324 | 0 | 0 | 0 | 41679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256083 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 9627438.59
| 05 | E55F3 | 45131115201 | 2025-02-04 | QTR3 | 24/25 | 1 | 0 | 150 | 183 | 183 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 4402920 | 58000 | 4344920 | 4402920 | 4332664 | 0 | 0 | 0 | 4332664 | 4326586 | 99.58% | 1 | -6078 | 0 | 20 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13234 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 |  | 2025-11-05 | QTR2 | 25/26 | 513 | 6422896.48
| 05 | E55F4 | 42690555201 | 2025-04-01 | QTR4 | 24/25 | 1 | 0 | 120 | 121 | 108 | 89.17% | 1 | 13 | 0 | 0 | 1 | 0 | 1132509 | 50000 | 1082509 | 1132509 | 1025664 | 0 | 0 | 0 | 1025664 | 1025664 | 94.75% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES LLC | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 514 | 1246519.8
| 05 | E55F6 | 44529815201 | 2025-03-04 | QTR3 | 24/25 | 1 | 2 | 180 | 230 | 214 | 91.11% | 1 | 16 | 0 | 0 | 50 | 0 | 7863435 | 100000 | 7763435 | 8058116 | 8341201 | 0 | 0 | 0 | 8341201 | 8333175 | 107.3% | 1 | -8027 | 194681 | 36 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 194681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194681 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-12-12 | QTR2 | 25/26 | 514 | 10455826.3
| 05 | E56B6 | 44521115201 | 2023-06-06 | QTR4 | 22/23 | 2 | 1 | 180 | 442 | 442 | 131.7% | 0 | 0 | 0 | 0 | 205 | 57 | 3196756 | 50000 | 3146756 | 3198241 | 3427202 | 0 | 0 | 0 | 3427202 | 3427202 | 108.9% | 1 | 0 | 1485 | 141 | 64 | 0 | 7 | 8757 | 0 | 0 | 30 | 12941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 28133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 49830 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-05-21 | QTR4 | 24/25 | 507 | 3501358.08
| 05 | E56F4 | 41025155201 | 2025-05-06 | QTR4 | 24/25 | 1 | 0 | 140 | 173 | 171 | 98.57% | 1 | 2 | 0 | 0 | 33 | 0 | 3296100 | 53000 | 3243100 | 3296100 | 3182948 | 0 | 0 | 0 | 3182948 | 3193975 | 98.49% | 1 | 11027 | 0 | 9 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2026-01-23 | QTR3 | 25/26 | 513 | 5178576.2
| 05 | E56F7 | 45305815201 | 2025-04-01 | QTR4 | 24/25 | 1 | 0 | 190 | 217 | 196 | 88.95% | 1 | 21 | 0 | 0 | 27 | 0 | 6639966 | 78000 | 6561966 | 6639966 | 6618677 | 0 | 0 | 0 | 6618677 | 6618677 | 100.9% | 1 | 0 | 0 | 7 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 |  | 2026-01-15 | QTR3 | 25/26 | 509 | 8028735.15
| 05 | E57B3 | 24259265201 | 2023-06-06 | QTR4 | 22/23 | 3 | 4 | 590 | 703 | 696 | 98.81% | 1 | 7 | 0 | 0 | 113 | 0 | 9899345 | 50000 | 9849345 | 10080554 | 10364962 | 0 | 0 | 0 | 10364962 | 10344890 | 105% | 1 | -9 | 181208 | 61 | 52 | 0 | 0 | 111146 | 0 | 0 | 0 | 51682 | 1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162828 | 1682 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2025-12-19 | QTR2 | 25/26 |  | 2025-09-23 | QTR1 | 25/26 | 507 | 8480188.02
| 05 | E57B5 | 44530315201 | 2023-06-06 | QTR4 | 22/23 | 3 | 3 | 490 | 635 | 634 | 99.8% | 1 | 1 | 0 | 0 | 145 | 0 | 11137584 | 50000 | 11087584 | 11274458 | 11215283 | 0 | 0 | 0 | 11215283 | 11200767 | 101% | 1 | -786 | 136874 | 80 | 65 | 0 | 0 | 39281 | 0 | 0 | 0 | 110135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149459 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 |  | 2025-08-01 | QTR1 | 25/26 | 507 | 8364007.55
| 05 | E57B7 | 44708515201 | 2023-06-06 | QTR4 | 22/23 | 3 | 5 | 500 | 634 | 634 | 101.2% | 1 | 0 | 0 | 0 | 128 | 6 | 13078910 | 128000 | 12950910 | 13273764 | 13547486 | 0 | 0 | 0 | 13547486 | 13528029 | 104.5% | 1 | -2602 | 194854 | 81 | 47 | 0 | 0 | 39880 | 0 | 0 | 32 | 217171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 257051 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-06-20 | QTR4 | 24/25 | 514 | 13524204.48 | A5 | ICC - BAM/BONUS
| 05 | E59A5 | 44780715201 | 2022-04-06 | QTR4 | 21/22 | 1 | 0 | 270 | 1159 | 1159 | 100% | 1 | 0 | 0 | 0 | 889 | 0 | 973615 | 34352 | 939263 | 973615 | 939263 | 0 | 0 | 0 | 939263 | 939263 | 100% | 1 | 0 | 0 | 141 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-09-19 | QTR1 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 509 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E59B2 | 43986415201 | 2024-02-06 | QTR3 | 23/24 | 3 | 3 | 200 | 286 | 286 | 100% | 1 | 0 | 0 | 0 | 86 | 0 | 3015224 | 50000 | 2965224 | 3086900 | 3009526 | 0 | 0 | 0 | 3009526 | 2958475 | 99.77% | 1 | -4843 | 71676 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-15 | QTR3 | 24/25 | 513 | 3337723.49
| 05 | E5Z18 | 24020045201 | 2018-08-22 | QTR1 | 18/19 | 4 | 18 | 1400 | 2248 | 2248 | 117.8% | 1 | 0 | 0 | 0 | 599 | 249 | 253332000 | 150000 | 253182000 | 267516079 | 267608352 | 0 | 25000 | 25000 | 267633352 | 268414123 | 106% | 1 | 8560014 | 14184079 | 138 | 461 | 0 | 0 | 2669763 | 0 | 0 | 0 | 2461289 | 94536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 946937 | 321742 | 0 | 0 | 30080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949329 | 0 | 0 | 249 | 7300000 | 7300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 14357398 | 7716278 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2024-12-20 | QTR2 | 24/25 | 507 | 283931078 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 25 | 48 | 61 | 7407 | 11609 | 11493 | 92% | 23 | 116 | 0 | 0 | 3634 | 568 | 387190388 | 1699876 | 385490512 | 403528005 | 403808310 | 0 | 25000 | 25000 | 403833310 | 404353226 | 100% | 25 | 8445108 | 16337617 | 1624 | 2010 | 0 | 35 | 3821056 | 23191 | 0 | 195 | 3802810 | 126555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1046434 | 321742 | 0 | 20 | 105293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949329 | 0 | 0 | 249 | 7300000 | 7300000 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -235426 | 0 | 0 | 576 | 16789497 | 7771488
| District 05 Totals |  |  |  |  | 53 | 142 | 179 | 17497 | 27610 | 27286 | 86.79% | 46 | 324 | 82 | 0 | 8531 | 1582 | 674596674 | 4175682 | 670420992 | 702325466 | 703624626 | 0 | 25000 | 25000 | 703649626 | 704027366 | 98.11% | 52 | 11295879 | 28298525 | 4209 | 4257 | 0 | 452 | 7176205 | 341494 | 0 | 512 | 8754850 | 1488306 | 0 | 10 | 50192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 135 | 2337417 | 523397 | 0 | 24 | 199367 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 1506400 | 0 | 0 | 374 | 8001157 | 7300000 | 0 | 222 | 631504 | 643594 | 0 | 0 | 0 | 0 | 0 | 0 | -235426 | 0 | 32 | 1729 | 28421664 | 10296791
| 06 | T6466 | 43992315201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 160 | 189 | 184 | 96.88% | 1 | 5 | 0 | 0 | 29 | 0 | 749749 | 36694 | 713055 | 750453 | 687268 | 0 | 0 | 0 | 687268 | 687166 | 96.37% | 1 | -102 | 704 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 613 | 759570.75
| 06 | T6514 | 44462215201 | 2022-04-27 | QTR4 | 21/22 | 3 | 6 | 450 | 576 | 465 | 87.78% | 1 | 111 | 0 | 0 | 70 | 56 | 12567171 | 112026 | 12455145 | 13007370 | 12865831 | 0 | 500000 | 500000 | 13365831 | 12808223 | 102.8% | 1 | -557608 | 440200 | 42 | 28 | 0 | 0 | 75620 | 0 | 0 | 0 | 66701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 320618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 462939 | 0 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2026-01-29 | QTR3 | 25/26 |  | 2024-08-07 | QTR1 | 24/25 | 613 | 11765757.23 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6541 | 44390215201 | 2023-02-22 | QTR3 | 22/23 | 4 | 3 | 400 | 476 | 462 | 96.5% | 1 | 14 | 0 | 0 | 76 | 0 | 6112543 | 50000 | 6062543 | 6196534 | 6055588 | 0 | 0 | 0 | 6055588 | 6046499 | 99.74% | 1 | -7887 | 83991 | 29 | 47 | 0 | 0 | 30261 | 0 | 0 | 0 | 18983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56474 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-06-11 | QTR4 | 24/25 | 613 | 4898503.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6547 | 44392115201 | 2023-05-24 | QTR4 | 22/23 | 4 | 6 | 340 | 533 | 513 | 97.94% | 1 | 20 | 0 | 0 | 180 | 13 | 7844825 | 81266 | 7763559 | 8071972 | 8026073 | 0 | 200000 | 200000 | 8226073 | 8025252 | 103.4% | 1 | -200821 | 227147 | 146 | 34 | 0 | 13 | 211928 | 0 | 0 | 0 | 27940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 239868 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-03-28 | QTR3 | 24/25 | 636 | 8411804.1 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6555 | 44598715201 | 2023-04-26 | QTR4 | 22/23 | 8 | 6 | 500 | 526 | 459 | 86.6% | 1 | 67 | 0 | 0 | 22 | 4 | 15230513 | 150000 | 15080513 | 15276979 | 14673045 | 0 | 440000 | 440000 | 15113045 | 14624087 | 96.97% | 1 | -460650 | 46466 | 10 | 16 | 0 | 0 | 43405 | 0 | 0 | 0 | 81997 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17514 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65908 | 0 | 0 | 0 | 79761 | 21158 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 636 | 16721997.85 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6556 | 44389615201 | 2023-05-24 | QTR4 | 22/23 | 5 | 5 | 450 | 493 | 434 | 86.89% | 1 | 59 | 0 | 0 | 43 | 0 | 12343500 | 99969 | 12243531 | 12329103 | 12004695 | 0 | 340000 | 340000 | 12344695 | 12003108 | 98.04% | 1 | -341587 | -14397 | 13 | 30 | 0 | 0 | 51988 | 0 | 0 | 0 | 192434 | 111954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6723 | 0 | 0 | 0 | 1786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -260667 | 0 | 0 | 0 | -7736 | 111954 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-02-06 | QTR3 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 636 | 10090244.35 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6562 | 44393715201 | 2023-03-29 | QTR3 | 22/23 | 6 | 0 | 400 | 455 | 384 | 82.25% | 1 | 71 | 0 | 0 | 55 | 0 | 9816354 | 102429 | 9713925 | 9816354 | 9814725 | 0 | 320000 | 320000 | 10134725 | 9792214 | 100.8% | 1 | -342511 | 0 | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-08 | QTR1 | 25/26 |  | 2025-01-20 | QTR3 | 24/25 | 613 | 10415642.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6564 | 44599515201 | 2023-12-06 | QTR2 | 23/24 | 2 | 2 | 240 | 259 | 219 | 83.33% | 1 | 40 | 0 | 0 | 19 | 0 | 2427793 | 50000 | 2377793 | 2522356 | 2377282 | 0 | 100000 | 100000 | 2477282 | 2374390 | 99.86% | 1 | -102891 | 94563 | 5 | 14 | 0 | 0 | 13136 | 0 | 0 | 0 | 34463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54683 | 3620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102281 | 3620 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 636 | 2381685.3 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6565 | 44389815202 | 2023-02-22 | QTR3 | 22/23 | 3 | 3 | 480 | 626 | 584 | 98.75% | 1 | 42 | 0 | 0 | 110 | 36 | 17424162 | 150000 | 17274162 | 17775584 | 17807123 | 0 | 360000 | 360000 | 18167123 | 17736459 | 102.7% | 1 | -430664 | 351422 | 80 | 30 | 0 | 0 | 84168 | 0 | 0 | 36 | 237134 | 22708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 443354 | 22708 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 |  | 2025-05-09 | QTR4 | 24/25 | 636 | 16704094.5 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6567 | 44757415201 | 2024-05-22 | QTR4 | 23/24 | 2 | 1 | 197 | 320 | 313 | 96.45% | 1 | 7 | 0 | 0 | 123 | 0 | 1669000 | 50000 | 1619000 | 1695000 | 1692054 | 0 | 0 | 0 | 1692054 | 1691797 | 104.5% | 1 | -258 | 26000 | 98 | 25 | 0 | 0 | 15742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15742 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-03-09 | QTR3 | 25/26 |  | 2026-01-30 | QTR3 | 25/26 | 613 | 1801028.4
| 06 | T6568 | 44393225201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 154 | 185 | 179 | 96.1% | 1 | 6 | 0 | 0 | 31 | 0 | 1068800 | 50000 | 1018800 | 1068800 | 1002901 | 0 | 0 | 0 | 1002901 | 1002859 | 98.44% | 1 | -41 | 0 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F832482227 | TRAFFICO LLC | N/A | N/A | N/A | N/A | 2026-01-22 | QTR3 | 25/26 |  | 2025-10-16 | QTR2 | 25/26 | 613 | 1151283.4
| 06 | T6573 | 44599115201 | 2023-12-06 | QTR2 | 23/24 | 4 | 3 | 450 | 488 | 422 | 85.33% | 1 | 66 | 0 | 0 | 38 | 0 | 7944520 | 85047 | 7859473 | 7965978 | 7740756 | 0 | 320000 | 320000 | 8060756 | 7730600 | 98.36% | 1 | -330157 | 21458 | 15 | 23 | 0 | 0 | 10477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2205 | 2205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12682 | 2205 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 636 | 8387398.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6574 | 44780515201 | 2023-10-25 | QTR2 | 23/24 | 2 | 2 | 300 | 333 | 284 | 83.67% | 1 | 49 | 0 | 0 | 33 | 0 | 3338573 | 50000 | 3288573 | 3388573 | 3361643 | 0 | 100000 | 100000 | 3461643 | 3354655 | 102% | 1 | -106988 | 50000 | 23 | 10 | 0 | 0 | 12008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33215 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-10-14 | QTR2 | 25/26 |  | 2025-03-27 | QTR3 | 24/25 | 613 | 3605553.8 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6575 | 44780615201 | 2024-01-31 | QTR3 | 23/24 | 2 | 1 | 200 | 303 | 303 | 111% | 1 | 0 | 0 | 0 | 103 | 0 | 4637389 | 50000 | 4587389 | 4652332 | 4600291 | 0 | 0 | 0 | 4600291 | 4582375 | 99.89% | 1 | -2973 | 14943 | 59 | 22 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 636 | 4247705.35 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6577 | 44390915201 | 2024-04-24 | QTR4 | 23/24 | 2 | 4 | 320 | 382 | 299 | 74.06% | 1 | 83 | 0 | 0 | 62 | 0 | 4280927 | 50000 | 4230927 | 4380927 | 4298470 | 0 | 180000 | 180000 | 4478470 | 4296065 | 101.5% | 1 | -182405 | 100000 | 51 | 11 | 0 | 0 | 25028 | 0 | 0 | 0 | 21810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22967 | 0 | 0 | 0 | 13118 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82924 | 2195 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-12-05 | QTR2 | 25/26 | 613 | 4677512.3 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6580 | 44600015201 | 2024-04-24 | QTR4 | 23/24 | 3 | 4 | 380 | 458 | 458 | 100% | 1 | 0 | 0 | 0 | 78 | 0 | 5947099 | 61718 | 5885381 | 6376641 | 6242028 | 0 | 0 | 0 | 6242028 | 6225782 | 105.8% | 1 | -16246 | 429541 | 35 | 43 | 0 | 0 | 266153 | 1847 | 0 | 0 | 30029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160523 | 0 | 0 | 0 | 2939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459644 | 1847 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2026-02-04 | QTR3 | 25/26 | 636 | 6394668.5 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6584 | 44391215201 | 2024-03-27 | QTR3 | 23/24 | 3 | 5 | 380 | 430 | 360 | 81.58% | 1 | 70 | 0 | 0 | 50 | 0 | 8558846 | 77205 | 8481641 | 8890402 | 8748106 | 0 | 220000 | 220000 | 8968106 | 8742165 | 103.1% | 1 | -225941 | 331556 | 27 | 23 | 0 | 0 | 69085 | 0 | 0 | 0 | 250233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65727 | 7495 | 0 | 0 | 7079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392125 | 7495 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 613 | 7821851.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6598 | 44780415201 | 2024-09-25 | QTR1 | 24/25 | 2 | 1 | 240 | 271 | 220 | 78.75% | 1 | 51 | 0 | 0 | 31 | 0 | 2627713 | 50000 | 2577713 | 2705308 | 2578007 | 0 | 120000 | 120000 | 2698007 | 2578006 | 100% | 1 | -120001 | 77594 | 23 | 8 | 0 | 0 | 11001 | 0 | 0 | 0 | 66593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77594 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-10-08 | QTR2 | 25/26 | 636 | 3026337.1 | B5 | ACC - INCENTIVE/DISINCENTIVE
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 18 | 57 | 53 | 6041 | 7303 | 6542 | 100% | 18 | 761 | 0 | 0 | 1153 | 109 | 124589477 | 1356354 | 123233123 | 126870666 | 124575886 | 0 | 3200000 | 3200000 | 127775886 | 124301702 | 100% | 18 | -3429731 | 2281188 | 729 | 406 | 0 | 13 | 920000 | 1847 | 22 | 36 | 1029021 | 155820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 778037 | 11115 | 0 | 0 | 51087 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -326575 | 0 | 22 | 105 | 2451571 | 173182
| 06 | E6L20 | 25054885201 | 2022-05-26 | QTR4 | 21/22 | 9 | 6 | 800 | 926 | 890 | 95.5% | 1 | 36 | 0 | 0 | 126 | 0 | 28158187 | 150000 | 28008187 | 28920235 | 27890563 | 0 | 120000 | 120000 | 28010563 | 27701758 | 98.91% | 1 | -239034 | 762049 | 79 | 47 | 0 | 0 | 54216 | 11723 | 0 | 0 | 229137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747305 | 11723 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-13 | QTR3 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 636 | 23137912.5 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | E6M86 | 43351125201 | 2021-05-27 | QTR4 | 20/21 | 3 | 13 | 1020 | 1267 | 1212 | 103.3% | 1 | 55 | 0 | 0 | 158 | 89 | 41366428 | 150000 | 41216428 | 43068537 | 43251556 | 0 | 1960000 | 1960000 | 45211556 | 43282192 | 105% | 1 | -173492 | 1702108 | 104 | 54 | 0 | 0 | 601267 | 0 | 0 | 0 | 386677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 685738 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -94401 | 0 | 0 | 89 | 1678869 | 0 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-03-12 | QTR3 | 24/25 | 613 | 33950112.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | E6N17 | 44716515201 | 2021-09-13 | QTR1 | 21/22 | 5 | 12 | 900 | 1272 | 1272 | 119.7% | 1 | 0 | 0 | 0 | 195 | 177 | 66054600 | 150000 | 65904600 | 66794016 | 66824078 | 0 | 1200000 | 1200000 | 68024078 | 67015448 | 101.7% | 1 | -977158 | 739416 | 132 | 63 | 0 | 0 | 168972 | 0 | 0 | 177 | 1395729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042425 | 0 | 0 | 0 | 396899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -994258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1304449 | 0 | 0 | 177 | 705319 | 0 | F834649779 | AGI DE MOYA JOINT VENTURE | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 |  | 2025-07-25 | QTR1 | 25/26 | 636 | 34964142.28 | B5:B5:B5::::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| 06 | E6O12 | 44391925201 | 2023-05-25 | QTR4 | 22/23 | 3 | 1 | 280 | 309 | 263 | 83.57% | 1 | 46 | 0 | 0 | 29 | 0 | 2869869 | 50000 | 2819869 | 2869869 | 2778313 | 0 | 140000 | 140000 | 2918313 | 2778250 | 98.52% | 1 | -140063 | 0 | 8 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 |  | 2025-04-24 | QTR4 | 24/25 | 636 | 2865779.1 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | E6O17 | 43029169201 | 2022-06-13 | QTR4 | 21/22 | 2 | 3 | 628 | 1156 | 1148 | 143.9% | 0 | 8 | 0 | 0 | 384 | 144 | 7237000 | 51988 | 7185012 | 7269318 | 7237180 | 0 | 0 | 0 | 7237180 | 0 | 0% | 1 | -7237180 | 32318 | 121 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 19850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 32318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 52168 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 636 | 5284476.93 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6O81 | 44598815201 | 2024-03-28 | QTR3 | 23/24 | 1 | 1 | 250 | 259 | 222 | 85.2% | 1 | 37 | 0 | 0 | 9 | 0 | 3370711 | 50000 | 3320711 | 3853261 | 3033601 | 0 | 120000 | 120000 | 3153601 | 3032315 | 91.32% | 1 | -121286 | 482550 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 482550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482550 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 613 | 3432003 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6P13 | 43029189201 | 2024-04-22 | QTR4 | 23/24 | 2 | 0 | 400 | 475 | 459 | 96% | 1 | 16 | 0 | 0 | 75 | 0 | 1315382 | 50000 | 1265382 | 1315382 | 1284180 | 0 | 0 | 0 | 1284180 | 0 | 0% | 1 | -1284180 | 0 | 44 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-11-13 | QTR2 | 25/26 |  | 2025-09-19 | QTR1 | 25/26 | 636 | 1725000 | Y | DESIGN/BUILD PROJECT
| 06 | E6P23 | 44391115201 | 2024-03-28 | QTR3 | 23/24 | 1 | 7 | 340 | 363 | 320 | 87.35% | 1 | 43 | 0 | 0 | 23 | 0 | 5790735 | 50000 | 5740735 | 6121430 | 5667306 | 0 | 100000 | 100000 | 5767306 | 5665707 | 98.69% | 1 | -101599 | 330695 | 13 | 10 | 0 | 0 | 58475 | 0 | 0 | 0 | 97436 | 21191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47458 | 32917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316829 | 54108 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-11-21 | QTR2 | 25/26 |  | 4862238.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 8 | 26 | 43 | 4618 | 6027 | 5786 | 87.5% | 7 | 241 | 0 | 0 | 999 | 410 | 156162912 | 701988 | 155460924 | 160212048 | 157966777 | 0 | 3640000 | 3640000 | 161606777 | 149475670 | 100% | 8 | -10273992 | 4049136 | 505 | 354 | 0 | 0 | 882930 | 11723 | 0 | 177 | 2611379 | 21191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233 | 2309831 | 0 | 0 | 0 | 470282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -935876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47458 | 32917 | 0 | 0 | 0 | 0 | 0 | 0 | -1398850 | 0 | 0 | 410 | 3987153 | 65831
| District 06 Totals |  |  |  |  | 26 | 83 | 96 | 10659 | 13330 | 12328 | 96.15% | 25 | 1002 | 0 | 0 | 2152 | 519 | 280752389 | 2058342 | 278694047 | 287082714 | 282542663 | 0 | 6840000 | 6840000 | 289382663 | 273777372 | 100% | 26 | -13703723 | 6330324 | 1234 | 760 | 0 | 13 | 1802930 | 13570 | 22 | 213 | 3640400 | 177011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 3087868 | 11115 | 0 | 0 | 521369 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | -935876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47458 | 32917 | 0 | 0 | 0 | 0 | 0 | 0 | -1725425 | 0 | 22 | 515 | 6438724 | 239013
| 07 | T7396 | 41673245201 | 2019-07-31 | QTR1 | 19/20 | 4 | 12 | 1200 | 1366 | 1366 | 100% | 1 | 0 | 0 | 0 | 166 | 0 | 55832153 | 444272 | 55387881 | 56499915 | 56120655 | 0 | 875160 | 875160 | 56995815 | 56570953 | 102.1% | 1 | -113501 | 667762 | 87 | 79 | 0 | 0 | 537977 | 184519 | 0 | 0 | 204897 | 116725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835048 | 301244 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2023-07-17 | QTR1 | 23/24 | 798 | 63202968.19 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 07 | T7472 | 43182125201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 1200 | 1362 | 1223 | 90.42% | 1 | 139 | 0 | 0 | 138 | 24 | 85239705 | 150000 | 85089705 | 94443373 | 95456225 | 0 | 0 | 0 | 95456225 | 95322196 | 112% | 0 | 2218662 | 9203668 | 61 | 77 | 0 | 0 | 459126 | 0 | 0 | 21 | 3062413 | 383024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 5033268 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 177538 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1334779 | 0 | 0 | 93 | 8284381 | 1601156 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-02-28 | QTR3 | 24/25 | 714 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7505 | 44166115201 | 2023-05-24 | QTR4 | 22/23 | 2 | 6 | 450 | 530 | 530 | 100% | 1 | 0 | 0 | 0 | 80 | 0 | 13856415 | 100000 | 13756415 | 13819912 | 13656236 | 0 | 0 | 0 | 13656236 | 13594713 | 98.82% | 1 | -2106 | -36503 | 45 | 35 | 0 | 0 | 25728 | 22538 | 0 | 0 | -116398 | 38900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -90670 | 61438 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-15 | QTR3 | 25/26 |  | 2025-05-19 | QTR4 | 24/25 | 796 | 14165000
| 07 | T7507 | 44600915201 | 2023-05-17 | QTR4 | 22/23 | 2 | 4 | 700 | 758 | 563 | 67.14% | 1 | 195 | 0 | 0 | 93 | -35 | 22407724 | 150000 | 22257724 | 24195428 | 26279346 | 0 | -10000 | -10000 | 26269346 | 25478372 | 114.5% | 0 | -2078 | 1787704 | 50 | 43 | 0 | 0 | -250600 | 0 | 0 | 0 | 189104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21834 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2026-02-10 | QTR3 | 25/26 |  | 2025-06-06 | QTR4 | 24/25 | 714 | 23830100
| 07 | T7509 | 44588615201 | 2023-02-22 | QTR3 | 22/23 | 1 | 3 | 225 | 324 | 324 | 112.9% | 1 | 0 | 0 | 0 | 99 | 0 | 8085082 | 90000 | 7995082 | 8115381 | 7967342 | 0 | 0 | 0 | 7967342 | 7885022 | 98.62% | 1 | -54392 | 30299 | 59 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 4879 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2024-11-21 | QTR2 | 24/25 | 799 | 9550800
| 07 | T7512 | 44334715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 3 | 210 | 477 | 477 | 112.9% | 1 | 0 | 0 | 0 | 230 | 37 | 6290573 | 50000 | 6240573 | 6754957 | 7072599 | 0 | 0 | 0 | 7072599 | 6755948 | 108.3% | 1 | -125 | 464384 | 209 | 31 | 0 | 20 | 65635 | 0 | 0 | 7 | 7306 | 0 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 157426 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 796 | 6135700
| 07 | T7514 | 45069315201 | 2023-09-27 | QTR1 | 23/24 | 1 | 2 | 150 | 311 | 311 | 100% | 1 | 0 | 0 | 0 | 161 | 0 | 2469300 | 50000 | 2419300 | 2490043 | 2487609 | 0 | 0 | 0 | 2487609 | 2486604 | 102.8% | 1 | -1005 | 20743 | 111 | 50 | 0 | 0 | 31460 | 0 | 0 | 0 | 8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39921 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-04-03 | QTR4 | 24/25 | 796 | 2285000
| 07 | T7515 | 44803615201 | 2023-06-14 | QTR4 | 22/23 | 2 | 10 | 300 | 571 | 566 | 117.7% | 1 | 5 | 0 | 0 | 271 | 0 | 13134873 | 115000 | 13019873 | 13851674 | 14146391 | 0 | 0 | 0 | 14146391 | 14074398 | 108.1% | 1 | -29541 | 716801 | 160 | 53 | 9 | 0 | 197732 | 0 | 0 | 0 | 430314 | 44320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 640481 | 44320 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-03-11 | QTR3 | 25/26 |  | 2025-07-22 | QTR1 | 25/26 | 799 | 13139100
| 07 | T7516 | 44006315201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 230 | 430 | 430 | 108.3% | 1 | 0 | 0 | 0 | 181 | 19 | 6730280 | 60000 | 6670280 | 6779810 | 6697913 | 0 | 0 | 0 | 6697913 | 6687877 | 100.3% | 1 | -10036 | 49529 | 152 | 29 | 0 | 0 | 9983 | 0 | 0 | 19 | 66053 | 39546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 19 | 76037 | 39546 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2024-12-04 | QTR2 | 24/25 | 798 | 7050800
| 07 | T7523 | 44697315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 196 | 316 | 315 | 99.49% | 1 | 1 | 0 | 0 | 120 | 0 | 2049777 | 50000 | 1999777 | 2049777 | 2101379 | 0 | 0 | 0 | 2101379 | 2098362 | 104.9% | 1 | -3017 | 0 | 95 | 25 | 0 | 0 | 2635 | 0 | 0 | 0 | 36652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39287 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 799 | 2385840
| 07 | T7529 | 44109835201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 200 | 262 | 262 | 100% | 1 | 0 | 0 | 0 | 62 | 0 | 1336107 | 50000 | 1286107 | 1336107 | 1267198 | 0 | 0 | 0 | 1267198 | 1266909 | 98.51% | 1 | -289 | 0 | 41 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-05-28 | QTR4 | 24/25 | 796 | 1581132
| 07 | T7538 | 44939815201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 100 | 122 | 122 | 115% | 1 | 0 | 0 | 0 | 22 | 0 | 545691 | 22198 | 523493 | 545691 | 518518 | 0 | 0 | 0 | 518518 | 518518 | 99.05% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-08 | QTR4 | 24/25 | 799 | 611133
| 07 | T7544 | 44025015201 | 2024-04-17 | QTR4 | 23/24 | 1 | 2 | 240 | 275 | 259 | 93.33% | 1 | 16 | 0 | 0 | 35 | 0 | 7475300 | 55000 | 7420300 | 7428809 | 7644411 | 0 | 0 | 0 | 7644411 | 7629621 | 102.8% | 1 | -14790 | -46492 | 13 | 22 | 0 | 0 | 569898 | 120795 | 0 | 0 | -594629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24731 | 120795 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2025-07-14 | QTR1 | 25/26 | 798 | 8386992
| 07 | T7548 | 44752215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 4 | 140 | 214 | 213 | 140% | 0 | 1 | 0 | 0 | 17 | 57 | 2173906 | 50000 | 2123906 | 2247825 | 2217265 | 0 | 0 | 0 | 2217265 | 2216464 | 104.4% | 1 | -801 | 73919 | 13 | 4 | 0 | 36 | 77735 | 0 | 0 | 21 | 8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15816 | 15816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 101654 | 15816 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2026-02-06 | QTR3 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 798 | 1912820
| 07 | T7550 | 45241215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 97 | 113 | 113 | 110.3% | 1 | 0 | 0 | 0 | 16 | 0 | 654321 | 27192 | 627129 | 654321 | 610593 | 0 | 0 | 0 | 610593 | 610593 | 97.36% | 1 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-05 | QTR2 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 796 | 826944
| 07 | T7555 | 44794815201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 205 | 224 | 157 | 67.32% | 1 | 67 | 0 | 0 | 19 | 0 | 5942087 | 79500 | 5862587 | 5942922 | 5968673 | 0 | 0 | 0 | 5968673 | 5968280 | 101.8% | 1 | -393 | 835 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-10-22 | QTR2 | 25/26 | 798 | 7672150
| 07 | T7573 | 45096915201 | 2025-03-26 | QTR3 | 24/25 | 1 | 2 | 65 | 88 | 87 | 98.46% | 1 | 1 | 0 | 0 | 23 | 0 | 365071 | 21000 | 344071 | 370411 | 359883 | 0 | 0 | 0 | 359883 | 354442 | 103% | 1 | -5442 | 5340 | 21 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6494 | 0 | F931411815 | LAKEVIEW CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-08-29 | QTR1 | 25/26 | 799 | 528390
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 17 | 25 | 75 | 5908 | 7743 | 7318 | 94.12% | 16 | 425 | 0 | 0 | 1733 | 102 | 234588365 | 1564162 | 233024203 | 247526356 | 250572236 | 0 | 865160 | 865160 | 251437396 | 249519272 | 88.24% | 15 | 1981146 | 12937989 | 1140 | 491 | 9 | 56 | 1727309 | 327852 | 15 | 68 | 3314484 | 622515 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 72 | 5047965 | 721885 | 10 | 0 | 911819 | 351786 | 0 | 0 | 0 | 0 | 51 | 0 | 343853 | 160277 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1334779 | 0 | 163 | 196 | 10092876 | 2184315
| 07 | E7N56 | 43726425201 | 2022-05-27 | QTR4 | 21/22 | 1 | 8 | 650 | 716 | 649 | 89.69% | 1 | 67 | 0 | 0 | 66 | 0 | 19975000 | 130000 | 19845000 | 20432970 | 21351585 | 0 | 0 | 0 | 21351585 | 21249872 | 107.1% | 1 | -59788 | 457970 | 29 | 37 | 0 | 0 | 362725 | 71071 | 0 | 0 | 34483 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125141 | 125141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586579 | 198586 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-01-20 | QTR3 | 25/26 |  | 2024-06-21 | QTR4 | 23/24 | 798 | 15858300
| 07 | E7P77 | 44146315201 | 2023-05-10 | QTR4 | 22/23 | 1 | 2 | 150 | 247 | 247 | 118% | 1 | 0 | 0 | 0 | 70 | 27 | 3366760 | 50000 | 3316760 | 3493112 | 3363518 | 0 | 300000 | 300000 | 3663518 | 3363518 | 101.4% | 1 | -300000 | 126352 | 45 | 25 | 0 | 22 | 20037 | 0 | 0 | 5 | 4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 135426 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-07-30 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 796 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | E7Q08 | 44761515201 | 2023-05-10 | QTR4 | 22/23 | 2 | 7 | 330 | 477 | 477 | 118.8% | 1 | 0 | 0 | 0 | 147 | 0 | 6147921 | 52728 | 6095192 | 6373747 | 6357061 | 0 | 0 | 0 | 6357061 | 6311539 | 103.5% | 1 | -1706 | 225826 | 61 | 24 | 0 | 0 | -18522 | 0 | 0 | 0 | 84658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84397 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 42409 | 34565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 192942 | 34565 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2026-01-20 | QTR3 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 714 | 5831100
| 07 | E7Q31 | 44384115201 | 2023-12-13 | QTR2 | 23/24 | 1 | 3 | 125 | 238 | 240 | 101.6% | 1 | -2 | 2 | 0 | 113 | 0 | 1681476 | 50000 | 1631476 | 1805476 | 1410753 | -3398 | 0 | -3398 | 1407355 | 1374355 | 84.24% | 1 | 0 | 124000 | 98 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2024-12-10 | QTR2 | 24/25 | 796 | 1673100
| 07 | E7Q39 | 44582815201 | 2024-02-14 | QTR3 | 23/24 | 2 | 0 | 284 | 330 | 326 | 98.59% | 1 | 4 | 0 | 0 | 46 | 0 | 1714027 | 50000 | 1664027 | 1714027 | 1704720 | 0 | 0 | 0 | 1704720 | 1704720 | 102.4% | 1 | 0 | 0 | 20 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-08-26 | QTR1 | 25/26 | 796 | 3483914
| 07 | E7Q53 | 44583015201 | 2024-05-08 | QTR4 | 23/24 | 1 | 2 | 230 | 260 | 210 | 78.26% | 1 | 50 | 0 | 0 | 30 | 0 | 1599000 | 50000 | 1549000 | 1601196 | 1343560 | 0 | 0 | 0 | 1343560 | 1341365 | 86.6% | 1 | 0 | 2196 | 17 | 13 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-07-08 | QTR1 | 25/26 |  | 2025-04-13 | QTR4 | 24/25 | 799 | 1936163
| 07 | E7Q55 | 44165115201 | 2024-03-13 | QTR3 | 23/24 | 1 | 3 | 150 | 272 | 272 | 119.3% | 1 | 0 | 0 | 0 | 93 | 29 | 4066019 | 50000 | 4016019 | 4201769 | 4164473 | 0 | 0 | 0 | 4164473 | 4071753 | 101.4% | 1 | -92719 | 135750 | 67 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 95050 | 87989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 6641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 29 | 149452 | 87989 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-06-01 | QTR4 | 24/25 | 799 | 4234476
| 07 | E7Q75 | 45288915201 | 2024-06-12 | QTR4 | 23/24 | 1 | 2 | 80 | 151 | 151 | 100% | 1 | 0 | 0 | 0 | 71 | 0 | 1296714 | 50000 | 1246714 | 1381899 | 1384246 | 0 | 0 | 0 | 1384246 | 1371017 | 110% | 1 | 0 | 85185 | 50 | 21 | 0 | 0 | 71957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71957 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-01-27 | QTR3 | 24/25 | 798 | 1695805
| 07 | E7Q94 | 45273615201 | 2024-12-11 | QTR2 | 24/25 | 1 | 0 | 30 | 33 | 29 | 86.67% | 1 | 4 | 0 | 0 | 3 | 0 | 259111 | 23000 | 236111 | 259111 | 235124 | 0 | 0 | 0 | 235124 | 235124 | 99.58% | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 |  | 2025-07-14 | QTR1 | 25/26 | 799 | 516283
| 07 | E7R15 | 44138815201 | 2021-01-29 | QTR3 | 20/21 | 4 | 2 | 450 | 724 | 724 | 100% | 1 | 0 | 0 | 0 | 274 | 0 | 21358193 | 150000 | 21208193 | 21288752 | 21103200 | 0 | 1150000 | 1150000 | 22253200 | 21628021 | 102% | 1 | -335192 | -69440 | 226 | 48 | 0 | 0 | 12752 | 0 | 0 | 0 | 107114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69440 | 0 | 185 | 0 | 50426 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-12-11 | QTR2 | 25/26 |  | 2023-07-28 | QTR1 | 23/24 | 796 | 26431774 | A3:A3:A3:B10 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
| 07 | E7R21 | 42451335201 | 2021-05-20 | QTR4 | 20/21 | 3 | 16 | 1115 | 1616 | 1308 | 100.8% | 1 | 308 | 0 | 0 | 184 | 317 | 81649200 | 150000 | 81499200 | 89787672 | 90056090 | 0 | 0 | 0 | 90056090 | 89818079 | 110.2% | 0 | 1620860 | 8138472 | 120 | 64 | 0 | 228 | 2666076 | 316345 | 0 | 0 | 1680130 | 35860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316666 | 208207 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 0 | -117901 | 0 | 0 | 373 | 4996124 | 1011566 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-08 | QTR3 | 24/25 | 714 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7R24 | 44132015201 | 2022-08-04 | QTR1 | 22/23 | 1 | 1 | 580 | 797 | 779 | 96.9% | 1 | 18 | 0 | 0 | 217 | 0 | 6997500 | 69934 | 6927567 | 7112720 | 7042786 | 0 | 0 | 0 | 7042786 | 7042581 | 101.7% | 1 | -205 | 115220 | 163 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2025-03-28 | QTR3 | 24/25 | 798 | 13119000
| 07 | E7R26 | 42925115201 | 2021-06-17 | QTR4 | 20/21 | 5 | 22 | 1100 | 1415 | 1414 | 112.5% | 1 | 1 | 0 | 0 | 176 | 139 | 89691574 | 162717 | 89528857 | 96531643 | 96716929 | -45000 | 0 | -45000 | 96671929 | 96896327 | 108.2% | 1 | 1490307 | 6840069 | 90 | 86 | 0 | 119 | 5277897 | 81590 | 0 | 20 | 1067716 | 347957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49676 | 0 | 0 | 0 | 8310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 6553399 | 429547 | F871503473 | PRINCE-AJAX DDI JV | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 |  | 2025-07-02 | QTR1 | 25/26 | 714 | 100030998 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7R35 | 43983215201 | 2023-05-25 | QTR4 | 22/23 | 3 | 4 | 580 | 697 | 697 | 100% | 1 | 0 | 0 | 0 | 117 | 0 | 10158800 | 110000 | 10048800 | 10244736 | 10281972 | 0 | 0 | 0 | 10281972 | 10243690 | 101.9% | 1 | -3637 | 85936 | 86 | 31 | 0 | 0 | 51291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51291 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-01-22 | QTR3 | 25/26 |  | 2025-06-23 | QTR4 | 24/25 | 798 | 12981331 | LBDB:LBDB | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
| 07 | E7R40 | 44335825201 | 2024-03-07 | QTR3 | 23/24 | 1 | 2 | 200 | 285 | 274 | 94.5% | 1 | 11 | 0 | 0 | 85 | 0 | 1322000 | 50000 | 1272000 | 1334250 | 1257998 | 0 | 0 | 0 | 1257998 | 1250561 | 98.31% | 1 | -4137 | 12250 | 46 | 39 | 0 | 0 | 4515 | 0 | 0 | 0 | 4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2025-02-03 | QTR3 | 24/25 | 798 | 1543770 | LBDB | LOW BID DESIGN BUILD
| 07 | E7U08 | 44366515201 | 2024-09-11 | QTR1 | 24/25 | 1 | 1 | 200 | 251 | 251 | 109% | 1 | 0 | 0 | 0 | 33 | 18 | 3709156 | 50000 | 3659156 | 3709156 | 3454248 | 0 | 0 | 0 | 3454248 | 3454248 | 94.4% | 1 | 0 | 0 | 19 | 14 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2025-12-10 | QTR2 | 25/26 | 796 | 3944855
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 16 | 29 | 75 | 6254 | 8509 | 8048 | 100% | 16 | 461 | 2 | 0 | 1725 | 530 | 254992451 | 1248379 | 253744072 | 271272236 | 271228263 | -48398 | 1450000 | 1401602 | 272629865 | 271356770 | 93.75% | 15 | 2313783 | 16279786 | 1138 | 525 | 0 | 369 | 8449244 | 469006 | 0 | 43 | 3284315 | 474181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292713 | 0 | 4 | 0 | 8310 | 0 | 0 | 0 | 0 | 0 | 204 | 0 | 530696 | 208207 | 0 | 0 | 0 | 0 | 58 | 174 | 625345 | 610860 | 0 | 0 | 0 | 0 | 0 | 0 | -187341 | 0 | 266 | 586 | 13003282 | 1762253
| District 07 Totals |  |  |  |  | 33 | 54 | 150 | 12162 | 16252 | 15366 | 96.97% | 32 | 886 | 2 | 0 | 3458 | 632 | 489580816 | 2812541 | 486768275 | 518798592 | 521800499 | -48398 | 2315160 | 2266762 | 524067261 | 520876042 | 90.91% | 30 | 4294929 | 29217775 | 2278 | 1016 | 9 | 425 | 10176553 | 796858 | 15 | 111 | 6598799 | 1096696 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 72 | 5340678 | 721885 | 14 | 0 | 920129 | 351786 | 0 | 0 | 0 | 0 | 255 | 0 | 874549 | 368484 | 0 | 0 | 0 | 0 | 107 | 174 | 625345 | 610860 | 0 | 0 | 0 | 0 | 0 | 0 | -1522120 | 0 | 429 | 782 | 23096158 | 3946568
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8R45 | 43799215201 | 2018-11-15 | QTR2 | 18/19 | 3 | 22 | 928 | 1578 | 1578 | 115.6% | 1 | 0 | 0 | 0 | 505 | 145 | 33928239 | 150000 | 33778239 | 47651600 | 47943952 | 0 | 0 | 0 | 47943952 | 47859737 | 141.7% | 0 | -39220 | 13723361 | 337 | 168 | 0 | 4 | 678065 | 0 | 0 | 0 | 444720 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 11027592 | 0 | 0 | 0 | 1427834 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 145 | 13655217 | 0 | F825435435 | CENTRAL MORRISON COBALT JV | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2023-10-20 | QTR2 | 23/24 | 854 | 41184698.49
| 08 | E8T48 | 43496835201 | 2022-04-19 | QTR4 | 21/22 | 1 | 2 | 1128 | 1286 | 1283 | 102.7% | 1 | 3 | 0 | 0 | 125 | 33 | 10781928 | 108430 | 10673498 | 10718856 | 10512572 | 0 | 0 | 0 | 10512572 | 10512572 | 98.49% | 1 | 0 | -63072 | 40 | 85 | 0 | 33 | -9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28279 | 0 | 0 | 0 | 8634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 27804 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 |  | 2025-12-18 | QTR2 | 25/26 | 854 | 11904888.56 | A3 | ICC - DESIGN/BUILD - MINOR
| 08 | E8T83 | 44276415201 | 2022-09-20 | QTR1 | 22/23 | 1 | 4 | 1277 | 1339 | 892 | 59.83% | 1 | 447 | 0 | 0 | 128 | -66 | 102999958 | 150000 | 102849958 | 103423210 | 104129622 | 0 | 4744548 | 4744548 | 108874170 | 102351127 | 99.51% | 1 | -6249791 | 423252 | 65 | 63 | 0 | 0 | 108966 | 0 | 0 | 0 | 78741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37076 | 0 | 0 | 0 | 2530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66 | 0 | 0 | 0 | -66 | 227314 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-03-27 | QTR3 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 854 | 121233962.23 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8U04 | 44602415201 | 2023-03-21 | QTR3 | 22/23 | 3 | 8 | 386 | 505 | 502 | 104.4% | 1 | 3 | 0 | 0 | 99 | 20 | 16184460 | 150000 | 16034460 | 17190583 | 16458548 | 0 | 0 | 0 | 16458548 | 16378636 | 102.1% | 1 | -46667 | 1006123 | 45 | 54 | 0 | 0 | 188590 | 0 | 0 | 0 | 366919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 463107 | 0 | 0 | 0 | 50339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1068954 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 854 | 18390076.74
| 08 | E8U19 | 44588515201 | 2023-04-11 | QTR4 | 22/23 | 2 | 1 | 314 | 523 | 523 | 109.6% | 1 | 0 | 0 | 0 | 179 | 30 | 11226810 | 114237 | 11112574 | 11263007 | 11344464 | 0 | 0 | 0 | 11344464 | 11303165 | 101.7% | 1 | -5101 | 36197 | 122 | 57 | 0 | 0 | 0 | 0 | 0 | 14 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 53038 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-28 | QTR1 | 25/26 |  | 2025-04-11 | QTR4 | 24/25 | 854 | 11461890.59
| 08 | E8U32 | 44925335201 | 2023-05-09 | QTR4 | 22/23 | 2 | 1 | 401 | 505 | 499 | 109.7% | 1 | 6 | 0 | 0 | 104 | 0 | 3649071 | 50000 | 3599071 | 3673424 | 3464348 | 0 | 0 | 0 | 3464348 | 3464348 | 96.26% | 1 | 0 | 24353 | 27 | 32 | 0 | 0 | 7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 11812 | 0 | 0 | 0 | 24353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 43886 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 854 | 4370418.34
| 08 | E8U46 | 43854815201 | 2024-05-14 | QTR4 | 23/24 | 1 | 0 | 497 | 543 | 254 | 41.85% | 1 | 289 | 0 | 0 | 46 | 0 | 4734726 | 79759 | 4654966 | 4734726 | 4628034 | 0 | 0 | 0 | 4628034 | 4628034 | 99.42% | 1 | 0 | 0 | 13 | 33 | 0 | 0 | 14990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 854 | 8236620.28
| 08 | E8U56 | 44942325201 | 2023-08-22 | QTR1 | 23/24 | 1 | 2 | 240 | 275 | 242 | 81.25% | 1 | 33 | 0 | 0 | 47 | -12 | 1804313 | 50000 | 1754313 | 1864511 | 1827419 | 0 | 37398 | 37398 | 1864817 | 1827419 | 104.2% | 1 | -37398 | 60198 | 24 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-24 | QTR3 | 24/25 | 854 | 1786238.37 | A6 | ICC - BAM/INCENTIVE-DISINCENT
| 08 | E8U67 | 44440215201 | 2023-09-12 | QTR1 | 23/24 | 4 | 7 | 580 | 715 | 656 | 91.21% | 1 | 59 | 0 | 0 | 127 | 8 | 24889345 | 150000 | 24739345 | 25770345 | 25416917 | 0 | 0 | 0 | 25416917 | 25256822 | 102.1% | 1 | -129095 | 881000 | 76 | 51 | 0 | 0 | 57314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 471317 | 0 | 0 | 0 | 439504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 968135 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-16 | QTR3 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 854 | 27205817.87
| 08 | E8U71 | 41592755201 | 2024-02-13 | QTR3 | 23/24 | 1 | 1 | 181 | 339 | 326 | 106.6% | 1 | 13 | 0 | 0 | 133 | 25 | 2794276 | 60345 | 2733930 | 2537251 | 2444066 | 0 | 0 | 0 | 2444066 | 2444066 | 89.4% | 1 | 0 | -257025 | 84 | 49 | 0 | 25 | 59995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -257025 | 0 | 0 | 25 | -197030 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-10-13 | QTR2 | 25/26 |  | 2025-09-17 | QTR1 | 25/26 | 854 | 6003501.55
| 08 | E8U73 | 44206215201 | 2024-03-12 | QTR3 | 23/24 | 2 | 5 | 280 | 321 | 315 | 97.86% | 1 | 6 | 0 | 0 | 41 | 0 | 13684469 | 150000 | 13534469 | 13793245 | 13317036 | 0 | 0 | 0 | 13317036 | 13288255 | 98.18% | 1 | -24020 | 108776 | 20 | 21 | 0 | 0 | 15607 | 0 | 0 | 0 | 43669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36331 | 0 | 0 | 0 | 131202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226808 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-07-18 | QTR1 | 25/26 | 854 | 19932483.01
| 08 | E8U91 | 44917545201 | 2024-06-11 | QTR4 | 23/24 | 1 | 4 | 242 | 308 | 302 | 97.52% | 1 | 6 | 0 | 0 | 66 | 0 | 4804962 | 50000 | 4754962 | 4908714 | 4813444 | 0 | 0 | 0 | 4813444 | 4807156 | 101.1% | 1 | -521 | 103751 | 36 | 30 | 0 | 0 | 46708 | 0 | 0 | 0 | 21070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791 | 0 | 0 | 0 | 55206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123774 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-07-21 | QTR1 | 25/26 | 854 | 4334607.7
| 08 | E8U95 | 44917535201 | 2024-04-09 | QTR4 | 23/24 | 1 | 0 | 140 | 176 | 173 | 97.86% | 1 | 3 | 0 | 0 | 36 | 0 | 1605678 | 50000 | 1555678 | 1605678 | 1663792 | 0 | 0 | 0 | 1663792 | 1663792 | 106.9% | 1 | 0 | 0 | 18 | 18 | 0 | 0 | 23069 | 0 | 0 | 0 | 5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49911 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 854 | 1739459.6
| 08 | E8V77 | 45211115201 | 2025-02-19 | QTR3 | 24/25 | 1 | 0 | 200 | 207 | 108 | 50.5% | 1 | 99 | 0 | 0 | 7 | 0 | 1699787 | 50000 | 1649787 | 1699787 | 1444210 | 0 | 0 | 0 | 1444210 | 1444159 | 87.54% | 1 | -52 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 854 | 1780237.34
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 14 | 24 | 57 | 6794 | 8620 | 7653 | #VALUE! | 14 | 967 | 0 | 0 | 1643 | 183 | 234788022 | 1362771 | 233425250 | 250834937 | 249408424 | 0 | 4781946 | 4781946 | 254190370 | 247229288 | 92.86% | 13 | -6531865 | 16046914 | 910 | 688 | 0 | 62 | 1191916 | 0 | 0 | 14 | 1082262 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 184 | 12133117 | 0 | 0 | 0 | 2140173 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66 | -257025 | 0 | 137 | 195 | 16367446 | 0
| District 08 Totals |  |  |  |  | 14 | 24 | 57 | 6794 | 8620 | 7653 | 100% | 14 | 967 | 0 | 0 | 1643 | 183 | 234788022 | 1362771 | 233425250 | 250834937 | 249408424 | 0 | 4781946 | 4781946 | 254190370 | 247229288 | 92.86% | 13 | -6531865 | 16046914 | 910 | 688 | 0 | 62 | 1191916 | 0 | 0 | 14 | 1082262 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 184 | 12133117 | 0 | 0 | 0 | 2140173 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66 | -257025 | 0 | 137 | 195 | 16367446 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 169 | 365 | 566 | 55571 | 85881 | 83238 | 77.51% | 131 | 2643 | 326 | 0 | 23688 | 6540 | 1548065050 | 13201965 | 1534863083 | 1638738499 | 1656700096 | -1372805 | 3972660 | 2599855 | 1659299951 | 1658175161 | 90.53% | 153 | 9870769 | 91763906 | 14345 | 7621 | 707 | 2152 | 15830572 | 1174973 | 957 | 2167 | 50828357 | 11732231 | 0 | 10 | 132416 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 5750 | 0 | 326 | 1033 | 17014141 | 4052014 | 253 | 154 | 1797753 | 423323 | 0 | 0 | 0 | 0 | 1184 | 526 | 1872789 | 163455 | 0 | 286 | 2254885 | 620012 | 122 | 406 | 2305189 | 1394067 | 117 | 148 | 0 | 0 | 0 | 0 | -2895005 | 0 | 3666 | 6882 | 89001418 | 19560074
| Statewide District Let Contracts SubTotal |  |  |  |  | 133 | 228 | 442 | 46654 | 67576 | 64827 | 86.47% | 115 | 2749 | 230 | 0 | 17395 | 3560 | 1750826020 | 9487389 | 1741338629 | 1852202104 | 1850349553 | -940414 | 10894446 | 9954032 | 1860303584 | 1841525925 | 95.49% | 127 | 10361616 | 101333953 | 9038 | 6051 | 428 | 668 | 17495922 | 1904975 | 651 | 866 | 16704805 | 657587 | 0 | 0 | 10318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1137 | 1213 | 50470120 | 3646639 | 19 | 24 | 5720255 | 75752 | 0 | 0 | 0 | 0 | 986 | 453 | 2061821 | 208207 | 0 | 249 | 7623579 | 7300000 | 224 | 214 | 758485 | 723474 | 26 | 0 | 0 | 0 | 0 | -66 | -2580868 | 0 | 3471 | 3621 | 98264428 | 14516632
| Statewide Totals |  |  |  |  | 302 | 593 | 1008 | 102225 | 153457 | 148065 | 81.46% | 246 | 5392 | 556 | 0 | 41083 | 10100 | 3298891070 | 22689354 | 3276201712 | 3490940603 | 3507049649 | -2313219 | 14867106 | 12553887 | 3519603535 | 3499701086 | 92.72% | 280 | 20232385 | 193097859 | 23383 | 13672 | 1135 | 2820 | 33326494 | 3079948 | 1608 | 3033 | 67533162 | 12389818 | 0 | 10 | 142734 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 5750 | 0 | 1463 | 2246 | 67484261 | 7698653 | 272 | 178 | 7518008 | 499075 | 0 | 0 | 0 | 0 | 2170 | 979 | 3934610 | 371662 | 0 | 535 | 9878464 | 7920012 | 346 | 620 | 3063674 | 2117541 | 143 | 148 | 0 | 0 | 0 | -66 | -5475873 | 0 | 7137 | 10503 | 187265846 | 34076706

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1R76 | 20121535201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2020-05-29 | 70460520 | 71635236 | 73663828 | 1174716.35 | -100000 | 77151838 | 0 | 0 | 0 | 0 | 0 | -100000 | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 73563828 | 77151838 | 3588010 | 57230748 | Y | DESIGN/BUILD PROJECT
1 | E1R87 | 20103255201 | F843374080 | AJAX-LEWARE JV | N/A | N/A | N/A | N/A | 2020-11-20 | 143923300 | 144607218 | 155372227 | 683918.32 | -40000 | 157627376 | 0 | 0 | 0 | 0 | 0 | -40000 | -40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40000 | 155332227 | 157627376 | 2295149 | 132713200 | B11:B7:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - A+B/BONUS:ACC - DESIGN/BUILD - MAJOR
1 | E1V08 | 19602265201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-11-02 | 6226258 | 6296806 | 6274547 | 70547.94 | 0 | 6264042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6274547 | 6264042 | -10506 | 7418504
1 | E1V09 | 44743215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-02-15 | 3665572 | 3665572 | 3704260 | 0 | 0 | 3693129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3704260 | 3693129 | -11132 | 4198566
1 | E1V10 | 44155015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-02-16 | 14609258 | 14044029 | 14088333 | -565228.69 | -3245 | 13959008 | -3245 | 0 | 0 | 0 | 0 | 0 | -3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3245 | 14085087 | 13959008 | -126080 | 14926350
1 | E1V13 | 44893915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-09-19 | 5289078 | 5392842 | 5545592 | 103763.45 | 0 | 5545735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5545592 | 5545735 | 143 | 5760652
1 | E1V22 | 44620615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-20 | 5142423 | 5047658 | 5138834 | -94764.75 | 0 | 5137805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5138834 | 5137805 | -1029 | 4496918
1 | E1V23 | 44743415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-07-20 | 5558710 | 5552034 | 5723019 | -6675.84 | 0 | 5741811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5723019 | 5741811 | 18793 | 5765208
1 | E1V51 | 44743715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-02 | 23141400 | 23931467 | 24545579 | 790066.61 | 0 | 24064967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24545579 | 24064967 | -480611 | 26691037 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1V60 | 44901515201 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 24655000 | 24840707 | 24676932 | 185707.07 | 941500 | 24668159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | -8500 | 941500 | 941500 | 25618432 | 24668159 | -950274 | 27242570 | B2:B5:Y | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:DESIGN/BUILD PROJECT
1 | E1W13 | 44594215201 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2024-02-15 | 2428636 | 2626766 | 2708707 | 198129.96 | -66250 | 2642436 | -66250 | 0 | 0 | 0 | 0 | 0 | -66250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66250 | 2642457 | 2642436 | -22 | 3681296
1 | E1W16 | 44738015201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-09-21 | 2844972 | 2870813 | 2826404 | 25840.92 | 0 | 2818713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2826404 | 2818713 | -7691 | 2548368
1 | E1W18 | 44743115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-04-18 | 2506911 | 2530764 | 2550717 | 23853.05 | 0 | 2546483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550717 | 2546483 | -4233 | 2727223
1 | E1W50 | 45279215201 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-26 | 2283584 | 2283584 | 2253806 | 0 | 0 | 2253543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2253806 | 2253543 | -264 | 2780605 | Y | DESIGN/BUILD PROJECT
1 | E1W75 | 44923315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-18 | 2560003 | 2560003 | 2586788 | 0 | 0 | 2586788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586788 | 2586788 | 0 | 3481659
1 | E1W76 | 44897215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-15 | 3352588 | 3352588 | 3378389 | 0 | 0 | 3377632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3378389 | 3377632 | -757 | 4285958
1 | E1W78 | 44927215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-15 | 1562427 | 1562023 | 1597413 | -403.64 | 0 | 1597413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1597413 | 1597413 | 0 | 1884402
1 | E1W79 | 44023015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-09-19 | 1118465 | 1118465 | 854089 | 0 | 0 | 854089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854089 | 854089 | -1 | 991704
1 | E1W85 | 44893115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-11-07 | 4458291 | 4710660 | 4720609 | 252368.4 | 0 | 4733331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4720609 | 4733331 | 12722 | 5001199
1 | E1W94 | 44917815201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-02-20 | 830702 | 830702 | 826937 | 0 | -15165 | 811772 | -15165 | 0 | 0 | 0 | 0 | 0 | -15165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15165 | 811772 | 811772 | 0 | 1048586
1 | E1X68 | 44895715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-17 | 2063849 | 2063849 | 1971937 | 0 | 0 | 1971937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1971937 | 1971937 | 0 | 2136352
1 | T1754 | 41924345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-06-10 | 44711727 | 45332170 | 46495372 | 620442.65 | 0 | 47278762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46495372 | 47278762 | 783390 | 49671696
1 | T1801 | 43355055201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2022-02-23 | 9943982 | 10795145 | 10516274 | 851163.08 | 0 | 10539225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10516274 | 10539225 | 22951 | 8613987
1 | T1807 | 44464115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 5486544 | 5582663 | 5697293 | 96119.73 | -30000 | 5667081 | 0 | 0 | 0 | 0 | 0 | -30000 | -30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | 5667293 | 5667081 | -212 | 4275732
1 | T1833 | 44634515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 16756829 | 16756829 | 16918647 | 0 | -70500 | 16748453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -70500 | -70500 | -70500 | 16848147 | 16748453 | -99694 | 17387335
1 | T1843 | 43695525201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-07-27 | 4165582 | 4197230 | 4319692 | 31647.71 | 0 | 4262739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4319692 | 4262739 | -56953 | 3563245
1 | T1850 | 43944115201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-04-24 | 5279314 | 5778359 | 5716286 | 499045.08 | 0 | 5713996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5716286 | 5713996 | -2290 | 7929522
1 | T1852 | 44787215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-02-28 | 3084175 | 3084175 | 3074445 | 0 | 0 | 3073651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3074445 | 3073651 | -795 | 2364266
1 | T1854 | 44480735201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-03-27 | 1273662 | 1300460 | 1232804 | 26798.65 | -22000 | 1210162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22000 | -22000 | -22000 | 1210804 | 1210162 | -642 | 1109605
1 | T1855 | 44547315201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 11238774 | 11323365 | 11568463 | 84591.09 | -143070 | 11393079 | -143070 | 0 | 0 | 0 | 0 | 0 | -143070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -143070 | 11425393 | 11393079 | -32314 | 12534705
1 | T1866 | 43903215201 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2023-11-15 | 3945642 | 4078353 | 4013289 | 132711.4 | -76850 | 3923705 | -76850 | 0 | 0 | 0 | 0 | 0 | -76850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76850 | 3936439 | 3923705 | -12734 | 5005578
1 | T1867 | 44546715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 7502026 | 8082796 | 8181304 | 580769.85 | 0 | 8176865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8181304 | 8176865 | -4440 | 7936833
1 | T1868 | 44740215201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-02-28 | 1036497 | 1074999 | 1074468 | 38501.79 | 0 | 1074468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074468 | 1074468 | 0 | 1164569
1 | T1873 | 44788015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-02-28 | 2902791 | 2941983 | 2705963 | 39192 | 0 | 2704866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2705963 | 2704866 | -1098 | 2895927
1 | T1881 | 43802715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-11-15 | 6196035 | 6206737 | 6556044 | 10701.34 | 0 | 6524950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6556044 | 6524950 | -31093 | 6886951
1 | T1889 | 44431315201 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-03-27 | 2636284 | 2666046 | 2714680 | 29762.4 | -3800 | 2705941 | 0 | 0 | 0 | 0 | 0 | -3800 | -3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3800 | 2710880 | 2705941 | -4939 | 3253357
1 | T1891 | 44743625201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 4742624 | 4787027 | 4779994 | 44403.46 | 0 | 4777172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4779994 | 4777172 | -2822 | 4605370
1 | T1895 | 44656015201 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2024-09-25 | 1414901 | 1450512 | 1460078 | 35610.63 | 0 | 1460017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460078 | 1460017 | -61 | 1992638
1 | T1905 | 44645215201 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2025-01-29 | 574929 | 574929 | 554144 | 0 | 0 | 555650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554144 | 555650 | 1507 | 670642
1 | T1927 | 44477325201 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2025-07-30 | 414963 | 414963 | 422033 | 0 | 0 | 422033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422033 | 422033 | 0 | 496785
2 | E200W | 44572615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-04-17 | 2930266 | 2930266 | 2970891 | 0 | 0 | 2968577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970891 | 2968577 | -2313 | 2593407
2 | E20S2 | 21054545201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-01 | 8601469 | 8601469 | 8734394 | 0 | 0 | 8453915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8734394 | 8453915 | -280479 | 8397276 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E20T6 | 44278015201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2023-02-15 | 1676236 | 1744958 | 1814629 | 68721.9 | 0 | 1814629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1814629 | 1814629 | 0 | 2494428
2 | E20X8 | 20840265201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-23 | 9409691 | 9409691 | 9709502 | 0 | 0 | 9670685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9709502 | 9670685 | -38817 | 8868810 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E20X9 | 44707615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-23 | 11213775 | 11213775 | 11321495 | 0 | 0 | 11257290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11321495 | 11257290 | -64205 | 11190658 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E2Z53 | 43035245201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2020-02-20 | 17677113 | 32771107 | 33306856 | 15093994.45 | 0 | 33713424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33306856 | 33713424 | 406568 | 14339167
2 | T2591 | 42886515201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2015-10-14 | 65973116 | 108070596 | 111765107 | 42097480.47 | 0 | 113168629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111765107 | 113168629 | 1403522 | 76779378
2 | T2757 | 43761115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 8709827 | 8796925 | 9281776 | 87098.27 | 0 | 9514074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9281776 | 9514074 | 232299 | 10240285
2 | T2790 | 43616815201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2021-01-27 | 15444874 | 18490817 | 18667723 | 3045942.89 | 0 | 18710310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18667723 | 18710310 | 42587 | 11733777
2 | T2839 | 44342115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-09 | 31969186 | 31969186 | 32489212 | 0 | 0 | 33982240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32489212 | 33982240 | 1493028 | 35449756
2 | T2844 | 43935615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 19892956 | 20310363 | 20717832 | 417407.11 | 0 | 20372452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20717832 | 20372452 | -345380 | 16227519
2 | T2854 | 44554515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-08 | 10095026 | 10267526 | 10526210 | 172500 | 0 | 10199858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10526210 | 10199858 | -326352 | 10655889
2 | T2863 | 43744115201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-01-12 | 14032373 | 15901285 | 16261074 | 1868911.96 | 0 | 16285649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16261074 | 16285649 | 24575 | 15021661
2 | T2865 | 44351715201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-11-16 | 7663000 | 8470199 | 9163770 | 807198.83 | 0 | 9151881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9163770 | 9151881 | -11890 | 7014633
2 | T2889 | 43575615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 3832776 | 4315395 | 4383212 | 482619.04 | 0 | 4383212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4383212 | 4383212 | 0 | 4521037
2 | T2890 | 44554715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 25595410 | 25761158 | 26450421 | 165747.22 | 0 | 25953030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26450421 | 25953030 | -497390 | 25708228
2 | T2894 | 44540215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 12471547 | 12747539 | 13553931 | 275991.77 | 0 | 13363147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13553931 | 13363147 | -190784 | 11980864
2 | T2910 | 44535215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 5895675 | 5981679 | 6100547 | 86003.71 | 0 | 6097264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100547 | 6097264 | -3283 | 6680440
2 | T2913 | 44707815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 4420617 | 4518180 | 4416217 | 97563.2 | 0 | 4412247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4416217 | 4412247 | -3971 | 4807508
2 | T2915 | 44718015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 11703806 | 11742594 | 12389230 | 38788.29 | 0 | 12394517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12389230 | 12394517 | 5287 | 10416036
2 | T2916 | 43993715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 10398707 | 10398707 | 10268067 | 0 | 0 | 10264664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10268067 | 10264664 | -3403 | 8834994
2 | T2917 | 44330415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-05-17 | 23947969 | 24055659 | 25032603 | 107690.09 | 0 | 25026994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25032603 | 25026994 | -5609 | 21934860
2 | T2924 | 20930185201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-04-26 | 19358596 | 19523393 | 20332171 | 164797.23 | 0 | 20313549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20332171 | 20313549 | -18621 | 19142187
2 | T2934 | 44331015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-12-07 | 26057502 | 26443445 | 27980036 | 385943.3 | 0 | 27874372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27980036 | 27874372 | -105664 | 24163400
2 | T2945 | 44542715201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 6853255 | 6853255 | 6989283 | 0 | 0 | 6981891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6989283 | 6981891 | -7392 | 7614578
2 | T2948 | 44712315201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 5794236 | 5794236 | 5977965 | 0 | 0 | 5958952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5977965 | 5958952 | -19013 | 5749685
2 | T2949 | 20969745201 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2023-11-15 | 1865813 | 1939049 | 1961474 | 73235.26 | 0 | 1960364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961474 | 1960364 | -1110 | 2230664
2 | T2954 | 44542015201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 3819110 | 3819110 | 3735111 | 0 | 0 | 3733457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3735111 | 3733457 | -1654 | 5040192
2 | T2961 | 43633015201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 3521000 | 3558326 | 3560864 | 37326.4 | 0 | 3626016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3560864 | 3626016 | 65152 | 3765541
2 | T2962 | 44796215201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 7958218 | 7958218 | 7882304 | 0 | 0 | 7877534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7882304 | 7877534 | -4770 | 8827614
2 | T2966 | 21086555201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 2921783 | 2921783 | 2938946 | 0 | 0 | 2938946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938946 | 2938946 | 0 | 3224885
2 | T2969 | 44703615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 10923210 | 10892472 | 11424138 | -30738.04 | 0 | 11378255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11424138 | 11378255 | -45883 | 10802904
2 | T2970 | 44712815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 6497196 | 6705393 | 7314719 | 208197.25 | 0 | 7294065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314719 | 7294065 | -20654 | 6729212
2 | T2974 | 44720415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-27 | 18339896 | 18339896 | 18394467 | 0 | 0 | 18347088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18394467 | 18347088 | -47379 | 19102224
2 | T2976 | 44755715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 25893810 | 26291007 | 27924429 | 397197.72 | 0 | 27880284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27924429 | 27880284 | -44146 | 21206563
2 | T2981 | 45220125201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 2914229 | 2914229 | 2917184 | 0 | 0 | 2917184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2917184 | 2917184 | 0 | 4244876
2 | T2985 | 43761415201 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-11-15 | 7308506 | 7308506 | 7304574 | 0 | 0 | 7285470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7304574 | 7285470 | -19104 | 8026688
2 | T2988 | 44721135201 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2024-04-24 | 1562105 | 1737694 | 1710662 | 175588.73 | 0 | 1710435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1710662 | 1710435 | -227 | 1572772
2 | T2997 | 44984425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 2499454 | 2573884 | 2437559 | 74429.6 | 0 | 2436488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2437559 | 2436488 | -1071 | 2231403
2 | T2A02 | 43431825201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-11-13 | 7419960 | 7419960 | 7285721 | 0 | 0 | 7282630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7285721 | 7282630 | -3091 | 8775588
2 | T2A05 | 20944145201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2025-02-26 | 2487602 | 2535510 | 2431426 | 47908.5 | 0 | 2431081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2431426 | 2431081 | -345 | 3542854
2 | T2A06 | 21003025201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-11-13 | 6571980 | 6571980 | 6862070 | 0 | 0 | 6863371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6862070 | 6863371 | 1301 | 6362365
2 | T2A09 | 21022385201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-12-04 | 4685902 | 4685902 | 4940814 | 0 | 0 | 4942704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4940814 | 4942704 | 1890 | 5665702
2 | T2A12 | 21071155201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 4071019 | 4106006 | 4039787 | 34986.19 | 0 | 4039787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4039787 | 4039787 | 0 | 4204426
2 | T9037 | 44627925214 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 755793 | 799963 | 782324 | 44170 | 0 | 782311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782324 | 782311 | -13 | 588438
2 | T9039 | 44532025214 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 2629396 | 2652851 | 2657516 | 23454.45 | 0 | 2657516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2657516 | 2657516 | 0 | 2484683
2 | T9041 | 44628015215 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-09-25 | 211688 | 211688 | 200166 | 0 | 0 | 200166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200166 | 200166 | 0 | 233430
2 | T9044 | 44628025216 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-01-29 | 393754 | 393754 | 371540 | 0 | 0 | 371540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371540 | 371540 | 0 | 505500
3 | E3U65 | 44188515201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-11-17 | 3672487 | 3672487 | 3781493 | 0 | -38880 | 3778340 | -38880 | 0 | 0 | 0 | 0 | 0 | -38880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38880 | 3742613 | 3778340 | 35727 | 3629577
3 | E3V54 | 44554115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-02-09 | 9981474 | 10203672 | 10678123 | 222197.51 | 0 | 10639564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10678123 | 10639564 | -38559 | 10144016
3 | E3V77 | 40919375201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-10-12 | 3075367 | 3075367 | 2907496 | 0 | 0 | 2907496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2907496 | 2907496 | 0 | 4067369
3 | E3V81 | 44563415201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2023-06-08 | 7280451 | 7422322 | 7437743 | 141871 | 0 | 7440600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7437743 | 7440600 | 2857 | 6184892
3 | E3W01 | 44559115201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2022-09-08 | 7469384 | 7480930 | 7424797 | 11546.09 | -374814 | 6838207 | -374814 | 0 | 0 | 0 | 0 | 0 | -374814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -374814 | 7049983 | 6838207 | -211775 | 9544566
3 | E3W12 | 44643355201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-08 | 2949285 | 2625347 | 2604415 | -323937.27 | 0 | 2604415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604415 | 2604415 | 0 | 3480038
3 | E3W30 | 44759615201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-06-08 | 4167167 | 4263313 | 3906647 | 96146.41 | 0 | 3906647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3906647 | 3906647 | 0 | 4722892
3 | E3W31 | 44554215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-06-08 | 12495664 | 12574093 | 13184954 | 78428.51 | 0 | 13181542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13184954 | 13181542 | -3412 | 11633200
3 | E3W40 | 44374425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-05-11 | 6286877 | 6497112 | 6613095 | 210234.99 | -68148 | 6607189 | -68148 | 0 | 0 | 0 | 0 | 0 | -68148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68148 | 6544947 | 6607189 | 62243 | 5983265
3 | E3W42 | 44559015201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-11 | 6987787 | 6987787 | 7253303 | 0 | -185514 | 7068223 | -185514 | 0 | 0 | 0 | 0 | 0 | -185514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -185514 | 7067789 | 7068223 | 435 | 10217707
3 | E3W68 | 45102815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-02-13 | 112106 | 112106 | 103639 | 0 | 0 | 103639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103639 | 103639 | 0 | 174993
3 | E3W69 | 42696125201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2023-11-09 | 4685111 | 4688658 | 4492681 | 3546.7 | 0 | 4485331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4492681 | 4485331 | -7350 | 5910727
3 | E3W79 | 45109915201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2024-04-11 | 485265 | 485265 | 487819 | 0 | 0 | 487819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487819 | 487819 | 0 | 555113
3 | E3X01 | 40619455201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-10-24 | 328567 | 328567 | 291720 | 0 | 0 | 291720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291720 | 291720 | 0 | 364798
3 | E3X03 | 40619635201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-03-13 | 169075 | 169075 | 154095 | 0 | 0 | 154095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154095 | 154095 | 0 | 240133
3 | E3X08 | 45103115201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-07-11 | 1112248 | 1112248 | 1077908 | 0 | 0 | 1077908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077908 | 1077908 | 0 | 1273505
3 | E3X17 | 44758915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-06-13 | 2342678 | 2369603 | 2340433 | 26925.01 | 0 | 2340369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340433 | 2340369 | -64 | 2975754
3 | E3X52 | 43078225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-11 | 4271650 | 4271650 | 4371998 | 0 | 0 | 4360199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4371998 | 4360199 | -11799 | 4754953
3 | E3X72 | 22020225201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-02-13 | 647631 | 647631 | 536583 | 0 | 0 | 536583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536583 | 536583 | 0 | 900233
3 | E3X87 | 45268615201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2024-09-12 | 1172775 | 1197264 | 1124063 | 24489.2 | 0 | 1124063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1124063 | 1124063 | 0 | 1445110
3 | E3Y07 | 43937125201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-01-30 | 493247 | 493247 | 468786 | 0 | 0 | 468786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468786 | 468786 | 0 | 566683
3 | E3Y25 | 45431115201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-03-13 | 430052 | 430052 | 391859 | 0 | 0 | 391859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391859 | 391859 | 0 | 619870
3 | E3Y28 | 45443415201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-04-10 | 339177 | 339177 | 318764 | 0 | 0 | 318764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318764 | 318764 | 0 | 393848
3 | T3618 | 21790935201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 27170428 | 30592621 | 31444648 | 3422192.89 | 0 | 32998164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31444648 | 32998164 | 1553516 | 35258008
3 | T3705 | 43581615201 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 21786584 | 24287618 | 24853167 | 2501033.2 | 0 | 24864564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24853167 | 24864564 | 11396 | 31799900
3 | T3722 | 41098185201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 16220760 | 16260965 | 16485438 | 40204.57 | -1083175 | 16125524 | -1083175 | 0 | 0 | 0 | 0 | 0 | -1083175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1083175 | 15402263 | 16125524 | 723261 | 24461057
3 | T3740 | 43626615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 6166449 | 6169465 | 6746581 | 3016.6 | 0 | 7858953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6746581 | 7858953 | 1112372 | 7986598
3 | T3789 | 43813315201 | F473361483 | T & T CIVIL CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-02-23 | 383899 | 397919 | 393163 | 14020 | -35910 | 329110 | -35910 | 0 | 0 | 0 | 0 | 0 | -35910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35910 | 357253 | 329110 | -28143 | 424158
3 | T3790 | 43748915201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 3547402 | 3547402 | 3587891 | 0 | 0 | 3586665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3587891 | 3586665 | -1225 | 4578762
3 | T3804 | 42697315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 6212045 | 6299150 | 6924822 | 87104.94 | 0 | 6889613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6924822 | 6889613 | -35209 | 5759918
3 | T3835 | 44563315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 10919335 | 11003378 | 11511158 | 84042.7 | 0 | 11473007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11511158 | 11473007 | -38151 | 11459374
3 | T3837 | 22259365201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 11772258 | 11871253 | 11834603 | 98994.59 | 0 | 11821261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11834603 | 11821261 | -13342 | 13447557
3 | T3843 | 43736615201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 14976878 | 15770067 | 16545874 | 793188.98 | 0 | 16474250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16545874 | 16474250 | -71624 | 17116856
3 | T3844 | 44581515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 16815829 | 16829871 | 17633297 | 14041.78 | 0 | 17609681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17633297 | 17609681 | -23615 | 15773894
3 | T3851 | 44292015201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-02-28 | 3185384 | 3188684 | 3129056 | 3300 | 0 | 3127773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129056 | 3127773 | -1283 | 3413370
3 | T3855 | 44401915201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 958894 | 958894 | 885299 | 0 | 0 | 885298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 885299 | 885298 | -1 | 1271778
3 | T3862 | 43977415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | 3433760 | 3478528 | 3538382 | 44767.5 | 0 | 3534775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3538382 | 3534775 | -3607 | 3773824
3 | T3868 | 41344925201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 1298401 | 1321412 | 1234071 | 23011 | 0 | 1234071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1234071 | 1234071 | 0 | 1300164
3 | T3871 | 42695025201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-06-12 | 3111541 | 2493770 | 2535278 | -617770.69 | 0 | 2534712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2535278 | 2534712 | -566 | 4093774
3 | T3874 | 44188015201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 988409 | 988409 | 938135 | 0 | 0 | 938135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938135 | 938135 | 0 | 990879
3 | T3891 | 43467815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 2823614 | 2855298 | 2780904 | 31684.39 | 0 | 2780236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780904 | 2780236 | -668 | 3805810
3 | T3901 | 41342535201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | 3608291 | 3609941 | 3619668 | 1650 | 0 | 3616057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3619668 | 3616057 | -3611 | 3187529
3 | T3913 | 21934625201 | F592990776 | AMERICAN SAND & X-CAVATION INC. DBA AMERICAN SAND & ASPHALT | N/A | N/A | N/A | N/A | 2024-08-28 | 2531784 | 2570548 | 2574902 | 38764.2 | 0 | 2573463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574902 | 2573463 | -1439 | 3011929
3 | T9043 | 44628415215 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-09-25 | 189979 | 189979 | 177334 | 0 | 0 | 177334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177334 | 177334 | 0 | 237358
3 | T9045 | 44628425216 | F592320406 | BILL SMITH ELECTRIC | N/A | N/A | N/A | N/A | 2025-01-29 | 511934 | 511934 | 495348 | 0 | 0 | 495348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495348 | 495348 | 0 | 509928
4 | E4Q32 | 43310845201 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2015-04-27 | 148749800 | 174962816 | 175180045 | 26213015.82 | 56000 | 175194917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 56000 | 56000 | 175236045 | 175194917 | -41128 | 122897181 | B10:B5:B8:::Y | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
4 | E4U48 | 44146615201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 2126000 | 2132929 | 1513603 | 6929.94 | 0 | 1513603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513603 | 1513603 | 0 | 2622052
4 | E4U88 | 43999925201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-04-07 | 10631541 | 10738131 | 11100934 | 106590.35 | 0 | 11099417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11100934 | 11099417 | -1518 | 10492575
4 | E4V62 | 43695815201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-08-18 | 31058595 | 33155117 | 32699199 | 1946522.44 | 0 | 32559543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32699199 | 32559543 | -139657 | 29695111
4 | E4W05 | 44047315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-12-02 | 3993841 | 4453325 | 4438530 | 459484.36 | 0 | 4433029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4438530 | 4433029 | -5501 | 4033616
4 | E4W54 | 44618515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-05 | 8153790 | 8619435 | 8570644 | 465645.84 | 0 | 8570644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8570644 | 8570644 | 0 | 7653131
4 | E4W61 | 44610415201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-08-04 | 5369226 | 5369226 | 5576786 | 0 | 0 | 5571433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576786 | 5571433 | -5352 | 4627615
4 | E4W65 | 44617415201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-01-05 | 4920477 | 4920477 | 4833727 | 0 | 0 | 4832964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4833727 | 4832964 | -763 | 4972818
4 | E4W71 | 44974015201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-05 | 827827 | 827827 | 848976 | 0 | 0 | 848976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848976 | 848976 | 0 | 1076147
4 | E4W72 | 44617015201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-11-03 | 4285836 | 4430549 | 4413846 | 144712.95 | 0 | 4404654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4413846 | 4404654 | -9192 | 4697027
4 | E4W82 | 44610515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-01-05 | 4881711 | 4893014 | 4759434 | 11302.53 | 0 | 4771645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4759434 | 4771645 | 12211 | 5716819
4 | E4W88 | 44765415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-02-02 | 6226524 | 6395874 | 6393098 | 169349.93 | 0 | 6387556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6393098 | 6387556 | -5542 | 6625404
4 | E4W89 | 44767415201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-07-12 | 3966137 | 3985889 | 3958991 | 19751.98 | 0 | 3953275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3958991 | 3953275 | -5716 | 4276093
4 | E4W93 | 44764815201 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-12 | 3198987 | 3198987 | 3046918 | 0 | 0 | 3045966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3046918 | 3045966 | -952 | 3443705
4 | E4X14 | 44932315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-04-05 | 3689059 | 3733032 | 3801506 | 43972.81 | 0 | 3800583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3801506 | 3800583 | -923 | 2884957
4 | E4X17 | 44655115201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-02 | 1849000 | 1870772 | 1768167 | 21772.08 | 0 | 1768167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768167 | 1768167 | 0 | 2011837
4 | E4X24 | 44931815201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-06 | 3983900 | 4183008 | 4262893 | 199107.9 | 0 | 4262893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4262893 | 4262893 | 0 | 5126069
4 | E4X33 | 44359525201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-09-06 | 2579048 | 2787519 | 2747199 | 208471 | 0 | 2747177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2747199 | 2747177 | -22 | 3891911
4 | E4X39 | 44768115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-06 | 2519093 | 2519093 | 2422842 | 0 | 0 | 2420995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422842 | 2420995 | -1848 | 2812112
4 | E4X51 | 44765815201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-08-02 | 3535833 | 3535833 | 3387300 | 0 | 0 | 3384814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3387300 | 3384814 | -2487 | 3764178
4 | T4560 | 44004315201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 2472960 | 2472960 | 2581880 | 0 | 0 | 2588651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2581880 | 2588651 | 6772 | 2686958
4 | T4580 | 43992915201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-05-26 | 18014663 | 17978017 | 17209306 | -36646.61 | 0 | 17757665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17209306 | 17757665 | 548358 | 22960743
4 | T4627 | 44384615201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 1831417 | 1831417 | 1800868 | 0 | 0 | 1800868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800868 | 1800868 | 0 | 2390409
4 | T4638 | 43580855201 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2023-07-26 | 8148235 | 8411133 | 8179681 | 262898 | 0 | 8175682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8179681 | 8175682 | -3998 | 8255267
4 | T4641 | 43984515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-04-26 | 11705000 | 12054276 | 11872830 | 349275.93 | 0 | 11861733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11872830 | 11861733 | -11097 | 11870989
4 | T4643 | 44637415201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 17748021 | 18627265 | 18943576 | 879243.5 | 0 | 18918036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18943576 | 18918036 | -25540 | 24914785
4 | T4645 | 44610215201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 12833449 | 12956058 | 12287948 | 122609.04 | 0 | 12290198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12287948 | 12290198 | 2250 | 14351247
4 | T4649 | 44839715201 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2023-06-14 | 4835155 | 5082020 | 5106645 | 246864.93 | 0 | 5105846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5106645 | 5105846 | -798 | 6110749
4 | T4651 | 44407915201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-10-25 | 7152200 | 7526530 | 7413084 | 374329.92 | 0 | 7398235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7413084 | 7398235 | -14849 | 6673207
4 | T4652 | 44616915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | 5424973 | 5477905 | 5676734 | 52931.68 | 0 | 5668308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5676734 | 5668308 | -8426 | 5383942
4 | T4654 | 44952015201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 5626066 | 5715669 | 5782761 | 89602.91 | 0 | 5782671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5782761 | 5782671 | -91 | 6458891
4 | T4661 | 44620015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-03-27 | 9458464 | 9790787 | 9649312 | 332323.68 | 0 | 9630778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9649312 | 9630778 | -18533 | 11108028
4 | T4662 | 44001515201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 2710165 | 2699856 | 2568771 | -10309.35 | 0 | 2568756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568771 | 2568756 | -16 | 3354140
4 | T4663 | 44764715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 11192757 | 11220679 | 11200266 | 27922.29 | 0 | 11169796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200266 | 11169796 | -30470 | 11705908
4 | T4664 | 44699715201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-13 | 1247247 | 1247247 | 1175544 | 0 | 0 | 1174544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1175544 | 1174544 | -1000 | 1347695
4 | T4665 | 44619515201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-02-28 | 5489802 | 5499093 | 5514945 | 9290.94 | 0 | 5496131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5514945 | 5496131 | -18814 | 5906510
4 | T4667 | 44764615201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-03-27 | 5722729 | 5878728 | 5826172 | 155998.27 | 0 | 5813776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5826172 | 5813776 | -12396 | 5723688
4 | T4677 | 44767915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 7765433 | 7871392 | 7668837 | 105958.4 | 0 | 7663134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7668837 | 7663134 | -5703 | 8421051
4 | T4679 | 44619615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 5469442 | 5469442 | 5544372 | 0 | 0 | 5542177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5544372 | 5542177 | -2195 | 5971109
4 | T4686 | 42957695201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2024-04-24 | 3298227 | 3298227 | 3079319 | 0 | 0 | 3078260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3079319 | 3078260 | -1060 | 3509812
4 | T4687 | 45222715201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-05-22 | 1600545 | 1600545 | 1508063 | 0 | 0 | 1508063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1508063 | 1508063 | 0 | 2128846
4 | T4694 | 44767115201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-07-31 | 3150955 | 3159605 | 3107001 | 8650 | 0 | 3106285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3107001 | 3106285 | -716 | 3340322
4 | T4708 | 44754315201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2024-07-31 | 1300000 | 1300000 | 1243700 | 0 | 0 | 1243700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243700 | 1243700 | 0 | 1369377
5 | E50B8 | 44521515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-06-06 | 11282143 | 11851012 | 12077791 | 568869.16 | 0 | 12077791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12077791 | 12077791 | 0 | 10131956
5 | E50F1 | 44656815201 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2024-02-06 | 1104118 | 1104118 | 1062935 | 0 | 0 | 1062929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062935 | 1062929 | -6 | 1174164
5 | E50F5 | 44316915201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2024-01-04 | 5036336 | 5073420 | 4545253 | 37084.7 | 0 | 4525803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4545253 | 4525803 | -19451 | 5619045
5 | E51F2 | 44768815201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-04-02 | 1504656 | 1506430 | 1447570 | 1774.33 | 0 | 1447098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1447570 | 1447098 | -472 | 1590260
5 | E51F6 | 43923415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-05 | 16652098 | 16895551 | 16781249 | 243452.83 | 0 | 16757648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16781249 | 16757648 | -23602 | 16309345
5 | E51F7 | 44530215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-03-05 | 5562121 | 5724310 | 5880473 | 162189.46 | 0 | 5865584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5880473 | 5865584 | -14889 | 6330177
5 | E51F9 | 43912415201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-02 | 4408516 | 4442576 | 4279968 | 34060.07 | 0 | 4279968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4279968 | 4279968 | 0 | 6688705
5 | E52F4 | 45293215201 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2024-06-04 | 1554510 | 1554510 | 1576041 | 0 | 0 | 1576454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576041 | 1576454 | 413 | 1518096
5 | E53F2 | 44879115201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-10-01 | 7065614 | 7183452 | 7253477 | 117838 | 0 | 7256561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7253477 | 7256561 | 3084 | 8985393
5 | E53F6 | 44880115201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2024-08-08 | 5664533 | 5664533 | 5824248 | 0 | 0 | 5821719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5824248 | 5821719 | -2529 | 5574707
5 | E53F7 | 44984515201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-12-03 | 925088 | 925088 | 953719 | 0 | 0 | 953719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953719 | 953719 | 0 | 845922
5 | E53F8 | 45022745201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-06-04 | 1498164 | 1498164 | 1468694 | 0 | 0 | 1468694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1468694 | 1468694 | 0 | 1507975
5 | E54B3 | 44521415201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-10-03 | 6964127 | 7171619 | 7043664 | 207492.45 | 0 | 6998013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7043664 | 6998013 | -45651 | 9627439
5 | E55F3 | 45131115201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-02-04 | 4402920 | 4402920 | 4332664 | 0 | 0 | 4326586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4332664 | 4326586 | -6078 | 6422896
5 | E55F4 | 42690555201 | F824750393 | COLLINS LAND SERVICES LLC | N/A | N/A | N/A | N/A | 2025-04-01 | 1132509 | 1132509 | 1025664 | 0 | 0 | 1025664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025664 | 1025664 | 0 | 1246520
5 | E55F6 | 44529815201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-04 | 7863435 | 8058116 | 8341201 | 194681.09 | 0 | 8333175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8341201 | 8333175 | -8027 | 10455826
5 | E56B6 | 44521115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 3196756 | 3198241 | 3427202 | 1484.92 | 0 | 3427202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427202 | 3427202 | 0 | 3501358
5 | E56F4 | 41025155201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-05-06 | 3296100 | 3296100 | 3182948 | 0 | 0 | 3193975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3182948 | 3193975 | 11027 | 5178576
5 | E56F7 | 45305815201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2025-04-01 | 6639966 | 6639966 | 6618677 | 0 | 0 | 6618677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6618677 | 6618677 | 0 | 8028735
5 | E57B3 | 24259265201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2023-06-06 | 9899345 | 10080554 | 10364962 | 181208.47 | 0 | 10364953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10364962 | 10364953 | -9 | 8480188
5 | E57B5 | 44530315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 11137584 | 11274458 | 11215283 | 136873.78 | 0 | 11214497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11215283 | 11214497 | -786 | 8364008
5 | E57B7 | 44708515201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-06-06 | 13078910 | 13273764 | 13547486 | 194854.3 | 0 | 13544883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13547486 | 13544883 | -2602 | 13524204 | A5 | ICC - BAM/BONUS
5 | E59A5 | 44780715201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-04-06 | 973615 | 973615 | 939263 | 0 | 0 | 939263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939263 | 939263 | 0 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E59B2 | 43986415201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2024-02-06 | 3015224 | 3086900 | 3009526 | 71675.77 | 0 | 3004683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009526 | 3004683 | -4843 | 3337723
5 | E5Z18 | 24020045201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-08-22 | 253332000 | 267516079 | 275166241 | 14184078.5 | 25000 | 276193366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 25000 | 275191241 | 276193366 | 1002125 | 283931078 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | T5650 | 23839555201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-03-11 | 44960000 | 46736451 | 46188504 | 1776450.82 | 0 | 47789854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46188504 | 47789854 | 1601350 | 45602808
5 | T5706 | 42955615201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 44888403 | 47699589 | 50521720 | 2811185.71 | 0 | 50750843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50521720 | 50750843 | 229122 | 37019155
5 | T5718 | 43763415201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 11250000 | 12978309 | 13223828 | 1728309.11 | 0 | 13379283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13223828 | 13379283 | 155455 | 10799983
5 | T5747 | 43366115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 6696978 | 7142732 | 7032054 | 445754.9 | 0 | 7032054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7032054 | 7032054 | 0 | 5918166
5 | T5759 | 44586715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-04-26 | 3865830 | 3991018 | 3937381 | 125187.71 | 0 | 3936003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3937381 | 3936003 | -1378 | 3318269
5 | T5760 | 44114515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 9020145 | 9091224 | 9371724 | 71078.78 | 0 | 9370672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9371724 | 9370672 | -1051 | 8000814
5 | T5777 | 44042425201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 22896706 | 23663870 | 23767312 | 767163.74 | 0 | 22940754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23767312 | 22940754 | -826558 | 28387050 | B10 | ACC - BONUS/INCENT/DISINCENT
5 | T5778 | 44569215201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 1617324 | 1637324 | 1467772 | 20000 | 0 | 1467140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1467772 | 1467140 | -632 | 1625739
5 | T5786 | 44521715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 10986719 | 11011859 | 11062198 | 25139.3 | 0 | 11057841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11062198 | 11057841 | -4358 | 14985674
5 | T5789 | 43547125201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 8448064 | 8800372 | 8800513 | 352307.8 | 0 | 8801368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8800513 | 8801368 | 855 | 8153515
5 | T5792 | 41025135201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 15097285 | 15626114 | 15519395 | 1098562.68 | 0 | 15511432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15519395 | 15511432 | -7963 | 25813007
5 | T5795 | 24259285201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 8347803 | 8496009 | 8830863 | 148205.6 | 0 | 8830373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8830863 | 8830373 | -490 | 8013785
5 | T5796 | 42617915201 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 3346229 | 3547942 | 3223459 | 201712.99 | 0 | 3223429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3223459 | 3223429 | -31 | 4393699
5 | T5797 | 44568915201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-26 | 6209544 | 6295030 | 5955348 | 85486.24 | 0 | 5954663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5955348 | 5954663 | -685 | 5653229
5 | T5799 | 44571615201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 7000000 | 7423497 | 7482575 | 423497.41 | 0 | 7448919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7482575 | 7448919 | -33657 | 8074701
5 | T5800 | 44585515201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-26 | 3679712 | 3851805 | 3808215 | 172092.45 | 0 | 3808146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3808215 | 3808146 | -69 | 2818722
5 | T5801 | 44521915201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 15286323 | 15295366 | 15592805 | 9042.58 | 0 | 15531171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15592805 | 15531171 | -61634 | 20005006
5 | T5804 | 43757515201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 3278993 | 3308018 | 3163264 | 29024.9 | 0 | 3163188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3163264 | 3163188 | -76 | 3131835
5 | T5805 | 44709215201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 3271306 | 3287930 | 3244926 | 16623.23 | 0 | 3224506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3244926 | 3224506 | -20420 | 4597691
5 | T5806 | 44709815201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 9892142 | 9938977 | 10455307 | 46835.26 | 0 | 10397121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10455307 | 10397121 | -58186 | 11922850
5 | T5809 | 43915615201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-09-27 | 19059007 | 19456279 | 20132774 | 397272.41 | 0 | 20058365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20132774 | 20058365 | -74410 | 20470643
5 | T5811 | 43233215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 15324226 | 16443632 | 16758792 | 1119405.88 | 0 | 16640684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16758792 | 16640684 | -118108 | 22228374
5 | T5826 | 45222915201 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-05-22 | 1180815 | 1180815 | 979467 | 0 | 0 | 981703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979467 | 981703 | 2236 | 1609251
5 | T5833 | 44708915201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 2100000 | 2100000 | 2001416 | 0 | 0 | 2001416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2001416 | 2001416 | 0 | 2701146
5 | T5835 | 44873915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-30 | 3081418 | 3081418 | 3111059 | 0 | 0 | 3112003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3111059 | 3112003 | 944 | 3300432
5 | T5857 | 45613715201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 117123 | 113191 | 103346 | -3931.68 | 0 | 103346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103346 | 103346 | 0 | 180486
5 | T5858 | 45616815201 | F850531344 | PREMIER PAVING LLC | N/A | N/A | N/A | N/A | 2025-03-26 | 948635 | 993577 | 604185 | 44942 | 0 | 604185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604185 | 604185 | 0 | 1621410
5 | T9030 | 44199035223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 5555556 | 5605113 | 5565155 | 49557.59 | 0 | 5565155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5565155 | 5565155 | 0 | 5530000
6 | E6L20 | 25054885201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-05-26 | 28158187 | 28920235 | 27890563 | 762048.51 | 120000 | 27771528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 28010563 | 27771528 | -239034 | 23137913 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | E6M86 | 43351125201 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2021-05-27 | 41366428 | 43068537 | 44950000 | 1702108.31 | 1960000 | 45038064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 160000 | 0 | 1960000 | 1960000 | 46910000 | 45038064 | -1871936 | 33950112 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | E6N17 | 44716515201 | F834649779 | AGI DE MOYA JOINT VENTURE | N/A | N/A | N/A | N/A | 2021-09-13 | 66054600 | 66794016 | 66824078 | 739415.88 | 1200000 | 67046919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 68024078 | 67046919 | -977158 | 34964142 | B5:B5:B5::::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
6 | E6O12 | 44391925201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-25 | 2869869 | 2869869 | 2778313 | 0 | 140000 | 2778250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 140000 | 140000 | 2918313 | 2778250 | -140063 | 2865779 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | E6O17 | 43029169201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-13 | 7237000 | 7269318 | 7237180 | 32318.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7237180 | 0 | -7237180 | 5284477 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6O81 | 44598815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-03-28 | 3370711 | 3853261 | 3033601 | 482549.84 | 120000 | 3032315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 3153601 | 3032315 | -121286 | 3432003 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6P13 | 43029189201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-04-22 | 1315382 | 1315382 | 1284180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284180 | 0 | -1284180 | 1725000 | Y | DESIGN/BUILD PROJECT
6 | E6P23 | 44391115201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-03-28 | 5790735 | 6121430 | 5667306 | 330694.99 | 100000 | 5665707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 5767306 | 5665707 | -101599 | 4862239 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6466 | 43992315201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 749749 | 750453 | 687268 | 704 | 0 | 687166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687268 | 687166 | -102 | 759571
6 | T6514 | 44462215201 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 12567171 | 13007370 | 12865831 | 440199.87 | 500000 | 12808223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 13365831 | 12808223 | -557608 | 11765757 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6541 | 44390215201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-02-22 | 6112543 | 6196534 | 6055588 | 83991.29 | 0 | 6047700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6055588 | 6047700 | -7887 | 4898503 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6547 | 44392115201 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2023-05-24 | 7844825 | 8071972 | 8026073 | 227147.21 | 200000 | 8025252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 8226073 | 8025252 | -200821 | 8411804 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6555 | 44598715201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2023-04-26 | 15230513 | 15276979 | 14673045 | 46466.35 | 440000 | 14652396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 440000 | 440000 | 15113045 | 14652396 | -460650 | 16721998 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6556 | 44389615201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-05-24 | 12343500 | 12329103 | 12004695 | -14397.46 | 340000 | 12003108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000 | 0 | 0 | 0 | 0 | 0 | 340000 | 340000 | 12344695 | 12003108 | -341587 | 10090244 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6562 | 44393715201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-03-29 | 9816354 | 9816354 | 9814725 | 0 | 320000 | 9792214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 10134725 | 9792214 | -342511 | 10415642 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6564 | 44599515201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2023-12-06 | 2427793 | 2522356 | 2377282 | 94563.1 | 100000 | 2374390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 2477282 | 2374390 | -102891 | 2381685 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6565 | 44389815202 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-02-22 | 17424162 | 17775584 | 17807123 | 351422.16 | 360000 | 17736459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 360000 | 360000 | 18167123 | 17736459 | -430664 | 16704095 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6567 | 44757415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 1669000 | 1695000 | 1692054 | 26000 | 0 | 1691797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1692054 | 1691797 | -258 | 1801028
6 | T6568 | 44393225201 | F832482227 | TRAFFICO LLC | N/A | N/A | N/A | N/A | 2024-08-28 | 1068800 | 1068800 | 1002901 | 0 | 0 | 1002859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1002901 | 1002859 | -41 | 1151283
6 | T6573 | 44599115201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-06 | 7944520 | 7965978 | 7740756 | 21457.87 | 320000 | 7730600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 8060756 | 7730600 | -330157 | 8387399 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6574 | 44780515201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2023-10-25 | 3338573 | 3388573 | 3361643 | 50000 | 100000 | 3354655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 3461643 | 3354655 | -106988 | 3605554 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6575 | 44780615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 4637389 | 4652332 | 4600291 | 14943 | 0 | 4597318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600291 | 4597318 | -2973 | 4247705 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6577 | 44390915201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-24 | 4280927 | 4380927 | 4298470 | 100000 | 180000 | 4296065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 4478470 | 4296065 | -182405 | 4677512 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6580 | 44600015201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-24 | 5947099 | 6376641 | 6242028 | 429541.28 | 0 | 6225782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6242028 | 6225782 | -16246 | 6394669 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6584 | 44391215201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-03-27 | 8558846 | 8890402 | 8748106 | 331555.89 | 220000 | 8742165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 220000 | 220000 | 8968106 | 8742165 | -225941 | 7821851 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6598 | 44780415201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2024-09-25 | 2627713 | 2705308 | 2578007 | 77594.38 | 120000 | 2578006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 2698007 | 2578006 | -120001 | 3026337 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | E7N56 | 43726425201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-05-27 | 19975000 | 20432970 | 21351585 | 457969.6 | 0 | 21291797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21351585 | 21291797 | -59788 | 15858300
7 | E7P77 | 44146315201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-05-10 | 3366760 | 3493112 | 3363518 | 126351.52 | 300000 | 3363518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 3663518 | 3363518 | -300000 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | E7Q08 | 44761515201 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2023-05-10 | 6147921 | 6373747 | 6357061 | 225826.32 | 0 | 6355355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6357061 | 6355355 | -1706 | 5831100
7 | E7Q31 | 44384115201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2023-12-13 | 1681476 | 1805476 | 1410753 | 124000 | -3398 | 1407355 | -3398 | 0 | 0 | 0 | 0 | 0 | -3398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3398 | 1407355 | 1407355 | 0 | 1673100
7 | E7Q39 | 44582815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-02-14 | 1714027 | 1714027 | 1704720 | 0 | 0 | 1704720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1704720 | 1704720 | 0 | 3483914
7 | E7Q53 | 44583015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-05-08 | 1599000 | 1601196 | 1343560 | 2195.84 | 0 | 1343560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343560 | 1343560 | 0 | 1936163
7 | E7Q55 | 44165115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-03-13 | 4066019 | 4201769 | 4164473 | 135750.09 | 0 | 4159743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4164473 | 4159743 | -4730 | 4234476
7 | E7Q75 | 45288915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-06-12 | 1296714 | 1381899 | 1384246 | 85184.94 | 0 | 1384246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384246 | 1384246 | 0 | 1695805
7 | E7Q94 | 45273615201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-12-11 | 259111 | 259111 | 235124 | 0 | 0 | 235124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235124 | 235124 | 0 | 516283
7 | E7R15 | 44138815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-29 | 21358193 | 21288752 | 21393187 | -69440.22 | 1150000 | 21918008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 1150000 | 1150000 | 22543187 | 21918008 | -625179 | 26431774 | A3:A3:A3:B10 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
7 | E7R21 | 42451335201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2021-05-20 | 81649200 | 89787672 | 91076513 | 8138472.09 | 0 | 91676950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91076513 | 91676950 | 600437 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7R24 | 44132015201 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2022-08-04 | 6997500 | 7112720 | 7042786 | 115219.68 | 0 | 7042581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7042786 | 7042581 | -205 | 13119000
7 | E7R26 | 42925115201 | F871503473 | PRINCE-AJAX DDI JV | N/A | N/A | N/A | N/A | 2021-06-17 | 89691574 | 96531643 | 97484006 | 6840069.17 | -45000 | 98162236 | 0 | 0 | 0 | 0 | 0 | -45000 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45000 | 97439006 | 98162236 | 723230 | 100030998 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7R35 | 43983215201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-25 | 10158800 | 10244736 | 10281972 | 85935.86 | 0 | 10278335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10281972 | 10278335 | -3637 | 12981331 | LBDB:LBDB | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
7 | E7R40 | 44335825201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-03-07 | 1322000 | 1334250 | 1257998 | 12249.84 | 0 | 1253861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1257998 | 1253861 | -4137 | 1543770 | LBDB | LOW BID DESIGN BUILD
7 | E7U08 | 44366515201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-09-11 | 3709156 | 3709156 | 3454248 | 0 | 0 | 3454248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3454248 | 3454248 | 0 | 3944855
7 | T7396 | 41673245201 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2019-07-31 | 55832153 | 56499915 | 56400689 | 667762.03 | 875160 | 56882314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875160 | 0 | 0 | 0 | 0 | 0 | 875160 | 875160 | 57275849 | 56882314 | -393534 | 63202968 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
7 | T7472 | 43182125201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-05-26 | 85239705 | 94443373 | 97569383 | 9203668.27 | 0 | 97817624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97569383 | 97817624 | 248241 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7505 | 44166115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 13856415 | 13819912 | 13656236 | -36503.46 | 0 | 13654130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13656236 | 13654130 | -2106 | 14165000
7 | T7507 | 44600915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2023-05-17 | 22407724 | 24195428 | 26279346 | 1787704.03 | -10000 | 26267268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | -10000 | 26269346 | 26267268 | -2078 | 23830100
7 | T7509 | 44588615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 8085082 | 8115381 | 7967342 | 30299.15 | 0 | 7993474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7967342 | 7993474 | 26132 | 9550800
7 | T7512 | 44334715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 6290573 | 6754957 | 7072599 | 464384.48 | 0 | 7072474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7072599 | 7072474 | -125 | 6135700
7 | T7514 | 45069315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 2469300 | 2490043 | 2487609 | 20743.16 | 0 | 2486604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487609 | 2486604 | -1005 | 2285000
7 | T7515 | 44803615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-06-14 | 13134873 | 13851674 | 14146391 | 716801.05 | 0 | 14153827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14146391 | 14153827 | 7436 | 13139100
7 | T7516 | 44006315201 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2023-06-14 | 6730280 | 6779810 | 6697913 | 49529.32 | 0 | 6699170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6697913 | 6699170 | 1257 | 7050800
7 | T7523 | 44697315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 2049777 | 2049777 | 2101379 | 0 | 0 | 2098362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101379 | 2098362 | -3017 | 2385840
7 | T7529 | 44109835201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-03-27 | 1336107 | 1336107 | 1267198 | 0 | 0 | 1266909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267198 | 1266909 | -289 | 1581132
7 | T7538 | 44939815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-05-15 | 545691 | 545691 | 518518 | 0 | 0 | 518518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518518 | 518518 | 0 | 611133
7 | T7544 | 44025015201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2024-04-17 | 7475300 | 7428809 | 7644411 | -46491.53 | 0 | 7629621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7644411 | 7629621 | -14790 | 8386992
7 | T7548 | 44752215201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2024-05-15 | 2173906 | 2247825 | 2217265 | 73919.24 | 0 | 2216464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2217265 | 2216464 | -801 | 1912820
7 | T7550 | 45241215201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-05-15 | 654321 | 654321 | 610593 | 0 | 0 | 610593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610593 | 610593 | 0 | 826944
7 | T7555 | 44794815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 5942087 | 5942922 | 5968673 | 835.12 | 0 | 5968280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5968673 | 5968280 | -393 | 7672150
7 | T7573 | 45096915201 | F931411815 | LAKEVIEW CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-03-26 | 365071 | 370411 | 359883 | 5340 | 0 | 354442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359883 | 354442 | -5442 | 528390
8 | E8R45 | 43799215201 | F825435435 | CENTRAL MORRISON COBALT JV | N/A | N/A | N/A | N/A | 2018-11-15 | 33928239 | 47651600 | 47969861 | 13723361.4 | 0 | 47904732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47969861 | 47904732 | -65129 | 41184698
8 | E8T48 | 43496835201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-04-19 | 10781928 | 10718856 | 10512572 | -63072.39 | 0 | 10512572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10512572 | 10512572 | 0 | 11904889 | A3 | ICC - DESIGN/BUILD - MINOR
8 | E8T83 | 44276415201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-09-20 | 102999958 | 103423210 | 104129622 | 423252.32 | 4744548 | 102654085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4744548 | 0 | 0 | 0 | 0 | 0 | 4744548 | 4744548 | 108874170 | 102654085 | -6220085 | 121233962 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8U04 | 44602415201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-03-21 | 16184460 | 17190583 | 16458548 | 1006122.94 | 0 | 16411881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16458548 | 16411881 | -46667 | 18390077
8 | E8U19 | 44588515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-04-11 | 11226810 | 11263007 | 11344464 | 36197.44 | 0 | 11339363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11344464 | 11339363 | -5101 | 11461891
8 | E8U32 | 44925335201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2023-05-09 | 3649071 | 3673424 | 3464348 | 24353 | 0 | 3464348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3464348 | 3464348 | 0 | 4370418
8 | E8U46 | 43854815201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-05-14 | 4734726 | 4734726 | 4628034 | 0 | 0 | 4628034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4628034 | 4628034 | 0 | 8236620
8 | E8U56 | 44942325201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2023-08-22 | 1804313 | 1864511 | 1827419 | 60197.92 | 37398 | 1827419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37398 | 0 | 0 | 0 | 0 | 0 | 37398 | 37398 | 1864817 | 1827419 | -37398 | 1786238 | A6 | ICC - BAM/INCENTIVE-DISINCENT
8 | E8U67 | 44440215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-12 | 24889345 | 25770345 | 25416917 | 880999.92 | 0 | 25287822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25416917 | 25287822 | -129095 | 27205818
8 | E8U71 | 41592755201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-02-13 | 2794276 | 2537251 | 2444066 | -257025.06 | 0 | 2444066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2444066 | 2444066 | 0 | 6003502
8 | E8U73 | 44206215201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-03-12 | 13684469 | 13793245 | 13317036 | 108776.05 | 0 | 13293015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13317036 | 13293015 | -24020 | 19932483
8 | E8U91 | 44917545201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-06-11 | 4804962 | 4908714 | 4813444 | 103751.34 | 0 | 4812923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4813444 | 4812923 | -521 | 4334608
8 | E8U95 | 44917535201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2024-04-09 | 1605678 | 1605678 | 1663792 | 0 | 0 | 1663792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663792 | 1663792 | 0 | 1739460
8 | E8V77 | 45211115201 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-02-19 | 1699787 | 1699787 | 1444210 | 0 | 0 | 1444159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1444210 | 1444159 | -52 | 1780237

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1754 | 41924345201 | 2020-06-10 | QTR4 | 19/20 | 1 | 8 | 1300 | 1542 | 1316 | 226 | 0 | 0 | 242 | 0 | 44711727 | 150000 | 44561727 | 45332170 | 44869139 | 0 | 0 | 0 | 44869139 | 45508351 | 2409623 | 620443 | 176 | 0 | 0 | 75074 | 0 | 0 | 0 | 369025 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65721 | 0 | 0 | 0 | 2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656851 | 70927 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 | 2024-04-12 | QTR4 | 23/24 | 118 | 49671695.98 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | CO | 19 | 01co | 1 | 19
01CO | 01 | T1801 | 43355055201 | 2022-02-23 | QTR3 | 21/22 | 4 | 11 | 450 | 785 | 785 | 0 | 0 | 0 | 157 | 178 | 9943982 | 61935 | 9882047 | 10795145 | 10516274 | 0 | 0 | 0 | 10516274 | 10451415 | 22951 | 851163 | 75 | 0 | 10 | 59915 | 0 | 14 | 35 | 107389 | 65872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 0 | 0 | 60900 | 0 | 0 | 0 | 314 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 15101 | 0 | 0 | 0 | 0 | 0 | 10 | 133 | 534836 | 45203 | 0 | 0 | 0 | 0 | 27 | 178 | 784204 | 111075 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2026-01-26 | QTR3 | 25/26 | 2024-12-23 | QTR2 | 24/25 | 115 | 8613987.04 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | CO | 21 | 01do | 20 | 40
01CO | 01 | T1807 | 44464115201 | 2023-05-24 | QTR4 | 22/23 | 2 | 8 | 250 | 356 | 355 | 1 | 0 | 0 | 95 | 11 | 5486544 | 50000 | 5436544 | 5582663 | 5697293 | -30000 | 0 | -30000 | 5667293 | 5634025 | -212 | 96120 | 56 | 21 | 11 | 58440 | 0 | 0 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 1490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 11 | 77189 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-18 | QTR3 | 25/26 | 2025-04-21 | QTR4 | 24/25 | 118 | 4275732.4 |  |  | 2 | 18 | 0 | 0 | 0 | 0 |  | CO | 42 | 02co | 41 | 82
01CO | 01 | T1833 | 44634515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 300 | 472 | 471 | 1 | 0 | 0 | 172 | 0 | 16756829 | 150000 | 16606829 | 16756829 | 16918647 | 0 | -70500 | -70500 | 16848147 | 16748453 | -99694 | 0 | 136 | 0 | 0 | 23670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 | 2023-12-05 | QTR2 | 23/24 | 106 | 17387334.58 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO | 6 | 02do | 83 | 88
01CO | 01 | T1843 | 43695525201 | 2022-07-27 | QTR1 | 22/23 | 1 | 6 | 225 | 443 | 443 | 0 | 0 | 0 | 201 | 17 | 4165582 | 50000 | 4115582 | 4197230 | 4319692 | 0 | 0 | 0 | 4319692 | 4254744 | -56953 | 31648 | 155 | 0 | 17 | 23652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 23652 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-08-27 | QTR1 | 25/26 | 2025-01-17 | QTR3 | 24/25 | 113 | 3563244.72 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO | 22 | 03co | 89 | 110
01CO | 01 | T1850 | 43944115201 | 2024-04-24 | QTR4 | 23/24 | 1 | 4 | 400 | 457 | 457 | 0 | 0 | 0 | 57 | 0 | 5279314 | 0 | 5279314 | 5778359 | 5716286 | 0 | 0 | 0 | 5716286 | 5630083 | -2290 | 499045 | 41 | 0 | 0 | 149726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349371 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 | 2025-10-28 | QTR2 | 25/26 | 108 | 7929522.13 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 23 | 03do | 111 | 133
01CO | 01 | T1852 | 44787215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 0 | 175 | 207 | 204 | 3 | 0 | 0 | 32 | 0 | 3084175 | 50000 | 3034175 | 3084175 | 3074445 | 0 | 0 | 0 | 3074445 | 3073651 | -795 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-05-01 | QTR4 | 24/25 | 115 | 2364265.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 23 | 04co | 134 | 156
01CO | 01 | T1854 | 44480735201 | 2024-03-27 | QTR3 | 23/24 | 1 | 1 | 125 | 192 | 182 | 10 | 0 | 0 | 47 | 20 | 1273662 | 46380 | 1227282 | 1300460 | 1232804 | 0 | -22000 | -22000 | 1210804 | 1210162 | -642 | 26799 | 27 | 0 | 20 | 26799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 26799 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 115 | 1109604.92 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO | 20 | 04do | 157 | 176
01CO | 01 | T1855 | 44547315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 5 | 300 | 577 | 607 | -30 | 30 | 0 | 176 | 101 | 11238774 | 116686 | 11122088 | 11323365 | 11568463 | -143070 | 0 | -143070 | 11425393 | 11375607 | -39102 | 84591 | 129 | 0 | 0 | 107185 | 0 | 0 | 101 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 114493 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 118 | 12534705.29 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO | 28 | 05co | 177 | 204
01CO | 01 | T1866 | 43903215201 | 2023-11-15 | QTR2 | 23/24 | 2 | 4 | 225 | 301 | 330 | -29 | 29 | 0 | 65 | 11 | 3945642 | 68014 | 3877628 | 4078353 | 4013289 | -76850 | 0 | -76850 | 3936439 | 3832582 | -14467 | 132711 | 40 | 0 | 9 | 43321 | 0 | 0 | 2 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 45054 | 0 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 | 2025-03-20 | QTR3 | 24/25 | 118 | 5005578.39 |  |  | 2 | 25 | 0 | 0 | 0 | 0 | T | CO | 25 | 05do | 205 | 229
01CO | 01 | T1867 | 44546715201 | 2024-01-31 | QTR3 | 23/24 | 2 | 4 | 250 | 361 | 352 | 9 | 0 | 0 | 83 | 28 | 7502026 | 73856 | 7428170 | 8082796 | 8181304 | 0 | 0 | 0 | 8181304 | 8176865 | -4440 | 580770 | 30 | 3 | 9 | 370939 | 0 | 3 | 0 | 23365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 201258 | 0 | 0 | 0 | 12662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 28 | 608224 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-02-11 | QTR3 | 25/26 | 2025-11-21 | QTR2 | 25/26 | 108 | 7936833.12 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 18 | 06co | 230 | 247
01CO | 01 | T1868 | 44740215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 2 | 100 | 207 | 206 | 1 | 0 | 0 | 107 | 0 | 1036497 | 45938 | 990559 | 1074999 | 1074468 | 0 | 0 | 0 | 1074468 | 1035967 | 0 | 38502 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 | 2025-02-05 | QTR3 | 24/25 | 115 | 1164568.56 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 8 | 06do | 248 | 255
01CO | 01 | T1873 | 44788015201 | 2024-02-28 | QTR3 | 23/24 | 2 | 3 | 200 | 287 | 285 | 2 | 0 | 0 | 87 | 0 | 2902791 | 50000 | 2852791 | 2941983 | 2705963 | 0 | 0 | 0 | 2705963 | 2704866 | -1098 | 39192 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 65279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65279 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-02-02 | QTR3 | 25/26 | 2025-11-07 | QTR2 | 25/26 | 113 | 2895926.83 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 17 | 07co | 256 | 272
01CO | 01 | T1881 | 43802715201 | 2023-11-15 | QTR2 | 23/24 | 2 | 1 | 200 | 310 | 310 | 0 | 0 | 0 | 94 | 16 | 6196035 | 68350 | 6127685 | 6206737 | 6556044 | 0 | 0 | 0 | 6556044 | 6524950 | -31093 | 10701 | 70 | 0 | 16 | 12210 | 0 | 0 | 0 | 19772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 31982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 | 2025-04-02 | QTR4 | 24/25 | 108 | 6886950.71 |  |  | 16 | 24 | 0 | 0 | 0 | 0 |  | CO | 16 | 07do | 273 | 288
01CO | 01 | T1889 | 44431315201 | 2024-03-27 | QTR3 | 23/24 | 2 | 1 | 200 | 346 | 346 | 0 | 0 | 0 | 116 | 0 | 2636284 | 50000 | 2586284 | 2666046 | 2714680 | -3800 | 0 | -3800 | 2710880 | 2705941 | -4939 | 29762 | 88 | 0 | 0 | 6254 | 0 | 0 | 0 | 60445 | 15459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66698 | 15459 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-27 | QTR3 | 25/26 | 2025-09-24 | QTR1 | 25/26 | 108 | 3253356.71 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 289 | 288
01CO | 01 | T1891 | 44743625201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 175 | 235 | 235 | 0 | 0 | 0 | 39 | 21 | 4742624 | 50000 | 4692624 | 4787027 | 4779994 | 0 | 0 | 0 | 4779994 | 4777172 | -2822 | 44403 | 18 | 0 | 0 | 0 | 0 | 0 | 21 | 50051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -585 | 0 | 0 | 0 | 13168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 62635 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-10 | QTR2 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 108 | 4605369.8 |  |  | 19 | 21 | 0 | 0 | 0 | 0 |  | CO | 14 | 08do | 289 | 302
01CO | 01 | T1895 | 44656015201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 125 | 169 | 169 | 0 | 0 | 0 | 20 | 24 | 1414901 | 0 | 1414901 | 1450512 | 1460078 | 0 | 0 | 0 | 1460078 | 1460017 | -61 | 35611 | 16 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 | 2025-07-28 | QTR1 | 25/26 | 108 | 1992638.1 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1905 | 44645215201 | 2025-01-29 | QTR3 | 24/25 | 1 | 1 | 100 | 144 | 144 | 0 | 0 | 0 | 34 | 10 | 574929 | 0 | 574929 | 574929 | 554144 | 0 | 0 | 0 | 554144 | 554144 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-02-02 | QTR3 | 25/26 | 2025-10-23 | QTR2 | 25/26 | 108 | 670642.47 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1927 | 44477325201 | 2025-07-30 | QTR1 | 25/26 | 1 | 0 | 100 | 116 | 115 | 1 | 0 | 0 | 16 | 0 | 414963 | 0 | 414963 | 414963 | 422033 | 0 | 0 | 0 | 422033 | 422033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 | 2026-02-12 | QTR3 | 25/26 | 118 | 496784.63 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO |  | 0
01DO | 01 | E1R76 | 20121535201 | 2020-05-29 | QTR4 | 19/20 | 1 | 5 | 1050 | 1489 | 1488 | 1 | 0 | 0 | 365 | 74 | 70460520 | 150000 | 70310520 | 71635236 | 71638136 | -100000 | 0 | -100000 | 71538136 | 74769243 | 5571562 | 1174716 | 264 | 0 | 0 | 60435 | 0 | 0 | 74 | 916285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 314762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 74 | 1301779 | 0 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-10-20 | QTR2 | 25/26 | 2024-09-12 | QTR1 | 24/25 | 108 | 57230747.75 | Y | DESIGN/BUILD PROJECT | 0 | 101 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R87 | 20103255201 | 2020-11-20 | QTR2 | 20/21 | 3 | 19 | 1400 | 1699 | 1699 | 0 | 0 | 0 | 265 | 34 | 143923300 | 150000 | 143773300 | 144607218 | 144885088 | -40000 | 0 | -40000 | 144845088 | 145590108 | 12782288 | 683918 | 199 | 0 | 0 | 857947 | 17389 | 0 | 0 | 113457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1718413 | 0 | 0 | 0 | 24827 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 569484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5985 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | -192910 | 17389 | F843374080 | AJAX-LEWARE JV | N/A | N/A | N/A | N/A | 2026-01-23 | QTR3 | 25/26 | 2025-10-25 | QTR2 | 25/26 | 106 | 132713200.45 | B11:B7:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - A+B/BONUS:ACC - DESIGN/BUILD - MAJOR | 0 | 100 | 0 | 0 | -46196 | 0 |  | DO
01DO | 01 | E1V08 | 19602265201 | 2023-11-02 | QTR2 | 23/24 | 2 | 3 | 350 | 424 | 375 | 49 | 0 | 0 | 74 | 0 | 6226258 | 61298 | 6164960 | 6296806 | 6274547 | 0 | 0 | 0 | 6274547 | 6215664 | -10506 | 70548 | 51 | 0 | 0 | 45061 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48763 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 | 2025-05-16 | QTR4 | 24/25 | 115 | 7418503.78 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V09 | 44743215201 | 2024-02-15 | QTR3 | 23/24 | 2 | 0 | 190 | 250 | 249 | 1 | 0 | 0 | 60 | 0 | 3665572 | 50000 | 3615572 | 3665572 | 3704260 | 0 | 0 | 0 | 3704260 | 3693129 | -11132 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 12979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 11006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24749 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 | 2025-08-07 | QTR1 | 25/26 | 108 | 4198565.92 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V10 | 44155015201 | 2023-02-16 | QTR3 | 22/23 | 1 | 5 | 300 | 551 | 561 | -10 | 10 | 0 | 205 | 46 | 14609258 | 150000 | 14459258 | 14044029 | 14088333 | -3245 | 0 | -3245 | 14085087 | 13929541 | -126080 | -565229 | 188 | 0 | 0 | -627778 | 0 | 0 | 21 | 85849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -541929 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-19 | QTR1 | 25/26 | 2025-04-18 | QTR4 | 24/25 | 115 | 14926349.94 |  |  | 21 | 42 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V13 | 44893915201 | 2024-09-19 | QTR1 | 24/25 | 1 | 1 | 150 | 195 | 194 | 1 | 0 | 0 | 45 | 0 | 5289078 | 65023 | 5224055 | 5392842 | 5545592 | 0 | 0 | 0 | 5545592 | 5545735 | 143 | 103763 | 8 | 0 | 0 | 103763 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 103763 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-25 | QTR1 | 25/26 | 2025-06-07 | QTR4 | 24/25 | 118 | 5760651.93 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V22 | 44620615201 | 2023-07-20 | QTR1 | 23/24 | 1 | 3 | 180 | 227 | 220 | 7 | 0 | 0 | 47 | 0 | 5142423 | 50000 | 5092423 | 5047658 | 5138834 | 0 | 0 | 0 | 5138834 | 5099867 | -1029 | -94765 | 25 | 0 | 0 | 44761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -87943 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-03-05 | QTR3 | 24/25 | 118 | 4496918.22 |  |  | 0 | 22 | 0 | 0 | -132703 | 0 |  | DO
01DO | 01 | E1V23 | 44743415201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 225 | 278 | 278 | 0 | 0 | 0 | 53 | 0 | 5558710 | 57494 | 5501216 | 5552034 | 5723019 | 0 | 0 | 0 | 5723019 | 5723218 | 199 | -6676 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | -6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4873 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-01 | QTR1 | 25/26 | 2024-10-23 | QTR2 | 24/25 | 108 | 5765208.01 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V51 | 44743715201 | 2022-08-02 | QTR1 | 22/23 | 3 | 3 | 650 | 763 | 763 | 0 | 0 | 0 | 113 | 0 | 23141400 | 150000 | 22991400 | 23931467 | 24545579 | 0 | 0 | 0 | 24545579 | 24060306 | -480611 | 790067 | 61 | 0 | 0 | 53994 | 0 | 0 | 0 | 770405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824400 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-21 | QTR1 | 25/26 | 2024-11-12 | QTR2 | 24/25 | 108 | 26691037.4 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 52 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V60 | 44901515201 | 2023-06-06 | QTR4 | 22/23 | 1 | 4 | 975 | 1035 | 559 | 476 | 0 | 0 | 60 | 0 | 24655000 | 150000 | 24505000 | 24840707 | 24676932 | 0 | 941500 | 941500 | 25618432 | 24522979 | -950274 | 185707 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 40527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51851 | 0 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 | 2025-02-18 | QTR3 | 24/25 | 113 | 27242569.81 | B2:B5:Y | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:DESIGN/BUILD PROJECT | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W13 | 44594215201 | 2024-02-15 | QTR3 | 23/24 | 1 | 10 | 200 | 292 | 317 | -25 | 25 | 0 | 66 | 26 | 2428636 | 0 | 2428636 | 2626766 | 2708707 | -66250 | 0 | -66250 | 2642457 | 2624968 | -22 | 198130 | 44 | 0 | 26 | 115608 | 0 | 0 | 0 | 65054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 180662 | 0 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 | 2025-04-22 | QTR4 | 24/25 | 115 | 3681296.02 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W16 | 44738015201 | 2023-09-21 | QTR1 | 23/24 | 1 | 5 | 200 | 302 | 296 | 6 | 0 | 0 | 58 | 44 | 2844972 | 50000 | 2794972 | 2870813 | 2826404 | 0 | 0 | 0 | 2826404 | 2806626 | -7691 | 25841 | 81 | 0 | 0 | 8709 | 0 | 0 | 0 | 5045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13754 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2026-03-18 | QTR3 | 25/26 | 2025-01-21 | QTR3 | 24/25 | 115 | 2548367.85 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W18 | 44743115201 | 2024-04-18 | QTR4 | 23/24 | 1 | 1 | 170 | 195 | 171 | 24 | 0 | 0 | 25 | 0 | 2506911 | 50000 | 2456911 | 2530764 | 2550717 | 0 | 0 | 0 | 2550717 | 2546483 | -4233 | 23853 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 | 2025-04-30 | QTR4 | 24/25 | 108 | 2727222.68 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W50 | 45279215201 | 2024-03-26 | QTR3 | 23/24 | 1 | 0 | 450 | 511 | 495 | 16 | 0 | 0 | 57 | 4 | 2283584 | 50000 | 2233584 | 2283584 | 2253806 | 0 | 0 | 0 | 2253806 | 2253543 | -264 | 0 | 24 | 0 | 4 | 25861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25861 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 | 2025-09-29 | QTR1 | 25/26 | 118 | 2780605.35 | Y | DESIGN/BUILD PROJECT | 4 | 33 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W75 | 44923315201 | 2024-07-18 | QTR1 | 24/25 | 1 | 0 | 115 | 150 | 150 | 0 | 0 | 0 | 35 | 0 | 2560003 | 50000 | 2510003 | 2560003 | 2586788 | 0 | 0 | 0 | 2586788 | 2586788 | 0 | 0 | 32 | 0 | 0 | 29053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29053 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 | 2025-06-04 | QTR4 | 24/25 | 108 | 3481659.24 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W76 | 44897215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 0 | 140 | 166 | 150 | 16 | 0 | 0 | 26 | 0 | 3352588 | 50000 | 3302588 | 3352588 | 3378389 | 0 | 0 | 0 | 3378389 | 3377632 | -757 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 | 2025-04-10 | QTR4 | 24/25 | 118 | 4285958.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W78 | 44927215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 1 | 100 | 127 | 110 | 17 | 0 | 0 | 27 | 0 | 1562427 | 50000 | 1512427 | 1562023 | 1597413 | 0 | 0 | 0 | 1597413 | 1597413 | 0 | -404 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 | 2025-03-11 | QTR3 | 24/25 | 108 | 1884401.65 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W79 | 44023015201 | 2024-09-19 | QTR1 | 24/25 | 1 | 2 | 140 | 150 | 124 | 26 | 0 | 0 | 10 | 0 | 1118465 | 40273 | 1078192 | 1118465 | 854089 | 0 | 0 | 0 | 854089 | 854089 | -1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-09-11 | QTR1 | 25/26 | 2025-08-11 | QTR1 | 25/26 | 118 | 991704.32 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W85 | 44893115201 | 2024-11-07 | QTR2 | 24/25 | 2 | 3 | 150 | 180 | 160 | 20 | 0 | 0 | 30 | 0 | 4458291 | 54289 | 4404002 | 4710660 | 4720609 | 0 | 0 | 0 | 4720609 | 4719730 | -879 | 252368 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-09-04 | QTR1 | 25/26 | 113 | 5001199.26 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W94 | 44917815201 | 2025-02-20 | QTR3 | 24/25 | 1 | 0 | 80 | 147 | 156 | -9 | 9 | 0 | 37 | 30 | 830702 | 40500 | 790202 | 830702 | 826937 | -15165 | 0 | -15165 | 811772 | 811772 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 30 | 17515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 17515 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-01-30 | QTR3 | 25/26 | 2025-12-10 | QTR2 | 25/26 | 108 | 1048586.14 |  |  | 30 | 8 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1X68 | 44895715201 | 2025-07-17 | QTR1 | 25/26 | 1 | 0 | 100 | 121 | 115 | 6 | 0 | 0 | 21 | 0 | 2063849 | 50000 | 2013849 | 2063849 | 1971937 | 0 | 0 | 0 | 1971937 | 1971937 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8496 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 | 2026-02-10 | QTR3 | 25/26 | 113 | 2136352.43 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2591 | 42886515201 | 2015-10-14 | QTR2 | 15/16 | 5 | 58 | 1200 | 3229 | 3229 | 0 | 0 | 0 | 905 | 1124 | 65973116 | 149995 | 65823121 | 108070596 | 111419612 | 0 | 0 | 0 | 111419612 | 112415734 | 1746230 | 42097480 | 322 | 133 | 66 | 1773148 | 375907 | 118 | 671 | 33362908 | 7141422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 335 | 4964601 | 3035499 | 0 | 0 | 325801 | 0 | 0 | 0 | 0 | 0 | 117 | 0 | 343725 | 2306 | 0 | 0 | 1388728 | 620012 | 0 | 52 | 1119347 | 685768 | 0 | 0 | 0 | 0 | 436 | 1124 | 42138723 | 11860914 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-03-23 | QTR3 | 25/26 | 2024-12-31 | QTR2 | 24/25 | 208 | 76779378.1 |  |  | 7 | 264 | 0 | 0 | -1139535 | 0 |  | CO
02CO | 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 329791 | 87098 | 104 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2790 | 43616815201 | 2021-01-27 | QTR3 | 20/21 | 1 | 4 | 730 | 1441 | 1441 | 0 | 0 | 0 | 711 | 0 | 15444874 | 116066 | 15328808 | 18490817 | 18458945 | 0 | 0 | 0 | 18458945 | 18501533 | 251365 | 3045943 | 306 | 0 | 0 | 677453 | 0 | 0 | 0 | 61510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1981123 | 14607 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 2720087 | 14607 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2025-12-05 | QTR2 | 25/26 | 2025-05-07 | QTR4 | 24/25 | 216 | 11733776.57 |  |  | 0 | 279 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2839 | 44342115201 | 2022-02-09 | QTR3 | 21/22 | 3 | 0 | 480 | 785 | 783 | 2 | 0 | 0 | 185 | 120 | 31969186 | 150000 | 31819186 | 31969186 | 32489212 | 0 | 0 | 0 | 32489212 | 33982240 | 1493028 | 0 | 244 | 0 | 2 | 18542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 120 | 18542 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-14 | QTR1 | 25/26 | 2024-06-14 | QTR4 | 23/24 | 209 | 35449756.12 |  |  | 120 | 59 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2844 | 43935615201 | 2022-06-15 | QTR4 | 21/22 | 3 | 6 | 479 | 915 | 913 | 2 | 0 | 0 | 311 | 125 | 19892956 | 180993 | 19711963 | 20310363 | 20717832 | 0 | 0 | 0 | 20717832 | 20350044 | -345380 | 417407 | 191 | 50 | 92 | 143934 | 0 | 0 | 15 | 291019 | 3470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681 | 0 | 0 | 18 | 42558 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 125 | 516682 | 3470 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-07-16 | QTR1 | 25/26 | 208 | 16227519.23 |  |  | 113 | 70 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2854 | 44554515201 | 2022-06-08 | QTR4 | 21/22 | 2 | 1 | 210 | 817 | 817 | 0 | 0 | 0 | 355 | 252 | 10095026 | 91284 | 10003741 | 10267526 | 10526210 | 0 | 0 | 0 | 10526210 | 10195263 | -330946 | 172500 | 390 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 110 | 172500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 252 | 172500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-04-18 | QTR4 | 24/25 | 209 | 10655889.17 |  |  | 232 | 55 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2863 | 43744115201 | 2022-01-12 | QTR3 | 21/22 | 3 | 6 | 550 | 1127 | 1125 | 2 | 0 | 0 | 161 | 416 | 14032373 | 165047 | 13867326 | 15901285 | 16261074 | 0 | 0 | 0 | 16261074 | 16278606 | 24575 | 1868912 | 57 | 0 | 416 | 1783542 | 0 | 0 | 0 | 59192 | 4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20176 | 0 | 0 | 0 | 38915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 1906703 | 4208 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 208 | 15021660.86 |  |  | 120 | 104 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2865 | 44351715201 | 2022-11-16 | QTR2 | 22/23 | 1 | 6 | 400 | 682 | 681 | 1 | 0 | 0 | 162 | 120 | 7663000 | 71865 | 7591135 | 8470199 | 9163770 | 0 | 0 | 0 | 9163770 | 9149657 | -14114 | 807199 | 68 | 45 | 91 | 723003 | 0 | 0 | 29 | 122914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 120 | 871252 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 | 2025-04-15 | QTR4 | 24/25 | 208 | 7014633.18 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2889 | 43575615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 5 | 280 | 638 | 638 | 0 | 0 | 0 | 199 | 159 | 3832776 | 50000 | 3782776 | 4315395 | 4383212 | 0 | 0 | 0 | 4383212 | 4383212 | 0 | 482619 | 107 | 0 | 24 | 38374 | 0 | 0 | 135 | 462409 | 134882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 500784 | 134882 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 | 2025-06-06 | QTR4 | 24/25 | 208 | 4521037.25 |  |  | 24 | 92 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2890 | 44554715201 | 2022-10-26 | QTR2 | 22/23 | 3 | 3 | 350 | 924 | 924 | 0 | 0 | 0 | 261 | 313 | 25595410 | 150000 | 25445410 | 25761158 | 26450421 | 0 | 0 | 0 | 26450421 | 25953030 | -497390 | 165747 | 280 | 0 | 213 | 120000 | 0 | 0 | 2 | 33247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 57500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 270747 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 | 2025-09-17 | QTR1 | 25/26 | 209 | 25708227.9 |  |  | 303 | 71 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2894 | 44540215201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 575 | 575 | 0 | 0 | 0 | 196 | 139 | 12471547 | 114486 | 12357061 | 12747539 | 13553931 | 0 | 0 | 0 | 13553931 | 13363147 | -190784 | 275992 | 290 | 0 | 57 | 256470 | 0 | 0 | 2 | 107104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 139 | 363574 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 | 2024-09-11 | QTR1 | 24/25 | 209 | 11980864.41 |  |  | 137 | 29 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2910 | 44535215201 | 2023-06-14 | QTR4 | 22/23 | 3 | 5 | 330 | 543 | 543 | 0 | 0 | 0 | 153 | 60 | 5895675 | 59623 | 5836052 | 5981679 | 6100547 | 0 | 0 | 0 | 6100547 | 6061260 | -3283 | 86004 | 101 | 0 | 20 | 48625 | 0 | 0 | 40 | 55572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 104197 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 | 2025-05-29 | QTR4 | 24/25 | 208 | 6680440.38 |  |  | 60 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2913 | 44707815201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 150 | 420 | 412 | 8 | 0 | 0 | 102 | 168 | 4420617 | 50000 | 4370617 | 4518180 | 4416217 | 0 | 0 | 0 | 4416217 | 4412247 | -3971 | 97563 | 72 | 0 | 30 | 0 | 0 | 0 | 138 | 97563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 97563 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 | 2025-06-23 | QTR4 | 24/25 | 209 | 4807508.45 |  |  | 75 | 30 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2915 | 44718015201 | 2023-03-29 | QTR3 | 22/23 | 1 | 1 | 300 | 660 | 659 | 1 | 0 | 0 | 346 | 14 | 11703806 | 89802 | 11614004 | 11742594 | 12389230 | 0 | 0 | 0 | 12389230 | 12372017 | -17213 | 38788 | 301 | 0 | 14 | 14951 | 0 | 0 | 0 | 38788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14 | 53739 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-20 | QTR2 | 25/26 | 2025-06-26 | QTR4 | 24/25 | 208 | 10416036.13 |  |  | 14 | 45 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2916 | 43993715201 | 2023-04-26 | QTR4 | 22/23 | 2 | 0 | 425 | 610 | 605 | 5 | 0 | 0 | 185 | 0 | 10398707 | 246 | 10398461 | 10398707 | 10268067 | 0 | 0 | 0 | 10268067 | 10264507 | -3560 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 | 2025-03-17 | QTR3 | 24/25 | 209 | 8834993.85 |  |  | 0 | 48 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2917 | 44330415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 2 | 330 | 604 | 604 | 0 | 0 | 0 | 174 | 100 | 23947969 | 150000 | 23797969 | 24055659 | 25032603 | 0 | 0 | 0 | 25032603 | 25026994 | -5609 | 107690 | 101 | 0 | 66 | 177659 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 180877 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 | 2025-06-25 | QTR4 | 24/25 | 208 | 21934859.67 |  |  | 100 | 73 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2924 | 20930185201 | 2023-04-26 | QTR4 | 22/23 | 1 | 2 | 300 | 751 | 751 | 0 | 0 | 0 | 250 | 201 | 19358596 | 150000 | 19208596 | 19523393 | 20332171 | 0 | 0 | 0 | 20332171 | 20313549 | -18621 | 164797 | 300 | 0 | 0 | 49110 | 0 | 27 | 51 | 133896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17832 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 9270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 201 | 210108 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-02-20 | QTR3 | 25/26 | 2025-10-27 | QTR2 | 25/26 | 208 | 19142187.33 |  |  | 165 | 68 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2934 | 44331015201 | 2022-12-07 | QTR2 | 22/23 | 2 | 5 | 450 | 714 | 711 | 3 | 0 | 0 | 264 | 0 | 26057502 | 150000 | 25907502 | 26443445 | 27980036 | 0 | 0 | 0 | 27980036 | 27874372 | -105664 | 385943 | 91 | 86 | 0 | 261787 | 11998 | 21 | 0 | 157751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 462296 | 11998 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 | 2025-03-13 | QTR3 | 24/25 | 208 | 24163399.99 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2945 | 44542715201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 300 | 503 | 501 | 2 | 0 | 0 | 113 | 90 | 6853255 | 73995 | 6779259 | 6853255 | 6989283 | 0 | 0 | 0 | 6989283 | 6981891 | -7392 | 0 | 72 | 0 | 10 | 13022 | 0 | 0 | 20 | 29941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 46335 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 | 2025-08-12 | QTR1 | 25/26 | 208 | 7614578.02 |  |  | 90 | 41 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2948 | 44712315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 300 | 431 | 414 | 17 | 0 | 0 | 71 | 60 | 5794236 | 50808 | 5743428 | 5794236 | 5977965 | 0 | 0 | 0 | 5977965 | 5956561 | -21404 | 0 | 93 | 0 | 0 | 14179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14179 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-12 | QTR2 | 25/26 | 2025-07-10 | QTR1 | 25/26 | 208 | 5749684.61 |  |  | 60 | 38 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2949 | 20969745201 | 2023-11-15 | QTR2 | 23/24 | 1 | 2 | 270 | 360 | 323 | 37 | 0 | 0 | 73 | 17 | 1865813 | 50000 | 1815813 | 1939049 | 1961474 | 0 | 0 | 0 | 1961474 | 1960364 | -1110 | 73235 | 44 | 0 | 16 | 39150 | 0 | 0 | 1 | 39471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 78621 | 0 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2025-11-07 | QTR2 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 208 | 2230663.64 |  |  | 1 | 29 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2954 | 44542015201 | 2023-12-06 | QTR2 | 23/24 | 2 | 0 | 270 | 373 | 372 | 1 | 0 | 0 | 103 | 0 | 3819110 | 50000 | 3769110 | 3819110 | 3735111 | 0 | 0 | 0 | 3735111 | 3733457 | -1654 | 0 | 67 | 0 | 0 | 702 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 208 | 5040191.6 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2961 | 43633015201 | 2023-12-06 | QTR2 | 23/24 | 3 | 3 | 400 | 450 | 393 | 57 | 0 | 0 | 50 | 0 | 3521000 | 246 | 3520754 | 3558326 | 3560864 | 0 | 0 | 0 | 3560864 | 3553846 | -957 | 37326 | 19 | 7 | 0 | 31265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 31265 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-03-19 | QTR3 | 24/25 | 209 | 3765540.75 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2962 | 44796215201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 180 | 370 | 370 | 0 | 0 | 0 | 160 | 30 | 7958218 | 85629 | 7872589 | 7958218 | 7882304 | 0 | 0 | 0 | 7882304 | 7877534 | -4770 | 0 | 79 | 0 | 30 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 30 | 1672 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 | 2025-08-06 | QTR1 | 25/26 | 214 | 8827613.66 |  |  | 30 | 56 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2966 | 21086555201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 120 | 236 | 232 | 4 | 0 | 0 | 56 | 60 | 2921783 | 50000 | 2871783 | 2921783 | 2938946 | 0 | 0 | 0 | 2938946 | 2938946 | 0 | 0 | 34 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 | 2025-04-14 | QTR4 | 24/25 | 209 | 3224885.25 |  |  | 60 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2969 | 44703615201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 300 | 408 | 406 | 2 | 0 | 0 | 50 | 58 | 10923210 | 112286 | 10810924 | 10892472 | 11424138 | 0 | 0 | 0 | 11424138 | 11378255 | -45883 | -30738 | 23 | 0 | 0 | 0 | 0 | 0 | 28 | 69752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 58 | 39014 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-24 | QTR2 | 25/26 | 2025-08-18 | QTR1 | 25/26 | 214 | 10802904.04 |  |  | 58 | 27 | 0 | 0 | -30738 | 0 |  | CO
02CO | 02 | T2970 | 44712815201 | 2024-02-28 | QTR3 | 23/24 | 3 | 5 | 180 | 392 | 392 | 0 | 0 | 0 | 140 | 72 | 6497196 | 70342 | 6426853 | 6705393 | 7314719 | 0 | 0 | 0 | 7314719 | 7267283 | -20654 | 208197 | 91 | 0 | 72 | 171277 | 99710 | 0 | 0 | 19849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 187461 | 99710 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 | 2025-09-24 | QTR1 | 25/26 | 208 | 6729211.88 |  |  | 2 | 49 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2974 | 44720415201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 300 | 461 | 461 | 0 | 0 | 0 | 155 | 6 | 18339896 | 150000 | 18189896 | 18339896 | 18394467 | 0 | 0 | 0 | 18394467 | 18347088 | -47379 | 0 | 113 | 0 | 3 | 40787 | 0 | 0 | 3 | 5308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 6 | 46094 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 | 2025-10-11 | QTR2 | 25/26 | 214 | 19102224.25 |  |  | 6 | 42 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2976 | 44755715201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 360 | 428 | 296 | 132 | 0 | 0 | 66 | 2 | 25893810 | 150000 | 25743810 | 26291007 | 27924429 | 0 | 0 | 0 | 27924429 | 27880284 | -44146 | 397198 | 39 | 0 | 0 | 417380 | 0 | 0 | 2 | 20401 | 3792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 437781 | 3792 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-21 | QTR2 | 25/26 | 2025-02-10 | QTR3 | 24/25 | 208 | 21206563.14 |  |  | 2 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2981 | 45220125201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 275 | 345 | 286 | 59 | 0 | 0 | 70 | 0 | 2914229 | 50000 | 2864229 | 2914229 | 2917184 | 0 | 0 | 0 | 2917184 | 2917184 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 | 2025-02-13 | QTR3 | 24/25 | 214 | 4244875.9 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2985 | 43761415201 | 2023-11-15 | QTR2 | 23/24 | 1 | 0 | 270 | 405 | 405 | 0 | 0 | 0 | 119 | 16 | 7308506 | 69947 | 7238559 | 7308506 | 7304574 | 0 | 0 | 0 | 7304574 | 7285470 | -19104 | 0 | 59 | 0 | 2 | 31262 | 0 | 0 | 14 | 18461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 16 | 49723 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 | 2025-05-02 | QTR4 | 24/25 | 208 | 8026688.02 |  |  | 16 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2988 | 44721135201 | 2024-04-24 | QTR4 | 23/24 | 1 | 1 | 180 | 225 | 95 | 130 | 0 | 0 | 45 | 0 | 1562105 | 50000 | 1512105 | 1737694 | 1710662 | 0 | 0 | 0 | 1710662 | 1710435 | -227 | 175589 | 41 | 0 | 0 | 175589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175589 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 | 2024-10-17 | QTR2 | 24/25 | 208 | 1572771.91 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2997 | 44984425201 | 2024-09-25 | QTR1 | 24/25 | 1 | 2 | 180 | 214 | 214 | 0 | 0 | 0 | 34 | 0 | 2499454 | 50000 | 2449454 | 2573884 | 2437559 | 0 | 0 | 0 | 2437559 | 2436488 | -1071 | 74430 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 24430 | 24430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61993 | 24430 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 | 2025-08-07 | QTR1 | 25/26 | 214 | 2231402.67 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A02 | 43431825201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 180 | 188 | 171 | 17 | 0 | 0 | 8 | 0 | 7419960 | 87264 | 7332696 | 7419960 | 7285721 | 0 | 0 | 0 | 7285721 | 7282630 | -3091 | 0 | 4 | 0 | 0 | 46438 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61171 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 214 | 8775588.25 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A05 | 20944145201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 150 | 194 | 192 | 2 | 0 | 0 | 41 | 3 | 2487602 | 50000 | 2437602 | 2535510 | 2431426 | 0 | 0 | 0 | 2431426 | 2431081 | -345 | 47909 | 17 | 0 | 3 | 47909 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 49559 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2026-02-27 | QTR3 | 25/26 | 2025-11-24 | QTR2 | 25/26 | 208 | 3542854 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A06 | 21003025201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 300 | 343 | 305 | 38 | 0 | 0 | 43 | 0 | 6571980 | 67485 | 6504495 | 6571980 | 6862070 | 0 | 0 | 0 | 6862070 | 6863371 | 1301 | 0 | 17 | 0 | 0 | 13750 | 0 | 0 | 0 | 15770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29520 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-11 | QTR3 | 25/26 | 2026-01-08 | QTR3 | 25/26 | 216 | 6362364.64 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A09 | 21022385201 | 2024-12-04 | QTR2 | 24/25 | 1 | 0 | 180 | 234 | 233 | 1 | 0 | 0 | 44 | 10 | 4685902 | 61983 | 4623919 | 4685902 | 4940814 | 0 | 0 | 0 | 4940814 | 4942704 | 1890 | 0 | 24 | 0 | 10 | 9787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9787 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 | 2026-01-16 | QTR3 | 25/26 | 216 | 5665701.92 |  |  | 10 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A12 | 21071155201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 120 | 214 | 212 | 2 | 0 | 0 | 85 | 9 | 4071019 | 50000 | 4021019 | 4106006 | 4039787 | 0 | 0 | 0 | 4039787 | 4039787 | 0 | 34986 | 61 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 | 2025-06-24 | QTR4 | 24/25 | 208 | 4204426.35 |  |  | 3 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9037 | 44627925214 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 300 | 323 | 260 | 63 | 0 | 0 | 23 | 0 | 755793 | 0 | 755793 | 799963 | 782324 | 0 | 0 | 0 | 782324 | 782311 | -13 | 44170 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 | 2025-06-30 | QTR4 | 24/25 | 216 | 588437.99 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9039 | 44532025214 | 2024-05-22 | QTR4 | 23/24 | 1 | 2 | 400 | 433 | 375 | 58 | 0 | 0 | 33 | 0 | 2629396 | 0 | 2629396 | 2652851 | 2657516 | 0 | 0 | 0 | 2657516 | 2657516 | 0 | 23454 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 23454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23454 | 0 | F593399145 | E. B. MORRIS GENERAL CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2026-02-03 | QTR3 | 25/26 | 2025-12-01 | QTR2 | 25/26 | 208 | 2484683.43 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9041 | 44628015215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 45 | 48 | 47 | 1 | 0 | 0 | 3 | 0 | 211688 | 9600 | 202088 | 211688 | 200166 | 0 | 0 | 0 | 200166 | 200166 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 | 2025-02-21 | QTR3 | 24/25 | 208 | 233429.76 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9044 | 44628025216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 120 | 126 | 92 | 34 | 0 | 0 | 6 | 0 | 393754 | 22100 | 371654 | 393754 | 371540 | 0 | 0 | 0 | 371540 | 371540 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 | 2025-10-23 | QTR2 | 25/26 | 208 | 505500 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E200W | 44572615201 | 2024-04-17 | QTR4 | 23/24 | 1 | 0 | 180 | 256 | 256 | 0 | 0 | 0 | 51 | 25 | 2930266 | 50000 | 2880266 | 2930266 | 2970891 | 0 | 0 | 0 | 2970891 | 2968577 | -2313 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17954 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18944 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 | 2025-06-29 | QTR4 | 24/25 | 209 | 2593407.4 |  |  | 25 | 23 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20S2 | 21054545201 | 2022-06-01 | QTR4 | 21/22 | 1 | 0 | 609 | 992 | 992 | 0 | 0 | 0 | 123 | 260 | 8601469 | 80882 | 8520588 | 8601469 | 8734394 | 0 | 0 | 0 | 8734394 | 8453915 | -280479 | 0 | 136 | 0 | 90 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 | 2025-05-02 | QTR4 | 24/25 | 209 | 8397276.42 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 260 | 77 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20T6 | 44278015201 | 2023-02-15 | QTR3 | 22/23 | 1 | 2 | 280 | 645 | 645 | 0 | 0 | 0 | 119 | 246 | 1676236 | 50000 | 1626236 | 1744958 | 1814629 | 0 | 0 | 0 | 1814629 | 1814629 | 0 | 68722 | 137 | 0 | 2 | 81415 | 0 | 0 | 141 | 31490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 112905 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 | 2025-07-07 | QTR1 | 25/26 | 208 | 2494427.5 |  |  | 246 | 85 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20X8 | 20840265201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 550 | 717 | 717 | 0 | 0 | 0 | 167 | 0 | 9409691 | 88302 | 9321389 | 9409691 | 9709502 | 0 | 0 | 0 | 9709502 | 9670685 | -38817 | 0 | 27 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 | 2025-05-22 | QTR4 | 24/25 | 209 | 8868810.45 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20X9 | 44707615201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 490 | 785 | 780 | 5 | 0 | 0 | 205 | 90 | 11213775 | 111419 | 11102356 | 11213775 | 11321495 | 0 | 0 | 0 | 11321495 | 11257290 | -64205 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 180 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 209 | 11190658.02 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 90 | 66 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z53 | 43035245201 | 2020-02-20 | QTR3 | 19/20 | 2 | 15 | 830 | 1569 | 1562 | 7 | 0 | 0 | 739 | 0 | 17677113 | 139633 | 17537480 | 32771107 | 33213700 | 0 | 0 | 0 | 33213700 | 33587618 | 498724 | 15093994 | 241 | 29 | 0 | 182603 | 0 | 56 | 0 | 402438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 14608377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 15230057 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 | 2025-03-17 | QTR3 | 24/25 | 214 | 14339167 |  |  | 0 | 106 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3618 | 21790935201 | 2020-05-20 | QTR4 | 19/20 | 1 | 25 | 1000 | 1915 | 1912 | 3 | 0 | 0 | 401 | 514 | 27170428 | 150000 | 27020428 | 30592621 | 31419600 | 0 | 0 | 0 | 31419600 | 32973116 | 1578565 | 3422193 | 242 | 0 | 106 | 96310 | 0 | 33 | 171 | 1524911 | 17782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 1824610 | 66674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 77645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 514 | 3523475 | 84456 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 | 2025-10-31 | QTR2 | 25/26 | 313 | 35258008.48 |  |  | 83 | 126 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3705 | 43581615201 | 2021-06-09 | QTR4 | 20/21 | 3 | 7 | 1150 | 1341 | 1299 | 42 | 0 | 0 | 191 | 0 | 21786584 | 150000 | 21636584 | 24287618 | 24447463 | 0 | 0 | 0 | 24447463 | 24458859 | 417101 | 2501033 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 1856044 | 1818253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2538824 | 1818253 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2025-07-24 | QTR1 | 25/26 | 308 | 31799900.02 |  |  | 0 | 80 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3722 | 41098185201 | 2022-06-15 | QTR4 | 21/22 | 1 | 6 | 600 | 878 | 1063 | -185 | 185 | 0 | 197 | 81 | 16220760 | 150000 | 16070760 | 16260965 | 16485438 | -1083175 | 0 | -1083175 | 15402263 | 16125524 | 723261 | 40205 | 122 | 0 | 81 | -39105 | 0 | 16 | 0 | 102671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81 | 77715 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 | 2025-10-24 | QTR2 | 25/26 | 314 | 24461056.7 |  |  | 30 | 59 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 2 | 365 | 689 | 689 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6169465 | 6682488 | 0 | 0 | 0 | 6682488 | 7794860 | 1176465 | 3017 | 170 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 100 | 21 | 70800 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-26 | QTR3 | 25/26 | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29 |  |  | 21 | 89 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3789 | 43813315201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 50 | 230 | 226 | 4 | 0 | 0 | 142 | 38 | 383899 | 19912 | 363987 | 397919 | 393163 | -35910 | 0 | -35910 | 357253 | 329110 | -28143 | 14020 | 115 | 0 | 0 | 0 | 0 | 0 | 38 | 14020 | 917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 38 | 14020 | 917 | F473361483 | T & T CIVIL CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2026-03-26 | QTR3 | 25/26 | 2023-01-27 | QTR3 | 22/23 | 314 | 424157.75 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3790 | 43748915201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 255 | 343 | 339 | 4 | 0 | 0 | 88 | 0 | 3547402 | 0 | 3547402 | 3547402 | 3587891 | 0 | 0 | 0 | 3587891 | 3586665 | -1225 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 | 2025-06-16 | QTR4 | 24/25 | 313 | 4578761.95 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3804 | 42697315201 | 2022-04-27 | QTR4 | 21/22 | 2 | 4 | 200 | 679 | 679 | 0 | 0 | 0 | 404 | 75 | 6212045 | 50000 | 6162045 | 6299150 | 6924822 | 0 | 0 | 0 | 6924822 | 6889613 | -35209 | 87105 | 260 | 161 | 0 | 0 | 0 | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 87105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 75 | 87105 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 | 2024-12-17 | QTR2 | 24/25 | 313 | 5759918.26 |  |  | 45 | 64 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3835 | 44563315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 2 | 435 | 712 | 712 | 0 | 0 | 0 | 265 | 12 | 10919335 | 105921 | 10813414 | 11003378 | 11511158 | 0 | 0 | 0 | 11511158 | 11473007 | -38151 | 84043 | 130 | 10 | 0 | 22048 | 0 | 52 | 12 | 94616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 12 | 116664 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 | 2025-09-08 | QTR1 | 25/26 | 314 | 11459373.75 |  |  | 0 | 73 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3837 | 22259365201 | 2022-12-07 | QTR2 | 22/23 | 2 | 3 | 425 | 608 | 608 | 0 | 0 | 0 | 146 | 37 | 11772258 | 136099 | 11636159 | 11871253 | 11834603 | 0 | 0 | 0 | 11834603 | 11821261 | -13342 | 98995 | 72 | 0 | 3 | 2170 | 0 | 4 | 12 | 33069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 130287 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37 | 165526 | 579 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-16 | QTR1 | 25/26 | 2025-02-07 | QTR3 | 24/25 | 321 | 13447557.24 |  |  | 20 | 70 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3843 | 43736615201 | 2023-02-22 | QTR3 | 22/23 | 3 | 3 | 450 | 880 | 880 | 0 | 0 | 0 | 397 | 33 | 14976878 | 150000 | 14826878 | 15770067 | 16545874 | 0 | 0 | 0 | 16545874 | 16474250 | -71624 | 793189 | 199 | 0 | 17 | 182706 | 0 | 90 | 14 | 676082 | 8918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 2 | 8973 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 33 | 867761 | 8918 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 | 2025-09-30 | QTR1 | 25/26 | 308 | 17116856.14 |  |  | 17 | 105 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3844 | 44581515201 | 2023-04-26 | QTR4 | 22/23 | 2 | 1 | 325 | 796 | 793 | 3 | 0 | 0 | 471 | 0 | 16815829 | 150000 | 16665829 | 16829871 | 17633297 | 0 | 0 | 0 | 17633297 | 17609681 | -23615 | 14042 | 181 | 0 | 0 | 0 | 0 | 195 | 0 | 14042 | 11490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 14042 | 11490 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 | 2025-09-12 | QTR1 | 25/26 | 306 | 15773894.2 |  |  | 0 | 95 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3851 | 44292015201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 290 | 517 | 514 | 3 | 0 | 0 | 227 | 0 | 3185384 | 0 | 3185384 | 3188684 | 3129056 | 0 | 0 | 0 | 3129056 | 3127773 | -1283 | 3300 | 108 | 0 | 0 | 0 | 0 | 10 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 | 2025-10-16 | QTR2 | 25/26 | 306 | 3413369.7 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3855 | 44401915201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 140 | 482 | 482 | 0 | 0 | 0 | 342 | 0 | 958894 | 50000 | 908894 | 958894 | 885299 | 0 | 0 | 0 | 885299 | 885298 | -1 | 0 | 159 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 | 2025-05-27 | QTR4 | 24/25 | 308 | 1271778.2 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3862 | 43977415201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 220 | 395 | 370 | 25 | 0 | 0 | 105 | 70 | 3433760 | 50000 | 3383760 | 3478528 | 3538382 | 0 | 0 | 0 | 3538382 | 3534775 | -3607 | 44768 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 44768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 44768 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 | 2025-10-20 | QTR2 | 25/26 | 313 | 3773823.76 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3868 | 41344925201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 90 | 421 | 420 | 1 | 0 | 0 | 213 | 118 | 1298401 | 50000 | 1248401 | 1321412 | 1234071 | 0 | 0 | 0 | 1234071 | 1234071 | 0 | 23011 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-05-24 | QTR4 | 24/25 | 313 | 1300164.1 |  |  | 118 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3871 | 42695025201 | 2024-06-12 | QTR4 | 23/24 | 2 | 1 | 260 | 335 | 326 | 9 | 0 | 0 | 75 | 0 | 3111541 | 50000 | 3061541 | 2493770 | 2535278 | 0 | 0 | 0 | 2535278 | 2534712 | -566 | -617771 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -617771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -617771 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 | 2025-09-25 | QTR1 | 25/26 | 314 | 4093773.7 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3874 | 44188015201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 74 | 447 | 447 | 0 | 0 | 0 | 373 | 0 | 988409 | 46367 | 942042 | 988409 | 938135 | 0 | 0 | 0 | 938135 | 938135 | 0 | 0 | 262 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 314 | 990878.67 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3891 | 43467815201 | 2024-01-31 | QTR3 | 23/24 | 2 | 2 | 200 | 288 | 288 | 0 | 0 | 0 | 88 | 0 | 2823614 | 50000 | 2773614 | 2855298 | 2780904 | 0 | 0 | 0 | 2780904 | 2780236 | -668 | 31684 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-05-16 | QTR4 | 24/25 | 308 | 3805809.9 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3901 | 41342535201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 205 | 261 | 254 | 7 | 0 | 0 | 54 | 2 | 3608291 | 50000 | 3558291 | 3609941 | 3619668 | 0 | 0 | 0 | 3619668 | 3616057 | -3611 | 1650 | 29 | 0 | 0 | 0 | 0 | 0 | 2 | 1650 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19319 | 1500 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2025-07-28 | QTR1 | 25/26 | 321 | 3187529.04 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3913 | 21934625201 | 2024-08-28 | QTR1 | 24/25 | 2 | 1 | 165 | 248 | 221 | 27 | 0 | 0 | 83 | 0 | 2531784 | 50000 | 2481784 | 2570548 | 2574902 | 0 | 0 | 0 | 2574902 | 2573463 | -1439 | 38764 | 59 | 0 | 0 | 61379 | 16559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61379 | 16559 | F592990776 | AMERICAN SAND & X-CAVATION INC. DBA AMERICAN SAND & ASPHALT | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 | 2025-08-11 | QTR1 | 25/26 | 314 | 3011928.8 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9043 | 44628415215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 90 | 124 | 124 | 0 | 0 | 0 | 34 | 0 | 189979 | 10000 | 179979 | 189979 | 177334 | 0 | 0 | 0 | 177334 | 177334 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-05-09 | QTR4 | 24/25 | 308 | 237358.31 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9045 | 44628425216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 180 | 199 | 122 | 77 | 0 | 0 | 14 | 5 | 511934 | 22600 | 489334 | 511934 | 495348 | 0 | 0 | 0 | 495348 | 495348 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | F592320406 | BILL SMITH ELECTRIC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 | 2025-11-05 | QTR2 | 25/26 | 308 | 509928.23 |  |  | 5 | 4 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3U65 | 44188515201 | 2022-11-17 | QTR2 | 22/23 | 1 | 0 | 250 | 680 | 695 | -15 | 15 | 0 | 430 | 0 | 3672487 | 50000 | 3622487 | 3672487 | 3781493 | -38880 | 0 | -38880 | 3742613 | 3778340 | 35727 | 0 | 186 | 0 | 0 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 | 2025-05-01 | QTR4 | 24/25 | 308 | 3629576.67 |  |  | 0 | 92 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V54 | 44554115201 | 2023-02-09 | QTR3 | 22/23 | 3 | 4 | 310 | 751 | 749 | 2 | 0 | 0 | 275 | 169 | 9981474 | 90589 | 9890885 | 10203672 | 10678123 | 0 | 0 | 0 | 10678123 | 10639564 | -38559 | 222198 | 136 | 0 | 51 | 147417 | 0 | 77 | 3 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 44650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 169 | 219567 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 | 2025-05-27 | QTR4 | 24/25 | 314 | 10144016.25 |  |  | 33 | 62 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V77 | 40919375201 | 2023-10-12 | QTR2 | 23/24 | 1 | 0 | 333 | 516 | 511 | 5 | 0 | 0 | 183 | 0 | 3075367 | 50000 | 3025367 | 3075367 | 2907496 | 0 | 0 | 0 | 2907496 | 2907496 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-06-13 | QTR4 | 24/25 | 313 | 4067368.66 |  |  | 0 | 68 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V81 | 44563415201 | 2023-06-08 | QTR4 | 22/23 | 3 | 1 | 385 | 538 | 538 | 0 | 0 | 0 | 144 | 9 | 7280451 | 56951 | 7223500 | 7422322 | 7437743 | 0 | 0 | 0 | 7437743 | 7440600 | 2857 | 141871 | 76 | 0 | 5 | 141871 | 0 | 0 | 0 | 2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 0 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9 | 159630 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-03-03 | QTR3 | 24/25 | 321 | 6184892.36 |  |  | 4 | 52 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W01 | 44559115201 | 2022-09-08 | QTR1 | 22/23 | 2 | 6 | 365 | 866 | 968 | -102 | 102 | 0 | 443 | 58 | 7469384 | 92731 | 7376653 | 7480930 | 7424797 | -374814 | 0 | -374814 | 7049983 | 6812783 | -211775 | 11546 | 143 | 0 | 3 | 8874 | 0 | 198 | 12 | 18933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 38 | 42680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 53 | 47234 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 | 2025-09-10 | QTR1 | 25/26 | 308 | 9544565.57 |  |  | 53 | 107 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W12 | 44643355201 | 2024-08-08 | QTR1 | 24/25 | 2 | 1 | 170 | 220 | 220 | 0 | 0 | 0 | 16 | 34 | 2949285 | 50000 | 2899285 | 2625347 | 2604415 | 0 | 0 | 0 | 2604415 | 2604415 | 0 | -323937 | 5 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | -323937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | -323937 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-09-22 | QTR1 | 25/26 | 321 | 3480038 |  |  | 34 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W30 | 44759615201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 365 | 665 | 665 | 0 | 0 | 0 | 220 | 110 | 4167167 | 50000 | 4117167 | 4263313 | 3906647 | 0 | 0 | 0 | 3906647 | 3906647 | 0 | 96146 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 | 2025-10-29 | QTR2 | 25/26 | 306 | 4722891.55 |  |  | 0 | 82 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W31 | 44554215201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 385 | 696 | 694 | 2 | 0 | 0 | 311 | 0 | 12495664 | 115497 | 12380167 | 12574093 | 13184954 | 0 | 0 | 0 | 13184954 | 13181542 | -3412 | 78429 | 133 | 8 | 0 | 78429 | 78429 | 30 | 0 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 85479 | 78429 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 | 2025-10-24 | QTR2 | 25/26 | 314 | 11633200.16 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W40 | 44374425201 | 2023-05-11 | QTR4 | 22/23 | 2 | 1 | 240 | 529 | 547 | -18 | 18 | 0 | 286 | 3 | 6286877 | 58278 | 6228599 | 6497112 | 6613095 | -68148 | 0 | -68148 | 6544947 | 6545243 | 297 | 210235 | 157 | 0 | 1 | 7085 | 0 | 45 | 2 | 211204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 3 | 218289 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-05-01 | QTR4 | 24/25 | 308 | 5983264.86 |  |  | 1 | 84 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W42 | 44559015201 | 2023-05-11 | QTR4 | 22/23 | 1 | 1 | 195 | 345 | 394 | -49 | 49 | 0 | 147 | 3 | 6987787 | 100654 | 6887133 | 6987787 | 7253303 | -185514 | 0 | -185514 | 7067789 | 7068223 | 435 | 0 | 104 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 3 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 | 2024-10-15 | QTR2 | 24/25 | 308 | 10217706.9 |  |  | 3 | 43 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W68 | 45102815201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 60 | 65 | 52 | 13 | 0 | 0 | 5 | 0 | 112106 | 8466 | 103639 | 112106 | 103639 | 0 | 0 | 0 | 103639 | 103639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 | 2025-06-12 | QTR4 | 24/25 | 314 | 174993.22 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W69 | 42696125201 | 2023-11-09 | QTR2 | 23/24 | 2 | 1 | 274 | 451 | 451 | 0 | 0 | 0 | 177 | 0 | 4685111 | 59134 | 4625977 | 4688658 | 4492681 | 0 | 0 | 0 | 4492681 | 4485331 | -7350 | 3547 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 3547 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 3547 | 1539 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-06-18 | QTR4 | 24/25 | 321 | 5910727.48 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W79 | 45109915201 | 2024-04-11 | QTR4 | 23/24 | 1 | 0 | 90 | 143 | 142 | 1 | 0 | 0 | 53 | 0 | 485265 | 30756 | 454509 | 485265 | 487819 | 0 | 0 | 0 | 487819 | 487819 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-02-04 | QTR3 | 24/25 | 321 | 555113.46 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X01 | 40619455201 | 2024-10-24 | QTR2 | 24/25 | 1 | 0 | 120 | 159 | 153 | 6 | 0 | 0 | 39 | 0 | 328567 | 17193 | 311374 | 328567 | 291720 | 0 | 0 | 0 | 291720 | 291720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-10-09 | QTR2 | 25/26 | 313 | 364798.17 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X03 | 40619635201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 90 | 112 | 86 | 26 | 0 | 0 | 22 | 0 | 169075 | 11395 | 157679 | 169075 | 154095 | 0 | 0 | 0 | 154095 | 154095 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2025-08-21 | QTR1 | 25/26 | 313 | 240133.12 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X08 | 45103115201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 225 | 303 | 223 | 80 | 0 | 0 | 78 | 0 | 1112248 | 50000 | 1062248 | 1112248 | 1077908 | 0 | 0 | 0 | 1077908 | 1077908 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-05-22 | QTR4 | 24/25 | 313 | 1273505.15 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X17 | 44758915201 | 2024-06-13 | QTR4 | 23/24 | 2 | 1 | 175 | 283 | 282 | 1 | 0 | 0 | 103 | 5 | 2342678 | 50000 | 2292678 | 2369603 | 2340433 | 0 | 0 | 0 | 2340433 | 2340369 | -64 | 26925 | 78 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-09-26 | QTR1 | 25/26 | 308 | 2975754.37 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X52 | 43078225201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 150 | 208 | 208 | 0 | 0 | 0 | 58 | 0 | 4271650 | 50000 | 4221650 | 4271650 | 4371998 | 0 | 0 | 0 | 4371998 | 4360199 | -11799 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 | 2025-05-20 | QTR4 | 24/25 | 314 | 4754953.2 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X72 | 22020225201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 150 | 200 | 155 | 45 | 0 | 0 | 50 | 0 | 647631 | 42452 | 605180 | 647631 | 536583 | 0 | 0 | 0 | 536583 | 536583 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 | 2025-09-29 | QTR1 | 25/26 | 313 | 900232.57 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X87 | 45268615201 | 2024-09-12 | QTR1 | 24/25 | 1 | 1 | 120 | 179 | 178 | 1 | 0 | 0 | 58 | 1 | 1172775 | 50000 | 1122775 | 1197264 | 1124063 | 0 | 0 | 0 | 1124063 | 1124063 | 0 | 24489 | 12 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 24489 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 321 | 1445110 |  |  | 1 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y07 | 43937125201 | 2025-01-30 | QTR3 | 24/25 | 1 | 0 | 120 | 128 | 115 | 13 | 0 | 0 | 8 | 0 | 493247 | 26670 | 466577 | 493247 | 468786 | 0 | 0 | 0 | 468786 | 468786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2025-09-24 | QTR1 | 25/26 | 321 | 566683.49 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y25 | 45431115201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 120 | 138 | 136 | 2 | 0 | 0 | 18 | 0 | 430052 | 29999 | 400053 | 430052 | 391859 | 0 | 0 | 0 | 391859 | 391859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 | 2026-01-08 | QTR3 | 25/26 | 321 | 619869.69 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y28 | 45443415201 | 2025-04-10 | QTR4 | 24/25 | 1 | 0 | 120 | 125 | 107 | 18 | 0 | 0 | 5 | 0 | 339177 | 19836 | 319341 | 339177 | 318764 | 0 | 0 | 0 | 318764 | 318764 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 | 2025-11-03 | QTR2 | 25/26 | 308 | 393848.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4560 | 44004315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 482 | 552 | 551 | 1 | 0 | 0 | 70 | 0 | 2472960 | 50000 | 2422960 | 2472960 | 2454293 | 0 | 0 | 0 | 2454293 | 2461065 | 134358 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 19903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21118 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2025-09-22 | QTR1 | 25/26 | 2023-02-03 | QTR3 | 22/23 | 409 | 2686957.88 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4580 | 43992915201 | 2021-05-26 | QTR4 | 20/21 | 5 | 8 | 739 | 1080 | 1080 | 0 | 0 | 0 | 321 | 20 | 18014663 | 150000 | 17864663 | 17978017 | 17209306 | 0 | 0 | 0 | 17209306 | 17705907 | 548358 | -36647 | 213 | 26 | 0 | 52717 | 0 | 28 | 0 | 96396 | 32818 | 0 | 0 | 0 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10479 | 0 | 0 | 0 | 8503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51758 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 19502 | 19502 | 0 | 0 | 0 | 0 | 54 | 20 | 30554 | 52320 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 | 2024-12-17 | QTR2 | 24/25 | 409 | 22960743.25 |  |  | 0 | 54 | 0 | 0 | -63378 | 0 |  | CO
04CO | 04 | T4627 | 44384615201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 353 | 497 | 497 | 0 | 0 | 0 | 114 | 30 | 1831417 | 50000 | 1781417 | 1831417 | 1800868 | 0 | 0 | 0 | 1800868 | 1800868 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 | 2025-06-16 | QTR4 | 24/25 | 412 | 2390409.32 |  |  | 30 | 30 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4638 | 43580855201 | 2023-07-26 | QTR1 | 23/24 | 4 | 4 | 345 | 512 | 512 | 0 | 0 | 0 | 137 | 30 | 8148235 | 82702 | 8065534 | 8411133 | 8179681 | 0 | 0 | 0 | 8179681 | 8160560 | -3998 | 262898 | 110 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2025-12-02 | QTR2 | 25/26 | 2025-07-23 | QTR1 | 25/26 | 412 | 8255267.22 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4641 | 43984515201 | 2023-04-26 | QTR4 | 22/23 | 4 | 5 | 721 | 810 | 789 | 21 | 0 | 0 | 89 | 0 | 11705000 | 114314 | 11590686 | 12054276 | 11872830 | 0 | 0 | 0 | 11872830 | 11832340 | -11097 | 349276 | 32 | 0 | 0 | 211859 | 0 | 0 | 0 | 163474 | 18545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386900 | 18545 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-16 | QTR3 | 25/26 | 2025-09-05 | QTR1 | 25/26 | 409 | 11870989.01 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4643 | 44637415201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 542 | 602 | 566 | 36 | 0 | 0 | 60 | 0 | 17748021 | 150000 | 17598021 | 18627265 | 18943576 | 0 | 0 | 0 | 18943576 | 18916878 | -25540 | 879244 | 29 | 0 | 0 | 886738 | 22797 | 0 | 0 | 7449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911403 | 22797 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 | 2025-11-17 | QTR2 | 25/26 | 409 | 24914785.02 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4645 | 44610215201 | 2023-05-24 | QTR4 | 22/23 | 2 | 4 | 430 | 560 | 558 | 2 | 0 | 0 | 130 | 0 | 12833449 | 133704 | 12699745 | 12956058 | 12287948 | 0 | 0 | 0 | 12287948 | 12282375 | 2250 | 122609 | 65 | 0 | 0 | 35147 | 0 | 21 | 0 | 79638 | 29413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114786 | 29413 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-31 | QTR1 | 25/26 | 2025-05-02 | QTR4 | 24/25 | 409 | 14351247.26 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4649 | 44839715201 | 2023-06-14 | QTR4 | 22/23 | 1 | 5 | 254 | 482 | 482 | 0 | 0 | 0 | 67 | 161 | 4835155 | 50000 | 4785155 | 5082020 | 5106645 | 0 | 0 | 0 | 5106645 | 5105846 | -798 | 246865 | 59 | 0 | 0 | 41171 | 0 | 0 | 0 | 40694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 246865 | 0 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 | 2025-04-28 | QTR4 | 24/25 | 408 | 6110749.35 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4651 | 44407915201 | 2023-10-25 | QTR2 | 23/24 | 3 | 6 | 473 | 492 | 347 | 145 | 0 | 0 | 43 | -24 | 7152200 | 65917 | 7086283 | 7526530 | 7413084 | 0 | 0 | 0 | 7413084 | 7393759 | -14849 | 529392 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 28959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28959 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 | 2025-04-18 | QTR4 | 24/25 | 409 | 6673207.01 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4652 | 44616915201 | 2023-11-15 | QTR2 | 23/24 | 2 | 3 | 259 | 447 | 447 | 0 | 0 | 0 | 188 | 0 | 5424973 | 53119 | 5371854 | 5477905 | 5676734 | 0 | 0 | 0 | 5676734 | 5654422 | -8426 | 52932 | 107 | 0 | 0 | 4345 | 0 | 30 | 0 | 53665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 58010 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-10 | QTR3 | 25/26 | 2025-08-14 | QTR1 | 25/26 | 408 | 5383942.21 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4654 | 44952015201 | 2024-01-31 | QTR3 | 23/24 | 2 | 8 | 289 | 471 | 469 | 2 | 0 | 0 | 182 | 0 | 5626066 | 61166 | 5564900 | 5715669 | 5782761 | 0 | 0 | 0 | 5782761 | 5777248 | -91 | 89603 | 124 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 4409 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2026-01-12 | QTR3 | 25/26 | 2025-11-13 | QTR2 | 25/26 | 412 | 6458891.07 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4661 | 44620015201 | 2024-03-27 | QTR3 | 23/24 | 4 | 4 | 422 | 432 | 352 | 80 | 0 | 0 | 33 | -46 | 9458464 | 113124 | 9345340 | 9790787 | 9649312 | 0 | 0 | 0 | 9649312 | 9617817 | -18533 | 566686 | 18 | 0 | 0 | 108078 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109406 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 | 2025-08-20 | QTR1 | 25/26 | 412 | 11108027.65 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4662 | 44001515201 | 2023-12-06 | QTR2 | 23/24 | 1 | 3 | 182 | 353 | 351 | 2 | 0 | 0 | 171 | 0 | 2710165 | 50000 | 2660165 | 2699856 | 2568771 | 0 | 0 | 0 | 2568771 | 2567076 | -16 | -10309 | 123 | 0 | 0 | 811 | 0 | 23 | 0 | -6653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | -5843 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 | 2025-08-11 | QTR1 | 25/26 | 409 | 3354139.5 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4663 | 44764715201 | 2023-12-06 | QTR2 | 23/24 | 2 | 3 | 245 | 397 | 395 | 2 | 0 | 0 | 152 | 0 | 11192757 | 116425 | 11076332 | 11220679 | 11200266 | 0 | 0 | 0 | 11200266 | 11159153 | -30470 | 27922 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 17915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17915 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 | 2025-08-11 | QTR1 | 25/26 | 408 | 11705908.23 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4664 | 44699715201 | 2023-09-13 | QTR1 | 23/24 | 3 | 0 | 210 | 395 | 394 | 1 | 0 | 0 | 185 | 0 | 1247247 | 50000 | 1197247 | 1247247 | 1175544 | 0 | 0 | 0 | 1175544 | 1174544 | -1000 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 | 2025-05-12 | QTR4 | 24/25 | 412 | 1347694.58 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4665 | 44619515201 | 2024-02-28 | QTR3 | 23/24 | 6 | 2 | 240 | 367 | 367 | 0 | 0 | 0 | 127 | 0 | 5489802 | 58699 | 5431104 | 5499093 | 5514945 | 0 | 0 | 0 | 5514945 | 5496131 | -18814 | 9291 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 9291 | 9291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9291 | 9291 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-07 | QTR3 | 25/26 | 2025-10-08 | QTR2 | 25/26 | 412 | 5906510.04 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4667 | 44764615201 | 2024-03-27 | QTR3 | 23/24 | 2 | 3 | 271 | 331 | 331 | 0 | 0 | 0 | 60 | 0 | 5722729 | 58760 | 5663969 | 5878728 | 5826172 | 0 | 0 | 0 | 5826172 | 5808077 | -12396 | 155998 | 38 | 0 | 0 | 1638 | 0 | 2 | 0 | 150300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 151938 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-05 | QTR3 | 25/26 | 2025-08-21 | QTR1 | 25/26 | 408 | 5723687.91 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4677 | 44767915201 | 2024-05-22 | QTR4 | 23/24 | 4 | 3 | 276 | 298 | 271 | 27 | 0 | 0 | 36 | -28 | 7765433 | 82562 | 7682871 | 7871392 | 7668837 | 0 | 0 | 0 | 7668837 | 7663134 | -5703 | 211917 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24680 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 | 2025-08-01 | QTR1 | 25/26 | 412 | 8421050.52 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4679 | 44619615201 | 2024-01-31 | QTR3 | 23/24 | 3 | 0 | 244 | 337 | 336 | 1 | 0 | 0 | 93 | 0 | 5469442 | 56677 | 5412765 | 5469442 | 5544372 | 0 | 0 | 0 | 5544372 | 5542177 | -2195 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-12-12 | QTR2 | 25/26 | 2025-06-30 | QTR4 | 24/25 | 412 | 5971108.66 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4686 | 42957695201 | 2024-04-24 | QTR4 | 23/24 | 2 | 0 | 244 | 488 | 488 | 0 | 0 | 0 | 244 | 0 | 3298227 | 50000 | 3248227 | 3298227 | 3079319 | 0 | 0 | 0 | 3079319 | 3078260 | -1060 | 0 | 148 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2026-02-23 | QTR3 | 25/26 | 2026-01-09 | QTR3 | 25/26 | 412 | 3509812.2 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4687 | 45222715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 167 | 237 | 237 | 0 | 0 | 0 | 70 | 0 | 1600545 | 50000 | 1550545 | 1600545 | 1508063 | 0 | 0 | 0 | 1508063 | 1508063 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 | 2025-05-16 | QTR4 | 24/25 | 408 | 2128846.17 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4694 | 44767115201 | 2024-07-31 | QTR1 | 24/25 | 3 | 2 | 291 | 358 | 351 | 7 | 0 | 0 | 67 | -15 | 3150955 | 50000 | 3100955 | 3159605 | 3107001 | 0 | 0 | 0 | 3107001 | 3106285 | -716 | 33997 | 45 | 0 | 0 | 27775 | 0 | 0 | 0 | 21950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49724 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 | 2026-01-14 | QTR3 | 25/26 | 409 | 3340322.06 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4708 | 44754315201 | 2024-07-31 | QTR1 | 24/25 | 1 | 0 | 200 | 237 | 211 | 26 | 0 | 0 | 37 | 0 | 1300000 | 50000 | 1250000 | 1300000 | 1243700 | 0 | 0 | 0 | 1243700 | 1243700 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2025-08-05 | QTR1 | 25/26 | 2025-06-30 | QTR4 | 24/25 | 412 | 1369377.1 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4Q32 | 43310845201 | 2015-04-27 | QTR4 | 14/15 | 2 | 51 | 1450 | 3156 | 3156 | 0 | 0 | 0 | 1179 | 527 | 148749800 | 150000 | 148599800 | 174962816 | 175180045 | 0 | 56000 | 56000 | 175236045 | 174744522 | -41128 | 26213016 | 414 | 0 | 0 | 1494952 | 0 | 0 | 0 | 142046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517 | 527 | 21512637 | 3321562 | 0 | 0 | 2751791 | 53052 | 0 | 0 | 0 | 0 | 186 | 0 | 468030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 703 | 527 | 26164878 | 3374614 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2026-02-26 | QTR3 | 25/26 | 2024-05-24 | QTR4 | 23/24 | 412 | 122897181 | B10:B5:B8:::Y | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 0 | 176 | 0 | 0 | -204577 | 0 |  | DO
04DO | 04 | E4U48 | 44146615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 281 | 416 | 416 | 0 | 0 | 0 | 135 | 0 | 2126000 | 50000 | 2076000 | 2132929 | 1513603 | 0 | 0 | 0 | 1513603 | 1506673 | 0 | 6930 | 77 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2025-08-04 | QTR1 | 25/26 | 2025-02-27 | QTR3 | 24/25 | 409 | 2622051.6 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U88 | 43999925201 | 2023-04-07 | QTR4 | 22/23 | 1 | 3 | 764 | 860 | 713 | 147 | 0 | 0 | 96 | 0 | 10631541 | 85557 | 10545984 | 10738131 | 11100934 | 0 | 0 | 0 | 11100934 | 11070252 | -1518 | 106590 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 | 2025-07-07 | QTR1 | 25/26 | 408 | 10492574.81 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V62 | 43695815201 | 2022-08-18 | QTR1 | 22/23 | 2 | 10 | 622 | 706 | 649 | 57 | 0 | 0 | 84 | 0 | 31058595 | 150000 | 30908595 | 33155117 | 32699199 | 0 | 0 | 0 | 32699199 | 32554410 | -144790 | 1946522 | 57 | 0 | 0 | 1746 | 0 | 0 | 0 | 1779105 | 8878 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239103 | 0 | 0 | 0 | 79175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989203 | 8878 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2024-10-18 | QTR2 | 24/25 | 412 | 29695111.36 |  |  | 0 | 27 | 0 | 0 | -118750 | 0 |  | DO
04DO | 04 | E4W05 | 44047315201 | 2022-12-02 | QTR2 | 22/23 | 2 | 11 | 324 | 551 | 550 | 1 | 0 | 0 | 179 | 48 | 3993841 | 50000 | 3943841 | 4453325 | 4438530 | 0 | 0 | 0 | 4438530 | 4429433 | -6049 | 459484 | 135 | 0 | 0 | 14920 | 0 | 0 | 48 | 317478 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 48 | 425398 | 258 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-03-21 | QTR3 | 24/25 | 408 | 4033616.25 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W54 | 44618515201 | 2023-05-05 | QTR4 | 22/23 | 2 | 5 | 241 | 466 | 466 | 0 | 0 | 0 | 225 | 0 | 8153790 | 72216 | 8081573 | 8619435 | 8570644 | 0 | 0 | 0 | 8570644 | 8567270 | 0 | 469019 | 175 | 0 | 0 | 121843 | 1201843 | 0 | 0 | 314395 | 24985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3335 | 3335 | 0 | 0 | 22700 | 22700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462272 | 1252862 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 | 2025-02-14 | QTR3 | 24/25 | 412 | 7653131.2 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W61 | 44610415201 | 2023-08-04 | QTR1 | 23/24 | 1 | 1 | 287 | 408 | 408 | 0 | 0 | 0 | 121 | 0 | 5369226 | 50000 | 5319226 | 5369226 | 5576786 | 0 | 0 | 0 | 5576786 | 5571433 | -5352 | 104495 | 64 | 28 | 0 | 31492 | 0 | 0 | 0 | 7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 38981 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 | 2025-04-09 | QTR4 | 24/25 | 409 | 4627615.06 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W65 | 44617415201 | 2024-01-05 | QTR3 | 23/24 | 3 | 0 | 163 | 241 | 241 | 0 | 0 | 0 | 78 | 0 | 4920477 | 50000 | 4870477 | 4920477 | 4833727 | 0 | 0 | 0 | 4833727 | 4832964 | -763 | 0 | 39 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-15 | QTR1 | 25/26 | 2025-06-11 | QTR4 | 24/25 | 409 | 4972817.95 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W71 | 44974015201 | 2023-05-05 | QTR4 | 22/23 | 1 | 0 | 82 | 523 | 522 | 1 | 0 | 0 | 441 | 0 | 827827 | 45348 | 782479 | 827827 | 848976 | 0 | 0 | 0 | 848976 | 848976 | 0 | 0 | 38 | 310 | 0 | 0 | 0 | 0 | 0 | 13151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 0 | 13151 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 412 | 1076147.07 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W72 | 44617015201 | 2023-11-03 | QTR2 | 23/24 | 3 | 5 | 182 | 306 | 303 | 3 | 0 | 0 | 105 | 19 | 4285836 | 50000 | 4235836 | 4430549 | 4413846 | 0 | 0 | 0 | 4413846 | 4401052 | -9192 | 144713 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 85267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 55844 | 55844 | 0 | 0 | 0 | 0 | 0 | 19 | 145465 | 55844 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-30 | QTR2 | 25/26 | 2025-06-16 | QTR4 | 24/25 | 408 | 4697027.08 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W82 | 44610515201 | 2024-01-05 | QTR3 | 23/24 | 2 | 2 | 274 | 356 | 355 | 1 | 0 | 0 | 82 | 0 | 4881711 | 57650 | 4824061 | 4893014 | 4759434 | 0 | 0 | 0 | 4759434 | 4740765 | -5116 | 11303 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 23092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 23092 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-04-17 | QTR4 | 24/25 | 409 | 5716819.1 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W88 | 44765415201 | 2024-02-02 | QTR3 | 23/24 | 3 | 3 | 233 | 271 | 240 | 31 | 0 | 0 | 55 | -17 | 6226524 | 63037 | 6163487 | 6395874 | 6393098 | 0 | 0 | 0 | 6393098 | 6379878 | -5542 | 169350 | 38 | 0 | 0 | 103394 | 103394 | 0 | 0 | 59105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162498 | 103394 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-04-09 | QTR4 | 24/25 | 412 | 6625403.9 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W89 | 44767415201 | 2024-07-12 | QTR1 | 24/25 | 1 | 1 | 180 | 262 | 260 | 2 | 0 | 0 | 82 | 0 | 3966137 | 50000 | 3916137 | 3985889 | 3958991 | 0 | 0 | 0 | 3958991 | 3953275 | -5716 | 19752 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 412 | 4276093.35 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W93 | 44764815201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 185 | 224 | 215 | 9 | 0 | 0 | 39 | 0 | 3198987 | 50000 | 3148987 | 3198987 | 3046918 | 0 | 0 | 0 | 3046918 | 3045966 | -952 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-18 | QTR1 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 408 | 3443705 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X14 | 44932315201 | 2024-04-05 | QTR4 | 23/24 | 1 | 5 | 209 | 308 | 298 | 10 | 0 | 0 | 78 | 21 | 3689059 | 50000 | 3639059 | 3733032 | 3801506 | 0 | 0 | 0 | 3801506 | 3800583 | -923 | 43973 | 65 | 5 | 0 | 0 | 0 | 0 | 21 | 74766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 21 | 74766 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-12 | QTR3 | 25/26 | 2025-10-30 | QTR2 | 25/26 | 408 | 2884956.63 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X17 | 44655115201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 132 | 174 | 174 | 0 | 0 | 0 | 42 | 0 | 1849000 | 50000 | 1799000 | 1870772 | 1768167 | 0 | 0 | 0 | 1768167 | 1768167 | 0 | 21772 | 38 | 0 | 0 | 4117 | 0 | 0 | 0 | 22787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26904 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-12 | QTR1 | 25/26 | 2025-07-02 | QTR1 | 25/26 | 409 | 2011837.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X24 | 44931815201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 222 | 278 | 278 | 0 | 0 | 0 | 56 | 0 | 3983900 | 50853 | 3933047 | 4183008 | 4262893 | 0 | 0 | 0 | 4262893 | 4262893 | 0 | 199108 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199108 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 | 2025-10-31 | QTR2 | 25/26 | 409 | 5126069.11 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X33 | 44359525201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 262 | 309 | 294 | 15 | 0 | 0 | 47 | 0 | 2579048 | 50000 | 2529048 | 2787519 | 2747199 | 0 | 0 | 0 | 2747199 | 2747177 | -22 | 208471 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 9697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218168 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 | 2025-11-13 | QTR2 | 25/26 | 408 | 3891911.4 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X39 | 44768115201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 170 | 193 | 193 | 0 | 0 | 0 | 23 | 0 | 2519093 | 50000 | 2469093 | 2519093 | 2422842 | 0 | 0 | 0 | 2422842 | 2420995 | -1848 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 | 2025-08-21 | QTR1 | 25/26 | 412 | 2812112.37 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X51 | 44765815201 | 2024-08-02 | QTR1 | 24/25 | 3 | 1 | 252 | 287 | 265 | 22 | 0 | 0 | 35 | 0 | 3535833 | 50000 | 3485833 | 3535833 | 3387300 | 0 | 0 | 0 | 3387300 | 3384814 | -2487 | 0 | 14 | 0 | 0 | 13204 | 0 | 0 | 0 | 7499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20703 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 | 2025-09-03 | QTR1 | 25/26 | 409 | 3764178.43 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5650 | 23839555201 | 2020-03-11 | QTR3 | 19/20 | 7 | 12 | 1030 | 1956 | 1956 | 0 | 0 | 0 | 711 | 215 | 44960000 | 248112 | 44711888 | 46736451 | 46188504 | 0 | 0 | 0 | 46188504 | 47704062 | 1586115 | 1776451 | 295 | 0 | 57 | 769813 | 208395 | 0 | 169 | 1007439 | 1180290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63867 | 0 | 0 | 0 | 48656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 1889774 | 1388685 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-02-05 | QTR3 | 25/26 | 2025-12-03 | QTR2 | 25/26 | 515 | 45602807.97 |  |  | 203 | 416 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5706 | 42955615201 | 2020-03-25 | QTR3 | 19/20 | 6 | 12 | 1100 | 1761 | 1761 | 0 | 0 | 0 | 559 | 102 | 44888403 | 150000 | 44738403 | 47699589 | 48432679 | 0 | 0 | 0 | 48432679 | 48287387 | 2317108 | 2811186 | 343 | 0 | 0 | 1647033 | 0 | 0 | 102 | 784469 | 30264 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26536 | 0 | 0 | 0 | 12848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 2823138 | 30264 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 | 2025-05-06 | QTR4 | 24/25 | 513 | 37019154.5 |  |  | 0 | 216 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5718 | 43763415201 | 2021-04-28 | QTR4 | 20/21 | 7 | 17 | 690 | 1399 | 1340 | 59 | 0 | 0 | 674 | 35 | 11250000 | 233500 | 11016500 | 12978309 | 13223828 | 0 | 0 | 0 | 13223828 | 13314228 | 155455 | 1728309 | 360 | 0 | 25 | 527918 | 11401 | 0 | 0 | 912863 | 0 | 0 | 10 | 40741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56556 | 0 | 0 | 0 | 355913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1901807 | 11401 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-10-23 | QTR2 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 507 | 10799982.79 |  |  | 28 | 314 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5747 | 43366115201 | 2022-05-25 | QTR4 | 21/22 | 5 | 7 | 280 | 568 | 568 | 0 | 0 | 0 | 156 | 132 | 6696978 | 50000 | 6646978 | 7142732 | 7032054 | 0 | 0 | 0 | 7032054 | 7019736 | 0 | 445755 | 106 | 0 | 4 | 88147 | 0 | 0 | 5 | 26731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318 | 0 | 0 | 125 | 296588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 425240 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 | 2024-10-22 | QTR2 | 24/25 | 512 | 5918166.26 |  |  | 7 | 50 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5759 | 44586715201 | 2023-04-26 | QTR4 | 22/23 | 5 | 6 | 170 | 600 | 588 | 12 | 0 | 0 | 430 | 0 | 3865830 | 50000 | 3815830 | 3991018 | 3937381 | 0 | 0 | 0 | 3937381 | 3936003 | -1378 | 125188 | 128 | 0 | 0 | -12273 | 0 | 0 | 0 | -103071 | 39310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251410 | 185032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136067 | 224342 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 | 2025-08-13 | QTR1 | 25/26 | 514 | 3318268.57 |  |  | 0 | 302 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5760 | 44114515201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 320 | 519 | 515 | 4 | 0 | 0 | 199 | 0 | 9020145 | 60000 | 8960145 | 9091224 | 9371724 | 0 | 0 | 0 | 9371724 | 9358265 | -1051 | 71079 | 39 | 0 | 0 | 58672 | 0 | 0 | 0 | 4020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62692 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 | 2025-06-27 | QTR4 | 24/25 | 509 | 8000814.19 |  |  | 0 | 130 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5777 | 44042425201 | 2023-01-25 | QTR3 | 22/23 | 3 | 5 | 650 | 704 | 611 | 93 | 0 | 0 | 86 | -32 | 22896706 | 150000 | 22746706 | 23663870 | 23767312 | 0 | 0 | 0 | 23767312 | 22921260 | -826558 | 767164 | 32 | 0 | 0 | 12008 | 0 | 0 | 0 | 246258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282497 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-03-11 | QTR3 | 24/25 | 514 | 28387049.83 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5778 | 44569215201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 250 | 396 | 395 | 1 | 0 | 0 | 146 | 0 | 1617324 | 47000 | 1570324 | 1637324 | 1467772 | 0 | 0 | 0 | 1467772 | 1467140 | -632 | 20000 | 119 | 0 | 0 | 34331 | 0 | 0 | 0 | 28098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62429 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-01-30 | QTR3 | 24/25 | 509 | 1625738.6 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5786 | 44521715201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 410 | 545 | 545 | 0 | 0 | 0 | 135 | 0 | 10986719 | 117744 | 10868975 | 11011859 | 11062198 | 0 | 0 | 0 | 11062198 | 11032701 | -4358 | 25139 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-28 | QTR2 | 25/26 | 2025-04-10 | QTR4 | 24/25 | 512 | 14985674.13 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5789 | 43547125201 | 2023-05-24 | QTR4 | 22/23 | 3 | 3 | 360 | 467 | 467 | 0 | 0 | 0 | 92 | 15 | 8448064 | 70000 | 8378064 | 8800372 | 8800513 | 0 | 0 | 0 | 8800513 | 8740511 | 855 | 352308 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 93573 | 14238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 221451 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 318271 | 14238 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 | 2024-12-17 | QTR2 | 24/25 | 515 | 8153514.72 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5792 | 41025135201 | 2023-06-14 | QTR4 | 22/23 | 3 | 9 | 610 | 822 | 816 | 6 | 0 | 0 | 180 | 32 | 15097285 | 150000 | 14947285 | 15626114 | 15519395 | 0 | 0 | 0 | 15519395 | 15475580 | -7963 | 1098563 | 116 | 0 | 0 | 64465 | 0 | 0 | 32 | 474785 | 8321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592234 | 0 | 0 | 0 | 1431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1132914 | 8321 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-13 | QTR3 | 25/26 | 2025-12-08 | QTR2 | 25/26 | 513 | 25813007.18 |  |  | 14 | 64 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5795 | 24259285201 | 2023-06-14 | QTR4 | 22/23 | 3 | 4 | 380 | 531 | 523 | 8 | 0 | 0 | 92 | 59 | 8347803 | 60000 | 8287803 | 8496009 | 8830863 | 0 | 0 | 0 | 8830863 | 8791083 | -490 | 148206 | 43 | 0 | 59 | 0 | 0 | 0 | 0 | 139202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 145982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-03-14 | QTR3 | 24/25 | 507 | 8013785.1 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5796 | 42617915201 | 2023-07-26 | QTR1 | 23/24 | 4 | 3 | 280 | 563 | 562 | 1 | 0 | 0 | 230 | 53 | 3346229 | 50000 | 3296229 | 3547942 | 3223459 | 0 | 0 | 0 | 3223459 | 3212971 | -31 | 201713 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 191255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 191255 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2026-01-07 | QTR3 | 25/26 | 2025-08-06 | QTR1 | 25/26 | 512 | 4393698.6 |  |  | 0 | 133 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5797 | 44568915201 | 2023-07-26 | QTR1 | 23/24 | 3 | 3 | 250 | 490 | 490 | 0 | 0 | 0 | 52 | 188 | 6209544 | 50000 | 6159544 | 6295030 | 5955348 | 0 | 0 | 0 | 5955348 | 5947678 | -685 | 85486 | 29 | 0 | 188 | 78501 | 61993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 78501 | 61993 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-01-14 | QTR3 | 25/26 | 2025-06-04 | QTR4 | 24/25 | 514 | 5653228.56 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5799 | 44571615201 | 2023-10-25 | QTR2 | 23/24 | 3 | 7 | 330 | 445 | 445 | 0 | 0 | 0 | 101 | 14 | 7000000 | 71000 | 6929000 | 7423497 | 7482575 | 0 | 0 | 0 | 7482575 | 7419445 | -33657 | 423497 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 220409 | 72070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156171 | 0 | 0 | 0 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378650 | 72070 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 | 2025-04-15 | QTR4 | 24/25 | 513 | 8074701.25 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5800 | 44585515201 | 2023-07-26 | QTR1 | 23/24 | 3 | 5 | 230 | 409 | 491 | -82 | 82 | 0 | 93 | 86 | 3679712 | 50000 | 3629712 | 3851805 | 3808215 | 0 | 0 | 0 | 3808215 | 3802526 | -69 | 172092 | 61 | 0 | 84 | 71357 | 36514 | 0 | 9 | 67803 | 17258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 29703 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 174435 | 53772 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 | 2025-06-05 | QTR4 | 24/25 | 514 | 2818721.96 |  |  | 15 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5801 | 44521915201 | 2023-09-27 | QTR1 | 23/24 | 3 | 1 | 370 | 513 | 509 | 4 | 0 | 0 | 143 | 0 | 15286323 | 100000 | 15186323 | 15295366 | 15592805 | 0 | 0 | 0 | 15592805 | 15522129 | -61634 | 9043 | 97 | 0 | 0 | 33061 | 0 | 0 | 0 | 46645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79706 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 | 2025-08-15 | QTR1 | 25/26 | 513 | 20005006.42 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5804 | 43757515201 | 2024-05-22 | QTR4 | 23/24 | 1 | 2 | 160 | 223 | 223 | 0 | 0 | 0 | 63 | 0 | 3278993 | 50000 | 3228993 | 3308018 | 3163264 | 0 | 0 | 0 | 3163264 | 3163188 | -76 | 29025 | 59 | 0 | 0 | -17884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17884 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-01-14 | QTR3 | 25/26 | 2025-08-23 | QTR1 | 25/26 | 509 | 3131835.47 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5805 | 44709215201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 280 | 334 | 332 | 2 | 0 | 0 | 54 | 0 | 3271306 | 50000 | 3221306 | 3287930 | 3244926 | 0 | 0 | 0 | 3244926 | 3224506 | -20420 | 16623 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 | 2024-11-26 | QTR2 | 24/25 | 514 | 4597690.87 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5806 | 44709815201 | 2023-09-27 | QTR1 | 23/24 | 3 | 3 | 300 | 435 | 431 | 4 | 0 | 0 | 135 | 0 | 9892142 | 110000 | 9782142 | 9938977 | 10455307 | 0 | 0 | 0 | 10455307 | 10363664 | -58186 | 46835 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 | 2025-04-01 | QTR4 | 24/25 | 515 | 11922850 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5809 | 43915615201 | 2023-09-27 | QTR1 | 23/24 | 4 | 2 | 420 | 517 | 481 | 36 | 0 | 0 | 97 | 0 | 19059007 | 150000 | 18909007 | 19456279 | 20132774 | 0 | 0 | 0 | 20132774 | 19987244 | -74410 | 397272 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-10-06 | QTR2 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 513 | 20470643.27 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5811 | 43233215201 | 2023-10-25 | QTR2 | 23/24 | 6 | 6 | 250 | 541 | 540 | 1 | 0 | 0 | 176 | 115 | 15324226 | 150000 | 15174226 | 16443632 | 16758792 | 0 | 0 | 0 | 16758792 | 16617261 | -118108 | 1119406 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 614667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51362 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 62034 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 380350 | 643594 | 0 | 0 | 0 | 0 | 10 | 115 | 1108414 | 643594 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 | 2025-08-04 | QTR1 | 25/26 | 515 | 22228374.21 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5826 | 45222915201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 200 | 276 | 273 | 3 | 0 | 0 | 76 | 0 | 1180815 | 50000 | 1130815 | 1180815 | 979467 | 0 | 0 | 0 | 979467 | 979467 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 | 2025-07-08 | QTR1 | 25/26 | 507 | 1609251.1 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5833 | 44708915201 | 2024-09-25 | QTR1 | 24/25 | 2 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 2100000 | 50000 | 2050000 | 2100000 | 2001416 | 0 | 0 | 0 | 2001416 | 2001416 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-07-30 | QTR1 | 25/26 | 513 | 2701146.14 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5835 | 44873915201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 160 | 209 | 209 | 0 | 0 | 0 | 49 | 0 | 3081418 | 50000 | 3031418 | 3081418 | 3111059 | 0 | 0 | 0 | 3111059 | 3112003 | 944 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 | 2025-09-02 | QTR1 | 25/26 | 515 | 3300432.25 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5857 | 45613715201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 40 | 40 | 10 | 30 | 0 | 0 | 0 | 0 | 117123 | 7000 | 110123 | 113191 | 103346 | 0 | 0 | 0 | 103346 | 103346 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-17 | QTR1 | 25/26 | 2025-06-25 | QTR4 | 24/25 | 513 | 180485.52 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5858 | 45616815201 | 2025-03-26 | QTR3 | 24/25 | 5 | 3 | 120 | 130 | 105 | 25 | 0 | 0 | 10 | 0 | 948635 | 47500 | 901135 | 993577 | 604185 | 0 | 0 | 0 | 604185 | 604185 | 0 | 44942 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 44942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44942 | 0 | F850531344 | PREMIER PAVING LLC | N/A | N/A | N/A | N/A | 2026-01-09 | QTR3 | 25/26 | 2025-09-16 | QTR1 | 25/26 | 514 | 1621409.55 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T9030 | 44199035223 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 270 | 367 | 366 | 1 | 0 | 0 | 97 | 0 | 5555556 | 53950 | 5501606 | 5605113 | 5565155 | 0 | 0 | 0 | 5565155 | 5565155 | 0 | 49558 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-05-05 | QTR4 | 24/25 | 513 | 5529999.88 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50B8 | 44521515201 | 2023-06-06 | QTR4 | 22/23 | 4 | 6 | 410 | 645 | 641 | 4 | 0 | 0 | 154 | 81 | 11282143 | 100000 | 11182143 | 11851012 | 12077791 | 0 | 0 | 0 | 12077791 | 12077791 | 0 | 568869 | 109 | 0 | 6 | 419002 | 23191 | 0 | 37 | 361551 | 8287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 56263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 601391 | 31478 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-03-02 | QTR3 | 25/26 | 2025-09-05 | QTR1 | 25/26 | 514 | 10131956.15 |  |  | 44 | 45 | 0 | 0 | -235426 | 0 |  | DO
05DO | 05 | E50F1 | 44656815201 | 2024-02-06 | QTR3 | 23/24 | 1 | 0 | 127 | 172 | 172 | 0 | 0 | 0 | 43 | 2 | 1104118 | 42000 | 1062118 | 1104118 | 1062935 | 0 | 0 | 0 | 1062935 | 1062929 | -6 | 0 | 25 | 0 | 0 | 3237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3237 | 0 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-02-27 | QTR3 | 24/25 | 509 | 1174163.5 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E50F5 | 44316915201 | 2024-01-04 | QTR3 | 23/24 | 1 | 1 | 290 | 430 | 429 | 1 | 0 | 0 | 71 | 69 | 5036336 | 50000 | 4986336 | 5073420 | 4545253 | 0 | 0 | 0 | 4545253 | 4525803 | -19451 | 37085 | 45 | 0 | 0 | 0 | 0 | 0 | 69 | 62085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 62085 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 | 2025-06-05 | QTR4 | 24/25 | 514 | 5619045.42 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F2 | 44768815201 | 2024-04-02 | QTR4 | 23/24 | 2 | 1 | 150 | 239 | 238 | 1 | 0 | 0 | 72 | 17 | 1504656 | 50000 | 1454656 | 1506430 | 1447570 | 0 | 0 | 0 | 1447570 | 1445324 | -472 | 1774 | 46 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-05-21 | QTR4 | 24/25 | 514 | 1590260.07 |  |  | 17 | 26 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F6 | 43923415201 | 2024-03-05 | QTR3 | 23/24 | 3 | 3 | 350 | 458 | 457 | 1 | 0 | 0 | 108 | 0 | 16652098 | 150000 | 16502098 | 16895551 | 16781249 | 0 | 0 | 0 | 16781249 | 16753875 | -23602 | 243453 | 50 | 0 | 0 | 254263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254263 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 | 2025-12-04 | QTR2 | 25/26 | 512 | 16309344.71 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F7 | 44530215201 | 2024-03-05 | QTR3 | 23/24 | 3 | 5 | 250 | 400 | 400 | 0 | 0 | 0 | 130 | 20 | 5562121 | 50000 | 5512121 | 5724310 | 5880473 | 0 | 0 | 0 | 5880473 | 5842942 | -14889 | 162189 | 89 | 0 | 0 | 29317 | 0 | 0 | 20 | 112422 | 22050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 141739 | 22050 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 | 2025-10-01 | QTR2 | 25/26 | 512 | 6330177.48 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F9 | 43912415201 | 2024-04-02 | QTR4 | 23/24 | 2 | 2 | 260 | 347 | 320 | 27 | 0 | 0 | 72 | 15 | 4408516 | 58000 | 4350516 | 4442576 | 4279968 | 0 | 0 | 0 | 4279968 | 4272484 | 0 | 34060 | 38 | 0 | 0 | 3850 | 0 | 0 | 0 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30938 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-05-19 | QTR4 | 24/25 | 513 | 6688704.65 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E52F4 | 45293215201 | 2024-06-04 | QTR4 | 23/24 | 1 | 0 | 160 | 367 | 366 | 1 | 0 | 0 | 195 | 12 | 1554510 | 50000 | 1504510 | 1554510 | 1576041 | 0 | 0 | 0 | 1576041 | 1575969 | -72 | 0 | 154 | 0 | 0 | 3946 | 0 | 0 | 7 | 16349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 36911 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-02-24 | QTR3 | 25/26 | 2026-01-06 | QTR3 | 25/26 | 507 | 1518095.5 |  |  | 7 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F2 | 44879115201 | 2024-10-01 | QTR2 | 24/25 | 1 | 3 | 170 | 268 | 268 | 0 | 0 | 0 | 93 | 5 | 7065614 | 86000 | 6979614 | 7183452 | 7253477 | 0 | 0 | 0 | 7253477 | 7256561 | 3084 | 117838 | 75 | 0 | 5 | 62000 | 0 | 0 | 0 | 47838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 109838 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 | 2025-10-23 | QTR2 | 25/26 | 514 | 8985393.39 |  |  | 5 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F6 | 44880115201 | 2024-08-08 | QTR1 | 24/25 | 1 | 0 | 270 | 372 | 353 | 19 | 0 | 0 | 88 | 14 | 5664533 | 50000 | 5614533 | 5664533 | 5824248 | 0 | 0 | 0 | 5824248 | 5821719 | -2529 | 0 | 50 | 0 | 0 | 6765 | 0 | 0 | 0 | 12871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19636 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2026-02-24 | QTR3 | 25/26 | 2025-11-25 | QTR2 | 25/26 | 509 | 5574707.4 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F7 | 44984515201 | 2024-12-03 | QTR2 | 24/25 | 1 | 0 | 130 | 255 | 255 | 0 | 0 | 0 | 125 | 0 | 925088 | 40024 | 885064 | 925088 | 953719 | 0 | 0 | 0 | 953719 | 953719 | 0 | 0 | 115 | 0 | 0 | 2525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2525 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-01-13 | QTR3 | 25/26 | 2025-11-18 | QTR2 | 25/26 | 507 | 845921.65 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F8 | 45022745201 | 2024-06-04 | QTR4 | 23/24 | 1 | 1 | 160 | 259 | 257 | 2 | 0 | 0 | 78 | 21 | 1498164 | 50000 | 1448164 | 1498164 | 1468694 | 0 | 0 | 0 | 1468694 | 1468694 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 24155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24155 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 | 2025-07-11 | QTR1 | 25/26 | 513 | 1507974.75 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54B3 | 44521415201 | 2023-10-03 | QTR2 | 23/24 | 3 | 3 | 270 | 366 | 366 | 0 | 0 | 0 | 96 | 0 | 6964127 | 72500 | 6891627 | 7171619 | 7043664 | 0 | 0 | 0 | 7043664 | 6984590 | -45651 | 207492 | 59 | 0 | 0 | 167324 | 0 | 0 | 0 | 41679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256083 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 | 2025-03-11 | QTR3 | 24/25 | 514 | 9627438.59 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55F3 | 45131115201 | 2025-02-04 | QTR3 | 24/25 | 1 | 0 | 150 | 183 | 183 | 0 | 0 | 0 | 33 | 0 | 4402920 | 58000 | 4344920 | 4402920 | 4332664 | 0 | 0 | 0 | 4332664 | 4326586 | -6078 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 13234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13234 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 | 2025-11-05 | QTR2 | 25/26 | 513 | 6422896.48 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55F4 | 42690555201 | 2025-04-01 | QTR4 | 24/25 | 1 | 0 | 120 | 121 | 108 | 13 | 0 | 0 | 1 | 0 | 1132509 | 50000 | 1082509 | 1132509 | 1025664 | 0 | 0 | 0 | 1025664 | 1025664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES LLC | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 | 2025-10-31 | QTR2 | 25/26 | 514 | 1246519.8 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55F6 | 44529815201 | 2025-03-04 | QTR3 | 24/25 | 1 | 2 | 180 | 230 | 214 | 16 | 0 | 0 | 50 | 0 | 7863435 | 100000 | 7763435 | 8058116 | 8341201 | 0 | 0 | 0 | 8341201 | 8333175 | -8027 | 194681 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 194681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194681 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 | 2025-12-12 | QTR2 | 25/26 | 514 | 10455826.3 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B6 | 44521115201 | 2023-06-06 | QTR4 | 22/23 | 2 | 1 | 180 | 442 | 442 | 0 | 0 | 0 | 205 | 57 | 3196756 | 50000 | 3146756 | 3198241 | 3427202 | 0 | 0 | 0 | 3427202 | 3427202 | 0 | 1485 | 141 | 0 | 7 | 8757 | 0 | 0 | 30 | 12941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 28133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 49830 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 | 2025-05-21 | QTR4 | 24/25 | 507 | 3501358.08 |  |  | 57 | 64 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56F4 | 41025155201 | 2025-05-06 | QTR4 | 24/25 | 1 | 0 | 140 | 173 | 171 | 2 | 0 | 0 | 33 | 0 | 3296100 | 53000 | 3243100 | 3296100 | 3182948 | 0 | 0 | 0 | 3182948 | 3193975 | 11027 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 | 2026-01-23 | QTR3 | 25/26 | 513 | 5178576.2 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56F7 | 45305815201 | 2025-04-01 | QTR4 | 24/25 | 1 | 0 | 190 | 217 | 196 | 21 | 0 | 0 | 27 | 0 | 6639966 | 78000 | 6561966 | 6639966 | 6618677 | 0 | 0 | 0 | 6618677 | 6618677 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 | 2026-01-15 | QTR3 | 25/26 | 509 | 8028735.15 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B3 | 24259265201 | 2023-06-06 | QTR4 | 22/23 | 3 | 4 | 590 | 703 | 696 | 7 | 0 | 0 | 113 | 0 | 9899345 | 50000 | 9849345 | 10080554 | 10364962 | 0 | 0 | 0 | 10364962 | 10344890 | -9 | 181208 | 61 | 0 | 0 | 111146 | 0 | 0 | 0 | 51682 | 1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162828 | 1682 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2025-12-19 | QTR2 | 25/26 | 2025-09-23 | QTR1 | 25/26 | 507 | 8480188.02 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B5 | 44530315201 | 2023-06-06 | QTR4 | 22/23 | 3 | 3 | 490 | 635 | 634 | 1 | 0 | 0 | 145 | 0 | 11137584 | 50000 | 11087584 | 11274458 | 11215283 | 0 | 0 | 0 | 11215283 | 11200767 | -786 | 136874 | 80 | 0 | 0 | 39281 | 0 | 0 | 0 | 110135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149459 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 | 2025-08-01 | QTR1 | 25/26 | 507 | 8364007.55 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B7 | 44708515201 | 2023-06-06 | QTR4 | 22/23 | 3 | 5 | 500 | 634 | 634 | 0 | 0 | 0 | 128 | 6 | 13078910 | 128000 | 12950910 | 13273764 | 13547486 | 0 | 0 | 0 | 13547486 | 13528029 | -2602 | 194854 | 81 | 0 | 0 | 39880 | 0 | 0 | 32 | 217171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 257051 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 | 2025-06-20 | QTR4 | 24/25 | 514 | 13524204.48 | A5 | ICC - BAM/BONUS | 8 | 47 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59A5 | 44780715201 | 2022-04-06 | QTR4 | 21/22 | 1 | 0 | 270 | 1159 | 1159 | 0 | 0 | 0 | 889 | 0 | 973615 | 34352 | 939263 | 973615 | 939263 | 0 | 0 | 0 | 939263 | 939263 | 0 | 0 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-09-19 | QTR1 | 25/26 | 2025-08-15 | QTR1 | 25/26 | 509 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 748 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59B2 | 43986415201 | 2024-02-06 | QTR3 | 23/24 | 3 | 3 | 200 | 286 | 286 | 0 | 0 | 0 | 86 | 0 | 3015224 | 50000 | 2965224 | 3086900 | 3009526 | 0 | 0 | 0 | 3009526 | 2958475 | -4843 | 71676 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-03-15 | QTR3 | 24/25 | 513 | 3337723.49 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z18 | 24020045201 | 2018-08-22 | QTR1 | 18/19 | 4 | 18 | 1400 | 2248 | 2248 | 0 | 0 | 0 | 599 | 249 | 253332000 | 150000 | 253182000 | 267516079 | 267608352 | 0 | 25000 | 25000 | 267633352 | 268414123 | 8560014 | 14184079 | 138 | 0 | 0 | 2669763 | 0 | 0 | 0 | 2461289 | 94536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 946937 | 321742 | 0 | 0 | 30080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949329 | 0 | 0 | 249 | 7300000 | 7300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 14357398 | 7716278 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 | 2024-12-20 | QTR2 | 24/25 | 507 | 283931078 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 461 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6466 | 43992315201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 160 | 189 | 184 | 5 | 0 | 0 | 29 | 0 | 749749 | 36694 | 713055 | 750453 | 687268 | 0 | 0 | 0 | 687268 | 687166 | -102 | 704 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 | 2025-05-06 | QTR4 | 24/25 | 613 | 759570.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6514 | 44462215201 | 2022-04-27 | QTR4 | 21/22 | 3 | 6 | 450 | 576 | 465 | 111 | 0 | 0 | 70 | 56 | 12567171 | 112026 | 12455145 | 13007370 | 12865831 | 0 | 500000 | 500000 | 13365831 | 12808223 | -557608 | 440200 | 42 | 0 | 0 | 75620 | 0 | 0 | 0 | 66701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 320618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 462939 | 0 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2026-01-29 | QTR3 | 25/26 | 2024-08-07 | QTR1 | 24/25 | 613 | 11765757.23 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6541 | 44390215201 | 2023-02-22 | QTR3 | 22/23 | 4 | 3 | 400 | 476 | 462 | 14 | 0 | 0 | 76 | 0 | 6112543 | 50000 | 6062543 | 6196534 | 6055588 | 0 | 0 | 0 | 6055588 | 6046499 | -7887 | 83991 | 29 | 0 | 0 | 30261 | 0 | 0 | 0 | 18983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56474 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 | 2025-06-11 | QTR4 | 24/25 | 613 | 4898503.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6547 | 44392115201 | 2023-05-24 | QTR4 | 22/23 | 4 | 6 | 340 | 533 | 513 | 20 | 0 | 0 | 180 | 13 | 7844825 | 81266 | 7763559 | 8071972 | 8026073 | 0 | 200000 | 200000 | 8226073 | 8025252 | -200821 | 227147 | 146 | 0 | 13 | 211928 | 0 | 0 | 0 | 27940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 239868 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 | 2025-03-28 | QTR3 | 24/25 | 636 | 8411804.1 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6555 | 44598715201 | 2023-04-26 | QTR4 | 22/23 | 8 | 6 | 500 | 526 | 459 | 67 | 0 | 0 | 22 | 4 | 15230513 | 150000 | 15080513 | 15276979 | 14673045 | 0 | 440000 | 440000 | 15113045 | 14624087 | -460650 | 46466 | 10 | 0 | 0 | 43405 | 0 | 0 | 0 | 81997 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17514 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79761 | 21158 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 | 2025-02-27 | QTR3 | 24/25 | 636 | 16721997.85 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | -65908 | 0 |  | CO
06CO | 06 | T6556 | 44389615201 | 2023-05-24 | QTR4 | 22/23 | 5 | 5 | 450 | 493 | 434 | 59 | 0 | 0 | 43 | 0 | 12343500 | 99969 | 12243531 | 12329103 | 12004695 | 0 | 340000 | 340000 | 12344695 | 12003108 | -341587 | -14397 | 13 | 0 | 0 | 51988 | 0 | 0 | 0 | 192434 | 111954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6723 | 0 | 0 | 0 | 1786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7736 | 111954 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-02-06 | QTR3 | 25/26 | 2025-04-15 | QTR4 | 24/25 | 636 | 10090244.35 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 30 | 0 | 0 | -260667 | 0 |  | CO
06CO | 06 | T6562 | 44393715201 | 2023-03-29 | QTR3 | 22/23 | 6 | 0 | 400 | 455 | 384 | 71 | 0 | 0 | 55 | 0 | 9816354 | 102429 | 9713925 | 9816354 | 9814725 | 0 | 320000 | 320000 | 10134725 | 9792214 | -342511 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-08 | QTR1 | 25/26 | 2025-01-20 | QTR3 | 24/25 | 613 | 10415642.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6564 | 44599515201 | 2023-12-06 | QTR2 | 23/24 | 2 | 2 | 240 | 259 | 219 | 40 | 0 | 0 | 19 | 0 | 2427793 | 50000 | 2377793 | 2522356 | 2377282 | 0 | 100000 | 100000 | 2477282 | 2374390 | -102891 | 94563 | 5 | 0 | 0 | 13136 | 0 | 0 | 0 | 34463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54683 | 3620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102281 | 3620 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 | 2025-06-19 | QTR4 | 24/25 | 636 | 2381685.3 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6565 | 44389815202 | 2023-02-22 | QTR3 | 22/23 | 3 | 3 | 480 | 626 | 584 | 42 | 0 | 0 | 110 | 36 | 17424162 | 150000 | 17274162 | 17775584 | 17807123 | 0 | 360000 | 360000 | 18167123 | 17736459 | -430664 | 351422 | 80 | 0 | 0 | 84168 | 0 | 0 | 36 | 237134 | 22708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 443354 | 22708 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 | 2025-05-09 | QTR4 | 24/25 | 636 | 16704094.5 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6567 | 44757415201 | 2024-05-22 | QTR4 | 23/24 | 2 | 1 | 197 | 320 | 313 | 7 | 0 | 0 | 123 | 0 | 1669000 | 50000 | 1619000 | 1695000 | 1692054 | 0 | 0 | 0 | 1692054 | 1691797 | -258 | 26000 | 98 | 0 | 0 | 15742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15742 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-03-09 | QTR3 | 25/26 | 2026-01-30 | QTR3 | 25/26 | 613 | 1801028.4 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6568 | 44393225201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 154 | 185 | 179 | 6 | 0 | 0 | 31 | 0 | 1068800 | 50000 | 1018800 | 1068800 | 1002901 | 0 | 0 | 0 | 1002901 | 1002859 | -41 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F832482227 | TRAFFICO LLC | N/A | N/A | N/A | N/A | 2026-01-22 | QTR3 | 25/26 | 2025-10-16 | QTR2 | 25/26 | 613 | 1151283.4 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6573 | 44599115201 | 2023-12-06 | QTR2 | 23/24 | 4 | 3 | 450 | 488 | 422 | 66 | 0 | 0 | 38 | 0 | 7944520 | 85047 | 7859473 | 7965978 | 7740756 | 0 | 320000 | 320000 | 8060756 | 7730600 | -330157 | 21458 | 15 | 0 | 0 | 10477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2205 | 2205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12682 | 2205 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 | 2025-08-07 | QTR1 | 25/26 | 636 | 8387398.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6574 | 44780515201 | 2023-10-25 | QTR2 | 23/24 | 2 | 2 | 300 | 333 | 284 | 49 | 0 | 0 | 33 | 0 | 3338573 | 50000 | 3288573 | 3388573 | 3361643 | 0 | 100000 | 100000 | 3461643 | 3354655 | -106988 | 50000 | 23 | 0 | 0 | 12008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33215 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-10-14 | QTR2 | 25/26 | 2025-03-27 | QTR3 | 24/25 | 613 | 3605553.8 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6575 | 44780615201 | 2024-01-31 | QTR3 | 23/24 | 2 | 1 | 200 | 303 | 303 | 0 | 0 | 0 | 103 | 0 | 4637389 | 50000 | 4587389 | 4652332 | 4600291 | 0 | 0 | 0 | 4600291 | 4582375 | -2973 | 14943 | 59 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 | 2025-04-01 | QTR4 | 24/25 | 636 | 4247705.35 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6577 | 44390915201 | 2024-04-24 | QTR4 | 23/24 | 2 | 4 | 320 | 382 | 299 | 83 | 0 | 0 | 62 | 0 | 4280927 | 50000 | 4230927 | 4380927 | 4298470 | 0 | 180000 | 180000 | 4478470 | 4296065 | -182405 | 100000 | 51 | 0 | 0 | 25028 | 0 | 0 | 0 | 21810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22967 | 0 | 0 | 0 | 13118 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82924 | 2195 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 | 2025-12-05 | QTR2 | 25/26 | 613 | 4677512.3 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6580 | 44600015201 | 2024-04-24 | QTR4 | 23/24 | 3 | 4 | 380 | 458 | 458 | 0 | 0 | 0 | 78 | 0 | 5947099 | 61718 | 5885381 | 6376641 | 6242028 | 0 | 0 | 0 | 6242028 | 6225782 | -16246 | 429541 | 35 | 0 | 0 | 266153 | 1847 | 0 | 0 | 30029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160523 | 0 | 0 | 0 | 2939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459644 | 1847 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 | 2026-02-04 | QTR3 | 25/26 | 636 | 6394668.5 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6584 | 44391215201 | 2024-03-27 | QTR3 | 23/24 | 3 | 5 | 380 | 430 | 360 | 70 | 0 | 0 | 50 | 0 | 8558846 | 77205 | 8481641 | 8890402 | 8748106 | 0 | 220000 | 220000 | 8968106 | 8742165 | -225941 | 331556 | 27 | 0 | 0 | 69085 | 0 | 0 | 0 | 250233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65727 | 7495 | 0 | 0 | 7079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392125 | 7495 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 | 2025-10-29 | QTR2 | 25/26 | 613 | 7821851.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6598 | 44780415201 | 2024-09-25 | QTR1 | 24/25 | 2 | 1 | 240 | 271 | 220 | 51 | 0 | 0 | 31 | 0 | 2627713 | 50000 | 2577713 | 2705308 | 2578007 | 0 | 120000 | 120000 | 2698007 | 2578006 | -120001 | 77594 | 23 | 0 | 0 | 11001 | 0 | 0 | 0 | 66593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77594 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 | 2025-10-08 | QTR2 | 25/26 | 636 | 3026337.1 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6L20 | 25054885201 | 2022-05-26 | QTR4 | 21/22 | 9 | 6 | 800 | 926 | 890 | 36 | 0 | 0 | 126 | 0 | 28158187 | 150000 | 28008187 | 28920235 | 27890563 | 0 | 120000 | 120000 | 28010563 | 27701758 | -239034 | 762049 | 79 | 0 | 0 | 54216 | 11723 | 0 | 0 | 229137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747305 | 11723 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-13 | QTR3 | 25/26 | 2025-07-07 | QTR1 | 25/26 | 636 | 23137912.5 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M86 | 43351125201 | 2021-05-27 | QTR4 | 20/21 | 3 | 13 | 1020 | 1267 | 1212 | 55 | 0 | 0 | 158 | 89 | 41366428 | 150000 | 41216428 | 43068537 | 43251556 | 0 | 1960000 | 1960000 | 45211556 | 43282192 | -173492 | 1702108 | 104 | 0 | 0 | 601267 | 0 | 0 | 0 | 386677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 685738 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1678869 | 0 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 | 2025-03-12 | QTR3 | 24/25 | 613 | 33950112.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 54 | 0 | 0 | -94401 | 0 |  | DO
06DO | 06 | E6N17 | 44716515201 | 2021-09-13 | QTR1 | 21/22 | 5 | 12 | 900 | 1272 | 1272 | 0 | 0 | 0 | 195 | 177 | 66054600 | 150000 | 65904600 | 66794016 | 66824078 | 0 | 1200000 | 1200000 | 68024078 | 67015448 | -977158 | 739416 | 132 | 0 | 0 | 168972 | 0 | 0 | 177 | 1395729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042425 | 0 | 0 | 0 | 396899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -994258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 705319 | 0 | F834649779 | AGI DE MOYA JOINT VENTURE | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 | 2025-07-25 | QTR1 | 25/26 | 636 | 34964142.28 | B5:B5:B5::::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 0 | 63 | 0 | 0 | -1304449 | 0 |  | DO
06DO | 06 | E6O12 | 44391925201 | 2023-05-25 | QTR4 | 22/23 | 3 | 1 | 280 | 309 | 263 | 46 | 0 | 0 | 29 | 0 | 2869869 | 50000 | 2819869 | 2869869 | 2778313 | 0 | 140000 | 140000 | 2918313 | 2778250 | -140063 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 | 2025-04-24 | QTR4 | 24/25 | 636 | 2865779.1 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O17 | 43029169201 | 2022-06-13 | QTR4 | 21/22 | 2 | 3 | 628 | 1156 | 1148 | 8 | 0 | 0 | 384 | 144 | 7237000 | 51988 | 7185012 | 7269318 | 7237180 | 0 | 0 | 0 | 7237180 | 0 | -7237180 | 32318 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 19850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 32318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 52168 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 | 2025-10-23 | QTR2 | 25/26 | 636 | 5284476.93 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 123 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O81 | 44598815201 | 2024-03-28 | QTR3 | 23/24 | 1 | 1 | 250 | 259 | 222 | 37 | 0 | 0 | 9 | 0 | 3370711 | 50000 | 3320711 | 3853261 | 3033601 | 0 | 120000 | 120000 | 3153601 | 3032315 | -121286 | 482550 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 482550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482550 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 | 2025-08-15 | QTR1 | 25/26 | 613 | 3432003 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6P13 | 43029189201 | 2024-04-22 | QTR4 | 23/24 | 2 | 0 | 400 | 475 | 459 | 16 | 0 | 0 | 75 | 0 | 1315382 | 50000 | 1265382 | 1315382 | 1284180 | 0 | 0 | 0 | 1284180 | 0 | -1284180 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-11-13 | QTR2 | 25/26 | 2025-09-19 | QTR1 | 25/26 | 636 | 1725000 | Y | DESIGN/BUILD PROJECT | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6P23 | 44391115201 | 2024-03-28 | QTR3 | 23/24 | 1 | 7 | 340 | 363 | 320 | 43 | 0 | 0 | 23 | 0 | 5790735 | 50000 | 5740735 | 6121430 | 5667306 | 0 | 100000 | 100000 | 5767306 | 5665707 | -101599 | 330695 | 13 | 0 | 0 | 58475 | 0 | 0 | 0 | 97436 | 21191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47458 | 32917 | 0 | 0 | 0 | 0 | 0 | 0 | 316829 | 54108 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 | 2025-11-21 | QTR2 | 25/26 |  | 4862238.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7396 | 41673245201 | 2019-07-31 | QTR1 | 19/20 | 4 | 12 | 1200 | 1366 | 1366 | 0 | 0 | 0 | 166 | 0 | 55832153 | 444272 | 55387881 | 56499915 | 56120655 | 0 | 875160 | 875160 | 56995815 | 56570953 | -113501 | 667762 | 87 | 0 | 0 | 537977 | 184519 | 0 | 0 | 204897 | 116725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835048 | 301244 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 | 2023-07-17 | QTR1 | 23/24 | 798 | 63202968.19 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 0 | 79 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7472 | 43182125201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 1200 | 1362 | 1223 | 139 | 0 | 0 | 138 | 24 | 85239705 | 150000 | 85089705 | 94443373 | 95456225 | 0 | 0 | 0 | 95456225 | 95322196 | 2218662 | 9203668 | 61 | 0 | 0 | 459126 | 0 | 0 | 21 | 3062413 | 383024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 5033268 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 177538 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 8284381 | 1601156 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 | 2025-02-28 | QTR3 | 24/25 | 714 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 77 | 0 | 0 | -1334779 | 0 |  | CO
07CO | 07 | T7505 | 44166115201 | 2023-05-24 | QTR4 | 22/23 | 2 | 6 | 450 | 530 | 530 | 0 | 0 | 0 | 80 | 0 | 13856415 | 100000 | 13756415 | 13819912 | 13656236 | 0 | 0 | 0 | 13656236 | 13594713 | -2106 | -36503 | 45 | 0 | 0 | 25728 | 22538 | 0 | 0 | -116398 | 38900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -90670 | 61438 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-15 | QTR3 | 25/26 | 2025-05-19 | QTR4 | 24/25 | 796 | 14165000 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7507 | 44600915201 | 2023-05-17 | QTR4 | 22/23 | 2 | 4 | 700 | 758 | 563 | 195 | 0 | 0 | 93 | -35 | 22407724 | 150000 | 22257724 | 24195428 | 26279346 | 0 | -10000 | -10000 | 26269346 | 25478372 | -2078 | 1787704 | 50 | 0 | 0 | -250600 | 0 | 0 | 0 | 189104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21834 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2026-02-10 | QTR3 | 25/26 | 2025-06-06 | QTR4 | 24/25 | 714 | 23830100 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7509 | 44588615201 | 2023-02-22 | QTR3 | 22/23 | 1 | 3 | 225 | 324 | 324 | 0 | 0 | 0 | 99 | 0 | 8085082 | 90000 | 7995082 | 8115381 | 7967342 | 0 | 0 | 0 | 7967342 | 7885022 | -54392 | 30299 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 4879 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 | 2024-11-21 | QTR2 | 24/25 | 799 | 9550800 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7512 | 44334715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 3 | 210 | 477 | 477 | 0 | 0 | 0 | 230 | 37 | 6290573 | 50000 | 6240573 | 6754957 | 7072599 | 0 | 0 | 0 | 7072599 | 6755948 | -125 | 464384 | 209 | 0 | 20 | 65635 | 0 | 0 | 7 | 7306 | 0 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 157426 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-04-28 | QTR4 | 24/25 | 796 | 6135700 |  |  | 25 | 31 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7514 | 45069315201 | 2023-09-27 | QTR1 | 23/24 | 1 | 2 | 150 | 311 | 311 | 0 | 0 | 0 | 161 | 0 | 2469300 | 50000 | 2419300 | 2490043 | 2487609 | 0 | 0 | 0 | 2487609 | 2486604 | -1005 | 20743 | 111 | 0 | 0 | 31460 | 0 | 0 | 0 | 8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39921 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 | 2025-04-03 | QTR4 | 24/25 | 796 | 2285000 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7515 | 44803615201 | 2023-06-14 | QTR4 | 22/23 | 2 | 10 | 300 | 571 | 566 | 5 | 0 | 0 | 271 | 0 | 13134873 | 115000 | 13019873 | 13851674 | 14146391 | 0 | 0 | 0 | 14146391 | 14074398 | -29541 | 716801 | 160 | 9 | 0 | 197732 | 0 | 0 | 0 | 430314 | 44320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 640481 | 44320 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-03-11 | QTR3 | 25/26 | 2025-07-22 | QTR1 | 25/26 | 799 | 13139100 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7516 | 44006315201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 230 | 430 | 430 | 0 | 0 | 0 | 181 | 19 | 6730280 | 60000 | 6670280 | 6779810 | 6697913 | 0 | 0 | 0 | 6697913 | 6687877 | -10036 | 49529 | 152 | 0 | 0 | 9983 | 0 | 0 | 19 | 66053 | 39546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 19 | 76037 | 39546 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 | 2024-12-04 | QTR2 | 24/25 | 798 | 7050800 |  |  | 19 | 29 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7523 | 44697315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 196 | 316 | 315 | 1 | 0 | 0 | 120 | 0 | 2049777 | 50000 | 1999777 | 2049777 | 2101379 | 0 | 0 | 0 | 2101379 | 2098362 | -3017 | 0 | 95 | 0 | 0 | 2635 | 0 | 0 | 0 | 36652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39287 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 | 2025-03-14 | QTR3 | 24/25 | 799 | 2385840 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7529 | 44109835201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 200 | 262 | 262 | 0 | 0 | 0 | 62 | 0 | 1336107 | 50000 | 1286107 | 1336107 | 1267198 | 0 | 0 | 0 | 1267198 | 1266909 | -289 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-05-28 | QTR4 | 24/25 | 796 | 1581132 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7538 | 44939815201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 100 | 122 | 122 | 0 | 0 | 0 | 22 | 0 | 545691 | 22198 | 523493 | 545691 | 518518 | 0 | 0 | 0 | 518518 | 518518 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-05-08 | QTR4 | 24/25 | 799 | 611133 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7544 | 44025015201 | 2024-04-17 | QTR4 | 23/24 | 1 | 2 | 240 | 275 | 259 | 16 | 0 | 0 | 35 | 0 | 7475300 | 55000 | 7420300 | 7428809 | 7644411 | 0 | 0 | 0 | 7644411 | 7629621 | -14790 | -46492 | 13 | 0 | 0 | 569898 | 120795 | 0 | 0 | -594629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24731 | 120795 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 | 2025-07-14 | QTR1 | 25/26 | 798 | 8386992 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7548 | 44752215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 4 | 140 | 214 | 213 | 1 | 0 | 0 | 17 | 57 | 2173906 | 50000 | 2123906 | 2247825 | 2217265 | 0 | 0 | 0 | 2217265 | 2216464 | -801 | 73919 | 13 | 0 | 36 | 77735 | 0 | 0 | 21 | 8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15816 | 15816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 101654 | 15816 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2026-02-06 | QTR3 | 25/26 | 2025-08-06 | QTR1 | 25/26 | 798 | 1912820 |  |  | 36 | 4 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7550 | 45241215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 97 | 113 | 113 | 0 | 0 | 0 | 16 | 0 | 654321 | 27192 | 627129 | 654321 | 610593 | 0 | 0 | 0 | 610593 | 610593 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-05 | QTR2 | 25/26 | 2025-04-28 | QTR4 | 24/25 | 796 | 826944 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7555 | 44794815201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 205 | 224 | 157 | 67 | 0 | 0 | 19 | 0 | 5942087 | 79500 | 5862587 | 5942922 | 5968673 | 0 | 0 | 0 | 5968673 | 5968280 | -393 | 835 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 | 2025-10-22 | QTR2 | 25/26 | 798 | 7672150 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7573 | 45096915201 | 2025-03-26 | QTR3 | 24/25 | 1 | 2 | 65 | 88 | 87 | 1 | 0 | 0 | 23 | 0 | 365071 | 21000 | 344071 | 370411 | 359883 | 0 | 0 | 0 | 359883 | 354442 | -5442 | 5340 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 6494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6494 | 0 | F931411815 | LAKEVIEW CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-08-29 | QTR1 | 25/26 | 799 | 528390 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7N56 | 43726425201 | 2022-05-27 | QTR4 | 21/22 | 1 | 8 | 650 | 716 | 649 | 67 | 0 | 0 | 66 | 0 | 19975000 | 130000 | 19845000 | 20432970 | 21351585 | 0 | 0 | 0 | 21351585 | 21249872 | -59788 | 457970 | 29 | 0 | 0 | 362725 | 71071 | 0 | 0 | 34483 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125141 | 125141 | 0 | 0 | 0 | 0 | 0 | 0 | 586579 | 198586 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-01-20 | QTR3 | 25/26 | 2024-06-21 | QTR4 | 23/24 | 798 | 15858300 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P77 | 44146315201 | 2023-05-10 | QTR4 | 22/23 | 1 | 2 | 150 | 247 | 247 | 0 | 0 | 0 | 70 | 27 | 3366760 | 50000 | 3316760 | 3493112 | 3363518 | 0 | 300000 | 300000 | 3663518 | 3363518 | -300000 | 126352 | 45 | 0 | 22 | 20037 | 0 | 0 | 5 | 4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 135426 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-07-30 | QTR1 | 25/26 | 2025-02-05 | QTR3 | 24/25 | 796 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT | 27 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q08 | 44761515201 | 2023-05-10 | QTR4 | 22/23 | 2 | 7 | 330 | 477 | 477 | 0 | 0 | 0 | 147 | 0 | 6147921 | 52728 | 6095192 | 6373747 | 6357061 | 0 | 0 | 0 | 6357061 | 6311539 | -1706 | 225826 | 61 | 0 | 0 | -18522 | 0 | 0 | 0 | 84658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84397 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 42409 | 34565 | 0 | 0 | 0 | 0 | 62 | 0 | 192942 | 34565 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2026-01-20 | QTR3 | 25/26 | 2025-04-28 | QTR4 | 24/25 | 714 | 5831100 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q31 | 44384115201 | 2023-12-13 | QTR2 | 23/24 | 1 | 3 | 125 | 238 | 240 | -2 | 2 | 0 | 113 | 0 | 1681476 | 50000 | 1631476 | 1805476 | 1410753 | -3398 | 0 | -3398 | 1407355 | 1374355 | 0 | 124000 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2024-12-10 | QTR2 | 24/25 | 796 | 1673100 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q39 | 44582815201 | 2024-02-14 | QTR3 | 23/24 | 2 | 0 | 284 | 330 | 326 | 4 | 0 | 0 | 46 | 0 | 1714027 | 50000 | 1664027 | 1714027 | 1704720 | 0 | 0 | 0 | 1704720 | 1704720 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 | 2025-08-26 | QTR1 | 25/26 | 796 | 3483914 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q53 | 44583015201 | 2024-05-08 | QTR4 | 23/24 | 1 | 2 | 230 | 260 | 210 | 50 | 0 | 0 | 30 | 0 | 1599000 | 50000 | 1549000 | 1601196 | 1343560 | 0 | 0 | 0 | 1343560 | 1341365 | 0 | 2196 | 17 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-07-08 | QTR1 | 25/26 | 2025-04-13 | QTR4 | 24/25 | 799 | 1936163 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q55 | 44165115201 | 2024-03-13 | QTR3 | 23/24 | 1 | 3 | 150 | 272 | 272 | 0 | 0 | 0 | 93 | 29 | 4066019 | 50000 | 4016019 | 4201769 | 4164473 | 0 | 0 | 0 | 4164473 | 4071753 | -92719 | 135750 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 95050 | 87989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 6641 | 0 | 0 | 0 | 0 | 0 | 19 | 29 | 149452 | 87989 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 | 2025-06-01 | QTR4 | 24/25 | 799 | 4234476 |  |  | 29 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q75 | 45288915201 | 2024-06-12 | QTR4 | 23/24 | 1 | 2 | 80 | 151 | 151 | 0 | 0 | 0 | 71 | 0 | 1296714 | 50000 | 1246714 | 1381899 | 1384246 | 0 | 0 | 0 | 1384246 | 1371017 | 0 | 85185 | 50 | 0 | 0 | 71957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71957 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 | 2025-01-27 | QTR3 | 24/25 | 798 | 1695805 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q94 | 45273615201 | 2024-12-11 | QTR2 | 24/25 | 1 | 0 | 30 | 33 | 29 | 4 | 0 | 0 | 3 | 0 | 259111 | 23000 | 236111 | 259111 | 235124 | 0 | 0 | 0 | 235124 | 235124 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 | 2025-07-14 | QTR1 | 25/26 | 799 | 516283 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R15 | 44138815201 | 2021-01-29 | QTR3 | 20/21 | 4 | 2 | 450 | 724 | 724 | 0 | 0 | 0 | 274 | 0 | 21358193 | 150000 | 21208193 | 21288752 | 21103200 | 0 | 1150000 | 1150000 | 22253200 | 21628021 | -335192 | -69440 | 226 | 0 | 0 | 12752 | 0 | 0 | 0 | 107114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 50426 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-12-11 | QTR2 | 25/26 | 2023-07-28 | QTR1 | 23/24 | 796 | 26431774 | A3:A3:A3:B10 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT | 0 | 48 | 0 | 0 | -69440 | 0 |  | DO
07DO | 07 | E7R21 | 42451335201 | 2021-05-20 | QTR4 | 20/21 | 3 | 16 | 1115 | 1616 | 1308 | 308 | 0 | 0 | 184 | 317 | 81649200 | 150000 | 81499200 | 89787672 | 90056090 | 0 | 0 | 0 | 90056090 | 89818079 | 1620860 | 8138472 | 120 | 0 | 228 | 2666076 | 316345 | 0 | 0 | 1680130 | 35860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316666 | 208207 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 373 | 4996124 | 1011566 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 | 2025-03-08 | QTR3 | 24/25 | 714 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 64 | 0 | 0 | -117901 | 0 |  | DO
07DO | 07 | E7R24 | 44132015201 | 2022-08-04 | QTR1 | 22/23 | 1 | 1 | 580 | 797 | 779 | 18 | 0 | 0 | 217 | 0 | 6997500 | 69934 | 6927567 | 7112720 | 7042786 | 0 | 0 | 0 | 7042786 | 7042581 | -205 | 115220 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 | 2025-03-28 | QTR3 | 24/25 | 798 | 13119000 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R26 | 42925115201 | 2021-06-17 | QTR4 | 20/21 | 5 | 22 | 1100 | 1415 | 1414 | 1 | 0 | 0 | 176 | 139 | 89691574 | 162717 | 89528857 | 96531643 | 96716929 | -45000 | 0 | -45000 | 96671929 | 96896327 | 1490307 | 6840069 | 90 | 0 | 119 | 5277897 | 81590 | 0 | 20 | 1067716 | 347957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49676 | 0 | 0 | 0 | 8310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 6553399 | 429547 | F871503473 | PRINCE-AJAX DDI JV | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 | 2025-07-02 | QTR1 | 25/26 | 714 | 100030998 | B8 | ACC - DESIGN/BUILD - MAJOR | 61 | 86 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R35 | 43983215201 | 2023-05-25 | QTR4 | 22/23 | 3 | 4 | 580 | 697 | 697 | 0 | 0 | 0 | 117 | 0 | 10158800 | 110000 | 10048800 | 10244736 | 10281972 | 0 | 0 | 0 | 10281972 | 10243690 | -3637 | 85936 | 86 | 0 | 0 | 51291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51291 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-01-22 | QTR3 | 25/26 | 2025-06-23 | QTR4 | 24/25 | 798 | 12981331 | LBDB:LBDB | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R40 | 44335825201 | 2024-03-07 | QTR3 | 23/24 | 1 | 2 | 200 | 285 | 274 | 11 | 0 | 0 | 85 | 0 | 1322000 | 50000 | 1272000 | 1334250 | 1257998 | 0 | 0 | 0 | 1257998 | 1250561 | -4137 | 12250 | 46 | 0 | 0 | 4515 | 0 | 0 | 0 | 4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 | 2025-02-03 | QTR3 | 24/25 | 798 | 1543770 | LBDB | LOW BID DESIGN BUILD | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7U08 | 44366515201 | 2024-09-11 | QTR1 | 24/25 | 1 | 1 | 200 | 251 | 251 | 0 | 0 | 0 | 33 | 18 | 3709156 | 50000 | 3659156 | 3709156 | 3454248 | 0 | 0 | 0 | 3454248 | 3454248 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 | 2025-12-10 | QTR2 | 25/26 | 796 | 3944855 |  |  | 18 | 14 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R45 | 43799215201 | 2018-11-15 | QTR2 | 18/19 | 3 | 22 | 928 | 1578 | 1578 | 0 | 0 | 0 | 505 | 145 | 33928239 | 150000 | 33778239 | 47651600 | 47943952 | 0 | 0 | 0 | 47943952 | 47859737 | -39220 | 13723361 | 337 | 0 | 4 | 678065 | 0 | 0 | 0 | 444720 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 11027592 | 0 | 0 | 0 | 1427834 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 145 | 13655217 | 0 | F825435435 | CENTRAL MORRISON COBALT JV | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 | 2023-10-20 | QTR2 | 23/24 | 854 | 41184698.49 |  |  | 0 | 168 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T48 | 43496835201 | 2022-04-19 | QTR4 | 21/22 | 1 | 2 | 1128 | 1286 | 1283 | 3 | 0 | 0 | 125 | 33 | 10781928 | 108430 | 10673498 | 10718856 | 10512572 | 0 | 0 | 0 | 10512572 | 10512572 | 0 | -63072 | 40 | 0 | 33 | -9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28279 | 0 | 0 | 0 | 8634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 27804 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 | 2025-12-18 | QTR2 | 25/26 | 854 | 11904888.56 | A3 | ICC - DESIGN/BUILD - MINOR | 33 | 85 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T83 | 44276415201 | 2022-09-20 | QTR1 | 22/23 | 1 | 4 | 1277 | 1339 | 892 | 447 | 0 | 0 | 128 | -66 | 102999958 | 150000 | 102849958 | 103423210 | 104129622 | 0 | 4744548 | 4744548 | 108874170 | 102351127 | -6249791 | 423252 | 65 | 0 | 0 | 108966 | 0 | 0 | 0 | 78741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37076 | 0 | 0 | 0 | 2530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66 | 227314 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-03-27 | QTR3 | 25/26 | 2025-09-10 | QTR1 | 25/26 | 854 | 121233962.23 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 63 | 0 | -66 | 0 | 0 |  | DO
08DO | 08 | E8U04 | 44602415201 | 2023-03-21 | QTR3 | 22/23 | 3 | 8 | 386 | 505 | 502 | 3 | 0 | 0 | 99 | 20 | 16184460 | 150000 | 16034460 | 17190583 | 16458548 | 0 | 0 | 0 | 16458548 | 16378636 | -46667 | 1006123 | 45 | 0 | 0 | 188590 | 0 | 0 | 0 | 366919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 463107 | 0 | 0 | 0 | 50339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1068954 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-03-14 | QTR3 | 24/25 | 854 | 18390076.74 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U19 | 44588515201 | 2023-04-11 | QTR4 | 22/23 | 2 | 1 | 314 | 523 | 523 | 0 | 0 | 0 | 179 | 30 | 11226810 | 114237 | 11112574 | 11263007 | 11344464 | 0 | 0 | 0 | 11344464 | 11303165 | -5101 | 36197 | 122 | 0 | 0 | 0 | 0 | 0 | 14 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 53038 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-28 | QTR1 | 25/26 | 2025-04-11 | QTR4 | 24/25 | 854 | 11461890.59 |  |  | 30 | 57 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U32 | 44925335201 | 2023-05-09 | QTR4 | 22/23 | 2 | 1 | 401 | 505 | 499 | 6 | 0 | 0 | 104 | 0 | 3649071 | 50000 | 3599071 | 3673424 | 3464348 | 0 | 0 | 0 | 3464348 | 3464348 | 0 | 24353 | 27 | 0 | 0 | 7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 11812 | 0 | 0 | 0 | 24353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 43886 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 | 2025-05-20 | QTR4 | 24/25 | 854 | 4370418.34 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U46 | 43854815201 | 2024-05-14 | QTR4 | 23/24 | 1 | 0 | 497 | 543 | 254 | 289 | 0 | 0 | 46 | 0 | 4734726 | 79759 | 4654966 | 4734726 | 4628034 | 0 | 0 | 0 | 4628034 | 4628034 | 0 | 0 | 13 | 0 | 0 | 14990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 | 2025-06-25 | QTR4 | 24/25 | 854 | 8236620.28 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U56 | 44942325201 | 2023-08-22 | QTR1 | 23/24 | 1 | 2 | 240 | 275 | 242 | 33 | 0 | 0 | 47 | -12 | 1804313 | 50000 | 1754313 | 1864511 | 1827419 | 0 | 37398 | 37398 | 1864817 | 1827419 | -37398 | 60198 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 | 2025-03-24 | QTR3 | 24/25 | 854 | 1786238.37 | A6 | ICC - BAM/INCENTIVE-DISINCENT | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U67 | 44440215201 | 2023-09-12 | QTR1 | 23/24 | 4 | 7 | 580 | 715 | 656 | 59 | 0 | 0 | 127 | 8 | 24889345 | 150000 | 24739345 | 25770345 | 25416917 | 0 | 0 | 0 | 25416917 | 25256822 | -129095 | 881000 | 76 | 0 | 0 | 57314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 471317 | 0 | 0 | 0 | 439504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 968135 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-16 | QTR3 | 25/26 | 2025-10-31 | QTR2 | 25/26 | 854 | 27205817.87 |  |  | 8 | 51 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U71 | 41592755201 | 2024-02-13 | QTR3 | 23/24 | 1 | 1 | 181 | 339 | 326 | 13 | 0 | 0 | 133 | 25 | 2794276 | 60345 | 2733930 | 2537251 | 2444066 | 0 | 0 | 0 | 2444066 | 2444066 | 0 | -257025 | 84 | 0 | 25 | 59995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | -197030 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-10-13 | QTR2 | 25/26 | 2025-09-17 | QTR1 | 25/26 | 854 | 6003501.55 |  |  | 25 | 49 | 0 | 0 | -257025 | 0 |  | DO
08DO | 08 | E8U73 | 44206215201 | 2024-03-12 | QTR3 | 23/24 | 2 | 5 | 280 | 321 | 315 | 6 | 0 | 0 | 41 | 0 | 13684469 | 150000 | 13534469 | 13793245 | 13317036 | 0 | 0 | 0 | 13317036 | 13288255 | -24020 | 108776 | 20 | 0 | 0 | 15607 | 0 | 0 | 0 | 43669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36331 | 0 | 0 | 0 | 131202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226808 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 | 2025-07-18 | QTR1 | 25/26 | 854 | 19932483.01 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U91 | 44917545201 | 2024-06-11 | QTR4 | 23/24 | 1 | 4 | 242 | 308 | 302 | 6 | 0 | 0 | 66 | 0 | 4804962 | 50000 | 4754962 | 4908714 | 4813444 | 0 | 0 | 0 | 4813444 | 4807156 | -521 | 103751 | 36 | 0 | 0 | 46708 | 0 | 0 | 0 | 21070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791 | 0 | 0 | 0 | 55206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123774 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 | 2025-07-21 | QTR1 | 25/26 | 854 | 4334607.7 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U95 | 44917535201 | 2024-04-09 | QTR4 | 23/24 | 1 | 0 | 140 | 176 | 173 | 3 | 0 | 0 | 36 | 0 | 1605678 | 50000 | 1555678 | 1605678 | 1663792 | 0 | 0 | 0 | 1663792 | 1663792 | 0 | 0 | 18 | 0 | 0 | 23069 | 0 | 0 | 0 | 5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49911 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 | 2025-04-25 | QTR4 | 24/25 | 854 | 1739459.6 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8V77 | 45211115201 | 2025-02-19 | QTR3 | 24/25 | 1 | 0 | 200 | 207 | 108 | 99 | 0 | 0 | 7 | 0 | 1699787 | 50000 | 1649787 | 1699787 | 1444210 | 0 | 0 | 0 | 1444210 | 1444159 | -52 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 | 2025-10-29 | QTR2 | 25/26 | 854 | 1780237.34 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0