## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 175529198 | 174014913 | 178799243 | 179210948 | -92500 | 178790526 | 2.744% | 96% | 3146511 | 1.808% | 3270046 | 1.863% | 6752 | 1726 | 25.56% | 676 | 10.01% | 546 | 8.086% | 553 | 8.19% | 7851 | 16.28% | 10150 | 9952 | 7550 | 11.82% | 72%
| District Let | 436776592 | 434338580 | 443557226 | 445702496 | 941500 | 448900194 | 3.353% | 96.88% | 6260769 | 1.441% | 6930632 | 1.587% | 9860 | 1987 | 20.15% | 841 | 8.529% | 45 | 0.4564% | 336 | 3.408% | 10241 | 3.864% | 13042 | 12148 | 9320 | -5.477% | 90.62%
| All Contracts | 612305790 | 608353493 | 622356469 | 624913444 | 849000 | 627690720 | 3.179% | 96.49% | 9407280 | 1.546% | 10200678 | 1.666% | 16612 | 3713 | 22.35% | 1517 | 9.132% | 591 | 3.558% | 889 | 5.352% | 18092 | 8.909% | 23192 | 22100 | 16870 | 1.553% | 82.46%
2 | Central Let | 609019890 | 604213418 | 667240103 | 684188558 | 0 | 685849724 | 13.51% | 86.67% | 59318751 | 9.818% | 58220211 | 9.56% | 18124 | 6204 | 34.23% | 2960 | 16.33% | 2277 | 12.56% | 5018 | 27.69% | 25419 | 40.25% | 32624 | 31708 | 22544 | 24.39% | 63.33%
| District Let | 100491942 | 99491228 | 119821585 | 121613511 | 0 | 120550364 | 21.17% | 70% | 19659220 | 19.76% | 19329643 | 19.24% | 4937 | 1019 | 20.64% | 645 | 13.06% | 510 | 10.33% | 1677 | 33.97% | 7124 | 44.3% | 8365 | 8169 | 6505 | 31.76% | 50%
| All Contracts | 709511832 | 703704646 | 787061688 | 805802069 | 0 | 806400088 | 14.59% | 84.29% | 78977971 | 11.22% | 77549854 | 10.93% | 23061 | 7223 | 31.32% | 3605 | 15.63% | 2787 | 12.09% | 6695 | 29.03% | 32543 | 41.12% | 40989 | 39877 | 29049 | 25.97% | 61.43%
3 | Central Let | 212801497 | 210481267 | 220859517 | 225278374 | 0 | 227122212 | 7.906% | 81.08% | 8601691 | 4.087% | 8058020 | 3.787% | 10195 | 3275 | 32.12% | 1742 | 17.09% | 1683 | 16.51% | 1367 | 13.41% | 13245 | 29.92% | 17779 | 17860 | 12843 | 25.97% | 62.16%
| District Let | 117369892 | 115658587 | 118002056 | 117280742 | 0 | 116301064 | 0.5555% | 100% | 822140 | 0.7108% | 632165 | 0.5386% | 6594 | 1817 | 27.56% | 1102 | 16.71% | 1426 | 21.63% | 400 | 6.066% | 8420 | 27.69% | 10848 | 10601 | 7682 | 16.5% | 65.62%
| All Contracts | 330171389 | 326139854 | 338861573 | 342559116 | 0 | 343423276 | 5.299% | 89.86% | 9423831 | 2.89% | 8690185 | 2.632% | 16789 | 5092 | 30.33% | 2844 | 16.94% | 3109 | 18.52% | 1767 | 10.52% | 21665 | 29.04% | 28627 | 28461 | 20525 | 22.25% | 63.77%
4 | Central Let | 218745831 | 216494748 | 228267034 | 227365001 | 210000 | 227402570 | 5.038% | 89.29% | 9257445 | 4.276% | 10041932 | 4.591% | 10315 | 2366 | 22.94% | 968 | 9.384% | 1418 | 13.75% | 418 | 4.052% | 12151 | 17.8% | 15351 | 14987 | 11653 | 12.97% | 82.14%
| District Let | 273063541 | 271488879 | 303504415 | 301859625 | 56000 | 301154285 | 10.93% | 92.31% | 30308149 | 11.16% | 30398745 | 11.13% | 7841 | 1706 | 21.76% | 684 | 8.723% | 1287 | 16.41% | 615 | 7.843% | 9743 | 24.26% | 11959 | 11529 | 9139 | 16.55% | 92.31%
| All Contracts | 491809372 | 487983627 | 531771449 | 529224626 | 266000 | 528556855 | 8.314% | 90.74% | 39565594 | 8.108% | 40440677 | 8.223% | 18156 | 4072 | 22.43% | 1652 | 9.099% | 2705 | 14.9% | 1033 | 5.69% | 21894 | 20.59% | 27310 | 26516 | 20792 | 14.52% | 87.04%
5 | Central Let | 440139683 | 436505742 | 464130662 | 466382291 | 897177 | 465161162 | 6.565% | 94.59% | 22131339 | 5.07% | 24560711 | 5.58% | 13497 | 3195 | 23.67% | 2820 | 20.89% | 62 | 0.4594% | 1911 | 14.16% | 15470 | 14.62% | 22026 | 21694 | 15679 | 16.17% | 78.38%
| District Let | 445974540 | 443469958 | 466332924 | 467006560 | 25000 | 467496766 | 5.418% | 92.31% | 20699669 | 4.668% | 20358384 | 4.565% | 10447 | 1987 | 19.02% | 2806 | 26.86% | 42 | 0.402% | 1203 | 11.52% | 11692 | 11.92% | 16738 | 16292 | 11499 | 10.07% | 87.18%
| All Contracts | 886114223 | 879975700 | 930463586 | 933388851 | 922177 | 932657928 | 5.987% | 93.42% | 42831008 | 4.867% | 44919095 | 5.069% | 23944 | 5182 | 21.64% | 5626 | 23.5% | 104 | 0.4343% | 3114 | 13.01% | 27162 | 13.44% | 38764 | 37986 | 27178 | 13.51% | 82.89%
6 | Central Let | 131450574 | 129944220 | 133878713 | 131363167 | 3500000 | 131078375 | 0.8728% | 100% | 2479042 | 1.908% | 2428138 | 1.847% | 6781 | 790 | 11.65% | 469 | 6.916% | 22 | 0.3244% | 105 | 1.548% | 6908 | 1.873% | 8150 | 7217 | 5958 | -12.14% | 100%
| District Let | 157939093 | 157187105 | 161988229 | 159765616 | 3640000 | 151274509 | -3.762% | 100% | 3987153 | 2.537% | 4049136 | 2.564% | 4898 | 579 | 11.82% | 379 | 7.738% | 0 | 0% | 410 | 8.371% | 5308 | 8.371% | 6406 | 6155 | 5197 | 6.105% | 88.89%
| All Contracts | 289389667 | 287131325 | 295866942 | 291128783 | 7140000 | 282352884 | -1.664% | 100% | 6466195 | 2.252% | 6477274 | 2.238% | 11679 | 1369 | 11.72% | 848 | 7.261% | 22 | 0.1884% | 515 | 4.41% | 12216 | 4.598% | 14556 | 13372 | 11155 | -4.487% | 96.67%
7 | Central Let | 562969180 | 558272503 | 588435660 | 596478546 | 865160 | 593014378 | 6.223% | 85.71% | 21404752 | 3.834% | 25466477 | 4.524% | 14805 | 2671 | 18.04% | 1332 | 8.997% | 276 | 1.864% | 938 | 6.336% | 16019 | 8.2% | 20096 | 21194 | 17191 | 16.12% | 82.86%
| District Let | 859304175 | 857302441 | 932652467 | 934233265 | 4230000 | 937244781 | 9.325% | 91.3% | 67181437 | 7.836% | 73348293 | 8.536% | 9444 | 2226 | 23.57% | 924 | 9.784% | 420 | 4.447% | 1868 | 19.78% | 11732 | 24.23% | 14457 | 13970 | 10820 | 14.57% | 91.3%
| All Contracts | 1422273355 | 1415574944 | 1521088127 | 1530711811 | 5095160 | 1530259159 | 8.102% | 87.93% | 88586189 | 6.258% | 98814770 | 6.948% | 24249 | 4897 | 20.19% | 2256 | 9.303% | 696 | 2.87% | 2806 | 11.57% | 27751 | 14.44% | 34553 | 35164 | 28011 | 15.51% | 86.21%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 316770984 | 314958212 | 335042535 | 333923456 | 5931650 | 331780544 | 5.341% | 94.12% | 17935662 | 5.695% | 18271551 | 5.768% | 9232 | 1153 | 12.49% | 880 | 9.532% | 184 | 1.993% | 391 | 4.235% | 9807 | 6.228% | 11664 | 10204 | 8171 | -11.49% | #VALUE!
| All Contracts | 316770984 | 314958212 | 335042535 | 333923456 | 5931650 | 331780544 | 5.341% | 94.12% | 17935662 | 5.695% | 18271551 | 5.768% | 9232 | 1153 | 12.49% | 880 | 9.532% | 184 | 1.993% | 391 | 4.235% | 9807 | 6.228% | 11664 | 10204 | 8171 | -11.49% | 100%
Totals This Qtr | Central Let | 2350655853 | 2329926811 | 2481610932 | 2510266885 | 5379837 | 2508418947 | 7.661% | 89.3% | 126339531 | 5.422% | 132045535 | 5.617% | 80469 | 20227 | 25.14% | 10967 | 13.63% | 6284 | 7.809% | 10310 | 12.81% | 97063 | 20.62% | 126176 | 124612 | 93418 | 16.09% | 74.49%
| District Let | 2707690759 | 2693894990 | 2880901437 | 2881385271 | 14824150 | 2874702507 | 6.712% | 93.62% | 166854199 | 6.194% | 173318549 | 6.401% | 63253 | 12474 | 19.72% | 8261 | 13.06% | 3914 | 6.188% | 6900 | 10.91% | 74067 | 17.1% | 93479 | 89068 | 68333 | 8.031% | 84.57%
| All Contracts | 5058346612 | 5023821801 | 5362512369 | 5391652156 | 20203987 | 5383121454 | 7.152% | 91.18% | 293193730 | 5.836% | 305364084 | 6.037% | 143722 | 32701 | 22.75% | 19228 | 13.38% | 10198 | 7.096% | 17210 | 11.97% | 171130 | 19.07% | 219655 | 213680 | 161751 | 12.54% | 78.89%
Totals Previous Quarter | Central Let | 1548065050 | 1534863083 | 1638738499 | 1656700096 | 3972660 | 1658175161 | 8.034% | 90.53% | 89001418 | 5.799% | 91763906 | 5.928% | 55571 | 14345 | 25.81% | 7621 | 13.71% | 3666 | 6.597% | 6882 | 12.38% | 66119 | 18.98% | 85881 | 83238 | 61272 | 10.26% | 77.51%
| District Let | 1750826020 | 1741338629 | 1852202104 | 1850349553 | 10894446 | 1841525925 | 5.753% | 95.49% | 98264428 | 5.643% | 101333953 | 5.788% | 46654 | 9038 | 19.37% | 6051 | 12.97% | 3471 | 7.44% | 3621 | 7.761% | 53746 | 15.2% | 67576 | 64827 | 49738 | 6.61% | 86.47%
| All Contracts | 3298891070 | 3276201712 | 3490940603 | 3507049649 | 14867106 | 3499701086 | 6.822% | 92.72% | 187265846 | 5.716% | 193097859 | 5.853% | 102225 | 23383 | 22.87% | 13672 | 13.37% | 7137 | 6.982% | 10503 | 10.27% | 119865 | 17.26% | 153457 | 148065 | 111010 | 8.594% | 81.46%
Totals Fiscal Year 2024/2025 | Central Let | 1279648903 | 1266221414 | 1312978963 | 1321473742 | 2536230 | 1326167192 | 4.734% | 90.72% | 35949687 | 2.839% | 33549474 | 2.622% | 54906 | 16687 | 30.39% | 7064 | 12.87% | 4509 | 8.212% | 6770 | 12.33% | 66185 | 20.54% | 86228 | 84771 | 61020 | 11.14% | 80.93%
| District Let | 1318833837 | 1310154031 | 1361025980 | 1368896349 | 5751239 | 1365653292 | 4.236% | 92.91% | 42375966 | 3.234% | 42720355 | 3.239% | 43619 | 9909 | 22.72% | 5114 | 11.72% | 2675 | 6.133% | 2106 | 4.828% | 48400 | 10.96% | 62882 | 61439 | 46416 | 6.412% | 89.76%
| All Contracts | 2598482740 | 2576375445 | 2674004943 | 2690370091 | 8287469 | 2691820484 | 4.481% | 91.59% | 78325653 | 3.04% | 76269829 | 2.935% | 98525 | 26596 | 26.99% | 12178 | 12.36% | 7184 | 7.292% | 8876 | 9.009% | 114585 | 16.3% | 149110 | 146210 | 107436 | 9.044% | 84.42%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1754 | 41924345201 | 2020-06-10 | QTR4 | 19/20 | 1 | 8 | 1300 | 1542 | 1316 | 82.62% | 1 | 226 | 0 | 0 | 242 | 0 | 44711727 | 150000 | 44561727 | 45332170 | 44869139 | 0 | 0 | 0 | 44869139 | 45508351 | 102.1% | 1 | 2409623 | 620443 | 176 | 66 | 0 | 0 | 75074 | 0 | 0 | 0 | 369025 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65721 | 0 | 0 | 0 | 2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656851 | 70927 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2024-04-12 | QTR4 | 23/24 | 118 | 49671695.98
| 01 | T1778 | 43805915201 | 2021-02-17 | QTR3 | 20/21 | 2 | 5 | 300 | 703 | 703 | 138.7% | 0 | 0 | 0 | 0 | 326 | 77 | 5124974 | 52558 | 5072416 | 5379131 | 5343032 | 0 | 0 | 0 | 5343032 | 5363673 | 105.7% | 1 | 399077 | 254157 | 241 | 46 | 0 | 0 | 44765 | 0 | 39 | 77 | 114092 | 58884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 113116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 77 | 261703 | 58884 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-06-09 | QTR4 | 25/26 |  | 2023-11-08 | QTR2 | 23/24 | 113 | 5113819.4
| 01 | T1801 | 43355055201 | 2022-02-23 | QTR3 | 21/22 | 4 | 11 | 450 | 785 | 785 | 145.6% | 0 | 0 | 0 | 0 | 157 | 178 | 9943982 | 61935 | 9882047 | 10795145 | 10516274 | 0 | 0 | 0 | 10516274 | 10451415 | 105.8% | 1 | 22951 | 851163 | 75 | 55 | 0 | 10 | 59915 | 0 | 14 | 35 | 107389 | 65872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 0 | 0 | 60900 | 0 | 0 | 0 | 314 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 15101 | 0 | 0 | 0 | 0 | 0 | 10 | 133 | 534836 | 45203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 178 | 784204 | 111075 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2026-01-26 | QTR3 | 25/26 |  | 2024-12-23 | QTR2 | 24/25 | 115 | 8613987.04
| 01 | T1807 | 44464115201 | 2023-05-24 | QTR4 | 22/23 | 2 | 8 | 250 | 356 | 355 | 112.4% | 1 | 1 | 0 | 0 | 95 | 11 | 5486544 | 50000 | 5436544 | 5582663 | 5697293 | -30000 | 0 | -30000 | 5667293 | 5634025 | 103.6% | 1 | -212 | 96120 | 56 | 18 | 21 | 11 | 58440 | 0 | 0 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 1490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 11 | 77189 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-18 | QTR3 | 25/26 |  | 2025-04-21 | QTR4 | 24/25 | 118 | 4275732.4
| 01 | T1833 | 44634515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 300 | 472 | 471 | 99.67% | 1 | 1 | 0 | 0 | 172 | 0 | 16756829 | 150000 | 16606829 | 16756829 | 16918647 | 0 | -70500 | -70500 | 16848147 | 16748453 | 100.9% | 1 | -99694 | 0 | 136 | 36 | 0 | 0 | 23670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2023-12-05 | QTR2 | 23/24 | 106 | 17387334.58
| 01 | T1843 | 43695525201 | 2022-07-27 | QTR1 | 22/23 | 1 | 6 | 225 | 443 | 443 | 107.6% | 1 | 0 | 0 | 0 | 201 | 17 | 4165582 | 50000 | 4115582 | 4197230 | 4319692 | 0 | 0 | 0 | 4319692 | 4254744 | 103.4% | 1 | -56953 | 31648 | 155 | 46 | 0 | 17 | 23652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 23652 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-08-27 | QTR1 | 25/26 |  | 2025-01-17 | QTR3 | 24/25 | 113 | 3563244.72
| 01 | T1850 | 43944115201 | 2024-04-24 | QTR4 | 23/24 | 1 | 4 | 400 | 457 | 457 | 100% | 1 | 0 | 0 | 0 | 57 | 0 | 5279314 | 0 | 5279314 | 5778359 | 5716286 | 0 | 0 | 0 | 5716286 | 5630083 | 106.6% | 1 | -2290 | 499045 | 41 | 16 | 0 | 0 | 149726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349371 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-10-28 | QTR2 | 25/26 | 108 | 7929522.13
| 01 | T1852 | 44787215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 0 | 175 | 207 | 204 | 98.29% | 1 | 3 | 0 | 0 | 32 | 0 | 3084175 | 50000 | 3034175 | 3084175 | 3074445 | 0 | 0 | 0 | 3074445 | 3073651 | 101.3% | 1 | -795 | 0 | 14 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 115 | 2364265.94
| 01 | T1854 | 44480735201 | 2024-03-27 | QTR3 | 23/24 | 1 | 1 | 125 | 192 | 182 | 108% | 1 | 10 | 0 | 0 | 47 | 20 | 1273662 | 46380 | 1227282 | 1300460 | 1232804 | 0 | -22000 | -22000 | 1210804 | 1210162 | 98.61% | 1 | -642 | 26799 | 27 | 20 | 0 | 20 | 26799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 26799 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 115 | 1109604.92
| 01 | T1855 | 44547315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 5 | 300 | 577 | 607 | 143.7% | 0 | -30 | 30 | 0 | 176 | 101 | 11238774 | 116686 | 11122088 | 11323365 | 11568463 | -143070 | 0 | -143070 | 11425393 | 11375607 | 102.3% | 1 | -39102 | 84591 | 129 | 47 | 0 | 0 | 107185 | 0 | 0 | 101 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 114493 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 118 | 12534705.29
| 01 | T1861 | 44044815201 | 2023-06-14 | QTR4 | 22/23 | 1 | 3 | 322 | 635 | 633 | 164% | 0 | 2 | 0 | 0 | 306 | 7 | 12860870 | 130308 | 12730562 | 12904011 | 13130189 | 0 | 0 | 0 | 13130189 | 12994186 | 102.1% | 1 | -171 | 43141 | 71 | 34 | 4 | 7 | 0 | 0 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92690 | 0 | 201 | 7 | -92690 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-06-09 | QTR4 | 25/26 |  | 2025-08-20 | QTR1 | 25/26 | 115 | 12102054.04
| 01 | T1866 | 43903215201 | 2023-11-15 | QTR2 | 23/24 | 2 | 4 | 225 | 301 | 330 | 117.8% | 1 | -29 | 29 | 0 | 65 | 11 | 3945642 | 68014 | 3877628 | 4078353 | 4013289 | -76850 | 0 | -76850 | 3936439 | 3832582 | 98.84% | 1 | -14467 | 132711 | 40 | 25 | 0 | 9 | 43321 | 0 | 0 | 2 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 45054 | 0 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-03-20 | QTR3 | 24/25 | 118 | 5005578.39
| 01 | T1867 | 44546715201 | 2024-01-31 | QTR3 | 23/24 | 2 | 4 | 250 | 361 | 352 | 120.4% | 0 | 9 | 0 | 0 | 83 | 28 | 7502026 | 73856 | 7428170 | 8082796 | 8181304 | 0 | 0 | 0 | 8181304 | 8176865 | 110.1% | 0 | -4440 | 580770 | 30 | 21 | 25 | 9 | 370939 | 0 | 3 | 0 | 23365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 201258 | 0 | 0 | 0 | 12662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 608224 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-02-11 | QTR3 | 25/26 |  | 2025-11-21 | QTR2 | 25/26 | 108 | 7936833.12
| 01 | T1868 | 44740215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 2 | 100 | 207 | 206 | 128% | 0 | 1 | 0 | 0 | 107 | 0 | 1036497 | 45938 | 990559 | 1074999 | 1074468 | 0 | 0 | 0 | 1074468 | 1035967 | 104.6% | 1 | 0 | 38502 | 57 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 115 | 1164568.56
| 01 | T1873 | 44788015201 | 2024-02-28 | QTR3 | 23/24 | 2 | 3 | 200 | 287 | 285 | 99% | 1 | 2 | 0 | 0 | 87 | 0 | 2902791 | 50000 | 2852791 | 2941983 | 2705963 | 0 | 0 | 0 | 2705963 | 2704866 | 94.81% | 1 | -1098 | 39192 | 78 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 65279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65279 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-02-02 | QTR3 | 25/26 |  | 2025-11-07 | QTR2 | 25/26 | 113 | 2895926.83
| 01 | T1874 | 43583015201 | 2024-08-28 | QTR1 | 24/25 | 1 | 1 | 250 | 271 | 271 | 100% | 1 | 0 | 0 | 0 | 21 | 0 | 2777889 | 0 | 2777889 | 2778854 | 2820140 | 0 | 0 | 0 | 2820140 | 2820008 | 101.5% | 1 | -133 | 965 | 13 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965 | 0 | F592163377 | THOMAS MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-04-08 | QTR4 | 25/26 |  | 2025-10-03 | QTR2 | 25/26 | 118 | 3495664.49
| 01 | T1881 | 43802715201 | 2023-11-15 | QTR2 | 23/24 | 2 | 1 | 200 | 310 | 310 | 108% | 1 | 0 | 0 | 0 | 94 | 16 | 6196035 | 68350 | 6127685 | 6206737 | 6556044 | 0 | 0 | 0 | 6556044 | 6524950 | 106.5% | 1 | -31093 | 10701 | 70 | 24 | 0 | 16 | 12210 | 0 | 0 | 0 | 19772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 31982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-04-02 | QTR4 | 24/25 | 108 | 6886950.71
| 01 | T1885 | 44629115201 | 2024-01-31 | QTR3 | 23/24 | 3 | 0 | 250 | 467 | 466 | 111.6% | 1 | 1 | 0 | 0 | 215 | 2 | 11193872 | 99929 | 11093943 | 11193872 | 11344239 | 0 | 0 | 0 | 11344239 | 11335446 | 102.2% | 1 | -8793 | 0 | 152 | 35 | 0 | 0 | 0 | 0 | 0 | 2 | 12403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 2 | 12403 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-21 | QTR4 | 25/26 |  | 2025-12-05 | QTR2 | 25/26 | 113 | 10309689.64
| 01 | T1889 | 44431315201 | 2024-03-27 | QTR3 | 23/24 | 2 | 1 | 200 | 346 | 346 | 115% | 1 | 0 | 0 | 0 | 116 | 30 | 2636284 | 50000 | 2586284 | 2666046 | 2714680 | -3800 | 0 | -3800 | 2710880 | 2705941 | 104.6% | 1 | -4939 | 29762 | 88 | 28 | 0 | 0 | 6254 | 0 | 0 | 0 | 60445 | 15459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 66698 | 15459 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-27 | QTR3 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 108 | 3253356.71
| 01 | T1891 | 44743625201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 175 | 235 | 235 | 112% | 1 | 0 | 0 | 0 | 39 | 21 | 4742624 | 50000 | 4692624 | 4787027 | 4779994 | 0 | 0 | 0 | 4779994 | 4777172 | 101.8% | 1 | -2822 | 44403 | 18 | 21 | 0 | 0 | 0 | 0 | 0 | 21 | 50051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -585 | 0 | 0 | 0 | 13168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 62635 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-10 | QTR2 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 108 | 4605369.8
| 01 | T1895 | 44656015201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 125 | 169 | 169 | 119.2% | 1 | 0 | 0 | 0 | 20 | 24 | 1414901 | 0 | 1414901 | 1450512 | 1460078 | 0 | 0 | 0 | 1460078 | 1460017 | 103.2% | 1 | -61 | 35611 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-07-28 | QTR1 | 25/26 | 108 | 1992638.1
| 01 | T1901 | 44893615201 | 2024-08-28 | QTR1 | 24/25 | 1 | 1 | 300 | 380 | 380 | 110% | 1 | 0 | 0 | 0 | 80 | 0 | 9549741 | 116136 | 9433605 | 9400063 | 9512022 | 0 | 0 | 0 | 9512022 | 9509899 | 100.8% | 1 | -2123 | -149678 | 13 | 37 | 30 | 0 | -176994 | 0 | 0 | 0 | 92911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | -84083 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-04-09 | QTR4 | 25/26 |  | 2026-01-27 | QTR3 | 25/26 | 118 | 10149489.54
| 01 | T1905 | 44645215201 | 2025-01-29 | QTR3 | 24/25 | 1 | 1 | 100 | 144 | 144 | 110% | 1 | 0 | 0 | 0 | 34 | 10 | 574929 | 0 | 574929 | 574929 | 554144 | 0 | 0 | 0 | 554144 | 554144 | 96.38% | 1 | 0 | 0 | 28 | 6 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-02-02 | QTR3 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 108 | 670642.47
| 01 | T1907 | 45240815201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 130 | 187 | 187 | 127.7% | 0 | 0 | 0 | 0 | 57 | 0 | 714571 | 34195 | 680376 | 714571 | 686286 | 0 | 0 | 0 | 686286 | 686286 | 100.9% | 1 | 0 | 0 | 2 | 19 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC. | N/A | N/A | N/A | N/A | 2026-05-13 | QTR4 | 25/26 |  | 2026-02-13 | QTR3 | 25/26 | 115 | 685303.86
| 01 | T1927 | 44477325201 | 2025-07-30 | QTR1 | 25/26 | 1 | 0 | 100 | 116 | 115 | 99% | 1 | 1 | 0 | 0 | 16 | 0 | 414963 | 0 | 414963 | 414963 | 422033 | 0 | 0 | 0 | 422033 | 422033 | 101.7% | 1 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2026-02-12 | QTR3 | 25/26 | 118 | 496784.63
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 25 | 40 | 74 | 6752 | 10150 | 9952 | 72% | 18 | 198 | 59 | 0 | 2845 | 553 | 175529198 | 1514285 | 174014913 | 178799243 | 179210948 | -253720 | -92500 | -346220 | 178864728 | 178790526 | 96% | 24 | 2561823 | 3270046 | 1726 | 676 | 80 | 99 | 824956 | 0 | 253 | 272 | 966850 | 246753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 29 | 19 | 525669 | 0 | 0 | 0 | 108747 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 272395 | 0 | 0 | 0 | 0 | 0 | 74 | 163 | 534836 | 45203 | 0 | 0 | 0 | 0 | 0 | 0 | -92690 | 0 | 546 | 553 | 3146511 | 291956
| 01 | E1R76 | 20121535201 | 2020-05-29 | QTR4 | 19/20 | 1 | 5 | 1050 | 1489 | 1488 | 107% | 1 | 1 | 0 | 0 | 365 | 74 | 70460520 | 150000 | 70310520 | 71635236 | 71638136 | -100000 | 0 | -100000 | 71538136 | 74769243 | 106.3% | 1 | 5571562 | 1174716 | 264 | 101 | 0 | 0 | 60435 | 0 | 0 | 74 | 916285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 314762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 74 | 1301779 | 0 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-10-20 | QTR2 | 25/26 |  | 2024-09-12 | QTR1 | 24/25 | 108 | 57230747.75 | Y | DESIGN/BUILD PROJECT
| 01 | E1R87 | 20103255201 | 2020-11-20 | QTR2 | 20/21 | 3 | 19 | 1400 | 1699 | 1699 | 100% | 1 | 0 | 0 | 0 | 265 | 34 | 143923300 | 150000 | 143773300 | 144607218 | 144885088 | -40000 | 0 | -40000 | 144845088 | 145590108 | 101.3% | 1 | 12782288 | 683918 | 199 | 100 | 0 | 0 | 857947 | 17389 | 0 | 0 | 113457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1718413 | 0 | 0 | 0 | 24827 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 569484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -46196 | 0 | 0 | 16 | -192910 | 17389 | F843374080 | AJAX-LEWARE JV | N/A | N/A | N/A | N/A | 2026-01-23 | QTR3 | 25/26 |  | 2025-10-25 | QTR2 | 25/26 | 106 | 132713200.45 | B11:B7:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - A+B/BONUS:ACC - DESIGN/BUILD - MAJOR
| 01 | E1U56 | 44400825201 | 2022-02-17 | QTR3 | 21/22 | 1 | 20 | 500 | 1032 | 1032 | 122.8% | 0 | 0 | 0 | 0 | 418 | 114 | 40877774 | 150000 | 40727774 | 43600530 | 44711094 | 0 | 0 | 0 | 44711094 | 45889241 | 112.7% | 0 | 1184557 | 2722756 | 343 | 75 | 0 | 0 | 295612 | 3520 | 0 | 0 | 156058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 2270096 | 0 | 0 | 0 | 156484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -52787 | 0 | 0 | 114 | 2831872 | 3520 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2026-06-15 | QTR4 | 25/26 |  | 2025-04-02 | QTR4 | 24/25 | 113 | 46748207.92
| 01 | E1V05 | 44400835201 | 2022-07-21 | QTR1 | 22/23 | 1 | 12 | 350 | 697 | 697 | 119.1% | 1 | 0 | 0 | 0 | 296 | 51 | 22180000 | 150000 | 22030000 | 22731000 | 22373423 | 0 | 0 | 0 | 22373423 | 21651639 | 98.28% | 1 | -721784 | 701000 | 237 | 43 | 0 | 0 | 169783 | 0 | 16 | 30 | 431865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66138 | 0 | 0 | 21 | 14304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 51 | 682090 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-06-08 | QTR4 | 25/26 |  | 2024-12-26 | QTR2 | 24/25 | 113 | 27316502.46
| 01 | E1V08 | 19602265201 | 2023-11-02 | QTR2 | 23/24 | 2 | 3 | 350 | 424 | 375 | 86% | 1 | 49 | 0 | 0 | 74 | 0 | 6226258 | 61298 | 6164960 | 6296806 | 6274547 | 0 | 0 | 0 | 6274547 | 6215664 | 100.8% | 1 | -10506 | 70548 | 51 | 23 | 0 | 0 | 45061 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48763 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 115 | 7418503.78
| 01 | E1V09 | 44743215201 | 2024-02-15 | QTR3 | 23/24 | 2 | 0 | 190 | 250 | 249 | 99.47% | 1 | 1 | 0 | 0 | 60 | 0 | 3665572 | 50000 | 3615572 | 3665572 | 3704260 | 0 | 0 | 0 | 3704260 | 3693129 | 102.1% | 1 | -11132 | 0 | 44 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 12979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 11006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24749 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 108 | 4198565.92
| 01 | E1V10 | 44155015201 | 2023-02-16 | QTR3 | 22/23 | 1 | 5 | 300 | 551 | 561 | 110.3% | 1 | -10 | 10 | 0 | 205 | 46 | 14609258 | 150000 | 14459258 | 14044029 | 14088333 | -3245 | 0 | -3245 | 14085087 | 13929541 | 96.34% | 1 | -126080 | -565229 | 188 | 42 | 0 | 0 | -627778 | 0 | 0 | 21 | 85849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -541929 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-19 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 115 | 14926349.94
| 01 | E1V12 | 43488625201 | 2023-05-18 | QTR4 | 22/23 | 6 | 11 | 700 | 782 | 627 | 77.86% | 1 | 155 | 0 | 0 | 82 | 0 | 18975000 | 150000 | 18825000 | 19595912 | 19771279 | 0 | 0 | 0 | 19771279 | 19695292 | 104.6% | 1 | -1753 | 620912 | 41 | 41 | -38 | 0 | 520753 | 0 | 0 | 0 | 75968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38 | 0 | 596721 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-05-11 | QTR4 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 108 | 18481181.07
| 01 | E1V13 | 44893915201 | 2024-09-19 | QTR1 | 24/25 | 1 | 1 | 150 | 195 | 194 | 111.3% | 1 | 1 | 0 | 0 | 45 | 0 | 5289078 | 65023 | 5224055 | 5392842 | 5545592 | 0 | 0 | 0 | 5545592 | 5545735 | 106.2% | 1 | 143 | 103763 | 8 | 19 | 0 | 0 | 103763 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 103763 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-25 | QTR1 | 25/26 |  | 2025-06-07 | QTR4 | 24/25 | 118 | 5760651.93
| 01 | E1V22 | 44620615201 | 2023-07-20 | QTR1 | 23/24 | 1 | 3 | 180 | 227 | 220 | 96.11% | 1 | 7 | 0 | 0 | 47 | 0 | 5142423 | 50000 | 5092423 | 5047658 | 5138834 | 0 | 0 | 0 | 5138834 | 5099867 | 100.1% | 1 | -1029 | -94765 | 25 | 22 | 0 | 0 | 44761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -132703 | 0 | 0 | 0 | -87943 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-05 | QTR3 | 24/25 | 118 | 4496918.22
| 01 | E1V23 | 44743415201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 225 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 53 | 0 | 5558710 | 57494 | 5501216 | 5552034 | 5723019 | 0 | 0 | 0 | 5723019 | 5723218 | 104% | 1 | 199 | -6676 | 44 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | -6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4873 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-01 | QTR1 | 25/26 |  | 2024-10-23 | QTR2 | 24/25 | 108 | 5765208.01
| 01 | E1V51 | 44743715201 | 2022-08-02 | QTR1 | 22/23 | 3 | 3 | 650 | 763 | 763 | 100% | 1 | 0 | 0 | 0 | 113 | 0 | 23141400 | 150000 | 22991400 | 23931467 | 24545579 | 0 | 0 | 0 | 24545579 | 24060306 | 104.6% | 1 | -480611 | 790067 | 61 | 52 | 0 | 0 | 53994 | 0 | 0 | 0 | 770405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824400 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-21 | QTR1 | 25/26 |  | 2024-11-12 | QTR2 | 24/25 | 108 | 26691037.4 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 01 | E1V60 | 44901515201 | 2023-06-06 | QTR4 | 22/23 | 1 | 4 | 975 | 1035 | 559 | 51.18% | 1 | 476 | 0 | 0 | 60 | 0 | 24655000 | 150000 | 24505000 | 24840707 | 24676932 | 0 | 941500 | 941500 | 25618432 | 24522979 | 100.1% | 1 | -950274 | 185707 | 17 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 40527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51851 | 0 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2025-02-18 | QTR3 | 24/25 | 113 | 27242569.81 | B2:B5:Y | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:DESIGN/BUILD PROJECT
| 01 | E1W11 | 45088215201 | 2025-10-16 | QTR2 | 25/26 | 1 | 0 | 80 | 82 | 49 | 58.75% | 1 | 33 | 0 | 0 | 2 | 0 | 1286987 | 50000 | 1236987 | 1286987 | 1219611 | 0 | 0 | 0 | 1219611 | 1218601 | 98.51% | 1 | -1009 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-06-22 | QTR4 | 25/26 |  | 2026-03-19 | QTR3 | 25/26 | 108 | 1583531
| 01 | E1W13 | 44594215201 | 2024-02-15 | QTR3 | 23/24 | 1 | 10 | 200 | 292 | 317 | 125.5% | 0 | -25 | 25 | 0 | 66 | 26 | 2428636 | 0 | 2428636 | 2626766 | 2708707 | -66250 | 0 | -66250 | 2642457 | 2624968 | 108.1% | 1 | -22 | 198130 | 44 | 22 | 0 | 26 | 115608 | 0 | 0 | 0 | 65054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 180662 | 0 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-04-22 | QTR4 | 24/25 | 115 | 3681296.02
| 01 | E1W16 | 44738015201 | 2023-09-21 | QTR1 | 23/24 | 1 | 5 | 200 | 302 | 296 | 97% | 1 | 6 | 0 | 0 | 58 | 44 | 2844972 | 50000 | 2794972 | 2870813 | 2826404 | 0 | 0 | 0 | 2826404 | 2806626 | 100.4% | 1 | -7691 | 25841 | 81 | 21 | 0 | 0 | 8709 | 0 | 0 | 0 | 5045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13754 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2026-03-18 | QTR3 | 25/26 |  | 2025-01-21 | QTR3 | 24/25 | 115 | 2548367.85
| 01 | E1W18 | 44743115201 | 2024-04-18 | QTR4 | 23/24 | 1 | 1 | 170 | 195 | 171 | 85.88% | 1 | 24 | 0 | 0 | 25 | 0 | 2506911 | 50000 | 2456911 | 2530764 | 2550717 | 0 | 0 | 0 | 2550717 | 2546483 | 103.6% | 1 | -4233 | 23853 | 8 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 |  | 2025-04-30 | QTR4 | 24/25 | 108 | 2727222.68
| 01 | E1W50 | 45279215201 | 2024-03-26 | QTR3 | 23/24 | 1 | 0 | 450 | 511 | 495 | 97.33% | 1 | 16 | 0 | 0 | 57 | 4 | 2283584 | 50000 | 2233584 | 2283584 | 2253806 | 0 | 0 | 0 | 2253806 | 2253543 | 100.9% | 1 | -264 | 0 | 24 | 33 | 0 | 4 | 25861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25861 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 |  | 2025-09-29 | QTR1 | 25/26 | 118 | 2780605.35 | Y | DESIGN/BUILD PROJECT
| 01 | E1W75 | 44923315201 | 2024-07-18 | QTR1 | 24/25 | 1 | 0 | 115 | 150 | 150 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 2560003 | 50000 | 2510003 | 2560003 | 2586788 | 0 | 0 | 0 | 2586788 | 2586788 | 103.1% | 1 | 0 | 0 | 32 | 3 | 0 | 0 | 29053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29053 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 |  | 2025-06-04 | QTR4 | 24/25 | 108 | 3481659.24
| 01 | E1W76 | 44897215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 0 | 140 | 166 | 150 | 88.57% | 1 | 16 | 0 | 0 | 26 | 0 | 3352588 | 50000 | 3302588 | 3352588 | 3378389 | 0 | 0 | 0 | 3378389 | 3377632 | 102.3% | 1 | -757 | 0 | 9 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-04-10 | QTR4 | 24/25 | 118 | 4285958.2
| 01 | E1W78 | 44927215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 1 | 100 | 127 | 110 | 83% | 1 | 17 | 0 | 0 | 27 | 0 | 1562427 | 50000 | 1512427 | 1562023 | 1597413 | 0 | 0 | 0 | 1597413 | 1597413 | 105.6% | 1 | 0 | -404 | 10 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 108 | 1884401.65
| 01 | E1W79 | 44023015201 | 2024-09-19 | QTR1 | 24/25 | 1 | 2 | 140 | 150 | 124 | 81.43% | 1 | 26 | 0 | 0 | 10 | 0 | 1118465 | 40273 | 1078192 | 1118465 | 854089 | 0 | 0 | 0 | 854089 | 854089 | 79.21% | 1 | -1 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-09-11 | QTR1 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 118 | 991704.32
| 01 | E1W84 | 43607915201 | 2024-11-07 | QTR2 | 24/25 | 1 | 2 | 135 | 148 | 143 | 96.3% | 1 | 5 | 0 | 0 | 13 | 0 | 2277103 | 50000 | 2227103 | 2321230 | 1781060 | 0 | 0 | 0 | 1781060 | 1781061 | 79.97% | 1 | 1 | 44127 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 19595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19595 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2026-06-22 | QTR4 | 25/26 |  | 2025-11-03 | QTR2 | 25/26 | 118 | 3667817.74
| 01 | E1W85 | 44893115201 | 2024-11-07 | QTR2 | 24/25 | 2 | 3 | 150 | 180 | 160 | 86.67% | 1 | 20 | 0 | 0 | 30 | 0 | 4458291 | 54289 | 4404002 | 4710660 | 4720609 | 0 | 0 | 0 | 4720609 | 4719730 | 107.2% | 1 | -879 | 252368 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-09-04 | QTR1 | 25/26 | 113 | 5001199.26
| 01 | E1W87 | 45089215201 | 2025-07-17 | QTR1 | 25/26 | 2 | 0 | 150 | 180 | 150 | 80% | 1 | 30 | 0 | 0 | 30 | 0 | 3771590 | 51486 | 3720104 | 3771590 | 3672932 | 0 | 0 | 0 | 3672932 | 3673179 | 98.74% | 1 | 247 | 0 | 13 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-06-02 | QTR4 | 25/26 |  | 2026-03-11 | QTR3 | 25/26 | 108 | 5146948.27
| 01 | E1W89 | 44927515201 | 2024-12-05 | QTR2 | 24/25 | 1 | 0 | 200 | 252 | 248 | 98% | 1 | 4 | 0 | 0 | 52 | 0 | 8846876 | 116108 | 8730768 | 8846876 | 9498223 | 0 | 0 | 0 | 9498223 | 9496897 | 108.8% | 1 | -1326 | 0 | 38 | 14 | 0 | 0 | 5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20916 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-04-06 | QTR4 | 25/26 |  | 2025-12-09 | QTR2 | 25/26 | 108 | 9903212.9
| 01 | E1W94 | 44917815201 | 2025-02-20 | QTR3 | 24/25 | 1 | 0 | 80 | 147 | 156 | 148.8% | 0 | -9 | 9 | 0 | 37 | 30 | 830702 | 40500 | 790202 | 830702 | 826937 | -15165 | 0 | -15165 | 811772 | 811772 | 102.7% | 1 | 0 | 0 | 29 | 8 | 0 | 0 | 0 | 0 | 0 | 30 | 17515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 17515 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-01-30 | QTR3 | 25/26 |  | 2025-12-10 | QTR2 | 25/26 | 108 | 1048586.14
| 01 | E1W97 | 45344615201 | 2025-03-20 | QTR3 | 24/25 | 1 | 0 | 100 | 178 | 178 | 100% | 1 | 0 | 0 | 0 | 78 | 0 | 586332 | 33727 | 552605 | 586332 | 567695 | -2950 | 0 | -2950 | 564745 | 564745 | 102.2% | 1 | 0 | 0 | 63 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2026-03-05 | QTR3 | 25/26 | 108 | 574883.78
| 01 | E1X61 | 44897315201 | 2025-05-15 | QTR4 | 24/25 | 1 | 0 | 150 | 224 | 224 | 100% | 1 | 0 | 0 | 0 | 74 | 0 | 6268574 | 78935 | 6189639 | 6268574 | 6617085 | 0 | 0 | 0 | 6617085 | 6634790 | 107.2% | 1 | 17705 | 0 | 52 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-04-29 | QTR4 | 25/26 |  | 2026-03-19 | QTR3 | 25/26 | 118 | 7458839.38
| 01 | E1X68 | 44895715201 | 2025-07-17 | QTR1 | 25/26 | 1 | 0 | 100 | 121 | 115 | 94% | 1 | 6 | 0 | 0 | 21 | 0 | 2063849 | 50000 | 2013849 | 2063849 | 1971937 | 0 | 0 | 0 | 1971937 | 1971937 | 97.92% | 1 | 0 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 8496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8496 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 |  | 2026-02-10 | QTR3 | 25/26 | 113 | 2136352.43
| 01 | E1X74 | 45087815201 | 2025-09-18 | QTR1 | 25/26 | 1 | 0 | 80 | 96 | 74 | 72.5% | 1 | 22 | 0 | 0 | 16 | 0 | 576122 | 38879 | 537243 | 576122 | 554252 | 0 | 0 | 0 | 554252 | 554252 | 103.2% | 1 | 0 | 0 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2026-03-19 | QTR3 | 25/26 | 108 | 728143.78
| 01 | E1X75 | 45127215201 | 2025-09-18 | QTR1 | 25/26 | 1 | 0 | 100 | 119 | 96 | 77% | 1 | 23 | 0 | 0 | 19 | 0 | 2448287 | 50000 | 2398287 | 2448287 | 2439726 | 0 | 0 | 0 | 2439726 | 2439726 | 101.7% | 1 | 0 | 0 | 8 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2026-03-06 | QTR3 | 25/26 | 113 | 3004335.58
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 32 | 45 | 111 | 9860 | 13042 | 12148 | 90.62% | 29 | 894 | 44 | 0 | 2759 | 423 | 436776592 | 2438012 | 434338580 | 443557226 | 445702496 | -227610 | 941500 | 713890 | 446416385 | 448900194 | 96.88% | 31 | 17237351 | 6930632 | 1987 | 841 | -38 | 30 | 1709270 | 20909 | 19 | 155 | 2998855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 629643 | 0 | 15 | 21 | 223632 | 0 | 0 | 0 | 0 | 0 | 49 | 16 | 901220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29838 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | -231686 | 0 | 45 | 336 | 6260769 | 44762
| District 01 Totals |  |  |  |  | 57 | 85 | 185 | 16612 | 23192 | 22100 | 82.46% | 47 | 1092 | 103 | 0 | 5604 | 976 | 612305790 | 3952297 | 608353493 | 622356469 | 624913444 | -481330 | 849000 | 367670 | 625281113 | 627690720 | 96.49% | 55 | 19799174 | 10200678 | 3713 | 1517 | 42 | 129 | 2534226 | 20909 | 272 | 427 | 3965705 | 246753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 29 | 133 | 1155312 | 0 | 15 | 21 | 332379 | 0 | 0 | 0 | 0 | 0 | 159 | 16 | 1173615 | 0 | 0 | 0 | 0 | 0 | 74 | 163 | 564674 | 69056 | 0 | 0 | 0 | 0 | 0 | 0 | -324376 | 0 | 591 | 889 | 9407280 | 336718
| 02 | T2591 | 42886515201 | 2015-10-14 | QTR2 | 15/16 | 5 | 58 | 1200 | 3229 | 3229 | 220.2% | 0 | 0 | 0 | 0 | 905 | 1124 | 65973116 | 149995 | 65823121 | 108070596 | 111419612 | 0 | 0 | 0 | 111419612 | 112415734 | 170.8% | 0 | 1746230 | 42097480 | 322 | 264 | 133 | 66 | 1773148 | 375907 | 118 | 671 | 33362908 | 7141422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 335 | 4964601 | 3035499 | 0 | 0 | 325801 | 0 | 0 | 0 | 0 | 0 | 117 | 0 | 343725 | 2306 | 0 | 0 | 1388728 | 620012 | 0 | 52 | 1119347 | 685768 | 0 | 0 | 0 | 0 | 0 | 0 | -1139535 | 0 | 436 | 1124 | 42138723 | 11860914 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-03-23 | QTR3 | 25/26 |  | 2024-12-31 | QTR2 | 24/25 | 208 | 76779378.1
| 02 | T2736 | 21002445201 | 2019-09-25 | QTR1 | 19/20 | 1 | 9 | 1000 | 1343 | 1343 | 112.8% | 1 | 0 | 0 | 0 | 229 | 114 | 49333142 | 150000 | 49183142 | 49318231 | 49328600 | 0 | 0 | 0 | 49328600 | 50856887 | 103.4% | 1 | 1816856 | -14911 | 135 | 80 | 14 | 88 | 388963 | 9343 | 0 | 26 | 65671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | -425234 | 0 | 51 | 114 | 42847 | 9343 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-04-24 | QTR4 | 25/26 |  | 2023-09-09 | QTR1 | 23/24 | 216 | 54425330.39
| 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 127.2% | 0 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 109.4% | 1 | 329791 | 87098 | 104 | 52 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6
| 02 | T2790 | 43616815201 | 2021-01-27 | QTR3 | 20/21 | 1 | 4 | 730 | 1441 | 1441 | 117.3% | 1 | 0 | 0 | 0 | 711 | 0 | 15444874 | 116066 | 15328808 | 18490817 | 18458945 | 0 | 0 | 0 | 18458945 | 18501533 | 120.7% | 0 | 251365 | 3045943 | 306 | 279 | 0 | 0 | 677453 | 0 | 0 | 0 | 61510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1981123 | 14607 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 2720087 | 14607 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2025-12-05 | QTR2 | 25/26 |  | 2025-05-07 | QTR4 | 24/25 | 216 | 11733776.57
| 02 | T2819 | 43384325201 | 2021-10-27 | QTR2 | 21/22 | 4 | 13 | 260 | 1451 | 1440 | 309.6% | 0 | 11 | 0 | 0 | 782 | 409 | 4659450 | 50000 | 4609450 | 10356438 | 10867437 | 0 | 0 | 0 | 10867437 | 10590254 | 229.8% | 0 | 248 | 5696988 | 396 | 239 | 147 | 400 | 4148470 | 896117 | 0 | 9 | 24518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7156 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 1399987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 409 | 5580131 | 896117 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-06-19 | QTR4 | 25/26 |  | 2026-03-13 | QTR3 | 25/26 | 216 | 4935260.07
| 02 | T2839 | 44342115201 | 2022-02-09 | QTR3 | 21/22 | 3 | 0 | 480 | 785 | 783 | 100% | 1 | 2 | 0 | 0 | 185 | 120 | 31969186 | 150000 | 31819186 | 31969186 | 32489212 | 0 | 0 | 0 | 32489212 | 33982240 | 106.8% | 1 | 1493028 | 0 | 244 | 59 | 0 | 2 | 18542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 18542 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-14 | QTR1 | 25/26 |  | 2024-06-14 | QTR4 | 23/24 | 209 | 35449756.12
| 02 | T2844 | 43935615201 | 2022-06-15 | QTR4 | 21/22 | 3 | 6 | 479 | 915 | 913 | 136.1% | 0 | 2 | 0 | 0 | 311 | 125 | 19892956 | 180993 | 19711963 | 20310363 | 20717832 | 0 | 0 | 0 | 20717832 | 20350044 | 103.2% | 1 | -345380 | 417407 | 191 | 70 | 50 | 92 | 143934 | 0 | 0 | 15 | 291019 | 3470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681 | 0 | 0 | 18 | 42558 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 125 | 516682 | 3470 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-07-16 | QTR1 | 25/26 | 208 | 16227519.23
| 02 | T2854 | 44554515201 | 2022-06-08 | QTR4 | 21/22 | 2 | 1 | 210 | 817 | 817 | 177.1% | 0 | 0 | 0 | 0 | 355 | 252 | 10095026 | 91284 | 10003741 | 10267526 | 10526210 | 0 | 0 | 0 | 10526210 | 10195263 | 101.9% | 1 | -330946 | 172500 | 390 | 55 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 110 | 172500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 252 | 172500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 209 | 10655889.17
| 02 | T2863 | 43744115201 | 2022-01-12 | QTR3 | 21/22 | 3 | 6 | 550 | 1127 | 1125 | 175.3% | 0 | 2 | 0 | 0 | 161 | 416 | 14032373 | 165047 | 13867326 | 15901285 | 16261074 | 0 | 0 | 0 | 16261074 | 16278606 | 117.4% | 0 | 24575 | 1868912 | 57 | 104 | 0 | 416 | 1783542 | 0 | 0 | 0 | 59192 | 4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20176 | 0 | 0 | 0 | 38915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 1906703 | 4208 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 208 | 15021660.86
| 02 | T2865 | 44351715201 | 2022-11-16 | QTR2 | 22/23 | 1 | 6 | 400 | 682 | 681 | 141% | 0 | 1 | 0 | 0 | 162 | 120 | 7663000 | 71865 | 7591135 | 8470199 | 9163770 | 0 | 0 | 0 | 9163770 | 9149657 | 120.5% | 0 | -14114 | 807199 | 68 | 49 | 45 | 91 | 723003 | 0 | 0 | 29 | 122914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 120 | 871252 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 208 | 7014633.18
| 02 | T2878 | 43205425201 | 2022-11-16 | QTR2 | 22/23 | 4 | 6 | 500 | 895 | 895 | 112% | 1 | 0 | 0 | 0 | 335 | 60 | 9330849 | 107922 | 9222927 | 9522394 | 9742335 | 0 | 0 | 0 | 9742335 | 9588826 | 104% | 1 | -24880 | 191545 | 283 | 52 | 0 | 0 | 0 | 0 | 0 | 60 | 62916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 20 | 152911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 80 | 215827 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 |  | 2025-08-27 | QTR1 | 25/26 | 209 | 10579788.59
| 02 | T2886 | 44554425201 | 2022-10-05 | QTR2 | 22/23 | 3 | 6 | 270 | 917 | 917 | 220.7% | 0 | 0 | 0 | 0 | 291 | 356 | 16754450 | 150000 | 16604450 | 17512907 | 18119731 | 0 | 0 | 0 | 18119731 | 17771453 | 107% | 1 | -335353 | 758457 | 254 | 67 | 0 | 30 | 34294 | 0 | 0 | 0 | 154830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 405798 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 30 | 178200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 326 | 773122 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-06-11 | QTR4 | 25/26 |  | 2025-08-22 | QTR1 | 25/26 | 209 | 17577251.58
| 02 | T2889 | 43575615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 5 | 280 | 638 | 638 | 156.8% | 0 | 0 | 0 | 0 | 199 | 159 | 3832776 | 50000 | 3782776 | 4315395 | 4383212 | 0 | 0 | 0 | 4383212 | 4383212 | 115.9% | 0 | 0 | 482619 | 107 | 92 | 0 | 24 | 38374 | 0 | 0 | 135 | 462409 | 134882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 500784 | 134882 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2025-06-06 | QTR4 | 24/25 | 208 | 4521037.25
| 02 | T2890 | 44554715201 | 2022-10-26 | QTR2 | 22/23 | 3 | 3 | 350 | 924 | 924 | 163.7% | 0 | 0 | 0 | 0 | 261 | 313 | 25595410 | 150000 | 25445410 | 25761158 | 26450421 | 0 | 0 | 0 | 26450421 | 25953030 | 102% | 1 | -497390 | 165747 | 280 | 71 | 0 | 213 | 120000 | 0 | 0 | 2 | 33247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 57500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 270747 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-09-17 | QTR1 | 25/26 | 209 | 25708227.9
| 02 | T2894 | 44540215201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 575 | 575 | 106.7% | 1 | 0 | 0 | 0 | 196 | 139 | 12471547 | 114486 | 12357061 | 12747539 | 13553931 | 0 | 0 | 0 | 13553931 | 13363147 | 108.1% | 1 | -190784 | 275992 | 290 | 29 | 0 | 57 | 256470 | 0 | 0 | 2 | 107104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 139 | 363574 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2024-09-11 | QTR1 | 24/25 | 209 | 11980864.41
| 02 | T2910 | 44535215201 | 2023-06-14 | QTR4 | 22/23 | 3 | 5 | 330 | 543 | 543 | 118.2% | 1 | 0 | 0 | 0 | 153 | 60 | 5895675 | 59623 | 5836052 | 5981679 | 6100547 | 0 | 0 | 0 | 6100547 | 6061260 | 103.9% | 1 | -3283 | 86004 | 101 | 52 | 0 | 20 | 48625 | 0 | 0 | 40 | 55572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 104197 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 |  | 2025-05-29 | QTR4 | 24/25 | 208 | 6680440.38
| 02 | T2913 | 44707815201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 150 | 420 | 412 | 206.7% | 0 | 8 | 0 | 0 | 102 | 168 | 4420617 | 50000 | 4370617 | 4518180 | 4416217 | 0 | 0 | 0 | 4416217 | 4412247 | 101% | 1 | -3971 | 97563 | 72 | 30 | 0 | 30 | 0 | 0 | 0 | 138 | 97563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 97563 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 |  | 2025-06-23 | QTR4 | 24/25 | 209 | 4807508.45
| 02 | T2914 | 44717215201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 350 | 882 | 882 | 135.4% | 0 | 0 | 0 | 0 | 427 | 105 | 14592365 | 150000 | 14442365 | 14773312 | 15181984 | 0 | 0 | 0 | 15181984 | 15184404 | 105.1% | 1 | 2420 | 180947 | 300 | 108 | 117 | 63 | 304259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 105 | 304259 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2026-01-28 | QTR3 | 25/26 | 216 | 15399944.09
| 02 | T2915 | 44718015201 | 2023-03-29 | QTR3 | 22/23 | 1 | 1 | 300 | 660 | 659 | 104.3% | 1 | 1 | 0 | 0 | 346 | 14 | 11703806 | 89802 | 11614004 | 11742594 | 12389230 | 0 | 0 | 0 | 12389230 | 12372017 | 106.5% | 1 | -17213 | 38788 | 301 | 45 | 0 | 14 | 14951 | 0 | 0 | 0 | 38788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14 | 53739 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-20 | QTR2 | 25/26 |  | 2025-06-26 | QTR4 | 24/25 | 208 | 10416036.13
| 02 | T2916 | 43993715201 | 2023-04-26 | QTR4 | 22/23 | 2 | 0 | 425 | 610 | 605 | 98.82% | 1 | 5 | 0 | 0 | 185 | 0 | 10398707 | 246 | 10398461 | 10398707 | 10268067 | 0 | 0 | 0 | 10268067 | 10264507 | 98.71% | 1 | -3560 | 0 | 137 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 209 | 8834993.85
| 02 | T2917 | 44330415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 2 | 330 | 604 | 604 | 130.3% | 0 | 0 | 0 | 0 | 174 | 100 | 23947969 | 150000 | 23797969 | 24055659 | 25032603 | 0 | 0 | 0 | 25032603 | 25026994 | 105.2% | 1 | -5609 | 107690 | 101 | 73 | 0 | 66 | 177659 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 180877 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 208 | 21934859.67
| 02 | T2924 | 20930185201 | 2023-04-26 | QTR4 | 22/23 | 1 | 2 | 300 | 751 | 751 | 127.7% | 0 | 0 | 0 | 0 | 250 | 201 | 19358596 | 150000 | 19208596 | 19523393 | 20332171 | 0 | 0 | 0 | 20332171 | 20313549 | 105.8% | 1 | -18621 | 164797 | 300 | 68 | 0 | 0 | 49110 | 0 | 27 | 51 | 133896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17832 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 9270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 201 | 210108 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-02-20 | QTR3 | 25/26 |  | 2025-10-27 | QTR2 | 25/26 | 208 | 19142187.33
| 02 | T2934 | 44331015201 | 2022-12-07 | QTR2 | 22/23 | 2 | 5 | 450 | 714 | 711 | 123.1% | 0 | 3 | 0 | 0 | 264 | 0 | 26057502 | 150000 | 25907502 | 26443445 | 27980036 | 0 | 0 | 0 | 27980036 | 27874372 | 107.6% | 1 | -105664 | 385943 | 91 | 66 | 86 | 0 | 261787 | 11998 | 21 | 0 | 157751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 462296 | 11998 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-03-13 | QTR3 | 24/25 | 208 | 24163399.99
| 02 | T2945 | 44542715201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 300 | 503 | 501 | 129.3% | 0 | 2 | 0 | 0 | 113 | 90 | 6853255 | 73995 | 6779259 | 6853255 | 6989283 | 0 | 0 | 0 | 6989283 | 6981891 | 103% | 1 | -7392 | 0 | 72 | 41 | 0 | 10 | 13022 | 0 | 0 | 20 | 29941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 46335 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-08-12 | QTR1 | 25/26 | 208 | 7614578.02
| 02 | T2948 | 44712315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 300 | 431 | 414 | 94.33% | 1 | 17 | 0 | 0 | 71 | 60 | 5794236 | 50808 | 5743428 | 5794236 | 5977965 | 0 | 0 | 0 | 5977965 | 5956561 | 103.7% | 1 | -21404 | 0 | 93 | 38 | 0 | 0 | 14179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14179 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-12 | QTR2 | 25/26 |  | 2025-07-10 | QTR1 | 25/26 | 208 | 5749684.61
| 02 | T2949 | 20969745201 | 2023-11-15 | QTR2 | 23/24 | 1 | 2 | 270 | 360 | 323 | 92.59% | 1 | 37 | 0 | 0 | 73 | 17 | 1865813 | 50000 | 1815813 | 1939049 | 1961474 | 0 | 0 | 0 | 1961474 | 1960364 | 108% | 1 | -1110 | 73235 | 44 | 29 | 0 | 16 | 39150 | 0 | 0 | 1 | 39471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 78621 | 0 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2025-11-07 | QTR2 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 208 | 2230663.64
| 02 | T2954 | 44542015201 | 2023-12-06 | QTR2 | 23/24 | 2 | 0 | 270 | 373 | 372 | 99.63% | 1 | 1 | 0 | 0 | 103 | 0 | 3819110 | 50000 | 3769110 | 3819110 | 3735111 | 0 | 0 | 0 | 3735111 | 3733457 | 99.05% | 1 | -1654 | 0 | 67 | 36 | 0 | 0 | 702 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 208 | 5040191.6
| 02 | T2961 | 43633015201 | 2023-12-06 | QTR2 | 23/24 | 3 | 3 | 400 | 450 | 393 | 87.5% | 1 | 57 | 0 | 0 | 50 | 0 | 3521000 | 246 | 3520754 | 3558326 | 3560864 | 0 | 0 | 0 | 3560864 | 3553846 | 100.9% | 1 | -957 | 37326 | 19 | 24 | 7 | 0 | 31265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 31265 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-03-19 | QTR3 | 24/25 | 209 | 3765540.75
| 02 | T2962 | 44796215201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 180 | 370 | 370 | 130.6% | 0 | 0 | 0 | 0 | 160 | 30 | 7958218 | 85629 | 7872589 | 7958218 | 7882304 | 0 | 0 | 0 | 7882304 | 7877534 | 100.1% | 1 | -4770 | 0 | 79 | 56 | 0 | 30 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 30 | 1672 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 214 | 8827613.66
| 02 | T2966 | 21086555201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 120 | 236 | 232 | 146.7% | 0 | 4 | 0 | 0 | 56 | 60 | 2921783 | 50000 | 2871783 | 2921783 | 2938946 | 0 | 0 | 0 | 2938946 | 2938946 | 102.3% | 1 | 0 | 0 | 34 | 22 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-04-14 | QTR4 | 24/25 | 209 | 3224885.25
| 02 | T2969 | 44703615201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 300 | 408 | 406 | 118.7% | 1 | 2 | 0 | 0 | 50 | 58 | 10923210 | 112286 | 10810924 | 10892472 | 11424138 | 0 | 0 | 0 | 11424138 | 11378255 | 105.2% | 1 | -45883 | -30738 | 23 | 27 | 0 | 0 | 0 | 0 | 0 | 28 | 69752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | -30738 | 0 | 0 | 58 | 39014 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-24 | QTR2 | 25/26 |  | 2025-08-18 | QTR1 | 25/26 | 214 | 10802904.04
| 02 | T2970 | 44712815201 | 2024-02-28 | QTR3 | 23/24 | 3 | 5 | 180 | 392 | 392 | 140% | 0 | 0 | 0 | 0 | 140 | 72 | 6497196 | 70342 | 6426853 | 6705393 | 7314719 | 0 | 0 | 0 | 7314719 | 7267283 | 113.1% | 0 | -20654 | 208197 | 91 | 49 | 0 | 72 | 171277 | 99710 | 0 | 0 | 19849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 187461 | 99710 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 208 | 6729211.88
| 02 | T2973 | 44542915201 | 2024-03-27 | QTR3 | 23/24 | 1 | 1 | 450 | 538 | 511 | 94% | 1 | 27 | 0 | 0 | 88 | 0 | 11487858 | 101697 | 11386161 | 11487858 | 11739228 | 0 | 0 | 0 | 11739228 | 11724947 | 103% | 1 | -14282 | 0 | 28 | 60 | 0 | 0 | 12545 | 0 | 0 | 0 | 53728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66273 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-06-03 | QTR4 | 25/26 |  | 2026-02-18 | QTR3 | 25/26 | 208 | 9400553.25
| 02 | T2974 | 44720415201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 300 | 461 | 461 | 102% | 1 | 0 | 0 | 0 | 155 | 6 | 18339896 | 150000 | 18189896 | 18339896 | 18394467 | 0 | 0 | 0 | 18394467 | 18347088 | 100.9% | 1 | -47379 | 0 | 113 | 42 | 0 | 3 | 40787 | 0 | 0 | 3 | 5308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 6 | 46094 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-10-11 | QTR2 | 25/26 | 214 | 19102224.25
| 02 | T2976 | 44755715201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 360 | 428 | 296 | 63.89% | 1 | 132 | 0 | 0 | 66 | 2 | 25893810 | 150000 | 25743810 | 26291007 | 27924429 | 0 | 0 | 0 | 27924429 | 27880284 | 108.3% | 1 | -44146 | 397198 | 39 | 27 | 0 | 0 | 417380 | 0 | 0 | 2 | 20401 | 3792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 437781 | 3792 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-21 | QTR2 | 25/26 |  | 2025-02-10 | QTR3 | 24/25 | 208 | 21206563.14
| 02 | T2981 | 45220125201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 275 | 345 | 286 | 78.55% | 1 | 59 | 0 | 0 | 70 | 0 | 2914229 | 50000 | 2864229 | 2914229 | 2917184 | 0 | 0 | 0 | 2917184 | 2917184 | 101.8% | 1 | 0 | 0 | 34 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-02-13 | QTR3 | 24/25 | 214 | 4244875.9
| 02 | T2985 | 43761415201 | 2023-11-15 | QTR2 | 23/24 | 1 | 0 | 270 | 405 | 405 | 116.7% | 1 | 0 | 0 | 0 | 119 | 16 | 7308506 | 69947 | 7238559 | 7308506 | 7304574 | 0 | 0 | 0 | 7304574 | 7285470 | 100.6% | 1 | -19104 | 0 | 59 | 31 | 0 | 2 | 31262 | 0 | 0 | 14 | 18461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 16 | 49723 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 208 | 8026688.02
| 02 | T2988 | 44721135201 | 2024-04-24 | QTR4 | 23/24 | 1 | 1 | 180 | 225 | 95 | 27.78% | 1 | 130 | 0 | 0 | 45 | 0 | 1562105 | 50000 | 1512105 | 1737694 | 1710662 | 0 | 0 | 0 | 1710662 | 1710435 | 113.1% | 0 | -227 | 175589 | 41 | 4 | 0 | 0 | 175589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175589 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 |  | 2024-10-17 | QTR2 | 24/25 | 208 | 1572771.91
| 02 | T2989 | 20782335201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 210 | 411 | 404 | 108.6% | 1 | 7 | 0 | 0 | 176 | 25 | 5914935 | 64380 | 5850554 | 5914935 | 5974865 | 0 | 0 | 0 | 5974865 | 5969794 | 102% | 1 | -5070 | 0 | 150 | 26 | 0 | 10 | 0 | 0 | 0 | 15 | 19570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 19570 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2026-06-04 | QTR4 | 25/26 |  | 2026-02-13 | QTR3 | 25/26 | 214 | 6456937.46
| 02 | T2990 | 20817735201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 250 | 385 | 385 | 104.8% | 1 | 0 | 0 | 0 | 63 | 72 | 8971608 | 119772 | 8851836 | 8971608 | 8756637 | 0 | 0 | 0 | 8756637 | 8744013 | 98.78% | 1 | -12624 | 0 | 98 | 25 | 0 | 12 | 0 | 0 | 0 | 0 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 10825 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2026-05-21 | QTR4 | 25/26 |  | 2026-02-09 | QTR3 | 25/26 | 216 | 11243024.19
| 02 | T2992 | 44603135201 | 2024-08-28 | QTR1 | 24/25 | 1 | 1 | 230 | 305 | 302 | 99.57% | 1 | 3 | 0 | 0 | 73 | 2 | 2368158 | 50000 | 2318158 | 2387905 | 2401749 | 0 | 0 | 0 | 2401749 | 2401749 | 103.6% | 1 | 0 | 19747 | 15 | 58 | 0 | 0 | 0 | 0 | 0 | 1 | 59350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 59933 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-05-21 | QTR4 | 25/26 |  | 2026-01-12 | QTR3 | 25/26 | 208 | 3418661.07
| 02 | T2997 | 44984425201 | 2024-09-25 | QTR1 | 24/25 | 1 | 2 | 180 | 214 | 214 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 2499454 | 50000 | 2449454 | 2573884 | 2437559 | 0 | 0 | 0 | 2437559 | 2436488 | 99.47% | 1 | -1071 | 74430 | 20 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 24430 | 24430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61993 | 24430 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 214 | 2231402.67
| 02 | T2999 | 21273445201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 180 | 250 | 256 | 122.8% | 0 | -6 | 6 | 0 | 35 | 35 | 9621507 | 91073 | 9530434 | 9621507 | 9860600 | -22878 | 0 | -22878 | 9837722 | 9862910 | 103.5% | 1 | 25188 | 0 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-21 | QTR4 | 25/26 |  | 2025-12-15 | QTR2 | 25/26 | 209 | 9367981.87
| 02 | T2A02 | 43431825201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 180 | 188 | 171 | 90.56% | 1 | 17 | 0 | 0 | 8 | 0 | 7419960 | 87264 | 7332696 | 7419960 | 7285721 | 0 | 0 | 0 | 7285721 | 7282630 | 99.32% | 1 | -3091 | 0 | 4 | 4 | 0 | 0 | 46438 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61171 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 214 | 8775588.25
| 02 | T2A05 | 20944145201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 150 | 194 | 192 | 100.7% | 1 | 2 | 0 | 0 | 41 | 3 | 2487602 | 50000 | 2437602 | 2535510 | 2431426 | 0 | 0 | 0 | 2431426 | 2431081 | 99.73% | 1 | -345 | 47909 | 17 | 24 | 0 | 3 | 47909 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 49559 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2026-02-27 | QTR3 | 25/26 |  | 2025-11-24 | QTR2 | 25/26 | 208 | 3542854
| 02 | T2A06 | 21003025201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 300 | 343 | 305 | 87.33% | 1 | 38 | 0 | 0 | 43 | 0 | 6571980 | 67485 | 6504495 | 6571980 | 6862070 | 0 | 0 | 0 | 6862070 | 6863371 | 105.5% | 1 | 1301 | 0 | 17 | 26 | 0 | 0 | 13750 | 0 | 0 | 0 | 15770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29520 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-11 | QTR3 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 216 | 6362364.64
| 02 | T2A09 | 21022385201 | 2024-12-04 | QTR2 | 24/25 | 1 | 0 | 180 | 234 | 233 | 105% | 1 | 1 | 0 | 0 | 44 | 10 | 4685902 | 61983 | 4623919 | 4685902 | 4940814 | 0 | 0 | 0 | 4940814 | 4942704 | 106.9% | 1 | 1890 | 0 | 24 | 20 | 0 | 10 | 9787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9787 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2026-01-16 | QTR3 | 25/26 | 216 | 5665701.92
| 02 | T2A11 | 21037845201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 180 | 228 | 226 | 104.4% | 1 | 2 | 0 | 0 | 38 | 10 | 4938588 | 53445 | 4885143 | 4938588 | 5114986 | 0 | 0 | 0 | 5114986 | 5114986 | 104.7% | 1 | 0 | 0 | 24 | 14 | 0 | 0 | 14784 | 0 | 0 | 10 | 12155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 26939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2025-12-03 | QTR2 | 25/26 | 214 | 4849324.71
| 02 | T2A12 | 21071155201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 120 | 214 | 212 | 105.8% | 1 | 2 | 0 | 0 | 85 | 9 | 4071019 | 50000 | 4021019 | 4106006 | 4039787 | 0 | 0 | 0 | 4039787 | 4039787 | 100.5% | 1 | 0 | 34986 | 61 | 24 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 |  | 2025-06-24 | QTR4 | 24/25 | 208 | 4204426.35
| 02 | T2A13 | 44721225201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 150 | 260 | 260 | 130.7% | 0 | 0 | 0 | 0 | 64 | 46 | 3440497 | 50000 | 3390497 | 3440497 | 3621976 | 0 | 0 | 0 | 3621976 | 3623713 | 106.9% | 1 | 1737 | 0 | 28 | 36 | 0 | 11 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2026-01-23 | QTR3 | 25/26 | 208 | 3982196.66
| 02 | T2A15 | 21056535201 | 2025-02-26 | QTR3 | 24/25 | 1 | 0 | 200 | 222 | 215 | 96.5% | 1 | 7 | 0 | 0 | 22 | 0 | 4346749 | 56257 | 4290492 | 4346749 | 4440530 | 0 | 0 | 0 | 4440530 | 4440118 | 103.5% | 1 | -412 | 0 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2025-12-17 | QTR2 | 25/26 | 208 | 5565013.46
| 02 | T2A22 | 20983125201 | 2025-04-30 | QTR4 | 24/25 | 1 | 0 | 130 | 137 | 107 | 76.92% | 1 | 30 | 0 | 0 | 7 | 0 | 4091439 | 50000 | 4041439 | 4091439 | 4148474 | 0 | 0 | 0 | 4148474 | 4148474 | 102.6% | 1 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-06-03 | QTR4 | 25/26 |  | 2025-11-05 | QTR2 | 25/26 | 209 | 4272746.94
| 02 | T2A25 | 45260325201 | 2025-06-11 | QTR4 | 24/25 | 1 | 0 | 120 | 128 | 72 | 53.33% | 1 | 56 | 0 | 0 | 8 | 0 | 1482455 | 50000 | 1432455 | 1482455 | 1471968 | 0 | 0 | 0 | 1471968 | 1471968 | 102.8% | 1 | 0 | 0 | 0 | 8 | 0 | 0 | 8713 | 0 | 0 | 0 | 6401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15114 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2025-12-23 | QTR2 | 25/26 | 208 | 1454042.95
| 02 | T2A31 | 43930215201 | 2025-07-30 | QTR1 | 25/26 | 1 | 0 | 90 | 104 | 64 | 55.56% | 1 | 40 | 0 | 0 | 14 | 0 | 541819 | 37145 | 504674 | 541819 | 531179 | 0 | 0 | 0 | 531179 | 531179 | 105.3% | 1 | 0 | 0 | 6 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 4453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4453 | 0 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2026-04-17 | QTR4 | 25/26 |  | 2025-12-23 | QTR2 | 25/26 | 208 | 573090.27
| 02 | T2A46 | 44721125201 | 2025-09-24 | QTR1 | 25/26 | 1 | 0 | 120 | 145 | 87 | 51.67% | 1 | 58 | 0 | 0 | 25 | 0 | 992131 | 50000 | 942131 | 992131 | 944723 | 0 | 0 | 0 | 944723 | 944723 | 100.3% | 1 | 0 | 0 | 22 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-06-05 | QTR4 | 25/26 |  | 2026-04-01 | QTR4 | 25/26 | 208 | 1219061.95
| 02 | T9037 | 44627925214 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 300 | 323 | 260 | 79% | 1 | 63 | 0 | 0 | 23 | 0 | 755793 | 0 | 755793 | 799963 | 782324 | 0 | 0 | 0 | 782324 | 782311 | 103.5% | 1 | -13 | 44170 | 2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | F593399145 | E.B.MORRIS GENERAL CONTRACTORS | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 216 | 588437.99
| 02 | T9039 | 44532025214 | 2024-05-22 | QTR4 | 23/24 | 1 | 2 | 400 | 433 | 375 | 85.5% | 1 | 58 | 0 | 0 | 33 | 0 | 2629396 | 0 | 2629396 | 2652851 | 2657516 | 0 | 0 | 0 | 2657516 | 2657516 | 101.1% | 1 | 0 | 23454 | 1 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 23454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23454 | 0 | F593399145 | E.B.MORRIS GENERAL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-02-03 | QTR3 | 25/26 |  | 2025-12-01 | QTR2 | 25/26 | 208 | 2484683.43
| 02 | T9041 | 44628015215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 45 | 48 | 47 | 97.78% | 1 | 1 | 0 | 0 | 3 | 0 | 211688 | 9600 | 202088 | 211688 | 200166 | 0 | 0 | 0 | 200166 | 200166 | 99.05% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-02-21 | QTR3 | 24/25 | 208 | 233429.76
| 02 | T9042 | 44628225214 | 2025-03-26 | QTR3 | 24/25 | 1 | 0 | 150 | 219 | 219 | 133.3% | 0 | 0 | 0 | 0 | 19 | 50 | 790012 | 22000 | 768012 | 790012 | 769140 | 0 | 0 | 0 | 769140 | 769140 | 100.1% | 1 | 0 | 0 | 11 | 8 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | F593399145 | E.B.MORRIS GENERAL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2026-04-20 | QTR4 | 25/26 | 209 | 477561.11
| 02 | T9044 | 44628025216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 120 | 126 | 92 | 71.67% | 1 | 34 | 0 | 0 | 6 | 0 | 393754 | 22100 | 371654 | 393754 | 371540 | 0 | 0 | 0 | 371540 | 371540 | 99.97% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 208 | 505500
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 60 | 91 | 165 | 18124 | 32624 | 31708 | 63.33% | 38 | 916 | 6 | 0 | 9472 | 5028 | 609019890 | 4806467 | 604213418 | 667240103 | 684188558 | -22878 | 0 | -22878 | 684165680 | 685849724 | 86.67% | 52 | 3546273 | 58220211 | 6204 | 2960 | 619 | 2031 | 12087170 | 1393075 | 166 | 1385 | 35878516 | 7325752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 556 | 7488845 | 3050106 | 155 | 196 | 600681 | 67137 | 0 | 0 | 0 | 0 | 1118 | 650 | 2350971 | 3178 | 0 | 0 | 1388728 | 620012 | 0 | 52 | 1119347 | 685768 | 126 | 148 | 0 | 0 | 0 | 0 | -1595507 | 0 | 2277 | 5018 | 59318751 | 13145027
| 02 | E200W | 44572615201 | 2024-04-17 | QTR4 | 23/24 | 1 | 0 | 180 | 256 | 256 | 113.9% | 1 | 0 | 0 | 0 | 51 | 25 | 2930266 | 50000 | 2880266 | 2930266 | 2970891 | 0 | 0 | 0 | 2970891 | 2968577 | 103.1% | 1 | -2313 | 0 | 28 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17954 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18944 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-06-29 | QTR4 | 24/25 | 209 | 2593407.4
| 02 | E20S0 | 20835235201 | 2022-06-01 | QTR4 | 21/22 | 1 | 2 | 659 | 1216 | 1216 | 166.5% | 0 | 0 | 0 | 0 | 119 | 438 | 10697084 | 97084 | 10600000 | 11279564 | 11359661 | 0 | 0 | 0 | 11359661 | 10989902 | 103.7% | 1 | -369758 | 582480 | 37 | 82 | 0 | 348 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 462480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438 | 582480 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-04-03 | QTR4 | 25/26 |  | 2025-12-14 | QTR2 | 25/26 | 209 | 9959694.79 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E20S1 | 20841835201 | 2022-06-01 | QTR4 | 21/22 | 1 | 1 | 709 | 1164 | 1164 | 143.9% | 0 | 0 | 0 | 0 | 144 | 311 | 11841194 | 116194 | 11725000 | 11946194 | 12025404 | 0 | 0 | 0 | 12025404 | 11833660 | 100.9% | 1 | -191744 | 105000 | 59 | 85 | 0 | 311 | 105047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 105047 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-11 | QTR4 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 209 | 11946614.88 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E20S2 | 21054545201 | 2022-06-01 | QTR4 | 21/22 | 1 | 0 | 609 | 992 | 992 | 127.9% | 0 | 0 | 0 | 0 | 123 | 260 | 8601469 | 80882 | 8520588 | 8601469 | 8734394 | 0 | 0 | 0 | 8734394 | 8453915 | 99.22% | 1 | -280479 | 0 | 136 | 77 | 0 | 90 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 209 | 8397276.42 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E20T6 | 44278015201 | 2023-02-15 | QTR3 | 22/23 | 1 | 2 | 280 | 645 | 645 | 151.1% | 0 | 0 | 0 | 0 | 119 | 246 | 1676236 | 50000 | 1626236 | 1744958 | 1814629 | 0 | 0 | 0 | 1814629 | 1814629 | 111.6% | 0 | 0 | 68722 | 137 | 85 | 0 | 2 | 81415 | 0 | 0 | 141 | 31490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 112905 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 208 | 2494427.5
| 02 | E20X8 | 20840265201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 550 | 717 | 717 | 116.4% | 1 | 0 | 0 | 0 | 167 | 0 | 9409691 | 88302 | 9321389 | 9409691 | 9709502 | 0 | 0 | 0 | 9709502 | 9670685 | 103.7% | 1 | -38817 | 0 | 27 | 50 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-05-22 | QTR4 | 24/25 | 209 | 8868810.45 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E20X9 | 44707615201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 490 | 785 | 780 | 103.3% | 1 | 5 | 0 | 0 | 205 | 90 | 11213775 | 111419 | 11102356 | 11213775 | 11321495 | 0 | 0 | 0 | 11321495 | 11257290 | 101.4% | 1 | -64205 | 0 | 208 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 180 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 209 | 11190658.02 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E21F5 | 43284915201 | 2024-01-09 | QTR3 | 23/24 | 2 | 5 | 480 | 739 | 555 | 97.92% | 1 | 184 | 0 | 0 | 92 | 167 | 13729182 | 150000 | 13579182 | 16720109 | 16682304 | 0 | 0 | 0 | 16682304 | 16681077 | 122.8% | 0 | -1228 | 2990927 | 41 | 44 | 7 | 167 | 3121267 | 143449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 167 | 3121267 | 143449 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-05-11 | QTR4 | 25/26 |  | 2025-10-28 | QTR2 | 25/26 | 208 | 17192402.49 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
| 02 | E21P1 | 21008525201 | 2025-01-15 | QTR3 | 24/25 | 2 | 1 | 150 | 282 | 282 | 100% | 1 | 0 | 0 | 0 | 82 | 50 | 12715932 | 117202 | 12598731 | 13204452 | 13781531 | 0 | 0 | 0 | 13781531 | 13293011 | 105.5% | 1 | 0 | 488520 | 105 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 488520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 488520 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-12 | QTR4 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 209 | 12431030.87
| 02 | E2Z53 | 43035245201 | 2020-02-20 | QTR3 | 19/20 | 2 | 15 | 830 | 1569 | 1562 | 146.4% | 0 | 7 | 0 | 0 | 739 | 0 | 17677113 | 139633 | 17537480 | 32771107 | 33213700 | 0 | 0 | 0 | 33213700 | 33587618 | 191.5% | 0 | 498724 | 15093994 | 241 | 106 | 29 | 0 | 182603 | 0 | 56 | 0 | 402438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 14608377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 15230057 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 214 | 14339167
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 10 | 13 | 26 | 4937 | 8365 | 8169 | 50% | 5 | 196 | 0 | 0 | 1841 | 1587 | 100491942 | 1000716 | 99491228 | 119821585 | 121613511 | 0 | 0 | 0 | 121613511 | 120550364 | 70% | 7 | -449820 | 19329643 | 1019 | 645 | 36 | 918 | 3610332 | 143449 | 146 | 221 | 434918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 110 | 15559377 | 0 | 0 | 0 | 17954 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 1677 | 19659220 | 143449
| District 02 Totals |  |  |  |  | 70 | 104 | 191 | 23061 | 40989 | 39877 | 61.43% | 43 | 1112 | 6 | 0 | 11313 | 6615 | 709511832 | 5807183 | 703704646 | 787061688 | 805802069 | -22878 | 0 | -22878 | 805779191 | 806400088 | 84.29% | 59 | 3096453 | 77549854 | 7223 | 3605 | 655 | 2949 | 15697502 | 1536524 | 312 | 1606 | 36313434 | 7325752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421 | 666 | 23048222 | 3050106 | 155 | 196 | 618635 | 67137 | 0 | 0 | 0 | 0 | 1118 | 1048 | 2387610 | 3178 | 0 | 0 | 1388728 | 620012 | 0 | 52 | 1119347 | 685768 | 126 | 178 | 0 | 0 | 0 | 0 | -1595507 | 0 | 2787 | 6695 | 78977971 | 13288476
| 03 | T3618 | 21790935201 | 2020-05-20 | QTR4 | 19/20 | 1 | 25 | 1000 | 1915 | 1912 | 154.4% | 0 | 3 | 0 | 0 | 401 | 514 | 27170428 | 150000 | 27020428 | 30592621 | 31419600 | 0 | 0 | 0 | 31419600 | 32973116 | 122% | 0 | 1578565 | 3422193 | 242 | 126 | 0 | 106 | 96310 | 0 | 33 | 171 | 1524911 | 17782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 1824610 | 66674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 77645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 514 | 3523475 | 84456 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 313 | 35258008.48
| 03 | T3705 | 43581615201 | 2021-06-09 | QTR4 | 20/21 | 3 | 7 | 1150 | 1341 | 1299 | 96.35% | 1 | 42 | 0 | 0 | 191 | 0 | 21786584 | 150000 | 21636584 | 24287618 | 24447463 | 0 | 0 | 0 | 24447463 | 24458859 | 113% | 0 | 417101 | 2501033 | 111 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 1856044 | 1818253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2538824 | 1818253 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-07-24 | QTR1 | 25/26 | 308 | 31799900.02
| 03 | T3712 | 43937115201 | 2021-11-17 | QTR2 | 21/22 | 1 | 3 | 240 | 280 | 543 | 209.6% | 0 | -263 | 263 | 0 | 40 | 0 | 4199999 | 0 | 4199999 | 4207543 | 4275092 | -681696 | 0 | -681696 | 3593396 | 4275464 | 101.8% | 1 | 682068 | 7544 | 22 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 7544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7544 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2023-08-31 | QTR1 | 23/24 | 321 | 3898368.97
| 03 | T3722 | 41098185201 | 2022-06-15 | QTR4 | 21/22 | 1 | 6 | 600 | 878 | 1063 | 147% | 0 | -185 | 185 | 0 | 197 | 81 | 16220760 | 150000 | 16070760 | 16260965 | 16485438 | -1083175 | 0 | -1083175 | 15402263 | 16125524 | 100.3% | 1 | 723261 | 40205 | 122 | 59 | 0 | 81 | -39105 | 0 | 16 | 0 | 102671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81 | 77715 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-10-24 | QTR2 | 25/26 | 314 | 24461056.7
| 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 2 | 365 | 689 | 689 | 117.8% | 1 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6169465 | 6682488 | 0 | 0 | 0 | 6682488 | 7794860 | 128.1% | 0 | 1176465 | 3017 | 170 | 89 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 21 | 70800 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-26 | QTR3 | 25/26 |  | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29
| 03 | T3786 | 21798625201 | 2022-06-15 | QTR4 | 21/22 | 3 | 2 | 310 | 1136 | 1134 | 192.6% | 0 | 2 | 0 | 0 | 626 | 200 | 12931177 | 73600 | 12857576 | 14015331 | 14246133 | 0 | 0 | 0 | 14246133 | 14084325 | 109.5% | 1 | -161808 | 1084154 | 322 | 215 | 0 | 200 | 1084154 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 200 | 1084154 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 |  | 2026-02-02 | QTR3 | 25/26 | 314 | 10461386.99
| 03 | T3789 | 43813315201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 50 | 230 | 226 | 168% | 0 | 4 | 0 | 0 | 142 | 38 | 383899 | 19912 | 363987 | 397919 | 393163 | -35910 | 0 | -35910 | 357253 | 329110 | 90.42% | 1 | -28143 | 14020 | 115 | 27 | 0 | 0 | 0 | 0 | 0 | 38 | 14020 | 917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 38 | 14020 | 917 | F473361483 | T & T CIVIL CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2026-03-26 | QTR3 | 25/26 |  | 2023-01-27 | QTR3 | 22/23 | 314 | 424157.75
| 03 | T3790 | 43748915201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 255 | 343 | 339 | 98.43% | 1 | 4 | 0 | 0 | 88 | 0 | 3547402 | 0 | 3547402 | 3547402 | 3587891 | 0 | 0 | 0 | 3587891 | 3586665 | 101.1% | 1 | -1225 | 0 | 66 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 313 | 4578761.95
| 03 | T3804 | 42697315201 | 2022-04-27 | QTR4 | 21/22 | 2 | 4 | 200 | 679 | 679 | 177.5% | 0 | 0 | 0 | 0 | 404 | 75 | 6212045 | 50000 | 6162045 | 6299150 | 6924822 | 0 | 0 | 0 | 6924822 | 6889613 | 111.8% | 0 | -35209 | 87105 | 260 | 64 | 161 | 0 | 0 | 0 | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 87105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 75 | 87105 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 313 | 5759918.26
| 03 | T3835 | 44563315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 2 | 435 | 712 | 712 | 117% | 1 | 0 | 0 | 0 | 265 | 12 | 10919335 | 105921 | 10813414 | 11003378 | 11511158 | 0 | 0 | 0 | 11511158 | 11473007 | 106.1% | 1 | -38151 | 84043 | 130 | 73 | 10 | 0 | 22048 | 0 | 52 | 12 | 94616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 12 | 116664 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-09-08 | QTR1 | 25/26 | 314 | 11459373.75
| 03 | T3837 | 22259365201 | 2022-12-07 | QTR2 | 22/23 | 2 | 3 | 425 | 608 | 608 | 109.6% | 1 | 0 | 0 | 0 | 146 | 37 | 11772258 | 136099 | 11636159 | 11871253 | 11834603 | 0 | 0 | 0 | 11834603 | 11821261 | 101.6% | 1 | -13342 | 98995 | 72 | 70 | 0 | 3 | 2170 | 0 | 4 | 12 | 33069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 130287 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37 | 165526 | 579 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-16 | QTR1 | 25/26 |  | 2025-02-07 | QTR3 | 24/25 | 321 | 13447557.24
| 03 | T3840 | 44560215201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 168 | 265 | 265 | 117.9% | 1 | 0 | 0 | 0 | 90 | 7 | 2093575 | 50000 | 2043575 | 2093575 | 2052800 | 0 | 0 | 0 | 2052800 | 2052014 | 100.4% | 1 | -786 | 0 | 38 | 29 | 23 | 7 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 7 | 2900 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2025-11-24 | QTR2 | 25/26 | 314 | 1776459.2
| 03 | T3843 | 43736615201 | 2023-02-22 | QTR3 | 22/23 | 3 | 3 | 450 | 880 | 880 | 128% | 0 | 0 | 0 | 0 | 397 | 33 | 14976878 | 150000 | 14826878 | 15770067 | 16545874 | 0 | 0 | 0 | 16545874 | 16474250 | 111.1% | 0 | -71624 | 793189 | 199 | 105 | 0 | 17 | 182706 | 0 | 90 | 14 | 676082 | 8918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 2 | 8973 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 33 | 867761 | 8918 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-09-30 | QTR1 | 25/26 | 308 | 17116856.14
| 03 | T3844 | 44581515201 | 2023-04-26 | QTR4 | 22/23 | 2 | 1 | 325 | 796 | 793 | 159.1% | 0 | 3 | 0 | 0 | 471 | 0 | 16815829 | 150000 | 16665829 | 16829871 | 17633297 | 0 | 0 | 0 | 17633297 | 17609681 | 105.7% | 1 | -23615 | 14042 | 181 | 95 | 0 | 0 | 0 | 0 | 195 | 0 | 14042 | 11490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 14042 | 11490 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-09-12 | QTR1 | 25/26 | 306 | 15773894.2
| 03 | T3851 | 44292015201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 290 | 517 | 514 | 126.9% | 0 | 3 | 0 | 0 | 227 | 0 | 3185384 | 0 | 3185384 | 3188684 | 3129056 | 0 | 0 | 0 | 3129056 | 3127773 | 98.19% | 1 | -1283 | 3300 | 108 | 38 | 0 | 0 | 0 | 0 | 10 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-10-16 | QTR2 | 25/26 | 306 | 3413369.7
| 03 | T3855 | 44401915201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 140 | 482 | 482 | 194.3% | 0 | 0 | 0 | 0 | 342 | 0 | 958894 | 50000 | 908894 | 958894 | 885299 | 0 | 0 | 0 | 885299 | 885298 | 97.4% | 1 | -1 | 0 | 159 | 51 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2025-05-27 | QTR4 | 24/25 | 308 | 1271778.2
| 03 | T3861 | 44573425201 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 150 | 429 | 429 | 202% | 0 | 0 | 0 | 0 | 156 | 123 | 6086126 | 54106 | 6032020 | 6138322 | 6717678 | 0 | 0 | 0 | 6717678 | 6699730 | 111.1% | 0 | -17947 | 52195 | 79 | 47 | 0 | 0 | 0 | 0 | 30 | 123 | 52195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 123 | 52195 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2025-11-11 | QTR2 | 25/26 | 313 | 6407295.93
| 03 | T3862 | 43977415201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 220 | 395 | 370 | 120.5% | 0 | 25 | 0 | 0 | 105 | 70 | 3433760 | 50000 | 3383760 | 3478528 | 3538382 | 0 | 0 | 0 | 3538382 | 3534775 | 104.5% | 1 | -3607 | 44768 | 61 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 44768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 44768 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 |  | 2025-10-20 | QTR2 | 25/26 | 313 | 3773823.76
| 03 | T3863 | 43256815201 | 2023-03-29 | QTR3 | 22/23 | 3 | 9 | 465 | 677 | 677 | 106.5% | 1 | 0 | 0 | 0 | 202 | 10 | 7039667 | 98677 | 6940990 | 7122635 | 6823877 | 0 | 0 | 0 | 6823877 | 6801370 | 97.99% | 1 | -22508 | 82968 | 107 | 75 | 0 | 9 | 27964 | 0 | 10 | 1 | 75272 | 2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5403 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 108639 | 2965 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2026-04-02 | QTR4 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 308 | 11146776.26
| 03 | T3866 | 21968945201 | 2023-12-06 | QTR2 | 23/24 | 5 | 1 | 395 | 525 | 521 | 110.9% | 1 | 4 | 0 | 0 | 118 | 12 | 7020914 | 104250 | 6916664 | 7091275 | 7209436 | 0 | 0 | 0 | 7209436 | 7195667 | 104% | 1 | -13769 | 70362 | 48 | 35 | 6 | 12 | 79362 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 12 | 79362 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2026-06-11 | QTR4 | 25/26 |  | 2025-08-18 | QTR1 | 25/26 | 321 | 10186904.66
| 03 | T3868 | 41344925201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 90 | 421 | 420 | 396.7% | 0 | 1 | 0 | 0 | 213 | 118 | 1298401 | 50000 | 1248401 | 1321412 | 1234071 | 0 | 0 | 0 | 1234071 | 1234071 | 98.85% | 1 | 0 | 23011 | 20 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-24 | QTR4 | 24/25 | 313 | 1300164.1
| 03 | T3871 | 42695025201 | 2024-06-12 | QTR4 | 23/24 | 2 | 1 | 260 | 335 | 326 | 96.54% | 1 | 9 | 0 | 0 | 75 | 0 | 3111541 | 50000 | 3061541 | 2493770 | 2535278 | 0 | 0 | 0 | 2535278 | 2534712 | 82.79% | 1 | -566 | -617771 | 28 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -617771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -617771 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-09-25 | QTR1 | 25/26 | 314 | 4093773.7
| 03 | T3874 | 44188015201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 74 | 447 | 447 | 181.1% | 0 | 0 | 0 | 0 | 373 | 0 | 988409 | 46367 | 942042 | 988409 | 938135 | 0 | 0 | 0 | 938135 | 938135 | 99.59% | 1 | 0 | 0 | 262 | 51 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 314 | 990878.67
| 03 | T3891 | 43467815201 | 2024-01-31 | QTR3 | 23/24 | 2 | 2 | 200 | 288 | 288 | 100% | 1 | 0 | 0 | 0 | 88 | 0 | 2823614 | 50000 | 2773614 | 2855298 | 2780904 | 0 | 0 | 0 | 2780904 | 2780236 | 100.2% | 1 | -668 | 31684 | 50 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 308 | 3805809.9
| 03 | T3896 | 21995125201 | 2024-10-30 | QTR2 | 24/25 | 2 | 0 | 200 | 272 | 269 | 113.5% | 1 | 3 | 0 | 0 | 72 | 0 | 2986323 | 50000 | 2936323 | 2986323 | 3098563 | 0 | 0 | 0 | 3098563 | 3098475 | 105.5% | 1 | -89 | 0 | 15 | 27 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2026-01-07 | QTR3 | 25/26 | 314 | 3943155.55
| 03 | T3901 | 41342535201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 205 | 261 | 254 | 97.56% | 1 | 7 | 0 | 0 | 54 | 2 | 3608291 | 50000 | 3558291 | 3609941 | 3619668 | 0 | 0 | 0 | 3619668 | 3616057 | 101.6% | 1 | -3611 | 1650 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 2 | 1650 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19319 | 1500 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-07-28 | QTR1 | 25/26 | 321 | 3187529.04
| 03 | T3903 | 43973815201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 150 | 231 | 231 | 109.3% | 1 | 0 | 0 | 0 | 81 | 0 | 3355890 | 50000 | 3305890 | 3355890 | 3514890 | 0 | 0 | 0 | 3514890 | 3515807 | 106.3% | 1 | 917 | 0 | 51 | 16 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-04-01 | QTR4 | 25/26 |  | 2025-12-23 | QTR2 | 25/26 | 314 | 4058350.02
| 03 | T3905 | 22392035201 | 2024-11-13 | QTR2 | 24/25 | 2 | 3 | 197 | 268 | 262 | 101.5% | 1 | 6 | 0 | 0 | 62 | 9 | 4631224 | 50398 | 4580826 | 4783835 | 4745931 | 0 | 0 | 0 | 4745931 | 4746412 | 103.6% | 1 | 481 | 152611 | 34 | 28 | 0 | 0 | 0 | 0 | 0 | 9 | 149127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 152611 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 | 01/23/2026 | 2026-01-23 | QTR3 | 25/26 | 321 | 5602104.94
| 03 | T3909 | 43627425201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 120 | 129 | 123 | 95% | 1 | 6 | 0 | 0 | 9 | 0 | 989048 | 50000 | 939048 | 1062486 | 1040496 | 0 | 0 | 0 | 1040496 | 1040496 | 110.8% | 0 | 0 | 73438 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73438 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2026-04-02 | QTR4 | 25/26 |  | 2025-10-01 | QTR2 | 25/26 | 308 | 1500432.08
| 03 | T3911 | 45100315201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 160 | 221 | 221 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 960717 | 48697 | 912021 | 960717 | 866512 | 0 | 0 | 0 | 866512 | 866512 | 95.01% | 1 | 0 | 0 | 37 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2026-01-13 | QTR3 | 25/26 | 308 | 1028033.47
| 03 | T3913 | 21934625201 | 2024-08-28 | QTR1 | 24/25 | 2 | 1 | 165 | 248 | 221 | 83.64% | 1 | 27 | 0 | 0 | 83 | 0 | 2531784 | 50000 | 2481784 | 2570548 | 2574902 | 0 | 0 | 0 | 2574902 | 2573463 | 103.7% | 1 | -1439 | 38764 | 59 | 24 | 0 | 0 | 61379 | 16559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61379 | 16559 | F592990776 | AMERICAN SAND & X-CAVATION INC. DBA AMERICAN SAND & ASPHALT | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 314 | 3011928.8
| 03 | T3936 | 45221255201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 180 | 235 | 208 | 85% | 1 | 27 | 0 | 0 | 55 | 0 | 993728 | 50000 | 943728 | 993728 | 582095 | 0 | 0 | 0 | 582095 | 582095 | 61.68% | 1 | 0 | 0 | 31 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2026-04-01 | QTR4 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 314 | 1931620.95
| 03 | T3974 | 45221245201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 171 | 186 | 125 | 64.33% | 1 | 61 | 0 | 0 | 15 | 0 | 664538 | 50000 | 614538 | 664538 | 561863 | 0 | 0 | 0 | 561863 | 561863 | 91.43% | 1 | 0 | 0 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 314 | 887346.85
| 03 | T3976 | 45586915201 | 2025-04-30 | QTR4 | 24/25 | 2 | 0 | 60 | 65 | 36 | 51.67% | 1 | 29 | 0 | 0 | 5 | 0 | 138618 | 8268 | 130350 | 138618 | 130350 | 0 | 0 | 0 | 130350 | 130350 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES LLC | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2025-12-08 | QTR2 | 25/26 | 321 | 174042.72
| 03 | T3A07 | 45587615201 | 2025-07-30 | QTR1 | 25/26 | 1 | 1 | 60 | 72 | 48 | 60% | 1 | 24 | 0 | 0 | 12 | 0 | 96095 | 7695 | 88400 | 47595 | 38484 | 0 | 0 | 0 | 38484 | 38484 | 43.53% | 1 | 0 | -48500 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48500 | 0 | F541769861 | WEBBER INFRASTRUCTURE MANAGEMENT INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2026-01-26 | QTR3 | 25/26 | 321 | 164000
| 03 | T9043 | 44628415215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 90 | 124 | 124 | 110% | 1 | 0 | 0 | 0 | 34 | 0 | 189979 | 10000 | 179979 | 189979 | 177334 | 0 | 0 | 0 | 177334 | 177334 | 98.53% | 1 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-05-09 | QTR4 | 24/25 | 308 | 237358.31
| 03 | T9045 | 44628425216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 180 | 199 | 122 | 60% | 1 | 77 | 0 | 0 | 14 | 5 | 511934 | 22600 | 489334 | 511934 | 495348 | 0 | 0 | 0 | 495348 | 495348 | 101.2% | 1 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | F592320406 | BILL SMITH ELECTRIC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-11-05 | QTR2 | 25/26 | 308 | 509928.23
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 37 | 61 | 83 | 10195 | 17779 | 17860 | 62.16% | 23 | -81 | 448 | 0 | 6217 | 1367 | 212801497 | 2320230 | 210481267 | 220859517 | 225278374 | -1800781 | 0 | -1800781 | 223477593 | 227122212 | 81.08% | 30 | 4139467 | 8058020 | 3275 | 1742 | 336 | 435 | 1519888 | 16559 | 715 | 432 | 4636227 | 1861825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 472 | 2291176 | 67253 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 28 | 154402 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683 | 1367 | 8601691 | 1945637
| 03 | E3U65 | 44188515201 | 2022-11-17 | QTR2 | 22/23 | 1 | 0 | 250 | 680 | 695 | 166.8% | 0 | -15 | 15 | 0 | 430 | 0 | 3672487 | 50000 | 3622487 | 3672487 | 3781493 | -38880 | 0 | -38880 | 3742613 | 3739460 | 103.2% | 1 | -3153 | 0 | 186 | 92 | 0 | 0 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 308 | 3629576.67
| 03 | E3V54 | 44554115201 | 2023-02-09 | QTR3 | 22/23 | 3 | 4 | 310 | 751 | 749 | 177.7% | 0 | 2 | 0 | 0 | 275 | 169 | 9981474 | 90589 | 9890885 | 10203672 | 10678123 | 0 | 0 | 0 | 10678123 | 10639564 | 107.6% | 1 | -38559 | 222198 | 136 | 62 | 0 | 51 | 147417 | 0 | 77 | 3 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 44650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 169 | 219567 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2025-05-27 | QTR4 | 24/25 | 314 | 10144016.25
| 03 | E3V77 | 40919375201 | 2023-10-12 | QTR2 | 23/24 | 1 | 0 | 333 | 516 | 511 | 106.9% | 1 | 5 | 0 | 0 | 183 | 0 | 3075367 | 50000 | 3025367 | 3075367 | 2907496 | 0 | 0 | 0 | 2907496 | 2907496 | 96.1% | 1 | 0 | 0 | 87 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-06-13 | QTR4 | 24/25 | 313 | 4067368.66
| 03 | E3V81 | 44563415201 | 2023-06-08 | QTR4 | 22/23 | 3 | 1 | 385 | 538 | 538 | 106.5% | 1 | 0 | 0 | 0 | 144 | 9 | 7280451 | 56951 | 7223500 | 7422322 | 7437743 | 0 | 0 | 0 | 7437743 | 7440600 | 103% | 1 | 2857 | 141871 | 76 | 52 | 0 | 5 | 141871 | 0 | 0 | 0 | 2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 0 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9 | 159630 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-03-03 | QTR3 | 24/25 | 321 | 6184892.36
| 03 | E3W01 | 44559115201 | 2022-09-08 | QTR1 | 22/23 | 2 | 6 | 365 | 828 | 968 | 196.7% | 0 | -140 | 140 | 0 | 443 | 20 | 7469384 | 92731 | 7376653 | 7480930 | 7419597 | -530040 | 0 | -530040 | 6889557 | 6812783 | 92.36% | 1 | -51349 | 11546 | 143 | 107 | 0 | 3 | 8874 | 0 | 198 | 12 | 18933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 42680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 15 | 47234 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 308 | 9544565.57
| 03 | E3W03 | 45034815201 | 2024-09-12 | QTR1 | 24/25 | 1 | 0 | 120 | 201 | 201 | 125% | 0 | 0 | 0 | 0 | 81 | 0 | 433807 | 23255 | 410552 | 433807 | 404077 | 0 | 0 | 0 | 404077 | 404077 | 98.42% | 1 | 0 | 0 | 39 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2026-04-04 | QTR4 | 25/26 |  | 2025-11-13 | QTR2 | 25/26 | 313 | 495857.94
| 03 | E3W12 | 44643355201 | 2024-08-08 | QTR1 | 24/25 | 2 | 1 | 170 | 220 | 220 | 120% | 1 | 0 | 0 | 0 | 16 | 34 | 2949285 | 50000 | 2899285 | 2625347 | 2604415 | 0 | 0 | 0 | 2604415 | 2604415 | 89.83% | 1 | 0 | -323937 | 5 | 11 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | -323937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | -323937 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-22 | QTR1 | 25/26 | 321 | 3480038
| 03 | E3W30 | 44759615201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 365 | 665 | 665 | 154.8% | 0 | 0 | 0 | 0 | 220 | 110 | 4167167 | 50000 | 4117167 | 4263313 | 3906647 | 0 | 0 | 0 | 3906647 | 3906647 | 94.89% | 1 | 0 | 96146 | 18 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 306 | 4722891.55
| 03 | E3W31 | 44554215201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 385 | 696 | 694 | 132.7% | 0 | 2 | 0 | 0 | 311 | 0 | 12495664 | 115497 | 12380167 | 12574093 | 13184954 | 0 | 0 | 0 | 13184954 | 13181542 | 106.5% | 1 | -3412 | 78429 | 133 | 50 | 8 | 0 | 78429 | 78429 | 30 | 0 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 85479 | 78429 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-10-24 | QTR2 | 25/26 | 314 | 11633200.16
| 03 | E3W40 | 44374425201 | 2023-05-11 | QTR4 | 22/23 | 2 | 1 | 240 | 529 | 547 | 127.5% | 0 | -18 | 18 | 0 | 286 | 3 | 6286877 | 58278 | 6228599 | 6497112 | 6613095 | -68148 | 0 | -68148 | 6544947 | 6545243 | 105.1% | 1 | 297 | 210235 | 157 | 84 | 0 | 1 | 7085 | 0 | 45 | 2 | 211204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 3 | 218289 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 308 | 5983264.86
| 03 | E3W42 | 44559015201 | 2023-05-11 | QTR4 | 22/23 | 1 | 1 | 195 | 345 | 394 | 126.7% | 0 | -49 | 49 | 0 | 147 | 3 | 6987787 | 100654 | 6887133 | 6987787 | 7253303 | -185514 | 0 | -185514 | 7067789 | 7068223 | 102.6% | 1 | 435 | 0 | 104 | 43 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 3 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2024-10-15 | QTR2 | 24/25 | 308 | 10217706.9
| 03 | E3W68 | 45102815201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 60 | 65 | 52 | 78.33% | 1 | 13 | 0 | 0 | 5 | 0 | 112106 | 8466 | 103639 | 112106 | 103639 | 0 | 0 | 0 | 103639 | 103639 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-06-12 | QTR4 | 24/25 | 314 | 174993.22
| 03 | E3W69 | 42696125201 | 2023-11-09 | QTR2 | 23/24 | 2 | 1 | 274 | 451 | 451 | 100% | 1 | 0 | 0 | 0 | 177 | 0 | 4685111 | 59134 | 4625977 | 4688658 | 4492681 | 0 | 0 | 0 | 4492681 | 4485331 | 96.96% | 1 | -7350 | 3547 | 133 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 3547 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 3547 | 1539 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-06-18 | QTR4 | 24/25 | 321 | 5910727.48
| 03 | E3W79 | 45109915201 | 2024-04-11 | QTR4 | 23/24 | 1 | 0 | 90 | 143 | 142 | 98.89% | 1 | 1 | 0 | 0 | 53 | 0 | 485265 | 30756 | 454509 | 485265 | 487819 | 0 | 0 | 0 | 487819 | 487819 | 107.3% | 1 | 0 | 0 | 34 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-02-04 | QTR3 | 24/25 | 321 | 555113.46
| 03 | E3X01 | 40619455201 | 2024-10-24 | QTR2 | 24/25 | 1 | 0 | 120 | 159 | 153 | 120% | 1 | 6 | 0 | 0 | 39 | 0 | 328567 | 17193 | 311374 | 328567 | 291720 | 0 | 0 | 0 | 291720 | 291720 | 93.69% | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-10-09 | QTR2 | 25/26 | 313 | 364798.17
| 03 | E3X02 | 44366115201 | 2024-01-18 | QTR3 | 23/24 | 3 | 3 | 395 | 561 | 561 | 105.8% | 1 | 0 | 0 | 0 | 143 | 23 | 17358711 | 150000 | 17208711 | 17495056 | 17763005 | 0 | 0 | 0 | 17763005 | 17748983 | 103.1% | 1 | -14021 | 136345 | 74 | 69 | 0 | 19 | 131100 | 0 | 0 | 4 | 86193 | 23145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 217293 | 23145 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2025-12-03 | QTR2 | 25/26 | 313 | 17119005.62
| 03 | E3X03 | 40619635201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 90 | 112 | 86 | 71.11% | 1 | 26 | 0 | 0 | 22 | 0 | 169075 | 11395 | 157679 | 169075 | 154095 | 0 | 0 | 0 | 154095 | 154095 | 97.73% | 1 | 0 | 0 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 313 | 240133.12
| 03 | E3X08 | 45103115201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 225 | 303 | 223 | 64.44% | 1 | 80 | 0 | 0 | 78 | 0 | 1112248 | 50000 | 1062248 | 1112248 | 1077908 | 0 | 0 | 0 | 1077908 | 1077908 | 101.5% | 1 | 0 | 0 | 44 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-22 | QTR4 | 24/25 | 313 | 1273505.15
| 03 | E3X10 | 41537525201 | 2024-07-11 | QTR1 | 24/25 | 1 | 1 | 245 | 439 | 439 | 124.9% | 0 | 0 | 0 | 0 | 140 | 54 | 6739140 | 74160 | 6664981 | 6837451 | 7312420 | 0 | 0 | 0 | 7312420 | 7306921 | 109.6% | 1 | -5499 | 98311 | 78 | 55 | 7 | 0 | 0 | 0 | 0 | 54 | 98311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 54 | 98311 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2026-01-06 | QTR3 | 25/26 | 314 | 7908180.95
| 03 | E3X17 | 44758915201 | 2024-06-13 | QTR4 | 23/24 | 2 | 1 | 175 | 283 | 282 | 102.3% | 1 | 1 | 0 | 0 | 103 | 5 | 2342678 | 50000 | 2292678 | 2369603 | 2340433 | 0 | 0 | 0 | 2340433 | 2340369 | 102.1% | 1 | -64 | 26925 | 78 | 25 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-26 | QTR1 | 25/26 | 308 | 2975754.37
| 03 | E3X52 | 43078225201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 150 | 208 | 208 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 4271650 | 50000 | 4221650 | 4271650 | 4371998 | 0 | 0 | 0 | 4371998 | 4360199 | 103.3% | 1 | -11799 | 0 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 314 | 4754953.2
| 03 | E3X67 | 45103015201 | 2025-03-20 | QTR3 | 24/25 | 1 | 1 | 120 | 121 | 87 | 71.67% | 1 | 34 | 0 | 0 | 1 | 0 | 756145 | 50000 | 706145 | 589518 | 538882 | 0 | 0 | 0 | 538882 | 538882 | 76.31% | 1 | 0 | -166627 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -166627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -166627 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-04-02 | QTR4 | 25/26 |  | 2025-11-20 | QTR2 | 25/26 | 321 | 979632.72
| 03 | E3X72 | 22020225201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 150 | 200 | 155 | 90% | 1 | 45 | 0 | 0 | 50 | 0 | 647631 | 42452 | 605180 | 647631 | 536583 | 0 | 0 | 0 | 536583 | 536583 | 88.67% | 1 | 0 | 0 | 9 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2025-09-29 | QTR1 | 25/26 | 313 | 900232.57
| 03 | E3X74 | 45102925201 | 2024-11-14 | QTR2 | 24/25 | 1 | 2 | 126 | 283 | 282 | 120.6% | 0 | 1 | 0 | 0 | 153 | 4 | 1642742 | 50000 | 1592742 | 1701821 | 1683345 | 0 | 0 | 0 | 1683345 | 1683345 | 105.7% | 1 | 0 | 59079 | 102 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 65465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 4 | 65465 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2026-04-23 | QTR4 | 25/26 |  | 2026-02-17 | QTR3 | 25/26 | 308 | 1852698.82
| 03 | E3X76 | 44546615201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 245 | 251 | 96 | 36.73% | 1 | 155 | 0 | 0 | 6 | 0 | 2098170 | 50000 | 2048170 | 2098170 | 256639 | 0 | 0 | 0 | 256639 | 256639 | 12.53% | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2025-08-19 | QTR1 | 25/26 | 313 | 2034848.91
| 03 | E3X87 | 45268615201 | 2024-09-12 | QTR1 | 24/25 | 1 | 1 | 120 | 179 | 178 | 132.5% | 0 | 1 | 0 | 0 | 58 | 1 | 1172775 | 50000 | 1122775 | 1197264 | 1124063 | 0 | 0 | 0 | 1124063 | 1124063 | 100.1% | 1 | 0 | 24489 | 12 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 24489 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 321 | 1445110
| 03 | E3X99 | 43622975201 | 2024-09-12 | QTR1 | 24/25 | 1 | 2 | 231 | 321 | 308 | 94.37% | 1 | 13 | 0 | 0 | 90 | 0 | 5036594 | 56398 | 4980196 | 5050202 | 5170364 | 0 | 0 | 0 | 5170364 | 5170313 | 103.8% | 1 | -51 | 13608 | 60 | 30 | 0 | 0 | 18969 | 0 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23069 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2026-02-20 | QTR3 | 25/26 | 308 | 6071472.22
| 03 | E3Y02 | 45258125201 | 2025-04-10 | QTR4 | 24/25 | 1 | 0 | 180 | 274 | 272 | 107.2% | 1 | 2 | 0 | 0 | 94 | 0 | 1467009 | 50000 | 1417009 | 1467009 | 1421040 | 0 | 0 | 0 | 1421040 | 1421040 | 100.3% | 1 | 0 | 0 | 56 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 |  | 2026-04-24 | QTR4 | 25/26 | 314 | 1617018
| 03 | E3Y07 | 43937125201 | 2025-01-30 | QTR3 | 24/25 | 1 | 0 | 120 | 128 | 115 | 89.17% | 1 | 13 | 0 | 0 | 8 | 0 | 493247 | 26670 | 466577 | 493247 | 468786 | 0 | 0 | 0 | 468786 | 468786 | 100.5% | 1 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 321 | 566683.49
| 03 | E3Y25 | 45431115201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 120 | 138 | 136 | 98.33% | 1 | 2 | 0 | 0 | 18 | 0 | 430052 | 29999 | 400053 | 430052 | 391859 | 0 | 0 | 0 | 391859 | 391859 | 97.95% | 1 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 321 | 619869.69
| 03 | E3Y28 | 45443415201 | 2025-04-10 | QTR4 | 24/25 | 1 | 0 | 120 | 125 | 107 | 85% | 1 | 18 | 0 | 0 | 5 | 0 | 339177 | 19836 | 319341 | 339177 | 318764 | 0 | 0 | 0 | 318764 | 318764 | 99.82% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-11-03 | QTR2 | 25/26 | 308 | 393848.24
| 03 | E3Y34 | 45430915201 | 2025-08-14 | QTR1 | 25/26 | 1 | 0 | 120 | 135 | 86 | 59.17% | 1 | 49 | 0 | 0 | 15 | 0 | 882049 | 46891 | 835158 | 882049 | 783756 | 0 | 0 | 0 | 783756 | 783756 | 93.85% | 1 | 0 | 0 | 2 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | F862261446 | UNITED MARINE CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2026-02-10 | QTR3 | 25/26 | 321 | 959603.73
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 32 | 43 | 28 | 6594 | 10848 | 10601 | 65.62% | 21 | 247 | 222 | 0 | 3852 | 435 | 117369892 | 1711305 | 115658587 | 118002056 | 117280742 | -822582 | 0 | -822582 | 116458160 | 116301064 | 100% | 32 | -131668 | 632165 | 1817 | 1102 | 15 | 99 | 533745 | 78429 | 502 | 80 | 486727 | 24684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 217 | -250527 | 0 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 511 | 0 | 42680 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1426 | 400 | 822140 | 103113
| District 03 Totals |  |  |  |  | 69 | 104 | 111 | 16789 | 28627 | 28461 | 63.77% | 44 | 166 | 670 | 0 | 10069 | 1802 | 330171389 | 4031535 | 326139854 | 338861573 | 342559116 | -2623363 | 0 | -2623363 | 339935753 | 343423276 | 89.86% | 62 | 4007799 | 8690185 | 5092 | 2844 | 351 | 534 | 2053633 | 94988 | 1217 | 512 | 5122954 | 1886509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 689 | 2040649 | 67253 | 81 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 802 | 28 | 197082 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3109 | 1767 | 9423831 | 2048750
| 04 | T4560 | 44004315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 482 | 552 | 551 | 99.79% | 1 | 1 | 0 | 0 | 70 | 0 | 2472960 | 50000 | 2422960 | 2472960 | 2454293 | 0 | 0 | 0 | 2454293 | 2461065 | 101.6% | 1 | 134358 | 0 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 19903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21118 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2025-09-22 | QTR1 | 25/26 |  | 2023-02-03 | QTR3 | 22/23 | 409 | 2686957.88
| 04 | T4576 | 43175265201 | 2021-07-28 | QTR1 | 21/22 | 2 | 7 | 709 | 1423 | 1423 | 154% | 0 | 0 | 0 | 0 | 588 | 126 | 11570179 | 110040 | 11460139 | 12011477 | 12175883 | 0 | 0 | 0 | 12175883 | 12224650 | 106.7% | 1 | 48767 | 441298 | 245 | 86 | 91 | 78 | 510193 | 0 | 82 | 0 | -111152 | 2327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 48 | 13588 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 25737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257 | 126 | 438366 | 2327 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2026-05-12 | QTR4 | 25/26 |  | 2025-12-19 | QTR2 | 25/26 | 408 | 11623971.59 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4580 | 43992915201 | 2021-05-26 | QTR4 | 20/21 | 5 | 8 | 739 | 1080 | 1080 | 110% | 1 | 0 | 0 | 0 | 321 | 20 | 18014663 | 150000 | 17864663 | 17978017 | 17209306 | 0 | 0 | 0 | 17209306 | 17705907 | 99.11% | 1 | 548358 | -36647 | 213 | 54 | 26 | 0 | 52717 | 0 | 28 | 0 | 96396 | 32818 | 0 | 0 | 0 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10479 | 0 | 0 | 0 | 8503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51758 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 19502 | 19502 | 0 | 0 | 0 | 0 | 0 | 0 | -63378 | 0 | 54 | 20 | 30554 | 52320 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 409 | 22960743.25
| 04 | T4582 | 43971415201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 701 | 1441 | 1432 | 169.3% | 0 | 9 | 0 | 0 | 740 | 0 | 28428146 | 150000 | 28278146 | 30792178 | 31403804 | 0 | 210000 | 210000 | 31613804 | 31414004 | 111.1% | 0 | 308408 | 2364032 | 135 | 110 | 283 | 0 | 783689 | 0 | 83 | 0 | 488491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1096988 | 0 | 74 | 0 | 33289 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 101236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15924 | 0 | 495 | 0 | 2494307 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2026-04-15 | QTR4 | 25/26 |  | 2025-08-08 | QTR1 | 25/26 | 412 | 26971212.73 | B10 | ACC - BONUS/INCENT/DISINCENT
| 04 | T4606 | 43175615201 | 2022-05-25 | QTR4 | 21/22 | 4 | 13 | 485 | 851 | 851 | 142.1% | 0 | 0 | 0 | 0 | 318 | 48 | 13650945 | 119988 | 13530957 | 16672549 | 16820299 | 0 | 0 | 0 | 16820299 | 16595748 | 122.7% | 0 | -213647 | 3021605 | 114 | 48 | 69 | 48 | 688143 | 187410 | 87 | 0 | 2603372 | 1424637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -232509 | 0 | 156 | 48 | 3059006 | 1612048 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2026-06-15 | QTR4 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 412 | 14924236.89 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4627 | 44384615201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 353 | 497 | 497 | 108.5% | 1 | 0 | 0 | 0 | 114 | 30 | 1831417 | 50000 | 1781417 | 1831417 | 1800868 | 0 | 0 | 0 | 1800868 | 1800868 | 101.1% | 1 | 0 | 0 | 84 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 412 | 2390409.32
| 04 | T4638 | 43580855201 | 2023-07-26 | QTR1 | 23/24 | 4 | 4 | 345 | 512 | 512 | 108.7% | 1 | 0 | 0 | 0 | 137 | 30 | 8148235 | 82702 | 8065534 | 8411133 | 8179681 | 0 | 0 | 0 | 8179681 | 8160560 | 101.2% | 1 | -3998 | 262898 | 110 | 27 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2025-12-02 | QTR2 | 25/26 |  | 2025-07-23 | QTR1 | 25/26 | 412 | 8255267.22
| 04 | T4641 | 43984515201 | 2023-04-26 | QTR4 | 22/23 | 4 | 5 | 721 | 810 | 789 | 97.09% | 1 | 21 | 0 | 0 | 89 | 0 | 11705000 | 114314 | 11590686 | 12054276 | 11872830 | 0 | 0 | 0 | 11872830 | 11832340 | 102.1% | 1 | -11097 | 349276 | 32 | 57 | 0 | 0 | 211859 | 0 | 0 | 0 | 163474 | 18545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386900 | 18545 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-16 | QTR3 | 25/26 |  | 2025-09-05 | QTR1 | 25/26 | 409 | 11870989.01
| 04 | T4643 | 44637415201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 542 | 602 | 566 | 93.36% | 1 | 36 | 0 | 0 | 60 | 0 | 17748021 | 150000 | 17598021 | 18627265 | 18943576 | 0 | 0 | 0 | 18943576 | 18916878 | 107.5% | 1 | -25540 | 879244 | 29 | 31 | 0 | 0 | 886738 | 22797 | 0 | 0 | 7449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911403 | 22797 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-11-17 | QTR2 | 25/26 | 409 | 24914785.02
| 04 | T4645 | 44610215201 | 2023-05-24 | QTR4 | 22/23 | 2 | 4 | 430 | 560 | 558 | 104.4% | 1 | 2 | 0 | 0 | 130 | 0 | 12833449 | 133704 | 12699745 | 12956058 | 12287948 | 0 | 0 | 0 | 12287948 | 12282375 | 96.71% | 1 | 2250 | 122609 | 65 | 44 | 0 | 0 | 35147 | 0 | 21 | 0 | 79638 | 29413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114786 | 29413 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-31 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 409 | 14351247.26
| 04 | T4649 | 44839715201 | 2023-06-14 | QTR4 | 22/23 | 1 | 5 | 254 | 482 | 482 | 163.4% | 0 | 0 | 0 | 0 | 67 | 161 | 4835155 | 50000 | 4785155 | 5082020 | 5106645 | 0 | 0 | 0 | 5106645 | 5105846 | 106.7% | 1 | -798 | 246865 | 59 | 8 | 0 | 0 | 41171 | 0 | 0 | 0 | 40694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 246865 | 0 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 408 | 6110749.35
| 04 | T4651 | 44407915201 | 2023-10-25 | QTR2 | 23/24 | 3 | 6 | 473 | 492 | 347 | 64.27% | 1 | 145 | 0 | 0 | 43 | -24 | 7152200 | 65917 | 7086283 | 7526530 | 7413084 | 0 | 0 | 0 | 7413084 | 7393759 | 104.3% | 1 | -14849 | 529392 | 20 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 28959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28959 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 409 | 6673207.01
| 04 | T4652 | 44616915201 | 2023-11-15 | QTR2 | 23/24 | 2 | 3 | 259 | 447 | 447 | 118.1% | 1 | 0 | 0 | 0 | 188 | 0 | 5424973 | 53119 | 5371854 | 5477905 | 5676734 | 0 | 0 | 0 | 5676734 | 5654422 | 105.3% | 1 | -8426 | 52932 | 107 | 34 | 0 | 0 | 4345 | 0 | 30 | 0 | 53665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 58010 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-10 | QTR3 | 25/26 |  | 2025-08-14 | QTR1 | 25/26 | 408 | 5383942.21
| 04 | T4654 | 44952015201 | 2024-01-31 | QTR3 | 23/24 | 2 | 8 | 289 | 471 | 469 | 109.7% | 1 | 2 | 0 | 0 | 182 | 0 | 5626066 | 61166 | 5564900 | 5715669 | 5782761 | 0 | 0 | 0 | 5782761 | 5777248 | 103.8% | 1 | -91 | 89603 | 124 | 28 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 4409 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2026-01-12 | QTR3 | 25/26 |  | 2025-11-13 | QTR2 | 25/26 | 412 | 6458891.07
| 04 | T4657 | 44447715201 | 2023-12-06 | QTR2 | 23/24 | 3 | 5 | 353 | 689 | 687 | 152.1% | 0 | 2 | 0 | 0 | 336 | 0 | 8333362 | 73888 | 8259474 | 9056685 | 9730673 | 0 | 0 | 0 | 9730673 | 9691783 | 117.3% | 0 | -17540 | 723323 | 101 | 49 | 178 | 0 | 614708 | 8611 | 6 | 0 | 153984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 5372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 0 | 774065 | 8611 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2026-04-15 | QTR4 | 25/26 | 409 | 8086004.65
| 04 | T4661 | 44620015201 | 2024-03-27 | QTR3 | 23/24 | 4 | 4 | 422 | 432 | 352 | 75.59% | 1 | 80 | 0 | 0 | 33 | -46 | 9458464 | 113124 | 9345340 | 9790787 | 9649312 | 0 | 0 | 0 | 9649312 | 9617817 | 102.9% | 1 | -18533 | 566686 | 18 | 15 | 0 | 0 | 108078 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109406 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 |  | 2025-08-20 | QTR1 | 25/26 | 412 | 11108027.65
| 04 | T4662 | 44001515201 | 2023-12-06 | QTR2 | 23/24 | 1 | 3 | 182 | 353 | 351 | 111.5% | 1 | 2 | 0 | 0 | 171 | 0 | 2710165 | 50000 | 2660165 | 2699856 | 2568771 | 0 | 0 | 0 | 2568771 | 2567076 | 96.5% | 1 | -16 | -10309 | 123 | 25 | 0 | 0 | 811 | 0 | 23 | 0 | -6653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | -5843 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 409 | 3354139.5
| 04 | T4663 | 44764715201 | 2023-12-06 | QTR2 | 23/24 | 2 | 3 | 245 | 397 | 395 | 99.18% | 1 | 2 | 0 | 0 | 152 | 0 | 11192757 | 116425 | 11076332 | 11220679 | 11200266 | 0 | 0 | 0 | 11200266 | 11159153 | 100.7% | 1 | -30470 | 27922 | 125 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 17915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17915 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 408 | 11705908.23
| 04 | T4664 | 44699715201 | 2023-09-13 | QTR1 | 23/24 | 3 | 0 | 210 | 395 | 394 | 99.52% | 1 | 1 | 0 | 0 | 185 | 0 | 1247247 | 50000 | 1197247 | 1247247 | 1175544 | 0 | 0 | 0 | 1175544 | 1174544 | 98.1% | 1 | -1000 | 0 | 157 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-05-12 | QTR4 | 24/25 | 412 | 1347694.58
| 04 | T4665 | 44619515201 | 2024-02-28 | QTR3 | 23/24 | 6 | 2 | 240 | 367 | 367 | 100% | 1 | 0 | 0 | 0 | 127 | 0 | 5489802 | 58699 | 5431104 | 5499093 | 5514945 | 0 | 0 | 0 | 5514945 | 5496131 | 101.2% | 1 | -18814 | 9291 | 101 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 9291 | 9291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9291 | 9291 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-07 | QTR3 | 25/26 |  | 2025-10-08 | QTR2 | 25/26 | 412 | 5906510.04
| 04 | T4667 | 44764615201 | 2024-03-27 | QTR3 | 23/24 | 2 | 3 | 271 | 331 | 331 | 100.7% | 1 | 0 | 0 | 0 | 60 | 0 | 5722729 | 58760 | 5663969 | 5878728 | 5826172 | 0 | 0 | 0 | 5826172 | 5808077 | 102.5% | 1 | -12396 | 155998 | 38 | 20 | 0 | 0 | 1638 | 0 | 2 | 0 | 150300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 151938 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-05 | QTR3 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 408 | 5723687.91
| 04 | T4677 | 44767915201 | 2024-05-22 | QTR4 | 23/24 | 4 | 3 | 276 | 298 | 271 | 85.14% | 1 | 27 | 0 | 0 | 36 | -28 | 7765433 | 82562 | 7682871 | 7871392 | 7668837 | 0 | 0 | 0 | 7668837 | 7663134 | 99.74% | 1 | -5703 | 211917 | 15 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 15171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24680 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2025-08-01 | QTR1 | 25/26 | 412 | 8421050.52
| 04 | T4679 | 44619615201 | 2024-01-31 | QTR3 | 23/24 | 3 | 0 | 244 | 337 | 336 | 99.59% | 1 | 1 | 0 | 0 | 93 | 0 | 5469442 | 56677 | 5412765 | 5469442 | 5544372 | 0 | 0 | 0 | 5544372 | 5542177 | 102.4% | 1 | -2195 | 0 | 70 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-12-12 | QTR2 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 412 | 5971108.66
| 04 | T4686 | 42957695201 | 2024-04-24 | QTR4 | 23/24 | 2 | 0 | 244 | 488 | 488 | 118.4% | 1 | 0 | 0 | 0 | 244 | 0 | 3298227 | 50000 | 3248227 | 3298227 | 3079319 | 0 | 0 | 0 | 3079319 | 3078260 | 94.77% | 1 | -1060 | 0 | 148 | 51 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2026-02-23 | QTR3 | 25/26 |  | 2026-01-09 | QTR3 | 25/26 | 412 | 3509812.2
| 04 | T4687 | 45222715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 167 | 237 | 237 | 117.4% | 1 | 0 | 0 | 0 | 70 | 0 | 1600545 | 50000 | 1550545 | 1600545 | 1508063 | 0 | 0 | 0 | 1508063 | 1508063 | 97.26% | 1 | 0 | 0 | 22 | 19 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 408 | 2128846.17
| 04 | T4694 | 44767115201 | 2024-07-31 | QTR1 | 24/25 | 3 | 2 | 291 | 358 | 351 | 97.59% | 1 | 7 | 0 | 0 | 67 | -15 | 3150955 | 50000 | 3100955 | 3159605 | 3107001 | 0 | 0 | 0 | 3107001 | 3106285 | 100.2% | 1 | -716 | 33997 | 45 | 22 | 0 | 0 | 27775 | 0 | 0 | 0 | 21950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49724 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 |  | 2026-01-14 | QTR3 | 25/26 | 409 | 3340322.06
| 04 | T4695 | 44394815201 | 2024-10-30 | QTR2 | 24/25 | 2 | 0 | 188 | 212 | 212 | 101.6% | 1 | 0 | 0 | 0 | 21 | 3 | 2565294 | 50000 | 2515294 | 2565294 | 2420314 | 0 | 0 | 0 | 2420314 | 2420700 | 96.24% | 1 | 386 | 0 | 14 | 7 | 0 | 3 | 921 | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 921 | 921 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2025-11-07 | QTR2 | 25/26 | 412 | 2864084.72
| 04 | T4708 | 44754315201 | 2024-07-31 | QTR1 | 24/25 | 1 | 0 | 200 | 237 | 211 | 87% | 1 | 26 | 0 | 0 | 37 | 0 | 1300000 | 50000 | 1250000 | 1300000 | 1243700 | 0 | 0 | 0 | 1243700 | 1243700 | 99.5% | 1 | 0 | 0 | 22 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2025-08-05 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 412 | 1369377.1
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 28 | 72 | 115 | 10315 | 15351 | 14987 | 82.14% | 23 | 364 | 0 | 0 | 4679 | 305 | 218745831 | 2251085 | 216494748 | 228267034 | 227365001 | 0 | 210000 | 210000 | 227575001 | 227402570 | 89.29% | 25 | 655638 | 10041932 | 2366 | 968 | 647 | 129 | 3967933 | 219739 | 466 | 60 | 4164840 | 1646628 | 0 | 0 | 0 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1126757 | 0 | 91 | 0 | 71790 | 0 | 0 | 0 | 0 | 0 | 208 | 48 | 166582 | 0 | 0 | 161 | 165000 | 0 | 4 | 20 | 51776 | 19502 | 0 | 0 | 0 | 0 | 0 | 0 | -311811 | 0 | 1418 | 418 | 9257445 | 1885870
| 04 | E4Q32 | 43310845201 | 2015-04-27 | QTR4 | 14/15 | 2 | 51 | 1450 | 3156 | 3156 | 177% | 0 | 0 | 0 | 0 | 1179 | 527 | 148749800 | 150000 | 148599800 | 174962816 | 175180045 | 0 | 56000 | 56000 | 175236045 | 174744522 | 117.6% | 0 | -41128 | 26213016 | 414 | 176 | 0 | 0 | 1494952 | 0 | 0 | 0 | 142046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517 | 527 | 21512637 | 3321562 | 0 | 0 | 2751791 | 53052 | 0 | 0 | 0 | 0 | 186 | 0 | 468030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -204577 | 0 | 703 | 527 | 26164878 | 3374614 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2026-02-26 | QTR3 | 25/26 |  | 2024-05-24 | QTR4 | 23/24 | 412 | 122897181 | B10:B5:B8:::Y | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| 04 | E4U48 | 44146615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 281 | 416 | 416 | 110.7% | 1 | 0 | 0 | 0 | 135 | 0 | 2126000 | 50000 | 2076000 | 2132929 | 1513603 | 0 | 0 | 0 | 1513603 | 1506673 | 72.58% | 1 | 0 | 6930 | 77 | 28 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2025-08-04 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 409 | 2622051.6
| 04 | E4U88 | 43999925201 | 2023-04-07 | QTR4 | 22/23 | 1 | 3 | 764 | 860 | 713 | 80.76% | 1 | 147 | 0 | 0 | 96 | 0 | 10631541 | 85557 | 10545984 | 10738131 | 11100934 | 0 | 0 | 0 | 11100934 | 11070252 | 105% | 1 | -1518 | 106590 | 57 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 408 | 10492574.81
| 04 | E4V62 | 43695815201 | 2022-08-18 | QTR1 | 22/23 | 2 | 10 | 622 | 706 | 649 | 90.84% | 1 | 57 | 0 | 0 | 84 | 0 | 31058595 | 150000 | 30908595 | 33155117 | 32699199 | 0 | 0 | 0 | 32699199 | 32554410 | 105.3% | 1 | -144790 | 1946522 | 57 | 27 | 0 | 0 | 1746 | 0 | 0 | 0 | 1779105 | 8878 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239103 | 0 | 0 | 0 | 79175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -118750 | 0 | 0 | 0 | 1989203 | 8878 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2024-10-18 | QTR2 | 24/25 | 412 | 29695111.36
| 04 | E4W05 | 44047315201 | 2022-12-02 | QTR2 | 22/23 | 2 | 11 | 324 | 551 | 550 | 114.5% | 1 | 1 | 0 | 0 | 179 | 48 | 3993841 | 50000 | 3943841 | 4453325 | 4438530 | 0 | 0 | 0 | 4438530 | 4429433 | 112.3% | 0 | -6049 | 459484 | 135 | 44 | 0 | 0 | 14920 | 0 | 0 | 48 | 317478 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 48 | 425398 | 258 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-03-21 | QTR3 | 24/25 | 408 | 4033616.25
| 04 | E4W54 | 44618515201 | 2023-05-05 | QTR4 | 22/23 | 2 | 5 | 241 | 466 | 466 | 100% | 1 | 0 | 0 | 0 | 225 | 0 | 8153790 | 72216 | 8081573 | 8619435 | 8570644 | 0 | 0 | 0 | 8570644 | 8567270 | 106% | 1 | 0 | 469019 | 175 | 50 | 0 | 0 | 121843 | 1201843 | 0 | 0 | 314395 | 24985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3335 | 3335 | 0 | 0 | 22700 | 22700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462272 | 1252862 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-02-14 | QTR3 | 24/25 | 412 | 7653131.2
| 04 | E4W61 | 44610415201 | 2023-08-04 | QTR1 | 23/24 | 1 | 1 | 287 | 408 | 408 | 109.8% | 1 | 0 | 0 | 0 | 121 | 0 | 5369226 | 50000 | 5319226 | 5369226 | 5576786 | 0 | 0 | 0 | 5576786 | 5571433 | 104.7% | 1 | -5352 | 104495 | 64 | 29 | 28 | 0 | 31492 | 0 | 0 | 0 | 7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 38981 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 |  | 2025-04-09 | QTR4 | 24/25 | 409 | 4627615.06
| 04 | E4W65 | 44617415201 | 2024-01-05 | QTR3 | 23/24 | 3 | 0 | 163 | 241 | 241 | 111% | 1 | 0 | 0 | 0 | 78 | 0 | 4920477 | 50000 | 4870477 | 4920477 | 4833727 | 0 | 0 | 0 | 4833727 | 4832964 | 99.23% | 1 | -763 | 0 | 39 | 21 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-15 | QTR1 | 25/26 |  | 2025-06-11 | QTR4 | 24/25 | 409 | 4972817.95
| 04 | E4W69 | 44617315201 | 2023-12-01 | QTR2 | 23/24 | 2 | 2 | 282 | 308 | 235 | 69.15% | 1 | 73 | 0 | 0 | 40 | -14 | 2294610 | 50000 | 2244610 | 2441883 | 2324253 | 0 | 0 | 0 | 2324253 | 2322959 | 103.5% | 1 | -1294 | 147274 | 17 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 32543 | 9889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32543 | 9889 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2026-05-12 | QTR4 | 25/26 |  | 2025-02-07 | QTR3 | 24/25 | 409 | 2294337.98
| 04 | E4W70 | 44617615201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 206 | 323 | 323 | 114.6% | 1 | 0 | 0 | 0 | 117 | 0 | 3860000 | 50000 | 3810000 | 3929208 | 3917472 | 0 | 0 | 0 | 3917472 | 3912966 | 102.7% | 1 | -4506 | 69208 | 62 | 25 | 30 | 0 | 113698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 113698 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2026-05-13 | QTR4 | 25/26 |  | 2026-01-05 | QTR3 | 25/26 | 409 | 3983140.23
| 04 | E4W71 | 44974015201 | 2023-05-05 | QTR4 | 22/23 | 1 | 0 | 82 | 523 | 522 | 550% | 0 | 1 | 0 | 0 | 441 | 0 | 827827 | 45348 | 782479 | 827827 | 848976 | 0 | 0 | 0 | 848976 | 848976 | 108.5% | 1 | 0 | 0 | 38 | 33 | 310 | 0 | 0 | 0 | 0 | 0 | 13151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 0 | 13151 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 412 | 1076147.07
| 04 | E4W72 | 44617015201 | 2023-11-03 | QTR2 | 23/24 | 3 | 5 | 182 | 306 | 303 | 108.8% | 1 | 3 | 0 | 0 | 105 | 19 | 4285836 | 50000 | 4235836 | 4430549 | 4413846 | 0 | 0 | 0 | 4413846 | 4401052 | 103.9% | 1 | -9192 | 144713 | 79 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 85267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 55844 | 55844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 145465 | 55844 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-30 | QTR2 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 408 | 4697027.08
| 04 | E4W82 | 44610515201 | 2024-01-05 | QTR3 | 23/24 | 2 | 2 | 274 | 356 | 355 | 109.1% | 1 | 1 | 0 | 0 | 82 | 0 | 4881711 | 57650 | 4824061 | 4893014 | 4759434 | 0 | 0 | 0 | 4759434 | 4740765 | 98.27% | 1 | -5116 | 11303 | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 23092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 23092 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-04-17 | QTR4 | 24/25 | 409 | 5716819.1
| 04 | E4W88 | 44765415201 | 2024-02-02 | QTR3 | 23/24 | 3 | 3 | 233 | 271 | 240 | 79.4% | 1 | 31 | 0 | 0 | 55 | -17 | 6226524 | 63037 | 6163487 | 6395874 | 6393098 | 0 | 0 | 0 | 6393098 | 6379878 | 103.5% | 1 | -5542 | 169350 | 38 | 17 | 0 | 0 | 103394 | 103394 | 0 | 0 | 59105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162498 | 103394 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-04-09 | QTR4 | 24/25 | 412 | 6625403.9
| 04 | E4W89 | 44767415201 | 2024-07-12 | QTR1 | 24/25 | 1 | 1 | 180 | 262 | 260 | 98.89% | 1 | 2 | 0 | 0 | 82 | 0 | 3966137 | 50000 | 3916137 | 3985889 | 3958991 | 0 | 0 | 0 | 3958991 | 3953275 | 100.9% | 1 | -5716 | 19752 | 60 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 412 | 4276093.35
| 04 | E4W93 | 44764815201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 185 | 224 | 215 | 95.14% | 1 | 9 | 0 | 0 | 39 | 0 | 3198987 | 50000 | 3148987 | 3198987 | 3046918 | 0 | 0 | 0 | 3046918 | 3045966 | 96.73% | 1 | -952 | 0 | 18 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-18 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 408 | 3443705
| 04 | E4X14 | 44932315201 | 2024-04-05 | QTR4 | 23/24 | 1 | 5 | 209 | 308 | 298 | 107.7% | 1 | 10 | 0 | 0 | 78 | 21 | 3689059 | 50000 | 3639059 | 3733032 | 3801506 | 0 | 0 | 0 | 3801506 | 3800583 | 104.4% | 1 | -923 | 43973 | 65 | 8 | 5 | 0 | 0 | 0 | 0 | 21 | 74766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 21 | 74766 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-12 | QTR3 | 25/26 |  | 2025-10-30 | QTR2 | 25/26 | 408 | 2884956.63
| 04 | E4X17 | 44655115201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 132 | 174 | 174 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 1849000 | 50000 | 1799000 | 1870772 | 1768167 | 0 | 0 | 0 | 1768167 | 1768167 | 98.29% | 1 | 0 | 21772 | 38 | 4 | 0 | 0 | 4117 | 0 | 0 | 0 | 22787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26904 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-12 | QTR1 | 25/26 |  | 2025-07-02 | QTR1 | 25/26 | 409 | 2011837.24
| 04 | E4X24 | 44931815201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 222 | 278 | 278 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 3983900 | 50853 | 3933047 | 4183008 | 4262893 | 0 | 0 | 0 | 4262893 | 4262893 | 108.4% | 1 | 0 | 199108 | 48 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199108 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 409 | 5126069.11
| 04 | E4X25 | 44766515201 | 2024-08-02 | QTR1 | 24/25 | 1 | 1 | 224 | 302 | 300 | 109.8% | 1 | 2 | 0 | 0 | 78 | 0 | 3160159 | 50000 | 3110159 | 3174469 | 3061340 | 0 | 0 | 0 | 3061340 | 3061200 | 98.43% | 1 | -140 | 14310 | 41 | 13 | 24 | 0 | 0 | 0 | 0 | 0 | 33144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 61710 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2025-12-02 | QTR2 | 25/26 | 409 | 3262205.68
| 04 | E4X26 | 44766715201 | 2024-10-04 | QTR2 | 24/25 | 3 | 3 | 208 | 217 | 180 | 80.29% | 1 | 37 | 0 | 0 | 19 | -10 | 1352924 | 50000 | 1302924 | 1396379 | 1294317 | 0 | 0 | 0 | 1294317 | 1294741 | 99.37% | 1 | 424 | 43455 | 9 | 4 | 6 | 0 | 5386 | 0 | 0 | 0 | 3300 | 1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 8686 | 1167 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2025-08-14 | QTR1 | 25/26 | 409 | 1552464.85
| 04 | E4X33 | 44359525201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 262 | 309 | 294 | 94.27% | 1 | 15 | 0 | 0 | 47 | 0 | 2579048 | 50000 | 2529048 | 2787519 | 2747199 | 0 | 0 | 0 | 2747199 | 2747177 | 108.6% | 1 | -22 | 208471 | 38 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218168 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-11-13 | QTR2 | 25/26 | 408 | 3891911.4
| 04 | E4X37 | 44768015201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 196 | 280 | 280 | 114.3% | 1 | 0 | 0 | 0 | 84 | 0 | 3165008 | 50000 | 3115008 | 3165008 | 3101006 | 0 | 0 | 0 | 3101006 | 3093987 | 99.33% | 1 | -7020 | 0 | 48 | 8 | 28 | 0 | 12230 | 0 | 0 | 0 | 17517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 29747 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-06-23 | QTR4 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 412 | 3833063.97
| 04 | E4X39 | 44768115201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 170 | 193 | 193 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 2519093 | 50000 | 2469093 | 2519093 | 2422842 | 0 | 0 | 0 | 2422842 | 2420995 | 98.05% | 1 | -1848 | 0 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 412 | 2812112.37
| 04 | E4X44 | 44766015201 | 2024-10-04 | QTR2 | 24/25 | 1 | 0 | 210 | 234 | 215 | 90.95% | 1 | 19 | 0 | 0 | 24 | 0 | 2684615 | 50000 | 2634615 | 2684615 | 2436599 | 0 | 0 | 0 | 2436599 | 2436934 | 92.5% | 1 | 335 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2025-10-30 | QTR2 | 25/26 | 409 | 2738308.26
| 04 | E4X51 | 44765815201 | 2024-08-02 | QTR1 | 24/25 | 3 | 1 | 252 | 287 | 265 | 91.27% | 1 | 22 | 0 | 0 | 35 | 0 | 3535833 | 50000 | 3485833 | 3535833 | 3387300 | 0 | 0 | 0 | 3387300 | 3384814 | 97.1% | 1 | -2487 | 0 | 14 | 21 | 0 | 0 | 13204 | 0 | 0 | 0 | 7499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20703 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 |  | 2025-09-03 | QTR1 | 25/26 | 409 | 3764178.43
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 26 | 44 | 111 | 7841 | 11959 | 11529 | 92.31% | 24 | 430 | 0 | 0 | 3544 | 574 | 273063541 | 1574661 | 271488879 | 303504415 | 301859625 | 0 | 56000 | 56000 | 301915625 | 301154285 | 92.31% | 24 | -243599 | 30398745 | 1706 | 684 | 479 | 0 | 1916982 | 1305237 | 0 | 69 | 2962133 | 45177 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517 | 527 | 21936429 | 3324897 | 0 | 0 | 2959657 | 75752 | 0 | 0 | 0 | 0 | 205 | 0 | 468030 | 0 | 0 | 0 | 323579 | 0 | 60 | 19 | 55844 | 55844 | 26 | 0 | 0 | 0 | 0 | 0 | -323327 | 0 | 1287 | 615 | 30308149 | 4806906
| District 04 Totals |  |  |  |  | 54 | 116 | 226 | 18156 | 27310 | 26516 | 87.04% | 47 | 794 | 0 | 0 | 8223 | 879 | 491809372 | 3825746 | 487983627 | 531771449 | 529224626 | 0 | 266000 | 266000 | 529490626 | 528556855 | 90.74% | 49 | 412039 | 40440677 | 4072 | 1652 | 1126 | 129 | 5884915 | 1524976 | 466 | 129 | 7126973 | 1691805 | 0 | 0 | 8824 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 0 | 0 | 519 | 527 | 23063186 | 3324897 | 91 | 0 | 3031447 | 75752 | 0 | 0 | 0 | 0 | 413 | 48 | 634612 | 0 | 0 | 161 | 488579 | 0 | 64 | 39 | 107620 | 75346 | 26 | 0 | 0 | 0 | 0 | 0 | -635138 | 0 | 2705 | 1033 | 39565594 | 6692776
| 05 | T5650 | 23839555201 | 2020-03-11 | QTR3 | 19/20 | 7 | 12 | 1030 | 1956 | 1956 | 120.9% | 0 | 0 | 0 | 0 | 711 | 215 | 44960000 | 248112 | 44711888 | 46736451 | 46188504 | 0 | 0 | 0 | 46188504 | 47664520 | 106.6% | 1 | 1546573 | 1776451 | 295 | 416 | 0 | 57 | 769813 | 208395 | 0 | 169 | 1007439 | 1180290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63867 | 0 | 0 | 0 | 48656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 1889774 | 1388685 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-02-05 | QTR3 | 25/26 |  | 2025-12-03 | QTR2 | 25/26 | 515 | 45602807.97
| 05 | T5686 | 43667915201 | 2020-05-20 | QTR4 | 19/20 | 7 | 19 | 350 | 1425 | 1427 | 366.9% | 0 | -2 | 2 | 0 | 143 | 932 | 10409198 | 154537 | 10254661 | 14440107 | 14275037 | -18086 | 0 | -18086 | 14256951 | 14546139 | 141.8% | 0 | 445847 | 4030909 | 93 | 50 | 0 | 133 | 999497 | 429 | 0 | 83 | 782660 | 53882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 1802110 | 54311 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-05-14 | QTR4 | 25/26 |  | 2025-02-21 | QTR3 | 24/25 | 507 | 9656860.63
| 05 | T5706 | 42955615201 | 2020-03-25 | QTR3 | 19/20 | 6 | 12 | 1100 | 1761 | 1761 | 109.3% | 1 | 0 | 0 | 0 | 559 | 102 | 44888403 | 150000 | 44738403 | 47699589 | 48432679 | 0 | 0 | 0 | 48432679 | 48287387 | 107.9% | 1 | 2317108 | 2811186 | 343 | 216 | 0 | 0 | 1647033 | 0 | 0 | 102 | 784469 | 30264 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26536 | 0 | 0 | 0 | 12848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 2823138 | 30264 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 513 | 37019154.5
| 05 | T5718 | 43763415201 | 2021-04-28 | QTR4 | 20/21 | 7 | 17 | 690 | 1399 | 1340 | 96.52% | 1 | 59 | 0 | 0 | 674 | 35 | 11250000 | 233500 | 11016500 | 12978309 | 13223828 | 0 | 0 | 0 | 13223828 | 13314228 | 120.9% | 0 | 155455 | 1728309 | 360 | 314 | 0 | 25 | 527918 | 11401 | 0 | 0 | 912863 | 0 | 0 | 10 | 40741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56556 | 0 | 0 | 0 | 355913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1901807 | 11401 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-10-23 | QTR2 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 507 | 10799982.79
| 05 | T5724 | 44111315201 | 2022-06-15 | QTR4 | 21/22 | 6 | 20 | 950 | 1135 | 1034 | 94.74% | 1 | 101 | 0 | 0 | 134 | 51 | 82895000 | 150000 | 82745000 | 89148107 | 90565070 | 0 | 897177 | 897177 | 91462247 | 89663672 | 108.4% | 1 | -1630727 | 6253107 | 70 | 64 | 0 | 98 | 2491682 | 1246739 | 0 | 0 | 3506222 | 15924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9339 | 0 | 0 | 0 | 113493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 6135826 | 1262662 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-05-11 | QTR4 | 25/26 |  | 2025-09-26 | QTR1 | 25/26 | 509 | 78970683.66 | A5 | ICC - BAM/BONUS
| 05 | T5736 | 41503065201 | 2021-05-26 | QTR4 | 20/21 | 9 | 10 | 640 | 1357 | 1351 | 130.3% | 0 | 6 | 0 | 0 | 517 | 200 | 19997789 | 347736 | 19650053 | 21610437 | 21395577 | 0 | 0 | 0 | 21395577 | 21020146 | 107% | 1 | -65708 | 1612647 | 279 | 238 | 0 | 0 | 233130 | 0 | 0 | 90 | 1120476 | 44665 | 0 | 110 | 243132 | 66051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1762159 | 110716 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-06-23 | QTR4 | 25/26 |  | 2025-09-19 | QTR1 | 25/26 | 507 | 17595887.28
| 05 | T5747 | 43366115201 | 2022-05-25 | QTR4 | 21/22 | 5 | 7 | 280 | 568 | 568 | 147.1% | 0 | 0 | 0 | 0 | 156 | 132 | 6696978 | 50000 | 6646978 | 7142732 | 7032054 | 0 | 0 | 0 | 7032054 | 7019736 | 105.6% | 1 | 0 | 445755 | 106 | 50 | 0 | 4 | 88147 | 0 | 0 | 5 | 26731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318 | 0 | 0 | 125 | 296588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 425240 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 |  | 2024-10-22 | QTR2 | 24/25 | 512 | 5918166.26
| 05 | T5759 | 44586715201 | 2023-04-26 | QTR4 | 22/23 | 5 | 6 | 170 | 600 | 588 | 92.94% | 1 | 12 | 0 | 0 | 430 | 0 | 3865830 | 50000 | 3815830 | 3991018 | 3937381 | 0 | 0 | 0 | 3937381 | 3936003 | 103.1% | 1 | -1378 | 125188 | 128 | 302 | 0 | 0 | -12273 | 0 | 0 | 0 | -103071 | 39310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251410 | 185032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136067 | 224342 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-08-13 | QTR1 | 25/26 | 514 | 3318268.57
| 05 | T5760 | 44114515201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 320 | 519 | 515 | 108.1% | 1 | 4 | 0 | 0 | 199 | 0 | 9020145 | 60000 | 8960145 | 9091224 | 9371724 | 0 | 0 | 0 | 9371724 | 9358265 | 104.4% | 1 | -1051 | 71079 | 39 | 130 | 0 | 0 | 75886 | 0 | 30 | 0 | 29231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 110730 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2025-06-27 | QTR4 | 24/25 | 509 | 8000814.19
| 05 | T5777 | 44042425201 | 2023-01-25 | QTR3 | 22/23 | 3 | 5 | 650 | 704 | 611 | 81.23% | 1 | 93 | 0 | 0 | 86 | -32 | 22896706 | 150000 | 22746706 | 23663870 | 23767312 | 0 | 0 | 0 | 23767312 | 22921260 | 100.8% | 1 | -826558 | 767164 | 32 | 51 | 0 | 0 | 12008 | 0 | 0 | 0 | 265981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302220 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 28387049.83 | B10 | ACC - BONUS/INCENT/DISINCENT
| 05 | T5778 | 44569215201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 250 | 396 | 395 | 99.6% | 1 | 1 | 0 | 0 | 146 | 0 | 1617324 | 47000 | 1570324 | 1637324 | 1467772 | 0 | 0 | 0 | 1467772 | 1467140 | 93.43% | 1 | -632 | 20000 | 119 | 27 | 0 | 0 | 34331 | 0 | 0 | 0 | 28098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62429 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-01-30 | QTR3 | 24/25 | 509 | 1625738.6
| 05 | T5786 | 44521715201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 410 | 545 | 545 | 100% | 1 | 0 | 0 | 0 | 135 | 0 | 10986719 | 117744 | 10868975 | 11011859 | 11062198 | 0 | 0 | 0 | 11062198 | 11032701 | 101.5% | 1 | -4358 | 25139 | 80 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-28 | QTR2 | 25/26 |  | 2025-04-10 | QTR4 | 24/25 | 512 | 14985674.13
| 05 | T5789 | 43547125201 | 2023-05-24 | QTR4 | 22/23 | 3 | 3 | 360 | 467 | 467 | 104.2% | 1 | 0 | 0 | 0 | 92 | 15 | 8448064 | 70000 | 8378064 | 8800372 | 8800513 | 0 | 0 | 0 | 8800513 | 8740511 | 104.3% | 1 | 855 | 352308 | 69 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 93573 | 14238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 221451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 318271 | 14238 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 515 | 8153514.72
| 05 | T5792 | 41025135201 | 2023-06-14 | QTR4 | 22/23 | 3 | 9 | 610 | 822 | 816 | 104.3% | 1 | 6 | 0 | 0 | 180 | 32 | 15097285 | 150000 | 14947285 | 15626114 | 15519395 | 0 | 0 | 0 | 15519395 | 15475580 | 103.5% | 1 | -7963 | 1098563 | 116 | 64 | 0 | 0 | 64465 | 0 | 0 | 32 | 474785 | 8321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592234 | 0 | 0 | 0 | 1431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1132914 | 8321 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-13 | QTR3 | 25/26 |  | 2025-12-08 | QTR2 | 25/26 | 513 | 25813007.18
| 05 | T5795 | 24259285201 | 2023-06-14 | QTR4 | 22/23 | 3 | 4 | 380 | 531 | 523 | 113.4% | 1 | 8 | 0 | 0 | 92 | 59 | 8347803 | 60000 | 8287803 | 8496009 | 8830863 | 0 | 0 | 0 | 8830863 | 8791083 | 106.1% | 1 | -490 | 148206 | 43 | 49 | 0 | 59 | 0 | 0 | 0 | 0 | 139202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 145982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 507 | 8013785.1
| 05 | T5796 | 42617915201 | 2023-07-26 | QTR1 | 23/24 | 4 | 3 | 280 | 563 | 562 | 118.6% | 1 | 1 | 0 | 0 | 230 | 53 | 3346229 | 50000 | 3296229 | 3547942 | 3223459 | 0 | 0 | 0 | 3223459 | 3212971 | 97.47% | 1 | -31 | 201713 | 97 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 191255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 191255 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2026-01-07 | QTR3 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 512 | 4393698.6
| 05 | T5797 | 44568915201 | 2023-07-26 | QTR1 | 23/24 | 3 | 3 | 250 | 490 | 490 | 175.2% | 0 | 0 | 0 | 0 | 52 | 188 | 6209544 | 50000 | 6159544 | 6295030 | 5955348 | 0 | 0 | 0 | 5955348 | 5947678 | 96.56% | 1 | -685 | 85486 | 29 | 23 | 0 | 188 | 78501 | 61993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 78501 | 61993 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-01-14 | QTR3 | 25/26 |  | 2025-06-04 | QTR4 | 24/25 | 514 | 5653228.56
| 05 | T5798 | 44569415201 | 2023-11-15 | QTR2 | 23/24 | 4 | 8 | 460 | 743 | 743 | 136.5% | 0 | 0 | 0 | 0 | 115 | 168 | 16797190 | 150000 | 16647190 | 17496951 | 17878429 | 0 | 0 | 0 | 17878429 | 17802427 | 106.9% | 1 | -28255 | 699761 | 63 | 52 | 0 | 10 | 136859 | 0 | 0 | 158 | 535108 | 233146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 671967 | 233146 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 |  | 2026-05-07 | QTR4 | 25/26 | 509 | 15802710.41
| 05 | T5800 | 44585515201 | 2023-07-26 | QTR1 | 23/24 | 3 | 5 | 230 | 409 | 491 | 173% | 0 | -82 | 82 | 0 | 93 | 86 | 3679712 | 50000 | 3629712 | 3851805 | 3808215 | 0 | 0 | 0 | 3808215 | 3802526 | 104.8% | 1 | -69 | 172092 | 61 | 32 | 0 | 84 | 71357 | 36514 | 0 | 9 | 67803 | 17258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 29703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 174435 | 53772 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 |  | 2025-06-05 | QTR4 | 24/25 | 514 | 2818721.96
| 05 | T5801 | 44521915201 | 2023-09-27 | QTR1 | 23/24 | 3 | 1 | 370 | 513 | 509 | 98.92% | 1 | 4 | 0 | 0 | 143 | 0 | 15286323 | 100000 | 15186323 | 15295366 | 15592805 | 0 | 0 | 0 | 15592805 | 15522129 | 102.2% | 1 | -61634 | 9043 | 97 | 46 | 0 | 0 | 33061 | 0 | 0 | 0 | 46645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79706 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 513 | 20005006.42
| 05 | T5804 | 43757515201 | 2024-05-22 | QTR4 | 23/24 | 1 | 2 | 160 | 223 | 223 | 100% | 1 | 0 | 0 | 0 | 63 | 0 | 3278993 | 50000 | 3228993 | 3308018 | 3163264 | 0 | 0 | 0 | 3163264 | 3163188 | 97.96% | 1 | -76 | 29025 | 59 | 4 | 0 | 0 | -17884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17884 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-01-14 | QTR3 | 25/26 |  | 2025-08-23 | QTR1 | 25/26 | 509 | 3131835.47
| 05 | T5805 | 44709215201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 280 | 334 | 332 | 99.29% | 1 | 2 | 0 | 0 | 54 | 0 | 3271306 | 50000 | 3221306 | 3287930 | 3244926 | 0 | 0 | 0 | 3244926 | 3224506 | 100.1% | 1 | -20420 | 16623 | 41 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2024-11-26 | QTR2 | 24/25 | 514 | 4597690.87
| 05 | T5806 | 44709815201 | 2023-09-27 | QTR1 | 23/24 | 3 | 3 | 300 | 435 | 431 | 98.67% | 1 | 4 | 0 | 0 | 135 | 0 | 9892142 | 110000 | 9782142 | 9938977 | 10455307 | 0 | 0 | 0 | 10455307 | 10363664 | 105.9% | 1 | -58186 | 46835 | 73 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 515 | 11922850
| 05 | T5809 | 43915615201 | 2023-09-27 | QTR1 | 23/24 | 4 | 2 | 420 | 517 | 481 | 91.43% | 1 | 36 | 0 | 0 | 97 | 0 | 19059007 | 150000 | 18909007 | 19456279 | 20132774 | 0 | 0 | 0 | 20132774 | 19987244 | 105.7% | 1 | -74410 | 397272 | 63 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-10-06 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 513 | 20470643.27
| 05 | T5811 | 43233215201 | 2023-10-25 | QTR2 | 23/24 | 6 | 6 | 250 | 541 | 540 | 149.6% | 0 | 1 | 0 | 0 | 176 | 115 | 15324226 | 150000 | 15174226 | 16443632 | 16758792 | 0 | 0 | 0 | 16758792 | 16617261 | 109.5% | 1 | -118108 | 1119406 | 124 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 614667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51362 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 62034 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 380350 | 643594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 115 | 1108414 | 643594 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-08-04 | QTR1 | 25/26 | 515 | 22228374.21
| 05 | T5813 | 44529715201 | 2024-05-22 | QTR4 | 23/24 | 8 | 8 | 350 | 524 | 523 | 115.7% | 1 | 1 | 0 | 0 | 118 | 56 | 12355556 | 110600 | 12244956 | 12704374 | 12876675 | 0 | 0 | 0 | 12876675 | 12856184 | 105% | 1 | -4437 | 348818 | 54 | 64 | 0 | 0 | 11111 | 0 | 0 | 56 | 180890 | 10678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 334941 | 10678 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2026-01-30 | QTR3 | 25/26 | 515 | 11348052.96
| 05 | T5826 | 45222915201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 200 | 276 | 273 | 98.5% | 1 | 3 | 0 | 0 | 76 | 0 | 1180815 | 50000 | 1130815 | 1180815 | 979467 | 0 | 0 | 0 | 979467 | 979467 | 86.62% | 1 | 0 | 0 | 71 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-07-08 | QTR1 | 25/26 | 507 | 1609251.1
| 05 | T5830 | 44711715201 | 2024-08-28 | QTR1 | 24/25 | 1 | 1 | 340 | 422 | 419 | 105% | 1 | 3 | 0 | 0 | 62 | 20 | 5590573 | 93262 | 5497311 | 5668631 | 5521349 | 0 | 0 | 0 | 5521349 | 5521187 | 100.4% | 1 | -162 | 78058 | 27 | 35 | 0 | 20 | 78058 | 72368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 78058 | 72368 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-04-29 | QTR4 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 513 | 9572296.4
| 05 | T5833 | 44708915201 | 2024-09-25 | QTR1 | 24/25 | 2 | 0 | 180 | 241 | 241 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 2100000 | 50000 | 2050000 | 2100000 | 2001416 | 0 | 0 | 0 | 2001416 | 2001416 | 97.63% | 1 | 0 | 0 | 8 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 513 | 2701146.14
| 05 | T5835 | 44873915201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 160 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 3081418 | 50000 | 3031418 | 3081418 | 3111059 | 0 | 0 | 0 | 3111059 | 3112003 | 102.7% | 1 | 944 | 0 | 37 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-02 | QTR1 | 25/26 | 515 | 3300432.25
| 05 | T5838 | 44761015201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 290 | 331 | 331 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 7714913 | 89000 | 7625913 | 7714913 | 7712132 | 0 | 0 | 0 | 7712132 | 7711973 | 101.1% | 1 | -159 | 0 | 24 | 17 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-05-05 | QTR4 | 25/26 |  | 2026-03-17 | QTR3 | 25/26 | 507 | 9228481.44
| 05 | T5845 | 45022725201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 160 | 255 | 255 | 113.8% | 1 | 0 | 0 | 0 | 95 | 0 | 2046788 | 50000 | 1996788 | 2046788 | 2023608 | 0 | 0 | 0 | 2023608 | 2023608 | 101.3% | 1 | 0 | 0 | 32 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2026-06-12 | QTR4 | 25/26 |  | 2026-04-16 | QTR4 | 25/26 | 562 | 2468960.18
| 05 | T5846 | 44879915201 | 2025-02-26 | QTR3 | 24/25 | 1 | 0 | 97 | 148 | 147 | 98.97% | 1 | 1 | 0 | 0 | 51 | 0 | 1377191 | 50000 | 1327191 | 1377191 | 1301358 | 0 | 0 | 0 | 1301358 | 1301358 | 98.05% | 1 | 0 | 0 | 34 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-04-13 | QTR4 | 25/26 |  | 2025-11-24 | QTR2 | 25/26 | 507 | 1307521.49
| 05 | T5856 | 45331815201 | 2025-06-11 | QTR4 | 24/25 | 1 | 0 | 100 | 130 | 116 | 86% | 1 | 14 | 0 | 0 | 30 | 0 | 549199 | 34000 | 515199 | 549199 | 499315 | 0 | 0 | 0 | 499315 | 499315 | 96.92% | 1 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2026-05-01 | QTR4 | 25/26 |  | 2026-03-31 | QTR3 | 25/26 | 513 | 501262.75
| 05 | T5857 | 45613715201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 40 | 40 | 10 | 25% | 1 | 30 | 0 | 0 | 0 | 0 | 117123 | 7000 | 110123 | 113191 | 103346 | 0 | 0 | 0 | 103346 | 103346 | 93.85% | 1 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-17 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 513 | 180485.52
| 05 | T5858 | 45616815201 | 2025-03-26 | QTR3 | 24/25 | 5 | 3 | 120 | 130 | 105 | 79.17% | 1 | 25 | 0 | 0 | 10 | 0 | 948635 | 47500 | 901135 | 993577 | 604185 | 0 | 0 | 0 | 604185 | 604185 | 67.05% | 1 | 0 | 44942 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 44942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44942 | 0 | F850531344 | PREMIER PAVING LLC | N/A | N/A | N/A | N/A | 2026-01-09 | QTR3 | 25/26 |  | 2025-09-16 | QTR1 | 25/26 | 514 | 1621409.55
| 05 | T9030 | 44199035223 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 270 | 367 | 366 | 107.8% | 1 | 1 | 0 | 0 | 97 | 0 | 5555556 | 53950 | 5501606 | 5605113 | 5565155 | 0 | 0 | 0 | 5565155 | 5565155 | 101.2% | 1 | 0 | 49558 | 26 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-05-05 | QTR4 | 24/25 | 513 | 5529999.88
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 37 | 130 | 177 | 13497 | 22026 | 21694 | 78.38% | 29 | 332 | 84 | 0 | 6102 | 2427 | 440139683 | 3633941 | 436505742 | 464130662 | 466382291 | -18086 | 897177 | 879091 | 467261382 | 465161162 | 94.59% | 35 | 1561285 | 24560711 | 3195 | 2820 | 0 | 678 | 7347700 | 1637839 | 30 | 704 | 10901921 | 1647976 | 0 | 120 | 293324 | 66051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 79 | 1287092 | 201655 | 0 | 4 | 211109 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 757535 | 0 | 0 | 125 | 701157 | 0 | 0 | 201 | 631504 | 643594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 1911 | 22131339 | 4197114
| 05 | E50B8 | 44521515201 | 2023-06-06 | QTR4 | 22/23 | 4 | 6 | 410 | 645 | 641 | 118.8% | 1 | 4 | 0 | 0 | 154 | 81 | 11282143 | 100000 | 11182143 | 11851012 | 12077791 | 0 | 0 | 0 | 12077791 | 12077791 | 108% | 1 | 0 | 568869 | 109 | 45 | 0 | 6 | 419002 | 23191 | 0 | 37 | 361551 | 8287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 56263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -235426 | 0 | 0 | 84 | 601391 | 31478 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-03-02 | QTR3 | 25/26 |  | 2025-09-05 | QTR1 | 25/26 | 514 | 10131956.15
| 05 | E50F1 | 44656815201 | 2024-02-06 | QTR3 | 23/24 | 1 | 0 | 127 | 172 | 172 | 101.6% | 1 | 0 | 0 | 0 | 43 | 2 | 1104118 | 42000 | 1062118 | 1104118 | 1062935 | 0 | 0 | 0 | 1062935 | 1062929 | 100.1% | 1 | -6 | 0 | 25 | 18 | 0 | 2 | 5887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5887 | 0 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 509 | 1174163.5
| 05 | E50F5 | 44316915201 | 2024-01-04 | QTR3 | 23/24 | 1 | 1 | 290 | 430 | 429 | 123.4% | 0 | 1 | 0 | 0 | 71 | 69 | 5036336 | 50000 | 4986336 | 5073420 | 4545253 | 0 | 0 | 0 | 4545253 | 4525803 | 90.76% | 1 | -19451 | 37085 | 45 | 26 | 0 | 0 | 0 | 0 | 0 | 69 | 62085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 62085 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-06-05 | QTR4 | 24/25 | 514 | 5619045.42
| 05 | E51F2 | 44768815201 | 2024-04-02 | QTR4 | 23/24 | 2 | 1 | 150 | 239 | 238 | 110.7% | 1 | 1 | 0 | 0 | 72 | 17 | 1504656 | 50000 | 1454656 | 1506430 | 1447570 | 0 | 0 | 0 | 1447570 | 1445324 | 99.36% | 1 | -472 | 1774 | 46 | 26 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-21 | QTR4 | 24/25 | 514 | 1590260.07
| 05 | E51F6 | 43923415201 | 2024-03-05 | QTR3 | 23/24 | 3 | 3 | 350 | 458 | 457 | 99.71% | 1 | 1 | 0 | 0 | 108 | 0 | 16652098 | 150000 | 16502098 | 16895551 | 16781249 | 0 | 0 | 0 | 16781249 | 16753875 | 101.5% | 1 | -23602 | 243453 | 50 | 58 | 0 | 0 | 254263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254263 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-12-04 | QTR2 | 25/26 | 512 | 16309344.71
| 05 | E51F7 | 44530215201 | 2024-03-05 | QTR3 | 23/24 | 3 | 5 | 250 | 400 | 400 | 108% | 1 | 0 | 0 | 0 | 130 | 20 | 5562121 | 50000 | 5512121 | 5724310 | 5880473 | 0 | 0 | 0 | 5880473 | 5842942 | 106% | 1 | -14889 | 162189 | 89 | 41 | 0 | 0 | 29317 | 0 | 0 | 20 | 112422 | 22050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 141739 | 22050 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 |  | 2025-10-01 | QTR2 | 25/26 | 512 | 6330177.48
| 05 | E51F9 | 43912415201 | 2024-04-02 | QTR4 | 23/24 | 2 | 2 | 260 | 347 | 320 | 95.38% | 1 | 27 | 0 | 0 | 72 | 15 | 4408516 | 58000 | 4350516 | 4442576 | 4279968 | 0 | 0 | 0 | 4279968 | 4272484 | 98.21% | 1 | 0 | 34060 | 38 | 34 | 0 | 0 | 3850 | 0 | 0 | 0 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30938 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-19 | QTR4 | 24/25 | 513 | 6688704.65
| 05 | E53F2 | 44879115201 | 2024-10-01 | QTR2 | 24/25 | 1 | 3 | 170 | 268 | 268 | 102.9% | 1 | 0 | 0 | 0 | 93 | 5 | 7065614 | 86000 | 6979614 | 7183452 | 7253477 | 0 | 0 | 0 | 7253477 | 7256561 | 104% | 1 | 3084 | 117838 | 75 | 18 | 0 | 5 | 62000 | 0 | 0 | 0 | 47838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 109838 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 514 | 8985393.39
| 05 | E53F5 | 44880015201 | 2024-09-04 | QTR1 | 24/25 | 1 | 0 | 130 | 322 | 321 | 118.5% | 1 | 1 | 0 | 0 | 167 | 25 | 3585802 | 50000 | 3535802 | 3585802 | 3601966 | 0 | 0 | 0 | 3601966 | 3601961 | 101.9% | 1 | -5 | 0 | 59 | 108 | 0 | 3 | 45461 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 45461 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2026-01-06 | QTR3 | 25/26 | 514 | 3427520.56
| 05 | E53F6 | 44880115201 | 2024-08-08 | QTR1 | 24/25 | 1 | 0 | 270 | 372 | 353 | 98.15% | 1 | 19 | 0 | 0 | 88 | 14 | 5664533 | 50000 | 5614533 | 5664533 | 5824248 | 0 | 0 | 0 | 5824248 | 5821719 | 103.7% | 1 | -2529 | 0 | 50 | 38 | 0 | 0 | 6765 | 0 | 0 | 14 | 12871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 19636 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2026-02-24 | QTR3 | 25/26 |  | 2025-11-25 | QTR2 | 25/26 | 509 | 5574707.4
| 05 | E53F7 | 44984515201 | 2024-12-03 | QTR2 | 24/25 | 1 | 0 | 130 | 255 | 255 | 100% | 1 | 0 | 0 | 0 | 125 | 0 | 925088 | 40024 | 885064 | 925088 | 953719 | 0 | 0 | 0 | 953719 | 953719 | 107.8% | 1 | 0 | 0 | 115 | 10 | 0 | 0 | 2525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2525 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-01-13 | QTR3 | 25/26 |  | 2025-11-18 | QTR2 | 25/26 | 507 | 845921.65
| 05 | E53F8 | 45022745201 | 2024-06-04 | QTR4 | 23/24 | 1 | 1 | 160 | 259 | 257 | 111.9% | 1 | 2 | 0 | 0 | 78 | 21 | 1498164 | 50000 | 1448164 | 1498164 | 1468694 | 0 | 0 | 0 | 1468694 | 1468694 | 101.4% | 1 | 0 | 0 | 12 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 24155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24155 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 513 | 1507974.75
| 05 | E54B3 | 44521415201 | 2023-10-03 | QTR2 | 23/24 | 3 | 3 | 270 | 366 | 366 | 100% | 1 | 0 | 0 | 0 | 96 | 0 | 6964127 | 72500 | 6891627 | 7171619 | 7043664 | 0 | 0 | 0 | 7043664 | 6984590 | 101.3% | 1 | -45651 | 207492 | 59 | 37 | 0 | 0 | 167324 | 0 | 0 | 0 | 41679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256083 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 9627438.59
| 05 | E54F0 | 45141535201 | 2024-12-03 | QTR2 | 24/25 | 1 | 0 | 160 | 274 | 274 | 118.8% | 1 | 0 | 0 | 0 | 84 | 30 | 3082346 | 50000 | 3032346 | 3082346 | 3072912 | 0 | 0 | 0 | 3072912 | 3072912 | 101.3% | 1 | 0 | 0 | 4 | 80 | 0 | 30 | 7407 | 6369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 7407 | 6369 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2026-05-01 | QTR4 | 25/26 |  | 2026-03-13 | QTR3 | 25/26 | 512 | 4142464.65
| 05 | E55F3 | 45131115201 | 2025-02-04 | QTR3 | 24/25 | 1 | 0 | 150 | 183 | 183 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 4402920 | 58000 | 4344920 | 4402920 | 4332664 | 0 | 0 | 0 | 4332664 | 4326586 | 99.58% | 1 | -6078 | 0 | 20 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13234 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 |  | 2025-11-05 | QTR2 | 25/26 | 513 | 6422896.48
| 05 | E55F4 | 42690555201 | 2025-04-01 | QTR4 | 24/25 | 1 | 0 | 120 | 121 | 108 | 89.17% | 1 | 13 | 0 | 0 | 1 | 0 | 1132509 | 50000 | 1082509 | 1132509 | 1025664 | 0 | 0 | 0 | 1025664 | 1025664 | 94.75% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES LLC | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 514 | 1246519.8
| 05 | E55F6 | 44529815201 | 2025-03-04 | QTR3 | 24/25 | 1 | 2 | 180 | 230 | 214 | 91.11% | 1 | 16 | 0 | 0 | 50 | 0 | 7863435 | 100000 | 7763435 | 8058116 | 8341201 | 0 | 0 | 0 | 8341201 | 8333175 | 107.3% | 1 | -8027 | 194681 | 36 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 194681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194681 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-12-12 | QTR2 | 25/26 | 514 | 10455826.3
| 05 | E55F9 | 45370915201 | 2025-08-05 | QTR1 | 25/26 | 1 | 0 | 130 | 198 | 159 | 70% | 1 | 39 | 0 | 0 | 68 | 0 | 494060 | 26106 | 467954 | 494060 | 523498 | 0 | 0 | 0 | 523498 | 523851 | 111.9% | 0 | 353 | 0 | 28 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-05-19 | QTR4 | 25/26 |  | 2026-04-13 | QTR4 | 25/26 | 513 | 553243.95
| 05 | E56B6 | 44521115201 | 2023-06-06 | QTR4 | 22/23 | 2 | 1 | 180 | 442 | 442 | 131.7% | 0 | 0 | 0 | 0 | 205 | 57 | 3196756 | 50000 | 3146756 | 3198241 | 3427202 | 0 | 0 | 0 | 3427202 | 3427202 | 108.9% | 1 | 0 | 1485 | 141 | 64 | 0 | 7 | 8757 | 0 | 0 | 30 | 12941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 28133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 49830 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-05-21 | QTR4 | 24/25 | 507 | 3501358.08
| 05 | E56F2 | 45057615201 | 2025-04-01 | QTR4 | 24/25 | 1 | 4 | 250 | 270 | 198 | 66% | 1 | 72 | 0 | 0 | 33 | -13 | 6262690 | 65000 | 6197690 | 6580074 | 6638647 | 0 | 0 | 0 | 6638647 | 6638621 | 107.1% | 1 | -26 | 317384 | 17 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 87115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97504 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2026-05-19 | QTR4 | 25/26 |  | 2026-02-03 | QTR3 | 25/26 | 507 | 7148293.32
| 05 | E56F4 | 41025155201 | 2025-05-06 | QTR4 | 24/25 | 1 | 0 | 140 | 173 | 171 | 98.57% | 1 | 2 | 0 | 0 | 33 | 0 | 3296100 | 53000 | 3243100 | 3296100 | 3182948 | 0 | 0 | 0 | 3182948 | 3193975 | 98.49% | 1 | 11027 | 0 | 9 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2026-01-23 | QTR3 | 25/26 | 513 | 5178576.2
| 05 | E56F7 | 45305815201 | 2025-04-01 | QTR4 | 24/25 | 1 | 0 | 190 | 217 | 196 | 88.95% | 1 | 21 | 0 | 0 | 27 | 0 | 6639966 | 78000 | 6561966 | 6639966 | 6618677 | 0 | 0 | 0 | 6618677 | 6618677 | 100.9% | 1 | 0 | 0 | 7 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 |  | 2026-01-15 | QTR3 | 25/26 | 509 | 8028735.15
| 05 | E57B2 | 44531615201 | 2024-05-07 | QTR4 | 23/24 | 4 | 4 | 350 | 396 | 338 | 83.43% | 1 | 58 | 0 | 0 | 46 | 0 | 5768393 | 58600 | 5709793 | 5840924 | 5658500 | 0 | 0 | 0 | 5658500 | 5645120 | 98.87% | 1 | -2740 | 72531 | 25 | 21 | 0 | 0 | 58741 | 0 | 0 | 0 | 1891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60632 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-06-17 | QTR4 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 507 | 6011562.42
| 05 | E57B3 | 24259265201 | 2023-06-06 | QTR4 | 22/23 | 3 | 4 | 590 | 703 | 696 | 98.81% | 1 | 7 | 0 | 0 | 113 | 0 | 9899345 | 50000 | 9849345 | 10080554 | 10364962 | 0 | 0 | 0 | 10364962 | 10344890 | 105% | 1 | -9 | 181208 | 61 | 52 | 0 | 0 | 111146 | 0 | 0 | 0 | 51682 | 1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162828 | 1682 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2025-12-19 | QTR2 | 25/26 |  | 2025-09-23 | QTR1 | 25/26 | 507 | 8480188.02
| 05 | E57B4 | 44198215201 | 2023-06-06 | QTR4 | 22/23 | 1 | 1 | 280 | 923 | 913 | 220.4% | 0 | 10 | 0 | 0 | 643 | 0 | 3503151 | 50000 | 3453151 | 3638714 | 3552928 | 0 | 0 | 0 | 3552928 | 3552928 | 102.9% | 1 | 0 | 135563 | 21 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 135563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 5102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 140665 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2026-03-06 | QTR3 | 25/26 | 562 | 3345708.84
| 05 | E57B5 | 44530315201 | 2023-06-06 | QTR4 | 22/23 | 3 | 3 | 490 | 635 | 634 | 99.8% | 1 | 1 | 0 | 0 | 145 | 0 | 11137584 | 50000 | 11087584 | 11274458 | 11215283 | 0 | 0 | 0 | 11215283 | 11200767 | 101% | 1 | -786 | 136874 | 80 | 65 | 0 | 0 | 39281 | 0 | 0 | 0 | 110135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149459 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 |  | 2025-08-01 | QTR1 | 25/26 | 507 | 8364007.55
| 05 | E57B7 | 44708515201 | 2023-06-06 | QTR4 | 22/23 | 3 | 5 | 500 | 634 | 634 | 101.2% | 1 | 0 | 0 | 0 | 128 | 6 | 13078910 | 128000 | 12950910 | 13273764 | 13547486 | 0 | 0 | 0 | 13547486 | 13528029 | 104.5% | 1 | -2602 | 194854 | 81 | 47 | 0 | 0 | 39880 | 0 | 0 | 32 | 217171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 257051 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-06-20 | QTR4 | 24/25 | 514 | 13524204.48 | A5 | ICC - BAM/BONUS
| 05 | E57B8 | 44709015201 | 2024-06-04 | QTR4 | 23/24 | 1 | 4 | 200 | 521 | 521 | 180% | 0 | 0 | 0 | 0 | 161 | 160 | 3852254 | 50000 | 3802254 | 4394289 | 4697644 | 0 | 0 | 0 | 4697644 | 4695025 | 123.5% | 0 | -2619 | 542035 | 78 | 83 | 0 | 0 | 1000 | 0 | 0 | 160 | 271211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 581771 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-06-23 | QTR4 | 25/26 |  | 2026-04-08 | QTR4 | 25/26 | 509 | 3125051.88
| 05 | E57F0 | 45057715201 | 2025-07-01 | QTR1 | 25/26 | 1 | 0 | 100 | 121 | 102 | 81% | 1 | 19 | 0 | 0 | 21 | 0 | 339907 | 17000 | 322907 | 339907 | 317523 | 0 | 0 | 0 | 317523 | 317523 | 98.33% | 1 | 0 | 0 | 6 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F333155560 | YOROCA ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2026-06-12 | QTR4 | 25/26 |  | 2026-01-19 | QTR3 | 25/26 | 509 | 405078.25
| 05 | E58F1 | 44529515201 | 2025-09-03 | QTR1 | 25/26 | 1 | 3 | 200 | 221 | 178 | 73.5% | 1 | 43 | 0 | 0 | 31 | -10 | 5893242 | 80000 | 5813242 | 5963607 | 6069935 | 0 | 0 | 0 | 6069935 | 6073721 | 104.5% | 1 | 3786 | 70365 | 13 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-06-22 | QTR4 | 25/26 |  | 2026-04-28 | QTR4 | 25/26 | 515 | 8198292.58
| 05 | E58F2 | 45063515201 | 2025-09-03 | QTR1 | 25/26 | 1 | 0 | 100 | 102 | 66 | 64% | 1 | 36 | 0 | 0 | 2 | 0 | 592801 | 34000 | 558801 | 592801 | 526193 | 0 | 0 | 0 | 526193 | 526193 | 94.16% | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-05-01 | QTR4 | 25/26 |  | 2026-03-25 | QTR3 | 25/26 | 515 | 700854.4
| 05 | E58F3 | 45077215201 | 2025-09-03 | QTR1 | 25/26 | 1 | 0 | 120 | 150 | 146 | 96.67% | 1 | 4 | 0 | 0 | 30 | 0 | 682916 | 30000 | 652916 | 682916 | 662216 | 0 | 0 | 0 | 662216 | 662216 | 101.4% | 1 | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2026-06-23 | QTR4 | 25/26 |  | 2026-04-24 | QTR4 | 25/26 | 515 | 700584.82
| 05 | E58F4 | 45062315201 | 2025-08-05 | QTR1 | 25/26 | 1 | 0 | 120 | 139 | 81 | 51.67% | 1 | 58 | 0 | 0 | 19 | 0 | 1291007 | 50000 | 1241007 | 1291007 | 1311928 | 0 | 0 | 0 | 1311928 | 1311928 | 105.7% | 1 | 0 | 0 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-13 | QTR4 | 25/26 |  | 2026-01-22 | QTR3 | 25/26 | 509 | 1935088.17
| 05 | E59A5 | 44780715201 | 2022-04-06 | QTR4 | 21/22 | 1 | 0 | 270 | 1159 | 1159 | 100% | 1 | 0 | 0 | 0 | 889 | 0 | 973615 | 34352 | 939263 | 973615 | 939263 | 0 | 0 | 0 | 939263 | 939263 | 100% | 1 | 0 | 0 | 141 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-09-19 | QTR1 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 509 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E59B2 | 43986415201 | 2024-02-06 | QTR3 | 23/24 | 3 | 3 | 200 | 286 | 286 | 100% | 1 | 0 | 0 | 0 | 86 | 0 | 3015224 | 50000 | 2965224 | 3086900 | 3009526 | 0 | 0 | 0 | 3009526 | 2958475 | 99.77% | 1 | -4843 | 71676 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-15 | QTR3 | 24/25 | 513 | 3337723.49
| 05 | E59B3 | 44710515201 | 2023-10-03 | QTR2 | 23/24 | 3 | 8 | 330 | 647 | 647 | 106.1% | 1 | 0 | 0 | 0 | 297 | 20 | 9171822 | 94000 | 9077822 | 9565947 | 9919938 | 0 | 0 | 0 | 9919938 | 9890809 | 109% | 1 | -15806 | 394125 | 183 | 114 | 0 | 0 | 271108 | 119817 | 0 | 0 | 179717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15544 | 34566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 466368 | 154383 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2026-02-19 | QTR3 | 25/26 | 513 | 10427761.81
| 05 | E59F3 | 44101515201 | 2025-08-05 | QTR1 | 25/26 | 1 | 0 | 150 | 178 | 112 | 56% | 1 | 66 | 0 | 0 | 28 | 0 | 2681271 | 50000 | 2631271 | 2681271 | 2693179 | 0 | 0 | 0 | 2693179 | 2693179 | 102.4% | 1 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-04-23 | QTR4 | 25/26 |  | 2026-02-17 | QTR3 | 25/26 | 507 | 3752504.41
| 05 | E5Y71 | 43710015201 | 2017-02-10 | QTR3 | 16/17 | 2 | 13 | 580 | 1034 | 1109 | 179% | 0 | -75 | 75 | 0 | 71 | 383 | 13137000 | 150000 | 12987000 | 15625764 | 15527284 | 0 | 0 | 0 | 15527284 | 15513522 | 119.5% | 0 | 0 | 2488764 | 43 | 28 | 0 | 38 | 141704 | 0 | 0 | 110 | 1784758 | 53460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17164 | 0 | 0 | 235 | 601000 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383 | 2544625 | 104460 | F592143889 | COLLAGE DESIGN & CONSTRUCTION G THE COLLAGE COMPANIES | N/A | N/A | N/A | N/A | 2026-06-15 | QTR4 | 25/26 |  | 2026-03-26 | QTR3 | 25/26 | 507 | 13833591
| 05 | E5Z18 | 24020045201 | 2018-08-22 | QTR1 | 18/19 | 4 | 18 | 1400 | 2248 | 2248 | 117.8% | 1 | 0 | 0 | 0 | 599 | 249 | 253332000 | 150000 | 253182000 | 267516079 | 267608352 | 0 | 25000 | 25000 | 267633352 | 268414123 | 106% | 1 | 8560014 | 14184079 | 138 | 461 | 0 | 0 | 2669763 | 0 | 0 | 0 | 2461289 | 94536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 946937 | 321742 | 0 | 0 | 30080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949329 | 0 | 0 | 249 | 7300000 | 7300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 14357398 | 7716278 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2024-12-20 | QTR2 | 24/25 | 507 | 283931078 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 39 | 68 | 98 | 10447 | 16738 | 16292 | 87.18% | 34 | 446 | 75 | 0 | 5140 | 1151 | 445974540 | 2504582 | 443469958 | 466332924 | 467006560 | 0 | 25000 | 25000 | 467031560 | 467496766 | 92.31% | 36 | 8428123 | 20358384 | 1987 | 2806 | 0 | 108 | 4345181 | 149377 | 0 | 494 | 6246716 | 180015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 76 | 1360024 | 356308 | 0 | 20 | 115682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966493 | 0 | 0 | 484 | 7901000 | 7351000 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -235426 | 0 | 42 | 1203 | 20699669 | 8036700
| District 05 Totals |  |  |  |  | 76 | 198 | 275 | 23944 | 38764 | 37986 | 82.89% | 63 | 778 | 159 | 0 | 11242 | 3578 | 886114223 | 6138523 | 879975700 | 930463586 | 933388851 | -18086 | 922177 | 904091 | 934292942 | 932657928 | 93.42% | 71 | 9989408 | 44919095 | 5182 | 5626 | 0 | 786 | 11692881 | 1787216 | 30 | 1198 | 17148637 | 1827991 | 0 | 120 | 293324 | 66051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 155 | 2647116 | 557963 | 0 | 24 | 326791 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 1724028 | 0 | 0 | 609 | 8602157 | 7351000 | 0 | 222 | 631504 | 643594 | 0 | 0 | 0 | 0 | 0 | 0 | -235426 | 0 | 104 | 3114 | 42831008 | 12233814
| 06 | T6466 | 43992315201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 160 | 189 | 184 | 96.88% | 1 | 5 | 0 | 0 | 29 | 0 | 749749 | 36694 | 713055 | 750453 | 687268 | 0 | 0 | 0 | 687268 | 687166 | 96.37% | 1 | -102 | 704 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 613 | 759570.75
| 06 | T6514 | 44462215201 | 2022-04-27 | QTR4 | 21/22 | 3 | 6 | 450 | 576 | 465 | 87.78% | 1 | 111 | 0 | 0 | 70 | 56 | 12567171 | 112026 | 12455145 | 13007370 | 12865831 | 0 | 500000 | 500000 | 13365831 | 12808223 | 102.8% | 1 | -557608 | 440200 | 42 | 28 | 0 | 0 | 75620 | 0 | 0 | 0 | 66701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 320618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 462939 | 0 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2026-01-29 | QTR3 | 25/26 |  | 2024-08-07 | QTR1 | 24/25 | 613 | 11765757.23 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6541 | 44390215201 | 2023-02-22 | QTR3 | 22/23 | 4 | 3 | 400 | 476 | 462 | 96.5% | 1 | 14 | 0 | 0 | 76 | 0 | 6112543 | 50000 | 6062543 | 6196534 | 6055588 | 0 | 0 | 0 | 6055588 | 6046499 | 99.74% | 1 | -7887 | 83991 | 29 | 47 | 0 | 0 | 30261 | 0 | 0 | 0 | 18983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56474 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-06-11 | QTR4 | 24/25 | 613 | 4898503.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6547 | 44392115201 | 2023-05-24 | QTR4 | 22/23 | 4 | 6 | 340 | 533 | 513 | 97.94% | 1 | 20 | 0 | 0 | 180 | 13 | 7844825 | 81266 | 7763559 | 8071972 | 8026073 | 0 | 200000 | 200000 | 8226073 | 8025252 | 103.4% | 1 | -200821 | 227147 | 146 | 34 | 0 | 13 | 211928 | 0 | 0 | 0 | 27940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 239868 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-03-28 | QTR3 | 24/25 | 636 | 8411804.1 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6555 | 44598715201 | 2023-04-26 | QTR4 | 22/23 | 8 | 6 | 500 | 526 | 459 | 86.6% | 1 | 67 | 0 | 0 | 22 | 4 | 15230513 | 150000 | 15080513 | 15276979 | 14673045 | 0 | 440000 | 440000 | 15113045 | 14624087 | 96.97% | 1 | -460650 | 46466 | 10 | 16 | 0 | 0 | 43405 | 0 | 0 | 0 | 81997 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17514 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65908 | 0 | 0 | 0 | 79761 | 21158 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 636 | 16721997.85 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6556 | 44389615201 | 2023-05-24 | QTR4 | 22/23 | 5 | 5 | 450 | 493 | 434 | 86.89% | 1 | 59 | 0 | 0 | 43 | 0 | 12343500 | 99969 | 12243531 | 12329103 | 12004695 | 0 | 340000 | 340000 | 12344695 | 12003108 | 98.04% | 1 | -341587 | -14397 | 13 | 30 | 0 | 0 | 51988 | 0 | 0 | 0 | 192434 | 111954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6723 | 0 | 0 | 0 | 1786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -260667 | 0 | 0 | 0 | -7736 | 111954 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-02-06 | QTR3 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 636 | 10090244.35 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6562 | 44393715201 | 2023-03-29 | QTR3 | 22/23 | 6 | 0 | 400 | 455 | 384 | 82.25% | 1 | 71 | 0 | 0 | 55 | 0 | 9816354 | 102429 | 9713925 | 9816354 | 9814725 | 0 | 320000 | 320000 | 10134725 | 9792214 | 100.8% | 1 | -342511 | 0 | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-08 | QTR1 | 25/26 |  | 2025-01-20 | QTR3 | 24/25 | 613 | 10415642.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6564 | 44599515201 | 2023-12-06 | QTR2 | 23/24 | 2 | 2 | 240 | 259 | 219 | 83.33% | 1 | 40 | 0 | 0 | 19 | 0 | 2427793 | 50000 | 2377793 | 2522356 | 2377282 | 0 | 100000 | 100000 | 2477282 | 2374390 | 99.86% | 1 | -102891 | 94563 | 5 | 14 | 0 | 0 | 13136 | 0 | 0 | 0 | 34463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54683 | 3620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102281 | 3620 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 636 | 2381685.3 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6565 | 44389815202 | 2023-02-22 | QTR3 | 22/23 | 3 | 3 | 480 | 626 | 584 | 98.75% | 1 | 42 | 0 | 0 | 110 | 36 | 17424162 | 150000 | 17274162 | 17775584 | 17807123 | 0 | 360000 | 360000 | 18167123 | 17726459 | 102.6% | 1 | -440664 | 351422 | 80 | 30 | 0 | 0 | 84168 | 0 | 0 | 36 | 237134 | 22708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 443354 | 22708 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 |  | 2025-05-09 | QTR4 | 24/25 | 636 | 16704094.5 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6567 | 44757415201 | 2024-05-22 | QTR4 | 23/24 | 2 | 1 | 197 | 320 | 313 | 96.45% | 1 | 7 | 0 | 0 | 123 | 0 | 1669000 | 50000 | 1619000 | 1695000 | 1692054 | 0 | 0 | 0 | 1692054 | 1691797 | 104.5% | 1 | -258 | 26000 | 98 | 25 | 0 | 0 | 15742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15742 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-03-09 | QTR3 | 25/26 |  | 2026-01-30 | QTR3 | 25/26 | 613 | 1801028.4
| 06 | T6568 | 44393225201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 154 | 185 | 179 | 96.1% | 1 | 6 | 0 | 0 | 31 | 0 | 1068800 | 50000 | 1018800 | 1068800 | 1002901 | 0 | 0 | 0 | 1002901 | 1002859 | 98.44% | 1 | -41 | 0 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F832482227 | TRAFFICO LLC | N/A | N/A | N/A | N/A | 2026-01-22 | QTR3 | 25/26 |  | 2025-10-16 | QTR2 | 25/26 | 613 | 1151283.4
| 06 | T6573 | 44599115201 | 2023-12-06 | QTR2 | 23/24 | 4 | 3 | 450 | 488 | 422 | 85.33% | 1 | 66 | 0 | 0 | 38 | 0 | 7944520 | 85047 | 7859473 | 7965978 | 7740756 | 0 | 320000 | 320000 | 8060756 | 7730600 | 98.36% | 1 | -330157 | 21458 | 15 | 23 | 0 | 0 | 10477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2205 | 2205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12682 | 2205 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 636 | 8387398.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6574 | 44780515201 | 2023-10-25 | QTR2 | 23/24 | 2 | 2 | 300 | 333 | 284 | 83.67% | 1 | 49 | 0 | 0 | 33 | 0 | 3338573 | 50000 | 3288573 | 3388573 | 3361643 | 0 | 100000 | 100000 | 3461643 | 3354655 | 102% | 1 | -106988 | 50000 | 23 | 10 | 0 | 0 | 12008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33215 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-10-14 | QTR2 | 25/26 |  | 2025-03-27 | QTR3 | 24/25 | 613 | 3605553.8 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6575 | 44780615201 | 2024-01-31 | QTR3 | 23/24 | 2 | 1 | 200 | 303 | 303 | 111% | 1 | 0 | 0 | 0 | 103 | 0 | 4637389 | 50000 | 4587389 | 4652332 | 4600291 | 0 | 0 | 0 | 4600291 | 4582375 | 99.89% | 1 | -2973 | 14943 | 59 | 22 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 636 | 4247705.35
| 06 | T6577 | 44390915201 | 2024-04-24 | QTR4 | 23/24 | 2 | 4 | 320 | 382 | 299 | 74.06% | 1 | 83 | 0 | 0 | 62 | 0 | 4280927 | 50000 | 4230927 | 4380927 | 4298470 | 0 | 180000 | 180000 | 4478470 | 4296065 | 101.5% | 1 | -182405 | 100000 | 51 | 11 | 0 | 0 | 25028 | 0 | 0 | 0 | 21810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22967 | 0 | 0 | 0 | 13118 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82924 | 2195 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-12-05 | QTR2 | 25/26 | 613 | 4677512.3 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6580 | 44600015201 | 2024-04-24 | QTR4 | 23/24 | 3 | 4 | 380 | 458 | 458 | 100% | 1 | 0 | 0 | 0 | 78 | 0 | 5947099 | 61718 | 5885381 | 6376641 | 6242028 | 0 | 0 | 0 | 6242028 | 6225782 | 105.8% | 1 | -16246 | 429541 | 35 | 43 | 0 | 0 | 266153 | 1847 | 0 | 0 | 30029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160523 | 0 | 0 | 0 | 2939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459644 | 1847 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2026-02-04 | QTR3 | 25/26 | 636 | 6394668.5 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6584 | 44391215201 | 2024-03-27 | QTR3 | 23/24 | 3 | 5 | 380 | 430 | 360 | 81.58% | 1 | 70 | 0 | 0 | 50 | 0 | 8558846 | 77205 | 8481641 | 8890402 | 8748106 | 0 | 220000 | 220000 | 8968106 | 8742165 | 103.1% | 1 | -225941 | 331556 | 27 | 23 | 0 | 0 | 69085 | 0 | 0 | 0 | 250233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65727 | 7495 | 0 | 0 | 7079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392125 | 7495 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 613 | 7821851.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6597 | 44936015201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 200 | 258 | 257 | 99.5% | 1 | 1 | 0 | 0 | 58 | 0 | 1671710 | 50000 | 1621710 | 1671710 | 1568639 | 0 | 0 | 0 | 1568639 | 1568617 | 96.73% | 1 | -22 | 0 | 24 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F843316177 | FLORIDA SIGNAL & LIGHTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2026-05-08 | QTR4 | 25/26 |  | 2026-02-27 | QTR3 | 25/26 | 636 | 1785608.4
| 06 | T6598 | 44780415201 | 2024-09-25 | QTR1 | 24/25 | 2 | 1 | 240 | 271 | 220 | 78.75% | 1 | 51 | 0 | 0 | 31 | 0 | 2627713 | 50000 | 2577713 | 2705308 | 2578007 | 0 | 120000 | 120000 | 2698007 | 2578006 | 100% | 1 | -120001 | 77594 | 23 | 8 | 0 | 0 | 11001 | 0 | 0 | 0 | 66593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77594 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-10-08 | QTR2 | 25/26 | 636 | 3026337.1 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6602 | 44623915201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 300 | 317 | 198 | 54.67% | 1 | 119 | 0 | 0 | 34 | -17 | 3433699 | 50000 | 3383699 | 3555649 | 3477140 | 0 | 100000 | 100000 | 3577140 | 3476420 | 102.7% | 1 | -100720 | 121950 | 26 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4647 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2025-12-19 | QTR2 | 25/26 | 613 | 3703879.83 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6605 | 44389945201 | 2024-12-04 | QTR2 | 24/25 | 4 | 1 | 240 | 272 | 220 | 78.33% | 1 | 52 | 0 | 0 | 32 | 0 | 1755688 | 50000 | 1705688 | 1780688 | 1741502 | 0 | 200000 | 200000 | 1941502 | 1741636 | 102.1% | 1 | -199866 | 25000 | 11 | 21 | 0 | 0 | 22824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22824 | 0 | F843316177 | FLORIDA SIGNAL & LIGHTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2026-05-18 | QTR4 | 25/26 |  | 2026-03-18 | QTR3 | 25/26 | 613 | 1854603.65 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 21 | 63 | 55 | 6781 | 8150 | 7217 | 100% | 21 | 933 | 0 | 0 | 1277 | 92 | 131450574 | 1506354 | 129944220 | 133878713 | 131363167 | 0 | 3500000 | 3500000 | 134863167 | 131078375 | 100% | 21 | -3740339 | 2428138 | 790 | 469 | 0 | 13 | 942824 | 1847 | 22 | 36 | 1029021 | 155820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 778037 | 11115 | 0 | 0 | 55734 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -326575 | 0 | 22 | 105 | 2479042 | 173182
| 06 | E6L20 | 25054885201 | 2022-05-26 | QTR4 | 21/22 | 9 | 6 | 800 | 926 | 890 | 95.5% | 1 | 36 | 0 | 0 | 126 | 0 | 28158187 | 150000 | 28008187 | 28920235 | 27890563 | 0 | 120000 | 120000 | 28010563 | 27701758 | 98.91% | 1 | -239034 | 762049 | 79 | 47 | 0 | 0 | 54216 | 11723 | 0 | 0 | 229137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747305 | 11723 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-13 | QTR3 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 636 | 23137912.5 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | E6M86 | 43351125201 | 2021-05-27 | QTR4 | 20/21 | 3 | 13 | 1020 | 1267 | 1212 | 103.3% | 1 | 55 | 0 | 0 | 158 | 89 | 41366428 | 150000 | 41216428 | 43068537 | 43251556 | 0 | 1960000 | 1960000 | 45211556 | 43282192 | 105% | 1 | -173492 | 1702108 | 104 | 54 | 0 | 0 | 601267 | 0 | 0 | 0 | 386677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 685738 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -94401 | 0 | 0 | 89 | 1678869 | 0 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-03-12 | QTR3 | 24/25 | 613 | 33950112.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | E6N17 | 44716515201 | 2021-09-13 | QTR1 | 21/22 | 5 | 12 | 900 | 1272 | 1272 | 119.7% | 1 | 0 | 0 | 0 | 195 | 177 | 66054600 | 150000 | 65904600 | 66794016 | 66824078 | 0 | 1200000 | 1200000 | 68024078 | 67015448 | 101.7% | 1 | -977158 | 739416 | 132 | 63 | 0 | 0 | 168972 | 0 | 0 | 177 | 1395729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042425 | 0 | 0 | 0 | 396899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -994258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1304449 | 0 | 0 | 177 | 705319 | 0 | F834649779 | AGI DE MOYA JOINT VENTURE | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 |  | 2025-07-25 | QTR1 | 25/26 | 636 | 34964142.28 | B5:B5:B5::::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| 06 | E6O12 | 44391925201 | 2023-05-25 | QTR4 | 22/23 | 3 | 1 | 280 | 309 | 263 | 83.57% | 1 | 46 | 0 | 0 | 29 | 0 | 2869869 | 50000 | 2819869 | 2869869 | 2778313 | 0 | 140000 | 140000 | 2918313 | 2778250 | 98.52% | 1 | -140063 | 0 | 8 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 |  | 2025-04-24 | QTR4 | 24/25 | 636 | 2865779.1 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | E6O17 | 43029169201 | 2022-06-13 | QTR4 | 21/22 | 2 | 3 | 628 | 1156 | 1148 | 143.9% | 0 | 8 | 0 | 0 | 384 | 144 | 7237000 | 51988 | 7185012 | 7269318 | 7237180 | 0 | 0 | 0 | 7237180 | 0 | 0% | 1 | -7237180 | 32318 | 121 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 19850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 32318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 52168 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 636 | 5284476.93 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6O81 | 44598815201 | 2024-03-28 | QTR3 | 23/24 | 1 | 1 | 250 | 259 | 222 | 85.2% | 1 | 37 | 0 | 0 | 9 | 0 | 3370711 | 50000 | 3320711 | 3853261 | 3033601 | 0 | 120000 | 120000 | 3153601 | 3032315 | 91.32% | 1 | -121286 | 482550 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 482550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482550 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 613 | 3432003 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6O89 | 44480315201 | 2024-07-25 | QTR1 | 24/25 | 1 | 1 | 280 | 379 | 369 | 96.43% | 1 | 10 | 0 | 0 | 99 | 0 | 1776181 | 50000 | 1726181 | 1776181 | 1798839 | 0 | 0 | 0 | 1798839 | 1798839 | 104.2% | 1 | 0 | 0 | 74 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2026-04-14 | QTR4 | 25/26 |  | 2026-01-30 | QTR3 | 25/26 | 613 | 2017257.53
| 06 | E6P13 | 43029189201 | 2024-04-22 | QTR4 | 23/24 | 2 | 0 | 400 | 475 | 459 | 96% | 1 | 16 | 0 | 0 | 75 | 0 | 1315382 | 50000 | 1265382 | 1315382 | 1284180 | 0 | 0 | 0 | 1284180 | 0 | 0% | 1 | -1284180 | 0 | 44 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-11-13 | QTR2 | 25/26 |  | 2025-09-19 | QTR1 | 25/26 | 636 | 1725000 | Y | DESIGN/BUILD PROJECT
| 06 | E6P23 | 44391115201 | 2024-03-28 | QTR3 | 23/24 | 1 | 7 | 340 | 363 | 320 | 87.35% | 1 | 43 | 0 | 0 | 23 | 0 | 5790735 | 50000 | 5740735 | 6121430 | 5667306 | 0 | 100000 | 100000 | 5767306 | 5665707 | 98.69% | 1 | -101599 | 330695 | 13 | 10 | 0 | 0 | 58475 | 0 | 0 | 0 | 97436 | 21191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47458 | 32917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316829 | 54108 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-11-21 | QTR2 | 25/26 |  | 4862238.65 | B5 | ACC - INCENTIVE/DISINCENTIVE
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 9 | 27 | 44 | 4898 | 6406 | 6155 | 88.89% | 8 | 251 | 0 | 0 | 1098 | 410 | 157939093 | 751988 | 157187105 | 161988229 | 159765616 | 0 | 3640000 | 3640000 | 163405616 | 151274509 | 100% | 9 | -10273992 | 4049136 | 579 | 379 | 0 | 0 | 882930 | 11723 | 0 | 177 | 2611379 | 21191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233 | 2309831 | 0 | 0 | 0 | 470282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -935876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47458 | 32917 | 0 | 0 | 0 | 0 | 0 | 0 | -1398850 | 0 | 0 | 410 | 3987153 | 65831
| District 06 Totals |  |  |  |  | 30 | 90 | 99 | 11679 | 14556 | 13372 | 96.67% | 29 | 1184 | 0 | 0 | 2375 | 502 | 289389667 | 2258342 | 287131325 | 295866942 | 291128783 | 0 | 7140000 | 7140000 | 298268783 | 282352884 | 100% | 30 | -14014331 | 6477274 | 1369 | 848 | 0 | 13 | 1825754 | 13570 | 22 | 213 | 3640400 | 177011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 3087868 | 11115 | 0 | 0 | 526016 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | -935876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47458 | 32917 | 0 | 0 | 0 | 0 | 0 | 0 | -1725425 | 0 | 22 | 515 | 6466195 | 239013
| 07 | T7388 | 41656125201 | 2017-05-24 | QTR4 | 16/17 | 2 | 11 | 1090 | 1577 | 2259 | 189.4% | 0 | -682 | 682 | 0 | 194 | 293 | 42444444 | 614375 | 41830070 | 42657075 | 42354504 | -1680946 | 0 | -1680946 | 40673558 | 42889778 | 102.5% | 1 | 2252365 | 212630 | 112 | 82 | 0 | 0 | 367285 | 42702 | 0 | 111 | 518341 | 24857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63256 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 975484 | 67559 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2024-02-02 | QTR3 | 23/24 | 798 | 46455035.14 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | T7396 | 41673245201 | 2019-07-31 | QTR1 | 19/20 | 4 | 12 | 1200 | 1366 | 1366 | 100% | 1 | 0 | 0 | 0 | 166 | 0 | 55832153 | 444272 | 55387881 | 56499915 | 56120655 | 0 | 875160 | 875160 | 56995815 | 56570953 | 102.1% | 1 | -113501 | 667762 | 87 | 79 | 0 | 0 | 537977 | 184519 | 0 | 0 | 204897 | 116725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835048 | 301244 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2023-07-17 | QTR1 | 23/24 | 798 | 63202968.19 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 07 | T7412 | 43057315201 | 2018-06-13 | QTR4 | 17/18 | 1 | 14 | 800 | 1068 | 1549 | 167.6% | 0 | -481 | 481 | 0 | 208 | 60 | 32988889 | 150000 | 32838889 | 34384864 | 34586933 | -1228315 | 0 | -1228315 | 33358618 | 33443535 | 101.8% | 1 | 320746 | 1395975 | 142 | 66 | 0 | 0 | 105009 | 45664 | 0 | 60 | 1508758 | 95248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238811 | 7454 | 0 | 0 | 2194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39767 | 23709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -376409 | 0 | 0 | 60 | 1518130 | 172075 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2023-04-04 | QTR4 | 22/23 | 714 | 37580000
| 07 | T7433 | 25632315201 | 2019-06-12 | QTR4 | 18/19 | 3 | 20 | 1200 | 1864 | 1979 | 143.1% | 0 | -115 | 115 | 0 | 262 | 402 | 49694444 | 321270 | 49373174 | 52738117 | 53453750 | -247450 | 0 | -247450 | 53206300 | 54510903 | 110.4% | 0 | 1422327 | 3043672 | 140 | 122 | 0 | 229 | 2933881 | 131927 | 0 | 3 | 125100 | 6866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7171 | 0 | 0 | 0 | 32928 | 16226 | 0 | 0 | 0 | 0 | 0 | 0 | 98540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | -101796 | 0 | 0 | 252 | 3095825 | 155019 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2025-01-29 | QTR3 | 24/25 | 798 | 58098403.79
| 07 | T7445 | 43751415201 | 2020-06-10 | QTR4 | 19/20 | 4 | 7 | 500 | 588 | 962 | 181.6% | 0 | -374 | 374 | 0 | 54 | 34 | 19998889 | 216781 | 19782108 | 21060736 | 21787737 | -1055507 | 0 | -1055507 | 20732231 | 20815167 | 105.2% | 1 | 287019 | 1061847 | 25 | 29 | 0 | 34 | 809476 | 0 | 0 | 0 | 39834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1009715 | 0 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2026-05-07 | QTR4 | 25/26 |  | 2023-08-28 | QTR1 | 23/24 | 798 | 21050900
| 07 | T7460 | 43604115201 | 2021-01-27 | QTR3 | 20/21 | 2 | 5 | 380 | 561 | 684 | 146.1% | 0 | -123 | 123 | 0 | 129 | 52 | 3677251 | 141565 | 3535686 | 4044013 | 3766516 | -317217 | 0 | -317217 | 3449299 | 3522837 | 99.64% | 1 | 192561 | 366762 | 107 | 22 | 0 | 0 | 59506 | 0 | 0 | 52 | 157769 | 111750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167254 | 6834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 384529 | 118583 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2023-11-17 | QTR2 | 23/24 | 796 | 3523200
| 07 | T7462 | 25716535201 | 2023-05-24 | QTR4 | 22/23 | 3 | 4 | 532 | 684 | 682 | 100% | 1 | 2 | 0 | 0 | 150 | 2 | 21597899 | 279988 | 21317911 | 21520785 | 21184572 | 0 | 0 | 0 | 21184572 | 21101702 | 98.99% | 1 | -1767 | -77114 | 109 | 41 | 0 | 0 | 29115 | 0 | 0 | 2 | 21294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -159215 | 0 | 0 | 2 | -70801 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-04-29 | QTR4 | 25/26 |  | 2025-08-13 | QTR1 | 25/26 | 798 | 20111600
| 07 | T7471 | 44138715201 | 2021-05-26 | QTR4 | 20/21 | 3 | 12 | 700 | 1190 | 1190 | 108.9% | 1 | 0 | 0 | 0 | 438 | 52 | 25596637 | 321434 | 25275203 | 26257328 | 26136613 | 0 | 0 | 0 | 26136613 | 26734266 | 105.8% | 1 | 642428 | 660691 | 335 | 93 | 0 | 21 | 508447 | 15927 | 0 | 19 | 699434 | 14637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 44775 | 37039 | 0 | 0 | 0 | 0 | 0 | 12 | 20008 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 52 | 1272665 | 67603 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-04-13 | QTR4 | 25/26 |  | 2025-02-26 | QTR3 | 24/25 | 796 | 27251800
| 07 | T7472 | 43182125201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 1200 | 1362 | 1223 | 90.42% | 1 | 139 | 0 | 0 | 138 | 24 | 85239705 | 150000 | 85089705 | 94443373 | 95456225 | 0 | 0 | 0 | 95456225 | 95322196 | 112% | 0 | 2218662 | 9203668 | 61 | 77 | 0 | 0 | 459126 | 0 | 0 | 21 | 3062413 | 383024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 5033268 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 177538 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1334779 | 0 | 0 | 93 | 8284381 | 1601156 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-02-28 | QTR3 | 24/25 | 714 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 07 | T7478 | 44024615201 | 2022-06-15 | QTR4 | 21/22 | 5 | 14 | 650 | 926 | 925 | 118.3% | 1 | 1 | 0 | 0 | 176 | 100 | 23033560 | 150000 | 22883560 | 24126786 | 23743700 | 0 | 0 | 0 | 23743700 | 23297352 | 101.8% | 1 | -443818 | 1093226 | 92 | 64 | 0 | 47 | 347814 | 0 | 0 | 49 | 97842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 4 | 18279 | 18279 | 0 | 0 | 0 | 0 | 0 | 0 | 2530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 100 | 466465 | 18279 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-05-19 | QTR4 | 25/26 |  | 2025-09-15 | QTR1 | 25/26 | 799 | 23181900
| 07 | T7493 | 44538015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 14 | 470 | 681 | 681 | 100% | 1 | 0 | 0 | 0 | 194 | 17 | 35735836 | 150000 | 35585836 | 37879264 | 40425341 | -36000 | 0 | -36000 | 40389341 | 39569176 | 111.2% | 0 | -376846 | 2143428 | 129 | 82 | 0 | 0 | 661576 | 3597 | 0 | 0 | 145477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 893056 | 733218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700108 | 736816 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-04-20 | QTR4 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 714 | 37724100
| 07 | T7505 | 44166115201 | 2023-05-24 | QTR4 | 22/23 | 2 | 6 | 450 | 530 | 530 | 100% | 1 | 0 | 0 | 0 | 80 | 0 | 13856415 | 100000 | 13756415 | 13819912 | 13656236 | 0 | 0 | 0 | 13656236 | 13594713 | 98.82% | 1 | -2106 | -36503 | 45 | 35 | 0 | 0 | 25728 | 22538 | 0 | 0 | -116398 | 38900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -90670 | 61438 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-15 | QTR3 | 25/26 |  | 2025-05-19 | QTR4 | 24/25 | 796 | 14165000
| 07 | T7507 | 44600915201 | 2023-05-17 | QTR4 | 22/23 | 2 | 4 | 700 | 758 | 563 | 67.14% | 1 | 195 | 0 | 0 | 93 | -35 | 22407724 | 150000 | 22257724 | 24195428 | 26279346 | 0 | -10000 | -10000 | 26269346 | 25478372 | 114.5% | 0 | -2078 | 1787704 | 50 | 43 | 0 | 0 | -250600 | 0 | 0 | 0 | 189104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21834 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2026-02-10 | QTR3 | 25/26 |  | 2025-06-06 | QTR4 | 24/25 | 714 | 23830100
| 07 | T7509 | 44588615201 | 2023-02-22 | QTR3 | 22/23 | 1 | 3 | 225 | 324 | 324 | 112.9% | 1 | 0 | 0 | 0 | 99 | 0 | 8085082 | 90000 | 7995082 | 8115381 | 7967342 | 0 | 0 | 0 | 7967342 | 7885022 | 98.62% | 1 | -54392 | 30299 | 59 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 4879 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2024-11-21 | QTR2 | 24/25 | 799 | 9550800
| 07 | T7511 | 44378415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 4 | 320 | 501 | 501 | 108.4% | 1 | 0 | 0 | 0 | 154 | 27 | 12651040 | 105000 | 12546040 | 13441313 | 13767680 | 0 | 0 | 0 | 13767680 | 13709361 | 109.3% | 1 | -2978 | 790273 | 123 | 31 | 0 | 0 | 718368 | 0 | 0 | 27 | 45653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 764021 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 798 | 12701400
| 07 | T7512 | 44334715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 3 | 210 | 477 | 477 | 112.9% | 1 | 0 | 0 | 0 | 230 | 37 | 6290573 | 50000 | 6240573 | 6754957 | 7072599 | 0 | 0 | 0 | 7072599 | 6755948 | 108.3% | 1 | -125 | 464384 | 209 | 31 | 0 | 20 | 65635 | 0 | 0 | 7 | 7306 | 0 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 157426 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 796 | 6135700
| 07 | T7513 | 44985215201 | 2023-11-15 | QTR2 | 23/24 | 1 | 2 | 130 | 190 | 190 | 100% | 1 | 0 | 0 | 0 | 60 | 0 | 2131372 | 50000 | 2081372 | 2126382 | 2055081 | 0 | 0 | 0 | 2055081 | 2042217 | 98.12% | 1 | -1708 | -4990 | 31 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16146 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-05-19 | QTR4 | 25/26 |  | 2025-03-07 | QTR3 | 24/25 | 796 | 1928410
| 07 | T7514 | 45069315201 | 2023-09-27 | QTR1 | 23/24 | 1 | 2 | 150 | 311 | 311 | 100% | 1 | 0 | 0 | 0 | 161 | 0 | 2469300 | 50000 | 2419300 | 2490043 | 2487609 | 0 | 0 | 0 | 2487609 | 2486604 | 102.8% | 1 | -1005 | 20743 | 111 | 50 | 0 | 0 | 31460 | 0 | 0 | 0 | 8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39921 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-04-03 | QTR4 | 24/25 | 796 | 2285000
| 07 | T7515 | 44803615201 | 2023-06-14 | QTR4 | 22/23 | 2 | 10 | 300 | 571 | 566 | 117.7% | 1 | 5 | 0 | 0 | 271 | 0 | 13134873 | 115000 | 13019873 | 13851674 | 14146391 | 0 | 0 | 0 | 14146391 | 14063633 | 108% | 1 | -40306 | 716801 | 160 | 53 | 9 | 0 | 197732 | 0 | 0 | 0 | 430314 | 44320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 640481 | 44320 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-03-11 | QTR3 | 25/26 |  | 2025-07-22 | QTR1 | 25/26 | 799 | 13139100
| 07 | T7516 | 44006315201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 230 | 430 | 430 | 108.3% | 1 | 0 | 0 | 0 | 181 | 19 | 6730280 | 60000 | 6670280 | 6779810 | 6697913 | 0 | 0 | 0 | 6697913 | 6687877 | 100.3% | 1 | -10036 | 49529 | 152 | 29 | 0 | 0 | 9983 | 0 | 0 | 19 | 66053 | 39546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 19 | 76037 | 39546 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2024-12-04 | QTR2 | 24/25 | 798 | 7050800
| 07 | T7522 | 44627015201 | 2024-06-12 | QTR4 | 23/24 | 2 | 2 | 310 | 404 | 397 | 106.8% | 1 | 7 | 0 | 0 | 94 | 0 | 8109258 | 115000 | 7994258 | 8171451 | 8246645 | 0 | 0 | 0 | 8246645 | 8245347 | 103.1% | 1 | -1298 | 62193 | 40 | 26 | 28 | 0 | 64340 | 0 | 0 | 0 | 47306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 111647 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-06-16 | QTR4 | 25/26 |  | 2026-02-06 | QTR3 | 25/26 | 796 | 11954146
| 07 | T7523 | 44697315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 196 | 316 | 315 | 99.49% | 1 | 1 | 0 | 0 | 120 | 0 | 2049777 | 50000 | 1999777 | 2049777 | 2101379 | 0 | 0 | 0 | 2101379 | 2098362 | 104.9% | 1 | -3017 | 0 | 95 | 25 | 0 | 0 | 2635 | 0 | 0 | 0 | 36652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39287 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 799 | 2385840
| 07 | T7524 | 44795215201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 250 | 308 | 308 | 111.6% | 1 | 0 | 0 | 0 | 29 | 29 | 5431188 | 58640 | 5372548 | 5431188 | 5567862 | 0 | 0 | 0 | 5567862 | 5571064 | 103.7% | 1 | 3202 | 0 | 5 | 24 | 0 | 29 | 30941 | 30941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 30941 | 30941 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-05-29 | QTR4 | 25/26 |  | 2026-03-10 | QTR3 | 25/26 | 798 | 6061975
| 07 | T7527 | 44363015201 | 2023-12-06 | QTR2 | 23/24 | 1 | 5 | 550 | 665 | 472 | 66.18% | 1 | 193 | 0 | 0 | 108 | 7 | 22643400 | 150000 | 22493400 | 24315347 | 26274401 | 0 | 0 | 0 | 26274401 | 25522977 | 113.5% | 0 | -1893 | 1671947 | 74 | 34 | 0 | 7 | 7300 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 16669 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2026-06-10 | QTR4 | 25/26 |  | 2025-10-08 | QTR2 | 25/26 | 714 | 25187500
| 07 | T7529 | 44109835201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 200 | 262 | 262 | 100% | 1 | 0 | 0 | 0 | 62 | 0 | 1336107 | 50000 | 1286107 | 1336107 | 1267198 | 0 | 0 | 0 | 1267198 | 1266909 | 98.51% | 1 | -289 | 0 | 41 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-05-28 | QTR4 | 24/25 | 796 | 1581132
| 07 | T7530 | 44753515201 | 2024-05-22 | QTR4 | 23/24 | 2 | 1 | 440 | 467 | 403 | 80.45% | 1 | 64 | 0 | 0 | 49 | -22 | 9184009 | 65000 | 9119009 | 9285334 | 9327564 | 0 | 0 | 0 | 9327564 | 9325285 | 102.3% | 1 | -2279 | 101325 | 19 | 30 | 0 | -22 | 118885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22 | 118885 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2026-05-27 | QTR4 | 25/26 |  | 2025-12-04 | QTR2 | 25/26 | 799 | 7458238
| 07 | T7536 | 44795415201 | 2024-11-13 | QTR2 | 24/25 | 1 | 1 | 175 | 197 | 197 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 5776172 | 75963 | 5700209 | 5745538 | 5802044 | 0 | 0 | 0 | 5802044 | 5802824 | 101.8% | 1 | 780 | -30634 | 5 | 17 | 0 | 0 | -30634 | 0 | 0 | 0 | 12774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17860 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-20 | QTR4 | 25/26 |  | 2026-01-26 | QTR3 | 25/26 | 798 | 7545892
| 07 | T7538 | 44939815201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 100 | 122 | 122 | 115% | 1 | 0 | 0 | 0 | 22 | 0 | 545691 | 22198 | 523493 | 545691 | 518518 | 0 | 0 | 0 | 518518 | 518518 | 99.05% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-08 | QTR4 | 24/25 | 799 | 611133
| 07 | T7539 | 45287715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 175 | 226 | 226 | 100% | 1 | 0 | 0 | 0 | 51 | 0 | 1109387 | 50000 | 1059387 | 1066722 | 1024280 | 0 | 0 | 0 | 1024280 | 1024198 | 96.68% | 1 | -82 | -42665 | 33 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42665 | 0 | 0 | 0 | -42665 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2025-05-14 | QTR4 | 24/25 | 796 | 1253844
| 07 | T7543 | 44795315201 | 2025-02-26 | QTR3 | 24/25 | 1 | 2 | 200 | 224 | 221 | 93.5% | 1 | 3 | 0 | 0 | 34 | -10 | 6298614 | 102500 | 6196114 | 6383875 | 6186613 | 0 | 0 | 0 | 6186613 | 6186612 | 99.85% | 1 | 0 | 85262 | 15 | 19 | 0 | 0 | -28859 | 0 | 0 | 0 | 29617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 758 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2026-01-29 | QTR3 | 25/26 | 798 | 9649905
| 07 | T7544 | 44025015201 | 2024-04-17 | QTR4 | 23/24 | 1 | 2 | 240 | 275 | 259 | 93.33% | 1 | 16 | 0 | 0 | 35 | 0 | 7475300 | 55000 | 7420300 | 7428809 | 7644411 | 0 | 0 | 0 | 7644411 | 7629621 | 102.8% | 1 | -14790 | -46492 | 13 | 22 | 0 | 0 | 569898 | 120795 | 0 | 0 | -594629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24731 | 120795 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2025-07-14 | QTR1 | 25/26 | 798 | 8386992
| 07 | T7548 | 44752215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 4 | 140 | 214 | 213 | 140% | 0 | 1 | 0 | 0 | 17 | 57 | 2173906 | 50000 | 2123906 | 2247825 | 2217265 | 0 | 0 | 0 | 2217265 | 2216464 | 104.4% | 1 | -801 | 73919 | 13 | 4 | 0 | 36 | 77735 | 0 | 0 | 21 | 8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15816 | 15816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 101654 | 15816 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2026-02-06 | QTR3 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 798 | 1912820
| 07 | T7550 | 45241215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 97 | 113 | 113 | 110.3% | 1 | 0 | 0 | 0 | 16 | 0 | 654321 | 27192 | 627129 | 654321 | 610593 | 0 | 0 | 0 | 610593 | 610593 | 97.36% | 1 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-05 | QTR2 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 796 | 826944
| 07 | T7555 | 44794815201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 205 | 224 | 157 | 67.32% | 1 | 67 | 0 | 0 | 19 | 0 | 5942087 | 79500 | 5862587 | 5942922 | 5968673 | 0 | 0 | 0 | 5968673 | 5968280 | 101.8% | 1 | -393 | 835 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-10-22 | QTR2 | 25/26 | 798 | 7672150
| 07 | T7570 | 45097015201 | 2025-03-26 | QTR3 | 24/25 | 1 | 0 | 90 | 120 | 137 | 118.9% | 1 | -17 | 17 | 0 | 30 | 0 | 643597 | 36000 | 607597 | 643597 | 574357 | -28645 | 0 | -28645 | 545712 | 545712 | 89.81% | 1 | 0 | 0 | 16 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2026-06-03 | QTR4 | 25/26 |  | 2026-01-25 | QTR3 | 25/26 | 798 | 761694
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 35 | 61 | 192 | 14805 | 20096 | 21194 | 82.86% | 29 | -1098 | 1792 | 0 | 4146 | 1145 | 562969180 | 4696678 | 558272503 | 588435660 | 596478546 | -4594080 | 865160 | -3728920 | 592749627 | 593014378 | 85.71% | 30 | 6264582 | 25466477 | 2671 | 1332 | 37 | 401 | 8429759 | 598610 | 15 | 419 | 6757189 | 875873 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 72 | 5315806 | 729339 | 10 | 4 | 1894247 | 1119509 | 0 | 0 | 0 | 0 | 106 | 0 | 920380 | 227859 | 0 | 0 | 0 | 0 | 49 | 22 | 20008 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | -2014864 | 0 | 276 | 938 | 21404752 | 3551190
| 07 | E7J46 | 43388015201 | 2017-05-25 | QTR4 | 16/17 | 5 | 45 | 1300 | 2870 | 2871 | 167% | 0 | -1 | 1 | 0 | 686 | 884 | 544690000 | 302200 | 544387800 | 602680022 | 604391547 | -158000 | 2780000 | 2622000 | 607013547 | 607454208 | 111.6% | 0 | 21389007 | 57990022 | 486 | 214 | 0 | 834 | 49299395 | 50147 | 0 | 0 | 598984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 3959563 | 0 | 0 | 0 | 923053 | 893656 | 0 | 0 | 0 | 0 | 0 | 28 | 1020021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -781340 | 0 | 0 | 898 | 55019676 | 943803 | F352566788 | ARCHER WESTERN-DEMOYA JOINT VEN | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 714 | 544690000 | B10:B8:B8 | ACC - BONUS/INCENT/DISINCENT:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 07 | E7N56 | 43726425201 | 2022-05-27 | QTR4 | 21/22 | 1 | 8 | 650 | 716 | 649 | 89.69% | 1 | 67 | 0 | 0 | 66 | 0 | 19975000 | 130000 | 19845000 | 20432970 | 21351585 | 0 | 0 | 0 | 21351585 | 21249872 | 107.1% | 1 | -59788 | 457970 | 29 | 37 | 0 | 0 | 362725 | 71071 | 0 | 0 | 34483 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125141 | 125141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586579 | 198586 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-01-20 | QTR3 | 25/26 |  | 2024-06-21 | QTR4 | 23/24 | 798 | 15858300
| 07 | E7P28 | 44797625201 | 2022-05-11 | QTR4 | 21/22 | 2 | 1 | 150 | 208 | 208 | 119.3% | 1 | 0 | 0 | 0 | 29 | 29 | 5133790 | 52155 | 5081635 | 5136444 | 5160545 | 0 | 0 | 0 | 5160545 | 5116597 | 100.7% | 1 | -43948 | 2654 | 22 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 11859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 11859 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2023-08-04 | QTR1 | 23/24 | 714 | 3774700
| 07 | E7P68 | 41673325201 | 2022-12-14 | QTR2 | 22/23 | 1 | 8 | 550 | 918 | 918 | 119.5% | 1 | 0 | 0 | 0 | 368 | 0 | 15756084 | 100000 | 15656084 | 16054430 | 16104094 | 0 | 0 | 0 | 16104094 | 15995436 | 102.2% | 1 | -74559 | 298346 | 220 | 41 | 5 | 0 | 224536 | 0 | 102 | 0 | 28230 | 21610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51528 | 0 | 0 | 0 | 8029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 331684 | 21610 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2026-06-16 | QTR4 | 25/26 |  | 2025-10-06 | QTR2 | 25/26 | 798 | 12965300
| 07 | E7P77 | 44146315201 | 2023-05-10 | QTR4 | 22/23 | 1 | 2 | 150 | 247 | 247 | 118% | 1 | 0 | 0 | 0 | 70 | 27 | 3366760 | 50000 | 3316760 | 3493112 | 3363518 | 0 | 300000 | 300000 | 3663518 | 3363518 | 101.4% | 1 | -300000 | 126352 | 45 | 25 | 0 | 22 | 20037 | 0 | 0 | 5 | 4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 135426 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-07-30 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 796 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | E7Q08 | 44761515201 | 2023-05-10 | QTR4 | 22/23 | 2 | 7 | 330 | 477 | 477 | 118.8% | 1 | 0 | 0 | 0 | 147 | 0 | 6147921 | 52728 | 6095192 | 6373747 | 6357061 | 0 | 0 | 0 | 6357061 | 6311539 | 103.5% | 1 | -1706 | 225826 | 61 | 24 | 0 | 0 | -18522 | 0 | 0 | 0 | 84658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84397 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 42409 | 34565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 192942 | 34565 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2026-01-20 | QTR3 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 714 | 5831100
| 07 | E7Q30 | 44380515201 | 2024-03-13 | QTR3 | 23/24 | 1 | 2 | 250 | 424 | 424 | 118.8% | 1 | 0 | 0 | 0 | 174 | 0 | 7234098 | 74000 | 7160098 | 6536418 | 6778566 | 0 | 0 | 0 | 6778566 | 6763361 | 94.46% | 1 | -15205 | -697680 | 96 | 31 | 0 | 0 | -652638 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | -652638 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2026-02-20 | QTR3 | 25/26 |  | 2025-10-03 | QTR2 | 25/26 | 798 | 7788450
| 07 | E7Q31 | 44384115201 | 2023-12-13 | QTR2 | 23/24 | 1 | 3 | 125 | 238 | 240 | 101.6% | 1 | -2 | 2 | 0 | 113 | 0 | 1681476 | 50000 | 1631476 | 1805476 | 1410753 | -3398 | 0 | -3398 | 1407355 | 1374355 | 84.24% | 1 | 0 | 124000 | 98 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2024-12-10 | QTR2 | 24/25 | 796 | 1673100
| 07 | E7Q32 | 44383715201 | 2025-05-14 | QTR4 | 24/25 | 1 | 0 | 120 | 159 | 159 | 112.5% | 1 | 0 | 0 | 0 | 24 | 15 | 1728143 | 50000 | 1678143 | 1728143 | 1516260 | 0 | 0 | 0 | 1516260 | 1516260 | 90.35% | 1 | 0 | 0 | 8 | 16 | 0 | 0 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4250 | 0 | F830512074 | TITAN CONSTRUCTION MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2026-06-16 | QTR4 | 25/26 |  | 2026-03-13 | QTR3 | 25/26 | 798 | 1889730
| 07 | E7Q39 | 44582815201 | 2024-02-14 | QTR3 | 23/24 | 2 | 0 | 284 | 330 | 326 | 98.59% | 1 | 4 | 0 | 0 | 46 | 0 | 1714027 | 50000 | 1664027 | 1714027 | 1704720 | 0 | 0 | 0 | 1704720 | 1704720 | 102.4% | 1 | 0 | 0 | 20 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-08-26 | QTR1 | 25/26 | 796 | 3483914
| 07 | E7Q53 | 44583015201 | 2024-05-08 | QTR4 | 23/24 | 1 | 2 | 230 | 260 | 210 | 78.26% | 1 | 50 | 0 | 0 | 30 | 0 | 1599000 | 50000 | 1549000 | 1601196 | 1343560 | 0 | 0 | 0 | 1343560 | 1341365 | 86.6% | 1 | 0 | 2196 | 17 | 13 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-07-08 | QTR1 | 25/26 |  | 2025-04-13 | QTR4 | 24/25 | 799 | 1936163
| 07 | E7Q55 | 44165115201 | 2024-03-13 | QTR3 | 23/24 | 1 | 3 | 150 | 272 | 272 | 119.3% | 1 | 0 | 0 | 0 | 93 | 29 | 4066019 | 50000 | 4016019 | 4201769 | 4164473 | 0 | 0 | 0 | 4164473 | 4071753 | 101.4% | 1 | -92719 | 135750 | 67 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 95050 | 87989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 6641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 29 | 149452 | 87989 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-06-01 | QTR4 | 24/25 | 799 | 4234476
| 07 | E7Q75 | 45288915201 | 2024-06-12 | QTR4 | 23/24 | 1 | 2 | 80 | 151 | 151 | 100% | 1 | 0 | 0 | 0 | 71 | 0 | 1296714 | 50000 | 1246714 | 1381899 | 1384246 | 0 | 0 | 0 | 1384246 | 1371017 | 110% | 1 | 0 | 85185 | 50 | 21 | 0 | 0 | 71957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71957 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-01-27 | QTR3 | 24/25 | 798 | 1695805
| 07 | E7Q85 | 44349225201 | 2025-01-08 | QTR3 | 24/25 | 1 | 0 | 180 | 203 | 178 | 86.11% | 1 | 25 | 0 | 0 | 23 | 0 | 576543 | 25000 | 551543 | 576543 | 519908 | 0 | 0 | 0 | 519908 | 519908 | 94.26% | 1 | 0 | 0 | 11 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-05-08 | QTR4 | 25/26 |  | 2025-12-11 | QTR2 | 25/26 | 796 | 536030
| 07 | E7Q94 | 45273615201 | 2024-12-11 | QTR2 | 24/25 | 1 | 0 | 30 | 33 | 29 | 86.67% | 1 | 4 | 0 | 0 | 3 | 0 | 259111 | 23000 | 236111 | 259111 | 235124 | 0 | 0 | 0 | 235124 | 235124 | 99.58% | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 |  | 2025-07-14 | QTR1 | 25/26 | 799 | 516283
| 07 | E7R15 | 44138815201 | 2021-01-29 | QTR3 | 20/21 | 4 | 2 | 450 | 724 | 724 | 100% | 1 | 0 | 0 | 0 | 274 | 0 | 21358193 | 150000 | 21208193 | 21288752 | 21103200 | 0 | 1150000 | 1150000 | 22253200 | 21628021 | 102% | 1 | -335192 | -69440 | 226 | 48 | 0 | 0 | 12752 | 0 | 0 | 0 | 107114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -69440 | 0 | 185 | 0 | 50426 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-12-11 | QTR2 | 25/26 |  | 2023-07-28 | QTR1 | 23/24 | 796 | 26431774 | A3:A3:A3:B10 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
| 07 | E7R21 | 42451335201 | 2021-05-20 | QTR4 | 20/21 | 3 | 16 | 1115 | 1618 | 1308 | 100.6% | 1 | 310 | 0 | 0 | 186 | 317 | 81649200 | 150000 | 81499200 | 89787672 | 90056090 | 0 | 0 | 0 | 90056090 | 89818079 | 110.2% | 0 | 1620860 | 8138472 | 122 | 64 | 0 | 228 | 2666076 | 316345 | 0 | 0 | 1680130 | 35860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316666 | 208207 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 0 | -117901 | 0 | 0 | 373 | 4996124 | 1011566 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-08 | QTR3 | 24/25 | 714 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7R22 | 44344535201 | 2022-05-27 | QTR4 | 21/22 | 6 | 2 | 640 | 1164 | 1164 | 131.7% | 0 | 0 | 0 | 0 | 184 | 340 | 29193066 | 150000 | 29043066 | 28668231 | 28534082 | 0 | 0 | 0 | 28534082 | 28522241 | 98.21% | 1 | 0 | -524835 | 243 | 78 | 0 | 118 | -536676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340 | -536676 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2026-05-08 | QTR4 | 25/26 |  | 2025-10-03 | QTR2 | 25/26 | 714 | 22376200
| 07 | E7R24 | 44132015201 | 2022-08-04 | QTR1 | 22/23 | 1 | 1 | 580 | 797 | 779 | 96.9% | 1 | 18 | 0 | 0 | 217 | 0 | 6997500 | 69934 | 6927567 | 7112720 | 7042786 | 0 | 0 | 0 | 7042786 | 7042581 | 101.7% | 1 | -205 | 115220 | 163 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2025-03-28 | QTR3 | 24/25 | 798 | 13119000
| 07 | E7R26 | 42925115201 | 2021-06-17 | QTR4 | 20/21 | 5 | 22 | 1100 | 1415 | 1414 | 112.5% | 1 | 1 | 0 | 0 | 176 | 139 | 89691574 | 162717 | 89528857 | 96531643 | 96716929 | -45000 | 0 | -45000 | 96671929 | 96896327 | 108.2% | 1 | 1490307 | 6840069 | 90 | 86 | 0 | 119 | 5277897 | 81590 | 0 | 20 | 1067716 | 347957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49676 | 0 | 0 | 0 | 8310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 6553399 | 429547 | F871503473 | PRINCE-AJAX DDI JV | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 |  | 2025-07-02 | QTR1 | 25/26 | 714 | 100030998 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7R35 | 43983215201 | 2023-05-25 | QTR4 | 22/23 | 3 | 4 | 580 | 697 | 697 | 100% | 1 | 0 | 0 | 0 | 117 | 0 | 10158800 | 110000 | 10048800 | 10244736 | 10281972 | 0 | 0 | 0 | 10281972 | 10243690 | 101.9% | 1 | -3637 | 85936 | 86 | 31 | 0 | 0 | 51291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51291 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-01-22 | QTR3 | 25/26 |  | 2025-06-23 | QTR4 | 24/25 | 798 | 12981331 | LBDB:LBDB | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
| 07 | E7R40 | 44335825201 | 2024-03-07 | QTR3 | 23/24 | 1 | 2 | 200 | 285 | 274 | 94.5% | 1 | 11 | 0 | 0 | 85 | 0 | 1322000 | 50000 | 1272000 | 1334250 | 1257998 | 0 | 0 | 0 | 1257998 | 1250561 | 98.31% | 1 | -4137 | 12250 | 46 | 39 | 0 | 0 | 4515 | 0 | 0 | 0 | 4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2025-02-03 | QTR3 | 24/25 | 798 | 1543770 | LBDB | LOW BID DESIGN BUILD
| 07 | E7U08 | 44366515201 | 2024-09-11 | QTR1 | 24/25 | 1 | 1 | 200 | 251 | 251 | 109% | 1 | 0 | 0 | 0 | 33 | 18 | 3709156 | 50000 | 3659156 | 3709156 | 3454248 | 0 | 0 | 0 | 3454248 | 3454248 | 94.4% | 1 | 0 | 0 | 19 | 14 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2025-12-10 | QTR2 | 25/26 | 796 | 3944855
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 23 | 46 | 133 | 9444 | 14457 | 13970 | 91.3% | 21 | 487 | 3 | 0 | 3215 | 1798 | 859304175 | 2001734 | 857302441 | 932652467 | 934233265 | -206398 | 4230000 | 4023602 | 938256867 | 937244781 | 91.3% | 21 | 23569078 | 73348293 | 2226 | 924 | 5 | 1321 | 56788111 | 519153 | 149 | 43 | 3923388 | 495791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 4303804 | 0 | 4 | 0 | 939392 | 893656 | 0 | 0 | 0 | 0 | 204 | 165 | 1570079 | 208207 | 0 | 0 | 0 | 0 | 58 | 203 | 625345 | 610860 | 0 | 0 | 0 | 0 | 0 | 0 | -968681 | 0 | 420 | 1868 | 67181437 | 2727666
| District 07 Totals |  |  |  |  | 58 | 107 | 325 | 24249 | 34553 | 35164 | 86.21% | 50 | -611 | 1795 | 0 | 7361 | 2943 | 1422273355 | 6698412 | 1415574944 | 1521088127 | 1530711811 | -4800478 | 5095160 | 294682 | 1531006494 | 1530259159 | 87.93% | 51 | 29833660 | 98814770 | 4897 | 2256 | 42 | 1722 | 65217870 | 1117763 | 164 | 462 | 10680577 | 1371664 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 208 | 9619610 | 729339 | 14 | 4 | 2833639 | 2013165 | 0 | 0 | 0 | 0 | 310 | 165 | 2490459 | 436066 | 0 | 0 | 0 | 0 | 107 | 225 | 645353 | 610860 | 10 | 20 | 0 | 0 | 0 | 0 | -2983545 | 0 | 696 | 2806 | 88586189 | 6278856
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8R45 | 43799215201 | 2018-11-15 | QTR2 | 18/19 | 3 | 22 | 928 | 1578 | 1578 | 115.6% | 1 | 0 | 0 | 0 | 505 | 145 | 33928239 | 150000 | 33778239 | 47651600 | 47943952 | 0 | 0 | 0 | 47943952 | 47859737 | 141.7% | 0 | -39220 | 13723361 | 337 | 168 | 0 | 4 | 678065 | 0 | 0 | 0 | 444720 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 11027592 | 0 | 0 | 0 | 1427834 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 145 | 13655217 | 0 | F825435435 | CENTRAL MORRISON COBALT JV | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2023-10-20 | QTR2 | 23/24 | 854 | 41184698.49
| 08 | E8S51 | 44085715201 | 2020-12-15 | QTR2 | 20/21 | 1 | 16 | 1086 | 1494 | 1494 | 114% | 1 | 0 | 0 | 0 | 256 | 152 | 31637485 | 150000 | 31487485 | 32856515 | 33411965 | -26500 | 0 | -26500 | 33385465 | 33453512 | 106.2% | 1 | 3631867 | 1219030 | 141 | 115 | 0 | 34 | 304333 | 0 | 0 | 28 | 445859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2360 | 0 | 0 | 0 | 172460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | -395237 | 0 | 0 | 152 | 574799 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2025-07-09 | QTR1 | 25/26 | 854 | 32721168.86
| 08 | E8T48 | 43496835201 | 2022-04-19 | QTR4 | 21/22 | 1 | 2 | 1128 | 1286 | 1283 | 102.7% | 1 | 3 | 0 | 0 | 125 | 33 | 10781928 | 108430 | 10673498 | 10718856 | 10512572 | 0 | 0 | 0 | 10512572 | 10512572 | 98.49% | 1 | 0 | -63072 | 40 | 85 | 0 | 33 | -9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28279 | 0 | 0 | 0 | 8634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 27804 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 |  | 2025-12-18 | QTR2 | 25/26 | 854 | 11904888.56 | A3 | ICC - DESIGN/BUILD - MINOR
| 08 | E8T83 | 44276415201 | 2022-09-20 | QTR1 | 22/23 | 1 | 4 | 1277 | 1339 | 892 | 59.83% | 1 | 447 | 0 | 0 | 128 | -66 | 102999958 | 150000 | 102849958 | 103423210 | 104129622 | 0 | 4744548 | 4744548 | 108874170 | 102351127 | 99.51% | 1 | -6249791 | 423252 | 65 | 63 | 0 | 0 | 108966 | 0 | 0 | 0 | 78741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37076 | 0 | 0 | 0 | 2530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66 | 0 | 0 | 0 | -66 | 227314 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-03-27 | QTR3 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 854 | 121233962.23 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8U04 | 44602415201 | 2023-03-21 | QTR3 | 22/23 | 3 | 8 | 386 | 505 | 502 | 104.4% | 1 | 3 | 0 | 0 | 99 | 20 | 16184460 | 150000 | 16034460 | 17190583 | 16458548 | 0 | 0 | 0 | 16458548 | 16378636 | 102.1% | 1 | -46667 | 1006123 | 45 | 54 | 0 | 0 | 188590 | 0 | 0 | 0 | 366919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 463107 | 0 | 0 | 0 | 50339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1068954 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 854 | 18390076.74
| 08 | E8U19 | 44588515201 | 2023-04-11 | QTR4 | 22/23 | 2 | 1 | 314 | 523 | 523 | 109.6% | 1 | 0 | 0 | 0 | 179 | 30 | 11226810 | 114237 | 11112574 | 11263007 | 11344464 | 0 | 0 | 0 | 11344464 | 11303165 | 101.7% | 1 | -5101 | 36197 | 122 | 57 | 0 | 0 | 0 | 0 | 0 | 14 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 53038 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-28 | QTR1 | 25/26 |  | 2025-04-11 | QTR4 | 24/25 | 854 | 11461890.59
| 08 | E8U32 | 44925335201 | 2023-05-09 | QTR4 | 22/23 | 2 | 1 | 401 | 505 | 499 | 109.7% | 1 | 6 | 0 | 0 | 104 | 0 | 3649071 | 50000 | 3599071 | 3673424 | 3464348 | 0 | 0 | 0 | 3464348 | 3464348 | 96.26% | 1 | 0 | 24353 | 27 | 32 | 0 | 0 | 7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 11812 | 0 | 0 | 0 | 24353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 43886 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 854 | 4370418.34
| 08 | E8U46 | 43854815201 | 2024-05-14 | QTR4 | 23/24 | 1 | 0 | 497 | 543 | 254 | 41.85% | 1 | 289 | 0 | 0 | 46 | 0 | 4734726 | 79759 | 4654966 | 4734726 | 4628034 | 0 | 0 | 0 | 4628034 | 4628034 | 99.42% | 1 | 0 | 0 | 13 | 33 | 0 | 0 | 14990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 854 | 8236620.28
| 08 | E8U56 | 44942325201 | 2023-08-22 | QTR1 | 23/24 | 1 | 2 | 240 | 275 | 242 | 81.25% | 1 | 33 | 0 | 0 | 47 | -12 | 1804313 | 50000 | 1754313 | 1864511 | 1827419 | 0 | 37398 | 37398 | 1864817 | 1827419 | 104.2% | 1 | -37398 | 60198 | 24 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-24 | QTR3 | 24/25 | 854 | 1786238.37 | A6 | ICC - BAM/INCENTIVE-DISINCENT
| 08 | E8U67 | 44440215201 | 2023-09-12 | QTR1 | 23/24 | 4 | 7 | 580 | 715 | 656 | 91.21% | 1 | 59 | 0 | 0 | 127 | 8 | 24889345 | 150000 | 24739345 | 25770345 | 25416917 | 0 | 0 | 0 | 25416917 | 25256822 | 102.1% | 1 | -129095 | 881000 | 76 | 51 | 0 | 0 | 57314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 471317 | 0 | 0 | 0 | 439504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 968135 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-16 | QTR3 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 854 | 27205817.87
| 08 | E8U70 | 44287615201 | 2024-04-09 | QTR4 | 23/24 | 1 | 4 | 661 | 717 | 529 | 68.38% | 1 | 188 | 0 | 0 | 77 | -21 | 19498886 | 150000 | 19348886 | 19784427 | 18004526 | 0 | 0 | 0 | 18004526 | 18003824 | 93.05% | 1 | -702 | 285541 | 38 | 39 | 0 | 0 | 105962 | 0 | 0 | 7 | 57145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 340506 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2026-05-18 | QTR4 | 25/26 |  | 2026-03-19 | QTR3 | 25/26 | 854 | 20898608.47
| 08 | E8U71 | 41592755201 | 2024-02-13 | QTR3 | 23/24 | 1 | 1 | 181 | 339 | 326 | 106.6% | 1 | 13 | 0 | 0 | 133 | 25 | 2794276 | 60345 | 2733930 | 2537251 | 2444066 | 0 | 0 | 0 | 2444066 | 2444066 | 89.4% | 1 | 0 | -257025 | 84 | 49 | 0 | 25 | 59995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -257025 | 0 | 0 | 25 | -197030 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-10-13 | QTR2 | 25/26 |  | 2025-09-17 | QTR1 | 25/26 | 854 | 6003501.55
| 08 | E8U73 | 44206215201 | 2024-03-12 | QTR3 | 23/24 | 2 | 5 | 280 | 321 | 315 | 97.86% | 1 | 6 | 0 | 0 | 41 | 0 | 13684469 | 150000 | 13534469 | 13793245 | 13317036 | 0 | 0 | 0 | 13317036 | 13288255 | 98.18% | 1 | -24020 | 108776 | 20 | 21 | 0 | 0 | 15607 | 0 | 0 | 0 | 43669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36331 | 0 | 0 | 0 | 131202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226808 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-07-18 | QTR1 | 25/26 | 854 | 19932483.01
| 08 | E8U75 | 41713255201 | 2024-06-11 | QTR4 | 23/24 | 2 | 4 | 691 | 833 | 528 | 61.65% | 1 | 305 | 0 | 0 | 149 | -7 | 30846591 | 150000 | 30696591 | 31566656 | 33098541 | 0 | 1149704 | 1149704 | 34248245 | 33093920 | 107.8% | 1 | -1154325 | 720066 | 64 | 38 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 650343 | 0 | 0 | 0 | 2568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 30 | 652911 | 0 | F811876890 | CONTINENTAL HEAVY CIVIL CORP. | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2026-03-24 | QTR3 | 25/26 | 854 | 46198157.71 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8U91 | 44917545201 | 2024-06-11 | QTR4 | 23/24 | 1 | 4 | 242 | 308 | 302 | 97.52% | 1 | 6 | 0 | 0 | 66 | 0 | 4804962 | 50000 | 4754962 | 4908714 | 4813444 | 0 | 0 | 0 | 4813444 | 4807156 | 101.1% | 1 | -521 | 103751 | 36 | 30 | 0 | 0 | 46708 | 0 | 0 | 0 | 21070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791 | 0 | 0 | 0 | 55206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123774 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-07-21 | QTR1 | 25/26 | 854 | 4334607.7
| 08 | E8U95 | 44917535201 | 2024-04-09 | QTR4 | 23/24 | 1 | 0 | 140 | 176 | 173 | 97.86% | 1 | 3 | 0 | 0 | 36 | 0 | 1605678 | 50000 | 1555678 | 1605678 | 1663792 | 0 | 0 | 0 | 1663792 | 1663792 | 106.9% | 1 | 0 | 0 | 18 | 18 | 0 | 0 | 23069 | 0 | 0 | 0 | 5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49911 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 854 | 1739459.6
| 08 | E8V77 | 45211115201 | 2025-02-19 | QTR3 | 24/25 | 1 | 0 | 200 | 207 | 108 | 50.5% | 1 | 99 | 0 | 0 | 7 | 0 | 1699787 | 50000 | 1649787 | 1699787 | 1444210 | 0 | 0 | 0 | 1444210 | 1444159 | 87.54% | 1 | -52 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 854 | 1780237.34
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 17 | 28 | 81 | 9232 | 11664 | 10204 | #VALUE! | 17 | 1460 | 0 | 0 | 2125 | 307 | 316770984 | 1812771 | 314958212 | 335042535 | 333923456 | -26500 | 5931650 | 5905150 | 339828606 | 331780544 | 94.12% | 16 | -4055025 | 18271551 | 1153 | 880 | 47 | 96 | 1602211 | 0 | 0 | 49 | 1585266 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 214 | 12950195 | 0 | 0 | 0 | 2315201 | 0 | 0 | 0 | 0 | 0 | 92 | 8 | 133562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | -66 | -652262 | 0 | 184 | 391 | 17935662 | 0
| District 08 Totals |  |  |  |  | 17 | 28 | 81 | 9232 | 11664 | 10204 | 100% | 17 | 1460 | 0 | 0 | 2125 | 307 | 316770984 | 1812771 | 314958212 | 335042535 | 333923456 | -26500 | 5931650 | 5905150 | 339828606 | 331780544 | 94.12% | 16 | -4055025 | 18271551 | 1153 | 880 | 47 | 96 | 1602211 | 0 | 0 | 49 | 1585266 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 214 | 12950195 | 0 | 0 | 0 | 2315201 | 0 | 0 | 0 | 0 | 0 | 92 | 8 | 133562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | -66 | -652262 | 0 | 184 | 391 | 17935662 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 243 | 518 | 861 | 80469 | 126176 | 124612 | 74.49% | 181 | 1564 | 2389 | 0 | 34738 | 10917 | 2350655853 | 20729040 | 2329926811 | 2481610932 | 2510266885 | -6689545 | 5379837 | -1309708 | 2508957178 | 2508418947 | 89.3% | 217 | 14988729 | 132045535 | 20227 | 10967 | 1719 | 3786 | 35120230 | 3867669 | 1667 | 3308 | 64334564 | 13760627 | 0 | 120 | 375548 | 66051 | 0 | 0 | -145423 | 0 | 0 | 0 | 5750 | 0 | 348 | 1254 | 18813382 | 4059468 | 337 | 204 | 2942308 | 1191046 | 0 | 0 | 0 | 0 | 1843 | 726 | 4622265 | 231037 | 0 | 286 | 2254885 | 620012 | 206 | 458 | 2357471 | 1394067 | 164 | 168 | 0 | 0 | 0 | 0 | -4341447 | 0 | 6284 | 10310 | 126339531 | 25189976
| Statewide District Let Contracts SubTotal |  |  |  |  | 188 | 314 | 632 | 63253 | 93479 | 89068 | 84.57% | 159 | 4411 | 344 | 0 | 23574 | 6685 | 2707690759 | 13795769 | 2693894990 | 2880901437 | 2881385271 | -1283090 | 14824150 | 13541060 | 2894926330 | 2874702507 | 93.62% | 176 | 34080448 | 173318549 | 12474 | 8261 | 544 | 2572 | 71388762 | 2228277 | 816 | 1288 | 21249382 | 766858 | 0 | 0 | 10318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1209 | 1627 | 58798776 | 3681205 | 19 | 45 | 7051315 | 969408 | 0 | 0 | 0 | 0 | 1061 | 587 | 3182827 | 208207 | 0 | 484 | 8224579 | 7351000 | 224 | 243 | 758485 | 723474 | 41 | 120 | 0 | 0 | 0 | -66 | -3810232 | 0 | 3914 | 6900 | 166854199 | 15928427
| Statewide Totals |  |  |  |  | 431 | 832 | 1493 | 143722 | 219655 | 213680 | 78.89% | 340 | 5975 | 2733 | 0 | 58312 | 17602 | 5058346612 | 34524809 | 5023821801 | 5362512369 | 5391652156 | -7972635 | 20203987 | 12231352 | 5403883508 | 5383121454 | 91.18% | 393 | 49069177 | 305364084 | 32701 | 19228 | 2263 | 6358 | 106508992 | 6095946 | 2483 | 4596 | 85583946 | 14527485 | 0 | 120 | 385866 | 66051 | 0 | 0 | -145423 | 0 | 0 | 0 | 5750 | 0 | 1557 | 2881 | 77612158 | 7740673 | 356 | 249 | 9993623 | 2160454 | 0 | 0 | 0 | 0 | 2904 | 1313 | 7805092 | 439244 | 0 | 770 | 10479464 | 7971012 | 430 | 701 | 3115956 | 2117541 | 205 | 288 | 0 | 0 | 0 | -66 | -8151679 | 0 | 10198 | 17210 | 293193730 | 41118403

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1R76 | 20121535201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2020-05-29 | 70460520 | 71635236 | 73663828 | 1174716.35 | -100000 | 77151838 | 0 | 0 | 0 | 0 | 0 | -100000 | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 73563828 | 77151838 | 3588010 | 57230748 | Y | DESIGN/BUILD PROJECT
1 | E1R87 | 20103255201 | F843374080 | AJAX-LEWARE JV | N/A | N/A | N/A | N/A | 2020-11-20 | 143923300 | 144607218 | 155372227 | 683918.32 | -40000 | 157627376 | 0 | 0 | 0 | 0 | 0 | -40000 | -40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40000 | 155332227 | 157627376 | 2295149 | 132713200 | B11:B7:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - A+B/BONUS:ACC - DESIGN/BUILD - MAJOR
1 | E1U56 | 44400825201 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2022-02-17 | 40877774 | 43600530 | 44711094 | 2722756.25 | 0 | 45895651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44711094 | 45895651 | 1184557 | 46748208
1 | E1V05 | 44400835201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-07-21 | 22180000 | 22731000 | 22373423 | 551000.43 | 0 | 21651639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22373423 | 21651639 | -721784 | 27316502
1 | E1V08 | 19602265201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-11-02 | 6226258 | 6296806 | 6274547 | 70547.94 | 0 | 6264042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6274547 | 6264042 | -10506 | 7418504
1 | E1V09 | 44743215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-02-15 | 3665572 | 3665572 | 3704260 | 0 | 0 | 3693129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3704260 | 3693129 | -11132 | 4198566
1 | E1V10 | 44155015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-02-16 | 14609258 | 14044029 | 14088333 | -565228.69 | -3245 | 13959008 | -3245 | 0 | 0 | 0 | 0 | 0 | -3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3245 | 14085087 | 13959008 | -126080 | 14926350
1 | E1V12 | 43488625201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-18 | 18975000 | 19595912 | 19771279 | 620912.39 | 0 | 19769526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19771279 | 19769526 | -1753 | 18481181
1 | E1V13 | 44893915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-09-19 | 5289078 | 5392842 | 5545592 | 103763.45 | 0 | 5545735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5545592 | 5545735 | 143 | 5760652
1 | E1V22 | 44620615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-20 | 5142423 | 5047658 | 5138834 | -94764.75 | 0 | 5137805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5138834 | 5137805 | -1029 | 4496918
1 | E1V23 | 44743415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-07-20 | 5558710 | 5552034 | 5723019 | -6675.84 | 0 | 5741811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5723019 | 5741811 | 18793 | 5765208
1 | E1V51 | 44743715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-02 | 23141400 | 23931467 | 24545579 | 790066.61 | 0 | 24064967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24545579 | 24064967 | -480611 | 26691037 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
1 | E1V60 | 44901515201 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 24655000 | 24840707 | 24676932 | 185707.07 | 941500 | 24668159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | -8500 | 941500 | 941500 | 25618432 | 24668159 | -950274 | 27242570 | B2:B5:Y | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:DESIGN/BUILD PROJECT
1 | E1W11 | 45088215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-10-16 | 1286987 | 1286987 | 1219611 | 0 | 0 | 1224641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1219611 | 1224641 | 5030 | 1583531
1 | E1W13 | 44594215201 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2024-02-15 | 2428636 | 2626766 | 2708707 | 198129.96 | -66250 | 2642436 | -66250 | 0 | 0 | 0 | 0 | 0 | -66250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66250 | 2642457 | 2642436 | -22 | 3681296
1 | E1W16 | 44738015201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-09-21 | 2844972 | 2870813 | 2826404 | 25840.92 | 0 | 2818713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2826404 | 2818713 | -7691 | 2548368
1 | E1W18 | 44743115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-04-18 | 2506911 | 2530764 | 2550717 | 23853.05 | 0 | 2546483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550717 | 2546483 | -4233 | 2727223
1 | E1W50 | 45279215201 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-26 | 2283584 | 2283584 | 2253806 | 0 | 0 | 2253543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2253806 | 2253543 | -264 | 2780605 | Y | DESIGN/BUILD PROJECT
1 | E1W75 | 44923315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-07-18 | 2560003 | 2560003 | 2586788 | 0 | 0 | 2586788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586788 | 2586788 | 0 | 3481659
1 | E1W76 | 44897215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-15 | 3352588 | 3352588 | 3378389 | 0 | 0 | 3377632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3378389 | 3377632 | -757 | 4285958
1 | E1W78 | 44927215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-08-15 | 1562427 | 1562023 | 1597413 | -403.64 | 0 | 1597413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1597413 | 1597413 | 0 | 1884402
1 | E1W79 | 44023015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-09-19 | 1118465 | 1118465 | 854089 | 0 | 0 | 854089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854089 | 854089 | -1 | 991704
1 | E1W84 | 43607915201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-11-07 | 2277103 | 2321230 | 1781060 | 44126.8 | 0 | 1781061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1781060 | 1781061 | 1 | 3667818
1 | E1W85 | 44893115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-11-07 | 4458291 | 4710660 | 4720609 | 252368.4 | 0 | 4733331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4720609 | 4733331 | 12722 | 5001199
1 | E1W87 | 45089215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-07-17 | 3771590 | 3771590 | 3672932 | 0 | 0 | 3673179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672932 | 3673179 | 247 | 5146948
1 | E1W89 | 44927515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-12-05 | 8846876 | 8846876 | 9498223 | 0 | 0 | 9498120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9498223 | 9498120 | -103 | 9903213
1 | E1W94 | 44917815201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-02-20 | 830702 | 830702 | 826937 | 0 | -15165 | 811772 | -15165 | 0 | 0 | 0 | 0 | 0 | -15165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15165 | 811772 | 811772 | 0 | 1048586
1 | E1W97 | 45344615201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-03-20 | 586332 | 586332 | 567695 | 0 | -2950 | 564745 | 0 | 0 | 0 | 0 | 0 | -2950 | -2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2950 | 564745 | 564745 | 0 | 574884
1 | E1X61 | 44897315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-05-15 | 6268574 | 6268574 | 6617085 | 0 | 0 | 6635936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6617085 | 6635936 | 18851 | 7458839
1 | E1X68 | 44895715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-17 | 2063849 | 2063849 | 1971937 | 0 | 0 | 1971937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1971937 | 1971937 | 0 | 2136352
1 | E1X74 | 45087815201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-18 | 576122 | 576122 | 554252 | 0 | 0 | 554252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554252 | 554252 | 0 | 728144
1 | E1X75 | 45127215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-09-18 | 2448287 | 2448287 | 2439726 | 0 | 0 | 2439726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2439726 | 2439726 | 0 | 3004336
1 | T1754 | 41924345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2020-06-10 | 44711727 | 45332170 | 46495372 | 620442.65 | 0 | 47278762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46495372 | 47278762 | 783390 | 49671696
1 | T1778 | 43805915201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-02-17 | 5124974 | 5379131 | 5608351 | 254156.8 | 0 | 5742108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5608351 | 5742108 | 133757 | 5113819
1 | T1801 | 43355055201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2022-02-23 | 9943982 | 10795145 | 10516274 | 851163.08 | 0 | 10539225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10516274 | 10539225 | 22951 | 8613987
1 | T1807 | 44464115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 5486544 | 5582663 | 5697293 | 96119.73 | -30000 | 5667081 | 0 | 0 | 0 | 0 | 0 | -30000 | -30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | 5667293 | 5667081 | -212 | 4275732
1 | T1833 | 44634515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 16756829 | 16756829 | 16918647 | 0 | -70500 | 16748453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -70500 | -70500 | -70500 | 16848147 | 16748453 | -99694 | 17387335
1 | T1843 | 43695525201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-07-27 | 4165582 | 4197230 | 4319692 | 31647.71 | 0 | 4262739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4319692 | 4262739 | -56953 | 3563245
1 | T1850 | 43944115201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-04-24 | 5279314 | 5778359 | 5716286 | 499045.08 | 0 | 5713996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5716286 | 5713996 | -2290 | 7929522
1 | T1852 | 44787215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-02-28 | 3084175 | 3084175 | 3074445 | 0 | 0 | 3073651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3074445 | 3073651 | -795 | 2364266
1 | T1854 | 44480735201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-03-27 | 1273662 | 1300460 | 1232804 | 26798.65 | -22000 | 1210162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22000 | -22000 | -22000 | 1210804 | 1210162 | -642 | 1109605
1 | T1855 | 44547315201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 11238774 | 11323365 | 11568463 | 84591.09 | -143070 | 11393079 | -143070 | 0 | 0 | 0 | 0 | 0 | -143070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -143070 | 11425393 | 11393079 | -32314 | 12534705
1 | T1861 | 44044815201 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 12860870 | 12904011 | 13130189 | 43141.21 | 0 | 13130017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13130189 | 13130017 | -171 | 12102054
1 | T1866 | 43903215201 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2023-11-15 | 3945642 | 4078353 | 4013289 | 132711.4 | -76850 | 3923705 | -76850 | 0 | 0 | 0 | 0 | 0 | -76850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76850 | 3936439 | 3923705 | -12734 | 5005578
1 | T1867 | 44546715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 7502026 | 8082796 | 8181304 | 580769.85 | 0 | 8176865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8181304 | 8176865 | -4440 | 7936833
1 | T1868 | 44740215201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-02-28 | 1036497 | 1074999 | 1074468 | 38501.79 | 0 | 1074468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074468 | 1074468 | 0 | 1164569
1 | T1873 | 44788015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-02-28 | 2902791 | 2941983 | 2705963 | 39192 | 0 | 2704866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2705963 | 2704866 | -1098 | 2895927
1 | T1874 | 43583015201 | F592163377 | THOMAS MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-08-28 | 2777889 | 2778854 | 2820140 | 965.1 | 0 | 2820008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2820140 | 2820008 | -133 | 3495664
1 | T1881 | 43802715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-11-15 | 6196035 | 6206737 | 6556044 | 10701.34 | 0 | 6524950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6556044 | 6524950 | -31093 | 6886951
1 | T1885 | 44629115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 11193872 | 11193872 | 11344239 | 0 | 0 | 11335446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11344239 | 11335446 | -8793 | 10309690
1 | T1889 | 44431315201 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-03-27 | 2636284 | 2666046 | 2714680 | 29762.4 | -3800 | 2705941 | 0 | 0 | 0 | 0 | 0 | -3800 | -3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3800 | 2710880 | 2705941 | -4939 | 3253357
1 | T1891 | 44743625201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 4742624 | 4787027 | 4779994 | 44403.46 | 0 | 4777172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4779994 | 4777172 | -2822 | 4605370
1 | T1895 | 44656015201 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2024-09-25 | 1414901 | 1450512 | 1460078 | 35610.63 | 0 | 1460017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460078 | 1460017 | -61 | 1992638
1 | T1901 | 44893615201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-08-28 | 9549741 | 9400063 | 9512022 | -149677.61 | 0 | 9509993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9512022 | 9509993 | -2029 | 10149490
1 | T1905 | 44645215201 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2025-01-29 | 574929 | 574929 | 554144 | 0 | 0 | 555650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554144 | 555650 | 1507 | 670642
1 | T1907 | 45240815201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC. | N/A | N/A | N/A | N/A | 2025-01-29 | 714571 | 714571 | 686286 | 0 | 0 | 686286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686286 | 686286 | 0 | 685304
1 | T1927 | 44477325201 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2025-07-30 | 414963 | 414963 | 422033 | 0 | 0 | 422033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422033 | 422033 | 0 | 496785
2 | E200W | 44572615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-04-17 | 2930266 | 2930266 | 2970891 | 0 | 0 | 2968577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970891 | 2968577 | -2313 | 2593407
2 | E20S0 | 20835235201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-01 | 10697084 | 11279564 | 11359661 | 582480 | 0 | 10989902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11359661 | 10989902 | -369758 | 9959695 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E20S1 | 20841835201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-01 | 11841194 | 11946194 | 12025404 | 105000 | 0 | 11833660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12025404 | 11833660 | -191744 | 11946615 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E20S2 | 21054545201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-01 | 8601469 | 8601469 | 8734394 | 0 | 0 | 8453915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8734394 | 8453915 | -280479 | 8397276 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E20T6 | 44278015201 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2023-02-15 | 1676236 | 1744958 | 1814629 | 68721.9 | 0 | 1814629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1814629 | 1814629 | 0 | 2494428
2 | E20X8 | 20840265201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-23 | 9409691 | 9409691 | 9709502 | 0 | 0 | 9670685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9709502 | 9670685 | -38817 | 8868810 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E20X9 | 44707615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-23 | 11213775 | 11213775 | 11321495 | 0 | 0 | 11257290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11321495 | 11257290 | -64205 | 11190658 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E21F5 | 43284915201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-01-09 | 13729182 | 16720109 | 16682304 | 2990926.53 | 0 | 16681077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16682304 | 16681077 | -1228 | 17192402 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT
2 | E21P1 | 21008525201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-01-15 | 12715932 | 13204452 | 13781531 | 488519.87 | 0 | 13781531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13781531 | 13781531 | 0 | 12431031
2 | E2Z53 | 43035245201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2020-02-20 | 17677113 | 32771107 | 33306856 | 15093994.45 | 0 | 33713424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33306856 | 33713424 | 406568 | 14339167
2 | T2591 | 42886515201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2015-10-14 | 65973116 | 108070596 | 111765107 | 42097480.47 | 0 | 113168629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111765107 | 113168629 | 1403522 | 76779378
2 | T2736 | 21002445201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 49333142 | 49318231 | 49613597 | -14911.35 | 0 | 51145456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49613597 | 51145456 | 1531859 | 54425330
2 | T2757 | 43761115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 8709827 | 8796925 | 9281776 | 87098.27 | 0 | 9514074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9281776 | 9514074 | 232299 | 10240285
2 | T2790 | 43616815201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2021-01-27 | 15444874 | 18490817 | 18667723 | 3045942.89 | 0 | 18710310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18667723 | 18710310 | 42587 | 11733777
2 | T2819 | 43384325201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 4659450 | 10356438 | 10867437 | 5696988.17 | 0 | 10867685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10867437 | 10867685 | 248 | 4935260
2 | T2839 | 44342115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-09 | 31969186 | 31969186 | 32489212 | 0 | 0 | 33982240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32489212 | 33982240 | 1493028 | 35449756
2 | T2844 | 43935615201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 19892956 | 20310363 | 20717832 | 417407.11 | 0 | 20372452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20717832 | 20372452 | -345380 | 16227519
2 | T2854 | 44554515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-08 | 10095026 | 10267526 | 10526210 | 172500 | 0 | 10199858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10526210 | 10199858 | -326352 | 10655889
2 | T2863 | 43744115201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-01-12 | 14032373 | 15901285 | 16261074 | 1868911.96 | 0 | 16285649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16261074 | 16285649 | 24575 | 15021661
2 | T2865 | 44351715201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-11-16 | 7663000 | 8470199 | 9163770 | 807198.83 | 0 | 9151881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9163770 | 9151881 | -11890 | 7014633
2 | T2878 | 43205425201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 9330849 | 9522394 | 9742335 | 191545 | 0 | 9717455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9742335 | 9717455 | -24880 | 10579789
2 | T2886 | 44554425201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 16754450 | 17512907 | 18119731 | 758456.68 | 0 | 17784378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18119731 | 17784378 | -335353 | 17577252
2 | T2889 | 43575615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 3832776 | 4315395 | 4383212 | 482619.04 | 0 | 4383212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4383212 | 4383212 | 0 | 4521037
2 | T2890 | 44554715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 25595410 | 25761158 | 26450421 | 165747.22 | 0 | 25953030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26450421 | 25953030 | -497390 | 25708228
2 | T2894 | 44540215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 12471547 | 12747539 | 13553931 | 275991.77 | 0 | 13363147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13553931 | 13363147 | -190784 | 11980864
2 | T2910 | 44535215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 5895675 | 5981679 | 6100547 | 86003.71 | 0 | 6097264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100547 | 6097264 | -3283 | 6680440
2 | T2913 | 44707815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 4420617 | 4518180 | 4416217 | 97563.2 | 0 | 4412247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4416217 | 4412247 | -3971 | 4807508
2 | T2914 | 44717215201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 14592365 | 14773312 | 15181984 | 180947.26 | 0 | 15184404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15181984 | 15184404 | 2420 | 15399944
2 | T2915 | 44718015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 11703806 | 11742594 | 12389230 | 38788.29 | 0 | 12394517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12389230 | 12394517 | 5287 | 10416036
2 | T2916 | 43993715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 10398707 | 10398707 | 10268067 | 0 | 0 | 10264664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10268067 | 10264664 | -3403 | 8834994
2 | T2917 | 44330415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-05-17 | 23947969 | 24055659 | 25032603 | 107690.09 | 0 | 25026994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25032603 | 25026994 | -5609 | 21934860
2 | T2924 | 20930185201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-04-26 | 19358596 | 19523393 | 20332171 | 164797.23 | 0 | 20313549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20332171 | 20313549 | -18621 | 19142187
2 | T2934 | 44331015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-12-07 | 26057502 | 26443445 | 27980036 | 385943.3 | 0 | 27874372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27980036 | 27874372 | -105664 | 24163400
2 | T2945 | 44542715201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 6853255 | 6853255 | 6989283 | 0 | 0 | 6981891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6989283 | 6981891 | -7392 | 7614578
2 | T2948 | 44712315201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 5794236 | 5794236 | 5977965 | 0 | 0 | 5958952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5977965 | 5958952 | -19013 | 5749685
2 | T2949 | 20969745201 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2023-11-15 | 1865813 | 1939049 | 1961474 | 73235.26 | 0 | 1960364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961474 | 1960364 | -1110 | 2230664
2 | T2954 | 44542015201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 3819110 | 3819110 | 3735111 | 0 | 0 | 3733457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3735111 | 3733457 | -1654 | 5040192
2 | T2961 | 43633015201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 3521000 | 3558326 | 3560864 | 37326.4 | 0 | 3626016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3560864 | 3626016 | 65152 | 3765541
2 | T2962 | 44796215201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 7958218 | 7958218 | 7882304 | 0 | 0 | 7877534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7882304 | 7877534 | -4770 | 8827614
2 | T2966 | 21086555201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 2921783 | 2921783 | 2938946 | 0 | 0 | 2938946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938946 | 2938946 | 0 | 3224885
2 | T2969 | 44703615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 10923210 | 10892472 | 11424138 | -30738.04 | 0 | 11378255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11424138 | 11378255 | -45883 | 10802904
2 | T2970 | 44712815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 6497196 | 6705393 | 7314719 | 208197.25 | 0 | 7294065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314719 | 7294065 | -20654 | 6729212
2 | T2973 | 44542915201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-27 | 11487858 | 11487858 | 11739228 | 0 | 0 | 11724947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11739228 | 11724947 | -14282 | 9400553
2 | T2974 | 44720415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-27 | 18339896 | 18339896 | 18394467 | 0 | 0 | 18347088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18394467 | 18347088 | -47379 | 19102224
2 | T2976 | 44755715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 25893810 | 26291007 | 27924429 | 397197.72 | 0 | 27880284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27924429 | 27880284 | -44146 | 21206563
2 | T2981 | 45220125201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 2914229 | 2914229 | 2917184 | 0 | 0 | 2917184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2917184 | 2917184 | 0 | 4244876
2 | T2985 | 43761415201 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-11-15 | 7308506 | 7308506 | 7304574 | 0 | 0 | 7285470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7304574 | 7285470 | -19104 | 8026688
2 | T2988 | 44721135201 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2024-04-24 | 1562105 | 1737694 | 1710662 | 175588.73 | 0 | 1710435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1710662 | 1710435 | -227 | 1572772
2 | T2989 | 20782335201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2024-08-28 | 5914935 | 5914935 | 5974865 | 0 | 0 | 5969794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974865 | 5969794 | -5070 | 6456937
2 | T2990 | 20817735201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-08-28 | 8971608 | 8971608 | 8756637 | 0 | 0 | 8744013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8756637 | 8744013 | -12624 | 11243024
2 | T2992 | 44603135201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-08-28 | 2368158 | 2387905 | 2401749 | 19747.2 | 0 | 2401749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2401749 | 2401749 | 0 | 3418661
2 | T2997 | 44984425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 2499454 | 2573884 | 2437559 | 74429.6 | 0 | 2436488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2437559 | 2436488 | -1071 | 2231403
2 | T2999 | 21273445201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-10-30 | 9621507 | 9621507 | 9860600 | 0 | -22878 | 9862910 | -22878 | 0 | 0 | 0 | 0 | 0 | -22878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22878 | 9837722 | 9862910 | 25188 | 9367982
2 | T2A02 | 43431825201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-11-13 | 7419960 | 7419960 | 7285721 | 0 | 0 | 7282630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7285721 | 7282630 | -3091 | 8775588
2 | T2A05 | 20944145201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2025-02-26 | 2487602 | 2535510 | 2431426 | 47908.5 | 0 | 2431081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2431426 | 2431081 | -345 | 3542854
2 | T2A06 | 21003025201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-11-13 | 6571980 | 6571980 | 6862070 | 0 | 0 | 6863371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6862070 | 6863371 | 1301 | 6362365
2 | T2A09 | 21022385201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-12-04 | 4685902 | 4685902 | 4940814 | 0 | 0 | 4942704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4940814 | 4942704 | 1890 | 5665702
2 | T2A11 | 21037845201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-01-29 | 4938588 | 4938588 | 5114986 | 0 | 0 | 5114986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5114986 | 5114986 | 0 | 4849325
2 | T2A12 | 21071155201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 4071019 | 4106006 | 4039787 | 34986.19 | 0 | 4039787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4039787 | 4039787 | 0 | 4204426
2 | T2A13 | 44721225201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-10-30 | 3440497 | 3440497 | 3621976 | 0 | 0 | 3623713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3621976 | 3623713 | 1737 | 3982197
2 | T2A15 | 21056535201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 4346749 | 4346749 | 4440530 | 0 | 0 | 4440461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4440530 | 4440461 | -69 | 5565013
2 | T2A22 | 20983125201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-04-30 | 4091439 | 4091439 | 4148474 | 0 | 0 | 4148474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4148474 | 4148474 | 0 | 4272747
2 | T2A25 | 45260325201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-06-11 | 1482455 | 1482455 | 1471968 | 0 | 0 | 1471968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1471968 | 1471968 | 0 | 1454043
2 | T2A31 | 43930215201 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2025-07-30 | 541819 | 541819 | 531179 | 0 | 0 | 531179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531179 | 531179 | 0 | 573090
2 | T2A46 | 44721125201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-09-24 | 992131 | 992131 | 944723 | 0 | 0 | 944723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944723 | 944723 | 0 | 1219062
2 | T9037 | 44627925214 | F593399145 | E.B.MORRIS GENERAL CONTRACTORS | N/A | N/A | N/A | N/A | 2024-05-22 | 755793 | 799963 | 782324 | 44170 | 0 | 782311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782324 | 782311 | -13 | 588438
2 | T9039 | 44532025214 | F593399145 | E.B.MORRIS GENERAL CONTRACTORS | N/A | N/A | N/A | N/A | 2024-05-22 | 2629396 | 2652851 | 2657516 | 23454.45 | 0 | 2657516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2657516 | 2657516 | 0 | 2484683
2 | T9041 | 44628015215 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-09-25 | 211688 | 211688 | 200166 | 0 | 0 | 200166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200166 | 200166 | 0 | 233430
2 | T9042 | 44628225214 | F593399145 | E.B.MORRIS GENERAL CONTRACTORS | N/A | N/A | N/A | N/A | 2025-03-26 | 790012 | 790012 | 769140 | 0 | 0 | 769140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 769140 | 769140 | 0 | 477561
2 | T9044 | 44628025216 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-01-29 | 393754 | 393754 | 371540 | 0 | 0 | 371540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371540 | 371540 | 0 | 505500
3 | E3U65 | 44188515201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-11-17 | 3672487 | 3672487 | 3781493 | 0 | -38880 | 3739460 | -38880 | 0 | 0 | 0 | 0 | 0 | -38880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38880 | 3742613 | 3739460 | -3153 | 3629577
3 | E3V54 | 44554115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-02-09 | 9981474 | 10203672 | 10678123 | 222197.51 | 0 | 10639564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10678123 | 10639564 | -38559 | 10144016
3 | E3V77 | 40919375201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-10-12 | 3075367 | 3075367 | 2907496 | 0 | 0 | 2907496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2907496 | 2907496 | 0 | 4067369
3 | E3V81 | 44563415201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2023-06-08 | 7280451 | 7422322 | 7437743 | 141871 | 0 | 7440600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7437743 | 7440600 | 2857 | 6184892
3 | E3W01 | 44559115201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2022-09-08 | 7469384 | 7480930 | 7419597 | 11546.09 | -530040 | 6838207 | -530040 | 0 | 0 | 0 | 0 | 0 | -530040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -530040 | 6889557 | 6838207 | -51349 | 9544566
3 | E3W03 | 45034815201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2024-09-12 | 433807 | 433807 | 404077 | 0 | 0 | 404077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404077 | 404077 | 0 | 495858
3 | E3W12 | 44643355201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-08-08 | 2949285 | 2625347 | 2604415 | -323937.27 | 0 | 2604415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604415 | 2604415 | 0 | 3480038
3 | E3W30 | 44759615201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-06-08 | 4167167 | 4263313 | 3906647 | 96146.41 | 0 | 3906647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3906647 | 3906647 | 0 | 4722892
3 | E3W31 | 44554215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-06-08 | 12495664 | 12574093 | 13184954 | 78428.51 | 0 | 13181542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13184954 | 13181542 | -3412 | 11633200
3 | E3W40 | 44374425201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-05-11 | 6286877 | 6497112 | 6613095 | 210234.99 | -68148 | 6607189 | -68148 | 0 | 0 | 0 | 0 | 0 | -68148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68148 | 6544947 | 6607189 | 62243 | 5983265
3 | E3W42 | 44559015201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-11 | 6987787 | 6987787 | 7253303 | 0 | -185514 | 7068223 | -185514 | 0 | 0 | 0 | 0 | 0 | -185514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -185514 | 7067789 | 7068223 | 435 | 10217707
3 | E3W68 | 45102815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-02-13 | 112106 | 112106 | 103639 | 0 | 0 | 103639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103639 | 103639 | 0 | 174993
3 | E3W69 | 42696125201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2023-11-09 | 4685111 | 4688658 | 4492681 | 3546.7 | 0 | 4485331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4492681 | 4485331 | -7350 | 5910727
3 | E3W79 | 45109915201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2024-04-11 | 485265 | 485265 | 487819 | 0 | 0 | 487819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487819 | 487819 | 0 | 555113
3 | E3X01 | 40619455201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-10-24 | 328567 | 328567 | 291720 | 0 | 0 | 291720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291720 | 291720 | 0 | 364798
3 | E3X02 | 44366115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-01-18 | 17358711 | 17495056 | 17763005 | 136344.64 | 0 | 17748983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17763005 | 17748983 | -14021 | 17119006
3 | E3X03 | 40619635201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-03-13 | 169075 | 169075 | 154095 | 0 | 0 | 154095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154095 | 154095 | 0 | 240133
3 | E3X08 | 45103115201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-07-11 | 1112248 | 1112248 | 1077908 | 0 | 0 | 1077908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077908 | 1077908 | 0 | 1273505
3 | E3X10 | 41537525201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-11 | 6739140 | 6837451 | 7312420 | 98311.08 | 0 | 7306921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7312420 | 7306921 | -5499 | 7908181
3 | E3X17 | 44758915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-06-13 | 2342678 | 2369603 | 2340433 | 26925.01 | 0 | 2340369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340433 | 2340369 | -64 | 2975754
3 | E3X52 | 43078225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-07-11 | 4271650 | 4271650 | 4371998 | 0 | 0 | 4360199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4371998 | 4360199 | -11799 | 4754953
3 | E3X67 | 45103015201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-03-20 | 756145 | 589518 | 538882 | -166626.68 | 0 | 538882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538882 | 538882 | 0 | 979633
3 | E3X72 | 22020225201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-02-13 | 647631 | 647631 | 536583 | 0 | 0 | 536583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536583 | 536583 | 0 | 900233
3 | E3X74 | 45102925201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2024-11-14 | 1642742 | 1701821 | 1683345 | 59079 | 0 | 1683345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683345 | 1683345 | 0 | 1852699
3 | E3X76 | 44546615201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-02-13 | 2098170 | 2098170 | 256639 | 0 | 0 | 256639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256639 | 256639 | 0 | 2034849
3 | E3X87 | 45268615201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2024-09-12 | 1172775 | 1197264 | 1124063 | 24489.2 | 0 | 1124063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1124063 | 1124063 | 0 | 1445110
3 | E3X99 | 43622975201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-12 | 5036594 | 5050202 | 5170364 | 13608 | 0 | 5170313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5170364 | 5170313 | -51 | 6071472
3 | E3Y02 | 45258125201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2025-04-10 | 1467009 | 1467009 | 1421040 | 0 | 0 | 1421040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1421040 | 1421040 | 0 | 1617018
3 | E3Y07 | 43937125201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-01-30 | 493247 | 493247 | 468786 | 0 | 0 | 468786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468786 | 468786 | 0 | 566683
3 | E3Y25 | 45431115201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-03-13 | 430052 | 430052 | 391859 | 0 | 0 | 391859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391859 | 391859 | 0 | 619870
3 | E3Y28 | 45443415201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-04-10 | 339177 | 339177 | 318764 | 0 | 0 | 318764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318764 | 318764 | 0 | 393848
3 | E3Y34 | 45430915201 | F862261446 | UNITED MARINE CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-08-14 | 882049 | 882049 | 783756 | 0 | 0 | 783756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783756 | 783756 | 0 | 959604
3 | T3618 | 21790935201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 27170428 | 30592621 | 31444648 | 3422192.89 | 0 | 32998164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31444648 | 32998164 | 1553516 | 35258008
3 | T3705 | 43581615201 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 21786584 | 24287618 | 24853167 | 2501033.2 | 0 | 24864564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24853167 | 24864564 | 11396 | 31799900
3 | T3712 | 43937115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-17 | 4199999 | 4207543 | 4275092 | 7543.56 | -681696 | 4275464 | -681696 | 0 | 0 | 0 | 0 | 0 | -681696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -681696 | 3593396 | 4275464 | 682068 | 3898369
3 | T3722 | 41098185201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 16220760 | 16260965 | 16485438 | 40204.57 | -1083175 | 16125524 | -1083175 | 0 | 0 | 0 | 0 | 0 | -1083175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1083175 | 15402263 | 16125524 | 723261 | 24461057
3 | T3740 | 43626615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 6166449 | 6169465 | 6746581 | 3016.6 | 0 | 7858953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6746581 | 7858953 | 1112372 | 7986598
3 | T3786 | 21798625201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 12931177 | 14015331 | 14246133 | 1084154.4 | 0 | 14084325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14246133 | 14084325 | -161808 | 10461387
3 | T3789 | 43813315201 | F473361483 | T & T CIVIL CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-02-23 | 383899 | 397919 | 393163 | 14020 | -35910 | 329110 | -35910 | 0 | 0 | 0 | 0 | 0 | -35910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35910 | 357253 | 329110 | -28143 | 424158
3 | T3790 | 43748915201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 3547402 | 3547402 | 3587891 | 0 | 0 | 3586665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3587891 | 3586665 | -1225 | 4578762
3 | T3804 | 42697315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 6212045 | 6299150 | 6924822 | 87104.94 | 0 | 6889613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6924822 | 6889613 | -35209 | 5759918
3 | T3835 | 44563315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 10919335 | 11003378 | 11511158 | 84042.7 | 0 | 11473007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11511158 | 11473007 | -38151 | 11459374
3 | T3837 | 22259365201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 11772258 | 11871253 | 11834603 | 98994.59 | 0 | 11821261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11834603 | 11821261 | -13342 | 13447557
3 | T3840 | 44560215201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-08-28 | 2093575 | 2093575 | 2052800 | 0 | 0 | 2052014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052800 | 2052014 | -786 | 1776459
3 | T3843 | 43736615201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 14976878 | 15770067 | 16545874 | 793188.98 | 0 | 16474250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16545874 | 16474250 | -71624 | 17116856
3 | T3844 | 44581515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-04-26 | 16815829 | 16829871 | 17633297 | 14041.78 | 0 | 17609681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17633297 | 17609681 | -23615 | 15773894
3 | T3851 | 44292015201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2024-02-28 | 3185384 | 3188684 | 3129056 | 3300 | 0 | 3127773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3129056 | 3127773 | -1283 | 3413370
3 | T3855 | 44401915201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 958894 | 958894 | 885299 | 0 | 0 | 885298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 885299 | 885298 | -1 | 1271778
3 | T3861 | 44573425201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 6086126 | 6138322 | 6717678 | 52195.42 | 0 | 6699730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6717678 | 6699730 | -17947 | 6407296
3 | T3862 | 43977415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | 3433760 | 3478528 | 3538382 | 44767.5 | 0 | 3534775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3538382 | 3534775 | -3607 | 3773824
3 | T3863 | 43256815201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2023-03-29 | 7039667 | 7122635 | 6823877 | 82967.87 | 0 | 6801370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6823877 | 6801370 | -22508 | 11146776
3 | T3866 | 21968945201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 7020914 | 7091275 | 7209436 | 70361.5 | 0 | 7197450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7209436 | 7197450 | -11986 | 10186905
3 | T3868 | 41344925201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 1298401 | 1321412 | 1234071 | 23011 | 0 | 1234071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1234071 | 1234071 | 0 | 1300164
3 | T3871 | 42695025201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-06-12 | 3111541 | 2493770 | 2535278 | -617770.69 | 0 | 2534712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2535278 | 2534712 | -566 | 4093774
3 | T3874 | 44188015201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 988409 | 988409 | 938135 | 0 | 0 | 938135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938135 | 938135 | 0 | 990879
3 | T3891 | 43467815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-01-31 | 2823614 | 2855298 | 2780904 | 31684.39 | 0 | 2780236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780904 | 2780236 | -668 | 3805810
3 | T3896 | 21995125201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-10-30 | 2986323 | 2986323 | 3098563 | 0 | 0 | 3098475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3098563 | 3098475 | -89 | 3943156
3 | T3901 | 41342535201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-31 | 3608291 | 3609941 | 3619668 | 1650 | 0 | 3616057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3619668 | 3616057 | -3611 | 3187529
3 | T3903 | 43973815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-10-30 | 3355890 | 3355890 | 3514890 | 0 | 0 | 3515807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514890 | 3515807 | 917 | 4058350
3 | T3905 | 22392035201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2024-11-13 | 4631224 | 4783835 | 4745931 | 152611.13 | 0 | 4746412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4745931 | 4746412 | 481 | 5602105
3 | T3909 | 43627425201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2025-02-26 | 989048 | 1062486 | 1040496 | 73438.04 | 0 | 1040496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040496 | 1040496 | 0 | 1500432
3 | T3911 | 45100315201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-11-13 | 960717 | 960717 | 866512 | 0 | 0 | 866512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866512 | 866512 | 0 | 1028033
3 | T3913 | 21934625201 | F592990776 | AMERICAN SAND & X-CAVATION INC. DBA AMERICAN SAND & ASPHALT | N/A | N/A | N/A | N/A | 2024-08-28 | 2531784 | 2570548 | 2574902 | 38764.2 | 0 | 2573463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574902 | 2573463 | -1439 | 3011929
3 | T3936 | 45221255201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-11-13 | 993728 | 993728 | 582095 | 0 | 0 | 582095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582095 | 582095 | 0 | 1931621
3 | T3974 | 45221245201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-01-29 | 664538 | 664538 | 561863 | 0 | 0 | 561863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561863 | 561863 | 0 | 887347
3 | T3976 | 45586915201 | F824750393 | COLLINS LAND SERVICES LLC | N/A | N/A | N/A | N/A | 2025-04-30 | 138618 | 138618 | 130350 | 0 | 0 | 130350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130350 | 130350 | 0 | 174043
3 | T3A07 | 45587615201 | F541769861 | WEBBER INFRASTRUCTURE MANAGEMENT INC. | N/A | N/A | N/A | N/A | 2025-07-30 | 96095 | 47595 | 38484 | -48500 | 0 | 38484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38484 | 38484 | 0 | 164000
3 | T9043 | 44628415215 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-09-25 | 189979 | 189979 | 177334 | 0 | 0 | 177334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177334 | 177334 | 0 | 237358
3 | T9045 | 44628425216 | F592320406 | BILL SMITH ELECTRIC | N/A | N/A | N/A | N/A | 2025-01-29 | 511934 | 511934 | 495348 | 0 | 0 | 495348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495348 | 495348 | 0 | 509928
4 | E4Q32 | 43310845201 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2015-04-27 | 148749800 | 174962816 | 175180045 | 26213015.82 | 56000 | 175194917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 56000 | 56000 | 175236045 | 175194917 | -41128 | 122897181 | B10:B5:B8:::Y | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
4 | E4U48 | 44146615201 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2023-06-14 | 2126000 | 2132929 | 1513603 | 6929.94 | 0 | 1513603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513603 | 1513603 | 0 | 2622052
4 | E4U88 | 43999925201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-04-07 | 10631541 | 10738131 | 11100934 | 106590.35 | 0 | 11099417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11100934 | 11099417 | -1518 | 10492575
4 | E4V62 | 43695815201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-08-18 | 31058595 | 33155117 | 32699199 | 1946522.44 | 0 | 32559543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32699199 | 32559543 | -139657 | 29695111
4 | E4W05 | 44047315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-12-02 | 3993841 | 4453325 | 4438530 | 459484.36 | 0 | 4433029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4438530 | 4433029 | -5501 | 4033616
4 | E4W54 | 44618515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-05-05 | 8153790 | 8619435 | 8570644 | 465645.84 | 0 | 8570644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8570644 | 8570644 | 0 | 7653131
4 | E4W61 | 44610415201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-08-04 | 5369226 | 5369226 | 5576786 | 0 | 0 | 5571433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576786 | 5571433 | -5352 | 4627615
4 | E4W65 | 44617415201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-01-05 | 4920477 | 4920477 | 4833727 | 0 | 0 | 4832964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4833727 | 4832964 | -763 | 4972818
4 | E4W69 | 44617315201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-12-01 | 2294610 | 2441883 | 2324253 | 147273.5 | 0 | 2322959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2324253 | 2322959 | -1294 | 2294338
4 | E4W70 | 44617615201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-02-02 | 3860000 | 3929208 | 3917472 | 69207.56 | 0 | 3912966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3917472 | 3912966 | -4506 | 3983140
4 | E4W71 | 44974015201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-05 | 827827 | 827827 | 848976 | 0 | 0 | 848976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848976 | 848976 | 0 | 1076147
4 | E4W72 | 44617015201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-11-03 | 4285836 | 4430549 | 4413846 | 144712.95 | 0 | 4404654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4413846 | 4404654 | -9192 | 4697027
4 | E4W82 | 44610515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-01-05 | 4881711 | 4893014 | 4759434 | 11302.53 | 0 | 4771645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4759434 | 4771645 | 12211 | 5716819
4 | E4W88 | 44765415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-02-02 | 6226524 | 6395874 | 6393098 | 169349.93 | 0 | 6387556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6393098 | 6387556 | -5542 | 6625404
4 | E4W89 | 44767415201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-07-12 | 3966137 | 3985889 | 3958991 | 19751.98 | 0 | 3953275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3958991 | 3953275 | -5716 | 4276093
4 | E4W93 | 44764815201 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-07-12 | 3198987 | 3198987 | 3046918 | 0 | 0 | 3045966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3046918 | 3045966 | -952 | 3443705
4 | E4X14 | 44932315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-04-05 | 3689059 | 3733032 | 3801506 | 43972.81 | 0 | 3800583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3801506 | 3800583 | -923 | 2884957
4 | E4X17 | 44655115201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-02 | 1849000 | 1870772 | 1768167 | 21772.08 | 0 | 1768167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768167 | 1768167 | 0 | 2011837
4 | E4X24 | 44931815201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-09-06 | 3983900 | 4183008 | 4262893 | 199107.9 | 0 | 4262893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4262893 | 4262893 | 0 | 5126069
4 | E4X25 | 44766515201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-08-02 | 3160159 | 3174469 | 3061340 | 14309.5 | 0 | 3061200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3061340 | 3061200 | -140 | 3262206
4 | E4X26 | 44766715201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-10-04 | 1352924 | 1396379 | 1294317 | 43455.02 | 0 | 1294741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1294317 | 1294741 | 424 | 1552465
4 | E4X33 | 44359525201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-09-06 | 2579048 | 2787519 | 2747199 | 208471 | 0 | 2747177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2747199 | 2747177 | -22 | 3891911
4 | E4X37 | 44768015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-07-12 | 3165008 | 3165008 | 3101006 | 0 | 0 | 3094587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3101006 | 3094587 | -6420 | 3833064
4 | E4X39 | 44768115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-06 | 2519093 | 2519093 | 2422842 | 0 | 0 | 2420995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422842 | 2420995 | -1848 | 2812112
4 | E4X44 | 44766015201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-10-04 | 2684615 | 2684615 | 2436599 | 0 | 0 | 2436934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2436599 | 2436934 | 335 | 2738308
4 | E4X51 | 44765815201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-08-02 | 3535833 | 3535833 | 3387300 | 0 | 0 | 3384814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3387300 | 3384814 | -2487 | 3764178
4 | T4560 | 44004315201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 2472960 | 2472960 | 2581880 | 0 | 0 | 2588651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2581880 | 2588651 | 6772 | 2686958
4 | T4576 | 43175265201 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2021-07-28 | 11570179 | 12011477 | 12175883 | 441298.1 | 0 | 12224650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12175883 | 12224650 | 48767 | 11623972 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4580 | 43992915201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-05-26 | 18014663 | 17978017 | 17209306 | -36646.61 | 0 | 17757665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17209306 | 17757665 | 548358 | 22960743
4 | T4582 | 43971415201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2021-05-26 | 28428146 | 30792178 | 31902413 | 2364032.01 | 210000 | 31922212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 210000 | 210000 | 32112413 | 31922212 | -190201 | 26971213 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | T4606 | 43175615201 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 13650945 | 16672549 | 16820299 | 3021604.61 | 0 | 16628208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16820299 | 16628208 | -192091 | 14924237 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4627 | 44384615201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 1831417 | 1831417 | 1800868 | 0 | 0 | 1800868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800868 | 1800868 | 0 | 2390409
4 | T4638 | 43580855201 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2023-07-26 | 8148235 | 8411133 | 8179681 | 262898 | 0 | 8175682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8179681 | 8175682 | -3998 | 8255267
4 | T4641 | 43984515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-04-26 | 11705000 | 12054276 | 11872830 | 349275.93 | 0 | 11861733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11872830 | 11861733 | -11097 | 11870989
4 | T4643 | 44637415201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 17748021 | 18627265 | 18943576 | 879243.5 | 0 | 18918036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18943576 | 18918036 | -25540 | 24914785
4 | T4645 | 44610215201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 12833449 | 12956058 | 12287948 | 122609.04 | 0 | 12290198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12287948 | 12290198 | 2250 | 14351247
4 | T4649 | 44839715201 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2023-06-14 | 4835155 | 5082020 | 5106645 | 246864.93 | 0 | 5105846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5106645 | 5105846 | -798 | 6110749
4 | T4651 | 44407915201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-10-25 | 7152200 | 7526530 | 7413084 | 374329.92 | 0 | 7398235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7413084 | 7398235 | -14849 | 6673207
4 | T4652 | 44616915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | 5424973 | 5477905 | 5676734 | 52931.68 | 0 | 5668308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5676734 | 5668308 | -8426 | 5383942
4 | T4654 | 44952015201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 5626066 | 5715669 | 5782761 | 89602.91 | 0 | 5782671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5782761 | 5782671 | -91 | 6458891
4 | T4657 | 44447715201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2023-12-06 | 8333362 | 9056685 | 9730673 | 723323.24 | 0 | 9713133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9730673 | 9713133 | -17540 | 8086005
4 | T4661 | 44620015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-03-27 | 9458464 | 9790787 | 9649312 | 332323.68 | 0 | 9630778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9649312 | 9630778 | -18533 | 11108028
4 | T4662 | 44001515201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 2710165 | 2699856 | 2568771 | -10309.35 | 0 | 2568756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568771 | 2568756 | -16 | 3354140
4 | T4663 | 44764715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 11192757 | 11220679 | 11200266 | 27922.29 | 0 | 11169796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200266 | 11169796 | -30470 | 11705908
4 | T4664 | 44699715201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-13 | 1247247 | 1247247 | 1175544 | 0 | 0 | 1174544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1175544 | 1174544 | -1000 | 1347695
4 | T4665 | 44619515201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-02-28 | 5489802 | 5499093 | 5514945 | 9290.94 | 0 | 5496131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5514945 | 5496131 | -18814 | 5906510
4 | T4667 | 44764615201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-03-27 | 5722729 | 5878728 | 5826172 | 155998.27 | 0 | 5813776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5826172 | 5813776 | -12396 | 5723688
4 | T4677 | 44767915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 7765433 | 7871392 | 7668837 | 105958.4 | 0 | 7663134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7668837 | 7663134 | -5703 | 8421051
4 | T4679 | 44619615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 5469442 | 5469442 | 5544372 | 0 | 0 | 5542177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5544372 | 5542177 | -2195 | 5971109
4 | T4686 | 42957695201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2024-04-24 | 3298227 | 3298227 | 3079319 | 0 | 0 | 3078260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3079319 | 3078260 | -1060 | 3509812
4 | T4687 | 45222715201 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2024-05-22 | 1600545 | 1600545 | 1508063 | 0 | 0 | 1508063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1508063 | 1508063 | 0 | 2128846
4 | T4694 | 44767115201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2024-07-31 | 3150955 | 3159605 | 3107001 | 8650 | 0 | 3106285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3107001 | 3106285 | -716 | 3340322
4 | T4695 | 44394815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-10-30 | 2565294 | 2565294 | 2420314 | 0 | 0 | 2420700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2420314 | 2420700 | 386 | 2864085
4 | T4708 | 44754315201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2024-07-31 | 1300000 | 1300000 | 1243700 | 0 | 0 | 1243700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243700 | 1243700 | 0 | 1369377
5 | E50B8 | 44521515201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-06-06 | 11282143 | 11851012 | 12077791 | 568869.16 | 0 | 12077791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12077791 | 12077791 | 0 | 10131956
5 | E50F1 | 44656815201 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2024-02-06 | 1104118 | 1104118 | 1062935 | 0 | 0 | 1062929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062935 | 1062929 | -6 | 1174164
5 | E50F5 | 44316915201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2024-01-04 | 5036336 | 5073420 | 4545253 | 37084.7 | 0 | 4525803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4545253 | 4525803 | -19451 | 5619045
5 | E51F2 | 44768815201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-04-02 | 1504656 | 1506430 | 1447570 | 1774.33 | 0 | 1447098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1447570 | 1447098 | -472 | 1590260
5 | E51F6 | 43923415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-05 | 16652098 | 16895551 | 16781249 | 243452.83 | 0 | 16757648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16781249 | 16757648 | -23602 | 16309345
5 | E51F7 | 44530215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-03-05 | 5562121 | 5724310 | 5880473 | 162189.46 | 0 | 5865584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5880473 | 5865584 | -14889 | 6330177
5 | E51F9 | 43912415201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-02 | 4408516 | 4442576 | 4279968 | 34060.07 | 0 | 4279968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4279968 | 4279968 | 0 | 6688705
5 | E53F2 | 44879115201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-10-01 | 7065614 | 7183452 | 7253477 | 117838 | 0 | 7256561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7253477 | 7256561 | 3084 | 8985393
5 | E53F5 | 44880015201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-09-04 | 3585802 | 3585802 | 3601966 | 0 | 0 | 3601961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3601966 | 3601961 | -5 | 3427521
5 | E53F6 | 44880115201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2024-08-08 | 5664533 | 5664533 | 5824248 | 0 | 0 | 5821719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5824248 | 5821719 | -2529 | 5574707
5 | E53F7 | 44984515201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-12-03 | 925088 | 925088 | 953719 | 0 | 0 | 953719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953719 | 953719 | 0 | 845922
5 | E53F8 | 45022745201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-06-04 | 1498164 | 1498164 | 1468694 | 0 | 0 | 1468694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1468694 | 1468694 | 0 | 1507975
5 | E54B3 | 44521415201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-10-03 | 6964127 | 7171619 | 7043664 | 207492.45 | 0 | 6998013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7043664 | 6998013 | -45651 | 9627439
5 | E54F0 | 45141535201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-12-03 | 3082346 | 3082346 | 3072912 | 0 | 0 | 3072912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072912 | 3072912 | 0 | 4142465
5 | E55F3 | 45131115201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-02-04 | 4402920 | 4402920 | 4332664 | 0 | 0 | 4326586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4332664 | 4326586 | -6078 | 6422896
5 | E55F4 | 42690555201 | F824750393 | COLLINS LAND SERVICES LLC | N/A | N/A | N/A | N/A | 2025-04-01 | 1132509 | 1132509 | 1025664 | 0 | 0 | 1025664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025664 | 1025664 | 0 | 1246520
5 | E55F6 | 44529815201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-03-04 | 7863435 | 8058116 | 8341201 | 194681.09 | 0 | 8333175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8341201 | 8333175 | -8027 | 10455826
5 | E55F9 | 45370915201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-08-05 | 494060 | 494060 | 523498 | 0 | 0 | 523851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523498 | 523851 | 353 | 553244
5 | E56B6 | 44521115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 3196756 | 3198241 | 3427202 | 1484.92 | 0 | 3427202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427202 | 3427202 | 0 | 3501358
5 | E56F2 | 45057615201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-04-01 | 6262690 | 6580074 | 6638647 | 317384.38 | 0 | 6638621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6638647 | 6638621 | -26 | 7148293
5 | E56F4 | 41025155201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-05-06 | 3296100 | 3296100 | 3182948 | 0 | 0 | 3193975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3182948 | 3193975 | 11027 | 5178576
5 | E56F7 | 45305815201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2025-04-01 | 6639966 | 6639966 | 6618677 | 0 | 0 | 6618677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6618677 | 6618677 | 0 | 8028735
5 | E57B2 | 44531615201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2024-05-07 | 5768393 | 5840924 | 5658500 | 72530.84 | 0 | 5655760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5658500 | 5655760 | -2740 | 6011562
5 | E57B3 | 24259265201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2023-06-06 | 9899345 | 10080554 | 10364962 | 181208.47 | 0 | 10364953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10364962 | 10364953 | -9 | 8480188
5 | E57B4 | 44198215201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 3503151 | 3638714 | 3552928 | 135563.24 | 0 | 3552928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3552928 | 3552928 | 0 | 3345709
5 | E57B5 | 44530315201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-06-06 | 11137584 | 11274458 | 11215283 | 136873.78 | 0 | 11214497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11215283 | 11214497 | -786 | 8364008
5 | E57B7 | 44708515201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-06-06 | 13078910 | 13273764 | 13547486 | 194854.3 | 0 | 13544883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13547486 | 13544883 | -2602 | 13524204 | A5 | ICC - BAM/BONUS
5 | E57B8 | 44709015201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-06-04 | 3852254 | 4394289 | 4697644 | 542035.07 | 0 | 4695025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4697644 | 4695025 | -2619 | 3125052
5 | E57F0 | 45057715201 | F333155560 | YOROCA ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2025-07-01 | 339907 | 339907 | 317523 | 0 | 0 | 317523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317523 | 317523 | 0 | 405078
5 | E58F1 | 44529515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-09-03 | 5893242 | 5963607 | 6069935 | 70365.41 | 0 | 6073721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6069935 | 6073721 | 3786 | 8198293
5 | E58F2 | 45063515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-09-03 | 592801 | 592801 | 526193 | 0 | 0 | 526193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526193 | 526193 | 0 | 700854
5 | E58F3 | 45077215201 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2025-09-03 | 682916 | 682916 | 662216 | 0 | 0 | 662216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662216 | 662216 | 0 | 700585
5 | E58F4 | 45062315201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-05 | 1291007 | 1291007 | 1311928 | 0 | 0 | 1312246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311928 | 1312246 | 318 | 1935088
5 | E59A5 | 44780715201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-04-06 | 973615 | 973615 | 939263 | 0 | 0 | 939263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939263 | 939263 | 0 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E59B2 | 43986415201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2024-02-06 | 3015224 | 3086900 | 3009526 | 71675.77 | 0 | 3004683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009526 | 3004683 | -4843 | 3337723
5 | E59B3 | 44710515201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-10-03 | 9171822 | 9565947 | 9919938 | 394124.52 | 0 | 9904132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9919938 | 9904132 | -15806 | 10427762
5 | E59F3 | 44101515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-05 | 2681271 | 2681271 | 2693179 | 0 | 0 | 2693179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2693179 | 2693179 | 0 | 3752504
5 | E5Y71 | 43710015201 | F592143889 | COLLAGE DESIGN & CONSTRUCTION G THE COLLAGE COMPANIES | N/A | N/A | N/A | N/A | 2017-02-10 | 13137000 | 15625764 | 15527284 | 2488763.94 | 0 | 15527284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15527284 | 15527284 | 0 | 13833591
5 | E5Z18 | 24020045201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-08-22 | 253332000 | 267516079 | 275166241 | 14184078.5 | 25000 | 276193366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 25000 | 275191241 | 276193366 | 1002125 | 283931078 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | T5650 | 23839555201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-03-11 | 44960000 | 46736451 | 46188504 | 1776450.82 | 0 | 47789854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46188504 | 47789854 | 1601350 | 45602808
5 | T5686 | 43667915201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-05-20 | 10409198 | 14440107 | 14411744 | 4030908.9 | -18086 | 14702798 | 0 | 0 | 0 | 0 | 0 | -18086 | -18086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18086 | 14393658 | 14702798 | 309140 | 9656861
5 | T5706 | 42955615201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2020-03-25 | 44888403 | 47699589 | 50521720 | 2811185.71 | 0 | 50750843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50521720 | 50750843 | 229122 | 37019155
5 | T5718 | 43763415201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 11250000 | 12978309 | 13223828 | 1728309.11 | 0 | 13379283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13223828 | 13379283 | 155455 | 10799983
5 | T5724 | 44111315201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-06-15 | 82895000 | 89148107 | 90565070 | 6253106.55 | 897177 | 89831520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897177 | 0 | 0 | 0 | 0 | 0 | 897177 | 897177 | 91462247 | 89831520 | -1630727 | 78970684 | A5 | ICC - BAM/BONUS
5 | T5736 | 41503065201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-05-26 | 19997789 | 21610437 | 21540657 | 1612647.43 | 0 | 21329869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21540657 | 21329869 | -210788 | 17595887
5 | T5747 | 43366115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 6696978 | 7142732 | 7032054 | 445754.9 | 0 | 7032054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7032054 | 7032054 | 0 | 5918166
5 | T5759 | 44586715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-04-26 | 3865830 | 3991018 | 3937381 | 125187.71 | 0 | 3936003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3937381 | 3936003 | -1378 | 3318269
5 | T5760 | 44114515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 9020145 | 9091224 | 9371724 | 71078.78 | 0 | 9370672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9371724 | 9370672 | -1051 | 8000814
5 | T5777 | 44042425201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 22896706 | 23663870 | 23767312 | 767163.74 | 0 | 22940754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23767312 | 22940754 | -826558 | 28387050 | B10 | ACC - BONUS/INCENT/DISINCENT
5 | T5778 | 44569215201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 1617324 | 1637324 | 1467772 | 20000 | 0 | 1467140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1467772 | 1467140 | -632 | 1625739
5 | T5786 | 44521715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 10986719 | 11011859 | 11062198 | 25139.3 | 0 | 11057841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11062198 | 11057841 | -4358 | 14985674
5 | T5789 | 43547125201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 8448064 | 8800372 | 8800513 | 352307.8 | 0 | 8801368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8800513 | 8801368 | 855 | 8153515
5 | T5792 | 41025135201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 15097285 | 15626114 | 15519395 | 1098562.68 | 0 | 15511432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15519395 | 15511432 | -7963 | 25813007
5 | T5795 | 24259285201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-06-14 | 8347803 | 8496009 | 8830863 | 148205.6 | 0 | 8830373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8830863 | 8830373 | -490 | 8013785
5 | T5796 | 42617915201 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2023-07-26 | 3346229 | 3547942 | 3223459 | 201712.99 | 0 | 3223429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3223459 | 3223429 | -31 | 4393699
5 | T5797 | 44568915201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-26 | 6209544 | 6295030 | 5955348 | 85486.24 | 0 | 5954663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5955348 | 5954663 | -685 | 5653229
5 | T5798 | 44569415201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-11-15 | 16797190 | 17496951 | 17878429 | 699761.4 | 0 | 17850174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17878429 | 17850174 | -28255 | 15802710
5 | T5800 | 44585515201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-26 | 3679712 | 3851805 | 3808215 | 172092.45 | 0 | 3808146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3808215 | 3808146 | -69 | 2818722
5 | T5801 | 44521915201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 15286323 | 15295366 | 15592805 | 9042.58 | 0 | 15531171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15592805 | 15531171 | -61634 | 20005006
5 | T5804 | 43757515201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 3278993 | 3308018 | 3163264 | 29024.9 | 0 | 3163188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3163264 | 3163188 | -76 | 3131835
5 | T5805 | 44709215201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 3271306 | 3287930 | 3244926 | 16623.23 | 0 | 3224506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3244926 | 3224506 | -20420 | 4597691
5 | T5806 | 44709815201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 9892142 | 9938977 | 10455307 | 46835.26 | 0 | 10397121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10455307 | 10397121 | -58186 | 11922850
5 | T5809 | 43915615201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-09-27 | 19059007 | 19456279 | 20132774 | 397272.41 | 0 | 20058365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20132774 | 20058365 | -74410 | 20470643
5 | T5811 | 43233215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 15324226 | 16443632 | 16758792 | 1119405.88 | 0 | 16640684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16758792 | 16640684 | -118108 | 22228374
5 | T5813 | 44529715201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 12355556 | 12704374 | 12876675 | 348818.33 | 0 | 12872238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12876675 | 12872238 | -4437 | 11348053
5 | T5826 | 45222915201 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-05-22 | 1180815 | 1180815 | 979467 | 0 | 0 | 981703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979467 | 981703 | 2236 | 1609251
5 | T5830 | 44711715201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-08-28 | 5590573 | 5668631 | 5521349 | 78057.63 | 0 | 5521187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5521349 | 5521187 | -162 | 9572296
5 | T5833 | 44708915201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-09-25 | 2100000 | 2100000 | 2001416 | 0 | 0 | 2001416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2001416 | 2001416 | 0 | 2701146
5 | T5835 | 44873915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-10-30 | 3081418 | 3081418 | 3111059 | 0 | 0 | 3112003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3111059 | 3112003 | 944 | 3300432
5 | T5838 | 44761015201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-01-29 | 7714913 | 7714913 | 7712132 | 0 | 0 | 7711973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7712132 | 7711973 | -159 | 9228481
5 | T5845 | 45022725201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-01-29 | 2046788 | 2046788 | 2023608 | 0 | 0 | 2023608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023608 | 2023608 | 0 | 2468960
5 | T5846 | 44879915201 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 1377191 | 1377191 | 1301358 | 0 | 0 | 1301358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301358 | 1301358 | 0 | 1307521
5 | T5856 | 45331815201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-06-11 | 549199 | 549199 | 499315 | 0 | 0 | 499315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499315 | 499315 | 0 | 501263
5 | T5857 | 45613715201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 117123 | 113191 | 103346 | -3931.68 | 0 | 103346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103346 | 103346 | 0 | 180486
5 | T5858 | 45616815201 | F850531344 | PREMIER PAVING LLC | N/A | N/A | N/A | N/A | 2025-03-26 | 948635 | 993577 | 604185 | 44942 | 0 | 604185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604185 | 604185 | 0 | 1621410
5 | T9030 | 44199035223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 5555556 | 5605113 | 5565155 | 49557.59 | 0 | 5565155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5565155 | 5565155 | 0 | 5530000
6 | E6L20 | 25054885201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-05-26 | 28158187 | 28920235 | 27890563 | 762048.51 | 120000 | 27771528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 28010563 | 27771528 | -239034 | 23137913 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | E6M86 | 43351125201 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2021-05-27 | 41366428 | 43068537 | 44950000 | 1702108.31 | 1960000 | 45038064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 160000 | 0 | 1960000 | 1960000 | 46910000 | 45038064 | -1871936 | 33950112 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | E6N17 | 44716515201 | F834649779 | AGI DE MOYA JOINT VENTURE | N/A | N/A | N/A | N/A | 2021-09-13 | 66054600 | 66794016 | 66824078 | 739415.88 | 1200000 | 67046919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 68024078 | 67046919 | -977158 | 34964142 | B5:B5:B5::::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
6 | E6O12 | 44391925201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-25 | 2869869 | 2869869 | 2778313 | 0 | 140000 | 2778250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 140000 | 140000 | 2918313 | 2778250 | -140063 | 2865779 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | E6O17 | 43029169201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-13 | 7237000 | 7269318 | 7237180 | 32318.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7237180 | 0 | -7237180 | 5284477 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6O81 | 44598815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-03-28 | 3370711 | 3853261 | 3033601 | 482549.84 | 120000 | 3032315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 3153601 | 3032315 | -121286 | 3432003 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6O89 | 44480315201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-07-25 | 1776181 | 1776181 | 1798839 | 0 | 0 | 1798839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1798839 | 1798839 | 0 | 2017258
6 | E6P13 | 43029189201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-04-22 | 1315382 | 1315382 | 1284180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284180 | 0 | -1284180 | 1725000 | Y | DESIGN/BUILD PROJECT
6 | E6P23 | 44391115201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-03-28 | 5790735 | 6121430 | 5667306 | 330694.99 | 100000 | 5665707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 5767306 | 5665707 | -101599 | 4862239 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6466 | 43992315201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-28 | 749749 | 750453 | 687268 | 704 | 0 | 687166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687268 | 687166 | -102 | 759571
6 | T6514 | 44462215201 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 12567171 | 13007370 | 12865831 | 440199.87 | 500000 | 12808223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 13365831 | 12808223 | -557608 | 11765757 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6541 | 44390215201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-02-22 | 6112543 | 6196534 | 6055588 | 83991.29 | 0 | 6047700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6055588 | 6047700 | -7887 | 4898503 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6547 | 44392115201 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2023-05-24 | 7844825 | 8071972 | 8026073 | 227147.21 | 200000 | 8025252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 8226073 | 8025252 | -200821 | 8411804 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6555 | 44598715201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2023-04-26 | 15230513 | 15276979 | 14673045 | 46466.35 | 440000 | 14652396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 440000 | 440000 | 15113045 | 14652396 | -460650 | 16721998 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6556 | 44389615201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-05-24 | 12343500 | 12329103 | 12004695 | -14397.46 | 340000 | 12003108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000 | 0 | 0 | 0 | 0 | 0 | 340000 | 340000 | 12344695 | 12003108 | -341587 | 10090244 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6562 | 44393715201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-03-29 | 9816354 | 9816354 | 9814725 | 0 | 320000 | 9792214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 10134725 | 9792214 | -342511 | 10415642 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6564 | 44599515201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2023-12-06 | 2427793 | 2522356 | 2377282 | 94563.1 | 100000 | 2374390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 2477282 | 2374390 | -102891 | 2381685 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6565 | 44389815202 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-02-22 | 17424162 | 17775584 | 17807123 | 351422.16 | 360000 | 17736459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 360000 | 360000 | 18167123 | 17736459 | -430664 | 16704095 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6567 | 44757415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-05-22 | 1669000 | 1695000 | 1692054 | 26000 | 0 | 1691797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1692054 | 1691797 | -258 | 1801028
6 | T6568 | 44393225201 | F832482227 | TRAFFICO LLC | N/A | N/A | N/A | N/A | 2024-08-28 | 1068800 | 1068800 | 1002901 | 0 | 0 | 1002859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1002901 | 1002859 | -41 | 1151283
6 | T6573 | 44599115201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-06 | 7944520 | 7965978 | 7740756 | 21457.87 | 320000 | 7730600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 8060756 | 7730600 | -330157 | 8387399 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6574 | 44780515201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2023-10-25 | 3338573 | 3388573 | 3361643 | 50000 | 100000 | 3354655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 3461643 | 3354655 | -106988 | 3605554 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6575 | 44780615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-01-31 | 4637389 | 4652332 | 4600291 | 14943 | 0 | 4597318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600291 | 4597318 | -2973 | 4247705
6 | T6577 | 44390915201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-24 | 4280927 | 4380927 | 4298470 | 100000 | 180000 | 4296065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 4478470 | 4296065 | -182405 | 4677512 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6580 | 44600015201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-24 | 5947099 | 6376641 | 6242028 | 429541.28 | 0 | 6225782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6242028 | 6225782 | -16246 | 6394669 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6584 | 44391215201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-03-27 | 8558846 | 8890402 | 8748106 | 331555.89 | 220000 | 8742165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 220000 | 220000 | 8968106 | 8742165 | -225941 | 7821851 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6597 | 44936015201 | F843316177 | FLORIDA SIGNAL & LIGHTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-08-28 | 1671710 | 1671710 | 1568639 | 0 | 0 | 1568617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568639 | 1568617 | -22 | 1785608
6 | T6598 | 44780415201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2024-09-25 | 2627713 | 2705308 | 2578007 | 77594.38 | 120000 | 2578006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 2698007 | 2578006 | -120001 | 3026337 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6602 | 44623915201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 3433699 | 3555649 | 3477140 | 121950.01 | 100000 | 3476420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 3577140 | 3476420 | -100720 | 3703880 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6605 | 44389945201 | F843316177 | FLORIDA SIGNAL & LIGHTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-12-04 | 1755688 | 1780688 | 1741502 | 25000 | 200000 | 1741636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 1941502 | 1741636 | -199866 | 1854604 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
7 | E7J46 | 43388015201 | F352566788 | ARCHER WESTERN-DEMOYA JOINT VEN | N/A | N/A | N/A | N/A | 2017-05-25 | 544690000 | 602680022 | 622157034 | 57990021.88 | 2622000 | 628402554 | 0 | 0 | 0 | 0 | 0 | -158000 | -158000 | 2780000 | 0 | 0 | 0 | 0 | 0 | 2780000 | 2622000 | 624779034 | 628402554 | 3623519 | 544690000 | B10:B8:B8 | ACC - BONUS/INCENT/DISINCENT:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
7 | E7N56 | 43726425201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-05-27 | 19975000 | 20432970 | 21351585 | 457969.6 | 0 | 21291797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21351585 | 21291797 | -59788 | 15858300
7 | E7P28 | 44797625201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2022-05-11 | 5133790 | 5136444 | 5160545 | 2653.88 | 0 | 5116597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5160545 | 5116597 | -43948 | 3774700
7 | E7P68 | 41673325201 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2022-12-14 | 15756084 | 16054430 | 16104094 | 298345.56 | 0 | 16029535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16104094 | 16029535 | -74559 | 12965300
7 | E7P77 | 44146315201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-05-10 | 3366760 | 3493112 | 3363518 | 126351.52 | 300000 | 3363518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 3663518 | 3363518 | -300000 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | E7Q08 | 44761515201 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2023-05-10 | 6147921 | 6373747 | 6357061 | 225826.32 | 0 | 6355355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6357061 | 6355355 | -1706 | 5831100
7 | E7Q30 | 44380515201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2024-03-13 | 7234098 | 6536418 | 6778566 | -697680.1 | 0 | 6763361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6778566 | 6763361 | -15205 | 7788450
7 | E7Q31 | 44384115201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2023-12-13 | 1681476 | 1805476 | 1410753 | 124000 | -3398 | 1407355 | -3398 | 0 | 0 | 0 | 0 | 0 | -3398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3398 | 1407355 | 1407355 | 0 | 1673100
7 | E7Q32 | 44383715201 | F830512074 | TITAN CONSTRUCTION MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2025-05-14 | 1728143 | 1728143 | 1516260 | 0 | 0 | 1516260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1516260 | 1516260 | 0 | 1889730
7 | E7Q39 | 44582815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-02-14 | 1714027 | 1714027 | 1704720 | 0 | 0 | 1704720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1704720 | 1704720 | 0 | 3483914
7 | E7Q53 | 44583015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-05-08 | 1599000 | 1601196 | 1343560 | 2195.84 | 0 | 1343560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343560 | 1343560 | 0 | 1936163
7 | E7Q55 | 44165115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-03-13 | 4066019 | 4201769 | 4164473 | 135750.09 | 0 | 4159743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4164473 | 4159743 | -4730 | 4234476
7 | E7Q75 | 45288915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-06-12 | 1296714 | 1381899 | 1384246 | 85184.94 | 0 | 1384246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384246 | 1384246 | 0 | 1695805
7 | E7Q85 | 44349225201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-01-08 | 576543 | 576543 | 519908 | 0 | 0 | 519908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519908 | 519908 | 0 | 536030
7 | E7Q94 | 45273615201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-12-11 | 259111 | 259111 | 235124 | 0 | 0 | 235124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235124 | 235124 | 0 | 516283
7 | E7R15 | 44138815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-29 | 21358193 | 21288752 | 21393187 | -69440.22 | 1150000 | 21918008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 1150000 | 1150000 | 22543187 | 21918008 | -625179 | 26431774 | A3:A3:A3:B10 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT
7 | E7R21 | 42451335201 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2021-05-20 | 81649200 | 89787672 | 91076513 | 8138472.09 | 0 | 91676950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91076513 | 91676950 | 600437 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7R22 | 44344535201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2022-05-27 | 29193066 | 28668231 | 28534082 | -524835.43 | 0 | 28534082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28534082 | 28534082 | 0 | 22376200
7 | E7R24 | 44132015201 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2022-08-04 | 6997500 | 7112720 | 7042786 | 115219.68 | 0 | 7042581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7042786 | 7042581 | -205 | 13119000
7 | E7R26 | 42925115201 | F871503473 | PRINCE-AJAX DDI JV | N/A | N/A | N/A | N/A | 2021-06-17 | 89691574 | 96531643 | 97484006 | 6840069.17 | -45000 | 98162236 | 0 | 0 | 0 | 0 | 0 | -45000 | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45000 | 97439006 | 98162236 | 723230 | 100030998 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7R35 | 43983215201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-25 | 10158800 | 10244736 | 10281972 | 85935.86 | 0 | 10278335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10281972 | 10278335 | -3637 | 12981331 | LBDB:LBDB | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD
7 | E7R40 | 44335825201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-03-07 | 1322000 | 1334250 | 1257998 | 12249.84 | 0 | 1253861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1257998 | 1253861 | -4137 | 1543770 | LBDB | LOW BID DESIGN BUILD
7 | E7U08 | 44366515201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-09-11 | 3709156 | 3709156 | 3454248 | 0 | 0 | 3454248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3454248 | 3454248 | 0 | 3944855
7 | T7388 | 41656125201 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2017-05-24 | 42444444 | 42657075 | 42372225 | 212630.21 | -1680946 | 43898009 | -1680946 | 0 | 0 | 0 | 0 | 0 | -1680946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1680946 | 40691279 | 43898009 | 3206730 | 46455035 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | T7396 | 41673245201 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2019-07-31 | 55832153 | 56499915 | 56400689 | 667762.03 | 875160 | 56882314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875160 | 0 | 0 | 0 | 0 | 0 | 875160 | 875160 | 57275849 | 56882314 | -393534 | 63202968 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
7 | T7412 | 43057315201 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2018-06-13 | 32988889 | 34384864 | 34806705 | 1395975.45 | -1228315 | 34791621 | -1168315 | 0 | 0 | 0 | 0 | -60000 | -1228315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1228315 | 33578390 | 34791621 | 1213232 | 37580000
7 | T7433 | 25632315201 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2019-06-12 | 49694444 | 52738117 | 53453750 | 3043672.49 | -247450 | 54900781 | -247450 | 0 | 0 | 0 | 0 | 0 | -247450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -247450 | 53206300 | 54900781 | 1694481 | 58098404
7 | T7445 | 43751415201 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2020-06-10 | 19998889 | 21060736 | 21831416 | 1061847.29 | -1055507 | 21019250 | -1055507 | 0 | 0 | 0 | 0 | 0 | -1055507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1055507 | 20775909 | 21019250 | 243341 | 21050900
7 | T7460 | 43604115201 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2021-01-27 | 3677251 | 4044013 | 3876014 | 366761.55 | -317217 | 3641859 | -317217 | 0 | 0 | 0 | 0 | 0 | -317217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -317217 | 3558797 | 3641859 | 83063 | 3523200
7 | T7462 | 25716535201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 21597899 | 21520785 | 21184572 | -77114.2 | 0 | 21182804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21184572 | 21182804 | -1767 | 20111600
7 | T7471 | 44138715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 25596637 | 26257328 | 26136613 | 660691.2 | 0 | 27502951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26136613 | 27502951 | 1366338 | 27251800
7 | T7472 | 43182125201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2021-05-26 | 85239705 | 94443373 | 97569383 | 9203668.27 | 0 | 97817624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97569383 | 97817624 | 248241 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE
7 | T7478 | 44024615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 23033560 | 24126786 | 23743700 | 1093226.08 | 0 | 23395970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23743700 | 23395970 | -347730 | 23181900
7 | T7493 | 44538015201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-01-25 | 35735836 | 37879264 | 40425341 | 2143427.72 | -36000 | 40012496 | 0 | 0 | 0 | 0 | 0 | -36000 | -36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36000 | 40389341 | 40012496 | -376846 | 37724100
7 | T7505 | 44166115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-05-24 | 13856415 | 13819912 | 13656236 | -36503.46 | 0 | 13654130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13656236 | 13654130 | -2106 | 14165000
7 | T7507 | 44600915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2023-05-17 | 22407724 | 24195428 | 26279346 | 1787704.03 | -10000 | 26267268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | -10000 | 26269346 | 26267268 | -2078 | 23830100
7 | T7509 | 44588615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 8085082 | 8115381 | 7967342 | 30299.15 | 0 | 7993474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7967342 | 7993474 | 26132 | 9550800
7 | T7511 | 44378415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-05-17 | 12651040 | 13441313 | 13767680 | 790272.74 | 0 | 13764702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13767680 | 13764702 | -2978 | 12701400
7 | T7512 | 44334715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-06-14 | 6290573 | 6754957 | 7072599 | 464384.48 | 0 | 7072474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7072599 | 7072474 | -125 | 6135700
7 | T7513 | 44985215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-11-15 | 2131372 | 2126382 | 2055081 | -4989.82 | 0 | 2053373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055081 | 2053373 | -1708 | 1928410
7 | T7514 | 45069315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-27 | 2469300 | 2490043 | 2487609 | 20743.16 | 0 | 2486604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487609 | 2486604 | -1005 | 2285000
7 | T7515 | 44803615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-06-14 | 13134873 | 13851674 | 14146391 | 716801.05 | 0 | 14143062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14146391 | 14143062 | -3329 | 13139100
7 | T7516 | 44006315201 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2023-06-14 | 6730280 | 6779810 | 6697913 | 49529.32 | 0 | 6699170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6697913 | 6699170 | 1257 | 7050800
7 | T7522 | 44627015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-06-12 | 8109258 | 8171451 | 8246645 | 62193.33 | 0 | 8245347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8246645 | 8245347 | -1298 | 11954146
7 | T7523 | 44697315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-25 | 2049777 | 2049777 | 2101379 | 0 | 0 | 2098362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101379 | 2098362 | -3017 | 2385840
7 | T7524 | 44795215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-10-30 | 5431188 | 5431188 | 5567862 | 0 | 0 | 5571064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5567862 | 5571064 | 3202 | 6061975
7 | T7527 | 44363015201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2023-12-06 | 22643400 | 24315347 | 26274401 | 1671947.49 | 0 | 26272509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26274401 | 26272509 | -1893 | 25187500
7 | T7529 | 44109835201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-03-27 | 1336107 | 1336107 | 1267198 | 0 | 0 | 1266909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267198 | 1266909 | -289 | 1581132
7 | T7530 | 44753515201 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2024-05-22 | 9184009 | 9285334 | 9327564 | 101324.52 | 0 | 9325285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9327564 | 9325285 | -2279 | 7458238
7 | T7536 | 44795415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-11-13 | 5776172 | 5745538 | 5802044 | -30634.09 | 0 | 5802824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5802044 | 5802824 | 780 | 7545892
7 | T7538 | 44939815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-05-15 | 545691 | 545691 | 518518 | 0 | 0 | 518518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518518 | 518518 | 0 | 611133
7 | T7539 | 45287715201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-05-22 | 1109387 | 1066722 | 1024280 | -42665.3 | 0 | 1024198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024280 | 1024198 | -82 | 1253844
7 | T7543 | 44795315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-02-26 | 6298614 | 6383875 | 6186613 | 85261.69 | 0 | 6186612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6186613 | 6186612 | 0 | 9649905
7 | T7544 | 44025015201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2024-04-17 | 7475300 | 7428809 | 7644411 | -46491.53 | 0 | 7629621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7644411 | 7629621 | -14790 | 8386992
7 | T7548 | 44752215201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2024-05-15 | 2173906 | 2247825 | 2217265 | 73919.24 | 0 | 2216464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2217265 | 2216464 | -801 | 1912820
7 | T7550 | 45241215201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-05-15 | 654321 | 654321 | 610593 | 0 | 0 | 610593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610593 | 610593 | 0 | 826944
7 | T7555 | 44794815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-02-26 | 5942087 | 5942922 | 5968673 | 835.12 | 0 | 5968280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5968673 | 5968280 | -393 | 7672150
7 | T7570 | 45097015201 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2025-03-26 | 643597 | 643597 | 574357 | 0 | -28645 | 545712 | -28645 | 0 | 0 | 0 | 0 | 0 | -28645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28645 | 545712 | 545712 | 0 | 761694
8 | E8R45 | 43799215201 | F825435435 | CENTRAL MORRISON COBALT JV | N/A | N/A | N/A | N/A | 2018-11-15 | 33928239 | 47651600 | 47969861 | 13723361.4 | 0 | 47904732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47969861 | 47904732 | -65129 | 41184698
8 | E8S51 | 44085715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-12-15 | 31637485 | 32856515 | 36211711 | 1219030.2 | -26500 | 37017332 | 0 | 0 | 0 | 0 | 0 | -26500 | -26500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26500 | 36185211 | 37017332 | 832121 | 32721169
8 | E8T48 | 43496835201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2022-04-19 | 10781928 | 10718856 | 10512572 | -63072.39 | 0 | 10512572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10512572 | 10512572 | 0 | 11904889 | A3 | ICC - DESIGN/BUILD - MINOR
8 | E8T83 | 44276415201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2022-09-20 | 102999958 | 103423210 | 104129622 | 423252.32 | 4744548 | 102654085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4744548 | 0 | 0 | 0 | 0 | 0 | 4744548 | 4744548 | 108874170 | 102654085 | -6220085 | 121233962 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8U04 | 44602415201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-03-21 | 16184460 | 17190583 | 16458548 | 1006122.94 | 0 | 16411881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16458548 | 16411881 | -46667 | 18390077
8 | E8U19 | 44588515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-04-11 | 11226810 | 11263007 | 11344464 | 36197.44 | 0 | 11339363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11344464 | 11339363 | -5101 | 11461891
8 | E8U32 | 44925335201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2023-05-09 | 3649071 | 3673424 | 3464348 | 24353 | 0 | 3464348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3464348 | 3464348 | 0 | 4370418
8 | E8U46 | 43854815201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-05-14 | 4734726 | 4734726 | 4628034 | 0 | 0 | 4628034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4628034 | 4628034 | 0 | 8236620
8 | E8U56 | 44942325201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2023-08-22 | 1804313 | 1864511 | 1827419 | 60197.92 | 37398 | 1827419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37398 | 0 | 0 | 0 | 0 | 0 | 37398 | 37398 | 1864817 | 1827419 | -37398 | 1786238 | A6 | ICC - BAM/INCENTIVE-DISINCENT
8 | E8U67 | 44440215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-12 | 24889345 | 25770345 | 25416917 | 880999.92 | 0 | 25287822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25416917 | 25287822 | -129095 | 27205818
8 | E8U70 | 44287615201 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2024-04-09 | 19498886 | 19784427 | 18004526 | 285540.7 | 0 | 18003824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18004526 | 18003824 | -702 | 20898608
8 | E8U71 | 41592755201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2024-02-13 | 2794276 | 2537251 | 2444066 | -257025.06 | 0 | 2444066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2444066 | 2444066 | 0 | 6003502
8 | E8U73 | 44206215201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-03-12 | 13684469 | 13793245 | 13317036 | 108776.05 | 0 | 13293015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13317036 | 13293015 | -24020 | 19932483
8 | E8U75 | 41713255201 | F811876890 | CONTINENTAL HEAVY CIVIL CORP. | N/A | N/A | N/A | N/A | 2024-06-11 | 30846591 | 31566656 | 33098541 | 720065.67 | 1149704 | 33093920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149704 | 0 | 0 | 0 | 0 | 0 | 1149704 | 1149704 | 34248245 | 33093920 | -1154325 | 46198158 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8U91 | 44917545201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-06-11 | 4804962 | 4908714 | 4813444 | 103751.34 | 0 | 4812923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4813444 | 4812923 | -521 | 4334608
8 | E8U95 | 44917535201 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2024-04-09 | 1605678 | 1605678 | 1663792 | 0 | 0 | 1663792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663792 | 1663792 | 0 | 1739460
8 | E8V77 | 45211115201 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-02-19 | 1699787 | 1699787 | 1444210 | 0 | 0 | 1444159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1444210 | 1444159 | -52 | 1780237

## Sheet1 (hidden)
01CO | 01 | T1754 | 41924345201 | 2020-06-10 | QTR4 | 19/20 | 1 | 8 | 1300 | 1542 | 1316 | 226 | 0 | 0 | 242 | 0 | 44711727 | 150000 | 44561727 | 45332170 | 44869139 | 0 | 0 | 0 | 44869139 | 45508351 | 2409623 | 620443 | 176 | 0 | 0 | 75074 | 0 | 0 | 0 | 369025 | 70927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65721 | 0 | 0 | 0 | 2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656851 | 70927 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2024-04-12 | QTR4 | 23/24 | 118 | 49671695.98 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | CO | 25 | 01co | 1 | 25
01CO | 01 | T1778 | 43805915201 | 2021-02-17 | QTR3 | 20/21 | 2 | 5 | 300 | 703 | 703 | 0 | 0 | 0 | 326 | 77 | 5124974 | 52558 | 5072416 | 5379131 | 5343032 | 0 | 0 | 0 | 5343032 | 5363673 | 399077 | 254157 | 241 | 0 | 0 | 44765 | 0 | 39 | 77 | 114092 | 58884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 113116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 77 | 261703 | 58884 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-06-09 | QTR4 | 25/26 |  | 2023-11-08 | QTR2 | 23/24 | 113 | 5113819.4 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO | 32 | 01do | 26 | 57
01CO | 01 | T1801 | 43355055201 | 2022-02-23 | QTR3 | 21/22 | 4 | 11 | 450 | 785 | 785 | 0 | 0 | 0 | 157 | 178 | 9943982 | 61935 | 9882047 | 10795145 | 10516274 | 0 | 0 | 0 | 10516274 | 10451415 | 22951 | 851163 | 75 | 0 | 10 | 59915 | 0 | 14 | 35 | 107389 | 65872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 0 | 0 | 60900 | 0 | 0 | 0 | 314 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 15101 | 0 | 0 | 0 | 0 | 0 | 10 | 133 | 534836 | 45203 | 0 | 0 | 0 | 0 | 27 | 178 | 784204 | 111075 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2026-01-26 | QTR3 | 25/26 |  | 2024-12-23 | QTR2 | 24/25 | 115 | 8613987.04 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | CO | 60 | 02co | 58 | 117
01CO | 01 | T1807 | 44464115201 | 2023-05-24 | QTR4 | 22/23 | 2 | 8 | 250 | 356 | 355 | 1 | 0 | 0 | 95 | 11 | 5486544 | 50000 | 5436544 | 5582663 | 5697293 | -30000 | 0 | -30000 | 5667293 | 5634025 | -212 | 96120 | 56 | 21 | 11 | 58440 | 0 | 0 | 0 | 8260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 1490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 11 | 77189 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-18 | QTR3 | 25/26 |  | 2025-04-21 | QTR4 | 24/25 | 118 | 4275732.4 |  |  | 2 | 18 | 0 | 0 | 0 | 0 |  | CO | 10 | 02do | 118 | 127
01CO | 01 | T1833 | 44634515201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 300 | 472 | 471 | 1 | 0 | 0 | 172 | 0 | 16756829 | 150000 | 16606829 | 16756829 | 16918647 | 0 | -70500 | -70500 | 16848147 | 16748453 | -99694 | 0 | 136 | 0 | 0 | 23670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100171 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2023-12-05 | QTR2 | 23/24 | 106 | 17387334.58 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO | 37 | 03co | 128 | 164
01CO | 01 | T1843 | 43695525201 | 2022-07-27 | QTR1 | 22/23 | 1 | 6 | 225 | 443 | 443 | 0 | 0 | 0 | 201 | 17 | 4165582 | 50000 | 4115582 | 4197230 | 4319692 | 0 | 0 | 0 | 4319692 | 4254744 | -56953 | 31648 | 155 | 0 | 17 | 23652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 23652 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-08-27 | QTR1 | 25/26 |  | 2025-01-17 | QTR3 | 24/25 | 113 | 3563244.72 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO | 32 | 03do | 165 | 196
01CO | 01 | T1850 | 43944115201 | 2024-04-24 | QTR4 | 23/24 | 1 | 4 | 400 | 457 | 457 | 0 | 0 | 0 | 57 | 0 | 5279314 | 0 | 5279314 | 5778359 | 5716286 | 0 | 0 | 0 | 5716286 | 5630083 | -2290 | 499045 | 41 | 0 | 0 | 149726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349371 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-10-28 | QTR2 | 25/26 | 108 | 7929522.13 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 28 | 04co | 197 | 224
01CO | 01 | T1852 | 44787215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 0 | 175 | 207 | 204 | 3 | 0 | 0 | 32 | 0 | 3084175 | 50000 | 3034175 | 3084175 | 3074445 | 0 | 0 | 0 | 3074445 | 3073651 | -795 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 115 | 2364265.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 26 | 04do | 225 | 250
01CO | 01 | T1854 | 44480735201 | 2024-03-27 | QTR3 | 23/24 | 1 | 1 | 125 | 192 | 182 | 10 | 0 | 0 | 47 | 20 | 1273662 | 46380 | 1227282 | 1300460 | 1232804 | 0 | -22000 | -22000 | 1210804 | 1210162 | -642 | 26799 | 27 | 0 | 20 | 26799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 26799 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 115 | 1109604.92 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO | 37 | 05co | 251 | 287
01CO | 01 | T1855 | 44547315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 5 | 300 | 577 | 607 | -30 | 30 | 0 | 176 | 101 | 11238774 | 116686 | 11122088 | 11323365 | 11568463 | -143070 | 0 | -143070 | 11425393 | 11375607 | -39102 | 84591 | 129 | 0 | 0 | 107185 | 0 | 0 | 101 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 114493 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 118 | 12534705.29 |  |  | 0 | 47 | 0 | 0 | 0 | 0 | T | CO | 39 | 05do | 288 | 326
01CO | 01 | T1861 | 44044815201 | 2023-06-14 | QTR4 | 22/23 | 1 | 3 | 322 | 635 | 633 | 2 | 0 | 0 | 306 | 7 | 12860870 | 130308 | 12730562 | 12904011 | 13130189 | 0 | 0 | 0 | 13130189 | 12994186 | -171 | 43141 | 71 | 4 | 7 | 0 | 0 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201 | 7 | -92690 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-06-09 | QTR4 | 25/26 |  | 2025-08-20 | QTR1 | 25/26 | 115 | 12102054.04 |  |  | 7 | 34 | 0 | 0 | -92690 | 0 |  | CO | 21 | 06co | 327 | 347
01CO | 01 | T1866 | 43903215201 | 2023-11-15 | QTR2 | 23/24 | 2 | 4 | 225 | 301 | 330 | -29 | 29 | 0 | 65 | 11 | 3945642 | 68014 | 3877628 | 4078353 | 4013289 | -76850 | 0 | -76850 | 3936439 | 3832582 | -14467 | 132711 | 40 | 0 | 9 | 43321 | 0 | 0 | 2 | 1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 45054 | 0 | F201524169 | MJC LAND DEVELOPMENT LLC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-03-20 | QTR3 | 24/25 | 118 | 5005578.39 |  |  | 2 | 25 | 0 | 0 | 0 | 0 |  | CO | 9 | 06do | 348 | 356
01CO | 01 | T1867 | 44546715201 | 2024-01-31 | QTR3 | 23/24 | 2 | 4 | 250 | 361 | 352 | 9 | 0 | 0 | 83 | 28 | 7502026 | 73856 | 7428170 | 8082796 | 8181304 | 0 | 0 | 0 | 8181304 | 8176865 | -4440 | 580770 | 30 | 25 | 9 | 370939 | 0 | 3 | 0 | 23365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 201258 | 0 | 0 | 0 | 12662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 608224 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-02-11 | QTR3 | 25/26 |  | 2025-11-21 | QTR2 | 25/26 | 108 | 7936833.12 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 35 | 07co | 357 | 391
01CO | 01 | T1868 | 44740215201 | 2024-02-28 | QTR3 | 23/24 | 1 | 2 | 100 | 207 | 206 | 1 | 0 | 0 | 107 | 0 | 1036497 | 45938 | 990559 | 1074999 | 1074468 | 0 | 0 | 0 | 1074468 | 1035967 | 0 | 38502 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 115 | 1164568.56 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 23 | 07do | 392 | 414
01CO | 01 | T1873 | 44788015201 | 2024-02-28 | QTR3 | 23/24 | 2 | 3 | 200 | 287 | 285 | 2 | 0 | 0 | 87 | 0 | 2902791 | 50000 | 2852791 | 2941983 | 2705963 | 0 | 0 | 0 | 2705963 | 2704866 | -1098 | 39192 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 65279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65279 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-02-02 | QTR3 | 25/26 |  | 2025-11-07 | QTR2 | 25/26 | 113 | 2895926.83 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 415 | 414
01CO | 01 | T1874 | 43583015201 | 2024-08-28 | QTR1 | 24/25 | 1 | 1 | 250 | 271 | 271 | 0 | 0 | 0 | 21 | 0 | 2777889 | 0 | 2777889 | 2778854 | 2820140 | 0 | 0 | 0 | 2820140 | 2820008 | -133 | 965 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965 | 0 | F592163377 | THOMAS MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-04-08 | QTR4 | 25/26 |  | 2025-10-03 | QTR2 | 25/26 | 118 | 3495664.49 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO | 17 | 08do | 415 | 431
01CO | 01 | T1881 | 43802715201 | 2023-11-15 | QTR2 | 23/24 | 2 | 1 | 200 | 310 | 310 | 0 | 0 | 0 | 94 | 16 | 6196035 | 68350 | 6127685 | 6206737 | 6556044 | 0 | 0 | 0 | 6556044 | 6524950 | -31093 | 10701 | 70 | 0 | 16 | 12210 | 0 | 0 | 0 | 19772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 31982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-04-02 | QTR4 | 24/25 | 108 | 6886950.71 |  |  | 16 | 24 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1885 | 44629115201 | 2024-01-31 | QTR3 | 23/24 | 3 | 0 | 250 | 467 | 466 | 1 | 0 | 0 | 215 | 2 | 11193872 | 99929 | 11093943 | 11193872 | 11344239 | 0 | 0 | 0 | 11344239 | 11335446 | -8793 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 2 | 12403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 2 | 12403 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-21 | QTR4 | 25/26 |  | 2025-12-05 | QTR2 | 25/26 | 113 | 10309689.64 |  |  | 2 | 35 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1889 | 44431315201 | 2024-03-27 | QTR3 | 23/24 | 2 | 1 | 200 | 346 | 346 | 0 | 0 | 0 | 116 | 30 | 2636284 | 50000 | 2586284 | 2666046 | 2714680 | -3800 | 0 | -3800 | 2710880 | 2705941 | -4939 | 29762 | 88 | 0 | 0 | 6254 | 0 | 0 | 0 | 60445 | 15459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 66698 | 15459 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-27 | QTR3 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 108 | 3253356.71 |  |  | 30 | 28 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1891 | 44743625201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 175 | 235 | 235 | 0 | 0 | 0 | 39 | 21 | 4742624 | 50000 | 4692624 | 4787027 | 4779994 | 0 | 0 | 0 | 4779994 | 4777172 | -2822 | 44403 | 18 | 0 | 0 | 0 | 0 | 0 | 21 | 50051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -585 | 0 | 0 | 0 | 13168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 62635 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-10 | QTR2 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 108 | 4605369.8 |  |  | 19 | 21 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1895 | 44656015201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 125 | 169 | 169 | 0 | 0 | 0 | 20 | 24 | 1414901 | 0 | 1414901 | 1450512 | 1460078 | 0 | 0 | 0 | 1460078 | 1460017 | -61 | 35611 | 16 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 35611 | 35611 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-07-28 | QTR1 | 25/26 | 108 | 1992638.1 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1901 | 44893615201 | 2024-08-28 | QTR1 | 24/25 | 1 | 1 | 300 | 380 | 380 | 0 | 0 | 0 | 80 | 0 | 9549741 | 116136 | 9433605 | 9400063 | 9512022 | 0 | 0 | 0 | 9512022 | 9509899 | -2123 | -149678 | 13 | 30 | 0 | -176994 | 0 | 0 | 0 | 92911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | -84083 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-04-09 | QTR4 | 25/26 |  | 2026-01-27 | QTR3 | 25/26 | 118 | 10149489.54 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1905 | 44645215201 | 2025-01-29 | QTR3 | 24/25 | 1 | 1 | 100 | 144 | 144 | 0 | 0 | 0 | 34 | 10 | 574929 | 0 | 574929 | 574929 | 554144 | 0 | 0 | 0 | 554144 | 554144 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-02-02 | QTR3 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 108 | 670642.47 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1907 | 45240815201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 130 | 187 | 187 | 0 | 0 | 0 | 57 | 0 | 714571 | 34195 | 680376 | 714571 | 686286 | 0 | 0 | 0 | 686286 | 686286 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC. | N/A | N/A | N/A | N/A | 2026-05-13 | QTR4 | 25/26 |  | 2026-02-13 | QTR3 | 25/26 | 115 | 685303.86 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1927 | 44477325201 | 2025-07-30 | QTR1 | 25/26 | 1 | 0 | 100 | 116 | 115 | 1 | 0 | 0 | 16 | 0 | 414963 | 0 | 414963 | 414963 | 422033 | 0 | 0 | 0 | 422033 | 422033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F851678853 | GARCIA CIVIL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2026-02-12 | QTR3 | 25/26 | 118 | 496784.63 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1R76 | 20121535201 | 2020-05-29 | QTR4 | 19/20 | 1 | 5 | 1050 | 1489 | 1488 | 1 | 0 | 0 | 365 | 74 | 70460520 | 150000 | 70310520 | 71635236 | 71638136 | -100000 | 0 | -100000 | 71538136 | 74769243 | 5571562 | 1174716 | 264 | 0 | 0 | 60435 | 0 | 0 | 74 | 916285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 314762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 74 | 1301779 | 0 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-10-20 | QTR2 | 25/26 |  | 2024-09-12 | QTR1 | 24/25 | 108 | 57230747.75 | Y | DESIGN/BUILD PROJECT | 0 | 101 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1R87 | 20103255201 | 2020-11-20 | QTR2 | 20/21 | 3 | 19 | 1400 | 1699 | 1699 | 0 | 0 | 0 | 265 | 34 | 143923300 | 150000 | 143773300 | 144607218 | 144885088 | -40000 | 0 | -40000 | 144845088 | 145590108 | 12782288 | 683918 | 199 | 0 | 0 | 857947 | 17389 | 0 | 0 | 113457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1718413 | 0 | 0 | 0 | 24827 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 569484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5985 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | -192910 | 17389 | F843374080 | AJAX-LEWARE JV | N/A | N/A | N/A | N/A | 2026-01-23 | QTR3 | 25/26 |  | 2025-10-25 | QTR2 | 25/26 | 106 | 132713200.45 | B11:B7:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - A+B/BONUS:ACC - DESIGN/BUILD - MAJOR | 0 | 100 | 0 | 0 | -46196 | 0 |  | DO
01DO | 01 | E1U56 | 44400825201 | 2022-02-17 | QTR3 | 21/22 | 1 | 20 | 500 | 1032 | 1032 | 0 | 0 | 0 | 418 | 114 | 40877774 | 150000 | 40727774 | 43600530 | 44711094 | 0 | 0 | 0 | 44711094 | 45889241 | 1184557 | 2722756 | 343 | 0 | 0 | 295612 | 3520 | 0 | 0 | 156058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 2270096 | 0 | 0 | 0 | 156484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 2831872 | 3520 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2026-06-15 | QTR4 | 25/26 |  | 2025-04-02 | QTR4 | 24/25 | 113 | 46748207.92 |  |  | 0 | 75 | 0 | 0 | -52787 | 0 |  | DO
01DO | 01 | E1V05 | 44400835201 | 2022-07-21 | QTR1 | 22/23 | 1 | 12 | 350 | 697 | 697 | 0 | 0 | 0 | 296 | 51 | 22180000 | 150000 | 22030000 | 22731000 | 22373423 | 0 | 0 | 0 | 22373423 | 21651639 | -721784 | 701000 | 237 | 0 | 0 | 169783 | 0 | 16 | 30 | 431865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66138 | 0 | 0 | 21 | 14304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 51 | 682090 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-06-08 | QTR4 | 25/26 |  | 2024-12-26 | QTR2 | 24/25 | 113 | 27316502.46 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V08 | 19602265201 | 2023-11-02 | QTR2 | 23/24 | 2 | 3 | 350 | 424 | 375 | 49 | 0 | 0 | 74 | 0 | 6226258 | 61298 | 6164960 | 6296806 | 6274547 | 0 | 0 | 0 | 6274547 | 6215664 | -10506 | 70548 | 51 | 0 | 0 | 45061 | 0 | 0 | 0 | 3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48763 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 115 | 7418503.78 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V09 | 44743215201 | 2024-02-15 | QTR3 | 23/24 | 2 | 0 | 190 | 250 | 249 | 1 | 0 | 0 | 60 | 0 | 3665572 | 50000 | 3615572 | 3665572 | 3704260 | 0 | 0 | 0 | 3704260 | 3693129 | -11132 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 12979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 11006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24749 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 108 | 4198565.92 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V10 | 44155015201 | 2023-02-16 | QTR3 | 22/23 | 1 | 5 | 300 | 551 | 561 | -10 | 10 | 0 | 205 | 46 | 14609258 | 150000 | 14459258 | 14044029 | 14088333 | -3245 | 0 | -3245 | 14085087 | 13929541 | -126080 | -565229 | 188 | 0 | 0 | -627778 | 0 | 0 | 21 | 85849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -541929 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-19 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 115 | 14926349.94 |  |  | 21 | 42 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V12 | 43488625201 | 2023-05-18 | QTR4 | 22/23 | 6 | 11 | 700 | 782 | 627 | 155 | 0 | 0 | 82 | 0 | 18975000 | 150000 | 18825000 | 19595912 | 19771279 | 0 | 0 | 0 | 19771279 | 19695292 | -1753 | 620912 | 41 | -38 | 0 | 520753 | 0 | 0 | 0 | 75968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38 | 0 | 596721 | 0 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-05-11 | QTR4 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 108 | 18481181.07 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V13 | 44893915201 | 2024-09-19 | QTR1 | 24/25 | 1 | 1 | 150 | 195 | 194 | 1 | 0 | 0 | 45 | 0 | 5289078 | 65023 | 5224055 | 5392842 | 5545592 | 0 | 0 | 0 | 5545592 | 5545735 | 143 | 103763 | 8 | 0 | 0 | 103763 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 103763 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-25 | QTR1 | 25/26 |  | 2025-06-07 | QTR4 | 24/25 | 118 | 5760651.93 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V22 | 44620615201 | 2023-07-20 | QTR1 | 23/24 | 1 | 3 | 180 | 227 | 220 | 7 | 0 | 0 | 47 | 0 | 5142423 | 50000 | 5092423 | 5047658 | 5138834 | 0 | 0 | 0 | 5138834 | 5099867 | -1029 | -94765 | 25 | 0 | 0 | 44761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -87943 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-05 | QTR3 | 24/25 | 118 | 4496918.22 |  |  | 0 | 22 | 0 | 0 | -132703 | 0 |  | DO
01DO | 01 | E1V23 | 44743415201 | 2023-07-20 | QTR1 | 23/24 | 1 | 1 | 225 | 278 | 278 | 0 | 0 | 0 | 53 | 0 | 5558710 | 57494 | 5501216 | 5552034 | 5723019 | 0 | 0 | 0 | 5723019 | 5723218 | 199 | -6676 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | -6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4873 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-01 | QTR1 | 25/26 |  | 2024-10-23 | QTR2 | 24/25 | 108 | 5765208.01 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V51 | 44743715201 | 2022-08-02 | QTR1 | 22/23 | 3 | 3 | 650 | 763 | 763 | 0 | 0 | 0 | 113 | 0 | 23141400 | 150000 | 22991400 | 23931467 | 24545579 | 0 | 0 | 0 | 24545579 | 24060306 | -480611 | 790067 | 61 | 0 | 0 | 53994 | 0 | 0 | 0 | 770405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824400 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-07-21 | QTR1 | 25/26 |  | 2024-11-12 | QTR2 | 24/25 | 108 | 26691037.4 | A3:LBDB:Y | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 52 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V60 | 44901515201 | 2023-06-06 | QTR4 | 22/23 | 1 | 4 | 975 | 1035 | 559 | 476 | 0 | 0 | 60 | 0 | 24655000 | 150000 | 24505000 | 24840707 | 24676932 | 0 | 941500 | 941500 | 25618432 | 24522979 | -950274 | 185707 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 40527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51851 | 0 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2025-02-18 | QTR3 | 24/25 | 113 | 27242569.81 | B2:B5:Y | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:DESIGN/BUILD PROJECT | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W11 | 45088215201 | 2025-10-16 | QTR2 | 25/26 | 1 | 0 | 80 | 82 | 49 | 33 | 0 | 0 | 2 | 0 | 1286987 | 50000 | 1236987 | 1286987 | 1219611 | 0 | 0 | 0 | 1219611 | 1218601 | -1009 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-06-22 | QTR4 | 25/26 |  | 2026-03-19 | QTR3 | 25/26 | 108 | 1583531 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W13 | 44594215201 | 2024-02-15 | QTR3 | 23/24 | 1 | 10 | 200 | 292 | 317 | -25 | 25 | 0 | 66 | 26 | 2428636 | 0 | 2428636 | 2626766 | 2708707 | -66250 | 0 | -66250 | 2642457 | 2624968 | -22 | 198130 | 44 | 0 | 26 | 115608 | 0 | 0 | 0 | 65054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 180662 | 0 | F391867552 | DRAX INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-04-22 | QTR4 | 24/25 | 115 | 3681296.02 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W16 | 44738015201 | 2023-09-21 | QTR1 | 23/24 | 1 | 5 | 200 | 302 | 296 | 6 | 0 | 0 | 58 | 44 | 2844972 | 50000 | 2794972 | 2870813 | 2826404 | 0 | 0 | 0 | 2826404 | 2806626 | -7691 | 25841 | 81 | 0 | 0 | 8709 | 0 | 0 | 0 | 5045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13754 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2026-03-18 | QTR3 | 25/26 |  | 2025-01-21 | QTR3 | 24/25 | 115 | 2548367.85 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W18 | 44743115201 | 2024-04-18 | QTR4 | 23/24 | 1 | 1 | 170 | 195 | 171 | 24 | 0 | 0 | 25 | 0 | 2506911 | 50000 | 2456911 | 2530764 | 2550717 | 0 | 0 | 0 | 2550717 | 2546483 | -4233 | 23853 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | 0 | 0 | 0 | 0 | 0 | 0 | 23853 | 23853 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 |  | 2025-04-30 | QTR4 | 24/25 | 108 | 2727222.68 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W50 | 45279215201 | 2024-03-26 | QTR3 | 23/24 | 1 | 0 | 450 | 511 | 495 | 16 | 0 | 0 | 57 | 4 | 2283584 | 50000 | 2233584 | 2283584 | 2253806 | 0 | 0 | 0 | 2253806 | 2253543 | -264 | 0 | 24 | 0 | 4 | 25861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25861 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 |  | 2025-09-29 | QTR1 | 25/26 | 118 | 2780605.35 | Y | DESIGN/BUILD PROJECT | 4 | 33 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W75 | 44923315201 | 2024-07-18 | QTR1 | 24/25 | 1 | 0 | 115 | 150 | 150 | 0 | 0 | 0 | 35 | 0 | 2560003 | 50000 | 2510003 | 2560003 | 2586788 | 0 | 0 | 0 | 2586788 | 2586788 | 0 | 0 | 32 | 0 | 0 | 29053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29053 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 |  | 2025-06-04 | QTR4 | 24/25 | 108 | 3481659.24 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W76 | 44897215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 0 | 140 | 166 | 150 | 16 | 0 | 0 | 26 | 0 | 3352588 | 50000 | 3302588 | 3352588 | 3378389 | 0 | 0 | 0 | 3378389 | 3377632 | -757 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-04-10 | QTR4 | 24/25 | 118 | 4285958.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W78 | 44927215201 | 2024-08-15 | QTR1 | 24/25 | 1 | 1 | 100 | 127 | 110 | 17 | 0 | 0 | 27 | 0 | 1562427 | 50000 | 1512427 | 1562023 | 1597413 | 0 | 0 | 0 | 1597413 | 1597413 | 0 | -404 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 108 | 1884401.65 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W79 | 44023015201 | 2024-09-19 | QTR1 | 24/25 | 1 | 2 | 140 | 150 | 124 | 26 | 0 | 0 | 10 | 0 | 1118465 | 40273 | 1078192 | 1118465 | 854089 | 0 | 0 | 0 | 854089 | 854089 | -1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-09-11 | QTR1 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 118 | 991704.32 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W84 | 43607915201 | 2024-11-07 | QTR2 | 24/25 | 1 | 2 | 135 | 148 | 143 | 5 | 0 | 0 | 13 | 0 | 2277103 | 50000 | 2227103 | 2321230 | 1781060 | 0 | 0 | 0 | 1781060 | 1781061 | 1 | 44127 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 19595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19595 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2026-06-22 | QTR4 | 25/26 |  | 2025-11-03 | QTR2 | 25/26 | 118 | 3667817.74 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W85 | 44893115201 | 2024-11-07 | QTR2 | 24/25 | 2 | 3 | 150 | 180 | 160 | 20 | 0 | 0 | 30 | 0 | 4458291 | 54289 | 4404002 | 4710660 | 4720609 | 0 | 0 | 0 | 4720609 | 4719730 | -879 | 252368 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282730 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-09-04 | QTR1 | 25/26 | 113 | 5001199.26 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W87 | 45089215201 | 2025-07-17 | QTR1 | 25/26 | 2 | 0 | 150 | 180 | 150 | 30 | 0 | 0 | 30 | 0 | 3771590 | 51486 | 3720104 | 3771590 | 3672932 | 0 | 0 | 0 | 3672932 | 3673179 | 247 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-06-02 | QTR4 | 25/26 |  | 2026-03-11 | QTR3 | 25/26 | 108 | 5146948.27 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W89 | 44927515201 | 2024-12-05 | QTR2 | 24/25 | 1 | 0 | 200 | 252 | 248 | 4 | 0 | 0 | 52 | 0 | 8846876 | 116108 | 8730768 | 8846876 | 9498223 | 0 | 0 | 0 | 9498223 | 9496897 | -1326 | 0 | 38 | 0 | 0 | 5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20916 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-04-06 | QTR4 | 25/26 |  | 2025-12-09 | QTR2 | 25/26 | 108 | 9903212.9 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W94 | 44917815201 | 2025-02-20 | QTR3 | 24/25 | 1 | 0 | 80 | 147 | 156 | -9 | 9 | 0 | 37 | 30 | 830702 | 40500 | 790202 | 830702 | 826937 | -15165 | 0 | -15165 | 811772 | 811772 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 30 | 17515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 17515 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-01-30 | QTR3 | 25/26 |  | 2025-12-10 | QTR2 | 25/26 | 108 | 1048586.14 |  |  | 30 | 8 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1W97 | 45344615201 | 2025-03-20 | QTR3 | 24/25 | 1 | 0 | 100 | 178 | 178 | 0 | 0 | 0 | 78 | 0 | 586332 | 33727 | 552605 | 586332 | 567695 | -2950 | 0 | -2950 | 564745 | 564745 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2026-03-05 | QTR3 | 25/26 | 108 | 574883.78 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1X61 | 44897315201 | 2025-05-15 | QTR4 | 24/25 | 1 | 0 | 150 | 224 | 224 | 0 | 0 | 0 | 74 | 0 | 6268574 | 78935 | 6189639 | 6268574 | 6617085 | 0 | 0 | 0 | 6617085 | 6634790 | 17705 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-04-29 | QTR4 | 25/26 |  | 2026-03-19 | QTR3 | 25/26 | 118 | 7458839.38 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1X68 | 44895715201 | 2025-07-17 | QTR1 | 25/26 | 1 | 0 | 100 | 121 | 115 | 6 | 0 | 0 | 21 | 0 | 2063849 | 50000 | 2013849 | 2063849 | 1971937 | 0 | 0 | 0 | 1971937 | 1971937 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8496 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 |  | 2026-02-10 | QTR3 | 25/26 | 113 | 2136352.43 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1X74 | 45087815201 | 2025-09-18 | QTR1 | 25/26 | 1 | 0 | 80 | 96 | 74 | 22 | 0 | 0 | 16 | 0 | 576122 | 38879 | 537243 | 576122 | 554252 | 0 | 0 | 0 | 554252 | 554252 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2026-03-19 | QTR3 | 25/26 | 108 | 728143.78 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1X75 | 45127215201 | 2025-09-18 | QTR1 | 25/26 | 1 | 0 | 100 | 119 | 96 | 23 | 0 | 0 | 19 | 0 | 2448287 | 50000 | 2398287 | 2448287 | 2439726 | 0 | 0 | 0 | 2439726 | 2439726 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2026-03-06 | QTR3 | 25/26 | 113 | 3004335.58 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2591 | 42886515201 | 2015-10-14 | QTR2 | 15/16 | 5 | 58 | 1200 | 3229 | 3229 | 0 | 0 | 0 | 905 | 1124 | 65973116 | 149995 | 65823121 | 108070596 | 111419612 | 0 | 0 | 0 | 111419612 | 112415734 | 1746230 | 42097480 | 322 | 133 | 66 | 1773148 | 375907 | 118 | 671 | 33362908 | 7141422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 335 | 4964601 | 3035499 | 0 | 0 | 325801 | 0 | 0 | 0 | 0 | 0 | 117 | 0 | 343725 | 2306 | 0 | 0 | 1388728 | 620012 | 0 | 52 | 1119347 | 685768 | 0 | 0 | 0 | 0 | 436 | 1124 | 42138723 | 11860914 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-03-23 | QTR3 | 25/26 |  | 2024-12-31 | QTR2 | 24/25 | 208 | 76779378.1 |  |  | 7 | 264 | 0 | 0 | -1139535 | 0 |  | CO
02CO | 02 | T2736 | 21002445201 | 2019-09-25 | QTR1 | 19/20 | 1 | 9 | 1000 | 1343 | 1343 | 0 | 0 | 0 | 229 | 114 | 49333142 | 150000 | 49183142 | 49318231 | 49328600 | 0 | 0 | 0 | 49328600 | 50856887 | 1816856 | -14911 | 135 | 14 | 88 | 388963 | 9343 | 0 | 26 | 65671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 51 | 114 | 42847 | 9343 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-04-24 | QTR4 | 25/26 |  | 2023-09-09 | QTR1 | 23/24 | 216 | 54425330.39 |  |  | 114 | 80 | 0 | 0 | -425234 | 0 |  | CO
02CO | 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 329791 | 87098 | 104 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2790 | 43616815201 | 2021-01-27 | QTR3 | 20/21 | 1 | 4 | 730 | 1441 | 1441 | 0 | 0 | 0 | 711 | 0 | 15444874 | 116066 | 15328808 | 18490817 | 18458945 | 0 | 0 | 0 | 18458945 | 18501533 | 251365 | 3045943 | 306 | 0 | 0 | 677453 | 0 | 0 | 0 | 61510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1981123 | 14607 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 2720087 | 14607 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2025-12-05 | QTR2 | 25/26 |  | 2025-05-07 | QTR4 | 24/25 | 216 | 11733776.57 |  |  | 0 | 279 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2819 | 43384325201 | 2021-10-27 | QTR2 | 21/22 | 4 | 13 | 260 | 1451 | 1440 | 11 | 0 | 0 | 782 | 409 | 4659450 | 50000 | 4609450 | 10356438 | 10867437 | 0 | 0 | 0 | 10867437 | 10590254 | 248 | 5696988 | 396 | 147 | 400 | 4148470 | 896117 | 0 | 9 | 24518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7156 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 1399987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 409 | 5580131 | 896117 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-06-19 | QTR4 | 25/26 |  | 2026-03-13 | QTR3 | 25/26 | 216 | 4935260.07 |  |  | 9 | 239 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2839 | 44342115201 | 2022-02-09 | QTR3 | 21/22 | 3 | 0 | 480 | 785 | 783 | 2 | 0 | 0 | 185 | 120 | 31969186 | 150000 | 31819186 | 31969186 | 32489212 | 0 | 0 | 0 | 32489212 | 33982240 | 1493028 | 0 | 244 | 0 | 2 | 18542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 120 | 18542 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-14 | QTR1 | 25/26 |  | 2024-06-14 | QTR4 | 23/24 | 209 | 35449756.12 |  |  | 120 | 59 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2844 | 43935615201 | 2022-06-15 | QTR4 | 21/22 | 3 | 6 | 479 | 915 | 913 | 2 | 0 | 0 | 311 | 125 | 19892956 | 180993 | 19711963 | 20310363 | 20717832 | 0 | 0 | 0 | 20717832 | 20350044 | -345380 | 417407 | 191 | 50 | 92 | 143934 | 0 | 0 | 15 | 291019 | 3470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681 | 0 | 0 | 18 | 42558 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 125 | 516682 | 3470 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-07-16 | QTR1 | 25/26 | 208 | 16227519.23 |  |  | 113 | 70 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2854 | 44554515201 | 2022-06-08 | QTR4 | 21/22 | 2 | 1 | 210 | 817 | 817 | 0 | 0 | 0 | 355 | 252 | 10095026 | 91284 | 10003741 | 10267526 | 10526210 | 0 | 0 | 0 | 10526210 | 10195263 | -330946 | 172500 | 390 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 110 | 172500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 252 | 172500 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 209 | 10655889.17 |  |  | 232 | 55 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2863 | 43744115201 | 2022-01-12 | QTR3 | 21/22 | 3 | 6 | 550 | 1127 | 1125 | 2 | 0 | 0 | 161 | 416 | 14032373 | 165047 | 13867326 | 15901285 | 16261074 | 0 | 0 | 0 | 16261074 | 16278606 | 24575 | 1868912 | 57 | 0 | 416 | 1783542 | 0 | 0 | 0 | 59192 | 4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20176 | 0 | 0 | 0 | 38915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 1906703 | 4208 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 208 | 15021660.86 |  |  | 120 | 104 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2865 | 44351715201 | 2022-11-16 | QTR2 | 22/23 | 1 | 6 | 400 | 682 | 681 | 1 | 0 | 0 | 162 | 120 | 7663000 | 71865 | 7591135 | 8470199 | 9163770 | 0 | 0 | 0 | 9163770 | 9149657 | -14114 | 807199 | 68 | 45 | 91 | 723003 | 0 | 0 | 29 | 122914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 120 | 871252 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-09-26 | QTR1 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 208 | 7014633.18 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2878 | 43205425201 | 2022-11-16 | QTR2 | 22/23 | 4 | 6 | 500 | 895 | 895 | 0 | 0 | 0 | 335 | 60 | 9330849 | 107922 | 9222927 | 9522394 | 9742335 | 0 | 0 | 0 | 9742335 | 9588826 | -24880 | 191545 | 283 | 0 | 0 | 0 | 0 | 0 | 60 | 62916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 20 | 152911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 80 | 215827 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 |  | 2025-08-27 | QTR1 | 25/26 | 209 | 10579788.59 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2886 | 44554425201 | 2022-10-05 | QTR2 | 22/23 | 3 | 6 | 270 | 917 | 917 | 0 | 0 | 0 | 291 | 356 | 16754450 | 150000 | 16604450 | 17512907 | 18119731 | 0 | 0 | 0 | 18119731 | 17771453 | -335353 | 758457 | 254 | 0 | 30 | 34294 | 0 | 0 | 0 | 154830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 405798 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 30 | 178200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 326 | 773122 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-06-11 | QTR4 | 25/26 |  | 2025-08-22 | QTR1 | 25/26 | 209 | 17577251.58 |  |  | 196 | 67 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2889 | 43575615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 5 | 280 | 638 | 638 | 0 | 0 | 0 | 199 | 159 | 3832776 | 50000 | 3782776 | 4315395 | 4383212 | 0 | 0 | 0 | 4383212 | 4383212 | 0 | 482619 | 107 | 0 | 24 | 38374 | 0 | 0 | 135 | 462409 | 134882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 500784 | 134882 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2025-06-06 | QTR4 | 24/25 | 208 | 4521037.25 |  |  | 24 | 92 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2890 | 44554715201 | 2022-10-26 | QTR2 | 22/23 | 3 | 3 | 350 | 924 | 924 | 0 | 0 | 0 | 261 | 313 | 25595410 | 150000 | 25445410 | 25761158 | 26450421 | 0 | 0 | 0 | 26450421 | 25953030 | -497390 | 165747 | 280 | 0 | 213 | 120000 | 0 | 0 | 2 | 33247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 57500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 270747 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-09-17 | QTR1 | 25/26 | 209 | 25708227.9 |  |  | 303 | 71 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2894 | 44540215201 | 2022-11-16 | QTR2 | 22/23 | 1 | 2 | 240 | 575 | 575 | 0 | 0 | 0 | 196 | 139 | 12471547 | 114486 | 12357061 | 12747539 | 13553931 | 0 | 0 | 0 | 13553931 | 13363147 | -190784 | 275992 | 290 | 0 | 57 | 256470 | 0 | 0 | 2 | 107104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 139 | 363574 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-03 | QTR1 | 25/26 |  | 2024-09-11 | QTR1 | 24/25 | 209 | 11980864.41 |  |  | 137 | 29 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2910 | 44535215201 | 2023-06-14 | QTR4 | 22/23 | 3 | 5 | 330 | 543 | 543 | 0 | 0 | 0 | 153 | 60 | 5895675 | 59623 | 5836052 | 5981679 | 6100547 | 0 | 0 | 0 | 6100547 | 6061260 | -3283 | 86004 | 101 | 0 | 20 | 48625 | 0 | 0 | 40 | 55572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 104197 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-06 | QTR2 | 25/26 |  | 2025-05-29 | QTR4 | 24/25 | 208 | 6680440.38 |  |  | 60 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2913 | 44707815201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 150 | 420 | 412 | 8 | 0 | 0 | 102 | 168 | 4420617 | 50000 | 4370617 | 4518180 | 4416217 | 0 | 0 | 0 | 4416217 | 4412247 | -3971 | 97563 | 72 | 0 | 30 | 0 | 0 | 0 | 138 | 97563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 97563 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 |  | 2025-06-23 | QTR4 | 24/25 | 209 | 4807508.45 |  |  | 75 | 30 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2914 | 44717215201 | 2023-06-14 | QTR4 | 22/23 | 1 | 1 | 350 | 882 | 882 | 0 | 0 | 0 | 427 | 105 | 14592365 | 150000 | 14442365 | 14773312 | 15181984 | 0 | 0 | 0 | 15181984 | 15184404 | 2420 | 180947 | 300 | 117 | 63 | 304259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 105 | 304259 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2026-01-28 | QTR3 | 25/26 | 216 | 15399944.09 |  |  | 105 | 108 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2915 | 44718015201 | 2023-03-29 | QTR3 | 22/23 | 1 | 1 | 300 | 660 | 659 | 1 | 0 | 0 | 346 | 14 | 11703806 | 89802 | 11614004 | 11742594 | 12389230 | 0 | 0 | 0 | 12389230 | 12372017 | -17213 | 38788 | 301 | 0 | 14 | 14951 | 0 | 0 | 0 | 38788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14 | 53739 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-20 | QTR2 | 25/26 |  | 2025-06-26 | QTR4 | 24/25 | 208 | 10416036.13 |  |  | 14 | 45 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2916 | 43993715201 | 2023-04-26 | QTR4 | 22/23 | 2 | 0 | 425 | 610 | 605 | 5 | 0 | 0 | 185 | 0 | 10398707 | 246 | 10398461 | 10398707 | 10268067 | 0 | 0 | 0 | 10268067 | 10264507 | -3560 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 209 | 8834993.85 |  |  | 0 | 48 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2917 | 44330415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 2 | 330 | 604 | 604 | 0 | 0 | 0 | 174 | 100 | 23947969 | 150000 | 23797969 | 24055659 | 25032603 | 0 | 0 | 0 | 25032603 | 25026994 | -5609 | 107690 | 101 | 0 | 66 | 177659 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 180877 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 208 | 21934859.67 |  |  | 100 | 73 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2924 | 20930185201 | 2023-04-26 | QTR4 | 22/23 | 1 | 2 | 300 | 751 | 751 | 0 | 0 | 0 | 250 | 201 | 19358596 | 150000 | 19208596 | 19523393 | 20332171 | 0 | 0 | 0 | 20332171 | 20313549 | -18621 | 164797 | 300 | 0 | 0 | 49110 | 0 | 27 | 51 | 133896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17832 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 9270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 201 | 210108 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-02-20 | QTR3 | 25/26 |  | 2025-10-27 | QTR2 | 25/26 | 208 | 19142187.33 |  |  | 165 | 68 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2934 | 44331015201 | 2022-12-07 | QTR2 | 22/23 | 2 | 5 | 450 | 714 | 711 | 3 | 0 | 0 | 264 | 0 | 26057502 | 150000 | 25907502 | 26443445 | 27980036 | 0 | 0 | 0 | 27980036 | 27874372 | -105664 | 385943 | 91 | 86 | 0 | 261787 | 11998 | 21 | 0 | 157751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 462296 | 11998 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-03-13 | QTR3 | 24/25 | 208 | 24163399.99 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2945 | 44542715201 | 2023-12-06 | QTR2 | 23/24 | 1 | 0 | 300 | 503 | 501 | 2 | 0 | 0 | 113 | 90 | 6853255 | 73995 | 6779259 | 6853255 | 6989283 | 0 | 0 | 0 | 6989283 | 6981891 | -7392 | 0 | 72 | 0 | 10 | 13022 | 0 | 0 | 20 | 29941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 46335 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-08-12 | QTR1 | 25/26 | 208 | 7614578.02 |  |  | 90 | 41 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2948 | 44712315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 300 | 431 | 414 | 17 | 0 | 0 | 71 | 60 | 5794236 | 50808 | 5743428 | 5794236 | 5977965 | 0 | 0 | 0 | 5977965 | 5956561 | -21404 | 0 | 93 | 0 | 0 | 14179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14179 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2025-11-12 | QTR2 | 25/26 |  | 2025-07-10 | QTR1 | 25/26 | 208 | 5749684.61 |  |  | 60 | 38 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2949 | 20969745201 | 2023-11-15 | QTR2 | 23/24 | 1 | 2 | 270 | 360 | 323 | 37 | 0 | 0 | 73 | 17 | 1865813 | 50000 | 1815813 | 1939049 | 1961474 | 0 | 0 | 0 | 1961474 | 1960364 | -1110 | 73235 | 44 | 0 | 16 | 39150 | 0 | 0 | 1 | 39471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 78621 | 0 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2025-11-07 | QTR2 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 208 | 2230663.64 |  |  | 1 | 29 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2954 | 44542015201 | 2023-12-06 | QTR2 | 23/24 | 2 | 0 | 270 | 373 | 372 | 1 | 0 | 0 | 103 | 0 | 3819110 | 50000 | 3769110 | 3819110 | 3735111 | 0 | 0 | 0 | 3735111 | 3733457 | -1654 | 0 | 67 | 0 | 0 | 702 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 208 | 5040191.6 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2961 | 43633015201 | 2023-12-06 | QTR2 | 23/24 | 3 | 3 | 400 | 450 | 393 | 57 | 0 | 0 | 50 | 0 | 3521000 | 246 | 3520754 | 3558326 | 3560864 | 0 | 0 | 0 | 3560864 | 3553846 | -957 | 37326 | 19 | 7 | 0 | 31265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 31265 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-03-19 | QTR3 | 24/25 | 209 | 3765540.75 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2962 | 44796215201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 180 | 370 | 370 | 0 | 0 | 0 | 160 | 30 | 7958218 | 85629 | 7872589 | 7958218 | 7882304 | 0 | 0 | 0 | 7882304 | 7877534 | -4770 | 0 | 79 | 0 | 30 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 30 | 1672 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 214 | 8827613.66 |  |  | 30 | 56 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2966 | 21086555201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 120 | 236 | 232 | 4 | 0 | 0 | 56 | 60 | 2921783 | 50000 | 2871783 | 2921783 | 2938946 | 0 | 0 | 0 | 2938946 | 2938946 | 0 | 0 | 34 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-04-14 | QTR4 | 24/25 | 209 | 3224885.25 |  |  | 60 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2969 | 44703615201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 300 | 408 | 406 | 2 | 0 | 0 | 50 | 58 | 10923210 | 112286 | 10810924 | 10892472 | 11424138 | 0 | 0 | 0 | 11424138 | 11378255 | -45883 | -30738 | 23 | 0 | 0 | 0 | 0 | 0 | 28 | 69752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 58 | 39014 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-24 | QTR2 | 25/26 |  | 2025-08-18 | QTR1 | 25/26 | 214 | 10802904.04 |  |  | 58 | 27 | 0 | 0 | -30738 | 0 |  | CO
02CO | 02 | T2970 | 44712815201 | 2024-02-28 | QTR3 | 23/24 | 3 | 5 | 180 | 392 | 392 | 0 | 0 | 0 | 140 | 72 | 6497196 | 70342 | 6426853 | 6705393 | 7314719 | 0 | 0 | 0 | 7314719 | 7267283 | -20654 | 208197 | 91 | 0 | 72 | 171277 | 99710 | 0 | 0 | 19849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 187461 | 99710 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 208 | 6729211.88 |  |  | 2 | 49 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2973 | 44542915201 | 2024-03-27 | QTR3 | 23/24 | 1 | 1 | 450 | 538 | 511 | 27 | 0 | 0 | 88 | 0 | 11487858 | 101697 | 11386161 | 11487858 | 11739228 | 0 | 0 | 0 | 11739228 | 11724947 | -14282 | 0 | 28 | 0 | 0 | 12545 | 0 | 0 | 0 | 53728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66273 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-06-03 | QTR4 | 25/26 |  | 2026-02-18 | QTR3 | 25/26 | 208 | 9400553.25 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2974 | 44720415201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 300 | 461 | 461 | 0 | 0 | 0 | 155 | 6 | 18339896 | 150000 | 18189896 | 18339896 | 18394467 | 0 | 0 | 0 | 18394467 | 18347088 | -47379 | 0 | 113 | 0 | 3 | 40787 | 0 | 0 | 3 | 5308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 6 | 46094 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-10-11 | QTR2 | 25/26 | 214 | 19102224.25 |  |  | 6 | 42 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2976 | 44755715201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 360 | 428 | 296 | 132 | 0 | 0 | 66 | 2 | 25893810 | 150000 | 25743810 | 26291007 | 27924429 | 0 | 0 | 0 | 27924429 | 27880284 | -44146 | 397198 | 39 | 0 | 0 | 417380 | 0 | 0 | 2 | 20401 | 3792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 437781 | 3792 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-21 | QTR2 | 25/26 |  | 2025-02-10 | QTR3 | 24/25 | 208 | 21206563.14 |  |  | 2 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2981 | 45220125201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 275 | 345 | 286 | 59 | 0 | 0 | 70 | 0 | 2914229 | 50000 | 2864229 | 2914229 | 2917184 | 0 | 0 | 0 | 2917184 | 2917184 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-07 | QTR1 | 25/26 |  | 2025-02-13 | QTR3 | 24/25 | 214 | 4244875.9 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2985 | 43761415201 | 2023-11-15 | QTR2 | 23/24 | 1 | 0 | 270 | 405 | 405 | 0 | 0 | 0 | 119 | 16 | 7308506 | 69947 | 7238559 | 7308506 | 7304574 | 0 | 0 | 0 | 7304574 | 7285470 | -19104 | 0 | 59 | 0 | 2 | 31262 | 0 | 0 | 14 | 18461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 16 | 49723 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 208 | 8026688.02 |  |  | 16 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2988 | 44721135201 | 2024-04-24 | QTR4 | 23/24 | 1 | 1 | 180 | 225 | 95 | 130 | 0 | 0 | 45 | 0 | 1562105 | 50000 | 1512105 | 1737694 | 1710662 | 0 | 0 | 0 | 1710662 | 1710435 | -227 | 175589 | 41 | 0 | 0 | 175589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175589 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 |  | 2024-10-17 | QTR2 | 24/25 | 208 | 1572771.91 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2989 | 20782335201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 210 | 411 | 404 | 7 | 0 | 0 | 176 | 25 | 5914935 | 64380 | 5850554 | 5914935 | 5974865 | 0 | 0 | 0 | 5974865 | 5969794 | -5070 | 0 | 150 | 0 | 10 | 0 | 0 | 0 | 15 | 19570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 19570 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2026-06-04 | QTR4 | 25/26 |  | 2026-02-13 | QTR3 | 25/26 | 214 | 6456937.46 |  |  | 25 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2990 | 20817735201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 250 | 385 | 385 | 0 | 0 | 0 | 63 | 72 | 8971608 | 119772 | 8851836 | 8971608 | 8756637 | 0 | 0 | 0 | 8756637 | 8744013 | -12624 | 0 | 98 | 0 | 12 | 0 | 0 | 0 | 0 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 10825 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2026-05-21 | QTR4 | 25/26 |  | 2026-02-09 | QTR3 | 25/26 | 216 | 11243024.19 |  |  | 72 | 25 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2992 | 44603135201 | 2024-08-28 | QTR1 | 24/25 | 1 | 1 | 230 | 305 | 302 | 3 | 0 | 0 | 73 | 2 | 2368158 | 50000 | 2318158 | 2387905 | 2401749 | 0 | 0 | 0 | 2401749 | 2401749 | 0 | 19747 | 15 | 0 | 0 | 0 | 0 | 0 | 1 | 59350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 59933 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-05-21 | QTR4 | 25/26 |  | 2026-01-12 | QTR3 | 25/26 | 208 | 3418661.07 |  |  | 2 | 58 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2997 | 44984425201 | 2024-09-25 | QTR1 | 24/25 | 1 | 2 | 180 | 214 | 214 | 0 | 0 | 0 | 34 | 0 | 2499454 | 50000 | 2449454 | 2573884 | 2437559 | 0 | 0 | 0 | 2437559 | 2436488 | -1071 | 74430 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 24430 | 24430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61993 | 24430 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 214 | 2231402.67 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2999 | 21273445201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 180 | 250 | 256 | -6 | 6 | 0 | 35 | 35 | 9621507 | 91073 | 9530434 | 9621507 | 9860600 | -22878 | 0 | -22878 | 9837722 | 9862910 | 25188 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-21 | QTR4 | 25/26 |  | 2025-12-15 | QTR2 | 25/26 | 209 | 9367981.87 |  |  | 35 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A02 | 43431825201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 180 | 188 | 171 | 17 | 0 | 0 | 8 | 0 | 7419960 | 87264 | 7332696 | 7419960 | 7285721 | 0 | 0 | 0 | 7285721 | 7282630 | -3091 | 0 | 4 | 0 | 0 | 46438 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61171 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-11-25 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 214 | 8775588.25 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A05 | 20944145201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 150 | 194 | 192 | 2 | 0 | 0 | 41 | 3 | 2487602 | 50000 | 2437602 | 2535510 | 2431426 | 0 | 0 | 0 | 2431426 | 2431081 | -345 | 47909 | 17 | 0 | 3 | 47909 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 49559 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2026-02-27 | QTR3 | 25/26 |  | 2025-11-24 | QTR2 | 25/26 | 208 | 3542854 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A06 | 21003025201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 300 | 343 | 305 | 38 | 0 | 0 | 43 | 0 | 6571980 | 67485 | 6504495 | 6571980 | 6862070 | 0 | 0 | 0 | 6862070 | 6863371 | 1301 | 0 | 17 | 0 | 0 | 13750 | 0 | 0 | 0 | 15770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29520 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-11 | QTR3 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 216 | 6362364.64 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A09 | 21022385201 | 2024-12-04 | QTR2 | 24/25 | 1 | 0 | 180 | 234 | 233 | 1 | 0 | 0 | 44 | 10 | 4685902 | 61983 | 4623919 | 4685902 | 4940814 | 0 | 0 | 0 | 4940814 | 4942704 | 1890 | 0 | 24 | 0 | 10 | 9787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9787 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2026-01-16 | QTR3 | 25/26 | 216 | 5665701.92 |  |  | 10 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A11 | 21037845201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 180 | 228 | 226 | 2 | 0 | 0 | 38 | 10 | 4938588 | 53445 | 4885143 | 4938588 | 5114986 | 0 | 0 | 0 | 5114986 | 5114986 | 0 | 0 | 24 | 0 | 0 | 14784 | 0 | 0 | 10 | 12155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 26939 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2025-12-03 | QTR2 | 25/26 | 214 | 4849324.71 |  |  | 10 | 14 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A12 | 21071155201 | 2024-09-25 | QTR1 | 24/25 | 1 | 1 | 120 | 214 | 212 | 2 | 0 | 0 | 85 | 9 | 4071019 | 50000 | 4021019 | 4106006 | 4039787 | 0 | 0 | 0 | 4039787 | 4039787 | 0 | 34986 | 61 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 57483 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 |  | 2025-06-24 | QTR4 | 24/25 | 208 | 4204426.35 |  |  | 3 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A13 | 44721225201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 150 | 260 | 260 | 0 | 0 | 0 | 64 | 46 | 3440497 | 50000 | 3390497 | 3440497 | 3621976 | 0 | 0 | 0 | 3621976 | 3623713 | 1737 | 0 | 28 | 0 | 11 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2026-01-23 | QTR3 | 25/26 | 208 | 3982196.66 |  |  | 46 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A15 | 21056535201 | 2025-02-26 | QTR3 | 24/25 | 1 | 0 | 200 | 222 | 215 | 7 | 0 | 0 | 22 | 0 | 4346749 | 56257 | 4290492 | 4346749 | 4440530 | 0 | 0 | 0 | 4440530 | 4440118 | -412 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2025-12-17 | QTR2 | 25/26 | 208 | 5565013.46 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A22 | 20983125201 | 2025-04-30 | QTR4 | 24/25 | 1 | 0 | 130 | 137 | 107 | 30 | 0 | 0 | 7 | 0 | 4091439 | 50000 | 4041439 | 4091439 | 4148474 | 0 | 0 | 0 | 4148474 | 4148474 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-06-03 | QTR4 | 25/26 |  | 2025-11-05 | QTR2 | 25/26 | 209 | 4272746.94 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A25 | 45260325201 | 2025-06-11 | QTR4 | 24/25 | 1 | 0 | 120 | 128 | 72 | 56 | 0 | 0 | 8 | 0 | 1482455 | 50000 | 1432455 | 1482455 | 1471968 | 0 | 0 | 0 | 1471968 | 1471968 | 0 | 0 | 0 | 0 | 0 | 8713 | 0 | 0 | 0 | 6401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15114 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2025-12-23 | QTR2 | 25/26 | 208 | 1454042.95 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A31 | 43930215201 | 2025-07-30 | QTR1 | 25/26 | 1 | 0 | 90 | 104 | 64 | 40 | 0 | 0 | 14 | 0 | 541819 | 37145 | 504674 | 541819 | 531179 | 0 | 0 | 0 | 531179 | 531179 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4453 | 0 | F863797014 | JANUS CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2026-04-17 | QTR4 | 25/26 |  | 2025-12-23 | QTR2 | 25/26 | 208 | 573090.27 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2A46 | 44721125201 | 2025-09-24 | QTR1 | 25/26 | 1 | 0 | 120 | 145 | 87 | 58 | 0 | 0 | 25 | 0 | 992131 | 50000 | 942131 | 992131 | 944723 | 0 | 0 | 0 | 944723 | 944723 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-06-05 | QTR4 | 25/26 |  | 2026-04-01 | QTR4 | 25/26 | 208 | 1219061.95 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9037 | 44627925214 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 300 | 323 | 260 | 63 | 0 | 0 | 23 | 0 | 755793 | 0 | 755793 | 799963 | 782324 | 0 | 0 | 0 | 782324 | 782311 | -13 | 44170 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44170 | 0 | F593399145 | E.B.MORRIS GENERAL CONTRACTORS | N/A | N/A | N/A | N/A | 2025-09-23 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 216 | 588437.99 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9039 | 44532025214 | 2024-05-22 | QTR4 | 23/24 | 1 | 2 | 400 | 433 | 375 | 58 | 0 | 0 | 33 | 0 | 2629396 | 0 | 2629396 | 2652851 | 2657516 | 0 | 0 | 0 | 2657516 | 2657516 | 0 | 23454 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 23454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23454 | 0 | F593399145 | E.B.MORRIS GENERAL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-02-03 | QTR3 | 25/26 |  | 2025-12-01 | QTR2 | 25/26 | 208 | 2484683.43 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9041 | 44628015215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 45 | 48 | 47 | 1 | 0 | 0 | 3 | 0 | 211688 | 9600 | 202088 | 211688 | 200166 | 0 | 0 | 0 | 200166 | 200166 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-02-21 | QTR3 | 24/25 | 208 | 233429.76 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9042 | 44628225214 | 2025-03-26 | QTR3 | 24/25 | 1 | 0 | 150 | 219 | 219 | 0 | 0 | 0 | 19 | 50 | 790012 | 22000 | 768012 | 790012 | 769140 | 0 | 0 | 0 | 769140 | 769140 | 0 | 0 | 11 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | F593399145 | E.B.MORRIS GENERAL CONTRACTORS | N/A | N/A | N/A | N/A | 2026-05-22 | QTR4 | 25/26 |  | 2026-04-20 | QTR4 | 25/26 | 209 | 477561.11 |  |  | 50 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9044 | 44628025216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 120 | 126 | 92 | 34 | 0 | 0 | 6 | 0 | 393754 | 22100 | 371654 | 393754 | 371540 | 0 | 0 | 0 | 371540 | 371540 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 208 | 505500 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E200W | 44572615201 | 2024-04-17 | QTR4 | 23/24 | 1 | 0 | 180 | 256 | 256 | 0 | 0 | 0 | 51 | 25 | 2930266 | 50000 | 2880266 | 2930266 | 2970891 | 0 | 0 | 0 | 2970891 | 2968577 | -2313 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17954 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18944 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-06-29 | QTR4 | 24/25 | 209 | 2593407.4 |  |  | 25 | 23 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20S0 | 20835235201 | 2022-06-01 | QTR4 | 21/22 | 1 | 2 | 659 | 1216 | 1216 | 0 | 0 | 0 | 119 | 438 | 10697084 | 97084 | 10600000 | 11279564 | 11359661 | 0 | 0 | 0 | 11359661 | 10989902 | -369758 | 582480 | 37 | 0 | 348 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 462480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438 | 582480 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-04-03 | QTR4 | 25/26 |  | 2025-12-14 | QTR2 | 25/26 | 209 | 9959694.79 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 268 | 82 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20S1 | 20841835201 | 2022-06-01 | QTR4 | 21/22 | 1 | 1 | 709 | 1164 | 1164 | 0 | 0 | 0 | 144 | 311 | 11841194 | 116194 | 11725000 | 11946194 | 12025404 | 0 | 0 | 0 | 12025404 | 11833660 | -191744 | 105000 | 59 | 0 | 311 | 105047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 105047 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-11 | QTR4 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 209 | 11946614.88 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 255 | 85 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20S2 | 21054545201 | 2022-06-01 | QTR4 | 21/22 | 1 | 0 | 609 | 992 | 992 | 0 | 0 | 0 | 123 | 260 | 8601469 | 80882 | 8520588 | 8601469 | 8734394 | 0 | 0 | 0 | 8734394 | 8453915 | -280479 | 0 | 136 | 0 | 90 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 209 | 8397276.42 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 260 | 77 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20T6 | 44278015201 | 2023-02-15 | QTR3 | 22/23 | 1 | 2 | 280 | 645 | 645 | 0 | 0 | 0 | 119 | 246 | 1676236 | 50000 | 1626236 | 1744958 | 1814629 | 0 | 0 | 0 | 1814629 | 1814629 | 0 | 68722 | 137 | 0 | 2 | 81415 | 0 | 0 | 141 | 31490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 112905 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2025-09-05 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 208 | 2494427.5 |  |  | 246 | 85 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20X8 | 20840265201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 550 | 717 | 717 | 0 | 0 | 0 | 167 | 0 | 9409691 | 88302 | 9321389 | 9409691 | 9709502 | 0 | 0 | 0 | 9709502 | 9670685 | -38817 | 0 | 27 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-10-15 | QTR2 | 25/26 |  | 2025-05-22 | QTR4 | 24/25 | 209 | 8868810.45 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20X9 | 44707615201 | 2023-03-23 | QTR3 | 22/23 | 1 | 0 | 490 | 785 | 780 | 5 | 0 | 0 | 205 | 90 | 11213775 | 111419 | 11102356 | 11213775 | 11321495 | 0 | 0 | 0 | 11321495 | 11257290 | -64205 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 180 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 209 | 11190658.02 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 90 | 66 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E21F5 | 43284915201 | 2024-01-09 | QTR3 | 23/24 | 2 | 5 | 480 | 739 | 555 | 184 | 0 | 0 | 92 | 167 | 13729182 | 150000 | 13579182 | 16720109 | 16682304 | 0 | 0 | 0 | 16682304 | 16681077 | -1228 | 2990927 | 41 | 7 | 167 | 3121267 | 143449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 167 | 3121267 | 143449 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-05-11 | QTR4 | 25/26 |  | 2025-10-28 | QTR2 | 25/26 | 208 | 17192402.49 | LBDB:Y | LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E21P1 | 21008525201 | 2025-01-15 | QTR3 | 24/25 | 2 | 1 | 150 | 282 | 282 | 0 | 0 | 0 | 82 | 50 | 12715932 | 117202 | 12598731 | 13204452 | 13781531 | 0 | 0 | 0 | 13781531 | 13293011 | 0 | 488520 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 488520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 50 | 488520 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-12 | QTR4 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 209 | 12431030.87 |  |  | 30 | 27 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z53 | 43035245201 | 2020-02-20 | QTR3 | 19/20 | 2 | 15 | 830 | 1569 | 1562 | 7 | 0 | 0 | 739 | 0 | 17677113 | 139633 | 17537480 | 32771107 | 33213700 | 0 | 0 | 0 | 33213700 | 33587618 | 498724 | 15093994 | 241 | 29 | 0 | 182603 | 0 | 56 | 0 | 402438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 14608377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 15230057 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-07-25 | QTR1 | 25/26 |  | 2025-03-17 | QTR3 | 24/25 | 214 | 14339167 |  |  | 0 | 106 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3618 | 21790935201 | 2020-05-20 | QTR4 | 19/20 | 1 | 25 | 1000 | 1915 | 1912 | 3 | 0 | 0 | 401 | 514 | 27170428 | 150000 | 27020428 | 30592621 | 31419600 | 0 | 0 | 0 | 31419600 | 32973116 | 1578565 | 3422193 | 242 | 0 | 106 | 96310 | 0 | 33 | 171 | 1524911 | 17782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 1824610 | 66674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 77645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 514 | 3523475 | 84456 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 313 | 35258008.48 |  |  | 83 | 126 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3705 | 43581615201 | 2021-06-09 | QTR4 | 20/21 | 3 | 7 | 1150 | 1341 | 1299 | 42 | 0 | 0 | 191 | 0 | 21786584 | 150000 | 21636584 | 24287618 | 24447463 | 0 | 0 | 0 | 24447463 | 24458859 | 417101 | 2501033 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 1856044 | 1818253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2538824 | 1818253 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-07-24 | QTR1 | 25/26 | 308 | 31799900.02 |  |  | 0 | 80 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3712 | 43937115201 | 2021-11-17 | QTR2 | 21/22 | 1 | 3 | 240 | 280 | 543 | -263 | 263 | 0 | 40 | 0 | 4199999 | 0 | 4199999 | 4207543 | 4275092 | -681696 | 0 | -681696 | 3593396 | 4275464 | 682068 | 7544 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 7544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7544 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2023-08-31 | QTR1 | 23/24 | 321 | 3898368.97 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3722 | 41098185201 | 2022-06-15 | QTR4 | 21/22 | 1 | 6 | 600 | 878 | 1063 | -185 | 185 | 0 | 197 | 81 | 16220760 | 150000 | 16070760 | 16260965 | 16485438 | -1083175 | 0 | -1083175 | 15402263 | 16125524 | 723261 | 40205 | 122 | 0 | 81 | -39105 | 0 | 16 | 0 | 102671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 81 | 77715 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-10-24 | QTR2 | 25/26 | 314 | 24461056.7 |  |  | 30 | 59 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 2 | 365 | 689 | 689 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6169465 | 6682488 | 0 | 0 | 0 | 6682488 | 7794860 | 1176465 | 3017 | 170 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 100 | 21 | 70800 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-26 | QTR3 | 25/26 |  | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29 |  |  | 21 | 89 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3786 | 21798625201 | 2022-06-15 | QTR4 | 21/22 | 3 | 2 | 310 | 1136 | 1134 | 2 | 0 | 0 | 626 | 200 | 12931177 | 73600 | 12857576 | 14015331 | 14246133 | 0 | 0 | 0 | 14246133 | 14084325 | -161808 | 1084154 | 322 | 0 | 200 | 1084154 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 200 | 1084154 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 |  | 2026-02-02 | QTR3 | 25/26 | 314 | 10461386.99 |  |  | 0 | 215 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3789 | 43813315201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 50 | 230 | 226 | 4 | 0 | 0 | 142 | 38 | 383899 | 19912 | 363987 | 397919 | 393163 | -35910 | 0 | -35910 | 357253 | 329110 | -28143 | 14020 | 115 | 0 | 0 | 0 | 0 | 0 | 38 | 14020 | 917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 38 | 14020 | 917 | F473361483 | T & T CIVIL CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2026-03-26 | QTR3 | 25/26 |  | 2023-01-27 | QTR3 | 22/23 | 314 | 424157.75 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3790 | 43748915201 | 2024-01-31 | QTR3 | 23/24 | 1 | 0 | 255 | 343 | 339 | 4 | 0 | 0 | 88 | 0 | 3547402 | 0 | 3547402 | 3547402 | 3587891 | 0 | 0 | 0 | 3587891 | 3586665 | -1225 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 313 | 4578761.95 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3804 | 42697315201 | 2022-04-27 | QTR4 | 21/22 | 2 | 4 | 200 | 679 | 679 | 0 | 0 | 0 | 404 | 75 | 6212045 | 50000 | 6162045 | 6299150 | 6924822 | 0 | 0 | 0 | 6924822 | 6889613 | -35209 | 87105 | 260 | 161 | 0 | 0 | 0 | 7 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 87105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 75 | 87105 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 313 | 5759918.26 |  |  | 45 | 64 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3835 | 44563315201 | 2023-03-29 | QTR3 | 22/23 | 2 | 2 | 435 | 712 | 712 | 0 | 0 | 0 | 265 | 12 | 10919335 | 105921 | 10813414 | 11003378 | 11511158 | 0 | 0 | 0 | 11511158 | 11473007 | -38151 | 84043 | 130 | 10 | 0 | 22048 | 0 | 52 | 12 | 94616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 12 | 116664 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-09-08 | QTR1 | 25/26 | 314 | 11459373.75 |  |  | 0 | 73 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3837 | 22259365201 | 2022-12-07 | QTR2 | 22/23 | 2 | 3 | 425 | 608 | 608 | 0 | 0 | 0 | 146 | 37 | 11772258 | 136099 | 11636159 | 11871253 | 11834603 | 0 | 0 | 0 | 11834603 | 11821261 | -13342 | 98995 | 72 | 0 | 3 | 2170 | 0 | 4 | 12 | 33069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 130287 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37 | 165526 | 579 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-16 | QTR1 | 25/26 |  | 2025-02-07 | QTR3 | 24/25 | 321 | 13447557.24 |  |  | 20 | 70 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3840 | 44560215201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 168 | 265 | 265 | 0 | 0 | 0 | 90 | 7 | 2093575 | 50000 | 2043575 | 2093575 | 2052800 | 0 | 0 | 0 | 2052800 | 2052014 | -786 | 0 | 38 | 23 | 7 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 7 | 2900 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2025-11-24 | QTR2 | 25/26 | 314 | 1776459.2 |  |  | 7 | 29 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3843 | 43736615201 | 2023-02-22 | QTR3 | 22/23 | 3 | 3 | 450 | 880 | 880 | 0 | 0 | 0 | 397 | 33 | 14976878 | 150000 | 14826878 | 15770067 | 16545874 | 0 | 0 | 0 | 16545874 | 16474250 | -71624 | 793189 | 199 | 0 | 17 | 182706 | 0 | 90 | 14 | 676082 | 8918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 2 | 8973 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 33 | 867761 | 8918 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-09-30 | QTR1 | 25/26 | 308 | 17116856.14 |  |  | 17 | 105 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3844 | 44581515201 | 2023-04-26 | QTR4 | 22/23 | 2 | 1 | 325 | 796 | 793 | 3 | 0 | 0 | 471 | 0 | 16815829 | 150000 | 16665829 | 16829871 | 17633297 | 0 | 0 | 0 | 17633297 | 17609681 | -23615 | 14042 | 181 | 0 | 0 | 0 | 0 | 195 | 0 | 14042 | 11490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 14042 | 11490 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-09-12 | QTR1 | 25/26 | 306 | 15773894.2 |  |  | 0 | 95 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3851 | 44292015201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 290 | 517 | 514 | 3 | 0 | 0 | 227 | 0 | 3185384 | 0 | 3185384 | 3188684 | 3129056 | 0 | 0 | 0 | 3129056 | 3127773 | -1283 | 3300 | 108 | 0 | 0 | 0 | 0 | 10 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 3300 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-10-16 | QTR2 | 25/26 | 306 | 3413369.7 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3855 | 44401915201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 140 | 482 | 482 | 0 | 0 | 0 | 342 | 0 | 958894 | 50000 | 908894 | 958894 | 885299 | 0 | 0 | 0 | 885299 | 885298 | -1 | 0 | 159 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2025-05-27 | QTR4 | 24/25 | 308 | 1271778.2 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3861 | 44573425201 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 150 | 429 | 429 | 0 | 0 | 0 | 156 | 123 | 6086126 | 54106 | 6032020 | 6138322 | 6717678 | 0 | 0 | 0 | 6717678 | 6699730 | -17947 | 52195 | 79 | 0 | 0 | 0 | 0 | 30 | 123 | 52195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 123 | 52195 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2025-11-11 | QTR2 | 25/26 | 313 | 6407295.93 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3862 | 43977415201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 220 | 395 | 370 | 25 | 0 | 0 | 105 | 70 | 3433760 | 50000 | 3383760 | 3478528 | 3538382 | 0 | 0 | 0 | 3538382 | 3534775 | -3607 | 44768 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 44768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 44768 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 |  | 2025-10-20 | QTR2 | 25/26 | 313 | 3773823.76 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3863 | 43256815201 | 2023-03-29 | QTR3 | 22/23 | 3 | 9 | 465 | 677 | 677 | 0 | 0 | 0 | 202 | 10 | 7039667 | 98677 | 6940990 | 7122635 | 6823877 | 0 | 0 | 0 | 6823877 | 6801370 | -22508 | 82968 | 107 | 0 | 9 | 27964 | 0 | 10 | 1 | 75272 | 2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5403 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 108639 | 2965 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2026-04-02 | QTR4 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 308 | 11146776.26 |  |  | 10 | 75 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3866 | 21968945201 | 2023-12-06 | QTR2 | 23/24 | 5 | 1 | 395 | 525 | 521 | 4 | 0 | 0 | 118 | 12 | 7020914 | 104250 | 6916664 | 7091275 | 7209436 | 0 | 0 | 0 | 7209436 | 7195667 | -13769 | 70362 | 48 | 6 | 12 | 79362 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 12 | 79362 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2026-06-11 | QTR4 | 25/26 |  | 2025-08-18 | QTR1 | 25/26 | 321 | 10186904.66 |  |  | 3 | 35 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3868 | 41344925201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 90 | 421 | 420 | 1 | 0 | 0 | 213 | 118 | 1298401 | 50000 | 1248401 | 1321412 | 1234071 | 0 | 0 | 0 | 1234071 | 1234071 | 0 | 23011 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 118 | 70737 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-24 | QTR4 | 24/25 | 313 | 1300164.1 |  |  | 118 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3871 | 42695025201 | 2024-06-12 | QTR4 | 23/24 | 2 | 1 | 260 | 335 | 326 | 9 | 0 | 0 | 75 | 0 | 3111541 | 50000 | 3061541 | 2493770 | 2535278 | 0 | 0 | 0 | 2535278 | 2534712 | -566 | -617771 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -617771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -617771 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-09-25 | QTR1 | 25/26 | 314 | 4093773.7 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3874 | 44188015201 | 2023-09-27 | QTR1 | 23/24 | 1 | 0 | 74 | 447 | 447 | 0 | 0 | 0 | 373 | 0 | 988409 | 46367 | 942042 | 988409 | 938135 | 0 | 0 | 0 | 938135 | 938135 | 0 | 0 | 262 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 314 | 990878.67 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3891 | 43467815201 | 2024-01-31 | QTR3 | 23/24 | 2 | 2 | 200 | 288 | 288 | 0 | 0 | 0 | 88 | 0 | 2823614 | 50000 | 2773614 | 2855298 | 2780904 | 0 | 0 | 0 | 2780904 | 2780236 | -668 | 31684 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31684 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 308 | 3805809.9 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3896 | 21995125201 | 2024-10-30 | QTR2 | 24/25 | 2 | 0 | 200 | 272 | 269 | 3 | 0 | 0 | 72 | 0 | 2986323 | 50000 | 2936323 | 2986323 | 3098563 | 0 | 0 | 0 | 3098563 | 3098475 | -89 | 0 | 15 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2026-01-07 | QTR3 | 25/26 | 314 | 3943155.55 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3901 | 41342535201 | 2024-07-31 | QTR1 | 24/25 | 1 | 1 | 205 | 261 | 254 | 7 | 0 | 0 | 54 | 2 | 3608291 | 50000 | 3558291 | 3609941 | 3619668 | 0 | 0 | 0 | 3619668 | 3616057 | -3611 | 1650 | 29 | 0 | 0 | 0 | 0 | 0 | 2 | 1650 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19319 | 1500 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-07-28 | QTR1 | 25/26 | 321 | 3187529.04 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3903 | 43973815201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 150 | 231 | 231 | 0 | 0 | 0 | 81 | 0 | 3355890 | 50000 | 3305890 | 3355890 | 3514890 | 0 | 0 | 0 | 3514890 | 3515807 | 917 | 0 | 51 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-04-01 | QTR4 | 25/26 |  | 2025-12-23 | QTR2 | 25/26 | 314 | 4058350.02 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3905 | 22392035201 | 2024-11-13 | QTR2 | 24/25 | 2 | 3 | 197 | 268 | 262 | 6 | 0 | 0 | 62 | 9 | 4631224 | 50398 | 4580826 | 4783835 | 4745931 | 0 | 0 | 0 | 4745931 | 4746412 | 481 | 152611 | 34 | 0 | 0 | 0 | 0 | 0 | 9 | 149127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 152611 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 | 01/23/2026 | 2026-01-23 | QTR3 | 25/26 | 321 | 5602104.94 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3909 | 43627425201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 120 | 129 | 123 | 6 | 0 | 0 | 9 | 0 | 989048 | 50000 | 939048 | 1062486 | 1040496 | 0 | 0 | 0 | 1040496 | 1040496 | 0 | 73438 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73438 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2026-04-02 | QTR4 | 25/26 |  | 2025-10-01 | QTR2 | 25/26 | 308 | 1500432.08 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3911 | 45100315201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 160 | 221 | 221 | 0 | 0 | 0 | 61 | 0 | 960717 | 48697 | 912021 | 960717 | 866512 | 0 | 0 | 0 | 866512 | 866512 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2026-01-13 | QTR3 | 25/26 | 308 | 1028033.47 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3913 | 21934625201 | 2024-08-28 | QTR1 | 24/25 | 2 | 1 | 165 | 248 | 221 | 27 | 0 | 0 | 83 | 0 | 2531784 | 50000 | 2481784 | 2570548 | 2574902 | 0 | 0 | 0 | 2574902 | 2573463 | -1439 | 38764 | 59 | 0 | 0 | 61379 | 16559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61379 | 16559 | F592990776 | AMERICAN SAND & X-CAVATION INC. DBA AMERICAN SAND & ASPHALT | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 314 | 3011928.8 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3936 | 45221255201 | 2024-11-13 | QTR2 | 24/25 | 1 | 0 | 180 | 235 | 208 | 27 | 0 | 0 | 55 | 0 | 993728 | 50000 | 943728 | 993728 | 582095 | 0 | 0 | 0 | 582095 | 582095 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2026-04-01 | QTR4 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 314 | 1931620.95 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3974 | 45221245201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 171 | 186 | 125 | 61 | 0 | 0 | 15 | 0 | 664538 | 50000 | 614538 | 664538 | 561863 | 0 | 0 | 0 | 561863 | 561863 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 314 | 887346.85 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3976 | 45586915201 | 2025-04-30 | QTR4 | 24/25 | 2 | 0 | 60 | 65 | 36 | 29 | 0 | 0 | 5 | 0 | 138618 | 8268 | 130350 | 138618 | 130350 | 0 | 0 | 0 | 130350 | 130350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES LLC | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2025-12-08 | QTR2 | 25/26 | 321 | 174042.72 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3A07 | 45587615201 | 2025-07-30 | QTR1 | 25/26 | 1 | 1 | 60 | 72 | 48 | 24 | 0 | 0 | 12 | 0 | 96095 | 7695 | 88400 | 47595 | 38484 | 0 | 0 | 0 | 38484 | 38484 | 0 | -48500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48500 | 0 | F541769861 | WEBBER INFRASTRUCTURE MANAGEMENT INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2026-01-26 | QTR3 | 25/26 | 321 | 164000 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9043 | 44628415215 | 2024-09-25 | QTR1 | 24/25 | 1 | 0 | 90 | 124 | 124 | 0 | 0 | 0 | 34 | 0 | 189979 | 10000 | 179979 | 189979 | 177334 | 0 | 0 | 0 | 177334 | 177334 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-05-09 | QTR4 | 24/25 | 308 | 237358.31 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9045 | 44628425216 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 180 | 199 | 122 | 77 | 0 | 0 | 14 | 5 | 511934 | 22600 | 489334 | 511934 | 495348 | 0 | 0 | 0 | 495348 | 495348 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | F592320406 | BILL SMITH ELECTRIC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-11-05 | QTR2 | 25/26 | 308 | 509928.23 |  |  | 5 | 4 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3U65 | 44188515201 | 2022-11-17 | QTR2 | 22/23 | 1 | 0 | 250 | 680 | 695 | -15 | 15 | 0 | 430 | 0 | 3672487 | 50000 | 3622487 | 3672487 | 3781493 | -38880 | 0 | -38880 | 3742613 | 3739460 | -3153 | 0 | 186 | 0 | 0 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 308 | 3629576.67 |  |  | 0 | 92 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V54 | 44554115201 | 2023-02-09 | QTR3 | 22/23 | 3 | 4 | 310 | 751 | 749 | 2 | 0 | 0 | 275 | 169 | 9981474 | 90589 | 9890885 | 10203672 | 10678123 | 0 | 0 | 0 | 10678123 | 10639564 | -38559 | 222198 | 136 | 0 | 51 | 147417 | 0 | 77 | 3 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 44650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 169 | 219567 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2025-05-27 | QTR4 | 24/25 | 314 | 10144016.25 |  |  | 33 | 62 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V77 | 40919375201 | 2023-10-12 | QTR2 | 23/24 | 1 | 0 | 333 | 516 | 511 | 5 | 0 | 0 | 183 | 0 | 3075367 | 50000 | 3025367 | 3075367 | 2907496 | 0 | 0 | 0 | 2907496 | 2907496 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-06-13 | QTR4 | 24/25 | 313 | 4067368.66 |  |  | 0 | 68 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V81 | 44563415201 | 2023-06-08 | QTR4 | 22/23 | 3 | 1 | 385 | 538 | 538 | 0 | 0 | 0 | 144 | 9 | 7280451 | 56951 | 7223500 | 7422322 | 7437743 | 0 | 0 | 0 | 7437743 | 7440600 | 2857 | 141871 | 76 | 0 | 5 | 141871 | 0 | 0 | 0 | 2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 0 | 0 | 4 | 9515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9 | 159630 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-03-03 | QTR3 | 24/25 | 321 | 6184892.36 |  |  | 4 | 52 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W01 | 44559115201 | 2022-09-08 | QTR1 | 22/23 | 2 | 6 | 365 | 828 | 968 | -140 | 140 | 0 | 443 | 20 | 7469384 | 92731 | 7376653 | 7480930 | 7419597 | -530040 | 0 | -530040 | 6889557 | 6812783 | -51349 | 11546 | 143 | 0 | 3 | 8874 | 0 | 198 | 12 | 18933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 42680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 15 | 47234 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 308 | 9544565.57 |  |  | 15 | 107 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W03 | 45034815201 | 2024-09-12 | QTR1 | 24/25 | 1 | 0 | 120 | 201 | 201 | 0 | 0 | 0 | 81 | 0 | 433807 | 23255 | 410552 | 433807 | 404077 | 0 | 0 | 0 | 404077 | 404077 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2026-04-04 | QTR4 | 25/26 |  | 2025-11-13 | QTR2 | 25/26 | 313 | 495857.94 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W12 | 44643355201 | 2024-08-08 | QTR1 | 24/25 | 2 | 1 | 170 | 220 | 220 | 0 | 0 | 0 | 16 | 34 | 2949285 | 50000 | 2899285 | 2625347 | 2604415 | 0 | 0 | 0 | 2604415 | 2604415 | 0 | -323937 | 5 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | -323937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | -323937 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-22 | QTR1 | 25/26 | 321 | 3480038 |  |  | 34 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W30 | 44759615201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 365 | 665 | 665 | 0 | 0 | 0 | 220 | 110 | 4167167 | 50000 | 4117167 | 4263313 | 3906647 | 0 | 0 | 0 | 3906647 | 3906647 | 0 | 96146 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 80 | 122581 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 306 | 4722891.55 |  |  | 0 | 82 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W31 | 44554215201 | 2023-06-08 | QTR4 | 22/23 | 1 | 1 | 385 | 696 | 694 | 2 | 0 | 0 | 311 | 0 | 12495664 | 115497 | 12380167 | 12574093 | 13184954 | 0 | 0 | 0 | 13184954 | 13181542 | -3412 | 78429 | 133 | 8 | 0 | 78429 | 78429 | 30 | 0 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 85479 | 78429 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-10-24 | QTR2 | 25/26 | 314 | 11633200.16 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W40 | 44374425201 | 2023-05-11 | QTR4 | 22/23 | 2 | 1 | 240 | 529 | 547 | -18 | 18 | 0 | 286 | 3 | 6286877 | 58278 | 6228599 | 6497112 | 6613095 | -68148 | 0 | -68148 | 6544947 | 6545243 | 297 | 210235 | 157 | 0 | 1 | 7085 | 0 | 45 | 2 | 211204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 3 | 218289 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-01 | QTR4 | 24/25 | 308 | 5983264.86 |  |  | 1 | 84 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W42 | 44559015201 | 2023-05-11 | QTR4 | 22/23 | 1 | 1 | 195 | 345 | 394 | -49 | 49 | 0 | 147 | 3 | 6987787 | 100654 | 6887133 | 6987787 | 7253303 | -185514 | 0 | -185514 | 7067789 | 7068223 | 435 | 0 | 104 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 3 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2024-10-15 | QTR2 | 24/25 | 308 | 10217706.9 |  |  | 3 | 43 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W68 | 45102815201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 60 | 65 | 52 | 13 | 0 | 0 | 5 | 0 | 112106 | 8466 | 103639 | 112106 | 103639 | 0 | 0 | 0 | 103639 | 103639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-06-12 | QTR4 | 24/25 | 314 | 174993.22 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W69 | 42696125201 | 2023-11-09 | QTR2 | 23/24 | 2 | 1 | 274 | 451 | 451 | 0 | 0 | 0 | 177 | 0 | 4685111 | 59134 | 4625977 | 4688658 | 4492681 | 0 | 0 | 0 | 4492681 | 4485331 | -7350 | 3547 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 3547 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 3547 | 1539 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-06-18 | QTR4 | 24/25 | 321 | 5910727.48 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W79 | 45109915201 | 2024-04-11 | QTR4 | 23/24 | 1 | 0 | 90 | 143 | 142 | 1 | 0 | 0 | 53 | 0 | 485265 | 30756 | 454509 | 485265 | 487819 | 0 | 0 | 0 | 487819 | 487819 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-08-06 | QTR1 | 25/26 |  | 2025-02-04 | QTR3 | 24/25 | 321 | 555113.46 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X01 | 40619455201 | 2024-10-24 | QTR2 | 24/25 | 1 | 0 | 120 | 159 | 153 | 6 | 0 | 0 | 39 | 0 | 328567 | 17193 | 311374 | 328567 | 291720 | 0 | 0 | 0 | 291720 | 291720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-10-09 | QTR2 | 25/26 | 313 | 364798.17 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X02 | 44366115201 | 2024-01-18 | QTR3 | 23/24 | 3 | 3 | 395 | 561 | 561 | 0 | 0 | 0 | 143 | 23 | 17358711 | 150000 | 17208711 | 17495056 | 17763005 | 0 | 0 | 0 | 17763005 | 17748983 | -14021 | 136345 | 74 | 0 | 19 | 131100 | 0 | 0 | 4 | 86193 | 23145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 217293 | 23145 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2025-12-03 | QTR2 | 25/26 | 313 | 17119005.62 |  |  | 9 | 69 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X03 | 40619635201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 90 | 112 | 86 | 26 | 0 | 0 | 22 | 0 | 169075 | 11395 | 157679 | 169075 | 154095 | 0 | 0 | 0 | 154095 | 154095 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 313 | 240133.12 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X08 | 45103115201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 225 | 303 | 223 | 80 | 0 | 0 | 78 | 0 | 1112248 | 50000 | 1062248 | 1112248 | 1077908 | 0 | 0 | 0 | 1077908 | 1077908 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-05-22 | QTR4 | 24/25 | 313 | 1273505.15 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X10 | 41537525201 | 2024-07-11 | QTR1 | 24/25 | 1 | 1 | 245 | 439 | 439 | 0 | 0 | 0 | 140 | 54 | 6739140 | 74160 | 6664981 | 6837451 | 7312420 | 0 | 0 | 0 | 7312420 | 7306921 | -5499 | 98311 | 78 | 7 | 0 | 0 | 0 | 0 | 54 | 98311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 54 | 98311 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2026-01-06 | QTR3 | 25/26 | 314 | 7908180.95 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X17 | 44758915201 | 2024-06-13 | QTR4 | 23/24 | 2 | 1 | 175 | 283 | 282 | 1 | 0 | 0 | 103 | 5 | 2342678 | 50000 | 2292678 | 2369603 | 2340433 | 0 | 0 | 0 | 2340433 | 2340369 | -64 | 26925 | 78 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26925 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-26 | QTR1 | 25/26 | 308 | 2975754.37 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X52 | 43078225201 | 2024-07-11 | QTR1 | 24/25 | 1 | 0 | 150 | 208 | 208 | 0 | 0 | 0 | 58 | 0 | 4271650 | 50000 | 4221650 | 4271650 | 4371998 | 0 | 0 | 0 | 4371998 | 4360199 | -11799 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2025-08-28 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 314 | 4754953.2 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X67 | 45103015201 | 2025-03-20 | QTR3 | 24/25 | 1 | 1 | 120 | 121 | 87 | 34 | 0 | 0 | 1 | 0 | 756145 | 50000 | 706145 | 589518 | 538882 | 0 | 0 | 0 | 538882 | 538882 | 0 | -166627 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -166627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -166627 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-04-02 | QTR4 | 25/26 |  | 2025-11-20 | QTR2 | 25/26 | 321 | 979632.72 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X72 | 22020225201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 150 | 200 | 155 | 45 | 0 | 0 | 50 | 0 | 647631 | 42452 | 605180 | 647631 | 536583 | 0 | 0 | 0 | 536583 | 536583 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN INC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2025-09-29 | QTR1 | 25/26 | 313 | 900232.57 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X74 | 45102925201 | 2024-11-14 | QTR2 | 24/25 | 1 | 2 | 126 | 283 | 282 | 1 | 0 | 0 | 153 | 4 | 1642742 | 50000 | 1592742 | 1701821 | 1683345 | 0 | 0 | 0 | 1683345 | 1683345 | 0 | 59079 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 65465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 4 | 65465 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2026-04-23 | QTR4 | 25/26 |  | 2026-02-17 | QTR3 | 25/26 | 308 | 1852698.82 |  |  | 4 | 28 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X76 | 44546615201 | 2025-02-13 | QTR3 | 24/25 | 1 | 0 | 245 | 251 | 96 | 155 | 0 | 0 | 6 | 0 | 2098170 | 50000 | 2048170 | 2098170 | 256639 | 0 | 0 | 0 | 256639 | 256639 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2025-08-19 | QTR1 | 25/26 | 313 | 2034848.91 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X87 | 45268615201 | 2024-09-12 | QTR1 | 24/25 | 1 | 1 | 120 | 179 | 178 | 1 | 0 | 0 | 58 | 1 | 1172775 | 50000 | 1122775 | 1197264 | 1124063 | 0 | 0 | 0 | 1124063 | 1124063 | 0 | 24489 | 12 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 24489 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-10-02 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 321 | 1445110 |  |  | 1 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3X99 | 43622975201 | 2024-09-12 | QTR1 | 24/25 | 1 | 2 | 231 | 321 | 308 | 13 | 0 | 0 | 90 | 0 | 5036594 | 56398 | 4980196 | 5050202 | 5170364 | 0 | 0 | 0 | 5170364 | 5170313 | -51 | 13608 | 60 | 0 | 0 | 18969 | 0 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23069 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2026-05-20 | QTR4 | 25/26 |  | 2026-02-20 | QTR3 | 25/26 | 308 | 6071472.22 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y02 | 45258125201 | 2025-04-10 | QTR4 | 24/25 | 1 | 0 | 180 | 274 | 272 | 2 | 0 | 0 | 94 | 0 | 1467009 | 50000 | 1417009 | 1467009 | 1421040 | 0 | 0 | 0 | 1421040 | 1421040 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 |  | 2026-04-24 | QTR4 | 25/26 | 314 | 1617018 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y07 | 43937125201 | 2025-01-30 | QTR3 | 24/25 | 1 | 0 | 120 | 128 | 115 | 13 | 0 | 0 | 8 | 0 | 493247 | 26670 | 466577 | 493247 | 468786 | 0 | 0 | 0 | 468786 | 468786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2025-09-24 | QTR1 | 25/26 | 321 | 566683.49 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y25 | 45431115201 | 2025-03-13 | QTR3 | 24/25 | 1 | 0 | 120 | 138 | 136 | 2 | 0 | 0 | 18 | 0 | 430052 | 29999 | 400053 | 430052 | 391859 | 0 | 0 | 0 | 391859 | 391859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 321 | 619869.69 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y28 | 45443415201 | 2025-04-10 | QTR4 | 24/25 | 1 | 0 | 120 | 125 | 107 | 18 | 0 | 0 | 5 | 0 | 339177 | 19836 | 319341 | 339177 | 318764 | 0 | 0 | 0 | 318764 | 318764 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-31 | QTR2 | 25/26 |  | 2025-11-03 | QTR2 | 25/26 | 308 | 393848.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Y34 | 45430915201 | 2025-08-14 | QTR1 | 25/26 | 1 | 0 | 120 | 135 | 86 | 49 | 0 | 0 | 15 | 0 | 882049 | 46891 | 835158 | 882049 | 783756 | 0 | 0 | 0 | 783756 | 783756 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | F862261446 | UNITED MARINE CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-04-30 | QTR4 | 25/26 |  | 2026-02-10 | QTR3 | 25/26 | 321 | 959603.73 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4560 | 44004315201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 482 | 552 | 551 | 1 | 0 | 0 | 70 | 0 | 2472960 | 50000 | 2422960 | 2472960 | 2454293 | 0 | 0 | 0 | 2454293 | 2461065 | 134358 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 19903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21118 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2025-09-22 | QTR1 | 25/26 |  | 2023-02-03 | QTR3 | 22/23 | 409 | 2686957.88 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4576 | 43175265201 | 2021-07-28 | QTR1 | 21/22 | 2 | 7 | 709 | 1423 | 1423 | 0 | 0 | 0 | 588 | 126 | 11570179 | 110040 | 11460139 | 12011477 | 12175883 | 0 | 0 | 0 | 12175883 | 12224650 | 48767 | 441298 | 245 | 91 | 78 | 510193 | 0 | 82 | 0 | -111152 | 2327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 48 | 13588 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 25737 | 0 | 0 | 0 | 0 | 0 | 257 | 126 | 438366 | 2327 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2026-05-12 | QTR4 | 25/26 |  | 2025-12-19 | QTR2 | 25/26 | 408 | 11623971.59 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 86 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4580 | 43992915201 | 2021-05-26 | QTR4 | 20/21 | 5 | 8 | 739 | 1080 | 1080 | 0 | 0 | 0 | 321 | 20 | 18014663 | 150000 | 17864663 | 17978017 | 17209306 | 0 | 0 | 0 | 17209306 | 17705907 | 548358 | -36647 | 213 | 26 | 0 | 52717 | 0 | 28 | 0 | 96396 | 32818 | 0 | 0 | 0 | 0 | 0 | 0 | -145423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10479 | 0 | 0 | 0 | 8503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51758 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 19502 | 19502 | 0 | 0 | 0 | 0 | 54 | 20 | 30554 | 52320 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 409 | 22960743.25 |  |  | 0 | 54 | 0 | 0 | -63378 | 0 |  | CO
04CO | 04 | T4582 | 43971415201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 701 | 1441 | 1432 | 9 | 0 | 0 | 740 | 0 | 28428146 | 150000 | 28278146 | 30792178 | 31403804 | 0 | 210000 | 210000 | 31613804 | 31414004 | 308408 | 2364032 | 135 | 283 | 0 | 783689 | 0 | 83 | 0 | 488491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1096988 | 0 | 74 | 0 | 33289 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 101236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6537 | 0 | 0 | 0 | 0 | 0 | 495 | 0 | 2494307 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2026-04-15 | QTR4 | 25/26 |  | 2025-08-08 | QTR1 | 25/26 | 412 | 26971212.73 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 110 | 0 | 0 | -15924 | 0 |  | CO
04CO | 04 | T4606 | 43175615201 | 2022-05-25 | QTR4 | 21/22 | 4 | 13 | 485 | 851 | 851 | 0 | 0 | 0 | 318 | 48 | 13650945 | 119988 | 13530957 | 16672549 | 16820299 | 0 | 0 | 0 | 16820299 | 16595748 | -213647 | 3021605 | 114 | 69 | 48 | 688143 | 187410 | 87 | 0 | 2603372 | 1424637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 48 | 3059006 | 1612048 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2026-06-15 | QTR4 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 412 | 14924236.89 | B5 | ACC - INCENTIVE/DISINCENTIVE | 19 | 48 | 0 | 0 | -232509 | 0 |  | CO
04CO | 04 | T4627 | 44384615201 | 2023-07-26 | QTR1 | 23/24 | 1 | 0 | 353 | 497 | 497 | 0 | 0 | 0 | 114 | 30 | 1831417 | 50000 | 1781417 | 1831417 | 1800868 | 0 | 0 | 0 | 1800868 | 1800868 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 47526 | 2447 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 412 | 2390409.32 |  |  | 30 | 30 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4638 | 43580855201 | 2023-07-26 | QTR1 | 23/24 | 4 | 4 | 345 | 512 | 512 | 0 | 0 | 0 | 137 | 30 | 8148235 | 82702 | 8065534 | 8411133 | 8179681 | 0 | 0 | 0 | 8179681 | 8160560 | -3998 | 262898 | 110 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 283139 | 127150 | F844728543 | STRONGCORE GROUP LLC | N/A | N/A | N/A | N/A | 2025-12-02 | QTR2 | 25/26 |  | 2025-07-23 | QTR1 | 25/26 | 412 | 8255267.22 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4641 | 43984515201 | 2023-04-26 | QTR4 | 22/23 | 4 | 5 | 721 | 810 | 789 | 21 | 0 | 0 | 89 | 0 | 11705000 | 114314 | 11590686 | 12054276 | 11872830 | 0 | 0 | 0 | 11872830 | 11832340 | -11097 | 349276 | 32 | 0 | 0 | 211859 | 0 | 0 | 0 | 163474 | 18545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386900 | 18545 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-16 | QTR3 | 25/26 |  | 2025-09-05 | QTR1 | 25/26 | 409 | 11870989.01 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4643 | 44637415201 | 2024-01-31 | QTR3 | 23/24 | 2 | 3 | 542 | 602 | 566 | 36 | 0 | 0 | 60 | 0 | 17748021 | 150000 | 17598021 | 18627265 | 18943576 | 0 | 0 | 0 | 18943576 | 18916878 | -25540 | 879244 | 29 | 0 | 0 | 886738 | 22797 | 0 | 0 | 7449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911403 | 22797 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-11-17 | QTR2 | 25/26 | 409 | 24914785.02 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4645 | 44610215201 | 2023-05-24 | QTR4 | 22/23 | 2 | 4 | 430 | 560 | 558 | 2 | 0 | 0 | 130 | 0 | 12833449 | 133704 | 12699745 | 12956058 | 12287948 | 0 | 0 | 0 | 12287948 | 12282375 | 2250 | 122609 | 65 | 0 | 0 | 35147 | 0 | 21 | 0 | 79638 | 29413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114786 | 29413 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-31 | QTR1 | 25/26 |  | 2025-05-02 | QTR4 | 24/25 | 409 | 14351247.26 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4649 | 44839715201 | 2023-06-14 | QTR4 | 22/23 | 1 | 5 | 254 | 482 | 482 | 0 | 0 | 0 | 67 | 161 | 4835155 | 50000 | 4785155 | 5082020 | 5106645 | 0 | 0 | 0 | 5106645 | 5105846 | -798 | 246865 | 59 | 0 | 0 | 41171 | 0 | 0 | 0 | 40694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 246865 | 0 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2026-01-28 | QTR3 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 408 | 6110749.35 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4651 | 44407915201 | 2023-10-25 | QTR2 | 23/24 | 3 | 6 | 473 | 492 | 347 | 145 | 0 | 0 | 43 | -24 | 7152200 | 65917 | 7086283 | 7526530 | 7413084 | 0 | 0 | 0 | 7413084 | 7393759 | -14849 | 529392 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 28959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28959 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2025-04-18 | QTR4 | 24/25 | 409 | 6673207.01 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4652 | 44616915201 | 2023-11-15 | QTR2 | 23/24 | 2 | 3 | 259 | 447 | 447 | 0 | 0 | 0 | 188 | 0 | 5424973 | 53119 | 5371854 | 5477905 | 5676734 | 0 | 0 | 0 | 5676734 | 5654422 | -8426 | 52932 | 107 | 0 | 0 | 4345 | 0 | 30 | 0 | 53665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 58010 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-10 | QTR3 | 25/26 |  | 2025-08-14 | QTR1 | 25/26 | 408 | 5383942.21 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4654 | 44952015201 | 2024-01-31 | QTR3 | 23/24 | 2 | 8 | 289 | 471 | 469 | 2 | 0 | 0 | 182 | 0 | 5626066 | 61166 | 5564900 | 5715669 | 5782761 | 0 | 0 | 0 | 5782761 | 5777248 | -91 | 89603 | 124 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 4409 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2026-01-12 | QTR3 | 25/26 |  | 2025-11-13 | QTR2 | 25/26 | 412 | 6458891.07 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4657 | 44447715201 | 2023-12-06 | QTR2 | 23/24 | 3 | 5 | 353 | 689 | 687 | 2 | 0 | 0 | 336 | 0 | 8333362 | 73888 | 8259474 | 9056685 | 9730673 | 0 | 0 | 0 | 9730673 | 9691783 | -17540 | 723323 | 101 | 178 | 0 | 614708 | 8611 | 6 | 0 | 153984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 5372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 0 | 774065 | 8611 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2026-05-28 | QTR4 | 25/26 |  | 2026-04-15 | QTR4 | 25/26 | 409 | 8086004.65 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4661 | 44620015201 | 2024-03-27 | QTR3 | 23/24 | 4 | 4 | 422 | 432 | 352 | 80 | 0 | 0 | 33 | -46 | 9458464 | 113124 | 9345340 | 9790787 | 9649312 | 0 | 0 | 0 | 9649312 | 9617817 | -18533 | 566686 | 18 | 0 | 0 | 108078 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109406 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-21 | QTR3 | 25/26 |  | 2025-08-20 | QTR1 | 25/26 | 412 | 11108027.65 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4662 | 44001515201 | 2023-12-06 | QTR2 | 23/24 | 1 | 3 | 182 | 353 | 351 | 2 | 0 | 0 | 171 | 0 | 2710165 | 50000 | 2660165 | 2699856 | 2568771 | 0 | 0 | 0 | 2568771 | 2567076 | -16 | -10309 | 123 | 0 | 0 | 811 | 0 | 23 | 0 | -6653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | -5843 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-09-25 | QTR1 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 409 | 3354139.5 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4663 | 44764715201 | 2023-12-06 | QTR2 | 23/24 | 2 | 3 | 245 | 397 | 395 | 2 | 0 | 0 | 152 | 0 | 11192757 | 116425 | 11076332 | 11220679 | 11200266 | 0 | 0 | 0 | 11200266 | 11159153 | -30470 | 27922 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 17915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17915 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 |  | 2025-08-11 | QTR1 | 25/26 | 408 | 11705908.23 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4664 | 44699715201 | 2023-09-13 | QTR1 | 23/24 | 3 | 0 | 210 | 395 | 394 | 1 | 0 | 0 | 185 | 0 | 1247247 | 50000 | 1197247 | 1247247 | 1175544 | 0 | 0 | 0 | 1175544 | 1174544 | -1000 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-05-12 | QTR4 | 24/25 | 412 | 1347694.58 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4665 | 44619515201 | 2024-02-28 | QTR3 | 23/24 | 6 | 2 | 240 | 367 | 367 | 0 | 0 | 0 | 127 | 0 | 5489802 | 58699 | 5431104 | 5499093 | 5514945 | 0 | 0 | 0 | 5514945 | 5496131 | -18814 | 9291 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 9291 | 9291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9291 | 9291 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-07 | QTR3 | 25/26 |  | 2025-10-08 | QTR2 | 25/26 | 412 | 5906510.04 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4667 | 44764615201 | 2024-03-27 | QTR3 | 23/24 | 2 | 3 | 271 | 331 | 331 | 0 | 0 | 0 | 60 | 0 | 5722729 | 58760 | 5663969 | 5878728 | 5826172 | 0 | 0 | 0 | 5826172 | 5808077 | -12396 | 155998 | 38 | 0 | 0 | 1638 | 0 | 2 | 0 | 150300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 151938 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-01-05 | QTR3 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 408 | 5723687.91 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4677 | 44767915201 | 2024-05-22 | QTR4 | 23/24 | 4 | 3 | 276 | 298 | 271 | 27 | 0 | 0 | 36 | -28 | 7765433 | 82562 | 7682871 | 7871392 | 7668837 | 0 | 0 | 0 | 7668837 | 7663134 | -5703 | 211917 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24680 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2025-08-01 | QTR1 | 25/26 | 412 | 8421050.52 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4679 | 44619615201 | 2024-01-31 | QTR3 | 23/24 | 3 | 0 | 244 | 337 | 336 | 1 | 0 | 0 | 93 | 0 | 5469442 | 56677 | 5412765 | 5469442 | 5544372 | 0 | 0 | 0 | 5544372 | 5542177 | -2195 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-12-12 | QTR2 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 412 | 5971108.66 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4686 | 42957695201 | 2024-04-24 | QTR4 | 23/24 | 2 | 0 | 244 | 488 | 488 | 0 | 0 | 0 | 244 | 0 | 3298227 | 50000 | 3248227 | 3298227 | 3079319 | 0 | 0 | 0 | 3079319 | 3078260 | -1060 | 0 | 148 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2026-02-23 | QTR3 | 25/26 |  | 2026-01-09 | QTR3 | 25/26 | 412 | 3509812.2 |  |  | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4687 | 45222715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 167 | 237 | 237 | 0 | 0 | 0 | 70 | 0 | 1600545 | 50000 | 1550545 | 1600545 | 1508063 | 0 | 0 | 0 | 1508063 | 1508063 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | F273376792 | TRP CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-05-16 | QTR4 | 24/25 | 408 | 2128846.17 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4694 | 44767115201 | 2024-07-31 | QTR1 | 24/25 | 3 | 2 | 291 | 358 | 351 | 7 | 0 | 0 | 67 | -15 | 3150955 | 50000 | 3100955 | 3159605 | 3107001 | 0 | 0 | 0 | 3107001 | 3106285 | -716 | 33997 | 45 | 0 | 0 | 27775 | 0 | 0 | 0 | 21950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49724 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 |  | 2026-01-14 | QTR3 | 25/26 | 409 | 3340322.06 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4695 | 44394815201 | 2024-10-30 | QTR2 | 24/25 | 2 | 0 | 188 | 212 | 212 | 0 | 0 | 0 | 21 | 3 | 2565294 | 50000 | 2515294 | 2565294 | 2420314 | 0 | 0 | 0 | 2420314 | 2420700 | 386 | 0 | 14 | 0 | 3 | 921 | 921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 921 | 921 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2025-11-07 | QTR2 | 25/26 | 412 | 2864084.72 |  |  | 3 | 7 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4708 | 44754315201 | 2024-07-31 | QTR1 | 24/25 | 1 | 0 | 200 | 237 | 211 | 26 | 0 | 0 | 37 | 0 | 1300000 | 50000 | 1250000 | 1300000 | 1243700 | 0 | 0 | 0 | 1243700 | 1243700 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2025-08-05 | QTR1 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 412 | 1369377.1 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4Q32 | 43310845201 | 2015-04-27 | QTR4 | 14/15 | 2 | 51 | 1450 | 3156 | 3156 | 0 | 0 | 0 | 1179 | 527 | 148749800 | 150000 | 148599800 | 174962816 | 175180045 | 0 | 56000 | 56000 | 175236045 | 174744522 | -41128 | 26213016 | 414 | 0 | 0 | 1494952 | 0 | 0 | 0 | 142046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517 | 527 | 21512637 | 3321562 | 0 | 0 | 2751791 | 53052 | 0 | 0 | 0 | 0 | 186 | 0 | 468030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 703 | 527 | 26164878 | 3374614 | F592629362 | THE DE MOYA GROUP INC. | N/A | N/A | N/A | N/A | 2026-02-26 | QTR3 | 25/26 |  | 2024-05-24 | QTR4 | 23/24 | 412 | 122897181 | B10:B5:B8:::Y | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 0 | 176 | 0 | 0 | -204577 | 0 |  | DO
04DO | 04 | E4U48 | 44146615201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 281 | 416 | 416 | 0 | 0 | 0 | 135 | 0 | 2126000 | 50000 | 2076000 | 2132929 | 1513603 | 0 | 0 | 0 | 1513603 | 1506673 | 0 | 6930 | 77 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2025-08-04 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 409 | 2622051.6 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U88 | 43999925201 | 2023-04-07 | QTR4 | 22/23 | 1 | 3 | 764 | 860 | 713 | 147 | 0 | 0 | 96 | 0 | 10631541 | 85557 | 10545984 | 10738131 | 11100934 | 0 | 0 | 0 | 11100934 | 11070252 | -1518 | 106590 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77426 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 408 | 10492574.81 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V62 | 43695815201 | 2022-08-18 | QTR1 | 22/23 | 2 | 10 | 622 | 706 | 649 | 57 | 0 | 0 | 84 | 0 | 31058595 | 150000 | 30908595 | 33155117 | 32699199 | 0 | 0 | 0 | 32699199 | 32554410 | -144790 | 1946522 | 57 | 0 | 0 | 1746 | 0 | 0 | 0 | 1779105 | 8878 | 0 | 0 | 8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239103 | 0 | 0 | 0 | 79175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989203 | 8878 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2024-10-18 | QTR2 | 24/25 | 412 | 29695111.36 |  |  | 0 | 27 | 0 | 0 | -118750 | 0 |  | DO
04DO | 04 | E4W05 | 44047315201 | 2022-12-02 | QTR2 | 22/23 | 2 | 11 | 324 | 551 | 550 | 1 | 0 | 0 | 179 | 48 | 3993841 | 50000 | 3943841 | 4453325 | 4438530 | 0 | 0 | 0 | 4438530 | 4429433 | -6049 | 459484 | 135 | 0 | 0 | 14920 | 0 | 0 | 48 | 317478 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 48 | 425398 | 258 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-03-21 | QTR3 | 24/25 | 408 | 4033616.25 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W54 | 44618515201 | 2023-05-05 | QTR4 | 22/23 | 2 | 5 | 241 | 466 | 466 | 0 | 0 | 0 | 225 | 0 | 8153790 | 72216 | 8081573 | 8619435 | 8570644 | 0 | 0 | 0 | 8570644 | 8567270 | 0 | 469019 | 175 | 0 | 0 | 121843 | 1201843 | 0 | 0 | 314395 | 24985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3335 | 3335 | 0 | 0 | 22700 | 22700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462272 | 1252862 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-15 | QTR1 | 25/26 |  | 2025-02-14 | QTR3 | 24/25 | 412 | 7653131.2 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W61 | 44610415201 | 2023-08-04 | QTR1 | 23/24 | 1 | 1 | 287 | 408 | 408 | 0 | 0 | 0 | 121 | 0 | 5369226 | 50000 | 5319226 | 5369226 | 5576786 | 0 | 0 | 0 | 5576786 | 5571433 | -5352 | 104495 | 64 | 28 | 0 | 31492 | 0 | 0 | 0 | 7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 38981 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-10-21 | QTR2 | 25/26 |  | 2025-04-09 | QTR4 | 24/25 | 409 | 4627615.06 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W65 | 44617415201 | 2024-01-05 | QTR3 | 23/24 | 3 | 0 | 163 | 241 | 241 | 0 | 0 | 0 | 78 | 0 | 4920477 | 50000 | 4870477 | 4920477 | 4833727 | 0 | 0 | 0 | 4833727 | 4832964 | -763 | 0 | 39 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-15 | QTR1 | 25/26 |  | 2025-06-11 | QTR4 | 24/25 | 409 | 4972817.95 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W69 | 44617315201 | 2023-12-01 | QTR2 | 23/24 | 2 | 2 | 282 | 308 | 235 | 73 | 0 | 0 | 40 | -14 | 2294610 | 50000 | 2244610 | 2441883 | 2324253 | 0 | 0 | 0 | 2324253 | 2322959 | -1294 | 147274 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 32543 | 9889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32543 | 9889 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2026-05-12 | QTR4 | 25/26 |  | 2025-02-07 | QTR3 | 24/25 | 409 | 2294337.98 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W70 | 44617615201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 206 | 323 | 323 | 0 | 0 | 0 | 117 | 0 | 3860000 | 50000 | 3810000 | 3929208 | 3917472 | 0 | 0 | 0 | 3917472 | 3912966 | -4506 | 69208 | 62 | 30 | 0 | 113698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 113698 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2026-05-13 | QTR4 | 25/26 |  | 2026-01-05 | QTR3 | 25/26 | 409 | 3983140.23 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W71 | 44974015201 | 2023-05-05 | QTR4 | 22/23 | 1 | 0 | 82 | 523 | 522 | 1 | 0 | 0 | 441 | 0 | 827827 | 45348 | 782479 | 827827 | 848976 | 0 | 0 | 0 | 848976 | 848976 | 0 | 0 | 38 | 310 | 0 | 0 | 0 | 0 | 0 | 13151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 0 | 13151 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 412 | 1076147.07 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W72 | 44617015201 | 2023-11-03 | QTR2 | 23/24 | 3 | 5 | 182 | 306 | 303 | 3 | 0 | 0 | 105 | 19 | 4285836 | 50000 | 4235836 | 4430549 | 4413846 | 0 | 0 | 0 | 4413846 | 4401052 | -9192 | 144713 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 85267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 55844 | 55844 | 0 | 0 | 0 | 0 | 0 | 19 | 145465 | 55844 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-30 | QTR2 | 25/26 |  | 2025-06-16 | QTR4 | 24/25 | 408 | 4697027.08 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W82 | 44610515201 | 2024-01-05 | QTR3 | 23/24 | 2 | 2 | 274 | 356 | 355 | 1 | 0 | 0 | 82 | 0 | 4881711 | 57650 | 4824061 | 4893014 | 4759434 | 0 | 0 | 0 | 4759434 | 4740765 | -5116 | 11303 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 23092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 23092 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-04-17 | QTR4 | 24/25 | 409 | 5716819.1 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W88 | 44765415201 | 2024-02-02 | QTR3 | 23/24 | 3 | 3 | 233 | 271 | 240 | 31 | 0 | 0 | 55 | -17 | 6226524 | 63037 | 6163487 | 6395874 | 6393098 | 0 | 0 | 0 | 6393098 | 6379878 | -5542 | 169350 | 38 | 0 | 0 | 103394 | 103394 | 0 | 0 | 59105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162498 | 103394 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-04-09 | QTR4 | 24/25 | 412 | 6625403.9 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W89 | 44767415201 | 2024-07-12 | QTR1 | 24/25 | 1 | 1 | 180 | 262 | 260 | 2 | 0 | 0 | 82 | 0 | 3966137 | 50000 | 3916137 | 3985889 | 3958991 | 0 | 0 | 0 | 3958991 | 3953275 | -5716 | 19752 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19752 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-29 | QTR1 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 412 | 4276093.35 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W93 | 44764815201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 185 | 224 | 215 | 9 | 0 | 0 | 39 | 0 | 3198987 | 50000 | 3148987 | 3198987 | 3046918 | 0 | 0 | 0 | 3046918 | 3045966 | -952 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650284242 | TIMOTHY ROSE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-18 | QTR1 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 408 | 3443705 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X14 | 44932315201 | 2024-04-05 | QTR4 | 23/24 | 1 | 5 | 209 | 308 | 298 | 10 | 0 | 0 | 78 | 21 | 3689059 | 50000 | 3639059 | 3733032 | 3801506 | 0 | 0 | 0 | 3801506 | 3800583 | -923 | 43973 | 65 | 5 | 0 | 0 | 0 | 0 | 21 | 74766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 21 | 74766 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-12 | QTR3 | 25/26 |  | 2025-10-30 | QTR2 | 25/26 | 408 | 2884956.63 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X17 | 44655115201 | 2024-02-02 | QTR3 | 23/24 | 1 | 1 | 132 | 174 | 174 | 0 | 0 | 0 | 42 | 0 | 1849000 | 50000 | 1799000 | 1870772 | 1768167 | 0 | 0 | 0 | 1768167 | 1768167 | 0 | 21772 | 38 | 0 | 0 | 4117 | 0 | 0 | 0 | 22787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26904 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-09-12 | QTR1 | 25/26 |  | 2025-07-02 | QTR1 | 25/26 | 409 | 2011837.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X24 | 44931815201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 222 | 278 | 278 | 0 | 0 | 0 | 56 | 0 | 3983900 | 50853 | 3933047 | 4183008 | 4262893 | 0 | 0 | 0 | 4262893 | 4262893 | 0 | 199108 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199108 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 409 | 5126069.11 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X25 | 44766515201 | 2024-08-02 | QTR1 | 24/25 | 1 | 1 | 224 | 302 | 300 | 2 | 0 | 0 | 78 | 0 | 3160159 | 50000 | 3110159 | 3174469 | 3061340 | 0 | 0 | 0 | 3061340 | 3061200 | -140 | 14310 | 41 | 24 | 0 | 0 | 0 | 0 | 0 | 33144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 61710 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2025-12-02 | QTR2 | 25/26 | 409 | 3262205.68 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X26 | 44766715201 | 2024-10-04 | QTR2 | 24/25 | 3 | 3 | 208 | 217 | 180 | 37 | 0 | 0 | 19 | -10 | 1352924 | 50000 | 1302924 | 1396379 | 1294317 | 0 | 0 | 0 | 1294317 | 1294741 | 424 | 43455 | 9 | 6 | 0 | 5386 | 0 | 0 | 0 | 3300 | 1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 8686 | 1167 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2025-08-14 | QTR1 | 25/26 | 409 | 1552464.85 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X33 | 44359525201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 262 | 309 | 294 | 15 | 0 | 0 | 47 | 0 | 2579048 | 50000 | 2529048 | 2787519 | 2747199 | 0 | 0 | 0 | 2747199 | 2747177 | -22 | 208471 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 9697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218168 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-11-13 | QTR2 | 25/26 | 408 | 3891911.4 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X37 | 44768015201 | 2024-07-12 | QTR1 | 24/25 | 2 | 0 | 196 | 280 | 280 | 0 | 0 | 0 | 84 | 0 | 3165008 | 50000 | 3115008 | 3165008 | 3101006 | 0 | 0 | 0 | 3101006 | 3093987 | -7020 | 0 | 48 | 28 | 0 | 12230 | 0 | 0 | 0 | 17517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 29747 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-06-23 | QTR4 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 412 | 3833063.97 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X39 | 44768115201 | 2024-09-06 | QTR1 | 24/25 | 1 | 1 | 170 | 193 | 193 | 0 | 0 | 0 | 23 | 0 | 2519093 | 50000 | 2469093 | 2519093 | 2422842 | 0 | 0 | 0 | 2422842 | 2420995 | -1848 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-08-21 | QTR1 | 25/26 | 412 | 2812112.37 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X44 | 44766015201 | 2024-10-04 | QTR2 | 24/25 | 1 | 0 | 210 | 234 | 215 | 19 | 0 | 0 | 24 | 0 | 2684615 | 50000 | 2634615 | 2684615 | 2436599 | 0 | 0 | 0 | 2436599 | 2436934 | 335 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2026-04-16 | QTR4 | 25/26 |  | 2025-10-30 | QTR2 | 25/26 | 409 | 2738308.26 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4X51 | 44765815201 | 2024-08-02 | QTR1 | 24/25 | 3 | 1 | 252 | 287 | 265 | 22 | 0 | 0 | 35 | 0 | 3535833 | 50000 | 3485833 | 3535833 | 3387300 | 0 | 0 | 0 | 3387300 | 3384814 | -2487 | 0 | 14 | 0 | 0 | 13204 | 0 | 0 | 0 | 7499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20703 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 |  | 2025-09-03 | QTR1 | 25/26 | 409 | 3764178.43 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5650 | 23839555201 | 2020-03-11 | QTR3 | 19/20 | 7 | 12 | 1030 | 1956 | 1956 | 0 | 0 | 0 | 711 | 215 | 44960000 | 248112 | 44711888 | 46736451 | 46188504 | 0 | 0 | 0 | 46188504 | 47664520 | 1546573 | 1776451 | 295 | 0 | 57 | 769813 | 208395 | 0 | 169 | 1007439 | 1180290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63867 | 0 | 0 | 0 | 48656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 1889774 | 1388685 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-02-05 | QTR3 | 25/26 |  | 2025-12-03 | QTR2 | 25/26 | 515 | 45602807.97 |  |  | 203 | 416 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5686 | 43667915201 | 2020-05-20 | QTR4 | 19/20 | 7 | 19 | 350 | 1425 | 1427 | -2 | 2 | 0 | 143 | 932 | 10409198 | 154537 | 10254661 | 14440107 | 14275037 | -18086 | 0 | -18086 | 14256951 | 14546139 | 445847 | 4030909 | 93 | 0 | 133 | 999497 | 429 | 0 | 83 | 782660 | 53882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 1802110 | 54311 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-05-14 | QTR4 | 25/26 |  | 2025-02-21 | QTR3 | 24/25 | 507 | 9656860.63 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5706 | 42955615201 | 2020-03-25 | QTR3 | 19/20 | 6 | 12 | 1100 | 1761 | 1761 | 0 | 0 | 0 | 559 | 102 | 44888403 | 150000 | 44738403 | 47699589 | 48432679 | 0 | 0 | 0 | 48432679 | 48287387 | 2317108 | 2811186 | 343 | 0 | 0 | 1647033 | 0 | 0 | 102 | 784469 | 30264 | 0 | 0 | 9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26536 | 0 | 0 | 0 | 12848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 2823138 | 30264 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 513 | 37019154.5 |  |  | 0 | 216 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5718 | 43763415201 | 2021-04-28 | QTR4 | 20/21 | 7 | 17 | 690 | 1399 | 1340 | 59 | 0 | 0 | 674 | 35 | 11250000 | 233500 | 11016500 | 12978309 | 13223828 | 0 | 0 | 0 | 13223828 | 13314228 | 155455 | 1728309 | 360 | 0 | 25 | 527918 | 11401 | 0 | 0 | 912863 | 0 | 0 | 10 | 40741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56556 | 0 | 0 | 0 | 355913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1901807 | 11401 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-10-23 | QTR2 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 507 | 10799982.79 |  |  | 28 | 314 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5724 | 44111315201 | 2022-06-15 | QTR4 | 21/22 | 6 | 20 | 950 | 1135 | 1034 | 101 | 0 | 0 | 134 | 51 | 82895000 | 150000 | 82745000 | 89148107 | 90565070 | 0 | 897177 | 897177 | 91462247 | 89663672 | -1630727 | 6253107 | 70 | 0 | 98 | 2491682 | 1246739 | 0 | 0 | 3506222 | 15924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9339 | 0 | 0 | 0 | 113493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 6135826 | 1262662 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-05-11 | QTR4 | 25/26 |  | 2025-09-26 | QTR1 | 25/26 | 509 | 78970683.66 | A5 | ICC - BAM/BONUS | 0 | 64 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5736 | 41503065201 | 2021-05-26 | QTR4 | 20/21 | 9 | 10 | 640 | 1357 | 1351 | 6 | 0 | 0 | 517 | 200 | 19997789 | 347736 | 19650053 | 21610437 | 21395577 | 0 | 0 | 0 | 21395577 | 21020146 | -65708 | 1612647 | 279 | 0 | 0 | 233130 | 0 | 0 | 90 | 1120476 | 44665 | 0 | 110 | 243132 | 66051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1762159 | 110716 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-06-23 | QTR4 | 25/26 |  | 2025-09-19 | QTR1 | 25/26 | 507 | 17595887.28 |  |  | 0 | 238 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5747 | 43366115201 | 2022-05-25 | QTR4 | 21/22 | 5 | 7 | 280 | 568 | 568 | 0 | 0 | 0 | 156 | 132 | 6696978 | 50000 | 6646978 | 7142732 | 7032054 | 0 | 0 | 0 | 7032054 | 7019736 | 0 | 445755 | 106 | 0 | 4 | 88147 | 0 | 0 | 5 | 26731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318 | 0 | 0 | 125 | 296588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 425240 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-07 | QTR2 | 25/26 |  | 2024-10-22 | QTR2 | 24/25 | 512 | 5918166.26 |  |  | 7 | 50 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5759 | 44586715201 | 2023-04-26 | QTR4 | 22/23 | 5 | 6 | 170 | 600 | 588 | 12 | 0 | 0 | 430 | 0 | 3865830 | 50000 | 3815830 | 3991018 | 3937381 | 0 | 0 | 0 | 3937381 | 3936003 | -1378 | 125188 | 128 | 0 | 0 | -12273 | 0 | 0 | 0 | -103071 | 39310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251410 | 185032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136067 | 224342 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-08-13 | QTR1 | 25/26 | 514 | 3318268.57 |  |  | 0 | 302 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5760 | 44114515201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 320 | 519 | 515 | 4 | 0 | 0 | 199 | 0 | 9020145 | 60000 | 8960145 | 9091224 | 9371724 | 0 | 0 | 0 | 9371724 | 9358265 | -1051 | 71079 | 39 | 0 | 0 | 75886 | 0 | 30 | 0 | 29231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 110730 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2025-06-27 | QTR4 | 24/25 | 509 | 8000814.19 |  |  | 0 | 130 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5777 | 44042425201 | 2023-01-25 | QTR3 | 22/23 | 3 | 5 | 650 | 704 | 611 | 93 | 0 | 0 | 86 | -32 | 22896706 | 150000 | 22746706 | 23663870 | 23767312 | 0 | 0 | 0 | 23767312 | 22921260 | -826558 | 767164 | 32 | 0 | 0 | 12008 | 0 | 0 | 0 | 265981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302220 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 28387049.83 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5778 | 44569215201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 250 | 396 | 395 | 1 | 0 | 0 | 146 | 0 | 1617324 | 47000 | 1570324 | 1637324 | 1467772 | 0 | 0 | 0 | 1467772 | 1467140 | -632 | 20000 | 119 | 0 | 0 | 34331 | 0 | 0 | 0 | 28098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62429 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-01-30 | QTR3 | 24/25 | 509 | 1625738.6 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5786 | 44521715201 | 2023-06-14 | QTR4 | 22/23 | 4 | 2 | 410 | 545 | 545 | 0 | 0 | 0 | 135 | 0 | 10986719 | 117744 | 10868975 | 11011859 | 11062198 | 0 | 0 | 0 | 11062198 | 11032701 | -4358 | 25139 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-10-28 | QTR2 | 25/26 |  | 2025-04-10 | QTR4 | 24/25 | 512 | 14985674.13 |  |  | 0 | 55 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5789 | 43547125201 | 2023-05-24 | QTR4 | 22/23 | 3 | 3 | 360 | 467 | 467 | 0 | 0 | 0 | 92 | 15 | 8448064 | 70000 | 8378064 | 8800372 | 8800513 | 0 | 0 | 0 | 8800513 | 8740511 | 855 | 352308 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 93573 | 14238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 221451 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 318271 | 14238 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-10-22 | QTR2 | 25/26 |  | 2024-12-17 | QTR2 | 24/25 | 515 | 8153514.72 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5792 | 41025135201 | 2023-06-14 | QTR4 | 22/23 | 3 | 9 | 610 | 822 | 816 | 6 | 0 | 0 | 180 | 32 | 15097285 | 150000 | 14947285 | 15626114 | 15519395 | 0 | 0 | 0 | 15519395 | 15475580 | -7963 | 1098563 | 116 | 0 | 0 | 64465 | 0 | 0 | 32 | 474785 | 8321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592234 | 0 | 0 | 0 | 1431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1132914 | 8321 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-13 | QTR3 | 25/26 |  | 2025-12-08 | QTR2 | 25/26 | 513 | 25813007.18 |  |  | 14 | 64 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5795 | 24259285201 | 2023-06-14 | QTR4 | 22/23 | 3 | 4 | 380 | 531 | 523 | 8 | 0 | 0 | 92 | 59 | 8347803 | 60000 | 8287803 | 8496009 | 8830863 | 0 | 0 | 0 | 8830863 | 8791083 | -490 | 148206 | 43 | 0 | 59 | 0 | 0 | 0 | 0 | 139202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 145982 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 507 | 8013785.1 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5796 | 42617915201 | 2023-07-26 | QTR1 | 23/24 | 4 | 3 | 280 | 563 | 562 | 1 | 0 | 0 | 230 | 53 | 3346229 | 50000 | 3296229 | 3547942 | 3223459 | 0 | 0 | 0 | 3223459 | 3212971 | -31 | 201713 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 191255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 191255 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2026-01-07 | QTR3 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 512 | 4393698.6 |  |  | 0 | 133 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5797 | 44568915201 | 2023-07-26 | QTR1 | 23/24 | 3 | 3 | 250 | 490 | 490 | 0 | 0 | 0 | 52 | 188 | 6209544 | 50000 | 6159544 | 6295030 | 5955348 | 0 | 0 | 0 | 5955348 | 5947678 | -685 | 85486 | 29 | 0 | 188 | 78501 | 61993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 78501 | 61993 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-01-14 | QTR3 | 25/26 |  | 2025-06-04 | QTR4 | 24/25 | 514 | 5653228.56 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5798 | 44569415201 | 2023-11-15 | QTR2 | 23/24 | 4 | 8 | 460 | 743 | 743 | 0 | 0 | 0 | 115 | 168 | 16797190 | 150000 | 16647190 | 17496951 | 17878429 | 0 | 0 | 0 | 17878429 | 17802427 | -28255 | 699761 | 63 | 0 | 10 | 136859 | 0 | 0 | 158 | 535108 | 233146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 671967 | 233146 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-06-24 | QTR4 | 25/26 |  | 2026-05-07 | QTR4 | 25/26 | 509 | 15802710.41 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5800 | 44585515201 | 2023-07-26 | QTR1 | 23/24 | 3 | 5 | 230 | 409 | 491 | -82 | 82 | 0 | 93 | 86 | 3679712 | 50000 | 3629712 | 3851805 | 3808215 | 0 | 0 | 0 | 3808215 | 3802526 | -69 | 172092 | 61 | 0 | 84 | 71357 | 36514 | 0 | 9 | 67803 | 17258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 29703 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 174435 | 53772 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 |  | 2025-06-05 | QTR4 | 24/25 | 514 | 2818721.96 |  |  | 15 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5801 | 44521915201 | 2023-09-27 | QTR1 | 23/24 | 3 | 1 | 370 | 513 | 509 | 4 | 0 | 0 | 143 | 0 | 15286323 | 100000 | 15186323 | 15295366 | 15592805 | 0 | 0 | 0 | 15592805 | 15522129 | -61634 | 9043 | 97 | 0 | 0 | 33061 | 0 | 0 | 0 | 46645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79706 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 513 | 20005006.42 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5804 | 43757515201 | 2024-05-22 | QTR4 | 23/24 | 1 | 2 | 160 | 223 | 223 | 0 | 0 | 0 | 63 | 0 | 3278993 | 50000 | 3228993 | 3308018 | 3163264 | 0 | 0 | 0 | 3163264 | 3163188 | -76 | 29025 | 59 | 0 | 0 | -17884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17884 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-01-14 | QTR3 | 25/26 |  | 2025-08-23 | QTR1 | 25/26 | 509 | 3131835.47 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5805 | 44709215201 | 2023-09-27 | QTR1 | 23/24 | 1 | 1 | 280 | 334 | 332 | 2 | 0 | 0 | 54 | 0 | 3271306 | 50000 | 3221306 | 3287930 | 3244926 | 0 | 0 | 0 | 3244926 | 3224506 | -20420 | 16623 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16623 | 16623 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2024-11-26 | QTR2 | 24/25 | 514 | 4597690.87 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5806 | 44709815201 | 2023-09-27 | QTR1 | 23/24 | 3 | 3 | 300 | 435 | 431 | 4 | 0 | 0 | 135 | 0 | 9892142 | 110000 | 9782142 | 9938977 | 10455307 | 0 | 0 | 0 | 10455307 | 10363664 | -58186 | 46835 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13379 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-08-07 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 515 | 11922850 |  |  | 0 | 62 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5809 | 43915615201 | 2023-09-27 | QTR1 | 23/24 | 4 | 2 | 420 | 517 | 481 | 36 | 0 | 0 | 97 | 0 | 19059007 | 150000 | 18909007 | 19456279 | 20132774 | 0 | 0 | 0 | 20132774 | 19987244 | -74410 | 397272 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333760 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-10-06 | QTR2 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 513 | 20470643.27 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5811 | 43233215201 | 2023-10-25 | QTR2 | 23/24 | 6 | 6 | 250 | 541 | 540 | 1 | 0 | 0 | 176 | 115 | 15324226 | 150000 | 15174226 | 16443632 | 16758792 | 0 | 0 | 0 | 16758792 | 16617261 | -118108 | 1119406 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 614667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51362 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 62034 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 380350 | 643594 | 0 | 0 | 0 | 0 | 10 | 115 | 1108414 | 643594 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-18 | QTR2 | 25/26 |  | 2025-08-04 | QTR1 | 25/26 | 515 | 22228374.21 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5813 | 44529715201 | 2024-05-22 | QTR4 | 23/24 | 8 | 8 | 350 | 524 | 523 | 1 | 0 | 0 | 118 | 56 | 12355556 | 110600 | 12244956 | 12704374 | 12876675 | 0 | 0 | 0 | 12876675 | 12856184 | -4437 | 348818 | 54 | 0 | 0 | 11111 | 0 | 0 | 56 | 180890 | 10678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 334941 | 10678 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2026-01-30 | QTR3 | 25/26 | 515 | 11348052.96 |  |  | 46 | 64 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5826 | 45222915201 | 2024-05-22 | QTR4 | 23/24 | 1 | 0 | 200 | 276 | 273 | 3 | 0 | 0 | 76 | 0 | 1180815 | 50000 | 1130815 | 1180815 | 979467 | 0 | 0 | 0 | 979467 | 979467 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-07-08 | QTR1 | 25/26 | 507 | 1609251.1 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5830 | 44711715201 | 2024-08-28 | QTR1 | 24/25 | 1 | 1 | 340 | 422 | 419 | 3 | 0 | 0 | 62 | 20 | 5590573 | 93262 | 5497311 | 5668631 | 5521349 | 0 | 0 | 0 | 5521349 | 5521187 | -162 | 78058 | 27 | 0 | 20 | 78058 | 72368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 78058 | 72368 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-04-29 | QTR4 | 25/26 |  | 2026-01-08 | QTR3 | 25/26 | 513 | 9572296.4 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5833 | 44708915201 | 2024-09-25 | QTR1 | 24/25 | 2 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 2100000 | 50000 | 2050000 | 2100000 | 2001416 | 0 | 0 | 0 | 2001416 | 2001416 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-07-30 | QTR1 | 25/26 | 513 | 2701146.14 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5835 | 44873915201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 160 | 209 | 209 | 0 | 0 | 0 | 49 | 0 | 3081418 | 50000 | 3031418 | 3081418 | 3111059 | 0 | 0 | 0 | 3111059 | 3112003 | 944 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-03 | QTR2 | 25/26 |  | 2025-09-02 | QTR1 | 25/26 | 515 | 3300432.25 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5838 | 44761015201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 290 | 331 | 331 | 0 | 0 | 0 | 41 | 0 | 7714913 | 89000 | 7625913 | 7714913 | 7712132 | 0 | 0 | 0 | 7712132 | 7711973 | -159 | 0 | 24 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-05-05 | QTR4 | 25/26 |  | 2026-03-17 | QTR3 | 25/26 | 507 | 9228481.44 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5845 | 45022725201 | 2025-01-29 | QTR3 | 24/25 | 1 | 0 | 160 | 255 | 255 | 0 | 0 | 0 | 95 | 0 | 2046788 | 50000 | 1996788 | 2046788 | 2023608 | 0 | 0 | 0 | 2023608 | 2023608 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2026-06-12 | QTR4 | 25/26 |  | 2026-04-16 | QTR4 | 25/26 | 562 | 2468960.18 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5846 | 44879915201 | 2025-02-26 | QTR3 | 24/25 | 1 | 0 | 97 | 148 | 147 | 1 | 0 | 0 | 51 | 0 | 1377191 | 50000 | 1327191 | 1377191 | 1301358 | 0 | 0 | 0 | 1301358 | 1301358 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-04-13 | QTR4 | 25/26 |  | 2025-11-24 | QTR2 | 25/26 | 507 | 1307521.49 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5856 | 45331815201 | 2025-06-11 | QTR4 | 24/25 | 1 | 0 | 100 | 130 | 116 | 14 | 0 | 0 | 30 | 0 | 549199 | 34000 | 515199 | 549199 | 499315 | 0 | 0 | 0 | 499315 | 499315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2026-05-01 | QTR4 | 25/26 |  | 2026-03-31 | QTR3 | 25/26 | 513 | 501262.75 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5857 | 45613715201 | 2025-02-26 | QTR3 | 24/25 | 2 | 1 | 40 | 40 | 10 | 30 | 0 | 0 | 0 | 0 | 117123 | 7000 | 110123 | 113191 | 103346 | 0 | 0 | 0 | 103346 | 103346 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-09-17 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 513 | 180485.52 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5858 | 45616815201 | 2025-03-26 | QTR3 | 24/25 | 5 | 3 | 120 | 130 | 105 | 25 | 0 | 0 | 10 | 0 | 948635 | 47500 | 901135 | 993577 | 604185 | 0 | 0 | 0 | 604185 | 604185 | 0 | 44942 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 44942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44942 | 0 | F850531344 | PREMIER PAVING LLC | N/A | N/A | N/A | N/A | 2026-01-09 | QTR3 | 25/26 |  | 2025-09-16 | QTR1 | 25/26 | 514 | 1621409.55 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T9030 | 44199035223 | 2023-10-25 | QTR2 | 23/24 | 1 | 1 | 270 | 367 | 366 | 1 | 0 | 0 | 97 | 0 | 5555556 | 53950 | 5501606 | 5605113 | 5565155 | 0 | 0 | 0 | 5565155 | 5565155 | 0 | 49558 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 49558 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-05-05 | QTR4 | 24/25 | 513 | 5529999.88 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50B8 | 44521515201 | 2023-06-06 | QTR4 | 22/23 | 4 | 6 | 410 | 645 | 641 | 4 | 0 | 0 | 154 | 81 | 11282143 | 100000 | 11182143 | 11851012 | 12077791 | 0 | 0 | 0 | 12077791 | 12077791 | 0 | 568869 | 109 | 0 | 6 | 419002 | 23191 | 0 | 37 | 361551 | 8287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 56263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 601391 | 31478 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-03-02 | QTR3 | 25/26 |  | 2025-09-05 | QTR1 | 25/26 | 514 | 10131956.15 |  |  | 44 | 45 | 0 | 0 | -235426 | 0 |  | DO
05DO | 05 | E50F1 | 44656815201 | 2024-02-06 | QTR3 | 23/24 | 1 | 0 | 127 | 172 | 172 | 0 | 0 | 0 | 43 | 2 | 1104118 | 42000 | 1062118 | 1104118 | 1062935 | 0 | 0 | 0 | 1062935 | 1062929 | -6 | 0 | 25 | 0 | 2 | 5887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5887 | 0 | F455448578 | TRAFFIC ENGINEERING AND MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 509 | 1174163.5 |  |  | 2 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E50F5 | 44316915201 | 2024-01-04 | QTR3 | 23/24 | 1 | 1 | 290 | 430 | 429 | 1 | 0 | 0 | 71 | 69 | 5036336 | 50000 | 4986336 | 5073420 | 4545253 | 0 | 0 | 0 | 4545253 | 4525803 | -19451 | 37085 | 45 | 0 | 0 | 0 | 0 | 0 | 69 | 62085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 62085 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-06-05 | QTR4 | 24/25 | 514 | 5619045.42 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F2 | 44768815201 | 2024-04-02 | QTR4 | 23/24 | 2 | 1 | 150 | 239 | 238 | 1 | 0 | 0 | 72 | 17 | 1504656 | 50000 | 1454656 | 1506430 | 1447570 | 0 | 0 | 0 | 1447570 | 1445324 | -472 | 1774 | 46 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-21 | QTR4 | 24/25 | 514 | 1590260.07 |  |  | 17 | 26 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F6 | 43923415201 | 2024-03-05 | QTR3 | 23/24 | 3 | 3 | 350 | 458 | 457 | 1 | 0 | 0 | 108 | 0 | 16652098 | 150000 | 16502098 | 16895551 | 16781249 | 0 | 0 | 0 | 16781249 | 16753875 | -23602 | 243453 | 50 | 0 | 0 | 254263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254263 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-12-04 | QTR2 | 25/26 | 512 | 16309344.71 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F7 | 44530215201 | 2024-03-05 | QTR3 | 23/24 | 3 | 5 | 250 | 400 | 400 | 0 | 0 | 0 | 130 | 20 | 5562121 | 50000 | 5512121 | 5724310 | 5880473 | 0 | 0 | 0 | 5880473 | 5842942 | -14889 | 162189 | 89 | 0 | 0 | 29317 | 0 | 0 | 20 | 112422 | 22050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 141739 | 22050 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-09 | QTR2 | 25/26 |  | 2025-10-01 | QTR2 | 25/26 | 512 | 6330177.48 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51F9 | 43912415201 | 2024-04-02 | QTR4 | 23/24 | 2 | 2 | 260 | 347 | 320 | 27 | 0 | 0 | 72 | 15 | 4408516 | 58000 | 4350516 | 4442576 | 4279968 | 0 | 0 | 0 | 4279968 | 4272484 | 0 | 34060 | 38 | 0 | 0 | 3850 | 0 | 0 | 0 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30938 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-19 | QTR4 | 24/25 | 513 | 6688704.65 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F2 | 44879115201 | 2024-10-01 | QTR2 | 24/25 | 1 | 3 | 170 | 268 | 268 | 0 | 0 | 0 | 93 | 5 | 7065614 | 86000 | 6979614 | 7183452 | 7253477 | 0 | 0 | 0 | 7253477 | 7256561 | 3084 | 117838 | 75 | 0 | 5 | 62000 | 0 | 0 | 0 | 47838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 109838 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 514 | 8985393.39 |  |  | 5 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F5 | 44880015201 | 2024-09-04 | QTR1 | 24/25 | 1 | 0 | 130 | 322 | 321 | 1 | 0 | 0 | 167 | 25 | 3585802 | 50000 | 3535802 | 3585802 | 3601966 | 0 | 0 | 0 | 3601966 | 3601961 | -5 | 0 | 59 | 0 | 3 | 45461 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 45461 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2026-01-06 | QTR3 | 25/26 | 514 | 3427520.56 |  |  | 25 | 108 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F6 | 44880115201 | 2024-08-08 | QTR1 | 24/25 | 1 | 0 | 270 | 372 | 353 | 19 | 0 | 0 | 88 | 14 | 5664533 | 50000 | 5614533 | 5664533 | 5824248 | 0 | 0 | 0 | 5824248 | 5821719 | -2529 | 0 | 50 | 0 | 0 | 6765 | 0 | 0 | 14 | 12871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 19636 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2026-02-24 | QTR3 | 25/26 |  | 2025-11-25 | QTR2 | 25/26 | 509 | 5574707.4 |  |  | 14 | 38 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F7 | 44984515201 | 2024-12-03 | QTR2 | 24/25 | 1 | 0 | 130 | 255 | 255 | 0 | 0 | 0 | 125 | 0 | 925088 | 40024 | 885064 | 925088 | 953719 | 0 | 0 | 0 | 953719 | 953719 | 0 | 0 | 115 | 0 | 0 | 2525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2525 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-01-13 | QTR3 | 25/26 |  | 2025-11-18 | QTR2 | 25/26 | 507 | 845921.65 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53F8 | 45022745201 | 2024-06-04 | QTR4 | 23/24 | 1 | 1 | 160 | 259 | 257 | 2 | 0 | 0 | 78 | 21 | 1498164 | 50000 | 1448164 | 1498164 | 1468694 | 0 | 0 | 0 | 1468694 | 1468694 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 24155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24155 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-08-21 | QTR1 | 25/26 |  | 2025-07-11 | QTR1 | 25/26 | 513 | 1507974.75 |  |  | 0 | 66 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54B3 | 44521415201 | 2023-10-03 | QTR2 | 23/24 | 3 | 3 | 270 | 366 | 366 | 0 | 0 | 0 | 96 | 0 | 6964127 | 72500 | 6891627 | 7171619 | 7043664 | 0 | 0 | 0 | 7043664 | 6984590 | -45651 | 207492 | 59 | 0 | 0 | 167324 | 0 | 0 | 0 | 41679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256083 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2025-09-02 | QTR1 | 25/26 |  | 2025-03-11 | QTR3 | 24/25 | 514 | 9627438.59 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54F0 | 45141535201 | 2024-12-03 | QTR2 | 24/25 | 1 | 0 | 160 | 274 | 274 | 0 | 0 | 0 | 84 | 30 | 3082346 | 50000 | 3032346 | 3082346 | 3072912 | 0 | 0 | 0 | 3072912 | 3072912 | 0 | 0 | 4 | 0 | 30 | 7407 | 6369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 7407 | 6369 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2026-05-01 | QTR4 | 25/26 |  | 2026-03-13 | QTR3 | 25/26 | 512 | 4142464.65 |  |  | 30 | 80 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55F3 | 45131115201 | 2025-02-04 | QTR3 | 24/25 | 1 | 0 | 150 | 183 | 183 | 0 | 0 | 0 | 33 | 0 | 4402920 | 58000 | 4344920 | 4402920 | 4332664 | 0 | 0 | 0 | 4332664 | 4326586 | -6078 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 13234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13234 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-06 | QTR3 | 25/26 |  | 2025-11-05 | QTR2 | 25/26 | 513 | 6422896.48 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55F4 | 42690555201 | 2025-04-01 | QTR4 | 24/25 | 1 | 0 | 120 | 121 | 108 | 13 | 0 | 0 | 1 | 0 | 1132509 | 50000 | 1082509 | 1132509 | 1025664 | 0 | 0 | 0 | 1025664 | 1025664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES LLC | N/A | N/A | N/A | N/A | 2026-03-30 | QTR3 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 514 | 1246519.8 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55F6 | 44529815201 | 2025-03-04 | QTR3 | 24/25 | 1 | 2 | 180 | 230 | 214 | 16 | 0 | 0 | 50 | 0 | 7863435 | 100000 | 7763435 | 8058116 | 8341201 | 0 | 0 | 0 | 8341201 | 8333175 | -8027 | 194681 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 194681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194681 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-12-12 | QTR2 | 25/26 | 514 | 10455826.3 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55F9 | 45370915201 | 2025-08-05 | QTR1 | 25/26 | 1 | 0 | 130 | 198 | 159 | 39 | 0 | 0 | 68 | 0 | 494060 | 26106 | 467954 | 494060 | 523498 | 0 | 0 | 0 | 523498 | 523851 | 353 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2026-05-19 | QTR4 | 25/26 |  | 2026-04-13 | QTR4 | 25/26 | 513 | 553243.95 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B6 | 44521115201 | 2023-06-06 | QTR4 | 22/23 | 2 | 1 | 180 | 442 | 442 | 0 | 0 | 0 | 205 | 57 | 3196756 | 50000 | 3146756 | 3198241 | 3427202 | 0 | 0 | 0 | 3427202 | 3427202 | 0 | 1485 | 141 | 0 | 7 | 8757 | 0 | 0 | 30 | 12941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 28133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 49830 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2025-12-23 | QTR2 | 25/26 |  | 2025-05-21 | QTR4 | 24/25 | 507 | 3501358.08 |  |  | 57 | 64 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56F2 | 45057615201 | 2025-04-01 | QTR4 | 24/25 | 1 | 4 | 250 | 270 | 198 | 72 | 0 | 0 | 33 | -13 | 6262690 | 65000 | 6197690 | 6580074 | 6638647 | 0 | 0 | 0 | 6638647 | 6638621 | -26 | 317384 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 87115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97504 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2026-05-19 | QTR4 | 25/26 |  | 2026-02-03 | QTR3 | 25/26 | 507 | 7148293.32 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56F4 | 41025155201 | 2025-05-06 | QTR4 | 24/25 | 1 | 0 | 140 | 173 | 171 | 2 | 0 | 0 | 33 | 0 | 3296100 | 53000 | 3243100 | 3296100 | 3182948 | 0 | 0 | 0 | 3182948 | 3193975 | 11027 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-04 | QTR3 | 25/26 |  | 2026-01-23 | QTR3 | 25/26 | 513 | 5178576.2 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56F7 | 45305815201 | 2025-04-01 | QTR4 | 24/25 | 1 | 0 | 190 | 217 | 196 | 21 | 0 | 0 | 27 | 0 | 6639966 | 78000 | 6561966 | 6639966 | 6618677 | 0 | 0 | 0 | 6618677 | 6618677 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2026-03-05 | QTR3 | 25/26 |  | 2026-01-15 | QTR3 | 25/26 | 509 | 8028735.15 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B2 | 44531615201 | 2024-05-07 | QTR4 | 23/24 | 4 | 4 | 350 | 396 | 338 | 58 | 0 | 0 | 46 | 0 | 5768393 | 58600 | 5709793 | 5840924 | 5658500 | 0 | 0 | 0 | 5658500 | 5645120 | -2740 | 72531 | 25 | 0 | 0 | 58741 | 0 | 0 | 0 | 1891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60632 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2026-06-17 | QTR4 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 507 | 6011562.42 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B3 | 24259265201 | 2023-06-06 | QTR4 | 22/23 | 3 | 4 | 590 | 703 | 696 | 7 | 0 | 0 | 113 | 0 | 9899345 | 50000 | 9849345 | 10080554 | 10364962 | 0 | 0 | 0 | 10364962 | 10344890 | -9 | 181208 | 61 | 0 | 0 | 111146 | 0 | 0 | 0 | 51682 | 1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162828 | 1682 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2025-12-19 | QTR2 | 25/26 |  | 2025-09-23 | QTR1 | 25/26 | 507 | 8480188.02 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B4 | 44198215201 | 2023-06-06 | QTR4 | 22/23 | 1 | 1 | 280 | 923 | 913 | 10 | 0 | 0 | 643 | 0 | 3503151 | 50000 | 3453151 | 3638714 | 3552928 | 0 | 0 | 0 | 3552928 | 3552928 | 0 | 135563 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 135563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 5102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 140665 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2026-03-06 | QTR3 | 25/26 | 562 | 3345708.84 |  |  | 0 | 275 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B5 | 44530315201 | 2023-06-06 | QTR4 | 22/23 | 3 | 3 | 490 | 635 | 634 | 1 | 0 | 0 | 145 | 0 | 11137584 | 50000 | 11087584 | 11274458 | 11215283 | 0 | 0 | 0 | 11215283 | 11200767 | -786 | 136874 | 80 | 0 | 0 | 39281 | 0 | 0 | 0 | 110135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149459 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 |  | 2025-08-01 | QTR1 | 25/26 | 507 | 8364007.55 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B7 | 44708515201 | 2023-06-06 | QTR4 | 22/23 | 3 | 5 | 500 | 634 | 634 | 0 | 0 | 0 | 128 | 6 | 13078910 | 128000 | 12950910 | 13273764 | 13547486 | 0 | 0 | 0 | 13547486 | 13528029 | -2602 | 194854 | 81 | 0 | 0 | 39880 | 0 | 0 | 32 | 217171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 257051 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-06-20 | QTR4 | 24/25 | 514 | 13524204.48 | A5 | ICC - BAM/BONUS | 8 | 47 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57B8 | 44709015201 | 2024-06-04 | QTR4 | 23/24 | 1 | 4 | 200 | 521 | 521 | 0 | 0 | 0 | 161 | 160 | 3852254 | 50000 | 3802254 | 4394289 | 4697644 | 0 | 0 | 0 | 4697644 | 4695025 | -2619 | 542035 | 78 | 0 | 0 | 1000 | 0 | 0 | 160 | 271211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 581771 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-06-23 | QTR4 | 25/26 |  | 2026-04-08 | QTR4 | 25/26 | 509 | 3125051.88 |  |  | 7 | 83 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57F0 | 45057715201 | 2025-07-01 | QTR1 | 25/26 | 1 | 0 | 100 | 121 | 102 | 19 | 0 | 0 | 21 | 0 | 339907 | 17000 | 322907 | 339907 | 317523 | 0 | 0 | 0 | 317523 | 317523 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F333155560 | YOROCA ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2026-06-12 | QTR4 | 25/26 |  | 2026-01-19 | QTR3 | 25/26 | 509 | 405078.25 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58F1 | 44529515201 | 2025-09-03 | QTR1 | 25/26 | 1 | 3 | 200 | 221 | 178 | 43 | 0 | 0 | 31 | -10 | 5893242 | 80000 | 5813242 | 5963607 | 6069935 | 0 | 0 | 0 | 6069935 | 6073721 | 3786 | 70365 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-06-22 | QTR4 | 25/26 |  | 2026-04-28 | QTR4 | 25/26 | 515 | 8198292.58 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58F2 | 45063515201 | 2025-09-03 | QTR1 | 25/26 | 1 | 0 | 100 | 102 | 66 | 36 | 0 | 0 | 2 | 0 | 592801 | 34000 | 558801 | 592801 | 526193 | 0 | 0 | 0 | 526193 | 526193 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-05-01 | QTR4 | 25/26 |  | 2026-03-25 | QTR3 | 25/26 | 515 | 700854.4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58F3 | 45077215201 | 2025-09-03 | QTR1 | 25/26 | 1 | 0 | 120 | 150 | 146 | 4 | 0 | 0 | 30 | 0 | 682916 | 30000 | 652916 | 682916 | 662216 | 0 | 0 | 0 | 662216 | 662216 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274113616 | PIGOTT ASPHALT AND SITEWORK LLC | N/A | N/A | N/A | N/A | 2026-06-23 | QTR4 | 25/26 |  | 2026-04-24 | QTR4 | 25/26 | 515 | 700584.82 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58F4 | 45062315201 | 2025-08-05 | QTR1 | 25/26 | 1 | 0 | 120 | 139 | 81 | 58 | 0 | 0 | 19 | 0 | 1291007 | 50000 | 1241007 | 1291007 | 1311928 | 0 | 0 | 0 | 1311928 | 1311928 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-13 | QTR4 | 25/26 |  | 2026-01-22 | QTR3 | 25/26 | 509 | 1935088.17 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59A5 | 44780715201 | 2022-04-06 | QTR4 | 21/22 | 1 | 0 | 270 | 1159 | 1159 | 0 | 0 | 0 | 889 | 0 | 973615 | 34352 | 939263 | 973615 | 939263 | 0 | 0 | 0 | 939263 | 939263 | 0 | 0 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-09-19 | QTR1 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 509 | 1511250 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 748 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59B2 | 43986415201 | 2024-02-06 | QTR3 | 23/24 | 3 | 3 | 200 | 286 | 286 | 0 | 0 | 0 | 86 | 0 | 3015224 | 50000 | 2965224 | 3086900 | 3009526 | 0 | 0 | 0 | 3009526 | 2958475 | -4843 | 71676 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62215 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-15 | QTR3 | 24/25 | 513 | 3337723.49 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59B3 | 44710515201 | 2023-10-03 | QTR2 | 23/24 | 3 | 8 | 330 | 647 | 647 | 0 | 0 | 0 | 297 | 20 | 9171822 | 94000 | 9077822 | 9565947 | 9919938 | 0 | 0 | 0 | 9919938 | 9890809 | -15806 | 394125 | 183 | 0 | 0 | 271108 | 119817 | 0 | 0 | 179717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15544 | 34566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 466368 | 154383 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2026-02-19 | QTR3 | 25/26 | 513 | 10427761.81 |  |  | 0 | 114 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59F3 | 44101515201 | 2025-08-05 | QTR1 | 25/26 | 1 | 0 | 150 | 178 | 112 | 66 | 0 | 0 | 28 | 0 | 2681271 | 50000 | 2631271 | 2681271 | 2693179 | 0 | 0 | 0 | 2693179 | 2693179 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-04-23 | QTR4 | 25/26 |  | 2026-02-17 | QTR3 | 25/26 | 507 | 3752504.41 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y71 | 43710015201 | 2017-02-10 | QTR3 | 16/17 | 2 | 13 | 580 | 1034 | 1109 | -75 | 75 | 0 | 71 | 383 | 13137000 | 150000 | 12987000 | 15625764 | 15527284 | 0 | 0 | 0 | 15527284 | 15513522 | 0 | 2488764 | 43 | 0 | 38 | 141704 | 0 | 0 | 110 | 1784758 | 53460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17164 | 0 | 0 | 235 | 601000 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383 | 2544625 | 104460 | F592143889 | COLLAGE DESIGN & CONSTRUCTION G THE COLLAGE COMPANIES | N/A | N/A | N/A | N/A | 2026-06-15 | QTR4 | 25/26 |  | 2026-03-26 | QTR3 | 25/26 | 507 | 13833591 |  |  | 110 | 28 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z18 | 24020045201 | 2018-08-22 | QTR1 | 18/19 | 4 | 18 | 1400 | 2248 | 2248 | 0 | 0 | 0 | 599 | 249 | 253332000 | 150000 | 253182000 | 267516079 | 267608352 | 0 | 25000 | 25000 | 267633352 | 268414123 | 8560014 | 14184079 | 138 | 0 | 0 | 2669763 | 0 | 0 | 0 | 2461289 | 94536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 946937 | 321742 | 0 | 0 | 30080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949329 | 0 | 0 | 249 | 7300000 | 7300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 14357398 | 7716278 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2024-12-20 | QTR2 | 24/25 | 507 | 283931078 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 461 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6466 | 43992315201 | 2024-02-28 | QTR3 | 23/24 | 1 | 1 | 160 | 189 | 184 | 5 | 0 | 0 | 29 | 0 | 749749 | 36694 | 713055 | 750453 | 687268 | 0 | 0 | 0 | 687268 | 687166 | -102 | 704 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-07-22 | QTR1 | 25/26 |  | 2025-05-06 | QTR4 | 24/25 | 613 | 759570.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6514 | 44462215201 | 2022-04-27 | QTR4 | 21/22 | 3 | 6 | 450 | 576 | 465 | 111 | 0 | 0 | 70 | 56 | 12567171 | 112026 | 12455145 | 13007370 | 12865831 | 0 | 500000 | 500000 | 13365831 | 12808223 | -557608 | 440200 | 42 | 0 | 0 | 75620 | 0 | 0 | 0 | 66701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 320618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 462939 | 0 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2026-01-29 | QTR3 | 25/26 |  | 2024-08-07 | QTR1 | 24/25 | 613 | 11765757.23 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6541 | 44390215201 | 2023-02-22 | QTR3 | 22/23 | 4 | 3 | 400 | 476 | 462 | 14 | 0 | 0 | 76 | 0 | 6112543 | 50000 | 6062543 | 6196534 | 6055588 | 0 | 0 | 0 | 6055588 | 6046499 | -7887 | 83991 | 29 | 0 | 0 | 30261 | 0 | 0 | 0 | 18983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56474 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2025-09-18 | QTR1 | 25/26 |  | 2025-06-11 | QTR4 | 24/25 | 613 | 4898503.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6547 | 44392115201 | 2023-05-24 | QTR4 | 22/23 | 4 | 6 | 340 | 533 | 513 | 20 | 0 | 0 | 180 | 13 | 7844825 | 81266 | 7763559 | 8071972 | 8026073 | 0 | 200000 | 200000 | 8226073 | 8025252 | -200821 | 227147 | 146 | 0 | 13 | 211928 | 0 | 0 | 0 | 27940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 239868 | 0 | F202087333 | RYAN INC. SOUTHERN | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-03-28 | QTR3 | 24/25 | 636 | 8411804.1 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6555 | 44598715201 | 2023-04-26 | QTR4 | 22/23 | 8 | 6 | 500 | 526 | 459 | 67 | 0 | 0 | 22 | 4 | 15230513 | 150000 | 15080513 | 15276979 | 14673045 | 0 | 440000 | 440000 | 15113045 | 14624087 | -460650 | 46466 | 10 | 0 | 0 | 43405 | 0 | 0 | 0 | 81997 | 21158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17514 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79761 | 21158 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-07-14 | QTR1 | 25/26 |  | 2025-02-27 | QTR3 | 24/25 | 636 | 16721997.85 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | -65908 | 0 |  | CO
06CO | 06 | T6556 | 44389615201 | 2023-05-24 | QTR4 | 22/23 | 5 | 5 | 450 | 493 | 434 | 59 | 0 | 0 | 43 | 0 | 12343500 | 99969 | 12243531 | 12329103 | 12004695 | 0 | 340000 | 340000 | 12344695 | 12003108 | -341587 | -14397 | 13 | 0 | 0 | 51988 | 0 | 0 | 0 | 192434 | 111954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6723 | 0 | 0 | 0 | 1786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7736 | 111954 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-02-06 | QTR3 | 25/26 |  | 2025-04-15 | QTR4 | 24/25 | 636 | 10090244.35 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 30 | 0 | 0 | -260667 | 0 |  | CO
06CO | 06 | T6562 | 44393715201 | 2023-03-29 | QTR3 | 22/23 | 6 | 0 | 400 | 455 | 384 | 71 | 0 | 0 | 55 | 0 | 9816354 | 102429 | 9713925 | 9816354 | 9814725 | 0 | 320000 | 320000 | 10134725 | 9792214 | -342511 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-09-08 | QTR1 | 25/26 |  | 2025-01-20 | QTR3 | 24/25 | 613 | 10415642.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6564 | 44599515201 | 2023-12-06 | QTR2 | 23/24 | 2 | 2 | 240 | 259 | 219 | 40 | 0 | 0 | 19 | 0 | 2427793 | 50000 | 2377793 | 2522356 | 2377282 | 0 | 100000 | 100000 | 2477282 | 2374390 | -102891 | 94563 | 5 | 0 | 0 | 13136 | 0 | 0 | 0 | 34463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54683 | 3620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102281 | 3620 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 |  | 2025-06-19 | QTR4 | 24/25 | 636 | 2381685.3 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6565 | 44389815202 | 2023-02-22 | QTR3 | 22/23 | 3 | 3 | 480 | 626 | 584 | 42 | 0 | 0 | 110 | 36 | 17424162 | 150000 | 17274162 | 17775584 | 17807123 | 0 | 360000 | 360000 | 18167123 | 17726459 | -440664 | 351422 | 80 | 0 | 0 | 84168 | 0 | 0 | 36 | 237134 | 22708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 443354 | 22708 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-01-08 | QTR3 | 25/26 |  | 2025-05-09 | QTR4 | 24/25 | 636 | 16704094.5 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6567 | 44757415201 | 2024-05-22 | QTR4 | 23/24 | 2 | 1 | 197 | 320 | 313 | 7 | 0 | 0 | 123 | 0 | 1669000 | 50000 | 1619000 | 1695000 | 1692054 | 0 | 0 | 0 | 1692054 | 1691797 | -258 | 26000 | 98 | 0 | 0 | 15742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15742 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-03-09 | QTR3 | 25/26 |  | 2026-01-30 | QTR3 | 25/26 | 613 | 1801028.4 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6568 | 44393225201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 154 | 185 | 179 | 6 | 0 | 0 | 31 | 0 | 1068800 | 50000 | 1018800 | 1068800 | 1002901 | 0 | 0 | 0 | 1002901 | 1002859 | -41 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F832482227 | TRAFFICO LLC | N/A | N/A | N/A | N/A | 2026-01-22 | QTR3 | 25/26 |  | 2025-10-16 | QTR2 | 25/26 | 613 | 1151283.4 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6573 | 44599115201 | 2023-12-06 | QTR2 | 23/24 | 4 | 3 | 450 | 488 | 422 | 66 | 0 | 0 | 38 | 0 | 7944520 | 85047 | 7859473 | 7965978 | 7740756 | 0 | 320000 | 320000 | 8060756 | 7730600 | -330157 | 21458 | 15 | 0 | 0 | 10477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2205 | 2205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12682 | 2205 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-09 | QTR3 | 25/26 |  | 2025-08-07 | QTR1 | 25/26 | 636 | 8387398.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6574 | 44780515201 | 2023-10-25 | QTR2 | 23/24 | 2 | 2 | 300 | 333 | 284 | 49 | 0 | 0 | 33 | 0 | 3338573 | 50000 | 3288573 | 3388573 | 3361643 | 0 | 100000 | 100000 | 3461643 | 3354655 | -106988 | 50000 | 23 | 0 | 0 | 12008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33215 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2025-10-14 | QTR2 | 25/26 |  | 2025-03-27 | QTR3 | 24/25 | 613 | 3605553.8 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6575 | 44780615201 | 2024-01-31 | QTR3 | 23/24 | 2 | 1 | 200 | 303 | 303 | 0 | 0 | 0 | 103 | 0 | 4637389 | 50000 | 4587389 | 4652332 | 4600291 | 0 | 0 | 0 | 4600291 | 4582375 | -2973 | 14943 | 59 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2025-07-24 | QTR1 | 25/26 |  | 2025-04-01 | QTR4 | 24/25 | 636 | 4247705.35 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6577 | 44390915201 | 2024-04-24 | QTR4 | 23/24 | 2 | 4 | 320 | 382 | 299 | 83 | 0 | 0 | 62 | 0 | 4280927 | 50000 | 4230927 | 4380927 | 4298470 | 0 | 180000 | 180000 | 4478470 | 4296065 | -182405 | 100000 | 51 | 0 | 0 | 25028 | 0 | 0 | 0 | 21810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22967 | 0 | 0 | 0 | 13118 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82924 | 2195 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-12-05 | QTR2 | 25/26 | 613 | 4677512.3 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6580 | 44600015201 | 2024-04-24 | QTR4 | 23/24 | 3 | 4 | 380 | 458 | 458 | 0 | 0 | 0 | 78 | 0 | 5947099 | 61718 | 5885381 | 6376641 | 6242028 | 0 | 0 | 0 | 6242028 | 6225782 | -16246 | 429541 | 35 | 0 | 0 | 266153 | 1847 | 0 | 0 | 30029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160523 | 0 | 0 | 0 | 2939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459644 | 1847 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2026-02-04 | QTR3 | 25/26 | 636 | 6394668.5 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6584 | 44391215201 | 2024-03-27 | QTR3 | 23/24 | 3 | 5 | 380 | 430 | 360 | 70 | 0 | 0 | 50 | 0 | 8558846 | 77205 | 8481641 | 8890402 | 8748106 | 0 | 220000 | 220000 | 8968106 | 8742165 | -225941 | 331556 | 27 | 0 | 0 | 69085 | 0 | 0 | 0 | 250233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65727 | 7495 | 0 | 0 | 7079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392125 | 7495 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2026-02-19 | QTR3 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 613 | 7821851.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6597 | 44936015201 | 2024-08-28 | QTR1 | 24/25 | 1 | 0 | 200 | 258 | 257 | 1 | 0 | 0 | 58 | 0 | 1671710 | 50000 | 1621710 | 1671710 | 1568639 | 0 | 0 | 0 | 1568639 | 1568617 | -22 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F843316177 | FLORIDA SIGNAL & LIGHTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2026-05-08 | QTR4 | 25/26 |  | 2026-02-27 | QTR3 | 25/26 | 636 | 1785608.4 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6598 | 44780415201 | 2024-09-25 | QTR1 | 24/25 | 2 | 1 | 240 | 271 | 220 | 51 | 0 | 0 | 31 | 0 | 2627713 | 50000 | 2577713 | 2705308 | 2578007 | 0 | 120000 | 120000 | 2698007 | 2578006 | -120001 | 77594 | 23 | 0 | 0 | 11001 | 0 | 0 | 0 | 66593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77594 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVELOPMENT LLC D/B/A B | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-10-08 | QTR2 | 25/26 | 636 | 3026337.1 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6602 | 44623915201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 300 | 317 | 198 | 119 | 0 | 0 | 34 | -17 | 3433699 | 50000 | 3383699 | 3555649 | 3477140 | 0 | 100000 | 100000 | 3577140 | 3476420 | -100720 | 121950 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4647 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2025-12-19 | QTR2 | 25/26 | 613 | 3703879.83 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6605 | 44389945201 | 2024-12-04 | QTR2 | 24/25 | 4 | 1 | 240 | 272 | 220 | 52 | 0 | 0 | 32 | 0 | 1755688 | 50000 | 1705688 | 1780688 | 1741502 | 0 | 200000 | 200000 | 1941502 | 1741636 | -199866 | 25000 | 11 | 0 | 0 | 22824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22824 | 0 | F843316177 | FLORIDA SIGNAL & LIGHTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2026-05-18 | QTR4 | 25/26 |  | 2026-03-18 | QTR3 | 25/26 | 613 | 1854603.65 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6L20 | 25054885201 | 2022-05-26 | QTR4 | 21/22 | 9 | 6 | 800 | 926 | 890 | 36 | 0 | 0 | 126 | 0 | 28158187 | 150000 | 28008187 | 28920235 | 27890563 | 0 | 120000 | 120000 | 28010563 | 27701758 | -239034 | 762049 | 79 | 0 | 0 | 54216 | 11723 | 0 | 0 | 229137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747305 | 11723 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2026-02-13 | QTR3 | 25/26 |  | 2025-07-07 | QTR1 | 25/26 | 636 | 23137912.5 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M86 | 43351125201 | 2021-05-27 | QTR4 | 20/21 | 3 | 13 | 1020 | 1267 | 1212 | 55 | 0 | 0 | 158 | 89 | 41366428 | 150000 | 41216428 | 43068537 | 43251556 | 0 | 1960000 | 1960000 | 45211556 | 43282192 | -173492 | 1702108 | 104 | 0 | 0 | 601267 | 0 | 0 | 0 | 386677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 685738 | 0 | 0 | 0 | 73383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1678869 | 0 | F650012669 | MASTEC CIVIL LLC | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-03-12 | QTR3 | 24/25 | 613 | 33950112.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 54 | 0 | 0 | -94401 | 0 |  | DO
06DO | 06 | E6N17 | 44716515201 | 2021-09-13 | QTR1 | 21/22 | 5 | 12 | 900 | 1272 | 1272 | 0 | 0 | 0 | 195 | 177 | 66054600 | 150000 | 65904600 | 66794016 | 66824078 | 0 | 1200000 | 1200000 | 68024078 | 67015448 | -977158 | 739416 | 132 | 0 | 0 | 168972 | 0 | 0 | 177 | 1395729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042425 | 0 | 0 | 0 | 396899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -994258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 705319 | 0 | F834649779 | AGI DE MOYA JOINT VENTURE | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 |  | 2025-07-25 | QTR1 | 25/26 | 636 | 34964142.28 | B5:B5:B5::::Y | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 0 | 63 | 0 | 0 | -1304449 | 0 |  | DO
06DO | 06 | E6O12 | 44391925201 | 2023-05-25 | QTR4 | 22/23 | 3 | 1 | 280 | 309 | 263 | 46 | 0 | 0 | 29 | 0 | 2869869 | 50000 | 2819869 | 2869869 | 2778313 | 0 | 140000 | 140000 | 2918313 | 2778250 | -140063 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2025-08-20 | QTR1 | 25/26 |  | 2025-04-24 | QTR4 | 24/25 | 636 | 2865779.1 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O17 | 43029169201 | 2022-06-13 | QTR4 | 21/22 | 2 | 3 | 628 | 1156 | 1148 | 8 | 0 | 0 | 384 | 144 | 7237000 | 51988 | 7185012 | 7269318 | 7237180 | 0 | 0 | 0 | 7237180 | 0 | -7237180 | 32318 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 19850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 32318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 52168 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-10-23 | QTR2 | 25/26 | 636 | 5284476.93 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 123 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O81 | 44598815201 | 2024-03-28 | QTR3 | 23/24 | 1 | 1 | 250 | 259 | 222 | 37 | 0 | 0 | 9 | 0 | 3370711 | 50000 | 3320711 | 3853261 | 3033601 | 0 | 120000 | 120000 | 3153601 | 3032315 | -121286 | 482550 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 482550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482550 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2025-08-15 | QTR1 | 25/26 | 613 | 3432003 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O89 | 44480315201 | 2024-07-25 | QTR1 | 24/25 | 1 | 1 | 280 | 379 | 369 | 10 | 0 | 0 | 99 | 0 | 1776181 | 50000 | 1726181 | 1776181 | 1798839 | 0 | 0 | 0 | 1798839 | 1798839 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2026-04-14 | QTR4 | 25/26 |  | 2026-01-30 | QTR3 | 25/26 | 613 | 2017257.53 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6P13 | 43029189201 | 2024-04-22 | QTR4 | 23/24 | 2 | 0 | 400 | 475 | 459 | 16 | 0 | 0 | 75 | 0 | 1315382 | 50000 | 1265382 | 1315382 | 1284180 | 0 | 0 | 0 | 1284180 | 0 | -1284180 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2025-11-13 | QTR2 | 25/26 |  | 2025-09-19 | QTR1 | 25/26 | 636 | 1725000 | Y | DESIGN/BUILD PROJECT | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6P23 | 44391115201 | 2024-03-28 | QTR3 | 23/24 | 1 | 7 | 340 | 363 | 320 | 43 | 0 | 0 | 23 | 0 | 5790735 | 50000 | 5740735 | 6121430 | 5667306 | 0 | 100000 | 100000 | 5767306 | 5665707 | -101599 | 330695 | 13 | 0 | 0 | 58475 | 0 | 0 | 0 | 97436 | 21191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47458 | 32917 | 0 | 0 | 0 | 0 | 0 | 0 | 316829 | 54108 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2026-01-27 | QTR3 | 25/26 |  | 2025-11-21 | QTR2 | 25/26 |  | 4862238.65 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7388 | 41656125201 | 2017-05-24 | QTR4 | 16/17 | 2 | 11 | 1090 | 1577 | 2259 | -682 | 682 | 0 | 194 | 293 | 42444444 | 614375 | 41830070 | 42657075 | 42354504 | -1680946 | 0 | -1680946 | 40673558 | 42889778 | 2252365 | 212630 | 112 | 0 | 0 | 367285 | 42702 | 0 | 111 | 518341 | 24857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63256 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 975484 | 67559 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2024-02-02 | QTR3 | 23/24 | 798 | 46455035.14 | B10 | ACC - BONUS/INCENT/DISINCENT | 10 | 82 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7396 | 41673245201 | 2019-07-31 | QTR1 | 19/20 | 4 | 12 | 1200 | 1366 | 1366 | 0 | 0 | 0 | 166 | 0 | 55832153 | 444272 | 55387881 | 56499915 | 56120655 | 0 | 875160 | 875160 | 56995815 | 56570953 | -113501 | 667762 | 87 | 0 | 0 | 537977 | 184519 | 0 | 0 | 204897 | 116725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835048 | 301244 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-29 | QTR2 | 25/26 |  | 2023-07-17 | QTR1 | 23/24 | 798 | 63202968.19 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 0 | 79 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7412 | 43057315201 | 2018-06-13 | QTR4 | 17/18 | 1 | 14 | 800 | 1068 | 1549 | -481 | 481 | 0 | 208 | 60 | 32988889 | 150000 | 32838889 | 34384864 | 34586933 | -1228315 | 0 | -1228315 | 33358618 | 33443535 | 320746 | 1395975 | 142 | 0 | 0 | 105009 | 45664 | 0 | 60 | 1508758 | 95248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238811 | 7454 | 0 | 0 | 2194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39767 | 23709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1518130 | 172075 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2023-04-04 | QTR4 | 22/23 | 714 | 37580000 |  |  | 0 | 66 | 0 | 0 | -376409 | 0 |  | CO
07CO | 07 | T7433 | 25632315201 | 2019-06-12 | QTR4 | 18/19 | 3 | 20 | 1200 | 1864 | 1979 | -115 | 115 | 0 | 262 | 402 | 49694444 | 321270 | 49373174 | 52738117 | 53453750 | -247450 | 0 | -247450 | 53206300 | 54510903 | 1422327 | 3043672 | 140 | 0 | 229 | 2933881 | 131927 | 0 | 3 | 125100 | 6866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7171 | 0 | 0 | 0 | 32928 | 16226 | 0 | 0 | 0 | 0 | 0 | 0 | 98540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 252 | 3095825 | 155019 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2025-01-29 | QTR3 | 24/25 | 798 | 58098403.79 |  |  | 50 | 122 | 0 | 0 | -101796 | 0 |  | CO
07CO | 07 | T7445 | 43751415201 | 2020-06-10 | QTR4 | 19/20 | 4 | 7 | 500 | 588 | 962 | -374 | 374 | 0 | 54 | 34 | 19998889 | 216781 | 19782108 | 21060736 | 21787737 | -1055507 | 0 | -1055507 | 20732231 | 20815167 | 287019 | 1061847 | 25 | 0 | 34 | 809476 | 0 | 0 | 0 | 39834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1009715 | 0 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2026-05-07 | QTR4 | 25/26 |  | 2023-08-28 | QTR1 | 23/24 | 798 | 21050900 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7460 | 43604115201 | 2021-01-27 | QTR3 | 20/21 | 2 | 5 | 380 | 561 | 684 | -123 | 123 | 0 | 129 | 52 | 3677251 | 141565 | 3535686 | 4044013 | 3766516 | -317217 | 0 | -317217 | 3449299 | 3522837 | 192561 | 366762 | 107 | 0 | 0 | 59506 | 0 | 0 | 52 | 157769 | 111750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167254 | 6834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 384529 | 118583 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2026-04-07 | QTR4 | 25/26 |  | 2023-11-17 | QTR2 | 23/24 | 796 | 3523200 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7462 | 25716535201 | 2023-05-24 | QTR4 | 22/23 | 3 | 4 | 532 | 684 | 682 | 2 | 0 | 0 | 150 | 2 | 21597899 | 279988 | 21317911 | 21520785 | 21184572 | 0 | 0 | 0 | 21184572 | 21101702 | -1767 | -77114 | 109 | 0 | 0 | 29115 | 0 | 0 | 2 | 21294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -70801 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-04-29 | QTR4 | 25/26 |  | 2025-08-13 | QTR1 | 25/26 | 798 | 20111600 |  |  | 2 | 41 | 0 | 0 | -159215 | 0 |  | CO
07CO | 07 | T7471 | 44138715201 | 2021-05-26 | QTR4 | 20/21 | 3 | 12 | 700 | 1190 | 1190 | 0 | 0 | 0 | 438 | 52 | 25596637 | 321434 | 25275203 | 26257328 | 26136613 | 0 | 0 | 0 | 26136613 | 26734266 | 642428 | 660691 | 335 | 0 | 21 | 508447 | 15927 | 0 | 19 | 699434 | 14637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 44775 | 37039 | 0 | 0 | 0 | 0 | 0 | 12 | 20008 | 0 | 10 | 0 | 0 | 0 | 65 | 52 | 1272665 | 67603 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-04-13 | QTR4 | 25/26 |  | 2025-02-26 | QTR3 | 24/25 | 796 | 27251800 |  |  | 52 | 93 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7472 | 43182125201 | 2021-05-26 | QTR4 | 20/21 | 2 | 24 | 1200 | 1362 | 1223 | 139 | 0 | 0 | 138 | 24 | 85239705 | 150000 | 85089705 | 94443373 | 95456225 | 0 | 0 | 0 | 95456225 | 95322196 | 2218662 | 9203668 | 61 | 0 | 0 | 459126 | 0 | 0 | 21 | 3062413 | 383024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 5033268 | 721885 | 0 | 0 | 886815 | 335970 | 0 | 0 | 0 | 0 | 0 | 0 | 177538 | 160277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 8284381 | 1601156 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2025-09-30 | QTR1 | 25/26 |  | 2025-02-28 | QTR3 | 24/25 | 714 | 78472500 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 77 | 0 | 0 | -1334779 | 0 |  | CO
07CO | 07 | T7478 | 44024615201 | 2022-06-15 | QTR4 | 21/22 | 5 | 14 | 650 | 926 | 925 | 1 | 0 | 0 | 176 | 100 | 23033560 | 150000 | 22883560 | 24126786 | 23743700 | 0 | 0 | 0 | 23743700 | 23297352 | -443818 | 1093226 | 92 | 0 | 47 | 347814 | 0 | 0 | 49 | 97842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 4 | 18279 | 18279 | 0 | 0 | 0 | 0 | 0 | 0 | 2530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 100 | 466465 | 18279 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-05-19 | QTR4 | 25/26 |  | 2025-09-15 | QTR1 | 25/26 | 799 | 23181900 |  |  | 96 | 64 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7493 | 44538015201 | 2023-01-25 | QTR3 | 22/23 | 1 | 14 | 470 | 681 | 681 | 0 | 0 | 0 | 194 | 17 | 35735836 | 150000 | 35585836 | 37879264 | 40425341 | -36000 | 0 | -36000 | 40389341 | 39569176 | -376846 | 2143428 | 129 | 0 | 0 | 661576 | 3597 | 0 | 0 | 145477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 893056 | 733218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700108 | 736816 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-04-20 | QTR4 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 714 | 37724100 |  |  | 0 | 82 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7505 | 44166115201 | 2023-05-24 | QTR4 | 22/23 | 2 | 6 | 450 | 530 | 530 | 0 | 0 | 0 | 80 | 0 | 13856415 | 100000 | 13756415 | 13819912 | 13656236 | 0 | 0 | 0 | 13656236 | 13594713 | -2106 | -36503 | 45 | 0 | 0 | 25728 | 22538 | 0 | 0 | -116398 | 38900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -90670 | 61438 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-01-15 | QTR3 | 25/26 |  | 2025-05-19 | QTR4 | 24/25 | 796 | 14165000 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7507 | 44600915201 | 2023-05-17 | QTR4 | 22/23 | 2 | 4 | 700 | 758 | 563 | 195 | 0 | 0 | 93 | -35 | 22407724 | 150000 | 22257724 | 24195428 | 26279346 | 0 | -10000 | -10000 | 26269346 | 25478372 | -2078 | 1787704 | 50 | 0 | 0 | -250600 | 0 | 0 | 0 | 189104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21834 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2026-02-10 | QTR3 | 25/26 |  | 2025-06-06 | QTR4 | 24/25 | 714 | 23830100 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7509 | 44588615201 | 2023-02-22 | QTR3 | 22/23 | 1 | 3 | 225 | 324 | 324 | 0 | 0 | 0 | 99 | 0 | 8085082 | 90000 | 7995082 | 8115381 | 7967342 | 0 | 0 | 0 | 7967342 | 7885022 | -54392 | 30299 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 4879 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2024-11-21 | QTR2 | 24/25 | 799 | 9550800 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7511 | 44378415201 | 2023-05-17 | QTR4 | 22/23 | 2 | 4 | 320 | 501 | 501 | 0 | 0 | 0 | 154 | 27 | 12651040 | 105000 | 12546040 | 13441313 | 13767680 | 0 | 0 | 0 | 13767680 | 13709361 | -2978 | 790273 | 123 | 0 | 0 | 718368 | 0 | 0 | 27 | 45653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 764021 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 798 | 12701400 |  |  | 27 | 31 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7512 | 44334715201 | 2023-06-14 | QTR4 | 22/23 | 2 | 3 | 210 | 477 | 477 | 0 | 0 | 0 | 230 | 37 | 6290573 | 50000 | 6240573 | 6754957 | 7072599 | 0 | 0 | 0 | 7072599 | 6755948 | -125 | 464384 | 209 | 0 | 20 | 65635 | 0 | 0 | 7 | 7306 | 0 | 0 | 0 | 82224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 157426 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 796 | 6135700 |  |  | 25 | 31 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7513 | 44985215201 | 2023-11-15 | QTR2 | 23/24 | 1 | 2 | 130 | 190 | 190 | 0 | 0 | 0 | 60 | 0 | 2131372 | 50000 | 2081372 | 2126382 | 2055081 | 0 | 0 | 0 | 2055081 | 2042217 | -1708 | -4990 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16146 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-05-19 | QTR4 | 25/26 |  | 2025-03-07 | QTR3 | 24/25 | 796 | 1928410 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7514 | 45069315201 | 2023-09-27 | QTR1 | 23/24 | 1 | 2 | 150 | 311 | 311 | 0 | 0 | 0 | 161 | 0 | 2469300 | 50000 | 2419300 | 2490043 | 2487609 | 0 | 0 | 0 | 2487609 | 2486604 | -1005 | 20743 | 111 | 0 | 0 | 31460 | 0 | 0 | 0 | 8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39921 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-18 | QTR1 | 25/26 |  | 2025-04-03 | QTR4 | 24/25 | 796 | 2285000 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7515 | 44803615201 | 2023-06-14 | QTR4 | 22/23 | 2 | 10 | 300 | 571 | 566 | 5 | 0 | 0 | 271 | 0 | 13134873 | 115000 | 13019873 | 13851674 | 14146391 | 0 | 0 | 0 | 14146391 | 14063633 | -40306 | 716801 | 160 | 9 | 0 | 197732 | 0 | 0 | 0 | 430314 | 44320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 640481 | 44320 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-03-11 | QTR3 | 25/26 |  | 2025-07-22 | QTR1 | 25/26 | 799 | 13139100 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7516 | 44006315201 | 2023-06-14 | QTR4 | 22/23 | 1 | 2 | 230 | 430 | 430 | 0 | 0 | 0 | 181 | 19 | 6730280 | 60000 | 6670280 | 6779810 | 6697913 | 0 | 0 | 0 | 6697913 | 6687877 | -10036 | 49529 | 152 | 0 | 0 | 9983 | 0 | 0 | 19 | 66053 | 39546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 19 | 76037 | 39546 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2024-12-04 | QTR2 | 24/25 | 798 | 7050800 |  |  | 19 | 29 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7522 | 44627015201 | 2024-06-12 | QTR4 | 23/24 | 2 | 2 | 310 | 404 | 397 | 7 | 0 | 0 | 94 | 0 | 8109258 | 115000 | 7994258 | 8171451 | 8246645 | 0 | 0 | 0 | 8246645 | 8245347 | -1298 | 62193 | 40 | 28 | 0 | 64340 | 0 | 0 | 0 | 47306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 111647 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-06-16 | QTR4 | 25/26 |  | 2026-02-06 | QTR3 | 25/26 | 796 | 11954146 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7523 | 44697315201 | 2023-10-25 | QTR2 | 23/24 | 1 | 0 | 196 | 316 | 315 | 1 | 0 | 0 | 120 | 0 | 2049777 | 50000 | 1999777 | 2049777 | 2101379 | 0 | 0 | 0 | 2101379 | 2098362 | -3017 | 0 | 95 | 0 | 0 | 2635 | 0 | 0 | 0 | 36652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39287 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-08-15 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 799 | 2385840 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7524 | 44795215201 | 2024-10-30 | QTR2 | 24/25 | 1 | 0 | 250 | 308 | 308 | 0 | 0 | 0 | 29 | 29 | 5431188 | 58640 | 5372548 | 5431188 | 5567862 | 0 | 0 | 0 | 5567862 | 5571064 | 3202 | 0 | 5 | 0 | 29 | 30941 | 30941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 30941 | 30941 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2026-05-29 | QTR4 | 25/26 |  | 2026-03-10 | QTR3 | 25/26 | 798 | 6061975 |  |  | 29 | 24 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7527 | 44363015201 | 2023-12-06 | QTR2 | 23/24 | 1 | 5 | 550 | 665 | 472 | 193 | 0 | 0 | 108 | 7 | 22643400 | 150000 | 22493400 | 24315347 | 26274401 | 0 | 0 | 0 | 26274401 | 25522977 | -1893 | 1671947 | 74 | 0 | 7 | 7300 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 16669 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2026-06-10 | QTR4 | 25/26 |  | 2025-10-08 | QTR2 | 25/26 | 714 | 25187500 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7529 | 44109835201 | 2024-03-27 | QTR3 | 23/24 | 1 | 0 | 200 | 262 | 262 | 0 | 0 | 0 | 62 | 0 | 1336107 | 50000 | 1286107 | 1336107 | 1267198 | 0 | 0 | 0 | 1267198 | 1266909 | -289 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-05-28 | QTR4 | 24/25 | 796 | 1581132 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7530 | 44753515201 | 2024-05-22 | QTR4 | 23/24 | 2 | 1 | 440 | 467 | 403 | 64 | 0 | 0 | 49 | -22 | 9184009 | 65000 | 9119009 | 9285334 | 9327564 | 0 | 0 | 0 | 9327564 | 9325285 | -2279 | 101325 | 19 | 0 | -22 | 118885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22 | 118885 | 0 | F922361847 | DE MOYA HIGHWAY INFRASTRUCTURE LLC | N/A | N/A | N/A | N/A | 2026-05-27 | QTR4 | 25/26 |  | 2025-12-04 | QTR2 | 25/26 | 799 | 7458238 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7536 | 44795415201 | 2024-11-13 | QTR2 | 24/25 | 1 | 1 | 175 | 197 | 197 | 0 | 0 | 0 | 22 | 0 | 5776172 | 75963 | 5700209 | 5745538 | 5802044 | 0 | 0 | 0 | 5802044 | 5802824 | 780 | -30634 | 5 | 0 | 0 | -30634 | 0 | 0 | 0 | 12774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17860 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2026-04-20 | QTR4 | 25/26 |  | 2026-01-26 | QTR3 | 25/26 | 798 | 7545892 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7538 | 44939815201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 100 | 122 | 122 | 0 | 0 | 0 | 22 | 0 | 545691 | 22198 | 523493 | 545691 | 518518 | 0 | 0 | 0 | 518518 | 518518 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-05-08 | QTR4 | 24/25 | 799 | 611133 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7539 | 45287715201 | 2024-05-22 | QTR4 | 23/24 | 1 | 1 | 175 | 226 | 226 | 0 | 0 | 0 | 51 | 0 | 1109387 | 50000 | 1059387 | 1066722 | 1024280 | 0 | 0 | 0 | 1024280 | 1024198 | -82 | -42665 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42665 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2025-05-14 | QTR4 | 24/25 | 796 | 1253844 |  |  | 0 | 18 | 0 | 0 | -42665 | 0 |  | CO
07CO | 07 | T7543 | 44795315201 | 2025-02-26 | QTR3 | 24/25 | 1 | 2 | 200 | 224 | 221 | 3 | 0 | 0 | 34 | -10 | 6298614 | 102500 | 6196114 | 6383875 | 6186613 | 0 | 0 | 0 | 6186613 | 6186612 | 0 | 85262 | 15 | 0 | 0 | -28859 | 0 | 0 | 0 | 29617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 758 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2026-01-29 | QTR3 | 25/26 | 798 | 9649905 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7544 | 44025015201 | 2024-04-17 | QTR4 | 23/24 | 1 | 2 | 240 | 275 | 259 | 16 | 0 | 0 | 35 | 0 | 7475300 | 55000 | 7420300 | 7428809 | 7644411 | 0 | 0 | 0 | 7644411 | 7629621 | -14790 | -46492 | 13 | 0 | 0 | 569898 | 120795 | 0 | 0 | -594629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24731 | 120795 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2025-10-10 | QTR2 | 25/26 |  | 2025-07-14 | QTR1 | 25/26 | 798 | 8386992 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7548 | 44752215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 4 | 140 | 214 | 213 | 1 | 0 | 0 | 17 | 57 | 2173906 | 50000 | 2123906 | 2247825 | 2217265 | 0 | 0 | 0 | 2217265 | 2216464 | -801 | 73919 | 13 | 0 | 36 | 77735 | 0 | 0 | 21 | 8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15816 | 15816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 101654 | 15816 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2026-02-06 | QTR3 | 25/26 |  | 2025-08-06 | QTR1 | 25/26 | 798 | 1912820 |  |  | 36 | 4 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7550 | 45241215201 | 2024-05-15 | QTR4 | 23/24 | 1 | 0 | 97 | 113 | 113 | 0 | 0 | 0 | 16 | 0 | 654321 | 27192 | 627129 | 654321 | 610593 | 0 | 0 | 0 | 610593 | 610593 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2025-11-05 | QTR2 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 796 | 826944 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7555 | 44794815201 | 2025-02-26 | QTR3 | 24/25 | 1 | 1 | 205 | 224 | 157 | 67 | 0 | 0 | 19 | 0 | 5942087 | 79500 | 5862587 | 5942922 | 5968673 | 0 | 0 | 0 | 5968673 | 5968280 | -393 | 835 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-10-22 | QTR2 | 25/26 | 798 | 7672150 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7570 | 45097015201 | 2025-03-26 | QTR3 | 24/25 | 1 | 0 | 90 | 120 | 137 | -17 | 17 | 0 | 30 | 0 | 643597 | 36000 | 607597 | 643597 | 574357 | -28645 | 0 | -28645 | 545712 | 545712 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2026-06-03 | QTR4 | 25/26 |  | 2026-01-25 | QTR3 | 25/26 | 798 | 761694 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7J46 | 43388015201 | 2017-05-25 | QTR4 | 16/17 | 5 | 45 | 1300 | 2870 | 2871 | -1 | 1 | 0 | 686 | 884 | 544690000 | 302200 | 544387800 | 602680022 | 604391547 | -158000 | 2780000 | 2622000 | 607013547 | 607454208 | 21389007 | 57990022 | 486 | 0 | 834 | 49299395 | 50147 | 0 | 0 | 598984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 3959563 | 0 | 0 | 0 | 923053 | 893656 | 0 | 0 | 0 | 0 | 0 | 28 | 1020021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 898 | 55019676 | 943803 | F352566788 | ARCHER WESTERN-DEMOYA JOINT VEN | N/A | N/A | N/A | N/A | 2026-05-06 | QTR4 | 25/26 |  | 2025-06-30 | QTR4 | 24/25 | 714 | 544690000 | B10:B8:B8 | ACC - BONUS/INCENT/DISINCENT:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 50 | 214 | 0 | 0 | -781340 | 0 |  | DO
07DO | 07 | E7N56 | 43726425201 | 2022-05-27 | QTR4 | 21/22 | 1 | 8 | 650 | 716 | 649 | 67 | 0 | 0 | 66 | 0 | 19975000 | 130000 | 19845000 | 20432970 | 21351585 | 0 | 0 | 0 | 21351585 | 21249872 | -59788 | 457970 | 29 | 0 | 0 | 362725 | 71071 | 0 | 0 | 34483 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125141 | 125141 | 0 | 0 | 0 | 0 | 0 | 0 | 586579 | 198586 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-01-20 | QTR3 | 25/26 |  | 2024-06-21 | QTR4 | 23/24 | 798 | 15858300 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P28 | 44797625201 | 2022-05-11 | QTR4 | 21/22 | 2 | 1 | 150 | 208 | 208 | 0 | 0 | 0 | 29 | 29 | 5133790 | 52155 | 5081635 | 5136444 | 5160545 | 0 | 0 | 0 | 5160545 | 5116597 | -43948 | 2654 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 11859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 11859 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2023-08-04 | QTR1 | 23/24 | 714 | 3774700 |  |  | 29 | 7 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P68 | 41673325201 | 2022-12-14 | QTR2 | 22/23 | 1 | 8 | 550 | 918 | 918 | 0 | 0 | 0 | 368 | 0 | 15756084 | 100000 | 15656084 | 16054430 | 16104094 | 0 | 0 | 0 | 16104094 | 15995436 | -74559 | 298346 | 220 | 5 | 0 | 224536 | 0 | 102 | 0 | 28230 | 21610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51528 | 0 | 0 | 0 | 8029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 331684 | 21610 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2026-06-16 | QTR4 | 25/26 |  | 2025-10-06 | QTR2 | 25/26 | 798 | 12965300 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P77 | 44146315201 | 2023-05-10 | QTR4 | 22/23 | 1 | 2 | 150 | 247 | 247 | 0 | 0 | 0 | 70 | 27 | 3366760 | 50000 | 3316760 | 3493112 | 3363518 | 0 | 300000 | 300000 | 3663518 | 3363518 | -300000 | 126352 | 45 | 0 | 22 | 20037 | 0 | 0 | 5 | 4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 135426 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-07-30 | QTR1 | 25/26 |  | 2025-02-05 | QTR3 | 24/25 | 796 | 3104100 | B10 | ACC - BONUS/INCENT/DISINCENT | 27 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q08 | 44761515201 | 2023-05-10 | QTR4 | 22/23 | 2 | 7 | 330 | 477 | 477 | 0 | 0 | 0 | 147 | 0 | 6147921 | 52728 | 6095192 | 6373747 | 6357061 | 0 | 0 | 0 | 6357061 | 6311539 | -1706 | 225826 | 61 | 0 | 0 | -18522 | 0 | 0 | 0 | 84658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84397 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 42409 | 34565 | 0 | 0 | 0 | 0 | 62 | 0 | 192942 | 34565 | F593221511 | PCS CIVIL LLC | N/A | N/A | N/A | N/A | 2026-01-20 | QTR3 | 25/26 |  | 2025-04-28 | QTR4 | 24/25 | 714 | 5831100 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q30 | 44380515201 | 2024-03-13 | QTR3 | 23/24 | 1 | 2 | 250 | 424 | 424 | 0 | 0 | 0 | 174 | 0 | 7234098 | 74000 | 7160098 | 6536418 | 6778566 | 0 | 0 | 0 | 6778566 | 6763361 | -15205 | -697680 | 96 | 0 | 0 | -652638 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | -652638 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2026-02-20 | QTR3 | 25/26 |  | 2025-10-03 | QTR2 | 25/26 | 798 | 7788450 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q31 | 44384115201 | 2023-12-13 | QTR2 | 23/24 | 1 | 3 | 125 | 238 | 240 | -2 | 2 | 0 | 113 | 0 | 1681476 | 50000 | 1631476 | 1805476 | 1410753 | -3398 | 0 | -3398 | 1407355 | 1374355 | 0 | 124000 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2024-12-10 | QTR2 | 24/25 | 796 | 1673100 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q32 | 44383715201 | 2025-05-14 | QTR4 | 24/25 | 1 | 0 | 120 | 159 | 159 | 0 | 0 | 0 | 24 | 15 | 1728143 | 50000 | 1678143 | 1728143 | 1516260 | 0 | 0 | 0 | 1516260 | 1516260 | 0 | 0 | 8 | 0 | 0 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4250 | 0 | F830512074 | TITAN CONSTRUCTION MANAGEMENT LLC | N/A | N/A | N/A | N/A | 2026-06-16 | QTR4 | 25/26 |  | 2026-03-13 | QTR3 | 25/26 | 798 | 1889730 |  |  | 15 | 16 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q39 | 44582815201 | 2024-02-14 | QTR3 | 23/24 | 2 | 0 | 284 | 330 | 326 | 4 | 0 | 0 | 46 | 0 | 1714027 | 50000 | 1664027 | 1714027 | 1704720 | 0 | 0 | 0 | 1704720 | 1704720 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-11-17 | QTR2 | 25/26 |  | 2025-08-26 | QTR1 | 25/26 | 796 | 3483914 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q53 | 44583015201 | 2024-05-08 | QTR4 | 23/24 | 1 | 2 | 230 | 260 | 210 | 50 | 0 | 0 | 30 | 0 | 1599000 | 50000 | 1549000 | 1601196 | 1343560 | 0 | 0 | 0 | 1343560 | 1341365 | 0 | 2196 | 17 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-07-08 | QTR1 | 25/26 |  | 2025-04-13 | QTR4 | 24/25 | 799 | 1936163 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q55 | 44165115201 | 2024-03-13 | QTR3 | 23/24 | 1 | 3 | 150 | 272 | 272 | 0 | 0 | 0 | 93 | 29 | 4066019 | 50000 | 4016019 | 4201769 | 4164473 | 0 | 0 | 0 | 4164473 | 4071753 | -92719 | 135750 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 95050 | 87989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 6641 | 0 | 0 | 0 | 0 | 0 | 19 | 29 | 149452 | 87989 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-22 | QTR2 | 25/26 |  | 2025-06-01 | QTR4 | 24/25 | 799 | 4234476 |  |  | 29 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q75 | 45288915201 | 2024-06-12 | QTR4 | 23/24 | 1 | 2 | 80 | 151 | 151 | 0 | 0 | 0 | 71 | 0 | 1296714 | 50000 | 1246714 | 1381899 | 1384246 | 0 | 0 | 0 | 1384246 | 1371017 | 0 | 85185 | 50 | 0 | 0 | 71957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71957 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-09-09 | QTR1 | 25/26 |  | 2025-01-27 | QTR3 | 24/25 | 798 | 1695805 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q85 | 44349225201 | 2025-01-08 | QTR3 | 24/25 | 1 | 0 | 180 | 203 | 178 | 25 | 0 | 0 | 23 | 0 | 576543 | 25000 | 551543 | 576543 | 519908 | 0 | 0 | 0 | 519908 | 519908 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-05-08 | QTR4 | 25/26 |  | 2025-12-11 | QTR2 | 25/26 | 796 | 536030 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q94 | 45273615201 | 2024-12-11 | QTR2 | 24/25 | 1 | 0 | 30 | 33 | 29 | 4 | 0 | 0 | 3 | 0 | 259111 | 23000 | 236111 | 259111 | 235124 | 0 | 0 | 0 | 235124 | 235124 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2025-09-10 | QTR1 | 25/26 |  | 2025-07-14 | QTR1 | 25/26 | 799 | 516283 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R15 | 44138815201 | 2021-01-29 | QTR3 | 20/21 | 4 | 2 | 450 | 724 | 724 | 0 | 0 | 0 | 274 | 0 | 21358193 | 150000 | 21208193 | 21288752 | 21103200 | 0 | 1150000 | 1150000 | 22253200 | 21628021 | -335192 | -69440 | 226 | 0 | 0 | 12752 | 0 | 0 | 0 | 107114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 50426 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-12-11 | QTR2 | 25/26 |  | 2023-07-28 | QTR1 | 23/24 | 796 | 26431774 | A3:A3:A3:B10 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ACC - BONUS/INCENT/DISINCENT | 0 | 48 | 0 | 0 | -69440 | 0 |  | DO
07DO | 07 | E7R21 | 42451335201 | 2021-05-20 | QTR4 | 20/21 | 3 | 16 | 1115 | 1618 | 1308 | 310 | 0 | 0 | 186 | 317 | 81649200 | 150000 | 81499200 | 89787672 | 90056090 | 0 | 0 | 0 | 90056090 | 89818079 | 1620860 | 8138472 | 122 | 0 | 228 | 2666076 | 316345 | 0 | 0 | 1680130 | 35860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316666 | 208207 | 0 | 0 | 0 | 0 | 0 | 145 | 451154 | 451154 | 0 | 0 | 0 | 0 | 0 | 373 | 4996124 | 1011566 | F540406660 | SKANSKA USA CIVIL SOUTHEAST INC. | N/A | N/A | N/A | N/A | 2025-07-10 | QTR1 | 25/26 |  | 2025-03-08 | QTR3 | 24/25 | 714 | 87776800 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 64 | 0 | 0 | -117901 | 0 |  | DO
07DO | 07 | E7R22 | 44344535201 | 2022-05-27 | QTR4 | 21/22 | 6 | 2 | 640 | 1164 | 1164 | 0 | 0 | 0 | 184 | 340 | 29193066 | 150000 | 29043066 | 28668231 | 28534082 | 0 | 0 | 0 | 28534082 | 28522241 | 0 | -524835 | 243 | 0 | 118 | -536676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340 | -536676 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2026-05-08 | QTR4 | 25/26 |  | 2025-10-03 | QTR2 | 25/26 | 714 | 22376200 |  |  | 340 | 78 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R24 | 44132015201 | 2022-08-04 | QTR1 | 22/23 | 1 | 1 | 580 | 797 | 779 | 18 | 0 | 0 | 217 | 0 | 6997500 | 69934 | 6927567 | 7112720 | 7042786 | 0 | 0 | 0 | 7042786 | 7042581 | -205 | 115220 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115220 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2025-03-28 | QTR3 | 24/25 | 798 | 13119000 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R26 | 42925115201 | 2021-06-17 | QTR4 | 20/21 | 5 | 22 | 1100 | 1415 | 1414 | 1 | 0 | 0 | 176 | 139 | 89691574 | 162717 | 89528857 | 96531643 | 96716929 | -45000 | 0 | -45000 | 96671929 | 96896327 | 1490307 | 6840069 | 90 | 0 | 119 | 5277897 | 81590 | 0 | 20 | 1067716 | 347957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49676 | 0 | 0 | 0 | 8310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 6553399 | 429547 | F871503473 | PRINCE-AJAX DDI JV | N/A | N/A | N/A | N/A | 2025-12-16 | QTR2 | 25/26 |  | 2025-07-02 | QTR1 | 25/26 | 714 | 100030998 | B8 | ACC - DESIGN/BUILD - MAJOR | 61 | 86 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R35 | 43983215201 | 2023-05-25 | QTR4 | 22/23 | 3 | 4 | 580 | 697 | 697 | 0 | 0 | 0 | 117 | 0 | 10158800 | 110000 | 10048800 | 10244736 | 10281972 | 0 | 0 | 0 | 10281972 | 10243690 | -3637 | 85936 | 86 | 0 | 0 | 51291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51291 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2026-01-22 | QTR3 | 25/26 |  | 2025-06-23 | QTR4 | 24/25 | 798 | 12981331 | LBDB:LBDB | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R40 | 44335825201 | 2024-03-07 | QTR3 | 23/24 | 1 | 2 | 200 | 285 | 274 | 11 | 0 | 0 | 85 | 0 | 1322000 | 50000 | 1272000 | 1334250 | 1257998 | 0 | 0 | 0 | 1257998 | 1250561 | -4137 | 12250 | 46 | 0 | 0 | 4515 | 0 | 0 | 0 | 4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2025-08-22 | QTR1 | 25/26 |  | 2025-02-03 | QTR3 | 24/25 | 798 | 1543770 | LBDB | LOW BID DESIGN BUILD | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7U08 | 44366515201 | 2024-09-11 | QTR1 | 24/25 | 1 | 1 | 200 | 251 | 251 | 0 | 0 | 0 | 33 | 18 | 3709156 | 50000 | 3659156 | 3709156 | 3454248 | 0 | 0 | 0 | 3454248 | 3454248 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2026-03-20 | QTR3 | 25/26 |  | 2025-12-10 | QTR2 | 25/26 | 796 | 3944855 |  |  | 18 | 14 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R45 | 43799215201 | 2018-11-15 | QTR2 | 18/19 | 3 | 22 | 928 | 1578 | 1578 | 0 | 0 | 0 | 505 | 145 | 33928239 | 150000 | 33778239 | 47651600 | 47943952 | 0 | 0 | 0 | 47943952 | 47859737 | -39220 | 13723361 | 337 | 0 | 4 | 678065 | 0 | 0 | 0 | 444720 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 11027592 | 0 | 0 | 0 | 1427834 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 75513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 145 | 13655217 | 0 | F825435435 | CENTRAL MORRISON COBALT JV | N/A | N/A | N/A | N/A | 2025-11-04 | QTR2 | 25/26 |  | 2023-10-20 | QTR2 | 23/24 | 854 | 41184698.49 |  |  | 0 | 168 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S51 | 44085715201 | 2020-12-15 | QTR2 | 20/21 | 1 | 16 | 1086 | 1494 | 1494 | 0 | 0 | 0 | 256 | 152 | 31637485 | 150000 | 31487485 | 32856515 | 33411965 | -26500 | 0 | -26500 | 33385465 | 33453512 | 3631867 | 1219030 | 141 | 0 | 34 | 304333 | 0 | 0 | 28 | 445859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2360 | 0 | 0 | 0 | 172460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 152 | 574799 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2026-03-31 | QTR3 | 25/26 |  | 2025-07-09 | QTR1 | 25/26 | 854 | 32721168.86 |  |  | 53 | 115 | 0 | 0 | -395237 | 0 |  | DO
08DO | 08 | E8T48 | 43496835201 | 2022-04-19 | QTR4 | 21/22 | 1 | 2 | 1128 | 1286 | 1283 | 3 | 0 | 0 | 125 | 33 | 10781928 | 108430 | 10673498 | 10718856 | 10512572 | 0 | 0 | 0 | 10512572 | 10512572 | 0 | -63072 | 40 | 0 | 33 | -9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28279 | 0 | 0 | 0 | 8634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 27804 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2026-02-04 | QTR3 | 25/26 |  | 2025-12-18 | QTR2 | 25/26 | 854 | 11904888.56 | A3 | ICC - DESIGN/BUILD - MINOR | 33 | 85 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T83 | 44276415201 | 2022-09-20 | QTR1 | 22/23 | 1 | 4 | 1277 | 1339 | 892 | 447 | 0 | 0 | 128 | -66 | 102999958 | 150000 | 102849958 | 103423210 | 104129622 | 0 | 4744548 | 4744548 | 108874170 | 102351127 | -6249791 | 423252 | 65 | 0 | 0 | 108966 | 0 | 0 | 0 | 78741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37076 | 0 | 0 | 0 | 2530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66 | 227314 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST LLC | N/A | N/A | N/A | N/A | 2026-03-27 | QTR3 | 25/26 |  | 2025-09-10 | QTR1 | 25/26 | 854 | 121233962.23 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 63 | 0 | -66 | 0 | 0 |  | DO
08DO | 08 | E8U04 | 44602415201 | 2023-03-21 | QTR3 | 22/23 | 3 | 8 | 386 | 505 | 502 | 3 | 0 | 0 | 99 | 20 | 16184460 | 150000 | 16034460 | 17190583 | 16458548 | 0 | 0 | 0 | 16458548 | 16378636 | -46667 | 1006123 | 45 | 0 | 0 | 188590 | 0 | 0 | 0 | 366919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 463107 | 0 | 0 | 0 | 50339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1068954 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-14 | QTR3 | 24/25 | 854 | 18390076.74 |  |  | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U19 | 44588515201 | 2023-04-11 | QTR4 | 22/23 | 2 | 1 | 314 | 523 | 523 | 0 | 0 | 0 | 179 | 30 | 11226810 | 114237 | 11112574 | 11263007 | 11344464 | 0 | 0 | 0 | 11344464 | 11303165 | -5101 | 36197 | 122 | 0 | 0 | 0 | 0 | 0 | 14 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 53038 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2025-07-28 | QTR1 | 25/26 |  | 2025-04-11 | QTR4 | 24/25 | 854 | 11461890.59 |  |  | 30 | 57 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U32 | 44925335201 | 2023-05-09 | QTR4 | 22/23 | 2 | 1 | 401 | 505 | 499 | 6 | 0 | 0 | 104 | 0 | 3649071 | 50000 | 3599071 | 3673424 | 3464348 | 0 | 0 | 0 | 3464348 | 3464348 | 0 | 24353 | 27 | 0 | 0 | 7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 11812 | 0 | 0 | 0 | 24353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 43886 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2025-07-29 | QTR1 | 25/26 |  | 2025-05-20 | QTR4 | 24/25 | 854 | 4370418.34 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U46 | 43854815201 | 2024-05-14 | QTR4 | 23/24 | 1 | 0 | 497 | 543 | 254 | 289 | 0 | 0 | 46 | 0 | 4734726 | 79759 | 4654966 | 4734726 | 4628034 | 0 | 0 | 0 | 4628034 | 4628034 | 0 | 0 | 13 | 0 | 0 | 14990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2025-08-08 | QTR1 | 25/26 |  | 2025-06-25 | QTR4 | 24/25 | 854 | 8236620.28 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U56 | 44942325201 | 2023-08-22 | QTR1 | 23/24 | 1 | 2 | 240 | 275 | 242 | 33 | 0 | 0 | 47 | -12 | 1804313 | 50000 | 1754313 | 1864511 | 1827419 | 0 | 37398 | 37398 | 1864817 | 1827419 | -37398 | 60198 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101875 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-01 | QTR1 | 25/26 |  | 2025-03-24 | QTR3 | 24/25 | 854 | 1786238.37 | A6 | ICC - BAM/INCENTIVE-DISINCENT | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U67 | 44440215201 | 2023-09-12 | QTR1 | 23/24 | 4 | 7 | 580 | 715 | 656 | 59 | 0 | 0 | 127 | 8 | 24889345 | 150000 | 24739345 | 25770345 | 25416917 | 0 | 0 | 0 | 25416917 | 25256822 | -129095 | 881000 | 76 | 0 | 0 | 57314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 471317 | 0 | 0 | 0 | 439504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 968135 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2026-02-16 | QTR3 | 25/26 |  | 2025-10-31 | QTR2 | 25/26 | 854 | 27205817.87 |  |  | 8 | 51 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U70 | 44287615201 | 2024-04-09 | QTR4 | 23/24 | 1 | 4 | 661 | 717 | 529 | 188 | 0 | 0 | 77 | -21 | 19498886 | 150000 | 19348886 | 19784427 | 18004526 | 0 | 0 | 0 | 18004526 | 18003824 | -702 | 285541 | 38 | 0 | 0 | 105962 | 0 | 0 | 7 | 57145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 340506 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LLC | N/A | N/A | N/A | N/A | 2026-05-18 | QTR4 | 25/26 |  | 2026-03-19 | QTR3 | 25/26 | 854 | 20898608.47 |  |  | 14 | 39 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U71 | 41592755201 | 2024-02-13 | QTR3 | 23/24 | 1 | 1 | 181 | 339 | 326 | 13 | 0 | 0 | 133 | 25 | 2794276 | 60345 | 2733930 | 2537251 | 2444066 | 0 | 0 | 0 | 2444066 | 2444066 | 0 | -257025 | 84 | 0 | 25 | 59995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | -197030 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS COUNTY INC. | N/A | N/A | N/A | N/A | 2025-10-13 | QTR2 | 25/26 |  | 2025-09-17 | QTR1 | 25/26 | 854 | 6003501.55 |  |  | 25 | 49 | 0 | 0 | -257025 | 0 |  | DO
08DO | 08 | E8U73 | 44206215201 | 2024-03-12 | QTR3 | 23/24 | 2 | 5 | 280 | 321 | 315 | 6 | 0 | 0 | 41 | 0 | 13684469 | 150000 | 13534469 | 13793245 | 13317036 | 0 | 0 | 0 | 13317036 | 13288255 | -24020 | 108776 | 20 | 0 | 0 | 15607 | 0 | 0 | 0 | 43669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36331 | 0 | 0 | 0 | 131202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226808 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2025-10-16 | QTR2 | 25/26 |  | 2025-07-18 | QTR1 | 25/26 | 854 | 19932483.01 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U75 | 41713255201 | 2024-06-11 | QTR4 | 23/24 | 2 | 4 | 691 | 833 | 528 | 305 | 0 | 0 | 149 | -7 | 30846591 | 150000 | 30696591 | 31566656 | 33098541 | 0 | 1149704 | 1149704 | 34248245 | 33093920 | -1154325 | 720066 | 64 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 650343 | 0 | 0 | 0 | 2568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 30 | 652911 | 0 | F811876890 | CONTINENTAL HEAVY CIVIL CORP. | N/A | N/A | N/A | N/A | 2026-04-28 | QTR4 | 25/26 |  | 2026-03-24 | QTR3 | 25/26 | 854 | 46198157.71 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 38 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U91 | 44917545201 | 2024-06-11 | QTR4 | 23/24 | 1 | 4 | 242 | 308 | 302 | 6 | 0 | 0 | 66 | 0 | 4804962 | 50000 | 4754962 | 4908714 | 4813444 | 0 | 0 | 0 | 4813444 | 4807156 | -521 | 103751 | 36 | 0 | 0 | 46708 | 0 | 0 | 0 | 21070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791 | 0 | 0 | 0 | 55206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123774 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2025-12-04 | QTR2 | 25/26 |  | 2025-07-21 | QTR1 | 25/26 | 854 | 4334607.7 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U95 | 44917535201 | 2024-04-09 | QTR4 | 23/24 | 1 | 0 | 140 | 176 | 173 | 3 | 0 | 0 | 36 | 0 | 1605678 | 50000 | 1555678 | 1605678 | 1663792 | 0 | 0 | 0 | 1663792 | 1663792 | 0 | 0 | 18 | 0 | 0 | 23069 | 0 | 0 | 0 | 5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49911 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC | N/A | N/A | N/A | N/A | 2025-07-02 | QTR1 | 25/26 |  | 2025-04-25 | QTR4 | 24/25 | 854 | 1739459.6 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8V77 | 45211115201 | 2025-02-19 | QTR3 | 24/25 | 1 | 0 | 200 | 207 | 108 | 99 | 0 | 0 | 7 | 0 | 1699787 | 50000 | 1649787 | 1699787 | 1444210 | 0 | 0 | 0 | 1444210 | 1444159 | -52 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | F510538182 | ENVIRONMENTAL LAND DEVELOPMENT | N/A | N/A | N/A | N/A | 2025-12-01 | QTR2 | 25/26 |  | 2025-10-29 | QTR2 | 25/26 | 854 | 1780237.34 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0