## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 38922950 | 38529309 | 38986404 | 38491703 | 0 | 38146485 | -0.9936% | 100% | -15818 | -0.04105% | 63453 | 0.163% | 2505 | 245 | 9.78% | 144 | 5.749% | 0 | 0% | 103 | 4.112% | 2608 | 4.112% | 3007 | 2959 | 2570 | 2.595% | 80%
| District Let | 7577448 | 7385655 | 7631322 | 7341705 | 75000 | 7486329 | 1.363% | 100% | 56543 | 0.7656% | 53873 | 0.711% | 740 | 74 | 10% | 38 | 5.135% | 25 | 3.378% | 0 | 0% | 765 | 3.378% | 877 | 812 | 700 | -5.405% | 100%
| All Contracts | 46500398 | 45914964 | 46617726 | 45833408 | 75000 | 45632814 | -0.6145% | 100% | 40725 | 0.0887% | 117326 | 0.2523% | 3245 | 319 | 9.831% | 182 | 5.609% | 25 | 0.7704% | 103 | 3.174% | 3373 | 3.945% | 3884 | 3771 | 3270 | 0.7704% | 88.24%
2 | Central Let | 16344398 | 16059533 | 17060983 | 16881981 | 0 | 16574281 | 3.205% | 100% | 853580 | 5.315% | 716585 | 4.384% | 1260 | 263 | 20.87% | 117 | 9.286% | 11 | 0.873% | 67 | 5.317% | 1338 | 6.19% | 1718 | 1709 | 1329 | 5.476% | 83.33%
| District Let | 20884385 | 20610631 | 22746360 | 23369004 | 0 | 23234126 | 12.73% | 60% | 1855001 | 9% | 1861977 | 8.916% | 1520 | 178 | 11.71% | 243 | 15.99% | 0 | 0% | 332 | 21.84% | 1852 | 21.84% | 2273 | 2210 | 1789 | 17.7% | 80%
| All Contracts | 37228783 | 36670164 | 39807343 | 40250985 | 0 | 39808407 | 8.558% | 81.82% | 2708581 | 7.386% | 2578562 | 6.926% | 2780 | 441 | 15.86% | 360 | 12.95% | 11 | 0.3957% | 399 | 14.35% | 3190 | 14.75% | 3991 | 3919 | 3118 | 12.16% | 81.82%
3 | Central Let | 3388719 | 3333695 | 3401528 | 3519176 | 0 | 3551603 | 6.537% | 100% | 18247 | 0.5474% | 12809 | 0.378% | 295 | 44 | 14.92% | 23 | 7.797% | 5 | 1.695% | 0 | 0% | 300 | 1.695% | 367 | 363 | 296 | 0.339% | 100%
| District Let | 782920 | 754173 | 809439 | 800466 | 0 | 800466 | 6.138% | 100% | 26519 | 3.516% | 26519 | 3.387% | 120 | 71 | 59.17% | 22 | 18.33% | 0 | 0% | 23 | 19.17% | 143 | 19.17% | 236 | 235 | 142 | 18.33% | 100%
| All Contracts | 4171639 | 4087868 | 4210967 | 4319642 | 0 | 4352069 | 6.463% | 100% | 44766 | 1.095% | 39328 | 0.9427% | 415 | 115 | 27.71% | 45 | 10.84% | 5 | 1.205% | 23 | 5.542% | 443 | 6.747% | 603 | 598 | 438 | 5.542% | 100%
4 | Central Let | 21881350 | 21480326 | 22585183 | 21850648 | 37125 | 21699573 | 1.021% | 100% | 691835 | 3.221% | 703833 | 3.217% | 2552 | 586 | 22.96% | 208 | 8.15% | 44 | 1.724% | 173 | 6.779% | 2769 | 8.503% | 3563 | 3490 | 2696 | 5.643% | 100%
| District Let | 26649734 | 26306202 | 27403306 | 26472108 | 0 | 26092508 | -0.8123% | 100% | 553232 | 2.103% | 753572 | 2.828% | 1784 | 531 | 29.76% | 134 | 7.511% | 26 | 1.457% | 85 | 4.765% | 1895 | 6.222% | 2560 | 2546 | 1881 | 5.437% | 100%
| All Contracts | 48531084 | 47786528 | 49988489 | 48322756 | 37125 | 47792081 | 0.01162% | 100% | 1245067 | 2.605% | 1457405 | 3.003% | 4336 | 1117 | 25.76% | 342 | 7.887% | 70 | 1.614% | 258 | 5.95% | 4664 | 7.565% | 6123 | 6036 | 4577 | 5.558% | 100%
5 | Central Let | 7298907 | 7154407 | 8602379 | 8243553 | 0 | 8202898 | 14.66% | 66.67% | 244630 | 3.419% | 1303472 | 17.86% | 630 | 235 | 37.3% | 87 | 13.81% | 0 | 0% | 105 | 16.67% | 735 | 16.67% | 1155 | 1141 | 819 | 30% | 33.33%
| District Let | 12088219 | 11765219 | 12534769 | 12121177 | 0 | 12054566 | 2.459% | 100% | 388400 | 3.301% | 446550 | 3.694% | 1420 | 350 | 24.65% | 206 | 14.51% | 0 | 0% | 49 | 3.451% | 1469 | 3.451% | 2025 | 1905 | 1349 | -5% | 100%
| All Contracts | 19387126 | 18919626 | 21137148 | 20364730 | 0 | 20257464 | 7.071% | 90.91% | 633030 | 3.346% | 1750022 | 9.027% | 2050 | 585 | 28.54% | 293 | 14.29% | 0 | 0% | 154 | 7.512% | 2204 | 7.512% | 3180 | 3046 | 2168 | 5.756% | 81.82%
6 | Central Let | 4457845 | 4353530 | 4633857 | 4339032 | 150000 | 4260376 | -2.14% | 100% | 138647 | 3.185% | 176012 | 3.948% | 490 | 101 | 20.61% | 45 | 9.184% | 33 | 6.735% | 0 | 0% | 523 | 6.735% | 669 | 552 | 406 | -17.14% | 100%
| District Let | 6427211 | 6297232 | 6601381 | 5957819 | 0 | 5334446 | -15.29% | 100% | 152757 | 2.426% | 174170 | 2.71% | 710 | 285 | 40.14% | 80 | 11.27% | 0 | 0% | 0 | 0% | 710 | 0% | 1113 | 1102 | 737 | 3.803% | 100%
| All Contracts | 10885056 | 10650762 | 11235238 | 10296851 | 150000 | 9594822 | -9.914% | 100% | 291404 | 2.736% | 350182 | 3.217% | 1200 | 386 | 32.17% | 125 | 10.42% | 33 | 2.75% | 0 | 0% | 1233 | 2.75% | 1782 | 1654 | 1143 | -4.75% | 100%
7 | Central Let | 51401772 | 50710208 | 51592569 | 51207689 | 0 | 50501358 | -0.4119% | 100% | 407456 | 0.8035% | 190796 | 0.3712% | 1540 | 390 | 25.32% | 132 | 8.571% | 66 | 4.286% | 64 | 4.156% | 1670 | 8.442% | 2192 | 2192 | 1670 | 8.442% | 100%
| District Let | 7833692 | 7643692 | 8316672 | 8222317 | 0 | 8099768 | 5.967% | 75% | 468957 | 6.135% | 482980 | 6.165% | 839 | 246 | 29.32% | 91 | 10.85% | 0 | 0% | 34 | 4.052% | 873 | 4.052% | 1210 | 1134 | 797 | -5.006% | 100%
| All Contracts | 59235464 | 58353900 | 59909241 | 59430006 | 0 | 58601126 | 0.4237% | 87.5% | 876413 | 1.502% | 673776 | 1.137% | 2379 | 636 | 26.73% | 223 | 9.374% | 66 | 2.774% | 98 | 4.119% | 2543 | 6.894% | 3402 | 3326 | 2467 | 3.699% | 100%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 8378688 | 8291809 | 9424319 | 9142821 | 0 | 9136712.84 | 10.19% | 0% | 888937 | 10.72% | 1045631 | 12.48% | 290 | 89 | 30.69% | 60 | 20.69% | 0 | 0% | 26 | 8.966% | 316 | 8.966% | 465 | 464 | 315 | 8.621% | #VALUE!
| All Contracts | 8378688 | 8291809 | 9424319 | 9142821 | 0 | 9136712.84 | 10.19% | 0% | 888937 | 10.72% | 1045631 | 12.48% | 290 | 89 | 30.69% | 60 | 20.69% | 0 | 0% | 26 | 8.966% | 316 | 8.966% | 465 | 464 | 315 | 8.621% | 100%
Totals This Qtr | Central Let | 143695941 | 141621008 | 146862903 | 144533782 | 187125 | 142936574 | 0.9289% | 97.3% | 2338577 | 1.651% | 3166960 | 2.204% | 9272 | 1864 | 20.1% | 756 | 8.154% | 159 | 1.715% | 512 | 5.522% | 9943 | 7.237% | 12671 | 12406 | 9786 | 5.544% | 86.49%
| District Let | 90622297 | 89054613 | 95467568 | 93427417 | 75000 | 92238921.84 | 3.576% | 88.57% | 4390346 | 4.93% | 4845272 | 5.347% | 7423 | 1824 | 24.57% | 874 | 11.77% | 51 | 0.6871% | 549 | 7.396% | 8023 | 8.083% | 10759 | 10408 | 7710 | 3.866% | 97.14%
| All Contracts | 234318238 | 230675621 | 242330471 | 237961199 | 262125 | 235175495.84 | 1.951% | 93.06% | 6728923 | 2.917% | 8012232 | 3.419% | 16695 | 3688 | 22.09% | 1630 | 9.763% | 210 | 1.258% | 1061 | 6.355% | 17966 | 7.613% | 23430 | 22814 | 17496 | 4.798% | 91.67%
Totals Previous Quarter | Central Let
District Let
All Contracts
Totals Fiscal Year 2018/2019 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1606 | 19801745201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 710 | 803 | 803 | 104.9% | 1 | 0 | 0 | 0 | 58 | 35 | 16630324 | 150000 | 16480324 | 16297713 | 16277472 | -39000 | 0 | -39000 | 16238472 | 15980331 | 96.97% | 1 | -247700 | -332612 | 33 | 25 | 0 | 0 | 120868 | 4623 | 0 | 32 | 119313 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -533590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | -293410 | 9563 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-07-18 | QTR1 | 18/19 |  | 2018-01-12 | QTR3 | 17/18 | 115 | 16471201.81 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1653 | 43317315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 3 | 225 | 323 | 323 | 104.4% | 1 | 0 | 0 | 0 | 88 | 10 | 3821588 | 50000 | 3771588 | 3892256 | 3742414 | 0 | 0 | 0 | 3742414 | 3732176 | 98.96% | 1 | 4666 | 70668 | 64 | 24 | 0 | 3 | 41635 | 0 | 0 | 0 | 14614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 75002 | 18752 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-10-05 | QTR2 | 17/18 | 113 | 2964599.15
| 01 | T1660 | 43161915201 | 2016-09-28 | QTR1 | 16/17 | 2 | 3 | 415 | 458 | 408 | 87.95% | 1 | 50 | 0 | 0 | 43 | 0 | 2357000 | 0 | 2357000 | 2424704 | 2337783 | 0 | 0 | 0 | 2337783 | 2243291 | 95.18% | 1 | -45614 | 67704 | 25 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 4220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-14 | QTR3 | 17/18 | 118 | 3040684.98
| 01 | T1672 | 43660015201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 265 | 377 | 371 | 105.3% | 1 | 6 | 0 | 0 | 92 | 20 | 5457714 | 67624 | 5390090 | 5650306 | 5444515 | 0 | 0 | 0 | 5444515 | 5557409 | 103.1% | 1 | 162288 | 192592 | 71 | 21 | 0 | 0 | 8386 | 0 | 0 | 20 | 155081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 163467 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2018-08-07 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 118 | 5914612.28
| 01 | T1674 | 43450515201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 85 | 91 | 144 | 162.4% | 0 | -53 | 53 | 0 | 6 | 0 | 739854 | 29338 | 710516 | 739854 | 710516 | -20592 | 0 | -20592 | 689924 | 655747 | 92.29% | 1 | -34177 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 115 | 559470.72 | B0 | ACC - LUMP SUM
| 01 | T1678 | 43492915201 | 2017-02-22 | QTR3 | 16/17 | 1 | 1 | 300 | 353 | 316 | 87.67% | 1 | 37 | 0 | 0 | 53 | 0 | 7590540 | 90051 | 7500489 | 7638810 | 7645659 | 0 | 0 | 0 | 7645659 | 7639455 | 101.9% | 1 | 42066 | 48270 | 30 | 23 | 0 | 0 | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-12 | QTR3 | 17/18 | 115 | 9127943.35
| 01 | T1683 | 43177215201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 235 | 253 | 247 | 97.45% | 1 | 6 | 0 | 0 | 18 | 0 | 1414597 | 0 | 1414597 | 1414597 | 1411808 | 0 | 0 | 0 | 1411808 | 1416013 | 100.1% | 1 | 4205 | 0 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-29 | QTR4 | 17/18 | 108 | 1198142.79
| 01 | T1685 | 44011715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 73 | 73 | 100% | 1 | 0 | 0 | 0 | 3 | 0 | 165758 | 6628 | 159130 | 165758 | 159130 | 0 | 0 | 0 | 159130 | 159130 | 100% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-13 | QTR1 | 18/19 |  | 2018-03-21 | QTR3 | 17/18 | 118 | 163745.59
| 01 | T1686 | 43318815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 125 | 190 | 190 | 138.4% | 0 | 0 | 0 | 0 | 17 | 48 | 304735 | 0 | 304735 | 321566 | 321566 | 0 | 0 | 0 | 321566 | 322093 | 105.7% | 1 | 527 | 16831 | 2 | 15 | 0 | 48 | 16831 | 16831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 16831 | 16831 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-17 | QTR1 | 18/19 |  | 2018-04-30 | QTR4 | 17/18 | 113 | 339200.17 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1688 | 43498415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 86 | 84 | 97.33% | 1 | 2 | 0 | 0 | 11 | 0 | 440840 | 0 | 440840 | 440840 | 440840 | 0 | 0 | 0 | 440840 | 440840 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 108 | 446098.62 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 10 | 14 | 18 | 2505 | 3007 | 2959 | 80% | 8 | 48 | 53 | 0 | 389 | 113 | 38922950 | 393641 | 38529309 | 38986404 | 38491703 | -59592 | 0 | -59592 | 38432111 | 38146485 | 100% | 10 | -113739 | 63453 | 245 | 144 | 0 | 51 | 191185 | 21454 | 0 | 52 | 293228 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -518983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | -15818 | 45146
| 01 | E1Q20 | 43979815201 | 2017-03-16 | QTR3 | 16/17 | 2 | 1 | 110 | 151 | 163 | 110.9% | 1 | -12 | 12 | 0 | 41 | 0 | 551623 | 26664 | 524959 | 557534 | 539909 | -19008 | 0 | -19008 | 520901 | 514991 | 98.1% | 1 | 0 | 5910 | 22 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 118 | 682344.11
| 01 | E1Q46 | 43659915201 | 2017-07-20 | QTR1 | 17/18 | 1 | 2 | 150 | 193 | 193 | 112.7% | 1 | 0 | 0 | 0 | 43 | 0 | 2486667 | 50000 | 2436667 | 2519936 | 2394841 | 0 | 0 | 0 | 2394841 | 2475891 | 101.6% | 1 | 81050 | 33269 | 18 | 6 | 19 | 0 | 34528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 34528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-22 | QTR1 | 18/19 |  | 2018-07-13 | QTR1 | 18/19 | 113 | 2833102.66
| 01 | E1Q76 | 43494115201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 190 | 211 | 181 | 87.37% | 1 | 30 | 0 | 0 | 21 | 0 | 3162332 | 50000 | 3112332 | 3162332 | 3141539 | 0 | 0 | 0 | 3141539 | 3230031 | 103.8% | 1 | 88492 | 0 | 11 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-07-25 | QTR1 | 18/19 | 118 | 3398633.17 | B0 | ACC - LUMP SUM
| 01 | E1R00 | 43798415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 2 | 55 | 64 | 64 | 100% | 1 | 0 | 0 | 0 | 9 | 0 | 399878 | 25227 | 374651 | 414572 | 373225 | 0 | 50000 | 50000 | 423225 | 373225 | 99.62% | 1 | -50000 | 14694 | 8 | 1 | 0 | 0 | 10240 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14694 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-11 | QTR4 | 17/18 | 118 | 410604.57 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R01 | 43668415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 0 | 85 | 89 | 76 | 84.71% | 1 | 13 | 0 | 0 | 4 | 0 | 367307 | 12629 | 354678 | 367307 | 318382 | 0 | 25000 | 25000 | 343382 | 318382 | 89.77% | 1 | -25000 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 115 | 312417.65 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1R02 | 44026315201 | 2017-11-16 | QTR2 | 17/18 | 1 | 1 | 75 | 76 | 53 | 69.33% | 1 | 23 | 0 | 0 | 1 | 0 | 253030 | 12790 | 240240 | 253030 | 240240 | 0 | 0 | 0 | 240240 | 240240 | 100% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-05-10 | QTR4 | 17/18 | 108 | 210003.63 | B0 | ACC - LUMP SUM
| 01 | E1R04 | 44035915201 | 2018-01-18 | QTR3 | 17/18 | 1 | 0 | 75 | 93 | 82 | 85.33% | 1 | 11 | 0 | 0 | 18 | 0 | 356611 | 14483 | 342128 | 356611 | 333569 | 0 | 0 | 0 | 333569 | 333569 | 97.5% | 1 | 0 | 0 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-20 | QTR1 | 18/19 |  | 2018-07-05 | QTR1 | 18/19 | 113 | 390668.63
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 7 | 8 | 6 | 740 | 877 | 812 | 100% | 7 | 65 | 12 | 0 | 137 | 0 | 7577448 | 191793 | 7385655 | 7631322 | 7341705 | -19008 | 75000 | 55992 | 7397697 | 7486329 | 100% | 7 | 94542 | 53873 | 74 | 38 | 25 | 0 | 44768 | 0 | 0 | 0 | 11775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 56543 | 0
| District 01 Totals |  |  |  |  | 17 | 22 | 24 | 3245 | 3884 | 3771 | 88.24% | 15 | 113 | 65 | 0 | 526 | 113 | 46500398 | 585434 | 45914964 | 46617726 | 45833408 | -78600 | 75000 | -3600 | 45829808 | 45632814 | 100% | 17 | -19197 | 117326 | 319 | 182 | 25 | 51 | 235953 | 21454 | 0 | 52 | 305003 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -518983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 103 | 40725 | 45146
| 02 | T2547 | 42975025201 | 2015-04-29 | QTR4 | 14/15 | 1 | 1 | 160 | 198 | 254 | 141.9% | 0 | -56 | 56 | 0 | 38 | 0 | 1879929 | 0 | 1879929 | 1879929 | 1845519 | -97552 | 0 | -97552 | 1747967 | 1685674 | 89.67% | 1 | -62293 | 0 | 12 | 15 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2016-03-25 | QTR3 | 15/16 | 209 | 1922742.1
| 02 | T2569 | 42870115201 | 2015-04-29 | QTR4 | 14/15 | 2 | 8 | 450 | 744 | 744 | 112.9% | 1 | 0 | 0 | 0 | 236 | 58 | 9199000 | 134745 | 9064255 | 9915585 | 9871416 | 0 | 0 | 0 | 9871416 | 9657046 | 106.5% | 1 | -214370 | 716585 | 179 | 57 | 0 | 40 | 464223 | 0 | 0 | 18 | 329397 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 794520 | 2083 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 |  | 2017-08-29 | QTR1 | 17/18 | 208 | 9784025.26
| 02 | T2643 | 43434015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 300 | 357 | 317 | 86.67% | 1 | 40 | 0 | 0 | 57 | 0 | 1483252 | 50000 | 1433252 | 1483252 | 1482220 | 0 | 0 | 0 | 1482220 | 1482220 | 103.4% | 1 | 0 | 0 | 21 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-07-05 | QTR1 | 18/19 |  | 2018-03-16 | QTR3 | 17/18 | 208 | 1682912.13
| 02 | T2648 | 43231015201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 140 | 177 | 173 | 100.7% | 1 | 4 | 0 | 0 | 32 | 5 | 1797592 | 50000 | 1747592 | 1797592 | 1737333 | 0 | 0 | 0 | 1737333 | 1782037 | 102% | 1 | 44704 | 0 | 28 | 4 | 0 | 1 | 14238 | 0 | 0 | 4 | 30734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44972 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-27 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 209 | 1880670.12
| 02 | T2674 | 43335915201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 100 | 107 | 86 | 79% | 1 | 21 | 0 | 0 | 7 | 0 | 360929 | 120 | 360809 | 360929 | 343649 | 0 | 0 | 0 | 343649 | 343649 | 95.24% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 209 | 413831.5
| 02 | T2676 | 43617515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 110 | 135 | 135 | 103.6% | 1 | 0 | 0 | 0 | 21 | 4 | 1623696 | 50000 | 1573696 | 1623696 | 1601844 | 0 | 0 | 0 | 1601844 | 1623655 | 103.2% | 1 | 21810 | 0 | 16 | 5 | 0 | 0 | 5575 | 0 | 0 | 4 | 8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 14088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-05-22 | QTR4 | 17/18 | 208 | 1682996.74
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 6 | 7 | 9 | 1260 | 1718 | 1709 | 83.33% | 5 | 9 | 56 | 0 | 391 | 67 | 16344398 | 284865 | 16059533 | 17060983 | 16881981 | -97552 | 0 | -97552 | 16784429 | 16574281 | 100% | 6 | -210149 | 716585 | 263 | 117 | 5 | 41 | 484036 | 0 | 6 | 26 | 368644 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 67 | 853580 | 2083
| 02 | E2T36 | 42442415201 | 2015-05-13 | QTR4 | 14/15 | 1 | 9 | 365 | 727 | 727 | 164.7% | 0 | 0 | 0 | 0 | 126 | 236 | 10725121 | 99413 | 10625708 | 12250426 | 12633691 | 0 | 0 | 0 | 12633691 | 12549851 | 118.1% | 0 | -412 | 1525306 | 47 | 79 | 0 | 0 | 26279 | 0 | 0 | 236 | 1452107 | 295700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1496831 | 295700 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-17 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 208 | 11100158.43
| 02 | E2U34 | 43025815201 | 2016-01-20 | QTR3 | 15/16 | 2 | 6 | 530 | 710 | 670 | 106.2% | 1 | 40 | 0 | 0 | 107 | 73 | 4266548 | 50000 | 4216548 | 4515459 | 4762225 | 0 | 0 | 0 | 4762225 | 4710138 | 111.7% | 0 | -22727 | 248912 | 44 | 63 | 0 | 0 | 7337 | 0 | 0 | 73 | 262215 | 26378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 269552 | 26378 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-27 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 208 | 3812868.47
| 02 | E2V63 | 43860115201 | 2017-05-17 | QTR4 | 16/17 | 2 | 1 | 180 | 201 | 199 | 98.89% | 1 | 2 | 0 | 0 | 21 | 0 | 1160401 | 24341 | 1136060 | 1188813 | 1137166 | 0 | 0 | 0 | 1137166 | 1137166 | 100.1% | 1 | 0 | 28412 | 5 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-09-19 | QTR1 | 18/19 |  | 2018-05-09 | QTR4 | 17/18 | 209 | 567894
| 02 | E2V65 | 43432315201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 220 | 353 | 333 | 97.73% | 1 | 20 | 0 | 0 | 118 | 15 | 3583873 | 50000 | 3533873 | 3643220 | 3692989 | 0 | 0 | 0 | 3692989 | 3693971 | 104.5% | 1 | 30133 | 59347 | 55 | 63 | 0 | 15 | 54887 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 55797 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-08-02 | QTR1 | 18/19 |  | 2018-06-07 | QTR4 | 17/18 | 214 | 3819418.25
| 02 | E2W07 | 43240515201 | 2017-03-15 | QTR3 | 16/17 | 1 | 0 | 225 | 282 | 281 | 103.1% | 1 | 1 | 0 | 0 | 49 | 8 | 1148442 | 50000 | 1098442 | 1148442 | 1142933 | 0 | 0 | 0 | 1142933 | 1143000 | 104.1% | 1 | 66 | 0 | 27 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-20 | QTR4 | 17/18 | 216 | 1300555.65
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 5 | 8 | 18 | 1520 | 2273 | 2210 | 80% | 4 | 63 | 0 | 0 | 421 | 332 | 20884385 | 273754 | 20610631 | 22746360 | 23369004 | 0 | 0 | 0 | 23369004 | 23234126 | 60% | 3 | 7060 | 1861977 | 178 | 243 | 0 | 15 | 88503 | 0 | 0 | 317 | 1748054 | 322078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332 | 1855001 | 322078
| District 02 Totals |  |  |  |  | 11 | 15 | 27 | 2780 | 3991 | 3919 | 81.82% | 9 | 72 | 56 | 0 | 812 | 399 | 37228783 | 558619 | 36670164 | 39807343 | 40250985 | -97552 | 0 | -97552 | 40153433 | 39808407 | 81.82% | 9 | -203089 | 2578562 | 441 | 360 | 5 | 56 | 572539 | 0 | 6 | 343 | 2116698 | 324161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 399 | 2708581 | 324161
| 03 | T3538 | 43357615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 25 | 38 | 36 | 112% | 1 | 2 | 0 | 0 | 13 | 0 | 90288 | 5024 | 85264 | 88663 | 74180 | 0 | 0 | 0 | 74180 | 74180 | 87% | 1 | 0 | -1624 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2015-10-30 | QTR2 | 15/16 | 308 | 110498.62 | B0 | ACC - LUMP SUM
| 03 | T3650 | 43014645201 | 2017-05-24 | QTR4 | 16/17 | 4 | 1 | 270 | 329 | 327 | 99.26% | 1 | 2 | 0 | 0 | 59 | 0 | 3298431 | 50000 | 3248431 | 3312865 | 3444996 | 0 | 0 | 0 | 3444996 | 3477423 | 107% | 1 | 32427 | 14433 | 38 | 21 | 0 | 0 | 3050 | 0 | 0 | 0 | 12545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19871 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 |  | 2018-06-08 | QTR4 | 17/18 | 321 | 4395538.46
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 2 | 5 | 2 | 295 | 367 | 363 | 100% | 2 | 4 | 0 | 0 | 72 | 0 | 3388719 | 55024 | 3333695 | 3401528 | 3519176 | 0 | 0 | 0 | 3519176 | 3551603 | 100% | 2 | 32427 | 12809 | 44 | 23 | 0 | 0 | 3050 | 0 | 0 | 0 | 12545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 18247 | 0
| 03 | E3Q40 | 43375215201 | 2017-02-09 | QTR3 | 16/17 | 1 | 3 | 120 | 236 | 235 | 118.3% | 1 | 1 | 0 | 0 | 93 | 23 | 782920 | 28747 | 754173 | 809439 | 800466 | 0 | 0 | 0 | 800466 | 800466 | 106.1% | 1 | 0 | 26519 | 71 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 17296 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 26519 | 217 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 |  | 2018-02-06 | QTR3 | 17/18 | 314 | 616284.72
[29 empty] | 0% | 0
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 1 | 1 | 3 | 120 | 236 | 235 | 100% | 1 | 1 | 0 | 0 | 93 | 23 | 782920 | 28747 | 754173 | 809439 | 800466 | 0 | 0 | 0 | 800466 | 800466 | 100% | 1 | 0 | 26519 | 71 | 22 | 0 | 0 | 0 | 0 | 0 | 8 | 17296 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 26519 | 217
| District 03 Totals |  |  |  |  | 3 | 6 | 5 | 415 | 603 | 598 | 100% | 3 | 5 | 0 | 0 | 165 | 23 | 4171639 | 83771 | 4087868 | 4210967 | 4319642 | 0 | 0 | 0 | 4319642 | 4352069 | 100% | 3 | 32427 | 39328 | 115 | 45 | 0 | 0 | 3050 | 0 | 0 | 8 | 29841 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 11875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 23 | 44766 | 217
| 04 | T4395 | 42936515201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 286 | 475 | 475 | 109.8% | 1 | 0 | 0 | 0 | 189 | 0 | 1928000 | 50000 | 1878000 | 1932802 | 1674394 | 0 | 0 | 0 | 1674394 | 1669592 | 88.9% | 1 | 0 | 4802 | 135 | 26 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-23 | QTR1 | 18/19 |  | 2018-05-26 | QTR4 | 17/18 | 412 | 1544787.59
| 04 | T4409 | 43019215201 | 2015-05-20 | QTR4 | 14/15 | 3 | 9 | 588 | 824 | 824 | 116% | 1 | 0 | 0 | 0 | 142 | 94 | 4789933 | 51040 | 4738893 | 5042467 | 4996786 | 0 | 0 | 0 | 4996786 | 4938750 | 104.2% | 1 | -14505 | 252534 | 101 | 41 | 0 | 64 | 102911 | 49551 | 0 | 30 | 132980 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 236958 | 121323 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-03-02 | QTR3 | 17/18 | 412 | 5274241.43 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 04 | T4422 | 43257425201 | 2016-12-07 | QTR2 | 16/17 | 4 | 4 | 257 | 429 | 429 | 116% | 1 | 0 | 0 | 0 | 137 | 35 | 4613776 | 50000 | 4563776 | 4938807 | 4932678 | 0 | 0 | 0 | 4932678 | 4896545 | 107.3% | 1 | -7370 | 325031 | 104 | 27 | 0 | 35 | 282288 | 220536 | 6 | 0 | 31835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 35 | 314123 | 220536 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL CONSTRUCTO | N/A | N/A | N/A | N/A | 2018-08-23 | QTR1 | 18/19 |  | 2018-06-28 | QTR4 | 17/18 | 408 | 4236194.4
| 04 | T4439 | 42872515201 | 2016-08-31 | QTR1 | 16/17 | 9 | 3 | 323 | 397 | 397 | 105.6% | 1 | 0 | 0 | 0 | 56 | 18 | 4580758 | 50000 | 4530758 | 4651658 | 4514932 | 0 | 0 | 0 | 4514932 | 4490132 | 99.1% | 1 | 4036 | 70900 | 32 | 24 | 0 | 0 | 42063 | 0 | 0 | 18 | 14807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64860 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 412 | 4467828.17 | B0 | ACC - LUMP SUM
| 04 | T4446 | 43294915201 | 2016-10-26 | QTR2 | 16/17 | 6 | 2 | 297 | 421 | 421 | 112.1% | 1 | 0 | 0 | 0 | 98 | 26 | 2621390 | 50000 | 2571390 | 2636483 | 2515200 | 0 | 0 | 0 | 2515200 | 2487433 | 96.73% | 1 | -10793 | 15092 | 66 | 22 | 10 | 0 | 2530 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1882 | 0 | 10 | 26 | 15473 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-04-23 | QTR4 | 17/18 | 412 | 2667037.97
| 04 | T4453 | 43786615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 1 | 195 | 236 | 236 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 741586 | 37708 | 703879 | 745892 | 706473 | 0 | 0 | 0 | 706473 | 703152 | 99.9% | 1 | 985 | 4306 | 21 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6442 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 |  | 2018-04-13 | QTR4 | 17/18 | 412 | 783049.15
| 04 | T4456 | 43509515201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 140 | 210 | 208 | 98.57% | 1 | 2 | 0 | 0 | 70 | 0 | 621302 | 37607 | 583695 | 621302 | 546893 | 0 | 0 | 0 | 546893 | 547874 | 93.86% | 1 | 981 | 0 | 50 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2018-03-27 | QTR3 | 17/18 | 412 | 787751.46
| 04 | T4457 | 43436015201 | 2017-04-26 | QTR4 | 16/17 | 1 | 1 | 250 | 294 | 242 | 79.2% | 1 | 52 | 0 | 0 | 44 | 0 | 1472242 | 50000 | 1422242 | 1503409 | 1494780 | 0 | 37125 | 37125 | 1531905 | 1497583 | 105.3% | 1 | -34322 | 31168 | 30 | 14 | 0 | 0 | 24128 | 0 | 0 | 0 | 7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31960 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-03-29 | QTR3 | 17/18 | 408 | 1576733.6 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4463 | 43167215201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 101 | 139 | 143 | 104% | 1 | -4 | 4 | 0 | 38 | 0 | 312963 | 14744 | 298219 | 312963 | 288646 | 0 | 0 | 0 | 288646 | 288646 | 96.79% | 1 | 0 | 0 | 28 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9078 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 412 | 301775.1
| 04 | T4468 | 43612415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 0 | 115 | 138 | 115 | 80% | 1 | 23 | 0 | 0 | 23 | 0 | 199400 | 9926 | 189474 | 199400 | 179866 | 0 | 0 | 0 | 179866 | 179866 | 94.93% | 1 | 0 | 0 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-09-24 | QTR1 | 18/19 |  | 2018-08-16 | QTR1 | 18/19 | 412 | 207511.24
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 10 | 30 | 21 | 2552 | 3563 | 3490 | 100% | 10 | 73 | 4 | 0 | 838 | 173 | 21881350 | 401025 | 21480326 | 22585183 | 21850648 | 0 | 37125 | 37125 | 21887773 | 21699573 | 100% | 10 | -60988 | 703833 | 586 | 208 | 10 | 99 | 453920 | 270087 | 34 | 48 | 212432 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17388 | 0 | 0 | 26 | 9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1882 | 0 | 44 | 173 | 691835 | 341859
| 04 | E4Q93 | 43120415201 | 2015-04-03 | QTR4 | 14/15 | 2 | 3 | 648 | 1005 | 997 | 102.6% | 1 | 8 | 0 | 0 | 332 | 25 | 9297344 | 92920 | 9204424 | 9772712 | 9607342 | 0 | 0 | 0 | 9607342 | 9206656 | 100% | 1 | -85027 | 475368 | 293 | 39 | 0 | 25 | 117418 | 0 | 0 | 0 | 131307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248724 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 |  | 2018-04-17 | QTR4 | 17/18 | 412 | 9241085.75
| 04 | E4R63 | 43060215201 | 2016-05-06 | QTR4 | 15/16 | 2 | 5 | 388 | 565 | 565 | 117.3% | 1 | 0 | 0 | 0 | 117 | 60 | 9397416 | 96524 | 9300892 | 9547860 | 9424445 | 0 | 0 | 0 | 9424445 | 9452808 | 101.6% | 1 | 93460 | 150444 | 82 | 28 | 0 | 60 | 99149 | 77536 | 0 | 0 | 57124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2204 | 2204 | 0 | 0 | 22259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 60 | 181628 | 79740 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-09-21 | QTR1 | 18/19 |  | 2018-07-21 | QTR1 | 18/19 | 412 | 9034278.15
| 04 | E4R89 | 43234915201 | 2016-09-02 | QTR1 | 16/17 | 5 | 3 | 265 | 401 | 401 | 107.2% | 1 | 0 | 0 | 0 | 136 | 0 | 4719445 | 54299 | 4665146 | 4847205 | 4456560 | 0 | 0 | 0 | 4456560 | 4442170 | 95.22% | 1 | 26852 | 127760 | 93 | 24 | 0 | 0 | 0 | 0 | 19 | 0 | 12884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87300 | 0 | 0 | 0 | 13431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 112833 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-21 | QTR3 | 17/18 | 409 | 5266696.01
| 04 | E4R95 | 43115625201 | 2017-02-10 | QTR3 | 16/17 | 1 | 0 | 246 | 317 | 317 | 100% | 1 | 0 | 0 | 0 | 71 | 0 | 2267494 | 50000 | 2217494 | 2267494 | 2078018 | 0 | 0 | 0 | 2078018 | 2079393 | 93.77% | 1 | 1375 | 0 | 46 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-04-01 | QTR4 | 17/18 | 412 | 2587772.29
| 04 | E4S30 | 43111015201 | 2017-07-07 | QTR1 | 17/18 | 1 | 0 | 133 | 154 | 150 | 96.99% | 1 | 4 | 0 | 0 | 21 | 0 | 419035 | 25601 | 393434 | 419035 | 393248 | 0 | 0 | 0 | 393248 | 393914 | 100.1% | 1 | 666 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 |  | 2018-02-27 | QTR3 | 17/18 | 412 | 602726.22
| 04 | E4S37 | 43716515201 | 2017-05-05 | QTR4 | 16/17 | 1 | 0 | 104 | 118 | 116 | 98.08% | 1 | 2 | 0 | 0 | 14 | 0 | 549000 | 24188 | 524812 | 549000 | 512495 | 0 | 0 | 0 | 512495 | 517567 | 98.62% | 1 | 5073 | 0 | 13 | 1 | 0 | 0 | 1154 | 0 | 0 | 0 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4601 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-09-04 | QTR1 | 18/19 |  | 2018-05-03 | QTR4 | 17/18 | 409 | 504683.43
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 6 | 12 | 11 | 1784 | 2560 | 2546 | 100% | 6 | 14 | 0 | 0 | 691 | 85 | 26649734 | 343532 | 26306202 | 27403306 | 26472108 | 0 | 0 | 0 | 26472108 | 26092508 | 100% | 6 | 42399 | 753572 | 531 | 134 | 0 | 85 | 217721 | 77536 | 19 | 0 | 210208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 89504 | 2204 | 0 | 0 | 35690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | 0 | 0 | 26 | 85 | 553232 | 79740
| District 04 Totals |  |  |  |  | 16 | 42 | 32 | 4336 | 6123 | 6036 | 100% | 16 | 87 | 4 | 0 | 1529 | 258 | 48531084 | 744557 | 47786528 | 49988489 | 48322756 | 0 | 37125 | 37125 | 48359881 | 47792081 | 100% | 16 | -18589 | 1457405 | 1117 | 342 | 10 | 184 | 671641 | 347623 | 53 | 48 | 422640 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 106892 | 2204 | 0 | 26 | 45666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | -1882 | 0 | 70 | 258 | 1245067 | 421599
| 05 | T5564 | 43505515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 2 | 230 | 419 | 417 | 105.2% | 1 | 2 | 0 | 0 | 175 | 14 | 2766468 | 50000 | 2716468 | 2822949 | 2775862 | 0 | 0 | 0 | 2775862 | 2766766 | 101.9% | 1 | 0 | 56481 | 144 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 |  | 2017-12-14 | QTR2 | 17/18 | 513 | 3396278.05
| 05 | T5578 | 43364815201 | 2016-06-15 | QTR4 | 15/16 | 4 | 3 | 270 | 480 | 470 | 135.2% | 0 | 10 | 0 | 0 | 105 | 105 | 3288934 | 50000 | 3238934 | 3404197 | 3184256 | -14055 | 0 | -14055 | 3170201 | 3151385 | 97.3% | 1 | 6944 | 115263 | 65 | 40 | 0 | 0 | 47245 | 0 | 0 | 105 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 197245 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-03-23 | QTR3 | 17/18 | 509 | 2864215.47
| 05 | T5612 | 44113035201 | 2017-06-14 | QTR4 | 16/17 | 8 | 1 | 130 | 256 | 254 | 163.1% | 0 | 2 | 0 | 0 | 42 | 84 | 1243505 | 44500 | 1199005 | 2375233 | 2283435 | 0 | 0 | 0 | 2283435 | 2284747 | 190.6% | 0 | 1313 | 1131728 | 26 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-08-31 | QTR1 | 18/19 |  | 2018-05-24 | QTR4 | 17/18 | 514 | 1351001.65
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 3 | 14 | 6 | 630 | 1155 | 1141 | 33.33% | 1 | 14 | 0 | 0 | 322 | 203 | 7298907 | 144500 | 7154407 | 8602379 | 8243553 | -14055 | 0 | -14055 | 8229498 | 8202898 | 66.67% | 2 | 8257 | 1303472 | 235 | 87 | 0 | 0 | 47245 | 0 | 0 | 105 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 244630 | 0
| 05 | E5Y56 | 43744715201 | 2017-05-02 | QTR4 | 16/17 | 2 | 2 | 280 | 375 | 372 | 102.9% | 1 | 3 | 0 | 0 | 84 | 11 | 1274655 | 50000 | 1224655 | 1351445 | 1346112 | 0 | 0 | 0 | 1346112 | 1333232 | 108.9% | 1 | 1238 | 76790 | 49 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 64134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 65307 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-08-04 | QTR1 | 18/19 | 513 | 1669932.25
| 05 | E5Y60 | 43474215201 | 2017-04-04 | QTR4 | 16/17 | 3 | 2 | 170 | 297 | 307 | 105.9% | 1 | -10 | 10 | 0 | 127 | 0 | 2282739 | 50000 | 2232739 | 2439656 | 2285278 | -15840 | 0 | -15840 | 2269438 | 2207733 | 98.88% | 1 | 26994 | 156917 | 98 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-05-01 | QTR4 | 17/18 | 514 | 2421411.03
| 05 | E5Y75 | 43565515201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 110 | 184 | 182 | 105.5% | 1 | 2 | 0 | 0 | 66 | 8 | 576675 | 28000 | 548675 | 576675 | 566351 | 0 | 0 | 0 | 566351 | 566351 | 103.2% | 1 | 0 | 0 | 60 | 6 | 0 | 3 | 2792 | 0 | 0 | 5 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17676 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 |  | 2018-08-01 | QTR1 | 18/19 | 514 | 601122.85
| 05 | E5Y77 | 43809615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 250 | 359 | 358 | 111.6% | 1 | 1 | 0 | 0 | 79 | 30 | 1828183 | 50000 | 1778183 | 1904273 | 1854273 | 0 | 0 | 0 | 1854273 | 1854273 | 104.3% | 1 | 0 | 76090 | 35 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 15453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 60637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 76090 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 |  | 2018-09-18 | QTR1 | 18/19 | 513 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y92 | 43243835201 | 2017-05-02 | QTR4 | 16/17 | 1 | 1 | 150 | 243 | 241 | 98.67% | 1 | 2 | 0 | 0 | 93 | 0 | 2098740 | 50000 | 2048740 | 2179800 | 2109348 | 0 | 0 | 0 | 2109348 | 2122937 | 103.6% | 1 | 13589 | 81060 | 48 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 25982 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87882 | 878 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-03-30 | QTR3 | 17/18 | 513 | 2861396.27
| 05 | E5Y96 | 43643415201 | 2017-06-06 | QTR4 | 16/17 | 2 | 2 | 180 | 259 | 259 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 3268345 | 50000 | 3218345 | 3324038 | 3293890 | 0 | 0 | 0 | 3293890 | 3302941 | 102.6% | 1 | 9051 | 55693 | 56 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-09-17 | QTR1 | 18/19 |  | 2018-05-25 | QTR4 | 17/18 | 507 | 2900877.1
| 05 | E5Y98 | 43927215201 | 2017-09-06 | QTR1 | 17/18 | 1 | 0 | 110 | 131 | 67 | 41.82% | 1 | 64 | 0 | 0 | 21 | 0 | 162149 | 10000 | 152149 | 162149 | 119762 | 0 | 0 | 0 | 119762 | 119762 | 78.71% | 1 | 0 | 0 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 509 | 240922
| 05 | E5Y99 | 43927615201 | 2017-10-03 | QTR2 | 17/18 | 1 | 0 | 170 | 177 | 119 | 65.88% | 1 | 58 | 0 | 0 | 7 | 0 | 596733 | 35000 | 561733 | 596733 | 546163 | 0 | 0 | 0 | 546163 | 547337 | 97.44% | 1 | 1173 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 |  | 2018-07-20 | QTR1 | 18/19 | 507 | 946415.4
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 8 | 12 | 9 | 1420 | 2025 | 1905 | 100% | 8 | 120 | 10 | 0 | 556 | 49 | 12088219 | 323000 | 11765219 | 12534769 | 12121177 | -15840 | 0 | -15840 | 12105337 | 12054566 | 100% | 8 | 52045 | 446550 | 350 | 206 | 0 | 3 | 2792 | 0 | 0 | 5 | 198937 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 186671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 388400 | 878
| District 05 Totals |  |  |  |  | 11 | 26 | 15 | 2050 | 3180 | 3046 | 81.82% | 9 | 134 | 10 | 0 | 878 | 252 | 19387126 | 467500 | 18919626 | 21137148 | 20364730 | -29895 | 0 | -29895 | 20334835 | 20257464 | 90.91% | 10 | 60302 | 1750022 | 585 | 293 | 0 | 3 | 50037 | 0 | 0 | 110 | 348937 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 234056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 633030 | 878
| 06 | T6415 | 43328625201 | 2016-12-07 | QTR2 | 16/17 | 6 | 1 | 310 | 379 | 262 | 62.26% | 1 | 117 | 0 | 0 | 69 | 0 | 2632861 | 51135 | 2581726 | 2661056 | 2517080 | 0 | 150000 | 150000 | 2667080 | 2502209 | 96.92% | 1 | -136676 | 28195 | 44 | 25 | 0 | 0 | 5582 | 0 | 0 | 0 | 3406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8987 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 |  | 2018-02-07 | QTR3 | 17/18 | 606 | 3416980.25 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6416 | 43305925201 | 2016-10-26 | QTR2 | 16/17 | 6 | 3 | 180 | 290 | 290 | 118.3% | 1 | 0 | 0 | 0 | 110 | 0 | 1824984 | 53180 | 1771804 | 1972801 | 1821952 | 0 | 0 | 0 | 1821952 | 1758167 | 99.23% | 1 | -29328 | 147817 | 57 | 20 | 12 | 0 | 120172 | 0 | 21 | 0 | 5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 129660 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-04-04 | QTR4 | 17/18 | 606 | 2103857.35
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 2 | 12 | 4 | 490 | 669 | 552 | 100% | 2 | 117 | 0 | 0 | 179 | 0 | 4457845 | 104315 | 4353530 | 4633857 | 4339032 | 0 | 150000 | 150000 | 4489032 | 4260376 | 100% | 2 | -166004 | 176012 | 101 | 45 | 12 | 0 | 125754 | 0 | 21 | 0 | 8845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 138647 | 0
| 06 | E6J51 | 43652415201 | 2016-05-26 | QTR4 | 15/16 | 3 | 1 | 380 | 641 | 631 | 97.37% | 1 | 10 | 0 | 0 | 261 | 0 | 2558857 | 50000 | 2508857 | 2607925 | 2393750 | 0 | 0 | 0 | 2393750 | 1751453 | 69.81% | 1 | -593229 | 49068 | 214 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-07-20 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 606 | 3068069
| 06 | E6J96 | 42918725201 | 2016-10-27 | QTR2 | 16/17 | 5 | 3 | 240 | 375 | 375 | 115.8% | 1 | 0 | 0 | 0 | 135 | 0 | 3292828 | 50450 | 3242378 | 3417930 | 3052117 | 0 | 0 | 0 | 3052117 | 3071041 | 94.72% | 1 | 30910 | 125102 | 67 | 30 | 0 | 0 | 4950 | 0 | 0 | 0 | 121888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126838 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 |  | 2018-05-04 | QTR4 | 17/18 | 606 | 3372730.65
| 06 | E6L32 | 44048515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 90 | 97 | 96 | 98.89% | 1 | 1 | 0 | 0 | 7 | 0 | 575526 | 29529 | 545997 | 575526 | 511952 | 0 | 0 | 0 | 511952 | 511952 | 93.76% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 1362 | 0 | 0 | 0 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 |  | 2018-06-19 | QTR4 | 17/18 | 606 | 593409.7
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 3 | 9 | 4 | 710 | 1113 | 1102 | 100% | 3 | 11 | 0 | 0 | 403 | 0 | 6427211 | 129979 | 6297232 | 6601381 | 5957819 | 0 | 0 | 0 | 5957819 | 5334446 | 100% | 3 | -562319 | 174170 | 285 | 80 | 0 | 0 | 6312 | 0 | 0 | 0 | 125643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152757 | 0
| District 06 Totals |  |  |  |  | 5 | 21 | 8 | 1200 | 1782 | 1654 | 100% | 5 | 128 | 0 | 0 | 582 | 0 | 10885056 | 234294 | 10650762 | 11235238 | 10296851 | 0 | 150000 | 150000 | 10446851 | 9594822 | 100% | 5 | -728323 | 350182 | 386 | 125 | 12 | 0 | 132066 | 0 | 21 | 0 | 134488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 291404 | 0
| 07 | T7304 | 40795135201 | 2012-06-20 | QTR4 | 11/12 | 7 | 10 | 925 | 1181 | 1181 | 105.4% | 1 | 0 | 0 | 0 | 240 | 16 | 39444222 | 516565 | 38927658 | 39305377 | 38780845 | -18000 | 0 | -18000 | 38762845 | 38004215 | 97.63% | 1 | -758630 | -138845 | 145 | 61 | 20 | 0 | -219966 | 81292 | 14 | 16 | 232100 | 30289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16 | 58822 | 111581 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | QTR1 | 18/19 |  | 2016-01-08 | QTR3 | 15/16 | 714 | 44767705.24 | ARRA | AMERICAN RECOVERY AND REINVEST
| 07 | T7379 | 42906015202 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 245 | 493 | 493 | 119.6% | 1 | 0 | 0 | 0 | 200 | 48 | 7691624 | 80000 | 7611624 | 7990485 | 8163052 | 0 | 0 | 0 | 8163052 | 8182033 | 107.5% | 1 | 18982 | 298860 | 167 | 33 | 0 | 0 | 130718 | 0 | 0 | 13 | 133405 | 30546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12566 | 0 | 0 | 0 | 12037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 287412 | 30546 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2017-12-20 | QTR2 | 17/18 | 709 | 9262147.22
| 07 | T7390 | 43480715201 | 2017-05-24 | QTR4 | 16/17 | 3 | 2 | 165 | 264 | 264 | 119.4% | 1 | 0 | 0 | 0 | 99 | 0 | 3002052 | 45000 | 2957052 | 3032833 | 3060237 | 0 | 0 | 0 | 3060237 | 3105091 | 105% | 1 | 44854 | 30781 | 47 | 20 | 0 | 0 | 18080 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 30781 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 50124 | 3741 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 |  | 2018-06-29 | QTR4 | 17/18 | 799 | 3538016.5
| 07 | T7394 | 43431715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 205 | 254 | 254 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 1263874 | 50000 | 1213874 | 1263874 | 1203555 | 0 | 0 | 0 | 1203555 | 1210019 | 99.68% | 1 | 6464 | 0 | 31 | 18 | 0 | 0 | 7260 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 |  | 2018-07-03 | QTR1 | 18/19 | 796 | 1558000
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 4 | 14 | 18 | 1540 | 2192 | 2192 | 100% | 4 | 0 | 0 | 0 | 588 | 64 | 51401772 | 691565 | 50710208 | 51592569 | 51207689 | -18000 | 0 | -18000 | 51189689 | 50501358 | 100% | 4 | -688330 | 190796 | 390 | 132 | 20 | 0 | -63908 | 81292 | 14 | 29 | 370606 | 60835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59253 | 0 | 32 | 0 | 42818 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 0 | 0 | 0 | 66 | 64 | 407456 | 145868
| 07 | E7L03 | 43656815201 | 2016-04-13 | QTR4 | 15/16 | 2 | 2 | 444 | 629 | 587 | 90.54% | 1 | 42 | 0 | 0 | 185 | 0 | 3851530 | 50000 | 3801530 | 4219010 | 4049852 | 0 | 0 | 0 | 4049852 | 3939655 | 103.6% | 1 | -54636 | 367480 | 145 | 40 | 0 | 0 | 311918 | 0 | 0 | 0 | 18167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335814 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 |  | 2018-06-04 | QTR4 | 17/18 | 709 | 3798000
| 07 | E7L45 | 43243515201 | 2017-02-08 | QTR3 | 16/17 | 2 | 2 | 200 | 265 | 245 | 90% | 1 | 20 | 0 | 0 | 65 | 0 | 885313 | 40000 | 845313 | 922332 | 833142 | 0 | 0 | 0 | 833142 | 795463 | 94.1% | 1 | -18692 | 37019 | 42 | 23 | 0 | 0 | 18033 | 18033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18033 | 18033 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 |  | 2018-01-16 | QTR3 | 17/18 | 709 | 1006200
| 07 | E7L59 | 43070815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 60 | 89 | 89 | 115% | 1 | 0 | 0 | 0 | 20 | 9 | 2175849 | 50000 | 2125849 | 2175830 | 2389823 | 0 | 0 | 0 | 2389823 | 2415150 | 113.6% | 0 | 25327 | -19 | 20 | 0 | 0 | 9 | 36418 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36610 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-09-05 | QTR1 | 18/19 |  | 2018-05-11 | QTR4 | 17/18 | 798 | 1660000
| 07 | E7L76 | 43589615201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 135 | 227 | 213 | 108.1% | 1 | 14 | 0 | 0 | 67 | 25 | 921000 | 50000 | 871000 | 999500 | 949500 | 0 | 0 | 0 | 949500 | 949500 | 109% | 1 | 0 | 78500 | 39 | 28 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-07-31 | QTR1 | 18/19 |  | 2018-06-18 | QTR4 | 17/18 | 799 | 2050000 | B0 | ACC - LUMP SUM
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 4 | 6 | 6 | 839 | 1210 | 1134 | 100% | 4 | 76 | 0 | 0 | 337 | 34 | 7833692 | 190000 | 7643692 | 8316672 | 8222317 | 0 | 0 | 0 | 8222317 | 8099768 | 75% | 3 | -48001 | 482980 | 246 | 91 | 0 | 9 | 366369 | 18033 | 0 | 25 | 96879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 468957 | 18033
| District 07 Totals |  |  |  |  | 8 | 20 | 24 | 2379 | 3402 | 3326 | 100% | 8 | 76 | 0 | 0 | 925 | 98 | 59235464 | 881565 | 58353900 | 59909241 | 59430006 | -18000 | 0 | -18000 | 59412006 | 58601126 | 87.5% | 7 | -736331 | 673776 | 636 | 223 | 20 | 9 | 302461 | 99325 | 14 | 54 | 467485 | 60835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59234 | 0 | 32 | 0 | 48547 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 0 | 0 | 0 | 66 | 98 | 876413 | 163901
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8P90 | 43561515201 | 2016-06-14 | QTR4 | 15/16 | 5 | 14 | 290 | 465 | 464 | 108.6% | 1 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 9136712.84 | 110.2% | 0 | -6108 | 1045631 | 89 | 60 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 |  | 2018-04-11 | QTR4 | 17/18 | 854 | 8835780.78
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 1 | 5 | 14 | 290 | 465 | 464 | #VALUE! | 1 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 9136712.84 | 0% | 0 | -6108 | 1045631 | 89 | 60 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000
| District 08 Totals |  |  |  |  | 1 | 5 | 14 | 290 | 465 | 464 | 100% | 1 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 9136712.84 | 0% | 0 | -6108 | 1045631 | 89 | 60 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000
| Statewide Central Let Contracts SubTotal |  |  |  |  | 37 | 96 | 78 | 9272 | 12671 | 12406 | 86.49% | 32 | 265 | 113 | 0 | 2779 | 620 | 143695941 | 2074935 | 141621008 | 146862903 | 144533782 | -189199 | 187125 | -2074 | 144531708 | 142936574 | 97.3% | 36 | -1198526 | 3166960 | 1864 | 756 | 47 | 191 | 1241282 | 372833 | 75 | 260 | 1416300 | 139630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -388256 | 0 | 32 | 26 | 53695 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 18752 | 18752 | 0 | 0 | -1313 | 0 | 0 | 0 | -1882 | 0 | 159 | 512 | 2338577 | 534956
| Statewide District Let Contracts SubTotal |  |  |  |  | 35 | 61 | 71 | 7423 | 10759 | 10408 | 97.14% | 34 | 351 | 22 | 0 | 2787 | 549 | 90622297 | 1567684 | 89054613 | 95467568 | 93427417 | -34848 | 75000 | 40152 | 93467569 | 92238921.84 | 88.57% | 31 | -420382 | 4845272 | 1824 | 874 | 25 | 112 | 794197 | 95569 | 19 | 355 | 2739369 | 501173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 82 | 753253 | 2204 | 0 | 0 | 41419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 0 | 0 | 0 | 0 | 51 | 549 | 4390346 | 598946
| Statewide Totals |  |  |  |  | 72 | 157 | 149 | 16695 | 23430 | 22814 | 91.67% | 66 | 616 | 135 | 0 | 5566 | 1169 | 234318238 | 3642619 | 230675621 | 242330471 | 237961199 | -224047 | 262125 | 38078 | 237999277 | 235175495.84 | 93.06% | 67 | -1618908 | 8012232 | 3688 | 1630 | 72 | 303 | 2035479 | 468402 | 94 | 615 | 4155669 | 640803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 82 | 364997 | 2204 | 32 | 26 | 95114 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 62892 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 18752 | 18752 | 0 | 0 | -2095 | 0 | 0 | 0 | -1882 | 0 | 210 | 1061 | 6728923 | 1133902

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1Q20 | 43979815201 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2017-03-16 | 551623 | 557534 | 539909 | 5910.12 | -19008 | 520901 | -19008 | 0 | 0 | 0 | 0 | 0 | -19008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19008 | 520901 | 520901 | 0 | 682344
1 | E1Q46 | 43659915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-07-20 | 2486667 | 2519936 | 2394841 | 33269.19 | 0 | 2475891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2394841 | 2475891 | 81050 | 2833103
1 | E1Q76 | 43494115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 3162332 | 3162332 | 3141539 | 0 | 0 | 3230031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141539 | 3230031 | 88492 | 3398633 | B0 | ACC - LUMP SUM
1 | E1R00 | 43798415201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-10-19 | 399878 | 414572 | 373225 | 14694.4 | 50000 | 373225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 423225 | 373225 | -50000 | 410605 | B1 | ACC - NO EXCUSE BONUS
1 | E1R01 | 43668415201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-01-25 | 367307 | 367307 | 318382 | 0 | 25000 | 318382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 25000 | 343382 | 318382 | -25000 | 312418 | B1 | ACC - NO EXCUSE BONUS
1 | E1R02 | 44026315201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-11-16 | 253030 | 253030 | 240240 | 0 | 0 | 240240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240240 | 240240 | 0 | 210004 | B0 | ACC - LUMP SUM
1 | E1R04 | 44035915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-01-18 | 356611 | 356611 | 333569 | 0 | 0 | 333569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333569 | 333569 | 0 | 390669
1 | T1606 | 19801745201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2015-06-17 | 16630324 | 16297713 | 16277472 | -332611.69 | -39000 | 15990772 | 0 | 0 | 0 | 0 | 0 | -39000 | -39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39000 | 16238472 | 15990772 | -247700 | 16471202 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1653 | 43317315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 3821588 | 3892256 | 3742414 | 70667.91 | 0 | 3747080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3742414 | 3747080 | 4666 | 2964599
1 | T1660 | 43161915201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-09-28 | 2357000 | 2424704 | 2337783 | 67704.15 | 0 | 2292169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2337783 | 2292169 | -45614 | 3040685
1 | T1672 | 43660015201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2017-02-22 | 5457714 | 5650306 | 5444515 | 192591.74 | 0 | 5606803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5444515 | 5606803 | 162288 | 5914612
1 | T1674 | 43450515201 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2017-05-24 | 739854 | 739854 | 710516 | 0 | -20592 | 655747 | -20592 | 0 | 0 | 0 | 0 | 0 | -20592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20592 | 689924 | 655747 | -34177 | 559471 | B0 | ACC - LUMP SUM
1 | T1678 | 43492915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-02-22 | 7590540 | 7638810 | 7645659 | 48270.16 | 0 | 7687725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7645659 | 7687725 | 42066 | 9127943
1 | T1683 | 43177215201 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1414597 | 1414597 | 1411808 | 0 | 0 | 1416013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411808 | 1416013 | 4205 | 1198143
1 | T1685 | 44011715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-06-14 | 165758 | 165758 | 159130 | 0 | 0 | 159130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159130 | 159130 | 0 | 163746
1 | T1686 | 43318815201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 304735 | 321566 | 321566 | 16831.45 | 0 | 322093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321566 | 322093 | 527 | 339200 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1688 | 43498415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 440840 | 440840 | 440840 | 0 | 0 | 440840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440840 | 440840 | 0 | 446099 | B0 | ACC - LUMP SUM
2 | E2T36 | 42442415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-05-13 | 10725121 | 12250426 | 12633691 | 1525305.59 | 0 | 12633279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12633691 | 12633279 | -412 | 11100158
2 | E2U34 | 43025815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-01-20 | 4266548 | 4515459 | 4762225 | 248911.81 | 0 | 4739499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762225 | 4739499 | -22727 | 3812868
2 | E2V63 | 43860115201 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-05-17 | 1160401 | 1188813 | 1137166 | 28412.16 | 0 | 1137166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1137166 | 1137166 | 0 | 567894
2 | E2V65 | 43432315201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2017-04-19 | 3583873 | 3643220 | 3692989 | 59346.81 | 0 | 3723122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3692989 | 3723122 | 30133 | 3819418
2 | E2W07 | 43240515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-03-15 | 1148442 | 1148442 | 1142933 | 0 | 0 | 1143000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142933 | 1143000 | 66 | 1300556
2 | T2547 | 42975025201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 1879929 | 1879929 | 1845519 | 0 | -97552 | 1685674 | -97552 | 0 | 0 | 0 | 0 | 0 | -97552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97552 | 1747967 | 1685674 | -62293 | 1922742
2 | T2569 | 42870115201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 9199000 | 9915585 | 9871416 | 716584.65 | 0 | 9657046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9871416 | 9657046 | -214370 | 9784025
2 | T2643 | 43434015201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2016-12-07 | 1483252 | 1483252 | 1482220 | 0 | 0 | 1482220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482220 | 1482220 | 0 | 1682912
2 | T2648 | 43231015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 1797592 | 1797592 | 1737333 | 0 | 0 | 1782037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1737333 | 1782037 | 44704 | 1880670
2 | T2674 | 43335915201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-08-30 | 360929 | 360929 | 343649 | 0 | 0 | 343649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343649 | 343649 | 0 | 413832
2 | T2676 | 43617515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 1623696 | 1623696 | 1601844 | 0 | 0 | 1623655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601844 | 1623655 | 21810 | 1682997
3 | E3Q40 | 43375215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-09 | 782920 | 809439 | 800466 | 26519.13 | 0 | 800466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800466 | 800466 | 0 | 616285
3 | T3538 | 43357615201 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2015-06-17 | 90288 | 88663 | 74180 | -1624.32 | 0 | 74180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74180 | 74180 | 0 | 110499 | B0 | ACC - LUMP SUM
3 | T3650 | 43014645201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 3298431 | 3312865 | 3444996 | 14433.44 | 0 | 3477423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3444996 | 3477423 | 32427 | 4395538
4 | E4Q93 | 43120415201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-04-03 | 9297344 | 9772712 | 9607342 | 475367.61 | 0 | 9522316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9607342 | 9522316 | -85027 | 9241086
4 | E4R63 | 43060215201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-05-06 | 9397416 | 9547860 | 9424445 | 150444.28 | 0 | 9517905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9424445 | 9517905 | 93460 | 9034278
4 | E4R89 | 43234915201 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2016-09-02 | 4719445 | 4847205 | 4456560 | 127759.9 | 0 | 4483412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4456560 | 4483412 | 26852 | 5266696
4 | E4R95 | 43115625201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-10 | 2267494 | 2267494 | 2078018 | 0 | 0 | 2079393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2078018 | 2079393 | 1375 | 2587772
4 | E4S30 | 43111015201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-07 | 419035 | 419035 | 393248 | 0 | 0 | 393914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393248 | 393914 | 666 | 602726
4 | E4S37 | 43716515201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-05-05 | 549000 | 549000 | 512495 | 0 | 0 | 517567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512495 | 517567 | 5073 | 504683
4 | T4395 | 42936515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 1928000 | 1932802 | 1674394 | 4801.64 | 0 | 1674394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674394 | 1674394 | 0 | 1544788
4 | T4409 | 43019215201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2015-05-20 | 4789933 | 5042467 | 4996786 | 252534.18 | 0 | 4982280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4996786 | 4982280 | -14505 | 5274241 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
4 | T4422 | 43257425201 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL CONSTRUCTO | N/A | N/A | N/A | N/A | 2016-12-07 | 4613776 | 4938807 | 4932678 | 325030.9 | 0 | 4925308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4932678 | 4925308 | -7370 | 4236194
4 | T4439 | 42872515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-31 | 4580758 | 4651658 | 4514932 | 70899.67 | 0 | 4518968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4514932 | 4518968 | 4036 | 4467828 | B0 | ACC - LUMP SUM
4 | T4446 | 43294915201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 2621390 | 2636483 | 2515200 | 15092.34 | 0 | 2504407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2515200 | 2504407 | -10793 | 2667038
4 | T4453 | 43786615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 741586 | 745892 | 706473 | 4306.13 | 0 | 708943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706473 | 708943 | 2470 | 783049
4 | T4456 | 43509515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 621302 | 621302 | 546893 | 0 | 0 | 547874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546893 | 547874 | 981 | 787751
4 | T4457 | 43436015201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-04-26 | 1472242 | 1503409 | 1494780 | 31167.68 | 37125 | 1497583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37125 | 0 | 0 | 0 | 0 | 0 | 37125 | 37125 | 1531905 | 1497583 | -34322 | 1576734 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4463 | 43167215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 312963 | 312963 | 288646 | 0 | 0 | 288646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288646 | 288646 | 0 | 301775
4 | T4468 | 43612415201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-10-25 | 199400 | 199400 | 179866 | 0 | 0 | 179866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179866 | 179866 | 0 | 207511
5 | E5Y56 | 43744715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-05-02 | 1274655 | 1351445 | 1346112 | 76789.87 | 0 | 1347350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346112 | 1347350 | 1238 | 1669932
5 | E5Y60 | 43474215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-04-04 | 2282739 | 2439656 | 2285278 | 156916.9 | -15840 | 2296432 | -15840 | 0 | 0 | 0 | 0 | 0 | -15840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15840 | 2269438 | 2296432 | 26994 | 2421411
5 | E5Y75 | 43565515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-08-01 | 576675 | 576675 | 566351 | 0 | 0 | 566351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566351 | 566351 | 0 | 601123
5 | E5Y77 | 43809615201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-04-26 | 1828183 | 1904273 | 1854273 | 76089.71 | 0 | 1854273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1854273 | 1854273 | 0 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5Y92 | 43243835201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-02 | 2098740 | 2179800 | 2109348 | 81060.22 | 0 | 2122937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2109348 | 2122937 | 13589 | 2861396
5 | E5Y96 | 43643415201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-06 | 3268345 | 3324038 | 3293890 | 55692.68 | 0 | 3302941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3293890 | 3302941 | 9051 | 2900877
5 | E5Y98 | 43927215201 | F273238420 | OCEANEER CONSULTING LLC | N/A | N/A | N/A | N/A | 2017-09-06 | 162149 | 162149 | 119762 | 0 | 0 | 119762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119762 | 119762 | 0 | 240922
5 | E5Y99 | 43927615201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2017-10-03 | 596733 | 596733 | 546163 | 0 | 0 | 547337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546163 | 547337 | 1173 | 946415
5 | T5564 | 43505515201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-05-25 | 2766468 | 2822949 | 2775862 | 56480.73 | 0 | 2775862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2775862 | 2775862 | 0 | 3396278
5 | T5578 | 43364815201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-06-15 | 3288934 | 3404197 | 3184256 | 115262.79 | -14055 | 3177145 | -14055 | 0 | 0 | 0 | 0 | 0 | -14055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14055 | 3170201 | 3177145 | 6944 | 2864215
5 | T5612 | 44113035201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1243505 | 2375233 | 2283435 | 1131727.86 | 0 | 2284747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283435 | 2284747 | 1313 | 1351002
6 | E6J51 | 43652415201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-05-26 | 2558857 | 2607925 | 2393750 | 49068.4 | 0 | 1800521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2393750 | 1800521 | -593229 | 3068069
6 | E6J96 | 42918725201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-10-27 | 3292828 | 3417930 | 3052117 | 125102.18 | 0 | 3083026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3052117 | 3083026 | 30910 | 3372731
6 | E6L32 | 44048515201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-11-30 | 575526 | 575526 | 511952 | 0 | 0 | 511952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511952 | 511952 | 0 | 593410
6 | T6415 | 43328625201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 2632861 | 2661056 | 2517080 | 28194.94 | 150000 | 2530404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 2667080 | 2530404 | -136676 | 3416980 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6416 | 43305925201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 1824984 | 1972801 | 1821952 | 147816.92 | 0 | 1792624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1821952 | 1792624 | -29328 | 2103857
7 | E7L03 | 43656815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-04-13 | 3851530 | 4219010 | 4049852 | 367479.64 | 0 | 3995216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049852 | 3995216 | -54636 | 3798000
7 | E7L45 | 43243515201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-02-08 | 885313 | 922332 | 833142 | 37019.32 | 0 | 814450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833142 | 814450 | -18692 | 1006200
7 | E7L59 | 43070815201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 2175849 | 2175830 | 2389823 | -19.12 | 0 | 2415150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2389823 | 2415150 | 25327 | 1660000
7 | E7L76 | 43589615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-08-09 | 921000 | 999500 | 949500 | 78500 | 0 | 949500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949500 | 949500 | 0 | 2050000 | B0 | ACC - LUMP SUM
7 | T7304 | 40795135201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2012-06-20 | 39444222 | 39305377 | 38780845 | -138845.42 | -18000 | 38004215 | 0 | 0 | 0 | 0 | 0 | -18000 | -18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18000 | 38762845 | 38004215 | -758630 | 44767705 | ARRA | AMERICAN RECOVERY AND REINVEST
7 | T7379 | 42906015202 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 7691624 | 7990485 | 8163052 | 298860.33 | 0 | 8182033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8163052 | 8182033 | 18982 | 9262147
7 | T7390 | 43480715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 3002052 | 3032833 | 3060237 | 30780.82 | 0 | 3105091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060237 | 3105091 | 44854 | 3538017
7 | T7394 | 43431715201 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 1263874 | 1263874 | 1203555 | 0 | 0 | 1210019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203555 | 1210019 | 6464 | 1558000
8 | E8P90 | 43561515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-06-14 | 8378688 | 9424319 | 9142821 | 1045631.46 | 0 | 9136713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9142821 | 9136713 | -6108 | 8835781

## Sheet1 (hidden)
01CO | 01 | T1606 | 19801745201 | 2015-06-17 | QTR4 | 14/15 | 3 | 8 | 710 | 803 | 803 | 0 | 0 | 0 | 58 | 35 | 16630324 | 150000 | 16480324 | 16297713 | 16277472 | -39000 | 0 | -39000 | 16238472 | 15980331 | -247700 | -332612 | 33 | 0 | 0 | 120868 | 4623 | 0 | 32 | 119313 | 4940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -533590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | -293410 | 9563 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2018-07-18 | QTR1 | 18/19 | 2018-01-12 | QTR3 | 17/18 | 115 | 16471201.81 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 10 | 01co | 1 | 10
01CO | 01 | T1653 | 43317315201 | 2016-05-25 | QTR4 | 15/16 | 1 | 3 | 225 | 323 | 323 | 0 | 0 | 0 | 88 | 10 | 3821588 | 50000 | 3771588 | 3892256 | 3742414 | 0 | 0 | 0 | 3742414 | 3732176 | 4666 | 70668 | 64 | 0 | 3 | 41635 | 0 | 0 | 0 | 14614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 0 | 0 | 0 | 0 | 0 | 3 | 75002 | 18752 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 | 2017-10-05 | QTR2 | 17/18 | 113 | 2964599.15 |  |  | 3 | 24 | 0 | 0 | 0 | 0 |  | CO | 7 | 01do | 11 | 17
01CO | 01 | T1660 | 43161915201 | 2016-09-28 | QTR1 | 16/17 | 2 | 3 | 415 | 458 | 408 | 50 | 0 | 0 | 43 | 0 | 2357000 | 0 | 2357000 | 2424704 | 2337783 | 0 | 0 | 0 | 2337783 | 2243291 | -45614 | 67704 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 4220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18827 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-02-14 | QTR3 | 17/18 | 118 | 3040684.98 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 6 | 02co | 18 | 23
01CO | 01 | T1672 | 43660015201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 265 | 377 | 371 | 6 | 0 | 0 | 92 | 20 | 5457714 | 67624 | 5390090 | 5650306 | 5444515 | 0 | 0 | 0 | 5444515 | 5557409 | 162288 | 192592 | 71 | 0 | 0 | 8386 | 0 | 0 | 20 | 155081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 163467 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2018-08-07 | QTR1 | 18/19 | 2018-06-29 | QTR4 | 17/18 | 118 | 5914612.28 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 5 | 02do | 24 | 28
01CO | 01 | T1674 | 43450515201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 85 | 91 | 144 | -53 | 53 | 0 | 6 | 0 | 739854 | 29338 | 710516 | 739854 | 710516 | -20592 | 0 | -20592 | 689924 | 655747 | -34177 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F720858086 | COASTAL BRIDGE COMPANY L.L.C. | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 | 2018-05-25 | QTR4 | 17/18 | 115 | 559470.72 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO | 2 | 03co | 29 | 30
01CO | 01 | T1678 | 43492915201 | 2017-02-22 | QTR3 | 16/17 | 1 | 1 | 300 | 353 | 316 | 37 | 0 | 0 | 53 | 0 | 7590540 | 90051 | 7500489 | 7638810 | 7645659 | 0 | 0 | 0 | 7645659 | 7639455 | 42066 | 48270 | 30 | 0 | 0 | 3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 | 2018-03-12 | QTR3 | 17/18 | 115 | 9127943.35 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO | 1 | 03do | 31 | 31
01CO | 01 | T1683 | 43177215201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 235 | 253 | 247 | 6 | 0 | 0 | 18 | 0 | 1414597 | 0 | 1414597 | 1414597 | 1411808 | 0 | 0 | 0 | 1411808 | 1416013 | 4205 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593571944 | DENSON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 | 2018-05-29 | QTR4 | 17/18 | 108 | 1198142.79 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 10 | 04co | 32 | 41
01CO | 01 | T1685 | 44011715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 73 | 73 | 0 | 0 | 0 | 3 | 0 | 165758 | 6628 | 159130 | 165758 | 159130 | 0 | 0 | 0 | 159130 | 159130 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-13 | QTR1 | 18/19 | 2018-03-21 | QTR3 | 17/18 | 118 | 163745.59 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 6 | 04do | 42 | 47
01CO | 01 | T1686 | 43318815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 1 | 125 | 190 | 190 | 0 | 0 | 0 | 17 | 48 | 304735 | 0 | 304735 | 321566 | 321566 | 0 | 0 | 0 | 321566 | 322093 | 527 | 16831 | 2 | 0 | 48 | 16831 | 16831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 16831 | 16831 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-08-17 | QTR1 | 18/19 | 2018-04-30 | QTR4 | 17/18 | 113 | 339200.17 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 3 | 05co | 48 | 50
01CO | 01 | T1688 | 43498415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 86 | 84 | 2 | 0 | 0 | 11 | 0 | 440840 | 0 | 440840 | 440840 | 440840 | 0 | 0 | 0 | 440840 | 440840 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 | 2018-03-30 | QTR3 | 17/18 | 108 | 446098.62 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 | T | CO | 8 | 05do | 51 | 58
01DO | 01 | E1Q20 | 43979815201 | 2017-03-16 | QTR3 | 16/17 | 2 | 1 | 110 | 151 | 163 | -12 | 12 | 0 | 41 | 0 | 551623 | 26664 | 524959 | 557534 | 539909 | -19008 | 0 | -19008 | 520901 | 514991 | 0 | 5910 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | F134268539 | C-SQUARED CERTIFIED GENERAL CONTRACTOR | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 | 2018-02-06 | QTR3 | 17/18 | 118 | 682344.11 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO | 2 | 06co | 59 | 60
01DO | 01 | E1Q46 | 43659915201 | 2017-07-20 | QTR1 | 17/18 | 1 | 2 | 150 | 193 | 193 | 0 | 0 | 0 | 43 | 0 | 2486667 | 50000 | 2436667 | 2519936 | 2394841 | 0 | 0 | 0 | 2394841 | 2475891 | 81050 | 33269 | 18 | 19 | 0 | 34528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 34528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-22 | QTR1 | 18/19 | 2018-07-13 | QTR1 | 18/19 | 113 | 2833102.66 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO | 3 | 06do | 61 | 63
01DO | 01 | E1Q76 | 43494115201 | 2017-10-19 | QTR2 | 17/18 | 1 | 0 | 190 | 211 | 181 | 30 | 0 | 0 | 21 | 0 | 3162332 | 50000 | 3112332 | 3162332 | 3141539 | 0 | 0 | 0 | 3141539 | 3230031 | 88492 | 0 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 | 2018-07-25 | QTR1 | 18/19 | 118 | 3398633.17 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | DO | 4 | 07co | 64 | 67
01DO | 01 | E1R00 | 43798415201 | 2017-10-19 | QTR2 | 17/18 | 1 | 2 | 55 | 64 | 64 | 0 | 0 | 0 | 9 | 0 | 399878 | 25227 | 374651 | 414572 | 373225 | 0 | 50000 | 50000 | 423225 | 373225 | -50000 | 14694 | 8 | 0 | 0 | 10240 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14694 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 | 2018-06-11 | QTR4 | 17/18 | 118 | 410604.57 | B1 | ACC - NO EXCUSE BONUS | 0 | 1 | 0 | 0 | 0 | 0 |  | DO | 4 | 07do | 68 | 71
01DO | 01 | E1R01 | 43668415201 | 2018-01-25 | QTR3 | 17/18 | 1 | 0 | 85 | 89 | 76 | 13 | 0 | 0 | 4 | 0 | 367307 | 12629 | 354678 | 367307 | 318382 | 0 | 25000 | 25000 | 343382 | 318382 | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 | 2018-08-01 | QTR1 | 18/19 | 115 | 312417.65 | B1 | ACC - NO EXCUSE BONUS | 0 | 4 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 72 | 71
01DO | 01 | E1R02 | 44026315201 | 2017-11-16 | QTR2 | 17/18 | 1 | 1 | 75 | 76 | 53 | 23 | 0 | 0 | 1 | 0 | 253030 | 12790 | 240240 | 253030 | 240240 | 0 | 0 | 0 | 240240 | 240240 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-05-10 | QTR4 | 17/18 | 108 | 210003.63 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO | 1 | 08do | 72 | 72
01DO | 01 | E1R04 | 44035915201 | 2018-01-18 | QTR3 | 17/18 | 1 | 0 | 75 | 93 | 82 | 11 | 0 | 0 | 18 | 0 | 356611 | 14483 | 342128 | 356611 | 333569 | 0 | 0 | 0 | 333569 | 333569 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-08-20 | QTR1 | 18/19 | 2018-07-05 | QTR1 | 18/19 | 113 | 390668.63 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2547 | 42975025201 | 2015-04-29 | QTR4 | 14/15 | 1 | 1 | 160 | 198 | 254 | -56 | 56 | 0 | 38 | 0 | 1879929 | 0 | 1879929 | 1879929 | 1845519 | -97552 | 0 | -97552 | 1747967 | 1685674 | -62293 | 0 | 12 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 | 2016-03-25 | QTR3 | 15/16 | 209 | 1922742.1 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2569 | 42870115201 | 2015-04-29 | QTR4 | 14/15 | 2 | 8 | 450 | 744 | 744 | 0 | 0 | 0 | 236 | 58 | 9199000 | 134745 | 9064255 | 9915585 | 9871416 | 0 | 0 | 0 | 9871416 | 9657046 | -214370 | 716585 | 179 | 0 | 40 | 464223 | 0 | 0 | 18 | 329397 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 794520 | 2083 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-08-24 | QTR1 | 18/19 | 2017-08-29 | QTR1 | 17/18 | 208 | 9784025.26 |  |  | 44 | 57 | 0 | 0 | 0 | 0 |  | CO |  | 0
02CO | 02 | T2643 | 43434015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 300 | 357 | 317 | 40 | 0 | 0 | 57 | 0 | 1483252 | 50000 | 1433252 | 1483252 | 1482220 | 0 | 0 | 0 | 1482220 | 1482220 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-07-05 | QTR1 | 18/19 | 2018-03-16 | QTR3 | 17/18 | 208 | 1682912.13 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2648 | 43231015201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 140 | 177 | 173 | 4 | 0 | 0 | 32 | 5 | 1797592 | 50000 | 1747592 | 1797592 | 1737333 | 0 | 0 | 0 | 1737333 | 1782037 | 44704 | 0 | 28 | 0 | 1 | 14238 | 0 | 0 | 4 | 30734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 44972 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-27 | QTR1 | 18/19 | 2018-06-29 | QTR4 | 17/18 | 209 | 1880670.12 |  |  | 5 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2674 | 43335915201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 100 | 107 | 86 | 21 | 0 | 0 | 7 | 0 | 360929 | 120 | 360809 | 360929 | 343649 | 0 | 0 | 0 | 343649 | 343649 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-08-14 | QTR1 | 18/19 | 2018-03-29 | QTR3 | 17/18 | 209 | 413831.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2676 | 43617515201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 110 | 135 | 135 | 0 | 0 | 0 | 21 | 4 | 1623696 | 50000 | 1573696 | 1623696 | 1601844 | 0 | 0 | 0 | 1601844 | 1623655 | 21810 | 0 | 16 | 0 | 0 | 5575 | 0 | 0 | 4 | 8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 14088 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 | 2018-05-22 | QTR4 | 17/18 | 208 | 1682996.74 |  |  | 4 | 5 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2T36 | 42442415201 | 2015-05-13 | QTR4 | 14/15 | 1 | 9 | 365 | 727 | 727 | 0 | 0 | 0 | 126 | 236 | 10725121 | 99413 | 10625708 | 12250426 | 12633691 | 0 | 0 | 0 | 12633691 | 12549851 | -412 | 1525306 | 47 | 0 | 0 | 26279 | 0 | 0 | 236 | 1452107 | 295700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1496831 | 295700 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-17 | QTR1 | 18/19 | 2018-04-04 | QTR4 | 17/18 | 208 | 11100158.43 |  |  | 14 | 79 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U34 | 43025815201 | 2016-01-20 | QTR3 | 15/16 | 2 | 6 | 530 | 710 | 670 | 40 | 0 | 0 | 107 | 73 | 4266548 | 50000 | 4216548 | 4515459 | 4762225 | 0 | 0 | 0 | 4762225 | 4710138 | -22727 | 248912 | 44 | 0 | 0 | 7337 | 0 | 0 | 73 | 262215 | 26378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 269552 | 26378 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-27 | QTR1 | 18/19 | 2018-04-13 | QTR4 | 17/18 | 208 | 3812868.47 |  |  | 0 | 63 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V63 | 43860115201 | 2017-05-17 | QTR4 | 16/17 | 2 | 1 | 180 | 201 | 199 | 2 | 0 | 0 | 21 | 0 | 1160401 | 24341 | 1136060 | 1188813 | 1137166 | 0 | 0 | 0 | 1137166 | 1137166 | 0 | 28412 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28412 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-09-19 | QTR1 | 18/19 | 2018-05-09 | QTR4 | 17/18 | 209 | 567894 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V65 | 43432315201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 220 | 353 | 333 | 20 | 0 | 0 | 118 | 15 | 3583873 | 50000 | 3533873 | 3643220 | 3692989 | 0 | 0 | 0 | 3692989 | 3693971 | 30133 | 59347 | 55 | 0 | 15 | 54887 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 55797 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-08-02 | QTR1 | 18/19 | 2018-06-07 | QTR4 | 17/18 | 214 | 3819418.25 |  |  | 12 | 63 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W07 | 43240515201 | 2017-03-15 | QTR3 | 16/17 | 1 | 0 | 225 | 282 | 281 | 1 | 0 | 0 | 49 | 8 | 1148442 | 50000 | 1098442 | 1148442 | 1142933 | 0 | 0 | 0 | 1142933 | 1143000 | 66 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4409 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 | 2018-06-20 | QTR4 | 17/18 | 216 | 1300555.65 |  |  | 8 | 22 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3538 | 43357615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 25 | 38 | 36 | 2 | 0 | 0 | 13 | 0 | 90288 | 5024 | 85264 | 88663 | 74180 | 0 | 0 | 0 | 74180 | 74180 | 0 | -1624 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -1624 | 0 | F473850128 | LEVIATHAN TRUCKING LLC | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 | 2015-10-30 | QTR2 | 15/16 | 308 | 110498.62 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3650 | 43014645201 | 2017-05-24 | QTR4 | 16/17 | 4 | 1 | 270 | 329 | 327 | 2 | 0 | 0 | 59 | 0 | 3298431 | 50000 | 3248431 | 3312865 | 3444996 | 0 | 0 | 0 | 3444996 | 3477423 | 32427 | 14433 | 38 | 0 | 0 | 3050 | 0 | 0 | 0 | 12545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19871 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-09-25 | QTR1 | 18/19 | 2018-06-08 | QTR4 | 17/18 | 321 | 4395538.46 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3Q40 | 43375215201 | 2017-02-09 | QTR3 | 16/17 | 1 | 3 | 120 | 236 | 235 | 1 | 0 | 0 | 93 | 23 | 782920 | 28747 | 754173 | 809439 | 800466 | 0 | 0 | 0 | 800466 | 800466 | 0 | 26519 | 71 | 0 | 0 | 0 | 0 | 0 | 8 | 17296 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 26519 | 217 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-08-13 | QTR1 | 18/19 | 2018-02-06 | QTR3 | 17/18 | 314 | 616284.72 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4395 | 42936515201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 286 | 475 | 475 | 0 | 0 | 0 | 189 | 0 | 1928000 | 50000 | 1878000 | 1932802 | 1674394 | 0 | 0 | 0 | 1674394 | 1669592 | 0 | 4802 | 135 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 11441 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-23 | QTR1 | 18/19 | 2018-05-26 | QTR4 | 17/18 | 412 | 1544787.59 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4409 | 43019215201 | 2015-05-20 | QTR4 | 14/15 | 3 | 9 | 588 | 824 | 824 | 0 | 0 | 0 | 142 | 94 | 4789933 | 51040 | 4738893 | 5042467 | 4996786 | 0 | 0 | 0 | 4996786 | 4938750 | -14505 | 252534 | 101 | 0 | 64 | 102911 | 49551 | 0 | 30 | 132980 | 71772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 236958 | 121323 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 | 2018-03-02 | QTR3 | 17/18 | 412 | 5274241.43 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4422 | 43257425201 | 2016-12-07 | QTR2 | 16/17 | 4 | 4 | 257 | 429 | 429 | 0 | 0 | 0 | 137 | 35 | 4613776 | 50000 | 4563776 | 4938807 | 4932678 | 0 | 0 | 0 | 4932678 | 4896545 | -7370 | 325031 | 104 | 0 | 35 | 282288 | 220536 | 6 | 0 | 31835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 35 | 314123 | 220536 | F900882359 | INFRASTRUCTURE AND INDUSTRIAL CONSTRUCTO | N/A | N/A | N/A | N/A | 2018-08-23 | QTR1 | 18/19 | 2018-06-28 | QTR4 | 17/18 | 408 | 4236194.4 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4439 | 42872515201 | 2016-08-31 | QTR1 | 16/17 | 9 | 3 | 323 | 397 | 397 | 0 | 0 | 0 | 56 | 18 | 4580758 | 50000 | 4530758 | 4651658 | 4514932 | 0 | 0 | 0 | 4514932 | 4490132 | 4036 | 70900 | 32 | 0 | 0 | 42063 | 0 | 0 | 18 | 14807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 64860 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-09 | QTR1 | 18/19 | 2018-03-23 | QTR3 | 17/18 | 412 | 4467828.17 | B0 | ACC - LUMP SUM | 18 | 24 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4446 | 43294915201 | 2016-10-26 | QTR2 | 16/17 | 6 | 2 | 297 | 421 | 421 | 0 | 0 | 0 | 98 | 26 | 2621390 | 50000 | 2571390 | 2636483 | 2515200 | 0 | 0 | 0 | 2515200 | 2487433 | -10793 | 15092 | 66 | 10 | 0 | 2530 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 26 | 15473 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 | 2018-04-23 | QTR4 | 17/18 | 412 | 2667037.97 |  |  | 26 | 22 | 0 | 0 | -1882 | 0 |  | CO
04CO | 04 | T4453 | 43786615201 | 2017-03-29 | QTR3 | 16/17 | 2 | 1 | 195 | 236 | 236 | 0 | 0 | 0 | 41 | 0 | 741586 | 37708 | 703879 | 745892 | 706473 | 0 | 0 | 0 | 706473 | 703152 | 985 | 4306 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6442 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-21 | QTR1 | 18/19 | 2018-04-13 | QTR4 | 17/18 | 412 | 783049.15 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4456 | 43509515201 | 2017-04-26 | QTR4 | 16/17 | 1 | 0 | 140 | 210 | 208 | 2 | 0 | 0 | 70 | 0 | 621302 | 37607 | 583695 | 621302 | 546893 | 0 | 0 | 0 | 546893 | 547874 | 981 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 | 2018-03-27 | QTR3 | 17/18 | 412 | 787751.46 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4457 | 43436015201 | 2017-04-26 | QTR4 | 16/17 | 1 | 1 | 250 | 294 | 242 | 52 | 0 | 0 | 44 | 0 | 1472242 | 50000 | 1422242 | 1503409 | 1494780 | 0 | 37125 | 37125 | 1531905 | 1497583 | -34322 | 31168 | 30 | 0 | 0 | 24128 | 0 | 0 | 0 | 7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31960 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-03-29 | QTR3 | 17/18 | 408 | 1576733.6 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4463 | 43167215201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 101 | 139 | 143 | -4 | 4 | 0 | 38 | 0 | 312963 | 14744 | 298219 | 312963 | 288646 | 0 | 0 | 0 | 288646 | 288646 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9078 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-30 | QTR1 | 18/19 | 2017-12-20 | QTR2 | 17/18 | 412 | 301775.1 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4468 | 43612415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 0 | 115 | 138 | 115 | 23 | 0 | 0 | 23 | 0 | 199400 | 9926 | 189474 | 199400 | 179866 | 0 | 0 | 0 | 179866 | 179866 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-09-24 | QTR1 | 18/19 | 2018-08-16 | QTR1 | 18/19 | 412 | 207511.24 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4Q93 | 43120415201 | 2015-04-03 | QTR4 | 14/15 | 2 | 3 | 648 | 1005 | 997 | 8 | 0 | 0 | 332 | 25 | 9297344 | 92920 | 9204424 | 9772712 | 9607342 | 0 | 0 | 0 | 9607342 | 9206656 | -85027 | 475368 | 293 | 0 | 25 | 117418 | 0 | 0 | 0 | 131307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 248724 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2018-08-16 | QTR1 | 18/19 | 2018-04-17 | QTR4 | 17/18 | 412 | 9241085.75 |  |  | 10 | 39 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R63 | 43060215201 | 2016-05-06 | QTR4 | 15/16 | 2 | 5 | 388 | 565 | 565 | 0 | 0 | 0 | 117 | 60 | 9397416 | 96524 | 9300892 | 9547860 | 9424445 | 0 | 0 | 0 | 9424445 | 9452808 | 93460 | 150444 | 82 | 0 | 60 | 99149 | 77536 | 0 | 0 | 57124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 2204 | 2204 | 0 | 0 | 22259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 60 | 181628 | 79740 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-09-21 | QTR1 | 18/19 | 2018-07-21 | QTR1 | 18/19 | 412 | 9034278.15 |  |  | 30 | 28 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R89 | 43234915201 | 2016-09-02 | QTR1 | 16/17 | 5 | 3 | 265 | 401 | 401 | 0 | 0 | 0 | 136 | 0 | 4719445 | 54299 | 4665146 | 4847205 | 4456560 | 0 | 0 | 0 | 4456560 | 4442170 | 26852 | 127760 | 93 | 0 | 0 | 0 | 0 | 19 | 0 | 12884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87300 | 0 | 0 | 0 | 13431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -782 | 0 | 19 | 0 | 112833 | 0 | F590702991 | HARDRIVES OF DELRAY INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-02-21 | QTR3 | 17/18 | 409 | 5266696.01 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R95 | 43115625201 | 2017-02-10 | QTR3 | 16/17 | 1 | 0 | 246 | 317 | 317 | 0 | 0 | 0 | 71 | 0 | 2267494 | 50000 | 2217494 | 2267494 | 2078018 | 0 | 0 | 0 | 2078018 | 2079393 | 1375 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-04-01 | QTR4 | 17/18 | 412 | 2587772.29 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S30 | 43111015201 | 2017-07-07 | QTR1 | 17/18 | 1 | 0 | 133 | 154 | 150 | 4 | 0 | 0 | 21 | 0 | 419035 | 25601 | 393434 | 419035 | 393248 | 0 | 0 | 0 | 393248 | 393914 | 666 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5446 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-02 | QTR1 | 18/19 | 2018-02-27 | QTR3 | 17/18 | 412 | 602726.22 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S37 | 43716515201 | 2017-05-05 | QTR4 | 16/17 | 1 | 0 | 104 | 118 | 116 | 2 | 0 | 0 | 14 | 0 | 549000 | 24188 | 524812 | 549000 | 512495 | 0 | 0 | 0 | 512495 | 517567 | 5073 | 0 | 13 | 0 | 0 | 1154 | 0 | 0 | 0 | 3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4601 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-09-04 | QTR1 | 18/19 | 2018-05-03 | QTR4 | 17/18 | 409 | 504683.43 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5564 | 43505515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 2 | 230 | 419 | 417 | 2 | 0 | 0 | 175 | 14 | 2766468 | 50000 | 2716468 | 2822949 | 2775862 | 0 | 0 | 0 | 2775862 | 2766766 | 0 | 56481 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47385 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-03 | QTR1 | 18/19 | 2017-12-14 | QTR2 | 17/18 | 513 | 3396278.05 |  |  | 14 | 31 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5578 | 43364815201 | 2016-06-15 | QTR4 | 15/16 | 4 | 3 | 270 | 480 | 470 | 10 | 0 | 0 | 105 | 105 | 3288934 | 50000 | 3238934 | 3404197 | 3184256 | -14055 | 0 | -14055 | 3170201 | 3151385 | 6944 | 115263 | 65 | 0 | 0 | 47245 | 0 | 0 | 105 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 197245 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 | 2018-03-23 | QTR3 | 17/18 | 509 | 2864215.47 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5612 | 44113035201 | 2017-06-14 | QTR4 | 16/17 | 8 | 1 | 130 | 256 | 254 | 2 | 0 | 0 | 42 | 84 | 1243505 | 44500 | 1199005 | 2375233 | 2283435 | 0 | 0 | 0 | 2283435 | 2284747 | 1313 | 1131728 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-08-31 | QTR1 | 18/19 | 2018-05-24 | QTR4 | 17/18 | 514 | 1351001.65 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5Y56 | 43744715201 | 2017-05-02 | QTR4 | 16/17 | 2 | 2 | 280 | 375 | 372 | 3 | 0 | 0 | 84 | 11 | 1274655 | 50000 | 1224655 | 1351445 | 1346112 | 0 | 0 | 0 | 1346112 | 1333232 | 1238 | 76790 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 64134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 65307 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 | 2018-08-04 | QTR1 | 18/19 | 513 | 1669932.25 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y60 | 43474215201 | 2017-04-04 | QTR4 | 16/17 | 3 | 2 | 170 | 297 | 307 | -10 | 10 | 0 | 127 | 0 | 2282739 | 50000 | 2232739 | 2439656 | 2285278 | -15840 | 0 | -15840 | 2269438 | 2207733 | 26994 | 156917 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68218 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 | 2018-05-01 | QTR4 | 17/18 | 514 | 2421411.03 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y75 | 43565515201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 110 | 184 | 182 | 2 | 0 | 0 | 66 | 8 | 576675 | 28000 | 548675 | 576675 | 566351 | 0 | 0 | 0 | 566351 | 566351 | 0 | 0 | 60 | 0 | 3 | 2792 | 0 | 0 | 5 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17676 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-09-26 | QTR1 | 18/19 | 2018-08-01 | QTR1 | 18/19 | 514 | 601122.85 |  |  | 8 | 6 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y77 | 43809615201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 250 | 359 | 358 | 1 | 0 | 0 | 79 | 30 | 1828183 | 50000 | 1778183 | 1904273 | 1854273 | 0 | 0 | 0 | 1854273 | 1854273 | 0 | 76090 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 15453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 60637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 76090 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-08-09 | QTR1 | 18/19 | 2018-09-18 | QTR1 | 18/19 | 513 | 1869435 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y92 | 43243835201 | 2017-05-02 | QTR4 | 16/17 | 1 | 1 | 150 | 243 | 241 | 2 | 0 | 0 | 93 | 0 | 2098740 | 50000 | 2048740 | 2179800 | 2109348 | 0 | 0 | 0 | 2109348 | 2122937 | 13589 | 81060 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 25982 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87882 | 878 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 | 2018-03-30 | QTR3 | 17/18 | 513 | 2861396.27 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y96 | 43643415201 | 2017-06-06 | QTR4 | 16/17 | 2 | 2 | 180 | 259 | 259 | 0 | 0 | 0 | 79 | 0 | 3268345 | 50000 | 3218345 | 3324038 | 3293890 | 0 | 0 | 0 | 3293890 | 3302941 | 9051 | 55693 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73227 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-09-17 | QTR1 | 18/19 | 2018-05-25 | QTR4 | 17/18 | 507 | 2900877.1 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y98 | 43927215201 | 2017-09-06 | QTR1 | 17/18 | 1 | 0 | 110 | 131 | 67 | 64 | 0 | 0 | 21 | 0 | 162149 | 10000 | 152149 | 162149 | 119762 | 0 | 0 | 0 | 119762 | 119762 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 | 2018-02-07 | QTR3 | 17/18 | 509 | 240922 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y99 | 43927615201 | 2017-10-03 | QTR2 | 17/18 | 1 | 0 | 170 | 177 | 119 | 58 | 0 | 0 | 7 | 0 | 596733 | 35000 | 561733 | 596733 | 546163 | 0 | 0 | 0 | 546163 | 547337 | 1173 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2018-08-06 | QTR1 | 18/19 | 2018-07-20 | QTR1 | 18/19 | 507 | 946415.4 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6415 | 43328625201 | 2016-12-07 | QTR2 | 16/17 | 6 | 1 | 310 | 379 | 262 | 117 | 0 | 0 | 69 | 0 | 2632861 | 51135 | 2581726 | 2661056 | 2517080 | 0 | 150000 | 150000 | 2667080 | 2502209 | -136676 | 28195 | 44 | 0 | 0 | 5582 | 0 | 0 | 0 | 3406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8987 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-07-16 | QTR1 | 18/19 | 2018-02-07 | QTR3 | 17/18 | 606 | 3416980.25 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6416 | 43305925201 | 2016-10-26 | QTR2 | 16/17 | 6 | 3 | 180 | 290 | 290 | 0 | 0 | 0 | 110 | 0 | 1824984 | 53180 | 1771804 | 1972801 | 1821952 | 0 | 0 | 0 | 1821952 | 1758167 | -29328 | 147817 | 57 | 12 | 0 | 120172 | 0 | 21 | 0 | 5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 129660 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 | 2018-04-04 | QTR4 | 17/18 | 606 | 2103857.35 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J51 | 43652415201 | 2016-05-26 | QTR4 | 15/16 | 3 | 1 | 380 | 641 | 631 | 10 | 0 | 0 | 261 | 0 | 2558857 | 50000 | 2508857 | 2607925 | 2393750 | 0 | 0 | 0 | 2393750 | 1751453 | -593229 | 49068 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-07-20 | QTR1 | 18/19 | 2018-06-18 | QTR4 | 17/18 | 606 | 3068069 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J96 | 42918725201 | 2016-10-27 | QTR2 | 16/17 | 5 | 3 | 240 | 375 | 375 | 0 | 0 | 0 | 135 | 0 | 3292828 | 50450 | 3242378 | 3417930 | 3052117 | 0 | 0 | 0 | 3052117 | 3071041 | 30910 | 125102 | 67 | 0 | 0 | 4950 | 0 | 0 | 0 | 121888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126838 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-08-28 | QTR1 | 18/19 | 2018-05-04 | QTR4 | 17/18 | 606 | 3372730.65 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6L32 | 44048515201 | 2017-11-30 | QTR2 | 17/18 | 1 | 0 | 90 | 97 | 96 | 1 | 0 | 0 | 7 | 0 | 575526 | 29529 | 545997 | 575526 | 511952 | 0 | 0 | 0 | 511952 | 511952 | 0 | 0 | 4 | 0 | 0 | 1362 | 0 | 0 | 0 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-07-30 | QTR1 | 18/19 | 2018-06-19 | QTR4 | 17/18 | 606 | 593409.7 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7304 | 40795135201 | 2012-06-20 | QTR4 | 11/12 | 7 | 10 | 925 | 1181 | 1181 | 0 | 0 | 0 | 240 | 16 | 39444222 | 516565 | 38927658 | 39305377 | 38780845 | -18000 | 0 | -18000 | 38762845 | 38004215 | -758630 | -138845 | 145 | 20 | 0 | -219966 | 81292 | 14 | 16 | 232100 | 30289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16 | 58822 | 111581 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-07-25 | QTR1 | 18/19 | 2016-01-08 | QTR3 | 15/16 | 714 | 44767705.24 | ARRA | AMERICAN RECOVERY AND REINVEST | 16 | 61 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7379 | 42906015202 | 2016-05-25 | QTR4 | 15/16 | 3 | 6 | 245 | 493 | 493 | 0 | 0 | 0 | 200 | 48 | 7691624 | 80000 | 7611624 | 7990485 | 8163052 | 0 | 0 | 0 | 8163052 | 8156533 | 18982 | 298860 | 167 | 0 | 0 | 130718 | 0 | 0 | 13 | 133405 | 30546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12566 | 0 | 0 | 0 | 12037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | -1313 | 0 | 0 | 48 | 287412 | 30546 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 | 2017-12-20 | QTR2 | 17/18 | 709 | 9262147.22 |  |  | 48 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7390 | 43480715201 | 2017-05-24 | QTR4 | 16/17 | 3 | 2 | 165 | 264 | 264 | 0 | 0 | 0 | 99 | 0 | 3002052 | 45000 | 2957052 | 3032833 | 3060237 | 0 | 0 | 0 | 3060237 | 3105091 | 44854 | 30781 | 47 | 0 | 0 | 18080 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 30781 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 50124 | 3741 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-09-28 | QTR1 | 18/19 | 2018-06-29 | QTR4 | 17/18 | 799 | 3538016.5 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7394 | 43431715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 205 | 254 | 254 | 0 | 0 | 0 | 49 | 0 | 1263874 | 50000 | 1213874 | 1263874 | 1203555 | 0 | 0 | 0 | 1203555 | 1210019 | 6464 | 0 | 31 | 0 | 0 | 7260 | 0 | 0 | 0 | 3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2018-08-03 | QTR1 | 18/19 | 2018-07-03 | QTR1 | 18/19 | 796 | 1558000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7L03 | 43656815201 | 2016-04-13 | QTR4 | 15/16 | 2 | 2 | 444 | 629 | 587 | 42 | 0 | 0 | 185 | 0 | 3851530 | 50000 | 3801530 | 4219010 | 4049852 | 0 | 0 | 0 | 4049852 | 3939655 | -54636 | 367480 | 145 | 0 | 0 | 311918 | 0 | 0 | 0 | 18167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335814 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-07-10 | QTR1 | 18/19 | 2018-06-04 | QTR4 | 17/18 | 709 | 3798000 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L45 | 43243515201 | 2017-02-08 | QTR3 | 16/17 | 2 | 2 | 200 | 265 | 245 | 20 | 0 | 0 | 65 | 0 | 885313 | 40000 | 845313 | 922332 | 833142 | 0 | 0 | 0 | 833142 | 795463 | -18692 | 37019 | 42 | 0 | 0 | 18033 | 18033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18033 | 18033 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2018-08-15 | QTR1 | 18/19 | 2018-01-16 | QTR3 | 17/18 | 709 | 1006200 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L59 | 43070815201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 60 | 89 | 89 | 0 | 0 | 0 | 20 | 9 | 2175849 | 50000 | 2125849 | 2175830 | 2389823 | 0 | 0 | 0 | 2389823 | 2415150 | 25327 | -19 | 20 | 0 | 9 | 36418 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36610 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-09-05 | QTR1 | 18/19 | 2018-05-11 | QTR4 | 17/18 | 798 | 1660000 |  |  | 9 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L76 | 43589615201 | 2017-08-09 | QTR1 | 17/18 | 1 | 1 | 135 | 227 | 213 | 14 | 0 | 0 | 67 | 25 | 921000 | 50000 | 871000 | 999500 | 949500 | 0 | 0 | 0 | 949500 | 949500 | 0 | 78500 | 39 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 78500 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-07-31 | QTR1 | 18/19 | 2018-06-18 | QTR4 | 17/18 | 799 | 2050000 | B0 | ACC - LUMP SUM | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P90 | 43561515201 | 2016-06-14 | QTR4 | 15/16 | 5 | 14 | 290 | 465 | 464 | 1 | 0 | 0 | 149 | 26 | 8378688 | 86879 | 8291809 | 9424319 | 9142821 | 0 | 0 | 0 | 9142821 | 9055971 | -6108 | 1045631 | 89 | 0 | 0 | 67732 | 0 | 0 | 0 | 330577 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 428627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 888937 | 178000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-07-06 | QTR1 | 18/19 | 2018-04-11 | QTR4 | 17/18 | 854 | 8835780.78 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0