## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 137877526 | 136252843 | 138340654 | 136997755 | 0 | 138707962 | 1.802% | 97.06% | 977924 | 0.7177% | 463132 | 0.3359% | 7665 | 949 | 12.38% | 383 | 4.997% | 93 | 1.213% | 553 | 7.215% | 8311 | 8.428% | 9674 | 9737 | 8405 | 9.654% | 91.18%
| District Let | 44887228 | 44110344 | 45299709 | 44642176 | 0 | 44508069 | 0.9017% | 96% | 579998 | 1.315% | 412482 | 0.9189% | 4790 | 379 | 7.912% | 193 | 4.029% | 72 | 1.503% | 202 | 4.217% | 5064 | 5.72% | 5639 | 5547 | 4975 | 3.862% | 92%
| All Contracts | 182764754 | 180363187 | 183640363 | 181639931 | 0 | 183216031 | 1.582% | 96.61% | 1557922 | 0.8638% | 875614 | 0.4791% | 12455 | 1328 | 10.66% | 576 | 4.625% | 165 | 1.325% | 755 | 6.062% | 13375 | 7.387% | 15313 | 15284 | 13380 | 7.427% | 91.53%
2 | Central Let | 81923408 | 80560060 | 84691185 | 84724704 | 0 | 84321520 | 4.669% | 80% | 3358888 | 4.169% | 2767776 | 3.378% | 5457 | 1095 | 20.07% | 442 | 8.1% | 48 | 0.8796% | 871 | 15.96% | 6376 | 16.84% | 7975 | 8258 | 6721 | 23.16% | 76.67%
| District Let | 38745763 | 38386748 | 39150252 | 38741477 | 0 | 38741475 | 0.9241% | 83.33% | 604452 | 1.575% | 404488 | 1.044% | 1478 | 266 | 18% | 91 | 6.157% | 8 | 0.5413% | 67 | 4.533% | 1553 | 5.074% | 1910 | 1897 | 1540 | 4.195% | 83.33%
| All Contracts | 120669171 | 118946808 | 123841437 | 123466181 | 0 | 123062995 | 3.461% | 80.56% | 3963340 | 3.332% | 3172264 | 2.629% | 6935 | 1361 | 19.63% | 533 | 7.686% | 56 | 0.8075% | 938 | 13.53% | 7929 | 14.33% | 9885 | 10155 | 8261 | 19.12% | 77.78%
3 | Central Let | 34627528 | 34159900 | 36688397 | 37367056 | 537500 | 37522913 | 9.845% | 87.5% | 2197797 | 6.434% | 2060868 | 5.952% | 3218 | 813 | 25.26% | 285 | 8.856% | 11 | 0.3418% | 249 | 7.738% | 3478 | 8.08% | 4576 | 4552 | 3454 | 7.334% | 93.75%
| District Let | 11868051 | 11491949 | 12294995 | 11906990 | 0 | 11879201 | 3.37% | 81.25% | 665468 | 5.791% | 426944 | 3.597% | 1225 | 213 | 17.39% | 76 | 6.204% | 8 | 0.6531% | 297 | 24.24% | 1530 | 24.9% | 1779 | 1637 | 1348 | 10.04% | 93.75%
| All Contracts | 46495579 | 45651849 | 48983392 | 49274046 | 537500 | 49402114 | 8.215% | 84.38% | 2863265 | 6.272% | 2487812 | 5.351% | 4443 | 1026 | 23.09% | 361 | 8.125% | 19 | 0.4276% | 546 | 12.29% | 5008 | 12.72% | 6355 | 6189 | 4802 | 8.08% | 93.75%
4 | Central Let | 70476185 | 69420961 | 70973495 | 68186521 | 0 | 69414462 | -0.009362% | 100% | 695304 | 1.002% | 497309 | 0.7056% | 5509 | 613 | 11.13% | 271 | 4.919% | 6 | 0.1089% | 253 | 4.592% | 5768 | 4.701% | 6654 | 6423 | 5539 | 0.5446% | 89.47%
| District Let | 137036577 | 136190465 | 139392162 | 139333540 | 0 | 140873821 | 3.439% | 95.24% | 2590165 | 1.902% | 2355588 | 1.719% | 5228 | 636 | 12.17% | 204 | 3.902% | 44 | 0.8416% | 96 | 1.836% | 5368 | 2.678% | 6217 | 5875 | 5035 | -3.692% | 95.24%
| All Contracts | 207512762 | 205611426 | 210365657 | 207520061 | 0 | 210288283 | 2.275% | 97.5% | 3285469 | 1.598% | 2852897 | 1.375% | 10737 | 1249 | 11.63% | 475 | 4.424% | 50 | 0.4657% | 349 | 3.25% | 11136 | 3.716% | 12871 | 12298 | 10574 | -1.518% | 92.5%
5 | Central Let | 70150955 | 69161955 | 74694715 | 74600747 | 0 | 74494408 | 7.71% | 72.22% | 4982653 | 7.204% | 4543761 | 6.477% | 4530 | 524 | 11.57% | 272 | 6.004% | 0 | 0% | 711 | 15.7% | 5241 | 15.7% | 6038 | 6249 | 5453 | 20.38% | 77.78%
| District Let | 19198464 | 18713027 | 19187126 | 18873525 | 0 | 18771696 | 0.3135% | 92.86% | 33253 | 0.1777% | -11338 | -0.05906% | 1806 | 215 | 11.9% | 96 | 5.316% | 73 | 4.042% | 41 | 2.27% | 1920 | 6.312% | 2231 | 2173 | 1862 | 3.101% | 85.71%
| All Contracts | 89349419 | 87874982 | 93881841 | 93474272 | 0 | 93266104 | 6.135% | 81.25% | 5015906 | 5.708% | 4532423 | 5.073% | 6336 | 739 | 11.66% | 368 | 5.808% | 73 | 1.152% | 752 | 11.87% | 7161 | 13.02% | 8269 | 8422 | 7315 | 15.45% | 81.25%
6 | Central Let | 64959224 | 63798164 | 66085909 | 63845173 | 0 | 63718975 | -0.1241% | 90.91% | 1717924 | 2.693% | 1126685 | 1.734% | 4995 | 1429 | 28.61% | 347 | 6.947% | 212 | 4.244% | 321 | 6.426% | 5528 | 10.67% | 7305 | 7288 | 5512 | 10.35% | 86.36%
| District Let | 15123713 | 14718231 | 15524696 | 14498264 | 100000 | 14513864 | -1.389% | 100% | 505951 | 3.438% | 400983 | 2.651% | 1990 | 306 | 15.38% | 84 | 4.221% | 45 | 2.261% | 12 | 0.603% | 2047 | 2.864% | 2437 | 2274 | 1884 | -5.327% | 91.67%
| All Contracts | 80082937 | 78516395 | 81610605 | 78343437 | 100000 | 78232839 | -0.3611% | 94.12% | 2223875 | 2.832% | 1527668 | 1.908% | 6985 | 1735 | 24.84% | 431 | 6.17% | 257 | 3.679% | 333 | 4.767% | 7575 | 8.447% | 9742 | 9562 | 7396 | 5.884% | 88.24%
7 | Central Let | 72777242 | 71822942 | 73579549 | 72484972 | 0 | 72374516 | 0.768% | 100% | 1151415 | 1.603% | 802306 | 1.102% | 4929 | 683 | 13.86% | 331 | 6.715% | 0 | 0% | 163 | 3.307% | 5092 | 3.307% | 6106 | 5981 | 4967 | 0.7709% | 88.89%
| District Let | 14609759 | 14218659 | 14684602 | 14061131 | 0 | 14063129 | -1.094% | 100% | 115282 | 0.8108% | 74843 | 0.5123% | 2370 | 296 | 12.49% | 149 | 6.287% | 21 | 0.8861% | 18 | 0.7595% | 2409 | 1.646% | 2854 | 2732 | 2287 | -3.502% | 100%
| All Contracts | 87387001 | 86041601 | 88264151 | 86546103 | 0 | 86437645 | 0.4603% | 100% | 1266697 | 1.472% | 877149 | 1.004% | 7299 | 979 | 13.41% | 480 | 6.576% | 21 | 0.2877% | 181 | 2.48% | 7501 | 2.768% | 8960 | 8713 | 7254 | -0.6165% | 93.55%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 35450792 | 34975528 | 34915407 | 34363959 | 0 | 34355635 | -1.772% | 77.78% | -313802 | -0.8972% | -535384 | -1.51% | 2210 | 250 | 11.31% | 149 | 6.742% | 23 | 1.041% | 119 | 5.385% | 2352 | 6.425% | 2751 | 2654 | 2255 | 2.036% | 0.002365%
| All Contracts | 35450792 | 34975528 | 34915407 | 34363959 | 0 | 34355635 | -1.772% | 77.78% | -313802 | -0.8972% | -535384 | -1.51% | 2210 | 250 | 11.31% | 149 | 6.742% | 23 | 1.041% | 119 | 5.385% | 2352 | 6.425% | 2751 | 2654 | 2255 | 2.036% | 100%
Totals This Qtr | Central Let | 532792068 | 525176825 | 545053904 | 538206928 | 537500 | 540554756 | 2.928% | 89.81% | 15081905 | 2.872% | 12261837 | 2.301% | 36303 | 6106 | 16.82% | 2331 | 6.421% | 370 | 1.019% | 3121 | 8.597% | 39794 | 9.616% | 48328 | 48488 | 40051 | 10.32% | 85.99%
| District Let | 316920347 | 312804951 | 320448949 | 316421062 | 100000 | 317706890 | 1.567% | 92.24% | 4780767 | 1.528% | 3528606 | 1.113% | 21097 | 2561 | 12.14% | 1042 | 4.939% | 294 | 1.394% | 852 | 4.038% | 22243 | 5.432% | 25818 | 24789 | 21186 | 0.4219% | 93.1%
| All Contracts | 849712415 | 837981776 | 865502853 | 854627990 | 637500 | 858261646 | 2.42% | 90.84% | 19862672 | 2.37% | 15790443 | 1.858% | 57400 | 8667 | 15.1% | 3373 | 5.876% | 664 | 1.157% | 3973 | 6.922% | 62037 | 8.078% | 74146 | 73277 | 61237 | 6.685% | 89.01%
Totals Previous Quarter | Central Let | 714324826 | 704915784 | 739803035 | 736872789 | $- | 738662792 | 4.79% | 86.21% | 28465957 | 4.04% | 25479404 | 3.57% | 45283 | 6760 | 14.93% | 2500 | 5.52% | 1129 | 2.49% | 1864 | 4.12% | 48276 | 6.61% | 57604 | 57388 | 48128 | 6.28% | 90.15%
| District Let | 540522559 | 532821843 | 558558681 | 552167020 | 905160 | 551105572 | 3.43% | 92.31% | 20538700 | 3.85% | 18264346 | 3.38% | 39622 | 4420 | 11.16% | 2013 | 5.08% | 692 | 1.75% | 3075 | 7.76% | 43389 | 9.51% | 49860 | 48493 | 42060 | 6.15% | 89.56%
| All Contracts | 1254847385 | 1237737627 | 1298361716 | 1289039809 | 905160 | 1289768364 | 4.2% | 89.09% | 49004657 | 3.96% | 43743750 | 3.49% | 84905 | 11180 | 13.17% | 4513 | 5.32% | 1821 | 2.14% | 4939 | 5.82% | 91665 | 7.96% | 107464 | 105881 | 90188 | 6.22% | 89.87%
Totals Fiscal Year 2014/2015 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1329 | 19571915201 | 2009-06-17 | QTR4 | 08/09 | 2 | 9 | 900 | 1054 | 1256 | 134.6% | 0 | -202 | 202 | 0 | 45 | 109 | 29755075 | 150000 | 29605075 | 30577699 | 30629189 | -1246694 | 0 | -1246694 | 29382495 | 31496712 | 106.4% | 1 | 2114217 | 822624 | 10 | 35 | 0 | 109 | 710268 | 0 | 0 | 0 | 236516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35660 | 35660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 938512 | 35660 | Z91-0742148 | SAFECO INSURANCE COMPANY OF AMERICA | N/A | N/A | N/A | N/A | 2015-01-06 | QTR3 | 14/15 |  | 2013-01-31 | QTR3 | 12/13 | 113 | 42389866.96 | ARRA | AMERICAN RECOVERY AND REINVEST
| 01 | T1389 | 41549015201 | 2010-07-28 | QTR1 | 10/11 | 2 | 8 | 650 | 950 | 1010 | 140.3% | 0 | -60 | 60 | 0 | 98 | 202 | 13850596 | 150000 | 13700596 | 14203576 | 13918706 | -198000 | 0 | -198000 | 13720706 | 14530532 | 106.1% | 1 | 809826 | 352980 | 73 | 25 | 0 | 0 | 230740 | 0 | 0 | 25 | 147113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 23 | 39208 | 39208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 418132 | 39208 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2014-12-05 | QTR2 | 14/15 |  | 2013-09-03 | QTR1 | 13/14 | 115 | 20340423.55
| 01 | T1403 | 19448515201 | 2011-05-25 | QTR4 | 10/11 | 2 | 2 | 450 | 667 | 666 | 105.3% | 1 | 1 | 0 | 0 | 215 | 2 | 10008331 | 100173 | 9908158 | 10076101 | 9902773 | 0 | 0 | 0 | 9902773 | 9879607 | 99.71% | 1 | -23166 | 67770 | 158 | 34 | 23 | 2 | 61478 | 0 | 0 | 0 | 44733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 2 | 106211 | 0 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2015-01-08 | QTR3 | 14/15 |  | 2013-12-30 | QTR2 | 13/14 | 118 | 9984033.56
| 01 | T1407 | 19576515201 | 2010-09-29 | QTR1 | 10/11 | 1 | 13 | 800 | 1084 | 1084 | 115.9% | 1 | 0 | 0 | 0 | 158 | 126 | 14220849 | 129405 | 14091444 | 15022102 | 14932461 | 0 | 0 | 0 | 14932461 | 15371000 | 109.1% | 1 | 438539 | 801253 | 129 | 28 | 0 | 0 | 98665 | 0 | 0 | 52 | 254259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 433920 | 1687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 786844 | 1687 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2014-10-13 | QTR2 | 14/15 |  | 2014-01-18 | QTR3 | 13/14 | 113 | 11264597.26
| 01 | T1463 | 41736515201 | 2011-06-22 | QTR4 | 10/11 | 1 | 7 | 600 | 759 | 759 | 103.3% | 1 | 0 | 0 | 0 | 144 | 15 | 9540474 | 111429 | 9429045 | 9918837 | 9702547 | 0 | 0 | 0 | 9702547 | 9701892 | 102.9% | 1 | -656 | 378364 | 106 | 33 | 0 | 0 | 247694 | 0 | 5 | 15 | 107813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68913 | 0 | 0 | 0 | 46774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 471194 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-09-19 | QTR1 | 14/15 |  | 2013-11-11 | QTR2 | 13/14 | 108 | 8323801.45
| 01 | T1477 | 19541645201 | 2012-04-25 | QTR4 | 11/12 | 1 | 3 | 450 | 641 | 641 | 115.1% | 1 | 0 | 0 | 0 | 191 | 0 | 10956198 | 94197 | 10862001 | 10957630 | 11051551 | 0 | 0 | 0 | 11051551 | 10999776 | 101.3% | 1 | -51776 | 1432 | 93 | 30 | 28 | 0 | 59789 | 0 | 10 | 0 | 4995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 23816 | 0 | F650507332 | GUYMANN CONSTRUCTION OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2014-07-31 | QTR1 | 14/15 |  | 2014-05-04 | QTR4 | 13/14 | 113 | 10699278.86
| 01 | T1506 | 40828625201 | 2012-06-06 | QTR4 | 11/12 | 1 | 2 | 450 | 536 | 534 | 101.8% | 1 | 2 | 0 | 0 | 86 | 0 | 9404527 | 107089 | 9297438 | 7654956 | 7289541 | 0 | 0 | 0 | 7289541 | 7297926 | 78.49% | 1 | 8385 | -1749571 | 44 | 32 | 0 | 0 | 0 | 0 | 10 | 0 | -1783315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67701 | 33744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | -1715614 | 33744 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-10-01 | QTR2 | 14/15 |  | 2014-02-07 | QTR3 | 13/14 | 113 | 9118320.26
| 01 | T1531 | 42952615201 | 2013-03-06 | QTR3 | 12/13 | 1 | 5 | 135 | 228 | 299 | 195.6% | 0 | -71 | 71 | 0 | 52 | 41 | 2149000 | 50000 | 2099000 | 2142630 | 2134577 | -108772 | 0 | -108772 | 2025805 | 2025601 | 96.5% | 1 | -204 | -6370 | 19 | 16 | 0 | 6 | 58402 | 0 | 17 | 34 | -31523 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 41 | 34709 | 355 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-12-03 | QTR2 | 14/15 |  | 2014-06-30 | QTR4 | 13/14 | 115 | 1997239.71 | B0 | ACC - LUMP SUM
| 01 | T1536 | 41369515201 | 2013-04-24 | QTR4 | 12/13 | 3 | 4 | 350 | 469 | 469 | 108.6% | 1 | 0 | 0 | 0 | 89 | 30 | 8076913 | 81786 | 7995127 | 8251439 | 8211651 | 0 | 0 | 0 | 8211651 | 8208595 | 102.7% | 1 | -3056 | 174527 | 57 | 32 | 0 | 3 | 26637 | 0 | 0 | 27 | 78024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 194476 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-01-29 | QTR3 | 14/15 |  | 2014-10-17 | QTR2 | 14/15 | 113 | 8781655.23
| 01 | T1537 | 42731015201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 171 | 157 | 91.33% | 1 | 14 | 0 | 0 | 20 | 1 | 934511 | 36636 | 897875 | 934511 | 907315 | 0 | 0 | 0 | 907315 | 907315 | 101.1% | 1 | 0 | 0 | 18 | 2 | 0 | 0 | 4551 | 0 | 0 | 1 | 4888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9439 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-07-30 | QTR1 | 14/15 |  | 2014-06-19 | QTR4 | 13/14 | 108 | 797883.09 | B0 | ACC - LUMP SUM
| 01 | T1542 | 42997715201 | 2013-06-19 | QTR4 | 12/13 | 1 | 2 | 120 | 137 | 137 | 113.3% | 1 | 0 | 0 | 0 | 1 | 16 | 1021641 | 50000 | 971641 | 957447 | 916780 | 0 | 0 | 0 | 916780 | 916780 | 94.35% | 1 | 0 | -64194 | 0 | 1 | 0 | 0 | -64194 | 0 | 0 | 0 | 9334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | -54861 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-03-12 | QTR3 | 14/15 |  | 2014-06-21 | QTR4 | 13/14 | 115 | 1259552.62 | B0 | ACC - LUMP SUM
| 01 | T1547 | 42981815201 | 2013-09-25 | QTR1 | 13/14 | 2 | 2 | 100 | 104 | 78 | 74% | 1 | 26 | 0 | 0 | 4 | 0 | 171010 | 0 | 171010 | 193060 | 193060 | 0 | 0 | 0 | 193060 | 193060 | 112.9% | 0 | 0 | 22050 | 3 | 1 | 0 | 0 | 22050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22050 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2014-07-01 | QTR1 | 14/15 |  | 2014-05-28 | QTR4 | 13/14 | 118 | 221957.39 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1549 | 43085615201 | 2013-08-28 | QTR1 | 13/14 | 1 | 1 | 80 | 82 | 78 | 95% | 1 | 4 | 0 | 0 | 2 | 0 | 313880 | 11980 | 301900 | 322391 | 310411 | 0 | 0 | 0 | 310411 | 310411 | 102.8% | 1 | 0 | 8511 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8511 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2014-07-24 | QTR1 | 14/15 |  | 2014-05-15 | QTR4 | 13/14 | 113 | 217061.41 | B0 | ACC - LUMP SUM
| 01 | T1555 | 42910015201 | 2013-07-31 | QTR1 | 13/14 | 1 | 0 | 275 | 300 | 261 | 85.82% | 1 | 39 | 0 | 0 | 25 | 0 | 6125184 | 59970 | 6065214 | 6125184 | 6180641 | 0 | 0 | 0 | 6180641 | 6186013 | 102% | 1 | 5372 | 0 | 11 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2014-09-25 | QTR1 | 14/15 |  | 2014-08-19 | QTR1 | 14/15 | 118 | 5960563.21 | B0 | ACC - LUMP SUM
| 01 | T1556 | 42911915201 | 2013-08-28 | QTR1 | 13/14 | 1 | 0 | 120 | 142 | 142 | 104.2% | 1 | 0 | 0 | 0 | 17 | 5 | 984307 | 50000 | 934307 | 984307 | 950925 | 0 | 0 | 0 | 950925 | 950925 | 101.8% | 1 | 0 | 0 | 17 | 0 | 0 | 3 | 9227 | 0 | 0 | 2 | 13279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 22506 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 |  | 2014-05-29 | QTR4 | 13/14 | 115 | 1028678.93 | B0 | ACC - LUMP SUM
| 01 | T1558 | 42949015201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 200 | 221 | 216 | 97.5% | 1 | 5 | 0 | 0 | 21 | 0 | 2007732 | 50000 | 1957732 | 2007732 | 1957732 | 0 | 0 | 0 | 1957732 | 1957732 | 100% | 1 | 0 | 0 | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2014-10-31 | QTR2 | 14/15 |  | 2014-09-26 | QTR1 | 14/15 | 108 | 3091367.37 | B0 | ACC - LUMP SUM
| 01 | T1563 | 42984215201 | 2013-05-22 | QTR4 | 12/13 | 1 | 2 | 80 | 87 | 87 | 103.8% | 1 | 0 | 0 | 0 | 4 | 3 | 276962 | 0 | 276962 | 290055 | 290055 | 0 | 0 | 0 | 290055 | 290055 | 104.7% | 1 | 0 | 13093 | 4 | 0 | 0 | 3 | 13093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 13093 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2014-07-23 | QTR1 | 14/15 |  | 2014-04-23 | QTR4 | 13/14 | 113 | 311947.51 | B0 | ACC - LUMP SUM
| 01 | T1564 | 43336015201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 80 | 91 | 79 | 85% | 1 | 12 | 0 | 0 | 11 | 0 | 249571 | 11091 | 238480 | 249571 | 238480 | 0 | 0 | 0 | 238480 | 238480 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593315987 | TUCKER PAVING INC. | N/A | N/A | N/A | N/A | 2015-02-05 | QTR3 | 14/15 |  | 2015-01-05 | QTR3 | 14/15 | 108 | 170337.73 | B0 | ACC - LUMP SUM
| 01 | T1568 | 42910215201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 145 | 169 | 168 | 99.31% | 1 | 1 | 0 | 0 | 24 | 0 | 2155214 | 50000 | 2105214 | 2155214 | 2109493 | 0 | 0 | 0 | 2109493 | 2109463 | 100.2% | 1 | -30 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2014-09-23 | QTR1 | 14/15 |  | 2014-05-22 | QTR4 | 13/14 | 118 | 2139342.73 | B0 | ACC - LUMP SUM
| 01 | T1571 | 43085815201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 80 | 114 | 112 | 100% | 1 | 2 | 0 | 0 | 32 | 2 | 434987 | 16298 | 418689 | 434987 | 424777 | 0 | 0 | 0 | 424777 | 424777 | 101.5% | 1 | 0 | 0 | 30 | 2 | 0 | 2 | 6088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6088 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-19 | QTR1 | 14/15 |  | 2014-07-15 | QTR1 | 14/15 | 113 | 326383.49 | B0 | ACC - LUMP SUM
| 01 | T1572 | 42954715201 | 2013-10-30 | QTR2 | 13/14 | 3 | 1 | 225 | 290 | 290 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 7786232 | 78221 | 7708011 | 7442764 | 7487178 | 0 | 0 | 0 | 7487178 | 7454628 | 96.71% | 1 | -32550 | -343467 | 46 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | -294593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30561 | 0 | 0 | 0 | -325154 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-03-26 | QTR3 | 14/15 |  | 2015-02-08 | QTR3 | 14/15 | 113 | 7638958.09 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1573 | 42542615201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 90 | 94 | 82 | 86.67% | 1 | 12 | 0 | 0 | 4 | 0 | 235732 | 22238 | 213494 | 235732 | 223084 | 0 | 0 | 0 | 223084 | 223084 | 104.5% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 9590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9590 | 0 | F650167126 | J. MORI PAINTING INC. | N/A | N/A | N/A | N/A | 2014-08-28 | QTR1 | 14/15 |  | 2014-08-08 | QTR1 | 14/15 | 113 | 507871.4 | B0 | ACC - LUMP SUM
| 01 | T1574 | 43092915201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 80 | 90 | 89 | 98.75% | 1 | 1 | 0 | 0 | 10 | 0 | 246539 | 11813 | 234726 | 246539 | 234726 | 0 | 0 | 0 | 234726 | 234726 | 100% | 1 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593315987 | TUCKER PAVING INC. | N/A | N/A | N/A | N/A | 2014-07-01 | QTR1 | 14/15 |  | 2014-05-16 | QTR4 | 13/14 | 108 | 243727.87 | B0 | ACC - LUMP SUM
| 01 | T1575 | 43112215201 | 2013-10-30 | QTR2 | 13/14 | 1 | 1 | 100 | 112 | 111 | 100% | 1 | 1 | 0 | 0 | 11 | 1 | 962381 | 44381 | 918000 | 965823 | 931845 | 0 | 0 | 0 | 931845 | 931845 | 101.5% | 1 | 0 | 3442 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3442 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-09-11 | QTR1 | 14/15 |  | 2014-06-14 | QTR4 | 13/14 | 108 | 912555.77 | B0 | ACC - LUMP SUM
| 01 | T1579 | 43086415201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 80 | 84 | 84 | 100% | 1 | 0 | 0 | 0 | 4 | 0 | 688541 | 19823 | 668718 | 688541 | 661017 | 0 | 0 | 0 | 661017 | 661017 | 98.85% | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-08-06 | QTR1 | 14/15 |  | 2014-06-29 | QTR4 | 13/14 | 113 | 402513.43 | B0 | ACC - LUMP SUM
| 01 | T1580 | 43093015201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 95 | 104 | 102 | 97.89% | 1 | 2 | 0 | 0 | 9 | 0 | 669283 | 26104 | 643179 | 669283 | 643179 | 0 | 0 | 0 | 643179 | 643179 | 100% | 1 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-10-07 | QTR2 | 14/15 |  | 2014-07-10 | QTR1 | 14/15 | 115 | 598937.28 | B0 | ACC - LUMP SUM
| 01 | T1581 | 43086315201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 100 | 118 | 118 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 796613 | 29314 | 767299 | 796613 | 781655 | 0 | 0 | 0 | 781655 | 781655 | 101.9% | 1 | 0 | 0 | 15 | 3 | 0 | 0 | 14356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14356 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-10-23 | QTR2 | 14/15 |  | 2014-09-15 | QTR1 | 14/15 | 115 | 729581.8 | B0 | ACC - LUMP SUM
| 01 | T1582 | 42814415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 165 | 187 | 142 | 72.73% | 1 | 45 | 0 | 0 | 22 | 0 | 783214 | 0 | 783214 | 763901 | 763901 | 0 | 0 | 0 | 763901 | 763901 | 97.53% | 1 | 0 | -19312 | 12 | 10 | 0 | 0 | -19312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19312 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-02-10 | QTR3 | 14/15 |  | 2015-01-13 | QTR3 | 14/15 | 118 | 863964.82 | B0 | ACC - LUMP SUM
| 01 | T1584 | 42911515201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 125 | 158 | 158 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 2020000 | 50000 | 1970000 | 2020000 | 1989315 | -8000 | 0 | -8000 | 1981315 | 1988085 | 100.9% | 1 | 6770 | 0 | 31 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-01-30 | QTR3 | 14/15 |  | 2014-11-12 | QTR2 | 14/15 | 108 | 2239271.25 | B0 | ACC - LUMP SUM
| 01 | T1586 | 43085915201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 100 | 110 | 89 | 79% | 1 | 21 | 0 | 0 | 10 | 0 | 515545 | 21126 | 494419 | 515545 | 504315 | 0 | 0 | 0 | 504315 | 504315 | 102% | 1 | 0 | 0 | 9 | 1 | 0 | 0 | 5981 | 0 | 0 | 0 | 1829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9896 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-11-21 | QTR2 | 14/15 |  | 2014-10-10 | QTR2 | 14/15 | 108 | 471359.65 | B0 | ACC - LUMP SUM
| 01 | T1A00 | 43091715201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 60 | 68 | 44 | 60% | 1 | 24 | 0 | 0 | 8 | 0 | 52640 | 0 | 52640 | 52640 | 52640 | 0 | 0 | 0 | 52640 | 52640 | 100% | 1 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2015-03-03 | QTR3 | 14/15 |  | 2015-01-28 | QTR3 | 14/15 | 118 | 53595.74 | B0 | ACC - LUMP SUM
| 01 | T1A03 | 42989515201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 60 | 64 | 60 | 93.33% | 1 | 4 | 0 | 0 | 4 | 0 | 223166 | 11609 | 211557 | 223166 | 211557 | 0 | 0 | 0 | 211557 | 211557 | 100% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-02-12 | QTR3 | 14/15 |  | 2014-12-12 | QTR2 | 14/15 | 113 | 201007.25 | B0 | ACC - LUMP SUM
| 01 | T1A08 | 42825415201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 70 | 83 | 82 | 98.57% | 1 | 1 | 0 | 0 | 13 | 0 | 93337 | 0 | 93337 | 93337 | 93337 | 0 | 0 | 0 | 93337 | 93337 | 100% | 1 | 0 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2015-02-17 | QTR3 | 14/15 |  | 2015-01-09 | QTR3 | 14/15 | 113 | 112933.56 | B0 | ACC - LUMP SUM
| 01 | T1A10 | 42825215201 | 2014-08-27 | QTR1 | 14/15 | 2 | 0 | 100 | 106 | 53 | 47% | 1 | 53 | 0 | 0 | 6 | 0 | 167341 | 0 | 167341 | 167341 | 167341 | 0 | 0 | 0 | 167341 | 167341 | 100% | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-03-12 | QTR3 | 14/15 |  | 2015-01-22 | QTR3 | 14/15 | 108 | 207740.45 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 34 | 43 | 63 | 7665 | 9674 | 9737 | 91.18% | 31 | -63 | 333 | 0 | 1456 | 553 | 137877526 | 1624683 | 136252843 | 138340654 | 136997755 | -1561466 | 0 | -1561466 | 135436289 | 138707962 | 97.06% | 33 | 3271671 | 463132 | 949 | 383 | 51 | 128 | 1485513 | 0 | 42 | 156 | -1188547 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | -29235 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 519384 | 35431 | 0 | 0 | 138674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 35660 | 35660 | 0 | 24 | 47038 | 39208 | 0 | 0 | 0 | 0 | 0 | 0 | -30561 | 0 | 93 | 553 | 977924 | 110654
| 01 | E1J73 | 41473015201 | 2012-02-16 | QTR3 | 11/12 | 3 | 3 | 760 | 931 | 931 | 105.3% | 1 | 0 | 0 | 0 | 131 | 40 | 20657452 | 150000 | 20507452 | 20909917 | 20769992 | 0 | 0 | 0 | 20769992 | 20769992 | 101.3% | 1 | 0 | 252465 | 99 | 32 | 0 | 40 | 294765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 294765 | 0 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2015-03-12 | QTR3 | 14/15 |  | 2014-11-12 | QTR2 | 14/15 | 115 | 30061049 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 01 | E1K49 | 43013915201 | 2012-01-30 | QTR3 | 11/12 | 3 | 1 | 375 | 574 | 643 | 159.7% | 0 | -69 | 69 | 0 | 44 | 155 | 1330800 | 50000 | 1280800 | 1196714 | 1137129 | -105708 | 0 | -105708 | 1031421 | 1031421 | 80.53% | 1 | 0 | -134086 | 26 | 18 | 0 | 0 | 0 | 0 | 0 | 155 | -134086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | -134086 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-01-06 | QTR3 | 14/15 |  | 2014-01-13 | QTR3 | 13/14 | 115 | 1710449 | A3:B0:A3:B:A:B0 | ICC - DESIGN/BUILD - MINOR:ACC - LUMP SUM:ICC - DESIGN/BUILD - MINOR:ACC - LUMP SUM:ICC - DESIGN/BUILD - MINOR:ACC - LUMP SUM
| 01 | E1K74 | 42893715201 | 2012-05-31 | QTR4 | 11/12 | 1 | 0 | 590 | 682 | 680 | 102.4% | 1 | 2 | 0 | 0 | 92 | 0 | 5688000 | 50000 | 5638000 | 5688000 | 5635501 | 0 | 0 | 0 | 5635501 | 5629901 | 99.86% | 1 | -5600 | 0 | 51 | 25 | 0 | 0 | 15816 | 0 | 0 | 0 | 2436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 35777 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2014-09-15 | QTR1 | 14/15 |  | 2014-07-07 | QTR1 | 14/15 | 108 | 5906610 | A3 | ICC - DESIGN/BUILD - MINOR
| 01 | E1L10 | 43171315201 | 2013-01-17 | QTR3 | 12/13 | 1 | 0 | 300 | 350 | 349 | 99.67% | 1 | 1 | 0 | 0 | 50 | 0 | 1963030 | 50000 | 1913030 | 1963030 | 1915078 | 0 | 0 | 0 | 1915078 | 1915078 | 100.1% | 1 | 0 | 0 | 34 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593273147 | INLAND CONSTRUCTION AND EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2014-10-02 | QTR2 | 14/15 |  | 2014-05-22 | QTR4 | 13/14 | 115 | 2035342.1
| 01 | E1L18 | 42987915201 | 2012-11-15 | QTR2 | 12/13 | 1 | 0 | 100 | 121 | 124 | 108% | 1 | -3 | 3 | 0 | 21 | 0 | 96622 | 4622 | 92000 | 96622 | 82079 | -2274 | 0 | -2274 | 79805 | 79805 | 86.74% | 1 | 0 | 0 | 14 | 2 | 0 | 0 | 0 | 0 | 5 | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 840 | 0 | F760715786 | F.W.A.K. INC. | N/A | N/A | N/A | N/A | 2014-08-18 | QTR1 | 14/15 |  | 2013-08-23 | QTR1 | 13/14 | 108 | 95068.54 | B0 | ACC - LUMP SUM
| 01 | E1L70 | 43142915201 | 2013-02-15 | QTR3 | 12/13 | 2 | 1 | 430 | 445 | 424 | 95.12% | 1 | 21 | 0 | 0 | 15 | 0 | 910918 | 0 | 910918 | 1021501 | 1004565 | 0 | 0 | 0 | 1004565 | 1004530 | 110.3% | 0 | -35 | 110583 | 4 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 110583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110583 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2014-09-16 | QTR1 | 14/15 |  | 2014-06-26 | QTR4 | 13/14 | 108 | 903190 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| 01 | E1M02 | 43266015201 | 2013-06-06 | QTR4 | 12/13 | 3 | 3 | 450 | 501 | 501 | 105.3% | 1 | 0 | 0 | 0 | 51 | 0 | 1799250 | 50000 | 1749250 | 1909786 | 1863529 | 0 | 0 | 0 | 1863529 | 1864315 | 106.6% | 1 | 786 | 110536 | 15 | 12 | 0 | 0 | 111394 | 0 | 0 | 0 | 2885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114279 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-03-12 | QTR3 | 14/15 |  | 2014-11-13 | QTR2 | 14/15 | 115 | 2081874 | A3:A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| 01 | E1M14 | 43249315201 | 2013-06-20 | QTR4 | 12/13 | 2 | 2 | 325 | 354 | 354 | 100.6% | 1 | 0 | 0 | 0 | 27 | 2 | 1576687 | 50000 | 1526687 | 1621260 | 1573398 | 0 | 0 | 0 | 1573398 | 1573845 | 103.1% | 1 | 447 | 44573 | 12 | 15 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 47376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 0 | 2 | 46711 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-09-19 | QTR1 | 14/15 |  | 2014-07-31 | QTR1 | 14/15 | 108 | 1611119 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1M36 | 42913015201 | 2014-01-16 | QTR3 | 13/14 | 1 | 0 | 110 | 114 | 81 | 70% | 1 | 33 | 0 | 0 | 4 | 0 | 988135 | 50000 | 938135 | 988135 | 965889 | 0 | 0 | 0 | 965889 | 965889 | 103% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 9045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9045 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-10-13 | QTR2 | 14/15 |  | 2014-07-10 | QTR1 | 14/15 | 115 | 1182267.37 | B0 | ACC - LUMP SUM
| 01 | E1M38 | 42365015201 | 2014-02-20 | QTR3 | 13/14 | 1 | 0 | 100 | 106 | 105 | 99% | 1 | 1 | 0 | 0 | 6 | 0 | 339276 | 15218 | 324058 | 339276 | 321083 | 0 | 0 | 0 | 321083 | 321083 | 99.08% | 1 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-10-22 | QTR2 | 14/15 |  | 2014-09-13 | QTR1 | 14/15 | 115 | 256512.72
| 01 | E1M39 | 42911725201 | 2013-08-15 | QTR1 | 13/14 | 2 | 1 | 80 | 83 | 77 | 92.5% | 1 | 6 | 0 | 0 | 3 | 0 | 1060000 | 50000 | 1010000 | 1070443 | 1033120 | 0 | 0 | 0 | 1033120 | 1033120 | 102.3% | 1 | 0 | 10443 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10443 | 3579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26621 | 3579 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-08-14 | QTR1 | 14/15 |  | 2014-05-14 | QTR4 | 13/14 | 115 | 1127477.99 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | E1M52 | 42909415201 | 2013-11-21 | QTR2 | 13/14 | 1 | 1 | 80 | 92 | 92 | 100% | 1 | 0 | 0 | 0 | 12 | 0 | 597931 | 24843 | 573088 | 600134 | 594316 | 0 | 0 | 0 | 594316 | 594316 | 103.7% | 1 | 0 | 2204 | 10 | 2 | 0 | 0 | 11021 | 0 | 0 | 0 | 2204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13225 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2015-02-12 | QTR3 | 14/15 |  | 2014-07-22 | QTR1 | 14/15 | 115 | 608071.16 | B0 | ACC - LUMP SUM
| 01 | E1M72 | 43385115201 | 2013-06-20 | QTR4 | 12/13 | 1 | 2 | 80 | 120 | 145 | 157.5% | 0 | -25 | 25 | 0 | 40 | 0 | 272547 | 11893 | 260654 | 277963 | 266070 | -24150 | 0 | -24150 | 241920 | 241920 | 92.81% | 1 | 0 | 5416 | 18 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 5416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 5416 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-09-29 | QTR1 | 14/15 |  | 2014-06-10 | QTR4 | 13/14 | 108 | 279217.08 | B0 | ACC - LUMP SUM
| 01 | E1N01 | 43403615201 | 2013-12-19 | QTR2 | 13/14 | 1 | 0 | 80 | 88 | 87 | 98.75% | 1 | 1 | 0 | 0 | 8 | 0 | 555692 | 25662 | 530030 | 555692 | 531495 | 0 | 0 | 0 | 531495 | 531495 | 100.3% | 1 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-10-13 | QTR2 | 14/15 |  | 2014-07-16 | QTR1 | 14/15 | 108 | 615008.31 | B0 | ACC - LUMP SUM
| 01 | E1N06 | 43193915201 | 2014-02-20 | QTR3 | 13/14 | 3 | 1 | 170 | 237 | 235 | 107.1% | 1 | 2 | 0 | 0 | 62 | 5 | 1230923 | 49430 | 1181493 | 1239584 | 1229167 | 0 | 0 | 0 | 1229167 | 1229167 | 104% | 1 | 0 | 8661 | 33 | 20 | 0 | 5 | 16612 | 0 | 9 | 0 | 1063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 5 | 17675 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-02-27 | QTR3 | 14/15 |  | 2015-01-08 | QTR3 | 14/15 | 118 | 1068146.09
| 01 | E1N07 | 43109115201 | 2014-03-20 | QTR3 | 13/14 | 1 | 1 | 60 | 60 | 31 | 51.67% | 1 | 29 | 0 | 0 | 0 | 0 | 98451 | 5451 | 93000 | 100138 | 94687 | 0 | 0 | 0 | 94687 | 94687 | 101.8% | 1 | 0 | 1687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687 | 825 | F593674850 | LAS CONTRACTING CORP | N/A | N/A | N/A | N/A | 2015-01-30 | QTR3 | 14/15 |  | 2014-08-13 | QTR1 | 14/15 | 108 | 116821.12 | B0 | ACC - LUMP SUM
| 01 | E1N09 | 42524415201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 80 | 92 | 95 | 103.8% | 1 | -3 | 3 | 0 | 12 | 0 | 862415 | 33537 | 828878 | 862415 | 828878 | -5226 | 0 | -5226 | 823652 | 823652 | 99.37% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-03-19 | QTR3 | 14/15 |  | 2014-12-18 | QTR2 | 14/15 | 108 | 694287.64 | B0 | ACC - LUMP SUM
| 01 | E1N10 | 43445815201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 75 | 83 | 75 | 89.33% | 1 | 8 | 0 | 0 | 8 | 0 | 272420 | 13207 | 259213 | 272420 | 263758 | 0 | 0 | 0 | 263758 | 263758 | 101.8% | 1 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4545 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-03-05 | QTR3 | 14/15 |  | 2015-01-16 | QTR3 | 14/15 | 115 | 173258.53 | A4 | ICC - LUMP SUM
| 01 | E1N22 | 42914815201 | 2013-11-21 | QTR2 | 13/14 | 2 | 0 | 160 | 198 | 197 | 99.38% | 1 | 1 | 0 | 0 | 38 | 0 | 2271958 | 50000 | 2221958 | 2271958 | 2273965 | 0 | 0 | 0 | 2273965 | 2281618 | 102.7% | 1 | 7653 | 0 | 32 | 6 | 0 | 0 | 11367 | 0 | 0 | 0 | 19159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31450 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-02-17 | QTR3 | 14/15 |  | 2014-12-09 | QTR2 | 14/15 | 108 | 2565542.41 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | E1N37 | 43384815201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 60 | 74 | 74 | 100% | 1 | 0 | 0 | 0 | 14 | 0 | 308905 | 10892 | 298013 | 308905 | 296513 | 0 | 0 | 0 | 296513 | 296513 | 99.5% | 1 | 0 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593586613 | EVANS CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2015-02-19 | QTR3 | 14/15 |  | 2015-01-15 | QTR3 | 14/15 | 118 | 205804.17
| 01 | E1N38 | 43445915201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 60 | 60 | 57 | 95% | 1 | 3 | 0 | 0 | 0 | 0 | 133143 | 6955 | 126188 | 133143 | 126188 | 0 | 0 | 0 | 126188 | 126188 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2014-12-15 | QTR2 | 14/15 |  | 2014-11-10 | QTR2 | 14/15 | 108 | 124658.51
| 01 | E1N41 | 43469815201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 75 | 78 | 52 | 65.33% | 1 | 26 | 0 | 0 | 3 | 0 | 110272 | 9602 | 100670 | 110272 | 88947 | 0 | 0 | 0 | 88947 | 88947 | 88.36% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-01-30 | QTR3 | 14/15 |  | 2014-10-29 | QTR2 | 14/15 | 108 | 131177.6
| 01 | E1N68 | 19541665201 | 2014-07-17 | QTR1 | 14/15 | 1 | 0 | 50 | 50 | 9 | 18% | 1 | 41 | 0 | 0 | 0 | 0 | 50855 | 4426 | 46429 | 50855 | 46429 | 0 | 0 | 0 | 46429 | 46429 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2014-10-24 | QTR2 | 14/15 |  | 2014-10-07 | QTR2 | 14/15 | 113 | 85198.71 | B0 | ACC - LUMP SUM
| 01 | E1N69 | 41612035201 | 2014-08-29 | QTR1 | 14/15 | 1 | 0 | 50 | 54 | 40 | 72% | 1 | 14 | 0 | 0 | 4 | 0 | 121546 | 11146 | 110400 | 121546 | 110400 | 0 | 0 | 0 | 110400 | 110400 | 100% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2015-01-05 | QTR3 | 14/15 |  | 2014-12-10 | QTR2 | 14/15 | 115 | 183400.33 | B0 | ACC - LUMP SUM
| 01 | E1N97 | 43193815202 | 2014-08-06 | QTR1 | 14/15 | 1 | 0 | 90 | 92 | 89 | 96.67% | 1 | 3 | 0 | 0 | 2 | 0 | 1590000 | 0 | 1590000 | 1590000 | 1590000 | 0 | 0 | 0 | 1590000 | 1590000 | 100% | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-02-12 | QTR3 | 14/15 |  | 2014-11-14 | QTR2 | 14/15 | 118 | 1300000 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 25 | 37 | 16 | 4790 | 5639 | 5547 | 92% | 23 | 92 | 100 | 0 | 647 | 202 | 44887228 | 776884 | 44110344 | 45299709 | 44642176 | -137358 | 0 | -137358 | 44504818 | 44508069 | 96% | 24 | 3251 | 412482 | 379 | 193 | 0 | 45 | 470500 | 0 | 35 | 155 | 34375 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 65825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 10443 | 3579 | 0 | 0 | 0 | 0 | 0 | 0 | -1146 | 0 | 72 | 202 | 579998 | 4404
| District 01 Totals |  |  |  |  | 59 | 80 | 79 | 12455 | 15313 | 15284 | 91.53% | 54 | 29 | 433 | 0 | 2103 | 755 | 182764754 | 2401567 | 180363187 | 183640363 | 181639931 | -1698824 | 0 | -1698824 | 179941107 | 183216031 | 96.61% | 57 | 3274922 | 875614 | 1328 | 576 | 51 | 173 | 1956013 | 0 | 77 | 311 | -1154172 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | -29235 | 0 | 0 | 0 | 0 | 0 | 16 | 93 | 585209 | 35431 | 0 | 0 | 138674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 35660 | 35660 | 21 | 24 | 57481 | 42787 | 0 | 0 | 0 | 0 | 0 | 0 | -31707 | 0 | 165 | 755 | 1557922 | 115058
| 02 | T2359 | 21321725201 | 2010-12-01 | QTR2 | 10/11 | 1 | 5 | 720 | 957 | 1332 | 152.2% | 0 | -375 | 375 | 0 | 236 | 1 | 12480050 | 150000 | 12330050 | 12930758 | 12778436 | 0 | 0 | 0 | 12778436 | 12779717 | 103.6% | 1 | 1281 | 450708 | 149 | 87 | 0 | 1 | 37427 | 0 | 0 | 0 | 8948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 510649 | 0 | F060613324 | COSTELLO INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-12-23 | QTR2 | 14/15 |  | 2014-10-21 | QTR2 | 14/15 | 208 | 18609389.29
| 02 | T2398 | 21087325201 | 2011-06-22 | QTR4 | 10/11 | 1 | 11 | 650 | 924 | 924 | 127.8% | 0 | 0 | 0 | 0 | 110 | 164 | 10935162 | 150000 | 10785162 | 12563524 | 12687376 | 0 | 0 | 0 | 12687376 | 12686893 | 117.6% | 0 | -483 | 1628362 | 51 | 42 | 0 | 0 | 0 | 0 | 0 | 45 | 289688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34133 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1429570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 1693125 | 0 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2014-08-18 | QTR1 | 14/15 |  | 2014-04-09 | QTR4 | 13/14 | 209 | 15856090.23
| 02 | T2413 | 42930415201 | 2012-06-20 | QTR4 | 11/12 | 2 | 0 | 365 | 573 | 581 | 133.7% | 0 | -8 | 8 | 0 | 119 | 89 | 13231111 | 150000 | 13081111 | 13231111 | 13309354 | -36992 | 0 | -36992 | 13272362 | 13309528 | 101.7% | 1 | 37166 | 0 | 62 | 31 | 0 | 63 | 79373 | 0 | 0 | 5 | 45477 | 0 | 0 | 0 | 568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 125418 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-07-30 | QTR1 | 14/15 |  | 2014-04-11 | QTR4 | 13/14 | 208 | 15830196.01
| 02 | T2446 | 21324345201 | 2012-10-31 | QTR2 | 12/13 | 1 | 0 | 300 | 424 | 422 | 124.3% | 0 | 2 | 0 | 0 | 49 | 75 | 745411 | 42811 | 702600 | 745411 | 704271 | 0 | 0 | 0 | 704271 | 704271 | 100.2% | 1 | 0 | 0 | 21 | 28 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2014-07-22 | QTR1 | 14/15 |  | 2014-06-06 | QTR4 | 13/14 | 208 | 770857.52
| 02 | T2452 | 42880915201 | 2013-02-27 | QTR3 | 12/13 | 1 | 1 | 260 | 435 | 434 | 105.8% | 1 | 1 | 0 | 0 | 159 | 16 | 11661112 | 127086 | 11534026 | 11812236 | 12453297 | 0 | 0 | 0 | 12453297 | 12453297 | 108% | 1 | 0 | 151124 | 122 | 37 | 0 | 16 | 193999 | 0 | 0 | 0 | 40959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 234958 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2014-10-14 | QTR2 | 14/15 |  | 2014-07-25 | QTR1 | 14/15 | 208 | 12368561.22
| 02 | T2453 | 42448515201 | 2013-02-06 | QTR3 | 12/13 | 1 | 1 | 245 | 368 | 346 | 101.6% | 1 | 22 | 0 | 0 | 97 | 26 | 2940728 | 50000 | 2890728 | 2984001 | 3277616 | 0 | 0 | 0 | 3277616 | 3276755 | 113.4% | 0 | -860 | 43273 | 78 | 19 | 0 | 6 | 21899 | 0 | 0 | 20 | 67770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 89670 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-07-02 | QTR1 | 14/15 |  | 2014-03-19 | QTR3 | 13/14 | 208 | 2955857.29
| 02 | T2457 | 42430815201 | 2013-03-27 | QTR3 | 12/13 | 1 | 5 | 200 | 439 | 471 | 196% | 0 | -32 | 32 | 0 | 89 | 150 | 1161902 | 50000 | 1111902 | 1273448 | 1280373 | -49024 | 0 | -49024 | 1231349 | 1231349 | 110.7% | 0 | 0 | 111546 | 58 | 21 | 0 | 121 | 73433 | 3077 | 0 | 29 | 31686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150 | 105118 | 3077 | F592655272 | WESTWIND CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-02-04 | QTR3 | 14/15 |  | 2014-10-02 | QTR2 | 14/15 | 216 | 1200430.58
| 02 | T2464 | 21053845201 | 2013-03-27 | QTR3 | 12/13 | 1 | 0 | 140 | 185 | 182 | 111.4% | 1 | 3 | 0 | 0 | 42 | 3 | 1105370 | 47755 | 1057614 | 1105370 | 1123305 | 0 | 0 | 0 | 1123305 | 1123304 | 106.2% | 1 | -1 | 0 | 12 | 14 | 5 | 0 | 0 | 0 | 0 | 3 | 29704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 3 | 29704 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-09-05 | QTR1 | 14/15 |  | 2014-03-03 | QTR3 | 13/14 | 209 | 966212.57
| 02 | T2472 | 42880615201 | 2013-07-31 | QTR1 | 13/14 | 1 | 0 | 200 | 364 | 362 | 99% | 1 | 2 | 0 | 0 | 164 | 0 | 7300000 | 82223 | 7217777 | 7300000 | 6704150 | 0 | 0 | 0 | 6704150 | 6712214 | 93% | 1 | 8064 | 0 | 99 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-01-28 | QTR3 | 14/15 |  | 2014-10-03 | QTR2 | 14/15 | 208 | 7992248.09
| 02 | T2480 | 42604715201 | 2013-06-19 | QTR4 | 12/13 | 2 | 0 | 190 | 282 | 282 | 101.6% | 1 | 0 | 0 | 0 | 89 | 3 | 2486826 | 50000 | 2436826 | 2486826 | 2347817 | 0 | 0 | 0 | 2347817 | 2349225 | 96.41% | 1 | 1409 | 0 | 77 | 12 | 0 | 0 | 0 | 0 | 0 | 3 | 16080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16080 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-23 | QTR2 | 14/15 |  | 2014-06-12 | QTR4 | 13/14 | 209 | 2545335.83
| 02 | T2481 | 43007015201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 180 | 186 | 179 | 96.11% | 1 | 7 | 0 | 0 | 6 | 0 | 369584 | 18149 | 351435 | 369584 | 361862 | 0 | 0 | 0 | 361862 | 361862 | 103% | 1 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11961 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-10-20 | QTR2 | 14/15 |  | 2014-08-21 | QTR1 | 14/15 | 214 | 377574.28
| 02 | T2483 | 42969415201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 185 | 185 | 109.3% | 1 | 0 | 0 | 0 | 21 | 14 | 2122783 | 50000 | 2072783 | 2122783 | 2066520 | 0 | 0 | 0 | 2066520 | 2066520 | 99.7% | 1 | 0 | 0 | 20 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 13183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 13183 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-11-14 | QTR2 | 14/15 |  | 2014-07-27 | QTR1 | 14/15 | 209 | 2033285.21
| 02 | T2486 | 42969615201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 166 | 137 | 80.67% | 1 | 29 | 0 | 0 | 16 | 0 | 213201 | 10807 | 202394 | 213201 | 201739 | 0 | 0 | 0 | 201739 | 201739 | 99.68% | 1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2014-07-17 | QTR1 | 14/15 |  | 2014-07-03 | QTR1 | 14/15 | 216 | 235866.69
| 02 | T2487 | 42975115201 | 2013-08-28 | QTR1 | 13/14 | 1 | 1 | 145 | 210 | 210 | 106.2% | 1 | 0 | 0 | 0 | 56 | 9 | 1948203 | 50000 | 1898203 | 1958517 | 1898534 | 0 | 0 | 0 | 1898534 | 1898509 | 100% | 1 | -25 | 10314 | 42 | 14 | 0 | 0 | 10608 | 0 | 0 | 9 | 13496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 24104 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-10-13 | QTR2 | 14/15 |  | 2014-06-20 | QTR4 | 13/14 | 208 | 1983074.42
| 02 | T2490 | 42975235201 | 2013-09-25 | QTR1 | 13/14 | 1 | 4 | 150 | 264 | 207 | 111.3% | 1 | 57 | 0 | 0 | 40 | 74 | 1344082 | 50000 | 1294082 | 1461903 | 1449421 | 0 | 0 | 0 | 1449421 | 1449421 | 112% | 0 | 0 | 117821 | 38 | 2 | 0 | 29 | 62601 | 44478 | 0 | 44 | 82151 | 34634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 147948 | 79112 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-01-21 | QTR3 | 14/15 |  | 2014-07-31 | QTR1 | 14/15 | 208 | 1036541.75 | B0 | ACC - LUMP SUM
| 02 | T2494 | 42720415201 | 2013-07-31 | QTR1 | 13/14 | 1 | 1 | 100 | 160 | 160 | 130% | 0 | 0 | 0 | 0 | 30 | 30 | 939461 | 40520 | 898941 | 967572 | 911204 | 0 | 0 | 0 | 911204 | 911204 | 101.4% | 1 | 0 | 28111 | 26 | 4 | 0 | 2 | 5691 | 0 | 0 | 28 | 52760 | 17879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 58452 | 17879 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2014-08-22 | QTR1 | 14/15 |  | 2014-07-08 | QTR1 | 14/15 | 208 | 854057.95
| 02 | T2495 | 42870815201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 180 | 266 | 263 | 117.2% | 1 | 3 | 0 | 0 | 62 | 24 | 4543998 | 52329 | 4491668 | 4593998 | 4820212 | 0 | 0 | 0 | 4820212 | 4818947 | 107.3% | 1 | -1265 | 50000 | 46 | 6 | 0 | 21 | 62696 | 1837 | 10 | 3 | 10417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 24 | 73113 | 1837 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-02-24 | QTR3 | 14/15 |  | 2014-09-25 | QTR1 | 14/15 | 208 | 5010885.74
| 02 | T2497 | 43091915201 | 2013-10-30 | QTR2 | 13/14 | 1 | 2 | 100 | 316 | 318 | 288% | 0 | -2 | 2 | 0 | 45 | 171 | 337196 | 17800 | 319396 | 426661 | 390457 | -1932 | 0 | -1932 | 388525 | 388525 | 121.6% | 0 | 0 | 89465 | 19 | 11 | 0 | 5 | 9235 | 0 | 15 | 39 | 36522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 58755 | 58755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 171 | 104513 | 58755 | F161659018 | CORE CONSTRUCTION COMPANY OF JACKSONVILL | N/A | N/A | N/A | N/A | 2015-03-02 | QTR3 | 14/15 |  | 2014-12-12 | QTR2 | 14/15 | 208 | 355118.9
| 02 | T2501 | 42445115201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 210 | 233 | 232 | 103.8% | 1 | 1 | 0 | 0 | 23 | 0 | 2399105 | 50000 | 2349105 | 2399105 | 2283379 | 0 | 0 | 0 | 2283379 | 2283645 | 97.21% | 1 | 265 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-01-20 | QTR3 | 14/15 |  | 2014-09-13 | QTR1 | 14/15 | 216 | 2180139.51
| 02 | T2502 | 42889715201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 100 | 122 | 121 | 99% | 1 | 1 | 0 | 0 | 22 | 0 | 343355 | 18399 | 324956 | 343355 | 318751 | 0 | 0 | 0 | 318751 | 318751 | 98.09% | 1 | 0 | 0 | 21 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 |  | 2014-05-30 | QTR4 | 13/14 | 209 | 405708.15
| 02 | T2504 | 42869115201 | 2013-10-30 | QTR2 | 13/14 | 1 | 1 | 95 | 116 | 115 | 103.2% | 1 | 1 | 0 | 0 | 17 | 4 | 619867 | 28993 | 590874 | 697349 | 706524 | 0 | 0 | 0 | 706524 | 706524 | 119.6% | 0 | 0 | 77482 | 10 | 7 | 0 | 4 | 104847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 104847 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-08-18 | QTR1 | 14/15 |  | 2014-06-02 | QTR4 | 13/14 | 214 | 669835.42
| 02 | T2507 | 43225415201 | 2013-12-04 | QTR2 | 13/14 | 1 | 1 | 90 | 106 | 106 | 105.6% | 1 | 0 | 0 | 0 | 13 | 3 | 248683 | 0 | 248683 | 249718 | 249718 | 0 | 0 | 0 | 249718 | 249718 | 100.4% | 1 | 0 | 1035 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1035 | 0 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 |  | 2014-06-11 | QTR4 | 13/14 | 209 | 274893.73 | B0 | ACC - LUMP SUM
| 02 | T2509 | 43051515201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 75 | 96 | 93 | 96% | 1 | 3 | 0 | 0 | 21 | 0 | 138499 | 0 | 138499 | 138499 | 138499 | 0 | 0 | 0 | 138499 | 138499 | 100% | 1 | 0 | 0 | 19 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452181662 | ADVANTA ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-08-26 | QTR1 | 14/15 |  | 2014-06-06 | QTR4 | 13/14 | 209 | 180396.28 | B0 | ACC - LUMP SUM
| 02 | T2511 | 43224815201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 30 | 33 | 33 | 100% | 1 | 0 | 0 | 0 | 3 | 0 | 59893 | 3494 | 56399 | 59893 | 56399 | 0 | 0 | 0 | 56399 | 56399 | 100% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452181662 | ADVANTA ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-08-14 | QTR1 | 14/15 |  | 2014-07-06 | QTR1 | 14/15 | 209 | 76062.84 | B0 | ACC - LUMP SUM
| 02 | T2518 | 43477515201 | 2014-02-05 | QTR3 | 13/14 | 1 | 0 | 72 | 72 | 70 | 97.22% | 1 | 2 | 0 | 0 | 0 | 0 | 84224 | 0 | 84224 | 84224 | 84224 | 0 | 0 | 0 | 84224 | 84224 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593564392 | RICHARDSON SITE PREP INC. | N/A | N/A | N/A | N/A | 2014-08-22 | QTR1 | 14/15 |  | 2014-07-10 | QTR1 | 14/15 | 209 | 176769.75 | B0 | ACC - LUMP SUM
| 02 | T2519 | 43335815201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 75 | 79 | 79 | 104% | 1 | 0 | 0 | 0 | 1 | 3 | 402306 | 15539 | 386767 | 402306 | 387767 | 0 | 0 | 0 | 387767 | 387767 | 100.3% | 1 | 0 | 0 | 0 | 1 | 0 | 3 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1000 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-11-25 | QTR2 | 14/15 |  | 2014-11-12 | QTR2 | 14/15 | 209 | 335957.94 | B0 | ACC - LUMP SUM
| 02 | T2521 | 43224415201 | 2014-02-26 | QTR3 | 13/14 | 1 | 0 | 35 | 42 | 42 | 108.6% | 1 | 0 | 0 | 0 | 5 | 2 | 109680 | 6758 | 102922 | 109680 | 104316 | 0 | 0 | 0 | 104316 | 104316 | 101.4% | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 1394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1394 | 0 | F593564392 | RICHARDSON SITE PREP INC. | N/A | N/A | N/A | N/A | 2014-09-11 | QTR1 | 14/15 |  | 2014-07-31 | QTR1 | 14/15 | 214 | 114968.28 | B0 | ACC - LUMP SUM
| 02 | T2525 | 42476715201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 40 | 65 | 65 | 105% | 1 | 0 | 0 | 0 | 25 | 0 | 101692 | 5502 | 96190 | 110228 | 104725 | 0 | 0 | 0 | 104725 | 104725 | 108.9% | 1 | 0 | 8535 | 21 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 8535 | 0 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2015-01-28 | QTR3 | 14/15 |  | 2014-10-04 | QTR2 | 14/15 | 214 | 119253.64 | B0 | ACC - LUMP SUM
| 02 | T2540 | 4328234G201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 90 | 160 | 160 | 102.2% | 1 | 0 | 0 | 0 | 70 | 0 | 344794 | 0 | 344794 | 344794 | 360786 | 0 | 0 | 0 | 360786 | 0 | 0% | 1 | -360786 | 0 | 61 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-02-26 | QTR3 | 14/15 |  | 2015-02-10 | QTR3 | 14/15 | 209 | 230306.1
| 02 | T2549 | 43551015201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 120 | 147 | 147 | 108.3% | 1 | 0 | 0 | 0 | 17 | 10 | 1205130 | 45181 | 1159949 | 1205130 | 1163672 | 0 | 0 | 0 | 1163672 | 1163672 | 100.3% | 1 | 0 | 0 | 6 | 11 | 0 | 0 | 1003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4081 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-03-10 | QTR3 | 14/15 |  | 2015-01-21 | QTR3 | 14/15 | 216 | 982529.51
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 30 | 32 | 36 | 5457 | 7975 | 8258 | 76.67% | 23 | -283 | 417 | 0 | 1647 | 871 | 81923408 | 1363346 | 80560060 | 84691185 | 84724704 | -87948 | 0 | -87948 | 84636756 | 84321520 | 80% | 24 | -315235 | 2767776 | 1095 | 442 | 5 | 271 | 663812 | 49392 | 25 | 322 | 749090 | 52513 | 0 | 0 | 568 | 0 | 0 | 0 | -34133 | 0 | 0 | 0 | 8000 | 0 | 0 | 127 | 523029 | 58755 | 0 | 0 | 12676 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 3079 | 0 | 0 | 119 | 1429570 | 0 | 18 | 7 | 3196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 871 | 3358888 | 160660
| 02 | E2P13 | 20954555201 | 2011-09-22 | QTR1 | 11/12 | 2 | 5 | 695 | 921 | 920 | 108.9% | 1 | 1 | 0 | 0 | 163 | 63 | 30532000 | 150000 | 30382000 | 30924278 | 30907321 | 0 | 0 | 0 | 30907321 | 30898233 | 101.7% | 1 | -9088 | 392278 | 116 | 47 | 0 | 31 | 119396 | 0 | 0 | 32 | 337971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 506867 | 0 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2014-08-29 | QTR1 | 14/15 |  | 2014-05-30 | QTR4 | 13/14 | 208 | 34254654.22 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2R03 | 20837135201 | 2013-04-17 | QTR4 | 12/13 | 4 | 0 | 365 | 486 | 482 | 98.9% | 1 | 4 | 0 | 0 | 121 | 0 | 1823323 | 50000 | 1773323 | 1823323 | 1649161 | 0 | 0 | 0 | 1649161 | 1649160 | 93% | 1 | -1 | 0 | 103 | 18 | 0 | 0 | 12126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25569 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2015-02-13 | QTR3 | 14/15 |  | 2014-12-19 | QTR2 | 14/15 | 214 | 2547672.59
| 02 | E2R90 | 20971015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 1 | 28 | 46 | 46 | 128.6% | 0 | 0 | 0 | 0 | 18 | 0 | 141019 | 9015 | 132004 | 153230 | 151100 | 0 | 0 | 0 | 151100 | 151100 | 114.5% | 0 | 0 | 12210 | 6 | 4 | 8 | 0 | 19096 | 2232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 19096 | 2232 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2015-03-04 | QTR3 | 14/15 |  | 2014-12-18 | QTR2 | 14/15 | 208 | 186563.71 | B0 | ACC - LUMP SUM
| 02 | E2S03 | 42870215201 | 2013-09-18 | QTR1 | 13/14 | 1 | 0 | 160 | 196 | 195 | 101.9% | 1 | 1 | 0 | 0 | 32 | 4 | 2539934 | 50000 | 2489934 | 2539934 | 2563383 | 0 | 0 | 0 | 2563383 | 2562645 | 102.9% | 1 | -738 | 0 | 27 | 5 | 0 | 4 | 33564 | 0 | 0 | 0 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37684 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-18 | QTR2 | 14/15 |  | 2014-08-08 | QTR1 | 14/15 | 208 | 2390761.42 | B0 | ACC - LUMP SUM
| 02 | E2S34 | 42869315201 | 2014-03-19 | QTR3 | 13/14 | 1 | 0 | 110 | 127 | 127 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 2053370 | 50000 | 2003370 | 2053370 | 1811375 | 0 | 0 | 0 | 1811375 | 1821200 | 90.91% | 1 | 9826 | 0 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7390 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-02-20 | QTR3 | 14/15 |  | 2014-10-15 | QTR2 | 14/15 | 209 | 1709666.27
| 02 | E2T05 | 43055015201 | 2014-07-23 | QTR1 | 14/15 | 1 | 0 | 120 | 134 | 127 | 94.17% | 1 | 7 | 0 | 0 | 14 | 0 | 1656117 | 50000 | 1606117 | 1656117 | 1659137 | 0 | 0 | 0 | 1659137 | 1659137 | 103.3% | 1 | 0 | 0 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7846 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-03-20 | QTR3 | 14/15 |  | 2015-01-19 | QTR3 | 14/15 | 209 | 1793903.12
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 6 | 10 | 6 | 1478 | 1910 | 1897 | 83.33% | 5 | 13 | 0 | 0 | 365 | 67 | 38745763 | 359015 | 38386748 | 39150252 | 38741477 | 0 | 0 | 0 | 38741477 | 38741475 | 83.33% | 5 | -1 | 404488 | 266 | 91 | 8 | 35 | 184182 | 2232 | 0 | 32 | 349481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 67 | 604452 | 2232
| District 02 Totals |  |  |  |  | 36 | 42 | 42 | 6935 | 9885 | 10155 | 77.78% | 28 | -270 | 417 | 0 | 2012 | 938 | 120669171 | 1722361 | 118946808 | 123841437 | 123466181 | -87948 | 0 | -87948 | 123378233 | 123062995 | 80.56% | 29 | -315236 | 3172264 | 1361 | 533 | 13 | 306 | 847994 | 51624 | 25 | 354 | 1098571 | 52513 | 0 | 0 | 568 | 0 | 0 | 0 | -34133 | 0 | 0 | 0 | 57500 | 0 | 0 | 127 | 523029 | 58755 | 0 | 0 | 20522 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 16522 | 0 | 0 | 119 | 1429570 | 0 | 18 | 7 | 3196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 938 | 3963340 | 162892
| 03 | T3319 | 42290015201 | 2013-02-06 | QTR3 | 12/13 | 1 | 0 | 292 | 378 | 377 | 103.4% | 1 | 1 | 0 | 0 | 86 | 0 | 1593695 | 0 | 1593695 | 1593695 | 1665227 | 0 | 0 | 0 | 1665227 | 1665227 | 104.5% | 1 | 0 | 0 | 60 | 15 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2014-07-03 | QTR1 | 14/15 |  | 2014-05-08 | QTR4 | 13/14 | 308 | 1600251.25
| 03 | T3346 | 22041275201 | 2010-07-28 | QTR1 | 10/11 | 2 | 12 | 916 | 1360 | 1360 | 123.1% | 0 | 0 | 0 | 0 | 232 | 212 | 10500079 | 100853 | 10399227 | 12397501 | 12548192 | 0 | 0 | 0 | 12548192 | 12773148 | 122.8% | 0 | 224955 | 1897421 | 162 | 70 | 0 | 50 | 228874 | 0 | 0 | 100 | 1133691 | 927959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 661097 | 258660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -126182 | 0 | 0 | 212 | 1986503 | 1186620 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 |  | 2014-07-08 | QTR1 | 14/15 | 308 | 10184133.3
| 03 | T3352 | 42289515201 | 2013-04-24 | QTR4 | 12/13 | 1 | 2 | 250 | 380 | 380 | 112% | 1 | 0 | 0 | 0 | 100 | 30 | 1128898 | 0 | 1128898 | 1282710 | 1246387 | 0 | 0 | 0 | 1246387 | 1246387 | 110.4% | 0 | 0 | 153812 | 87 | 13 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 144312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 153812 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2014-09-25 | QTR1 | 14/15 |  | 2014-07-08 | QTR1 | 14/15 | 308 | 1153101.93
| 03 | T3387 | 41931215201 | 2012-09-26 | QTR1 | 12/13 | 2 | 1 | 455 | 593 | 593 | 100% | 1 | 0 | 0 | 0 | 138 | 0 | 10256485 | 97092 | 10159393 | 10266588 | 10798722 | 0 | 0 | 0 | 10798722 | 10767112 | 106% | 1 | -31610 | 10103 | 61 | 77 | 0 | 0 | 18146 | 0 | 0 | 0 | 10103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28249 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-10-20 | QTR2 | 14/15 |  | 2014-07-25 | QTR1 | 14/15 | 314 | 9797232.92
| 03 | T3393 | 42764815201 | 2014-02-26 | QTR3 | 13/14 | 1 | 0 | 115 | 121 | 120 | 100% | 1 | 1 | 0 | 0 | 5 | 1 | 235382 | 14952 | 220430 | 235382 | 217296 | 0 | 0 | 0 | 217296 | 217296 | 98.58% | 1 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 4058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4058 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2014-12-01 | QTR2 | 14/15 |  | 2014-09-26 | QTR1 | 14/15 | 308 | 313418.07
| 03 | T3407 | 42708915201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 120 | 151 | 151 | 91.67% | 1 | 0 | 0 | 0 | 41 | -10 | 1432492 | 50000 | 1382492 | 1432492 | 1414923 | 0 | 0 | 0 | 1414923 | 1414923 | 102.3% | 1 | 0 | 0 | 39 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 0 | 0 | 0 | -10 | 1080 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-09-30 | QTR1 | 14/15 |  | 2014-06-05 | QTR4 | 13/14 | 313 | 1601803.96
| 03 | T3414 | 42624215201 | 2014-05-07 | QTR4 | 13/14 | 1 | 0 | 80 | 108 | 91 | 78.75% | 1 | 17 | 0 | 0 | 28 | 0 | 524227 | 0 | 524227 | 524227 | 524513 | 0 | 0 | 0 | 524513 | 524513 | 100.1% | 1 | 0 | 0 | 27 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 |  | 2014-10-19 | QTR2 | 14/15 | 313 | 433162.54
| 03 | T3420 | 42624115201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 145 | 243 | 233 | 93.1% | 1 | 10 | 0 | 0 | 98 | 0 | 725683 | 0 | 725683 | 725683 | 712533 | 0 | 0 | 0 | 712533 | 712533 | 98.19% | 1 | 0 | 0 | 92 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2014-10-08 | QTR2 | 14/15 |  | 2014-09-09 | QTR1 | 14/15 | 313 | 936031.12
| 03 | T3439 | 42624015201 | 2014-02-26 | QTR3 | 13/14 | 2 | 0 | 70 | 132 | 131 | 98.57% | 1 | 1 | 0 | 0 | 62 | 0 | 351199 | 0 | 351199 | 351199 | 379044 | 0 | 0 | 0 | 379044 | 379044 | 107.9% | 1 | 0 | 0 | 55 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2014-11-13 | QTR2 | 14/15 |  | 2014-09-25 | QTR1 | 14/15 | 313 | 325109.06
| 03 | T3444 | 42873515201 | 2013-07-31 | QTR1 | 13/14 | 1 | 0 | 125 | 228 | 228 | 110.4% | 1 | 0 | 0 | 0 | 90 | 13 | 1618073 | 50000 | 1568073 | 1618073 | 1610344 | 0 | 0 | 0 | 1610344 | 1610562 | 102.7% | 1 | 218 | 0 | 50 | 40 | 0 | 13 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 400 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-07 | QTR2 | 14/15 |  | 2014-06-02 | QTR4 | 13/14 | 314 | 1729641.89
| 03 | T3447 | 42462125201 | 2013-04-24 | QTR4 | 12/13 | 2 | 1 | 200 | 330 | 330 | 100% | 1 | 0 | 0 | 0 | 130 | 0 | 1437977 | 50000 | 1387977 | 1413565 | 1379096 | 0 | 0 | 0 | 1379096 | 1378972 | 99.35% | 1 | -124 | -24412 | 87 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22312 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-09-22 | QTR1 | 14/15 |  | 2014-06-06 | QTR4 | 13/14 | 314 | 1241396.09
| 03 | T3448 | 42289215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 20 | 26 | 26 | 100% | 1 | 0 | 0 | 0 | 6 | 0 | 67717 | 0 | 67717 | 67717 | 67717 | 0 | 0 | 0 | 67717 | 67717 | 100% | 1 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263312611 | R B M CONTRACTING SERVICES LLC | N/A | N/A | N/A | N/A | 2014-11-25 | QTR2 | 14/15 |  | 2014-10-25 | QTR2 | 14/15 | 313 | 72380.08
| 03 | T3458 | 42952015201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 200 | 261 | 278 | 110% | 1 | -17 | 17 | 0 | 58 | 3 | 2559715 | 50000 | 2509715 | 2583659 | 2625549 | -37984 | 0 | -37984 | 2587565 | 2587966 | 103.1% | 1 | 401 | 23944 | 52 | 6 | 0 | 3 | 26106 | 0 | 0 | 0 | 3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 29979 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 |  | 2014-10-09 | QTR2 | 14/15 | 308 | 2618783.02
| 03 | T3490 | 41268235201 | 2014-05-07 | QTR4 | 13/14 | 1 | 0 | 45 | 48 | 45 | 93.33% | 1 | 3 | 0 | 0 | 3 | 0 | 70232 | 4732 | 65500 | 70232 | 65500 | 0 | 0 | 0 | 65500 | 65500 | 100% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204129847 | MAIN STREET CONSTRUCTION SERVICES LLC | N/A | N/A | N/A | N/A | 2014-09-15 | QTR1 | 14/15 |  | 2014-08-22 | QTR1 | 14/15 | 313 | 88398.13 | B0 | ACC - LUMP SUM
| 03 | T3499 | 43213715201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 105 | 107 | 103 | 96.19% | 1 | 4 | 0 | 0 | 2 | 0 | 1631904 | 50000 | 1581904 | 1631904 | 1616123 | 0 | 537500 | 537500 | 2153623 | 1616123 | 102.2% | 1 | -537500 | 0 | 0 | 2 | 0 | 0 | 2200 | 0 | 0 | 0 | 13828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16028 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-16 | QTR2 | 14/15 |  | 2014-08-29 | QTR1 | 14/15 | 321 | 1503606.97 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 03 | T3509 | 42635715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 80 | 110 | 106 | 95% | 1 | 4 | 0 | 0 | 30 | 0 | 493770 | 0 | 493770 | 493770 | 495890 | 0 | 0 | 0 | 495890 | 495890 | 100.4% | 1 | 0 | 0 | 29 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 |  | 2014-11-10 | QTR2 | 14/15 | 313 | 436183.99
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 16 | 20 | 18 | 3218 | 4576 | 4552 | 93.75% | 15 | 24 | 17 | 0 | 1109 | 249 | 34627528 | 467629 | 34159900 | 36688397 | 37367056 | -37984 | 537500 | 499516 | 37866572 | 37522913 | 87.5% | 14 | -343660 | 2060868 | 813 | 285 | 11 | 66 | 285226 | 0 | 0 | 101 | 1165553 | 927959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 782077 | 258660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -126182 | 0 | 11 | 249 | 2197797 | 1186620
| 03 | E3K71 | 42694915201 | 2013-10-10 | QTR2 | 13/14 | 2 | 0 | 125 | 174 | 173 | 110.4% | 1 | 1 | 0 | 0 | 35 | 14 | 1995786 | 50000 | 1945786 | 1995786 | 1979207 | 0 | 0 | 0 | 1979207 | 1982470 | 101.9% | 1 | 3263 | 0 | 15 | 20 | 0 | 14 | 2000 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 4200 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-29 | QTR2 | 14/15 |  | 2014-07-01 | QTR1 | 14/15 | 314 | 2340966.29
| 03 | E3L10 | 41557525201 | 2013-03-14 | QTR3 | 12/13 | 1 | 2 | 145 | 339 | 296 | 202.1% | 0 | 43 | 0 | 0 | 3 | 191 | 533421 | 37241 | 496180 | 735554 | 237341 | 0 | 0 | 0 | 237341 | 237341 | 47.83% | 1 | 0 | 202133 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 140095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62038 | 34816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 202133 | 34816 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2015-02-16 | QTR3 | 14/15 |  | 2014-03-13 | QTR3 | 13/14 | 308 | 782055.17
| 03 | E3L32 | 22283225201 | 2014-01-09 | QTR3 | 13/14 | 1 | 0 | 55 | 107 | 106 | 98.18% | 1 | 1 | 0 | 0 | 52 | 0 | 292884 | 12670 | 280214 | 292884 | 288038 | 0 | 0 | 0 | 288038 | 288038 | 102.8% | 1 | 0 | 0 | 48 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593428518 | MARSHALL BROTHERS CONSTRUCTION & ENGINEE | N/A | N/A | N/A | N/A | 2014-11-12 | QTR2 | 14/15 |  | 2014-07-07 | QTR1 | 14/15 | 313 | 266060.99
| 03 | E3L65 | 42357745201 | 2014-05-08 | QTR4 | 13/14 | 1 | 0 | 90 | 120 | 117 | 112.2% | 1 | 3 | 0 | 0 | 16 | 14 | 311461 | 11461 | 300000 | 311461 | 300000 | 0 | 0 | 0 | 300000 | 300000 | 100% | 1 | 0 | 0 | 11 | 5 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | F593428518 | MARSHALL BROTHERS CONSTRUCTION & ENGINEE | N/A | N/A | N/A | N/A | 2015-01-14 | QTR3 | 14/15 |  | 2014-12-17 | QTR2 | 14/15 | 314 | 240688.14
| 03 | E3L96 | 41767735201 | 2013-11-14 | QTR2 | 13/14 | 1 | 0 | 65 | 95 | 95 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 82868 | 2290 | 80578 | 82868 | 80578 | 0 | 0 | 0 | 80578 | 80578 | 100% | 1 | 0 | 0 | 13 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-07-02 | QTR1 | 14/15 |  | 2014-05-13 | QTR4 | 13/14 | 314 | 48100.13
| 03 | E3M21 | 42187825201 | 2014-01-09 | QTR3 | 13/14 | 1 | 0 | 60 | 94 | 94 | 105% | 1 | 0 | 0 | 0 | 31 | 3 | 842964 | 39931 | 803033 | 842964 | 857292 | 0 | 0 | 0 | 857292 | 857292 | 106.8% | 1 | 0 | 0 | 28 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 18257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18257 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-08-01 | QTR1 | 14/15 |  | 2014-07-01 | QTR1 | 14/15 | 313 | 838555.84
| 03 | E3M23 | 42695815201 | 2014-01-09 | QTR3 | 13/14 | 1 | 0 | 70 | 78 | 78 | 100% | 1 | 0 | 0 | 0 | 8 | 0 | 1549934 | 50000 | 1499934 | 1549934 | 1527279 | 0 | 0 | 0 | 1527279 | 1527279 | 101.8% | 1 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-01 | QTR2 | 14/15 |  | 2014-06-14 | QTR4 | 13/14 | 313 | 1966885.65 | B0 | ACC - LUMP SUM
| 03 | E3M24 | 42693315201 | 2013-12-12 | QTR2 | 13/14 | 2 | 2 | 210 | 291 | 290 | 119% | 1 | 1 | 0 | 0 | 48 | 33 | 3867191 | 50000 | 3817191 | 4050762 | 4276825 | 0 | 0 | 0 | 4276825 | 4245773 | 111.2% | 0 | -31052 | 183571 | 30 | 10 | 0 | 80 | 320908 | 0 | 0 | -7 | 30683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 73 | 351591 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-03-10 | QTR3 | 14/15 |  | 2014-12-22 | QTR2 | 14/15 | 314 | 4425803.28
| 03 | E3M35 | 42543325201 | 2014-04-10 | QTR4 | 13/14 | 1 | 0 | 30 | 30 | 15 | 50% | 1 | 15 | 0 | 0 | 0 | 0 | 58110 | 2539 | 55571 | 58110 | 55571 | 0 | 0 | 0 | 55571 | 55571 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453031471 | LIVE OAK MANAGEMENT GROUP L.L.C. | N/A | N/A | N/A | N/A | 2014-07-30 | QTR1 | 14/15 |  | 2014-07-21 | QTR1 | 14/15 | 314 | 53308.77
| 03 | E3M36 | 21934425201 | 2014-03-13 | QTR3 | 13/14 | 1 | 1 | 90 | 97 | 97 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 268872 | 15344 | 253528 | 310112 | 294768 | 0 | 0 | 0 | 294768 | 294768 | 116.3% | 0 | 0 | 41240 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 41240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41240 | 0 | F522182511 | GULF COAST UTILITY CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2014-09-22 | QTR1 | 14/15 |  | 2014-09-05 | QTR1 | 14/15 | 314 | 322223.89
| 03 | E3M39 | 42188935201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 30 | 30 | 20 | 66.67% | 1 | 10 | 0 | 0 | 0 | 0 | 41842 | 2595 | 39247 | 41842 | 48742 | 0 | 0 | 0 | 48742 | 48742 | 124.2% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591565266 | MCCORMICK CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2014-07-23 | QTR1 | 14/15 |  | 2014-06-25 | QTR4 | 13/14 | 313 | 54498.15
| 03 | E3M40 | 43303415201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 30 | 34 | 28 | 80% | 1 | 6 | 0 | 0 | 4 | 0 | 77224 | 997 | 76227 | 77224 | 76227 | 0 | 0 | 0 | 76227 | 76227 | 100% | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-07-24 | QTR1 | 14/15 |  | 2014-07-03 | QTR1 | 14/15 | 314 | 20935.9
| 03 | E3M41 | 43301715201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 45 | 72 | 72 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 199790 | 5070 | 194721 | 199790 | 194721 | 0 | 0 | 0 | 194721 | 194721 | 100% | 1 | 0 | 0 | 26 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-09-12 | QTR1 | 14/15 |  | 2014-08-15 | QTR1 | 14/15 | 313 | 106467.89
| 03 | E3M62 | 41101635201 | 2014-02-13 | QTR3 | 13/14 | 1 | 0 | 90 | 100 | 51 | 47.78% | 1 | 49 | 0 | 0 | 8 | 2 | 861171 | 39975 | 821196 | 861171 | 848543 | 0 | 0 | 0 | 848543 | 848543 | 103.3% | 1 | 0 | 0 | 6 | 2 | 0 | 2 | 19442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 27347 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-07-30 | QTR1 | 14/15 |  | 2014-07-10 | QTR1 | 14/15 | 308 | 839474.9
| 03 | E3N21 | 42543625201 | 2014-06-30 | QTR4 | 13/14 | 1 | 0 | 30 | 43 | 30 | 56.67% | 1 | 13 | 0 | 0 | 13 | 0 | 395355 | 14449 | 380906 | 395355 | 375669 | 0 | 0 | 0 | 375669 | 375669 | 98.63% | 1 | 0 | 0 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2015-01-14 | QTR3 | 14/15 |  | 2014-12-15 | QTR2 | 14/15 | 314 | 303422.4
| 03 | E3N25 | 41110235202 | 2014-04-29 | QTR4 | 13/14 | 3 | 0 | 60 | 75 | 75 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 489178 | 41541 | 447637 | 489178 | 466189 | 0 | 0 | 0 | 466189 | 466189 | 104.1% | 1 | 0 | 0 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20700 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2014-09-29 | QTR1 | 14/15 |  | 2014-08-09 | QTR1 | 14/15 | 308 | 872363.6
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 16 | 20 | 5 | 1225 | 1779 | 1637 | 93.75% | 15 | 142 | 0 | 0 | 297 | 257 | 11868051 | 376103 | 11491949 | 12294995 | 11906990 | 0 | 0 | 0 | 11906990 | 11879201 | 81.25% | 13 | -27789 | 426944 | 213 | 76 | 0 | 110 | 342350 | 0 | 0 | -4 | 92380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 191 | 168700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62038 | 34816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 297 | 665468 | 34816
| District 03 Totals |  |  |  |  | 32 | 40 | 23 | 4443 | 6355 | 6189 | 93.75% | 30 | 166 | 17 | 0 | 1406 | 506 | 46495579 | 843732 | 45651849 | 48983392 | 49274046 | -37984 | 537500 | 499516 | 49773562 | 49402114 | 84.38% | 27 | -371449 | 2487812 | 1026 | 361 | 11 | 176 | 627576 | 0 | 0 | 97 | 1257933 | 927959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 283 | 950777 | 258660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91123 | 0 | 0 | 0 | 62038 | 34816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -126182 | 0 | 19 | 546 | 2863265 | 1221436
| 04 | T4231 | 23026225201 | 2010-10-27 | QTR2 | 10/11 | 1 | 5 | 1233 | 1392 | 1319 | 99.59% | 1 | 73 | 0 | 0 | 97 | 62 | 18782629 | 150000 | 18632629 | 19297262 | 18712392 | 0 | 0 | 0 | 18712392 | 19989362 | 107.3% | 1 | 1276970 | 514633 | 64 | 27 | 6 | 23 | 179221 | 0 | 0 | 39 | 312675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 62 | 459652 | 0 | F203608929 | GUETTLER BROTHERS CONSTRUCTION | N/A | N/A | N/A | N/A | 2015-01-14 | QTR3 | 14/15 |  | 2014-09-10 | QTR1 | 14/15 | 408 | 21341977.53
| 04 | T4302 | 42165925201 | 2011-02-23 | QTR3 | 10/11 | 1 | 2 | 855 | 934 | 877 | 93.33% | 1 | 57 | 0 | 0 | 79 | 0 | 5777225 | 64239 | 5712986 | 5816337 | 5751222 | 0 | 0 | 0 | 5751222 | 5834538 | 102.1% | 1 | 83317 | 39112 | 46 | 33 | 0 | 0 | 10650 | 10650 | 0 | 0 | 40264 | 6621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70236 | 17271 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 |  | 2013-11-27 | QTR2 | 13/14 | 412 | 6362930.61
| 04 | T4304 | 42465815201 | 2011-05-25 | QTR4 | 10/11 | 1 | 0 | 196 | 214 | 226 | 106.1% | 1 | -12 | 12 | 0 | 18 | 0 | 6245041 | 65382 | 6179659 | 6245041 | 5814959 | -30168 | 0 | -30168 | 5784791 | 5792664 | 93.74% | 1 | 7873 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2014-11-13 | QTR2 | 14/15 |  | 2012-04-24 | QTR4 | 11/12 | 409 | 6491710.44
| 04 | T4317 | 22989725201 | 2012-05-23 | QTR4 | 11/12 | 4 | 4 | 500 | 576 | 572 | 99.4% | 1 | 4 | 0 | 0 | 75 | 1 | 12189533 | 141257 | 12048276 | 12136729 | 11383036 | 0 | 0 | 0 | 11383036 | 11348816 | 94.19% | 1 | -34220 | -52804 | 50 | 25 | 0 | 1 | 351627 | 0 | 0 | 0 | -35116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -346622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -30111 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-08-01 | QTR1 | 14/15 |  | 2014-05-30 | QTR4 | 13/14 | 409 | 13843853.6
| 04 | T4343 | 42700615201 | 2013-02-06 | QTR3 | 12/13 | 1 | 0 | 270 | 325 | 316 | 96.67% | 1 | 9 | 0 | 0 | 55 | 0 | 4110157 | 50000 | 4060157 | 4110157 | 3912758 | 0 | 0 | 0 | 3912758 | 3908261 | 96.26% | 1 | -4497 | 0 | 35 | 20 | 0 | 0 | 4901 | 0 | 0 | 0 | 6528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11429 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-07-03 | QTR1 | 14/15 |  | 2014-03-07 | QTR3 | 13/14 | 412 | 4806481.71
| 04 | T4354 | 42701015202 | 2013-02-06 | QTR3 | 12/13 | 2 | 0 | 135 | 157 | 152 | 96.3% | 1 | 5 | 0 | 0 | 22 | 0 | 1494392 | 50000 | 1444392 | 1494392 | 1415437 | 0 | 0 | 0 | 1415437 | 1414762 | 97.95% | 1 | -675 | 0 | 19 | 3 | 0 | 0 | 16007 | 0 | 0 | 0 | 2510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18517 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 |  | 2013-09-20 | QTR1 | 13/14 | 412 | 1689811.51
| 04 | T4358 | 42595915201 | 2013-04-24 | QTR4 | 12/13 | 1 | 1 | 236 | 337 | 337 | 116.9% | 1 | 0 | 0 | 0 | 61 | 40 | 2422014 | 50000 | 2372014 | 2432708 | 2371735 | 0 | 0 | 0 | 2371735 | 2371392 | 99.97% | 1 | -344 | 10693 | 46 | 15 | 0 | 8 | 1353 | 0 | 0 | 30 | 17670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 19023 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-07 | QTR2 | 14/15 |  | 2014-06-27 | QTR4 | 13/14 | 409 | 2517656.6
| 04 | T4361 | 43180215201 | 2013-03-27 | QTR3 | 12/13 | 2 | 1 | 95 | 234 | 234 | 191.6% | 0 | 0 | 0 | 0 | 52 | 87 | 689978 | 33230 | 656748 | 758529 | 711942 | 0 | 0 | 0 | 711942 | 711942 | 108.4% | 1 | 0 | 68551 | 31 | 21 | 0 | 0 | 0 | 0 | 0 | 87 | 68551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 68551 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-07-03 | QTR1 | 14/15 |  | 2014-04-22 | QTR4 | 13/14 | 412 | 637973.2 | B0 | ACC - LUMP SUM
| 04 | T4363 | 42702315201 | 2013-04-24 | QTR4 | 12/13 | 1 | 1 | 355 | 400 | 382 | 94.93% | 1 | 18 | 0 | 0 | 45 | 0 | 4643370 | 53517 | 4589853 | 4643367 | 4430846 | 0 | 0 | 0 | 4430846 | 4429353 | 96.5% | 1 | -1493 | -3 | 29 | 16 | 0 | 0 | 6177 | 0 | 0 | 0 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19801 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2014-10-03 | QTR2 | 14/15 |  | 2014-07-24 | QTR1 | 14/15 | 408 | 5421475.17
| 04 | T4364 | 42827315201 | 2013-08-28 | QTR1 | 13/14 | 1 | 0 | 123 | 172 | 165 | 110.6% | 1 | 7 | 0 | 0 | 29 | 20 | 721864 | 50000 | 671864 | 721864 | 722927 | 0 | 0 | 0 | 722927 | 722927 | 107.6% | 1 | 0 | 0 | 27 | 2 | 0 | 0 | 24823 | 0 | 0 | 20 | 19517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 44341 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-30 | QTR2 | 14/15 |  | 2014-08-28 | QTR1 | 14/15 | 412 | 992063.41
| 04 | T4365 | 41965335201 | 2013-04-24 | QTR4 | 12/13 | 2 | 2 | 290 | 316 | 280 | 87.59% | 1 | 36 | 0 | 0 | 26 | 0 | 3339650 | 50000 | 3289650 | 3389650 | 3397354 | 0 | 0 | 0 | 3397354 | 3396581 | 103.3% | 1 | -773 | 50000 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-08-19 | QTR1 | 14/15 |  | 2014-05-30 | QTR4 | 13/14 | 408 | 4422362.92
| 04 | T4368 | 42759115201 | 2013-05-22 | QTR4 | 12/13 | 2 | 2 | 150 | 274 | 312 | 142% | 0 | -38 | 38 | 0 | 99 | 25 | 1215736 | 50000 | 1165736 | 1260164 | 1228303 | -58216 | 0 | -58216 | 1170087 | 1170858 | 100.4% | 1 | 771 | 44428 | 81 | 18 | 0 | 0 | 44428 | 44428 | 0 | 25 | 41786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 86214 | 44428 | F592655272 | WESTWIND CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-09-30 | QTR1 | 14/15 |  | 2014-07-26 | QTR1 | 14/15 | 412 | 1299911.4
| 04 | T4370 | 42302215201 | 2013-06-19 | QTR4 | 12/13 | 1 | 4 | 351 | 432 | 430 | 99.43% | 1 | 2 | 0 | 0 | 81 | 0 | 3994488 | 50000 | 3944488 | 3817187 | 3633879 | 0 | 0 | 0 | 3633879 | 3631334 | 92.06% | 1 | -2546 | -177301 | 53 | 28 | 0 | 0 | 47123 | 0 | 0 | 0 | 21929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -251373 | 0 | 0 | 0 | -182320 | 0 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2015-03-24 | QTR3 | 14/15 |  | 2015-01-08 | QTR3 | 14/15 | 408 | 4662648.45
| 04 | T4375 | 43079815201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 108 | 157 | 156 | 99.07% | 1 | 1 | 0 | 0 | 49 | 0 | 498954 | 24682 | 474271 | 498954 | 489047 | 0 | 0 | 0 | 489047 | 489047 | 103.1% | 1 | 0 | 0 | 45 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3562 | 0 | F590895890 | WILLIAMS PAVING COMPANY INC. | N/A | N/A | N/A | N/A | 2015-01-27 | QTR3 | 14/15 |  | 2014-10-06 | QTR2 | 14/15 | 412 | 522993.7
| 04 | T4378 | 43254915201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 140 | 149 | 105 | 68.57% | 1 | 44 | 0 | 0 | 9 | 0 | 1785000 | 50000 | 1735000 | 1785000 | 1735000 | 0 | 0 | 0 | 1735000 | 1735000 | 100% | 1 | 0 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2014-07-29 | QTR1 | 14/15 |  | 2014-06-26 | QTR4 | 13/14 | 409 | 2295537.87 | B0 | ACC - LUMP SUM
| 04 | T4379 | 42701225201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 105 | 118 | 110 | 92.38% | 1 | 8 | 0 | 0 | 13 | 0 | 539489 | 27111 | 512378 | 539489 | 527684 | 0 | 0 | 0 | 527684 | 527684 | 103% | 1 | 0 | 0 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 14632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14632 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-10 | QTR2 | 14/15 |  | 2014-08-22 | QTR1 | 14/15 | 412 | 587592.14
| 04 | T4385 | 41925045201 | 2014-04-30 | QTR4 | 13/14 | 1 | 0 | 120 | 133 | 120 | 89.17% | 1 | 13 | 0 | 0 | 13 | 0 | 337659 | 21299 | 316360 | 337659 | 319291 | 0 | 0 | 0 | 319291 | 319291 | 100.9% | 1 | 0 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-03-03 | QTR3 | 14/15 |  | 2015-01-28 | QTR3 | 14/15 | 408 | 445321.82
| 04 | T4390 | 22793825201 | 2014-02-26 | QTR3 | 13/14 | 1 | 0 | 115 | 186 | 186 | 117.4% | 1 | 0 | 0 | 0 | 51 | 20 | 517006 | 24506 | 492500 | 517006 | 511187 | 0 | 0 | 0 | 511187 | 511187 | 103.8% | 1 | 0 | 0 | 37 | 14 | 0 | 15 | 11876 | 0 | 0 | 5 | 6810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 18687 | 0 | F364509634 | MAYTIN ENGINEERING CORP. | N/A | N/A | N/A | N/A | 2015-03-24 | QTR3 | 14/15 |  | 2015-01-25 | QTR3 | 14/15 | 412 | 515260.79 | A4 | ICC - LUMP SUM
| 04 | T4391 | 42700415201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 132 | 148 | 144 | 96.97% | 1 | 4 | 0 | 0 | 16 | 0 | 1172000 | 50000 | 1122000 | 1172000 | 1117522 | 0 | 0 | 0 | 1117522 | 1109463 | 98.88% | 1 | -8059 | 0 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 23090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23090 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-02-03 | QTR3 | 14/15 |  | 2014-12-23 | QTR2 | 14/15 | 412 | 1321863.11 | B0 | ACC - LUMP SUM
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 19 | 26 | 22 | 5509 | 6654 | 6423 | 89.47% | 17 | 231 | 50 | 0 | 890 | 255 | 70476185 | 1055223 | 69420961 | 70973495 | 68186521 | -88384 | 0 | -88384 | 68098137 | 69414462 | 100% | 19 | 1316324 | 497309 | 613 | 271 | 6 | 47 | 698186 | 55078 | 0 | 206 | 544405 | 6621 | 0 | 0 | 0 | 0 | 0 | 0 | -34179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -274055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -251373 | 0 | 6 | 253 | 695304 | 61699
| 04 | E4L72 | 41925025201 | 2011-06-24 | QTR4 | 10/11 | 1 | 4 | 1029 | 1126 | 1015 | 90.09% | 1 | 111 | 0 | 0 | 97 | 0 | 31906521 | 150000 | 31756521 | 33004982 | 32827693 | 0 | 0 | 0 | 32827693 | 32827750 | 103.4% | 1 | 57 | 1098461 | 64 | 24 | 0 | 0 | 802316 | 0 | 0 | 0 | 92012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098227 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-11-18 | QTR2 | 14/15 |  | 2014-07-03 | QTR1 | 14/15 | 408 | 52109389.9 | B8 | ACC - DESIGN/BUILD - MAJOR
| 04 | E4L76 | 41304615201 | 2011-03-04 | QTR3 | 10/11 | 2 | 6 | 1096 | 1249 | 1249 | 100.9% | 1 | 0 | 0 | 0 | 145 | 8 | 78270000 | 150000 | 78120000 | 79259528 | 79765800 | 0 | 0 | 0 | 79765800 | 81306557 | 104.1% | 1 | 1540757 | 989528 | 99 | 44 | 2 | 0 | 841941 | 52421 | 0 | 8 | 229983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 1133208 | 52421 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-01-21 | QTR3 | 14/15 |  | 2014-11-14 | QTR2 | 14/15 | 408 | 81639616 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
| 04 | E4M33 | 42844915201 | 2012-04-06 | QTR4 | 11/12 | 2 | 0 | 470 | 631 | 631 | 108.9% | 1 | 0 | 0 | 0 | 161 | 0 | 4582291 | 50000 | 4532291 | 4582291 | 4526291 | 0 | 0 | 0 | 4526291 | 4526291 | 99.87% | 1 | 0 | 0 | 83 | 36 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | F590361850 | MILLER ELECTRIC COMPANY | N/A | N/A | N/A | N/A | 2014-07-17 | QTR1 | 14/15 |  | 2014-04-21 | QTR4 | 13/14 | 412 | 4607566 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| 04 | E4M79 | 42968715201 | 2012-11-09 | QTR2 | 12/13 | 1 | 0 | 510 | 590 | 590 | 100% | 1 | 0 | 0 | 0 | 80 | 0 | 5356871 | 50000 | 5306871 | 5356871 | 5309868 | 0 | 0 | 0 | 5309868 | 5309868 | 100.1% | 1 | 0 | 0 | 59 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6122 | 0 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2014-10-07 | QTR2 | 14/15 |  | 2014-08-27 | QTR1 | 14/15 | 412 | 4541213 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
| 04 | E4N38 | 42443015201 | 2013-02-01 | QTR3 | 12/13 | 1 | 4 | 224 | 415 | 411 | 115.6% | 1 | 4 | 0 | 0 | 152 | 39 | 5772088 | 50000 | 5722088 | 6524967 | 6670851 | 0 | 0 | 0 | 6670851 | 6670318 | 116.6% | 0 | -533 | 752880 | 132 | 20 | 0 | 0 | 397367 | 0 | 0 | 35 | 307272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 48240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 752880 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2015-01-21 | QTR3 | 14/15 |  | 2014-06-09 | QTR4 | 13/14 | 412 | 3858013.38
| 04 | E4N78 | 42413115201 | 2013-06-07 | QTR4 | 12/13 | 1 | 2 | 230 | 302 | 302 | 121.3% | 0 | 0 | 0 | 0 | 23 | 49 | 2265000 | 50000 | 2215000 | 2263132 | 2257066 | 0 | 0 | 0 | 2257066 | 2257066 | 101.9% | 1 | 0 | -1868 | 20 | 3 | 0 | 41 | 47287 | 0 | 0 | 0 | 6648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11868 | 0 | 0 | 49 | 42066 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2015-01-13 | QTR3 | 14/15 |  | 2014-11-03 | QTR2 | 14/15 | 409 | 2068984.39 | B0 | ACC - LUMP SUM
| 04 | E4N85 | 43279615201 | 2013-07-12 | QTR1 | 13/14 | 1 | 1 | 192 | 225 | 225 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 749284 | 40199 | 709084 | 724527 | 703896 | 0 | 0 | 0 | 703896 | 703896 | 99.27% | 1 | 0 | -24756 | 29 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15336 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-07-24 | QTR1 | 14/15 |  | 2014-05-23 | QTR4 | 13/14 | 412 | 1004546.54
| 04 | E4P16 | 43393715201 | 2014-03-07 | QTR3 | 13/14 | 1 | 0 | 59 | 65 | 63 | 96.61% | 1 | 2 | 0 | 0 | 6 | 0 | 161019 | 9118 | 151901 | 161019 | 154042 | 0 | 0 | 0 | 154042 | 154042 | 101.4% | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-09-09 | QTR1 | 14/15 |  | 2014-07-24 | QTR1 | 14/15 | 412 | 190010.49
| 04 | E4P17 | 43279715201 | 2013-12-06 | QTR2 | 13/14 | 1 | 1 | 133 | 159 | 159 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 329900 | 23678 | 306222 | 282285 | 258607 | 0 | 0 | 0 | 258607 | 258607 | 84.45% | 1 | 0 | -47615 | 22 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | -47615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47615 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2015-01-27 | QTR3 | 14/15 |  | 2014-09-05 | QTR1 | 14/15 | 412 | 509246.58
| 04 | E4P22 | 43111315201 | 2014-01-03 | QTR3 | 13/14 | 1 | 0 | 125 | 139 | 136 | 97.6% | 1 | 3 | 0 | 0 | 14 | 0 | 2580338 | 50000 | 2530338 | 2580338 | 2552570 | 0 | 0 | 0 | 2552570 | 2552570 | 100.9% | 1 | -1 | 0 | 12 | 2 | 0 | 0 | 12057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12057 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-09-23 | QTR1 | 14/15 |  | 2014-08-29 | QTR1 | 14/15 | 412 | 2873226.53
| 04 | E4P40 | 43396215201 | 2014-04-04 | QTR4 | 13/14 | 1 | 0 | 103 | 165 | 165 | 100% | 1 | 0 | 0 | 0 | 62 | 0 | 198331 | 11337 | 186994 | 198331 | 185045 | 0 | 0 | 0 | 185045 | 185045 | 98.96% | 1 | 0 | 0 | 53 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F800499292 | L.C.C.I CONSTRUCTION L.L.C. | N/A | N/A | N/A | N/A | 2015-03-20 | QTR3 | 14/15 |  | 2014-12-23 | QTR2 | 14/15 | 412 | 239987.4
| 04 | E4P41 | 43397115201 | 2014-04-04 | QTR4 | 13/14 | 4 | 1 | 171 | 186 | 186 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 1322521 | 45898 | 1276624 | 1322892 | 1154843 | 0 | 0 | 0 | 1154843 | 1154843 | 90.46% | 1 | 0 | 371 | 1 | 14 | 0 | 0 | 9883 | 0 | 0 | 0 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10254 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-03-04 | QTR3 | 14/15 |  | 2015-01-20 | QTR3 | 14/15 | 409 | 973351.52
| 04 | E4P44 | 42909515201 | 2014-03-07 | QTR3 | 13/14 | 1 | 0 | 184 | 187 | 150 | 79.89% | 1 | 37 | 0 | 0 | 3 | 0 | 582291 | 36623 | 545668 | 582291 | 578750 | 0 | 0 | 0 | 578750 | 578750 | 106.1% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592582830 | SIEG & SONS INC. | N/A | N/A | N/A | N/A | 2015-01-22 | QTR3 | 14/15 |  | 2014-11-12 | QTR2 | 14/15 | 412 | 766888.8
| 04 | E4P45 | 42823915201 | 2014-04-04 | QTR4 | 13/14 | 1 | 0 | 66 | 76 | 65 | 83.33% | 1 | 11 | 0 | 0 | 10 | 0 | 267686 | 15549 | 252137 | 267686 | 225755 | 0 | 0 | 0 | 225755 | 225755 | 89.54% | 1 | 0 | 0 | 8 | 2 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2014-10-15 | QTR2 | 14/15 |  | 2014-09-10 | QTR1 | 14/15 | 409 | 324766.26
| 04 | E4P53 | 43397015201 | 2014-04-04 | QTR4 | 13/14 | 1 | 0 | 86 | 93 | 87 | 93.02% | 1 | 6 | 0 | 0 | 7 | 0 | 147095 | 7330 | 139765 | 147095 | 139765 | 0 | 0 | 0 | 139765 | 139765 | 100% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2015-02-17 | QTR3 | 14/15 |  | 2014-11-17 | QTR2 | 14/15 | 409 | 142914.8 | B0 | ACC - LUMP SUM
| 04 | E4P67 | 43396715201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 62 | 72 | 63 | 85.48% | 1 | 9 | 0 | 0 | 10 | 0 | 411559 | 18203 | 393356 | 411559 | 405359 | 0 | 0 | 0 | 405359 | 405359 | 103.1% | 1 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2667 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-12-17 | QTR2 | 14/15 |  | 2014-10-08 | QTR2 | 14/15 | 412 | 372615.07
| 04 | E4P68 | 43400315201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 50 | 51 | 45 | 88% | 1 | 6 | 0 | 0 | 1 | 0 | 374632 | 19781 | 354850 | 374632 | 354850 | 0 | 0 | 0 | 354850 | 354850 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-10-28 | QTR2 | 14/15 |  | 2014-09-26 | QTR1 | 14/15 | 412 | 274084.51
| 04 | E4P78 | 43397615201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 60 | 79 | 71 | 86.67% | 1 | 8 | 0 | 0 | 19 | 0 | 279985 | 12354 | 267631 | 279985 | 270451 | 0 | 0 | 0 | 270451 | 270451 | 101.1% | 1 | 0 | 0 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2820 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2014-11-12 | QTR2 | 14/15 |  | 2014-10-16 | QTR2 | 14/15 | 408 | 250696.53
| 04 | E4P90 | 43397815201 | 2014-06-06 | QTR4 | 13/14 | 1 | 1 | 69 | 82 | 82 | 100% | 1 | 0 | 0 | 0 | 13 | 0 | 181737 | 6705 | 175032 | 146595 | 141584 | 0 | 0 | 0 | 141584 | 141584 | 80.89% | 1 | 0 | -35141 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | -35141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35141 | 0 | F205822418 | DP DEVELOPMENT OF THE TREASURE COAST LL | N/A | N/A | N/A | N/A | 2015-01-21 | QTR3 | 14/15 |  | 2014-12-08 | QTR2 | 14/15 | 412 | 172493.1
| 04 | E4Q12 | 43397515201 | 2014-06-06 | QTR4 | 13/14 | 3 | 0 | 233 | 240 | 95 | 37.77% | 1 | 145 | 0 | 0 | 7 | 0 | 786543 | 32995 | 753548 | 786543 | 731049 | 0 | 0 | 0 | 731049 | 731049 | 97.01% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2015-02-11 | QTR3 | 14/15 |  | 2014-12-12 | QTR2 | 14/15 | 408 | 742852.75
| 04 | E4Q15 | 43400015201 | 2014-05-02 | QTR4 | 13/14 | 2 | 2 | 76 | 85 | 85 | 100% | 1 | 0 | 0 | 0 | 9 | 0 | 510885 | 16340 | 494544 | 134613 | 119405 | 0 | 0 | 0 | 119405 | 119405 | 24.14% | 1 | 0 | -376272 | 9 | 0 | 0 | 0 | -265512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -110760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -376272 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-01-14 | QTR3 | 14/15 |  | 2014-11-07 | QTR2 | 14/15 | 412 | 343149.34
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 21 | 29 | 22 | 5228 | 6217 | 5875 | 95.24% | 20 | 342 | 0 | 0 | 893 | 96 | 137036577 | 846110 | 136190465 | 139392162 | 139333540 | 0 | 0 | 0 | 139333540 | 140873821 | 95.24% | 20 | 1540280 | 2355588 | 636 | 204 | 2 | 41 | 1849567 | 52421 | 42 | 43 | 569380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 116624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11868 | 0 | 44 | 96 | 2590165 | 52421
| District 04 Totals |  |  |  |  | 40 | 55 | 44 | 10737 | 12871 | 12298 | 92.5% | 37 | 573 | 50 | 0 | 1783 | 351 | 207512762 | 1901333 | 205611426 | 210365657 | 207520061 | -88384 | 0 | -88384 | 207431677 | 210288283 | 97.5% | 39 | 2856604 | 2852897 | 1249 | 475 | 8 | 88 | 2547753 | 107499 | 42 | 249 | 1113785 | 6621 | 0 | 0 | 0 | 0 | 0 | 0 | -34179 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | -157431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -263241 | 0 | 50 | 349 | 3285469 | 114120
| 05 | BDU54 | 41299435213 | 2012-06-11 | QTR4 | 11/12 | 5 | 15 | 360 | 637 | 918 | 242.5% | 0 | -281 | 281 | 0 | 46 | 231 | 20846867 | 150000 | 20696867 | 22943912 | 22943912 | 0 | 0 | 0 | 22943912 | 22943912 | 110.9% | 0 | 0 | 2097045 | 18 | 27 | 0 | 187 | 705821 | 43487 | 0 | 0 | 220100 | 34968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 1321124 | 73171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 2247045 | 151627 | F593483018 | WELBRO BUILDING CORPORATION | N/A | N/A | N/A | N/A | 2015-03-10 | QTR3 | 14/15 |  | 2015-02-06 | QTR3 | 14/15 | 507 | 20831867 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE
| 05 | BDV94 | 42344695204 | 2013-03-04 | QTR3 | 12/13 | 1 | 3 | 100 | 195 | 191 | 181% | 0 | 4 | 0 | 0 | 10 | 85 | 554250 | 35000 | 519250 | 673855 | 638855 | 0 | 0 | 0 | 638855 | 638855 | 123% | 0 | 0 | 119605 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 63 | 119605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 119605 | 0 | F232938638 | GREGORI CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-08-11 | QTR1 | 14/15 |  | 2014-01-03 | QTR3 | 13/14 | 507 | 601014.98 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 05 | T5322 | 23839545201 | 2011-07-27 | QTR1 | 11/12 | 3 | 5 | 660 | 1050 | 1050 | 140.6% | 0 | 0 | 0 | 0 | 122 | 268 | 16278889 | 200000 | 16078889 | 17781760 | 18052209 | 0 | 0 | 0 | 18052209 | 18046412 | 112.2% | 0 | -5797 | 1502871 | 84 | 38 | 0 | 2 | 181385 | 0 | 0 | 264 | 1352063 | 656900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268 | 1537048 | 656900 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-12-08 | QTR2 | 14/15 |  | 2014-07-27 | QTR1 | 14/15 | 515 | 20574418.63
| 05 | T5401 | 42201515201 | 2013-04-24 | QTR4 | 12/13 | 4 | 4 | 290 | 345 | 361 | 107.2% | 1 | -16 | 16 | 0 | 50 | 5 | 4603457 | 50000 | 4553457 | 4721215 | 4590801 | -37984 | 0 | -37984 | 4552817 | 4552297 | 99.97% | 1 | -520 | 117758 | 32 | 18 | 0 | 5 | 53464 | 12260 | 0 | 0 | 115937 | 13247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 169401 | 25507 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-02-09 | QTR3 | 14/15 |  | 2014-08-18 | QTR1 | 14/15 | 509 | 4500359.97
| 05 | T5413 | 23953525201 | 2012-04-25 | QTR4 | 11/12 | 1 | 1 | 560 | 641 | 641 | 102.1% | 1 | 0 | 0 | 0 | 69 | 12 | 7288562 | 76000 | 7212562 | 7290708 | 7262460 | 0 | 0 | 0 | 7262460 | 7196331 | 99.77% | 1 | -66129 | 2146 | 42 | 27 | 0 | 0 | 55238 | 0 | 0 | 0 | 5140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 60378 | 0 | F381818208 | DEWITT EXCAVATING INC. | N/A | N/A | N/A | N/A | 2014-08-22 | QTR1 | 14/15 |  | 2014-04-24 | QTR4 | 13/14 | 509 | 7727247.9
| 05 | T5422 | 41499915201 | 2013-03-27 | QTR3 | 12/13 | 1 | 1 | 200 | 241 | 240 | 104% | 1 | 1 | 0 | 0 | 32 | 9 | 1069577 | 43000 | 1026577 | 1147357 | 1122595 | 0 | 0 | 0 | 1122595 | 1122595 | 109.4% | 1 | 0 | 77780 | 16 | 16 | 0 | 0 | 77780 | 0 | 0 | 9 | 39527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 117307 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-12-18 | QTR2 | 14/15 |  | 2014-06-27 | QTR4 | 13/14 | 509 | 919550.79
| 05 | T5430 | 42741715201 | 2013-05-22 | QTR4 | 12/13 | 2 | 0 | 250 | 286 | 276 | 104.4% | 1 | 10 | 0 | 0 | 15 | 21 | 953616 | 42000 | 911616 | 953616 | 956091 | 0 | 0 | 0 | 956091 | 956091 | 104.9% | 1 | 0 | 0 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 21 | 7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 7577 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-08-20 | QTR1 | 14/15 |  | 2014-05-28 | QTR4 | 13/14 | 509 | 891853.25
| 05 | T5434 | 42723215201 | 2013-04-30 | QTR4 | 12/13 | 3 | 1 | 290 | 325 | 317 | 97.24% | 1 | 8 | 0 | 0 | 35 | 0 | 3828333 | 50000 | 3778333 | 3780214 | 3778884 | 0 | 0 | 0 | 3778884 | 3778736 | 100% | 1 | -148 | -48118 | 18 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | -41371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41371 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2014-11-19 | QTR2 | 14/15 |  | 2014-09-03 | QTR1 | 14/15 | 513 | 3888111 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 05 | T5444 | 42722815201 | 2013-05-22 | QTR4 | 12/13 | 2 | 5 | 380 | 477 | 477 | 100% | 1 | 0 | 0 | 0 | 97 | 0 | 6220488 | 50000 | 6170488 | 6853650 | 6842947 | 0 | 0 | 0 | 6842947 | 6847216 | 111% | 0 | 4269 | 633162 | 59 | 38 | 0 | 0 | 205611 | 0 | 0 | 0 | 93547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671405 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-03-30 | QTR3 | 14/15 |  | 2015-01-03 | QTR3 | 14/15 | 509 | 5174412.91
| 05 | T5447 | 41802015201 | 2013-03-27 | QTR3 | 12/13 | 1 | 0 | 250 | 315 | 314 | 99.6% | 1 | 1 | 0 | 0 | 65 | 0 | 1249934 | 50000 | 1199934 | 1249934 | 1221093 | 0 | 0 | 0 | 1221093 | 1221093 | 101.8% | 1 | 0 | 0 | 31 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 6376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6376 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-09-09 | QTR1 | 14/15 |  | 2014-08-11 | QTR1 | 14/15 | 513 | 1261845.5
| 05 | T5453 | 42949115201 | 2013-02-27 | QTR3 | 12/13 | 1 | 0 | 320 | 474 | 470 | 98.75% | 1 | 4 | 0 | 0 | 154 | 0 | 2793910 | 50000 | 2743910 | 2793910 | 2851601 | 0 | 0 | 0 | 2851601 | 2851571 | 103.9% | 1 | -30 | 0 | 141 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-02-13 | QTR3 | 14/15 |  | 2014-10-07 | QTR2 | 14/15 | 514 | 3153725.6
| 05 | T5470 | 43067215201 | 2013-06-19 | QTR4 | 12/13 | 1 | 1 | 330 | 344 | 303 | 87.58% | 1 | 41 | 0 | 0 | 14 | 0 | 1428196 | 50000 | 1378196 | 1456196 | 1447568 | 0 | 0 | 0 | 1447568 | 1447568 | 105% | 1 | 0 | 28000 | 9 | 5 | 0 | 0 | 3529 | 0 | 0 | 0 | 66385 | 11936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68488 | 11936 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 |  | 2014-07-21 | QTR1 | 14/15 | 509 | 1674860.83
| 05 | T5475 | 43018715201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 125 | 148 | 145 | 97.6% | 1 | 3 | 0 | 0 | 23 | 0 | 769979 | 37000 | 732979 | 769979 | 735665 | 0 | 0 | 0 | 735665 | 735665 | 100.4% | 1 | 0 | 0 | 22 | 1 | 0 | 0 | 875 | 0 | 0 | 0 | 1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2686 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-09-29 | QTR1 | 14/15 |  | 2014-06-26 | QTR4 | 13/14 | 515 | 786469.1 | B0 | ACC - LUMP SUM
| 05 | T5479 | 42887715201 | 2014-02-05 | QTR3 | 13/14 | 1 | 0 | 90 | 110 | 107 | 96.67% | 1 | 3 | 0 | 0 | 20 | 0 | 1018000 | 50000 | 968000 | 1018000 | 967574 | 0 | 0 | 0 | 967574 | 967574 | 99.96% | 1 | 0 | 0 | 18 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-12-08 | QTR2 | 14/15 |  | 2014-07-30 | QTR1 | 14/15 | 509 | 1181765.33 | B0 | ACC - LUMP SUM
| 05 | T5481 | 24099225201 | 2013-06-19 | QTR4 | 12/13 | 1 | 0 | 160 | 192 | 192 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 662854 | 23000 | 639854 | 662854 | 625918 | 0 | 0 | 0 | 625918 | 625918 | 97.82% | 1 | 0 | 0 | 13 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-07-15 | QTR1 | 14/15 |  | 2014-05-01 | QTR4 | 13/14 | 513 | 488486.9
| 05 | T5484 | 43359515201 | 2013-06-19 | QTR4 | 12/13 | 1 | 2 | 65 | 140 | 140 | 213.8% | 0 | 0 | 0 | 0 | 1 | 74 | 160823 | 11000 | 149823 | 160823 | 149823 | 0 | 0 | 0 | 149823 | 149823 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-07-22 | QTR1 | 14/15 |  | 2014-05-22 | QTR4 | 13/14 | 509 | 234402.5
| 05 | T5490 | 42893415201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 70 | 71 | 67 | 94.29% | 1 | 4 | 0 | 0 | 1 | 0 | 299220 | 16000 | 283220 | 299220 | 281239 | 0 | 0 | 0 | 281239 | 281239 | 99.3% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2014-12-05 | QTR2 | 14/15 |  | 2014-10-28 | QTR2 | 14/15 | 509 | 355403.88 | B0 | ACC - LUMP SUM
| 05 | T5505 | 43018225201 | 2014-04-30 | QTR4 | 13/14 | 1 | 1 | 30 | 47 | 40 | 96.67% | 1 | 7 | 0 | 0 | 11 | 6 | 124000 | 6000 | 118000 | 137512 | 131512 | 0 | 0 | 0 | 131512 | 131512 | 111.5% | 0 | 0 | 13512 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 13512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 13512 | 0 | F593484839 | BUILT-RITE CONSTRUCTION OF CENTRAL FLORI | N/A | N/A | N/A | N/A | 2014-09-04 | QTR1 | 14/15 |  | 2014-08-15 | QTR1 | 14/15 | 513 | 135276.27 | B0 | ACC - LUMP SUM
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 18 | 31 | 39 | 4530 | 6038 | 6249 | 77.78% | 14 | -211 | 297 | 0 | 797 | 711 | 70150955 | 989000 | 69161955 | 74694715 | 74600747 | -37984 | 0 | -37984 | 74562763 | 74494408 | 72.22% | 13 | -68355 | 4543761 | 524 | 272 | 0 | 194 | 1283703 | 55747 | 0 | 437 | 2000586 | 717051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1315291 | 73171 | 0 | 0 | 372247 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10826 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711 | 4982653 | 845970
| 05 | E5R53 | 42474415201 | 2012-10-08 | QTR2 | 12/13 | 1 | 1 | 70 | 136 | 210 | 291.4% | 0 | -74 | 74 | 0 | 66 | 0 | 1125000 | 40000 | 1085000 | 1073026 | 1032679 | -113368 | 0 | -113368 | 919311 | 919311 | 84.73% | 1 | 0 | -51974 | 4 | 2 | 0 | 0 | -51974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | -51974 | 0 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2014-11-12 | QTR2 | 14/15 |  | 2013-12-17 | QTR2 | 13/14 | 514 | 851030.88
| 05 | E5R74 | 42936215201 | 2013-06-04 | QTR4 | 12/13 | 1 | 0 | 310 | 352 | 288 | 79.35% | 1 | 64 | 0 | 0 | 42 | 0 | 2343983 | 50000 | 2293983 | 2343983 | 2295699 | 0 | 0 | 0 | 2295699 | 2295699 | 100.1% | 1 | 0 | 0 | 23 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-03-19 | QTR3 | 14/15 |  | 2014-07-08 | QTR1 | 14/15 | 514 | 1283485.96 | B0 | ACC - LUMP SUM
| 05 | E5R78 | 43106515201 | 2013-06-04 | QTR4 | 12/13 | 1 | 2 | 240 | 285 | 260 | 89.58% | 1 | 25 | 0 | 0 | 45 | 0 | 1432200 | 50000 | 1382200 | 1441797 | 1377218 | 0 | 0 | 0 | 1377218 | 1377218 | 99.64% | 1 | 0 | 9597 | 16 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 9597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9597 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2014-09-09 | QTR1 | 14/15 |  | 2014-07-24 | QTR1 | 14/15 | 513 | 2258202.53
| 05 | E5R83 | 23930415201 | 2013-06-26 | QTR4 | 12/13 | 1 | 2 | 345 | 456 | 455 | 106.4% | 1 | 1 | 0 | 0 | 101 | 10 | 10203400 | 130000 | 10073400 | 10234439 | 10164588 | 0 | 0 | 0 | 10164588 | 10184967 | 101.1% | 1 | 20379 | 31039 | 67 | 21 | 13 | 10 | 66674 | 0 | 0 | 0 | 8367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16561 | 0 | 13 | 10 | 58481 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-02-19 | QTR3 | 14/15 |  | 2014-11-25 | QTR2 | 14/15 | 515 | 13028975.6 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E5R89 | 42756215201 | 2013-05-07 | QTR4 | 12/13 | 1 | 0 | 160 | 171 | 162 | 94.38% | 1 | 9 | 0 | 0 | 11 | 0 | 1080000 | 45000 | 1035000 | 1080000 | 1147540 | 0 | 0 | 0 | 1147540 | 1147540 | 110.9% | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 10276 | 0 | 0 | 0 | 1868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12144 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-23 | QTR2 | 14/15 |  | 2014-06-16 | QTR4 | 13/14 | 515 | 978706.5
| 05 | E5W15 | 43326215201 | 2014-04-01 | QTR4 | 13/14 | 1 | 0 | 60 | 63 | 61 | 96.67% | 1 | 2 | 0 | 0 | 3 | 0 | 188644 | 11700 | 176944 | 188644 | 173944 | 0 | 0 | 0 | 173944 | 173944 | 98.3% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2014-10-06 | QTR2 | 14/15 |  | 2014-09-05 | QTR1 | 14/15 | 513 | 247000
| 05 | E5W16 | 43326515201 | 2014-04-01 | QTR4 | 13/14 | 1 | 0 | 90 | 149 | 149 | 115.6% | 1 | 0 | 0 | 0 | 45 | 14 | 155129 | 1244 | 153885 | 155129 | 165956 | 0 | 0 | 0 | 165956 | 165956 | 107.8% | 1 | 0 | 0 | 43 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-01-22 | QTR3 | 14/15 |  | 2014-11-13 | QTR2 | 14/15 | 590 | 127000
| 05 | E5W17 | 43326115201 | 2014-03-04 | QTR3 | 13/14 | 1 | 0 | 45 | 46 | 39 | 84.44% | 1 | 7 | 0 | 0 | 1 | 0 | 116628 | 5878 | 110750 | 116628 | 110750 | 0 | 0 | 0 | 110750 | 110750 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592582830 | SIEG & SONS INC. | N/A | N/A | N/A | N/A | 2014-07-03 | QTR1 | 14/15 |  | 2014-06-12 | QTR4 | 13/14 | 507 | 123784 | B0 | ACC - LUMP SUM
| 05 | E5W19 | 43107015201 | 2014-01-07 | QTR3 | 13/14 | 1 | 0 | 90 | 115 | 111 | 95.56% | 1 | 4 | 0 | 0 | 25 | 0 | 932822 | 50000 | 882822 | 932822 | 882819 | 0 | 0 | 0 | 882819 | 882819 | 100% | 1 | 0 | 0 | 23 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-09-17 | QTR1 | 14/15 |  | 2014-08-01 | QTR1 | 14/15 | 514 | 1251513.5
| 05 | E5W20 | 43353715201 | 2014-02-04 | QTR3 | 13/14 | 1 | 1 | 30 | 62 | 72 | 190% | 0 | -10 | 10 | 0 | 15 | 17 | 95060 | 2810 | 92250 | 95060 | 92250 | -8840 | 0 | -8840 | 83410 | 83410 | 90.42% | 1 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F263976898 | AMROAD LLC | N/A | N/A | N/A | N/A | 2014-12-22 | QTR2 | 14/15 |  | 2014-09-16 | QTR1 | 14/15 | 513 | 60363.9
| 05 | E5W22 | 43353815201 | 2014-02-04 | QTR3 | 13/14 | 1 | 0 | 60 | 66 | 65 | 98.33% | 1 | 1 | 0 | 0 | 6 | 0 | 87843 | 6805 | 81038 | 87843 | 81038 | 0 | 0 | 0 | 81038 | 81038 | 100% | 1 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2014-08-07 | QTR1 | 14/15 |  | 2014-07-07 | QTR1 | 14/15 | 509 | 143675
| 05 | E5W24 | 43326715201 | 2014-04-01 | QTR4 | 13/14 | 1 | 0 | 116 | 120 | 93 | 76.72% | 1 | 27 | 0 | 0 | 4 | 0 | 597000 | 50000 | 547000 | 597000 | 547000 | 0 | 0 | 0 | 547000 | 547000 | 100% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2014-10-29 | QTR2 | 14/15 |  | 2014-09-19 | QTR1 | 14/15 | 514 | 1070116
| 05 | E5W34 | 41937015201 | 2014-04-01 | QTR4 | 13/14 | 1 | 0 | 80 | 83 | 82 | 98.75% | 1 | 1 | 0 | 0 | 3 | 0 | 365000 | 23000 | 342000 | 365000 | 345289 | 0 | 0 | 0 | 345289 | 345289 | 101% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3289 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2014-09-29 | QTR1 | 14/15 |  | 2014-09-15 | QTR1 | 14/15 | 515 | 485000 | B0 | ACC - LUMP SUM
| 05 | E5W48 | 42309615201 | 2014-06-24 | QTR4 | 13/14 | 1 | 0 | 110 | 127 | 126 | 99.09% | 1 | 1 | 0 | 0 | 17 | 0 | 475755 | 19000 | 456755 | 475755 | 456755 | 0 | 0 | 0 | 456755 | 456755 | 100% | 1 | 0 | 0 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-03-10 | QTR3 | 14/15 |  | 2015-02-06 | QTR3 | 14/15 | 515 | 389710.8 | B0 | ACC - LUMP SUM
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 14 | 14 | 6 | 1806 | 2231 | 2173 | 85.71% | 12 | 58 | 84 | 0 | 384 | 41 | 19198464 | 485437 | 18713027 | 19187126 | 18873525 | -122208 | 0 | -122208 | 18751317 | 18771696 | 92.86% | 13 | 20379 | -11338 | 215 | 96 | 13 | 10 | 24976 | 0 | 0 | 17 | 24837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16561 | 0 | 73 | 41 | 33253 | 0
| District 05 Totals |  |  |  |  | 32 | 45 | 45 | 6336 | 8269 | 8422 | 81.25% | 26 | -153 | 381 | 0 | 1181 | 752 | 89349419 | 1474437 | 87874982 | 93881841 | 93474272 | -160192 | 0 | -160192 | 93314080 | 93266104 | 81.25% | 26 | -47976 | 4532423 | 739 | 368 | 13 | 204 | 1308679 | 55747 | 0 | 454 | 2025423 | 717051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 80 | 1315291 | 73171 | 0 | 0 | 372247 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10826 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16561 | 0 | 73 | 752 | 5015906 | 845970
| 06 | T6198 | 41985915201 | 2012-10-31 | QTR2 | 12/13 | 2 | 2 | 280 | 435 | 435 | 128.6% | 0 | 0 | 0 | 0 | 111 | 44 | 11628469 | 104247 | 11524222 | 11728469 | 10870085 | 0 | 0 | 0 | 10870085 | 10854373 | 94.19% | 1 | -15712 | 100000 | 56 | 19 | 36 | 0 | 21740 | 0 | 0 | 44 | 179096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 44 | 200837 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-12-18 | QTR2 | 14/15 |  | 2014-06-23 | QTR4 | 13/14 | 606 | 10326839.15
| 06 | T6219 | 41263735201 | 2011-09-28 | QTR1 | 11/12 | 3 | 2 | 320 | 412 | 411 | 99.69% | 1 | 1 | 0 | 0 | 92 | 0 | 1879940 | 50000 | 1829940 | 1901780 | 1884231 | 0 | 0 | 0 | 1884231 | 1884152 | 103% | 1 | -79 | 21840 | 74 | 18 | 0 | 0 | 34535 | 0 | 0 | 0 | 2274 | 761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55844 | 761 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2014-09-12 | QTR1 | 14/15 |  | 2013-07-19 | QTR1 | 13/14 | 606 | 2076784.7
| 06 | T6256 | 42551315201 | 2012-01-25 | QTR3 | 11/12 | 3 | 2 | 280 | 376 | 376 | 102.5% | 1 | 0 | 0 | 0 | 96 | 0 | 3491765 | 50000 | 3441765 | 3554006 | 3465121 | 0 | 0 | 0 | 3465121 | 3465336 | 100.7% | 1 | 216 | 62241 | 74 | 15 | 7 | 0 | 27522 | 0 | 0 | 0 | 33934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 61457 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-09-10 | QTR1 | 14/15 |  | 2013-08-23 | QTR1 | 13/14 | 606 | 3404006.95
| 06 | T6257 | 42514515201 | 2012-02-29 | QTR3 | 11/12 | 7 | 3 | 300 | 575 | 571 | 147% | 0 | 4 | 0 | 0 | 233 | 42 | 6803533 | 72281 | 6731252 | 6805439 | 6562695 | 0 | 0 | 0 | 6562695 | 6528724 | 96.99% | 1 | -33971 | 1906 | 96 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 35325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 42 | 7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 42 | 42399 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-01 | QTR2 | 14/15 |  | 2014-01-09 | QTR3 | 13/14 | 606 | 7124777.15
| 06 | T6274 | 42563715202 | 2012-04-25 | QTR4 | 11/12 | 3 | 1 | 220 | 356 | 356 | 100% | 1 | 0 | 0 | 0 | 136 | 0 | 3389619 | 50000 | 3339619 | 3415244 | 3434878 | 0 | 0 | 0 | 3434878 | 3408033 | 102% | 1 | -26845 | 25625 | 122 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44169 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-05 | QTR1 | 14/15 |  | 2013-09-15 | QTR1 | 13/14 | 606 | 3192722.38
| 06 | T6277 | 41247355201 | 2012-03-28 | QTR3 | 11/12 | 6 | 2 | 200 | 468 | 481 | 207% | 0 | -13 | 13 | 0 | 68 | 200 | 973813 | 39869 | 933944 | 1084662 | 1056849 | -18384 | 0 | -18384 | 1038465 | 1038465 | 111.2% | 0 | 0 | 110849 | 29 | 38 | 0 | 0 | 1804 | 0 | 0 | 0 | 37953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 80849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120606 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-09-26 | QTR1 | 14/15 |  | 2014-01-30 | QTR3 | 13/14 | 606 | 887142.75
| 06 | T6283 | 42915915201 | 2013-06-19 | QTR4 | 12/13 | 4 | 5 | 250 | 376 | 375 | 99.6% | 1 | 1 | 0 | 0 | 126 | 0 | 2420034 | 50000 | 2370034 | 2716910 | 2586180 | 0 | 0 | 0 | 2586180 | 2586385 | 109.1% | 1 | 206 | 296876 | 109 | 17 | 0 | 0 | 226424 | 0 | 0 | 0 | 65580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317311 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-03-05 | QTR3 | 14/15 |  | 2014-12-11 | QTR2 | 14/15 | 606 | 2632098.25
| 06 | T6286 | 42827915201 | 2013-02-27 | QTR3 | 12/13 | 4 | 1 | 180 | 227 | 227 | 100% | 1 | 0 | 0 | 0 | 47 | 0 | 1727127 | 120000 | 1607127 | 1737127 | 1574494 | 0 | 0 | 0 | 1574494 | 1574494 | 97.97% | 1 | 0 | 10000 | 34 | 13 | 0 | 0 | 8977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17168 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2014-07-07 | QTR1 | 14/15 |  | 2014-04-17 | QTR4 | 13/14 | 606 | 1754775.45
| 06 | T6289 | 42914415201 | 2013-04-24 | QTR4 | 12/13 | 4 | 0 | 130 | 223 | 223 | 100% | 1 | 0 | 0 | 0 | 93 | 0 | 1574706 | 50000 | 1524706 | 1574706 | 1468896 | 0 | 0 | 0 | 1468896 | 1468672 | 96.32% | 1 | -224 | 0 | 76 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15663 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-06 | QTR2 | 14/15 |  | 2014-03-22 | QTR3 | 13/14 | 606 | 1515264.75
| 06 | T6292 | 42527115201 | 2013-03-27 | QTR3 | 12/13 | 4 | 3 | 180 | 264 | 264 | 106.1% | 1 | 0 | 0 | 0 | 79 | 5 | 1776432 | 50000 | 1726432 | 1782401 | 1728838 | 0 | 0 | 0 | 1728838 | 1728477 | 100.1% | 1 | -361 | 5969 | 56 | 17 | 0 | 5 | 43189 | 26824 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 5969 | 26824 | F590895890 | WILLIAMS PAVING COMPANY INC. | N/A | N/A | N/A | N/A | 2014-07-22 | QTR1 | 14/15 |  | 2014-02-28 | QTR3 | 13/14 | 606 | 1922112.65
| 06 | T6294 | 25023635201 | 2013-02-06 | QTR3 | 12/13 | 5 | 2 | 430 | 564 | 564 | 110.5% | 1 | 0 | 0 | 0 | 104 | 30 | 6142510 | 52222 | 6090288 | 6260112 | 6132269 | 0 | 0 | 0 | 6132269 | 6128940 | 100.6% | 1 | -3329 | 117602 | 58 | 31 | 9 | 0 | 17693 | 0 | 0 | 0 | 35185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30 | 101504 | 94459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12150 | 7256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30 | 166533 | 101714 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-03-20 | QTR3 | 14/15 |  | 2014-12-18 | QTR2 | 14/15 | 606 | 5163835.05 | B1:B2 | ACC - NO EXCUSE BONUS:ACC - A+B (COST+TIME BIDDING)
| 06 | T6296 | 42848615201 | 2013-04-24 | QTR4 | 12/13 | 2 | 0 | 160 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 86 | 0 | 2559781 | 50000 | 2509781 | 2559781 | 2436245 | 0 | 0 | 0 | 2436245 | 2435764 | 97.05% | 1 | -481 | 0 | 78 | 8 | 0 | 0 | 7730 | 0 | 0 | 0 | 21328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29058 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-01-09 | QTR3 | 14/15 |  | 2014-09-15 | QTR1 | 14/15 | 606 | 2814516.15
| 06 | T6298 | 25168835201 | 2012-09-12 | QTR1 | 12/13 | 1 | 4 | 420 | 511 | 511 | 103.3% | 1 | 0 | 0 | 0 | 91 | 0 | 4246242 | 59864 | 4186378 | 4389022 | 4329187 | 0 | 0 | 0 | 4329187 | 4315357 | 103.1% | 1 | -13831 | 142780 | 62 | 15 | 0 | 0 | 97129 | 0 | 14 | 0 | 77412 | 15360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 170821 | 15360 | F650220703 | ODEBRECHT CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-10-14 | QTR2 | 14/15 |  | 2014-06-22 | QTR4 | 13/14 | 606 | 5988419.9
| 06 | T6302 | 24961485201 | 2013-02-27 | QTR3 | 12/13 | 1 | 0 | 125 | 174 | 173 | 99.2% | 1 | 1 | 0 | 0 | 49 | 0 | 1928019 | 50000 | 1878019 | 1928019 | 1840895 | 0 | 0 | 0 | 1840895 | 1839871 | 97.97% | 1 | -1023 | 0 | 46 | 3 | 0 | 0 | 35104 | 0 | 0 | 0 | 3323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38427 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-05 | QTR1 | 14/15 |  | 2013-11-08 | QTR2 | 13/14 | 606 | 2088604.55
| 06 | T6304 | 40557555201 | 2013-02-06 | QTR3 | 12/13 | 1 | 2 | 250 | 367 | 365 | 107.6% | 1 | 2 | 0 | 0 | 117 | 0 | 4441233 | 50000 | 4391233 | 4506233 | 4520669 | 0 | 0 | 0 | 4520669 | 4514737 | 102.8% | 1 | -5932 | 65000 | 80 | 16 | 0 | 0 | 40401 | 0 | 21 | 0 | 71736 | 50700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 112137 | 50700 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-23 | QTR1 | 14/15 |  | 2014-04-28 | QTR4 | 13/14 | 606 | 4729314.9
| 06 | T6306 | 42847615201 | 2012-10-31 | QTR2 | 12/13 | 2 | 0 | 170 | 237 | 237 | 100% | 1 | 0 | 0 | 0 | 67 | 0 | 1150126 | 50000 | 1100126 | 1150126 | 1099652 | 0 | 0 | 0 | 1099652 | 1097498 | 99.76% | 1 | -2153 | 0 | 60 | 7 | 0 | 0 | 12845 | 0 | 0 | 0 | 8512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21357 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-09-05 | QTR1 | 14/15 |  | 2013-09-11 | QTR1 | 13/14 | 606 | 1107477.6
| 06 | T6307 | 42751715201 | 2012-10-31 | QTR2 | 12/13 | 3 | 0 | 300 | 433 | 432 | 99.67% | 1 | 1 | 0 | 0 | 133 | 0 | 3138611 | 50000 | 3088611 | 3138611 | 3086278 | 0 | 0 | 0 | 3086278 | 3082048 | 99.79% | 1 | -4230 | 0 | 112 | 21 | 0 | 0 | 17610 | 0 | 0 | 0 | 24868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42478 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-21 | QTR1 | 14/15 |  | 2014-05-30 | QTR4 | 13/14 | 606 | 3015901.78
| 06 | T6310 | 42848415201 | 2013-05-22 | QTR4 | 12/13 | 3 | 3 | 200 | 271 | 271 | 105% | 1 | 0 | 0 | 0 | 71 | 0 | 2643396 | 51770 | 2591626 | 2747670 | 2738183 | 0 | 0 | 0 | 2738183 | 2739220 | 105.7% | 1 | 1037 | 104274 | 48 | 13 | 5 | 0 | 21554 | 0 | 5 | 0 | 110809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16249 | 10114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 148612 | 10114 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-10-30 | QTR2 | 14/15 |  | 2014-07-25 | QTR1 | 14/15 | 606 | 2596227.9
| 06 | T6317 | 42558215201 | 2013-06-19 | QTR4 | 12/13 | 1 | 1 | 150 | 177 | 175 | 98.67% | 1 | 2 | 0 | 0 | 27 | 0 | 611611 | 17500 | 594111 | 642192 | 597121 | 0 | 0 | 0 | 597121 | 597121 | 100.5% | 1 | 0 | 30581 | 14 | 13 | 0 | 0 | 19071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18415 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-07-17 | QTR1 | 14/15 |  | 2014-05-14 | QTR4 | 13/14 | 606 | 528419
| 06 | T6321 | 42914615201 | 2013-08-28 | QTR1 | 13/14 | 3 | 2 | 200 | 271 | 271 | 100% | 1 | 0 | 0 | 0 | 71 | 0 | 1568943 | 50930 | 1518013 | 1572068 | 1511503 | 0 | 0 | 0 | 1511503 | 1510404 | 99.5% | 1 | -1099 | 3125 | 66 | 5 | 0 | 0 | 834 | 0 | 0 | 0 | 8694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43828 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-02-06 | QTR3 | 14/15 |  | 2014-11-18 | QTR2 | 14/15 | 606 | 1671944.25
| 06 | T6326 | 42848025201 | 2013-06-19 | QTR4 | 12/13 | 2 | 1 | 150 | 222 | 221 | 99.33% | 1 | 1 | 0 | 0 | 72 | 0 | 598775 | 28167 | 570608 | 626792 | 663757 | 0 | 0 | 0 | 663757 | 663757 | 116.3% | 0 | 0 | 28017 | 69 | 3 | 0 | 0 | 7737 | 0 | 0 | 0 | 27937 | 6179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35674 | 6179 | F650806153 | AGC ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-10-06 | QTR2 | 14/15 |  | 2014-08-28 | QTR1 | 14/15 | 606 | 583862.15
| 06 | T6354 | 43076115201 | 2014-04-30 | QTR4 | 13/14 | 2 | 0 | 100 | 120 | 103 | 83% | 1 | 17 | 0 | 0 | 20 | 0 | 264539 | 14210 | 250329 | 264539 | 257147 | 0 | 0 | 0 | 257147 | 257147 | 102.7% | 1 | 0 | 0 | 10 | 10 | 0 | 0 | 8395 | 0 | 0 | 0 | 766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9161 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-01-30 | QTR3 | 14/15 |  | 2014-12-29 | QTR2 | 14/15 | 606 | 308910 | B0 | ACC - LUMP SUM
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 22 | 66 | 36 | 4995 | 7305 | 7288 | 86.36% | 19 | 17 | 13 | 0 | 1989 | 321 | 64959224 | 1161060 | 63798164 | 66085909 | 63845173 | -18384 | 0 | -18384 | 63826789 | 63718975 | 90.91% | 20 | -107811 | 1126685 | 1429 | 347 | 57 | 5 | 650294 | 26824 | 46 | 44 | 744732 | 73000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 272 | 310744 | 104573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12150 | 7256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 321 | 1717924 | 211652
| 06 | E6H35 | 41809425201 | 2013-06-27 | QTR4 | 12/13 | 2 | 0 | 140 | 214 | 218 | 136.4% | 0 | -4 | 4 | 0 | 62 | 12 | 647361 | 20711 | 626650 | 647361 | 646164 | -6128 | 0 | -6128 | 640036 | 640036 | 102.1% | 1 | 0 | 0 | 13 | 14 | 7 | 0 | 7322 | 0 | 28 | 12 | 12192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 12 | 19514 | 0 | F650838100 | SUPERIOR LANDSCAPING & LAWN SERVICE INC | N/A | N/A | N/A | N/A | 2015-02-10 | QTR3 | 14/15 |  | 2014-05-28 | QTR4 | 13/14 | 606 | 434916.5 | B0 | ACC - LUMP SUM
| 06 | E6H42 | 42999715201 | 2013-06-27 | QTR4 | 12/13 | 1 | 0 | 400 | 485 | 481 | 99.5% | 1 | 4 | 0 | 0 | 85 | 0 | 2888376 | 50000 | 2838376 | 2888376 | 2518315 | 0 | 0 | 0 | 2518315 | 2518314 | 88.72% | 1 | 0 | 0 | 54 | 29 | 2 | 0 | 0 | 0 | 0 | 0 | 3545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3545 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2015-03-05 | QTR3 | 14/15 |  | 2015-01-23 | QTR3 | 14/15 | 606 | 1952251.75
| 06 | E6H55 | 42999515201 | 2013-07-25 | QTR1 | 13/14 | 1 | 2 | 360 | 377 | 290 | 75.83% | 1 | 87 | 0 | 0 | 17 | 0 | 2196108 | 50000 | 2146108 | 2547091 | 2355415 | 0 | 0 | 0 | 2355415 | 2355414 | 109.8% | 1 | -1 | 350983 | 7 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356705 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-01-09 | QTR3 | 14/15 |  | 2014-12-03 | QTR2 | 14/15 | 606 | 3793360.4
| 06 | E6H89 | 42934715201 | 2013-10-31 | QTR2 | 13/14 | 2 | 0 | 140 | 185 | 185 | 103.6% | 1 | 0 | 0 | 0 | 45 | 0 | 1656869 | 10675 | 1646194 | 1656869 | 1642271 | 0 | 0 | 0 | 1642271 | 1642337 | 99.77% | 1 | 66 | 0 | 38 | 2 | 5 | 0 | 3933 | 0 | 0 | 0 | 2992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 6925 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-01-26 | QTR3 | 14/15 |  | 2014-08-06 | QTR1 | 14/15 | 606 | 1957425 | B0 | ACC - LUMP SUM
| 06 | E6I00 | 42914915201 | 2014-08-28 | QTR1 | 14/15 | 1 | 0 | 60 | 68 | 68 | 100% | 1 | 0 | 0 | 0 | 8 | 0 | 97909 | 4409 | 93500 | 97909 | 95480 | 0 | 0 | 0 | 95480 | 95480 | 102.1% | 1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2015-03-31 | QTR3 | 14/15 |  | 2015-03-13 | QTR3 | 14/15 | 606 | 92584.58 | B0 | ACC - LUMP SUM
| 06 | E6I06 | 42914315201 | 2014-01-30 | QTR3 | 13/14 | 1 | 0 | 90 | 106 | 106 | 103.3% | 1 | 0 | 0 | 0 | 16 | 0 | 511391 | 23247 | 488144 | 511391 | 492255 | 0 | 0 | 0 | 492255 | 492255 | 100.8% | 1 | 0 | 0 | 10 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-10-23 | QTR2 | 14/15 |  | 2014-09-15 | QTR1 | 14/15 | 606 | 488186.85
| 06 | E6I10 | 25168455201 | 2013-09-26 | QTR1 | 13/14 | 1 | 0 | 180 | 207 | 204 | 98.33% | 1 | 3 | 0 | 0 | 27 | 0 | 1336493 | 50000 | 1286493 | 1336493 | 1270841 | 0 | 0 | 0 | 1270841 | 1270806 | 98.78% | 1 | -35 | 0 | 24 | 3 | 0 | 0 | 2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2014-09-10 | QTR1 | 14/15 |  | 2014-07-28 | QTR1 | 14/15 | 606 | 1445286.04
| 06 | E6I12 | 43195115201 | 2013-11-21 | QTR2 | 13/14 | 1 | 0 | 100 | 172 | 171 | 99% | 1 | 1 | 0 | 0 | 72 | 0 | 328770 | 16810 | 311960 | 328770 | 319896 | 0 | 0 | 0 | 319896 | 319896 | 102.5% | 1 | 0 | 0 | 69 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-02-09 | QTR3 | 14/15 |  | 2014-11-19 | QTR2 | 14/15 | 606 | 353008.1
| 06 | E6I21 | 42914515201 | 2013-11-21 | QTR2 | 13/14 | 2 | 0 | 140 | 174 | 174 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 917461 | 45355 | 872106 | 917461 | 804065 | 0 | 0 | 0 | 804065 | 804065 | 92.2% | 1 | 0 | 0 | 30 | 4 | 0 | 0 | 8080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8080 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-10-24 | QTR2 | 14/15 |  | 2014-09-08 | QTR1 | 14/15 | 606 | 936667.9
| 06 | E6I40 | 42916235201 | 2013-08-29 | QTR1 | 13/14 | 2 | 0 | 120 | 129 | 128 | 99.17% | 1 | 1 | 0 | 0 | 9 | 0 | 876233 | 50480 | 825753 | 876233 | 842419 | 0 | 0 | 0 | 842419 | 842419 | 102% | 1 | 0 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4438 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-20 | QTR1 | 14/15 |  | 2014-05-20 | QTR4 | 13/14 | 606 | 1053760.7
| 06 | E6I41 | 42918815201 | 2014-02-27 | QTR3 | 13/14 | 2 | 1 | 180 | 220 | 160 | 66.67% | 1 | 60 | 0 | 0 | 40 | 0 | 3051904 | 51000 | 3000904 | 3101904 | 2954581 | 0 | 100000 | 100000 | 3054581 | 2976280 | 99.18% | 1 | -78302 | 50000 | 36 | 4 | 0 | 0 | 3713 | 0 | 0 | 0 | 96287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-01-13 | QTR3 | 14/15 |  | 2014-11-02 | QTR2 | 14/15 | 606 | 3242256.25 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6I50 | 43117115201 | 2014-07-31 | QTR1 | 14/15 | 1 | 0 | 80 | 100 | 89 | 86.25% | 1 | 11 | 0 | 0 | 20 | 0 | 614838 | 32795 | 582043 | 614838 | 556562 | 0 | 0 | 0 | 556562 | 556562 | 95.62% | 1 | 0 | 0 | 9 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-03-19 | QTR3 | 14/15 |  | 2015-01-07 | QTR3 | 14/15 | 606 | 688700.25
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 12 | 17 | 3 | 1990 | 2437 | 2274 | 91.67% | 11 | 163 | 4 | 0 | 435 | 12 | 15123713 | 405482 | 14718231 | 15524696 | 14498264 | -6128 | 100000 | 93872 | 14592136 | 14513864 | 100% | 12 | -78272 | 400983 | 306 | 84 | 17 | 0 | 25862 | 0 | 28 | 12 | 123384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 12 | 505951 | 0
| District 06 Totals |  |  |  |  | 34 | 83 | 39 | 6985 | 9742 | 9562 | 88.24% | 30 | 180 | 17 | 0 | 2424 | 333 | 80082937 | 1566542 | 78516395 | 81610605 | 78343437 | -24512 | 100000 | 75488 | 78418925 | 78232839 | 94.12% | 32 | -186083 | 1527668 | 1735 | 431 | 74 | 5 | 676156 | 26824 | 74 | 56 | 868116 | 73000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 272 | 667449 | 104573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12150 | 7256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257 | 333 | 2223875 | 211652
| 07 | T7145 | 25558515201 | 2011-05-25 | QTR4 | 10/11 | 3 | 4 | 880 | 1018 | 1018 | 100% | 1 | 0 | 0 | 0 | 138 | 0 | 14782862 | 150000 | 14632862 | 14840038 | 14923334 | 0 | 0 | 0 | 14923334 | 14855530 | 101.5% | 1 | -67804 | 57175 | 86 | 52 | 0 | 0 | 11606 | 0 | 0 | 0 | 159130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170736 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2015-03-04 | QTR3 | 14/15 |  | 2014-05-24 | QTR4 | 13/14 | 714 | 19051619.67
| 07 | T7215 | 25715515201 | 2011-04-27 | QTR4 | 10/11 | 4 | 14 | 775 | 875 | 875 | 102.1% | 1 | 0 | 0 | 0 | 84 | 16 | 16908928 | 150000 | 16758928 | 17117199 | 16333232 | 0 | 0 | 0 | 16333232 | 16338017 | 97.49% | 1 | 4785 | 208271 | 55 | 29 | 0 | 16 | 208072 | 2084 | 0 | 0 | 127926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -93114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 328843 | 2084 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-08-11 | QTR1 | 14/15 |  | 2013-12-23 | QTR2 | 13/14 | 709 | 16235635
| 07 | T7306 | 42152415201 | 2012-06-06 | QTR4 | 11/12 | 1 | 3 | 600 | 718 | 701 | 97.17% | 1 | 17 | 0 | 0 | 118 | 0 | 7218846 | 64000 | 7154846 | 7457221 | 7033415 | 0 | 0 | 0 | 7033415 | 7024970 | 98.18% | 1 | -8445 | 238375 | 76 | 42 | 0 | 0 | 14639 | 0 | 0 | 0 | 261306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275945 | 0 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-12-09 | QTR2 | 14/15 |  | 2014-08-05 | QTR1 | 14/15 | 717 | 6826296.6
| 07 | T7312 | 42716515201 | 2013-02-06 | QTR3 | 12/13 | 1 | 2 | 365 | 432 | 421 | 96.99% | 1 | 11 | 0 | 0 | 67 | 0 | 6969069 | 60000 | 6909069 | 7176465 | 7341593 | 0 | 0 | 0 | 7341593 | 7330210 | 106.1% | 1 | -11383 | 207396 | 47 | 20 | 0 | 0 | 3764 | 0 | 0 | 0 | 211308 | 207396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215071 | 207396 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-08-27 | QTR1 | 14/15 |  | 2014-07-08 | QTR1 | 14/15 | 717 | 6739999.01
| 07 | T7313 | 42896015201 | 2013-07-31 | QTR1 | 13/14 | 1 | 0 | 150 | 164 | 148 | 89.33% | 1 | 16 | 0 | 0 | 14 | 0 | 1385209 | 50000 | 1335209 | 1385209 | 1350699 | 0 | 0 | 0 | 1350699 | 1351385 | 101.2% | 1 | 686 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5700 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-07-11 | QTR1 | 14/15 |  | 2014-03-03 | QTR3 | 13/14 | 798 | 1507561.7 | B0 | ACC - LUMP SUM
| 07 | T7315 | 42715015201 | 2013-02-27 | QTR3 | 12/13 | 1 | 1 | 230 | 375 | 375 | 113.9% | 1 | 0 | 0 | 0 | 113 | 32 | 2464444 | 50000 | 2414444 | 2519444 | 2482385 | 0 | 0 | 0 | 2482385 | 2479294 | 102.7% | 1 | -3091 | 55000 | 90 | 23 | 0 | 3 | 23479 | 0 | 0 | 29 | 61845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 85878 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-02-17 | QTR3 | 14/15 |  | 2014-05-22 | QTR4 | 13/14 | 798 | 2475000
| 07 | T7316 | 43232815201 | 2013-03-27 | QTR3 | 12/13 | 5 | 0 | 325 | 345 | 345 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 2398657 | 50000 | 2348657 | 2398657 | 2325044 | 0 | 0 | 0 | 2325044 | 2324965 | 98.99% | 1 | -79 | 0 | 2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-07-31 | QTR1 | 14/15 |  | 2014-05-13 | QTR4 | 13/14 | 717 | 2025384
| 07 | T7318 | 42455215201 | 2013-04-24 | QTR4 | 12/13 | 3 | 1 | 220 | 335 | 335 | 100% | 1 | 0 | 0 | 0 | 115 | 0 | 5017437 | 50000 | 4967437 | 5021145 | 5017012 | 0 | 0 | 0 | 5017012 | 5015310 | 101% | 1 | -1702 | 3708 | 96 | 19 | 0 | 0 | 6938 | 0 | 0 | 0 | 7166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14104 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-10-29 | QTR2 | 14/15 |  | 2014-06-02 | QTR4 | 13/14 | 717 | 4985000 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 07 | T7319 | 42714815201 | 2013-04-24 | QTR4 | 12/13 | 2 | 0 | 200 | 274 | 283 | 104.5% | 1 | -9 | 9 | 0 | 74 | 0 | 2862257 | 50000 | 2812257 | 2862257 | 3093254 | -21366 | 0 | -21366 | 3071888 | 3071316 | 109.2% | 1 | -572 | 0 | 56 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | F900095113 | RAINEY CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-09-16 | QTR1 | 14/15 |  | 2014-04-11 | QTR4 | 13/14 | 798 | 3571073 | B0 | ACC - LUMP SUM
| 07 | T7320 | 42716215201 | 2013-05-22 | QTR4 | 12/13 | 1 | 1 | 330 | 428 | 428 | 100% | 1 | 0 | 0 | 0 | 98 | 0 | 6688741 | 60000 | 6628741 | 6711402 | 6714167 | 0 | 0 | 0 | 6714167 | 6717183 | 101.3% | 1 | 3015 | 22661 | 40 | 58 | 0 | 0 | 22661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22661 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-02-26 | QTR3 | 14/15 |  | 2014-09-30 | QTR1 | 14/15 | 709 | 6752451.38
| 07 | T7321 | 42715325201 | 2013-03-27 | QTR3 | 12/13 | 1 | 1 | 139 | 215 | 220 | 124.5% | 0 | -5 | 5 | 0 | 47 | 29 | 464335 | 19000 | 445335 | 474055 | 463114 | -4830 | 0 | -4830 | 458284 | 458284 | 102.9% | 1 | 0 | 9720 | 30 | 17 | 0 | 0 | 0 | 0 | 0 | 29 | 17079 | 9720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 17079 | 9720 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2014-07-09 | QTR1 | 14/15 |  | 2014-03-05 | QTR3 | 13/14 | 798 | 380000
| 07 | T7327 | 42900815201 | 2013-08-28 | QTR1 | 13/14 | 1 | 0 | 145 | 165 | 165 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 1393333 | 50000 | 1343333 | 1393333 | 1317331 | 0 | 0 | 0 | 1317331 | 1317300 | 98.06% | 1 | -31 | 0 | 19 | 1 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-12-30 | QTR2 | 14/15 |  | 2014-06-19 | QTR4 | 13/14 | 717 | 1390033
| 07 | T7332 | 42896615201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 100 | 172 | 172 | 100% | 1 | 0 | 0 | 0 | 72 | 0 | 1602900 | 50000 | 1552900 | 1602900 | 1581283 | 0 | 0 | 0 | 1581283 | 1581643 | 101.9% | 1 | 360 | 0 | 55 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 |  | 2014-09-06 | QTR1 | 14/15 | 717 | 1750000 | B0 | ACC - LUMP SUM
| 07 | T7333 | 25705025201 | 2013-08-28 | QTR1 | 13/14 | 1 | 0 | 90 | 191 | 191 | 195.6% | 0 | 0 | 0 | 0 | 15 | 86 | 615166 | 25000 | 590166 | 615166 | 597766 | 0 | 0 | 0 | 597766 | 597766 | 101.3% | 1 | 0 | 0 | 12 | 3 | 0 | 26 | 2255 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 2255 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2014-12-30 | QTR2 | 14/15 |  | 2014-10-14 | QTR2 | 14/15 | 714 | 588987
| 07 | T7336 | 42900715201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 70 | 81 | 81 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 899650 | 38000 | 861650 | 899650 | 831750 | 0 | 0 | 0 | 831750 | 831750 | 96.53% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-07-01 | QTR1 | 14/15 |  | 2014-03-27 | QTR3 | 13/14 | 709 | 830000 | B0 | ACC - LUMP SUM
| 07 | T7338 | 43339215201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 145 | 147 | 143 | 97.24% | 1 | 4 | 0 | 0 | 2 | 0 | 339122 | 12500 | 326622 | 339122 | 340142 | 0 | 0 | 0 | 340142 | 340142 | 104.1% | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 710 | 0 | 0 | 0 | 3769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4479 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-02-12 | QTR3 | 14/15 |  | 2014-08-20 | QTR1 | 14/15 | 717 | 334189.35
| 07 | T7342 | 43304515201 | 2014-02-05 | QTR3 | 13/14 | 1 | 0 | 105 | 111 | 66 | 57.14% | 1 | 45 | 0 | 0 | 6 | 0 | 492500 | 20000 | 472500 | 492500 | 472500 | 0 | 0 | 0 | 472500 | 472500 | 100% | 1 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-09-10 | QTR1 | 14/15 |  | 2014-06-18 | QTR4 | 13/14 | 717 | 473311 | B0 | ACC - LUMP SUM
| 07 | T7344 | 42907735201 | 2014-02-26 | QTR3 | 13/14 | 1 | 0 | 60 | 60 | 14 | 23.33% | 1 | 46 | 0 | 0 | 0 | 0 | 273786 | 5800 | 267986 | 273786 | 266951 | 0 | 0 | 0 | 266951 | 266951 | 99.61% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-01-08 | QTR3 | 14/15 |  | 2014-10-29 | QTR2 | 14/15 | 717 | 157000 | B0 | ACC - LUMP SUM
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 18 | 30 | 27 | 4929 | 6106 | 5981 | 88.89% | 16 | 125 | 14 | 0 | 1014 | 163 | 72777242 | 954300 | 71822942 | 73579549 | 72484972 | -26196 | 0 | -26196 | 72458776 | 72374516 | 100% | 18 | -84261 | 802306 | 683 | 331 | 0 | 45 | 302624 | 2084 | 0 | 118 | 855393 | 217116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 1151415 | 219200
| 07 | E7H15 | 42347915201 | 2011-04-13 | QTR4 | 10/11 | 1 | 0 | 365 | 402 | 343 | 83.84% | 1 | 59 | 0 | 0 | 37 | 0 | 1489801 | 50000 | 1439801 | 1489801 | 1397774 | 0 | 0 | 0 | 1397774 | 1397774 | 97.08% | 1 | 0 | 0 | 18 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593273147 | INLAND CONSTRUCTION AND EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-01-08 | QTR3 | 14/15 |  | 2012-06-28 | QTR4 | 11/12 | 738 | 1900000
| 07 | E7I10 | 41664135201 | 2012-08-08 | QTR1 | 12/13 | 1 | 0 | 500 | 604 | 591 | 97.4% | 1 | 13 | 0 | 0 | 104 | 0 | 2609000 | 50000 | 2559000 | 2609000 | 2539098 | 0 | 0 | 0 | 2539098 | 2539098 | 99.22% | 1 | 0 | 0 | 91 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4304 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-10-30 | QTR2 | 14/15 |  | 2014-07-10 | QTR1 | 14/15 | 738 | 2255500
| 07 | E7I12 | 42716115201 | 2013-02-13 | QTR3 | 12/13 | 1 | 2 | 250 | 291 | 291 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 3211501 | 50000 | 3161501 | 3241645 | 3087832 | 0 | 0 | 0 | 3087832 | 3087171 | 97.65% | 1 | -661 | 30144 | 24 | 17 | 0 | 0 | 7970 | 2468 | 0 | 0 | 22174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30144 | 2468 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-07-22 | QTR1 | 14/15 |  | 2014-02-25 | QTR3 | 13/14 | 709 | 2968524.2
| 07 | E7I20 | 42716015201 | 2013-05-29 | QTR4 | 12/13 | 1 | 0 | 250 | 306 | 306 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 2103847 | 50000 | 2053847 | 2103847 | 2012521 | 0 | 0 | 0 | 2012521 | 2015180 | 98.12% | 1 | 2659 | 0 | 37 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 5906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5906 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-09-08 | QTR1 | 14/15 |  | 2014-06-08 | QTR4 | 13/14 | 717 | 1798723
| 07 | E7I27 | 42470715201 | 2013-05-08 | QTR4 | 12/13 | 2 | 1 | 60 | 61 | 59 | 96.67% | 1 | 2 | 0 | 0 | 1 | 0 | 262455 | 12000 | 250455 | 288455 | 274422 | 0 | 0 | 0 | 274422 | 274422 | 109.6% | 1 | 0 | 26000 | 1 | 0 | 0 | 0 | 1756 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27756 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-07-10 | QTR1 | 14/15 |  | 2013-11-27 | QTR2 | 13/14 | 709 | 250000
| 07 | E7I65 | 42950015201 | 2013-08-14 | QTR1 | 13/14 | 2 | 0 | 120 | 154 | 153 | 107.5% | 1 | 1 | 0 | 0 | 24 | 10 | 545794 | 15000 | 530794 | 545794 | 534041 | 0 | 0 | 0 | 534041 | 534041 | 100.6% | 1 | 0 | 0 | 20 | 4 | 0 | 0 | 4095 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4095 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2014-09-03 | QTR1 | 14/15 |  | 2014-07-26 | QTR1 | 14/15 | 717 | 363220
| 07 | E7I73 | 42888215201 | 2014-03-12 | QTR3 | 13/14 | 1 | 0 | 80 | 83 | 67 | 80% | 1 | 16 | 0 | 0 | 3 | 0 | 161753 | 4000 | 157753 | 161753 | 168071 | 0 | 0 | 0 | 168071 | 168071 | 106.5% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-01-12 | QTR3 | 14/15 |  | 2014-09-04 | QTR1 | 14/15 | 717 | 90000
| 07 | E7I74 | 42888225201 | 2014-03-12 | QTR3 | 13/14 | 1 | 0 | 80 | 115 | 115 | 110% | 1 | 0 | 0 | 0 | 27 | 8 | 174384 | 8300 | 166084 | 174384 | 173484 | 0 | 0 | 0 | 173484 | 173484 | 104.5% | 1 | 0 | 0 | 23 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 7400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 7400 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2015-01-26 | QTR3 | 14/15 |  | 2014-12-02 | QTR2 | 14/15 | 709 | 180597.9
| 07 | E7I75 | 42895915201 | 2014-03-12 | QTR3 | 13/14 | 1 | 0 | 150 | 161 | 161 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 1272505 | 40000 | 1232505 | 1272505 | 1236184 | 0 | 0 | 0 | 1236184 | 1236184 | 100.3% | 1 | 0 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3679 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-02-10 | QTR3 | 14/15 |  | 2014-12-13 | QTR2 | 14/15 | 709 | 869000 | B0 | ACC - LUMP SUM
| 07 | E7I79 | 43070915201 | 2014-03-12 | QTR3 | 13/14 | 1 | 0 | 45 | 46 | 46 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 143573 | 7300 | 136273 | 143573 | 140811 | 0 | 0 | 0 | 140811 | 140811 | 103.3% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | -2075 | 0 | 0 | 0 | 6614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4538 | 0 | F593759317 | CHEYENNE ASPHALT INCORPORATED | N/A | N/A | N/A | N/A | 2014-12-30 | QTR2 | 14/15 |  | 2014-11-13 | QTR2 | 14/15 | 798 | 151900 | B0 | ACC - LUMP SUM
| 07 | E7I84 | 43253415201 | 2014-05-14 | QTR4 | 13/14 | 1 | 0 | 120 | 139 | 139 | 100% | 1 | 0 | 0 | 0 | 19 | 0 | 865555 | 50000 | 815555 | 865555 | 815555 | 0 | 0 | 0 | 815555 | 815555 | 100% | 1 | 0 | 0 | 6 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-03-09 | QTR3 | 14/15 |  | 2015-01-24 | QTR3 | 14/15 | 709 | 1222605 | B0 | ACC - LUMP SUM
| 07 | E7I86 | 43270815201 | 2014-02-12 | QTR3 | 13/14 | 1 | 1 | 140 | 242 | 211 | 77.86% | 1 | 31 | 0 | 0 | 102 | 0 | 570177 | 12500 | 557677 | 588876 | 579662 | 0 | 0 | 0 | 579662 | 579662 | 103.9% | 1 | 0 | 18699 | 60 | 42 | 0 | 0 | 3286 | 0 | 0 | 0 | 18700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21986 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-03-09 | QTR3 | 14/15 |  | 2015-02-09 | QTR3 | 14/15 | 709 | 415000
| 07 | E7J03 | 41090965201 | 2013-07-26 | QTR1 | 13/14 | 1 | 0 | 210 | 250 | 250 | 110% | 1 | 0 | 0 | 0 | 40 | 0 | 1199414 | 42000 | 1157414 | 1199414 | 1101676 | 0 | 0 | 0 | 1101676 | 1101676 | 95.18% | 1 | 0 | 0 | 7 | 12 | 0 | 0 | 4903 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 4903 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2014-09-18 | QTR1 | 14/15 |  | 2014-08-07 | QTR1 | 14/15 | 714 | 915000 | B0 | ACC - LUMP SUM
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 13 | 15 | 4 | 2370 | 2854 | 2732 | 100% | 13 | 122 | 0 | 0 | 466 | 18 | 14609759 | 391100 | 14218659 | 14684602 | 14061131 | 0 | 0 | 0 | 14061131 | 14063129 | 100% | 13 | 1998 | 74843 | 296 | 149 | 0 | 0 | 19935 | 2468 | 21 | 10 | 83644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 18 | 115282 | 2468
| District 07 Totals |  |  |  |  | 31 | 45 | 31 | 7299 | 8960 | 8713 | 93.55% | 29 | 247 | 14 | 0 | 1480 | 181 | 87387001 | 1345400 | 86041601 | 88264151 | 86546103 | -26196 | 0 | -26196 | 86519907 | 86437645 | 100% | 31 | -82263 | 877149 | 979 | 480 | 0 | 45 | 322559 | 4552 | 21 | 128 | 939037 | 217116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | -80856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 181 | 1266697 | 221668
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8L44 | 42615515201 | 2011-06-14 | QTR4 | 10/11 | 4 | 8 | 505 | 662 | 662 | 110.9% | 1 | 0 | 0 | 0 | 102 | 55 | 12289957 | 104315 | 12185642 | 10231956 | 9993214 | 0 | 0 | 0 | 9993214 | 9995692 | 82.03% | 1 | 2477 | -2058001 | 64 | 38 | 0 | 55 | -2248071 | 0 | 0 | 0 | 62314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | -1990939 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-10-10 | QTR2 | 14/15 |  | 2013-08-14 | QTR1 | 13/14 | 854 | 10562969.59
| 08 | E8M46 | 42732415201 | 2013-02-26 | QTR3 | 12/13 | 2 | 8 | 380 | 465 | 458 | 105.8% | 1 | 7 | 0 | 0 | 56 | 29 | 5445620 | 56515 | 5389105 | 6044163 | 6171776 | 0 | 0 | 0 | 6171776 | 6166359 | 114.4% | 0 | -5417 | 598543 | 29 | 27 | 0 | 29 | 599131 | 113574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50320 | 14174 | 0 | 0 | 0 | 0 | 0 | 0 | -15753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 633698 | 127747 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-12-09 | QTR2 | 14/15 |  | 2014-08-29 | QTR1 | 14/15 | 854 | 5468996.15
| 08 | E8M61 | 42815415201 | 2013-03-12 | QTR3 | 12/13 | 1 | 1 | 285 | 360 | 360 | 111.6% | 1 | 0 | 0 | 0 | 65 | 10 | 3237604 | 50000 | 3187604 | 3287206 | 3085111 | 0 | 0 | 0 | 3085111 | 3085111 | 96.78% | 1 | 0 | 49603 | 24 | 18 | 0 | 7 | 38970 | 0 | 0 | 3 | 18135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 10 | 57104 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2014-07-18 | QTR1 | 14/15 |  | 2014-05-27 | QTR4 | 13/14 | 854 | 4295669.25
| 08 | E8M79 | 43107915201 | 2013-04-09 | QTR4 | 12/13 | 2 | 1 | 270 | 316 | 316 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 6589154 | 84145 | 6505009 | 6599869 | 6691510 | -10000 | 0 | -10000 | 6681510 | 6680921 | 102.7% | 1 | -590 | 10715 | 27 | 19 | 0 | 0 | 10649 | 0 | 0 | 0 | 16362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31470 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-01-13 | QTR3 | 14/15 |  | 2014-05-19 | QTR4 | 13/14 | 854 | 8498964.05
| 08 | E8N06 | 43245615201 | 2014-02-18 | QTR3 | 13/14 | 1 | 1 | 140 | 159 | 138 | 85% | 1 | 21 | 0 | 0 | 19 | 0 | 2777072 | 50000 | 2727072 | 2677984 | 2402653 | 0 | 0 | 0 | 2402653 | 2405693 | 88.22% | 1 | 3040 | -99088 | 13 | 6 | 0 | 0 | 35151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56321 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 |  | 2014-09-19 | QTR1 | 14/15 | 854 | 3098705.3
| 08 | E8N07 | 42933315201 | 2013-11-12 | QTR2 | 13/14 | 1 | 0 | 140 | 187 | 187 | 100% | 1 | 0 | 0 | 0 | 47 | 0 | 994390 | 43390 | 951000 | 994390 | 970021 | 0 | 0 | 0 | 970021 | 970021 | 102% | 1 | 0 | 0 | 36 | 11 | 0 | 0 | 11179 | 0 | 0 | 0 | 13828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25007 | 0 | F263435185 | ENGECON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-12 | QTR2 | 14/15 |  | 2014-10-17 | QTR2 | 14/15 | 854 | 911270.35
| 08 | E8N16 | 42897315201 | 2014-03-11 | QTR3 | 13/14 | 1 | 0 | 190 | 203 | 135 | 64.21% | 1 | 68 | 0 | 0 | 13 | 0 | 341935 | 21935 | 320000 | 341935 | 320243 | 0 | 0 | 0 | 320243 | 320243 | 100.1% | 1 | 0 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2014-12-15 | QTR2 | 14/15 |  | 2014-10-28 | QTR2 | 14/15 | 854 | 460675.05 | B0 | ACC - LUMP SUM
| 08 | E8N22 | 42902515201 | 2014-01-14 | QTR3 | 13/14 | 2 | 2 | 150 | 222 | 222 | 116.7% | 1 | 0 | 0 | 0 | 47 | 25 | 3404444 | 50000 | 3354444 | 4367288 | 4369052 | 0 | 0 | 0 | 4369052 | 4371216 | 130.3% | 0 | 2163 | 962844 | 37 | 10 | 0 | 0 | 13264 | 0 | 0 | 21 | 967946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 981210 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-03-13 | QTR3 | 14/15 |  | 2014-10-31 | QTR2 | 14/15 | 854 | 3784112.76
| 08 | E8N27 | 43368915201 | 2014-05-20 | QTR4 | 13/14 | 1 | 0 | 150 | 177 | 176 | 99.33% | 1 | 1 | 0 | 0 | 27 | 0 | 370616 | 14964 | 355652 | 370616 | 360379 | 0 | 0 | 0 | 360379 | 360379 | 101.3% | 1 | 0 | 0 | 11 | 16 | 0 | 0 | 1094 | 0 | 0 | 0 | 3632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726 | 0 | F650546351 | MANCIL'S TRACTOR SERVICE INC. | N/A | N/A | N/A | N/A | 2015-03-19 | QTR3 | 14/15 |  | 2015-02-09 | QTR3 | 14/15 | 854 | 314246.78 | B0 | ACC - LUMP SUM
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 9 | 15 | 21 | 2210 | 2751 | 2654 | 0.002365% | 9 | 97 | 0 | 0 | 422 | 119 | 35450792 | 475264 | 34975528 | 34915407 | 34363959 | -10000 | 0 | -10000 | 34353959 | 34355635 | 77.78% | 7 | 1673 | -535384 | 250 | 149 | 0 | 91 | -1538633 | 113574 | 0 | 24 | 1082217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 4 | 158126 | 14174 | 0 | 0 | 243 | 0 | 0 | 0 | -15753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 119 | -313802 | 127747
| District 08 Totals |  |  |  |  | 9 | 15 | 21 | 2210 | 2751 | 2654 | 100% | 9 | 97 | 0 | 0 | 422 | 119 | 35450792 | 475264 | 34975528 | 34915407 | 34363959 | -10000 | 0 | -10000 | 34353959 | 34355635 | 77.78% | 7 | 1673 | -535384 | 250 | 149 | 0 | 91 | -1538633 | 113574 | 0 | 24 | 1082217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 4 | 158126 | 14174 | 0 | 0 | 243 | 0 | 0 | 0 | -15753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 119 | -313802 | 127747
| Statewide Central Let Contracts SubTotal |  |  |  |  | 157 | 248 | 241 | 36303 | 48328 | 48488 | 85.99% | 135 | -160 | 1141 | 0 | 8902 | 3123 | 532792068 | 7615241 | 525176825 | 545053904 | 538206928 | -1858346 | 537500 | -1320846 | 536886082 | 540554756 | 89.81% | 141 | 3668673 | 12261837 | 6106 | 2331 | 130 | 756 | 5369358 | 189125 | 113 | 1384 | 4871212 | 1994615 | 0 | 0 | 568 | 0 | 0 | 0 | -97547 | 0 | 0 | 0 | 8000 | 0 | 109 | 648 | 3083910 | 530590 | 0 | 0 | 523597 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 117345 | 0 | 0 | 273 | 1551188 | 35660 | 18 | 43 | 62384 | 46464 | 0 | 0 | 0 | 0 | 0 | -10 | -408116 | 0 | 370 | 3121 | 15081905 | 2796455
| Statewide District Let Contracts SubTotal |  |  |  |  | 116 | 157 | 83 | 21097 | 25818 | 24789 | 93.1% | 108 | 1029 | 188 | 0 | 3909 | 812 | 316920347 | 4115395 | 312804951 | 320448949 | 316421062 | -275694 | 100000 | -175694 | 316245368 | 317706890 | 92.24% | 107 | 1461519 | 3528606 | 2561 | 1042 | 40 | 332 | 1378739 | 170695 | 126 | 289 | 2359698 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 107 | 231 | 877684 | 14174 | 0 | 0 | 8089 | 0 | 0 | 0 | -15753 | 0 | 0 | 0 | 74726 | 0 | 0 | 0 | 62038 | 34816 | 21 | 0 | 15622 | 3579 | 0 | 0 | 0 | 0 | 0 | 0 | -29575 | 0 | 294 | 852 | 4780767 | 224088
| Statewide Totals |  |  |  |  | 273 | 405 | 324 | 57400 | 74146 | 73277 | 89.01% | 243 | 869 | 1329 | 0 | 12811 | 3935 | 849712415 | 11730636 | 837981776 | 865502853 | 854627990 | -2134040 | 637500 | -1496540 | 853131450 | 858261646 | 90.84% | 248 | 5130192 | 15790443 | 8667 | 3373 | 170 | 1088 | 6748097 | 359820 | 239 | 1673 | 7230910 | 1995440 | 0 | 0 | 568 | 0 | 0 | 0 | -97547 | 0 | 0 | 0 | 57500 | 0 | 216 | 879 | 3961594 | 544764 | 0 | 0 | 531686 | 0 | 0 | 0 | -15753 | 0 | 0 | 27 | 192071 | 0 | 0 | 273 | 1613226 | 70476 | 39 | 43 | 78006 | 50043 | 0 | 0 | 0 | 0 | 0 | -10 | -437691 | 0 | 664 | 3973 | 19862672 | 3020543

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1J73 | 41473015201 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2012-02-16 | 20657452 | 20909917 | 20769992 | 252465.12 | 0 | 20769992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20769992 | 20769992 | 0 | 30061049 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
1 | E1K49 | 43013915201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2012-01-30 | 1330800 | 1196714 | 1137129 | -134085.93 | -105708 | 1034934 | -105708 | 0 | 0 | 0 | 0 | 0 | -105708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105708 | 1031421 | 1034934 | 3513 | 1710449 | A3:B0:A3:B:A:B0 | ICC - DESIGN/BUILD - MINOR:ACC - LUMP SUM:ICC - DESIGN/BUILD - MINOR:ACC - LUMP SUM:ICC - DESIGN/BUILD - MINOR:ACC - LUMP SUM
1 | E1K74 | 42893715201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2012-05-31 | 5688000 | 5688000 | 5635501 | 0 | 0 | 5629901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5635501 | 5629901 | -5600 | 5906610 | A3 | ICC - DESIGN/BUILD - MINOR
1 | E1L10 | 43171315201 | F593273147 | INLAND CONSTRUCTION AND EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2013-01-17 | 1963030 | 1963030 | 1915078 | 0 | 0 | 1915078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1915078 | 1915078 | 0 | 2035342
1 | E1L18 | 42987915201 | F760715786 | F.W.A.K. INC. | N/A | N/A | N/A | N/A | 2012-11-15 | 96622 | 96622 | 82079 | 0 | -2274 | 79805 | -2274 | 0 | 0 | 0 | 0 | 0 | -2274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2274 | 79805 | 79805 | 0 | 95069 | B0 | ACC - LUMP SUM
1 | E1L70 | 43142915201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2013-02-15 | 910918 | 1021501 | 1004565 | 110582.72 | 0 | 1005491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1004565 | 1005491 | 926 | 903190 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
1 | E1M02 | 43266015201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2013-06-06 | 1799250 | 1909786 | 1863529 | 110536.22 | 0 | 1864315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1863529 | 1864315 | 786 | 2081874 | A3:A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
1 | E1M14 | 43249315201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2013-06-20 | 1576687 | 1621260 | 1573398 | 44573.06 | 0 | 1573845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573398 | 1573845 | 447 | 1611119 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1M36 | 42913015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-01-16 | 988135 | 988135 | 965889 | 0 | 0 | 965889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965889 | 965889 | 0 | 1182267 | B0 | ACC - LUMP SUM
1 | E1M38 | 42365015201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-02-20 | 339276 | 339276 | 321083 | 0 | 0 | 321083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321083 | 321083 | 0 | 256513
1 | E1M39 | 42911725201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2013-08-15 | 1060000 | 1070443 | 1033120 | 10443.39 | 0 | 1033120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1033120 | 1033120 | 0 | 1127478 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | E1M52 | 42909415201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2013-11-21 | 597931 | 600134 | 594316 | 2203.52 | 0 | 594316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594316 | 594316 | 0 | 608071 | B0 | ACC - LUMP SUM
1 | E1M72 | 43385115201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2013-06-20 | 272547 | 277963 | 266070 | 5415.96 | -24150 | 252913 | -24150 | 0 | 0 | 0 | 0 | 0 | -24150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24150 | 241920 | 252913 | 10993 | 279217 | B0 | ACC - LUMP SUM
1 | E1N01 | 43403615201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2013-12-19 | 555692 | 555692 | 531495 | 0 | 0 | 531495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531495 | 531495 | 0 | 615008 | B0 | ACC - LUMP SUM
1 | E1N06 | 43193915201 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2014-02-20 | 1230923 | 1239584 | 1229167 | 8661.3 | 0 | 1229167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1229167 | 1229167 | 0 | 1068146
1 | E1N07 | 43109115201 | F593674850 | LAS CONTRACTING CORP | N/A | N/A | N/A | N/A | 2014-03-20 | 98451 | 100138 | 94687 | 1687.11 | 0 | 94687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94687 | 94687 | 0 | 116821 | B0 | ACC - LUMP SUM
1 | E1N09 | 42524415201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-06-19 | 862415 | 862415 | 828878 | 0 | -5226 | 823652 | -5226 | 0 | 0 | 0 | 0 | 0 | -5226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5226 | 823652 | 823652 | 0 | 694288 | B0 | ACC - LUMP SUM
1 | E1N10 | 43445815201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-06-19 | 272420 | 272420 | 263758 | 0 | 0 | 263758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263758 | 263758 | 0 | 173259 | A4 | ICC - LUMP SUM
1 | E1N22 | 42914815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-11-21 | 2271958 | 2271958 | 2273965 | 0 | 0 | 2281618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2273965 | 2281618 | 7653 | 2565542 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | E1N37 | 43384815201 | F593586613 | EVANS CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-06-19 | 308905 | 308905 | 296513 | 0 | 0 | 296513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296513 | 296513 | 0 | 205804
1 | E1N38 | 43445915201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2014-06-19 | 133143 | 133143 | 126188 | 0 | 0 | 126188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126188 | 126188 | 0 | 124659
1 | E1N41 | 43469815201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2014-06-19 | 110272 | 110272 | 88947 | 0 | 0 | 88947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88947 | 88947 | 0 | 131178
1 | E1N68 | 19541665201 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2014-07-17 | 50855 | 50855 | 46429 | 0 | 0 | 46429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46429 | 46429 | 0 | 85199 | B0 | ACC - LUMP SUM
1 | E1N69 | 41612035201 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2014-08-29 | 121546 | 121546 | 110400 | 0 | 0 | 110400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110400 | 110400 | 0 | 183400 | B0 | ACC - LUMP SUM
1 | E1N97 | 43193815202 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-08-06 | 1590000 | 1590000 | 1590000 | 0 | 0 | 1590000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1590000 | 1590000 | 0 | 1300000 | B0 | ACC - LUMP SUM
1 | T1329 | 19571915201 | Z91-0742148 | SAFECO INSURANCE COMPANY OF AMERICA | N/A | N/A | N/A | N/A | 2009-06-17 | 29755075 | 30577699 | 30629189 | 822623.58 | -1246694 | 31496712 | -1246694 | 0 | 0 | 0 | 0 | 0 | -1246694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1246694 | 29382495 | 31496712 | 2114217 | 42389867 | ARRA | AMERICAN RECOVERY AND REINVEST
1 | T1389 | 41549015201 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2010-07-28 | 13850596 | 14203576 | 13918706 | 352980.43 | -198000 | 14530532 | -198000 | 0 | 0 | 0 | 0 | 0 | -198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -198000 | 13720706 | 14530532 | 809826 | 20340424
1 | T1403 | 19448515201 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2011-05-25 | 10008331 | 10076101 | 9902773 | 67769.67 | 0 | 9879607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9902773 | 9879607 | -23166 | 9984034
1 | T1407 | 19576515201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2010-09-29 | 14220849 | 15022102 | 14932461 | 801252.71 | 0 | 15371000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14932461 | 15371000 | 438539 | 11264597
1 | T1463 | 41736515201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2011-06-22 | 9540474 | 9918837 | 9702547 | 378363.58 | 0 | 9701892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9702547 | 9701892 | -656 | 8323801
1 | T1477 | 19541645201 | F650507332 | GUYMANN CONSTRUCTION OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2012-04-25 | 10956198 | 10957630 | 11051551 | 1431.56 | 0 | 11065769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11051551 | 11065769 | 14218 | 10699279
1 | T1506 | 40828625201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2012-06-06 | 9404527 | 7654956 | 7289541 | -1749571.01 | 0 | 7297926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7289541 | 7297926 | 8385 | 9118320
1 | T1531 | 42952615201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2013-03-06 | 2149000 | 2142630 | 2134577 | -6369.73 | -108772 | 2025601 | -108772 | 0 | 0 | 0 | 0 | 0 | -108772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -108772 | 2025805 | 2025601 | -204 | 1997240 | B0 | ACC - LUMP SUM
1 | T1536 | 41369515201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2013-04-24 | 8076913 | 8251439 | 8211651 | 174526.82 | 0 | 8208595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8211651 | 8208595 | -3056 | 8781655
1 | T1537 | 42731015201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2013-09-25 | 934511 | 934511 | 907315 | 0 | 0 | 907315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907315 | 907315 | 0 | 797883 | B0 | ACC - LUMP SUM
1 | T1542 | 42997715201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 1021641 | 957447 | 916780 | -64194.4 | 0 | 916780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 916780 | 916780 | 0 | 1259553 | B0 | ACC - LUMP SUM
1 | T1547 | 42981815201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2013-09-25 | 171010 | 193060 | 193060 | 22050.39 | 0 | 193060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193060 | 193060 | 0 | 221957 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1549 | 43085615201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2013-08-28 | 313880 | 322391 | 310411 | 8510.56 | 0 | 310411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310411 | 310411 | 0 | 217061 | B0 | ACC - LUMP SUM
1 | T1555 | 42910015201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2013-07-31 | 6125184 | 6125184 | 6180641 | 0 | 0 | 6186013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6180641 | 6186013 | 5372 | 5960563 | B0 | ACC - LUMP SUM
1 | T1556 | 42911915201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2013-08-28 | 984307 | 984307 | 950925 | 0 | 0 | 950925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950925 | 950925 | 0 | 1028679 | B0 | ACC - LUMP SUM
1 | T1558 | 42949015201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 2007732 | 2007732 | 1957732 | 0 | 0 | 1957732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1957732 | 1957732 | 0 | 3091367 | B0 | ACC - LUMP SUM
1 | T1563 | 42984215201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2013-05-22 | 276962 | 290055 | 290055 | 13092.89 | 0 | 290055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290055 | 290055 | 0 | 311948 | B0 | ACC - LUMP SUM
1 | T1564 | 43336015201 | F593315987 | TUCKER PAVING INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 249571 | 249571 | 238480 | 0 | 0 | 238480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238480 | 238480 | 0 | 170338 | B0 | ACC - LUMP SUM
1 | T1568 | 42910215201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2013-09-25 | 2155214 | 2155214 | 2109493 | 0 | 0 | 2109463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2109493 | 2109463 | -30 | 2139343 | B0 | ACC - LUMP SUM
1 | T1571 | 43085815201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-09-25 | 434987 | 434987 | 424777 | 0 | 0 | 424777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424777 | 424777 | 0 | 326383 | B0 | ACC - LUMP SUM
1 | T1572 | 42954715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2013-10-30 | 7786232 | 7442764 | 7487178 | -343467.34 | 0 | 7454628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7487178 | 7454628 | -32550 | 7638958 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
1 | T1573 | 42542615201 | F650167126 | J. MORI PAINTING INC. | N/A | N/A | N/A | N/A | 2013-10-30 | 235732 | 235732 | 223084 | 0 | 0 | 223084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223084 | 223084 | 0 | 507871 | B0 | ACC - LUMP SUM
1 | T1574 | 43092915201 | F593315987 | TUCKER PAVING INC. | N/A | N/A | N/A | N/A | 2013-10-30 | 246539 | 246539 | 234726 | 0 | 0 | 234726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234726 | 234726 | 0 | 243728 | B0 | ACC - LUMP SUM
1 | T1575 | 43112215201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2013-10-30 | 962381 | 965823 | 931845 | 3441.95 | 0 | 931845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931845 | 931845 | 0 | 912556 | B0 | ACC - LUMP SUM
1 | T1579 | 43086415201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 688541 | 688541 | 661017 | 0 | 0 | 661017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661017 | 661017 | 0 | 402513 | B0 | ACC - LUMP SUM
1 | T1580 | 43093015201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2013-12-04 | 669283 | 669283 | 643179 | 0 | 0 | 643179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643179 | 643179 | 0 | 598937 | B0 | ACC - LUMP SUM
1 | T1581 | 43086315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 796613 | 796613 | 781655 | 0 | 0 | 781655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781655 | 781655 | 0 | 729582 | B0 | ACC - LUMP SUM
1 | T1582 | 42814415201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2014-06-18 | 783214 | 763901 | 763901 | -19312.41 | 0 | 763901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763901 | 763901 | 0 | 863965 | B0 | ACC - LUMP SUM
1 | T1584 | 42911515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-03-26 | 2020000 | 2020000 | 1989315 | 0 | -8000 | 1988085 | 0 | 0 | 0 | 0 | 0 | -8000 | -8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8000 | 1981315 | 1988085 | 6770 | 2239271 | B0 | ACC - LUMP SUM
1 | T1586 | 43085915201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-03-26 | 515545 | 515545 | 504315 | 0 | 0 | 504315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504315 | 504315 | 0 | 471360 | B0 | ACC - LUMP SUM
1 | T1A00 | 43091715201 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2014-09-24 | 52640 | 52640 | 52640 | 0 | 0 | 52640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52640 | 52640 | 0 | 53596 | B0 | ACC - LUMP SUM
1 | T1A03 | 42989515201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2014-07-30 | 223166 | 223166 | 211557 | 0 | 0 | 211557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211557 | 211557 | 0 | 201007 | B0 | ACC - LUMP SUM
1 | T1A08 | 42825415201 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 93337 | 93337 | 93337 | 0 | 0 | 93337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93337 | 93337 | 0 | 112934 | B0 | ACC - LUMP SUM
1 | T1A10 | 42825215201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2014-08-27 | 167341 | 167341 | 167341 | 0 | 0 | 167341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167341 | 167341 | 0 | 207740 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
2 | E2P13 | 20954555201 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2011-09-22 | 30532000 | 30924278 | 30907321 | 392278.05 | 0 | 30898233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30907321 | 30898233 | -9088 | 34254654 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2R03 | 20837135201 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2013-04-17 | 1823323 | 1823323 | 1649161 | 0 | 0 | 1649160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649161 | 1649160 | -1 | 2547673
2 | E2R90 | 20971015201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2014-05-14 | 141019 | 153230 | 151100 | 12210.4 | 0 | 151100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151100 | 151100 | 0 | 186564 | B0 | ACC - LUMP SUM
2 | E2S03 | 42870215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-09-18 | 2539934 | 2539934 | 2563383 | 0 | 0 | 2562645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2563383 | 2562645 | -738 | 2390761 | B0 | ACC - LUMP SUM
2 | E2S34 | 42869315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-03-19 | 2053370 | 2053370 | 1811375 | 0 | 0 | 1821200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1811375 | 1821200 | 9826 | 1709666
2 | E2T05 | 43055015201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2014-07-23 | 1656117 | 1656117 | 1659137 | 0 | 0 | 1659137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659137 | 1659137 | 0 | 1793903
2 | T2359 | 21321725201 | F060613324 | COSTELLO INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2010-12-01 | 12480050 | 12930758 | 12778436 | 450708.16 | 0 | 12996044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12778436 | 12996044 | 217607 | 18609389
2 | T2398 | 21087325201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2011-06-22 | 10935162 | 12563524 | 12687376 | 1628361.76 | 0 | 12686893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12687376 | 12686893 | -483 | 15856090
2 | T2413 | 42930415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2012-06-20 | 13231111 | 13231111 | 13309354 | 0 | -36992 | 13309528 | -36992 | 0 | 0 | 0 | 0 | 0 | -36992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36992 | 13272362 | 13309528 | 37166 | 15830196
2 | T2446 | 21324345201 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2012-10-31 | 745411 | 745411 | 704271 | 0 | 0 | 704271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704271 | 704271 | 0 | 770858
2 | T2452 | 42880915201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2013-02-27 | 11661112 | 11812236 | 12453297 | 151124.35 | 0 | 12453297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12453297 | 12453297 | 0 | 12368561
2 | T2453 | 42448515201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2013-02-06 | 2940728 | 2984001 | 3277616 | 43273.02 | 0 | 3276755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3277616 | 3276755 | -860 | 2955857
2 | T2457 | 42430815201 | F592655272 | WESTWIND CONTRACTING INC. | N/A | N/A | N/A | N/A | 2013-03-27 | 1161902 | 1273448 | 1280373 | 111545.72 | -49024 | 1231349 | -49024 | 0 | 0 | 0 | 0 | 0 | -49024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49024 | 1231349 | 1231349 | 0 | 1200431
2 | T2464 | 21053845201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-03-27 | 1105370 | 1105370 | 1123305 | 0 | 0 | 1123304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123305 | 1123304 | -1 | 966213
2 | T2472 | 42880615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2013-07-31 | 7300000 | 7300000 | 6704150 | 0 | 0 | 6712214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6704150 | 6712214 | 8064 | 7992248
2 | T2480 | 42604715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 2486826 | 2486826 | 2347817 | 0 | 0 | 2349225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2347817 | 2349225 | 1409 | 2545336
2 | T2481 | 43007015201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2013-10-30 | 369584 | 369584 | 361862 | 0 | 0 | 361862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361862 | 361862 | 0 | 377574
2 | T2483 | 42969415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 2122783 | 2122783 | 2066520 | 0 | 0 | 2066520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2066520 | 2066520 | 0 | 2033285
2 | T2486 | 42969615201 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2013-09-25 | 213201 | 213201 | 201739 | 0 | 0 | 201739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201739 | 201739 | 0 | 235867
2 | T2487 | 42975115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2013-08-28 | 1948203 | 1958517 | 1898534 | 10314 | 0 | 1898509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898534 | 1898509 | -25 | 1983074
2 | T2490 | 42975235201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 1344082 | 1461903 | 1449421 | 117820.78 | 0 | 1449421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1449421 | 1449421 | 0 | 1036542 | B0 | ACC - LUMP SUM
2 | T2494 | 42720415201 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2013-07-31 | 939461 | 967572 | 911204 | 28111.21 | 0 | 911204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911204 | 911204 | 0 | 854058
2 | T2495 | 42870815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 4543998 | 4593998 | 4820212 | 50000 | 0 | 4818947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4820212 | 4818947 | -1265 | 5010886
2 | T2497 | 43091915201 | F161659018 | CORE CONSTRUCTION COMPANY OF JACKSONVILL | N/A | N/A | N/A | N/A | 2013-10-30 | 337196 | 426661 | 390457 | 89464.7 | -1932 | 388525 | -1932 | 0 | 0 | 0 | 0 | 0 | -1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1932 | 388525 | 388525 | 0 | 355119
2 | T2501 | 42445115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-10-30 | 2399105 | 2399105 | 2283379 | 0 | 0 | 2284817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283379 | 2284817 | 1438 | 2180140
2 | T2502 | 42889715201 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2013-10-30 | 343355 | 343355 | 318751 | 0 | 0 | 318751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318751 | 318751 | 0 | 405708
2 | T2504 | 42869115201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2013-10-30 | 619867 | 697349 | 706524 | 77482 | 0 | 706524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706524 | 706524 | 0 | 669835
2 | T2507 | 43225415201 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 248683 | 249718 | 249718 | 1035 | 0 | 249718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249718 | 249718 | 0 | 274894 | B0 | ACC - LUMP SUM
2 | T2509 | 43051515201 | F452181662 | ADVANTA ASPHALT INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 138499 | 138499 | 138499 | 0 | 0 | 138499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138499 | 138499 | 0 | 180396 | B0 | ACC - LUMP SUM
2 | T2511 | 43224815201 | F452181662 | ADVANTA ASPHALT INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 59893 | 59893 | 56399 | 0 | 0 | 56399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56399 | 56399 | 0 | 76063 | B0 | ACC - LUMP SUM
2 | T2518 | 43477515201 | F593564392 | RICHARDSON SITE PREP INC. | N/A | N/A | N/A | N/A | 2014-02-05 | 84224 | 84224 | 84224 | 0 | 0 | 84224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84224 | 84224 | 0 | 176770 | B0 | ACC - LUMP SUM
2 | T2519 | 43335815201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-03-26 | 402306 | 402306 | 387767 | 0 | 0 | 387767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387767 | 387767 | 0 | 335958 | B0 | ACC - LUMP SUM
2 | T2521 | 43224415201 | F593564392 | RICHARDSON SITE PREP INC. | N/A | N/A | N/A | N/A | 2014-02-26 | 109680 | 109680 | 104316 | 0 | 0 | 104316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104316 | 104316 | 0 | 114968 | B0 | ACC - LUMP SUM
2 | T2525 | 42476715201 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2014-05-07 | 101692 | 110228 | 104725 | 8535.2 | 0 | 104725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104725 | 104725 | 0 | 119254 | B0 | ACC - LUMP SUM
2 | T2540 | 4328234G201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 344794 | 344794 | 360786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360786 | 0 | -360786 | 230306
2 | T2549 | 43551015201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-06-18 | 1205130 | 1205130 | 1163672 | 0 | 0 | 1163672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163672 | 1163672 | 0 | 982530
3 | E3K71 | 42694915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-10-10 | 1995786 | 1995786 | 1979207 | 0 | 0 | 1982470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1979207 | 1982470 | 3263 | 2340966
3 | E3L10 | 41557525201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2013-03-14 | 533421 | 735554 | 237341 | 202132.67 | 0 | 237341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237341 | 237341 | 0 | 782055
3 | E3L32 | 22283225201 | F593428518 | MARSHALL BROTHERS CONSTRUCTION & ENGINEE | N/A | N/A | N/A | N/A | 2014-01-09 | 292884 | 292884 | 288038 | 0 | 0 | 288038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288038 | 288038 | 0 | 266061
3 | E3L65 | 42357745201 | F593428518 | MARSHALL BROTHERS CONSTRUCTION & ENGINEE | N/A | N/A | N/A | N/A | 2014-05-08 | 311461 | 311461 | 300000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 | 240688
3 | E3L96 | 41767735201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2013-11-14 | 82868 | 82868 | 80578 | 0 | 0 | 80578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80578 | 80578 | 0 | 48100
3 | E3M21 | 42187825201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-01-09 | 842964 | 842964 | 857292 | 0 | 0 | 857292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857292 | 857292 | 0 | 838556
3 | E3M23 | 42695815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-01-09 | 1549934 | 1549934 | 1527279 | 0 | 0 | 1527279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1527279 | 1527279 | 0 | 1966886 | B0 | ACC - LUMP SUM
3 | E3M24 | 42693315201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2013-12-12 | 3867191 | 4050762 | 4276825 | 183571.02 | 0 | 4245773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4276825 | 4245773 | -31052 | 4425803
3 | E3M35 | 42543325201 | F453031471 | LIVE OAK MANAGEMENT GROUP L.L.C. | N/A | N/A | N/A | N/A | 2014-04-10 | 58110 | 58110 | 55571 | 0 | 0 | 55571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55571 | 55571 | 0 | 53309
3 | E3M36 | 21934425201 | F522182511 | GULF COAST UTILITY CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2014-03-13 | 268872 | 310112 | 294768 | 41240 | 0 | 294768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294768 | 294768 | 0 | 322224
3 | E3M39 | 42188935201 | F591565266 | MCCORMICK CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2014-03-13 | 41842 | 41842 | 48742 | 0 | 0 | 48742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48742 | 48742 | 0 | 54498
3 | E3M40 | 43303415201 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-03-13 | 77224 | 77224 | 76227 | 0 | 0 | 76227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76227 | 76227 | 0 | 20936
3 | E3M41 | 43301715201 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-03-13 | 199790 | 199790 | 194721 | 0 | 0 | 194721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194721 | 194721 | 0 | 106468
3 | E3M62 | 41101635201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-02-13 | 861171 | 861171 | 848543 | 0 | 0 | 848543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848543 | 848543 | 0 | 839475
3 | E3N21 | 42543625201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2014-06-30 | 395355 | 395355 | 375669 | 0 | 0 | 375669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375669 | 375669 | 0 | 303422
3 | E3N25 | 41110235202 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2014-04-29 | 489178 | 489178 | 466189 | 0 | 0 | 466189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466189 | 466189 | 0 | 872364
3 | T3319 | 42290015201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2013-02-06 | 1593695 | 1593695 | 1665227 | 0 | 0 | 1665227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665227 | 1665227 | 0 | 1600251
3 | T3346 | 22041275201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2010-07-28 | 10500079 | 12397501 | 12548192 | 1897421.4 | 0 | 12773148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12548192 | 12773148 | 224955 | 10184133
3 | T3352 | 42289515201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2013-04-24 | 1128898 | 1282710 | 1246387 | 153811.75 | 0 | 1246387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1246387 | 1246387 | 0 | 1153102
3 | T3387 | 41931215201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2012-09-26 | 10256485 | 10266588 | 10798722 | 10103.38 | 0 | 10767112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10798722 | 10767112 | -31610 | 9797233
3 | T3393 | 42764815201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2014-02-26 | 235382 | 235382 | 217296 | 0 | 0 | 217296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217296 | 217296 | 0 | 313418
3 | T3407 | 42708915201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 1432492 | 1432492 | 1414923 | 0 | 0 | 1414923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1414923 | 1414923 | 0 | 1601804
3 | T3414 | 42624215201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-05-07 | 524227 | 524227 | 524513 | 0 | 0 | 524513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524513 | 524513 | 0 | 433163
3 | T3420 | 42624115201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2013-10-30 | 725683 | 725683 | 712533 | 0 | 0 | 712533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712533 | 712533 | 0 | 936031
3 | T3439 | 42624015201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2014-02-26 | 351199 | 351199 | 379044 | 0 | 0 | 379044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379044 | 379044 | 0 | 325109
3 | T3444 | 42873515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-07-31 | 1618073 | 1618073 | 1610344 | 0 | 0 | 1610562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610344 | 1610562 | 218 | 1729642
3 | T3447 | 42462125201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-04-24 | 1437977 | 1413565 | 1379096 | -24412.45 | 0 | 1378972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1379096 | 1378972 | -124 | 1241396
3 | T3448 | 42289215201 | F263312611 | R B M CONTRACTING SERVICES LLC | N/A | N/A | N/A | N/A | 2014-07-30 | 67717 | 67717 | 67717 | 0 | 0 | 67717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67717 | 67717 | 0 | 72380
3 | T3458 | 42952015201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2013-09-25 | 2559715 | 2583659 | 2625549 | 23943.75 | -37984 | 2587966 | -37984 | 0 | 0 | 0 | 0 | 0 | -37984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37984 | 2587565 | 2587966 | 401 | 2618783
3 | T3490 | 41268235201 | F204129847 | MAIN STREET CONSTRUCTION SERVICES LLC | N/A | N/A | N/A | N/A | 2014-05-07 | 70232 | 70232 | 65500 | 0 | 0 | 65500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65500 | 65500 | 0 | 88398 | B0 | ACC - LUMP SUM
3 | T3499 | 43213715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-03-26 | 1631904 | 1631904 | 1616123 | 0 | 537500 | 1616123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537500 | 0 | 0 | 0 | 0 | 0 | 537500 | 537500 | 2153623 | 1616123 | -537500 | 1503607 | B5 | ACC - INCENTIVE/DISINCENTIVE
3 | T3509 | 42635715201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-05-21 | 493770 | 493770 | 495890 | 0 | 0 | 495890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495890 | 495890 | 0 | 436184
4 | E4L72 | 41925025201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2011-06-24 | 31906521 | 33004982 | 32827693 | 1098461.25 | 0 | 32827750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32827693 | 32827750 | 57 | 52109390 | B8 | ACC - DESIGN/BUILD - MAJOR
4 | E4L76 | 41304615201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2011-03-04 | 78270000 | 79259528 | 79765800 | 989528.46 | 0 | 81306557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79765800 | 81306557 | 1540757 | 81639616 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
4 | E4M33 | 42844915201 | F590361850 | MILLER ELECTRIC COMPANY | N/A | N/A | N/A | N/A | 2012-04-06 | 4582291 | 4582291 | 4526291 | 0 | 0 | 4526291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526291 | 4526291 | 0 | 4607566 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
4 | E4M79 | 42968715201 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2012-11-09 | 5356871 | 5356871 | 5309868 | 0 | 0 | 5309868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5309868 | 5309868 | 0 | 4541213 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
4 | E4N38 | 42443015201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2013-02-01 | 5772088 | 6524967 | 6670851 | 752879.54 | 0 | 6672289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6670851 | 6672289 | 1438 | 3858013
4 | E4N78 | 42413115201 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2013-06-07 | 2265000 | 2263132 | 2257066 | -1868.23 | 0 | 2257066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257066 | 2257066 | 0 | 2068984 | B0 | ACC - LUMP SUM
4 | E4N85 | 43279615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2013-07-12 | 749284 | 724527 | 703896 | -24756.49 | 0 | 703896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 703896 | 703896 | 0 | 1004547
4 | E4P16 | 43393715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-03-07 | 161019 | 161019 | 154042 | 0 | 0 | 154042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154042 | 154042 | 0 | 190010
4 | E4P17 | 43279715201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2013-12-06 | 329900 | 282285 | 258607 | -47614.98 | 0 | 258607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258607 | 258607 | 0 | 509247
4 | E4P22 | 43111315201 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-01-03 | 2580338 | 2580338 | 2552570 | 0 | 0 | 2552570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2552570 | 2552570 | -1 | 2873227
4 | E4P40 | 43396215201 | F800499292 | L.C.C.I CONSTRUCTION L.L.C. | N/A | N/A | N/A | N/A | 2014-04-04 | 198331 | 198331 | 185045 | 0 | 0 | 185045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185045 | 185045 | 0 | 239987
4 | E4P41 | 43397115201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-04-04 | 1322521 | 1322892 | 1154843 | 371.14 | 0 | 1154843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1154843 | 1154843 | 0 | 973352
4 | E4P44 | 42909515201 | F592582830 | SIEG & SONS INC. | N/A | N/A | N/A | N/A | 2014-03-07 | 582291 | 582291 | 578750 | 0 | 0 | 578750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578750 | 578750 | 0 | 766889
4 | E4P45 | 42823915201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2014-04-04 | 267686 | 267686 | 225755 | 0 | 0 | 225755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225755 | 225755 | 0 | 324766
4 | E4P53 | 43397015201 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2014-04-04 | 147095 | 147095 | 139765 | 0 | 0 | 139765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139765 | 139765 | 0 | 142915 | B0 | ACC - LUMP SUM
4 | E4P67 | 43396715201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-05-02 | 411559 | 411559 | 405359 | 0 | 0 | 405359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405359 | 405359 | 0 | 372615
4 | E4P68 | 43400315201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-05-02 | 374632 | 374632 | 354850 | 0 | 0 | 354850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354850 | 354850 | 0 | 274085
4 | E4P78 | 43397615201 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2014-05-02 | 279985 | 279985 | 270451 | 0 | 0 | 270451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270451 | 270451 | 0 | 250697
4 | E4P90 | 43397815201 | F205822418 | DP DEVELOPMENT OF THE TREASURE COAST LL | N/A | N/A | N/A | N/A | 2014-06-06 | 181737 | 146595 | 141584 | -35141.26 | 0 | 141584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141584 | 141584 | 0 | 172493
4 | E4Q12 | 43397515201 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2014-06-06 | 786543 | 786543 | 731049 | 0 | 0 | 731049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 731049 | 731049 | 0 | 742853
4 | E4Q15 | 43400015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-05-02 | 510885 | 134613 | 119405 | -376271.74 | 0 | 119405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119405 | 119405 | 0 | 343149
4 | T4231 | 23026225201 | F203608929 | GUETTLER BROTHERS CONSTRUCTION | N/A | N/A | N/A | N/A | 2010-10-27 | 18782629 | 19297262 | 18712392 | 514633.04 | 0 | 19989362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18712392 | 19989362 | 1276970 | 21341978
4 | T4302 | 42165925201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2011-02-23 | 5777225 | 5816337 | 5751222 | 39111.95 | 0 | 5840554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5751222 | 5840554 | 89333 | 6362931
4 | T4304 | 42465815201 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2011-05-25 | 6245041 | 6245041 | 5814959 | 0 | -30168 | 5794326 | -30168 | 0 | 0 | 0 | 0 | 0 | -30168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30168 | 5784791 | 5794326 | 9535 | 6491710
4 | T4317 | 22989725201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2012-05-23 | 12189533 | 12136729 | 11383036 | -52803.88 | 0 | 11348816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11383036 | 11348816 | -34220 | 13843854
4 | T4343 | 42700615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-02-06 | 4110157 | 4110157 | 3912758 | 0 | 0 | 3908261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3912758 | 3908261 | -4497 | 4806482
4 | T4354 | 42701015202 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-02-06 | 1494392 | 1494392 | 1415437 | 0 | 0 | 1414762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1415437 | 1414762 | -675 | 1689812
4 | T4358 | 42595915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2013-04-24 | 2422014 | 2432708 | 2371735 | 10693.31 | 0 | 2371392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2371735 | 2371392 | -344 | 2517657
4 | T4361 | 43180215201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2013-03-27 | 689978 | 758529 | 711942 | 68551.39 | 0 | 711942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711942 | 711942 | 0 | 637973 | B0 | ACC - LUMP SUM
4 | T4363 | 42702315201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2013-04-24 | 4643370 | 4643367 | 4430846 | -3.15 | 0 | 4429353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4430846 | 4429353 | -1493 | 5421475
4 | T4364 | 42827315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2013-08-28 | 721864 | 721864 | 722927 | 0 | 0 | 722927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722927 | 722927 | 0 | 992063
4 | T4365 | 41965335201 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-04-24 | 3339650 | 3389650 | 3397354 | 50000 | 0 | 3396581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3397354 | 3396581 | -773 | 4422363
4 | T4368 | 42759115201 | F592655272 | WESTWIND CONTRACTING INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 1215736 | 1260164 | 1228303 | 44428 | -58216 | 1170858 | -58216 | 0 | 0 | 0 | 0 | 0 | -58216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -58216 | 1170087 | 1170858 | 771 | 1299911
4 | T4370 | 42302215201 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 3994488 | 3817187 | 3633879 | -177300.64 | 0 | 3631334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3633879 | 3631334 | -2546 | 4662648
4 | T4375 | 43079815201 | F590895890 | WILLIAMS PAVING COMPANY INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 498954 | 498954 | 489047 | 0 | 0 | 489047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489047 | 489047 | 0 | 522994
4 | T4378 | 43254915201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2013-12-04 | 1785000 | 1785000 | 1735000 | 0 | 0 | 1735000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1735000 | 1735000 | 0 | 2295538 | B0 | ACC - LUMP SUM
4 | T4379 | 42701225201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 539489 | 539489 | 527684 | 0 | 0 | 527684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527684 | 527684 | 0 | 587592
4 | T4385 | 41925045201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2014-04-30 | 337659 | 337659 | 319291 | 0 | 0 | 319291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319291 | 319291 | 0 | 445322
4 | T4390 | 22793825201 | F364509634 | MAYTIN ENGINEERING CORP. | N/A | N/A | N/A | N/A | 2014-02-26 | 517006 | 517006 | 511187 | 0 | 0 | 511187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511187 | 511187 | 0 | 515261 | A4 | ICC - LUMP SUM
4 | T4391 | 42700415201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 1172000 | 1172000 | 1117522 | 0 | 0 | 1109463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117522 | 1109463 | -8059 | 1321863 | B0 | ACC - LUMP SUM
5 | BDU54 | 41299435213 | F593483018 | WELBRO BUILDING CORPORATION | N/A | N/A | N/A | N/A | 2012-06-11 | 20846867 | 22943912 | 22943912 | 2097044.55 | 0 | 22943912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22943912 | 22943912 | 0 | 20831867 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE
5 | BDV94 | 42344695204 | F232938638 | GREGORI CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-03-04 | 554250 | 673855 | 638855 | 119605.46 | 0 | 638855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638855 | 638855 | 0 | 601015 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | E5R53 | 42474415201 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2012-10-08 | 1125000 | 1073026 | 1032679 | -51974 | -113368 | 919311 | -113368 | 0 | 0 | 0 | 0 | 0 | -113368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -113368 | 919311 | 919311 | 0 | 851031
5 | E5R74 | 42936215201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2013-06-04 | 2343983 | 2343983 | 2295699 | 0 | 0 | 2295699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295699 | 2295699 | 0 | 1283486 | B0 | ACC - LUMP SUM
5 | E5R78 | 43106515201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2013-06-04 | 1432200 | 1441797 | 1377218 | 9597.17 | 0 | 1377218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377218 | 1377218 | 0 | 2258203
5 | E5R83 | 23930415201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2013-06-26 | 10203400 | 10234439 | 10164588 | 31039.19 | 0 | 10184967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10164588 | 10184967 | 20379 | 13028976 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E5R89 | 42756215201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-05-07 | 1080000 | 1080000 | 1147540 | 0 | 0 | 1147540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1147540 | 1147540 | 0 | 978707
5 | E5W15 | 43326215201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2014-04-01 | 188644 | 188644 | 173944 | 0 | 0 | 173944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173944 | 173944 | 0 | 247000
5 | E5W16 | 43326515201 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-04-01 | 155129 | 155129 | 165956 | 0 | 0 | 165956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165956 | 165956 | 0 | 127000
5 | E5W17 | 43326115201 | F592582830 | SIEG & SONS INC. | N/A | N/A | N/A | N/A | 2014-03-04 | 116628 | 116628 | 110750 | 0 | 0 | 110750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110750 | 110750 | 0 | 123784 | B0 | ACC - LUMP SUM
5 | E5W19 | 43107015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-01-07 | 932822 | 932822 | 882819 | 0 | 0 | 882819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882819 | 882819 | 0 | 1251514
5 | E5W20 | 43353715201 | F263976898 | AMROAD LLC | N/A | N/A | N/A | N/A | 2014-02-04 | 95060 | 95060 | 92250 | 0 | -8840 | 83410 | -8840 | 0 | 0 | 0 | 0 | 0 | -8840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8840 | 83410 | 83410 | 0 | 60364
5 | E5W22 | 43353815201 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2014-02-04 | 87843 | 87843 | 81038 | 0 | 0 | 81038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81038 | 81038 | 0 | 143675
5 | E5W24 | 43326715201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2014-04-01 | 597000 | 597000 | 547000 | 0 | 0 | 547000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547000 | 547000 | 0 | 1070116
5 | E5W34 | 41937015201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2014-04-01 | 365000 | 365000 | 345289 | 0 | 0 | 345289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345289 | 345289 | 0 | 485000 | B0 | ACC - LUMP SUM
5 | E5W48 | 42309615201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2014-06-24 | 475755 | 475755 | 456755 | 0 | 0 | 456755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456755 | 456755 | 0 | 389711 | B0 | ACC - LUMP SUM
5 | T5322 | 23839545201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2011-07-27 | 16278889 | 17781760 | 18052209 | 1502871.12 | 0 | 18046412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18052209 | 18046412 | -5797 | 20574419
5 | T5401 | 42201515201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-04-24 | 4603457 | 4721215 | 4590801 | 117758.21 | -37984 | 4552297 | -37984 | 0 | 0 | 0 | 0 | 0 | -37984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37984 | 4552817 | 4552297 | -520 | 4500360
5 | T5413 | 23953525201 | F381818208 | DEWITT EXCAVATING INC. | N/A | N/A | N/A | N/A | 2012-04-25 | 7288562 | 7290708 | 7262460 | 2146.35 | 0 | 7196331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262460 | 7196331 | -66129 | 7727248
5 | T5422 | 41499915201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2013-03-27 | 1069577 | 1147357 | 1122595 | 77780.28 | 0 | 1122595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1122595 | 1122595 | 0 | 919551
5 | T5430 | 42741715201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 953616 | 953616 | 956091 | 0 | 0 | 956091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 956091 | 956091 | 0 | 891853
5 | T5434 | 42723215201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2013-04-30 | 3828333 | 3780214 | 3778884 | -48118.04 | 0 | 3778736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3778884 | 3778736 | -148 | 3888111 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
5 | T5444 | 42722815201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 6220488 | 6853650 | 6842947 | 633162.48 | 0 | 6847216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6842947 | 6847216 | 4269 | 5174413
5 | T5447 | 41802015201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2013-03-27 | 1249934 | 1249934 | 1221093 | 0 | 0 | 1221093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221093 | 1221093 | 0 | 1261846
5 | T5453 | 42949115201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-02-27 | 2793910 | 2793910 | 2851601 | 0 | 0 | 2851571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2851601 | 2851571 | -30 | 3153726
5 | T5470 | 43067215201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2013-06-19 | 1428196 | 1456196 | 1447568 | 28000 | 0 | 1447568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1447568 | 1447568 | 0 | 1674861
5 | T5475 | 43018715201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 769979 | 769979 | 735665 | 0 | 0 | 735665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735665 | 735665 | 0 | 786469 | B0 | ACC - LUMP SUM
5 | T5479 | 42887715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-02-05 | 1018000 | 1018000 | 967574 | 0 | 0 | 967574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967574 | 967574 | 0 | 1181765 | B0 | ACC - LUMP SUM
5 | T5481 | 24099225201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 662854 | 662854 | 625918 | 0 | 0 | 625918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625918 | 625918 | 0 | 488487
5 | T5484 | 43359515201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 160823 | 160823 | 149823 | 0 | 0 | 149823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149823 | 149823 | 0 | 234403
5 | T5490 | 42893415201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2014-05-21 | 299220 | 299220 | 281239 | 0 | 0 | 281239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281239 | 281239 | 0 | 355404 | B0 | ACC - LUMP SUM
5 | T5505 | 43018225201 | F593484839 | BUILT-RITE CONSTRUCTION OF CENTRAL FLORI | N/A | N/A | N/A | N/A | 2014-04-30 | 124000 | 137512 | 131512 | 13512 | 0 | 131512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131512 | 131512 | 0 | 135276 | B0 | ACC - LUMP SUM
6 | E6H35 | 41809425201 | F650838100 | SUPERIOR LANDSCAPING & LAWN SERVICE INC | N/A | N/A | N/A | N/A | 2013-06-27 | 647361 | 647361 | 646164 | 0 | -6128 | 640036 | -6128 | 0 | 0 | 0 | 0 | 0 | -6128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6128 | 640036 | 640036 | 0 | 434917 | B0 | ACC - LUMP SUM
6 | E6H42 | 42999715201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2013-06-27 | 2888376 | 2888376 | 2518315 | 0 | 0 | 2518314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2518315 | 2518314 | 0 | 1952252
6 | E6H55 | 42999515201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2013-07-25 | 2196108 | 2547091 | 2355415 | 350983 | 0 | 2355414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355415 | 2355414 | -1 | 3793360
6 | E6H89 | 42934715201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-10-31 | 1656869 | 1656869 | 1642271 | 0 | 0 | 1642337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642271 | 1642337 | 66 | 1957425 | B0 | ACC - LUMP SUM
6 | E6I00 | 42914915201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2014-08-28 | 97909 | 97909 | 95480 | 0 | 0 | 95480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95480 | 95480 | 0 | 92585 | B0 | ACC - LUMP SUM
6 | E6I06 | 42914315201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-01-30 | 511391 | 511391 | 492255 | 0 | 0 | 492255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492255 | 492255 | 0 | 488187
6 | E6I10 | 25168455201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2013-09-26 | 1336493 | 1336493 | 1270841 | 0 | 0 | 1270806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270841 | 1270806 | -35 | 1445286
6 | E6I12 | 43195115201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2013-11-21 | 328770 | 328770 | 319896 | 0 | 0 | 319896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319896 | 319896 | 0 | 353008
6 | E6I21 | 42914515201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2013-11-21 | 917461 | 917461 | 804065 | 0 | 0 | 804065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 804065 | 804065 | 0 | 936668
6 | E6I40 | 42916235201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2013-08-29 | 876233 | 876233 | 842419 | 0 | 0 | 842419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 842419 | 842419 | 0 | 1053761
6 | E6I41 | 42918815201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-02-27 | 3051904 | 3101904 | 2954581 | 50000 | 100000 | 2976280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 3054581 | 2976280 | -78302 | 3242256 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6I50 | 43117115201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-07-31 | 614838 | 614838 | 556562 | 0 | 0 | 556562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556562 | 556562 | 0 | 688700
6 | T6198 | 41985915201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2012-10-31 | 11628469 | 11728469 | 10870085 | 100000 | 0 | 10854373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10870085 | 10854373 | -15712 | 10326839
6 | T6219 | 41263735201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2011-09-28 | 1879940 | 1901780 | 1884231 | 21840 | 0 | 1884152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884231 | 1884152 | -79 | 2076785
6 | T6256 | 42551315201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2012-01-25 | 3491765 | 3554006 | 3465121 | 62241.32 | 0 | 3465336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465121 | 3465336 | 216 | 3404007
6 | T6257 | 42514515201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2012-02-29 | 6803533 | 6805439 | 6562695 | 1906.37 | 0 | 6528724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6562695 | 6528724 | -33971 | 7124777
6 | T6274 | 42563715202 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2012-04-25 | 3389619 | 3415244 | 3434878 | 25625 | 0 | 3408033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3434878 | 3408033 | -26845 | 3192722
6 | T6277 | 41247355201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2012-03-28 | 973813 | 1084662 | 1056849 | 110849 | -18384 | 1038465 | -18384 | 0 | 0 | 0 | 0 | 0 | -18384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18384 | 1038465 | 1038465 | 0 | 887143
6 | T6283 | 42915915201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 2420034 | 2716910 | 2586180 | 296876.35 | 0 | 2586385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586180 | 2586385 | 206 | 2632098
6 | T6286 | 42827915201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2013-02-27 | 1727127 | 1737127 | 1574494 | 10000 | 0 | 1574494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1574494 | 1574494 | 0 | 1754775
6 | T6289 | 42914415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2013-04-24 | 1574706 | 1574706 | 1468896 | 0 | 0 | 1468672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1468896 | 1468672 | -224 | 1515265
6 | T6292 | 42527115201 | F590895890 | WILLIAMS PAVING COMPANY INC. | N/A | N/A | N/A | N/A | 2013-03-27 | 1776432 | 1782401 | 1728838 | 5968.52 | 0 | 1728477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1728838 | 1728477 | -361 | 1922113
6 | T6294 | 25023635201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-02-06 | 6142510 | 6260112 | 6132269 | 117601.72 | 0 | 6128940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6132269 | 6128940 | -3329 | 5163835 | B1:B2 | ACC - NO EXCUSE BONUS:ACC - A+B (COST+TIME BIDDING)
6 | T6296 | 42848615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-04-24 | 2559781 | 2559781 | 2436245 | 0 | 0 | 2435764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2436245 | 2435764 | -481 | 2814516
6 | T6298 | 25168835201 | F650220703 | ODEBRECHT CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2012-09-12 | 4246242 | 4389022 | 4329187 | 142780 | 0 | 4315357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4329187 | 4315357 | -13831 | 5988420
6 | T6302 | 24961485201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-02-27 | 1928019 | 1928019 | 1840895 | 0 | 0 | 1839871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840895 | 1839871 | -1023 | 2088605
6 | T6304 | 40557555201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-02-06 | 4441233 | 4506233 | 4520669 | 65000 | 0 | 4514737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520669 | 4514737 | -5932 | 4729315
6 | T6306 | 42847615201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2012-10-31 | 1150126 | 1150126 | 1099652 | 0 | 0 | 1097498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1099652 | 1097498 | -2153 | 1107478
6 | T6307 | 42751715201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2012-10-31 | 3138611 | 3138611 | 3086278 | 0 | 0 | 3082048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3086278 | 3082048 | -4230 | 3015902
6 | T6310 | 42848415201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 2643396 | 2747670 | 2738183 | 104273.57 | 0 | 2739220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2738183 | 2739220 | 1037 | 2596228
6 | T6317 | 42558215201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 611611 | 642192 | 597121 | 30580.55 | 0 | 597121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597121 | 597121 | 0 | 528419
6 | T6321 | 42914615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2013-08-28 | 1568943 | 1572068 | 1511503 | 3125.09 | 0 | 1510404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1511503 | 1510404 | -1099 | 1671944
6 | T6326 | 42848025201 | F650806153 | AGC ELECTRIC INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 598775 | 626792 | 663757 | 28017 | 0 | 663757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663757 | 663757 | 0 | 583862
6 | T6354 | 43076115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-04-30 | 264539 | 264539 | 257147 | 0 | 0 | 257147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257147 | 257147 | 0 | 308910 | B0 | ACC - LUMP SUM
7 | E7H15 | 42347915201 | F593273147 | INLAND CONSTRUCTION AND EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2011-04-13 | 1489801 | 1489801 | 1397774 | 0 | 0 | 1397774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397774 | 1397774 | 0 | 1900000
7 | E7I10 | 41664135201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2012-08-08 | 2609000 | 2609000 | 2539098 | 0 | 0 | 2539098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2539098 | 2539098 | 0 | 2255500
7 | E7I12 | 42716115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-02-13 | 3211501 | 3241645 | 3087832 | 30144.1 | 0 | 3087171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3087832 | 3087171 | -661 | 2968524
7 | E7I20 | 42716015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-05-29 | 2103847 | 2103847 | 2012521 | 0 | 0 | 2015180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012521 | 2015180 | 2659 | 1798723
7 | E7I27 | 42470715201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2013-05-08 | 262455 | 288455 | 274422 | 26000 | 0 | 274422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274422 | 274422 | 0 | 250000
7 | E7I65 | 42950015201 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2013-08-14 | 545794 | 545794 | 534041 | 0 | 0 | 534041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534041 | 534041 | 0 | 363220
7 | E7I73 | 42888215201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2014-03-12 | 161753 | 161753 | 168071 | 0 | 0 | 168071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 168071 | 0 | 90000
7 | E7I74 | 42888225201 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2014-03-12 | 174384 | 174384 | 173484 | 0 | 0 | 173484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173484 | 173484 | 0 | 180598
7 | E7I75 | 42895915201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-03-12 | 1272505 | 1272505 | 1236184 | 0 | 0 | 1236184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236184 | 1236184 | 0 | 869000 | B0 | ACC - LUMP SUM
7 | E7I79 | 43070915201 | F593759317 | CHEYENNE ASPHALT INCORPORATED | N/A | N/A | N/A | N/A | 2014-03-12 | 143573 | 143573 | 140811 | 0 | 0 | 140811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140811 | 140811 | 0 | 151900 | B0 | ACC - LUMP SUM
7 | E7I84 | 43253415201 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2014-05-14 | 865555 | 865555 | 815555 | 0 | 0 | 815555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815555 | 815555 | 0 | 1222605 | B0 | ACC - LUMP SUM
7 | E7I86 | 43270815201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-02-12 | 570177 | 588876 | 579662 | 18699.2 | 0 | 579662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579662 | 579662 | 0 | 415000
7 | E7J03 | 41090965201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2013-07-26 | 1199414 | 1199414 | 1101676 | 0 | 0 | 1101676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101676 | 1101676 | 0 | 915000 | B0 | ACC - LUMP SUM
7 | T7145 | 25558515201 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2011-05-25 | 14782862 | 14840038 | 14923334 | 57175.45 | 0 | 14855530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14923334 | 14855530 | -67804 | 19051620
7 | T7215 | 25715515201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2011-04-27 | 16908928 | 17117199 | 16333232 | 208271.01 | 0 | 16338017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16333232 | 16338017 | 4785 | 16235635
7 | T7306 | 42152415201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2012-06-06 | 7218846 | 7457221 | 7033415 | 238374.63 | 0 | 7024970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033415 | 7024970 | -8445 | 6826297
7 | T7312 | 42716515201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2013-02-06 | 6969069 | 7176465 | 7341593 | 207396.3 | 0 | 7330210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7341593 | 7330210 | -11383 | 6739999
7 | T7313 | 42896015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-07-31 | 1385209 | 1385209 | 1350699 | 0 | 0 | 1351385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350699 | 1351385 | 686 | 1507562 | B0 | ACC - LUMP SUM
7 | T7315 | 42715015201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2013-02-27 | 2464444 | 2519444 | 2482385 | 55000 | 0 | 2479294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2482385 | 2479294 | -3091 | 2475000
7 | T7316 | 43232815201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2013-03-27 | 2398657 | 2398657 | 2325044 | 0 | 0 | 2324965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2325044 | 2324965 | -79 | 2025384
7 | T7318 | 42455215201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2013-04-24 | 5017437 | 5021145 | 5017012 | 3707.96 | 0 | 5015310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5017012 | 5015310 | -1702 | 4985000 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
7 | T7319 | 42714815201 | F900095113 | RAINEY CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2013-04-24 | 2862257 | 2862257 | 3093254 | 0 | -21366 | 3071316 | -21366 | 0 | 0 | 0 | 0 | 0 | -21366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21366 | 3071888 | 3071316 | -572 | 3571073 | B0 | ACC - LUMP SUM
7 | T7320 | 42716215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 6688741 | 6711402 | 6714167 | 22661.12 | 0 | 6717183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6714167 | 6717183 | 3015 | 6752451
7 | T7321 | 42715325201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2013-03-27 | 464335 | 474055 | 463114 | 9720 | -4830 | 458284 | -4830 | 0 | 0 | 0 | 0 | 0 | -4830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4830 | 458284 | 458284 | 0 | 380000
7 | T7327 | 42900815201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2013-08-28 | 1393333 | 1393333 | 1317331 | 0 | 0 | 1317300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317331 | 1317300 | -31 | 1390033
7 | T7332 | 42896615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 1602900 | 1602900 | 1581283 | 0 | 0 | 1581643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1581283 | 1581643 | 360 | 1750000 | B0 | ACC - LUMP SUM
7 | T7333 | 25705025201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2013-08-28 | 615166 | 615166 | 597766 | 0 | 0 | 597766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597766 | 597766 | 0 | 588987
7 | T7336 | 42900715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 899650 | 899650 | 831750 | 0 | 0 | 831750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 831750 | 831750 | 0 | 830000 | B0 | ACC - LUMP SUM
7 | T7338 | 43339215201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2013-12-04 | 339122 | 339122 | 340142 | 0 | 0 | 340142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340142 | 340142 | 0 | 334189
7 | T7342 | 43304515201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-02-05 | 492500 | 492500 | 472500 | 0 | 0 | 472500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472500 | 472500 | 0 | 473311 | B0 | ACC - LUMP SUM
7 | T7344 | 42907735201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-02-26 | 273786 | 273786 | 266951 | 0 | 0 | 266951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266951 | 266951 | 0 | 157000 | B0 | ACC - LUMP SUM
8 | E8L44 | 42615515201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2011-06-14 | 12289957 | 10231956 | 9993214 | -2058000.89 | 0 | 9995692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9993214 | 9995692 | 2477 | 10562970
8 | E8M46 | 42732415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2013-02-26 | 5445620 | 6044163 | 6171776 | 598543.26 | 0 | 6166359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6171776 | 6166359 | -5417 | 5468996
8 | E8M61 | 42815415201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2013-03-12 | 3237604 | 3287206 | 3085111 | 49602.55 | 0 | 3085111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3085111 | 3085111 | 0 | 4295669
8 | E8M79 | 43107915201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-04-09 | 6589154 | 6599869 | 6691510 | 10715.3 | -10000 | 6680921 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 6681510 | 6680921 | -590 | 8498964
8 | E8N06 | 43245615201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-02-18 | 2777072 | 2677984 | 2402653 | -99087.64 | 0 | 2405693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402653 | 2405693 | 3040 | 3098705
8 | E8N07 | 42933315201 | F263435185 | ENGECON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-11-12 | 994390 | 994390 | 970021 | 0 | 0 | 970021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 970021 | 970021 | 0 | 911270
8 | E8N16 | 42897315201 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2014-03-11 | 341935 | 341935 | 320243 | 0 | 0 | 320243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320243 | 320243 | 0 | 460675 | B0 | ACC - LUMP SUM
8 | E8N22 | 42902515201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-01-14 | 3404444 | 4367288 | 4369052 | 962843.75 | 0 | 4371216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4369052 | 4371216 | 2163 | 3784113
8 | E8N27 | 43368915201 | F650546351 | MANCIL'S TRACTOR SERVICE INC. | N/A | N/A | N/A | N/A | 2014-05-20 | 370616 | 370616 | 360379 | 0 | 0 | 360379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360379 | 360379 | 0 | 314247 | B0 | ACC - LUMP SUM

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1329 | 19571915201 | 2009-06-17 | QTR4 | 08/09 | 2 | 9 | 900 | 1054 | 1256 | -202 | 202 | 0 | 45 | 109 | 29755075 | 150000 | 29605075 | 30577699 | 30629189 | -1246694 | 0 | -1246694 | 29382495 | 31496712 | 2114217 | 822624 | 10 | 0 | 109 | 710268 | 0 | 0 | 0 | 236516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35660 | 35660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 938512 | 35660 | Z91-0742148 | SAFECO INSURANCE COMPANY OF AMERICA | N/A | N/A | N/A | N/A | 2015-01-06 | QTR3 | 14/15 | 2013-01-31 | QTR3 | 12/13 | 113 | 42389866.96 | ARRA | AMERICAN RECOVERY AND REINVEST | 0 | 35 | 0 | 0 | 0 | 0 |  | CO | 34 | 01co | 1 | 34
01CO | 01 | T1389 | 41549015201 | 2010-07-28 | QTR1 | 10/11 | 2 | 8 | 650 | 950 | 1010 | -60 | 60 | 0 | 98 | 202 | 13850596 | 150000 | 13700596 | 14203576 | 13918706 | -198000 | 0 | -198000 | 13720706 | 14530532 | 809826 | 352980 | 73 | 0 | 0 | 230740 | 0 | 0 | 25 | 147113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 23 | 39208 | 39208 | 0 | 0 | 0 | 0 | 0 | 202 | 418132 | 39208 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2014-12-05 | QTR2 | 14/15 | 2013-09-03 | QTR1 | 13/14 | 115 | 20340423.55 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 25 | 01do | 35 | 59
01CO | 01 | T1403 | 19448515201 | 2011-05-25 | QTR4 | 10/11 | 2 | 2 | 450 | 667 | 666 | 1 | 0 | 0 | 215 | 2 | 10008331 | 100173 | 9908158 | 10076101 | 9902773 | 0 | 0 | 0 | 9902773 | 9879607 | -23166 | 67770 | 158 | 23 | 2 | 61478 | 0 | 0 | 0 | 44733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 2 | 106211 | 0 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2015-01-08 | QTR3 | 14/15 | 2013-12-30 | QTR2 | 13/14 | 118 | 9984033.56 |  |  | 2 | 34 | 0 | 0 | 0 | 0 |  | CO | 30 | 02co | 60 | 89
01CO | 01 | T1407 | 19576515201 | 2010-09-29 | QTR1 | 10/11 | 1 | 13 | 800 | 1084 | 1084 | 0 | 0 | 0 | 158 | 126 | 14220849 | 129405 | 14091444 | 15022102 | 14932461 | 0 | 0 | 0 | 14932461 | 15371000 | 438539 | 801253 | 129 | 0 | 0 | 98665 | 0 | 0 | 52 | 254259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 433920 | 1687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 786844 | 1687 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2014-10-13 | QTR2 | 14/15 | 2014-01-18 | QTR3 | 13/14 | 113 | 11264597.26 |  |  | 45 | 28 | 0 | 0 | 0 | 0 |  | CO | 6 | 02do | 90 | 95
01CO | 01 | T1463 | 41736515201 | 2011-06-22 | QTR4 | 10/11 | 1 | 7 | 600 | 759 | 759 | 0 | 0 | 0 | 144 | 15 | 9540474 | 111429 | 9429045 | 9918837 | 9702547 | 0 | 0 | 0 | 9702547 | 9701892 | -656 | 378364 | 106 | 0 | 0 | 247694 | 0 | 5 | 15 | 107813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68913 | 0 | 0 | 0 | 46774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 471194 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-09-19 | QTR1 | 14/15 | 2013-11-11 | QTR2 | 13/14 | 108 | 8323801.45 |  |  | 15 | 33 | 0 | 0 | 0 | 0 |  | CO | 16 | 03co | 96 | 111
01CO | 01 | T1477 | 19541645201 | 2012-04-25 | QTR4 | 11/12 | 1 | 3 | 450 | 641 | 641 | 0 | 0 | 0 | 191 | 0 | 10956198 | 94197 | 10862001 | 10957630 | 11051551 | 0 | 0 | 0 | 11051551 | 10999776 | -51776 | 1432 | 93 | 28 | 0 | 59789 | 0 | 10 | 0 | 4995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 23816 | 0 | F650507332 | GUYMANN CONSTRUCTION OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2014-07-31 | QTR1 | 14/15 | 2014-05-04 | QTR4 | 13/14 | 113 | 10699278.86 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO | 16 | 03do | 112 | 127
01CO | 01 | T1506 | 40828625201 | 2012-06-06 | QTR4 | 11/12 | 1 | 2 | 450 | 536 | 534 | 2 | 0 | 0 | 86 | 0 | 9404527 | 107089 | 9297438 | 7654956 | 7289541 | 0 | 0 | 0 | 7289541 | 7297926 | 8385 | -1749571 | 44 | 0 | 0 | 0 | 0 | 10 | 0 | -1783315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67701 | 33744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | -1715614 | 33744 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-10-01 | QTR2 | 14/15 | 2014-02-07 | QTR3 | 13/14 | 113 | 9118320.26 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO | 19 | 04co | 128 | 146
01CO | 01 | T1531 | 42952615201 | 2013-03-06 | QTR3 | 12/13 | 1 | 5 | 135 | 228 | 299 | -71 | 71 | 0 | 52 | 41 | 2149000 | 50000 | 2099000 | 2142630 | 2134577 | -108772 | 0 | -108772 | 2025805 | 2025601 | -204 | -6370 | 19 | 0 | 6 | 58402 | 0 | 17 | 34 | -31523 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7830 | 0 | 0 | 0 | 0 | 0 | 17 | 41 | 34709 | 355 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-12-03 | QTR2 | 14/15 | 2014-06-30 | QTR4 | 13/14 | 115 | 1997239.71 | B0 | ACC - LUMP SUM | 8 | 16 | 0 | 0 | 0 | 0 |  | CO | 21 | 04do | 147 | 167
01CO | 01 | T1536 | 41369515201 | 2013-04-24 | QTR4 | 12/13 | 3 | 4 | 350 | 469 | 469 | 0 | 0 | 0 | 89 | 30 | 8076913 | 81786 | 7995127 | 8251439 | 8211651 | 0 | 0 | 0 | 8211651 | 8208595 | -3056 | 174527 | 57 | 0 | 3 | 26637 | 0 | 0 | 27 | 78024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 194476 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-01-29 | QTR3 | 14/15 | 2014-10-17 | QTR2 | 14/15 | 113 | 8781655.23 |  |  | 3 | 32 | 0 | 0 | 0 | 0 |  | CO | 18 | 05co | 168 | 185
01CO | 01 | T1537 | 42731015201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 171 | 157 | 14 | 0 | 0 | 20 | 1 | 934511 | 36636 | 897875 | 934511 | 907315 | 0 | 0 | 0 | 907315 | 907315 | 0 | 0 | 18 | 0 | 0 | 4551 | 0 | 0 | 1 | 4888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9439 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-07-30 | QTR1 | 14/15 | 2014-06-19 | QTR4 | 13/14 | 108 | 797883.09 | B0 | ACC - LUMP SUM | 1 | 2 | 0 | 0 | 0 | 0 | T | CO | 14 | 05do | 186 | 199
01CO | 01 | T1542 | 42997715201 | 2013-06-19 | QTR4 | 12/13 | 1 | 2 | 120 | 137 | 137 | 0 | 0 | 0 | 1 | 16 | 1021641 | 50000 | 971641 | 957447 | 916780 | 0 | 0 | 0 | 916780 | 916780 | 0 | -64194 | 0 | 0 | 0 | -64194 | 0 | 0 | 0 | 9334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | -54861 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-03-12 | QTR3 | 14/15 | 2014-06-21 | QTR4 | 13/14 | 115 | 1259552.62 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 22 | 06co | 200 | 221
01CO | 01 | T1547 | 42981815201 | 2013-09-25 | QTR1 | 13/14 | 2 | 2 | 100 | 104 | 78 | 26 | 0 | 0 | 4 | 0 | 171010 | 0 | 171010 | 193060 | 193060 | 0 | 0 | 0 | 193060 | 193060 | 0 | 22050 | 3 | 0 | 0 | 22050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22050 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2014-07-01 | QTR1 | 14/15 | 2014-05-28 | QTR4 | 13/14 | 118 | 221957.39 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 12 | 06do | 222 | 233
01CO | 01 | T1549 | 43085615201 | 2013-08-28 | QTR1 | 13/14 | 1 | 1 | 80 | 82 | 78 | 4 | 0 | 0 | 2 | 0 | 313880 | 11980 | 301900 | 322391 | 310411 | 0 | 0 | 0 | 310411 | 310411 | 0 | 8511 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 8511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8511 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2014-07-24 | QTR1 | 14/15 | 2014-05-15 | QTR4 | 13/14 | 113 | 217061.41 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO | 18 | 07co | 234 | 251
01CO | 01 | T1555 | 42910015201 | 2013-07-31 | QTR1 | 13/14 | 1 | 0 | 275 | 300 | 261 | 39 | 0 | 0 | 25 | 0 | 6125184 | 59970 | 6065214 | 6125184 | 6180641 | 0 | 0 | 0 | 6180641 | 6186013 | 5372 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2014-09-25 | QTR1 | 14/15 | 2014-08-19 | QTR1 | 14/15 | 118 | 5960563.21 | B0 | ACC - LUMP SUM | 0 | 14 | 0 | 0 | 0 | 0 |  | CO | 13 | 07do | 252 | 264
01CO | 01 | T1556 | 42911915201 | 2013-08-28 | QTR1 | 13/14 | 1 | 0 | 120 | 142 | 142 | 0 | 0 | 0 | 17 | 5 | 984307 | 50000 | 934307 | 984307 | 950925 | 0 | 0 | 0 | 950925 | 950925 | 0 | 0 | 17 | 0 | 3 | 9227 | 0 | 0 | 2 | 13279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 22506 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 | 2014-05-29 | QTR4 | 13/14 | 115 | 1028678.93 | B0 | ACC - LUMP SUM | 5 | 0 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 265 | 264
01CO | 01 | T1558 | 42949015201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 200 | 221 | 216 | 5 | 0 | 0 | 21 | 0 | 2007732 | 50000 | 1957732 | 2007732 | 1957732 | 0 | 0 | 0 | 1957732 | 1957732 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2014-10-31 | QTR2 | 14/15 | 2014-09-26 | QTR1 | 14/15 | 108 | 3091367.37 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 9 | 08do | 265 | 273
01CO | 01 | T1563 | 42984215201 | 2013-05-22 | QTR4 | 12/13 | 1 | 2 | 80 | 87 | 87 | 0 | 0 | 0 | 4 | 3 | 276962 | 0 | 276962 | 290055 | 290055 | 0 | 0 | 0 | 290055 | 290055 | 0 | 13093 | 4 | 0 | 3 | 13093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 13093 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2014-07-23 | QTR1 | 14/15 | 2014-04-23 | QTR4 | 13/14 | 113 | 311947.51 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1564 | 43336015201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 80 | 91 | 79 | 12 | 0 | 0 | 11 | 0 | 249571 | 11091 | 238480 | 249571 | 238480 | 0 | 0 | 0 | 238480 | 238480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593315987 | TUCKER PAVING INC. | N/A | N/A | N/A | N/A | 2015-02-05 | QTR3 | 14/15 | 2015-01-05 | QTR3 | 14/15 | 108 | 170337.73 | B0 | ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1568 | 42910215201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 145 | 169 | 168 | 1 | 0 | 0 | 24 | 0 | 2155214 | 50000 | 2105214 | 2155214 | 2109493 | 0 | 0 | 0 | 2109493 | 2109463 | -30 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2014-09-23 | QTR1 | 14/15 | 2014-05-22 | QTR4 | 13/14 | 118 | 2139342.73 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1571 | 43085815201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 80 | 114 | 112 | 2 | 0 | 0 | 32 | 2 | 434987 | 16298 | 418689 | 434987 | 424777 | 0 | 0 | 0 | 424777 | 424777 | 0 | 0 | 30 | 0 | 2 | 6088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6088 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-19 | QTR1 | 14/15 | 2014-07-15 | QTR1 | 14/15 | 113 | 326383.49 | B0 | ACC - LUMP SUM | 2 | 2 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1572 | 42954715201 | 2013-10-30 | QTR2 | 13/14 | 3 | 1 | 225 | 290 | 290 | 0 | 0 | 0 | 65 | 0 | 7786232 | 78221 | 7708011 | 7442764 | 7487178 | 0 | 0 | 0 | 7487178 | 7454628 | -32550 | -343467 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | -294593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -325154 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-03-26 | QTR3 | 14/15 | 2015-02-08 | QTR3 | 14/15 | 113 | 7638958.09 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 19 | 0 | 0 | -30561 | 0 |  | CO
01CO | 01 | T1573 | 42542615201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 90 | 94 | 82 | 12 | 0 | 0 | 4 | 0 | 235732 | 22238 | 213494 | 235732 | 223084 | 0 | 0 | 0 | 223084 | 223084 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 9590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9590 | 0 | F650167126 | J. MORI PAINTING INC. | N/A | N/A | N/A | N/A | 2014-08-28 | QTR1 | 14/15 | 2014-08-08 | QTR1 | 14/15 | 113 | 507871.4 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1574 | 43092915201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 80 | 90 | 89 | 1 | 0 | 0 | 10 | 0 | 246539 | 11813 | 234726 | 246539 | 234726 | 0 | 0 | 0 | 234726 | 234726 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593315987 | TUCKER PAVING INC. | N/A | N/A | N/A | N/A | 2014-07-01 | QTR1 | 14/15 | 2014-05-16 | QTR4 | 13/14 | 108 | 243727.87 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1575 | 43112215201 | 2013-10-30 | QTR2 | 13/14 | 1 | 1 | 100 | 112 | 111 | 1 | 0 | 0 | 11 | 1 | 962381 | 44381 | 918000 | 965823 | 931845 | 0 | 0 | 0 | 931845 | 931845 | 0 | 3442 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3442 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-09-11 | QTR1 | 14/15 | 2014-06-14 | QTR4 | 13/14 | 108 | 912555.77 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1579 | 43086415201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 80 | 84 | 84 | 0 | 0 | 0 | 4 | 0 | 688541 | 19823 | 668718 | 688541 | 661017 | 0 | 0 | 0 | 661017 | 661017 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-08-06 | QTR1 | 14/15 | 2014-06-29 | QTR4 | 13/14 | 113 | 402513.43 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1580 | 43093015201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 95 | 104 | 102 | 2 | 0 | 0 | 9 | 0 | 669283 | 26104 | 643179 | 669283 | 643179 | 0 | 0 | 0 | 643179 | 643179 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-10-07 | QTR2 | 14/15 | 2014-07-10 | QTR1 | 14/15 | 115 | 598937.28 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1581 | 43086315201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 100 | 118 | 118 | 0 | 0 | 0 | 18 | 0 | 796613 | 29314 | 767299 | 796613 | 781655 | 0 | 0 | 0 | 781655 | 781655 | 0 | 0 | 15 | 0 | 0 | 14356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14356 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-10-23 | QTR2 | 14/15 | 2014-09-15 | QTR1 | 14/15 | 115 | 729581.8 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1582 | 42814415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 165 | 187 | 142 | 45 | 0 | 0 | 22 | 0 | 783214 | 0 | 783214 | 763901 | 763901 | 0 | 0 | 0 | 763901 | 763901 | 0 | -19312 | 12 | 0 | 0 | -19312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19312 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-02-10 | QTR3 | 14/15 | 2015-01-13 | QTR3 | 14/15 | 118 | 863964.82 | B0 | ACC - LUMP SUM | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1584 | 42911515201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 125 | 158 | 158 | 0 | 0 | 0 | 33 | 0 | 2020000 | 50000 | 1970000 | 2020000 | 1989315 | -8000 | 0 | -8000 | 1981315 | 1988085 | 6770 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-01-30 | QTR3 | 14/15 | 2014-11-12 | QTR2 | 14/15 | 108 | 2239271.25 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1586 | 43085915201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 100 | 110 | 89 | 21 | 0 | 0 | 10 | 0 | 515545 | 21126 | 494419 | 515545 | 504315 | 0 | 0 | 0 | 504315 | 504315 | 0 | 0 | 9 | 0 | 0 | 5981 | 0 | 0 | 0 | 1829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9896 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-11-21 | QTR2 | 14/15 | 2014-10-10 | QTR2 | 14/15 | 108 | 471359.65 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A00 | 43091715201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 60 | 68 | 44 | 24 | 0 | 0 | 8 | 0 | 52640 | 0 | 52640 | 52640 | 52640 | 0 | 0 | 0 | 52640 | 52640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593080708 | EXCAVATION POINT INC. | N/A | N/A | N/A | N/A | 2015-03-03 | QTR3 | 14/15 | 2015-01-28 | QTR3 | 14/15 | 118 | 53595.74 | B0 | ACC - LUMP SUM | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A03 | 42989515201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 60 | 64 | 60 | 4 | 0 | 0 | 4 | 0 | 223166 | 11609 | 211557 | 223166 | 211557 | 0 | 0 | 0 | 211557 | 211557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-02-12 | QTR3 | 14/15 | 2014-12-12 | QTR2 | 14/15 | 113 | 201007.25 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A08 | 42825415201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 70 | 83 | 82 | 1 | 0 | 0 | 13 | 0 | 93337 | 0 | 93337 | 93337 | 93337 | 0 | 0 | 0 | 93337 | 93337 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2015-02-17 | QTR3 | 14/15 | 2015-01-09 | QTR3 | 14/15 | 113 | 112933.56 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A10 | 42825215201 | 2014-08-27 | QTR1 | 14/15 | 2 | 0 | 100 | 106 | 53 | 53 | 0 | 0 | 6 | 0 | 167341 | 0 | 167341 | 167341 | 167341 | 0 | 0 | 0 | 167341 | 167341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-03-12 | QTR3 | 14/15 | 2015-01-22 | QTR3 | 14/15 | 108 | 207740.45 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1J73 | 41473015201 | 2012-02-16 | QTR3 | 11/12 | 3 | 3 | 760 | 931 | 931 | 0 | 0 | 0 | 131 | 40 | 20657452 | 150000 | 20507452 | 20909917 | 20769992 | 0 | 0 | 0 | 20769992 | 20769992 | 0 | 252465 | 99 | 0 | 40 | 294765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 294765 | 0 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2015-03-12 | QTR3 | 14/15 | 2014-11-12 | QTR2 | 14/15 | 115 | 30061049 | B8:B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 40 | 32 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1K49 | 43013915201 | 2012-01-30 | QTR3 | 11/12 | 3 | 1 | 375 | 574 | 643 | -69 | 69 | 0 | 44 | 155 | 1330800 | 50000 | 1280800 | 1196714 | 1137129 | -105708 | 0 | -105708 | 1031421 | 1031421 | 0 | -134086 | 26 | 0 | 0 | 0 | 0 | 0 | 155 | -134086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | -134086 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-01-06 | QTR3 | 14/15 | 2014-01-13 | QTR3 | 13/14 | 115 | 1710449 | A3:B0:A3:B:A:B0 | ICC - DESIGN/BUILD - MINOR:ACC - LUMP SUM:ICC - DESIGN/BUILD - MINOR:ACC - LUMP SUM:ICC - DESIGN/BUILD - MINOR:ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1K74 | 42893715201 | 2012-05-31 | QTR4 | 11/12 | 1 | 0 | 590 | 682 | 680 | 2 | 0 | 0 | 92 | 0 | 5688000 | 50000 | 5638000 | 5688000 | 5635501 | 0 | 0 | 0 | 5635501 | 5629901 | -5600 | 0 | 51 | 0 | 0 | 15816 | 0 | 0 | 0 | 2436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 17525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 35777 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2014-09-15 | QTR1 | 14/15 | 2014-07-07 | QTR1 | 14/15 | 108 | 5906610 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1L10 | 43171315201 | 2013-01-17 | QTR3 | 12/13 | 1 | 0 | 300 | 350 | 349 | 1 | 0 | 0 | 50 | 0 | 1963030 | 50000 | 1913030 | 1963030 | 1915078 | 0 | 0 | 0 | 1915078 | 1915078 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593273147 | INLAND CONSTRUCTION AND EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2014-10-02 | QTR2 | 14/15 | 2014-05-22 | QTR4 | 13/14 | 115 | 2035342.1 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1L18 | 42987915201 | 2012-11-15 | QTR2 | 12/13 | 1 | 0 | 100 | 121 | 124 | -3 | 3 | 0 | 21 | 0 | 96622 | 4622 | 92000 | 96622 | 82079 | -2274 | 0 | -2274 | 79805 | 79805 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 5 | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 840 | 0 | F760715786 | F.W.A.K. INC. | N/A | N/A | N/A | N/A | 2014-08-18 | QTR1 | 14/15 | 2013-08-23 | QTR1 | 13/14 | 108 | 95068.54 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1L70 | 43142915201 | 2013-02-15 | QTR3 | 12/13 | 2 | 1 | 430 | 445 | 424 | 21 | 0 | 0 | 15 | 0 | 910918 | 0 | 910918 | 1021501 | 1004565 | 0 | 0 | 0 | 1004565 | 1004530 | -35 | 110583 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 110583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110583 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2014-09-16 | QTR1 | 14/15 | 2014-06-26 | QTR4 | 13/14 | 108 | 903190 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1M02 | 43266015201 | 2013-06-06 | QTR4 | 12/13 | 3 | 3 | 450 | 501 | 501 | 0 | 0 | 0 | 51 | 0 | 1799250 | 50000 | 1749250 | 1909786 | 1863529 | 0 | 0 | 0 | 1863529 | 1864315 | 786 | 110536 | 15 | 0 | 0 | 111394 | 0 | 0 | 0 | 2885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 114279 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-03-12 | QTR3 | 14/15 | 2014-11-13 | QTR2 | 14/15 | 115 | 2081874 | A3:A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1M14 | 43249315201 | 2013-06-20 | QTR4 | 12/13 | 2 | 2 | 325 | 354 | 354 | 0 | 0 | 0 | 27 | 2 | 1576687 | 50000 | 1526687 | 1621260 | 1573398 | 0 | 0 | 0 | 1573398 | 1573845 | 447 | 44573 | 12 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 47376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 46711 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-09-19 | QTR1 | 14/15 | 2014-07-31 | QTR1 | 14/15 | 108 | 1611119 | B8 | ACC - DESIGN/BUILD - MAJOR | 2 | 15 | 0 | 0 | -1146 | 0 |  | DO
01DO | 01 | E1M36 | 42913015201 | 2014-01-16 | QTR3 | 13/14 | 1 | 0 | 110 | 114 | 81 | 33 | 0 | 0 | 4 | 0 | 988135 | 50000 | 938135 | 988135 | 965889 | 0 | 0 | 0 | 965889 | 965889 | 0 | 0 | 2 | 0 | 0 | 9045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9045 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-10-13 | QTR2 | 14/15 | 2014-07-10 | QTR1 | 14/15 | 115 | 1182267.37 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1M38 | 42365015201 | 2014-02-20 | QTR3 | 13/14 | 1 | 0 | 100 | 106 | 105 | 1 | 0 | 0 | 6 | 0 | 339276 | 15218 | 324058 | 339276 | 321083 | 0 | 0 | 0 | 321083 | 321083 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-10-22 | QTR2 | 14/15 | 2014-09-13 | QTR1 | 14/15 | 115 | 256512.72 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1M39 | 42911725201 | 2013-08-15 | QTR1 | 13/14 | 2 | 1 | 80 | 83 | 77 | 6 | 0 | 0 | 3 | 0 | 1060000 | 50000 | 1010000 | 1070443 | 1033120 | 0 | 0 | 0 | 1033120 | 1033120 | 0 | 10443 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 16178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10443 | 3579 | 0 | 0 | 0 | 0 | 0 | 0 | 26621 | 3579 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-08-14 | QTR1 | 14/15 | 2014-05-14 | QTR4 | 13/14 | 115 | 1127477.99 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1M52 | 42909415201 | 2013-11-21 | QTR2 | 13/14 | 1 | 1 | 80 | 92 | 92 | 0 | 0 | 0 | 12 | 0 | 597931 | 24843 | 573088 | 600134 | 594316 | 0 | 0 | 0 | 594316 | 594316 | 0 | 2204 | 10 | 0 | 0 | 11021 | 0 | 0 | 0 | 2204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13225 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2015-02-12 | QTR3 | 14/15 | 2014-07-22 | QTR1 | 14/15 | 115 | 608071.16 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1M72 | 43385115201 | 2013-06-20 | QTR4 | 12/13 | 1 | 2 | 80 | 120 | 145 | -25 | 25 | 0 | 40 | 0 | 272547 | 11893 | 260654 | 277963 | 266070 | -24150 | 0 | -24150 | 241920 | 241920 | 0 | 5416 | 18 | 0 | 0 | 0 | 0 | 21 | 0 | 5416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 5416 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-09-29 | QTR1 | 14/15 | 2014-06-10 | QTR4 | 13/14 | 108 | 279217.08 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N01 | 43403615201 | 2013-12-19 | QTR2 | 13/14 | 1 | 0 | 80 | 88 | 87 | 1 | 0 | 0 | 8 | 0 | 555692 | 25662 | 530030 | 555692 | 531495 | 0 | 0 | 0 | 531495 | 531495 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-10-13 | QTR2 | 14/15 | 2014-07-16 | QTR1 | 14/15 | 108 | 615008.31 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N06 | 43193915201 | 2014-02-20 | QTR3 | 13/14 | 3 | 1 | 170 | 237 | 235 | 2 | 0 | 0 | 62 | 5 | 1230923 | 49430 | 1181493 | 1239584 | 1229167 | 0 | 0 | 0 | 1229167 | 1229167 | 0 | 8661 | 33 | 0 | 5 | 16612 | 0 | 9 | 0 | 1063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 5 | 17675 | 0 | F593362663 | BUN CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-02-27 | QTR3 | 14/15 | 2015-01-08 | QTR3 | 14/15 | 118 | 1068146.09 |  |  | 5 | 20 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N07 | 43109115201 | 2014-03-20 | QTR3 | 13/14 | 1 | 1 | 60 | 60 | 31 | 29 | 0 | 0 | 0 | 0 | 98451 | 5451 | 93000 | 100138 | 94687 | 0 | 0 | 0 | 94687 | 94687 | 0 | 1687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687 | 825 | F593674850 | LAS CONTRACTING CORP | N/A | N/A | N/A | N/A | 2015-01-30 | QTR3 | 14/15 | 2014-08-13 | QTR1 | 14/15 | 108 | 116821.12 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N09 | 42524415201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 80 | 92 | 95 | -3 | 3 | 0 | 12 | 0 | 862415 | 33537 | 828878 | 862415 | 828878 | -5226 | 0 | -5226 | 823652 | 823652 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-03-19 | QTR3 | 14/15 | 2014-12-18 | QTR2 | 14/15 | 108 | 694287.64 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N10 | 43445815201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 75 | 83 | 75 | 8 | 0 | 0 | 8 | 0 | 272420 | 13207 | 259213 | 272420 | 263758 | 0 | 0 | 0 | 263758 | 263758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4545 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-03-05 | QTR3 | 14/15 | 2015-01-16 | QTR3 | 14/15 | 115 | 173258.53 | A4 | ICC - LUMP SUM | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N22 | 42914815201 | 2013-11-21 | QTR2 | 13/14 | 2 | 0 | 160 | 198 | 197 | 1 | 0 | 0 | 38 | 0 | 2271958 | 50000 | 2221958 | 2271958 | 2273965 | 0 | 0 | 0 | 2273965 | 2281618 | 7653 | 0 | 32 | 0 | 0 | 11367 | 0 | 0 | 0 | 19159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31450 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-02-17 | QTR3 | 14/15 | 2014-12-09 | QTR2 | 14/15 | 108 | 2565542.41 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N37 | 43384815201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 60 | 74 | 74 | 0 | 0 | 0 | 14 | 0 | 308905 | 10892 | 298013 | 308905 | 296513 | 0 | 0 | 0 | 296513 | 296513 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593586613 | EVANS CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2015-02-19 | QTR3 | 14/15 | 2015-01-15 | QTR3 | 14/15 | 118 | 205804.17 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N38 | 43445915201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 60 | 60 | 57 | 3 | 0 | 0 | 0 | 0 | 133143 | 6955 | 126188 | 133143 | 126188 | 0 | 0 | 0 | 126188 | 126188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2014-12-15 | QTR2 | 14/15 | 2014-11-10 | QTR2 | 14/15 | 108 | 124658.51 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N41 | 43469815201 | 2014-06-19 | QTR4 | 13/14 | 1 | 0 | 75 | 78 | 52 | 26 | 0 | 0 | 3 | 0 | 110272 | 9602 | 100670 | 110272 | 88947 | 0 | 0 | 0 | 88947 | 88947 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-01-30 | QTR3 | 14/15 | 2014-10-29 | QTR2 | 14/15 | 108 | 131177.6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N68 | 19541665201 | 2014-07-17 | QTR1 | 14/15 | 1 | 0 | 50 | 50 | 9 | 41 | 0 | 0 | 0 | 0 | 50855 | 4426 | 46429 | 50855 | 46429 | 0 | 0 | 0 | 46429 | 46429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2014-10-24 | QTR2 | 14/15 | 2014-10-07 | QTR2 | 14/15 | 113 | 85198.71 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N69 | 41612035201 | 2014-08-29 | QTR1 | 14/15 | 1 | 0 | 50 | 54 | 40 | 14 | 0 | 0 | 4 | 0 | 121546 | 11146 | 110400 | 121546 | 110400 | 0 | 0 | 0 | 110400 | 110400 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2015-01-05 | QTR3 | 14/15 | 2014-12-10 | QTR2 | 14/15 | 115 | 183400.33 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N97 | 43193815202 | 2014-08-06 | QTR1 | 14/15 | 1 | 0 | 90 | 92 | 89 | 3 | 0 | 0 | 2 | 0 | 1590000 | 0 | 1590000 | 1590000 | 1590000 | 0 | 0 | 0 | 1590000 | 1590000 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-02-12 | QTR3 | 14/15 | 2014-11-14 | QTR2 | 14/15 | 118 | 1300000 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2359 | 21321725201 | 2010-12-01 | QTR2 | 10/11 | 1 | 5 | 720 | 957 | 1332 | -375 | 375 | 0 | 236 | 1 | 12480050 | 150000 | 12330050 | 12930758 | 12778436 | 0 | 0 | 0 | 12778436 | 12779717 | 1281 | 450708 | 149 | 0 | 1 | 37427 | 0 | 0 | 0 | 8948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 510649 | 0 | F060613324 | COSTELLO INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-12-23 | QTR2 | 14/15 | 2014-10-21 | QTR2 | 14/15 | 208 | 18609389.29 |  |  | 1 | 87 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2398 | 21087325201 | 2011-06-22 | QTR4 | 10/11 | 1 | 11 | 650 | 924 | 924 | 0 | 0 | 0 | 110 | 164 | 10935162 | 150000 | 10785162 | 12563524 | 12687376 | 0 | 0 | 0 | 12687376 | 12686893 | -483 | 1628362 | 51 | 0 | 0 | 0 | 0 | 0 | 45 | 289688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34133 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1429570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 1693125 | 0 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2014-08-18 | QTR1 | 14/15 | 2014-04-09 | QTR4 | 13/14 | 209 | 15856090.23 |  |  | 4 | 42 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2413 | 42930415201 | 2012-06-20 | QTR4 | 11/12 | 2 | 0 | 365 | 573 | 581 | -8 | 8 | 0 | 119 | 89 | 13231111 | 150000 | 13081111 | 13231111 | 13309354 | -36992 | 0 | -36992 | 13272362 | 13309528 | 37166 | 0 | 62 | 0 | 63 | 79373 | 0 | 0 | 5 | 45477 | 0 | 0 | 0 | 568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 125418 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-07-30 | QTR1 | 14/15 | 2014-04-11 | QTR4 | 13/14 | 208 | 15830196.01 |  |  | 89 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2446 | 21324345201 | 2012-10-31 | QTR2 | 12/13 | 1 | 0 | 300 | 424 | 422 | 2 | 0 | 0 | 49 | 75 | 745411 | 42811 | 702600 | 745411 | 704271 | 0 | 0 | 0 | 704271 | 704271 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2014-07-22 | QTR1 | 14/15 | 2014-06-06 | QTR4 | 13/14 | 208 | 770857.52 |  |  | 75 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2452 | 42880915201 | 2013-02-27 | QTR3 | 12/13 | 1 | 1 | 260 | 435 | 434 | 1 | 0 | 0 | 159 | 16 | 11661112 | 127086 | 11534026 | 11812236 | 12453297 | 0 | 0 | 0 | 12453297 | 12453297 | 0 | 151124 | 122 | 0 | 16 | 193999 | 0 | 0 | 0 | 40959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 234958 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2014-10-14 | QTR2 | 14/15 | 2014-07-25 | QTR1 | 14/15 | 208 | 12368561.22 |  |  | 14 | 37 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2453 | 42448515201 | 2013-02-06 | QTR3 | 12/13 | 1 | 1 | 245 | 368 | 346 | 22 | 0 | 0 | 97 | 26 | 2940728 | 50000 | 2890728 | 2984001 | 3277616 | 0 | 0 | 0 | 3277616 | 3276755 | -860 | 43273 | 78 | 0 | 6 | 21899 | 0 | 0 | 20 | 67770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 89670 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-07-02 | QTR1 | 14/15 | 2014-03-19 | QTR3 | 13/14 | 208 | 2955857.29 |  |  | 11 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2457 | 42430815201 | 2013-03-27 | QTR3 | 12/13 | 1 | 5 | 200 | 439 | 471 | -32 | 32 | 0 | 89 | 150 | 1161902 | 50000 | 1111902 | 1273448 | 1280373 | -49024 | 0 | -49024 | 1231349 | 1231349 | 0 | 111546 | 58 | 0 | 121 | 73433 | 3077 | 0 | 29 | 31686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 150 | 105118 | 3077 | F592655272 | WESTWIND CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-02-04 | QTR3 | 14/15 | 2014-10-02 | QTR2 | 14/15 | 216 | 1200430.58 |  |  | 33 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2464 | 21053845201 | 2013-03-27 | QTR3 | 12/13 | 1 | 0 | 140 | 185 | 182 | 3 | 0 | 0 | 42 | 3 | 1105370 | 47755 | 1057614 | 1105370 | 1123305 | 0 | 0 | 0 | 1123305 | 1123304 | -1 | 0 | 12 | 5 | 0 | 0 | 0 | 0 | 3 | 29704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 3 | 29704 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-09-05 | QTR1 | 14/15 | 2014-03-03 | QTR3 | 13/14 | 209 | 966212.57 |  |  | 3 | 14 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2472 | 42880615201 | 2013-07-31 | QTR1 | 13/14 | 1 | 0 | 200 | 364 | 362 | 2 | 0 | 0 | 164 | 0 | 7300000 | 82223 | 7217777 | 7300000 | 6704150 | 0 | 0 | 0 | 6704150 | 6712214 | 8064 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-01-28 | QTR3 | 14/15 | 2014-10-03 | QTR2 | 14/15 | 208 | 7992248.09 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2480 | 42604715201 | 2013-06-19 | QTR4 | 12/13 | 2 | 0 | 190 | 282 | 282 | 0 | 0 | 0 | 89 | 3 | 2486826 | 50000 | 2436826 | 2486826 | 2347817 | 0 | 0 | 0 | 2347817 | 2349225 | 1409 | 0 | 77 | 0 | 0 | 0 | 0 | 0 | 3 | 16080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16080 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-23 | QTR2 | 14/15 | 2014-06-12 | QTR4 | 13/14 | 209 | 2545335.83 |  |  | 3 | 12 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2481 | 43007015201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 180 | 186 | 179 | 7 | 0 | 0 | 6 | 0 | 369584 | 18149 | 351435 | 369584 | 361862 | 0 | 0 | 0 | 361862 | 361862 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11961 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-10-20 | QTR2 | 14/15 | 2014-08-21 | QTR1 | 14/15 | 214 | 377574.28 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2483 | 42969415201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 185 | 185 | 0 | 0 | 0 | 21 | 14 | 2122783 | 50000 | 2072783 | 2122783 | 2066520 | 0 | 0 | 0 | 2066520 | 2066520 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 14 | 13183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 13183 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-11-14 | QTR2 | 14/15 | 2014-07-27 | QTR1 | 14/15 | 209 | 2033285.21 |  |  | 14 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2486 | 42969615201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 166 | 137 | 29 | 0 | 0 | 16 | 0 | 213201 | 10807 | 202394 | 213201 | 201739 | 0 | 0 | 0 | 201739 | 201739 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2014-07-17 | QTR1 | 14/15 | 2014-07-03 | QTR1 | 14/15 | 216 | 235866.69 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2487 | 42975115201 | 2013-08-28 | QTR1 | 13/14 | 1 | 1 | 145 | 210 | 210 | 0 | 0 | 0 | 56 | 9 | 1948203 | 50000 | 1898203 | 1958517 | 1898534 | 0 | 0 | 0 | 1898534 | 1898509 | -25 | 10314 | 42 | 0 | 0 | 10608 | 0 | 0 | 9 | 13496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 24104 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-10-13 | QTR2 | 14/15 | 2014-06-20 | QTR4 | 13/14 | 208 | 1983074.42 |  |  | 9 | 14 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2490 | 42975235201 | 2013-09-25 | QTR1 | 13/14 | 1 | 4 | 150 | 264 | 207 | 57 | 0 | 0 | 40 | 74 | 1344082 | 50000 | 1294082 | 1461903 | 1449421 | 0 | 0 | 0 | 1449421 | 1449421 | 0 | 117821 | 38 | 0 | 29 | 62601 | 44478 | 0 | 44 | 82151 | 34634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3196 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 147948 | 79112 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-01-21 | QTR3 | 14/15 | 2014-07-31 | QTR1 | 14/15 | 208 | 1036541.75 | B0 | ACC - LUMP SUM | 66 | 2 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2494 | 42720415201 | 2013-07-31 | QTR1 | 13/14 | 1 | 1 | 100 | 160 | 160 | 0 | 0 | 0 | 30 | 30 | 939461 | 40520 | 898941 | 967572 | 911204 | 0 | 0 | 0 | 911204 | 911204 | 0 | 28111 | 26 | 0 | 2 | 5691 | 0 | 0 | 28 | 52760 | 17879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 58452 | 17879 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2014-08-22 | QTR1 | 14/15 | 2014-07-08 | QTR1 | 14/15 | 208 | 854057.95 |  |  | 7 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2495 | 42870815201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 180 | 266 | 263 | 3 | 0 | 0 | 62 | 24 | 4543998 | 52329 | 4491668 | 4593998 | 4820212 | 0 | 0 | 0 | 4820212 | 4818947 | -1265 | 50000 | 46 | 0 | 21 | 62696 | 1837 | 10 | 3 | 10417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 24 | 73113 | 1837 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-02-24 | QTR3 | 14/15 | 2014-09-25 | QTR1 | 14/15 | 208 | 5010885.74 |  |  | 24 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2497 | 43091915201 | 2013-10-30 | QTR2 | 13/14 | 1 | 2 | 100 | 316 | 318 | -2 | 2 | 0 | 45 | 171 | 337196 | 17800 | 319396 | 426661 | 390457 | -1932 | 0 | -1932 | 388525 | 388525 | 0 | 89465 | 19 | 0 | 5 | 9235 | 0 | 15 | 39 | 36522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 58755 | 58755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 171 | 104513 | 58755 | F161659018 | CORE CONSTRUCTION COMPANY OF JACKSONVILL | N/A | N/A | N/A | N/A | 2015-03-02 | QTR3 | 14/15 | 2014-12-12 | QTR2 | 14/15 | 208 | 355118.9 |  |  | 30 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2501 | 42445115201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 210 | 233 | 232 | 1 | 0 | 0 | 23 | 0 | 2399105 | 50000 | 2349105 | 2399105 | 2283379 | 0 | 0 | 0 | 2283379 | 2283645 | 265 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-01-20 | QTR3 | 14/15 | 2014-09-13 | QTR1 | 14/15 | 216 | 2180139.51 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2502 | 42889715201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 100 | 122 | 121 | 1 | 0 | 0 | 22 | 0 | 343355 | 18399 | 324956 | 343355 | 318751 | 0 | 0 | 0 | 318751 | 318751 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 | 2014-05-30 | QTR4 | 13/14 | 209 | 405708.15 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2504 | 42869115201 | 2013-10-30 | QTR2 | 13/14 | 1 | 1 | 95 | 116 | 115 | 1 | 0 | 0 | 17 | 4 | 619867 | 28993 | 590874 | 697349 | 706524 | 0 | 0 | 0 | 706524 | 706524 | 0 | 77482 | 10 | 0 | 4 | 104847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 104847 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-08-18 | QTR1 | 14/15 | 2014-06-02 | QTR4 | 13/14 | 214 | 669835.42 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2507 | 43225415201 | 2013-12-04 | QTR2 | 13/14 | 1 | 1 | 90 | 106 | 106 | 0 | 0 | 0 | 13 | 3 | 248683 | 0 | 248683 | 249718 | 249718 | 0 | 0 | 0 | 249718 | 249718 | 0 | 1035 | 10 | 0 | 0 | 0 | 0 | 0 | 3 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1035 | 0 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 | 2014-06-11 | QTR4 | 13/14 | 209 | 274893.73 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2509 | 43051515201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 75 | 96 | 93 | 3 | 0 | 0 | 21 | 0 | 138499 | 0 | 138499 | 138499 | 138499 | 0 | 0 | 0 | 138499 | 138499 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452181662 | ADVANTA ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-08-26 | QTR1 | 14/15 | 2014-06-06 | QTR4 | 13/14 | 209 | 180396.28 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2511 | 43224815201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 30 | 33 | 33 | 0 | 0 | 0 | 3 | 0 | 59893 | 3494 | 56399 | 59893 | 56399 | 0 | 0 | 0 | 56399 | 56399 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452181662 | ADVANTA ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-08-14 | QTR1 | 14/15 | 2014-07-06 | QTR1 | 14/15 | 209 | 76062.84 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2518 | 43477515201 | 2014-02-05 | QTR3 | 13/14 | 1 | 0 | 72 | 72 | 70 | 2 | 0 | 0 | 0 | 0 | 84224 | 0 | 84224 | 84224 | 84224 | 0 | 0 | 0 | 84224 | 84224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593564392 | RICHARDSON SITE PREP INC. | N/A | N/A | N/A | N/A | 2014-08-22 | QTR1 | 14/15 | 2014-07-10 | QTR1 | 14/15 | 209 | 176769.75 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2519 | 43335815201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 75 | 79 | 79 | 0 | 0 | 0 | 1 | 3 | 402306 | 15539 | 386767 | 402306 | 387767 | 0 | 0 | 0 | 387767 | 387767 | 0 | 0 | 0 | 0 | 3 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1000 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-11-25 | QTR2 | 14/15 | 2014-11-12 | QTR2 | 14/15 | 209 | 335957.94 | B0 | ACC - LUMP SUM | 3 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2521 | 43224415201 | 2014-02-26 | QTR3 | 13/14 | 1 | 0 | 35 | 42 | 42 | 0 | 0 | 0 | 5 | 2 | 109680 | 6758 | 102922 | 109680 | 104316 | 0 | 0 | 0 | 104316 | 104316 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1394 | 0 | F593564392 | RICHARDSON SITE PREP INC. | N/A | N/A | N/A | N/A | 2014-09-11 | QTR1 | 14/15 | 2014-07-31 | QTR1 | 14/15 | 214 | 114968.28 | B0 | ACC - LUMP SUM | 2 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2525 | 42476715201 | 2014-05-07 | QTR4 | 13/14 | 1 | 1 | 40 | 65 | 65 | 0 | 0 | 0 | 25 | 0 | 101692 | 5502 | 96190 | 110228 | 104725 | 0 | 0 | 0 | 104725 | 104725 | 0 | 8535 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 8535 | 0 | F593382032 | MARQUEE DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2015-01-28 | QTR3 | 14/15 | 2014-10-04 | QTR2 | 14/15 | 214 | 119253.64 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2540 | 4328234G201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 90 | 160 | 160 | 0 | 0 | 0 | 70 | 0 | 344794 | 0 | 344794 | 344794 | 360786 | 0 | 0 | 0 | 360786 | 0 | -360786 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-02-26 | QTR3 | 14/15 | 2015-02-10 | QTR3 | 14/15 | 209 | 230306.1 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2549 | 43551015201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 120 | 147 | 147 | 0 | 0 | 0 | 17 | 10 | 1205130 | 45181 | 1159949 | 1205130 | 1163672 | 0 | 0 | 0 | 1163672 | 1163672 | 0 | 0 | 6 | 0 | 0 | 1003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4081 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-03-10 | QTR3 | 14/15 | 2015-01-21 | QTR3 | 14/15 | 216 | 982529.51 |  |  | 10 | 11 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2P13 | 20954555201 | 2011-09-22 | QTR1 | 11/12 | 2 | 5 | 695 | 921 | 920 | 1 | 0 | 0 | 163 | 63 | 30532000 | 150000 | 30382000 | 30924278 | 30907321 | 0 | 0 | 0 | 30907321 | 30898233 | -9088 | 392278 | 116 | 0 | 31 | 119396 | 0 | 0 | 32 | 337971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 506867 | 0 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2014-08-29 | QTR1 | 14/15 | 2014-05-30 | QTR4 | 13/14 | 208 | 34254654.22 | B8 | ACC - DESIGN/BUILD - MAJOR | 63 | 47 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R03 | 20837135201 | 2013-04-17 | QTR4 | 12/13 | 4 | 0 | 365 | 486 | 482 | 4 | 0 | 0 | 121 | 0 | 1823323 | 50000 | 1773323 | 1823323 | 1649161 | 0 | 0 | 0 | 1649161 | 1649160 | -1 | 0 | 103 | 0 | 0 | 12126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25569 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2015-02-13 | QTR3 | 14/15 | 2014-12-19 | QTR2 | 14/15 | 214 | 2547672.59 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R90 | 20971015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 1 | 28 | 46 | 46 | 0 | 0 | 0 | 18 | 0 | 141019 | 9015 | 132004 | 153230 | 151100 | 0 | 0 | 0 | 151100 | 151100 | 0 | 12210 | 6 | 8 | 0 | 19096 | 2232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 19096 | 2232 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2015-03-04 | QTR3 | 14/15 | 2014-12-18 | QTR2 | 14/15 | 208 | 186563.71 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2S03 | 42870215201 | 2013-09-18 | QTR1 | 13/14 | 1 | 0 | 160 | 196 | 195 | 1 | 0 | 0 | 32 | 4 | 2539934 | 50000 | 2489934 | 2539934 | 2563383 | 0 | 0 | 0 | 2563383 | 2562645 | -738 | 0 | 27 | 0 | 4 | 33564 | 0 | 0 | 0 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 37684 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-18 | QTR2 | 14/15 | 2014-08-08 | QTR1 | 14/15 | 208 | 2390761.42 | B0 | ACC - LUMP SUM | 4 | 5 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2S34 | 42869315201 | 2014-03-19 | QTR3 | 13/14 | 1 | 0 | 110 | 127 | 127 | 0 | 0 | 0 | 17 | 0 | 2053370 | 50000 | 2003370 | 2053370 | 1811375 | 0 | 0 | 0 | 1811375 | 1821200 | 9826 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 7390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7390 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-02-20 | QTR3 | 14/15 | 2014-10-15 | QTR2 | 14/15 | 209 | 1709666.27 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T05 | 43055015201 | 2014-07-23 | QTR1 | 14/15 | 1 | 0 | 120 | 134 | 127 | 7 | 0 | 0 | 14 | 0 | 1656117 | 50000 | 1606117 | 1656117 | 1659137 | 0 | 0 | 0 | 1659137 | 1659137 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7846 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-03-20 | QTR3 | 14/15 | 2015-01-19 | QTR3 | 14/15 | 209 | 1793903.12 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3319 | 42290015201 | 2013-02-06 | QTR3 | 12/13 | 1 | 0 | 292 | 378 | 377 | 1 | 0 | 0 | 86 | 0 | 1593695 | 0 | 1593695 | 1593695 | 1665227 | 0 | 0 | 0 | 1665227 | 1665227 | 0 | 0 | 60 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2014-07-03 | QTR1 | 14/15 | 2014-05-08 | QTR4 | 13/14 | 308 | 1600251.25 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3346 | 22041275201 | 2010-07-28 | QTR1 | 10/11 | 2 | 12 | 916 | 1360 | 1360 | 0 | 0 | 0 | 232 | 212 | 10500079 | 100853 | 10399227 | 12397501 | 12548192 | 0 | 0 | 0 | 12548192 | 12773148 | 224955 | 1897421 | 162 | 0 | 50 | 228874 | 0 | 0 | 100 | 1133691 | 927959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 661097 | 258660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 1986503 | 1186620 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 | 2014-07-08 | QTR1 | 14/15 | 308 | 10184133.3 |  |  | 31 | 70 | 0 | 0 | -126182 | 0 |  | CO
03CO | 03 | T3352 | 42289515201 | 2013-04-24 | QTR4 | 12/13 | 1 | 2 | 250 | 380 | 380 | 0 | 0 | 0 | 100 | 30 | 1128898 | 0 | 1128898 | 1282710 | 1246387 | 0 | 0 | 0 | 1246387 | 1246387 | 0 | 153812 | 87 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 144312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 153812 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2014-09-25 | QTR1 | 14/15 | 2014-07-08 | QTR1 | 14/15 | 308 | 1153101.93 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3387 | 41931215201 | 2012-09-26 | QTR1 | 12/13 | 2 | 1 | 455 | 593 | 593 | 0 | 0 | 0 | 138 | 0 | 10256485 | 97092 | 10159393 | 10266588 | 10798722 | 0 | 0 | 0 | 10798722 | 10767112 | -31610 | 10103 | 61 | 0 | 0 | 18146 | 0 | 0 | 0 | 10103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28249 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-10-20 | QTR2 | 14/15 | 2014-07-25 | QTR1 | 14/15 | 314 | 9797232.92 |  |  | 0 | 77 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3393 | 42764815201 | 2014-02-26 | QTR3 | 13/14 | 1 | 0 | 115 | 121 | 120 | 1 | 0 | 0 | 5 | 1 | 235382 | 14952 | 220430 | 235382 | 217296 | 0 | 0 | 0 | 217296 | 217296 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 4058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4058 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2014-12-01 | QTR2 | 14/15 | 2014-09-26 | QTR1 | 14/15 | 308 | 313418.07 |  |  | 1 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3407 | 42708915201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 120 | 151 | 151 | 0 | 0 | 0 | 41 | -10 | 1432492 | 50000 | 1382492 | 1432492 | 1414923 | 0 | 0 | 0 | 1414923 | 1414923 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 1080 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-09-30 | QTR1 | 14/15 | 2014-06-05 | QTR4 | 13/14 | 313 | 1601803.96 |  |  | 0 | 2 | 0 | -10 | 0 | 0 |  | CO
03CO | 03 | T3414 | 42624215201 | 2014-05-07 | QTR4 | 13/14 | 1 | 0 | 80 | 108 | 91 | 17 | 0 | 0 | 28 | 0 | 524227 | 0 | 524227 | 524227 | 524513 | 0 | 0 | 0 | 524513 | 524513 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 | 2014-10-19 | QTR2 | 14/15 | 313 | 433162.54 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3420 | 42624115201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 145 | 243 | 233 | 10 | 0 | 0 | 98 | 0 | 725683 | 0 | 725683 | 725683 | 712533 | 0 | 0 | 0 | 712533 | 712533 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2014-10-08 | QTR2 | 14/15 | 2014-09-09 | QTR1 | 14/15 | 313 | 936031.12 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3439 | 42624015201 | 2014-02-26 | QTR3 | 13/14 | 2 | 0 | 70 | 132 | 131 | 1 | 0 | 0 | 62 | 0 | 351199 | 0 | 351199 | 351199 | 379044 | 0 | 0 | 0 | 379044 | 379044 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2014-11-13 | QTR2 | 14/15 | 2014-09-25 | QTR1 | 14/15 | 313 | 325109.06 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3444 | 42873515201 | 2013-07-31 | QTR1 | 13/14 | 1 | 0 | 125 | 228 | 228 | 0 | 0 | 0 | 90 | 13 | 1618073 | 50000 | 1568073 | 1618073 | 1610344 | 0 | 0 | 0 | 1610344 | 1610562 | 218 | 0 | 50 | 0 | 13 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 400 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-07 | QTR2 | 14/15 | 2014-06-02 | QTR4 | 13/14 | 314 | 1729641.89 |  |  | 13 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3447 | 42462125201 | 2013-04-24 | QTR4 | 12/13 | 2 | 1 | 200 | 330 | 330 | 0 | 0 | 0 | 130 | 0 | 1437977 | 50000 | 1387977 | 1413565 | 1379096 | 0 | 0 | 0 | 1379096 | 1378972 | -124 | -24412 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22312 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-09-22 | QTR1 | 14/15 | 2014-06-06 | QTR4 | 13/14 | 314 | 1241396.09 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3448 | 42289215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 20 | 26 | 26 | 0 | 0 | 0 | 6 | 0 | 67717 | 0 | 67717 | 67717 | 67717 | 0 | 0 | 0 | 67717 | 67717 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263312611 | R B M CONTRACTING SERVICES LLC | N/A | N/A | N/A | N/A | 2014-11-25 | QTR2 | 14/15 | 2014-10-25 | QTR2 | 14/15 | 313 | 72380.08 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3458 | 42952015201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 200 | 261 | 278 | -17 | 17 | 0 | 58 | 3 | 2559715 | 50000 | 2509715 | 2583659 | 2625549 | -37984 | 0 | -37984 | 2587565 | 2587966 | 401 | 23944 | 52 | 0 | 3 | 26106 | 0 | 0 | 0 | 3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 29979 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 | 2014-10-09 | QTR2 | 14/15 | 308 | 2618783.02 |  |  | 1 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3490 | 41268235201 | 2014-05-07 | QTR4 | 13/14 | 1 | 0 | 45 | 48 | 45 | 3 | 0 | 0 | 3 | 0 | 70232 | 4732 | 65500 | 70232 | 65500 | 0 | 0 | 0 | 65500 | 65500 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204129847 | MAIN STREET CONSTRUCTION SERVICES LLC | N/A | N/A | N/A | N/A | 2014-09-15 | QTR1 | 14/15 | 2014-08-22 | QTR1 | 14/15 | 313 | 88398.13 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3499 | 43213715201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 105 | 107 | 103 | 4 | 0 | 0 | 2 | 0 | 1631904 | 50000 | 1581904 | 1631904 | 1616123 | 0 | 537500 | 537500 | 2153623 | 1616123 | -537500 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 13828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16028 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-16 | QTR2 | 14/15 | 2014-08-29 | QTR1 | 14/15 | 321 | 1503606.97 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3509 | 42635715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 80 | 110 | 106 | 4 | 0 | 0 | 30 | 0 | 493770 | 0 | 493770 | 493770 | 495890 | 0 | 0 | 0 | 495890 | 495890 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 | 2014-11-10 | QTR2 | 14/15 | 313 | 436183.99 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3K71 | 42694915201 | 2013-10-10 | QTR2 | 13/14 | 2 | 0 | 125 | 174 | 173 | 1 | 0 | 0 | 35 | 14 | 1995786 | 50000 | 1945786 | 1995786 | 1979207 | 0 | 0 | 0 | 1979207 | 1982470 | 3263 | 0 | 15 | 0 | 14 | 2000 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 4200 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-29 | QTR2 | 14/15 | 2014-07-01 | QTR1 | 14/15 | 314 | 2340966.29 |  |  | 14 | 20 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L10 | 41557525201 | 2013-03-14 | QTR3 | 12/13 | 1 | 2 | 145 | 339 | 296 | 43 | 0 | 0 | 3 | 191 | 533421 | 37241 | 496180 | 735554 | 237341 | 0 | 0 | 0 | 237341 | 237341 | 0 | 202133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 140095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62038 | 34816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 202133 | 34816 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2015-02-16 | QTR3 | 14/15 | 2014-03-13 | QTR3 | 13/14 | 308 | 782055.17 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L32 | 22283225201 | 2014-01-09 | QTR3 | 13/14 | 1 | 0 | 55 | 107 | 106 | 1 | 0 | 0 | 52 | 0 | 292884 | 12670 | 280214 | 292884 | 288038 | 0 | 0 | 0 | 288038 | 288038 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593428518 | MARSHALL BROTHERS CONSTRUCTION & ENGINEE | N/A | N/A | N/A | N/A | 2014-11-12 | QTR2 | 14/15 | 2014-07-07 | QTR1 | 14/15 | 313 | 266060.99 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L65 | 42357745201 | 2014-05-08 | QTR4 | 13/14 | 1 | 0 | 90 | 120 | 117 | 3 | 0 | 0 | 16 | 14 | 311461 | 11461 | 300000 | 311461 | 300000 | 0 | 0 | 0 | 300000 | 300000 | 0 | 0 | 11 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | F593428518 | MARSHALL BROTHERS CONSTRUCTION & ENGINEE | N/A | N/A | N/A | N/A | 2015-01-14 | QTR3 | 14/15 | 2014-12-17 | QTR2 | 14/15 | 314 | 240688.14 |  |  | 14 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L96 | 41767735201 | 2013-11-14 | QTR2 | 13/14 | 1 | 0 | 65 | 95 | 95 | 0 | 0 | 0 | 30 | 0 | 82868 | 2290 | 80578 | 82868 | 80578 | 0 | 0 | 0 | 80578 | 80578 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-07-02 | QTR1 | 14/15 | 2014-05-13 | QTR4 | 13/14 | 314 | 48100.13 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M21 | 42187825201 | 2014-01-09 | QTR3 | 13/14 | 1 | 0 | 60 | 94 | 94 | 0 | 0 | 0 | 31 | 3 | 842964 | 39931 | 803033 | 842964 | 857292 | 0 | 0 | 0 | 857292 | 857292 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 3 | 18257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18257 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-08-01 | QTR1 | 14/15 | 2014-07-01 | QTR1 | 14/15 | 313 | 838555.84 |  |  | 3 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M23 | 42695815201 | 2014-01-09 | QTR3 | 13/14 | 1 | 0 | 70 | 78 | 78 | 0 | 0 | 0 | 8 | 0 | 1549934 | 50000 | 1499934 | 1549934 | 1527279 | 0 | 0 | 0 | 1527279 | 1527279 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-01 | QTR2 | 14/15 | 2014-06-14 | QTR4 | 13/14 | 313 | 1966885.65 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M24 | 42693315201 | 2013-12-12 | QTR2 | 13/14 | 2 | 2 | 210 | 291 | 290 | 1 | 0 | 0 | 48 | 33 | 3867191 | 50000 | 3817191 | 4050762 | 4276825 | 0 | 0 | 0 | 4276825 | 4245773 | -31052 | 183571 | 30 | 0 | 80 | 320908 | 0 | 0 | -7 | 30683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 73 | 351591 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-03-10 | QTR3 | 14/15 | 2014-12-22 | QTR2 | 14/15 | 314 | 4425803.28 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M35 | 42543325201 | 2014-04-10 | QTR4 | 13/14 | 1 | 0 | 30 | 30 | 15 | 15 | 0 | 0 | 0 | 0 | 58110 | 2539 | 55571 | 58110 | 55571 | 0 | 0 | 0 | 55571 | 55571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453031471 | LIVE OAK MANAGEMENT GROUP L.L.C. | N/A | N/A | N/A | N/A | 2014-07-30 | QTR1 | 14/15 | 2014-07-21 | QTR1 | 14/15 | 314 | 53308.77 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M36 | 21934425201 | 2014-03-13 | QTR3 | 13/14 | 1 | 1 | 90 | 97 | 97 | 0 | 0 | 0 | 7 | 0 | 268872 | 15344 | 253528 | 310112 | 294768 | 0 | 0 | 0 | 294768 | 294768 | 0 | 41240 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 41240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41240 | 0 | F522182511 | GULF COAST UTILITY CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2014-09-22 | QTR1 | 14/15 | 2014-09-05 | QTR1 | 14/15 | 314 | 322223.89 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M39 | 42188935201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 30 | 30 | 20 | 10 | 0 | 0 | 0 | 0 | 41842 | 2595 | 39247 | 41842 | 48742 | 0 | 0 | 0 | 48742 | 48742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591565266 | MCCORMICK CONTRACTING CO. INC. | N/A | N/A | N/A | N/A | 2014-07-23 | QTR1 | 14/15 | 2014-06-25 | QTR4 | 13/14 | 313 | 54498.15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M40 | 43303415201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 30 | 34 | 28 | 6 | 0 | 0 | 4 | 0 | 77224 | 997 | 76227 | 77224 | 76227 | 0 | 0 | 0 | 76227 | 76227 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-07-24 | QTR1 | 14/15 | 2014-07-03 | QTR1 | 14/15 | 314 | 20935.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M41 | 43301715201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 45 | 72 | 72 | 0 | 0 | 0 | 27 | 0 | 199790 | 5070 | 194721 | 199790 | 194721 | 0 | 0 | 0 | 194721 | 194721 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-09-12 | QTR1 | 14/15 | 2014-08-15 | QTR1 | 14/15 | 313 | 106467.89 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M62 | 41101635201 | 2014-02-13 | QTR3 | 13/14 | 1 | 0 | 90 | 100 | 51 | 49 | 0 | 0 | 8 | 2 | 861171 | 39975 | 821196 | 861171 | 848543 | 0 | 0 | 0 | 848543 | 848543 | 0 | 0 | 6 | 0 | 2 | 19442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 27347 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-07-30 | QTR1 | 14/15 | 2014-07-10 | QTR1 | 14/15 | 308 | 839474.9 |  |  | 2 | 2 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N21 | 42543625201 | 2014-06-30 | QTR4 | 13/14 | 1 | 0 | 30 | 43 | 30 | 13 | 0 | 0 | 13 | 0 | 395355 | 14449 | 380906 | 395355 | 375669 | 0 | 0 | 0 | 375669 | 375669 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2015-01-14 | QTR3 | 14/15 | 2014-12-15 | QTR2 | 14/15 | 314 | 303422.4 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N25 | 41110235202 | 2014-04-29 | QTR4 | 13/14 | 3 | 0 | 60 | 75 | 75 | 0 | 0 | 0 | 15 | 0 | 489178 | 41541 | 447637 | 489178 | 466189 | 0 | 0 | 0 | 466189 | 466189 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20700 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2014-09-29 | QTR1 | 14/15 | 2014-08-09 | QTR1 | 14/15 | 308 | 872363.6 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4231 | 23026225201 | 2010-10-27 | QTR2 | 10/11 | 1 | 5 | 1233 | 1392 | 1319 | 73 | 0 | 0 | 97 | 62 | 18782629 | 150000 | 18632629 | 19297262 | 18712392 | 0 | 0 | 0 | 18712392 | 19989362 | 1276970 | 514633 | 64 | 6 | 23 | 179221 | 0 | 0 | 39 | 312675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 62 | 459652 | 0 | F203608929 | GUETTLER BROTHERS CONSTRUCTION | N/A | N/A | N/A | N/A | 2015-01-14 | QTR3 | 14/15 | 2014-09-10 | QTR1 | 14/15 | 408 | 21341977.53 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4302 | 42165925201 | 2011-02-23 | QTR3 | 10/11 | 1 | 2 | 855 | 934 | 877 | 57 | 0 | 0 | 79 | 0 | 5777225 | 64239 | 5712986 | 5816337 | 5751222 | 0 | 0 | 0 | 5751222 | 5834538 | 83317 | 39112 | 46 | 0 | 0 | 10650 | 10650 | 0 | 0 | 40264 | 6621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70236 | 17271 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 | 2013-11-27 | QTR2 | 13/14 | 412 | 6362930.61 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4304 | 42465815201 | 2011-05-25 | QTR4 | 10/11 | 1 | 0 | 196 | 214 | 226 | -12 | 12 | 0 | 18 | 0 | 6245041 | 65382 | 6179659 | 6245041 | 5814959 | -30168 | 0 | -30168 | 5784791 | 5792664 | 7873 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204076160 | ASPHALT GROUP INC. | N/A | N/A | N/A | N/A | 2014-11-13 | QTR2 | 14/15 | 2012-04-24 | QTR4 | 11/12 | 409 | 6491710.44 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4317 | 22989725201 | 2012-05-23 | QTR4 | 11/12 | 4 | 4 | 500 | 576 | 572 | 4 | 0 | 0 | 75 | 1 | 12189533 | 141257 | 12048276 | 12136729 | 11383036 | 0 | 0 | 0 | 11383036 | 11348816 | -34220 | -52804 | 50 | 0 | 1 | 351627 | 0 | 0 | 0 | -35116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -346622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -30111 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-08-01 | QTR1 | 14/15 | 2014-05-30 | QTR4 | 13/14 | 409 | 13843853.6 |  |  | 1 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4343 | 42700615201 | 2013-02-06 | QTR3 | 12/13 | 1 | 0 | 270 | 325 | 316 | 9 | 0 | 0 | 55 | 0 | 4110157 | 50000 | 4060157 | 4110157 | 3912758 | 0 | 0 | 0 | 3912758 | 3908261 | -4497 | 0 | 35 | 0 | 0 | 4901 | 0 | 0 | 0 | 6528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11429 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-07-03 | QTR1 | 14/15 | 2014-03-07 | QTR3 | 13/14 | 412 | 4806481.71 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4354 | 42701015202 | 2013-02-06 | QTR3 | 12/13 | 2 | 0 | 135 | 157 | 152 | 5 | 0 | 0 | 22 | 0 | 1494392 | 50000 | 1444392 | 1494392 | 1415437 | 0 | 0 | 0 | 1415437 | 1414762 | -675 | 0 | 19 | 0 | 0 | 16007 | 0 | 0 | 0 | 2510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18517 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 | 2013-09-20 | QTR1 | 13/14 | 412 | 1689811.51 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4358 | 42595915201 | 2013-04-24 | QTR4 | 12/13 | 1 | 1 | 236 | 337 | 337 | 0 | 0 | 0 | 61 | 40 | 2422014 | 50000 | 2372014 | 2432708 | 2371735 | 0 | 0 | 0 | 2371735 | 2371392 | -344 | 10693 | 46 | 0 | 8 | 1353 | 0 | 0 | 30 | 17670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 19023 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-07 | QTR2 | 14/15 | 2014-06-27 | QTR4 | 13/14 | 409 | 2517656.6 |  |  | 40 | 15 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4361 | 43180215201 | 2013-03-27 | QTR3 | 12/13 | 2 | 1 | 95 | 234 | 234 | 0 | 0 | 0 | 52 | 87 | 689978 | 33230 | 656748 | 758529 | 711942 | 0 | 0 | 0 | 711942 | 711942 | 0 | 68551 | 31 | 0 | 0 | 0 | 0 | 0 | 87 | 68551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 68551 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-07-03 | QTR1 | 14/15 | 2014-04-22 | QTR4 | 13/14 | 412 | 637973.2 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4363 | 42702315201 | 2013-04-24 | QTR4 | 12/13 | 1 | 1 | 355 | 400 | 382 | 18 | 0 | 0 | 45 | 0 | 4643370 | 53517 | 4589853 | 4643367 | 4430846 | 0 | 0 | 0 | 4430846 | 4429353 | -1493 | -3 | 29 | 0 | 0 | 6177 | 0 | 0 | 0 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19801 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2014-10-03 | QTR2 | 14/15 | 2014-07-24 | QTR1 | 14/15 | 408 | 5421475.17 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4364 | 42827315201 | 2013-08-28 | QTR1 | 13/14 | 1 | 0 | 123 | 172 | 165 | 7 | 0 | 0 | 29 | 20 | 721864 | 50000 | 671864 | 721864 | 722927 | 0 | 0 | 0 | 722927 | 722927 | 0 | 0 | 27 | 0 | 0 | 24823 | 0 | 0 | 20 | 19517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 44341 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-30 | QTR2 | 14/15 | 2014-08-28 | QTR1 | 14/15 | 412 | 992063.41 |  |  | 20 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4365 | 41965335201 | 2013-04-24 | QTR4 | 12/13 | 2 | 2 | 290 | 316 | 280 | 36 | 0 | 0 | 26 | 0 | 3339650 | 50000 | 3289650 | 3389650 | 3397354 | 0 | 0 | 0 | 3397354 | 3396581 | -773 | 50000 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-08-19 | QTR1 | 14/15 | 2014-05-30 | QTR4 | 13/14 | 408 | 4422362.92 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4368 | 42759115201 | 2013-05-22 | QTR4 | 12/13 | 2 | 2 | 150 | 274 | 312 | -38 | 38 | 0 | 99 | 25 | 1215736 | 50000 | 1165736 | 1260164 | 1228303 | -58216 | 0 | -58216 | 1170087 | 1170858 | 771 | 44428 | 81 | 0 | 0 | 44428 | 44428 | 0 | 25 | 41786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 86214 | 44428 | F592655272 | WESTWIND CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-09-30 | QTR1 | 14/15 | 2014-07-26 | QTR1 | 14/15 | 412 | 1299911.4 |  |  | 18 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4370 | 42302215201 | 2013-06-19 | QTR4 | 12/13 | 1 | 4 | 351 | 432 | 430 | 2 | 0 | 0 | 81 | 0 | 3994488 | 50000 | 3944488 | 3817187 | 3633879 | 0 | 0 | 0 | 3633879 | 3631334 | -2546 | -177301 | 53 | 0 | 0 | 47123 | 0 | 0 | 0 | 21929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -182320 | 0 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2015-03-24 | QTR3 | 14/15 | 2015-01-08 | QTR3 | 14/15 | 408 | 4662648.45 |  |  | 0 | 28 | 0 | 0 | -251373 | 0 |  | CO
04CO | 04 | T4375 | 43079815201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 108 | 157 | 156 | 1 | 0 | 0 | 49 | 0 | 498954 | 24682 | 474271 | 498954 | 489047 | 0 | 0 | 0 | 489047 | 489047 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 3562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3562 | 0 | F590895890 | WILLIAMS PAVING COMPANY INC. | N/A | N/A | N/A | N/A | 2015-01-27 | QTR3 | 14/15 | 2014-10-06 | QTR2 | 14/15 | 412 | 522993.7 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4378 | 43254915201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 140 | 149 | 105 | 44 | 0 | 0 | 9 | 0 | 1785000 | 50000 | 1735000 | 1785000 | 1735000 | 0 | 0 | 0 | 1735000 | 1735000 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2014-07-29 | QTR1 | 14/15 | 2014-06-26 | QTR4 | 13/14 | 409 | 2295537.87 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4379 | 42701225201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 105 | 118 | 110 | 8 | 0 | 0 | 13 | 0 | 539489 | 27111 | 512378 | 539489 | 527684 | 0 | 0 | 0 | 527684 | 527684 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 14632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14632 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-10 | QTR2 | 14/15 | 2014-08-22 | QTR1 | 14/15 | 412 | 587592.14 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4385 | 41925045201 | 2014-04-30 | QTR4 | 13/14 | 1 | 0 | 120 | 133 | 120 | 13 | 0 | 0 | 13 | 0 | 337659 | 21299 | 316360 | 337659 | 319291 | 0 | 0 | 0 | 319291 | 319291 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-03-03 | QTR3 | 14/15 | 2015-01-28 | QTR3 | 14/15 | 408 | 445321.82 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4390 | 22793825201 | 2014-02-26 | QTR3 | 13/14 | 1 | 0 | 115 | 186 | 186 | 0 | 0 | 0 | 51 | 20 | 517006 | 24506 | 492500 | 517006 | 511187 | 0 | 0 | 0 | 511187 | 511187 | 0 | 0 | 37 | 0 | 15 | 11876 | 0 | 0 | 5 | 6810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 18687 | 0 | F364509634 | MAYTIN ENGINEERING CORP. | N/A | N/A | N/A | N/A | 2015-03-24 | QTR3 | 14/15 | 2015-01-25 | QTR3 | 14/15 | 412 | 515260.79 | A4 | ICC - LUMP SUM | 20 | 14 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4391 | 42700415201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 132 | 148 | 144 | 4 | 0 | 0 | 16 | 0 | 1172000 | 50000 | 1122000 | 1172000 | 1117522 | 0 | 0 | 0 | 1117522 | 1109463 | -8059 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 23090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23090 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-02-03 | QTR3 | 14/15 | 2014-12-23 | QTR2 | 14/15 | 412 | 1321863.11 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4L72 | 41925025201 | 2011-06-24 | QTR4 | 10/11 | 1 | 4 | 1029 | 1126 | 1015 | 111 | 0 | 0 | 97 | 0 | 31906521 | 150000 | 31756521 | 33004982 | 32827693 | 0 | 0 | 0 | 32827693 | 32827750 | 57 | 1098461 | 64 | 0 | 0 | 802316 | 0 | 0 | 0 | 92012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098227 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-11-18 | QTR2 | 14/15 | 2014-07-03 | QTR1 | 14/15 | 408 | 52109389.9 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4L76 | 41304615201 | 2011-03-04 | QTR3 | 10/11 | 2 | 6 | 1096 | 1249 | 1249 | 0 | 0 | 0 | 145 | 8 | 78270000 | 150000 | 78120000 | 79259528 | 79765800 | 0 | 0 | 0 | 79765800 | 81306557 | 1540757 | 989528 | 99 | 2 | 0 | 841941 | 52421 | 0 | 8 | 229983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 1133208 | 52421 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-01-21 | QTR3 | 14/15 | 2014-11-14 | QTR2 | 14/15 | 408 | 81639616 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR | 8 | 44 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4M33 | 42844915201 | 2012-04-06 | QTR4 | 11/12 | 2 | 0 | 470 | 631 | 631 | 0 | 0 | 0 | 161 | 0 | 4582291 | 50000 | 4532291 | 4582291 | 4526291 | 0 | 0 | 0 | 4526291 | 4526291 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | F590361850 | MILLER ELECTRIC COMPANY | N/A | N/A | N/A | N/A | 2014-07-17 | QTR1 | 14/15 | 2014-04-21 | QTR4 | 13/14 | 412 | 4607566 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 36 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4M79 | 42968715201 | 2012-11-09 | QTR2 | 12/13 | 1 | 0 | 510 | 590 | 590 | 0 | 0 | 0 | 80 | 0 | 5356871 | 50000 | 5306871 | 5356871 | 5309868 | 0 | 0 | 0 | 5309868 | 5309868 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6122 | 0 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2014-10-07 | QTR2 | 14/15 | 2014-08-27 | QTR1 | 14/15 | 412 | 4541213 | A3:Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4N38 | 42443015201 | 2013-02-01 | QTR3 | 12/13 | 1 | 4 | 224 | 415 | 411 | 4 | 0 | 0 | 152 | 39 | 5772088 | 50000 | 5722088 | 6524967 | 6670851 | 0 | 0 | 0 | 6670851 | 6670318 | -533 | 752880 | 132 | 0 | 0 | 397367 | 0 | 0 | 35 | 307272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 48240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 752880 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2015-01-21 | QTR3 | 14/15 | 2014-06-09 | QTR4 | 13/14 | 412 | 3858013.38 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4N78 | 42413115201 | 2013-06-07 | QTR4 | 12/13 | 1 | 2 | 230 | 302 | 302 | 0 | 0 | 0 | 23 | 49 | 2265000 | 50000 | 2215000 | 2263132 | 2257066 | 0 | 0 | 0 | 2257066 | 2257066 | 0 | -1868 | 20 | 0 | 41 | 47287 | 0 | 0 | 0 | 6648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 42066 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2015-01-13 | QTR3 | 14/15 | 2014-11-03 | QTR2 | 14/15 | 409 | 2068984.39 | B0 | ACC - LUMP SUM | 49 | 3 | 0 | 0 | -11868 | 0 |  | DO
04DO | 04 | E4N85 | 43279615201 | 2013-07-12 | QTR1 | 13/14 | 1 | 1 | 192 | 225 | 225 | 0 | 0 | 0 | 33 | 0 | 749284 | 40199 | 709084 | 724527 | 703896 | 0 | 0 | 0 | 703896 | 703896 | 0 | -24756 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 4241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15336 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-07-24 | QTR1 | 14/15 | 2014-05-23 | QTR4 | 13/14 | 412 | 1004546.54 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P16 | 43393715201 | 2014-03-07 | QTR3 | 13/14 | 1 | 0 | 59 | 65 | 63 | 2 | 0 | 0 | 6 | 0 | 161019 | 9118 | 151901 | 161019 | 154042 | 0 | 0 | 0 | 154042 | 154042 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-09-09 | QTR1 | 14/15 | 2014-07-24 | QTR1 | 14/15 | 412 | 190010.49 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P17 | 43279715201 | 2013-12-06 | QTR2 | 13/14 | 1 | 1 | 133 | 159 | 159 | 0 | 0 | 0 | 26 | 0 | 329900 | 23678 | 306222 | 282285 | 258607 | 0 | 0 | 0 | 258607 | 258607 | 0 | -47615 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | -47615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47615 | 0 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2015-01-27 | QTR3 | 14/15 | 2014-09-05 | QTR1 | 14/15 | 412 | 509246.58 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P22 | 43111315201 | 2014-01-03 | QTR3 | 13/14 | 1 | 0 | 125 | 139 | 136 | 3 | 0 | 0 | 14 | 0 | 2580338 | 50000 | 2530338 | 2580338 | 2552570 | 0 | 0 | 0 | 2552570 | 2552570 | -1 | 0 | 12 | 0 | 0 | 12057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12057 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-09-23 | QTR1 | 14/15 | 2014-08-29 | QTR1 | 14/15 | 412 | 2873226.53 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P40 | 43396215201 | 2014-04-04 | QTR4 | 13/14 | 1 | 0 | 103 | 165 | 165 | 0 | 0 | 0 | 62 | 0 | 198331 | 11337 | 186994 | 198331 | 185045 | 0 | 0 | 0 | 185045 | 185045 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F800499292 | L.C.C.I CONSTRUCTION L.L.C. | N/A | N/A | N/A | N/A | 2015-03-20 | QTR3 | 14/15 | 2014-12-23 | QTR2 | 14/15 | 412 | 239987.4 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P41 | 43397115201 | 2014-04-04 | QTR4 | 13/14 | 4 | 1 | 171 | 186 | 186 | 0 | 0 | 0 | 15 | 0 | 1322521 | 45898 | 1276624 | 1322892 | 1154843 | 0 | 0 | 0 | 1154843 | 1154843 | 0 | 371 | 1 | 0 | 0 | 9883 | 0 | 0 | 0 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10254 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-03-04 | QTR3 | 14/15 | 2015-01-20 | QTR3 | 14/15 | 409 | 973351.52 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P44 | 42909515201 | 2014-03-07 | QTR3 | 13/14 | 1 | 0 | 184 | 187 | 150 | 37 | 0 | 0 | 3 | 0 | 582291 | 36623 | 545668 | 582291 | 578750 | 0 | 0 | 0 | 578750 | 578750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592582830 | SIEG & SONS INC. | N/A | N/A | N/A | N/A | 2015-01-22 | QTR3 | 14/15 | 2014-11-12 | QTR2 | 14/15 | 412 | 766888.8 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P45 | 42823915201 | 2014-04-04 | QTR4 | 13/14 | 1 | 0 | 66 | 76 | 65 | 11 | 0 | 0 | 10 | 0 | 267686 | 15549 | 252137 | 267686 | 225755 | 0 | 0 | 0 | 225755 | 225755 | 0 | 0 | 8 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2014-10-15 | QTR2 | 14/15 | 2014-09-10 | QTR1 | 14/15 | 409 | 324766.26 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P53 | 43397015201 | 2014-04-04 | QTR4 | 13/14 | 1 | 0 | 86 | 93 | 87 | 6 | 0 | 0 | 7 | 0 | 147095 | 7330 | 139765 | 147095 | 139765 | 0 | 0 | 0 | 139765 | 139765 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES L.C. | N/A | N/A | N/A | N/A | 2015-02-17 | QTR3 | 14/15 | 2014-11-17 | QTR2 | 14/15 | 409 | 142914.8 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P67 | 43396715201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 62 | 72 | 63 | 9 | 0 | 0 | 10 | 0 | 411559 | 18203 | 393356 | 411559 | 405359 | 0 | 0 | 0 | 405359 | 405359 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2667 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-12-17 | QTR2 | 14/15 | 2014-10-08 | QTR2 | 14/15 | 412 | 372615.07 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P68 | 43400315201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 50 | 51 | 45 | 6 | 0 | 0 | 1 | 0 | 374632 | 19781 | 354850 | 374632 | 354850 | 0 | 0 | 0 | 354850 | 354850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-10-28 | QTR2 | 14/15 | 2014-09-26 | QTR1 | 14/15 | 412 | 274084.51 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P78 | 43397615201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 60 | 79 | 71 | 8 | 0 | 0 | 19 | 0 | 279985 | 12354 | 267631 | 279985 | 270451 | 0 | 0 | 0 | 270451 | 270451 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 2820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2820 | 0 | F591753888 | JOHNSON-DAVIS INC. | N/A | N/A | N/A | N/A | 2014-11-12 | QTR2 | 14/15 | 2014-10-16 | QTR2 | 14/15 | 408 | 250696.53 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P90 | 43397815201 | 2014-06-06 | QTR4 | 13/14 | 1 | 1 | 69 | 82 | 82 | 0 | 0 | 0 | 13 | 0 | 181737 | 6705 | 175032 | 146595 | 141584 | 0 | 0 | 0 | 141584 | 141584 | 0 | -35141 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -35141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35141 | 0 | F205822418 | DP DEVELOPMENT OF THE TREASURE COAST LL | N/A | N/A | N/A | N/A | 2015-01-21 | QTR3 | 14/15 | 2014-12-08 | QTR2 | 14/15 | 412 | 172493.1 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q12 | 43397515201 | 2014-06-06 | QTR4 | 13/14 | 3 | 0 | 233 | 240 | 95 | 145 | 0 | 0 | 7 | 0 | 786543 | 32995 | 753548 | 786543 | 731049 | 0 | 0 | 0 | 731049 | 731049 | 0 | 0 | 4 | 0 | 0 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2015-02-11 | QTR3 | 14/15 | 2014-12-12 | QTR2 | 14/15 | 408 | 742852.75 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q15 | 43400015201 | 2014-05-02 | QTR4 | 13/14 | 2 | 2 | 76 | 85 | 85 | 0 | 0 | 0 | 9 | 0 | 510885 | 16340 | 494544 | 134613 | 119405 | 0 | 0 | 0 | 119405 | 119405 | 0 | -376272 | 9 | 0 | 0 | -265512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -110760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -376272 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-01-14 | QTR3 | 14/15 | 2014-11-07 | QTR2 | 14/15 | 412 | 343149.34 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | BDU54 | 41299435213 | 2012-06-11 | QTR4 | 11/12 | 5 | 15 | 360 | 637 | 918 | -281 | 281 | 0 | 46 | 231 | 20846867 | 150000 | 20696867 | 22943912 | 22943912 | 0 | 0 | 0 | 22943912 | 22943912 | 0 | 2097045 | 18 | 0 | 187 | 705821 | 43487 | 0 | 0 | 220100 | 34968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 1321124 | 73171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 2247045 | 151627 | F593483018 | WELBRO BUILDING CORPORATION | N/A | N/A | N/A | N/A | 2015-03-10 | QTR3 | 14/15 | 2015-02-06 | QTR3 | 14/15 | 507 | 20831867 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | BDV94 | 42344695204 | 2013-03-04 | QTR3 | 12/13 | 1 | 3 | 100 | 195 | 191 | 4 | 0 | 0 | 10 | 85 | 554250 | 35000 | 519250 | 673855 | 638855 | 0 | 0 | 0 | 638855 | 638855 | 0 | 119605 | 2 | 0 | 0 | 0 | 0 | 0 | 63 | 119605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 119605 | 0 | F232938638 | GREGORI CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-08-11 | QTR1 | 14/15 | 2014-01-03 | QTR3 | 13/14 | 507 | 601014.98 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 22 | 8 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5322 | 23839545201 | 2011-07-27 | QTR1 | 11/12 | 3 | 5 | 660 | 1050 | 1050 | 0 | 0 | 0 | 122 | 268 | 16278889 | 200000 | 16078889 | 17781760 | 18052209 | 0 | 0 | 0 | 18052209 | 18046412 | -5797 | 1502871 | 84 | 0 | 2 | 181385 | 0 | 0 | 264 | 1352063 | 656900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268 | 1537048 | 656900 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-12-08 | QTR2 | 14/15 | 2014-07-27 | QTR1 | 14/15 | 515 | 20574418.63 |  |  | 18 | 38 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5401 | 42201515201 | 2013-04-24 | QTR4 | 12/13 | 4 | 4 | 290 | 345 | 361 | -16 | 16 | 0 | 50 | 5 | 4603457 | 50000 | 4553457 | 4721215 | 4590801 | -37984 | 0 | -37984 | 4552817 | 4552297 | -520 | 117758 | 32 | 0 | 5 | 53464 | 12260 | 0 | 0 | 115937 | 13247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 169401 | 25507 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-02-09 | QTR3 | 14/15 | 2014-08-18 | QTR1 | 14/15 | 509 | 4500359.97 |  |  | 3 | 18 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5413 | 23953525201 | 2012-04-25 | QTR4 | 11/12 | 1 | 1 | 560 | 641 | 641 | 0 | 0 | 0 | 69 | 12 | 7288562 | 76000 | 7212562 | 7290708 | 7262460 | 0 | 0 | 0 | 7262460 | 7196331 | -66129 | 2146 | 42 | 0 | 0 | 55238 | 0 | 0 | 0 | 5140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 60378 | 0 | F381818208 | DEWITT EXCAVATING INC. | N/A | N/A | N/A | N/A | 2014-08-22 | QTR1 | 14/15 | 2014-04-24 | QTR4 | 13/14 | 509 | 7727247.9 |  |  | 12 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5422 | 41499915201 | 2013-03-27 | QTR3 | 12/13 | 1 | 1 | 200 | 241 | 240 | 1 | 0 | 0 | 32 | 9 | 1069577 | 43000 | 1026577 | 1147357 | 1122595 | 0 | 0 | 0 | 1122595 | 1122595 | 0 | 77780 | 16 | 0 | 0 | 77780 | 0 | 0 | 9 | 39527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 117307 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-12-18 | QTR2 | 14/15 | 2014-06-27 | QTR4 | 13/14 | 509 | 919550.79 |  |  | 9 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5430 | 42741715201 | 2013-05-22 | QTR4 | 12/13 | 2 | 0 | 250 | 286 | 276 | 10 | 0 | 0 | 15 | 21 | 953616 | 42000 | 911616 | 953616 | 956091 | 0 | 0 | 0 | 956091 | 956091 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 21 | 7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 7577 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-08-20 | QTR1 | 14/15 | 2014-05-28 | QTR4 | 13/14 | 509 | 891853.25 |  |  | 21 | 7 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5434 | 42723215201 | 2013-04-30 | QTR4 | 12/13 | 3 | 1 | 290 | 325 | 317 | 8 | 0 | 0 | 35 | 0 | 3828333 | 50000 | 3778333 | 3780214 | 3778884 | 0 | 0 | 0 | 3778884 | 3778736 | -148 | -48118 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | -41371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41371 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2014-11-19 | QTR2 | 14/15 | 2014-09-03 | QTR1 | 14/15 | 513 | 3888111 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5444 | 42722815201 | 2013-05-22 | QTR4 | 12/13 | 2 | 5 | 380 | 477 | 477 | 0 | 0 | 0 | 97 | 0 | 6220488 | 50000 | 6170488 | 6853650 | 6842947 | 0 | 0 | 0 | 6842947 | 6847216 | 4269 | 633162 | 59 | 0 | 0 | 205611 | 0 | 0 | 0 | 93547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671405 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-03-30 | QTR3 | 14/15 | 2015-01-03 | QTR3 | 14/15 | 509 | 5174412.91 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5447 | 41802015201 | 2013-03-27 | QTR3 | 12/13 | 1 | 0 | 250 | 315 | 314 | 1 | 0 | 0 | 65 | 0 | 1249934 | 50000 | 1199934 | 1249934 | 1221093 | 0 | 0 | 0 | 1221093 | 1221093 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 6376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6376 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-09-09 | QTR1 | 14/15 | 2014-08-11 | QTR1 | 14/15 | 513 | 1261845.5 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5453 | 42949115201 | 2013-02-27 | QTR3 | 12/13 | 1 | 0 | 320 | 474 | 470 | 4 | 0 | 0 | 154 | 0 | 2793910 | 50000 | 2743910 | 2793910 | 2851601 | 0 | 0 | 0 | 2851601 | 2851571 | -30 | 0 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-02-13 | QTR3 | 14/15 | 2014-10-07 | QTR2 | 14/15 | 514 | 3153725.6 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5470 | 43067215201 | 2013-06-19 | QTR4 | 12/13 | 1 | 1 | 330 | 344 | 303 | 41 | 0 | 0 | 14 | 0 | 1428196 | 50000 | 1378196 | 1456196 | 1447568 | 0 | 0 | 0 | 1447568 | 1447568 | 0 | 28000 | 9 | 0 | 0 | 3529 | 0 | 0 | 0 | 66385 | 11936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68488 | 11936 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2014-09-02 | QTR1 | 14/15 | 2014-07-21 | QTR1 | 14/15 | 509 | 1674860.83 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5475 | 43018715201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 125 | 148 | 145 | 3 | 0 | 0 | 23 | 0 | 769979 | 37000 | 732979 | 769979 | 735665 | 0 | 0 | 0 | 735665 | 735665 | 0 | 0 | 22 | 0 | 0 | 875 | 0 | 0 | 0 | 1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2686 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-09-29 | QTR1 | 14/15 | 2014-06-26 | QTR4 | 13/14 | 515 | 786469.1 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5479 | 42887715201 | 2014-02-05 | QTR3 | 13/14 | 1 | 0 | 90 | 110 | 107 | 3 | 0 | 0 | 20 | 0 | 1018000 | 50000 | 968000 | 1018000 | 967574 | 0 | 0 | 0 | 967574 | 967574 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-12-08 | QTR2 | 14/15 | 2014-07-30 | QTR1 | 14/15 | 509 | 1181765.33 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5481 | 24099225201 | 2013-06-19 | QTR4 | 12/13 | 1 | 0 | 160 | 192 | 192 | 0 | 0 | 0 | 32 | 0 | 662854 | 23000 | 639854 | 662854 | 625918 | 0 | 0 | 0 | 625918 | 625918 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-07-15 | QTR1 | 14/15 | 2014-05-01 | QTR4 | 13/14 | 513 | 488486.9 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5484 | 43359515201 | 2013-06-19 | QTR4 | 12/13 | 1 | 2 | 65 | 140 | 140 | 0 | 0 | 0 | 1 | 74 | 160823 | 11000 | 149823 | 160823 | 149823 | 0 | 0 | 0 | 149823 | 149823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-07-22 | QTR1 | 14/15 | 2014-05-22 | QTR4 | 13/14 | 509 | 234402.5 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5490 | 42893415201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 70 | 71 | 67 | 4 | 0 | 0 | 1 | 0 | 299220 | 16000 | 283220 | 299220 | 281239 | 0 | 0 | 0 | 281239 | 281239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2014-12-05 | QTR2 | 14/15 | 2014-10-28 | QTR2 | 14/15 | 509 | 355403.88 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5505 | 43018225201 | 2014-04-30 | QTR4 | 13/14 | 1 | 1 | 30 | 47 | 40 | 7 | 0 | 0 | 11 | 6 | 124000 | 6000 | 118000 | 137512 | 131512 | 0 | 0 | 0 | 131512 | 131512 | 0 | 13512 | 11 | 0 | 0 | 0 | 0 | 0 | 6 | 13512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 13512 | 0 | F593484839 | BUILT-RITE CONSTRUCTION OF CENTRAL FLORI | N/A | N/A | N/A | N/A | 2014-09-04 | QTR1 | 14/15 | 2014-08-15 | QTR1 | 14/15 | 513 | 135276.27 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5R53 | 42474415201 | 2012-10-08 | QTR2 | 12/13 | 1 | 1 | 70 | 136 | 210 | -74 | 74 | 0 | 66 | 0 | 1125000 | 40000 | 1085000 | 1073026 | 1032679 | -113368 | 0 | -113368 | 919311 | 919311 | 0 | -51974 | 4 | 0 | 0 | -51974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | -51974 | 0 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2014-11-12 | QTR2 | 14/15 | 2013-12-17 | QTR2 | 13/14 | 514 | 851030.88 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5R74 | 42936215201 | 2013-06-04 | QTR4 | 12/13 | 1 | 0 | 310 | 352 | 288 | 64 | 0 | 0 | 42 | 0 | 2343983 | 50000 | 2293983 | 2343983 | 2295699 | 0 | 0 | 0 | 2295699 | 2295699 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-03-19 | QTR3 | 14/15 | 2014-07-08 | QTR1 | 14/15 | 514 | 1283485.96 | B0 | ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5R78 | 43106515201 | 2013-06-04 | QTR4 | 12/13 | 1 | 2 | 240 | 285 | 260 | 25 | 0 | 0 | 45 | 0 | 1432200 | 50000 | 1382200 | 1441797 | 1377218 | 0 | 0 | 0 | 1377218 | 1377218 | 0 | 9597 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 9597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9597 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2014-09-09 | QTR1 | 14/15 | 2014-07-24 | QTR1 | 14/15 | 513 | 2258202.53 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5R83 | 23930415201 | 2013-06-26 | QTR4 | 12/13 | 1 | 2 | 345 | 456 | 455 | 1 | 0 | 0 | 101 | 10 | 10203400 | 130000 | 10073400 | 10234439 | 10164588 | 0 | 0 | 0 | 10164588 | 10184967 | 20379 | 31039 | 67 | 13 | 10 | 66674 | 0 | 0 | 0 | 8367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 58481 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-02-19 | QTR3 | 14/15 | 2014-11-25 | QTR2 | 14/15 | 515 | 13028975.6 | A3 | ICC - DESIGN/BUILD - MINOR | 10 | 21 | 0 | 0 | -16561 | 0 |  | DO
05DO | 05 | E5R89 | 42756215201 | 2013-05-07 | QTR4 | 12/13 | 1 | 0 | 160 | 171 | 162 | 9 | 0 | 0 | 11 | 0 | 1080000 | 45000 | 1035000 | 1080000 | 1147540 | 0 | 0 | 0 | 1147540 | 1147540 | 0 | 0 | 11 | 0 | 0 | 10276 | 0 | 0 | 0 | 1868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12144 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-23 | QTR2 | 14/15 | 2014-06-16 | QTR4 | 13/14 | 515 | 978706.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W15 | 43326215201 | 2014-04-01 | QTR4 | 13/14 | 1 | 0 | 60 | 63 | 61 | 2 | 0 | 0 | 3 | 0 | 188644 | 11700 | 176944 | 188644 | 173944 | 0 | 0 | 0 | 173944 | 173944 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2014-10-06 | QTR2 | 14/15 | 2014-09-05 | QTR1 | 14/15 | 513 | 247000 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W16 | 43326515201 | 2014-04-01 | QTR4 | 13/14 | 1 | 0 | 90 | 149 | 149 | 0 | 0 | 0 | 45 | 14 | 155129 | 1244 | 153885 | 155129 | 165956 | 0 | 0 | 0 | 165956 | 165956 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | F593030434 | OLYMPUS PAINTING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-01-22 | QTR3 | 14/15 | 2014-11-13 | QTR2 | 14/15 | 590 | 127000 |  |  | 14 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W17 | 43326115201 | 2014-03-04 | QTR3 | 13/14 | 1 | 0 | 45 | 46 | 39 | 7 | 0 | 0 | 1 | 0 | 116628 | 5878 | 110750 | 116628 | 110750 | 0 | 0 | 0 | 110750 | 110750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592582830 | SIEG & SONS INC. | N/A | N/A | N/A | N/A | 2014-07-03 | QTR1 | 14/15 | 2014-06-12 | QTR4 | 13/14 | 507 | 123784 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W19 | 43107015201 | 2014-01-07 | QTR3 | 13/14 | 1 | 0 | 90 | 115 | 111 | 4 | 0 | 0 | 25 | 0 | 932822 | 50000 | 882822 | 932822 | 882819 | 0 | 0 | 0 | 882819 | 882819 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-09-17 | QTR1 | 14/15 | 2014-08-01 | QTR1 | 14/15 | 514 | 1251513.5 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W20 | 43353715201 | 2014-02-04 | QTR3 | 13/14 | 1 | 1 | 30 | 62 | 72 | -10 | 10 | 0 | 15 | 17 | 95060 | 2810 | 92250 | 95060 | 92250 | -8840 | 0 | -8840 | 83410 | 83410 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | F263976898 | AMROAD LLC | N/A | N/A | N/A | N/A | 2014-12-22 | QTR2 | 14/15 | 2014-09-16 | QTR1 | 14/15 | 513 | 60363.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W22 | 43353815201 | 2014-02-04 | QTR3 | 13/14 | 1 | 0 | 60 | 66 | 65 | 1 | 0 | 0 | 6 | 0 | 87843 | 6805 | 81038 | 87843 | 81038 | 0 | 0 | 0 | 81038 | 81038 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2014-08-07 | QTR1 | 14/15 | 2014-07-07 | QTR1 | 14/15 | 509 | 143675 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W24 | 43326715201 | 2014-04-01 | QTR4 | 13/14 | 1 | 0 | 116 | 120 | 93 | 27 | 0 | 0 | 4 | 0 | 597000 | 50000 | 547000 | 597000 | 547000 | 0 | 0 | 0 | 547000 | 547000 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2014-10-29 | QTR2 | 14/15 | 2014-09-19 | QTR1 | 14/15 | 514 | 1070116 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W34 | 41937015201 | 2014-04-01 | QTR4 | 13/14 | 1 | 0 | 80 | 83 | 82 | 1 | 0 | 0 | 3 | 0 | 365000 | 23000 | 342000 | 365000 | 345289 | 0 | 0 | 0 | 345289 | 345289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3289 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2014-09-29 | QTR1 | 14/15 | 2014-09-15 | QTR1 | 14/15 | 515 | 485000 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W48 | 42309615201 | 2014-06-24 | QTR4 | 13/14 | 1 | 0 | 110 | 127 | 126 | 1 | 0 | 0 | 17 | 0 | 475755 | 19000 | 456755 | 475755 | 456755 | 0 | 0 | 0 | 456755 | 456755 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-03-10 | QTR3 | 14/15 | 2015-02-06 | QTR3 | 14/15 | 515 | 389710.8 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6198 | 41985915201 | 2012-10-31 | QTR2 | 12/13 | 2 | 2 | 280 | 435 | 435 | 0 | 0 | 0 | 111 | 44 | 11628469 | 104247 | 11524222 | 11728469 | 10870085 | 0 | 0 | 0 | 10870085 | 10854373 | -15712 | 100000 | 56 | 36 | 0 | 21740 | 0 | 0 | 44 | 179096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 44 | 200837 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-12-18 | QTR2 | 14/15 | 2014-06-23 | QTR4 | 13/14 | 606 | 10326839.15 |  |  | 44 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6219 | 41263735201 | 2011-09-28 | QTR1 | 11/12 | 3 | 2 | 320 | 412 | 411 | 1 | 0 | 0 | 92 | 0 | 1879940 | 50000 | 1829940 | 1901780 | 1884231 | 0 | 0 | 0 | 1884231 | 1884152 | -79 | 21840 | 74 | 0 | 0 | 34535 | 0 | 0 | 0 | 2274 | 761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55844 | 761 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2014-09-12 | QTR1 | 14/15 | 2013-07-19 | QTR1 | 13/14 | 606 | 2076784.7 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6256 | 42551315201 | 2012-01-25 | QTR3 | 11/12 | 3 | 2 | 280 | 376 | 376 | 0 | 0 | 0 | 96 | 0 | 3491765 | 50000 | 3441765 | 3554006 | 3465121 | 0 | 0 | 0 | 3465121 | 3465336 | 216 | 62241 | 74 | 7 | 0 | 27522 | 0 | 0 | 0 | 33934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 61457 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-09-10 | QTR1 | 14/15 | 2013-08-23 | QTR1 | 13/14 | 606 | 3404006.95 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6257 | 42514515201 | 2012-02-29 | QTR3 | 11/12 | 7 | 3 | 300 | 575 | 571 | 4 | 0 | 0 | 233 | 42 | 6803533 | 72281 | 6731252 | 6805439 | 6562695 | 0 | 0 | 0 | 6562695 | 6528724 | -33971 | 1906 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 35325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 42 | 7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 42 | 42399 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-01 | QTR2 | 14/15 | 2014-01-09 | QTR3 | 13/14 | 606 | 7124777.15 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6274 | 42563715202 | 2012-04-25 | QTR4 | 11/12 | 3 | 1 | 220 | 356 | 356 | 0 | 0 | 0 | 136 | 0 | 3389619 | 50000 | 3339619 | 3415244 | 3434878 | 0 | 0 | 0 | 3434878 | 3408033 | -26845 | 25625 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44169 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-05 | QTR1 | 14/15 | 2013-09-15 | QTR1 | 13/14 | 606 | 3192722.38 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6277 | 41247355201 | 2012-03-28 | QTR3 | 11/12 | 6 | 2 | 200 | 468 | 481 | -13 | 13 | 0 | 68 | 200 | 973813 | 39869 | 933944 | 1084662 | 1056849 | -18384 | 0 | -18384 | 1038465 | 1038465 | 0 | 110849 | 29 | 0 | 0 | 1804 | 0 | 0 | 0 | 37953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 80849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120606 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-09-26 | QTR1 | 14/15 | 2014-01-30 | QTR3 | 13/14 | 606 | 887142.75 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6283 | 42915915201 | 2013-06-19 | QTR4 | 12/13 | 4 | 5 | 250 | 376 | 375 | 1 | 0 | 0 | 126 | 0 | 2420034 | 50000 | 2370034 | 2716910 | 2586180 | 0 | 0 | 0 | 2586180 | 2586385 | 206 | 296876 | 109 | 0 | 0 | 226424 | 0 | 0 | 0 | 65580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317311 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-03-05 | QTR3 | 14/15 | 2014-12-11 | QTR2 | 14/15 | 606 | 2632098.25 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6286 | 42827915201 | 2013-02-27 | QTR3 | 12/13 | 4 | 1 | 180 | 227 | 227 | 0 | 0 | 0 | 47 | 0 | 1727127 | 120000 | 1607127 | 1737127 | 1574494 | 0 | 0 | 0 | 1574494 | 1574494 | 0 | 10000 | 34 | 0 | 0 | 8977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17168 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2014-07-07 | QTR1 | 14/15 | 2014-04-17 | QTR4 | 13/14 | 606 | 1754775.45 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6289 | 42914415201 | 2013-04-24 | QTR4 | 12/13 | 4 | 0 | 130 | 223 | 223 | 0 | 0 | 0 | 93 | 0 | 1574706 | 50000 | 1524706 | 1574706 | 1468896 | 0 | 0 | 0 | 1468896 | 1468672 | -224 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15663 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-06 | QTR2 | 14/15 | 2014-03-22 | QTR3 | 13/14 | 606 | 1515264.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6292 | 42527115201 | 2013-03-27 | QTR3 | 12/13 | 4 | 3 | 180 | 264 | 264 | 0 | 0 | 0 | 79 | 5 | 1776432 | 50000 | 1726432 | 1782401 | 1728838 | 0 | 0 | 0 | 1728838 | 1728477 | -361 | 5969 | 56 | 0 | 5 | 43189 | 26824 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 5969 | 26824 | F590895890 | WILLIAMS PAVING COMPANY INC. | N/A | N/A | N/A | N/A | 2014-07-22 | QTR1 | 14/15 | 2014-02-28 | QTR3 | 13/14 | 606 | 1922112.65 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6294 | 25023635201 | 2013-02-06 | QTR3 | 12/13 | 5 | 2 | 430 | 564 | 564 | 0 | 0 | 0 | 104 | 30 | 6142510 | 52222 | 6090288 | 6260112 | 6132269 | 0 | 0 | 0 | 6132269 | 6128940 | -3329 | 117602 | 58 | 9 | 0 | 17693 | 0 | 0 | 0 | 35185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30 | 101504 | 94459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12150 | 7256 | 0 | 0 | 0 | 0 | 15 | 30 | 166533 | 101714 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-03-20 | QTR3 | 14/15 | 2014-12-18 | QTR2 | 14/15 | 606 | 5163835.05 | B1:B2 | ACC - NO EXCUSE BONUS:ACC - A+B (COST+TIME BIDDING) | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6296 | 42848615201 | 2013-04-24 | QTR4 | 12/13 | 2 | 0 | 160 | 246 | 246 | 0 | 0 | 0 | 86 | 0 | 2559781 | 50000 | 2509781 | 2559781 | 2436245 | 0 | 0 | 0 | 2436245 | 2435764 | -481 | 0 | 78 | 0 | 0 | 7730 | 0 | 0 | 0 | 21328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29058 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-01-09 | QTR3 | 14/15 | 2014-09-15 | QTR1 | 14/15 | 606 | 2814516.15 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6298 | 25168835201 | 2012-09-12 | QTR1 | 12/13 | 1 | 4 | 420 | 511 | 511 | 0 | 0 | 0 | 91 | 0 | 4246242 | 59864 | 4186378 | 4389022 | 4329187 | 0 | 0 | 0 | 4329187 | 4315357 | -13831 | 142780 | 62 | 0 | 0 | 97129 | 0 | 14 | 0 | 77412 | 15360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 170821 | 15360 | F650220703 | ODEBRECHT CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-10-14 | QTR2 | 14/15 | 2014-06-22 | QTR4 | 13/14 | 606 | 5988419.9 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6302 | 24961485201 | 2013-02-27 | QTR3 | 12/13 | 1 | 0 | 125 | 174 | 173 | 1 | 0 | 0 | 49 | 0 | 1928019 | 50000 | 1878019 | 1928019 | 1840895 | 0 | 0 | 0 | 1840895 | 1839871 | -1023 | 0 | 46 | 0 | 0 | 35104 | 0 | 0 | 0 | 3323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38427 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-05 | QTR1 | 14/15 | 2013-11-08 | QTR2 | 13/14 | 606 | 2088604.55 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6304 | 40557555201 | 2013-02-06 | QTR3 | 12/13 | 1 | 2 | 250 | 367 | 365 | 2 | 0 | 0 | 117 | 0 | 4441233 | 50000 | 4391233 | 4506233 | 4520669 | 0 | 0 | 0 | 4520669 | 4514737 | -5932 | 65000 | 80 | 0 | 0 | 40401 | 0 | 21 | 0 | 71736 | 50700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 112137 | 50700 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-09-23 | QTR1 | 14/15 | 2014-04-28 | QTR4 | 13/14 | 606 | 4729314.9 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6306 | 42847615201 | 2012-10-31 | QTR2 | 12/13 | 2 | 0 | 170 | 237 | 237 | 0 | 0 | 0 | 67 | 0 | 1150126 | 50000 | 1100126 | 1150126 | 1099652 | 0 | 0 | 0 | 1099652 | 1097498 | -2153 | 0 | 60 | 0 | 0 | 12845 | 0 | 0 | 0 | 8512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21357 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-09-05 | QTR1 | 14/15 | 2013-09-11 | QTR1 | 13/14 | 606 | 1107477.6 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6307 | 42751715201 | 2012-10-31 | QTR2 | 12/13 | 3 | 0 | 300 | 433 | 432 | 1 | 0 | 0 | 133 | 0 | 3138611 | 50000 | 3088611 | 3138611 | 3086278 | 0 | 0 | 0 | 3086278 | 3082048 | -4230 | 0 | 112 | 0 | 0 | 17610 | 0 | 0 | 0 | 24868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42478 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-21 | QTR1 | 14/15 | 2014-05-30 | QTR4 | 13/14 | 606 | 3015901.78 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6310 | 42848415201 | 2013-05-22 | QTR4 | 12/13 | 3 | 3 | 200 | 271 | 271 | 0 | 0 | 0 | 71 | 0 | 2643396 | 51770 | 2591626 | 2747670 | 2738183 | 0 | 0 | 0 | 2738183 | 2739220 | 1037 | 104274 | 48 | 5 | 0 | 21554 | 0 | 5 | 0 | 110809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16249 | 10114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 148612 | 10114 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-10-30 | QTR2 | 14/15 | 2014-07-25 | QTR1 | 14/15 | 606 | 2596227.9 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6317 | 42558215201 | 2013-06-19 | QTR4 | 12/13 | 1 | 1 | 150 | 177 | 175 | 2 | 0 | 0 | 27 | 0 | 611611 | 17500 | 594111 | 642192 | 597121 | 0 | 0 | 0 | 597121 | 597121 | 0 | 30581 | 14 | 0 | 0 | 19071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18415 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-07-17 | QTR1 | 14/15 | 2014-05-14 | QTR4 | 13/14 | 606 | 528419 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6321 | 42914615201 | 2013-08-28 | QTR1 | 13/14 | 3 | 2 | 200 | 271 | 271 | 0 | 0 | 0 | 71 | 0 | 1568943 | 50930 | 1518013 | 1572068 | 1511503 | 0 | 0 | 0 | 1511503 | 1510404 | -1099 | 3125 | 66 | 0 | 0 | 834 | 0 | 0 | 0 | 8694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43828 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-02-06 | QTR3 | 14/15 | 2014-11-18 | QTR2 | 14/15 | 606 | 1671944.25 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6326 | 42848025201 | 2013-06-19 | QTR4 | 12/13 | 2 | 1 | 150 | 222 | 221 | 1 | 0 | 0 | 72 | 0 | 598775 | 28167 | 570608 | 626792 | 663757 | 0 | 0 | 0 | 663757 | 663757 | 0 | 28017 | 69 | 0 | 0 | 7737 | 0 | 0 | 0 | 27937 | 6179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35674 | 6179 | F650806153 | AGC ELECTRIC INC. | N/A | N/A | N/A | N/A | 2014-10-06 | QTR2 | 14/15 | 2014-08-28 | QTR1 | 14/15 | 606 | 583862.15 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6354 | 43076115201 | 2014-04-30 | QTR4 | 13/14 | 2 | 0 | 100 | 120 | 103 | 17 | 0 | 0 | 20 | 0 | 264539 | 14210 | 250329 | 264539 | 257147 | 0 | 0 | 0 | 257147 | 257147 | 0 | 0 | 10 | 0 | 0 | 8395 | 0 | 0 | 0 | 766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9161 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-01-30 | QTR3 | 14/15 | 2014-12-29 | QTR2 | 14/15 | 606 | 308910 | B0 | ACC - LUMP SUM | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6H35 | 41809425201 | 2013-06-27 | QTR4 | 12/13 | 2 | 0 | 140 | 214 | 218 | -4 | 4 | 0 | 62 | 12 | 647361 | 20711 | 626650 | 647361 | 646164 | -6128 | 0 | -6128 | 640036 | 640036 | 0 | 0 | 13 | 7 | 0 | 7322 | 0 | 28 | 12 | 12192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 12 | 19514 | 0 | F650838100 | SUPERIOR LANDSCAPING & LAWN SERVICE INC | N/A | N/A | N/A | N/A | 2015-02-10 | QTR3 | 14/15 | 2014-05-28 | QTR4 | 13/14 | 606 | 434916.5 | B0 | ACC - LUMP SUM | 12 | 14 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6H42 | 42999715201 | 2013-06-27 | QTR4 | 12/13 | 1 | 0 | 400 | 485 | 481 | 4 | 0 | 0 | 85 | 0 | 2888376 | 50000 | 2838376 | 2888376 | 2518315 | 0 | 0 | 0 | 2518315 | 2518314 | 0 | 0 | 54 | 2 | 0 | 0 | 0 | 0 | 0 | 3545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3545 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2015-03-05 | QTR3 | 14/15 | 2015-01-23 | QTR3 | 14/15 | 606 | 1952251.75 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6H55 | 42999515201 | 2013-07-25 | QTR1 | 13/14 | 1 | 2 | 360 | 377 | 290 | 87 | 0 | 0 | 17 | 0 | 2196108 | 50000 | 2146108 | 2547091 | 2355415 | 0 | 0 | 0 | 2355415 | 2355414 | -1 | 350983 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356705 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-01-09 | QTR3 | 14/15 | 2014-12-03 | QTR2 | 14/15 | 606 | 3793360.4 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6H89 | 42934715201 | 2013-10-31 | QTR2 | 13/14 | 2 | 0 | 140 | 185 | 185 | 0 | 0 | 0 | 45 | 0 | 1656869 | 10675 | 1646194 | 1656869 | 1642271 | 0 | 0 | 0 | 1642271 | 1642337 | 66 | 0 | 38 | 5 | 0 | 3933 | 0 | 0 | 0 | 2992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 6925 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-01-26 | QTR3 | 14/15 | 2014-08-06 | QTR1 | 14/15 | 606 | 1957425 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I00 | 42914915201 | 2014-08-28 | QTR1 | 14/15 | 1 | 0 | 60 | 68 | 68 | 0 | 0 | 0 | 8 | 0 | 97909 | 4409 | 93500 | 97909 | 95480 | 0 | 0 | 0 | 95480 | 95480 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2015-03-31 | QTR3 | 14/15 | 2015-03-13 | QTR3 | 14/15 | 606 | 92584.58 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I06 | 42914315201 | 2014-01-30 | QTR3 | 13/14 | 1 | 0 | 90 | 106 | 106 | 0 | 0 | 0 | 16 | 0 | 511391 | 23247 | 488144 | 511391 | 492255 | 0 | 0 | 0 | 492255 | 492255 | 0 | 0 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-10-23 | QTR2 | 14/15 | 2014-09-15 | QTR1 | 14/15 | 606 | 488186.85 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I10 | 25168455201 | 2013-09-26 | QTR1 | 13/14 | 1 | 0 | 180 | 207 | 204 | 3 | 0 | 0 | 27 | 0 | 1336493 | 50000 | 1286493 | 1336493 | 1270841 | 0 | 0 | 0 | 1270841 | 1270806 | -35 | 0 | 24 | 0 | 0 | 2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2014-09-10 | QTR1 | 14/15 | 2014-07-28 | QTR1 | 14/15 | 606 | 1445286.04 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I12 | 43195115201 | 2013-11-21 | QTR2 | 13/14 | 1 | 0 | 100 | 172 | 171 | 1 | 0 | 0 | 72 | 0 | 328770 | 16810 | 311960 | 328770 | 319896 | 0 | 0 | 0 | 319896 | 319896 | 0 | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 1482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-02-09 | QTR3 | 14/15 | 2014-11-19 | QTR2 | 14/15 | 606 | 353008.1 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I21 | 42914515201 | 2013-11-21 | QTR2 | 13/14 | 2 | 0 | 140 | 174 | 174 | 0 | 0 | 0 | 34 | 0 | 917461 | 45355 | 872106 | 917461 | 804065 | 0 | 0 | 0 | 804065 | 804065 | 0 | 0 | 30 | 0 | 0 | 8080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8080 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-10-24 | QTR2 | 14/15 | 2014-09-08 | QTR1 | 14/15 | 606 | 936667.9 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I40 | 42916235201 | 2013-08-29 | QTR1 | 13/14 | 2 | 0 | 120 | 129 | 128 | 1 | 0 | 0 | 9 | 0 | 876233 | 50480 | 825753 | 876233 | 842419 | 0 | 0 | 0 | 842419 | 842419 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 4438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4438 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-20 | QTR1 | 14/15 | 2014-05-20 | QTR4 | 13/14 | 606 | 1053760.7 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I41 | 42918815201 | 2014-02-27 | QTR3 | 13/14 | 2 | 1 | 180 | 220 | 160 | 60 | 0 | 0 | 40 | 0 | 3051904 | 51000 | 3000904 | 3101904 | 2954581 | 0 | 100000 | 100000 | 3054581 | 2976280 | -78302 | 50000 | 36 | 0 | 0 | 3713 | 0 | 0 | 0 | 96287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-01-13 | QTR3 | 14/15 | 2014-11-02 | QTR2 | 14/15 | 606 | 3242256.25 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I50 | 43117115201 | 2014-07-31 | QTR1 | 14/15 | 1 | 0 | 80 | 100 | 89 | 11 | 0 | 0 | 20 | 0 | 614838 | 32795 | 582043 | 614838 | 556562 | 0 | 0 | 0 | 556562 | 556562 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-03-19 | QTR3 | 14/15 | 2015-01-07 | QTR3 | 14/15 | 606 | 688700.25 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7145 | 25558515201 | 2011-05-25 | QTR4 | 10/11 | 3 | 4 | 880 | 1018 | 1018 | 0 | 0 | 0 | 138 | 0 | 14782862 | 150000 | 14632862 | 14840038 | 14923334 | 0 | 0 | 0 | 14923334 | 14855530 | -67804 | 57175 | 86 | 0 | 0 | 11606 | 0 | 0 | 0 | 159130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170736 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2015-03-04 | QTR3 | 14/15 | 2014-05-24 | QTR4 | 13/14 | 714 | 19051619.67 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7215 | 25715515201 | 2011-04-27 | QTR4 | 10/11 | 4 | 14 | 775 | 875 | 875 | 0 | 0 | 0 | 84 | 16 | 16908928 | 150000 | 16758928 | 17117199 | 16333232 | 0 | 0 | 0 | 16333232 | 16338017 | 4785 | 208271 | 55 | 0 | 16 | 208072 | 2084 | 0 | 0 | 127926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -93114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 328843 | 2084 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-08-11 | QTR1 | 14/15 | 2013-12-23 | QTR2 | 13/14 | 709 | 16235635 |  |  | 16 | 29 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7306 | 42152415201 | 2012-06-06 | QTR4 | 11/12 | 1 | 3 | 600 | 718 | 701 | 17 | 0 | 0 | 118 | 0 | 7218846 | 64000 | 7154846 | 7457221 | 7033415 | 0 | 0 | 0 | 7033415 | 7024970 | -8445 | 238375 | 76 | 0 | 0 | 14639 | 0 | 0 | 0 | 261306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275945 | 0 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-12-09 | QTR2 | 14/15 | 2014-08-05 | QTR1 | 14/15 | 717 | 6826296.6 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7312 | 42716515201 | 2013-02-06 | QTR3 | 12/13 | 1 | 2 | 365 | 432 | 421 | 11 | 0 | 0 | 67 | 0 | 6969069 | 60000 | 6909069 | 7176465 | 7341593 | 0 | 0 | 0 | 7341593 | 7330210 | -11383 | 207396 | 47 | 0 | 0 | 3764 | 0 | 0 | 0 | 211308 | 207396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215071 | 207396 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-08-27 | QTR1 | 14/15 | 2014-07-08 | QTR1 | 14/15 | 717 | 6739999.01 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7313 | 42896015201 | 2013-07-31 | QTR1 | 13/14 | 1 | 0 | 150 | 164 | 148 | 16 | 0 | 0 | 14 | 0 | 1385209 | 50000 | 1335209 | 1385209 | 1350699 | 0 | 0 | 0 | 1350699 | 1351385 | 686 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5700 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-07-11 | QTR1 | 14/15 | 2014-03-03 | QTR3 | 13/14 | 798 | 1507561.7 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7315 | 42715015201 | 2013-02-27 | QTR3 | 12/13 | 1 | 1 | 230 | 375 | 375 | 0 | 0 | 0 | 113 | 32 | 2464444 | 50000 | 2414444 | 2519444 | 2482385 | 0 | 0 | 0 | 2482385 | 2479294 | -3091 | 55000 | 90 | 0 | 3 | 23479 | 0 | 0 | 29 | 61845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 85878 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-02-17 | QTR3 | 14/15 | 2014-05-22 | QTR4 | 13/14 | 798 | 2475000 |  |  | 28 | 23 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7316 | 43232815201 | 2013-03-27 | QTR3 | 12/13 | 5 | 0 | 325 | 345 | 345 | 0 | 0 | 0 | 20 | 0 | 2398657 | 50000 | 2348657 | 2398657 | 2325044 | 0 | 0 | 0 | 2325044 | 2324965 | -79 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-07-31 | QTR1 | 14/15 | 2014-05-13 | QTR4 | 13/14 | 717 | 2025384 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7318 | 42455215201 | 2013-04-24 | QTR4 | 12/13 | 3 | 1 | 220 | 335 | 335 | 0 | 0 | 0 | 115 | 0 | 5017437 | 50000 | 4967437 | 5021145 | 5017012 | 0 | 0 | 0 | 5017012 | 5015310 | -1702 | 3708 | 96 | 0 | 0 | 6938 | 0 | 0 | 0 | 7166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14104 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-10-29 | QTR2 | 14/15 | 2014-06-02 | QTR4 | 13/14 | 717 | 4985000 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7319 | 42714815201 | 2013-04-24 | QTR4 | 12/13 | 2 | 0 | 200 | 274 | 283 | -9 | 9 | 0 | 74 | 0 | 2862257 | 50000 | 2812257 | 2862257 | 3093254 | -21366 | 0 | -21366 | 3071888 | 3071316 | -572 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | F900095113 | RAINEY CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-09-16 | QTR1 | 14/15 | 2014-04-11 | QTR4 | 13/14 | 798 | 3571073 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7320 | 42716215201 | 2013-05-22 | QTR4 | 12/13 | 1 | 1 | 330 | 428 | 428 | 0 | 0 | 0 | 98 | 0 | 6688741 | 60000 | 6628741 | 6711402 | 6714167 | 0 | 0 | 0 | 6714167 | 6717183 | 3015 | 22661 | 40 | 0 | 0 | 22661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22661 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-02-26 | QTR3 | 14/15 | 2014-09-30 | QTR1 | 14/15 | 709 | 6752451.38 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7321 | 42715325201 | 2013-03-27 | QTR3 | 12/13 | 1 | 1 | 139 | 215 | 220 | -5 | 5 | 0 | 47 | 29 | 464335 | 19000 | 445335 | 474055 | 463114 | -4830 | 0 | -4830 | 458284 | 458284 | 0 | 9720 | 30 | 0 | 0 | 0 | 0 | 0 | 29 | 17079 | 9720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 17079 | 9720 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2014-07-09 | QTR1 | 14/15 | 2014-03-05 | QTR3 | 13/14 | 798 | 380000 |  |  | 29 | 17 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7327 | 42900815201 | 2013-08-28 | QTR1 | 13/14 | 1 | 0 | 145 | 165 | 165 | 0 | 0 | 0 | 20 | 0 | 1393333 | 50000 | 1343333 | 1393333 | 1317331 | 0 | 0 | 0 | 1317331 | 1317300 | -31 | 0 | 19 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-12-30 | QTR2 | 14/15 | 2014-06-19 | QTR4 | 13/14 | 717 | 1390033 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7332 | 42896615201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 100 | 172 | 172 | 0 | 0 | 0 | 72 | 0 | 1602900 | 50000 | 1552900 | 1602900 | 1581283 | 0 | 0 | 0 | 1581283 | 1581643 | 360 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 | 2014-09-06 | QTR1 | 14/15 | 717 | 1750000 | B0 | ACC - LUMP SUM | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7333 | 25705025201 | 2013-08-28 | QTR1 | 13/14 | 1 | 0 | 90 | 191 | 191 | 0 | 0 | 0 | 15 | 86 | 615166 | 25000 | 590166 | 615166 | 597766 | 0 | 0 | 0 | 597766 | 597766 | 0 | 0 | 12 | 0 | 26 | 2255 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 2255 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2014-12-30 | QTR2 | 14/15 | 2014-10-14 | QTR2 | 14/15 | 714 | 588987 |  |  | 86 | 3 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7336 | 42900715201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 70 | 81 | 81 | 0 | 0 | 0 | 11 | 0 | 899650 | 38000 | 861650 | 899650 | 831750 | 0 | 0 | 0 | 831750 | 831750 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-07-01 | QTR1 | 14/15 | 2014-03-27 | QTR3 | 13/14 | 709 | 830000 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7338 | 43339215201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 145 | 147 | 143 | 4 | 0 | 0 | 2 | 0 | 339122 | 12500 | 326622 | 339122 | 340142 | 0 | 0 | 0 | 340142 | 340142 | 0 | 0 | 1 | 0 | 0 | 710 | 0 | 0 | 0 | 3769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4479 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-02-12 | QTR3 | 14/15 | 2014-08-20 | QTR1 | 14/15 | 717 | 334189.35 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7342 | 43304515201 | 2014-02-05 | QTR3 | 13/14 | 1 | 0 | 105 | 111 | 66 | 45 | 0 | 0 | 6 | 0 | 492500 | 20000 | 472500 | 492500 | 472500 | 0 | 0 | 0 | 472500 | 472500 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-09-10 | QTR1 | 14/15 | 2014-06-18 | QTR4 | 13/14 | 717 | 473311 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7344 | 42907735201 | 2014-02-26 | QTR3 | 13/14 | 1 | 0 | 60 | 60 | 14 | 46 | 0 | 0 | 0 | 0 | 273786 | 5800 | 267986 | 273786 | 266951 | 0 | 0 | 0 | 266951 | 266951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-01-08 | QTR3 | 14/15 | 2014-10-29 | QTR2 | 14/15 | 717 | 157000 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7H15 | 42347915201 | 2011-04-13 | QTR4 | 10/11 | 1 | 0 | 365 | 402 | 343 | 59 | 0 | 0 | 37 | 0 | 1489801 | 50000 | 1439801 | 1489801 | 1397774 | 0 | 0 | 0 | 1397774 | 1397774 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593273147 | INLAND CONSTRUCTION AND EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-01-08 | QTR3 | 14/15 | 2012-06-28 | QTR4 | 11/12 | 738 | 1900000 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I10 | 41664135201 | 2012-08-08 | QTR1 | 12/13 | 1 | 0 | 500 | 604 | 591 | 13 | 0 | 0 | 104 | 0 | 2609000 | 50000 | 2559000 | 2609000 | 2539098 | 0 | 0 | 0 | 2539098 | 2539098 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4304 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-10-30 | QTR2 | 14/15 | 2014-07-10 | QTR1 | 14/15 | 738 | 2255500 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I12 | 42716115201 | 2013-02-13 | QTR3 | 12/13 | 1 | 2 | 250 | 291 | 291 | 0 | 0 | 0 | 41 | 0 | 3211501 | 50000 | 3161501 | 3241645 | 3087832 | 0 | 0 | 0 | 3087832 | 3087171 | -661 | 30144 | 24 | 0 | 0 | 7970 | 2468 | 0 | 0 | 22174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30144 | 2468 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-07-22 | QTR1 | 14/15 | 2014-02-25 | QTR3 | 13/14 | 709 | 2968524.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I20 | 42716015201 | 2013-05-29 | QTR4 | 12/13 | 1 | 0 | 250 | 306 | 306 | 0 | 0 | 0 | 56 | 0 | 2103847 | 50000 | 2053847 | 2103847 | 2012521 | 0 | 0 | 0 | 2012521 | 2015180 | 2659 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 5906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5906 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-09-08 | QTR1 | 14/15 | 2014-06-08 | QTR4 | 13/14 | 717 | 1798723 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I27 | 42470715201 | 2013-05-08 | QTR4 | 12/13 | 2 | 1 | 60 | 61 | 59 | 2 | 0 | 0 | 1 | 0 | 262455 | 12000 | 250455 | 288455 | 274422 | 0 | 0 | 0 | 274422 | 274422 | 0 | 26000 | 1 | 0 | 0 | 1756 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27756 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2014-07-10 | QTR1 | 14/15 | 2013-11-27 | QTR2 | 13/14 | 709 | 250000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I65 | 42950015201 | 2013-08-14 | QTR1 | 13/14 | 2 | 0 | 120 | 154 | 153 | 1 | 0 | 0 | 24 | 10 | 545794 | 15000 | 530794 | 545794 | 534041 | 0 | 0 | 0 | 534041 | 534041 | 0 | 0 | 20 | 0 | 0 | 4095 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4095 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2014-09-03 | QTR1 | 14/15 | 2014-07-26 | QTR1 | 14/15 | 717 | 363220 |  |  | 10 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I73 | 42888215201 | 2014-03-12 | QTR3 | 13/14 | 1 | 0 | 80 | 83 | 67 | 16 | 0 | 0 | 3 | 0 | 161753 | 4000 | 157753 | 161753 | 168071 | 0 | 0 | 0 | 168071 | 168071 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-01-12 | QTR3 | 14/15 | 2014-09-04 | QTR1 | 14/15 | 717 | 90000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I74 | 42888225201 | 2014-03-12 | QTR3 | 13/14 | 1 | 0 | 80 | 115 | 115 | 0 | 0 | 0 | 27 | 8 | 174384 | 8300 | 166084 | 174384 | 173484 | 0 | 0 | 0 | 173484 | 173484 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 7400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 7400 | 0 | F030562259 | VIKTOR CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2015-01-26 | QTR3 | 14/15 | 2014-12-02 | QTR2 | 14/15 | 709 | 180597.9 |  |  | 8 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I75 | 42895915201 | 2014-03-12 | QTR3 | 13/14 | 1 | 0 | 150 | 161 | 161 | 0 | 0 | 0 | 11 | 0 | 1272505 | 40000 | 1232505 | 1272505 | 1236184 | 0 | 0 | 0 | 1236184 | 1236184 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3679 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-02-10 | QTR3 | 14/15 | 2014-12-13 | QTR2 | 14/15 | 709 | 869000 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I79 | 43070915201 | 2014-03-12 | QTR3 | 13/14 | 1 | 0 | 45 | 46 | 46 | 0 | 0 | 0 | 1 | 0 | 143573 | 7300 | 136273 | 143573 | 140811 | 0 | 0 | 0 | 140811 | 140811 | 0 | 0 | 0 | 0 | 0 | -2075 | 0 | 0 | 0 | 6614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4538 | 0 | F593759317 | CHEYENNE ASPHALT INCORPORATED | N/A | N/A | N/A | N/A | 2014-12-30 | QTR2 | 14/15 | 2014-11-13 | QTR2 | 14/15 | 798 | 151900 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I84 | 43253415201 | 2014-05-14 | QTR4 | 13/14 | 1 | 0 | 120 | 139 | 139 | 0 | 0 | 0 | 19 | 0 | 865555 | 50000 | 815555 | 865555 | 815555 | 0 | 0 | 0 | 815555 | 815555 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-03-09 | QTR3 | 14/15 | 2015-01-24 | QTR3 | 14/15 | 709 | 1222605 | B0 | ACC - LUMP SUM | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I86 | 43270815201 | 2014-02-12 | QTR3 | 13/14 | 1 | 1 | 140 | 242 | 211 | 31 | 0 | 0 | 102 | 0 | 570177 | 12500 | 557677 | 588876 | 579662 | 0 | 0 | 0 | 579662 | 579662 | 0 | 18699 | 60 | 0 | 0 | 3286 | 0 | 0 | 0 | 18700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21986 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-03-09 | QTR3 | 14/15 | 2015-02-09 | QTR3 | 14/15 | 709 | 415000 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7J03 | 41090965201 | 2013-07-26 | QTR1 | 13/14 | 1 | 0 | 210 | 250 | 250 | 0 | 0 | 0 | 40 | 0 | 1199414 | 42000 | 1157414 | 1199414 | 1101676 | 0 | 0 | 0 | 1101676 | 1101676 | 0 | 0 | 7 | 0 | 0 | 4903 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 4903 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2014-09-18 | QTR1 | 14/15 | 2014-08-07 | QTR1 | 14/15 | 714 | 915000 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8L44 | 42615515201 | 2011-06-14 | QTR4 | 10/11 | 4 | 8 | 505 | 662 | 662 | 0 | 0 | 0 | 102 | 55 | 12289957 | 104315 | 12185642 | 10231956 | 9993214 | 0 | 0 | 0 | 9993214 | 9995692 | 2477 | -2058001 | 64 | 0 | 55 | -2248071 | 0 | 0 | 0 | 62314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | -1990939 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-10-10 | QTR2 | 14/15 | 2013-08-14 | QTR1 | 13/14 | 854 | 10562969.59 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M46 | 42732415201 | 2013-02-26 | QTR3 | 12/13 | 2 | 8 | 380 | 465 | 458 | 7 | 0 | 0 | 56 | 29 | 5445620 | 56515 | 5389105 | 6044163 | 6171776 | 0 | 0 | 0 | 6171776 | 6166359 | -5417 | 598543 | 29 | 0 | 29 | 599131 | 113574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50320 | 14174 | 0 | 0 | 0 | 0 | 0 | 0 | -15753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 633698 | 127747 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-12-09 | QTR2 | 14/15 | 2014-08-29 | QTR1 | 14/15 | 854 | 5468996.15 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M61 | 42815415201 | 2013-03-12 | QTR3 | 12/13 | 1 | 1 | 285 | 360 | 360 | 0 | 0 | 0 | 65 | 10 | 3237604 | 50000 | 3187604 | 3287206 | 3085111 | 0 | 0 | 0 | 3085111 | 3085111 | 0 | 49603 | 24 | 0 | 7 | 38970 | 0 | 0 | 3 | 18135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 10 | 57104 | 0 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2014-07-18 | QTR1 | 14/15 | 2014-05-27 | QTR4 | 13/14 | 854 | 4295669.25 |  |  | 1 | 18 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M79 | 43107915201 | 2013-04-09 | QTR4 | 12/13 | 2 | 1 | 270 | 316 | 316 | 0 | 0 | 0 | 46 | 0 | 6589154 | 84145 | 6505009 | 6599869 | 6691510 | -10000 | 0 | -10000 | 6681510 | 6680921 | -590 | 10715 | 27 | 0 | 0 | 10649 | 0 | 0 | 0 | 16362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31470 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-01-13 | QTR3 | 14/15 | 2014-05-19 | QTR4 | 13/14 | 854 | 8498964.05 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N06 | 43245615201 | 2014-02-18 | QTR3 | 13/14 | 1 | 1 | 140 | 159 | 138 | 21 | 0 | 0 | 19 | 0 | 2777072 | 50000 | 2727072 | 2677984 | 2402653 | 0 | 0 | 0 | 2402653 | 2405693 | 3040 | -99088 | 13 | 0 | 0 | 35151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56321 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-12-10 | QTR2 | 14/15 | 2014-09-19 | QTR1 | 14/15 | 854 | 3098705.3 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N07 | 42933315201 | 2013-11-12 | QTR2 | 13/14 | 1 | 0 | 140 | 187 | 187 | 0 | 0 | 0 | 47 | 0 | 994390 | 43390 | 951000 | 994390 | 970021 | 0 | 0 | 0 | 970021 | 970021 | 0 | 0 | 36 | 0 | 0 | 11179 | 0 | 0 | 0 | 13828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25007 | 0 | F263435185 | ENGECON CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-12 | QTR2 | 14/15 | 2014-10-17 | QTR2 | 14/15 | 854 | 911270.35 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N16 | 42897315201 | 2014-03-11 | QTR3 | 13/14 | 1 | 0 | 190 | 203 | 135 | 68 | 0 | 0 | 13 | 0 | 341935 | 21935 | 320000 | 341935 | 320243 | 0 | 0 | 0 | 320243 | 320243 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 0 | F522084089 | GEMSTONE LLC | N/A | N/A | N/A | N/A | 2014-12-15 | QTR2 | 14/15 | 2014-10-28 | QTR2 | 14/15 | 854 | 460675.05 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N22 | 42902515201 | 2014-01-14 | QTR3 | 13/14 | 2 | 2 | 150 | 222 | 222 | 0 | 0 | 0 | 47 | 25 | 3404444 | 50000 | 3354444 | 4367288 | 4369052 | 0 | 0 | 0 | 4369052 | 4371216 | 2163 | 962844 | 37 | 0 | 0 | 13264 | 0 | 0 | 21 | 967946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 981210 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-03-13 | QTR3 | 14/15 | 2014-10-31 | QTR2 | 14/15 | 854 | 3784112.76 |  |  | 4 | 10 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N27 | 43368915201 | 2014-05-20 | QTR4 | 13/14 | 1 | 0 | 150 | 177 | 176 | 1 | 0 | 0 | 27 | 0 | 370616 | 14964 | 355652 | 370616 | 360379 | 0 | 0 | 0 | 360379 | 360379 | 0 | 0 | 11 | 0 | 0 | 1094 | 0 | 0 | 0 | 3632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726 | 0 | F650546351 | MANCIL'S TRACTOR SERVICE INC. | N/A | N/A | N/A | N/A | 2015-03-19 | QTR3 | 14/15 | 2015-02-09 | QTR3 | 14/15 | 854 | 314246.78 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0