## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 36119430 | 35720053 | 37715285 | 36948951 | 0 | 36468032 | 2.094% | 100% | 1705441 | 4.774% | 1595855 | 4.418% | 2338 | 262 | 11.21% | 111 | 4.748% | 15 | 0.6416% | 37 | 1.583% | 2390 | 2.224% | 2768 | 2888 | 2515 | 7.571% | 71.43%
| District Let | 16889804 | 16643447 | 17811143 | 17740932 | 0 | 17625070 | 5.898% | 71.43% | 910070 | 5.468% | 921338 | 5.455% | 1310 | 93 | 7.099% | 85 | 6.489% | 7 | 0.5344% | 308 | 23.51% | 1625 | 24.05% | 1803 | 1716 | 1538 | 17.4% | 85.71%
| All Contracts | 53009234 | 52363500 | 55526428 | 54689883 | 0 | 54093102 | 3.303% | 85.71% | 2615511 | 4.995% | 2517193 | 4.749% | 3648 | 355 | 9.731% | 196 | 5.373% | 22 | 0.6031% | 345 | 9.457% | 4015 | 10.06% | 4571 | 4604 | 4053 | 11.1% | 78.57%
2 | Central Let | 22267120 | 21964483 | 22443263 | 22575676 | 0 | 22311491 | 1.58% | 100% | 209159 | 0.9523% | 176142 | 0.791% | 945 | 241 | 25.5% | 84 | 8.889% | 38 | 4.021% | 55 | 5.82% | 1038 | 9.841% | 1368 | 1356 | 1031 | 9.101% | 83.33%
| District Let | 20325221 | 20073863 | 20230829 | 19860500 | 0 | 19610043 | -2.311% | 100% | 71427 | 0.3558% | -94392 | -0.4644% | 1599 | 149 | 9.318% | 91 | 5.691% | 0 | 0% | 66 | 4.128% | 1665 | 4.128% | 1905 | 1869 | 1629 | 1.876% | 100%
| All Contracts | 42592341 | 42038346 | 42674092 | 42436176 | 0 | 41921534 | -0.2779% | 100% | 280586 | 0.6675% | 81750 | 0.1919% | 2544 | 390 | 15.33% | 175 | 6.879% | 38 | 1.494% | 121 | 4.756% | 2703 | 6.25% | 3273 | 3225 | 2660 | 4.56% | 90%
3 | Central Let | 30248483 | 29901205 | 30916540 | 30693433 | 0 | 30455214 | 1.853% | 92.31% | 618059 | 2.067% | 668057 | 2.209% | 2698 | 774 | 28.69% | 209 | 7.746% | 75 | 2.78% | 99 | 3.669% | 2872 | 6.449% | 3855 | 3823 | 2840 | 5.263% | 100%
| District Let | 4427316 | 4277316 | 4427316 | 4401555 | 0 | 4261787 | -0.3631% | 100% | 6531 | 0.1527% | 0 | 0% | 330 | 38 | 11.52% | 32 | 9.697% | 0 | 0% | 3 | 0.9091% | 333 | 0.9091% | 403 | 402 | 332 | 0.6061% | 100%
| All Contracts | 34675799 | 34178521 | 35343856 | 35094988 | 0 | 34717001 | 1.575% | 93.75% | 624590 | 1.827% | 668057 | 1.927% | 3028 | 812 | 26.82% | 241 | 7.959% | 75 | 2.477% | 102 | 3.369% | 3205 | 5.845% | 4258 | 4225 | 3172 | 4.756% | 100%
4 | Central Let | 7393646 | 7185984 | 9457653 | 9270767 | 0 | 9167719 | 27.58% | 83.33% | 2128626 | 29.62% | 2064007 | 27.92% | 987 | 139 | 14.08% | 55 | 5.572% | 14 | 1.418% | 333 | 33.74% | 1334 | 35.16% | 1528 | 1575 | 1381 | 39.92% | 66.67%
| District Let | 5473740 | 5302340 | 5519070 | 5465928 | 0 | 5465689 | 3.081% | 100% | 90569 | 1.708% | 45331 | 0.8282% | 1096 | 78 | 7.117% | 60 | 5.474% | 45 | 4.106% | 54 | 4.927% | 1195 | 9.033% | 1333 | 1321 | 1183 | 7.938% | 100%
| All Contracts | 12867386 | 12488324 | 14976723 | 14736695 | 0 | 14633408 | 17.18% | 90% | 2219195 | 17.77% | 2109338 | 16.39% | 2083 | 217 | 10.42% | 115 | 5.521% | 59 | 2.832% | 387 | 18.58% | 2529 | 21.41% | 2861 | 2896 | 2564 | 23.09% | 80%
5 | Central Let | 62048584 | 61481584 | 64513128 | 64136636 | 0 | 63571916 | 3.4% | 100% | 2802065 | 4.558% | 2464544 | 3.972% | 2658 | 464 | 17.46% | 184 | 6.922% | 0 | 0% | 401 | 15.09% | 3059 | 15.09% | 3735 | 3943 | 3295 | 23.97% | 88.89%
| District Let | 4365063 | 4283063 | 4346259 | 4269107 | 0 | 733522 | -82.87% | 100% | -12805 | -0.299% | -18805 | -0.4308% | 585 | 6 | 1.026% | 25 | 4.274% | 0 | 0% | 15 | 2.564% | 600 | 2.564% | 631 | 626 | 595 | 1.709% | 100%
| All Contracts | 66413647 | 65764647 | 68859387 | 68405743 | 0 | 64305438 | -2.219% | 100% | 2789260 | 4.241% | 2445739 | 3.683% | 3243 | 470 | 14.49% | 209 | 6.445% | 0 | 0% | 416 | 12.83% | 3659 | 12.83% | 4366 | 4569 | 3890 | 19.95% | 91.67%
6 | Central Let | 35574479 | 34996847 | 36318119 | 37702028 | 0 | 37604540 | 7.451% | 77.78% | 1000396 | 2.859% | 743640 | 2.09% | 2440 | 696 | 28.52% | 185 | 7.582% | 116 | 4.754% | 166 | 6.803% | 2722 | 11.56% | 3603 | 3561 | 2680 | 9.836% | 100%
| District Let | 11899358 | 11490883 | 11899358 | 11215508 | 0 | 10677722 | -7.077% | 100% | 30080 | 0.2618% | 0 | 0% | 1995 | 352 | 17.64% | 117 | 5.865% | 76 | 3.81% | 8 | 0.401% | 2079 | 4.211% | 2548 | 2498 | 2029 | 1.704% | 100%
| All Contracts | 47473837 | 46487730 | 48217477 | 48917536 | 0 | 48282262 | 3.86% | 89.47% | 1030476 | 2.217% | 743640 | 1.566% | 4435 | 1048 | 23.63% | 302 | 6.809% | 192 | 4.329% | 174 | 3.923% | 4801 | 8.253% | 6151 | 6059 | 4709 | 6.178% | 100%
7 | Central Let | 27989382 | 27714382 | 28648921 | 28444448 | 0 | 28362267 | 2.338% | 100% | 710818 | 2.565% | 659540 | 2.356% | 1090 | 205 | 18.81% | 78 | 7.156% | 0 | 0% | 20 | 1.835% | 1110 | 1.835% | 1393 | 1390 | 1107 | 1.56% | 100%
| District Let | 2030000 | 1980000 | 2030000 | 1980915 | 0 | 1934577 | -2.294% | 200% | 9760 | 0.4929% | 0 | 0% | 150 | 26 | 17.33% | 7 | 4.667% | 0 | 0% | 0 | 0% | 150 | 0% | 183 | 183 | 150 | 0% | 100%
| All Contracts | 30019382 | 29694382 | 30678921 | 30425363 | 0 | 30296844 | 2.029% | 120% | 720578 | 2.427% | 659540 | 2.197% | 1240 | 231 | 18.63% | 85 | 6.855% | 0 | 0% | 20 | 1.613% | 1260 | 1.613% | 1576 | 1573 | 1257 | 1.371% | 100%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 52161110 | 51627909 | 52848306 | 52388485 | 0 | 52049359 | 0.8163% | 100% | 973051 | 1.885% | 687195 | 1.317% | 2475 | 212 | 8.566% | 199 | 8.04% | 0 | 0% | 119 | 4.808% | 2594 | 4.808% | 3005 | 2914 | 2503 | 1.131% | 0.002363%
| All Contracts | 52161110 | 51627909 | 52848306 | 52388485 | 0 | 52049359 | 0.8163% | 100% | 973051 | 1.885% | 687195 | 1.317% | 2475 | 212 | 8.566% | 199 | 8.04% | 0 | 0% | 119 | 4.808% | 2594 | 4.808% | 3005 | 2914 | 2503 | 1.131% | 100%
Totals This Qtr | Central Let | 221641124 | 218964538 | 230012909 | 229771939 | 0 | 227941179 | 4.1% | 92.59% | 9174564 | 4.19% | 8371785 | 3.777% | 13156 | 2781 | 21.14% | 906 | 6.887% | 258 | 1.961% | 1111 | 8.445% | 14525 | 10.41% | 18250 | 18536 | 14849 | 12.87% | 88.89%
| District Let | 117571612 | 115678821 | 119112281 | 117322930 | 0 | 112357769 | -2.871% | 97.3% | 2078683 | 1.797% | 1540667 | 1.31% | 9540 | 954 | 10% | 616 | 6.457% | 128 | 1.342% | 573 | 6.006% | 10241 | 7.348% | 11811 | 11529 | 9959 | 4.392% | 97.3%
| All Contracts | 339212736 | 334643359 | 349125190 | 347094869 | 0 | 340298948 | 1.69% | 94.51% | 11253247 | 3.363% | 9912452 | 2.922% | 22696 | 3735 | 16.46% | 1522 | 6.706% | 386 | 1.701% | 1684 | 7.42% | 24766 | 9.121% | 30061 | 30065 | 24808 | 9.306% | 92.31%
Totals Previous Quarter | Central Let
District Let
All Contracts
Totals Fiscal Year 2014/2015 | Central Let | 714324826 | 704915784 | 739803035 | 736872789 | 0 | 738662792 | 4.787% | 86.21% | 28465957 | 4.038% | 25479404 | 3.567% | 45283 | 6760 | 14.93% | 2500 | 5.521% | 1129 | 2.493% | 1864 | 4.116% | 48276 | 6.61% | 57604 | 57388 | 48128 | 6.283% | 90.15%
| District Let | 540522559 | 532821843 | 558558681 | 552167020 | 905160 | 551105572 | 3.431% | 92.31% | 20538700 | 3.855% | 18264346 | 3.379% | 39622 | 4420 | 11.16% | 2013 | 5.081% | 692 | 1.747% | 3075 | 7.761% | 43389 | 9.507% | 49860 | 48493 | 42060 | 6.153% | 89.56%
| All Contracts | 1254847385 | 1237737627 | 1298361716 | 1289039809 | 905160 | 1289768364 | 4.204% | 89.09% | 49004657 | 3.959% | 43743750 | 3.486% | 84905 | 11180 | 13.17% | 4513 | 5.315% | 1821 | 2.145% | 4939 | 5.817% | 91665 | 7.962% | 107464 | 105881 | 90188 | 6.222% | 89.87%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1497 | 43003715201 | 2012-03-28 | QTR3 | 11/12 | 1 | 1 | 60 | 99 | 261 | 376.7% | 0 | -162 | 162 | 0 | 39 | 0 | 90611 | 0 | 90611 | 89035 | 88897 | -43964 | 0 | -43964 | 44933 | 44933 | 49.59% | 1 | 0 | -1576 | 17 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | -1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | -1576 | 0 | F593490202 | ALDON BOOKHARDT ROOFING INC. | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 |  | 2013-05-30 | QTR4 | 12/13 | 113 | 111867.75 | B0 | ACC - LUMP SUM
| 01 | T1501 | 40828635201 | 2012-06-20 | QTR4 | 11/12 | 1 | 7 | 700 | 779 | 779 | 101.3% | 1 | 0 | 0 | 0 | 75 | 4 | 14784300 | 133862 | 14650438 | 15330267 | 14964740 | 0 | 0 | 0 | 14964740 | 15047703 | 102.7% | 1 | 82963 | 545967 | 48 | 22 | 0 | 4 | 334024 | 0 | 0 | 0 | 328205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 635924 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-09-10 | QTR1 | 15/16 |  | 2014-10-22 | QTR2 | 14/15 | 113 | 13767013.79
| 01 | T1527 | 41787615201 | 2013-02-06 | QTR3 | 12/13 | 2 | 9 | 768 | 835 | 810 | 96.74% | 1 | 25 | 0 | 0 | 67 | 0 | 12312349 | 150000 | 12162349 | 13258294 | 12897465 | 0 | 0 | 0 | 12897465 | 12514104 | 102.9% | 1 | -383360 | 945945 | 41 | 26 | 0 | 0 | 262529 | 0 | 0 | 0 | 689450 | 18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 951980 | 18277 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-10 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 115 | 15340403.45
| 01 | T1546 | 42910415201 | 2014-02-26 | QTR3 | 13/14 | 1 | 2 | 130 | 190 | 219 | 149.2% | 0 | -29 | 29 | 0 | 36 | 24 | 2195109 | 50000 | 2145109 | 2159801 | 2156391 | -50518 | 0 | -50518 | 2105873 | 2085969 | 97.24% | 1 | -19904 | -35308 | 11 | 14 | 0 | 10 | -17725 | 0 | 11 | 14 | 8387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 24 | -9339 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2015-09-13 | QTR1 | 15/16 |  | 2015-04-14 | QTR4 | 14/15 | 115 | 2641240.24 | B0 | ACC - LUMP SUM
| 01 | T1566 | 20010575201 | 2014-04-30 | QTR4 | 13/14 | 1 | 4 | 300 | 324 | 281 | 85.67% | 1 | 43 | 0 | 0 | 24 | 0 | 855140 | 0 | 855140 | 880470 | 883951 | 0 | 0 | 0 | 883951 | 883951 | 103.4% | 1 | 0 | 25330 | 14 | 10 | 0 | 0 | 17931 | 1430 | 0 | 0 | 7399 | 7399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25330 | 8829 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 |  | 2015-08-06 | QTR1 | 15/16 | 118 | 1061209.63
| 01 | T1578 | 43086015201 | 2013-12-04 | QTR2 | 13/14 | 2 | 9 | 270 | 410 | 407 | 98.89% | 1 | 3 | 0 | 0 | 140 | 0 | 5634855 | 53649 | 5581206 | 5727333 | 5707127 | 0 | 0 | 0 | 5707127 | 5640992 | 101.1% | 1 | -66135 | 92478 | 121 | 19 | 0 | 0 | 20908 | 2691 | 0 | 0 | 36741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80103 | 2691 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-07-06 | QTR1 | 15/16 |  | 2015-05-04 | QTR4 | 14/15 | 108 | 5433904.15 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1A14 | 43341115201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 110 | 131 | 131 | 108.2% | 1 | 0 | 0 | 0 | 12 | 9 | 247066 | 11866 | 235200 | 270085 | 250380 | 0 | 0 | 0 | 250380 | 250380 | 106.5% | 1 | 0 | 23019 | 10 | 2 | 0 | 9 | 23019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 23019 | 0 | F593339407 | TAGARELLI CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-08-11 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 108 | 256990.36 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 7 | 9 | 33 | 2338 | 2768 | 2888 | 71.43% | 5 | -120 | 191 | 0 | 393 | 37 | 36119430 | 399377 | 35720053 | 37715285 | 36948951 | -94482 | 0 | -94482 | 36854469 | 36468032 | 100% | 7 | -386436 | 1595855 | 262 | 111 | 4 | 23 | 640686 | 4121 | 11 | 14 | 1068606 | 25676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 37 | 1705441 | 29797
| 01 | E1J71 | 41263625201 | 2012-05-31 | QTR4 | 11/12 | 2 | 14 | 565 | 936 | 936 | 153.5% | 0 | 0 | 0 | 0 | 69 | 302 | 6703703 | 50000 | 6653703 | 7531485 | 7530256 | 0 | 0 | 0 | 7530256 | 7530256 | 113.2% | 0 | 0 | 827782 | 22 | 47 | 0 | 121 | 99861 | 9614 | 0 | 95 | 314019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 401293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 815173 | 9614 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 |  | 2015-06-08 | QTR4 | 14/15 | 113 | 638850 | A3 | ICC - DESIGN/BUILD - MINOR
| 01 | E1N08 | 42347115201 | 2014-06-19 | QTR4 | 13/14 | 1 | 4 | 200 | 242 | 242 | 106.5% | 1 | 0 | 0 | 0 | 36 | 6 | 1880948 | 50000 | 1830948 | 1908269 | 1858269 | 0 | 0 | 0 | 1858269 | 1834616 | 100.2% | 1 | -23653 | 27320 | 16 | 13 | 0 | 0 | 0 | 0 | 7 | 5 | 22343 | 8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 27320 | 8999 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-07-31 | QTR1 | 15/16 |  | 2015-06-22 | QTR4 | 14/15 | 108 | 1405116.38 | B0 | ACC - LUMP SUM
| 01 | E1N47 | 43019125201 | 2014-06-19 | QTR4 | 13/14 | 2 | 1 | 175 | 213 | 204 | 94.86% | 1 | 9 | 0 | 0 | 38 | 0 | 4346396 | 50000 | 4296396 | 4413679 | 4400332 | 0 | 0 | 0 | 4400332 | 4322422 | 100.6% | 1 | -77910 | 67283 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 67283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67283 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2015-08-13 | QTR1 | 15/16 |  | 2015-04-13 | QTR4 | 14/15 | 118 | 4460046.21 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | E1N64 | 43160515201 | 2014-08-29 | QTR1 | 14/15 | 1 | 0 | 150 | 176 | 175 | 99.33% | 1 | 1 | 0 | 0 | 26 | 0 | 3021172 | 50000 | 2971172 | 3021172 | 3068023 | 0 | 0 | 0 | 3068023 | 2921086 | 98.31% | 1 | -146936 | 0 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-25 | QTR1 | 15/16 |  | 2015-06-12 | QTR4 | 14/15 | 118 | 3419370.6
| 01 | E1N71 | 43006015201 | 2015-01-15 | QTR3 | 14/15 | 1 | 0 | 80 | 95 | 92 | 96.25% | 1 | 3 | 0 | 0 | 15 | 0 | 567387 | 27173 | 540214 | 567387 | 532744 | 0 | 0 | 0 | 532744 | 532744 | 98.62% | 1 | 0 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2015-09-23 | QTR1 | 15/16 |  | 2015-08-18 | QTR1 | 15/16 | 118 | 519186.9 | B0 | ACC - LUMP SUM
| 01 | E1N96 | 42949925201 | 2014-10-16 | QTR2 | 14/15 | 1 | 1 | 90 | 91 | 51 | 55.56% | 1 | 40 | 0 | 0 | 1 | 0 | 229418 | 9702 | 219716 | 228371 | 218669 | 0 | 0 | 0 | 218669 | 218669 | 99.52% | 1 | 0 | -1047 | 0 | 1 | 0 | 0 | -1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1047 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-07-21 | QTR1 | 15/16 |  | 2015-06-09 | QTR4 | 14/15 | 115 | 179058.8 | B0 | ACC - LUMP SUM
| 01 | E1O06 | 43574215201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 50 | 50 | 16 | 32% | 1 | 34 | 0 | 0 | 0 | 0 | 140780 | 9482 | 131298 | 140780 | 132639 | 0 | 0 | 0 | 132639 | 265277 | 202% | 0 | 132639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 0 | F650968383 | WHITELEAF LLC DBA TRAFFIC SOLUTIONS | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 |  | 2015-03-02 | QTR3 | 14/15 | 113 | 193962.81 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 7 | 9 | 20 | 1310 | 1803 | 1716 | 85.71% | 6 | 87 | 0 | 0 | 185 | 308 | 16889804 | 246357 | 16643447 | 17811143 | 17740932 | 0 | 0 | 0 | 17740932 | 17625070 | 71.43% | 5 | -115860 | 921338 | 93 | 85 | 0 | 121 | 98814 | 9614 | 7 | 100 | 404986 | 8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 401293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 308 | 910070 | 18613
| District 01 Totals |  |  |  |  | 14 | 18 | 53 | 3648 | 4571 | 4604 | 78.57% | 11 | -33 | 191 | 0 | 578 | 345 | 53009234 | 645734 | 52363500 | 55526428 | 54689883 | -94482 | 0 | -94482 | 54595401 | 54093102 | 85.71% | 12 | -502296 | 2517193 | 355 | 196 | 4 | 144 | 739500 | 13735 | 18 | 114 | 1473592 | 34675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 397442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 345 | 2615511 | 48410
| 02 | T2443 | 42698615201 | 2013-02-06 | QTR3 | 12/13 | 1 | 0 | 150 | 204 | 203 | 105.3% | 1 | 1 | 0 | 0 | 45 | 9 | 4870523 | 56040 | 4814483 | 4870523 | 4844339 | 0 | 0 | 0 | 4844339 | 4835215 | 100.4% | 1 | -9124 | 0 | 37 | 8 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-07-13 | QTR1 | 15/16 |  | 2013-12-22 | QTR2 | 13/14 | 209 | 5528433.55
| 02 | T2512 | 42869015201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 260 | 389 | 389 | 100% | 1 | 0 | 0 | 0 | 129 | 0 | 8787879 | 96597 | 8691282 | 8787879 | 8967904 | 0 | 0 | 0 | 8967904 | 8851811 | 101.8% | 1 | -116093 | 0 | 104 | 25 | 0 | 0 | 5708 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10581 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 |  | 2015-04-10 | QTR4 | 14/15 | 214 | 9570318.55
| 02 | T2527 | 42870515201 | 2014-05-21 | QTR4 | 13/14 | 1 | 2 | 195 | 311 | 311 | 111.8% | 1 | 0 | 0 | 0 | 93 | 23 | 3855596 | 50000 | 3805596 | 3937461 | 4006951 | 0 | 0 | 0 | 4006951 | 3890841 | 102.2% | 1 | -116110 | 81865 | 69 | 24 | 0 | 7 | 33849 | 0 | 0 | 16 | 66627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 100476 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 |  | 2015-06-10 | QTR4 | 14/15 | 208 | 3913298.22
| 02 | T2530 | 21156035201 | 2014-05-21 | QTR4 | 13/14 | 1 | 3 | 150 | 207 | 196 | 118.7% | 1 | 11 | 0 | 0 | 57 | 0 | 1259477 | 0 | 1259477 | 1284233 | 1254859 | 0 | 0 | 0 | 1254859 | 1254859 | 99.63% | 1 | 0 | 24756 | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 24756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 24756 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 |  | 2015-05-26 | QTR4 | 14/15 | 216 | 957005.79
| 02 | T2535 | 42053145201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 120 | 164 | 164 | 121.7% | 0 | 0 | 0 | 0 | 21 | 23 | 1754776 | 50000 | 1704776 | 1824298 | 1779783 | 0 | 0 | 0 | 1779783 | 1779783 | 104.4% | 1 | 0 | 69521 | 15 | 3 | 0 | 0 | 160 | 0 | 0 | 23 | 73186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 73346 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 |  | 2015-06-17 | QTR4 | 14/15 | 214 | 1169715.46 | B0 | ACC - LUMP SUM
| 02 | T2543 | 43055515201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 70 | 93 | 93 | 101.4% | 1 | 0 | 0 | 0 | 23 | 0 | 1738869 | 50000 | 1688869 | 1738869 | 1721840 | 0 | 0 | 0 | 1721840 | 1698982 | 100.6% | 1 | -22858 | 0 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-07-01 | QTR1 | 15/16 |  | 2015-02-13 | QTR3 | 14/15 | 214 | 1963162.15
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 6 | 6 | 6 | 945 | 1368 | 1356 | 83.33% | 5 | 12 | 0 | 0 | 368 | 55 | 22267120 | 302637 | 21964483 | 22443263 | 22575676 | 0 | 0 | 0 | 22575676 | 22311491 | 100% | 6 | -264185 | 176142 | 241 | 84 | 0 | 7 | 39717 | 0 | 0 | 48 | 168069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 55 | 209159 | 0
| 02 | E2R18 | 42468515201 | 2013-05-23 | QTR4 | 12/13 | 2 | 2 | 540 | 689 | 689 | 102.4% | 1 | 0 | 0 | 0 | 136 | 13 | 8195419 | 86278 | 8109141 | 8206705 | 8178408 | 0 | 0 | 0 | 8178408 | 8124680 | 100.2% | 1 | -53727 | 11286 | 89 | 47 | 0 | 0 | 43065 | 0 | 0 | 13 | 15182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11855 | 0 | 0 | 13 | 69534 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-08-18 | QTR1 | 15/16 |  | 2015-06-03 | QTR4 | 14/15 | 214 | 8761555.44 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2R94 | 42822915201 | 2013-08-21 | QTR1 | 13/14 | 1 | 0 | 469 | 536 | 533 | 106.2% | 1 | 3 | 0 | 0 | 35 | 32 | 2445796 | 50000 | 2395796 | 2445796 | 2450466 | 0 | 0 | 0 | 2450466 | 2449755 | 102.3% | 1 | -711 | 0 | 13 | 22 | 0 | 0 | 20184 | 0 | 0 | 32 | 14554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 49896 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-17 | QTR1 | 15/16 |  | 2015-06-12 | QTR4 | 14/15 | 216 | 2404678.02
| 02 | E2S71 | 42869515201 | 2014-04-23 | QTR4 | 13/14 | 1 | 1 | 230 | 307 | 307 | 109.1% | 1 | 0 | 0 | 0 | 56 | 21 | 7686286 | 65080 | 7621206 | 7580608 | 7142686 | 0 | 0 | 0 | 7142686 | 6953829 | 91.24% | 1 | -188858 | -105678 | 42 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 57675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105678 | 0 | 0 | 21 | -48003 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 |  | 2015-05-14 | QTR4 | 14/15 | 209 | 6348256.45
| 02 | E2S89 | 20954125201 | 2014-04-23 | QTR4 | 13/14 | 1 | 0 | 360 | 373 | 340 | 90.83% | 1 | 33 | 0 | 0 | 13 | 0 | 1997720 | 50000 | 1947720 | 1997720 | 2088940 | 0 | 0 | 0 | 2088940 | 2081779 | 106.9% | 1 | -7161 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 |  | 2015-06-16 | QTR4 | 14/15 | 208 | 2345342.1
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 4 | 5 | 3 | 1599 | 1905 | 1869 | 100% | 4 | 36 | 0 | 0 | 240 | 66 | 20325221 | 251358 | 20073863 | 20230829 | 19860500 | 0 | 0 | 0 | 19860500 | 19610043 | 100% | 4 | -250457 | -94392 | 149 | 91 | 0 | 0 | 63249 | 0 | 0 | 66 | 87411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -117533 | 0 | 0 | 66 | 71427 | 0
| District 02 Totals |  |  |  |  | 10 | 11 | 9 | 2544 | 3273 | 3225 | 90% | 9 | 48 | 0 | 0 | 608 | 121 | 42592341 | 553995 | 42038346 | 42674092 | 42436176 | 0 | 0 | 0 | 42436176 | 41921534 | 100% | 10 | -514642 | 81750 | 390 | 175 | 0 | 7 | 102966 | 0 | 0 | 114 | 255480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15157 | 0 | 0 | 0 | 1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23141 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | -117533 | 0 | 38 | 121 | 280586 | 0
| 03 | T3088 | 21894615201 | 2012-07-25 | QTR1 | 12/13 | 1 | 6 | 608 | 853 | 852 | 106.4% | 1 | 1 | 0 | 0 | 205 | 40 | 13348458 | 0 | 13348458 | 13883485 | 14095924 | 0 | 0 | 0 | 14095924 | 14095514 | 105.6% | 1 | -409 | 535027 | 149 | 56 | 0 | 0 | 90305 | 0 | 0 | 40 | 281269 | 169088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -173321 | 0 | 0 | 40 | 414064 | 169088 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 |  | 2015-02-24 | QTR3 | 14/15 | 321 | 14378815.2
| 03 | T3396 | 42323315201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 300 | 504 | 498 | 108.3% | 1 | 6 | 0 | 0 | 173 | 31 | 2789487 | 50000 | 2739487 | 2763621 | 2700963 | 0 | 0 | 0 | 2700963 | 2673321 | 97.58% | 1 | -27642 | -25866 | 154 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 17268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25866 | 0 | 0 | 31 | -8599 | 0 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-05-18 | QTR4 | 14/15 | 314 | 2906373.5
| 03 | T3401 | 42323415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 300 | 478 | 474 | 98.67% | 1 | 4 | 0 | 0 | 178 | 0 | 2645210 | 50000 | 2595210 | 2645210 | 2628131 | 0 | 0 | 0 | 2628131 | 2609172 | 100.5% | 1 | -18959 | 0 | 164 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2015-07-06 | QTR1 | 15/16 |  | 2015-05-08 | QTR4 | 14/15 | 314 | 2957617.43
| 03 | T3409 | 42462215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 145 | 201 | 197 | 97.24% | 1 | 4 | 0 | 0 | 56 | 0 | 2097227 | 50000 | 2047227 | 2097227 | 2093592 | 0 | 0 | 0 | 2093592 | 1978887 | 96.66% | 1 | -114705 | 0 | 38 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-09 | QTR1 | 15/16 |  | 2015-05-05 | QTR4 | 14/15 | 321 | 2813050.27
| 03 | T3411 | 42636815201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 130 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 66 | 0 | 577753 | 0 | 577753 | 577753 | 581122 | 0 | 0 | 0 | 581122 | 581122 | 100.6% | 1 | 0 | 0 | 62 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263312611 | R B M CONTRACTING SERVICES LLC | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 |  | 2015-07-22 | QTR1 | 15/16 | 313 | 613088.19
| 03 | T3424 | 41343515201 | 2013-02-06 | QTR3 | 12/13 | 2 | 3 | 355 | 512 | 508 | 114.1% | 1 | 4 | 0 | 0 | 142 | 15 | 3882641 | 50000 | 3832641 | 3972326 | 3728903 | 0 | 0 | 0 | 3728903 | 3719464 | 97.05% | 1 | -9439 | 89685 | 86 | 17 | 0 | 4 | 26009 | 0 | 39 | 11 | 77908 | 92400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 15 | 103918 | 92400 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 |  | 2014-09-16 | QTR1 | 14/15 | 308 | 4647469.69
| 03 | T3434 | 42987815201 | 2014-08-27 | QTR1 | 14/15 | 2 | 0 | 160 | 197 | 197 | 101.2% | 1 | 0 | 0 | 0 | 35 | 2 | 459930 | 20930 | 439000 | 459930 | 451610 | 0 | 0 | 0 | 451610 | 451610 | 102.9% | 1 | 0 | 0 | 17 | 18 | 0 | 0 | 1560 | 0 | 0 | 2 | 11050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12610 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 |  | 2015-06-15 | QTR4 | 14/15 | 313 | 439830 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 03 | T3455 | 43000415201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 150 | 176 | 176 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 919509 | 0 | 919509 | 919509 | 927409 | 0 | 0 | 0 | 927409 | 927409 | 100.9% | 1 | 0 | 0 | 24 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 |  | 2015-07-16 | QTR1 | 15/16 | 308 | 817764.49
| 03 | T3468 | 42696515201 | 2014-06-18 | QTR4 | 13/14 | 2 | 0 | 220 | 294 | 284 | 108.6% | 1 | 10 | 0 | 0 | 74 | 0 | 1826839 | 50000 | 1776839 | 1826839 | 1794755 | 0 | 0 | 0 | 1794755 | 1727691 | 97.23% | 1 | -67064 | 0 | 24 | 21 | 0 | 0 | 14633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 1080 | 0 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 18747 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 |  | 2015-06-15 | QTR4 | 14/15 | 321 | 1783054.33
| 03 | T3502 | 42764915201 | 2014-06-18 | QTR4 | 13/14 | 2 | 2 | 125 | 199 | 197 | 112.8% | 1 | 2 | 0 | 0 | 63 | 11 | 633977 | 26778 | 607199 | 703188 | 695402 | 0 | 0 | 0 | 695402 | 695402 | 114.5% | 0 | 0 | 69211 | 34 | 22 | 0 | 8 | 5089 | 0 | 0 | 3 | 70611 | 25322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 11 | 75699 | 25322 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-08-19 | QTR1 | 15/16 |  | 2015-05-21 | QTR4 | 14/15 | 308 | 559212.99
| 03 | T3530 | 43174415201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 60 | 67 | 66 | 98.33% | 1 | 1 | 0 | 0 | 7 | 0 | 217000 | 0 | 217000 | 217000 | 216611 | 0 | 0 | 0 | 216611 | 216611 | 99.82% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593715775 | PYRAMID EXCAVATION INC. | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 |  | 2015-06-19 | QTR4 | 14/15 | 321 | 236371.06
| 03 | T3535 | 42693615201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 85 | 109 | 109 | 100% | 1 | 0 | 0 | 0 | 24 | 0 | 481388 | 26436 | 454953 | 481388 | 440397 | 0 | 0 | 0 | 440397 | 440397 | 96.8% | 1 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 |  | 2015-06-21 | QTR4 | 14/15 | 313 | 540650.67
| 03 | T3536 | 40393125201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 60 | 69 | 69 | 100% | 1 | 0 | 0 | 0 | 9 | 0 | 369064 | 23136 | 345929 | 369064 | 338614 | 0 | 0 | 0 | 338614 | 338614 | 97.89% | 1 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-07-21 | QTR1 | 15/16 |  | 2015-06-13 | QTR4 | 14/15 | 321 | 486851.74
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 13 | 17 | 12 | 2698 | 3855 | 3823 | 100% | 13 | 32 | 0 | 0 | 1058 | 99 | 30248483 | 347280 | 29901205 | 30916540 | 30693433 | 0 | 0 | 0 | 30693433 | 30455214 | 92.31% | 12 | -238218 | 668057 | 774 | 209 | 0 | 12 | 137596 | 0 | 39 | 56 | 442458 | 286810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 171140 | 0 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 7 | 31 | 63020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -199187 | 0 | 75 | 99 | 618059 | 286810
| 03 | E3L71 | 42874415201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 160 | 192 | 192 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 1490639 | 50000 | 1440639 | 1490639 | 1445553 | 0 | 0 | 0 | 1445553 | 1451830 | 100.8% | 1 | 6277 | 0 | 23 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 |  | 2014-12-14 | QTR2 | 14/15 | 314 | 1584506.78
| 03 | E3M60 | 42697215201 | 2014-12-11 | QTR2 | 14/15 | 1 | 0 | 100 | 134 | 134 | 102% | 1 | 0 | 0 | 0 | 32 | 2 | 1718927 | 50000 | 1668927 | 1718927 | 1766800 | 0 | 0 | 0 | 1766800 | 1673682 | 100.3% | 1 | -93118 | 0 | 10 | 22 | 0 | 2 | 3651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3651 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-07-22 | QTR1 | 15/16 | 308 | 2202753.65
| 03 | E3M93 | 43078215201 | 2014-12-11 | QTR2 | 14/15 | 1 | 0 | 70 | 77 | 76 | 100% | 1 | 1 | 0 | 0 | 6 | 1 | 1217750 | 50000 | 1167750 | 1217750 | 1189202 | 0 | 0 | 0 | 1189202 | 1136275 | 97.3% | 1 | -52927 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2880 | 0 | F580538940 | OXFORD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-09-08 | QTR1 | 15/16 |  | 2015-07-08 | QTR1 | 15/16 | 314 | 1216619.67
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 3 | 3 | 0 | 330 | 403 | 402 | 100% | 3 | 1 | 0 | 0 | 70 | 3 | 4427316 | 150000 | 4277316 | 4427316 | 4401555 | 0 | 0 | 0 | 4401555 | 4261787 | 100% | 3 | -139768 | 0 | 38 | 32 | 0 | 2 | 3651 | 0 | 0 | 1 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6531 | 0
| District 03 Totals |  |  |  |  | 16 | 20 | 12 | 3028 | 4258 | 4225 | 100% | 16 | 33 | 0 | 0 | 1128 | 102 | 34675799 | 497280 | 34178521 | 35343856 | 35094988 | 0 | 0 | 0 | 35094988 | 34717001 | 93.75% | 15 | -377986 | 668057 | 812 | 241 | 0 | 14 | 141247 | 0 | 39 | 57 | 445338 | 286810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 171140 | 0 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 7 | 31 | 63020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -199187 | 0 | 75 | 102 | 624590 | 286810
| 04 | T4311 | 42924615201 | 2011-04-27 | QTR4 | 10/11 | 1 | 1 | 180 | 266 | 319 | 150.6% | 0 | -53 | 53 | 0 | 48 | 38 | 3983113 | 50000 | 3933113 | 4102286 | 4023382 | -101442 | 0 | -101442 | 3921940 | 3920334 | 99.68% | 1 | -1606 | 119174 | 36 | 12 | 0 | 2 | 3257 | 0 | 0 | 33 | 132841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 136098 | 0 | F593749359 | DESIGN-BUILD ENGINEERS & CONTRA | N/A | N/A | N/A | N/A | 2015-08-20 | QTR1 | 15/16 |  | 2012-05-07 | QTR4 | 11/12 | 409 | 3335896.13
| 04 | T4345 | 40836215201 | 2013-05-22 | QTR4 | 12/13 | 1 | 5 | 266 | 650 | 650 | 216.2% | 0 | 0 | 0 | 0 | 89 | 295 | 1202547 | 50000 | 1152547 | 3085087 | 3080524 | 0 | 0 | 0 | 3080524 | 3080524 | 267.3% | 0 | 0 | 1882539 | 48 | 27 | 14 | 266 | 1575597 | 0 | 0 | 29 | 324673 | 98769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8860 | 8860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 295 | 1908989 | 107629 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 |  | 2015-05-21 | QTR4 | 14/15 | 412 | 1238644.33
| 04 | T4374 | 43019615201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 102 | 112 | 110 | 98.04% | 1 | 2 | 0 | 0 | 10 | 0 | 348825 | 18115 | 330710 | 348825 | 339314 | 0 | 0 | 0 | 339314 | 339314 | 102.6% | 1 | 0 | 0 | 9 | 1 | 0 | 0 | 3246 | 0 | 0 | 0 | 5358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8604 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-22 | QTR1 | 15/16 |  | 2015-06-10 | QTR4 | 14/15 | 412 | 385157.48
| 04 | T4380 | 42974015201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 100 | 118 | 117 | 99% | 1 | 1 | 0 | 0 | 18 | 0 | 480024 | 22736 | 457288 | 480024 | 456013 | 0 | 0 | 0 | 456013 | 456013 | 99.72% | 1 | 0 | 0 | 16 | 2 | 0 | 0 | 2267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2267 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 412 | 486438.28
| 04 | T4384 | 42973815201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 96 | 101 | 99 | 97.92% | 1 | 2 | 0 | 0 | 5 | 0 | 547622 | 25962 | 521660 | 548351 | 527560 | 0 | 0 | 0 | 527560 | 527560 | 101.1% | 1 | 0 | 729 | 4 | 1 | 0 | 0 | 1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 |  | 2015-07-02 | QTR1 | 15/16 | 409 | 546487.47
| 04 | T4394 | 43060225203 | 2014-05-21 | QTR4 | 13/14 | 3 | 1 | 243 | 281 | 280 | 99.59% | 1 | 1 | 0 | 0 | 38 | 0 | 831515 | 40849 | 790666 | 893080 | 843974 | 0 | 0 | 0 | 843974 | 843974 | 106.7% | 1 | 0 | 61565 | 26 | 12 | 0 | 0 | 2400 | 0 | 0 | 0 | 68329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70729 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 |  | 2015-06-08 | QTR4 | 14/15 | 412 | 850266.14
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 6 | 8 | 8 | 987 | 1528 | 1575 | 66.67% | 4 | -47 | 53 | 0 | 208 | 333 | 7393646 | 207662 | 7185984 | 9457653 | 9270767 | -101442 | 0 | -101442 | 9169325 | 9167719 | 83.33% | 5 | -1606 | 2064007 | 139 | 55 | 14 | 268 | 1588706 | 0 | 0 | 62 | 531201 | 98769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8860 | 8860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 333 | 2128626 | 107629
| 04 | E4P28 | 43053415201 | 2014-01-03 | QTR3 | 13/14 | 1 | 1 | 265 | 342 | 335 | 114.3% | 1 | 7 | 0 | 0 | 77 | 0 | 1630613 | 50000 | 1580613 | 1680613 | 1713025 | 0 | 0 | 0 | 1713025 | 1712786 | 108.4% | 1 | -239 | 50000 | 15 | 17 | 45 | 0 | 0 | 0 | 0 | 0 | 46404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 46404 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2015-08-13 | QTR1 | 15/16 |  | 2015-07-09 | QTR1 | 15/16 | 408 | 1510582.53
| 04 | E4P42 | 42744115201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 237 | 285 | 285 | 112.7% | 1 | 0 | 0 | 0 | 18 | 30 | 1055000 | 50000 | 1005000 | 1055000 | 1018660 | 0 | 0 | 0 | 1018660 | 1018660 | 101.4% | 1 | 0 | 0 | 7 | 11 | 0 | 0 | 5225 | 0 | 0 | 30 | 11535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16760 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-09-24 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 409 | 1104492 | B0 | ACC - LUMP SUM
| 04 | E4P43 | 42636215201 | 2014-03-31 | QTR3 | 13/14 | 1 | 0 | 371 | 415 | 411 | 100% | 1 | 4 | 0 | 0 | 40 | 4 | 2106087 | 50000 | 2056087 | 2106087 | 2037825 | 0 | 0 | 0 | 2037825 | 2037825 | 99.11% | 1 | 0 | 0 | 25 | 15 | 0 | 0 | 4164 | 0 | 0 | 0 | 5698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 15442 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 |  | 2015-08-14 | QTR1 | 15/16 | 408 | 2671513.63
| 04 | E4P91 | 43397915201 | 2014-06-06 | QTR4 | 13/14 | 4 | 1 | 223 | 291 | 290 | 108.5% | 1 | 1 | 0 | 0 | 48 | 20 | 682040 | 21400 | 660640 | 677370 | 696418 | 0 | 0 | 0 | 696418 | 696418 | 105.4% | 1 | 0 | -4669 | 31 | 17 | 0 | 0 | 5986 | 0 | 0 | 20 | 10647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 11963 | 0 | F364509634 | MAYTIN ENGINEERING CORP. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 412 | 468107.77
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 4 | 7 | 2 | 1096 | 1333 | 1321 | 100% | 4 | 12 | 0 | 0 | 183 | 54 | 5473740 | 171400 | 5302340 | 5519070 | 5465928 | 0 | 0 | 0 | 5465928 | 5465689 | 100% | 4 | -239 | 45331 | 78 | 60 | 45 | 0 | 15375 | 0 | 0 | 50 | 74284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 54 | 90569 | 0
| District 04 Totals |  |  |  |  | 10 | 15 | 10 | 2083 | 2861 | 2896 | 80% | 8 | -35 | 53 | 0 | 391 | 387 | 12867386 | 379062 | 12488324 | 14976723 | 14736695 | -101442 | 0 | -101442 | 14635253 | 14633408 | 90% | 9 | -1845 | 2109338 | 217 | 115 | 59 | 268 | 1604081 | 0 | 0 | 112 | 605485 | 98769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8860 | 8860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 387 | 2219195 | 107629
| 05 | BDT74 | 41299435201 | 2011-11-07 | QTR2 | 11/12 | 5 | 15 | 460 | 802 | 1058 | 219.3% | 0 | -256 | 256 | 0 | 77 | 265 | 27584500 | 150000 | 27434500 | 29571831 | 29554288 | 0 | 0 | 0 | 29554288 | 29554288 | 107.7% | 1 | 0 | 1987331 | 26 | 23 | 0 | 0 | 294952 | 5697 | 0 | 0 | 366049 | 3040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 1475287 | 169381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 2136288 | 178118 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2015-09-07 | QTR1 | 15/16 |  | 2015-02-11 | QTR3 | 14/15 | 507 | 27584500 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE
| 05 | T5401 | 42201515201 | 2013-04-24 | QTR4 | 12/13 | 4 | 5 | 290 | 361 | 361 | 107.2% | 1 | 0 | 0 | 0 | 50 | 21 | 4603457 | 50000 | 4553457 | 4806215 | 4675801 | 0 | 0 | 0 | 4675801 | 4675281 | 102.7% | 1 | -520 | 202758 | 32 | 18 | 0 | 5 | 67573 | 12260 | 0 | 16 | 186828 | 13247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 254401 | 25507 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-08 | QTR1 | 15/16 |  | 2014-08-18 | QTR1 | 14/15 | 509 | 4500359.97
| 05 | T5404 | 24023335201 | 2012-05-23 | QTR4 | 11/12 | 5 | 6 | 710 | 980 | 980 | 114.8% | 1 | 0 | 0 | 0 | 165 | 105 | 10111333 | 50000 | 10061333 | 10458539 | 10091859 | 0 | 0 | 0 | 10091859 | 10008344 | 99.47% | 1 | -83514 | 347206 | 129 | 36 | 0 | 21 | 292661 | 435 | 0 | 84 | 60822 | 1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 355274 | 1518 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 |  | 2015-05-03 | QTR4 | 14/15 | 507 | 9890702.1
| 05 | T5483 | 42727915201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 200 | 273 | 273 | 105% | 1 | 0 | 0 | 0 | 63 | 10 | 2914000 | 50000 | 2864000 | 2914000 | 2885939 | 0 | 0 | 0 | 2885939 | 2771829 | 96.78% | 1 | -114111 | 0 | 37 | 26 | 0 | 10 | 1702 | 0 | 0 | 0 | 14745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 16446 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 |  | 2015-06-12 | QTR4 | 14/15 | 513 | 2978859.49 | B0 | ACC - LUMP SUM
| 05 | T5488 | 42907915201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 290 | 439 | 439 | 100% | 1 | 0 | 0 | 0 | 149 | 0 | 5354000 | 59000 | 5295000 | 5354000 | 5430627 | -11100 | 0 | -11100 | 5419527 | 5329312 | 100.6% | 1 | -90214 | 0 | 128 | 21 | 0 | 0 | 17682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17682 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-18 | QTR1 | 15/16 |  | 2015-05-29 | QTR4 | 14/15 | 509 | 5993024.89 | B0 | ACC - LUMP SUM
| 05 | T5494 | 42488715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 180 | 247 | 247 | 100% | 1 | 0 | 0 | 0 | 67 | 0 | 1795728 | 50000 | 1745728 | 1795728 | 1805364 | 0 | 0 | 0 | 1805364 | 1760006 | 100.8% | 1 | -45358 | 0 | 46 | 21 | 0 | 0 | 5154 | 0 | 0 | 0 | 24811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29965 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 |  | 2015-05-11 | QTR4 | 14/15 | 514 | 1761956.22 | B0 | ACC - LUMP SUM
| 05 | T5495 | 42886715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 1 | 300 | 328 | 303 | 91.67% | 1 | 25 | 0 | 0 | 28 | 0 | 6951000 | 72000 | 6879000 | 6886782 | 6967320 | 0 | 0 | 0 | 6967320 | 6782907 | 98.6% | 1 | -184413 | -64218 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -72353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -64218 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 |  | 2015-06-30 | QTR4 | 14/15 | 509 | 7479522.66 | B0 | ACC - LUMP SUM
| 05 | T5501 | 42886215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 110 | 176 | 176 | 100% | 1 | 0 | 0 | 0 | 66 | 0 | 2189795 | 50000 | 2139795 | 2189795 | 2201353 | 0 | 0 | 0 | 2201353 | 2169152 | 101.4% | 1 | -32201 | 0 | 42 | 24 | 0 | 0 | 54576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54576 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 |  | 2015-04-24 | QTR4 | 14/15 | 507 | 2211253.07 | B0 | ACC - LUMP SUM
| 05 | T5520 | 23867825201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 118 | 129 | 106 | 80.51% | 1 | 23 | 0 | 0 | 11 | 0 | 544771 | 36000 | 508771 | 536238 | 524085 | 0 | 0 | 0 | 524085 | 520797 | 102.4% | 1 | -3288 | -8533 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1651 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 |  | 2015-06-01 | QTR4 | 14/15 | 512 | 761207.45
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 9 | 20 | 28 | 2658 | 3735 | 3943 | 88.89% | 8 | -208 | 256 | 0 | 676 | 401 | 62048584 | 567000 | 61481584 | 64513128 | 64136636 | -11100 | 0 | -11100 | 64125536 | 63571916 | 100% | 9 | -553619 | 2464544 | 464 | 184 | 0 | 36 | 734300 | 18392 | 0 | 100 | 671575 | 17371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 1396192 | 169381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401 | 2802065 | 205143
| 05 | E5W28 | 41499925201 | 2014-05-06 | QTR4 | 13/14 | 1 | 1 | 100 | 127 | 125 | 113% | 1 | 2 | 0 | 0 | 12 | 15 | 260959 | 11000 | 249959 | 242155 | 231155 | 0 | 0 | 0 | 231155 | 231155 | 92.48% | 1 | 0 | -18805 | 3 | 9 | 0 | 0 | 0 | 0 | 0 | 15 | -18805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -18805 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2015-09-08 | QTR1 | 15/16 |  | 2015-04-15 | QTR4 | 14/15 | 509 | 250000
| 05 | E5W30 | 43214919201 | 2014-02-18 | QTR3 | 13/14 | 1 | 0 | 365 | 380 | 380 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 3585585 | 50000 | 3535585 | 3585585 | 3535585 | 0 | 0 | 0 | 3535585 | 0 | 0% | 1 | -3535585 | 0 | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-07-10 | QTR1 | 15/16 |  | 2015-05-29 | QTR4 | 14/15 | 509 | 3478319.3 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E5W68 | 24099295201 | 2014-12-02 | QTR2 | 14/15 | 2 | 0 | 120 | 124 | 121 | 97.5% | 1 | 3 | 0 | 0 | 4 | 0 | 518519 | 21000 | 497519 | 518519 | 502367 | 0 | 0 | 0 | 502367 | 502367 | 101% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2974 | 0 | 0 | 0 | 3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-07-28 | QTR1 | 15/16 |  | 2015-07-14 | QTR1 | 15/16 | 513 | 460954.46
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 3 | 4 | 1 | 585 | 631 | 626 | 100% | 3 | 5 | 0 | 0 | 31 | 15 | 4365063 | 82000 | 4283063 | 4346259 | 4269107 | 0 | 0 | 0 | 4269107 | 733522 | 100% | 3 | -3535585 | -18805 | 6 | 25 | 0 | 0 | 2974 | 0 | 0 | 15 | -15779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -12805 | 0
| District 05 Totals |  |  |  |  | 12 | 24 | 29 | 3243 | 4366 | 4569 | 91.67% | 11 | -203 | 256 | 0 | 707 | 416 | 66413647 | 649000 | 65764647 | 68859387 | 68405743 | -11100 | 0 | -11100 | 68394643 | 64305438 | 100% | 12 | -4089204 | 2445739 | 470 | 209 | 0 | 36 | 737274 | 18392 | 0 | 115 | 655796 | 17371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 1396192 | 169381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 2789260 | 205143
| 06 | T6207 | 41984815201 | 2013-05-22 | QTR4 | 12/13 | 3 | 5 | 280 | 396 | 396 | 118.6% | 1 | 0 | 0 | 0 | 74 | 42 | 6954601 | 80000 | 6874601 | 7631613 | 7814383 | 0 | 0 | 0 | 7814383 | 7814501 | 113.7% | 0 | 117 | 677012 | 49 | 15 | 10 | 0 | 192852 | 0 | 0 | 42 | 499242 | 19532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 42 | 692093 | 19532 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 |  | 2015-02-26 | QTR3 | 14/15 | 606 | 8225852.05
| 06 | T6278 | 24994115201 | 2012-05-23 | QTR4 | 11/12 | 4 | 6 | 650 | 1028 | 1028 | 119.1% | 1 | 0 | 0 | 0 | 254 | 124 | 14358568 | 211699 | 14146869 | 13941778 | 14063237 | 0 | 0 | 0 | 14063237 | 13981485 | 98.83% | 1 | -81752 | -416790 | 215 | 39 | 0 | 69 | 338260 | 0 | 0 | 0 | 2917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198178 | 6413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | -823116 | 0 | 0 | 124 | -283761 | 6413 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2015-09-22 | QTR1 | 15/16 |  | 2015-07-11 | QTR1 | 15/16 | 606 | 12500128.6
| 06 | T6322 | 42750525201 | 2013-09-25 | QTR1 | 13/14 | 4 | 2 | 240 | 450 | 450 | 117.5% | 1 | 0 | 0 | 0 | 210 | 0 | 2272423 | 51180 | 2221243 | 2348653 | 2183494 | 0 | 0 | 0 | 2183494 | 2177671 | 98.04% | 1 | -5822 | 76230 | 121 | 47 | 0 | 0 | 34580 | 0 | 42 | 0 | 65393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 99973 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-09-25 | QTR1 | 15/16 |  | 2015-07-28 | QTR1 | 15/16 | 606 | 2206205.25
| 06 | T6324 | 42913615201 | 2013-09-25 | QTR1 | 13/14 | 2 | 2 | 260 | 410 | 407 | 110.4% | 1 | 3 | 0 | 0 | 150 | 0 | 3959132 | 51415 | 3907717 | 4129233 | 4133336 | 0 | 0 | 0 | 4133336 | 4124281 | 105.5% | 1 | -9055 | 170101 | 105 | 15 | 0 | 0 | 3694 | 0 | 30 | 0 | 157988 | 70393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 184274 | 70393 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-15 | QTR1 | 15/16 |  | 2015-04-07 | QTR4 | 14/15 | 606 | 4168713.7
| 06 | T6351 | 42904315201 | 2014-02-05 | QTR3 | 13/14 | 3 | 0 | 180 | 241 | 241 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 643250 | 39250 | 604000 | 643250 | 597697 | 0 | 0 | 0 | 597697 | 597697 | 98.96% | 1 | 0 | 0 | 50 | 11 | 0 | 0 | 7236 | 0 | 0 | 0 | 8819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16056 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-17 | QTR1 | 15/16 |  | 2015-05-06 | QTR4 | 14/15 | 606 | 824250 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 06 | T6355 | 42902115201 | 2014-05-21 | QTR4 | 13/14 | 2 | 0 | 160 | 194 | 194 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1061111 | 50130 | 1010981 | 1061111 | 1066049 | 0 | 0 | 0 | 1066049 | 1066049 | 105.4% | 1 | 0 | 0 | 23 | 11 | 0 | 0 | 32501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49048 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-24 | QTR1 | 15/16 |  | 2015-06-22 | QTR4 | 14/15 | 606 | 1021385.13 | B0 | ACC - LUMP SUM
| 06 | T6361 | 43003115201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 150 | 191 | 187 | 97.33% | 1 | 4 | 0 | 0 | 41 | 0 | 327561 | 14958 | 312603 | 327561 | 279990 | 0 | 0 | 0 | 279990 | 279933 | 89.55% | 1 | -57 | 0 | 36 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263976898 | AMROAD LLC | N/A | N/A | N/A | N/A | 2015-09-24 | QTR1 | 15/16 |  | 2015-07-31 | QTR1 | 15/16 | 606 | 306614
| 06 | T6363 | 42751515201 | 2013-05-22 | QTR4 | 12/13 | 1 | 5 | 350 | 521 | 521 | 109.7% | 1 | 0 | 0 | 0 | 171 | 0 | 5378636 | 50000 | 5328636 | 5591336 | 6965131 | 0 | 0 | 0 | 6965131 | 6964220 | 130.7% | 0 | -911 | 212700 | 97 | 40 | 0 | 0 | 415000 | 0 | 34 | 0 | 152786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 45540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -403000 | 0 | 34 | 0 | 218326 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 |  | 2015-02-18 | QTR3 | 14/15 | 606 | 4504473.9
| 06 | T6368 | 43003315201 | 2014-07-30 | QTR1 | 14/15 | 1 | 1 | 170 | 172 | 137 | 79.41% | 1 | 35 | 0 | 0 | 2 | 0 | 619197 | 29000 | 590197 | 643584 | 598711 | 0 | 0 | 0 | 598711 | 598703 | 101.4% | 1 | -8 | 24387 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 24387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24387 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2015-07-10 | QTR1 | 15/16 |  | 2015-06-04 | QTR4 | 14/15 | 606 | 631340
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 9 | 21 | 21 | 2440 | 3603 | 3561 | 100% | 9 | 42 | 0 | 0 | 997 | 166 | 35574479 | 577632 | 34996847 | 36318119 | 37702028 | 0 | 0 | 0 | 37702028 | 37604540 | 77.78% | 7 | -97488 | 743640 | 696 | 185 | 10 | 69 | 1024123 | 0 | 106 | 42 | 911532 | 89925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 282858 | 6413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | -1226116 | 0 | 116 | 166 | 1000396 | 96338
| 06 | E6G56 | 42611915201 | 2013-01-31 | QTR3 | 12/13 | 1 | 0 | 560 | 775 | 774 | 104.8% | 1 | 1 | 0 | 0 | 215 | 0 | 4988310 | 58000 | 4930310 | 4988310 | 4865434 | 0 | 0 | 0 | 4865434 | 4865434 | 98.68% | 1 | 0 | 0 | 152 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2015-08-03 | QTR1 | 15/16 |  | 2015-07-02 | QTR1 | 15/16 | 606 | 5875815.5
| 06 | E6H61 | 43119215201 | 2014-06-12 | QTR4 | 13/14 | 1 | 0 | 280 | 317 | 317 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 838500 | 40300 | 798200 | 838500 | 763060 | 0 | 0 | 0 | 763060 | 763060 | 95.6% | 1 | 0 | 0 | 18 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 |  | 2015-08-11 | QTR1 | 15/16 | 606 | 850347
| 06 | E6I14 | 43209815201 | 2014-02-27 | QTR3 | 13/14 | 1 | 0 | 120 | 234 | 198 | 90% | 1 | 36 | 0 | 0 | 114 | 0 | 328706 | 17632 | 311074 | 328706 | 320865 | 0 | 0 | 0 | 320865 | 320865 | 103.1% | 1 | 0 | 0 | 76 | 14 | 24 | 0 | 9791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 9791 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 |  | 2015-06-25 | QTR4 | 14/15 | 606 | 370268.95 | B0 | ACC - LUMP SUM
| 06 | E6I57 | 43119015201 | 2014-09-25 | QTR1 | 14/15 | 1 | 0 | 120 | 138 | 138 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 619046 | 39934 | 579112 | 619046 | 562195 | 0 | 0 | 0 | 562195 | 562195 | 97.08% | 1 | 0 | 0 | 15 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-09-23 | QTR1 | 15/16 |  | 2015-07-03 | QTR1 | 15/16 | 606 | 838614
| 06 | E6I77 | 24994175201 | 2014-08-28 | QTR1 | 14/15 | 1 | 0 | 160 | 194 | 194 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1198756 | 50000 | 1148756 | 1198756 | 1094981 | 0 | 0 | 0 | 1094981 | 1094981 | 95.32% | 1 | 0 | 0 | 31 | 3 | 0 | 0 | 1200 | 0 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11878 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-07-17 | QTR1 | 15/16 | 606 | 1268938.13
| 06 | E6I78 | 43081615201 | 2014-07-31 | QTR1 | 14/15 | 2 | 0 | 140 | 173 | 173 | 105.7% | 1 | 0 | 0 | 0 | 25 | 8 | 1207213 | 51325 | 1155888 | 1207213 | 1139099 | 0 | 0 | 0 | 1139099 | 1129248 | 97.7% | 1 | -9851 | 0 | 12 | 13 | 0 | 0 | 0 | 0 | 0 | 3 | 5483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6468 | 0 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 |  | 2015-04-24 | QTR4 | 14/15 | 606 | 1208779.95
| 06 | E6I83 | 43081415201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 65 | 96 | 93 | 95.38% | 1 | 3 | 0 | 0 | 31 | 0 | 94720 | 6040 | 88680 | 94720 | 88652 | 0 | 0 | 0 | 88652 | 88652 | 99.97% | 1 | 0 | 0 | 28 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-07-14 | QTR1 | 15/16 | 606 | 126847 | B0 | ACC - LUMP SUM
| 06 | E6I85 | 41774079201 | 2014-03-27 | QTR3 | 13/14 | 1 | 0 | 300 | 346 | 346 | 108% | 1 | 0 | 0 | 0 | 46 | 0 | 502650 | 32313 | 470337 | 502650 | 470337 | 0 | 0 | 0 | 470337 | 0 | 0% | 1 | -470337 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-05-13 | QTR4 | 14/15 | 606 | 678578.25 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6I87 | 42934415201 | 2014-10-30 | QTR2 | 14/15 | 3 | 0 | 170 | 192 | 190 | 98.82% | 1 | 2 | 0 | 0 | 22 | 0 | 1872759 | 101085 | 1771674 | 1872759 | 1693855 | 0 | 0 | 0 | 1693855 | 1636257 | 92.36% | 1 | -57598 | 0 | 20 | 2 | 0 | 0 | 1943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-09-17 | QTR1 | 15/16 |  | 2015-07-29 | QTR1 | 15/16 | 606 | 1934017.45
| 06 | E6J40 | 43590015201 | 2015-01-29 | QTR3 | 14/15 | 1 | 0 | 80 | 83 | 75 | 90% | 1 | 8 | 0 | 0 | 3 | 0 | 248698 | 11846 | 236852 | 248698 | 217030 | 0 | 0 | 0 | 217030 | 217030 | 91.63% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-09-25 | QTR1 | 15/16 |  | 2015-09-11 | QTR1 | 15/16 | 606 | 248762.6
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 10 | 13 | 0 | 1995 | 2548 | 2498 | 100% | 10 | 50 | 0 | 0 | 545 | 8 | 11899358 | 408475 | 11490883 | 11899358 | 11215508 | 0 | 0 | 0 | 11215508 | 10677722 | 100% | 10 | -537786 | 0 | 352 | 117 | 24 | 0 | 12934 | 0 | 24 | 3 | 9783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6377 | 0 | 0 | 5 | 985 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 8 | 30080 | 0
| District 06 Totals |  |  |  |  | 19 | 34 | 21 | 4435 | 6151 | 6059 | 100% | 19 | 92 | 0 | 0 | 1542 | 174 | 47473837 | 986107 | 46487730 | 48217477 | 48917536 | 0 | 0 | 0 | 48917536 | 48282262 | 89.47% | 17 | -635274 | 743640 | 1048 | 302 | 34 | 69 | 1037057 | 0 | 130 | 45 | 921315 | 89925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 289235 | 6413 | 0 | 5 | 985 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | -1226116 | 0 | 192 | 174 | 1030476 | 96338
| 07 | T7325 | 42900515201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 350 | 453 | 453 | 105.7% | 1 | 0 | 0 | 0 | 83 | 20 | 15491284 | 120000 | 15371284 | 16150823 | 16100076 | 0 | 0 | 0 | 16100076 | 16143898 | 105% | 1 | 43822 | 659540 | 60 | 23 | 0 | 1 | 10092 | 0 | 0 | 19 | 662533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 683477 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-08-21 | QTR1 | 15/16 |  | 2014-11-21 | QTR2 | 14/15 | 709 | 16955600
| 07 | T7329 | 42907325201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 270 | 369 | 369 | 100% | 1 | 0 | 0 | 0 | 99 | 0 | 5019226 | 50000 | 4969226 | 5019226 | 4985077 | 0 | 0 | 0 | 4985077 | 4951447 | 99.64% | 1 | -33631 | 0 | 82 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 18054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18054 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-07-23 | QTR1 | 15/16 |  | 2015-04-01 | QTR4 | 14/15 | 717 | 4751500 | B0 | ACC - LUMP SUM
| 07 | T7340 | 42715415201 | 2014-04-30 | QTR4 | 13/14 | 2 | 0 | 150 | 188 | 187 | 99.33% | 1 | 1 | 0 | 0 | 38 | 0 | 1688000 | 50000 | 1638000 | 1688000 | 1644638 | 0 | 0 | 0 | 1644638 | 1606582 | 98.08% | 1 | -38056 | 0 | 25 | 13 | 0 | 0 | 9287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9287 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 |  | 2015-03-27 | QTR3 | 14/15 | 798 | 2156800 | B0 | ACC - LUMP SUM
| 07 | T7341 | 42896115201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 320 | 383 | 381 | 99.38% | 1 | 2 | 0 | 0 | 63 | 0 | 5790872 | 55000 | 5735872 | 5790872 | 5714657 | 0 | 0 | 0 | 5714657 | 5660340 | 98.68% | 1 | -54316 | 0 | 38 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-09-15 | QTR1 | 15/16 |  | 2015-06-17 | QTR4 | 14/15 | 717 | 6079410
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 4 | 5 | 8 | 1090 | 1393 | 1390 | 100% | 4 | 3 | 0 | 0 | 283 | 20 | 27989382 | 275000 | 27714382 | 28648921 | 28444448 | 0 | 0 | 0 | 28444448 | 28362267 | 100% | 4 | -82181 | 659540 | 205 | 78 | 0 | 1 | 19379 | 0 | 0 | 19 | 680587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 710818 | 0
| 07 | E7J96 | 43066115201 | 2014-11-26 | QTR2 | 14/15 | 1 | 0 | 150 | 183 | 183 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 2030000 | 50000 | 1980000 | 2030000 | 1980915 | 0 | 0 | 0 | 1980915 | 1934577 | 97.71% | 1 | -46338 | 0 | 26 | 7 | 0 | 0 | 1006 | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9760 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-29 | QTR1 | 15/16 |  | 2015-08-19 | QTR1 | 15/16 | 709 | 1984600 | B0 | ACC - LUMP SUM
[29 empty] | 0% | 1
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 1 | 1 | 0 | 150 | 183 | 183 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 2030000 | 50000 | 1980000 | 2030000 | 1980915 | 0 | 0 | 0 | 1980915 | 1934577 | 200% | 2 | -46338 | 0 | 26 | 7 | 0 | 0 | 1006 | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9760 | 0
| District 07 Totals |  |  |  |  | 5 | 6 | 8 | 1240 | 1576 | 1573 | 100% | 5 | 3 | 0 | 0 | 316 | 20 | 30019382 | 325000 | 29694382 | 30678921 | 30425363 | 0 | 0 | 0 | 30425363 | 30296844 | 120% | 6 | -128519 | 659540 | 231 | 85 | 0 | 1 | 20385 | 0 | 0 | 19 | 683287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10852 | 0 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 720578 | 0
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8L99 | 41546225202 | 2012-05-22 | QTR4 | 11/12 | 1 | 9 | 785 | 901 | 901 | 103.6% | 1 | 0 | 0 | 0 | 88 | 28 | 19914762 | 150000 | 19764762 | 20008584 | 19972782 | -154000 | 0 | -154000 | 19818782 | 19745451 | 99.9% | 1 | -73332 | 93822 | 25 | 63 | 0 | 0 | 66402 | 0 | 0 | 0 | 119752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 35659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -130930 | 0 | 0 | 28 | 90883 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-09-28 | QTR1 | 15/16 |  | 2015-02-13 | QTR3 | 14/15 | 854 | 20630726.61
| 08 | E8M77 | 40615145201 | 2013-03-26 | QTR3 | 12/13 | 2 | 4 | 645 | 777 | 730 | 105.7% | 1 | 47 | 0 | 0 | 48 | 84 | 11249740 | 150000 | 11099740 | 11481897 | 10973748 | 0 | 0 | 0 | 10973748 | 10925662 | 98.43% | 1 | -48086 | 232157 | 25 | 23 | 0 | 84 | 150630 | 103254 | 0 | 0 | 162171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 312801 | 103254 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-09-04 | QTR1 | 15/16 |  | 2015-07-07 | QTR1 | 15/16 | 854 | 11244846.35
| 08 | E8M80 | 42768515201 | 2013-05-14 | QTR4 | 12/13 | 1 | 2 | 425 | 469 | 425 | 89.65% | 1 | 44 | 0 | 0 | 44 | 0 | 6746576 | 63950 | 6682626 | 6938552 | 6915696 | 0 | 0 | 0 | 6915696 | 6919857 | 103.5% | 1 | 4160 | 191976 | 15 | 29 | 0 | 0 | 66193 | 0 | 0 | 0 | 5863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249853 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-09-14 | QTR1 | 15/16 |  | 2014-10-06 | QTR2 | 14/15 | 854 | 6459217.72
| 08 | E8M93 | 43108935201 | 2013-05-21 | QTR4 | 12/13 | 1 | 2 | 450 | 587 | 587 | 100% | 1 | 0 | 0 | 0 | 137 | 0 | 7676614 | 84515 | 7592099 | 7714483 | 7540572 | 0 | 0 | 0 | 7540572 | 7491522 | 98.68% | 1 | -49050 | 37868 | 85 | 52 | 0 | 0 | 122140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122140 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-07-07 | QTR1 | 15/16 |  | 2015-05-15 | QTR4 | 14/15 | 854 | 8536508.95
| 08 | E8N21 | 42902315201 | 2014-03-11 | QTR3 | 13/14 | 2 | 5 | 170 | 271 | 271 | 104.1% | 1 | 0 | 0 | 0 | 94 | 7 | 6573418 | 84736 | 6488682 | 6704790 | 6985687 | -3000 | 0 | -3000 | 6982687 | 6966867 | 107.4% | 1 | -15820 | 131372 | 62 | 32 | 0 | 0 | 14408 | 0 | 0 | 7 | 173176 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68650 | 0 | 0 | 0 | 8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 67841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 197374 | 5845 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-14 | QTR1 | 15/16 |  | 2015-02-09 | QTR3 | 14/15 | 854 | 8559769.2
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 5 | 7 | 22 | 2475 | 3005 | 2914 | 0.002363% | 5 | 91 | 0 | 0 | 411 | 119 | 52161110 | 533201 | 51627909 | 52848306 | 52388485 | -157000 | 0 | -157000 | 52231485 | 52049359 | 100% | 5 | -182128 | 687195 | 212 | 199 | 0 | 84 | 419773 | 103254 | 0 | 7 | 460962 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 144806 | 0 | 0 | 0 | 8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 67841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -130930 | 0 | 0 | 119 | 973051 | 109099
| District 08 Totals |  |  |  |  | 5 | 7 | 22 | 2475 | 3005 | 2914 | 100% | 5 | 91 | 0 | 0 | 411 | 119 | 52161110 | 533201 | 51627909 | 52848306 | 52388485 | -157000 | 0 | -157000 | 52231485 | 52049359 | 100% | 5 | -182128 | 687195 | 212 | 199 | 0 | 84 | 419773 | 103254 | 0 | 7 | 460962 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 144806 | 0 | 0 | 0 | 8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 67841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -130930 | 0 | 0 | 119 | 973051 | 109099
| Statewide Central Let Contracts SubTotal |  |  |  |  | 54 | 86 | 116 | 13156 | 18250 | 18536 | 88.89% | 48 | -286 | 500 | 0 | 3983 | 1111 | 221641124 | 2676588 | 218964538 | 230012909 | 229771939 | -207024 | 0 | -207024 | 229564915 | 227941179 | 92.59% | 50 | -1623733 | 8371785 | 2781 | 906 | 28 | 416 | 4184507 | 22513 | 156 | 341 | 4474028 | 518551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 29 | 265 | 1857049 | 175794 | 0 | 0 | 4407 | 0 | 0 | 0 | 0 | 0 | 7 | 34 | 63020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8860 | 8860 | 38 | 0 | 0 | 0 | 0 | 55 | -1425303 | 0 | 258 | 1111 | 9174564 | 725717
| Statewide District Let Contracts SubTotal |  |  |  |  | 37 | 49 | 48 | 9540 | 11811 | 11529 | 97.3% | 36 | 282 | 0 | 0 | 1698 | 573 | 117571612 | 1892791 | 115678821 | 119112281 | 117322930 | -157000 | 0 | -157000 | 117165930 | 112357769 | 97.3% | 36 | -4808161 | 1540667 | 954 | 616 | 69 | 207 | 617776 | 112868 | 31 | 242 | 1027227 | 14844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 568544 | 0 | 0 | 5 | 15660 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1977 | 0 | 0 | 0 | 67841 | 0 | 0 | 1 | 28118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -248463 | 0 | 128 | 573 | 2078683 | 127712
| Statewide Totals |  |  |  |  | 91 | 135 | 164 | 22696 | 30061 | 30065 | 92.31% | 84 | -4 | 500 | 0 | 5681 | 1684 | 339212736 | 4569379 | 334643359 | 349125190 | 347094869 | -364024 | 0 | -364024 | 346730845 | 340298948 | 94.51% | 86 | -6431894 | 9912452 | 3735 | 1522 | 97 | 623 | 4802283 | 135381 | 187 | 583 | 5501255 | 533395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 29 | 383 | 2425593 | 175794 | 0 | 5 | 20067 | 0 | 0 | 0 | 0 | 0 | 35 | 34 | 64997 | 0 | 0 | 0 | 67841 | 0 | 0 | 1 | 36978 | 8860 | 38 | 0 | 0 | 0 | 0 | 55 | -1673766 | 0 | 386 | 1684 | 11253247 | 853429

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1J71 | 41263625201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2012-05-31 | 6703703 | 7531485 | 7530256 | 827781.72 | 0 | 7530256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7530256 | 7530256 | 0 | 638850 | A3 | ICC - DESIGN/BUILD - MINOR
1 | E1N08 | 42347115201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-06-19 | 1880948 | 1908269 | 1858269 | 27320.39 | 0 | 1834616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1858269 | 1834616 | -23653 | 1405116 | B0 | ACC - LUMP SUM
1 | E1N47 | 43019125201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2014-06-19 | 4346396 | 4413679 | 4400332 | 67283.26 | 0 | 4322422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4400332 | 4322422 | -77910 | 4460046 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | E1N64 | 43160515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-08-29 | 3021172 | 3021172 | 3068023 | 0 | 0 | 2921086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3068023 | 2921086 | -146936 | 3419371
1 | E1N71 | 43006015201 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2015-01-15 | 567387 | 567387 | 532744 | 0 | 0 | 532744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532744 | 532744 | 0 | 519187 | B0 | ACC - LUMP SUM
1 | E1N96 | 42949925201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-10-16 | 229418 | 228371 | 218669 | -1047.37 | 0 | 218669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218669 | 218669 | 0 | 179059 | B0 | ACC - LUMP SUM
1 | E1O06 | 43574215201 | F650968383 | WHITELEAF LLC DBA TRAFFIC SOLUTIONS | N/A | N/A | N/A | N/A | 2014-11-20 | 140780 | 140780 | 132639 | 0 | 0 | 265277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132639 | 265277 | 132639 | 193963 | B0 | ACC - LUMP SUM
1 | T1497 | 43003715201 | F593490202 | ALDON BOOKHARDT ROOFING INC. | N/A | N/A | N/A | N/A | 2012-03-28 | 90611 | 89035 | 88897 | -1575.84 | -43964 | 44933 | -43964 | 0 | 0 | 0 | 0 | 0 | -43964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43964 | 44933 | 44933 | 0 | 111868 | B0 | ACC - LUMP SUM
1 | T1501 | 40828635201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2012-06-20 | 14784300 | 15330267 | 14964740 | 545967.35 | 0 | 15047703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14964740 | 15047703 | 82963 | 13767014
1 | T1527 | 41787615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2013-02-06 | 12312349 | 13258294 | 12897465 | 945944.85 | 0 | 12514104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12897465 | 12514104 | -383360 | 15340403
1 | T1546 | 42910415201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-02-26 | 2195109 | 2159801 | 2156391 | -35307.58 | -50518 | 2085969 | -50518 | 0 | 0 | 0 | 0 | 0 | -50518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50518 | 2105873 | 2085969 | -19904 | 2641240 | B0 | ACC - LUMP SUM
1 | T1566 | 20010575201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2014-04-30 | 855140 | 880470 | 883951 | 25330.32 | 0 | 883951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883951 | 883951 | 0 | 1061210
1 | T1578 | 43086015201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2013-12-04 | 5634855 | 5727333 | 5707127 | 92478.17 | 0 | 5640992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5707127 | 5640992 | -66135 | 5433904 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1A14 | 43341115201 | F593339407 | TAGARELLI CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 247066 | 270085 | 250380 | 23018.51 | 0 | 250380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250380 | 250380 | 0 | 256990 | B0 | ACC - LUMP SUM
2 | E2R18 | 42468515201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-05-23 | 8195419 | 8206705 | 8178408 | 11286.44 | 0 | 8124680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8178408 | 8124680 | -53727 | 8761555 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2R94 | 42822915201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-08-21 | 2445796 | 2445796 | 2450466 | 0 | 0 | 2449755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450466 | 2449755 | -711 | 2404678
2 | E2S71 | 42869515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-04-23 | 7686286 | 7580608 | 7142686 | -105678.26 | 0 | 6953829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7142686 | 6953829 | -188858 | 6348256
2 | E2S89 | 20954125201 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2014-04-23 | 1997720 | 1997720 | 2088940 | 0 | 0 | 2081779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088940 | 2081779 | -7161 | 2345342
2 | T2443 | 42698615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-02-06 | 4870523 | 4870523 | 4844339 | 0 | 0 | 4835215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4844339 | 4835215 | -9124 | 5528434
2 | T2512 | 42869015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 8787879 | 8787879 | 8967904 | 0 | 0 | 8851811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8967904 | 8851811 | -116093 | 9570319
2 | T2527 | 42870515201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 3855596 | 3937461 | 4006951 | 81865.16 | 0 | 3890841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4006951 | 3890841 | -116110 | 3913298
2 | T2530 | 21156035201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-05-21 | 1259477 | 1284233 | 1254859 | 24756.19 | 0 | 1254859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1254859 | 1254859 | 0 | 957006
2 | T2535 | 42053145201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 1754776 | 1824298 | 1779783 | 69521.29 | 0 | 1779783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1779783 | 1779783 | 0 | 1169715 | B0 | ACC - LUMP SUM
2 | T2543 | 43055515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 1738869 | 1738869 | 1721840 | 0 | 0 | 1698982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1721840 | 1698982 | -22858 | 1963162
3 | E3L71 | 42874415201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-03-13 | 1490639 | 1490639 | 1445553 | 0 | 0 | 1451830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1445553 | 1451830 | 6277 | 1584507
3 | E3M60 | 42697215201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2014-12-11 | 1718927 | 1718927 | 1766800 | 0 | 0 | 1673682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766800 | 1673682 | -93118 | 2202754
3 | E3M93 | 43078215201 | F580538940 | OXFORD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-12-11 | 1217750 | 1217750 | 1189202 | 0 | 0 | 1136275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189202 | 1136275 | -52927 | 1216620
3 | T3088 | 21894615201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2012-07-25 | 13348458 | 13883485 | 14095924 | 535027.17 | 0 | 14095514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14095924 | 14095514 | -409 | 14378815
3 | T3396 | 42323315201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2013-09-25 | 2789487 | 2763621 | 2700963 | -25866.15 | 0 | 2673321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700963 | 2673321 | -27642 | 2906374
3 | T3401 | 42323415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2013-10-30 | 2645210 | 2645210 | 2628131 | 0 | 0 | 2609172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2628131 | 2609172 | -18959 | 2957617
3 | T3409 | 42462215201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 2097227 | 2097227 | 2093592 | 0 | 0 | 1978887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2093592 | 1978887 | -114705 | 2813050
3 | T3411 | 42636815201 | F263312611 | R B M CONTRACTING SERVICES LLC | N/A | N/A | N/A | N/A | 2014-10-29 | 577753 | 577753 | 581122 | 0 | 0 | 581122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581122 | 581122 | 0 | 613088
3 | T3424 | 41343515201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2013-02-06 | 3882641 | 3972326 | 3728903 | 89685.08 | 0 | 3719464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3728903 | 3719464 | -9439 | 4647470
3 | T3434 | 42987815201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 459930 | 459930 | 451610 | 0 | 0 | 451610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451610 | 451610 | 0 | 439830 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
3 | T3455 | 43000415201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2014-10-29 | 919509 | 919509 | 927409 | 0 | 0 | 927409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927409 | 927409 | 0 | 817764
3 | T3468 | 42696515201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 1826839 | 1826839 | 1794755 | 0 | 0 | 1727691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1794755 | 1727691 | -67064 | 1783054
3 | T3502 | 42764915201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 633977 | 703188 | 695402 | 69210.6 | 0 | 695402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695402 | 695402 | 0 | 559213
3 | T3530 | 43174415201 | F593715775 | PYRAMID EXCAVATION INC. | N/A | N/A | N/A | N/A | 2015-01-28 | 217000 | 217000 | 216611 | 0 | 0 | 216611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216611 | 216611 | 0 | 236371
3 | T3535 | 42693615201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 481388 | 481388 | 440397 | 0 | 0 | 440397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440397 | 440397 | 0 | 540651
3 | T3536 | 40393125201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-01-28 | 369064 | 369064 | 338614 | 0 | 0 | 338614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338614 | 338614 | 0 | 486852
4 | E4P28 | 43053415201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2014-01-03 | 1630613 | 1680613 | 1713025 | 50000 | 0 | 1712786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1713025 | 1712786 | -239 | 1510583
4 | E4P42 | 42744115201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2014-05-02 | 1055000 | 1055000 | 1018660 | 0 | 0 | 1018660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1018660 | 1018660 | 0 | 1104492 | B0 | ACC - LUMP SUM
4 | E4P43 | 42636215201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-03-31 | 2106087 | 2106087 | 2037825 | 0 | 0 | 2037825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037825 | 2037825 | 0 | 2671514
4 | E4P91 | 43397915201 | F364509634 | MAYTIN ENGINEERING CORP. | N/A | N/A | N/A | N/A | 2014-06-06 | 682040 | 677370 | 696418 | -4669.44 | 0 | 696418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696418 | 696418 | 0 | 468108
4 | T4311 | 42924615201 | F593749359 | DESIGN-BUILD ENGINEERS & CONTRA | N/A | N/A | N/A | N/A | 2011-04-27 | 3983113 | 4102286 | 4023382 | 119173.98 | -101442 | 3920334 | -101442 | 0 | 0 | 0 | 0 | 0 | -101442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101442 | 3921940 | 3920334 | -1606 | 3335896
4 | T4345 | 40836215201 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2013-05-22 | 1202547 | 3085087 | 3080524 | 1882539.48 | 0 | 3080524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080524 | 3080524 | 0 | 1238644
4 | T4374 | 43019615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 348825 | 348825 | 339314 | 0 | 0 | 339314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339314 | 339314 | 0 | 385157
4 | T4380 | 42974015201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2014-09-24 | 480024 | 480024 | 456013 | 0 | 0 | 456013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456013 | 456013 | 0 | 486438
4 | T4384 | 42973815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 547622 | 548351 | 527560 | 728.52 | 0 | 527560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527560 | 527560 | 0 | 546487
4 | T4394 | 43060225203 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 831515 | 893080 | 843974 | 61564.57 | 0 | 843974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843974 | 843974 | 0 | 850266
5 | BDT74 | 41299435201 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2011-11-07 | 27584500 | 29571831 | 29554288 | 1987331.16 | 0 | 29554288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29554288 | 29554288 | 0 | 27584500 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE
5 | E5W28 | 41499925201 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2014-05-06 | 260959 | 242155 | 231155 | -18804.58 | 0 | 231155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231155 | 231155 | 0 | 250000
5 | E5W30 | 43214919201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2014-02-18 | 3585585 | 3585585 | 3535585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3535585 | 0 | -3535585 | 3478319 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E5W68 | 24099295201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2014-12-02 | 518519 | 518519 | 502367 | 0 | 0 | 502367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502367 | 502367 | 0 | 460954
5 | T5401 | 42201515201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-04-24 | 4603457 | 4806215 | 4675801 | 202758.21 | 0 | 4675281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4675801 | 4675281 | -520 | 4500360
5 | T5404 | 24023335201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2012-05-23 | 10111333 | 10458539 | 10091859 | 347206.49 | 0 | 10008344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10091859 | 10008344 | -83514 | 9890702
5 | T5483 | 42727915201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 2914000 | 2914000 | 2885939 | 0 | 0 | 2771829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2885939 | 2771829 | -114111 | 2978859 | B0 | ACC - LUMP SUM
5 | T5488 | 42907915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 5354000 | 5354000 | 5430627 | 0 | -11100 | 5333292 | 0 | 0 | 0 | 0 | 0 | -11100 | -11100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11100 | 5419527 | 5333292 | -86235 | 5993025 | B0 | ACC - LUMP SUM
5 | T5494 | 42488715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 1795728 | 1795728 | 1805364 | 0 | 0 | 1760006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1805364 | 1760006 | -45358 | 1761956 | B0 | ACC - LUMP SUM
5 | T5495 | 42886715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 6951000 | 6886782 | 6967320 | -64218.06 | 0 | 6782907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6967320 | 6782907 | -184413 | 7479523 | B0 | ACC - LUMP SUM
5 | T5501 | 42886215201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 2189795 | 2189795 | 2201353 | 0 | 0 | 2169152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2201353 | 2169152 | -32201 | 2211253 | B0 | ACC - LUMP SUM
5 | T5520 | 23867825201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-12-03 | 544771 | 536238 | 524085 | -8533.35 | 0 | 520797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524085 | 520797 | -3288 | 761207
6 | E6G56 | 42611915201 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2013-01-31 | 4988310 | 4988310 | 4865434 | 0 | 0 | 4865434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4865434 | 4865434 | 0 | 5875816
6 | E6H61 | 43119215201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2014-06-12 | 838500 | 838500 | 763060 | 0 | 0 | 763060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763060 | 763060 | 0 | 850347
6 | E6I14 | 43209815201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2014-02-27 | 328706 | 328706 | 320865 | 0 | 0 | 320865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320865 | 320865 | 0 | 370269 | B0 | ACC - LUMP SUM
6 | E6I57 | 43119015201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2014-09-25 | 619046 | 619046 | 562195 | 0 | 0 | 562195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562195 | 562195 | 0 | 838614
6 | E6I77 | 24994175201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2014-08-28 | 1198756 | 1198756 | 1094981 | 0 | 0 | 1094981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094981 | 1094981 | 0 | 1268938
6 | E6I78 | 43081615201 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2014-07-31 | 1207213 | 1207213 | 1139099 | 0 | 0 | 1129248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139099 | 1129248 | -9851 | 1208780
6 | E6I83 | 43081415201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-11-20 | 94720 | 94720 | 88652 | 0 | 0 | 88652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88652 | 88652 | 0 | 126847 | B0 | ACC - LUMP SUM
6 | E6I85 | 41774079201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2014-03-27 | 502650 | 502650 | 470337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470337 | 0 | -470337 | 678578 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6I87 | 42934415201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-10-30 | 1872759 | 1872759 | 1693855 | 0 | 0 | 1636257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1693855 | 1636257 | -57598 | 1934017
6 | E6J40 | 43590015201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-01-29 | 248698 | 248698 | 217030 | 0 | 0 | 217030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217030 | 217030 | 0 | 248763
6 | T6207 | 41984815201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 6954601 | 7631613 | 7814383 | 677012.41 | 0 | 7814501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814383 | 7814501 | 117 | 8225852
6 | T6278 | 24994115201 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2012-05-23 | 14358568 | 13941778 | 14063237 | -416790.24 | 0 | 13981485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14063237 | 13981485 | -81752 | 12500129
6 | T6322 | 42750525201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 2272423 | 2348653 | 2183494 | 76230.06 | 0 | 2177671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2183494 | 2177671 | -5822 | 2206205
6 | T6324 | 42913615201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 3959132 | 4129233 | 4133336 | 170101.12 | 0 | 4124281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4133336 | 4124281 | -9055 | 4168714
6 | T6351 | 42904315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-02-05 | 643250 | 643250 | 597697 | 0 | 0 | 597697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597697 | 597697 | 0 | 824250 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
6 | T6355 | 42902115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 1061111 | 1061111 | 1066049 | 0 | 0 | 1066049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066049 | 1066049 | 0 | 1021385 | B0 | ACC - LUMP SUM
6 | T6361 | 43003115201 | F263976898 | AMROAD LLC | N/A | N/A | N/A | N/A | 2014-09-24 | 327561 | 327561 | 279990 | 0 | 0 | 279933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279990 | 279933 | -57 | 306614
6 | T6363 | 42751515201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 5378636 | 5591336 | 6965131 | 212700 | 0 | 6964220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6965131 | 6964220 | -911 | 4504474
6 | T6368 | 43003315201 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2014-07-30 | 619197 | 643584 | 598711 | 24386.71 | 0 | 598703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598711 | 598703 | -8 | 631340
7 | E7J96 | 43066115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-11-26 | 2030000 | 2030000 | 1980915 | 0 | 0 | 1934577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980915 | 1934577 | -46338 | 1984600 | B0 | ACC - LUMP SUM
7 | T7325 | 42900515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2013-06-19 | 15491284 | 16150823 | 16100076 | 659539.56 | 0 | 16143898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16100076 | 16143898 | 43822 | 16955600
7 | T7329 | 42907325201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-10-30 | 5019226 | 5019226 | 4985077 | 0 | 0 | 4951447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4985077 | 4951447 | -33631 | 4751500 | B0 | ACC - LUMP SUM
7 | T7340 | 42715415201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-04-30 | 1688000 | 1688000 | 1644638 | 0 | 0 | 1606582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1644638 | 1606582 | -38056 | 2156800 | B0 | ACC - LUMP SUM
7 | T7341 | 42896115201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-03-26 | 5790872 | 5790872 | 5714657 | 0 | 0 | 5660340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5714657 | 5660340 | -54316 | 6079410
8 | E8L99 | 41546225202 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2012-05-22 | 19914762 | 20008584 | 19972782 | 93822.3 | -154000 | 19745451 | 0 | 0 | 0 | 0 | 0 | -154000 | -154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -154000 | 19818782 | 19745451 | -73332 | 20630727
8 | E8M77 | 40615145201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2013-03-26 | 11249740 | 11481897 | 10973748 | 232156.69 | 0 | 10925662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10973748 | 10925662 | -48086 | 11244846
8 | E8M80 | 42768515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2013-05-14 | 6746576 | 6938552 | 6915696 | 191976.43 | 0 | 6919857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6915696 | 6919857 | 4160 | 6459218
8 | E8M93 | 43108935201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2013-05-21 | 7676614 | 7714483 | 7540572 | 37868.44 | 0 | 7491522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7540572 | 7491522 | -49050 | 8536509
8 | E8N21 | 42902315201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2014-03-11 | 6573418 | 6704790 | 6985687 | 131371.79 | -3000 | 6966867 | 0 | 0 | 0 | 0 | 0 | -3000 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 6982687 | 6966867 | -15820 | 8559769

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1497 | 43003715201 | 2012-03-28 | QTR3 | 11/12 | 1 | 1 | 60 | 99 | 261 | -162 | 162 | 0 | 39 | 0 | 90611 | 0 | 90611 | 89035 | 88897 | -43964 | 0 | -43964 | 44933 | 44933 | 0 | -1576 | 17 | 4 | 0 | 0 | 0 | 0 | 0 | -1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | -1576 | 0 | F593490202 | ALDON BOOKHARDT ROOFING INC. | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 | 2013-05-30 | QTR4 | 12/13 | 113 | 111867.75 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 7 | 01co | 1 | 7
01CO | 01 | T1501 | 40828635201 | 2012-06-20 | QTR4 | 11/12 | 1 | 7 | 700 | 779 | 779 | 0 | 0 | 0 | 75 | 4 | 14784300 | 133862 | 14650438 | 15330267 | 14964740 | 0 | 0 | 0 | 14964740 | 15047703 | 82963 | 545967 | 48 | 0 | 4 | 334024 | 0 | 0 | 0 | 328205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 635924 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-09-10 | QTR1 | 15/16 | 2014-10-22 | QTR2 | 14/15 | 113 | 13767013.79 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 7 | 01do | 8 | 14
01CO | 01 | T1527 | 41787615201 | 2013-02-06 | QTR3 | 12/13 | 2 | 9 | 768 | 835 | 810 | 25 | 0 | 0 | 67 | 0 | 12312349 | 150000 | 12162349 | 13258294 | 12897465 | 0 | 0 | 0 | 12897465 | 12514104 | -383360 | 945945 | 41 | 0 | 0 | 262529 | 0 | 0 | 0 | 689450 | 18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 951980 | 18277 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-10 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 115 | 15340403.45 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 6 | 02co | 15 | 20
01CO | 01 | T1546 | 42910415201 | 2014-02-26 | QTR3 | 13/14 | 1 | 2 | 130 | 190 | 219 | -29 | 29 | 0 | 36 | 24 | 2195109 | 50000 | 2145109 | 2159801 | 2156391 | -50518 | 0 | -50518 | 2105873 | 2085969 | -19904 | -35308 | 11 | 0 | 10 | -17725 | 0 | 11 | 14 | 8387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 24 | -9339 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2015-09-13 | QTR1 | 15/16 | 2015-04-14 | QTR4 | 14/15 | 115 | 2641240.24 | B0 | ACC - LUMP SUM | 16 | 14 | 0 | 0 | 0 | 0 |  | CO | 4 | 02do | 21 | 24
01CO | 01 | T1566 | 20010575201 | 2014-04-30 | QTR4 | 13/14 | 1 | 4 | 300 | 324 | 281 | 43 | 0 | 0 | 24 | 0 | 855140 | 0 | 855140 | 880470 | 883951 | 0 | 0 | 0 | 883951 | 883951 | 0 | 25330 | 14 | 0 | 0 | 17931 | 1430 | 0 | 0 | 7399 | 7399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25330 | 8829 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 | 2015-08-06 | QTR1 | 15/16 | 118 | 1061209.63 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO | 13 | 03co | 25 | 37
01CO | 01 | T1578 | 43086015201 | 2013-12-04 | QTR2 | 13/14 | 2 | 9 | 270 | 410 | 407 | 3 | 0 | 0 | 140 | 0 | 5634855 | 53649 | 5581206 | 5727333 | 5707127 | 0 | 0 | 0 | 5707127 | 5640992 | -66135 | 92478 | 121 | 0 | 0 | 20908 | 2691 | 0 | 0 | 36741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80103 | 2691 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-07-06 | QTR1 | 15/16 | 2015-05-04 | QTR4 | 14/15 | 108 | 5433904.15 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 |  | CO | 3 | 03do | 38 | 40
01CO | 01 | T1A14 | 43341115201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 110 | 131 | 131 | 0 | 0 | 0 | 12 | 9 | 247066 | 11866 | 235200 | 270085 | 250380 | 0 | 0 | 0 | 250380 | 250380 | 0 | 23019 | 10 | 0 | 9 | 23019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 23019 | 0 | F593339407 | TAGARELLI CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-08-11 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 108 | 256990.36 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO | 6 | 04co | 41 | 46
01DO | 01 | E1J71 | 41263625201 | 2012-05-31 | QTR4 | 11/12 | 2 | 14 | 565 | 936 | 936 | 0 | 0 | 0 | 69 | 302 | 6703703 | 50000 | 6653703 | 7531485 | 7530256 | 0 | 0 | 0 | 7530256 | 7530256 | 0 | 827782 | 22 | 0 | 121 | 99861 | 9614 | 0 | 95 | 314019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 401293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 815173 | 9614 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 | 2015-06-08 | QTR4 | 14/15 | 113 | 638850 | A3 | ICC - DESIGN/BUILD - MINOR | 57 | 47 | 0 | 0 | 0 | 0 |  | DO | 4 | 04do | 47 | 50
01DO | 01 | E1N08 | 42347115201 | 2014-06-19 | QTR4 | 13/14 | 1 | 4 | 200 | 242 | 242 | 0 | 0 | 0 | 36 | 6 | 1880948 | 50000 | 1830948 | 1908269 | 1858269 | 0 | 0 | 0 | 1858269 | 1834616 | -23653 | 27320 | 16 | 0 | 0 | 0 | 0 | 7 | 5 | 22343 | 8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4977 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 27320 | 8999 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-07-31 | QTR1 | 15/16 | 2015-06-22 | QTR4 | 14/15 | 108 | 1405116.38 | B0 | ACC - LUMP SUM | 0 | 13 | 0 | 0 | 0 | 0 |  | DO | 9 | 05co | 51 | 59
01DO | 01 | E1N47 | 43019125201 | 2014-06-19 | QTR4 | 13/14 | 2 | 1 | 175 | 213 | 204 | 9 | 0 | 0 | 38 | 0 | 4346396 | 50000 | 4296396 | 4413679 | 4400332 | 0 | 0 | 0 | 4400332 | 4322422 | -77910 | 67283 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 67283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67283 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2015-08-13 | QTR1 | 15/16 | 2015-04-13 | QTR4 | 14/15 | 118 | 4460046.21 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 13 | 0 | 0 | 0 | 0 | T | DO | 3 | 05do | 60 | 62
01DO | 01 | E1N64 | 43160515201 | 2014-08-29 | QTR1 | 14/15 | 1 | 0 | 150 | 176 | 175 | 1 | 0 | 0 | 26 | 0 | 3021172 | 50000 | 2971172 | 3021172 | 3068023 | 0 | 0 | 0 | 3068023 | 2921086 | -146936 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-25 | QTR1 | 15/16 | 2015-06-12 | QTR4 | 14/15 | 118 | 3419370.6 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO | 9 | 06co | 63 | 71
01DO | 01 | E1N71 | 43006015201 | 2015-01-15 | QTR3 | 14/15 | 1 | 0 | 80 | 95 | 92 | 3 | 0 | 0 | 15 | 0 | 567387 | 27173 | 540214 | 567387 | 532744 | 0 | 0 | 0 | 532744 | 532744 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2015-09-23 | QTR1 | 15/16 | 2015-08-18 | QTR1 | 15/16 | 118 | 519186.9 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO | 10 | 06do | 72 | 81
01DO | 01 | E1N96 | 42949925201 | 2014-10-16 | QTR2 | 14/15 | 1 | 1 | 90 | 91 | 51 | 40 | 0 | 0 | 1 | 0 | 229418 | 9702 | 219716 | 228371 | 218669 | 0 | 0 | 0 | 218669 | 218669 | 0 | -1047 | 0 | 0 | 0 | -1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1047 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-07-21 | QTR1 | 15/16 | 2015-06-09 | QTR4 | 14/15 | 115 | 179058.8 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO | 4 | 07co | 82 | 85
01DO | 01 | E1O06 | 43574215201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 50 | 50 | 16 | 34 | 0 | 0 | 0 | 0 | 140780 | 9482 | 131298 | 140780 | 132639 | 0 | 0 | 0 | 132639 | 265277 | 132639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 0 | F650968383 | WHITELEAF LLC DBA TRAFFIC SOLUTIONS | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 | 2015-03-02 | QTR3 | 14/15 | 113 | 193962.81 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO | 1 | 07do | 86 | 86
02CO | 02 | T2443 | 42698615201 | 2013-02-06 | QTR3 | 12/13 | 1 | 0 | 150 | 204 | 203 | 1 | 0 | 0 | 45 | 9 | 4870523 | 56040 | 4814483 | 4870523 | 4844339 | 0 | 0 | 0 | 4844339 | 4835215 | -9124 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-07-13 | QTR1 | 15/16 | 2013-12-22 | QTR2 | 13/14 | 209 | 5528433.55 |  |  | 9 | 8 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 87 | 86
02CO | 02 | T2512 | 42869015201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 260 | 389 | 389 | 0 | 0 | 0 | 129 | 0 | 8787879 | 96597 | 8691282 | 8787879 | 8967904 | 0 | 0 | 0 | 8967904 | 8851811 | -116093 | 0 | 104 | 0 | 0 | 5708 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10581 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 | 2015-04-10 | QTR4 | 14/15 | 214 | 9570318.55 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 5 | 08do | 87 | 91
02CO | 02 | T2527 | 42870515201 | 2014-05-21 | QTR4 | 13/14 | 1 | 2 | 195 | 311 | 311 | 0 | 0 | 0 | 93 | 23 | 3855596 | 50000 | 3805596 | 3937461 | 4006951 | 0 | 0 | 0 | 4006951 | 3890841 | -116110 | 81865 | 69 | 0 | 7 | 33849 | 0 | 0 | 16 | 66627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 100476 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 | 2015-06-10 | QTR4 | 14/15 | 208 | 3913298.22 |  |  | 18 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2530 | 21156035201 | 2014-05-21 | QTR4 | 13/14 | 1 | 3 | 150 | 207 | 196 | 11 | 0 | 0 | 57 | 0 | 1259477 | 0 | 1259477 | 1284233 | 1254859 | 0 | 0 | 0 | 1254859 | 1254859 | 0 | 24756 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 24756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 38 | 0 | 24756 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 | 2015-05-26 | QTR4 | 14/15 | 216 | 957005.79 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2535 | 42053145201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 120 | 164 | 164 | 0 | 0 | 0 | 21 | 23 | 1754776 | 50000 | 1704776 | 1824298 | 1779783 | 0 | 0 | 0 | 1779783 | 1779783 | 0 | 69521 | 15 | 0 | 0 | 160 | 0 | 0 | 23 | 73186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 73346 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 | 2015-06-17 | QTR4 | 14/15 | 214 | 1169715.46 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO |  | 0
02CO | 02 | T2543 | 43055515201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 70 | 93 | 93 | 0 | 0 | 0 | 23 | 0 | 1738869 | 50000 | 1688869 | 1738869 | 1721840 | 0 | 0 | 0 | 1721840 | 1698982 | -22858 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-07-01 | QTR1 | 15/16 | 2015-02-13 | QTR3 | 14/15 | 214 | 1963162.15 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2R18 | 42468515201 | 2013-05-23 | QTR4 | 12/13 | 2 | 2 | 540 | 689 | 689 | 0 | 0 | 0 | 136 | 13 | 8195419 | 86278 | 8109141 | 8206705 | 8178408 | 0 | 0 | 0 | 8178408 | 8124680 | -53727 | 11286 | 89 | 0 | 0 | 43065 | 0 | 0 | 13 | 15182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23141 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 69534 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-08-18 | QTR1 | 15/16 | 2015-06-03 | QTR4 | 14/15 | 214 | 8761555.44 | B8 | ACC - DESIGN/BUILD - MAJOR | 13 | 47 | 0 | 0 | -11855 | 0 |  | DO
02DO | 02 | E2R94 | 42822915201 | 2013-08-21 | QTR1 | 13/14 | 1 | 0 | 469 | 536 | 533 | 3 | 0 | 0 | 35 | 32 | 2445796 | 50000 | 2395796 | 2445796 | 2450466 | 0 | 0 | 0 | 2450466 | 2449755 | -711 | 0 | 13 | 0 | 0 | 20184 | 0 | 0 | 32 | 14554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 49896 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-17 | QTR1 | 15/16 | 2015-06-12 | QTR4 | 14/15 | 216 | 2404678.02 |  |  | 32 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2S71 | 42869515201 | 2014-04-23 | QTR4 | 13/14 | 1 | 1 | 230 | 307 | 307 | 0 | 0 | 0 | 56 | 21 | 7686286 | 65080 | 7621206 | 7580608 | 7142686 | 0 | 0 | 0 | 7142686 | 6953829 | -188858 | -105678 | 42 | 0 | 0 | 0 | 0 | 0 | 21 | 57675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -48003 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 | 2015-05-14 | QTR4 | 14/15 | 209 | 6348256.45 |  |  | 21 | 14 | 0 | 0 | -105678 | 0 |  | DO
02DO | 02 | E2S89 | 20954125201 | 2014-04-23 | QTR4 | 13/14 | 1 | 0 | 360 | 373 | 340 | 33 | 0 | 0 | 13 | 0 | 1997720 | 50000 | 1947720 | 1997720 | 2088940 | 0 | 0 | 0 | 2088940 | 2081779 | -7161 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 | 2015-06-16 | QTR4 | 14/15 | 208 | 2345342.1 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3088 | 21894615201 | 2012-07-25 | QTR1 | 12/13 | 1 | 6 | 608 | 853 | 852 | 1 | 0 | 0 | 205 | 40 | 13348458 | 0 | 13348458 | 13883485 | 14095924 | 0 | 0 | 0 | 14095924 | 14095514 | -409 | 535027 | 149 | 0 | 0 | 90305 | 0 | 0 | 40 | 281269 | 169088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 414064 | 169088 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 | 2015-02-24 | QTR3 | 14/15 | 321 | 14378815.2 |  |  | 10 | 56 | 0 | 0 | -173321 | 0 |  | CO
03CO | 03 | T3396 | 42323315201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 300 | 504 | 498 | 6 | 0 | 0 | 173 | 31 | 2789487 | 50000 | 2739487 | 2763621 | 2700963 | 0 | 0 | 0 | 2700963 | 2673321 | -27642 | -25866 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 17268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | -8599 | 0 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-05-18 | QTR4 | 14/15 | 314 | 2906373.5 |  |  | 31 | 19 | 0 | 0 | -25866 | 0 |  | CO
03CO | 03 | T3401 | 42323415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 300 | 478 | 474 | 4 | 0 | 0 | 178 | 0 | 2645210 | 50000 | 2595210 | 2645210 | 2628131 | 0 | 0 | 0 | 2628131 | 2609172 | -18959 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2015-07-06 | QTR1 | 15/16 | 2015-05-08 | QTR4 | 14/15 | 314 | 2957617.43 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3409 | 42462215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 145 | 201 | 197 | 4 | 0 | 0 | 56 | 0 | 2097227 | 50000 | 2047227 | 2097227 | 2093592 | 0 | 0 | 0 | 2093592 | 1978887 | -114705 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-09 | QTR1 | 15/16 | 2015-05-05 | QTR4 | 14/15 | 321 | 2813050.27 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3411 | 42636815201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 130 | 196 | 196 | 0 | 0 | 0 | 66 | 0 | 577753 | 0 | 577753 | 577753 | 581122 | 0 | 0 | 0 | 581122 | 581122 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263312611 | R B M CONTRACTING SERVICES LLC | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 | 2015-07-22 | QTR1 | 15/16 | 313 | 613088.19 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3424 | 41343515201 | 2013-02-06 | QTR3 | 12/13 | 2 | 3 | 355 | 512 | 508 | 4 | 0 | 0 | 142 | 15 | 3882641 | 50000 | 3832641 | 3972326 | 3728903 | 0 | 0 | 0 | 3728903 | 3719464 | -9439 | 89685 | 86 | 0 | 4 | 26009 | 0 | 39 | 11 | 77908 | 92400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 15 | 103918 | 92400 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 | 2014-09-16 | QTR1 | 14/15 | 308 | 4647469.69 |  |  | 15 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3434 | 42987815201 | 2014-08-27 | QTR1 | 14/15 | 2 | 0 | 160 | 197 | 197 | 0 | 0 | 0 | 35 | 2 | 459930 | 20930 | 439000 | 459930 | 451610 | 0 | 0 | 0 | 451610 | 451610 | 0 | 0 | 17 | 0 | 0 | 1560 | 0 | 0 | 2 | 11050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12610 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 | 2015-06-15 | QTR4 | 14/15 | 313 | 439830 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 2 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3455 | 43000415201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 150 | 176 | 176 | 0 | 0 | 0 | 26 | 0 | 919509 | 0 | 919509 | 919509 | 927409 | 0 | 0 | 0 | 927409 | 927409 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 | 2015-07-16 | QTR1 | 15/16 | 308 | 817764.49 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3468 | 42696515201 | 2014-06-18 | QTR4 | 13/14 | 2 | 0 | 220 | 294 | 284 | 10 | 0 | 0 | 74 | 0 | 1826839 | 50000 | 1776839 | 1826839 | 1794755 | 0 | 0 | 0 | 1794755 | 1727691 | -67064 | 0 | 24 | 0 | 0 | 14633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 1080 | 0 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 18747 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 | 2015-06-15 | QTR4 | 14/15 | 321 | 1783054.33 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3502 | 42764915201 | 2014-06-18 | QTR4 | 13/14 | 2 | 2 | 125 | 199 | 197 | 2 | 0 | 0 | 63 | 11 | 633977 | 26778 | 607199 | 703188 | 695402 | 0 | 0 | 0 | 695402 | 695402 | 0 | 69211 | 34 | 0 | 8 | 5089 | 0 | 0 | 3 | 70611 | 25322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 11 | 75699 | 25322 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-08-19 | QTR1 | 15/16 | 2015-05-21 | QTR4 | 14/15 | 308 | 559212.99 |  |  | 8 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3530 | 43174415201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 60 | 67 | 66 | 1 | 0 | 0 | 7 | 0 | 217000 | 0 | 217000 | 217000 | 216611 | 0 | 0 | 0 | 216611 | 216611 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593715775 | PYRAMID EXCAVATION INC. | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 | 2015-06-19 | QTR4 | 14/15 | 321 | 236371.06 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3535 | 42693615201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 85 | 109 | 109 | 0 | 0 | 0 | 24 | 0 | 481388 | 26436 | 454953 | 481388 | 440397 | 0 | 0 | 0 | 440397 | 440397 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 | 2015-06-21 | QTR4 | 14/15 | 313 | 540650.67 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3536 | 40393125201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 60 | 69 | 69 | 0 | 0 | 0 | 9 | 0 | 369064 | 23136 | 345929 | 369064 | 338614 | 0 | 0 | 0 | 338614 | 338614 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-07-21 | QTR1 | 15/16 | 2015-06-13 | QTR4 | 14/15 | 321 | 486851.74 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3L71 | 42874415201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 160 | 192 | 192 | 0 | 0 | 0 | 32 | 0 | 1490639 | 50000 | 1440639 | 1490639 | 1445553 | 0 | 0 | 0 | 1445553 | 1451830 | 6277 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 | 2014-12-14 | QTR2 | 14/15 | 314 | 1584506.78 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M60 | 42697215201 | 2014-12-11 | QTR2 | 14/15 | 1 | 0 | 100 | 134 | 134 | 0 | 0 | 0 | 32 | 2 | 1718927 | 50000 | 1668927 | 1718927 | 1766800 | 0 | 0 | 0 | 1766800 | 1673682 | -93118 | 0 | 10 | 0 | 2 | 3651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3651 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-07-22 | QTR1 | 15/16 | 308 | 2202753.65 |  |  | 2 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M93 | 43078215201 | 2014-12-11 | QTR2 | 14/15 | 1 | 0 | 70 | 77 | 76 | 1 | 0 | 0 | 6 | 1 | 1217750 | 50000 | 1167750 | 1217750 | 1189202 | 0 | 0 | 0 | 1189202 | 1136275 | -52927 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2880 | 0 | F580538940 | OXFORD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-09-08 | QTR1 | 15/16 | 2015-07-08 | QTR1 | 15/16 | 314 | 1216619.67 |  |  | 1 | 1 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4311 | 42924615201 | 2011-04-27 | QTR4 | 10/11 | 1 | 1 | 180 | 266 | 319 | -53 | 53 | 0 | 48 | 38 | 3983113 | 50000 | 3933113 | 4102286 | 4023382 | -101442 | 0 | -101442 | 3921940 | 3920334 | -1606 | 119174 | 36 | 0 | 2 | 3257 | 0 | 0 | 33 | 132841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 136098 | 0 | F593749359 | DESIGN-BUILD ENGINEERS & CONTRA | N/A | N/A | N/A | N/A | 2015-08-20 | QTR1 | 15/16 | 2012-05-07 | QTR4 | 11/12 | 409 | 3335896.13 |  |  | 9 | 12 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4345 | 40836215201 | 2013-05-22 | QTR4 | 12/13 | 1 | 5 | 266 | 650 | 650 | 0 | 0 | 0 | 89 | 295 | 1202547 | 50000 | 1152547 | 3085087 | 3080524 | 0 | 0 | 0 | 3080524 | 3080524 | 0 | 1882539 | 48 | 14 | 266 | 1575597 | 0 | 0 | 29 | 324673 | 98769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8860 | 8860 | 0 | 0 | 0 | 0 | 14 | 295 | 1908989 | 107629 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 | 2015-05-21 | QTR4 | 14/15 | 412 | 1238644.33 |  |  | 118 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4374 | 43019615201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 102 | 112 | 110 | 2 | 0 | 0 | 10 | 0 | 348825 | 18115 | 330710 | 348825 | 339314 | 0 | 0 | 0 | 339314 | 339314 | 0 | 0 | 9 | 0 | 0 | 3246 | 0 | 0 | 0 | 5358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8604 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-22 | QTR1 | 15/16 | 2015-06-10 | QTR4 | 14/15 | 412 | 385157.48 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4380 | 42974015201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 100 | 118 | 117 | 1 | 0 | 0 | 18 | 0 | 480024 | 22736 | 457288 | 480024 | 456013 | 0 | 0 | 0 | 456013 | 456013 | 0 | 0 | 16 | 0 | 0 | 2267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2267 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 412 | 486438.28 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4384 | 42973815201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 96 | 101 | 99 | 2 | 0 | 0 | 5 | 0 | 547622 | 25962 | 521660 | 548351 | 527560 | 0 | 0 | 0 | 527560 | 527560 | 0 | 729 | 4 | 0 | 0 | 1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 | 2015-07-02 | QTR1 | 15/16 | 409 | 546487.47 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4394 | 43060225203 | 2014-05-21 | QTR4 | 13/14 | 3 | 1 | 243 | 281 | 280 | 1 | 0 | 0 | 38 | 0 | 831515 | 40849 | 790666 | 893080 | 843974 | 0 | 0 | 0 | 843974 | 843974 | 0 | 61565 | 26 | 0 | 0 | 2400 | 0 | 0 | 0 | 68329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70729 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 | 2015-06-08 | QTR4 | 14/15 | 412 | 850266.14 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4P28 | 43053415201 | 2014-01-03 | QTR3 | 13/14 | 1 | 1 | 265 | 342 | 335 | 7 | 0 | 0 | 77 | 0 | 1630613 | 50000 | 1580613 | 1680613 | 1713025 | 0 | 0 | 0 | 1713025 | 1712786 | -239 | 50000 | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 46404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 46404 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2015-08-13 | QTR1 | 15/16 | 2015-07-09 | QTR1 | 15/16 | 408 | 1510582.53 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P42 | 42744115201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 237 | 285 | 285 | 0 | 0 | 0 | 18 | 30 | 1055000 | 50000 | 1005000 | 1055000 | 1018660 | 0 | 0 | 0 | 1018660 | 1018660 | 0 | 0 | 7 | 0 | 0 | 5225 | 0 | 0 | 30 | 11535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16760 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-09-24 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 409 | 1104492 | B0 | ACC - LUMP SUM | 30 | 11 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P43 | 42636215201 | 2014-03-31 | QTR3 | 13/14 | 1 | 0 | 371 | 415 | 411 | 4 | 0 | 0 | 40 | 4 | 2106087 | 50000 | 2056087 | 2106087 | 2037825 | 0 | 0 | 0 | 2037825 | 2037825 | 0 | 0 | 25 | 0 | 0 | 4164 | 0 | 0 | 0 | 5698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 15442 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 | 2015-08-14 | QTR1 | 15/16 | 408 | 2671513.63 |  |  | 4 | 15 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P91 | 43397915201 | 2014-06-06 | QTR4 | 13/14 | 4 | 1 | 223 | 291 | 290 | 1 | 0 | 0 | 48 | 20 | 682040 | 21400 | 660640 | 677370 | 696418 | 0 | 0 | 0 | 696418 | 696418 | 0 | -4669 | 31 | 0 | 0 | 5986 | 0 | 0 | 20 | 10647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 11963 | 0 | F364509634 | MAYTIN ENGINEERING CORP. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 412 | 468107.77 |  |  | 20 | 17 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | BDT74 | 41299435201 | 2011-11-07 | QTR2 | 11/12 | 5 | 15 | 460 | 802 | 1058 | -256 | 256 | 0 | 77 | 265 | 27584500 | 150000 | 27434500 | 29571831 | 29554288 | 0 | 0 | 0 | 29554288 | 29554288 | 0 | 1987331 | 26 | 0 | 0 | 294952 | 5697 | 0 | 0 | 366049 | 3040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 1475287 | 169381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 2136288 | 178118 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2015-09-07 | QTR1 | 15/16 | 2015-02-11 | QTR3 | 14/15 | 507 | 27584500 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5401 | 42201515201 | 2013-04-24 | QTR4 | 12/13 | 4 | 5 | 290 | 361 | 361 | 0 | 0 | 0 | 50 | 21 | 4603457 | 50000 | 4553457 | 4806215 | 4675801 | 0 | 0 | 0 | 4675801 | 4675281 | -520 | 202758 | 32 | 0 | 5 | 67573 | 12260 | 0 | 16 | 186828 | 13247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 254401 | 25507 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-08 | QTR1 | 15/16 | 2014-08-18 | QTR1 | 14/15 | 509 | 4500359.97 |  |  | 3 | 18 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5404 | 24023335201 | 2012-05-23 | QTR4 | 11/12 | 5 | 6 | 710 | 980 | 980 | 0 | 0 | 0 | 165 | 105 | 10111333 | 50000 | 10061333 | 10458539 | 10091859 | 0 | 0 | 0 | 10091859 | 10008344 | -83514 | 347206 | 129 | 0 | 21 | 292661 | 435 | 0 | 84 | 60822 | 1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 355274 | 1518 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 | 2015-05-03 | QTR4 | 14/15 | 507 | 9890702.1 |  |  | 105 | 36 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5483 | 42727915201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 200 | 273 | 273 | 0 | 0 | 0 | 63 | 10 | 2914000 | 50000 | 2864000 | 2914000 | 2885939 | 0 | 0 | 0 | 2885939 | 2771829 | -114111 | 0 | 37 | 0 | 10 | 1702 | 0 | 0 | 0 | 14745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 16446 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 | 2015-06-12 | QTR4 | 14/15 | 513 | 2978859.49 | B0 | ACC - LUMP SUM | 10 | 26 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5488 | 42907915201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 290 | 439 | 439 | 0 | 0 | 0 | 149 | 0 | 5354000 | 59000 | 5295000 | 5354000 | 5430627 | -11100 | 0 | -11100 | 5419527 | 5329312 | -90214 | 0 | 128 | 0 | 0 | 17682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17682 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-18 | QTR1 | 15/16 | 2015-05-29 | QTR4 | 14/15 | 509 | 5993024.89 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5494 | 42488715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 180 | 247 | 247 | 0 | 0 | 0 | 67 | 0 | 1795728 | 50000 | 1745728 | 1795728 | 1805364 | 0 | 0 | 0 | 1805364 | 1760006 | -45358 | 0 | 46 | 0 | 0 | 5154 | 0 | 0 | 0 | 24811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29965 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 | 2015-05-11 | QTR4 | 14/15 | 514 | 1761956.22 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5495 | 42886715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 1 | 300 | 328 | 303 | 25 | 0 | 0 | 28 | 0 | 6951000 | 72000 | 6879000 | 6886782 | 6967320 | 0 | 0 | 0 | 6967320 | 6782907 | -184413 | -64218 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -72353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -64218 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 | 2015-06-30 | QTR4 | 14/15 | 509 | 7479522.66 | B0 | ACC - LUMP SUM | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5501 | 42886215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 110 | 176 | 176 | 0 | 0 | 0 | 66 | 0 | 2189795 | 50000 | 2139795 | 2189795 | 2201353 | 0 | 0 | 0 | 2201353 | 2169152 | -32201 | 0 | 42 | 0 | 0 | 54576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54576 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 | 2015-04-24 | QTR4 | 14/15 | 507 | 2211253.07 | B0 | ACC - LUMP SUM | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5520 | 23867825201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 118 | 129 | 106 | 23 | 0 | 0 | 11 | 0 | 544771 | 36000 | 508771 | 536238 | 524085 | 0 | 0 | 0 | 524085 | 520797 | -3288 | -8533 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1651 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 | 2015-06-01 | QTR4 | 14/15 | 512 | 761207.45 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W28 | 41499925201 | 2014-05-06 | QTR4 | 13/14 | 1 | 1 | 100 | 127 | 125 | 2 | 0 | 0 | 12 | 15 | 260959 | 11000 | 249959 | 242155 | 231155 | 0 | 0 | 0 | 231155 | 231155 | 0 | -18805 | 3 | 0 | 0 | 0 | 0 | 0 | 15 | -18805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -18805 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2015-09-08 | QTR1 | 15/16 | 2015-04-15 | QTR4 | 14/15 | 509 | 250000 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W30 | 43214919201 | 2014-02-18 | QTR3 | 13/14 | 1 | 0 | 365 | 380 | 380 | 0 | 0 | 0 | 15 | 0 | 3585585 | 50000 | 3535585 | 3585585 | 3535585 | 0 | 0 | 0 | 3535585 | 0 | -3535585 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-07-10 | QTR1 | 15/16 | 2015-05-29 | QTR4 | 14/15 | 509 | 3478319.3 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W68 | 24099295201 | 2014-12-02 | QTR2 | 14/15 | 2 | 0 | 120 | 124 | 121 | 3 | 0 | 0 | 4 | 0 | 518519 | 21000 | 497519 | 518519 | 502367 | 0 | 0 | 0 | 502367 | 502367 | 0 | 0 | 2 | 0 | 0 | 2974 | 0 | 0 | 0 | 3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-07-28 | QTR1 | 15/16 | 2015-07-14 | QTR1 | 15/16 | 513 | 460954.46 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6207 | 41984815201 | 2013-05-22 | QTR4 | 12/13 | 3 | 5 | 280 | 396 | 396 | 0 | 0 | 0 | 74 | 42 | 6954601 | 80000 | 6874601 | 7631613 | 7814383 | 0 | 0 | 0 | 7814383 | 7814501 | 117 | 677012 | 49 | 10 | 0 | 192852 | 0 | 0 | 42 | 499242 | 19532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 42 | 692093 | 19532 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 | 2015-02-26 | QTR3 | 14/15 | 606 | 8225852.05 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6278 | 24994115201 | 2012-05-23 | QTR4 | 11/12 | 4 | 6 | 650 | 1028 | 1028 | 0 | 0 | 0 | 254 | 124 | 14358568 | 211699 | 14146869 | 13941778 | 14063237 | 0 | 0 | 0 | 14063237 | 13981485 | -81752 | -416790 | 215 | 0 | 69 | 338260 | 0 | 0 | 0 | 2917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198178 | 6413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | -283761 | 6413 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2015-09-22 | QTR1 | 15/16 | 2015-07-11 | QTR1 | 15/16 | 606 | 12500128.6 |  |  | 0 | 39 | 0 | 55 | -823116 | 0 |  | CO
06CO | 06 | T6322 | 42750525201 | 2013-09-25 | QTR1 | 13/14 | 4 | 2 | 240 | 450 | 450 | 0 | 0 | 0 | 210 | 0 | 2272423 | 51180 | 2221243 | 2348653 | 2183494 | 0 | 0 | 0 | 2183494 | 2177671 | -5822 | 76230 | 121 | 0 | 0 | 34580 | 0 | 42 | 0 | 65393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 99973 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-09-25 | QTR1 | 15/16 | 2015-07-28 | QTR1 | 15/16 | 606 | 2206205.25 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6324 | 42913615201 | 2013-09-25 | QTR1 | 13/14 | 2 | 2 | 260 | 410 | 407 | 3 | 0 | 0 | 150 | 0 | 3959132 | 51415 | 3907717 | 4129233 | 4133336 | 0 | 0 | 0 | 4133336 | 4124281 | -9055 | 170101 | 105 | 0 | 0 | 3694 | 0 | 30 | 0 | 157988 | 70393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 184274 | 70393 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-15 | QTR1 | 15/16 | 2015-04-07 | QTR4 | 14/15 | 606 | 4168713.7 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6351 | 42904315201 | 2014-02-05 | QTR3 | 13/14 | 3 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 643250 | 39250 | 604000 | 643250 | 597697 | 0 | 0 | 0 | 597697 | 597697 | 0 | 0 | 50 | 0 | 0 | 7236 | 0 | 0 | 0 | 8819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16056 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-17 | QTR1 | 15/16 | 2015-05-06 | QTR4 | 14/15 | 606 | 824250 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6355 | 42902115201 | 2014-05-21 | QTR4 | 13/14 | 2 | 0 | 160 | 194 | 194 | 0 | 0 | 0 | 34 | 0 | 1061111 | 50130 | 1010981 | 1061111 | 1066049 | 0 | 0 | 0 | 1066049 | 1066049 | 0 | 0 | 23 | 0 | 0 | 32501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49048 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-24 | QTR1 | 15/16 | 2015-06-22 | QTR4 | 14/15 | 606 | 1021385.13 | B0 | ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6361 | 43003115201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 150 | 191 | 187 | 4 | 0 | 0 | 41 | 0 | 327561 | 14958 | 312603 | 327561 | 279990 | 0 | 0 | 0 | 279990 | 279933 | -57 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263976898 | AMROAD LLC | N/A | N/A | N/A | N/A | 2015-09-24 | QTR1 | 15/16 | 2015-07-31 | QTR1 | 15/16 | 606 | 306614 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6363 | 42751515201 | 2013-05-22 | QTR4 | 12/13 | 1 | 5 | 350 | 521 | 521 | 0 | 0 | 0 | 171 | 0 | 5378636 | 50000 | 5328636 | 5591336 | 6965131 | 0 | 0 | 0 | 6965131 | 6964220 | -911 | 212700 | 97 | 0 | 0 | 415000 | 0 | 34 | 0 | 152786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 45540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 218326 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 | 2015-02-18 | QTR3 | 14/15 | 606 | 4504473.9 |  |  | 0 | 40 | 0 | 0 | -403000 | 0 |  | CO
06CO | 06 | T6368 | 43003315201 | 2014-07-30 | QTR1 | 14/15 | 1 | 1 | 170 | 172 | 137 | 35 | 0 | 0 | 2 | 0 | 619197 | 29000 | 590197 | 643584 | 598711 | 0 | 0 | 0 | 598711 | 598703 | -8 | 24387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24387 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2015-07-10 | QTR1 | 15/16 | 2015-06-04 | QTR4 | 14/15 | 606 | 631340 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6G56 | 42611915201 | 2013-01-31 | QTR3 | 12/13 | 1 | 0 | 560 | 775 | 774 | 1 | 0 | 0 | 215 | 0 | 4988310 | 58000 | 4930310 | 4988310 | 4865434 | 0 | 0 | 0 | 4865434 | 4865434 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2015-08-03 | QTR1 | 15/16 | 2015-07-02 | QTR1 | 15/16 | 606 | 5875815.5 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6H61 | 43119215201 | 2014-06-12 | QTR4 | 13/14 | 1 | 0 | 280 | 317 | 317 | 0 | 0 | 0 | 37 | 0 | 838500 | 40300 | 798200 | 838500 | 763060 | 0 | 0 | 0 | 763060 | 763060 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 | 2015-08-11 | QTR1 | 15/16 | 606 | 850347 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I14 | 43209815201 | 2014-02-27 | QTR3 | 13/14 | 1 | 0 | 120 | 234 | 198 | 36 | 0 | 0 | 114 | 0 | 328706 | 17632 | 311074 | 328706 | 320865 | 0 | 0 | 0 | 320865 | 320865 | 0 | 0 | 76 | 24 | 0 | 9791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 9791 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 | 2015-06-25 | QTR4 | 14/15 | 606 | 370268.95 | B0 | ACC - LUMP SUM | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I57 | 43119015201 | 2014-09-25 | QTR1 | 14/15 | 1 | 0 | 120 | 138 | 138 | 0 | 0 | 0 | 18 | 0 | 619046 | 39934 | 579112 | 619046 | 562195 | 0 | 0 | 0 | 562195 | 562195 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-09-23 | QTR1 | 15/16 | 2015-07-03 | QTR1 | 15/16 | 606 | 838614 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I77 | 24994175201 | 2014-08-28 | QTR1 | 14/15 | 1 | 0 | 160 | 194 | 194 | 0 | 0 | 0 | 34 | 0 | 1198756 | 50000 | 1148756 | 1198756 | 1094981 | 0 | 0 | 0 | 1094981 | 1094981 | 0 | 0 | 31 | 0 | 0 | 1200 | 0 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11878 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-07-17 | QTR1 | 15/16 | 606 | 1268938.13 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I78 | 43081615201 | 2014-07-31 | QTR1 | 14/15 | 2 | 0 | 140 | 173 | 173 | 0 | 0 | 0 | 25 | 8 | 1207213 | 51325 | 1155888 | 1207213 | 1139099 | 0 | 0 | 0 | 1139099 | 1129248 | -9851 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 3 | 5483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6468 | 0 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 | 2015-04-24 | QTR4 | 14/15 | 606 | 1208779.95 |  |  | 8 | 13 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I83 | 43081415201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 65 | 96 | 93 | 3 | 0 | 0 | 31 | 0 | 94720 | 6040 | 88680 | 94720 | 88652 | 0 | 0 | 0 | 88652 | 88652 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-07-14 | QTR1 | 15/16 | 606 | 126847 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I85 | 41774079201 | 2014-03-27 | QTR3 | 13/14 | 1 | 0 | 300 | 346 | 346 | 0 | 0 | 0 | 46 | 0 | 502650 | 32313 | 470337 | 502650 | 470337 | 0 | 0 | 0 | 470337 | 0 | -470337 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-05-13 | QTR4 | 14/15 | 606 | 678578.25 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I87 | 42934415201 | 2014-10-30 | QTR2 | 14/15 | 3 | 0 | 170 | 192 | 190 | 2 | 0 | 0 | 22 | 0 | 1872759 | 101085 | 1771674 | 1872759 | 1693855 | 0 | 0 | 0 | 1693855 | 1636257 | -57598 | 0 | 20 | 0 | 0 | 1943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-09-17 | QTR1 | 15/16 | 2015-07-29 | QTR1 | 15/16 | 606 | 1934017.45 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J40 | 43590015201 | 2015-01-29 | QTR3 | 14/15 | 1 | 0 | 80 | 83 | 75 | 8 | 0 | 0 | 3 | 0 | 248698 | 11846 | 236852 | 248698 | 217030 | 0 | 0 | 0 | 217030 | 217030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-09-25 | QTR1 | 15/16 | 2015-09-11 | QTR1 | 15/16 | 606 | 248762.6 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7325 | 42900515201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 350 | 453 | 453 | 0 | 0 | 0 | 83 | 20 | 15491284 | 120000 | 15371284 | 16150823 | 16100076 | 0 | 0 | 0 | 16100076 | 16143898 | 43822 | 659540 | 60 | 0 | 1 | 10092 | 0 | 0 | 19 | 662533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 683477 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-08-21 | QTR1 | 15/16 | 2014-11-21 | QTR2 | 14/15 | 709 | 16955600 |  |  | 1 | 23 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7329 | 42907325201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 270 | 369 | 369 | 0 | 0 | 0 | 99 | 0 | 5019226 | 50000 | 4969226 | 5019226 | 4985077 | 0 | 0 | 0 | 4985077 | 4951447 | -33631 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 18054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18054 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-07-23 | QTR1 | 15/16 | 2015-04-01 | QTR4 | 14/15 | 717 | 4751500 | B0 | ACC - LUMP SUM | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7340 | 42715415201 | 2014-04-30 | QTR4 | 13/14 | 2 | 0 | 150 | 188 | 187 | 1 | 0 | 0 | 38 | 0 | 1688000 | 50000 | 1638000 | 1688000 | 1644638 | 0 | 0 | 0 | 1644638 | 1606582 | -38056 | 0 | 25 | 0 | 0 | 9287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9287 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 | 2015-03-27 | QTR3 | 14/15 | 798 | 2156800 | B0 | ACC - LUMP SUM | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7341 | 42896115201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 320 | 383 | 381 | 2 | 0 | 0 | 63 | 0 | 5790872 | 55000 | 5735872 | 5790872 | 5714657 | 0 | 0 | 0 | 5714657 | 5660340 | -54316 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-09-15 | QTR1 | 15/16 | 2015-06-17 | QTR4 | 14/15 | 717 | 6079410 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7J96 | 43066115201 | 2014-11-26 | QTR2 | 14/15 | 1 | 0 | 150 | 183 | 183 | 0 | 0 | 0 | 33 | 0 | 2030000 | 50000 | 1980000 | 2030000 | 1980915 | 0 | 0 | 0 | 1980915 | 1934577 | -46338 | 0 | 26 | 0 | 0 | 1006 | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9760 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-29 | QTR1 | 15/16 | 2015-08-19 | QTR1 | 15/16 | 709 | 1984600 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8L99 | 41546225202 | 2012-05-22 | QTR4 | 11/12 | 1 | 9 | 785 | 901 | 901 | 0 | 0 | 0 | 88 | 28 | 19914762 | 150000 | 19764762 | 20008584 | 19972782 | -154000 | 0 | -154000 | 19818782 | 19745451 | -73332 | 93822 | 25 | 0 | 0 | 66402 | 0 | 0 | 0 | 119752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 35659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 90883 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-09-28 | QTR1 | 15/16 | 2015-02-13 | QTR3 | 14/15 | 854 | 20630726.61 |  |  | 0 | 63 | 0 | 0 | -130930 | 0 |  | DO
08DO | 08 | E8M77 | 40615145201 | 2013-03-26 | QTR3 | 12/13 | 2 | 4 | 645 | 777 | 730 | 47 | 0 | 0 | 48 | 84 | 11249740 | 150000 | 11099740 | 11481897 | 10973748 | 0 | 0 | 0 | 10973748 | 10925662 | -48086 | 232157 | 25 | 0 | 84 | 150630 | 103254 | 0 | 0 | 162171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 312801 | 103254 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-09-04 | QTR1 | 15/16 | 2015-07-07 | QTR1 | 15/16 | 854 | 11244846.35 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M80 | 42768515201 | 2013-05-14 | QTR4 | 12/13 | 1 | 2 | 425 | 469 | 425 | 44 | 0 | 0 | 44 | 0 | 6746576 | 63950 | 6682626 | 6938552 | 6915696 | 0 | 0 | 0 | 6915696 | 6919857 | 4160 | 191976 | 15 | 0 | 0 | 66193 | 0 | 0 | 0 | 5863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249853 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-09-14 | QTR1 | 15/16 | 2014-10-06 | QTR2 | 14/15 | 854 | 6459217.72 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M93 | 43108935201 | 2013-05-21 | QTR4 | 12/13 | 1 | 2 | 450 | 587 | 587 | 0 | 0 | 0 | 137 | 0 | 7676614 | 84515 | 7592099 | 7714483 | 7540572 | 0 | 0 | 0 | 7540572 | 7491522 | -49050 | 37868 | 85 | 0 | 0 | 122140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122140 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-07-07 | QTR1 | 15/16 | 2015-05-15 | QTR4 | 14/15 | 854 | 8536508.95 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N21 | 42902315201 | 2014-03-11 | QTR3 | 13/14 | 2 | 5 | 170 | 271 | 271 | 0 | 0 | 0 | 94 | 7 | 6573418 | 84736 | 6488682 | 6704790 | 6985687 | -3000 | 0 | -3000 | 6982687 | 6966867 | -15820 | 131372 | 62 | 0 | 0 | 14408 | 0 | 0 | 7 | 173176 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68650 | 0 | 0 | 0 | 8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 67841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 197374 | 5845 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-14 | QTR1 | 15/16 | 2015-02-09 | QTR3 | 14/15 | 854 | 8559769.2 |  |  | 7 | 32 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0