## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 85548236 | 84569199 | 88981839 | 88209727 | 120000 | 86817339 | 2.658% | 88.24% | 3858965 | 4.563% | 3433603 | 4.014% | 5083 | 809 | 15.92% | 209 | 4.112% | 64 | 1.259% | 189 | 3.718% | 5336 | 4.977% | 6359 | 6441 | 5423 | 6.689% | 82.35%
| District Let | 85770956 | 85163778 | 89166703 | 88716827 | 80000 | 88171816 | 3.532% | 82.35% | 3563600 | 4.184% | 3395746 | 3.959% | 3311 | 326 | 9.846% | 156 | 4.712% | 23 | 0.6947% | 451 | 13.62% | 3785 | 14.32% | 4271 | 4052 | 3570 | 7.822% | 94.12%
| All Contracts | 171319192 | 169732977 | 178148542 | 176926554 | 200000 | 174989155 | 3.097% | 85.29% | 7422565 | 4.373% | 6829349 | 3.986% | 8394 | 1135 | 13.52% | 365 | 4.348% | 87 | 1.036% | 640 | 7.624% | 9121 | 8.661% | 10630 | 10493 | 8993 | 7.136% | 88.24%
2 | Central Let | 67817660 | 66924562 | 68376367 | 69396362 | 0 | 66913551 | -0.01645% | 94.74% | 767247 | 1.146% | 558706 | 0.8238% | 3135 | 826 | 26.35% | 294 | 9.378% | 207 | 6.603% | 229 | 7.305% | 3571 | 13.91% | 4697 | 4666 | 3546 | 13.11% | 73.68%
| District Let | 29485881 | 29029635 | 29520999 | 28733724 | 0 | 28052248 | -3.367% | 90% | 219883 | 0.7574% | 35119 | 0.1191% | 2544 | 228 | 8.962% | 167 | 6.564% | 76 | 2.987% | 109 | 4.285% | 2729 | 7.272% | 3124 | 3460 | 3065 | 20.48% | 70%
| All Contracts | 97303541 | 95954197 | 97897366 | 98130086 | 0 | 94965799 | -1.03% | 93.1% | 987130 | 1.029% | 593825 | 0.6103% | 5679 | 1054 | 18.56% | 461 | 8.118% | 283 | 4.983% | 338 | 5.952% | 6300 | 10.94% | 7821 | 8126 | 6611 | 16.41% | 72.41%
3 | Central Let | 58428614 | 57695476 | 59147291 | 61499877 | 0 | 60642597 | 5.108% | 85% | 880723 | 1.527% | 718678 | 1.23% | 4794 | 1141 | 23.8% | 384 | 8.01% | 75 | 1.564% | 480 | 10.01% | 5349 | 11.58% | 6874 | 6904 | 5379 | 12.2% | 95%
| District Let | 13616152 | 13258552 | 13785523 | 13440699 | 0 | 12875816 | -2.887% | 88.89% | 211298 | 1.594% | 169371 | 1.244% | 968 | 172 | 17.77% | 54 | 5.579% | 0 | 0% | 71 | 7.335% | 1039 | 7.335% | 1265 | 1259 | 1033 | 6.715% | 88.89%
| All Contracts | 72044766 | 70954028 | 72932814 | 74940576 | 0 | 73518413 | 3.614% | 86.21% | 1092021 | 1.539% | 888049 | 1.233% | 5762 | 1313 | 22.79% | 438 | 7.602% | 75 | 1.302% | 551 | 9.563% | 6388 | 10.86% | 8139 | 8163 | 6412 | 11.28% | 93.1%
4 | Central Let | 44802764 | 44424187 | 50539401 | 50916161 | 0 | 51071611 | 14.96% | 75% | 5872691 | 13.22% | 5736637 | 12.8% | 2033 | 298 | 14.66% | 116 | 5.706% | 14 | 0.6886% | 579 | 28.48% | 2626 | 29.17% | 3040 | 3087 | 2673 | 31.48% | 62.5%
| District Let | 64442426 | 63989980 | 64942883 | 64334572 | 0 | 64023754 | 0.05278% | 88.89% | 672664 | 1.051% | 500458 | 0.7766% | 2582 | 473 | 18.32% | 135 | 5.229% | 81 | 3.137% | 153 | 5.926% | 2816 | 9.063% | 3430 | 3382 | 2774 | 7.436% | 100%
| All Contracts | 109245190 | 108414167 | 115482284 | 115250733 | 0 | 115095365 | 6.163% | 82.35% | 6545355 | 6.037% | 6237095 | 5.709% | 4615 | 771 | 16.71% | 251 | 5.439% | 95 | 2.059% | 732 | 15.86% | 5442 | 17.92% | 6470 | 6469 | 5447 | 18.03% | 82.35%
5 | Central Let | 102197606 | 101118606 | 104437169 | 103704447 | 0 | 102626787 | 1.491% | 100% | 2786003 | 2.755% | 2239563 | 2.191% | 5128 | 675 | 13.16% | 301 | 5.87% | 0 | 0% | 523 | 10.2% | 5651 | 10.2% | 6658 | 6861 | 5885 | 14.76% | 87.5%
| District Let | 245409334 | 244493334 | 279760560 | 278733414 | 2601667 | 248787822 | 1.756% | 100% | 34316812 | 14.04% | 34351225 | 14% | 3561 | 380 | 10.67% | 157 | 4.409% | 0 | 0% | 757 | 21.26% | 4318 | 21.26% | 4864 | 4797 | 4260 | 19.63% | 77.78%
| All Contracts | 347606940 | 345611940 | 384197729 | 382437861 | 2601667 | 351414609 | 1.679% | 100% | 37102815 | 10.74% | 36590788 | 10.53% | 8689 | 1055 | 12.14% | 458 | 5.271% | 0 | 0% | 1280 | 14.73% | 9969 | 14.73% | 11522 | 11658 | 10145 | 16.76% | 84%
6 | Central Let | 45914529 | 45130528 | 46822859 | 47885708 | 0 | 47536436 | 5.331% | 84.62% | 1250222 | 2.77% | 908330 | 1.978% | 3260 | 930 | 28.53% | 224 | 6.871% | 139 | 4.264% | 273 | 8.374% | 3672 | 12.64% | 4826 | 4820 | 3666 | 12.45% | 84.62%
| District Let | 22117289 | 21493376 | 23269744 | 22304614 | 0 | 21639497 | 0.6798% | 93.33% | 1229109 | 5.719% | 1152455 | 5.211% | 2890 | 439 | 15.19% | 161 | 5.571% | 224 | 7.751% | 8 | 0.2768% | 3122 | 8.028% | 3722 | 3615 | 3015 | 4.325% | 93.33%
| All Contracts | 68031818 | 66623904 | 70092603 | 70190322 | 0 | 69175933 | 3.831% | 89.29% | 2479331 | 3.721% | 2060785 | 3.029% | 6150 | 1369 | 22.26% | 385 | 6.26% | 363 | 5.902% | 281 | 4.569% | 6794 | 10.47% | 8548 | 8435 | 6681 | 8.634% | 89.29%
7 | Central Let | 63099805 | 62410305 | 64150657 | 63796641 | 0 | 63512488 | 1.766% | 100% | 1286416 | 2.061% | 1050853 | 1.665% | 2805 | 497 | 17.72% | 179 | 6.381% | 2 | 0.0713% | 117 | 4.171% | 2924 | 4.242% | 3600 | 3558 | 2882 | 2.745% | 100%
| District Let | 10776825 | 10510825 | 10776825 | 10535358 | 0 | 10326396 | -1.755% | 100% | 58356 | 0.5552% | 0 | 0% | 935 | 117 | 12.51% | 97 | 10.37% | 47 | 5.027% | -29 | -3.102% | 953 | 1.925% | 1167 | 1151 | 937 | 0.2139% | 100%
| All Contracts | 73876630 | 72921130 | 74927482 | 74331999 | 0 | 73838884 | 1.259% | 100% | 1344772 | 1.844% | 1050853 | 1.422% | 3740 | 614 | 16.42% | 276 | 7.38% | 49 | 1.31% | 88 | 2.353% | 3877 | 3.663% | 4767 | 4709 | 3819 | 2.112% | 100%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 93211398 | 92503257 | 94115927 | 93527888 | 0 | 92959210 | 0.4929% | 100% | 1302128 | 1.408% | 904528 | 0.9704% | 3397 | 263 | 7.742% | 241 | 7.094% | 0 | 0% | 155 | 4.563% | 3552 | 4.563% | 4056 | 3962 | 3458 | 1.796% | 0.002343%
| All Contracts | 93211398 | 92503257 | 94115927 | 93527888 | 0 | 92959210 | 0.4929% | 100% | 1302128 | 1.408% | 904528 | 0.9704% | 3397 | 263 | 7.742% | 241 | 7.094% | 0 | 0% | 155 | 4.563% | 3552 | 4.563% | 4056 | 3962 | 3458 | 1.796% | 100%
Totals This Qtr | Central Let | 467809214 | 462272863 | 482455583 | 485408923 | 120000 | 479120809 | 3.645% | 90.29% | 16702267 | 3.613% | 14646370 | 3.131% | 26238 | 5176 | 19.73% | 1707 | 6.506% | 501 | 1.909% | 2390 | 9.109% | 29129 | 11.02% | 36054 | 36337 | 29454 | 12.26% | 84.47%
| District Let | 564830261 | 560442737 | 605339164 | 600327096 | 2681667 | 566836559 | 1.141% | 91.46% | 41573850 | 7.418% | 40508902 | 7.172% | 20188 | 2398 | 11.88% | 1168 | 5.786% | 451 | 2.234% | 1675 | 8.297% | 22314 | 10.53% | 25899 | 25678 | 22112 | 9.53% | 90.24%
| All Contracts | 1032639475 | 1022715600 | 1087794747 | 1085736019 | 2801667 | 1045957368 | 2.273% | 90.81% | 58276117 | 5.698% | 55155272 | 5.341% | 46426 | 7574 | 16.31% | 2875 | 6.193% | 952 | 2.051% | 4065 | 8.756% | 51443 | 10.81% | 61953 | 62015 | 51566 | 11.07% | 87.03%
Totals Previous Quarter | Central Let | 270529610 | 267219607 | 279576384 | 279554852 | 0 | 276799110 | 3.585% | 92.54% | 10109474 | 3.783% | 9046774 | 3.344% | 15848 | 3237 | 20.43% | 1048 | 6.613% | 293 | 1.849% | 1293 | 8.159% | 17434 | 10.01% | 21759 | 22077 | 17792 | 12.27% | 86.57%
| District Let | 271484393 | 268889073 | 273658312 | 271145841 | 0 | 265865243 | -1.125% | 95.65% | 3047298 | 1.133% | 2173918 | 0.8008% | 12931 | 1650 | 12.76% | 806 | 6.233% | 211 | 1.632% | 752 | 5.815% | 13894 | 7.447% | 16356 | 16064 | 13608 | 5.235% | 95.65%
| All Contracts | 542014003 | 536108680 | 553234696 | 550700693 | 0 | 542664353 | 1.223% | 93.81% | 13156772 | 2.454% | 11220692 | 2.07% | 28779 | 4887 | 16.98% | 1854 | 6.442% | 504 | 1.751% | 2045 | 7.106% | 31328 | 8.857% | 38115 | 38141 | 31400 | 9.107% | 90.27%
Totals Fiscal Year 2014/2015 | Central Let | 714324826 | 704915784 | 739803035 | 736872789 | 0 | 738662792 | 4.787% | 86.21% | 28465957 | 4.038% | 25479404 | 3.567% | 45283 | 6760 | 14.93% | 2500 | 5.521% | 1129 | 2.493% | 1864 | 4.116% | 48276 | 6.61% | 57604 | 57388 | 48128 | 6.283% | 90.15%
| District Let | 540522559 | 532821843 | 558558681 | 552167020 | 905160 | 551105572 | 3.431% | 92.31% | 20538700 | 3.855% | 18264346 | 3.379% | 39622 | 4420 | 11.16% | 2013 | 5.081% | 692 | 1.747% | 3075 | 7.761% | 43389 | 9.507% | 49860 | 48493 | 42060 | 6.153% | 89.56%
| All Contracts | 1254847385 | 1237737627 | 1298361716 | 1289039809 | 905160 | 1289768364 | 4.204% | 89.09% | 49004657 | 3.959% | 43743750 | 3.486% | 84905 | 11180 | 13.17% | 4513 | 5.315% | 1821 | 2.145% | 4939 | 5.817% | 91665 | 7.962% | 107464 | 105881 | 90188 | 6.222% | 89.87%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1497 | 43003715201 | 2012-03-28 | QTR3 | 11/12 | 1 | 1 | 60 | 99 | 261 | 376.7% | 0 | -162 | 162 | 0 | 39 | 0 | 90611 | 0 | 90611 | 89035 | 88897 | -43964 | 0 | -43964 | 44933 | 44933 | 49.59% | 1 | 0 | -1576 | 17 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | -1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | -1576 | 0 | F593490202 | ALDON BOOKHARDT ROOFING INC. | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 |  | 2013-05-30 | QTR4 | 12/13 | 113 | 111867.75 | B0 | ACC - LUMP SUM
| 01 | T1501 | 40828635201 | 2012-06-20 | QTR4 | 11/12 | 1 | 7 | 700 | 779 | 779 | 101.3% | 1 | 0 | 0 | 0 | 75 | 4 | 14784300 | 133862 | 14650438 | 15330267 | 14964740 | 0 | 0 | 0 | 14964740 | 15047703 | 102.7% | 1 | 82963 | 545967 | 48 | 22 | 0 | 4 | 334024 | 0 | 0 | 0 | 328205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 635924 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-09-10 | QTR1 | 15/16 |  | 2014-10-22 | QTR2 | 14/15 | 113 | 13767013.79
| 01 | T1512 | 40826835201 | 2012-09-26 | QTR1 | 12/13 | 3 | 19 | 650 | 871 | 865 | 107.8% | 1 | 6 | 0 | 0 | 164 | 57 | 19473948 | 150000 | 19323948 | 20142554 | 20429764 | 0 | 0 | 0 | 20429764 | 20268347 | 104.9% | 1 | -161418 | 668606 | 138 | 26 | 0 | 0 | 335638 | 10644 | 0 | 57 | 446552 | 194978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 797698 | 205622 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-10-19 | QTR2 | 15/16 |  | 2015-07-30 | QTR1 | 15/16 | 108 | 19967593.35
| 01 | T1527 | 41787615201 | 2013-02-06 | QTR3 | 12/13 | 2 | 9 | 768 | 835 | 810 | 96.74% | 1 | 25 | 0 | 0 | 67 | 0 | 12312349 | 150000 | 12162349 | 13258294 | 12897465 | 0 | 0 | 0 | 12897465 | 12514104 | 102.9% | 1 | -383360 | 945945 | 41 | 26 | 0 | 0 | 262529 | 0 | 0 | 0 | 689450 | 18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 951980 | 18277 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-10 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 115 | 15340403.45
| 01 | T1541 | 42525115201 | 2013-06-19 | QTR4 | 12/13 | 2 | 4 | 600 | 681 | 680 | 100.5% | 1 | 1 | 0 | 0 | 77 | 4 | 7929564 | 70779 | 7858785 | 8206423 | 8142299 | 0 | 0 | 0 | 8142299 | 8010531 | 101.9% | 1 | -131769 | 276859 | 58 | 19 | 0 | 0 | 248527 | 9547 | 0 | 4 | 79218 | 11206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 327744 | 20752 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-11-19 | QTR2 | 15/16 |  | 2015-09-24 | QTR1 | 15/16 | 108 | 7502697.01
| 01 | T1546 | 42910415201 | 2014-02-26 | QTR3 | 13/14 | 1 | 2 | 130 | 190 | 219 | 149.2% | 0 | -29 | 29 | 0 | 36 | 24 | 2195109 | 50000 | 2145109 | 2159801 | 2156391 | -50518 | 0 | -50518 | 2105873 | 2085969 | 97.24% | 1 | -19904 | -35308 | 11 | 14 | 0 | 10 | -17725 | 0 | 11 | 14 | 8387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 24 | -9339 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2015-09-13 | QTR1 | 15/16 |  | 2015-04-14 | QTR4 | 14/15 | 115 | 2641240.24 | B0 | ACC - LUMP SUM
| 01 | T1557 | 42928415201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 175 | 202 | 201 | 101.1% | 1 | 1 | 0 | 0 | 27 | 0 | 2509778 | 50000 | 2459778 | 2509778 | 2520762 | 0 | 0 | 0 | 2520762 | 2358044 | 95.86% | 1 | -162718 | 0 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 |  | 2015-08-07 | QTR1 | 15/16 | 108 | 2840170.1 | B0 | ACC - LUMP SUM
| 01 | T1566 | 20010575201 | 2014-04-30 | QTR4 | 13/14 | 1 | 4 | 300 | 324 | 281 | 85.67% | 1 | 43 | 0 | 0 | 24 | 0 | 855140 | 0 | 855140 | 880470 | 883951 | 0 | 0 | 0 | 883951 | 883951 | 103.4% | 1 | 0 | 25330 | 14 | 10 | 0 | 0 | 17931 | 1430 | 0 | 0 | 7399 | 7399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25330 | 8829 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 |  | 2015-08-06 | QTR1 | 15/16 | 118 | 1061209.63
| 01 | T1570 | 42584615201 | 2014-03-26 | QTR3 | 13/14 | 3 | 4 | 250 | 305 | 305 | 112% | 1 | 0 | 0 | 0 | 55 | 0 | 2796051 | 50000 | 2746051 | 3242177 | 3374573 | 0 | 120000 | 120000 | 3494573 | 3324455 | 121.1% | 0 | -170118 | 446126 | 14 | 11 | 0 | 0 | 36506 | 0 | 30 | 0 | 458800 | 45280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 495306 | 45280 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 |  | 2015-07-19 | QTR1 | 15/16 | 118 | 2726352.03 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1578 | 43086015201 | 2013-12-04 | QTR2 | 13/14 | 2 | 9 | 270 | 410 | 407 | 98.89% | 1 | 3 | 0 | 0 | 140 | 0 | 5634855 | 53649 | 5581206 | 5727333 | 5707127 | 0 | 0 | 0 | 5707127 | 5640992 | 101.1% | 1 | -66135 | 92478 | 121 | 19 | 0 | 0 | 20908 | 2691 | 0 | 0 | 36741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80103 | 2691 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-07-06 | QTR1 | 15/16 |  | 2015-05-04 | QTR4 | 14/15 | 108 | 5433904.15 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1591 | 43130115201 | 2014-04-30 | QTR4 | 13/14 | 1 | 2 | 270 | 452 | 447 | 100% | 1 | 5 | 0 | 0 | 177 | 5 | 7824413 | 94834 | 7729579 | 8062184 | 7860334 | 0 | 0 | 0 | 7860334 | 7721971 | 99.9% | 1 | -138364 | 237771 | 159 | 18 | 0 | 5 | 259901 | 0 | 0 | 0 | 26087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 285988 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-11-16 | QTR2 | 15/16 |  | 2015-09-28 | QTR1 | 15/16 | 108 | 8889524.26
| 01 | T1592 | 42729815201 | 2014-05-21 | QTR4 | 13/14 | 5 | 1 | 275 | 313 | 312 | 99.64% | 1 | 1 | 0 | 0 | 38 | 0 | 1644078 | 50000 | 1594078 | 1668510 | 1623620 | 0 | 0 | 0 | 1623620 | 1623620 | 101.9% | 1 | 0 | 24432 | 32 | 6 | 0 | 0 | 2784 | 0 | 0 | 0 | 27758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30542 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-12-09 | QTR2 | 15/16 |  | 2015-11-12 | QTR2 | 15/16 | 115 | 1618341.71 | B0:B0:B0:B:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1594 | 43135415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 5 | 130 | 258 | 258 | 164.6% | 0 | 0 | 0 | 0 | 44 | 84 | 989000 | 0 | 989000 | 1119395 | 1113069 | 0 | 0 | 0 | 1113069 | 1113069 | 112.5% | 0 | 0 | 130395 | 39 | 5 | 0 | 13 | 19459 | 0 | 0 | 4 | 6266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 104670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 130395 | 0 | F464740152 | CATHCART CONSTRUCTION COMPANY - FLORIDA | N/A | N/A | N/A | N/A | 2015-12-10 | QTR2 | 15/16 |  | 2015-09-19 | QTR1 | 15/16 | 108 | 857499.8 | B0 | ACC - LUMP SUM
| 01 | T1996 | 43086115201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 90 | 133 | 133 | 120% | 1 | 0 | 0 | 0 | 41 | 2 | 336490 | 14047 | 322443 | 336490 | 331697 | 0 | 0 | 0 | 331697 | 331697 | 102.9% | 1 | 0 | 0 | 21 | 4 | 0 | 0 | 7107 | 0 | 16 | 2 | 2148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 9255 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 |  | 2015-09-21 | QTR1 | 15/16 | 115 | 347757.16 | B0 | ACC - LUMP SUM
| 01 | T1A05 | 42910815201 | 2014-10-29 | QTR2 | 14/15 | 1 | 2 | 160 | 182 | 158 | 85% | 1 | 24 | 0 | 0 | 22 | 0 | 2154862 | 50000 | 2104862 | 2208421 | 2164641 | 0 | 0 | 0 | 2164641 | 2077091 | 98.68% | 1 | -87549 | 53559 | 20 | 2 | 0 | 0 | 18835 | 0 | 0 | 0 | 14169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51972 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-12-10 | QTR2 | 15/16 |  | 2015-08-27 | QTR1 | 15/16 | 108 | 2061296.31 | B0 | ACC - LUMP SUM
| 01 | T1A12 | 43121015201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 145 | 194 | 194 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 3770622 | 50000 | 3720622 | 3770622 | 3700017 | 0 | 0 | 0 | 3700017 | 3520482 | 94.62% | 1 | -179536 | 0 | 44 | 5 | 0 | 0 | 24624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24624 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-12-14 | QTR2 | 15/16 |  | 2015-10-16 | QTR2 | 15/16 | 113 | 3557076.77
| 01 | T1A14 | 43341115201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 110 | 131 | 131 | 108.2% | 1 | 0 | 0 | 0 | 12 | 9 | 247066 | 11866 | 235200 | 270085 | 250380 | 0 | 0 | 0 | 250380 | 250380 | 106.5% | 1 | 0 | 23019 | 10 | 2 | 0 | 9 | 23019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 23019 | 0 | F593339407 | TAGARELLI CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-08-11 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 108 | 256990.36 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 17 | 28 | 70 | 5083 | 6359 | 6441 | 82.35% | 14 | -82 | 191 | 0 | 1087 | 189 | 85548236 | 979037 | 84569199 | 88981839 | 88209727 | -94482 | 120000 | 25518 | 88235245 | 86817339 | 88.24% | 15 | -1417908 | 3433603 | 809 | 209 | 4 | 41 | 1594067 | 24312 | 57 | 81 | 2129604 | 277140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 67 | 135295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 189 | 3858965 | 301451
| 01 | E1J69 | 20074625201 | 2012-06-29 | QTR4 | 11/12 | 1 | 6 | 550 | 629 | 629 | 110% | 1 | 0 | 0 | 0 | 37 | 42 | 8819248 | 50000 | 8769248 | 9865997 | 9845954 | 0 | 0 | 0 | 9845954 | 9861107 | 112.5% | 0 | 15153 | 1046749 | 0 | 24 | 9 | 42 | 835826 | 0 | 0 | 0 | 56914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 0 | 0 | 0 | 200041 | 200041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6891 | 0 | 9 | 42 | 1096506 | 200041 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-11-13 | QTR2 | 15/16 |  | 2014-08-25 | QTR1 | 14/15 | 113 | 9894002 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1J71 | 41263625201 | 2012-05-31 | QTR4 | 11/12 | 2 | 14 | 565 | 936 | 936 | 153.5% | 0 | 0 | 0 | 0 | 69 | 302 | 6703703 | 50000 | 6653703 | 7531485 | 7530256 | 0 | 0 | 0 | 7530256 | 7530256 | 113.2% | 0 | 0 | 827782 | 22 | 47 | 0 | 121 | 99861 | 9614 | 0 | 95 | 314019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 401293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 815173 | 9614 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 |  | 2015-06-08 | QTR4 | 14/15 | 113 | 638850 | A3 | ICC - DESIGN/BUILD - MINOR
| 01 | E1J72 | 41664925201 | 2012-05-17 | QTR4 | 11/12 | 1 | 5 | 795 | 1092 | 1092 | 112.7% | 1 | 0 | 0 | 0 | 196 | 101 | 54100000 | 150000 | 53950000 | 55514659 | 55350517 | 0 | 0 | 0 | 55350517 | 55125629 | 102.2% | 1 | -224888 | 1414659 | 165 | 31 | 0 | 101 | 1373941 | 0 | 0 | 0 | 96582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1492682 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-12-09 | QTR2 | 15/16 |  | 2015-07-23 | QTR1 | 15/16 | 106 | 72523865 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1N08 | 42347115201 | 2014-06-19 | QTR4 | 13/14 | 1 | 4 | 200 | 242 | 242 | 106.5% | 1 | 0 | 0 | 0 | 36 | 6 | 1880948 | 50000 | 1830948 | 1908269 | 1858269 | 0 | 0 | 0 | 1858269 | 1834616 | 100.2% | 1 | -23653 | 27320 | 16 | 13 | 0 | 0 | 0 | 0 | 7 | 5 | 22343 | 8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 27320 | 8999 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-07-31 | QTR1 | 15/16 |  | 2015-06-22 | QTR4 | 14/15 | 108 | 1405116.38 | B0 | ACC - LUMP SUM
| 01 | E1N35 | 43496715201 | 2014-06-19 | QTR4 | 13/14 | 1 | 1 | 60 | 67 | 61 | 90% | 1 | 6 | 0 | 0 | 7 | 0 | 93903 | 3487 | 90416 | 106903 | 100206 | 0 | 0 | 0 | 100206 | 100206 | 110.8% | 0 | 0 | 13000 | 3 | 4 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2015-11-19 | QTR2 | 15/16 |  | 2014-12-12 | QTR2 | 14/15 | 118 | 71243.52
| 01 | E1N47 | 43019125201 | 2014-06-19 | QTR4 | 13/14 | 2 | 1 | 175 | 213 | 204 | 94.86% | 1 | 9 | 0 | 0 | 38 | 0 | 4346396 | 50000 | 4296396 | 4413679 | 4400332 | 0 | 0 | 0 | 4400332 | 4322422 | 100.6% | 1 | -77910 | 67283 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 67283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67283 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2015-08-13 | QTR1 | 15/16 |  | 2015-04-13 | QTR4 | 14/15 | 118 | 4460046.21 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | E1N64 | 43160515201 | 2014-08-29 | QTR1 | 14/15 | 1 | 0 | 150 | 176 | 175 | 99.33% | 1 | 1 | 0 | 0 | 26 | 0 | 3021172 | 50000 | 2971172 | 3021172 | 3068023 | 0 | 0 | 0 | 3068023 | 2921086 | 98.31% | 1 | -146936 | 0 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-25 | QTR1 | 15/16 |  | 2015-06-12 | QTR4 | 14/15 | 118 | 3419370.6
| 01 | E1N65 | 42909615201 | 2014-10-16 | QTR2 | 14/15 | 1 | 0 | 130 | 153 | 150 | 97.69% | 1 | 3 | 0 | 0 | 23 | 0 | 1285754 | 50000 | 1235754 | 1285754 | 1252542 | 0 | 0 | 0 | 1252542 | 1182541 | 95.69% | 1 | -70001 | 0 | 21 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2015-11-02 | QTR2 | 15/16 |  | 2015-09-24 | QTR1 | 15/16 | 115 | 1296120.13 | B0 | ACC - LUMP SUM
| 01 | E1N66 | 41787625201 | 2015-06-18 | QTR4 | 14/15 | 1 | 0 | 65 | 67 | 23 | 32.31% | 1 | 44 | 0 | 0 | 2 | 0 | 135934 | 8934 | 127000 | 135934 | 127000 | 0 | 0 | 0 | 127000 | 127000 | 100% | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650968383 | WHITELEAF LLC DBA TRAFFIC SOLUTIONS | N/A | N/A | N/A | N/A | 2015-11-03 | QTR2 | 15/16 |  | 2015-10-13 | QTR2 | 15/16 | 115 | 208343.37 | B0 | ACC - LUMP SUM
| 01 | E1N67 | 43121315201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 70 | 91 | 91 | 110% | 1 | 0 | 0 | 0 | 21 | 0 | 660116 | 29692 | 630424 | 660116 | 658410 | 0 | 0 | 0 | 658410 | 658410 | 104.4% | 1 | 0 | 0 | 12 | 2 | 0 | 0 | 27986 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 27986 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-11-19 | QTR2 | 15/16 |  | 2015-07-26 | QTR1 | 15/16 | 108 | 633762.78 | B0 | ACC - LUMP SUM
| 01 | E1N70 | 40826895201 | 2015-01-15 | QTR3 | 14/15 | 1 | 0 | 50 | 63 | 63 | 100% | 1 | 0 | 0 | 0 | 13 | 0 | 129260 | 9480 | 119780 | 129260 | 124484 | 0 | 0 | 0 | 124484 | 124484 | 103.9% | 1 | 0 | 0 | 13 | 0 | 0 | 0 | 4704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4704 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2015-12-11 | QTR2 | 15/16 |  | 2015-11-01 | QTR2 | 15/16 | 108 | 172354.33 | B0 | ACC - LUMP SUM
| 01 | E1N71 | 43006015201 | 2015-01-15 | QTR3 | 14/15 | 1 | 0 | 80 | 95 | 92 | 96.25% | 1 | 3 | 0 | 0 | 15 | 0 | 567387 | 27173 | 540214 | 567387 | 532744 | 0 | 0 | 0 | 532744 | 532744 | 98.62% | 1 | 0 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2015-09-23 | QTR1 | 15/16 |  | 2015-08-18 | QTR1 | 15/16 | 118 | 519186.9 | B0 | ACC - LUMP SUM
| 01 | E1N76 | 43510615201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 180 | 195 | 160 | 80.56% | 1 | 35 | 0 | 0 | 15 | 0 | 3493285 | 50000 | 3443285 | 3493285 | 3362358 | 0 | 80000 | 80000 | 3442358 | 3345583 | 97.16% | 1 | -96775 | 0 | 7 | 8 | 0 | 0 | 12658 | 0 | 0 | 0 | 5994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18652 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-11-25 | QTR2 | 15/16 |  | 2015-09-11 | QTR1 | 15/16 | 115 | 2641060.47 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1N96 | 42949925201 | 2014-10-16 | QTR2 | 14/15 | 1 | 1 | 90 | 91 | 51 | 55.56% | 1 | 40 | 0 | 0 | 1 | 0 | 229418 | 9702 | 219716 | 228371 | 218669 | 0 | 0 | 0 | 218669 | 218669 | 99.52% | 1 | 0 | -1047 | 0 | 1 | 0 | 0 | -1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1047 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-07-21 | QTR1 | 15/16 |  | 2015-06-09 | QTR4 | 14/15 | 115 | 179058.8 | B0 | ACC - LUMP SUM
| 01 | E1O06 | 43574215201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 50 | 50 | 16 | 32% | 1 | 34 | 0 | 0 | 0 | 0 | 140780 | 9482 | 131298 | 140780 | 132639 | 0 | 0 | 0 | 132639 | 132639 | 101% | 1 | 132639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 0 | F650968383 | WHITELEAF LLC DBA TRAFFIC SOLUTIONS | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 |  | 2015-03-02 | QTR3 | 14/15 | 113 | 193962.81 | B0 | ACC - LUMP SUM
| 01 | E1O17 | 43642215201 | 2015-05-21 | QTR4 | 14/15 | 1 | 0 | 41 | 51 | 48 | 92.68% | 1 | 3 | 0 | 0 | 10 | 0 | 122267 | 6051 | 116216 | 122267 | 116216 | 0 | 0 | 0 | 116216 | 116216 | 100% | 1 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2015-12-16 | QTR2 | 15/16 |  | 2015-11-23 | QTR2 | 15/16 | 108 | 128069.07 | B0 | ACC - LUMP SUM
| 01 | E1O84 | 43494415201 | 2015-07-16 | QTR1 | 15/16 | 1 | 0 | 60 | 60 | 19 | 31.67% | 1 | 41 | 0 | 0 | 0 | 0 | 41385 | 3177 | 38208 | 41385 | 38208 | 0 | 0 | 0 | 38208 | 38208 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2015-11-13 | QTR2 | 15/16 |  | 2015-10-13 | QTR2 | 15/16 | 113 | 66757.33 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 17 | 19 | 32 | 3311 | 4271 | 4052 | 94.12% | 16 | 219 | 0 | 0 | 509 | 451 | 85770956 | 607178 | 85163778 | 89166703 | 88716827 | 0 | 80000 | 80000 | 88796827 | 88171816 | 82.35% | 14 | -492371 | 3395746 | 326 | 156 | 9 | 264 | 2366929 | 9614 | 14 | 100 | 564476 | 8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 0 | 0 | 86 | 617865 | 200041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15403 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6891 | 0 | 23 | 451 | 3563600 | 218654
| District 01 Totals |  |  |  |  | 34 | 47 | 102 | 8394 | 10630 | 10493 | 88.24% | 30 | 137 | 191 | 0 | 1596 | 640 | 171319192 | 1586215 | 169732977 | 178148542 | 176926554 | -94482 | 200000 | 105518 | 177032072 | 174989155 | 85.29% | 29 | -1910279 | 6829349 | 1135 | 365 | 13 | 305 | 3960996 | 33926 | 71 | 181 | 2694080 | 286139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 0 | 3 | 153 | 753160 | 200041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15403 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6891 | 0 | 87 | 640 | 7422565 | 520105
| 02 | T2415 | 42884215201 | 2012-03-28 | QTR3 | 11/12 | 1 | 1 | 40 | 131 | 131 | 280% | 0 | 0 | 0 | 0 | 49 | 42 | 75000 | 0 | 75000 | 91225 | 91225 | 0 | 0 | 0 | 91225 | 91225 | 121.6% | 0 | 0 | 16225 | 12 | 7 | 0 | 42 | 16225 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 42 | 16225 | 0 | F593490202 | ALDON BOOKHARDT ROOFING INC. | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 |  | 2012-12-16 | QTR2 | 12/13 | 208 | 93853.67 | B0 | ACC - LUMP SUM
| 02 | T2439 | 42732815201 | 2012-09-26 | QTR1 | 12/13 | 1 | 0 | 70 | 75 | 111 | 151.4% | 0 | -36 | 36 | 0 | 5 | 0 | 240847 | 16502 | 224345 | 240847 | 224345 | -71365 | 0 | -71365 | 152980 | 152980 | 68.19% | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592733482 | ONAS CORPORATION | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 |  | 2013-04-23 | QTR4 | 12/13 | 208 | 250711.01
| 02 | T2443 | 42698615201 | 2013-02-06 | QTR3 | 12/13 | 1 | 0 | 150 | 204 | 203 | 105.3% | 1 | 1 | 0 | 0 | 45 | 9 | 4870523 | 56040 | 4814483 | 4870523 | 4844339 | 0 | 0 | 0 | 4844339 | 4835215 | 100.4% | 1 | -9124 | 0 | 37 | 8 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-07-13 | QTR1 | 15/16 |  | 2013-12-22 | QTR2 | 13/14 | 209 | 5528433.55
| 02 | T2512 | 42869015201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 260 | 389 | 389 | 100% | 1 | 0 | 0 | 0 | 129 | 0 | 8787879 | 96597 | 8691282 | 8787879 | 8967904 | 0 | 0 | 0 | 8967904 | 8851811 | 101.8% | 1 | -116093 | 0 | 104 | 25 | 0 | 0 | 5708 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10581 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 |  | 2015-04-10 | QTR4 | 14/15 | 214 | 9570318.55
| 02 | T2517 | 41695325201 | 2014-02-26 | QTR3 | 13/14 | 1 | 3 | 300 | 488 | 488 | 127.3% | 0 | 0 | 0 | 0 | 112 | 76 | 5124750 | 58877 | 5065873 | 5335260 | 5663021 | 0 | 0 | 0 | 5663021 | 5552944 | 109.6% | 1 | -110077 | 210510 | 75 | 31 | 0 | 0 | 17045 | 703 | 0 | 53 | 130746 | 29421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 44849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 58566 | 58566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 76 | 251206 | 88690 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-12-22 | QTR2 | 15/16 |  | 2015-09-26 | QTR1 | 15/16 | 208 | 6059850.2
| 02 | T2524 | 42870915201 | 2014-05-07 | QTR4 | 13/14 | 2 | 2 | 150 | 298 | 302 | 112.7% | 1 | -4 | 4 | 0 | 133 | 15 | 3832891 | 67277 | 3765614 | 3864530 | 3881828 | -9496 | 0 | -9496 | 3872332 | 3786451 | 100.6% | 1 | -85881 | 31639 | 106 | 27 | 0 | 14 | 49251 | 0 | 0 | 1 | 42542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 94387 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-11-17 | QTR2 | 15/16 |  | 2015-05-21 | QTR4 | 14/15 | 208 | 3923781.3 | B0 | ACC - LUMP SUM
| 02 | T2527 | 42870515201 | 2014-05-21 | QTR4 | 13/14 | 1 | 2 | 195 | 311 | 311 | 111.8% | 1 | 0 | 0 | 0 | 93 | 23 | 3855596 | 50000 | 3805596 | 3937461 | 4006951 | 0 | 0 | 0 | 4006951 | 3890841 | 102.2% | 1 | -116110 | 81865 | 69 | 24 | 0 | 7 | 33849 | 0 | 0 | 16 | 66627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 100476 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 |  | 2015-06-10 | QTR4 | 14/15 | 208 | 3913298.22
| 02 | T2528 | 42870615201 | 2014-05-21 | QTR4 | 13/14 | 2 | 1 | 260 | 425 | 425 | 113.5% | 1 | 0 | 0 | 0 | 150 | 15 | 6187853 | 81793 | 6106060 | 6237853 | 6218179 | 0 | 0 | 0 | 6218179 | 5933793 | 97.18% | 1 | -284386 | 50000 | 96 | 34 | 0 | 10 | 28305 | 0 | 20 | 5 | 46802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15 | 75107 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-12-22 | QTR2 | 15/16 |  | 2015-11-05 | QTR2 | 15/16 | 208 | 5027804.24
| 02 | T2529 | 42871215201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 190 | 354 | 354 | 152.6% | 0 | 0 | 0 | 0 | 164 | 0 | 5035067 | 50000 | 4985067 | 5035067 | 5418212 | 0 | 0 | 0 | 5418212 | 5280952 | 105.9% | 1 | -137260 | 0 | 48 | 16 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 1324 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-07 | QTR2 | 15/16 |  | 2015-07-28 | QTR1 | 15/16 | 216 | 5026805.45
| 02 | T2530 | 21156035201 | 2014-05-21 | QTR4 | 13/14 | 1 | 3 | 150 | 207 | 196 | 118.7% | 1 | 11 | 0 | 0 | 57 | 0 | 1259477 | 0 | 1259477 | 1284233 | 1254859 | 0 | 0 | 0 | 1254859 | 1254859 | 99.63% | 1 | 0 | 24756 | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 24756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 24756 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 |  | 2015-05-26 | QTR4 | 14/15 | 216 | 957005.79
| 02 | T2535 | 42053145201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 120 | 164 | 164 | 121.7% | 0 | 0 | 0 | 0 | 21 | 23 | 1754776 | 50000 | 1704776 | 1824298 | 1779783 | 0 | 0 | 0 | 1779783 | 1779783 | 104.4% | 1 | 0 | 69521 | 15 | 3 | 0 | 0 | 160 | 0 | 0 | 23 | 73186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 73346 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 |  | 2015-06-17 | QTR4 | 14/15 | 214 | 1169715.46 | B0 | ACC - LUMP SUM
| 02 | T2543 | 43055515201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 70 | 93 | 93 | 101.4% | 1 | 0 | 0 | 0 | 23 | 0 | 1738869 | 50000 | 1688869 | 1738869 | 1721840 | 0 | 0 | 0 | 1721840 | 1698982 | 100.6% | 1 | -22858 | 0 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-07-01 | QTR1 | 15/16 |  | 2015-02-13 | QTR3 | 14/15 | 214 | 1963162.15
| 02 | T2544 | 42880815201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 180 | 342 | 340 | 101.7% | 1 | 2 | 0 | 0 | 157 | 5 | 7085441 | 54149 | 7031292 | 7135441 | 7222230 | 0 | 0 | 0 | 7222230 | 6861498 | 97.59% | 1 | -360732 | 50000 | 100 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 8711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 57216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 65927 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-12-04 | QTR2 | 15/16 |  | 2015-10-12 | QTR2 | 15/16 | 208 | 5804681.6
| 02 | T2546 | 42889615201 | 2014-09-24 | QTR1 | 14/15 | 1 | 4 | 190 | 261 | 261 | 106.8% | 1 | 0 | 0 | 0 | 71 | 0 | 1837492 | 0 | 1837492 | 1861682 | 1898076 | 0 | 0 | 0 | 1898076 | 1898076 | 103.3% | 1 | 0 | 24190 | 39 | 19 | 0 | 0 | 8416 | 0 | 13 | 0 | 15774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 24190 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-12-17 | QTR2 | 15/16 |  | 2015-11-11 | QTR2 | 15/16 | 214 | 1560659.59
| 02 | T2551 | 43035225201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 180 | 237 | 235 | 107.8% | 1 | 2 | 0 | 0 | 41 | 16 | 6221583 | 61863 | 6159720 | 6221583 | 6254748 | 0 | 0 | 0 | 6254748 | 5599650 | 90.91% | 1 | -655098 | 0 | 35 | 6 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-01 | QTR2 | 15/16 |  | 2015-09-14 | QTR1 | 15/16 | 214 | 6248824.82 | B0 | ACC - LUMP SUM
| 02 | T2552 | 43055415201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 90 | 114 | 114 | 105.6% | 1 | 0 | 0 | 0 | 19 | 5 | 1940620 | 50000 | 1890620 | 1940620 | 1924570 | 0 | 0 | 0 | 1924570 | 1856552 | 98.2% | 1 | -68018 | 0 | 14 | 5 | 0 | 5 | 7272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7272 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-10-01 | QTR2 | 15/16 |  | 2015-05-28 | QTR4 | 14/15 | 214 | 2021176.83
| 02 | T2554 | 43112915201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 140 | 151 | 150 | 99.29% | 1 | 1 | 0 | 0 | 11 | 0 | 4054390 | 50000 | 4004390 | 4054390 | 4069302 | 0 | 0 | 0 | 4069302 | 3749497 | 93.63% | 1 | -319805 | 0 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F580952077 | SCRUGGS COMPANY (THE) | N/A | N/A | N/A | N/A | 2015-10-21 | QTR2 | 15/16 |  | 2015-06-19 | QTR4 | 14/15 | 209 | 4996678.96
| 02 | T2556 | 21007535201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 280 | 288 | 236 | 81.79% | 1 | 52 | 0 | 0 | 8 | 0 | 1492042 | 50000 | 1442042 | 1492042 | 1448762 | 0 | 0 | 0 | 1448762 | 1448762 | 100.5% | 1 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 8900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8900 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-12-11 | QTR2 | 15/16 |  | 2015-08-28 | QTR1 | 15/16 | 209 | 1755423.21
| 02 | T2560 | 43054615201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 120 | 165 | 163 | 98.33% | 1 | 2 | 0 | 0 | 45 | 0 | 2422564 | 50000 | 2372564 | 2422564 | 2506188 | 0 | 0 | 0 | 2506188 | 2389680 | 100.7% | 1 | -116508 | 0 | 41 | 4 | 0 | 0 | 4281 | 0 | 0 | 0 | 5345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568 | 0 | 0 | 0 | 1357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13550 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-14 | QTR2 | 15/16 |  | 2015-08-07 | QTR1 | 15/16 | 208 | 2628642.62
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 19 | 21 | 18 | 3135 | 4697 | 4666 | 73.68% | 14 | 31 | 40 | 0 | 1333 | 229 | 67817660 | 893098 | 66924562 | 68376367 | 69396362 | -80861 | 0 | -80861 | 69315501 | 66913551 | 94.74% | 18 | -2401950 | 558706 | 826 | 294 | 0 | 78 | 170512 | 703 | 66 | 123 | 426889 | 29421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5162 | 0 | 6 | 5 | 106119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 58566 | 58566 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 229 | 767247 | 88690
| 02 | E2Q76 | 42931315201 | 2013-02-20 | QTR3 | 12/13 | 1 | 2 | 150 | 217 | 470 | 286.7% | 0 | -253 | 253 | 0 | 67 | 0 | 645001 | 40470 | 604531 | 605429 | 554900 | -15320 | 0 | -15320 | 539579 | 539579 | 89.26% | 1 | 0 | -39572 | 18 | 22 | 0 | 0 | -50000 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | -39572 | 0 | F420429710 | DEVELOPERS SURETY AND INDEMNITY COMPANY | N/A | N/A | N/A | N/A | 2015-11-24 | QTR2 | 15/16 |  | 2014-10-09 | QTR2 | 14/15 | 209 | 892356.39
| 02 | E2Q95 | 42886915201 | 2012-09-19 | QTR1 | 12/13 | 1 | 1 | 45 | 76 | 121 | 235.6% | 0 | -45 | 45 | 0 | 15 | 16 | 86971 | 6529 | 80442 | 96284 | 96295 | -16502 | 0 | -16502 | 79792 | 79792 | 99.19% | 1 | 0 | 9314 | 6 | 9 | 0 | 2 | 9795 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9795 | 0 | F592733482 | ONAS CORPORATION | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 |  | 2013-04-12 | QTR4 | 12/13 | 208 | 85579.8
| 02 | E2R18 | 42468515201 | 2013-05-23 | QTR4 | 12/13 | 2 | 2 | 540 | 689 | 689 | 102.4% | 1 | 0 | 0 | 0 | 136 | 13 | 8195419 | 86278 | 8109141 | 8206705 | 8178408 | 0 | 0 | 0 | 8178408 | 8124680 | 100.2% | 1 | -53727 | 11286 | 89 | 47 | 0 | 0 | 43065 | 0 | 0 | 13 | 15182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11855 | 0 | 0 | 13 | 69534 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-08-18 | QTR1 | 15/16 |  | 2015-06-03 | QTR4 | 14/15 | 214 | 8761555.44 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2R93 | 42607215201 | 2013-08-21 | QTR1 | 13/14 | 1 | 1 | 285 | 344 | 418 | 140.7% | 0 | -74 | 74 | 0 | 59 | 0 | 1520777 | 50000 | 1470777 | 1520777 | 1507456 | -61280 | 0 | -61280 | 1446176 | 1443425 | 98.14% | 1 | -2751 | 0 | 0 | 17 | 42 | 0 | 0 | 0 | 0 | 0 | 14250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 14250 | 0 | F650447555 | L & S CONCRETE RESTORATION INC | N/A | N/A | N/A | N/A | 2015-11-17 | QTR2 | 15/16 |  | 2015-02-27 | QTR3 | 14/15 | 208 | 1839323.68
| 02 | E2R94 | 42822915201 | 2013-08-21 | QTR1 | 13/14 | 1 | 0 | 469 | 536 | 533 | 106.2% | 1 | 3 | 0 | 0 | 35 | 32 | 2445796 | 50000 | 2395796 | 2445796 | 2450466 | 0 | 0 | 0 | 2450466 | 2449755 | 102.3% | 1 | -711 | 0 | 13 | 22 | 0 | 0 | 20184 | 0 | 0 | 32 | 14554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 49896 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-17 | QTR1 | 15/16 |  | 2015-06-12 | QTR4 | 14/15 | 216 | 2404678.02
| 02 | E2S71 | 42869515201 | 2014-04-23 | QTR4 | 13/14 | 1 | 1 | 230 | 307 | 307 | 109.1% | 1 | 0 | 0 | 0 | 56 | 21 | 7686286 | 65080 | 7621206 | 7580608 | 7142686 | 0 | 0 | 0 | 7142686 | 6953829 | 91.24% | 1 | -188858 | -105678 | 42 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 57675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105678 | 0 | 0 | 21 | -48003 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 |  | 2015-05-14 | QTR4 | 14/15 | 209 | 6348256.45
| 02 | E2S89 | 20954125201 | 2014-04-23 | QTR4 | 13/14 | 1 | 0 | 360 | 373 | 340 | 90.83% | 1 | 33 | 0 | 0 | 13 | 0 | 1997720 | 50000 | 1947720 | 1997720 | 2088940 | 0 | 0 | 0 | 2088940 | 2081779 | 106.9% | 1 | -7161 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 |  | 2015-06-16 | QTR4 | 14/15 | 208 | 2345342.1
| 02 | E2T03 | 42871115201 | 2014-07-23 | QTR1 | 14/15 | 1 | 0 | 255 | 322 | 322 | 103.9% | 1 | 0 | 0 | 0 | 64 | 3 | 5283383 | 50000 | 5233383 | 5283383 | 4965217 | 0 | 0 | 0 | 4965217 | 4630053 | 88.47% | 1 | -335164 | 0 | 34 | 23 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-11-24 | QTR2 | 15/16 |  | 2015-08-22 | QTR1 | 15/16 | 208 | 4581887.25
| 02 | E2T06 | 43074715201 | 2014-07-23 | QTR1 | 14/15 | 1 | 0 | 90 | 96 | 96 | 100% | 1 | 0 | 0 | 0 | 6 | 0 | 205480 | 7889 | 197591 | 205480 | 200119 | 0 | 0 | 0 | 200119 | 200119 | 101.3% | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 |  | 2015-05-27 | QTR4 | 14/15 | 209 | 167996.51
| 02 | E2T32 | 43194215201 | 2014-12-10 | QTR2 | 14/15 | 1 | 1 | 120 | 164 | 164 | 120% | 1 | 0 | 0 | 0 | 20 | 24 | 1419048 | 50000 | 1369048 | 1578817 | 1549237 | 0 | 0 | 0 | 1549237 | 1549237 | 113.2% | 0 | 0 | 159769 | 18 | 2 | 0 | 0 | 0 | 0 | 0 | 24 | 163983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 163983 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-12-21 | QTR2 | 15/16 |  | 2015-11-17 | QTR2 | 15/16 | 216 | 1414155.44
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 10 | 11 | 8 | 2544 | 3124 | 3460 | 70% | 7 | -336 | 372 | 0 | 471 | 109 | 29485881 | 456246 | 29029635 | 29520999 | 28733724 | -93102 | 0 | -93102 | 28640620 | 28052248 | 90% | 9 | -588372 | 35119 | 228 | 167 | 42 | 2 | 23044 | 0 | 34 | 105 | 265644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | 0 | 0 | 23141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -117533 | 0 | 76 | 109 | 219883 | 0
| District 02 Totals |  |  |  |  | 29 | 32 | 26 | 5679 | 7821 | 8126 | 72.41% | 21 | -305 | 412 | 0 | 1804 | 338 | 97303541 | 1349344 | 95954197 | 97897366 | 98130086 | -173963 | 0 | -173963 | 97956121 | 94965799 | 93.1% | 27 | -2990322 | 593825 | 1054 | 461 | 42 | 80 | 193556 | 703 | 100 | 228 | 692533 | 29421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 20319 | 0 | 6 | 5 | 106119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | 0 | 23 | 81707 | 58566 | 135 | 0 | 0 | 0 | 0 | 0 | -117533 | 0 | 283 | 338 | 987130 | 88690
| 03 | T3088 | 21894615201 | 2012-07-25 | QTR1 | 12/13 | 1 | 6 | 608 | 853 | 852 | 106.4% | 1 | 1 | 0 | 0 | 205 | 40 | 13348458 | 0 | 13348458 | 13883485 | 14095924 | 0 | 0 | 0 | 14095924 | 14095514 | 105.6% | 1 | -409 | 535027 | 149 | 56 | 0 | 0 | 90305 | 0 | 0 | 40 | 281269 | 169088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -173321 | 0 | 0 | 40 | 414064 | 169088 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 |  | 2015-02-24 | QTR3 | 14/15 | 321 | 14378815.2
| 03 | T3311 | 22041265201 | 2009-06-17 | QTR4 | 08/09 | 1 | 6 | 800 | 1260 | 1323 | 145.8% | 0 | -63 | 63 | 0 | 157 | 303 | 5621006 | 87031 | 5533975 | 6208685 | 6054584 | -158382 | 0 | -158382 | 5896202 | 6102577 | 110.3% | 0 | 206375 | 587679 | 74 | 83 | 0 | 0 | 14881 | 0 | 0 | 301 | 643272 | 420470 | 0 | 0 | 0 | 0 | 0 | 0 | -31593 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | -52050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 52356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303 | 630166 | 420470 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-11-03 | QTR2 | 15/16 |  | 2013-04-04 | QTR4 | 12/13 | 308 | 9080395.55 | ARRA | AMERICAN RECOVERY AND REINVEST
| 03 | T3396 | 42323315201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 300 | 504 | 498 | 108.3% | 1 | 6 | 0 | 0 | 173 | 31 | 2789487 | 50000 | 2739487 | 2763621 | 2700963 | 0 | 0 | 0 | 2700963 | 2673321 | 97.58% | 1 | -27642 | -25866 | 154 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 17268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25866 | 0 | 0 | 31 | -8599 | 0 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-05-18 | QTR4 | 14/15 | 314 | 2906373.5
| 03 | T3401 | 42323415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 300 | 478 | 474 | 98.67% | 1 | 4 | 0 | 0 | 178 | 0 | 2645210 | 50000 | 2595210 | 2645210 | 2628131 | 0 | 0 | 0 | 2628131 | 2609172 | 100.5% | 1 | -18959 | 0 | 164 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2015-07-06 | QTR1 | 15/16 |  | 2015-05-08 | QTR4 | 14/15 | 314 | 2957617.43
| 03 | T3409 | 42462215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 145 | 201 | 197 | 97.24% | 1 | 4 | 0 | 0 | 56 | 0 | 2097227 | 50000 | 2047227 | 2097227 | 2093592 | 0 | 0 | 0 | 2093592 | 1978887 | 96.66% | 1 | -114705 | 0 | 38 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-15 | QTR1 | 15/16 |  | 2015-05-05 | QTR4 | 14/15 | 321 | 2813050.27
| 03 | T3411 | 42636815201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 130 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 66 | 0 | 577753 | 0 | 577753 | 577753 | 581122 | 0 | 0 | 0 | 581122 | 581122 | 100.6% | 1 | 0 | 0 | 62 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263312611 | R B M CONTRACTING SERVICES LLC | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 |  | 2015-07-22 | QTR1 | 15/16 | 313 | 613088.19
| 03 | T3423 | 42164425201 | 2013-03-27 | QTR3 | 12/13 | 3 | 6 | 530 | 798 | 798 | 105.8% | 1 | 0 | 0 | 0 | 237 | 31 | 12358153 | 132771 | 12225382 | 11830936 | 14453163 | 0 | 0 | 0 | 14453163 | 14207037 | 116.2% | 0 | -246126 | -527216 | 209 | 28 | 0 | 4 | 106851 | 0 | 0 | 22 | 178456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -777502 | 1039155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 79271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | -412925 | 1039155 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-09 | QTR2 | 15/16 |  | 2015-08-19 | QTR1 | 15/16 | 308 | 13406269.99
| 03 | T3424 | 41343515201 | 2013-02-06 | QTR3 | 12/13 | 2 | 3 | 355 | 512 | 508 | 114.1% | 1 | 4 | 0 | 0 | 142 | 15 | 3882641 | 50000 | 3832641 | 3972326 | 3728903 | 0 | 0 | 0 | 3728903 | 3719464 | 97.05% | 1 | -9439 | 89685 | 86 | 17 | 0 | 4 | 26009 | 0 | 39 | 11 | 77908 | 92400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 15 | 103918 | 92400 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 |  | 2014-09-16 | QTR1 | 14/15 | 308 | 4647469.69
| 03 | T3434 | 42987815201 | 2014-08-27 | QTR1 | 14/15 | 2 | 0 | 160 | 197 | 197 | 101.2% | 1 | 0 | 0 | 0 | 35 | 2 | 459930 | 20930 | 439000 | 459930 | 451610 | 0 | 0 | 0 | 451610 | 451610 | 102.9% | 1 | 0 | 0 | 17 | 18 | 0 | 0 | 1560 | 0 | 0 | 2 | 11050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12610 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 |  | 2015-06-15 | QTR4 | 14/15 | 313 | 439830 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 03 | T3455 | 43000415201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 150 | 176 | 176 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 919509 | 0 | 919509 | 919509 | 927409 | 0 | 0 | 0 | 927409 | 927409 | 100.9% | 1 | 0 | 0 | 24 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 |  | 2015-07-16 | QTR1 | 15/16 | 308 | 817764.49
| 03 | T3468 | 42696515201 | 2014-06-18 | QTR4 | 13/14 | 2 | 0 | 220 | 294 | 284 | 108.6% | 1 | 10 | 0 | 0 | 74 | 0 | 1826839 | 50000 | 1776839 | 1826839 | 1794755 | 0 | 0 | 0 | 1794755 | 1727691 | 97.23% | 1 | -67064 | 0 | 24 | 21 | 0 | 0 | 14633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 1080 | 0 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 18747 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 |  | 2015-06-15 | QTR4 | 14/15 | 321 | 1783054.33
| 03 | T3476 | 42385815201 | 2014-03-26 | QTR3 | 13/14 | 1 | 1 | 276 | 370 | 370 | 117% | 1 | 0 | 0 | 0 | 47 | 47 | 2307108 | 50000 | 2257108 | 2297266 | 2266725 | 0 | 0 | 0 | 2266725 | 2239507 | 99.22% | 1 | -27218 | -9842 | 28 | 19 | 0 | 47 | 24743 | 0 | 0 | 0 | 11268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 28194 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 |  | 2015-06-16 | QTR4 | 14/15 | 321 | 2319570.2
| 03 | T3502 | 42764915201 | 2014-06-18 | QTR4 | 13/14 | 2 | 2 | 125 | 199 | 197 | 112.8% | 1 | 2 | 0 | 0 | 63 | 11 | 633977 | 26778 | 607199 | 703188 | 695402 | 0 | 0 | 0 | 695402 | 695402 | 114.5% | 0 | 0 | 69211 | 34 | 22 | 0 | 8 | 5089 | 0 | 0 | 3 | 70611 | 25322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 11 | 75699 | 25322 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-08-19 | QTR1 | 15/16 |  | 2015-05-21 | QTR4 | 14/15 | 308 | 559212.99
| 03 | T3510 | 43077615201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 190 | 241 | 240 | 99.47% | 1 | 1 | 0 | 0 | 51 | 0 | 3964092 | 50000 | 3914092 | 3964092 | 4024706 | 0 | 0 | 0 | 4024706 | 3718840 | 95.01% | 1 | -305866 | 0 | 27 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 11957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11957 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-28 | QTR2 | 15/16 |  | 2015-09-01 | QTR1 | 15/16 | 314 | 4154252.32
| 03 | T3530 | 43174415201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 60 | 67 | 66 | 98.33% | 1 | 1 | 0 | 0 | 7 | 0 | 217000 | 0 | 217000 | 217000 | 216611 | 0 | 0 | 0 | 216611 | 216611 | 99.82% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593715775 | PYRAMID EXCAVATION INC. | N/A | N/A | N/A | N/A | 2015-09-08 | QTR1 | 15/16 |  | 2015-06-19 | QTR4 | 14/15 | 321 | 236371.06
| 03 | T3532 | 43253215201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 120 | 143 | 143 | 100% | 1 | 0 | 0 | 0 | 23 | 0 | 3173126 | 50000 | 3123126 | 3173126 | 3259005 | 0 | 0 | 0 | 3259005 | 3171161 | 101.5% | 1 | -87844 | 0 | 12 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 |  | 2015-09-11 | QTR1 | 15/16 | 314 | 2959991
| 03 | T3535 | 42693615201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 85 | 109 | 109 | 100% | 1 | 0 | 0 | 0 | 24 | 0 | 481388 | 26436 | 454953 | 481388 | 440397 | 0 | 0 | 0 | 440397 | 440397 | 96.8% | 1 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 |  | 2015-06-21 | QTR4 | 14/15 | 313 | 540650.67
| 03 | T3536 | 40393125201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 60 | 69 | 69 | 100% | 1 | 0 | 0 | 0 | 9 | 0 | 369064 | 23136 | 345929 | 369064 | 338614 | 0 | 0 | 0 | 338614 | 338614 | 97.89% | 1 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-07-21 | QTR1 | 15/16 |  | 2015-06-13 | QTR4 | 14/15 | 321 | 486851.74
| 03 | T3540 | 21988025201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 120 | 141 | 141 | 100% | 1 | 0 | 0 | 0 | 21 | 0 | 347017 | 16058 | 330959 | 347017 | 338632 | 0 | 0 | 0 | 338632 | 338632 | 102.3% | 1 | 0 | 0 | 15 | 6 | 0 | 0 | 354 | 0 | 0 | 0 | 4919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5272 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-11-02 | QTR2 | 15/16 |  | 2015-08-24 | QTR1 | 15/16 | 321 | 352628.28
| 03 | T3555 | 43630635201 | 2015-04-29 | QTR4 | 14/15 | 3 | 0 | 60 | 66 | 66 | 100% | 1 | 0 | 0 | 0 | 6 | 0 | 409629 | 0 | 409629 | 409629 | 409629 | 0 | 0 | 0 | 409629 | 409629 | 100% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 |  | 2015-09-16 | QTR1 | 15/16 | 321 | 270025.98 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 20 | 28 | 25 | 4794 | 6874 | 6904 | 95% | 19 | -30 | 63 | 0 | 1600 | 480 | 58428614 | 733140 | 57695476 | 59147291 | 61499877 | -158382 | 0 | -158382 | 61341495 | 60642597 | 85% | 17 | -698897 | 718678 | 1141 | 384 | 0 | 63 | 284425 | 0 | 39 | 379 | 1292330 | 707280 | 0 | 0 | 0 | 0 | 0 | 0 | -31593 | 0 | 0 | 0 | 3300 | 0 | 29 | 1 | -666229 | 1039155 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 7 | 37 | 194647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -199187 | 0 | 75 | 480 | 880723 | 1746435
| 03 | E3K74 | 42692815201 | 2014-11-13 | QTR2 | 14/15 | 1 | 0 | 160 | 219 | 219 | 107.5% | 1 | 0 | 0 | 0 | 47 | 12 | 1363705 | 50000 | 1313705 | 1363705 | 1373851 | 0 | 0 | 0 | 1373851 | 1311778 | 99.85% | 1 | -62073 | 0 | 43 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 30968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 30968 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-12-17 | QTR2 | 15/16 |  | 2015-09-11 | QTR1 | 15/16 | 308 | 1604605.95
| 03 | E3L71 | 42874415201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 160 | 192 | 192 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 1490639 | 50000 | 1440639 | 1490639 | 1445553 | 0 | 0 | 0 | 1445553 | 1451830 | 100.8% | 1 | 6277 | 0 | 23 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 |  | 2014-12-14 | QTR2 | 14/15 | 314 | 1584506.78
| 03 | E3L98 | 42874615201 | 2014-11-13 | QTR2 | 14/15 | 2 | 1 | 180 | 201 | 200 | 99.44% | 1 | 1 | 0 | 0 | 21 | 0 | 4259734 | 50000 | 4209734 | 4287109 | 4172519 | 0 | 0 | 0 | 4172519 | 3907768 | 92.83% | 1 | -264750 | 27375 | 16 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 27375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27375 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-11-03 | QTR2 | 15/16 |  | 2015-08-20 | QTR1 | 15/16 | 321 | 4989174.47
| 03 | E3M60 | 42697215201 | 2014-12-11 | QTR2 | 14/15 | 1 | 0 | 100 | 134 | 134 | 102% | 1 | 0 | 0 | 0 | 32 | 2 | 1718927 | 50000 | 1668927 | 1718927 | 1766800 | 0 | 0 | 0 | 1766800 | 1673682 | 100.3% | 1 | -93118 | 0 | 10 | 22 | 0 | 2 | 3651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3651 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-07-22 | QTR1 | 15/16 | 308 | 2202753.65
| 03 | E3M93 | 43078215201 | 2014-12-11 | QTR2 | 14/15 | 1 | 0 | 70 | 77 | 76 | 100% | 1 | 1 | 0 | 0 | 6 | 1 | 1217750 | 50000 | 1167750 | 1217750 | 1189202 | 0 | 0 | 0 | 1189202 | 1136275 | 97.3% | 1 | -52927 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2880 | 0 | F580538940 | OXFORD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 |  | 2015-07-08 | QTR1 | 15/16 | 314 | 1216619.67
| 03 | E3N07 | 43460315201 | 2015-07-09 | QTR1 | 15/16 | 1 | 0 | 28 | 28 | 27 | 96.43% | 1 | 1 | 0 | 0 | 0 | 0 | 31110 | 1910 | 29200 | 31110 | 28465 | 0 | 0 | 0 | 28465 | 28465 | 97.48% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-12-10 | QTR2 | 15/16 |  | 2015-10-26 | QTR2 | 15/16 | 308 | 45126.8
| 03 | E3N22 | 41547435201 | 2014-10-09 | QTR2 | 14/15 | 1 | 1 | 90 | 168 | 168 | 145.6% | 0 | 0 | 0 | 0 | 37 | 41 | 785011 | 50000 | 735011 | 874968 | 824968 | 0 | 0 | 0 | 824968 | 824968 | 112.2% | 0 | 0 | 89957 | 33 | 4 | 0 | 0 | 0 | 0 | 0 | 41 | 89957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 89957 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2015-12-08 | QTR2 | 15/16 |  | 2015-08-07 | QTR1 | 15/16 | 308 | 1252571.9
| 03 | E3N70 | 41694415201 | 2014-11-13 | QTR2 | 14/15 | 1 | 1 | 120 | 166 | 163 | 101.7% | 1 | 3 | 0 | 0 | 41 | 5 | 2595171 | 50000 | 2545171 | 2642211 | 2488780 | 0 | 0 | 0 | 2488780 | 2390489 | 93.92% | 1 | -98291 | 47040 | 34 | 7 | 0 | 0 | 3190 | 0 | 0 | 3 | 47040 | 23968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 51468 | 23968 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2015-11-09 | QTR2 | 15/16 |  | 2015-08-17 | QTR1 | 15/16 | 314 | 2402720.45
| 03 | E3N81 | 43558115201 | 2015-05-14 | QTR4 | 14/15 | 1 | 1 | 60 | 80 | 80 | 116.7% | 1 | 0 | 0 | 0 | 10 | 10 | 154105 | 5690 | 148415 | 159104 | 150561 | 0 | 0 | 0 | 150561 | 150561 | 101.4% | 1 | 0 | 4999 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4999 | 4999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4999 | 4999 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-12-28 | QTR2 | 15/16 |  | 2015-10-22 | QTR2 | 15/16 | 308 | 119492.78
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 9 | 10 | 4 | 968 | 1265 | 1259 | 88.89% | 8 | 6 | 0 | 0 | 226 | 71 | 13616152 | 357600 | 13258552 | 13785523 | 13440699 | 0 | 0 | 0 | 13440699 | 12875816 | 88.89% | 8 | -564882 | 169371 | 172 | 54 | 0 | 2 | 6841 | 0 | 0 | 45 | 167252 | 23968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 37205 | 4999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 211298 | 28967
| District 03 Totals |  |  |  |  | 29 | 38 | 29 | 5762 | 8139 | 8163 | 93.1% | 27 | -24 | 63 | 0 | 1826 | 551 | 72044766 | 1090740 | 70954028 | 72932814 | 74940576 | -158382 | 0 | -158382 | 74782194 | 73518413 | 86.21% | 25 | -1263779 | 888049 | 1313 | 438 | 0 | 65 | 291266 | 0 | 39 | 424 | 1459582 | 731248 | 0 | 0 | 0 | 0 | 0 | 0 | -31593 | 0 | 0 | 0 | 3300 | 0 | 29 | 25 | -629024 | 1044154 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 7 | 37 | 194647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -199187 | 0 | 75 | 551 | 1092021 | 1775402
| 04 | T4255 | 40398415201 | 2010-12-08 | QTR2 | 10/11 | 1 | 24 | 920 | 1352 | 1352 | 126.7% | 0 | 0 | 0 | 0 | 186 | 246 | 36988133 | 150000 | 36838133 | 40660763 | 41250312 | 0 | 0 | 0 | 41250312 | 41508810 | 112.7% | 0 | 258498 | 3672630 | 127 | 59 | 0 | 0 | 712871 | 128765 | 0 | 246 | 4139811 | 2271858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1705619 | 30394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205492 | 0 | 0 | 0 | 271969 | 271969 | 0 | 0 | 115942 | 115942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 3740465 | 2818928 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-12-17 | QTR2 | 15/16 |  | 2015-03-17 | QTR3 | 14/15 | 412 | 44275084.25
| 04 | T4311 | 42924615201 | 2011-04-27 | QTR4 | 10/11 | 1 | 1 | 180 | 266 | 319 | 150.6% | 0 | -53 | 53 | 0 | 48 | 38 | 3983113 | 50000 | 3933113 | 4102286 | 4023382 | -101442 | 0 | -101442 | 3921940 | 3920334 | 99.68% | 1 | -1606 | 119174 | 36 | 12 | 0 | 2 | 3257 | 0 | 0 | 33 | 132841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 136098 | 0 | F593749359 | DESIGN-BUILD ENGINEERS & CONTRA | N/A | N/A | N/A | N/A | 2015-08-20 | QTR1 | 15/16 |  | 2012-05-07 | QTR4 | 11/12 | 409 | 3335896.13
| 04 | T4345 | 40836215201 | 2013-05-22 | QTR4 | 12/13 | 1 | 5 | 266 | 650 | 650 | 216.2% | 0 | 0 | 0 | 0 | 89 | 295 | 1202547 | 50000 | 1152547 | 3085087 | 3080524 | 0 | 0 | 0 | 3080524 | 3080524 | 267.3% | 0 | 0 | 1882539 | 48 | 27 | 14 | 266 | 1575597 | 0 | 0 | 29 | 324673 | 98769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8860 | 8860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 295 | 1908989 | 107629 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 |  | 2015-05-21 | QTR4 | 14/15 | 412 | 1238644.33
| 04 | T4374 | 43019615201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 102 | 112 | 110 | 98.04% | 1 | 2 | 0 | 0 | 10 | 0 | 348825 | 18115 | 330710 | 348825 | 339314 | 0 | 0 | 0 | 339314 | 339314 | 102.6% | 1 | 0 | 0 | 9 | 1 | 0 | 0 | 3246 | 0 | 0 | 0 | 5358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8604 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-22 | QTR1 | 15/16 |  | 2015-06-10 | QTR4 | 14/15 | 412 | 385157.48
| 04 | T4380 | 42974015201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 100 | 118 | 117 | 99% | 1 | 1 | 0 | 0 | 18 | 0 | 480024 | 22736 | 457288 | 480024 | 456013 | 0 | 0 | 0 | 456013 | 456013 | 99.72% | 1 | 0 | 0 | 16 | 2 | 0 | 0 | 2267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2267 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 412 | 486438.28
| 04 | T4384 | 42973815201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 96 | 101 | 99 | 97.92% | 1 | 2 | 0 | 0 | 5 | 0 | 547622 | 25962 | 521660 | 548351 | 527560 | 0 | 0 | 0 | 527560 | 527560 | 101.1% | 1 | 0 | 729 | 4 | 1 | 0 | 0 | 1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 |  | 2015-07-02 | QTR1 | 15/16 | 409 | 546487.47
| 04 | T4394 | 43060225203 | 2014-05-21 | QTR4 | 13/14 | 3 | 1 | 243 | 281 | 280 | 99.59% | 1 | 1 | 0 | 0 | 38 | 0 | 831515 | 40849 | 790666 | 893080 | 843974 | 0 | 0 | 0 | 843974 | 843974 | 106.7% | 1 | 0 | 61565 | 26 | 12 | 0 | 0 | 2400 | 0 | 0 | 0 | 68329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70729 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 |  | 2015-06-08 | QTR4 | 14/15 | 412 | 850266.14
| 04 | T4398 | 42974115201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 126 | 160 | 160 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 420985 | 20915 | 400070 | 420985 | 395082 | 0 | 0 | 0 | 395082 | 395082 | 98.75% | 1 | 0 | 0 | 32 | 2 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-10-15 | QTR2 | 15/16 |  | 2015-09-03 | QTR1 | 15/16 | 412 | 439143.73
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 8 | 10 | 32 | 2033 | 3040 | 3087 | 62.5% | 5 | -47 | 53 | 0 | 428 | 579 | 44802764 | 378577 | 44424187 | 50539401 | 50916161 | -101442 | 0 | -101442 | 50814719 | 51071611 | 75% | 6 | 256892 | 5736637 | 298 | 116 | 14 | 268 | 2305177 | 128765 | 0 | 308 | 4671012 | 2370627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1705761 | 30394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 205492 | 0 | 0 | 0 | 271969 | 271969 | 0 | 0 | 124802 | 124802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 579 | 5872691 | 2926557
| 04 | E4L95 | 41304815201 | 2011-06-21 | QTR4 | 10/11 | 1 | 5 | 878 | 1407 | 1406 | 111.6% | 1 | 1 | 0 | 0 | 447 | 82 | 54423100 | 150000 | 54273100 | 54843389 | 54825050 | 0 | 0 | 0 | 54825050 | 54583811 | 100.6% | 1 | -241240 | 420289 | 367 | 59 | 15 | 82 | 536157 | 0 | 0 | 0 | 5762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 82 | 542342 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 |  | 2015-08-03 | QTR1 | 15/16 | 408 | 56635287.97 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4P28 | 43053415201 | 2014-01-03 | QTR3 | 13/14 | 1 | 1 | 265 | 342 | 335 | 114.3% | 1 | 7 | 0 | 0 | 77 | 0 | 1630613 | 50000 | 1580613 | 1680613 | 1713025 | 0 | 0 | 0 | 1713025 | 1712786 | 108.4% | 1 | -239 | 50000 | 15 | 17 | 45 | 0 | 0 | 0 | 0 | 0 | 46404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 46404 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2015-08-13 | QTR1 | 15/16 |  | 2015-07-09 | QTR1 | 15/16 | 408 | 1510582.53
| 04 | E4P42 | 42744115201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 237 | 285 | 285 | 112.7% | 1 | 0 | 0 | 0 | 18 | 30 | 1055000 | 50000 | 1005000 | 1055000 | 1018660 | 0 | 0 | 0 | 1018660 | 1018660 | 101.4% | 1 | 0 | 0 | 7 | 11 | 0 | 0 | 5225 | 0 | 0 | 30 | 11535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16760 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-09-24 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 409 | 1104492 | B0 | ACC - LUMP SUM
| 04 | E4P43 | 42636215201 | 2014-03-31 | QTR3 | 13/14 | 1 | 0 | 371 | 415 | 411 | 100% | 1 | 4 | 0 | 0 | 40 | 4 | 2106087 | 50000 | 2056087 | 2106087 | 2037825 | 0 | 0 | 0 | 2037825 | 2037825 | 99.11% | 1 | 0 | 0 | 25 | 15 | 0 | 0 | 4164 | 0 | 0 | 0 | 5698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 15442 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 |  | 2015-08-14 | QTR1 | 15/16 | 408 | 2671513.63
| 04 | E4P91 | 43397915201 | 2014-06-06 | QTR4 | 13/14 | 4 | 1 | 223 | 291 | 290 | 108.5% | 1 | 1 | 0 | 0 | 48 | 20 | 682040 | 21400 | 660640 | 677370 | 696418 | 0 | 0 | 0 | 696418 | 696418 | 105.4% | 1 | 0 | -4669 | 31 | 17 | 0 | 0 | 5986 | 0 | 0 | 20 | 10647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 11963 | 0 | F364509634 | MAYTIN ENGINEERING CORP. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 |  | 2015-07-10 | QTR1 | 15/16 | 412 | 468107.77
| 04 | E4Q13 | 43060515201 | 2014-08-01 | QTR1 | 14/15 | 1 | 0 | 303 | 346 | 346 | 106.9% | 1 | 0 | 0 | 0 | 43 | 0 | 3035506 | 50000 | 2985506 | 3035506 | 2614486 | 0 | 0 | 0 | 2614486 | 2545146 | 85.25% | 1 | -69341 | 0 | 13 | 9 | 0 | 0 | 0 | 0 | 21 | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 1925 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-30 | QTR2 | 15/16 |  | 2015-09-28 | QTR1 | 15/16 | 412 | 3179103.94
| 04 | E4Q62 | 42993615201 | 2015-01-09 | QTR3 | 14/15 | 1 | 0 | 115 | 122 | 121 | 99.13% | 1 | 1 | 0 | 0 | 7 | 0 | 886950 | 50000 | 836950 | 886950 | 810170 | 0 | 0 | 0 | 810170 | 810170 | 96.8% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-11-05 | QTR2 | 15/16 |  | 2015-09-30 | QTR1 | 15/16 | 408 | 1238736
| 04 | E4Q67 | 42824115201 | 2015-02-06 | QTR3 | 14/15 | 2 | 1 | 90 | 119 | 118 | 117.8% | 1 | 1 | 0 | 0 | 12 | 17 | 186978 | 11022 | 175956 | 221816 | 214581 | 0 | 0 | 0 | 214581 | 214581 | 122% | 0 | 0 | 34838 | 10 | 2 | 0 | 17 | 34838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 34838 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2015-11-18 | QTR2 | 15/16 |  | 2015-10-20 | QTR2 | 15/16 | 408 | 231295.35
| 04 | E4Q81 | 43400615201 | 2015-04-03 | QTR4 | 14/15 | 2 | 0 | 100 | 103 | 70 | 67% | 1 | 33 | 0 | 0 | 3 | 0 | 436152 | 20024 | 416128 | 436152 | 404357 | 0 | 0 | 0 | 404357 | 404357 | 97.17% | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2660 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2990 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-11-05 | QTR2 | 15/16 |  | 2015-10-02 | QTR2 | 15/16 | 409 | 395430.51
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 9 | 14 | 8 | 2582 | 3430 | 3382 | 100% | 9 | 48 | 0 | 0 | 695 | 153 | 64442426 | 452446 | 63989980 | 64942883 | 64334572 | 0 | 0 | 0 | 64334572 | 64023754 | 88.89% | 8 | -310820 | 500458 | 473 | 135 | 60 | 99 | 589030 | 0 | 21 | 50 | 82301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 153 | 672664 | 0
| District 04 Totals |  |  |  |  | 17 | 24 | 40 | 4615 | 6470 | 6469 | 82.35% | 14 | 1 | 53 | 0 | 1123 | 732 | 109245190 | 831023 | 108414167 | 115482284 | 115250733 | -101442 | 0 | -101442 | 115149291 | 115095365 | 82.35% | 14 | -53928 | 6237095 | 771 | 251 | 74 | 367 | 2894207 | 128765 | 21 | 358 | 4753313 | 2370627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | -1704850 | 30394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 205916 | 0 | 0 | 0 | 271969 | 271969 | 0 | 0 | 124802 | 124802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 732 | 6545355 | 2926557
| 05 | BDT74 | 41299435201 | 2011-11-07 | QTR2 | 11/12 | 5 | 15 | 460 | 802 | 1058 | 219.3% | 0 | -256 | 256 | 0 | 77 | 265 | 27584500 | 150000 | 27434500 | 29571831 | 29554288 | 0 | 0 | 0 | 29554288 | 29554288 | 107.7% | 1 | 0 | 1987331 | 26 | 23 | 0 | 0 | 294952 | 5697 | 0 | 0 | 366049 | 3040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 1475287 | 169381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 2136288 | 178118 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2015-09-07 | QTR1 | 15/16 |  | 2015-02-11 | QTR3 | 14/15 | 507 | 27584500
| 05 | T5401 | 42201515201 | 2013-04-24 | QTR4 | 12/13 | 4 | 5 | 290 | 361 | 361 | 107.2% | 1 | 0 | 0 | 0 | 50 | 21 | 4603457 | 50000 | 4553457 | 4806215 | 4675801 | 0 | 0 | 0 | 4675801 | 4675281 | 102.7% | 1 | -520 | 202758 | 32 | 18 | 0 | 5 | 67573 | 12260 | 0 | 16 | 186828 | 13247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 254401 | 25507 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-08 | QTR1 | 15/16 |  | 2014-08-18 | QTR1 | 14/15 | 509 | 4500359.97
| 05 | T5404 | 24023335201 | 2012-05-23 | QTR4 | 11/12 | 5 | 6 | 710 | 980 | 980 | 114.8% | 1 | 0 | 0 | 0 | 165 | 105 | 10111333 | 50000 | 10061333 | 10458539 | 10091859 | 0 | 0 | 0 | 10091859 | 10008344 | 99.47% | 1 | -83514 | 347206 | 129 | 36 | 0 | 21 | 292661 | 435 | 0 | 84 | 60822 | 1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 355274 | 1518 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-11 | QTR2 | 15/16 |  | 2015-05-03 | QTR4 | 14/15 | 507 | 9890702.1
| 05 | T5417 | 40735545201 | 2012-04-25 | QTR4 | 11/12 | 1 | 2 | 870 | 1082 | 1082 | 109.1% | 1 | 0 | 0 | 0 | 133 | 79 | 18388845 | 150000 | 18238845 | 18447512 | 18384136 | 0 | 0 | 0 | 18384136 | 18074458 | 99.1% | 1 | -309678 | 58667 | 85 | 48 | 0 | 15 | 46621 | 19776 | 0 | 7 | 79676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 38891 | 38891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 165189 | 58667 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-11-25 | QTR2 | 15/16 |  | 2015-07-02 | QTR1 | 15/16 | 513 | 20359976.85
| 05 | T5419 | 23953555201 | 2012-06-27 | QTR4 | 11/12 | 4 | 9 | 800 | 863 | 863 | 100% | 1 | 0 | 0 | 0 | 63 | 0 | 15255527 | 150000 | 15105527 | 14971879 | 14890213 | 0 | 0 | 0 | 14890213 | 14848574 | 98.3% | 1 | -41639 | -283648 | 45 | 18 | 0 | 0 | 137015 | 0 | 0 | 0 | 68402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -463188 | 0 | 0 | 0 | -245067 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-12-11 | QTR2 | 15/16 |  | 2015-05-29 | QTR4 | 14/15 | 509 | 17113122.57
| 05 | T5427 | 43174815201 | 2012-10-31 | QTR2 | 12/13 | 1 | 0 | 90 | 126 | 132 | 122.2% | 0 | -6 | 6 | 0 | 22 | 14 | 398541 | 16000 | 382541 | 398541 | 381567 | 0 | 0 | 0 | 381567 | 381567 | 99.75% | 1 | 0 | 0 | 16 | 6 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | F592733482 | ONAS CORPORATION | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 |  | 2013-06-04 | QTR4 | 12/13 | 513 | 490626
| 05 | T5464 | 42363025201 | 2014-04-30 | QTR4 | 13/14 | 1 | 0 | 250 | 322 | 322 | 106.8% | 1 | 0 | 0 | 0 | 57 | 15 | 1180000 | 50000 | 1130000 | 1180000 | 1130000 | 0 | 0 | 0 | 1130000 | 1130000 | 100% | 1 | 0 | 0 | 34 | 21 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-10-07 | QTR2 | 15/16 |  | 2015-09-03 | QTR1 | 15/16 | 514 | 1074627.1 | B0 | ACC - LUMP SUM
| 05 | T5483 | 42727915201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 200 | 273 | 273 | 105% | 1 | 0 | 0 | 0 | 63 | 10 | 2914000 | 50000 | 2864000 | 2914000 | 2885939 | 0 | 0 | 0 | 2885939 | 2771829 | 96.78% | 1 | -114111 | 0 | 37 | 26 | 0 | 10 | 1702 | 0 | 0 | 0 | 14745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 16446 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 |  | 2015-06-12 | QTR4 | 14/15 | 513 | 2978859.49 | B0 | ACC - LUMP SUM
| 05 | T5488 | 42907915201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 290 | 439 | 439 | 100% | 1 | 0 | 0 | 0 | 149 | 0 | 5354000 | 59000 | 5295000 | 5354000 | 5430627 | -11100 | 0 | -11100 | 5419527 | 5329312 | 100.6% | 1 | -90214 | 0 | 128 | 21 | 0 | 0 | 17682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17682 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-18 | QTR1 | 15/16 |  | 2015-05-29 | QTR4 | 14/15 | 509 | 5993024.89 | B0 | ACC - LUMP SUM
| 05 | T5494 | 42488715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 180 | 247 | 247 | 100% | 1 | 0 | 0 | 0 | 67 | 0 | 1795728 | 50000 | 1745728 | 1795728 | 1805364 | 0 | 0 | 0 | 1805364 | 1760006 | 100.8% | 1 | -45358 | 0 | 46 | 21 | 0 | 0 | 5154 | 0 | 0 | 0 | 24811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29965 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 |  | 2015-05-11 | QTR4 | 14/15 | 514 | 1761956.22 | B0 | ACC - LUMP SUM
| 05 | T5495 | 42886715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 1 | 300 | 328 | 303 | 91.67% | 1 | 25 | 0 | 0 | 28 | 0 | 6951000 | 72000 | 6879000 | 6886782 | 6967320 | 0 | 0 | 0 | 6967320 | 6782907 | 98.6% | 1 | -184413 | -64218 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -72353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -64218 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 |  | 2015-06-30 | QTR4 | 14/15 | 509 | 7479522.66 | B0 | ACC - LUMP SUM
| 05 | T5501 | 42886215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 110 | 176 | 176 | 100% | 1 | 0 | 0 | 0 | 66 | 0 | 2189795 | 50000 | 2139795 | 2189795 | 2201353 | 0 | 0 | 0 | 2201353 | 2169152 | 101.4% | 1 | -32201 | 0 | 42 | 24 | 0 | 0 | 54576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54576 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 |  | 2015-04-24 | QTR4 | 14/15 | 507 | 2211253.07 | B0 | ACC - LUMP SUM
| 05 | T5503 | 42868815201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 220 | 263 | 262 | 106.4% | 1 | 1 | 0 | 0 | 29 | 14 | 2402000 | 50000 | 2352000 | 2402000 | 2340586 | 0 | 0 | 0 | 2340586 | 2178963 | 92.64% | 1 | -161623 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 45453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 45453 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2015-11-30 | QTR2 | 15/16 |  | 2015-10-09 | QTR2 | 15/16 | 513 | 2568891.1 | B0 | ACC - LUMP SUM
| 05 | T5518 | 43471315201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 120 | 137 | 127 | 91.67% | 1 | 10 | 0 | 0 | 17 | 0 | 813663 | 46000 | 767663 | 813663 | 766183 | 0 | 0 | 0 | 766183 | 766183 | 99.81% | 1 | 0 | 0 | 12 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-12-15 | QTR2 | 15/16 |  | 2015-10-01 | QTR2 | 15/16 | 507 | 994320
| 05 | T5520 | 23867825201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 118 | 129 | 106 | 80.51% | 1 | 23 | 0 | 0 | 11 | 0 | 544771 | 36000 | 508771 | 536238 | 524085 | 0 | 0 | 0 | 524085 | 520797 | 102.4% | 1 | -3288 | -8533 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1651 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 |  | 2015-06-01 | QTR4 | 14/15 | 512 | 761207.45
| 05 | T5539 | 43471215201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 120 | 130 | 130 | 100% | 1 | 0 | 0 | 0 | 10 | 0 | 1710446 | 50000 | 1660446 | 1710446 | 1675126 | 0 | 0 | 0 | 1675126 | 1675126 | 100.9% | 1 | 0 | 0 | 5 | 5 | 0 | 0 | 16193 | 0 | 0 | 0 | 2170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18363 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2015-12-23 | QTR2 | 15/16 |  | 2015-10-05 | QTR2 | 15/16 | 513 | 2082709.85
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 16 | 30 | 39 | 5128 | 6658 | 6861 | 87.5% | 14 | -203 | 262 | 0 | 1007 | 523 | 102197606 | 1079000 | 101118606 | 104437169 | 103704447 | -11100 | 0 | -11100 | 103693347 | 102626787 | 100% | 16 | -1066559 | 2239563 | 675 | 301 | 0 | 56 | 934129 | 38168 | 0 | 135 | 867276 | 17371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 1387422 | 169381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 60365 | 38891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -463188 | 0 | 0 | 523 | 2786003 | 263810
| 05 | E5L71 | 41299445201 | 2009-02-23 | QTR3 | 08/09 | 15 | 55 | 810 | 1383 | 1383 | 162.5% | 0 | 0 | 0 | 0 | 67 | 506 | 163288700 | 450000 | 162838700 | 196216668 | 195534566 | 0 | 2601667 | 2601667 | 198136233 | 169140051 | 103.9% | 1 | -28996182 | 32927968 | 26 | 41 | 0 | 0 | 13525802 | 50599 | 0 | 0 | 8209344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506 | 10832312 | 492992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506 | 32675391 | 543591 | F261605378 | ARCHER WESTERN CONTRACTORS-RAIL | N/A | N/A | N/A | N/A | 2015-11-17 | QTR2 | 15/16 |  | 2015-04-17 | QTR4 | 14/15 | 507 | 0 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 05 | E5R02 | 41307215201 | 2011-10-13 | QTR2 | 11/12 | 1 | 2 | 821 | 1119 | 1120 | 109.3% | 1 | -1 | 1 | 0 | 223 | 75 | 51759000 | 150000 | 51609000 | 51745315 | 51437545 | 0 | 0 | 0 | 51437545 | 51645443 | 100.1% | 1 | 207898 | -13685 | 190 | 33 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 35645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13685 | 0 | 0 | 75 | 21960 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-10-23 | QTR2 | 15/16 |  | 2015-01-24 | QTR3 | 14/15 | 514 | 55948237 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5R52 | 23827565201 | 2012-09-27 | QTR1 | 12/13 | 2 | 8 | 685 | 1010 | 1009 | 123.4% | 0 | 1 | 0 | 0 | 164 | 161 | 23633000 | 150000 | 23483000 | 24988747 | 25103249 | 0 | 0 | 0 | 25103249 | 24880177 | 105.9% | 1 | -223072 | 1355747 | 126 | 38 | 0 | 161 | 1413568 | 0 | 0 | 0 | 50450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1486965 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-12-02 | QTR2 | 15/16 |  | 2015-08-31 | QTR1 | 15/16 | 507 | 32557148 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 05 | E5W28 | 41499925201 | 2014-05-06 | QTR4 | 13/14 | 1 | 1 | 100 | 127 | 125 | 113% | 1 | 2 | 0 | 0 | 12 | 15 | 260959 | 11000 | 249959 | 242155 | 231155 | 0 | 0 | 0 | 231155 | 231155 | 92.48% | 1 | 0 | -18805 | 3 | 9 | 0 | 0 | 0 | 0 | 0 | 15 | -18805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -18805 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2015-09-08 | QTR1 | 15/16 |  | 2015-04-15 | QTR4 | 14/15 | 509 | 250000
| 05 | E5W30 | 43214919201 | 2014-02-18 | QTR3 | 13/14 | 1 | 0 | 365 | 380 | 380 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 3585585 | 50000 | 3535585 | 3585585 | 3535585 | 0 | 0 | 0 | 3535585 | 0 | 0% | 1 | -3535585 | 0 | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-07-10 | QTR1 | 15/16 |  | 2015-05-29 | QTR4 | 14/15 | 509 | 3478319.3 | A3 | ICC - DESIGN/BUILD - MINOR
| 05 | E5W57 | 41299435214 | 2014-06-03 | QTR4 | 13/14 | 1 | 2 | 360 | 370 | 359 | 96.94% | 1 | 11 | 0 | 0 | 10 | 0 | 1657000 | 50000 | 1607000 | 1757000 | 1745808 | 0 | 0 | 0 | 1745808 | 1745490 | 108.6% | 1 | -318 | 100000 | 2 | 8 | 0 | 0 | 35063 | 0 | 0 | 0 | 105738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140801 | 0 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2015-12-02 | QTR2 | 15/16 |  | 2015-09-02 | QTR1 | 15/16 | 509 | 2729000 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE
| 05 | E5W68 | 24099295201 | 2014-12-02 | QTR2 | 14/15 | 2 | 0 | 120 | 124 | 121 | 97.5% | 1 | 3 | 0 | 0 | 4 | 0 | 518519 | 21000 | 497519 | 518519 | 502367 | 0 | 0 | 0 | 502367 | 502367 | 101% | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2974 | 0 | 0 | 0 | 3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-07-28 | QTR1 | 15/16 |  | 2015-07-14 | QTR1 | 15/16 | 513 | 460954.46
| 05 | E5W73 | 43524315201 | 2015-01-06 | QTR3 | 14/15 | 1 | 0 | 150 | 193 | 176 | 94.67% | 1 | 17 | 0 | 0 | 43 | 0 | 149000 | 5000 | 144000 | 149000 | 148500 | 0 | 0 | 0 | 148500 | 148500 | 103.1% | 1 | 0 | 0 | 25 | 9 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | F900605972 | GENESIS CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-11-13 | QTR2 | 15/16 |  | 2015-10-25 | QTR2 | 15/16 | 514 | 230960.1
| 05 | E5W75 | 43528315201 | 2015-02-03 | QTR3 | 14/15 | 1 | 0 | 150 | 158 | 124 | 77.33% | 1 | 34 | 0 | 0 | 8 | 0 | 557571 | 29000 | 528571 | 557571 | 494639 | 0 | 0 | 0 | 494639 | 494639 | 93.58% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-12-10 | QTR2 | 15/16 |  | 2015-12-01 | QTR2 | 15/16 | 514 | 721944
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 9 | 25 | 68 | 3561 | 4864 | 4797 | 77.78% | 7 | 67 | 1 | 0 | 546 | 757 | 245409334 | 916000 | 244493334 | 279760560 | 278733414 | 0 | 2601667 | 2601667 | 281335081 | 248787822 | 100% | 9 | -32547259 | 34351225 | 380 | 157 | 0 | 161 | 14981907 | 50599 | 0 | 45 | 8349753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 10890904 | 492992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13685 | 0 | 0 | 757 | 34316812 | 543591
| District 05 Totals |  |  |  |  | 25 | 55 | 107 | 8689 | 11522 | 11658 | 84% | 21 | -136 | 263 | 0 | 1553 | 1280 | 347606940 | 1995000 | 345611940 | 384197729 | 382437861 | -11100 | 2601667 | 2590567 | 385028428 | 351414609 | 100% | 25 | -33613818 | 36590788 | 1055 | 458 | 0 | 217 | 15916036 | 88767 | 0 | 180 | 9217029 | 17371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826 | 12278326 | 662373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 168298 | 38891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -476873 | 0 | 0 | 1280 | 37102815 | 807401
| 06 | T6207 | 41984815201 | 2013-05-22 | QTR4 | 12/13 | 3 | 5 | 280 | 396 | 396 | 118.6% | 1 | 0 | 0 | 0 | 74 | 42 | 6954601 | 80000 | 6874601 | 7631613 | 7814383 | 0 | 0 | 0 | 7814383 | 7814501 | 113.7% | 0 | 117 | 677012 | 49 | 15 | 10 | 0 | 192852 | 0 | 0 | 42 | 499242 | 19532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 42 | 692093 | 19532 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 |  | 2015-02-26 | QTR3 | 14/15 | 606 | 8225852.05
| 06 | T6278 | 24994115201 | 2012-05-23 | QTR4 | 11/12 | 4 | 6 | 650 | 1028 | 1028 | 119.1% | 1 | 0 | 0 | 0 | 254 | 124 | 14358568 | 211699 | 14146869 | 13941778 | 14063237 | 0 | 0 | 0 | 14063237 | 13981485 | 98.83% | 1 | -81752 | -416790 | 215 | 39 | 0 | 69 | 338260 | 0 | 0 | 0 | 2917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198178 | 6413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | -823116 | 0 | 0 | 124 | -283761 | 6413 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2015-09-22 | QTR1 | 15/16 |  | 2015-07-11 | QTR1 | 15/16 | 606 | 12500128.6
| 06 | T6308 | 42751315201 | 2013-06-19 | QTR4 | 12/13 | 3 | 2 | 280 | 454 | 473 | 147.9% | 0 | -19 | 19 | 0 | 82 | 92 | 3950337 | 50000 | 3900337 | 4058444 | 4025547 | -45106 | 0 | -45106 | 3980441 | 3968548 | 101.7% | 1 | -11893 | 108107 | 40 | 19 | 0 | 92 | 72303 | 17559 | 14 | 0 | 23094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 92 | 153504 | 17559 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-12-07 | QTR2 | 15/16 |  | 2015-05-08 | QTR4 | 14/15 | 606 | 3555731.5
| 06 | T6322 | 42750525201 | 2013-09-25 | QTR1 | 13/14 | 4 | 2 | 240 | 450 | 450 | 117.5% | 1 | 0 | 0 | 0 | 210 | 0 | 2272423 | 51180 | 2221243 | 2348653 | 2183494 | 0 | 0 | 0 | 2183494 | 2177671 | 98.04% | 1 | -5822 | 76230 | 121 | 47 | 0 | 0 | 34580 | 0 | 42 | 0 | 65393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 99973 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-09-25 | QTR1 | 15/16 |  | 2015-07-28 | QTR1 | 15/16 | 606 | 2206205.25
| 06 | T6324 | 42913615201 | 2013-09-25 | QTR1 | 13/14 | 2 | 2 | 260 | 410 | 407 | 110.4% | 1 | 3 | 0 | 0 | 150 | 0 | 3959132 | 51415 | 3907717 | 4129233 | 4133336 | 0 | 0 | 0 | 4133336 | 4124281 | 105.5% | 1 | -9055 | 170101 | 105 | 15 | 0 | 0 | 3694 | 0 | 30 | 0 | 157988 | 70393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 184274 | 70393 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-15 | QTR1 | 15/16 |  | 2015-04-07 | QTR4 | 14/15 | 606 | 4168713.7
| 06 | T6327 | 43080515201 | 2014-03-26 | QTR3 | 13/14 | 6 | 0 | 280 | 368 | 366 | 99.29% | 1 | 2 | 0 | 0 | 88 | 0 | 4029465 | 50120 | 3979345 | 4029465 | 3868532 | 0 | 0 | 0 | 3868532 | 3761105 | 94.52% | 1 | -107427 | 0 | 74 | 14 | 0 | 0 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16021 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 |  | 2015-08-04 | QTR1 | 15/16 | 606 | 4215348.73 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6351 | 42904315201 | 2014-02-05 | QTR3 | 13/14 | 3 | 0 | 180 | 241 | 241 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 643250 | 39250 | 604000 | 643250 | 597697 | 0 | 0 | 0 | 597697 | 597697 | 98.96% | 1 | 0 | 0 | 50 | 11 | 0 | 0 | 7236 | 0 | 0 | 0 | 8819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16056 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-17 | QTR1 | 15/16 |  | 2015-05-06 | QTR4 | 14/15 | 606 | 824250 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 06 | T6355 | 42902115201 | 2014-05-21 | QTR4 | 13/14 | 2 | 0 | 160 | 194 | 194 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1061111 | 50130 | 1010981 | 1061111 | 1066049 | 0 | 0 | 0 | 1066049 | 1066049 | 105.4% | 1 | 0 | 0 | 23 | 11 | 0 | 0 | 32501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49048 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-24 | QTR1 | 15/16 |  | 2015-06-22 | QTR4 | 14/15 | 606 | 1021385.13 | B0 | ACC - LUMP SUM
| 06 | T6361 | 43003115201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 150 | 191 | 187 | 97.33% | 1 | 4 | 0 | 0 | 41 | 0 | 327561 | 14958 | 312603 | 327561 | 279990 | 0 | 0 | 0 | 279990 | 279933 | 89.55% | 1 | -57 | 0 | 36 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263976898 | AMROAD LLC | N/A | N/A | N/A | N/A | 2015-09-24 | QTR1 | 15/16 |  | 2015-07-31 | QTR1 | 15/16 | 606 | 306614
| 06 | T6363 | 42751515201 | 2013-05-22 | QTR4 | 12/13 | 1 | 5 | 350 | 521 | 521 | 109.7% | 1 | 0 | 0 | 0 | 171 | 0 | 5378636 | 50000 | 5328636 | 5591336 | 6965131 | 0 | 0 | 0 | 6965131 | 6964220 | 130.7% | 0 | -911 | 212700 | 97 | 40 | 0 | 0 | 415000 | 0 | 34 | 0 | 152786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 45540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -403000 | 0 | 34 | 0 | 218326 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 |  | 2015-02-18 | QTR3 | 14/15 | 606 | 4504473.9
| 06 | T6368 | 43003315201 | 2014-07-30 | QTR1 | 14/15 | 1 | 1 | 170 | 172 | 137 | 79.41% | 1 | 35 | 0 | 0 | 2 | 0 | 619197 | 29000 | 590197 | 643584 | 598711 | 0 | 0 | 0 | 598711 | 598703 | 101.4% | 1 | -8 | 24387 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 24387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24387 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2015-07-10 | QTR1 | 15/16 |  | 2015-06-04 | QTR4 | 14/15 | 606 | 631340
| 06 | T6369 | 43081915201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 120 | 180 | 199 | 128.3% | 0 | -19 | 19 | 0 | 45 | 15 | 896920 | 46528 | 850392 | 896920 | 810742 | -33098 | 0 | -33098 | 777644 | 777644 | 91.45% | 1 | 0 | 0 | 43 | 2 | 0 | 15 | 13883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14481 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 |  | 2015-09-09 | QTR1 | 15/16 | 606 | 973033.4
| 06 | T6370 | 42913715201 | 2014-08-27 | QTR1 | 14/15 | 3 | 1 | 140 | 221 | 221 | 100% | 1 | 0 | 0 | 0 | 81 | 0 | 1463328 | 59721 | 1403607 | 1519911 | 1478859 | 0 | 0 | 0 | 1478859 | 1424599 | 101.5% | 1 | -54260 | 56583 | 77 | 4 | 0 | 0 | 56583 | 0 | 0 | 0 | 5021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65820 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-11-18 | QTR2 | 15/16 |  | 2015-09-10 | QTR1 | 15/16 | 606 | 1605781.15
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 13 | 34 | 24 | 3260 | 4826 | 4820 | 84.62% | 11 | 6 | 38 | 0 | 1293 | 273 | 45914529 | 784001 | 45130528 | 46822859 | 47885708 | -78204 | 0 | -78204 | 47807504 | 47536436 | 84.62% | 11 | -271068 | 908330 | 930 | 224 | 10 | 176 | 1168564 | 17559 | 120 | 42 | 939647 | 89925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 360128 | 6413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | -1226116 | 0 | 139 | 273 | 1250222 | 113897
| 06 | E6G56 | 42611915201 | 2013-01-31 | QTR3 | 12/13 | 1 | 0 | 560 | 775 | 774 | 104.8% | 1 | 1 | 0 | 0 | 215 | 0 | 4988310 | 58000 | 4930310 | 4988310 | 4865434 | 0 | 0 | 0 | 4865434 | 4865434 | 98.68% | 1 | 0 | 0 | 152 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2015-08-03 | QTR1 | 15/16 |  | 2015-07-02 | QTR1 | 15/16 | 606 | 5875815.5
| 06 | E6H34 | 42560035201 | 2013-06-27 | QTR4 | 12/13 | 2 | 9 | 240 | 411 | 411 | 152.9% | 0 | 0 | 0 | 0 | 171 | 0 | 6337856 | 59110 | 6278746 | 7490311 | 7429547 | 0 | 0 | 0 | 7429547 | 7303699 | 116.3% | 0 | -125847 | 1152455 | 27 | 17 | 104 | 0 | 168081 | 139232 | 23 | 0 | 976488 | 435329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 0 | 1162568 | 574561 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-12-09 | QTR2 | 15/16 |  | 2015-06-19 | QTR4 | 14/15 | 606 | 5970124.1
| 06 | E6H59 | 42999915201 | 2014-03-27 | QTR3 | 13/14 | 1 | 0 | 350 | 393 | 353 | 88.57% | 1 | 40 | 0 | 0 | 43 | 0 | 1579746 | 50000 | 1529746 | 1579746 | 1465179 | 0 | 0 | 0 | 1465179 | 1465179 | 95.78% | 1 | 0 | 0 | 24 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 |  | 2015-08-20 | QTR1 | 15/16 | 606 | 2298506.5 | B0 | ACC - LUMP SUM
| 06 | E6H61 | 43119215201 | 2014-06-12 | QTR4 | 13/14 | 1 | 0 | 280 | 317 | 317 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 838500 | 40300 | 798200 | 838500 | 763060 | 0 | 0 | 0 | 763060 | 763060 | 95.6% | 1 | 0 | 0 | 18 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 |  | 2015-08-11 | QTR1 | 15/16 | 606 | 850347
| 06 | E6I14 | 43209815201 | 2014-02-27 | QTR3 | 13/14 | 1 | 0 | 120 | 234 | 198 | 90% | 1 | 36 | 0 | 0 | 114 | 0 | 328706 | 17632 | 311074 | 328706 | 320865 | 0 | 0 | 0 | 320865 | 320865 | 103.1% | 1 | 0 | 0 | 76 | 14 | 24 | 0 | 9791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 9791 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 |  | 2015-06-25 | QTR4 | 14/15 | 606 | 370268.95 | B0 | ACC - LUMP SUM
| 06 | E6I33 | 43067015201 | 2015-02-26 | QTR3 | 14/15 | 1 | 0 | 140 | 156 | 148 | 94.29% | 1 | 8 | 0 | 0 | 16 | 0 | 1219000 | 50000 | 1169000 | 1219000 | 1179457 | 0 | 0 | 0 | 1179457 | 1177974 | 100.8% | 1 | -1484 | 0 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 16577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16577 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-12-23 | QTR2 | 15/16 |  | 2015-11-23 | QTR2 | 15/16 | 606 | 1266281 | B0 | ACC - LUMP SUM
| 06 | E6I57 | 43119015201 | 2014-09-25 | QTR1 | 14/15 | 1 | 0 | 120 | 138 | 138 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 619046 | 39934 | 579112 | 619046 | 562195 | 0 | 0 | 0 | 562195 | 562195 | 97.08% | 1 | 0 | 0 | 15 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-09-23 | QTR1 | 15/16 |  | 2015-07-03 | QTR1 | 15/16 | 606 | 838614
| 06 | E6I58 | 43119415201 | 2014-08-28 | QTR1 | 14/15 | 1 | 0 | 120 | 162 | 162 | 117.5% | 1 | 0 | 0 | 0 | 42 | 0 | 931395 | 49000 | 882395 | 931395 | 872317 | 0 | 0 | 0 | 872317 | 872317 | 98.86% | 1 | 0 | 0 | 16 | 5 | 21 | 0 | 19884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 19884 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 |  | 2015-08-11 | QTR1 | 15/16 | 606 | 978848.5
| 06 | E6I77 | 24994175201 | 2014-08-28 | QTR1 | 14/15 | 1 | 0 | 160 | 194 | 194 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1198756 | 50000 | 1148756 | 1198756 | 1094981 | 0 | 0 | 0 | 1094981 | 1094981 | 95.32% | 1 | 0 | 0 | 31 | 3 | 0 | 0 | 1200 | 0 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11878 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-07-17 | QTR1 | 15/16 | 606 | 1268938.13
| 06 | E6I78 | 43081615201 | 2014-07-31 | QTR1 | 14/15 | 2 | 0 | 140 | 173 | 173 | 105.7% | 1 | 0 | 0 | 0 | 25 | 8 | 1207213 | 51325 | 1155888 | 1207213 | 1139099 | 0 | 0 | 0 | 1139099 | 1129248 | 97.7% | 1 | -9851 | 0 | 12 | 13 | 0 | 0 | 0 | 0 | 0 | 3 | 5483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6468 | 0 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 |  | 2015-04-24 | QTR4 | 14/15 | 606 | 1208779.95
| 06 | E6I83 | 43081415201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 65 | 96 | 93 | 95.38% | 1 | 3 | 0 | 0 | 31 | 0 | 94720 | 6040 | 88680 | 94720 | 88652 | 0 | 0 | 0 | 88652 | 88652 | 99.97% | 1 | 0 | 0 | 28 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-07-14 | QTR1 | 15/16 | 606 | 126847 | B0 | ACC - LUMP SUM
| 06 | E6I85 | 41774079201 | 2014-03-27 | QTR3 | 13/14 | 1 | 0 | 300 | 346 | 346 | 108% | 1 | 0 | 0 | 0 | 46 | 0 | 502650 | 32313 | 470337 | 502650 | 470337 | 0 | 0 | 0 | 470337 | 0 | 0% | 1 | -470337 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 |  | 2015-05-13 | QTR4 | 14/15 | 606 | 678578.25 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6I87 | 42934415201 | 2014-10-30 | QTR2 | 14/15 | 3 | 0 | 170 | 192 | 190 | 98.82% | 1 | 2 | 0 | 0 | 22 | 0 | 1872759 | 101085 | 1771674 | 1872759 | 1693855 | 0 | 0 | 0 | 1693855 | 1636257 | 92.36% | 1 | -57598 | 0 | 20 | 2 | 0 | 0 | 1943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-09-17 | QTR1 | 15/16 |  | 2015-07-29 | QTR1 | 15/16 | 606 | 1934017.45
| 06 | E6J40 | 43590015201 | 2015-01-29 | QTR3 | 14/15 | 1 | 0 | 80 | 83 | 75 | 90% | 1 | 8 | 0 | 0 | 3 | 0 | 248698 | 11846 | 236852 | 248698 | 217030 | 0 | 0 | 0 | 217030 | 217030 | 91.63% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-09-25 | QTR1 | 15/16 |  | 2015-09-11 | QTR1 | 15/16 | 606 | 248762.6
| 06 | E6J70 | 43717615201 | 2015-06-11 | QTR4 | 14/15 | 1 | 0 | 45 | 52 | 43 | 80% | 1 | 9 | 0 | 0 | 7 | 0 | 149934 | 7328 | 142606 | 149934 | 142606 | 0 | 0 | 0 | 142606 | 142606 | 100% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2015-11-16 | QTR2 | 15/16 |  | 2015-10-26 | QTR2 | 15/16 | 606 | 153889 | B0 | ACC - LUMP SUM
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 15 | 19 | 9 | 2890 | 3722 | 3615 | 93.33% | 14 | 107 | 0 | 0 | 824 | 8 | 22117289 | 623913 | 21493376 | 23269744 | 22304614 | 0 | 0 | 0 | 22304614 | 21639497 | 93.33% | 14 | -665117 | 1152455 | 439 | 161 | 149 | 0 | 200899 | 139232 | 47 | 3 | 1002848 | 435329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24377 | 0 | 0 | 5 | 985 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 8 | 1229109 | 574561
| District 06 Totals |  |  |  |  | 28 | 53 | 33 | 6150 | 8548 | 8435 | 89.29% | 25 | 113 | 38 | 0 | 2117 | 281 | 68031818 | 1407914 | 66623904 | 70092603 | 70190322 | -78204 | 0 | -78204 | 70112118 | 69175933 | 89.29% | 25 | -936185 | 2060785 | 1369 | 385 | 159 | 176 | 1369463 | 156791 | 167 | 45 | 1942495 | 525254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 384505 | 6413 | 0 | 5 | 985 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | -1226116 | 0 | 363 | 281 | 2479331 | 688458
| 07 | T7307 | 42715215201 | 2012-12-05 | QTR2 | 12/13 | 1 | 0 | 615 | 785 | 785 | 100.7% | 1 | 0 | 0 | 0 | 168 | 2 | 14844440 | 135000 | 14709440 | 14844440 | 15019838 | 0 | 0 | 0 | 15019838 | 14905397 | 101.3% | 1 | -114441 | 0 | 142 | 24 | 2 | 2 | 53880 | 0 | 0 | 0 | 6839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 60719 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-10-15 | QTR2 | 15/16 |  | 2015-04-06 | QTR4 | 14/15 | 798 | 15370623
| 07 | T7325 | 42900515201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 350 | 453 | 453 | 105.7% | 1 | 0 | 0 | 0 | 83 | 20 | 15491284 | 120000 | 15371284 | 16150823 | 16100076 | 0 | 0 | 0 | 16100076 | 16143898 | 105% | 1 | 43822 | 659540 | 60 | 23 | 0 | 1 | 10092 | 0 | 0 | 19 | 662533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 683477 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-08-21 | QTR1 | 15/16 |  | 2014-11-21 | QTR2 | 14/15 | 709 | 16955600
| 07 | T7329 | 42907325201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 270 | 369 | 369 | 100% | 1 | 0 | 0 | 0 | 99 | 0 | 5019226 | 50000 | 4969226 | 5019226 | 4985077 | 0 | 0 | 0 | 4985077 | 4951447 | 99.64% | 1 | -33631 | 0 | 82 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 18054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18054 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-07-23 | QTR1 | 15/16 |  | 2015-04-01 | QTR4 | 14/15 | 717 | 4751500 | B0 | ACC - LUMP SUM
| 07 | T7334 | 42455015201 | 2013-08-28 | QTR1 | 13/14 | 1 | 2 | 385 | 518 | 518 | 116.9% | 1 | 0 | 0 | 0 | 68 | 65 | 8989959 | 84500 | 8905459 | 9299052 | 9312842 | -3600 | 0 | -3600 | 9309242 | 9306402 | 104.5% | 1 | -2840 | 309093 | 39 | 29 | 0 | 0 | 51532 | 0 | 0 | 65 | 309093 | 80331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 360626 | 80331 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-11-10 | QTR2 | 15/16 |  | 2015-04-01 | QTR4 | 14/15 | 717 | 8578716.51
| 07 | T7337 | 42907315201 | 2013-10-30 | QTR2 | 13/14 | 2 | 2 | 200 | 300 | 300 | 115% | 1 | 0 | 0 | 0 | 70 | 30 | 4224761 | 50000 | 4174761 | 4277589 | 4397983 | 0 | 0 | 0 | 4397983 | 4415486 | 105.8% | 1 | 17503 | 52828 | 59 | 11 | 0 | 30 | 33461 | 3083 | 0 | 0 | 5193 | 1819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38654 | 4902 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-08 | QTR2 | 15/16 |  | 2014-12-23 | QTR2 | 14/15 | 717 | 4480000
| 07 | T7340 | 42715415201 | 2014-04-30 | QTR4 | 13/14 | 2 | 0 | 150 | 188 | 187 | 99.33% | 1 | 1 | 0 | 0 | 38 | 0 | 1688000 | 50000 | 1638000 | 1688000 | 1644638 | 0 | 0 | 0 | 1644638 | 1606582 | 98.08% | 1 | -38056 | 0 | 25 | 13 | 0 | 0 | 9287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9287 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 |  | 2015-03-27 | QTR3 | 14/15 | 798 | 2156800 | B0 | ACC - LUMP SUM
| 07 | T7341 | 42896115201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 320 | 383 | 381 | 99.38% | 1 | 2 | 0 | 0 | 63 | 0 | 5790872 | 55000 | 5735872 | 5790872 | 5714657 | 0 | 0 | 0 | 5714657 | 5660340 | 98.68% | 1 | -54316 | 0 | 38 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-09-15 | QTR1 | 15/16 |  | 2015-06-17 | QTR4 | 14/15 | 717 | 6079410
| 07 | T7343 | 42308815202 | 2014-05-21 | QTR4 | 13/14 | 4 | 0 | 270 | 304 | 267 | 86.3% | 1 | 37 | 0 | 0 | 34 | 0 | 4553063 | 50000 | 4503063 | 4553063 | 4196722 | 0 | 0 | 0 | 4196722 | 4140383 | 91.95% | 1 | -56339 | 0 | 23 | 11 | 0 | 0 | 15813 | 0 | 0 | 0 | 3916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19729 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 |  | 2015-05-11 | QTR4 | 14/15 | 717 | 4416500
| 07 | T7358 | 43140415201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 110 | 136 | 134 | 98.18% | 1 | 2 | 0 | 0 | 26 | 0 | 1033200 | 45000 | 988200 | 1033200 | 920104 | 0 | 0 | 0 | 920104 | 920104 | 93.11% | 1 | 0 | 0 | 2 | 24 | 0 | 0 | 20461 | 0 | 0 | 0 | 742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21202 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-10-22 | QTR2 | 15/16 |  | 2015-07-13 | QTR1 | 15/16 | 709 | 1010220 | B0 | ACC - LUMP SUM
| 07 | T7361 | 42906115202 | 2014-12-03 | QTR2 | 14/15 | 2 | 1 | 135 | 164 | 164 | 100% | 1 | 0 | 0 | 0 | 29 | 0 | 1465000 | 50000 | 1415000 | 1494392 | 1504704 | 0 | 0 | 0 | 1504704 | 1462449 | 103.4% | 1 | -42254 | 29392 | 27 | 2 | 0 | 0 | 23469 | 0 | 0 | 0 | 51199 | 11673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74668 | 11673 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-11-05 | QTR2 | 15/16 |  | 2015-08-28 | QTR1 | 15/16 | 717 | 1300371 | B0 | ACC - LUMP SUM
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 10 | 16 | 13 | 2805 | 3600 | 3558 | 100% | 10 | 42 | 0 | 0 | 678 | 117 | 63099805 | 689500 | 62410305 | 64150657 | 63796641 | -3600 | 0 | -3600 | 63793041 | 63512488 | 100% | 10 | -280552 | 1050853 | 497 | 179 | 2 | 33 | 217995 | 3083 | 0 | 84 | 1057569 | 93823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 117 | 1286416 | 96906
| 07 | E7I67 | 42893615201 | 2014-06-11 | QTR4 | 13/14 | 1 | 0 | 195 | 284 | 281 | 98.46% | 1 | 3 | 0 | 0 | 89 | 0 | 3868793 | 50000 | 3818793 | 3868793 | 3814687 | 0 | 0 | 0 | 3814687 | 3688104 | 96.58% | 1 | -126583 | 0 | 30 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-11-05 | QTR2 | 15/16 |  | 2015-08-17 | QTR1 | 15/16 | 717 | 3735600 | B0 | ACC - LUMP SUM
| 07 | E7I81 | 43113715201 | 2014-06-11 | QTR4 | 13/14 | 1 | 0 | 120 | 157 | 156 | 99.17% | 1 | 1 | 0 | 0 | 37 | 0 | 1095029 | 47000 | 1048029 | 1095029 | 997607 | 0 | 0 | 0 | 997607 | 997607 | 95.19% | 1 | 0 | 0 | 23 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-10-12 | QTR2 | 15/16 |  | 2015-02-10 | QTR3 | 14/15 | 717 | 992000
| 07 | E7I96 | 40625565201 | 2014-06-11 | QTR4 | 13/14 | 1 | 0 | 260 | 305 | 305 | 106.5% | 1 | 0 | 0 | 0 | 75 | -30 | 1992240 | 50000 | 1942240 | 1992240 | 1975737 | 0 | 0 | 0 | 1975737 | 1975126 | 101.7% | 1 | -611 | 0 | 15 | 13 | 47 | -30 | 3493 | 0 | 0 | 0 | 6964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | -30 | 10457 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-10-29 | QTR2 | 15/16 |  | 2015-09-03 | QTR1 | 15/16 | 714 | 2322106
| 07 | E7J96 | 43066115201 | 2014-11-26 | QTR2 | 14/15 | 1 | 0 | 150 | 183 | 183 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 2030000 | 50000 | 1980000 | 2030000 | 1980915 | 0 | 0 | 0 | 1980915 | 1934577 | 97.71% | 1 | -46338 | 0 | 26 | 7 | 0 | 0 | 1006 | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9760 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-29 | QTR1 | 15/16 |  | 2015-08-19 | QTR1 | 15/16 | 709 | 1984600 | B0 | ACC - LUMP SUM
| 07 | E7J98 | 42907715201 | 2014-12-10 | QTR2 | 14/15 | 1 | 0 | 130 | 143 | 131 | 90.77% | 1 | 12 | 0 | 0 | 13 | 0 | 1378500 | 50000 | 1328500 | 1378500 | 1371830 | 0 | 0 | 0 | 1371830 | 1336400 | 100.6% | 1 | -35430 | 0 | 11 | 2 | 0 | 0 | 36819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36819 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-10-16 | QTR2 | 15/16 |  | 2015-06-29 | QTR4 | 14/15 | 717 | 1271900 | B0 | ACC - LUMP SUM
| 07 | E7K00 | 42907215201 | 2015-02-11 | QTR3 | 14/15 | 1 | 0 | 80 | 95 | 95 | 101.2% | 1 | 0 | 0 | 0 | 14 | 1 | 412263 | 19000 | 393263 | 412263 | 394582 | 0 | 0 | 0 | 394582 | 394582 | 100.3% | 1 | 0 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1320 | 0 | F593759317 | CHEYENNE ASPHALT INCORPORATED | N/A | N/A | N/A | N/A | 2015-11-09 | QTR2 | 15/16 |  | 2015-07-17 | QTR1 | 15/16 | 717 | 398900 | B0 | ACC - LUMP SUM
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 6 | 6 | 0 | 935 | 1167 | 1151 | 100% | 6 | 16 | 0 | 0 | 261 | -29 | 10776825 | 266000 | 10510825 | 10776825 | 10535358 | 0 | 0 | 0 | 10535358 | 10326396 | 100% | 6 | -208962 | 0 | 117 | 97 | 47 | -30 | 41318 | 0 | 0 | 1 | 10984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | -29 | 58356 | 0
| District 07 Totals |  |  |  |  | 16 | 22 | 13 | 3740 | 4767 | 4709 | 100% | 16 | 58 | 0 | 0 | 939 | 88 | 73876630 | 955500 | 72921130 | 74927482 | 74331999 | -3600 | 0 | -3600 | 74328399 | 73838884 | 100% | 16 | -489514 | 1050853 | 614 | 276 | 49 | 3 | 259313 | 3083 | 0 | 85 | 1068553 | 93823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10852 | 0 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 88 | 1344772 | 96906
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8L99 | 41546225202 | 2012-05-22 | QTR4 | 11/12 | 1 | 9 | 785 | 901 | 901 | 103.6% | 1 | 0 | 0 | 0 | 88 | 28 | 19914762 | 150000 | 19764762 | 20008584 | 19972782 | -154000 | 0 | -154000 | 19818782 | 19745451 | 99.9% | 1 | -73332 | 93822 | 25 | 63 | 0 | 0 | 66402 | 0 | 0 | 0 | 119752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 35659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -130930 | 0 | 0 | 28 | 90883 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-09-28 | QTR1 | 15/16 |  | 2015-02-13 | QTR3 | 14/15 | 854 | 20630726.61
| 08 | E8M05 | 43128115201 | 2013-02-25 | QTR3 | 12/13 | 2 | 6 | 667 | 783 | 781 | 105.1% | 1 | 2 | 0 | 0 | 80 | 36 | 40666800 | 150000 | 40516800 | 40884133 | 40781351 | -49500 | 0 | -49500 | 40731851 | 40551799 | 100.1% | 1 | -180052 | 217333 | 44 | 36 | 0 | 0 | -13220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 497038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -156461 | 0 | 0 | 36 | 327358 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-10-27 | QTR2 | 15/16 |  | 2015-05-22 | QTR4 | 14/15 | 854 | 36916236.02 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
| 08 | E8M77 | 40615145201 | 2013-03-26 | QTR3 | 12/13 | 2 | 4 | 645 | 777 | 730 | 105.7% | 1 | 47 | 0 | 0 | 48 | 84 | 11249740 | 150000 | 11099740 | 11481897 | 10973748 | 0 | 0 | 0 | 10973748 | 10925662 | 98.43% | 1 | -48086 | 232157 | 25 | 23 | 0 | 84 | 150630 | 103254 | 0 | 0 | 162171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 312801 | 103254 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-09-04 | QTR1 | 15/16 |  | 2015-07-07 | QTR1 | 15/16 | 854 | 11244846.35
| 08 | E8M80 | 42768515201 | 2013-05-14 | QTR4 | 12/13 | 1 | 2 | 425 | 469 | 425 | 89.65% | 1 | 44 | 0 | 0 | 44 | 0 | 6746576 | 63950 | 6682626 | 6938552 | 6915696 | 0 | 0 | 0 | 6915696 | 6919857 | 103.5% | 1 | 4160 | 191976 | 15 | 29 | 0 | 0 | 66193 | 0 | 0 | 0 | 5863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249853 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-09-14 | QTR1 | 15/16 |  | 2014-10-06 | QTR2 | 14/15 | 854 | 6459217.72
| 08 | E8M93 | 43108935201 | 2013-05-21 | QTR4 | 12/13 | 1 | 2 | 450 | 587 | 587 | 100% | 1 | 0 | 0 | 0 | 137 | 0 | 7676614 | 84515 | 7592099 | 7714483 | 7540572 | 0 | 0 | 0 | 7540572 | 7491522 | 98.68% | 1 | -49050 | 37868 | 85 | 52 | 0 | 0 | 122140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122140 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-07-07 | QTR1 | 15/16 |  | 2015-05-15 | QTR4 | 14/15 | 854 | 8536508.95
| 08 | E8N21 | 42902315201 | 2014-03-11 | QTR3 | 13/14 | 2 | 5 | 170 | 271 | 271 | 104.1% | 1 | 0 | 0 | 0 | 94 | 7 | 6573418 | 84736 | 6488682 | 6704790 | 6985687 | -3000 | 0 | -3000 | 6982687 | 6966867 | 107.4% | 1 | -15820 | 131372 | 62 | 32 | 0 | 0 | 14408 | 0 | 0 | 7 | 173176 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68650 | 0 | 0 | 0 | 8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 67841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 197374 | 5845 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-14 | QTR1 | 15/16 |  | 2015-02-09 | QTR3 | 14/15 | 854 | 8559769.2
| 08 | E8N37 | 43112315201 | 2014-06-10 | QTR4 | 13/14 | 1 | 0 | 255 | 268 | 267 | 99.61% | 1 | 1 | 0 | 0 | 13 | 0 | 383488 | 24940 | 358548 | 383488 | 358052 | 0 | 0 | 0 | 358052 | 358052 | 99.86% | 1 | 0 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1719 | 0 | F593285921 | S & D INDUSTRIAL PAINTING INC. | N/A | N/A | N/A | N/A | 2015-12-18 | QTR2 | 15/16 |  | 2015-09-28 | QTR1 | 15/16 | 854 | 523746.64
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 7 | 10 | 28 | 3397 | 4056 | 3962 | 0.002343% | 7 | 94 | 0 | 0 | 504 | 155 | 93211398 | 708141 | 92503257 | 94115927 | 93527888 | -206500 | 0 | -206500 | 93321388 | 92959210 | 100% | 7 | -362180 | 904528 | 263 | 241 | 0 | 84 | 406553 | 103254 | 0 | 7 | 460962 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 643563 | 0 | 0 | 0 | 8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 67841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287391 | 0 | 0 | 155 | 1302128 | 109099
| District 08 Totals |  |  |  |  | 7 | 10 | 28 | 3397 | 4056 | 3962 | 100% | 7 | 94 | 0 | 0 | 504 | 155 | 93211398 | 708141 | 92503257 | 94115927 | 93527888 | -206500 | 0 | -206500 | 93321388 | 92959210 | 100% | 7 | -362180 | 904528 | 263 | 241 | 0 | 84 | 406553 | 103254 | 0 | 7 | 460962 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 643563 | 0 | 0 | 0 | 8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 67841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287391 | 0 | 0 | 155 | 1302128 | 109099
| Statewide Central Let Contracts SubTotal |  |  |  |  | 103 | 167 | 221 | 26238 | 36054 | 36337 | 84.47% | 87 | -283 | 647 | 0 | 7426 | 2390 | 467809214 | 5536353 | 462272863 | 482455583 | 485408923 | -528071 | 120000 | -408071 | 485000852 | 479120809 | 90.29% | 93 | -5880042 | 14646370 | 5176 | 1707 | 30 | 715 | 6674869 | 212590 | 282 | 1152 | 11384327 | 3585587 | 0 | 0 | 0 | 0 | 0 | 0 | -31593 | 0 | 0 | 0 | 11300 | 0 | 32 | 343 | -473131 | 1245343 | 6 | 5 | 109153 | 0 | 0 | 0 | 0 | 0 | 7 | 40 | 400139 | 0 | 0 | 57 | 332334 | 310860 | 9 | 23 | 183368 | 183368 | 135 | 0 | 0 | 0 | 0 | 55 | -1888491 | 0 | 501 | 2390 | 16702267 | 5537746
| Statewide District Let Contracts SubTotal |  |  |  |  | 82 | 114 | 157 | 20188 | 25899 | 25678 | 90.24% | 74 | 221 | 373 | 0 | 4036 | 1675 | 564830261 | 4387524 | 560442737 | 605339164 | 600327096 | -299602 | 2681667 | 2382065 | 602709159 | 566836559 | 91.46% | 75 | -35739963 | 40508902 | 2398 | 1168 | 307 | 582 | 18616521 | 302699 | 116 | 356 | 10904220 | 474141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 0 | 0 | 731 | 12229982 | 698032 | 0 | 5 | 15660 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 17804 | 0 | 0 | 0 | 186202 | 0 | 0 | 1 | 28118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -425500 | 0 | 451 | 1675 | 41573850 | 1474872
| Statewide Totals |  |  |  |  | 185 | 281 | 378 | 46426 | 61953 | 62015 | 87.03% | 161 | -62 | 1020 | 0 | 11462 | 4065 | 1032639475 | 9923877 | 1022715600 | 1087794747 | 1085736019 | -827673 | 2801667 | 1973994 | 1087710011 | 1045957368 | 90.81% | 168 | -41620005 | 55155272 | 7574 | 2875 | 337 | 1297 | 25291390 | 515289 | 398 | 1508 | 22288547 | 4059728 | 0 | 0 | 0 | 0 | 0 | 0 | -31593 | 0 | 0 | 0 | 12140 | 0 | 32 | 1074 | 11756851 | 1943375 | 6 | 10 | 124813 | 0 | 0 | 0 | 0 | 0 | 35 | 40 | 417943 | 0 | 0 | 57 | 518536 | 310860 | 9 | 24 | 211486 | 183368 | 135 | 0 | 0 | 0 | 0 | 55 | -2313991 | 0 | 952 | 4065 | 58276117 | 7012618

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1J69 | 20074625201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2012-06-29 | 8819248 | 9865997 | 9845954 | 1046748.74 | 0 | 9861107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9845954 | 9861107 | 15153 | 9894002 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1J71 | 41263625201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2012-05-31 | 6703703 | 7531485 | 7530256 | 827781.72 | 0 | 7530256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7530256 | 7530256 | 0 | 638850 | A3 | ICC - DESIGN/BUILD - MINOR
1 | E1J72 | 41664925201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2012-05-17 | 54100000 | 55514659 | 55350517 | 1414659.4 | 0 | 55125629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55350517 | 55125629 | -224888 | 72523865 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1N08 | 42347115201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-06-19 | 1880948 | 1908269 | 1858269 | 27320.39 | 0 | 1834616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1858269 | 1834616 | -23653 | 1405116 | B0 | ACC - LUMP SUM
1 | E1N35 | 43496715201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2014-06-19 | 93903 | 106903 | 100206 | 12999.83 | 0 | 100206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100206 | 100206 | 0 | 71244
1 | E1N47 | 43019125201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2014-06-19 | 4346396 | 4413679 | 4400332 | 67283.26 | 0 | 4322422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4400332 | 4322422 | -77910 | 4460046 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | E1N64 | 43160515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-08-29 | 3021172 | 3021172 | 3068023 | 0 | 0 | 2921086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3068023 | 2921086 | -146936 | 3419371
1 | E1N65 | 42909615201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-10-16 | 1285754 | 1285754 | 1252542 | 0 | 0 | 1182541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252542 | 1182541 | -70001 | 1296120 | B0 | ACC - LUMP SUM
1 | E1N66 | 41787625201 | F650968383 | WHITELEAF LLC DBA TRAFFIC SOLUTIONS | N/A | N/A | N/A | N/A | 2015-06-18 | 135934 | 135934 | 127000 | 0 | 0 | 127000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127000 | 127000 | 0 | 208343 | B0 | ACC - LUMP SUM
1 | E1N67 | 43121315201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-11-20 | 660116 | 660116 | 658410 | 0 | 0 | 658410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 658410 | 658410 | 0 | 633763 | B0 | ACC - LUMP SUM
1 | E1N70 | 40826895201 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2015-01-15 | 129260 | 129260 | 124484 | 0 | 0 | 124484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124484 | 124484 | 0 | 172354 | B0 | ACC - LUMP SUM
1 | E1N71 | 43006015201 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2015-01-15 | 567387 | 567387 | 532744 | 0 | 0 | 532744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532744 | 532744 | 0 | 519187 | B0 | ACC - LUMP SUM
1 | E1N76 | 43510615201 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-11-20 | 3493285 | 3493285 | 3362358 | 0 | 80000 | 3345583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 80000 | 80000 | 3442358 | 3345583 | -96775 | 2641060 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1N96 | 42949925201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-10-16 | 229418 | 228371 | 218669 | -1047.37 | 0 | 218669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218669 | 218669 | 0 | 179059 | B0 | ACC - LUMP SUM
1 | E1O06 | 43574215201 | F650968383 | WHITELEAF LLC DBA TRAFFIC SOLUTIONS | N/A | N/A | N/A | N/A | 2014-11-20 | 140780 | 140780 | 132639 | 0 | 0 | 265277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132639 | 265277 | 132639 | 193963 | B0 | ACC - LUMP SUM
1 | E1O17 | 43642215201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2015-05-21 | 122267 | 122267 | 116216 | 0 | 0 | 116216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116216 | 116216 | 0 | 128069 | B0 | ACC - LUMP SUM
1 | E1O84 | 43494415201 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2015-07-16 | 41385 | 41385 | 38208 | 0 | 0 | 38208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38208 | 38208 | 0 | 66757 | B0 | ACC - LUMP SUM
1 | T1497 | 43003715201 | F593490202 | ALDON BOOKHARDT ROOFING INC. | N/A | N/A | N/A | N/A | 2012-03-28 | 90611 | 89035 | 88897 | -1575.84 | -43964 | 44933 | -43964 | 0 | 0 | 0 | 0 | 0 | -43964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43964 | 44933 | 44933 | 0 | 111868 | B0 | ACC - LUMP SUM
1 | T1501 | 40828635201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2012-06-20 | 14784300 | 15330267 | 14964740 | 545967.35 | 0 | 15047703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14964740 | 15047703 | 82963 | 13767014
1 | T1512 | 40826835201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2012-09-26 | 19473948 | 20142554 | 20429764 | 668606.29 | 0 | 20268347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20429764 | 20268347 | -161418 | 19967593
1 | T1527 | 41787615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2013-02-06 | 12312349 | 13258294 | 12897465 | 945944.85 | 0 | 12514104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12897465 | 12514104 | -383360 | 15340403
1 | T1541 | 42525115201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2013-06-19 | 7929564 | 8206423 | 8142299 | 276859.34 | 0 | 8010531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8142299 | 8010531 | -131769 | 7502697
1 | T1546 | 42910415201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-02-26 | 2195109 | 2159801 | 2156391 | -35307.58 | -50518 | 2085969 | -50518 | 0 | 0 | 0 | 0 | 0 | -50518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50518 | 2105873 | 2085969 | -19904 | 2641240 | B0 | ACC - LUMP SUM
1 | T1557 | 42928415201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 2509778 | 2509778 | 2520762 | 0 | 0 | 2358044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520762 | 2358044 | -162718 | 2840170 | B0 | ACC - LUMP SUM
1 | T1566 | 20010575201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2014-04-30 | 855140 | 880470 | 883951 | 25330.32 | 0 | 883951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883951 | 883951 | 0 | 1061210
1 | T1570 | 42584615201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-03-26 | 2796051 | 3242177 | 3374573 | 446125.98 | 120000 | 3324455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 3494573 | 3324455 | -170118 | 2726352 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1578 | 43086015201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2013-12-04 | 5634855 | 5727333 | 5707127 | 92478.17 | 0 | 5640992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5707127 | 5640992 | -66135 | 5433904 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1591 | 43130115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-04-30 | 7824413 | 8062184 | 7860334 | 237771.12 | 0 | 7721971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7860334 | 7721971 | -138364 | 8889524
1 | T1592 | 42729815201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 1644078 | 1668510 | 1623620 | 24432.38 | 0 | 1623620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623620 | 1623620 | 0 | 1618342 | B0:B0:B0:B:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
1 | T1594 | 43135415201 | F464740152 | CATHCART CONSTRUCTION COMPANY - FLORIDA | N/A | N/A | N/A | N/A | 2014-06-18 | 989000 | 1119395 | 1113069 | 130394.69 | 0 | 1113069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113069 | 1113069 | 0 | 857500 | B0 | ACC - LUMP SUM
1 | T1996 | 43086115201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-01-28 | 336490 | 336490 | 331697 | 0 | 0 | 331697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 331697 | 331697 | 0 | 347757 | B0 | ACC - LUMP SUM
1 | T1A05 | 42910815201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-10-29 | 2154862 | 2208421 | 2164641 | 53558.88 | 0 | 2077091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2164641 | 2077091 | -87549 | 2061296 | B0 | ACC - LUMP SUM
1 | T1A12 | 43121015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-12-03 | 3770622 | 3770622 | 3700017 | 0 | 0 | 3520482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700017 | 3520482 | -179536 | 3557077
1 | T1A14 | 43341115201 | F593339407 | TAGARELLI CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 247066 | 270085 | 250380 | 23018.51 | 0 | 250380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250380 | 250380 | 0 | 256990 | B0 | ACC - LUMP SUM
2 | E2Q76 | 42931315201 | F420429710 | DEVELOPERS SURETY AND INDEMNITY COMPANY | N/A | N/A | N/A | N/A | 2013-02-20 | 645001 | 605429 | 554900 | -39571.95 | -15320 | 539579 | -15320 | 0 | 0 | 0 | 0 | 0 | -15320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15320 | 539579 | 539579 | 0 | 892356
2 | E2Q95 | 42886915201 | F592733482 | ONAS CORPORATION | N/A | N/A | N/A | N/A | 2012-09-19 | 86971 | 96284 | 96295 | 9313.74 | -16502 | 79792 | -12886 | 0 | 0 | 0 | -3616 | 0 | -16502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16502 | 79792 | 79792 | 0 | 85580
2 | E2R18 | 42468515201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-05-23 | 8195419 | 8206705 | 8178408 | 11286.44 | 0 | 8124680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8178408 | 8124680 | -53727 | 8761555 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2R93 | 42607215201 | F650447555 | L & S CONCRETE RESTORATION INC | N/A | N/A | N/A | N/A | 2013-08-21 | 1520777 | 1520777 | 1507456 | 0 | -61280 | 1443425 | -61280 | 0 | 0 | 0 | 0 | 0 | -61280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -61280 | 1446176 | 1443425 | -2751 | 1839324
2 | E2R94 | 42822915201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-08-21 | 2445796 | 2445796 | 2450466 | 0 | 0 | 2449755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450466 | 2449755 | -711 | 2404678
2 | E2S71 | 42869515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-04-23 | 7686286 | 7580608 | 7142686 | -105678.26 | 0 | 6953829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7142686 | 6953829 | -188858 | 6348256
2 | E2S89 | 20954125201 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2014-04-23 | 1997720 | 1997720 | 2088940 | 0 | 0 | 2081779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088940 | 2081779 | -7161 | 2345342
2 | E2T03 | 42871115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2014-07-23 | 5283383 | 5283383 | 4965217 | 0 | 0 | 4630053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4965217 | 4630053 | -335164 | 4581887
2 | E2T06 | 43074715201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2014-07-23 | 205480 | 205480 | 200119 | 0 | 0 | 200119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200119 | 200119 | 0 | 167997
2 | E2T32 | 43194215201 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2014-12-10 | 1419048 | 1578817 | 1549237 | 159768.81 | 0 | 1549237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1549237 | 1549237 | 0 | 1414155
2 | T2415 | 42884215201 | F593490202 | ALDON BOOKHARDT ROOFING INC. | N/A | N/A | N/A | N/A | 2012-03-28 | 75000 | 91225 | 91225 | 16224.72 | 0 | 91225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91225 | 91225 | 0 | 93854 | B0 | ACC - LUMP SUM
2 | T2439 | 42732815201 | F592733482 | ONAS CORPORATION | N/A | N/A | N/A | N/A | 2012-09-26 | 240847 | 240847 | 224345 | 0 | -71365 | 152980 | 0 | 0 | 0 | 0 | -71365 | 0 | -71365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -71365 | 152980 | 152980 | 0 | 250711
2 | T2443 | 42698615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-02-06 | 4870523 | 4870523 | 4844339 | 0 | 0 | 4835215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4844339 | 4835215 | -9124 | 5528434
2 | T2512 | 42869015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 8787879 | 8787879 | 8967904 | 0 | 0 | 8851811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8967904 | 8851811 | -116093 | 9570319
2 | T2517 | 41695325201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-02-26 | 5124750 | 5335260 | 5663021 | 210509.74 | 0 | 5552944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5663021 | 5552944 | -110077 | 6059850
2 | T2524 | 42870915201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2014-05-07 | 3832891 | 3864530 | 3881828 | 31638.61 | -9496 | 3786451 | -9496 | 0 | 0 | 0 | 0 | 0 | -9496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9496 | 3872332 | 3786451 | -85881 | 3923781 | B0 | ACC - LUMP SUM
2 | T2527 | 42870515201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 3855596 | 3937461 | 4006951 | 81865.16 | 0 | 3890841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4006951 | 3890841 | -116110 | 3913298
2 | T2528 | 42870615201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 6187853 | 6237853 | 6218179 | 50000 | 0 | 5933793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6218179 | 5933793 | -284386 | 5027804
2 | T2529 | 42871215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 5035067 | 5035067 | 5418212 | 0 | 0 | 5280952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5418212 | 5280952 | -137260 | 5026805
2 | T2530 | 21156035201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-05-21 | 1259477 | 1284233 | 1254859 | 24756.19 | 0 | 1254859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1254859 | 1254859 | 0 | 957006
2 | T2535 | 42053145201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 1754776 | 1824298 | 1779783 | 69521.29 | 0 | 1779783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1779783 | 1779783 | 0 | 1169715 | B0 | ACC - LUMP SUM
2 | T2543 | 43055515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 1738869 | 1738869 | 1721840 | 0 | 0 | 1698982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1721840 | 1698982 | -22858 | 1963162
2 | T2544 | 42880815201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-08-27 | 7085441 | 7135441 | 7222230 | 50000 | 0 | 6861498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7222230 | 6861498 | -360732 | 5804682
2 | T2546 | 42889615201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-09-24 | 1837492 | 1861682 | 1898076 | 24189.81 | 0 | 1898076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898076 | 1898076 | 0 | 1560660
2 | T2551 | 43035225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-29 | 6221583 | 6221583 | 6254748 | 0 | 0 | 5599650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6254748 | 5599650 | -655098 | 6248825 | B0 | ACC - LUMP SUM
2 | T2552 | 43055415201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2014-10-29 | 1940620 | 1940620 | 1924570 | 0 | 0 | 1856552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1924570 | 1856552 | -68018 | 2021177
2 | T2554 | 43112915201 | F580952077 | SCRUGGS COMPANY (THE) | N/A | N/A | N/A | N/A | 2014-10-29 | 4054390 | 4054390 | 4069302 | 0 | 0 | 3749497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4069302 | 3749497 | -319805 | 4996679
2 | T2556 | 21007535201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-09-24 | 1492042 | 1492042 | 1448762 | 0 | 0 | 1448762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448762 | 1448762 | 0 | 1755423
2 | T2560 | 43054615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 2422564 | 2422564 | 2506188 | 0 | 0 | 2389680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2506188 | 2389680 | -116508 | 2628643
3 | E3K74 | 42692815201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2014-11-13 | 1363705 | 1363705 | 1373851 | 0 | 0 | 1311778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373851 | 1311778 | -62073 | 1604606
3 | E3L71 | 42874415201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-03-13 | 1490639 | 1490639 | 1445553 | 0 | 0 | 1451830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1445553 | 1451830 | 6277 | 1584507
3 | E3L98 | 42874615201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2014-11-13 | 4259734 | 4287109 | 4172519 | 27375.06 | 0 | 3907768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4172519 | 3907768 | -264750 | 4989174
3 | E3M60 | 42697215201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2014-12-11 | 1718927 | 1718927 | 1766800 | 0 | 0 | 1673682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766800 | 1673682 | -93118 | 2202754
3 | E3M93 | 43078215201 | F580538940 | OXFORD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-12-11 | 1217750 | 1217750 | 1189202 | 0 | 0 | 1136275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189202 | 1136275 | -52927 | 1216620
3 | E3N07 | 43460315201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-07-09 | 31110 | 31110 | 28465 | 0 | 0 | 28465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28465 | 28465 | 0 | 45127
3 | E3N22 | 41547435201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2014-10-09 | 785011 | 874968 | 824968 | 89956.57 | 0 | 824968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824968 | 824968 | 0 | 1252572
3 | E3N70 | 41694415201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2014-11-13 | 2595171 | 2642211 | 2488780 | 47040 | 0 | 2390489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2488780 | 2390489 | -98291 | 2402720
3 | E3N81 | 43558115201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-05-14 | 154105 | 159104 | 150561 | 4998.88 | 0 | 150561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150561 | 150561 | 0 | 119493
3 | T3088 | 21894615201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2012-07-25 | 13348458 | 13883485 | 14095924 | 535027.17 | 0 | 14095514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14095924 | 14095514 | -409 | 14378815
3 | T3311 | 22041265201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2009-06-17 | 5621006 | 6208685 | 6054584 | 587679.07 | -158382 | 6102577 | -158382 | 0 | 0 | 0 | 0 | 0 | -158382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -158382 | 5896202 | 6102577 | 206375 | 9080396 | ARRA | AMERICAN RECOVERY AND REINVEST
3 | T3396 | 42323315201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2013-09-25 | 2789487 | 2763621 | 2700963 | -25866.15 | 0 | 2673321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700963 | 2673321 | -27642 | 2906374
3 | T3401 | 42323415201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2013-10-30 | 2645210 | 2645210 | 2628131 | 0 | 0 | 2609172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2628131 | 2609172 | -18959 | 2957617
3 | T3409 | 42462215201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 2097227 | 2097227 | 2093592 | 0 | 0 | 1978887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2093592 | 1978887 | -114705 | 2813050
3 | T3411 | 42636815201 | F263312611 | R B M CONTRACTING SERVICES LLC | N/A | N/A | N/A | N/A | 2014-10-29 | 577753 | 577753 | 581122 | 0 | 0 | 581122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581122 | 581122 | 0 | 613088
3 | T3423 | 42164425201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-03-27 | 12358153 | 11830936 | 14453163 | -527216.4 | 0 | 14207037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14453163 | 14207037 | -246126 | 13406270
3 | T3424 | 41343515201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2013-02-06 | 3882641 | 3972326 | 3728903 | 89685.08 | 0 | 3719464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3728903 | 3719464 | -9439 | 4647470
3 | T3434 | 42987815201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 459930 | 459930 | 451610 | 0 | 0 | 451610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451610 | 451610 | 0 | 439830 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
3 | T3455 | 43000415201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2014-10-29 | 919509 | 919509 | 927409 | 0 | 0 | 927409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927409 | 927409 | 0 | 817764
3 | T3468 | 42696515201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 1826839 | 1826839 | 1794755 | 0 | 0 | 1727691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1794755 | 1727691 | -67064 | 1783054
3 | T3476 | 42385815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-03-26 | 2307108 | 2297266 | 2266725 | -9842.14 | 0 | 2239507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2266725 | 2239507 | -27218 | 2319570
3 | T3502 | 42764915201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 633977 | 703188 | 695402 | 69210.6 | 0 | 695402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695402 | 695402 | 0 | 559213
3 | T3510 | 43077615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-09-24 | 3964092 | 3964092 | 4024706 | 0 | 0 | 3718840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4024706 | 3718840 | -305866 | 4154252
3 | T3530 | 43174415201 | F593715775 | PYRAMID EXCAVATION INC. | N/A | N/A | N/A | N/A | 2015-01-28 | 217000 | 217000 | 216611 | 0 | 0 | 216611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216611 | 216611 | 0 | 236371
3 | T3532 | 43253215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-02-25 | 3173126 | 3173126 | 3259005 | 0 | 0 | 3171161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3259005 | 3171161 | -87844 | 2959991
3 | T3535 | 42693615201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 481388 | 481388 | 440397 | 0 | 0 | 440397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440397 | 440397 | 0 | 540651
3 | T3536 | 40393125201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-01-28 | 369064 | 369064 | 338614 | 0 | 0 | 338614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338614 | 338614 | 0 | 486852
3 | T3540 | 21988025201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-01-28 | 347017 | 347017 | 338632 | 0 | 0 | 338632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338632 | 338632 | 0 | 352628
3 | T3555 | 43630635201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 409629 | 409629 | 409629 | 0 | 0 | 409629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409629 | 409629 | 0 | 270026 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
4 | E4L95 | 41304815201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2011-06-21 | 54423100 | 54843389 | 54825050 | 420288.68 | 0 | 54583811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54825050 | 54583811 | -241240 | 56635288 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4P28 | 43053415201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2014-01-03 | 1630613 | 1680613 | 1713025 | 50000 | 0 | 1712786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1713025 | 1712786 | -239 | 1510583
4 | E4P42 | 42744115201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2014-05-02 | 1055000 | 1055000 | 1018660 | 0 | 0 | 1018660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1018660 | 1018660 | 0 | 1104492 | B0 | ACC - LUMP SUM
4 | E4P43 | 42636215201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-03-31 | 2106087 | 2106087 | 2037825 | 0 | 0 | 2037825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037825 | 2037825 | 0 | 2671514
4 | E4P91 | 43397915201 | F364509634 | MAYTIN ENGINEERING CORP. | N/A | N/A | N/A | N/A | 2014-06-06 | 682040 | 677370 | 696418 | -4669.44 | 0 | 696418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696418 | 696418 | 0 | 468108
4 | E4Q13 | 43060515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-01 | 3035506 | 3035506 | 2614486 | 0 | 0 | 2545146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2614486 | 2545146 | -69341 | 3179104
4 | E4Q62 | 42993615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-01-09 | 886950 | 886950 | 810170 | 0 | 0 | 810170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810170 | 810170 | 0 | 1238736
4 | E4Q67 | 42824115201 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2015-02-06 | 186978 | 221816 | 214581 | 34837.58 | 0 | 214581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214581 | 214581 | 0 | 231295
4 | E4Q81 | 43400615201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-04-03 | 436152 | 436152 | 404357 | 0 | 0 | 404357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404357 | 404357 | 0 | 395431
4 | T4255 | 40398415201 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2010-12-08 | 36988133 | 40660763 | 41250312 | 3672630.48 | 0 | 41508810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41250312 | 41508810 | 258498 | 44275084
4 | T4311 | 42924615201 | F593749359 | DESIGN-BUILD ENGINEERS & CONTRA | N/A | N/A | N/A | N/A | 2011-04-27 | 3983113 | 4102286 | 4023382 | 119173.98 | -101442 | 3920334 | -101442 | 0 | 0 | 0 | 0 | 0 | -101442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101442 | 3921940 | 3920334 | -1606 | 3335896
4 | T4345 | 40836215201 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2013-05-22 | 1202547 | 3085087 | 3080524 | 1882539.48 | 0 | 3080524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080524 | 3080524 | 0 | 1238644
4 | T4374 | 43019615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 348825 | 348825 | 339314 | 0 | 0 | 339314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339314 | 339314 | 0 | 385157
4 | T4380 | 42974015201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2014-09-24 | 480024 | 480024 | 456013 | 0 | 0 | 456013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456013 | 456013 | 0 | 486438
4 | T4384 | 42973815201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 547622 | 548351 | 527560 | 728.52 | 0 | 527560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527560 | 527560 | 0 | 546487
4 | T4394 | 43060225203 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 831515 | 893080 | 843974 | 61564.57 | 0 | 843974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843974 | 843974 | 0 | 850266
4 | T4398 | 42974115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 420985 | 420985 | 395082 | 0 | 0 | 395082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395082 | 395082 | 0 | 439144
5 | BDT74 | 41299435201 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2011-11-07 | 27584500 | 29571831 | 29554288 | 1987331.16 | 0 | 29554288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29554288 | 29554288 | 0 | 27584500
5 | E5L71 | 41299445201 | F261605378 | ARCHER WESTERN CONTRACTORS-RAIL | N/A | N/A | N/A | N/A | 2009-02-23 | 163288700 | 196216668 | 195534566 | 32927967.93 | 2601667 | 169140051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989667 | 0 | 612000 | 0 | 0 | 0 | 2601667 | 2601667 | 198136233 | 169140051 | -28996182 | 0 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | E5R02 | 41307215201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2011-10-13 | 51759000 | 51745315 | 51437545 | -13684.78 | 0 | 51645443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51437545 | 51645443 | 207898 | 55948237 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5R52 | 23827565201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2012-09-27 | 23633000 | 24988747 | 25103249 | 1355747.2 | 0 | 24880177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25103249 | 24880177 | -223072 | 32557148 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
5 | E5W28 | 41499925201 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2014-05-06 | 260959 | 242155 | 231155 | -18804.58 | 0 | 231155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231155 | 231155 | 0 | 250000
5 | E5W30 | 43214919201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2014-02-18 | 3585585 | 3585585 | 3535585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3535585 | 0 | -3535585 | 3478319 | A3 | ICC - DESIGN/BUILD - MINOR
5 | E5W57 | 41299435214 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2014-06-03 | 1657000 | 1757000 | 1745808 | 100000 | 0 | 1745490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1745808 | 1745490 | -318 | 2729000 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE
5 | E5W68 | 24099295201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2014-12-02 | 518519 | 518519 | 502367 | 0 | 0 | 502367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502367 | 502367 | 0 | 460954
5 | E5W73 | 43524315201 | F900605972 | GENESIS CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-01-06 | 149000 | 149000 | 148500 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148500 | 148500 | 0 | 230960
5 | E5W75 | 43528315201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-02-03 | 557571 | 557571 | 494639 | 0 | 0 | 494639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494639 | 494639 | 0 | 721944
5 | T5401 | 42201515201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-04-24 | 4603457 | 4806215 | 4675801 | 202758.21 | 0 | 4675281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4675801 | 4675281 | -520 | 4500360
5 | T5404 | 24023335201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2012-05-23 | 10111333 | 10458539 | 10091859 | 347206.49 | 0 | 10008344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10091859 | 10008344 | -83514 | 9890702
5 | T5417 | 40735545201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2012-04-25 | 18388845 | 18447512 | 18384136 | 58667.44 | 0 | 18074458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18384136 | 18074458 | -309678 | 20359977
5 | T5419 | 23953555201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2012-06-27 | 15255527 | 14971879 | 14890213 | -283647.92 | 0 | 14848574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14890213 | 14848574 | -41639 | 17113123
5 | T5427 | 43174815201 | F592733482 | ONAS CORPORATION | N/A | N/A | N/A | N/A | 2012-10-31 | 398541 | 398541 | 381567 | 0 | 0 | 381567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381567 | 381567 | 0 | 490626
5 | T5464 | 42363025201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2014-04-30 | 1180000 | 1180000 | 1130000 | 0 | 0 | 1130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1130000 | 1130000 | 0 | 1074627 | B0 | ACC - LUMP SUM
5 | T5483 | 42727915201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 2914000 | 2914000 | 2885939 | 0 | 0 | 2771829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2885939 | 2771829 | -114111 | 2978859 | B0 | ACC - LUMP SUM
5 | T5488 | 42907915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 5354000 | 5354000 | 5430627 | 0 | -11100 | 5333292 | 0 | 0 | 0 | 0 | 0 | -11100 | -11100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11100 | 5419527 | 5333292 | -86235 | 5993025 | B0 | ACC - LUMP SUM
5 | T5494 | 42488715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 1795728 | 1795728 | 1805364 | 0 | 0 | 1760006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1805364 | 1760006 | -45358 | 1761956 | B0 | ACC - LUMP SUM
5 | T5495 | 42886715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 6951000 | 6886782 | 6967320 | -64218.06 | 0 | 6782907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6967320 | 6782907 | -184413 | 7479523 | B0 | ACC - LUMP SUM
5 | T5501 | 42886215201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 2189795 | 2189795 | 2201353 | 0 | 0 | 2169152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2201353 | 2169152 | -32201 | 2211253 | B0 | ACC - LUMP SUM
5 | T5503 | 42868815201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 2402000 | 2402000 | 2340586 | 0 | 0 | 2178963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340586 | 2178963 | -161623 | 2568891 | B0 | ACC - LUMP SUM
5 | T5518 | 43471315201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-02-25 | 813663 | 813663 | 766183 | 0 | 0 | 766183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766183 | 766183 | 0 | 994320
5 | T5520 | 23867825201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2014-12-03 | 544771 | 536238 | 524085 | -8533.35 | 0 | 520797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524085 | 520797 | -3288 | 761207
5 | T5539 | 43471215201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2015-02-25 | 1710446 | 1710446 | 1675126 | 0 | 0 | 1675126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675126 | 1675126 | 0 | 2082710
6 | E6G56 | 42611915201 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2013-01-31 | 4988310 | 4988310 | 4865434 | 0 | 0 | 4865434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4865434 | 4865434 | 0 | 5875816
6 | E6H34 | 42560035201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2013-06-27 | 6337856 | 7490311 | 7429547 | 1152454.82 | 0 | 7303699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7429547 | 7303699 | -125847 | 5970124
6 | E6H59 | 42999915201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2014-03-27 | 1579746 | 1579746 | 1465179 | 0 | 0 | 1465179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465179 | 1465179 | 0 | 2298507 | B0 | ACC - LUMP SUM
6 | E6H61 | 43119215201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2014-06-12 | 838500 | 838500 | 763060 | 0 | 0 | 763060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763060 | 763060 | 0 | 850347
6 | E6I14 | 43209815201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2014-02-27 | 328706 | 328706 | 320865 | 0 | 0 | 320865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320865 | 320865 | 0 | 370269 | B0 | ACC - LUMP SUM
6 | E6I33 | 43067015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-02-26 | 1219000 | 1219000 | 1179457 | 0 | 0 | 1177974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1179457 | 1177974 | -1484 | 1266281 | B0 | ACC - LUMP SUM
6 | E6I57 | 43119015201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2014-09-25 | 619046 | 619046 | 562195 | 0 | 0 | 562195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562195 | 562195 | 0 | 838614
6 | E6I58 | 43119415201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2014-08-28 | 931395 | 931395 | 872317 | 0 | 0 | 872317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872317 | 872317 | 0 | 978849
6 | E6I77 | 24994175201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2014-08-28 | 1198756 | 1198756 | 1094981 | 0 | 0 | 1094981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094981 | 1094981 | 0 | 1268938
6 | E6I78 | 43081615201 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2014-07-31 | 1207213 | 1207213 | 1139099 | 0 | 0 | 1129248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139099 | 1129248 | -9851 | 1208780
6 | E6I83 | 43081415201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-11-20 | 94720 | 94720 | 88652 | 0 | 0 | 88652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88652 | 88652 | 0 | 126847 | B0 | ACC - LUMP SUM
6 | E6I85 | 41774079201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2014-03-27 | 502650 | 502650 | 470337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470337 | 0 | -470337 | 678578 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6I87 | 42934415201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-10-30 | 1872759 | 1872759 | 1693855 | 0 | 0 | 1636257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1693855 | 1636257 | -57598 | 1934017
6 | E6J40 | 43590015201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-01-29 | 248698 | 248698 | 217030 | 0 | 0 | 217030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217030 | 217030 | 0 | 248763
6 | E6J70 | 43717615201 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2015-06-11 | 149934 | 149934 | 142606 | 0 | 0 | 142606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142606 | 142606 | 0 | 153889 | B0 | ACC - LUMP SUM
6 | T6207 | 41984815201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 6954601 | 7631613 | 7814383 | 677012.41 | 0 | 7814501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814383 | 7814501 | 117 | 8225852
6 | T6278 | 24994115201 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2012-05-23 | 14358568 | 13941778 | 14063237 | -416790.24 | 0 | 13981485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14063237 | 13981485 | -81752 | 12500129
6 | T6308 | 42751315201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-06-19 | 3950337 | 4058444 | 4025547 | 108107.06 | -45106 | 3968548 | -45106 | 0 | 0 | 0 | 0 | 0 | -45106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45106 | 3980441 | 3968548 | -11893 | 3555732
6 | T6322 | 42750525201 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 2272423 | 2348653 | 2183494 | 76230.06 | 0 | 2177671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2183494 | 2177671 | -5822 | 2206205
6 | T6324 | 42913615201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 3959132 | 4129233 | 4133336 | 170101.12 | 0 | 4124281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4133336 | 4124281 | -9055 | 4168714
6 | T6327 | 43080515201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2014-03-26 | 4029465 | 4029465 | 3868532 | 0 | 0 | 3761105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3868532 | 3761105 | -107427 | 4215349 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6351 | 42904315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-02-05 | 643250 | 643250 | 597697 | 0 | 0 | 597697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597697 | 597697 | 0 | 824250 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
6 | T6355 | 42902115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-05-21 | 1061111 | 1061111 | 1066049 | 0 | 0 | 1066049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066049 | 1066049 | 0 | 1021385 | B0 | ACC - LUMP SUM
6 | T6361 | 43003115201 | F263976898 | AMROAD LLC | N/A | N/A | N/A | N/A | 2014-09-24 | 327561 | 327561 | 279990 | 0 | 0 | 279933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279990 | 279933 | -57 | 306614
6 | T6363 | 42751515201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2013-05-22 | 5378636 | 5591336 | 6965131 | 212700 | 0 | 6964220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6965131 | 6964220 | -911 | 4504474
6 | T6368 | 43003315201 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2014-07-30 | 619197 | 643584 | 598711 | 24386.71 | 0 | 598703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598711 | 598703 | -8 | 631340
6 | T6369 | 43081915201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2014-10-29 | 896920 | 896920 | 810742 | 0 | -33098 | 777644 | -33098 | 0 | 0 | 0 | 0 | 0 | -33098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33098 | 777644 | 777644 | 0 | 973033
6 | T6370 | 42913715201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 1463328 | 1519911 | 1478859 | 56583.43 | 0 | 1424599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1478859 | 1424599 | -54260 | 1605781
7 | E7I67 | 42893615201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-06-11 | 3868793 | 3868793 | 3814687 | 0 | 0 | 3688104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3814687 | 3688104 | -126583 | 3735600 | B0 | ACC - LUMP SUM
7 | E7I81 | 43113715201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-06-11 | 1095029 | 1095029 | 997607 | 0 | 0 | 997607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997607 | 997607 | 0 | 992000
7 | E7I96 | 40625565201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2014-06-11 | 1992240 | 1992240 | 1975737 | 0 | 0 | 1975126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975737 | 1975126 | -611 | 2322106
7 | E7J96 | 43066115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-11-26 | 2030000 | 2030000 | 1980915 | 0 | 0 | 1934577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980915 | 1934577 | -46338 | 1984600 | B0 | ACC - LUMP SUM
7 | E7J98 | 42907715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-10 | 1378500 | 1378500 | 1371830 | 0 | 0 | 1336400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371830 | 1336400 | -35430 | 1271900 | B0 | ACC - LUMP SUM
7 | E7K00 | 42907215201 | F593759317 | CHEYENNE ASPHALT INCORPORATED | N/A | N/A | N/A | N/A | 2015-02-11 | 412263 | 412263 | 394582 | 0 | 0 | 394582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394582 | 394582 | 0 | 398900 | B0 | ACC - LUMP SUM
7 | T7307 | 42715215201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2012-12-05 | 14844440 | 14844440 | 15019838 | 0 | 0 | 14905397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15019838 | 14905397 | -114441 | 15370623
7 | T7325 | 42900515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2013-06-19 | 15491284 | 16150823 | 16100076 | 659539.56 | 0 | 16143898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16100076 | 16143898 | 43822 | 16955600
7 | T7329 | 42907325201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-10-30 | 5019226 | 5019226 | 4985077 | 0 | 0 | 4951447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4985077 | 4951447 | -33631 | 4751500 | B0 | ACC - LUMP SUM
7 | T7334 | 42455015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2013-08-28 | 8989959 | 9299052 | 9312842 | 309093.47 | -3600 | 9306402 | 0 | 0 | 0 | 0 | 0 | -3600 | -3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3600 | 9309242 | 9306402 | -2840 | 8578717
7 | T7337 | 42907315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2013-10-30 | 4224761 | 4277589 | 4397983 | 52828.12 | 0 | 4415486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4397983 | 4415486 | 17503 | 4480000
7 | T7340 | 42715415201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2014-04-30 | 1688000 | 1688000 | 1644638 | 0 | 0 | 1606582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1644638 | 1606582 | -38056 | 2156800 | B0 | ACC - LUMP SUM
7 | T7341 | 42896115201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-03-26 | 5790872 | 5790872 | 5714657 | 0 | 0 | 5660340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5714657 | 5660340 | -54316 | 6079410
7 | T7343 | 42308815202 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2014-05-21 | 4553063 | 4553063 | 4196722 | 0 | 0 | 4140383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4196722 | 4140383 | -56339 | 4416500
7 | T7358 | 43140415201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 1033200 | 1033200 | 920104 | 0 | 0 | 920104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920104 | 920104 | 0 | 1010220 | B0 | ACC - LUMP SUM
7 | T7361 | 42906115202 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-12-03 | 1465000 | 1494392 | 1504704 | 29391.67 | 0 | 1462449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1504704 | 1462449 | -42254 | 1300371 | B0 | ACC - LUMP SUM
8 | E8L99 | 41546225202 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2012-05-22 | 19914762 | 20008584 | 19972782 | 93822.3 | -154000 | 19745451 | 0 | 0 | 0 | 0 | 0 | -154000 | -154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -154000 | 19818782 | 19745451 | -73332 | 20630727
8 | E8M05 | 43128115201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2013-02-25 | 40666800 | 40884133 | 40781351 | 217332.73 | -49500 | 40551799 | 0 | 0 | 0 | 0 | 0 | -49500 | -49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49500 | 40731851 | 40551799 | -180052 | 36916236 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
8 | E8M77 | 40615145201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2013-03-26 | 11249740 | 11481897 | 10973748 | 232156.69 | 0 | 10925662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10973748 | 10925662 | -48086 | 11244846
8 | E8M80 | 42768515201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2013-05-14 | 6746576 | 6938552 | 6915696 | 191976.43 | 0 | 6919857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6915696 | 6919857 | 4160 | 6459218
8 | E8M93 | 43108935201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2013-05-21 | 7676614 | 7714483 | 7540572 | 37868.44 | 0 | 7491522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7540572 | 7491522 | -49050 | 8536509
8 | E8N21 | 42902315201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2014-03-11 | 6573418 | 6704790 | 6985687 | 131371.79 | -3000 | 6966867 | 0 | 0 | 0 | 0 | 0 | -3000 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 6982687 | 6966867 | -15820 | 8559769
8 | E8N37 | 43112315201 | F593285921 | S & D INDUSTRIAL PAINTING INC. | N/A | N/A | N/A | N/A | 2014-06-10 | 383488 | 383488 | 358052 | 0 | 0 | 358052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358052 | 358052 | 0 | 523747

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1497 | 43003715201 | 2012-03-28 | QTR3 | 11/12 | 1 | 1 | 60 | 99 | 261 | -162 | 162 | 0 | 39 | 0 | 90611 | 0 | 90611 | 89035 | 88897 | -43964 | 0 | -43964 | 44933 | 44933 | 0 | -1576 | 17 | 4 | 0 | 0 | 0 | 0 | 0 | -1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | -1576 | 0 | F593490202 | ALDON BOOKHARDT ROOFING INC. | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 | 2013-05-30 | QTR4 | 12/13 | 113 | 111867.75 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 17 | 01co | 1 | 17
01CO | 01 | T1501 | 40828635201 | 2012-06-20 | QTR4 | 11/12 | 1 | 7 | 700 | 779 | 779 | 0 | 0 | 0 | 75 | 4 | 14784300 | 133862 | 14650438 | 15330267 | 14964740 | 0 | 0 | 0 | 14964740 | 15047703 | 82963 | 545967 | 48 | 0 | 4 | 334024 | 0 | 0 | 0 | 328205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 635924 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-09-10 | QTR1 | 15/16 | 2014-10-22 | QTR2 | 14/15 | 113 | 13767013.79 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 17 | 01do | 18 | 34
01CO | 01 | T1512 | 40826835201 | 2012-09-26 | QTR1 | 12/13 | 3 | 19 | 650 | 871 | 865 | 6 | 0 | 0 | 164 | 57 | 19473948 | 150000 | 19323948 | 20142554 | 20429764 | 0 | 0 | 0 | 20429764 | 20268347 | -161418 | 668606 | 138 | 0 | 0 | 335638 | 10644 | 0 | 57 | 446552 | 194978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 797698 | 205622 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-10-19 | QTR2 | 15/16 | 2015-07-30 | QTR1 | 15/16 | 108 | 19967593.35 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 19 | 02co | 35 | 53
01CO | 01 | T1527 | 41787615201 | 2013-02-06 | QTR3 | 12/13 | 2 | 9 | 768 | 835 | 810 | 25 | 0 | 0 | 67 | 0 | 12312349 | 150000 | 12162349 | 13258294 | 12897465 | 0 | 0 | 0 | 12897465 | 12514104 | -383360 | 945945 | 41 | 0 | 0 | 262529 | 0 | 0 | 0 | 689450 | 18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 951980 | 18277 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-10 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 115 | 15340403.45 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 10 | 02do | 54 | 63
01CO | 01 | T1541 | 42525115201 | 2013-06-19 | QTR4 | 12/13 | 2 | 4 | 600 | 681 | 680 | 1 | 0 | 0 | 77 | 4 | 7929564 | 70779 | 7858785 | 8206423 | 8142299 | 0 | 0 | 0 | 8142299 | 8010531 | -131769 | 276859 | 58 | 0 | 0 | 248527 | 9547 | 0 | 4 | 79218 | 11206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 327744 | 20752 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-11-19 | QTR2 | 15/16 | 2015-09-24 | QTR1 | 15/16 | 108 | 7502697.01 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO | 20 | 03co | 64 | 83
01CO | 01 | T1546 | 42910415201 | 2014-02-26 | QTR3 | 13/14 | 1 | 2 | 130 | 190 | 219 | -29 | 29 | 0 | 36 | 24 | 2195109 | 50000 | 2145109 | 2159801 | 2156391 | -50518 | 0 | -50518 | 2105873 | 2085969 | -19904 | -35308 | 11 | 0 | 10 | -17725 | 0 | 11 | 14 | 8387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 24 | -9339 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2015-09-13 | QTR1 | 15/16 | 2015-04-14 | QTR4 | 14/15 | 115 | 2641240.24 | B0 | ACC - LUMP SUM | 16 | 14 | 0 | 0 | 0 | 0 |  | CO | 9 | 03do | 84 | 92
01CO | 01 | T1557 | 42928415201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 175 | 202 | 201 | 1 | 0 | 0 | 27 | 0 | 2509778 | 50000 | 2459778 | 2509778 | 2520762 | 0 | 0 | 0 | 2520762 | 2358044 | -162718 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 | 2015-08-07 | QTR1 | 15/16 | 108 | 2840170.1 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO | 8 | 04co | 93 | 100
01CO | 01 | T1566 | 20010575201 | 2014-04-30 | QTR4 | 13/14 | 1 | 4 | 300 | 324 | 281 | 43 | 0 | 0 | 24 | 0 | 855140 | 0 | 855140 | 880470 | 883951 | 0 | 0 | 0 | 883951 | 883951 | 0 | 25330 | 14 | 0 | 0 | 17931 | 1430 | 0 | 0 | 7399 | 7399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25330 | 8829 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 | 2015-08-06 | QTR1 | 15/16 | 118 | 1061209.63 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO | 9 | 04do | 101 | 109
01CO | 01 | T1570 | 42584615201 | 2014-03-26 | QTR3 | 13/14 | 3 | 4 | 250 | 305 | 305 | 0 | 0 | 0 | 55 | 0 | 2796051 | 50000 | 2746051 | 3242177 | 3374573 | 0 | 120000 | 120000 | 3494573 | 3324455 | -170118 | 446126 | 14 | 0 | 0 | 36506 | 0 | 30 | 0 | 458800 | 45280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 495306 | 45280 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 | 2015-07-19 | QTR1 | 15/16 | 118 | 2726352.03 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | 0 | 0 |  | CO | 16 | 05co | 110 | 125
01CO | 01 | T1578 | 43086015201 | 2013-12-04 | QTR2 | 13/14 | 2 | 9 | 270 | 410 | 407 | 3 | 0 | 0 | 140 | 0 | 5634855 | 53649 | 5581206 | 5727333 | 5707127 | 0 | 0 | 0 | 5707127 | 5640992 | -66135 | 92478 | 121 | 0 | 0 | 20908 | 2691 | 0 | 0 | 36741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80103 | 2691 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-07-06 | QTR1 | 15/16 | 2015-05-04 | QTR4 | 14/15 | 108 | 5433904.15 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 | T | CO | 9 | 05do | 126 | 134
01CO | 01 | T1591 | 43130115201 | 2014-04-30 | QTR4 | 13/14 | 1 | 2 | 270 | 452 | 447 | 5 | 0 | 0 | 177 | 5 | 7824413 | 94834 | 7729579 | 8062184 | 7860334 | 0 | 0 | 0 | 7860334 | 7721971 | -138364 | 237771 | 159 | 0 | 5 | 259901 | 0 | 0 | 0 | 26087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 285988 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-11-16 | QTR2 | 15/16 | 2015-09-28 | QTR1 | 15/16 | 108 | 8889524.26 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 13 | 06co | 135 | 147
01CO | 01 | T1592 | 42729815201 | 2014-05-21 | QTR4 | 13/14 | 5 | 1 | 275 | 313 | 312 | 1 | 0 | 0 | 38 | 0 | 1644078 | 50000 | 1594078 | 1668510 | 1623620 | 0 | 0 | 0 | 1623620 | 1623620 | 0 | 24432 | 32 | 0 | 0 | 2784 | 0 | 0 | 0 | 27758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30542 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-12-09 | QTR2 | 15/16 | 2015-11-12 | QTR2 | 15/16 | 115 | 1618341.71 | B0:B0:B0:B:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 15 | 06do | 148 | 162
01CO | 01 | T1594 | 43135415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 5 | 130 | 258 | 258 | 0 | 0 | 0 | 44 | 84 | 989000 | 0 | 989000 | 1119395 | 1113069 | 0 | 0 | 0 | 1113069 | 1113069 | 0 | 130395 | 39 | 0 | 13 | 19459 | 0 | 0 | 4 | 6266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 104670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 130395 | 0 | F464740152 | CATHCART CONSTRUCTION COMPANY - FLORIDA | N/A | N/A | N/A | N/A | 2015-12-10 | QTR2 | 15/16 | 2015-09-19 | QTR1 | 15/16 | 108 | 857499.8 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 10 | 07co | 163 | 172
01CO | 01 | T1996 | 43086115201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 90 | 133 | 133 | 0 | 0 | 0 | 41 | 2 | 336490 | 14047 | 322443 | 336490 | 331697 | 0 | 0 | 0 | 331697 | 331697 | 0 | 0 | 21 | 0 | 0 | 7107 | 0 | 16 | 2 | 2148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 9255 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 | 2015-09-21 | QTR1 | 15/16 | 115 | 347757.16 | B0 | ACC - LUMP SUM | 2 | 4 | 0 | 0 | 0 | 0 |  | CO | 6 | 07do | 173 | 178
01CO | 01 | T1A05 | 42910815201 | 2014-10-29 | QTR2 | 14/15 | 1 | 2 | 160 | 182 | 158 | 24 | 0 | 0 | 22 | 0 | 2154862 | 50000 | 2104862 | 2208421 | 2164641 | 0 | 0 | 0 | 2164641 | 2077091 | -87549 | 53559 | 20 | 0 | 0 | 18835 | 0 | 0 | 0 | 14169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51972 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-12-10 | QTR2 | 15/16 | 2015-08-27 | QTR1 | 15/16 | 108 | 2061296.31 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 179 | 178
01CO | 01 | T1A12 | 43121015201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 145 | 194 | 194 | 0 | 0 | 0 | 49 | 0 | 3770622 | 50000 | 3720622 | 3770622 | 3700017 | 0 | 0 | 0 | 3700017 | 3520482 | -179536 | 0 | 44 | 0 | 0 | 24624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24624 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-12-14 | QTR2 | 15/16 | 2015-10-16 | QTR2 | 15/16 | 113 | 3557076.77 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO | 7 | 08do | 179 | 185
01CO | 01 | T1A14 | 43341115201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 110 | 131 | 131 | 0 | 0 | 0 | 12 | 9 | 247066 | 11866 | 235200 | 270085 | 250380 | 0 | 0 | 0 | 250380 | 250380 | 0 | 23019 | 10 | 0 | 9 | 23019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 23019 | 0 | F593339407 | TAGARELLI CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-08-11 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 108 | 256990.36 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1J69 | 20074625201 | 2012-06-29 | QTR4 | 11/12 | 1 | 6 | 550 | 629 | 629 | 0 | 0 | 0 | 37 | 42 | 8819248 | 50000 | 8769248 | 9865997 | 9845954 | 0 | 0 | 0 | 9845954 | 9861107 | 15153 | 1046749 | 0 | 9 | 42 | 835826 | 0 | 0 | 0 | 56914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 0 | 0 | 0 | 200041 | 200041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 42 | 1096506 | 200041 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-11-13 | QTR2 | 15/16 | 2014-08-25 | QTR1 | 14/15 | 113 | 9894002 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 24 | 0 | 0 | -6891 | 0 |  | DO
01DO | 01 | E1J71 | 41263625201 | 2012-05-31 | QTR4 | 11/12 | 2 | 14 | 565 | 936 | 936 | 0 | 0 | 0 | 69 | 302 | 6703703 | 50000 | 6653703 | 7531485 | 7530256 | 0 | 0 | 0 | 7530256 | 7530256 | 0 | 827782 | 22 | 0 | 121 | 99861 | 9614 | 0 | 95 | 314019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 401293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 815173 | 9614 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 | 2015-06-08 | QTR4 | 14/15 | 113 | 638850 | A3 | ICC - DESIGN/BUILD - MINOR | 57 | 47 | 0 | 0 | 0 | 0 |  | DO |  | 0
01DO | 01 | E1J72 | 41664925201 | 2012-05-17 | QTR4 | 11/12 | 1 | 5 | 795 | 1092 | 1092 | 0 | 0 | 0 | 196 | 101 | 54100000 | 150000 | 53950000 | 55514659 | 55350517 | 0 | 0 | 0 | 55350517 | 55125629 | -224888 | 1414659 | 165 | 0 | 101 | 1373941 | 0 | 0 | 0 | 96582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1492682 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2015-12-09 | QTR2 | 15/16 | 2015-07-23 | QTR1 | 15/16 | 106 | 72523865 | B8 | ACC - DESIGN/BUILD - MAJOR | 51 | 31 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N08 | 42347115201 | 2014-06-19 | QTR4 | 13/14 | 1 | 4 | 200 | 242 | 242 | 0 | 0 | 0 | 36 | 6 | 1880948 | 50000 | 1830948 | 1908269 | 1858269 | 0 | 0 | 0 | 1858269 | 1834616 | -23653 | 27320 | 16 | 0 | 0 | 0 | 0 | 7 | 5 | 22343 | 8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4977 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 27320 | 8999 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-07-31 | QTR1 | 15/16 | 2015-06-22 | QTR4 | 14/15 | 108 | 1405116.38 | B0 | ACC - LUMP SUM | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N35 | 43496715201 | 2014-06-19 | QTR4 | 13/14 | 1 | 1 | 60 | 67 | 61 | 6 | 0 | 0 | 7 | 0 | 93903 | 3487 | 90416 | 106903 | 100206 | 0 | 0 | 0 | 100206 | 100206 | 0 | 13000 | 3 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2015-11-19 | QTR2 | 15/16 | 2014-12-12 | QTR2 | 14/15 | 118 | 71243.52 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N47 | 43019125201 | 2014-06-19 | QTR4 | 13/14 | 2 | 1 | 175 | 213 | 204 | 9 | 0 | 0 | 38 | 0 | 4346396 | 50000 | 4296396 | 4413679 | 4400332 | 0 | 0 | 0 | 4400332 | 4322422 | -77910 | 67283 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 67283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67283 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2015-08-13 | QTR1 | 15/16 | 2015-04-13 | QTR4 | 14/15 | 118 | 4460046.21 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N64 | 43160515201 | 2014-08-29 | QTR1 | 14/15 | 1 | 0 | 150 | 176 | 175 | 1 | 0 | 0 | 26 | 0 | 3021172 | 50000 | 2971172 | 3021172 | 3068023 | 0 | 0 | 0 | 3068023 | 2921086 | -146936 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-25 | QTR1 | 15/16 | 2015-06-12 | QTR4 | 14/15 | 118 | 3419370.6 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N65 | 42909615201 | 2014-10-16 | QTR2 | 14/15 | 1 | 0 | 130 | 153 | 150 | 3 | 0 | 0 | 23 | 0 | 1285754 | 50000 | 1235754 | 1285754 | 1252542 | 0 | 0 | 0 | 1252542 | 1182541 | -70001 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2015-11-02 | QTR2 | 15/16 | 2015-09-24 | QTR1 | 15/16 | 115 | 1296120.13 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N66 | 41787625201 | 2015-06-18 | QTR4 | 14/15 | 1 | 0 | 65 | 67 | 23 | 44 | 0 | 0 | 2 | 0 | 135934 | 8934 | 127000 | 135934 | 127000 | 0 | 0 | 0 | 127000 | 127000 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650968383 | WHITELEAF LLC DBA TRAFFIC SOLUTIONS | N/A | N/A | N/A | N/A | 2015-11-03 | QTR2 | 15/16 | 2015-10-13 | QTR2 | 15/16 | 115 | 208343.37 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N67 | 43121315201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 70 | 91 | 91 | 0 | 0 | 0 | 21 | 0 | 660116 | 29692 | 630424 | 660116 | 658410 | 0 | 0 | 0 | 658410 | 658410 | 0 | 0 | 12 | 0 | 0 | 27986 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 27986 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-11-19 | QTR2 | 15/16 | 2015-07-26 | QTR1 | 15/16 | 108 | 633762.78 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N70 | 40826895201 | 2015-01-15 | QTR3 | 14/15 | 1 | 0 | 50 | 63 | 63 | 0 | 0 | 0 | 13 | 0 | 129260 | 9480 | 119780 | 129260 | 124484 | 0 | 0 | 0 | 124484 | 124484 | 0 | 0 | 13 | 0 | 0 | 4704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4704 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2015-12-11 | QTR2 | 15/16 | 2015-11-01 | QTR2 | 15/16 | 108 | 172354.33 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N71 | 43006015201 | 2015-01-15 | QTR3 | 14/15 | 1 | 0 | 80 | 95 | 92 | 3 | 0 | 0 | 15 | 0 | 567387 | 27173 | 540214 | 567387 | 532744 | 0 | 0 | 0 | 532744 | 532744 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2015-09-23 | QTR1 | 15/16 | 2015-08-18 | QTR1 | 15/16 | 118 | 519186.9 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N76 | 43510615201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 180 | 195 | 160 | 35 | 0 | 0 | 15 | 0 | 3493285 | 50000 | 3443285 | 3493285 | 3362358 | 0 | 80000 | 80000 | 3442358 | 3345583 | -96775 | 0 | 7 | 0 | 0 | 12658 | 0 | 0 | 0 | 5994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18652 | 0 | F591448314 | ZEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-11-25 | QTR2 | 15/16 | 2015-09-11 | QTR1 | 15/16 | 115 | 2641060.47 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N96 | 42949925201 | 2014-10-16 | QTR2 | 14/15 | 1 | 1 | 90 | 91 | 51 | 40 | 0 | 0 | 1 | 0 | 229418 | 9702 | 219716 | 228371 | 218669 | 0 | 0 | 0 | 218669 | 218669 | 0 | -1047 | 0 | 0 | 0 | -1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1047 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-07-21 | QTR1 | 15/16 | 2015-06-09 | QTR4 | 14/15 | 115 | 179058.8 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O06 | 43574215201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 50 | 50 | 16 | 34 | 0 | 0 | 0 | 0 | 140780 | 9482 | 131298 | 140780 | 132639 | 0 | 0 | 0 | 132639 | 265277 | 132639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 0 | F650968383 | WHITELEAF LLC DBA TRAFFIC SOLUTIONS | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 | 2015-03-02 | QTR3 | 14/15 | 113 | 193962.81 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O17 | 43642215201 | 2015-05-21 | QTR4 | 14/15 | 1 | 0 | 41 | 51 | 48 | 3 | 0 | 0 | 10 | 0 | 122267 | 6051 | 116216 | 122267 | 116216 | 0 | 0 | 0 | 116216 | 116216 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2015-12-16 | QTR2 | 15/16 | 2015-11-23 | QTR2 | 15/16 | 108 | 128069.07 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O84 | 43494415201 | 2015-07-16 | QTR1 | 15/16 | 1 | 0 | 60 | 60 | 19 | 41 | 0 | 0 | 0 | 0 | 41385 | 3177 | 38208 | 41385 | 38208 | 0 | 0 | 0 | 38208 | 38208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2015-11-13 | QTR2 | 15/16 | 2015-10-13 | QTR2 | 15/16 | 113 | 66757.33 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2415 | 42884215201 | 2012-03-28 | QTR3 | 11/12 | 1 | 1 | 40 | 131 | 131 | 0 | 0 | 0 | 49 | 42 | 75000 | 0 | 75000 | 91225 | 91225 | 0 | 0 | 0 | 91225 | 91225 | 0 | 16225 | 12 | 0 | 42 | 16225 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 42 | 16225 | 0 | F593490202 | ALDON BOOKHARDT ROOFING INC. | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 | 2012-12-16 | QTR2 | 12/13 | 208 | 93853.67 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2439 | 42732815201 | 2012-09-26 | QTR1 | 12/13 | 1 | 0 | 70 | 75 | 111 | -36 | 36 | 0 | 5 | 0 | 240847 | 16502 | 224345 | 240847 | 224345 | -71365 | 0 | -71365 | 152980 | 152980 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592733482 | ONAS CORPORATION | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 | 2013-04-23 | QTR4 | 12/13 | 208 | 250711.01 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2443 | 42698615201 | 2013-02-06 | QTR3 | 12/13 | 1 | 0 | 150 | 204 | 203 | 1 | 0 | 0 | 45 | 9 | 4870523 | 56040 | 4814483 | 4870523 | 4844339 | 0 | 0 | 0 | 4844339 | 4835215 | -9124 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-07-13 | QTR1 | 15/16 | 2013-12-22 | QTR2 | 13/14 | 209 | 5528433.55 |  |  | 9 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2512 | 42869015201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 260 | 389 | 389 | 0 | 0 | 0 | 129 | 0 | 8787879 | 96597 | 8691282 | 8787879 | 8967904 | 0 | 0 | 0 | 8967904 | 8851811 | -116093 | 0 | 104 | 0 | 0 | 5708 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10581 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 | 2015-04-10 | QTR4 | 14/15 | 214 | 9570318.55 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2517 | 41695325201 | 2014-02-26 | QTR3 | 13/14 | 1 | 3 | 300 | 488 | 488 | 0 | 0 | 0 | 112 | 76 | 5124750 | 58877 | 5065873 | 5335260 | 5663021 | 0 | 0 | 0 | 5663021 | 5552944 | -110077 | 210510 | 75 | 0 | 0 | 17045 | 703 | 0 | 53 | 130746 | 29421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 44849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 58566 | 58566 | 0 | 0 | 0 | 0 | 6 | 76 | 251206 | 88690 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-12-22 | QTR2 | 15/16 | 2015-09-26 | QTR1 | 15/16 | 208 | 6059850.2 |  |  | 16 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2524 | 42870915201 | 2014-05-07 | QTR4 | 13/14 | 2 | 2 | 150 | 298 | 302 | -4 | 4 | 0 | 133 | 15 | 3832891 | 67277 | 3765614 | 3864530 | 3881828 | -9496 | 0 | -9496 | 3872332 | 3786451 | -85881 | 31639 | 106 | 0 | 14 | 49251 | 0 | 0 | 1 | 42542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 94387 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-11-17 | QTR2 | 15/16 | 2015-05-21 | QTR4 | 14/15 | 208 | 3923781.3 | B0 | ACC - LUMP SUM | 7 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2527 | 42870515201 | 2014-05-21 | QTR4 | 13/14 | 1 | 2 | 195 | 311 | 311 | 0 | 0 | 0 | 93 | 23 | 3855596 | 50000 | 3805596 | 3937461 | 4006951 | 0 | 0 | 0 | 4006951 | 3890841 | -116110 | 81865 | 69 | 0 | 7 | 33849 | 0 | 0 | 16 | 66627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 100476 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-09-03 | QTR1 | 15/16 | 2015-06-10 | QTR4 | 14/15 | 208 | 3913298.22 |  |  | 18 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2528 | 42870615201 | 2014-05-21 | QTR4 | 13/14 | 2 | 1 | 260 | 425 | 425 | 0 | 0 | 0 | 150 | 15 | 6187853 | 81793 | 6106060 | 6237853 | 6218179 | 0 | 0 | 0 | 6218179 | 5933793 | -284386 | 50000 | 96 | 0 | 10 | 28305 | 0 | 20 | 5 | 46802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15 | 75107 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-12-22 | QTR2 | 15/16 | 2015-11-05 | QTR2 | 15/16 | 208 | 5027804.24 |  |  | 15 | 34 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2529 | 42871215201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 190 | 354 | 354 | 0 | 0 | 0 | 164 | 0 | 5035067 | 50000 | 4985067 | 5035067 | 5418212 | 0 | 0 | 0 | 5418212 | 5280952 | -137260 | 0 | 48 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 0 | 0 | 0 | 100 | 0 | 1324 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-07 | QTR2 | 15/16 | 2015-07-28 | QTR1 | 15/16 | 216 | 5026805.45 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2530 | 21156035201 | 2014-05-21 | QTR4 | 13/14 | 1 | 3 | 150 | 207 | 196 | 11 | 0 | 0 | 57 | 0 | 1259477 | 0 | 1259477 | 1284233 | 1254859 | 0 | 0 | 0 | 1254859 | 1254859 | 0 | 24756 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 24756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 38 | 0 | 24756 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 | 2015-05-26 | QTR4 | 14/15 | 216 | 957005.79 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2535 | 42053145201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 120 | 164 | 164 | 0 | 0 | 0 | 21 | 23 | 1754776 | 50000 | 1704776 | 1824298 | 1779783 | 0 | 0 | 0 | 1779783 | 1779783 | 0 | 69521 | 15 | 0 | 0 | 160 | 0 | 0 | 23 | 73186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 73346 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 | 2015-06-17 | QTR4 | 14/15 | 214 | 1169715.46 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2543 | 43055515201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 70 | 93 | 93 | 0 | 0 | 0 | 23 | 0 | 1738869 | 50000 | 1688869 | 1738869 | 1721840 | 0 | 0 | 0 | 1721840 | 1698982 | -22858 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-07-01 | QTR1 | 15/16 | 2015-02-13 | QTR3 | 14/15 | 214 | 1963162.15 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2544 | 42880815201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 180 | 342 | 340 | 2 | 0 | 0 | 157 | 5 | 7085441 | 54149 | 7031292 | 7135441 | 7222230 | 0 | 0 | 0 | 7222230 | 6861498 | -360732 | 50000 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 8711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 57216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 65927 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-12-04 | QTR2 | 15/16 | 2015-10-12 | QTR2 | 15/16 | 208 | 5804681.6 |  |  | 5 | 57 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2546 | 42889615201 | 2014-09-24 | QTR1 | 14/15 | 1 | 4 | 190 | 261 | 261 | 0 | 0 | 0 | 71 | 0 | 1837492 | 0 | 1837492 | 1861682 | 1898076 | 0 | 0 | 0 | 1898076 | 1898076 | 0 | 24190 | 39 | 0 | 0 | 8416 | 0 | 13 | 0 | 15774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 24190 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-12-17 | QTR2 | 15/16 | 2015-11-11 | QTR2 | 15/16 | 214 | 1560659.59 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2551 | 43035225201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 180 | 237 | 235 | 2 | 0 | 0 | 41 | 16 | 6221583 | 61863 | 6159720 | 6221583 | 6254748 | 0 | 0 | 0 | 6254748 | 5599650 | -655098 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-01 | QTR2 | 15/16 | 2015-09-14 | QTR1 | 15/16 | 214 | 6248824.82 | B0 | ACC - LUMP SUM | 16 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2552 | 43055415201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 90 | 114 | 114 | 0 | 0 | 0 | 19 | 5 | 1940620 | 50000 | 1890620 | 1940620 | 1924570 | 0 | 0 | 0 | 1924570 | 1856552 | -68018 | 0 | 14 | 0 | 5 | 7272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7272 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-10-01 | QTR2 | 15/16 | 2015-05-28 | QTR4 | 14/15 | 214 | 2021176.83 |  |  | 5 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2554 | 43112915201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 140 | 151 | 150 | 1 | 0 | 0 | 11 | 0 | 4054390 | 50000 | 4004390 | 4054390 | 4069302 | 0 | 0 | 0 | 4069302 | 3749497 | -319805 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F580952077 | SCRUGGS COMPANY (THE) | N/A | N/A | N/A | N/A | 2015-10-21 | QTR2 | 15/16 | 2015-06-19 | QTR4 | 14/15 | 209 | 4996678.96 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2556 | 21007535201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 280 | 288 | 236 | 52 | 0 | 0 | 8 | 0 | 1492042 | 50000 | 1442042 | 1492042 | 1448762 | 0 | 0 | 0 | 1448762 | 1448762 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 8900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8900 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-12-11 | QTR2 | 15/16 | 2015-08-28 | QTR1 | 15/16 | 209 | 1755423.21 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2560 | 43054615201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 120 | 165 | 163 | 2 | 0 | 0 | 45 | 0 | 2422564 | 50000 | 2372564 | 2422564 | 2506188 | 0 | 0 | 0 | 2506188 | 2389680 | -116508 | 0 | 41 | 0 | 0 | 4281 | 0 | 0 | 0 | 5345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568 | 0 | 0 | 0 | 1357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13550 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-14 | QTR2 | 15/16 | 2015-08-07 | QTR1 | 15/16 | 208 | 2628642.62 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2Q76 | 42931315201 | 2013-02-20 | QTR3 | 12/13 | 1 | 2 | 150 | 217 | 470 | -253 | 253 | 0 | 67 | 0 | 645001 | 40470 | 604531 | 605429 | 554900 | -15320 | 0 | -15320 | 539579 | 539579 | 0 | -39572 | 18 | 0 | 0 | -50000 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | -39572 | 0 | F420429710 | DEVELOPERS SURETY AND INDEMNITY COMPANY | N/A | N/A | N/A | N/A | 2015-11-24 | QTR2 | 15/16 | 2014-10-09 | QTR2 | 14/15 | 209 | 892356.39 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Q95 | 42886915201 | 2012-09-19 | QTR1 | 12/13 | 1 | 1 | 45 | 76 | 121 | -45 | 45 | 0 | 15 | 16 | 86971 | 6529 | 80442 | 96284 | 96295 | -16502 | 0 | -16502 | 79792 | 79792 | 0 | 9314 | 6 | 0 | 2 | 9795 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9795 | 0 | F592733482 | ONAS CORPORATION | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 | 2013-04-12 | QTR4 | 12/13 | 208 | 85579.8 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R18 | 42468515201 | 2013-05-23 | QTR4 | 12/13 | 2 | 2 | 540 | 689 | 689 | 0 | 0 | 0 | 136 | 13 | 8195419 | 86278 | 8109141 | 8206705 | 8178408 | 0 | 0 | 0 | 8178408 | 8124680 | -53727 | 11286 | 89 | 0 | 0 | 43065 | 0 | 0 | 13 | 15182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23141 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 69534 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-08-18 | QTR1 | 15/16 | 2015-06-03 | QTR4 | 14/15 | 214 | 8761555.44 | B8 | ACC - DESIGN/BUILD - MAJOR | 13 | 47 | 0 | 0 | -11855 | 0 |  | DO
02DO | 02 | E2R93 | 42607215201 | 2013-08-21 | QTR1 | 13/14 | 1 | 1 | 285 | 344 | 418 | -74 | 74 | 0 | 59 | 0 | 1520777 | 50000 | 1470777 | 1520777 | 1507456 | -61280 | 0 | -61280 | 1446176 | 1443425 | -2751 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 14250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 14250 | 0 | F650447555 | L & S CONCRETE RESTORATION INC | N/A | N/A | N/A | N/A | 2015-11-17 | QTR2 | 15/16 | 2015-02-27 | QTR3 | 14/15 | 208 | 1839323.68 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R94 | 42822915201 | 2013-08-21 | QTR1 | 13/14 | 1 | 0 | 469 | 536 | 533 | 3 | 0 | 0 | 35 | 32 | 2445796 | 50000 | 2395796 | 2445796 | 2450466 | 0 | 0 | 0 | 2450466 | 2449755 | -711 | 0 | 13 | 0 | 0 | 20184 | 0 | 0 | 32 | 14554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 49896 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-17 | QTR1 | 15/16 | 2015-06-12 | QTR4 | 14/15 | 216 | 2404678.02 |  |  | 32 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2S71 | 42869515201 | 2014-04-23 | QTR4 | 13/14 | 1 | 1 | 230 | 307 | 307 | 0 | 0 | 0 | 56 | 21 | 7686286 | 65080 | 7621206 | 7580608 | 7142686 | 0 | 0 | 0 | 7142686 | 6953829 | -188858 | -105678 | 42 | 0 | 0 | 0 | 0 | 0 | 21 | 57675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | -48003 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 | 2015-05-14 | QTR4 | 14/15 | 209 | 6348256.45 |  |  | 21 | 14 | 0 | 0 | -105678 | 0 |  | DO
02DO | 02 | E2S89 | 20954125201 | 2014-04-23 | QTR4 | 13/14 | 1 | 0 | 360 | 373 | 340 | 33 | 0 | 0 | 13 | 0 | 1997720 | 50000 | 1947720 | 1997720 | 2088940 | 0 | 0 | 0 | 2088940 | 2081779 | -7161 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 | 2015-06-16 | QTR4 | 14/15 | 208 | 2345342.1 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T03 | 42871115201 | 2014-07-23 | QTR1 | 14/15 | 1 | 0 | 255 | 322 | 322 | 0 | 0 | 0 | 64 | 3 | 5283383 | 50000 | 5233383 | 5283383 | 4965217 | 0 | 0 | 0 | 4965217 | 4630053 | -335164 | 0 | 34 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-11-24 | QTR2 | 15/16 | 2015-08-22 | QTR1 | 15/16 | 208 | 4581887.25 |  |  | 3 | 23 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T06 | 43074715201 | 2014-07-23 | QTR1 | 14/15 | 1 | 0 | 90 | 96 | 96 | 0 | 0 | 0 | 6 | 0 | 205480 | 7889 | 197591 | 205480 | 200119 | 0 | 0 | 0 | 200119 | 200119 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 | 2015-05-27 | QTR4 | 14/15 | 209 | 167996.51 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T32 | 43194215201 | 2014-12-10 | QTR2 | 14/15 | 1 | 1 | 120 | 164 | 164 | 0 | 0 | 0 | 20 | 24 | 1419048 | 50000 | 1369048 | 1578817 | 1549237 | 0 | 0 | 0 | 1549237 | 1549237 | 0 | 159769 | 18 | 0 | 0 | 0 | 0 | 0 | 24 | 163983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 163983 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-12-21 | QTR2 | 15/16 | 2015-11-17 | QTR2 | 15/16 | 216 | 1414155.44 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3088 | 21894615201 | 2012-07-25 | QTR1 | 12/13 | 1 | 6 | 608 | 853 | 852 | 1 | 0 | 0 | 205 | 40 | 13348458 | 0 | 13348458 | 13883485 | 14095924 | 0 | 0 | 0 | 14095924 | 14095514 | -409 | 535027 | 149 | 0 | 0 | 90305 | 0 | 0 | 40 | 281269 | 169088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 414064 | 169088 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 | 2015-02-24 | QTR3 | 14/15 | 321 | 14378815.2 |  |  | 10 | 56 | 0 | 0 | -173321 | 0 |  | CO
03CO | 03 | T3311 | 22041265201 | 2009-06-17 | QTR4 | 08/09 | 1 | 6 | 800 | 1260 | 1323 | -63 | 63 | 0 | 157 | 303 | 5621006 | 87031 | 5533975 | 6208685 | 6054584 | -158382 | 0 | -158382 | 5896202 | 6102577 | 206375 | 587679 | 74 | 0 | 0 | 14881 | 0 | 0 | 301 | 643272 | 420470 | 0 | 0 | 0 | 0 | 0 | 0 | -31593 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | -52050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 52356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303 | 630166 | 420470 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-11-03 | QTR2 | 15/16 | 2013-04-04 | QTR4 | 12/13 | 308 | 9080395.55 | ARRA | AMERICAN RECOVERY AND REINVEST | 2 | 83 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3396 | 42323315201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 300 | 504 | 498 | 6 | 0 | 0 | 173 | 31 | 2789487 | 50000 | 2739487 | 2763621 | 2700963 | 0 | 0 | 0 | 2700963 | 2673321 | -27642 | -25866 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 17268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | -8599 | 0 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-05-18 | QTR4 | 14/15 | 314 | 2906373.5 |  |  | 31 | 19 | 0 | 0 | -25866 | 0 |  | CO
03CO | 03 | T3401 | 42323415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 300 | 478 | 474 | 4 | 0 | 0 | 178 | 0 | 2645210 | 50000 | 2595210 | 2645210 | 2628131 | 0 | 0 | 0 | 2628131 | 2609172 | -18959 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2015-07-06 | QTR1 | 15/16 | 2015-05-08 | QTR4 | 14/15 | 314 | 2957617.43 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3409 | 42462215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 145 | 201 | 197 | 4 | 0 | 0 | 56 | 0 | 2097227 | 50000 | 2047227 | 2097227 | 2093592 | 0 | 0 | 0 | 2093592 | 1978887 | -114705 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-15 | QTR1 | 15/16 | 2015-05-05 | QTR4 | 14/15 | 321 | 2813050.27 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3411 | 42636815201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 130 | 196 | 196 | 0 | 0 | 0 | 66 | 0 | 577753 | 0 | 577753 | 577753 | 581122 | 0 | 0 | 0 | 581122 | 581122 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263312611 | R B M CONTRACTING SERVICES LLC | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 | 2015-07-22 | QTR1 | 15/16 | 313 | 613088.19 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3423 | 42164425201 | 2013-03-27 | QTR3 | 12/13 | 3 | 6 | 530 | 798 | 798 | 0 | 0 | 0 | 237 | 31 | 12358153 | 132771 | 12225382 | 11830936 | 14453163 | 0 | 0 | 0 | 14453163 | 14207037 | -246126 | -527216 | 209 | 0 | 4 | 106851 | 0 | 0 | 22 | 178456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -777502 | 1039155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 79271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | -412925 | 1039155 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-09 | QTR2 | 15/16 | 2015-08-19 | QTR1 | 15/16 | 308 | 13406269.99 |  |  | 5 | 28 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3424 | 41343515201 | 2013-02-06 | QTR3 | 12/13 | 2 | 3 | 355 | 512 | 508 | 4 | 0 | 0 | 142 | 15 | 3882641 | 50000 | 3832641 | 3972326 | 3728903 | 0 | 0 | 0 | 3728903 | 3719464 | -9439 | 89685 | 86 | 0 | 4 | 26009 | 0 | 39 | 11 | 77908 | 92400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 15 | 103918 | 92400 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 | 2014-09-16 | QTR1 | 14/15 | 308 | 4647469.69 |  |  | 15 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3434 | 42987815201 | 2014-08-27 | QTR1 | 14/15 | 2 | 0 | 160 | 197 | 197 | 0 | 0 | 0 | 35 | 2 | 459930 | 20930 | 439000 | 459930 | 451610 | 0 | 0 | 0 | 451610 | 451610 | 0 | 0 | 17 | 0 | 0 | 1560 | 0 | 0 | 2 | 11050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12610 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 | 2015-06-15 | QTR4 | 14/15 | 313 | 439830 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 2 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3455 | 43000415201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 150 | 176 | 176 | 0 | 0 | 0 | 26 | 0 | 919509 | 0 | 919509 | 919509 | 927409 | 0 | 0 | 0 | 927409 | 927409 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 | 2015-07-16 | QTR1 | 15/16 | 308 | 817764.49 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3468 | 42696515201 | 2014-06-18 | QTR4 | 13/14 | 2 | 0 | 220 | 294 | 284 | 10 | 0 | 0 | 74 | 0 | 1826839 | 50000 | 1776839 | 1826839 | 1794755 | 0 | 0 | 0 | 1794755 | 1727691 | -67064 | 0 | 24 | 0 | 0 | 14633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 1080 | 0 | 0 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 18747 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 | 2015-06-15 | QTR4 | 14/15 | 321 | 1783054.33 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3476 | 42385815201 | 2014-03-26 | QTR3 | 13/14 | 1 | 1 | 276 | 370 | 370 | 0 | 0 | 0 | 47 | 47 | 2307108 | 50000 | 2257108 | 2297266 | 2266725 | 0 | 0 | 0 | 2266725 | 2239507 | -27218 | -9842 | 28 | 0 | 47 | 24743 | 0 | 0 | 0 | 11268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 28194 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 | 2015-06-16 | QTR4 | 14/15 | 321 | 2319570.2 |  |  | 47 | 19 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3502 | 42764915201 | 2014-06-18 | QTR4 | 13/14 | 2 | 2 | 125 | 199 | 197 | 2 | 0 | 0 | 63 | 11 | 633977 | 26778 | 607199 | 703188 | 695402 | 0 | 0 | 0 | 695402 | 695402 | 0 | 69211 | 34 | 0 | 8 | 5089 | 0 | 0 | 3 | 70611 | 25322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 11 | 75699 | 25322 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-08-19 | QTR1 | 15/16 | 2015-05-21 | QTR4 | 14/15 | 308 | 559212.99 |  |  | 8 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3510 | 43077615201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 190 | 241 | 240 | 1 | 0 | 0 | 51 | 0 | 3964092 | 50000 | 3914092 | 3964092 | 4024706 | 0 | 0 | 0 | 4024706 | 3718840 | -305866 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 11957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11957 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-28 | QTR2 | 15/16 | 2015-09-01 | QTR1 | 15/16 | 314 | 4154252.32 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3530 | 43174415201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 60 | 67 | 66 | 1 | 0 | 0 | 7 | 0 | 217000 | 0 | 217000 | 217000 | 216611 | 0 | 0 | 0 | 216611 | 216611 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593715775 | PYRAMID EXCAVATION INC. | N/A | N/A | N/A | N/A | 2015-09-08 | QTR1 | 15/16 | 2015-06-19 | QTR4 | 14/15 | 321 | 236371.06 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3532 | 43253215201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 120 | 143 | 143 | 0 | 0 | 0 | 23 | 0 | 3173126 | 50000 | 3123126 | 3173126 | 3259005 | 0 | 0 | 0 | 3259005 | 3171161 | -87844 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 | 2015-09-11 | QTR1 | 15/16 | 314 | 2959991 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3535 | 42693615201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 85 | 109 | 109 | 0 | 0 | 0 | 24 | 0 | 481388 | 26436 | 454953 | 481388 | 440397 | 0 | 0 | 0 | 440397 | 440397 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 | 2015-06-21 | QTR4 | 14/15 | 313 | 540650.67 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3536 | 40393125201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 60 | 69 | 69 | 0 | 0 | 0 | 9 | 0 | 369064 | 23136 | 345929 | 369064 | 338614 | 0 | 0 | 0 | 338614 | 338614 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2015-07-21 | QTR1 | 15/16 | 2015-06-13 | QTR4 | 14/15 | 321 | 486851.74 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3540 | 21988025201 | 2015-01-28 | QTR3 | 14/15 | 1 | 0 | 120 | 141 | 141 | 0 | 0 | 0 | 21 | 0 | 347017 | 16058 | 330959 | 347017 | 338632 | 0 | 0 | 0 | 338632 | 338632 | 0 | 0 | 15 | 0 | 0 | 354 | 0 | 0 | 0 | 4919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5272 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-11-02 | QTR2 | 15/16 | 2015-08-24 | QTR1 | 15/16 | 321 | 352628.28 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3555 | 43630635201 | 2015-04-29 | QTR4 | 14/15 | 3 | 0 | 60 | 66 | 66 | 0 | 0 | 0 | 6 | 0 | 409629 | 0 | 409629 | 409629 | 409629 | 0 | 0 | 0 | 409629 | 409629 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 | 2015-09-16 | QTR1 | 15/16 | 321 | 270025.98 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3K74 | 42692815201 | 2014-11-13 | QTR2 | 14/15 | 1 | 0 | 160 | 219 | 219 | 0 | 0 | 0 | 47 | 12 | 1363705 | 50000 | 1313705 | 1363705 | 1373851 | 0 | 0 | 0 | 1373851 | 1311778 | -62073 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 30968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 30968 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-12-17 | QTR2 | 15/16 | 2015-09-11 | QTR1 | 15/16 | 308 | 1604605.95 |  |  | 12 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L71 | 42874415201 | 2014-03-13 | QTR3 | 13/14 | 1 | 0 | 160 | 192 | 192 | 0 | 0 | 0 | 32 | 0 | 1490639 | 50000 | 1440639 | 1490639 | 1445553 | 0 | 0 | 0 | 1445553 | 1451830 | 6277 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 | 2014-12-14 | QTR2 | 14/15 | 314 | 1584506.78 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L98 | 42874615201 | 2014-11-13 | QTR2 | 14/15 | 2 | 1 | 180 | 201 | 200 | 1 | 0 | 0 | 21 | 0 | 4259734 | 50000 | 4209734 | 4287109 | 4172519 | 0 | 0 | 0 | 4172519 | 3907768 | -264750 | 27375 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 27375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27375 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-11-03 | QTR2 | 15/16 | 2015-08-20 | QTR1 | 15/16 | 321 | 4989174.47 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M60 | 42697215201 | 2014-12-11 | QTR2 | 14/15 | 1 | 0 | 100 | 134 | 134 | 0 | 0 | 0 | 32 | 2 | 1718927 | 50000 | 1668927 | 1718927 | 1766800 | 0 | 0 | 0 | 1766800 | 1673682 | -93118 | 0 | 10 | 0 | 2 | 3651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3651 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-07-22 | QTR1 | 15/16 | 308 | 2202753.65 |  |  | 2 | 22 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M93 | 43078215201 | 2014-12-11 | QTR2 | 14/15 | 1 | 0 | 70 | 77 | 76 | 1 | 0 | 0 | 6 | 1 | 1217750 | 50000 | 1167750 | 1217750 | 1189202 | 0 | 0 | 0 | 1189202 | 1136275 | -52927 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2880 | 0 | F580538940 | OXFORD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 | 2015-07-08 | QTR1 | 15/16 | 314 | 1216619.67 |  |  | 1 | 1 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N07 | 43460315201 | 2015-07-09 | QTR1 | 15/16 | 1 | 0 | 28 | 28 | 27 | 1 | 0 | 0 | 0 | 0 | 31110 | 1910 | 29200 | 31110 | 28465 | 0 | 0 | 0 | 28465 | 28465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-12-10 | QTR2 | 15/16 | 2015-10-26 | QTR2 | 15/16 | 308 | 45126.8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N22 | 41547435201 | 2014-10-09 | QTR2 | 14/15 | 1 | 1 | 90 | 168 | 168 | 0 | 0 | 0 | 37 | 41 | 785011 | 50000 | 735011 | 874968 | 824968 | 0 | 0 | 0 | 824968 | 824968 | 0 | 89957 | 33 | 0 | 0 | 0 | 0 | 0 | 41 | 89957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 89957 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2015-12-08 | QTR2 | 15/16 | 2015-08-07 | QTR1 | 15/16 | 308 | 1252571.9 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N70 | 41694415201 | 2014-11-13 | QTR2 | 14/15 | 1 | 1 | 120 | 166 | 163 | 3 | 0 | 0 | 41 | 5 | 2595171 | 50000 | 2545171 | 2642211 | 2488780 | 0 | 0 | 0 | 2488780 | 2390489 | -98291 | 47040 | 34 | 0 | 0 | 3190 | 0 | 0 | 3 | 47040 | 23968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 51468 | 23968 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2015-11-09 | QTR2 | 15/16 | 2015-08-17 | QTR1 | 15/16 | 314 | 2402720.45 |  |  | 2 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N81 | 43558115201 | 2015-05-14 | QTR4 | 14/15 | 1 | 1 | 60 | 80 | 80 | 0 | 0 | 0 | 10 | 10 | 154105 | 5690 | 148415 | 159104 | 150561 | 0 | 0 | 0 | 150561 | 150561 | 0 | 4999 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4999 | 4999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4999 | 4999 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-12-28 | QTR2 | 15/16 | 2015-10-22 | QTR2 | 15/16 | 308 | 119492.78 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4255 | 40398415201 | 2010-12-08 | QTR2 | 10/11 | 1 | 24 | 920 | 1352 | 1352 | 0 | 0 | 0 | 186 | 246 | 36988133 | 150000 | 36838133 | 40660763 | 41250312 | 0 | 0 | 0 | 41250312 | 41508810 | 258498 | 3672630 | 127 | 0 | 0 | 712871 | 128765 | 0 | 246 | 4139811 | 2271858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1705619 | 30394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205492 | 0 | 0 | 0 | 271969 | 271969 | 0 | 0 | 115942 | 115942 | 0 | 0 | 0 | 0 | 0 | 246 | 3740465 | 2818928 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-12-17 | QTR2 | 15/16 | 2015-03-17 | QTR3 | 14/15 | 412 | 44275084.25 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4311 | 42924615201 | 2011-04-27 | QTR4 | 10/11 | 1 | 1 | 180 | 266 | 319 | -53 | 53 | 0 | 48 | 38 | 3983113 | 50000 | 3933113 | 4102286 | 4023382 | -101442 | 0 | -101442 | 3921940 | 3920334 | -1606 | 119174 | 36 | 0 | 2 | 3257 | 0 | 0 | 33 | 132841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 136098 | 0 | F593749359 | DESIGN-BUILD ENGINEERS & CONTRA | N/A | N/A | N/A | N/A | 2015-08-20 | QTR1 | 15/16 | 2012-05-07 | QTR4 | 11/12 | 409 | 3335896.13 |  |  | 9 | 12 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4345 | 40836215201 | 2013-05-22 | QTR4 | 12/13 | 1 | 5 | 266 | 650 | 650 | 0 | 0 | 0 | 89 | 295 | 1202547 | 50000 | 1152547 | 3085087 | 3080524 | 0 | 0 | 0 | 3080524 | 3080524 | 0 | 1882539 | 48 | 14 | 266 | 1575597 | 0 | 0 | 29 | 324673 | 98769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8860 | 8860 | 0 | 0 | 0 | 0 | 14 | 295 | 1908989 | 107629 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 | 2015-05-21 | QTR4 | 14/15 | 412 | 1238644.33 |  |  | 118 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4374 | 43019615201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 102 | 112 | 110 | 2 | 0 | 0 | 10 | 0 | 348825 | 18115 | 330710 | 348825 | 339314 | 0 | 0 | 0 | 339314 | 339314 | 0 | 0 | 9 | 0 | 0 | 3246 | 0 | 0 | 0 | 5358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8604 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-22 | QTR1 | 15/16 | 2015-06-10 | QTR4 | 14/15 | 412 | 385157.48 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4380 | 42974015201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 100 | 118 | 117 | 1 | 0 | 0 | 18 | 0 | 480024 | 22736 | 457288 | 480024 | 456013 | 0 | 0 | 0 | 456013 | 456013 | 0 | 0 | 16 | 0 | 0 | 2267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2267 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2015-08-28 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 412 | 486438.28 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4384 | 42973815201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 96 | 101 | 99 | 2 | 0 | 0 | 5 | 0 | 547622 | 25962 | 521660 | 548351 | 527560 | 0 | 0 | 0 | 527560 | 527560 | 0 | 729 | 4 | 0 | 0 | 1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-04 | QTR1 | 15/16 | 2015-07-02 | QTR1 | 15/16 | 409 | 546487.47 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4394 | 43060225203 | 2014-05-21 | QTR4 | 13/14 | 3 | 1 | 243 | 281 | 280 | 1 | 0 | 0 | 38 | 0 | 831515 | 40849 | 790666 | 893080 | 843974 | 0 | 0 | 0 | 843974 | 843974 | 0 | 61565 | 26 | 0 | 0 | 2400 | 0 | 0 | 0 | 68329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70729 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 | 2015-06-08 | QTR4 | 14/15 | 412 | 850266.14 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4398 | 42974115201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 126 | 160 | 160 | 0 | 0 | 0 | 34 | 0 | 420985 | 20915 | 400070 | 420985 | 395082 | 0 | 0 | 0 | 395082 | 395082 | 0 | 0 | 32 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-10-15 | QTR2 | 15/16 | 2015-09-03 | QTR1 | 15/16 | 412 | 439143.73 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4L95 | 41304815201 | 2011-06-21 | QTR4 | 10/11 | 1 | 5 | 878 | 1407 | 1406 | 1 | 0 | 0 | 447 | 82 | 54423100 | 150000 | 54273100 | 54843389 | 54825050 | 0 | 0 | 0 | 54825050 | 54583811 | -241240 | 420289 | 367 | 15 | 82 | 536157 | 0 | 0 | 0 | 5762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 82 | 542342 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 | 2015-08-03 | QTR1 | 15/16 | 408 | 56635287.97 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 6 | 59 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P28 | 43053415201 | 2014-01-03 | QTR3 | 13/14 | 1 | 1 | 265 | 342 | 335 | 7 | 0 | 0 | 77 | 0 | 1630613 | 50000 | 1580613 | 1680613 | 1713025 | 0 | 0 | 0 | 1713025 | 1712786 | -239 | 50000 | 15 | 45 | 0 | 0 | 0 | 0 | 0 | 46404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 46404 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2015-08-13 | QTR1 | 15/16 | 2015-07-09 | QTR1 | 15/16 | 408 | 1510582.53 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P42 | 42744115201 | 2014-05-02 | QTR4 | 13/14 | 1 | 0 | 237 | 285 | 285 | 0 | 0 | 0 | 18 | 30 | 1055000 | 50000 | 1005000 | 1055000 | 1018660 | 0 | 0 | 0 | 1018660 | 1018660 | 0 | 0 | 7 | 0 | 0 | 5225 | 0 | 0 | 30 | 11535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 16760 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-09-24 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 409 | 1104492 | B0 | ACC - LUMP SUM | 30 | 11 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P43 | 42636215201 | 2014-03-31 | QTR3 | 13/14 | 1 | 0 | 371 | 415 | 411 | 4 | 0 | 0 | 40 | 4 | 2106087 | 50000 | 2056087 | 2106087 | 2037825 | 0 | 0 | 0 | 2037825 | 2037825 | 0 | 0 | 25 | 0 | 0 | 4164 | 0 | 0 | 0 | 5698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 15442 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-09-16 | QTR1 | 15/16 | 2015-08-14 | QTR1 | 15/16 | 408 | 2671513.63 |  |  | 4 | 15 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P91 | 43397915201 | 2014-06-06 | QTR4 | 13/14 | 4 | 1 | 223 | 291 | 290 | 1 | 0 | 0 | 48 | 20 | 682040 | 21400 | 660640 | 677370 | 696418 | 0 | 0 | 0 | 696418 | 696418 | 0 | -4669 | 31 | 0 | 0 | 5986 | 0 | 0 | 20 | 10647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 11963 | 0 | F364509634 | MAYTIN ENGINEERING CORP. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 | 2015-07-10 | QTR1 | 15/16 | 412 | 468107.77 |  |  | 20 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q13 | 43060515201 | 2014-08-01 | QTR1 | 14/15 | 1 | 0 | 303 | 346 | 346 | 0 | 0 | 0 | 43 | 0 | 3035506 | 50000 | 2985506 | 3035506 | 2614486 | 0 | 0 | 0 | 2614486 | 2545146 | -69341 | 0 | 13 | 0 | 0 | 0 | 0 | 21 | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 1925 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-30 | QTR2 | 15/16 | 2015-09-28 | QTR1 | 15/16 | 412 | 3179103.94 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q62 | 42993615201 | 2015-01-09 | QTR3 | 14/15 | 1 | 0 | 115 | 122 | 121 | 1 | 0 | 0 | 7 | 0 | 886950 | 50000 | 836950 | 886950 | 810170 | 0 | 0 | 0 | 810170 | 810170 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-11-05 | QTR2 | 15/16 | 2015-09-30 | QTR1 | 15/16 | 408 | 1238736 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q67 | 42824115201 | 2015-02-06 | QTR3 | 14/15 | 2 | 1 | 90 | 119 | 118 | 1 | 0 | 0 | 12 | 17 | 186978 | 11022 | 175956 | 221816 | 214581 | 0 | 0 | 0 | 214581 | 214581 | 0 | 34838 | 10 | 0 | 17 | 34838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 34838 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2015-11-18 | QTR2 | 15/16 | 2015-10-20 | QTR2 | 15/16 | 408 | 231295.35 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q81 | 43400615201 | 2015-04-03 | QTR4 | 14/15 | 2 | 0 | 100 | 103 | 70 | 33 | 0 | 0 | 3 | 0 | 436152 | 20024 | 416128 | 436152 | 404357 | 0 | 0 | 0 | 404357 | 404357 | 0 | 0 | 1 | 0 | 0 | 2660 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2990 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-11-05 | QTR2 | 15/16 | 2015-10-02 | QTR2 | 15/16 | 409 | 395430.51 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | BDT74 | 41299435201 | 2011-11-07 | QTR2 | 11/12 | 5 | 15 | 460 | 802 | 1058 | -256 | 256 | 0 | 77 | 265 | 27584500 | 150000 | 27434500 | 29571831 | 29554288 | 0 | 0 | 0 | 29554288 | 29554288 | 0 | 1987331 | 26 | 0 | 0 | 294952 | 5697 | 0 | 0 | 366049 | 3040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 1475287 | 169381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 2136288 | 178118 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2015-09-07 | QTR1 | 15/16 | 2015-02-11 | QTR3 | 14/15 | 507 | 27584500 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5401 | 42201515201 | 2013-04-24 | QTR4 | 12/13 | 4 | 5 | 290 | 361 | 361 | 0 | 0 | 0 | 50 | 21 | 4603457 | 50000 | 4553457 | 4806215 | 4675801 | 0 | 0 | 0 | 4675801 | 4675281 | -520 | 202758 | 32 | 0 | 5 | 67573 | 12260 | 0 | 16 | 186828 | 13247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 254401 | 25507 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-08 | QTR1 | 15/16 | 2014-08-18 | QTR1 | 14/15 | 509 | 4500359.97 |  |  | 3 | 18 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5404 | 24023335201 | 2012-05-23 | QTR4 | 11/12 | 5 | 6 | 710 | 980 | 980 | 0 | 0 | 0 | 165 | 105 | 10111333 | 50000 | 10061333 | 10458539 | 10091859 | 0 | 0 | 0 | 10091859 | 10008344 | -83514 | 347206 | 129 | 0 | 21 | 292661 | 435 | 0 | 84 | 60822 | 1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 355274 | 1518 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-11 | QTR2 | 15/16 | 2015-05-03 | QTR4 | 14/15 | 507 | 9890702.1 |  |  | 105 | 36 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5417 | 40735545201 | 2012-04-25 | QTR4 | 11/12 | 1 | 2 | 870 | 1082 | 1082 | 0 | 0 | 0 | 133 | 79 | 18388845 | 150000 | 18238845 | 18447512 | 18384136 | 0 | 0 | 0 | 18384136 | 18074458 | -309678 | 58667 | 85 | 0 | 15 | 46621 | 19776 | 0 | 7 | 79676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 38891 | 38891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 165189 | 58667 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-11-25 | QTR2 | 15/16 | 2015-07-02 | QTR1 | 15/16 | 513 | 20359976.85 |  |  | 15 | 48 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5419 | 23953555201 | 2012-06-27 | QTR4 | 11/12 | 4 | 9 | 800 | 863 | 863 | 0 | 0 | 0 | 63 | 0 | 15255527 | 150000 | 15105527 | 14971879 | 14890213 | 0 | 0 | 0 | 14890213 | 14848574 | -41639 | -283648 | 45 | 0 | 0 | 137015 | 0 | 0 | 0 | 68402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -245067 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-12-11 | QTR2 | 15/16 | 2015-05-29 | QTR4 | 14/15 | 509 | 17113122.57 |  |  | 0 | 18 | 0 | 0 | -463188 | 0 |  | CO
05CO | 05 | T5427 | 43174815201 | 2012-10-31 | QTR2 | 12/13 | 1 | 0 | 90 | 126 | 132 | -6 | 6 | 0 | 22 | 14 | 398541 | 16000 | 382541 | 398541 | 381567 | 0 | 0 | 0 | 381567 | 381567 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | F592733482 | ONAS CORPORATION | N/A | N/A | N/A | N/A | 2015-10-02 | QTR2 | 15/16 | 2013-06-04 | QTR4 | 12/13 | 513 | 490626 |  |  | 14 | 6 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5464 | 42363025201 | 2014-04-30 | QTR4 | 13/14 | 1 | 0 | 250 | 322 | 322 | 0 | 0 | 0 | 57 | 15 | 1180000 | 50000 | 1130000 | 1180000 | 1130000 | 0 | 0 | 0 | 1130000 | 1130000 | 0 | 0 | 34 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-10-07 | QTR2 | 15/16 | 2015-09-03 | QTR1 | 15/16 | 514 | 1074627.1 | B0 | ACC - LUMP SUM | 15 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5483 | 42727915201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 200 | 273 | 273 | 0 | 0 | 0 | 63 | 10 | 2914000 | 50000 | 2864000 | 2914000 | 2885939 | 0 | 0 | 0 | 2885939 | 2771829 | -114111 | 0 | 37 | 0 | 10 | 1702 | 0 | 0 | 0 | 14745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 16446 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-20 | QTR1 | 15/16 | 2015-06-12 | QTR4 | 14/15 | 513 | 2978859.49 | B0 | ACC - LUMP SUM | 10 | 26 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5488 | 42907915201 | 2013-12-04 | QTR2 | 13/14 | 1 | 0 | 290 | 439 | 439 | 0 | 0 | 0 | 149 | 0 | 5354000 | 59000 | 5295000 | 5354000 | 5430627 | -11100 | 0 | -11100 | 5419527 | 5329312 | -90214 | 0 | 128 | 0 | 0 | 17682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17682 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-18 | QTR1 | 15/16 | 2015-05-29 | QTR4 | 14/15 | 509 | 5993024.89 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5494 | 42488715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 180 | 247 | 247 | 0 | 0 | 0 | 67 | 0 | 1795728 | 50000 | 1745728 | 1795728 | 1805364 | 0 | 0 | 0 | 1805364 | 1760006 | -45358 | 0 | 46 | 0 | 0 | 5154 | 0 | 0 | 0 | 24811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29965 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 | 2015-05-11 | QTR4 | 14/15 | 514 | 1761956.22 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5495 | 42886715201 | 2014-05-21 | QTR4 | 13/14 | 1 | 1 | 300 | 328 | 303 | 25 | 0 | 0 | 28 | 0 | 6951000 | 72000 | 6879000 | 6886782 | 6967320 | 0 | 0 | 0 | 6967320 | 6782907 | -184413 | -64218 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -72353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -64218 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-08-27 | QTR1 | 15/16 | 2015-06-30 | QTR4 | 14/15 | 509 | 7479522.66 | B0 | ACC - LUMP SUM | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5501 | 42886215201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 110 | 176 | 176 | 0 | 0 | 0 | 66 | 0 | 2189795 | 50000 | 2139795 | 2189795 | 2201353 | 0 | 0 | 0 | 2201353 | 2169152 | -32201 | 0 | 42 | 0 | 0 | 54576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54576 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 | 2015-04-24 | QTR4 | 14/15 | 507 | 2211253.07 | B0 | ACC - LUMP SUM | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5503 | 42868815201 | 2014-08-27 | QTR1 | 14/15 | 1 | 0 | 220 | 263 | 262 | 1 | 0 | 0 | 29 | 14 | 2402000 | 50000 | 2352000 | 2402000 | 2340586 | 0 | 0 | 0 | 2340586 | 2178963 | -161623 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 45453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 45453 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2015-11-30 | QTR2 | 15/16 | 2015-10-09 | QTR2 | 15/16 | 513 | 2568891.1 | B0 | ACC - LUMP SUM | 14 | 14 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5518 | 43471315201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 120 | 137 | 127 | 10 | 0 | 0 | 17 | 0 | 813663 | 46000 | 767663 | 813663 | 766183 | 0 | 0 | 0 | 766183 | 766183 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-12-15 | QTR2 | 15/16 | 2015-10-01 | QTR2 | 15/16 | 507 | 994320 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5520 | 23867825201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 118 | 129 | 106 | 23 | 0 | 0 | 11 | 0 | 544771 | 36000 | 508771 | 536238 | 524085 | 0 | 0 | 0 | 524085 | 520797 | -3288 | -8533 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1651 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 | 2015-06-01 | QTR4 | 14/15 | 512 | 761207.45 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5539 | 43471215201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 120 | 130 | 130 | 0 | 0 | 0 | 10 | 0 | 1710446 | 50000 | 1660446 | 1710446 | 1675126 | 0 | 0 | 0 | 1675126 | 1675126 | 0 | 0 | 5 | 0 | 0 | 16193 | 0 | 0 | 0 | 2170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18363 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2015-12-23 | QTR2 | 15/16 | 2015-10-05 | QTR2 | 15/16 | 513 | 2082709.85 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5L71 | 41299445201 | 2009-02-23 | QTR3 | 08/09 | 15 | 55 | 810 | 1383 | 1383 | 0 | 0 | 0 | 67 | 506 | 163288700 | 450000 | 162838700 | 196216668 | 195534566 | 0 | 2601667 | 2601667 | 198136233 | 169140051 | -28996182 | 32927968 | 26 | 0 | 0 | 13525802 | 50599 | 0 | 0 | 8209344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506 | 10832312 | 492992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506 | 32675391 | 543591 | F261605378 | ARCHER WESTERN CONTRACTORS-RAIL | N/A | N/A | N/A | N/A | 2015-11-17 | QTR2 | 15/16 | 2015-04-17 | QTR4 | 14/15 | 507 | 0 | B1:B5:B8 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5R02 | 41307215201 | 2011-10-13 | QTR2 | 11/12 | 1 | 2 | 821 | 1119 | 1120 | -1 | 1 | 0 | 223 | 75 | 51759000 | 150000 | 51609000 | 51745315 | 51437545 | 0 | 0 | 0 | 51437545 | 51645443 | 207898 | -13685 | 190 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 35645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 21960 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-10-23 | QTR2 | 15/16 | 2015-01-24 | QTR3 | 14/15 | 514 | 55948237 | B8 | ACC - DESIGN/BUILD - MAJOR | 30 | 33 | 0 | 0 | -13685 | 0 |  | DO
05DO | 05 | E5R52 | 23827565201 | 2012-09-27 | QTR1 | 12/13 | 2 | 8 | 685 | 1010 | 1009 | 1 | 0 | 0 | 164 | 161 | 23633000 | 150000 | 23483000 | 24988747 | 25103249 | 0 | 0 | 0 | 25103249 | 24880177 | -223072 | 1355747 | 126 | 0 | 161 | 1413568 | 0 | 0 | 0 | 50450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1486965 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-12-02 | QTR2 | 15/16 | 2015-08-31 | QTR1 | 15/16 | 507 | 32557148 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 38 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W28 | 41499925201 | 2014-05-06 | QTR4 | 13/14 | 1 | 1 | 100 | 127 | 125 | 2 | 0 | 0 | 12 | 15 | 260959 | 11000 | 249959 | 242155 | 231155 | 0 | 0 | 0 | 231155 | 231155 | 0 | -18805 | 3 | 0 | 0 | 0 | 0 | 0 | 15 | -18805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -18805 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2015-09-08 | QTR1 | 15/16 | 2015-04-15 | QTR4 | 14/15 | 509 | 250000 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W30 | 43214919201 | 2014-02-18 | QTR3 | 13/14 | 1 | 0 | 365 | 380 | 380 | 0 | 0 | 0 | 15 | 0 | 3585585 | 50000 | 3535585 | 3585585 | 3535585 | 0 | 0 | 0 | 3535585 | 0 | -3535585 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-07-10 | QTR1 | 15/16 | 2015-05-29 | QTR4 | 14/15 | 509 | 3478319.3 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W57 | 41299435214 | 2014-06-03 | QTR4 | 13/14 | 1 | 2 | 360 | 370 | 359 | 11 | 0 | 0 | 10 | 0 | 1657000 | 50000 | 1607000 | 1757000 | 1745808 | 0 | 0 | 0 | 1745808 | 1745490 | -318 | 100000 | 2 | 0 | 0 | 35063 | 0 | 0 | 0 | 105738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140801 | 0 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2015-12-02 | QTR2 | 15/16 | 2015-09-02 | QTR1 | 15/16 | 509 | 2729000 | B1:B5 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W68 | 24099295201 | 2014-12-02 | QTR2 | 14/15 | 2 | 0 | 120 | 124 | 121 | 3 | 0 | 0 | 4 | 0 | 518519 | 21000 | 497519 | 518519 | 502367 | 0 | 0 | 0 | 502367 | 502367 | 0 | 0 | 2 | 0 | 0 | 2974 | 0 | 0 | 0 | 3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-07-28 | QTR1 | 15/16 | 2015-07-14 | QTR1 | 15/16 | 513 | 460954.46 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W73 | 43524315201 | 2015-01-06 | QTR3 | 14/15 | 1 | 0 | 150 | 193 | 176 | 17 | 0 | 0 | 43 | 0 | 149000 | 5000 | 144000 | 149000 | 148500 | 0 | 0 | 0 | 148500 | 148500 | 0 | 0 | 25 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | F900605972 | GENESIS CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-11-13 | QTR2 | 15/16 | 2015-10-25 | QTR2 | 15/16 | 514 | 230960.1 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W75 | 43528315201 | 2015-02-03 | QTR3 | 14/15 | 1 | 0 | 150 | 158 | 124 | 34 | 0 | 0 | 8 | 0 | 557571 | 29000 | 528571 | 557571 | 494639 | 0 | 0 | 0 | 494639 | 494639 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-12-10 | QTR2 | 15/16 | 2015-12-01 | QTR2 | 15/16 | 514 | 721944 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6207 | 41984815201 | 2013-05-22 | QTR4 | 12/13 | 3 | 5 | 280 | 396 | 396 | 0 | 0 | 0 | 74 | 42 | 6954601 | 80000 | 6874601 | 7631613 | 7814383 | 0 | 0 | 0 | 7814383 | 7814501 | 117 | 677012 | 49 | 10 | 0 | 192852 | 0 | 0 | 42 | 499242 | 19532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 42 | 692093 | 19532 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-08-06 | QTR1 | 15/16 | 2015-02-26 | QTR3 | 14/15 | 606 | 8225852.05 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6278 | 24994115201 | 2012-05-23 | QTR4 | 11/12 | 4 | 6 | 650 | 1028 | 1028 | 0 | 0 | 0 | 254 | 124 | 14358568 | 211699 | 14146869 | 13941778 | 14063237 | 0 | 0 | 0 | 14063237 | 13981485 | -81752 | -416790 | 215 | 0 | 69 | 338260 | 0 | 0 | 0 | 2917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198178 | 6413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | -283761 | 6413 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2015-09-22 | QTR1 | 15/16 | 2015-07-11 | QTR1 | 15/16 | 606 | 12500128.6 |  |  | 0 | 39 | 0 | 55 | -823116 | 0 |  | CO
06CO | 06 | T6308 | 42751315201 | 2013-06-19 | QTR4 | 12/13 | 3 | 2 | 280 | 454 | 473 | -19 | 19 | 0 | 82 | 92 | 3950337 | 50000 | 3900337 | 4058444 | 4025547 | -45106 | 0 | -45106 | 3980441 | 3968548 | -11893 | 108107 | 40 | 0 | 92 | 72303 | 17559 | 14 | 0 | 23094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 92 | 153504 | 17559 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-12-07 | QTR2 | 15/16 | 2015-05-08 | QTR4 | 14/15 | 606 | 3555731.5 |  |  | 92 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6322 | 42750525201 | 2013-09-25 | QTR1 | 13/14 | 4 | 2 | 240 | 450 | 450 | 0 | 0 | 0 | 210 | 0 | 2272423 | 51180 | 2221243 | 2348653 | 2183494 | 0 | 0 | 0 | 2183494 | 2177671 | -5822 | 76230 | 121 | 0 | 0 | 34580 | 0 | 42 | 0 | 65393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 99973 | 0 | F591782227 | CENTRAL FLORIDA EQUIPMENT RENTALS INC. | N/A | N/A | N/A | N/A | 2015-09-25 | QTR1 | 15/16 | 2015-07-28 | QTR1 | 15/16 | 606 | 2206205.25 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6324 | 42913615201 | 2013-09-25 | QTR1 | 13/14 | 2 | 2 | 260 | 410 | 407 | 3 | 0 | 0 | 150 | 0 | 3959132 | 51415 | 3907717 | 4129233 | 4133336 | 0 | 0 | 0 | 4133336 | 4124281 | -9055 | 170101 | 105 | 0 | 0 | 3694 | 0 | 30 | 0 | 157988 | 70393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 184274 | 70393 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-15 | QTR1 | 15/16 | 2015-04-07 | QTR4 | 14/15 | 606 | 4168713.7 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6327 | 43080515201 | 2014-03-26 | QTR3 | 13/14 | 6 | 0 | 280 | 368 | 366 | 2 | 0 | 0 | 88 | 0 | 4029465 | 50120 | 3979345 | 4029465 | 3868532 | 0 | 0 | 0 | 3868532 | 3761105 | -107427 | 0 | 74 | 0 | 0 | 1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16021 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 | 2015-08-04 | QTR1 | 15/16 | 606 | 4215348.73 | B5:B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6351 | 42904315201 | 2014-02-05 | QTR3 | 13/14 | 3 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 643250 | 39250 | 604000 | 643250 | 597697 | 0 | 0 | 0 | 597697 | 597697 | 0 | 0 | 50 | 0 | 0 | 7236 | 0 | 0 | 0 | 8819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16056 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-17 | QTR1 | 15/16 | 2015-05-06 | QTR4 | 14/15 | 606 | 824250 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6355 | 42902115201 | 2014-05-21 | QTR4 | 13/14 | 2 | 0 | 160 | 194 | 194 | 0 | 0 | 0 | 34 | 0 | 1061111 | 50130 | 1010981 | 1061111 | 1066049 | 0 | 0 | 0 | 1066049 | 1066049 | 0 | 0 | 23 | 0 | 0 | 32501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49048 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-07-24 | QTR1 | 15/16 | 2015-06-22 | QTR4 | 14/15 | 606 | 1021385.13 | B0 | ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6361 | 43003115201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 150 | 191 | 187 | 4 | 0 | 0 | 41 | 0 | 327561 | 14958 | 312603 | 327561 | 279990 | 0 | 0 | 0 | 279990 | 279933 | -57 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263976898 | AMROAD LLC | N/A | N/A | N/A | N/A | 2015-09-24 | QTR1 | 15/16 | 2015-07-31 | QTR1 | 15/16 | 606 | 306614 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6363 | 42751515201 | 2013-05-22 | QTR4 | 12/13 | 1 | 5 | 350 | 521 | 521 | 0 | 0 | 0 | 171 | 0 | 5378636 | 50000 | 5328636 | 5591336 | 6965131 | 0 | 0 | 0 | 6965131 | 6964220 | -911 | 212700 | 97 | 0 | 0 | 415000 | 0 | 34 | 0 | 152786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 45540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 218326 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 | 2015-02-18 | QTR3 | 14/15 | 606 | 4504473.9 |  |  | 0 | 40 | 0 | 0 | -403000 | 0 |  | CO
06CO | 06 | T6368 | 43003315201 | 2014-07-30 | QTR1 | 14/15 | 1 | 1 | 170 | 172 | 137 | 35 | 0 | 0 | 2 | 0 | 619197 | 29000 | 590197 | 643584 | 598711 | 0 | 0 | 0 | 598711 | 598703 | -8 | 24387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24387 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2015-07-10 | QTR1 | 15/16 | 2015-06-04 | QTR4 | 14/15 | 606 | 631340 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6369 | 43081915201 | 2014-10-29 | QTR2 | 14/15 | 1 | 0 | 120 | 180 | 199 | -19 | 19 | 0 | 45 | 15 | 896920 | 46528 | 850392 | 896920 | 810742 | -33098 | 0 | -33098 | 777644 | 777644 | 0 | 0 | 43 | 0 | 15 | 13883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14481 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 | 2015-09-09 | QTR1 | 15/16 | 606 | 973033.4 |  |  | 15 | 2 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6370 | 42913715201 | 2014-08-27 | QTR1 | 14/15 | 3 | 1 | 140 | 221 | 221 | 0 | 0 | 0 | 81 | 0 | 1463328 | 59721 | 1403607 | 1519911 | 1478859 | 0 | 0 | 0 | 1478859 | 1424599 | -54260 | 56583 | 77 | 0 | 0 | 56583 | 0 | 0 | 0 | 5021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65820 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-11-18 | QTR2 | 15/16 | 2015-09-10 | QTR1 | 15/16 | 606 | 1605781.15 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6G56 | 42611915201 | 2013-01-31 | QTR3 | 12/13 | 1 | 0 | 560 | 775 | 774 | 1 | 0 | 0 | 215 | 0 | 4988310 | 58000 | 4930310 | 4988310 | 4865434 | 0 | 0 | 0 | 4865434 | 4865434 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2015-08-03 | QTR1 | 15/16 | 2015-07-02 | QTR1 | 15/16 | 606 | 5875815.5 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6H34 | 42560035201 | 2013-06-27 | QTR4 | 12/13 | 2 | 9 | 240 | 411 | 411 | 0 | 0 | 0 | 171 | 0 | 6337856 | 59110 | 6278746 | 7490311 | 7429547 | 0 | 0 | 0 | 7429547 | 7303699 | -125847 | 1152455 | 27 | 104 | 0 | 168081 | 139232 | 23 | 0 | 976488 | 435329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 0 | 1162568 | 574561 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-12-09 | QTR2 | 15/16 | 2015-06-19 | QTR4 | 14/15 | 606 | 5970124.1 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6H59 | 42999915201 | 2014-03-27 | QTR3 | 13/14 | 1 | 0 | 350 | 393 | 353 | 40 | 0 | 0 | 43 | 0 | 1579746 | 50000 | 1529746 | 1579746 | 1465179 | 0 | 0 | 0 | 1465179 | 1465179 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 | 2015-08-20 | QTR1 | 15/16 | 606 | 2298506.5 | B0 | ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6H61 | 43119215201 | 2014-06-12 | QTR4 | 13/14 | 1 | 0 | 280 | 317 | 317 | 0 | 0 | 0 | 37 | 0 | 838500 | 40300 | 798200 | 838500 | 763060 | 0 | 0 | 0 | 763060 | 763060 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-09-30 | QTR1 | 15/16 | 2015-08-11 | QTR1 | 15/16 | 606 | 850347 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I14 | 43209815201 | 2014-02-27 | QTR3 | 13/14 | 1 | 0 | 120 | 234 | 198 | 36 | 0 | 0 | 114 | 0 | 328706 | 17632 | 311074 | 328706 | 320865 | 0 | 0 | 0 | 320865 | 320865 | 0 | 0 | 76 | 24 | 0 | 9791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 9791 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2015-08-05 | QTR1 | 15/16 | 2015-06-25 | QTR4 | 14/15 | 606 | 370268.95 | B0 | ACC - LUMP SUM | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I33 | 43067015201 | 2015-02-26 | QTR3 | 14/15 | 1 | 0 | 140 | 156 | 148 | 8 | 0 | 0 | 16 | 0 | 1219000 | 50000 | 1169000 | 1219000 | 1179457 | 0 | 0 | 0 | 1179457 | 1177974 | -1484 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 16577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16577 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-12-23 | QTR2 | 15/16 | 2015-11-23 | QTR2 | 15/16 | 606 | 1266281 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I57 | 43119015201 | 2014-09-25 | QTR1 | 14/15 | 1 | 0 | 120 | 138 | 138 | 0 | 0 | 0 | 18 | 0 | 619046 | 39934 | 579112 | 619046 | 562195 | 0 | 0 | 0 | 562195 | 562195 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-09-23 | QTR1 | 15/16 | 2015-07-03 | QTR1 | 15/16 | 606 | 838614 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I58 | 43119415201 | 2014-08-28 | QTR1 | 14/15 | 1 | 0 | 120 | 162 | 162 | 0 | 0 | 0 | 42 | 0 | 931395 | 49000 | 882395 | 931395 | 872317 | 0 | 0 | 0 | 872317 | 872317 | 0 | 0 | 16 | 21 | 0 | 19884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 19884 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-10-20 | QTR2 | 15/16 | 2015-08-11 | QTR1 | 15/16 | 606 | 978848.5 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I77 | 24994175201 | 2014-08-28 | QTR1 | 14/15 | 1 | 0 | 160 | 194 | 194 | 0 | 0 | 0 | 34 | 0 | 1198756 | 50000 | 1148756 | 1198756 | 1094981 | 0 | 0 | 0 | 1094981 | 1094981 | 0 | 0 | 31 | 0 | 0 | 1200 | 0 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11878 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-07-17 | QTR1 | 15/16 | 606 | 1268938.13 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I78 | 43081615201 | 2014-07-31 | QTR1 | 14/15 | 2 | 0 | 140 | 173 | 173 | 0 | 0 | 0 | 25 | 8 | 1207213 | 51325 | 1155888 | 1207213 | 1139099 | 0 | 0 | 0 | 1139099 | 1129248 | -9851 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 3 | 5483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6468 | 0 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2015-09-09 | QTR1 | 15/16 | 2015-04-24 | QTR4 | 14/15 | 606 | 1208779.95 |  |  | 8 | 13 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I83 | 43081415201 | 2014-11-20 | QTR2 | 14/15 | 1 | 0 | 65 | 96 | 93 | 3 | 0 | 0 | 31 | 0 | 94720 | 6040 | 88680 | 94720 | 88652 | 0 | 0 | 0 | 88652 | 88652 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-07-14 | QTR1 | 15/16 | 606 | 126847 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I85 | 41774079201 | 2014-03-27 | QTR3 | 13/14 | 1 | 0 | 300 | 346 | 346 | 0 | 0 | 0 | 46 | 0 | 502650 | 32313 | 470337 | 502650 | 470337 | 0 | 0 | 0 | 470337 | 0 | -470337 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-08-31 | QTR1 | 15/16 | 2015-05-13 | QTR4 | 14/15 | 606 | 678578.25 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I87 | 42934415201 | 2014-10-30 | QTR2 | 14/15 | 3 | 0 | 170 | 192 | 190 | 2 | 0 | 0 | 22 | 0 | 1872759 | 101085 | 1771674 | 1872759 | 1693855 | 0 | 0 | 0 | 1693855 | 1636257 | -57598 | 0 | 20 | 0 | 0 | 1943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-09-17 | QTR1 | 15/16 | 2015-07-29 | QTR1 | 15/16 | 606 | 1934017.45 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J40 | 43590015201 | 2015-01-29 | QTR3 | 14/15 | 1 | 0 | 80 | 83 | 75 | 8 | 0 | 0 | 3 | 0 | 248698 | 11846 | 236852 | 248698 | 217030 | 0 | 0 | 0 | 217030 | 217030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-09-25 | QTR1 | 15/16 | 2015-09-11 | QTR1 | 15/16 | 606 | 248762.6 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J70 | 43717615201 | 2015-06-11 | QTR4 | 14/15 | 1 | 0 | 45 | 52 | 43 | 9 | 0 | 0 | 7 | 0 | 149934 | 7328 | 142606 | 149934 | 142606 | 0 | 0 | 0 | 142606 | 142606 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651119942 | CONSTRUCT GROUP CORP. | N/A | N/A | N/A | N/A | 2015-11-16 | QTR2 | 15/16 | 2015-10-26 | QTR2 | 15/16 | 606 | 153889 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7307 | 42715215201 | 2012-12-05 | QTR2 | 12/13 | 1 | 0 | 615 | 785 | 785 | 0 | 0 | 0 | 168 | 2 | 14844440 | 135000 | 14709440 | 14844440 | 15019838 | 0 | 0 | 0 | 15019838 | 14905397 | -114441 | 0 | 142 | 2 | 2 | 53880 | 0 | 0 | 0 | 6839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 60719 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-10-15 | QTR2 | 15/16 | 2015-04-06 | QTR4 | 14/15 | 798 | 15370623 |  |  | 2 | 24 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7325 | 42900515201 | 2013-06-19 | QTR4 | 12/13 | 1 | 8 | 350 | 453 | 453 | 0 | 0 | 0 | 83 | 20 | 15491284 | 120000 | 15371284 | 16150823 | 16100076 | 0 | 0 | 0 | 16100076 | 16143898 | 43822 | 659540 | 60 | 0 | 1 | 10092 | 0 | 0 | 19 | 662533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 683477 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-08-21 | QTR1 | 15/16 | 2014-11-21 | QTR2 | 14/15 | 709 | 16955600 |  |  | 1 | 23 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7329 | 42907325201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 270 | 369 | 369 | 0 | 0 | 0 | 99 | 0 | 5019226 | 50000 | 4969226 | 5019226 | 4985077 | 0 | 0 | 0 | 4985077 | 4951447 | -33631 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 18054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18054 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-07-23 | QTR1 | 15/16 | 2015-04-01 | QTR4 | 14/15 | 717 | 4751500 | B0 | ACC - LUMP SUM | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7334 | 42455015201 | 2013-08-28 | QTR1 | 13/14 | 1 | 2 | 385 | 518 | 518 | 0 | 0 | 0 | 68 | 65 | 8989959 | 84500 | 8905459 | 9299052 | 9312842 | -3600 | 0 | -3600 | 9309242 | 9306402 | -2840 | 309093 | 39 | 0 | 0 | 51532 | 0 | 0 | 65 | 309093 | 80331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 360626 | 80331 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-11-10 | QTR2 | 15/16 | 2015-04-01 | QTR4 | 14/15 | 717 | 8578716.51 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7337 | 42907315201 | 2013-10-30 | QTR2 | 13/14 | 2 | 2 | 200 | 300 | 300 | 0 | 0 | 0 | 70 | 30 | 4224761 | 50000 | 4174761 | 4277589 | 4397983 | 0 | 0 | 0 | 4397983 | 4415486 | 17503 | 52828 | 59 | 0 | 30 | 33461 | 3083 | 0 | 0 | 5193 | 1819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 38654 | 4902 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-08 | QTR2 | 15/16 | 2014-12-23 | QTR2 | 14/15 | 717 | 4480000 |  |  | 30 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7340 | 42715415201 | 2014-04-30 | QTR4 | 13/14 | 2 | 0 | 150 | 188 | 187 | 1 | 0 | 0 | 38 | 0 | 1688000 | 50000 | 1638000 | 1688000 | 1644638 | 0 | 0 | 0 | 1644638 | 1606582 | -38056 | 0 | 25 | 0 | 0 | 9287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9287 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-14 | QTR1 | 15/16 | 2015-03-27 | QTR3 | 14/15 | 798 | 2156800 | B0 | ACC - LUMP SUM | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7341 | 42896115201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 320 | 383 | 381 | 2 | 0 | 0 | 63 | 0 | 5790872 | 55000 | 5735872 | 5790872 | 5714657 | 0 | 0 | 0 | 5714657 | 5660340 | -54316 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-09-15 | QTR1 | 15/16 | 2015-06-17 | QTR4 | 14/15 | 717 | 6079410 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7343 | 42308815202 | 2014-05-21 | QTR4 | 13/14 | 4 | 0 | 270 | 304 | 267 | 37 | 0 | 0 | 34 | 0 | 4553063 | 50000 | 4503063 | 4553063 | 4196722 | 0 | 0 | 0 | 4196722 | 4140383 | -56339 | 0 | 23 | 0 | 0 | 15813 | 0 | 0 | 0 | 3916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19729 | 0 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2015-12-29 | QTR2 | 15/16 | 2015-05-11 | QTR4 | 14/15 | 717 | 4416500 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7358 | 43140415201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 110 | 136 | 134 | 2 | 0 | 0 | 26 | 0 | 1033200 | 45000 | 988200 | 1033200 | 920104 | 0 | 0 | 0 | 920104 | 920104 | 0 | 0 | 2 | 0 | 0 | 20461 | 0 | 0 | 0 | 742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21202 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-10-22 | QTR2 | 15/16 | 2015-07-13 | QTR1 | 15/16 | 709 | 1010220 | B0 | ACC - LUMP SUM | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7361 | 42906115202 | 2014-12-03 | QTR2 | 14/15 | 2 | 1 | 135 | 164 | 164 | 0 | 0 | 0 | 29 | 0 | 1465000 | 50000 | 1415000 | 1494392 | 1504704 | 0 | 0 | 0 | 1504704 | 1462449 | -42254 | 29392 | 27 | 0 | 0 | 23469 | 0 | 0 | 0 | 51199 | 11673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74668 | 11673 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-11-05 | QTR2 | 15/16 | 2015-08-28 | QTR1 | 15/16 | 717 | 1300371 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7I67 | 42893615201 | 2014-06-11 | QTR4 | 13/14 | 1 | 0 | 195 | 284 | 281 | 3 | 0 | 0 | 89 | 0 | 3868793 | 50000 | 3818793 | 3868793 | 3814687 | 0 | 0 | 0 | 3814687 | 3688104 | -126583 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-11-05 | QTR2 | 15/16 | 2015-08-17 | QTR1 | 15/16 | 717 | 3735600 | B0 | ACC - LUMP SUM | 0 | 59 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I81 | 43113715201 | 2014-06-11 | QTR4 | 13/14 | 1 | 0 | 120 | 157 | 156 | 1 | 0 | 0 | 37 | 0 | 1095029 | 47000 | 1048029 | 1095029 | 997607 | 0 | 0 | 0 | 997607 | 997607 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-10-12 | QTR2 | 15/16 | 2015-02-10 | QTR3 | 14/15 | 717 | 992000 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I96 | 40625565201 | 2014-06-11 | QTR4 | 13/14 | 1 | 0 | 260 | 305 | 305 | 0 | 0 | 0 | 75 | -30 | 1992240 | 50000 | 1942240 | 1992240 | 1975737 | 0 | 0 | 0 | 1975737 | 1975126 | -611 | 0 | 15 | 47 | -30 | 3493 | 0 | 0 | 0 | 6964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | -30 | 10457 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-10-29 | QTR2 | 15/16 | 2015-09-03 | QTR1 | 15/16 | 714 | 2322106 |  |  | -30 | 13 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7J96 | 43066115201 | 2014-11-26 | QTR2 | 14/15 | 1 | 0 | 150 | 183 | 183 | 0 | 0 | 0 | 33 | 0 | 2030000 | 50000 | 1980000 | 2030000 | 1980915 | 0 | 0 | 0 | 1980915 | 1934577 | -46338 | 0 | 26 | 0 | 0 | 1006 | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9760 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-29 | QTR1 | 15/16 | 2015-08-19 | QTR1 | 15/16 | 709 | 1984600 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7J98 | 42907715201 | 2014-12-10 | QTR2 | 14/15 | 1 | 0 | 130 | 143 | 131 | 12 | 0 | 0 | 13 | 0 | 1378500 | 50000 | 1328500 | 1378500 | 1371830 | 0 | 0 | 0 | 1371830 | 1336400 | -35430 | 0 | 11 | 0 | 0 | 36819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36819 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-10-16 | QTR2 | 15/16 | 2015-06-29 | QTR4 | 14/15 | 717 | 1271900 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K00 | 42907215201 | 2015-02-11 | QTR3 | 14/15 | 1 | 0 | 80 | 95 | 95 | 0 | 0 | 0 | 14 | 1 | 412263 | 19000 | 393263 | 412263 | 394582 | 0 | 0 | 0 | 394582 | 394582 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1320 | 0 | F593759317 | CHEYENNE ASPHALT INCORPORATED | N/A | N/A | N/A | N/A | 2015-11-09 | QTR2 | 15/16 | 2015-07-17 | QTR1 | 15/16 | 717 | 398900 | B0 | ACC - LUMP SUM | 1 | 2 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8L99 | 41546225202 | 2012-05-22 | QTR4 | 11/12 | 1 | 9 | 785 | 901 | 901 | 0 | 0 | 0 | 88 | 28 | 19914762 | 150000 | 19764762 | 20008584 | 19972782 | -154000 | 0 | -154000 | 19818782 | 19745451 | -73332 | 93822 | 25 | 0 | 0 | 66402 | 0 | 0 | 0 | 119752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 35659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 90883 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-09-28 | QTR1 | 15/16 | 2015-02-13 | QTR3 | 14/15 | 854 | 20630726.61 |  |  | 0 | 63 | 0 | 0 | -130930 | 0 |  | DO
08DO | 08 | E8M05 | 43128115201 | 2013-02-25 | QTR3 | 12/13 | 2 | 6 | 667 | 783 | 781 | 2 | 0 | 0 | 80 | 36 | 40666800 | 150000 | 40516800 | 40884133 | 40781351 | -49500 | 0 | -49500 | 40731851 | 40551799 | -180052 | 217333 | 44 | 0 | 0 | -13220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 497038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 327358 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-10-27 | QTR2 | 15/16 | 2015-05-22 | QTR4 | 14/15 | 854 | 36916236.02 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR | 28 | 36 | 0 | 0 | -156461 | 0 |  | DO
08DO | 08 | E8M77 | 40615145201 | 2013-03-26 | QTR3 | 12/13 | 2 | 4 | 645 | 777 | 730 | 47 | 0 | 0 | 48 | 84 | 11249740 | 150000 | 11099740 | 11481897 | 10973748 | 0 | 0 | 0 | 10973748 | 10925662 | -48086 | 232157 | 25 | 0 | 84 | 150630 | 103254 | 0 | 0 | 162171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 312801 | 103254 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2015-09-04 | QTR1 | 15/16 | 2015-07-07 | QTR1 | 15/16 | 854 | 11244846.35 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M80 | 42768515201 | 2013-05-14 | QTR4 | 12/13 | 1 | 2 | 425 | 469 | 425 | 44 | 0 | 0 | 44 | 0 | 6746576 | 63950 | 6682626 | 6938552 | 6915696 | 0 | 0 | 0 | 6915696 | 6919857 | 4160 | 191976 | 15 | 0 | 0 | 66193 | 0 | 0 | 0 | 5863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249853 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-09-14 | QTR1 | 15/16 | 2014-10-06 | QTR2 | 14/15 | 854 | 6459217.72 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M93 | 43108935201 | 2013-05-21 | QTR4 | 12/13 | 1 | 2 | 450 | 587 | 587 | 0 | 0 | 0 | 137 | 0 | 7676614 | 84515 | 7592099 | 7714483 | 7540572 | 0 | 0 | 0 | 7540572 | 7491522 | -49050 | 37868 | 85 | 0 | 0 | 122140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122140 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-07-07 | QTR1 | 15/16 | 2015-05-15 | QTR4 | 14/15 | 854 | 8536508.95 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N21 | 42902315201 | 2014-03-11 | QTR3 | 13/14 | 2 | 5 | 170 | 271 | 271 | 0 | 0 | 0 | 94 | 7 | 6573418 | 84736 | 6488682 | 6704790 | 6985687 | -3000 | 0 | -3000 | 6982687 | 6966867 | -15820 | 131372 | 62 | 0 | 0 | 14408 | 0 | 0 | 7 | 173176 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68650 | 0 | 0 | 0 | 8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 67841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 197374 | 5845 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-09-14 | QTR1 | 15/16 | 2015-02-09 | QTR3 | 14/15 | 854 | 8559769.2 |  |  | 7 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N37 | 43112315201 | 2014-06-10 | QTR4 | 13/14 | 1 | 0 | 255 | 268 | 267 | 1 | 0 | 0 | 13 | 0 | 383488 | 24940 | 358548 | 383488 | 358052 | 0 | 0 | 0 | 358052 | 358052 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1719 | 0 | F593285921 | S & D INDUSTRIAL PAINTING INC. | N/A | N/A | N/A | N/A | 2015-12-18 | QTR2 | 15/16 | 2015-09-28 | QTR1 | 15/16 | 854 | 523746.64 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0