## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 33085163 | 32496826 | 33397085 | 33461099 | 0 | 32188551 | -0.9486% | 84.62% | 491752 | 1.513% | 311922 | 0.9428% | 2149 | 259 | 12.05% | 131 | 6.096% | 0 | 0% | 153 | 7.12% | 2302 | 7.12% | 2692 | 2735 | 2345 | 9.121% | 84.62%
| District Let | 11875231 | 11711878 | 12963244 | 12645454 | 0 | 12262515 | 4.702% | 100% | 1151523 | 9.832% | 1088013 | 9.162% | 835 | 53 | 6.347% | 46 | 5.509% | 0 | 0% | 30 | 3.593% | 865 | 3.593% | 964 | 956 | 857 | 2.635% | 100%
| All Contracts | 44960394 | 44208704 | 46360329 | 46106553 | 0 | 44451066 | 0.5482% | 88.24% | 1643275 | 3.717% | 1399935 | 3.114% | 2984 | 312 | 10.46% | 177 | 5.932% | 0 | 0% | 183 | 6.133% | 3167 | 6.133% | 3656 | 3691 | 3202 | 7.306% | 88.24%
2 | Central Let | 18877999 | 18714472 | 19310556 | 20727019 | 0 | 20474274 | 9.403% | 77.78% | 449883 | 2.404% | 432556 | 2.291% | 1402 | 205 | 14.62% | 118 | 8.417% | 3 | 0.214% | 70 | 4.993% | 1475 | 5.207% | 1816 | 1840 | 1517 | 8.203% | 77.78%
| District Let | 17948922 | 17661979 | 17938687 | 17840723 | 0 | 17570301 | -0.5191% | 100% | 88720 | 0.5023% | -10235 | -0.05702% | 1205 | 62 | 5.145% | 74 | 6.141% | 3 | 0.249% | 74 | 6.141% | 1282 | 6.39% | 1418 | 1446 | 1310 | 8.714% | 75%
| All Contracts | 36826921 | 36376451 | 37249243 | 38567742 | 0 | 38044575 | 4.586% | 84.62% | 538603 | 1.481% | 422321 | 1.147% | 2607 | 267 | 10.24% | 192 | 7.365% | 6 | 0.2301% | 144 | 5.524% | 2757 | 5.754% | 3234 | 3286 | 2827 | 8.439% | 76.92%
3 | Central Let | 58978825 | 58258371 | 62822108 | 62783787 | 0 | 60692302 | 4.178% | 90% | 4241642 | 7.281% | 3843282 | 6.516% | 4091 | 1112 | 27.18% | 407 | 9.949% | 311 | 7.602% | 700 | 17.11% | 5102 | 24.71% | 6621 | 6528 | 5009 | 22.44% | 80%
| District Let | 42250571 | 41627877 | 42630463 | 43229594 | 0 | 42816543 | 2.855% | 84.62% | 639360 | 1.536% | 379893 | 0.8991% | 1959 | 605 | 30.88% | 222 | 11.33% | 192 | 9.801% | 372 | 18.99% | 2523 | 28.79% | 3350 | 3309 | 2482 | 26.7% | 76.92%
| All Contracts | 101229396 | 99886248 | 105452571 | 106013381 | 0 | 103508845 | 3.627% | 86.96% | 4881002 | 4.887% | 4223175 | 4.172% | 6050 | 1717 | 28.38% | 629 | 10.4% | 503 | 8.314% | 1072 | 17.72% | 7625 | 26.03% | 9971 | 9837 | 7491 | 23.82% | 78.26%
4 | Central Let | 26576686 | 26253328 | 26855566 | 26310568 | 630700 | 25471537 | -2.978% | 100% | 495540 | 1.888% | 278880 | 1.049% | 2202 | 168 | 7.629% | 97 | 4.405% | 43 | 1.953% | 31 | 1.408% | 2276 | 3.361% | 2542 | 2330 | 2065 | -6.222% | 100%
| District Let | 2859509 | 2748474 | 2883670 | 2801625 | 0 | 2794524 | 1.675% | 100% | 52990 | 1.928% | 24162 | 0.845% | 389 | 46 | 11.83% | 20 | 5.141% | 0 | 0% | 4 | 1.028% | 393 | 1.028% | 474 | 470 | 404 | 3.856% | 100%
| All Contracts | 29436195 | 29001802 | 29739236 | 29112193 | 630700 | 28266061 | -2.537% | 100% | 548530 | 1.891% | 303042 | 1.029% | 2591 | 214 | 8.259% | 117 | 4.516% | 43 | 1.66% | 35 | 1.351% | 2669 | 3.01% | 3016 | 2800 | 2469 | -4.709% | 100%
5 | Central Let | 31648724 | 31217724 | 32396787 | 32243824 | 0 | 30694778 | -1.675% | 85.71% | 909307 | 2.913% | 748063 | 2.364% | 1898 | 411 | 21.65% | 142 | 7.482% | 0 | 0% | 101 | 5.321% | 1999 | 5.321% | 2551 | 2471 | 1918 | 1.054% | 100%
| District Let | 5875447 | 5736447 | 5782564 | 5618941 | 0 | 5525437 | -3.678% | 100% | -92883 | -1.619% | -92883 | -1.581% | 670 | 13 | 1.94% | 29 | 4.328% | 0 | 0% | 27 | 4.03% | 697 | 4.03% | 739 | 764 | 722 | 7.761% | 66.67%
| All Contracts | 37524171 | 36954171 | 38179351 | 37862765 | 0 | 36220215 | -1.986% | 90% | 816424 | 2.209% | 655180 | 1.746% | 2568 | 424 | 16.51% | 171 | 6.659% | 0 | 0% | 128 | 4.984% | 2696 | 4.984% | 3290 | 3235 | 2640 | 2.804% | 90%
6 | Central Let | 35164141 | 34744081 | 36114097 | 34759432 | 715000 | 33865105 | -2.53% | 100% | 1082978 | 3.117% | 949956 | 2.701% | 1935 | 290 | 14.99% | 75 | 3.876% | 33 | 1.705% | 6 | 0.3101% | 1974 | 2.016% | 2339 | 2095 | 1730 | -10.59% | 100%
| District Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| All Contracts | 35164141 | 34744081 | 36114097 | 34759432 | 715000 | 33865105 | -2.53% | 100% | 1082978 | 3.117% | 949956 | 2.701% | 1935 | 290 | 14.99% | 75 | 3.876% | 33 | 1.705% | 6 | 0.3101% | 1974 | 2.016% | 2339 | 2095 | 1730 | -10.59% | 100%
7 | Central Let | 404115664 | 403866664 | 445334880 | 452609281 | 0 | 453943921 | 12.4% | 75% | 41131378 | 10.18% | 41219216 | 10.2% | 1805 | 257 | 14.24% | 97 | 5.374% | 23 | 1.274% | 539 | 29.86% | 2367 | 31.14% | 2721 | 2900 | 2546 | 41.05% | 50%
| District Let | 33359673 | 32776673 | 34330191 | 33706068 | 0 | 32552288 | -0.6846% | 100% | 1204591 | 3.675% | 970518 | 2.909% | 1980 | 319 | 16.11% | 162 | 8.182% | 45 | 2.273% | 83 | 4.192% | 2108 | 6.465% | 2589 | 2424 | 1943 | -1.869% | 100%
| All Contracts | 437475337 | 436643337 | 479665071 | 486315349 | 0 | 486496209 | 11.42% | 92.86% | 42335969 | 9.696% | 42189734 | 9.644% | 3785 | 576 | 15.22% | 259 | 6.843% | 68 | 1.797% | 622 | 16.43% | 4475 | 18.23% | 5310 | 5324 | 4489 | 18.6% | 85.71%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 13733594 | 13536754 | 13823910 | 13640083 | 0 | 13424380 | -0.8301% | 100% | 134397 | 0.9928% | 90316 | 0.6576% | 730 | 58 | 7.945% | 62 | 8.493% | 1 | 0.137% | 4 | 0.5479% | 735 | 0.6849% | 855 | 852 | 732 | 0.274% | 100%
| All Contracts | 13733594 | 13536754 | 13823910 | 13640083 | 0 | 13424380 | -0.8301% | 100% | 134397 | 0.9928% | 90316 | 0.6576% | 730 | 58 | 7.945% | 62 | 8.493% | 1 | 0.137% | 4 | 0.5479% | 735 | 0.6849% | 855 | 852 | 732 | 0.274% | 100%
Totals This Qtr | Central Let | 608447202 | 605551466 | 656231079 | 662895010 | 1345700 | 657330468 | 8.551% | 86.54% | 48802480 | 8.059% | 47783875 | 7.853% | 15482 | 2702 | 17.45% | 1067 | 6.892% | 413 | 2.668% | 1600 | 10.33% | 17495 | 13% | 21282 | 20899 | 17130 | 10.64% | 84.62%
| District Let | 127902947 | 125800082 | 130352729 | 129482488 | 0 | 126945988 | 0.9109% | 95% | 3178698 | 2.527% | 2449784 | 1.915% | 7768 | 1156 | 14.88% | 615 | 7.917% | 241 | 3.102% | 594 | 7.647% | 8603 | 10.75% | 10389 | 10221 | 8450 | 8.78% | 87.5%
| All Contracts | 736350149 | 731351548 | 786583808 | 792377498 | 1345700 | 784276456 | 7.237% | 90.22% | 51981178 | 7.108% | 50233659 | 6.822% | 23250 | 3858 | 16.59% | 1682 | 7.234% | 654 | 2.813% | 2194 | 9.437% | 26098 | 12.25% | 31671 | 31120 | 25580 | 10.02% | 85.87%
Totals Previous Quarter | Central Let
District Let
All Contracts
Totals Fiscal Year 2015/2016 | Central Let | 939392055 | 928183064 | 968008671 | 980536241 | 5086000 | 963305142 | 3.784% | 91.71% | 32914329 | 3.546% | 28616617 | 3.046% | 52868 | 8893 | 16.82% | 3474 | 6.571% | 961 | 1.818% | 3777 | 7.144% | 57606 | 8.962% | 70058 | 70737 | 58370 | 10.41% | 83.9%
| District Let | 984092963 | 976092333 | 1036587854 | 1030584161 | 5781667 | 998653518 | 2.311% | 92.36% | 57365087 | 5.877% | 55188579 | 5.608% | 37490 | 4617 | 12.32% | 2121 | 5.658% | 1331 | 3.55% | 3490 | 9.309% | 42311 | 12.86% | 48945 | 49037 | 42299 | 12.83% | 87.9%
| All Contracts | 1923485018 | 1904275397 | 2004596525 | 2011120402 | 10867667 | 1961958660 | 3.029% | 91.99% | 90279416 | 4.741% | 83805196 | 4.357% | 90358 | 13510 | 14.95% | 5595 | 6.192% | 2292 | 2.537% | 7267 | 8.042% | 99917 | 10.58% | 119003 | 119774 | 100669 | 11.41% | 85.64%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
1
| 01 | T1560 | 42910115201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 250 | 268 | 268 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 4883160 | 57482 | 4825678 | 4883160 | 4742567 | 0 | 0 | 0 | 4742567 | 4581604 | 94.94% | 1 | -160964 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 118 | 5451824.59
| 01 | T1583 | 42910715201 | 2014-05-21 | QTR4 | 13/14 | 2 | 12 | 365 | 542 | 598 | 134.8% | 0 | -56 | 56 | 0 | 106 | 71 | 12221582 | 124617 | 12096965 | 12321397 | 12316064 | -258944 | 0 | -258944 | 12057120 | 11369478 | 93.99% | 1 | -687643 | 99815 | 77 | 29 | 0 | 55 | 73297 | 0 | 0 | 16 | 102194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 177856 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 108 | 11851721.99
| 01 | T1601 | 42910615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 0 | 180 | 206 | 206 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 2560715 | 50000 | 2510715 | 2560715 | 2601322 | 0 | 0 | 0 | 2601322 | 2476584 | 98.64% | 1 | -124738 | 0 | 16 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 108 | 2539521.53
| 01 | T1604 | 43340715201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 130 | 138 | 139 | 98.46% | 1 | -1 | 1 | 0 | 11 | -3 | 1272557 | 50000 | 1222557 | 1265786 | 1215247 | 0 | 0 | 0 | 1215247 | 1215247 | 99.4% | 1 | 0 | -6770 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -6770 | 0 | 0 | -3 | -6770 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-20 | QTR4 | 15/16 | 113 | 1175938.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1610 | 43337615201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 140 | 157 | 173 | 111.4% | 1 | -16 | 16 | 0 | 17 | 0 | 766880 | 38788 | 728092 | 763925 | 702653 | -27872 | 0 | -27872 | 674781 | 674781 | 92.68% | 1 | 0 | -2956 | 10 | 7 | 0 | 0 | -73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2956 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-28 | QTR4 | 15/16 | 108 | 1032307.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1612 | 43539315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 2 | 139 | 163 | 162 | 99.28% | 1 | 1 | 0 | 0 | 24 | 0 | 965039 | 0 | 965039 | 965864 | 949501 | 0 | 0 | 0 | 949501 | 941761 | 97.59% | 1 | -7741 | 825 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-05 | QTR1 | 16/17 |  | 2016-04-14 | QTR4 | 15/16 | 113 | 968994.66
| 01 | T1615 | 42950615201 | 2015-06-17 | QTR4 | 14/15 | 2 | 0 | 150 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1470894 | 50000 | 1420894 | 1470894 | 1424904 | 0 | 0 | 0 | 1424904 | 1424904 | 100.3% | 1 | 0 | 0 | 30 | 4 | 0 | 0 | 3080 | 0 | 0 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4010 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-07-05 | QTR1 | 16/17 | 115 | 1441634.98 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1617 | 43337515201 | 2015-06-17 | QTR4 | 14/15 | 1 | 2 | 150 | 170 | 169 | 99.33% | 1 | 1 | 0 | 0 | 20 | 0 | 1087453 | 50000 | 1037453 | 1211375 | 1165751 | 0 | 0 | 0 | 1165751 | 1165751 | 112.4% | 0 | 0 | 123922 | 11 | 9 | 0 | 0 | 135887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128298 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 108 | 1092794.1 | B0 | ACC - LUMP SUM
| 01 | T1618 | 43340815201 | 2015-06-17 | QTR4 | 14/15 | 2 | 2 | 150 | 185 | 185 | 104.7% | 1 | 0 | 0 | 0 | 28 | 7 | 1135821 | 50000 | 1085821 | 1138128 | 1108067 | 0 | 0 | 0 | 1108067 | 1103946 | 101.7% | 1 | -4121 | 2307 | 17 | 11 | 0 | 4 | 3712 | 0 | 0 | 3 | 18533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 22246 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 108 | 1209049.68 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1629 | 43325615201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 85 | 88 | 74 | 83.53% | 1 | 14 | 0 | 0 | 3 | 0 | 910000 | 47212 | 862788 | 910000 | 883227 | 0 | 0 | 0 | 883227 | 883227 | 102.4% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 13198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13198 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-28 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 115 | 857875.38 | B0 | ACC - LUMP SUM
| 01 | T1651 | 43134115201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 90 | 91 | 78 | 85.56% | 1 | 13 | 0 | 0 | 1 | 0 | 194630 | 9734 | 184896 | 194630 | 184896 | 0 | 0 | 0 | 184896 | 184896 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-06-06 | QTR4 | 15/16 | 118 | 236550.37 | B0 | ACC - LUMP SUM
| 01 | T1A02 | 42518315201 | 2014-12-03 | QTR2 | 14/15 | 1 | 4 | 250 | 403 | 402 | 130.8% | 0 | 1 | 0 | 0 | 75 | 78 | 5396928 | 50000 | 5346928 | 5491707 | 5952983 | 0 | 0 | 0 | 5952983 | 5952455 | 111.3% | 0 | -528 | 94779 | 57 | 18 | 0 | 75 | 18567 | 0 | 0 | 3 | 122779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 141346 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-05-19 | QTR4 | 15/16 | 115 | 4358786.71 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1A15 | 43325515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 70 | 97 | 97 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 219504 | 10504 | 209000 | 219504 | 213917 | 0 | 0 | 0 | 213917 | 213917 | 102.4% | 1 | 0 | 0 | 15 | 12 | 0 | 0 | 4917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4917 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-02-20 | QTR3 | 15/16 | 106 | 200589.29 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 13 | 18 | 25 | 2149 | 2692 | 2735 | 84.62% | 11 | -43 | 73 | 0 | 390 | 153 | 33085163 | 588337 | 32496826 | 33397085 | 33461099 | -286816 | 0 | -286816 | 33174283 | 32188551 | 84.62% | 11 | -985735 | 311922 | 259 | 131 | 0 | 134 | 252585 | 0 | 0 | 22 | 254043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10471 | 0 | 0 | 0 | 2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -6770 | 0 | 0 | 153 | 491752 | 0
| 01 | E1N74 | 42912015201 | 2014-12-18 | QTR2 | 14/15 | 1 | 0 | 185 | 212 | 212 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 3107573 | 50000 | 3057573 | 3107573 | 3110593 | 0 | 0 | 0 | 3110593 | 2961957 | 96.87% | 1 | -148636 | 0 | 9 | 18 | 0 | 0 | 7628 | 0 | 0 | 0 | 8425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16053 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-01-21 | QTR3 | 15/16 | 113 | 3280021.43
| 01 | E1N87 | 43120915201 | 2015-02-19 | QTR3 | 14/15 | 1 | 0 | 300 | 336 | 336 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 3172000 | 50000 | 3122000 | 3172000 | 3272265 | 0 | 0 | 0 | 3272265 | 3269380 | 104.7% | 1 | -2886 | 0 | 24 | 12 | 0 | 0 | 7188 | 0 | 0 | 0 | 21276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40644 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-25 | QTR4 | 15/16 | 108 | 3312411.11
| 01 | E1O02 | 43161515201 | 2015-01-15 | QTR3 | 14/15 | 1 | 2 | 290 | 354 | 354 | 110.3% | 1 | 0 | 0 | 0 | 34 | 30 | 5445703 | 56538 | 5389165 | 6533716 | 6114803 | 0 | 0 | 0 | 6114803 | 5883385 | 109.2% | 1 | -231419 | 1088013 | 19 | 15 | 0 | 20 | 396717 | 0 | 0 | 10 | 691296 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1088013 | 691296 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 113 | 4971481.53
| 01 | E1O75 | 43503815201 | 2016-01-21 | QTR3 | 15/16 | 1 | 0 | 60 | 62 | 54 | 86.67% | 1 | 8 | 0 | 0 | 2 | 0 | 149955 | 6815 | 143140 | 149955 | 147793 | 0 | 0 | 0 | 147793 | 147793 | 103.3% | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 6813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6813 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-06-21 | QTR4 | 15/16 | 118 | 157973.52
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 4 | 4 | 2 | 835 | 964 | 956 | 100% | 4 | 8 | 0 | 0 | 99 | 30 | 11875231 | 163353 | 11711878 | 12963244 | 12645454 | 0 | 0 | 0 | 12645454 | 12262515 | 100% | 4 | -382941 | 1088013 | 53 | 46 | 0 | 20 | 418346 | 0 | 0 | 10 | 720997 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1151523 | 691296
| District 01 Totals |  |  |  |  | 17 | 22 | 27 | 2984 | 3656 | 3691 | 88.24% | 15 | -35 | 73 | 0 | 489 | 183 | 44960394 | 751690 | 44208704 | 46360329 | 46106553 | -286816 | 0 | -286816 | 45819737 | 44451066 | 88.24% | 15 | -1368676 | 1399935 | 312 | 177 | 0 | 154 | 670931 | 0 | 0 | 32 | 975040 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6621 | 0 | 0 | 0 | 10696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -6770 | 0 | 0 | 183 | 1643275 | 691296
| 02 | T2506 | 43040415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 45 | 48 | 103 | 222.2% | 0 | -55 | 55 | 0 | 3 | 0 | 136157 | 7800 | 128357 | 136157 | 128357 | -47602 | 0 | -47602 | 80754 | 80754 | 62.91% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-09-14 | QTR1 | 16/17 |  | 2014-05-14 | QTR4 | 13/14 | 208 | 153002.52 | B0 | ACC - LUMP SUM
| 02 | T2533 | 43355415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 3 | 400 | 535 | 535 | 104.5% | 1 | 0 | 0 | 0 | 117 | 18 | 8533240 | 72079 | 8461162 | 8598881 | 9356445 | 0 | 0 | 0 | 9356445 | 9207548 | 108.8% | 1 | -148897 | 65641 | 58 | 59 | 0 | 0 | 229 | 0 | 0 | 18 | 64256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19692 | 0 | 0 | 18 | 46705 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 208 | 7794225.55
| 02 | T2567 | 43224715201 | 2015-02-25 | QTR3 | 14/15 | 1 | 8 | 135 | 252 | 252 | 141.5% | 0 | 0 | 0 | 0 | 79 | 38 | 1013111 | 0 | 1013111 | 1368388 | 1368010 | 0 | 0 | 0 | 1368010 | 1368010 | 135% | 0 | 0 | 355277 | 46 | 15 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-02-01 | QTR3 | 15/16 | 214 | 1004174.39 | B0 | ACC - LUMP SUM
| 02 | T2572 | 43061415201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 150 | 191 | 191 | 102% | 1 | 0 | 0 | 0 | 41 | 0 | 1990811 | 0 | 1990811 | 2002450 | 2059822 | 0 | 0 | 0 | 2059822 | 2059822 | 103.5% | 1 | 0 | 11638 | 21 | 17 | 0 | 0 | 11638 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 11638 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-07-21 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 214 | 1508389.63
| 02 | T2587 | 43265515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 120 | 151 | 151 | 100% | 1 | 0 | 0 | 0 | 31 | 0 | 718800 | 0 | 718800 | 718800 | 718800 | 0 | 0 | 0 | 718800 | 718800 | 100% | 1 | 0 | 0 | 26 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453689782 | SOUTHERN STATES PAVEMENT MARKINGS INC. | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2016-06-02 | QTR4 | 15/16 | 209 | 769166.88 | B0 | ACC - LUMP SUM
| 02 | T2594 | 43265415201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 152 | 152 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 475000 | 0 | 475000 | 475000 | 475000 | 0 | 0 | 0 | 475000 | 475000 | 100% | 1 | 0 | 0 | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-09-30 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 209 | 428505.77 | B0 | ACC - LUMP SUM
| 02 | T2603 | 43075915201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 95 | 95 | 118.7% | 1 | 0 | 0 | 0 | 6 | 14 | 521218 | 23780 | 497438 | 521218 | 506672 | 0 | 0 | 0 | 506672 | 506672 | 101.9% | 1 | 0 | 0 | 3 | 3 | 0 | 10 | 1681 | 0 | 0 | 0 | 7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 9235 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-07-01 | QTR1 | 16/17 | 214 | 510081.72
| 02 | T2608 | 43055825201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 84 | 80 | 94.67% | 1 | 4 | 0 | 0 | 9 | 0 | 148375 | 8369 | 140006 | 148375 | 138616 | 0 | 0 | 0 | 138616 | 138616 | 99.01% | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 209 | 178082.19
| 02 | T9006 | 43675915201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 282 | 308 | 281 | 90.43% | 1 | 27 | 0 | 0 | 26 | 0 | 5341287 | 51500 | 5289787 | 5341287 | 5975297 | 0 | 0 | 0 | 5975297 | 5919052 | 111.9% | 0 | -56245 | 0 | 12 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 27028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27028 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-06-15 | QTR4 | 15/16 | 209 | 5370611
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 9 | 9 | 14 | 1402 | 1816 | 1840 | 77.78% | 7 | -24 | 55 | 0 | 344 | 70 | 18877999 | 163528 | 18714472 | 19310556 | 20727019 | -47602 | 0 | -47602 | 20679416 | 20474274 | 77.78% | 7 | -205142 | 432556 | 205 | 118 | 0 | 10 | 13548 | 0 | 3 | 56 | 454114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19692 | 0 | 3 | 70 | 449883 | 0
| 02 | E2R04 | 21066125201 | 2012-12-12 | QTR2 | 12/13 | 2 | 1 | 90 | 192 | 224 | 216.7% | 0 | -32 | 32 | 0 | 32 | 70 | 1430432 | 50000 | 1380432 | 1430840 | 1393606 | -49024 | 0 | -49024 | 1344582 | 1344578 | 97.4% | 1 | -4 | 408 | 14 | 15 | 3 | 0 | 4074 | 0 | 0 | 70 | 21643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 70 | 25716 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 | 07/17/2014 | 2014-03-07 | QTR3 | 13/14 | 208 | 1293927.32
| 02 | E2R17 | 21237935201 | 2013-06-20 | QTR4 | 12/13 | 5 | 1 | 790 | 846 | 846 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 11440230 | 150000 | 11290230 | 11429587 | 11316805 | 0 | 0 | 0 | 11316805 | 11261013 | 99.74% | 1 | -55793 | -10643 | 7 | 49 | 0 | 0 | -621 | 0 | 0 | 0 | 42964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11541 | 0 | 0 | 0 | 32321 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2015-12-07 | QTR2 | 15/16 | 208 | 13890662.92 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
| 02 | E2T70 | 43219415201 | 2015-07-15 | QTR1 | 15/16 | 1 | 0 | 190 | 217 | 214 | 100.5% | 1 | 3 | 0 | 0 | 23 | 4 | 741630 | 36943 | 704687 | 741630 | 709180 | 0 | 0 | 0 | 709180 | 709010 | 100.6% | 1 | -170 | 0 | 14 | 9 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 214 | 775810
| 02 | E2T74 | 42342715201 | 2015-09-16 | QTR1 | 15/16 | 1 | 0 | 135 | 163 | 162 | 99.26% | 1 | 1 | 0 | 0 | 28 | 0 | 4336630 | 50000 | 4286630 | 4336630 | 4421132 | 0 | 0 | 0 | 4421132 | 4255700 | 99.28% | 1 | -165433 | 0 | 27 | 1 | 0 | 0 | 17388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17388 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-28 | QTR1 | 16/17 |  | 2016-06-13 | QTR4 | 15/16 | 209 | 4754490.59
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 4 | 9 | 2 | 1205 | 1418 | 1446 | 75% | 3 | -28 | 32 | 0 | 139 | 74 | 17948922 | 286943 | 17661979 | 17938687 | 17840723 | -49024 | 0 | -49024 | 17791699 | 17570301 | 100% | 4 | -221400 | -10235 | 62 | 74 | 3 | 0 | 20841 | 0 | 0 | 74 | 77902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11541 | 0 | 3 | 74 | 88720 | 0
| District 02 Totals |  |  |  |  | 13 | 18 | 16 | 2607 | 3234 | 3286 | 76.92% | 10 | -52 | 87 | 0 | 483 | 144 | 36826921 | 450471 | 36376451 | 37249243 | 38567742 | -96626 | 0 | -96626 | 38471115 | 38044575 | 84.62% | 11 | -426542 | 422321 | 267 | 192 | 3 | 10 | 34389 | 0 | 3 | 130 | 532016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31233 | 0 | 6 | 144 | 538603 | 0
| 03 | T3349 | 22041285201 | 2010-12-08 | QTR2 | 10/11 | 3 | 28 | 835 | 1802 | 1804 | 182% | 0 | -2 | 2 | 0 | 381 | 586 | 7357219 | 72479 | 7284740 | 10528722 | 10638848 | -93018 | 0 | -93018 | 10545830 | 10537771 | 144.7% | 0 | -8059 | 3171503 | 203 | 81 | 0 | 428 | 2195488 | 844067 | 0 | 120 | 436311 | 60348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 81300 | 13615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 365823 | 185379 | 97 | 0 | 126858 | 126858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 586 | 3205779 | 1230267 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-03-11 | QTR3 | 15/16 | 308 | 7320354.71 | ARRA | AMERICAN RECOVERY AND REINVEST
| 03 | T3375 | 42124315201 | 2012-02-29 | QTR3 | 11/12 | 3 | 3 | 1194 | 1402 | 1400 | 103% | 1 | 2 | 0 | 0 | 170 | 38 | 14736078 | 150000 | 14586078 | 15035632 | 14669101 | 0 | 0 | 0 | 14669101 | 14620764 | 100.2% | 1 | -48338 | 299554 | 105 | 65 | 0 | 38 | 320021 | 0 | 0 | 0 | 102024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59292 | 0 | 0 | 0 | 7231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 371313 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-30 | QTR4 | 15/16 | 308 | 18080147.32
| 03 | T3418 | 42551915201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 350 | 475 | 472 | 99.14% | 1 | 3 | 0 | 0 | 125 | 0 | 2589441 | 50000 | 2539441 | 2672648 | 2648983 | 0 | 0 | 0 | 2648983 | 2635144 | 103.8% | 1 | -13838 | 83207 | 114 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-07-06 | QTR1 | 16/17 | 308 | 2582602.98
| 03 | T3427 | 42164415201 | 2013-07-31 | QTR1 | 13/14 | 4 | 2 | 475 | 888 | 888 | 112% | 1 | 0 | 0 | 0 | 369 | 44 | 11476305 | 126776 | 11349528 | 11609159 | 11286785 | -11250 | 0 | -11250 | 11275535 | 10699458 | 94.27% | 1 | -576077 | 132854 | 265 | 91 | 0 | 19 | 140137 | 0 | 0 | 15 | 65665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 12852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 44 | 228449 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 308 | 12800389.92
| 03 | T3443 | 42693415201 | 2014-12-03 | QTR2 | 14/15 | 2 | 1 | 247 | 408 | 408 | 113.8% | 1 | 0 | 0 | 0 | 143 | 18 | 4037987 | 50000 | 3987987 | 4183812 | 4167957 | 0 | 0 | 0 | 4167957 | 3846478 | 96.45% | 1 | -321479 | 145825 | 106 | 21 | 13 | 17 | 28230 | 0 | 3 | 1 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18 | 175160 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 308 | 4397278.78
| 03 | T3482 | 42884515201 | 2015-01-28 | QTR3 | 14/15 | 2 | 1 | 300 | 396 | 388 | 97.33% | 1 | 8 | 0 | 0 | 96 | 0 | 7416925 | 85537 | 7331389 | 7437265 | 7758460 | -880 | 0 | -880 | 7757580 | 7441692 | 101.5% | 1 | -315888 | 20339 | 66 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 27217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30580 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 313 | 8733987.91
| 03 | T3495 | 42695615201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 90 | 226 | 225 | 98.89% | 1 | 1 | 0 | 0 | 136 | 0 | 1619321 | 50000 | 1569321 | 1619321 | 1588249 | 0 | 0 | 0 | 1588249 | 1566711 | 99.83% | 1 | -21538 | 0 | 102 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-05-18 | QTR4 | 15/16 | 321 | 1991519.93
| 03 | T3515 | 43090835201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 240 | 568 | 567 | 164.2% | 0 | 1 | 0 | 0 | 314 | 14 | 8076272 | 85662 | 7990610 | 8066272 | 8349102 | 0 | 0 | 0 | 8349102 | 7667982 | 95.96% | 1 | -681120 | -10000 | 119 | 54 | 1 | 14 | 68182 | 0 | 0 | 0 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 14 | 58182 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 313 | 8827284.67
| 03 | T3589 | 43174315201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 120 | 126 | 77 | 59.17% | 1 | 49 | 0 | 0 | 6 | 0 | 169047 | 0 | 169047 | 169047 | 169047 | 0 | 0 | 0 | 169047 | 169047 | 100% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 321 | 199840.42 | B0 | ACC - LUMP SUM
| 03 | T9009 | 43035625201 | 2015-06-24 | QTR4 | 14/15 | 1 | 0 | 240 | 330 | 299 | 105.4% | 1 | 31 | 0 | 0 | 90 | 0 | 1500230 | 50000 | 1450230 | 1500230 | 1507255 | 0 | 0 | 0 | 1507255 | 1507255 | 103.9% | 1 | 0 | 0 | 30 | 16 | 30 | 0 | 0 | 0 | 14 | 0 | 29504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 49973 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 314 | 1868902.5
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 10 | 19 | 37 | 4091 | 6621 | 6528 | 80% | 8 | 93 | 2 | 0 | 1830 | 700 | 58978825 | 720454 | 58258371 | 62822108 | 62783787 | -105148 | 0 | -105148 | 62678639 | 60692302 | 90% | 9 | -1986337 | 3843282 | 1112 | 407 | 44 | 516 | 2752058 | 844067 | 17 | 136 | 651826 | 60348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 18 | 383981 | 13615 | 0 | 0 | 3363 | 0 | 0 | 0 | -59292 | 0 | 0 | 30 | 382850 | 185379 | 97 | 0 | 126858 | 126858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 700 | 4241642 | 1230267
| 03 | E3K73 | 42693515201 | 2014-03-13 | QTR3 | 13/14 | 2 | 1 | 200 | 344 | 344 | 109.5% | 1 | 0 | 0 | 0 | 125 | 19 | 1221881 | 50000 | 1171881 | 1231781 | 1143560 | 0 | 0 | 0 | 1143560 | 1120620 | 95.63% | 1 | -22940 | 9900 | 106 | 19 | 0 | 0 | 0 | 0 | 0 | 19 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 10560 | 6600 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2015-06-14 | QTR4 | 14/15 | 308 | 1514949.05
| 03 | E3L90 | 42840315201 | 2013-06-28 | QTR4 | 12/13 | 1 | 3 | 534 | 975 | 975 | 139.7% | 0 | 0 | 0 | 0 | 304 | 137 | 24049000 | 150000 | 23899000 | 24338104 | 24337828 | 0 | 0 | 0 | 24337828 | 24337642 | 101.8% | 1 | -186 | 289104 | 165 | 64 | 0 | 0 | 10000 | 0 | 20 | 0 | 59678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 363800 | 298854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 137 | 438828 | 298854 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2016-08-30 | QTR1 | 16/17 |  | 2016-04-26 | QTR4 | 15/16 | 313 | 21314871.51 | A3 | ICC - DESIGN/BUILD - MINOR
| 03 | E3M17 | 40747845201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 90 | 109 | 107 | 97.78% | 1 | 2 | 0 | 0 | 19 | 0 | 149498 | 7779 | 141719 | 149498 | 139613 | 0 | 0 | 0 | 139613 | 139613 | 98.51% | 1 | 0 | 0 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455085205 | PRINCIPLE PROPERTIES INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-06-08 | QTR4 | 15/16 | 308 | 163264.04
| 03 | E3M55 | 42805825201 | 2014-01-31 | QTR3 | 13/14 | 1 | 1 | 265 | 629 | 628 | 198.1% | 0 | 1 | 0 | 0 | 211 | 153 | 1540571 | 50000 | 1490571 | 1579254 | 1571464 | 0 | 0 | 0 | 1571464 | 1571464 | 105.4% | 1 | 0 | 38683 | 83 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-01-19 | QTR3 | 15/16 | 308 | 1529160 | A3 | ICC - DESIGN/BUILD - MINOR
| 03 | E3M95 | 41694315201 | 2015-07-09 | QTR1 | 15/16 | 1 | 3 | 140 | 240 | 239 | 118.6% | 1 | 1 | 0 | 0 | 73 | 27 | 2738862 | 50000 | 2688862 | 3014082 | 3595051 | 0 | 0 | 0 | 3595051 | 3484491 | 129.6% | 0 | -110560 | 275220 | 36 | 37 | 0 | 0 | 0 | 0 | 0 | 5 | 288220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 12155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 27 | 287375 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-19 | QTR1 | 16/17 |  | 2016-06-27 | QTR4 | 15/16 | 314 | 3204695.35
| 03 | E3N17 | 43392715201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 65 | 65 | 50 | 73.85% | 1 | 15 | 0 | 0 | 2 | -2 | 1734968 | 50000 | 1684968 | 1417537 | 1360898 | 0 | 0 | 0 | 1360898 | 1360898 | 80.77% | 1 | 0 | -317430 | 2 | 0 | 0 | -2 | -313024 | 0 | 0 | 0 | 4578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | -308196 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-05-23 | QTR4 | 15/16 | 321 | 1346663.5
| 03 | E3N18 | 43391815201 | 2015-10-08 | QTR2 | 15/16 | 1 | 1 | 65 | 117 | 116 | 130.8% | 0 | 1 | 0 | 0 | 31 | 21 | 1245237 | 49942 | 1195296 | 1323870 | 1408799 | 0 | 0 | 0 | 1408799 | 1408799 | 117.9% | 0 | 0 | 78633 | 30 | 1 | 0 | 21 | 108680 | 16182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 108680 | 16182 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-01 | QTR4 | 15/16 | 308 | 1048525.47
| 03 | E3N39 | 43078815201 | 2015-05-14 | QTR4 | 14/15 | 2 | 2 | 185 | 318 | 294 | 90.81% | 1 | 24 | 0 | 0 | 133 | 0 | 3111936 | 50000 | 3061936 | 3033818 | 2963684 | -11504 | 0 | -11504 | 2952180 | 2882199 | 94.13% | 1 | -69981 | -78118 | 85 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 18424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -96542 | 0 | 7 | 0 | -78118 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-20 | QTR4 | 15/16 | 314 | 3291622.83
| 03 | E3N74 | 42696915201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 125 | 164 | 164 | 100% | 1 | 0 | 0 | 0 | 39 | 0 | 2813937 | 50000 | 2763937 | 2813937 | 2913809 | 0 | 0 | 0 | 2913809 | 2837766 | 102.7% | 1 | -76042 | 0 | 28 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 308 | 3196208.79
| 03 | E3N80 | 42577825201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 60 | 79 | 87 | 116.7% | 1 | -8 | 8 | 0 | 19 | 0 | 246955 | 8741 | 238214 | 246955 | 248745 | -7664 | 0 | -7664 | 241081 | 241081 | 101.2% | 1 | 0 | 0 | 10 | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | F208328161 | AN-KAR CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 308 | 183110.5
| 03 | E3O47 | 43253815201 | 2015-10-15 | QTR2 | 15/16 | 1 | 0 | 100 | 128 | 128 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 2030029 | 50000 | 1980029 | 2030029 | 2131829 | 0 | 0 | 0 | 2131829 | 2045055 | 103.3% | 1 | -86775 | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-12 | QTR1 | 16/17 | 321 | 2649534.01
| 03 | E3O62 | 43079215201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 90 | 131 | 129 | 116.7% | 1 | 2 | 0 | 0 | 24 | 17 | 1298500 | 50000 | 1248500 | 1382401 | 1347119 | 0 | 0 | 0 | 1347119 | 1319720 | 105.7% | 1 | -27399 | 83901 | 17 | 7 | 0 | 17 | 83901 | 15601 | 0 | 0 | 3826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 87727 | 15601 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-08 | QTR1 | 16/17 |  | 2016-07-11 | QTR1 | 16/17 | 321 | 1564334.7 | B0 | ACC - LUMP SUM
| 03 | E3P32 | 42460825201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 40 | 51 | 48 | 92.5% | 1 | 3 | 0 | 0 | 11 | 0 | 69197 | 6233 | 62964 | 69197 | 67195 | 0 | 0 | 0 | 67195 | 67195 | 106.7% | 1 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-01 | QTR1 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 321 | 143399.73
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 13 | 15 | 13 | 1959 | 3350 | 3309 | 76.92% | 10 | 41 | 8 | 0 | 1019 | 372 | 42250571 | 622695 | 41627877 | 42630463 | 43229594 | -19168 | 0 | -19168 | 43210426 | 42816543 | 84.62% | 11 | -393883 | 379893 | 605 | 222 | 0 | 36 | -110443 | 31783 | 22 | 24 | 375386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 115 | 291 | 478359 | 305454 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -109542 | 0 | 192 | 372 | 639360 | 337237
| District 03 Totals |  |  |  |  | 23 | 34 | 50 | 6050 | 9971 | 9837 | 78.26% | 18 | 134 | 10 | 0 | 2849 | 1072 | 101229396 | 1343149 | 99886248 | 105452571 | 106013381 | -124316 | 0 | -124316 | 105889065 | 103508845 | 86.96% | 20 | -2380220 | 4223175 | 1717 | 629 | 44 | 552 | 2641615 | 875850 | 39 | 160 | 1027212 | 60348 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 268 | 309 | 862340 | 319069 | 0 | 0 | 3613 | 0 | 0 | 0 | -59292 | 0 | 0 | 51 | 397950 | 185379 | 97 | 0 | 126858 | 126858 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -109542 | 0 | 503 | 1072 | 4881002 | 1567504
| 04 | T4341 | 23073015201 | 2013-02-06 | QTR3 | 12/13 | 2 | 8 | 674 | 896 | 896 | 111% | 1 | 0 | 0 | 0 | 191 | 31 | 6592014 | 73358 | 6518656 | 6833204 | 6617553 | 0 | 0 | 0 | 6617553 | 6330385 | 97.11% | 1 | -287168 | 241190 | 105 | 43 | 0 | 31 | 138206 | 0 | 4 | 0 | 108342 | 50933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 31 | 314541 | 50933 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2016-07-06 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 412 | 7354583.81
| 04 | T4389 | 23097825201 | 2014-04-30 | QTR4 | 13/14 | 1 | 2 | 750 | 801 | 631 | 77.33% | 1 | 170 | 0 | 0 | 51 | 0 | 15715809 | 150000 | 15565809 | 15753499 | 15520925 | 0 | 630700 | 630700 | 16151625 | 14963445 | 96.13% | 1 | -1188180 | 37690 | 29 | 22 | 0 | 0 | 48793 | 0 | 0 | 0 | 38749 | 2893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66399 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158063 | 2893 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2016-09-12 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 408 | 15839218.13 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4402 | 42973715201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 540 | 577 | 542 | 93.52% | 1 | 35 | 0 | 0 | 37 | 0 | 2824000 | 50000 | 2774000 | 2824000 | 2773850 | 0 | 0 | 0 | 2773850 | 2779467 | 100.2% | 1 | 5617 | 0 | 15 | 22 | 0 | 0 | 8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8687 | 0 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 408 | 3519184.32 | B0 | ACC - LUMP SUM
| 04 | T4416 | 43171715201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 238 | 268 | 261 | 97.48% | 1 | 7 | 0 | 0 | 30 | 0 | 1444863 | 50000 | 1394863 | 1444863 | 1398240 | 0 | 0 | 0 | 1398240 | 1398240 | 100.2% | 1 | 0 | 0 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 412 | 1613353.82
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 4 | 6 | 10 | 2202 | 2542 | 2330 | 100% | 4 | 212 | 0 | 0 | 309 | 31 | 26576686 | 323358 | 26253328 | 26855566 | 26310568 | 0 | 630700 | 630700 | 26941268 | 25471537 | 100% | 4 | -1469731 | 278880 | 168 | 97 | 0 | 31 | 195686 | 0 | 4 | 0 | 147091 | 53826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143804 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 31 | 495540 | 53826
| 04 | E4P98 | 42605315201 | 2015-02-06 | QTR3 | 14/15 | 2 | 2 | 238 | 283 | 280 | 104.6% | 1 | 3 | 0 | 0 | 45 | 0 | 1670723 | 50000 | 1620723 | 1694884 | 1701995 | 0 | 0 | 0 | 1701995 | 1694894 | 104.6% | 1 | -7101 | 24162 | 17 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 9687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43444 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-02-26 | QTR3 | 15/16 | 409 | 1844040.91
| 04 | E4Q70 | 43056615201 | 2015-04-03 | QTR4 | 14/15 | 1 | 0 | 86 | 99 | 99 | 100% | 1 | 0 | 0 | 0 | 13 | 0 | 594927 | 36890 | 558037 | 594927 | 563713 | 0 | 0 | 0 | 563713 | 563713 | 101% | 1 | 0 | 0 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-07-08 | QTR1 | 16/17 | 412 | 789528.37
| 04 | E4R65 | 43538615201 | 2016-01-08 | QTR3 | 15/16 | 2 | 0 | 65 | 92 | 91 | 106.2% | 1 | 1 | 0 | 0 | 23 | 4 | 593859 | 24145 | 569714 | 593859 | 535917 | 0 | 0 | 0 | 535917 | 535917 | 94.07% | 1 | 0 | 0 | 18 | 4 | 0 | 4 | 8796 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9546 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 409 | 495318.22
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 3 | 5 | 2 | 389 | 474 | 470 | 100% | 3 | 4 | 0 | 0 | 81 | 4 | 2859509 | 111035 | 2748474 | 2883670 | 2801625 | 0 | 0 | 0 | 2801625 | 2794524 | 100% | 3 | -7101 | 24162 | 46 | 20 | 0 | 4 | 8796 | 0 | 0 | 0 | 10437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 52990 | 0
| District 04 Totals |  |  |  |  | 7 | 11 | 12 | 2591 | 3016 | 2800 | 100% | 7 | 216 | 0 | 0 | 390 | 35 | 29436195 | 434393 | 29001802 | 29739236 | 29112193 | 0 | 630700 | 630700 | 29742893 | 28266061 | 100% | 7 | -1476832 | 303042 | 214 | 117 | 0 | 35 | 204482 | 0 | 4 | 0 | 157528 | 53826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177561 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 35 | 548530 | 53826
| 05 | T5496 | 43106615201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 460 | 684 | 678 | 97.61% | 1 | 6 | 0 | 0 | 224 | 0 | 4198661 | 57000 | 4141661 | 4198661 | 4290920 | 0 | 0 | 0 | 4290920 | 4280333 | 103.3% | 1 | -10587 | 0 | 199 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 514 | 5833243.5
| 05 | T5497 | 43113915201 | 2014-06-18 | QTR4 | 13/14 | 4 | 2 | 350 | 479 | 448 | 99.71% | 1 | 31 | 0 | 0 | 99 | 30 | 5577400 | 50000 | 5527400 | 5630674 | 5316503 | 0 | 0 | 0 | 5316503 | 5110931 | 92.47% | 1 | -205572 | 53274 | 72 | 27 | 0 | 0 | 16219 | 0 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 62720 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-13 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 514 | 5261131.52 | B0:B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 05 | T5507 | 42908315201 | 2014-10-29 | QTR2 | 14/15 | 2 | 3 | 352 | 458 | 457 | 105.7% | 1 | 1 | 0 | 0 | 85 | 21 | 13950000 | 132000 | 13818000 | 14304220 | 14416417 | 0 | 0 | 0 | 14416417 | 13245104 | 95.85% | 1 | -1171314 | 354220 | 70 | 15 | 0 | 0 | 36422 | 0 | 0 | 0 | 46490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 308750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 391661 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 512 | 13411584.34
| 05 | T5515 | 43066815201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 210 | 284 | 284 | 115.2% | 1 | 0 | 0 | 0 | 44 | 30 | 1884019 | 50000 | 1834019 | 1929335 | 1919435 | 0 | 0 | 0 | 1919435 | 1870656 | 102% | 1 | -48780 | 45316 | 30 | 12 | 0 | 24 | 59005 | 0 | 0 | 6 | 21372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 80377 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2016-05-05 | QTR4 | 15/16 | 514 | 1716624.23 | B0 | ACC - LUMP SUM
| 05 | T5528 | 43066915201 | 2015-05-27 | QTR4 | 14/15 | 1 | 1 | 200 | 245 | 224 | 90.5% | 1 | 21 | 0 | 0 | 45 | 0 | 2181000 | 50000 | 2131000 | 2446253 | 2396253 | 0 | 0 | 0 | 2396253 | 2380075 | 111.7% | 0 | -16178 | 265253 | 19 | 24 | 0 | 0 | 145670 | 0 | 0 | 0 | 119583 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265253 | 508 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-07-01 | QTR1 | 16/17 |  | 2016-04-06 | QTR4 | 15/16 | 507 | 1883279.22
| 05 | T5536 | 43067715201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 216 | 247 | 233 | 93.52% | 1 | 14 | 0 | 0 | 31 | 0 | 2584884 | 50000 | 2534884 | 2614884 | 2636650 | 0 | 0 | 0 | 2636650 | 2540033 | 100.2% | 1 | -96617 | 30000 | 12 | 19 | 0 | 0 | 15490 | 0 | 0 | 0 | 58864 | 13921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74355 | 13921 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-07-22 | QTR1 | 16/17 | 513 | 2795913.94
| 05 | T5537 | 43244215201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 110 | 154 | 147 | 111.8% | 1 | 7 | 0 | 0 | 24 | 20 | 1272760 | 42000 | 1230760 | 1272760 | 1267646 | 0 | 0 | 0 | 1267646 | 1267646 | 103% | 1 | 0 | 0 | 9 | 15 | 0 | 0 | 615 | 0 | 0 | 20 | 34326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 34941 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-06-10 | QTR4 | 15/16 | 513 | 919590 | B0 | ACC - LUMP SUM
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 7 | 12 | 9 | 1898 | 2551 | 2471 | 100% | 7 | 80 | 0 | 0 | 552 | 101 | 31648724 | 431000 | 31217724 | 32396787 | 32243824 | 0 | 0 | 0 | 32243824 | 30694778 | 85.71% | 6 | -1549048 | 748063 | 411 | 142 | 0 | 24 | 273421 | 0 | 0 | 26 | 285935 | 14429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 308750 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 909307 | 14429
| 05 | E5W67 | 43198915201 | 2014-10-07 | QTR2 | 14/15 | 1 | 2 | 300 | 340 | 393 | 126.7% | 0 | -53 | 53 | 0 | 13 | 27 | 2340785 | 50000 | 2290785 | 2247902 | 2197902 | -92326 | 0 | -92326 | 2105576 | 2104471 | 91.87% | 1 | -1105 | -92883 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | -92883 | 0 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-02-10 | QTR3 | 15/16 | 509 | 2486510
| 05 | E5W83 | 43528215201 | 2015-04-07 | QTR4 | 14/15 | 1 | 0 | 240 | 265 | 264 | 99.58% | 1 | 1 | 0 | 0 | 25 | 0 | 2750721 | 50000 | 2700721 | 2750721 | 2676098 | 0 | 0 | 0 | 2676098 | 2676025 | 99.09% | 1 | -73 | 0 | 7 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-07-20 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 513 | 2985731
| 05 | E5Y02 | 43705815201 | 2015-09-01 | QTR1 | 15/16 | 1 | 0 | 130 | 134 | 107 | 79.23% | 1 | 27 | 0 | 0 | 4 | 0 | 783941 | 39000 | 744941 | 783941 | 744941 | 0 | 0 | 0 | 744941 | 744941 | 100% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-08-09 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 515 | 821518.11
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 3 | 3 | 2 | 670 | 739 | 764 | 66.67% | 2 | -25 | 53 | 0 | 42 | 27 | 5875447 | 139000 | 5736447 | 5782564 | 5618941 | -92326 | 0 | -92326 | 5526615 | 5525437 | 100% | 3 | -1178 | -92883 | 13 | 29 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | -92883 | 0
| District 05 Totals |  |  |  |  | 10 | 15 | 11 | 2568 | 3290 | 3235 | 90% | 9 | 55 | 53 | 0 | 594 | 128 | 37524171 | 570000 | 36954171 | 38179351 | 37862765 | -92326 | 0 | -92326 | 37770439 | 36220215 | 90% | 9 | -1550226 | 655180 | 424 | 171 | 0 | 24 | 273421 | 0 | 0 | 53 | 285935 | 14429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 215867 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 816424 | 14429
| 06 | T6320 | 42914015201 | 2014-06-18 | QTR4 | 13/14 | 3 | 3 | 450 | 503 | 387 | 74.22% | 1 | 116 | 0 | 0 | 53 | 0 | 14295524 | 150000 | 14145524 | 14692214 | 13690377 | 0 | 245000 | 245000 | 13935377 | 13056864 | 92.3% | 1 | -878513 | 396690 | 43 | 10 | 0 | 0 | 18351 | 0 | 0 | 0 | 421570 | 152744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447735 | 152744 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 606 | 15289319.55 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6325 | 25055425201 | 2012-10-31 | QTR2 | 12/13 | 1 | 3 | 700 | 903 | 870 | 96.43% | 1 | 33 | 0 | 0 | 197 | 6 | 11430054 | 123500 | 11306554 | 11749528 | 11929942 | 0 | 0 | 0 | 11929942 | 11924070 | 105.5% | 1 | -5871 | 319473 | 154 | 41 | 2 | 0 | 266319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 63468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 370763 | 0 | F410827177 | JOHNSON BROS. CORPORATION | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 606 | 12087502
| 06 | T6373 | 43080915201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 230 | 328 | 326 | 112.6% | 1 | 2 | 0 | 0 | 98 | 0 | 2376742 | 50130 | 2326612 | 2426742 | 2460615 | 0 | 0 | 0 | 2460615 | 2384892 | 102.5% | 1 | -75723 | 50000 | 56 | 11 | 31 | 0 | 16266 | 0 | 0 | 0 | 14872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 71617 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-12 | QTR4 | 15/16 | 606 | 2292101.6
| 06 | T6376 | 43081715201 | 2015-02-25 | QTR3 | 14/15 | 2 | 4 | 435 | 468 | 375 | 78.62% | 1 | 93 | 0 | 0 | 33 | 0 | 6621887 | 69750 | 6552137 | 6805679 | 6261293 | 0 | 470000 | 470000 | 6731293 | 6082074 | 92.83% | 1 | -649219 | 183793 | 21 | 12 | 0 | 0 | 71716 | 0 | 0 | 0 | 115147 | 9450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186863 | 9450 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-27 | QTR1 | 16/17 |  | 2016-05-08 | QTR4 | 15/16 | 606 | 6429680.27 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6384 | 43350815201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 439934 | 26680 | 413254 | 439934 | 417205 | 0 | 0 | 0 | 417205 | 417205 | 101% | 1 | 0 | 0 | 16 | 1 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 606 | 559680 | B0 | ACC - LUMP SUM
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 5 | 9 | 11 | 1935 | 2339 | 2095 | 100% | 5 | 244 | 0 | 0 | 398 | 6 | 35164141 | 420060 | 34744081 | 36114097 | 34759432 | 0 | 715000 | 715000 | 35474432 | 33865105 | 100% | 5 | -1609326 | 949956 | 290 | 75 | 33 | 0 | 378652 | 0 | 0 | 0 | 551589 | 162194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 71282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 6 | 1082978 | 162194
[29 empty] | 0% | 1
| Dist 06 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 06 Totals |  |  |  |  | 5 | 9 | 11 | 1935 | 2339 | 2095 | 100% | 5 | 244 | 0 | 0 | 398 | 6 | 35164141 | 420060 | 34744081 | 36114097 | 34759432 | 0 | 715000 | 715000 | 35474432 | 33865105 | 100% | 5 | -1609326 | 949956 | 290 | 75 | 33 | 0 | 378652 | 0 | 0 | 0 | 551589 | 162194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 71282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 6 | 1082978 | 162194
| 07 | T7209 | 25841515201 | 2009-09-16 | QTR1 | 09/10 | 7 | 55 | 1065 | 1694 | 1694 | 151% | 0 | 0 | 0 | 0 | 109 | 520 | 389463750 | 75000 | 389388750 | 430319761 | 437468272 | 0 | 0 | 0 | 437468272 | 439424048 | 112.8% | 0 | 1955776 | 40856011 | 52 | 34 | 22 | 67 | 10225188 | 4993195 | 1 | 121 | 13703270 | 4748092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 6407054 | 1636245 | 0 | 0 | 10009318 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 173923 | 100951 | 0 | 0 | 210466 | 210466 | 0 | 0 | 3584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 520 | 40732802 | 11688949 | F263258515 | PCL/ARCHER WESTERN A JOINT VEN | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2014-10-19 | QTR2 | 14/15 | 714 | 412328910.33 | ARRA:B2:B5:P:B2 | AMERICAN RECOVERY AND REINVEST:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:PUBLIC PRIVATE PARTNERSHIP:ACC - A+B (COST+TIME BIDDING)
| 07 | T7236 | 25589325201 | 2011-09-28 | QTR1 | 11/12 | 2 | 7 | 410 | 560 | 740 | 148.5% | 0 | -180 | 180 | 0 | 131 | 19 | 7147510 | 74000 | 7073510 | 7510715 | 7761739 | -452520 | 0 | -452520 | 7309219 | 7308427 | 103.3% | 1 | -793 | 363205 | 107 | 24 | 0 | 15 | 337971 | 0 | 0 | 4 | 38132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 372176 | 0 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2016-08-10 | QTR1 | 16/17 |  | 2014-06-13 | QTR4 | 13/14 | 717 | 8423805.36
| 07 | T7362 | 42907725202 | 2015-03-25 | QTR3 | 14/15 | 2 | 0 | 180 | 256 | 256 | 100% | 1 | 0 | 0 | 0 | 76 | 0 | 5709404 | 50000 | 5659404 | 5709404 | 5625130 | 0 | 0 | 0 | 5625130 | 5464793 | 96.56% | 1 | -160337 | 0 | 57 | 19 | 0 | 0 | 8822 | 0 | 0 | 0 | 10150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-08-19 | QTR1 | 16/17 |  | 2016-05-16 | QTR4 | 15/16 | 717 | 5660000
| 07 | T7366 | 43113215201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 150 | 211 | 210 | 99.33% | 1 | 1 | 0 | 0 | 61 | 0 | 1795000 | 50000 | 1745000 | 1795000 | 1754140 | 0 | 0 | 0 | 1754140 | 1746653 | 100.1% | 1 | -7487 | 0 | 41 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-19 | QTR1 | 16/17 |  | 2016-03-18 | QTR3 | 15/16 | 717 | 1415000 | B0 | ACC - LUMP SUM
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 4 | 13 | 62 | 1805 | 2721 | 2900 | 50% | 2 | -179 | 180 | 0 | 377 | 539 | 404115664 | 249000 | 403866664 | 445334880 | 452609281 | -452520 | 0 | -452520 | 452156761 | 453943921 | 75% | 3 | 1787159 | 41219216 | 257 | 97 | 22 | 82 | 10571981 | 4993195 | 1 | 125 | 13751552 | 4748092 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 6414481 | 1636245 | 0 | 0 | 10009318 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 173923 | 100951 | 0 | 0 | 210466 | 210466 | 0 | 0 | 3584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 539 | 41131378 | 11688949
| 07 | E7I46 | 25633925201 | 2014-08-14 | QTR1 | 14/15 | 1 | 4 | 450 | 623 | 622 | 107.8% | 1 | 1 | 0 | 0 | 137 | 36 | 15944000 | 150000 | 15794000 | 16474127 | 16294835 | 0 | 0 | 0 | 16294835 | 15360010 | 97.25% | 1 | -934824 | 530127 | 97 | 40 | 0 | 0 | 56222 | 0 | 0 | 1 | 186898 | 3530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 346909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 590029 | 3530 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-15 | QTR1 | 16/17 |  | 2016-06-25 | QTR4 | 15/16 | 714 | 18310419.41 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 07 | E7J99 | 42715515201 | 2015-04-08 | QTR4 | 14/15 | 1 | 1 | 199 | 302 | 274 | 101% | 1 | 28 | 0 | 0 | 103 | 0 | 1844400 | 50000 | 1794400 | 1881240 | 1852163 | 0 | 0 | 0 | 1852163 | 1792416 | 99.89% | 1 | -59746 | 36840 | 47 | 26 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 |  | 2016-06-28 | QTR4 | 15/16 | 798 | 1650000
| 07 | E7K02 | 43090115201 | 2015-02-11 | QTR3 | 14/15 | 1 | 3 | 125 | 176 | 176 | 109.6% | 1 | 0 | 0 | 0 | 39 | 12 | 2683100 | 50000 | 2633100 | 2806747 | 2817266 | 0 | 0 | 0 | 2817266 | 2772695 | 105.3% | 1 | -44571 | 123647 | 34 | 5 | 0 | 12 | 67604 | 15358 | 0 | 0 | 123204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17782 | 0 | 0 | 12 | 173025 | 15358 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-07 | QTR1 | 16/17 |  | 2015-11-30 | QTR2 | 15/16 | 709 | 2450000 | B0 | ACC - LUMP SUM
| 07 | E7K04 | 43066015201 | 2015-03-11 | QTR3 | 14/15 | 1 | 2 | 180 | 281 | 281 | 118.9% | 1 | 0 | 0 | 0 | 82 | 19 | 2680382 | 50000 | 2630382 | 2750471 | 2763085 | 0 | 0 | 0 | 2763085 | 2699178 | 102.6% | 1 | -63907 | 70089 | 46 | 21 | 0 | 0 | 0 | 0 | 0 | 19 | 111980 | 18119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 19 | 114701 | 18119 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-03-14 | QTR3 | 15/16 | 709 | 2007403 | B0 | ACC - LUMP SUM
| 07 | E7K05 | 43243225201 | 2015-03-11 | QTR3 | 14/15 | 1 | 0 | 220 | 262 | 261 | 99.55% | 1 | 1 | 0 | 0 | 42 | 0 | 1086230 | 50000 | 1036230 | 1086230 | 1062839 | 0 | 0 | 0 | 1062839 | 1062824 | 102.6% | 1 | -15 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2016-09-26 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 717 | 1230200
| 07 | E7K17 | 43094815201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 220 | 258 | 212 | 79.09% | 1 | 46 | 0 | 0 | 38 | 0 | 2888000 | 50000 | 2838000 | 2888000 | 2727932 | 0 | 0 | 0 | 2727932 | 2690622 | 94.81% | 1 | -37311 | 0 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-16 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 798 | 3200000 | B0 | ACC - LUMP SUM
| 07 | E7K67 | 43149515201 | 2015-05-13 | QTR4 | 14/15 | 1 | 4 | 140 | 178 | 178 | 107.1% | 1 | 0 | 0 | 0 | 28 | 10 | 2794895 | 50000 | 2744895 | 2964710 | 2918290 | -7200 | 0 | -7200 | 2911090 | 2905726 | 105.9% | 1 | -5363 | 169815 | 17 | 11 | 0 | 5 | 49615 | 0 | 0 | 5 | 161418 | 7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17145 | 0 | 0 | 10 | 193888 | 7074 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 717 | 1905000
| 07 | E7K78 | 43080235201 | 2015-09-09 | QTR1 | 15/16 | 2 | 0 | 206 | 217 | 128 | 56.8% | 1 | 89 | 0 | 0 | 11 | 0 | 1271000 | 50000 | 1221000 | 1271000 | 1221000 | 0 | 0 | 0 | 1221000 | 1221000 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-05-10 | QTR4 | 15/16 | 717 | 2206022.47 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 07 | E7K80 | 43478115201 | 2015-08-12 | QTR1 | 15/16 | 2 | 2 | 160 | 203 | 203 | 101.2% | 1 | 0 | 0 | 0 | 41 | 2 | 1052289 | 33000 | 1019289 | 1092289 | 992268 | 0 | 0 | 0 | 992268 | 991427 | 97.27% | 1 | -840 | 40000 | 21 | 20 | 0 | 0 | 7453 | 0 | 0 | 2 | 55456 | 19923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 62908 | 19923 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 717 | 752249.19
| 07 | E7L07 | 43258315201 | 2015-11-12 | QTR2 | 15/16 | 1 | 0 | 80 | 89 | 89 | 105% | 1 | 0 | 0 | 0 | 5 | 4 | 1115377 | 50000 | 1065377 | 1115377 | 1056390 | 0 | 0 | 0 | 1056390 | 1056390 | 99.16% | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 798 | 1450000 | B0 | ACC - LUMP SUM
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 10 | 12 | 16 | 1980 | 2589 | 2424 | 100% | 10 | 165 | 0 | 0 | 526 | 83 | 33359673 | 583000 | 32776673 | 34330191 | 33706068 | -7200 | 0 | -7200 | 33698868 | 32552288 | 100% | 10 | -1146577 | 970518 | 319 | 162 | 0 | 17 | 180894 | 15358 | 30 | 27 | 683063 | 48646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 39 | 375562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34927 | 0 | 45 | 83 | 1204591 | 64004
| District 07 Totals |  |  |  |  | 14 | 25 | 78 | 3785 | 5310 | 5324 | 85.71% | 12 | -14 | 180 | 0 | 903 | 622 | 437475337 | 832000 | 436643337 | 479665071 | 486315349 | -459720 | 0 | -459720 | 485855629 | 486496209 | 92.86% | 13 | 640582 | 42189734 | 576 | 259 | 22 | 99 | 10752875 | 5008553 | 31 | 152 | 14434615 | 4796738 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 15 | 346 | 6790043 | 1636245 | 0 | 0 | 10009318 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 173923 | 100951 | 0 | 0 | 210466 | 210466 | 0 | 0 | 3584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34927 | 0 | 68 | 622 | 42335969 | 11752953
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8N60 | 41546265201 | 2014-05-20 | QTR4 | 13/14 | 1 | 3 | 475 | 545 | 545 | 100.2% | 1 | 0 | 0 | 0 | 70 | 0 | 10628174 | 96840 | 10531334 | 10702005 | 10703365 | -6500 | 0 | -6500 | 10696865 | 10548835 | 100.2% | 1 | -148030 | 73831 | 23 | 46 | 0 | 0 | 8969 | 0 | 0 | 0 | 107706 | 13562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 117912 | 13562 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-04-12 | QTR4 | 15/16 | 854 | 9781121.21
| 08 | E8P54 | 43110015201 | 2015-10-20 | QTR2 | 15/16 | 1 | 1 | 115 | 121 | 118 | 97.39% | 1 | 3 | 0 | 0 | 6 | 0 | 1369271 | 50000 | 1319271 | 1355607 | 1258468 | 0 | 0 | 0 | 1258468 | 1224485 | 92.82% | 1 | -33984 | -13664 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-06-24 | QTR4 | 15/16 | 854 | 1662320.12
| 08 | E8P55 | 43561715201 | 2015-06-16 | QTR4 | 14/15 | 1 | 1 | 140 | 189 | 189 | 102.9% | 1 | 0 | 0 | 0 | 45 | 4 | 1736149 | 50000 | 1686149 | 1766298 | 1678250 | -26500 | 0 | -26500 | 1651750 | 1651060 | 97.92% | 1 | -690 | 30149 | 29 | 16 | 0 | 4 | 30149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 30149 | 0 | F203908361 | MIDASCO LLC | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 854 | 1991671.8
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 3 | 3 | 5 | 730 | 855 | 852 | 100% | 3 | 3 | 0 | 0 | 121 | 4 | 13733594 | 196840 | 13536754 | 13823910 | 13640083 | -33000 | 0 | -33000 | 13607083 | 13424380 | 100% | 3 | -182704 | 90316 | 58 | 62 | 0 | 4 | 39118 | 0 | 0 | 0 | 94042 | 26163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 134397 | 26163
| District 08 Totals |  |  |  |  | 3 | 3 | 5 | 730 | 855 | 852 | 100% | 3 | 3 | 0 | 0 | 121 | 4 | 13733594 | 196840 | 13536754 | 13823910 | 13640083 | -33000 | 0 | -33000 | 13607083 | 13424380 | 100% | 3 | -182704 | 90316 | 58 | 62 | 0 | 4 | 39118 | 0 | 0 | 0 | 94042 | 26163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 134397 | 26163
| Statewide Central Let Contracts SubTotal |  |  |  |  | 52 | 86 | 168 | 15482 | 21282 | 20899 | 84.62% | 44 | 383 | 310 | 0 | 4200 | 1600 | 608447202 | 2895737 | 605551466 | 656231079 | 662895010 | -892086 | 1345700 | 453614 | 663348623 | 657330468 | 86.54% | 45 | -6018160 | 47783875 | 2702 | 1067 | 99 | 797 | 14437931 | 5837262 | 25 | 365 | 16096150 | 5038889 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 153 | 350 | 7323912 | 1649860 | 0 | 30 | 10060369 | 0 | 0 | 0 | -59292 | 0 | 0 | 61 | 628055 | 286330 | 97 | 0 | 337324 | 337324 | 39 | 0 | 8421 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -26462 | 0 | 413 | 1600 | 48802480 | 13149665
| Statewide District Let Contracts SubTotal |  |  |  |  | 40 | 51 | 42 | 7768 | 10389 | 10221 | 87.5% | 35 | 168 | 93 | 0 | 2027 | 594 | 127902947 | 2102866 | 125800082 | 130352729 | 129482488 | -200718 | 0 | -200718 | 129281770 | 126945988 | 95% | 38 | -2335784 | 2449784 | 1156 | 615 | 3 | 81 | 557552 | 47141 | 52 | 162 | 1961827 | 766105 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 131 | 330 | 800164 | 305454 | 0 | 0 | 9818 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -156010 | 0 | 241 | 594 | 3178698 | 1118700
| Statewide Totals |  |  |  |  | 92 | 137 | 210 | 23250 | 31671 | 31120 | 85.87% | 79 | 551 | 403 | 0 | 6227 | 2194 | 736350149 | 4998603 | 731351548 | 786583808 | 792377498 | -1092804 | 1345700 | 252896 | 792630393 | 784276456 | 90.22% | 83 | -8353944 | 50233659 | 3858 | 1682 | 102 | 878 | 14995483 | 5884403 | 77 | 527 | 18057977 | 5804994 | 0 | 0 | 0 | 0 | 0 | 0 | -13677 | 0 | 0 | 0 | 0 | 0 | 284 | 680 | 8124076 | 1955314 | 0 | 30 | 10070187 | 0 | 0 | 0 | -59292 | 0 | 0 | 82 | 643155 | 286330 | 97 | 0 | 337324 | 337324 | 94 | 0 | 8421 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -182472 | 0 | 654 | 2194 | 51981178 | 14268365

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1N74 | 42912015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-18 | 3107573 | 3107573 | 3110593 | 0 | 0 | 2961957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3110593 | 2961957 | -148636 | 3280021
1 | E1N87 | 43120915201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2015-02-19 | 3172000 | 3172000 | 3272265 | 0 | 0 | 3269380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3272265 | 3269380 | -2886 | 3312411
1 | E1O02 | 43161515201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-01-15 | 5445703 | 6533716 | 6114803 | 1088013.37 | 0 | 5883385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6114803 | 5883385 | -231419 | 4971482
1 | E1O75 | 43503815201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-01-21 | 149955 | 149955 | 147793 | 0 | 0 | 147793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147793 | 147793 | 0 | 157974
1 | T1417 | 41612015201 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2011-12-07 | 12691971 | 13256420 | 13055581 | 564449.7 | -656700 | 12402265 | -656700 | 0 | 0 | 0 | 0 | 0 | -656700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -656700 | 12398881 | 12402265 | 3384 | 11408242
1 | T1560 | 42910115201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-08-26 | 4883160 | 4883160 | 4742567 | 0 | 0 | 4581604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4742567 | 4581604 | -160964 | 5451825
1 | T1583 | 42910715201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-05-21 | 12221582 | 12321397 | 12316064 | 99814.55 | -258944 | 11369478 | -258944 | 0 | 0 | 0 | 0 | 0 | -258944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -258944 | 12057120 | 11369478 | -687643 | 11851722
1 | T1601 | 42910615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 2560715 | 2560715 | 2601322 | 0 | 0 | 2476584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601322 | 2476584 | -124738 | 2539522
1 | T1604 | 43340715201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1272557 | 1265786 | 1215247 | -6770.49 | 0 | 1215247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215247 | 1215247 | 0 | 1175939 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1610 | 43337615201 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2015-05-20 | 766880 | 763925 | 702653 | -2955.57 | -27872 | 674781 | -27872 | 0 | 0 | 0 | 0 | 0 | -27872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27872 | 674781 | 674781 | 0 | 1032308 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1612 | 43539315201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 965039 | 965864 | 949501 | 824.93 | 0 | 941761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949501 | 941761 | -7741 | 968995
1 | T1615 | 42950615201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1470894 | 1470894 | 1424904 | 0 | 0 | 1424904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424904 | 1424904 | 0 | 1441635 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1617 | 43337515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1087453 | 1211375 | 1165751 | 123921.65 | 0 | 1165751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165751 | 1165751 | 0 | 1092794 | B0 | ACC - LUMP SUM
1 | T1618 | 43340815201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-06-17 | 1135821 | 1138128 | 1108067 | 2307.3 | 0 | 1103946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108067 | 1103946 | -4121 | 1209050 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1629 | 43325615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-30 | 910000 | 910000 | 883227 | 0 | 0 | 883227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883227 | 883227 | 0 | 857875 | B0 | ACC - LUMP SUM
1 | T1651 | 43134115201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-01-27 | 194630 | 194630 | 184896 | 0 | 0 | 184896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184896 | 184896 | 0 | 236550 | B0 | ACC - LUMP SUM
1 | T1A02 | 42518315201 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 5396928 | 5491707 | 5952983 | 94778.73 | 0 | 5952455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5952983 | 5952455 | -528 | 4358787 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1A15 | 43325515201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 219504 | 219504 | 213917 | 0 | 0 | 213917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213917 | 213917 | 0 | 200589 | B0 | ACC - LUMP SUM
2 | E2R04 | 21066125201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2012-12-12 | 1430432 | 1430840 | 1393606 | 408.1 | -49024 | 1344578 | -49024 | 0 | 0 | 0 | 0 | 0 | -49024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49024 | 1344582 | 1344578 | -4 | 1293927
2 | E2R17 | 21237935201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2013-06-20 | 11440230 | 11429587 | 11316805 | -10643.03 | 0 | 11261013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11316805 | 11261013 | -55793 | 13890663 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
2 | E2T70 | 43219415201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2015-07-15 | 741630 | 741630 | 709180 | 0 | 0 | 709010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709180 | 709010 | -170 | 775810
2 | E2T74 | 42342715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-09-16 | 4336630 | 4336630 | 4421132 | 0 | 0 | 4255700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4421132 | 4255700 | -165433 | 4754491
2 | T2506 | 43040415201 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2013-10-30 | 136157 | 136157 | 128357 | 0 | -47602 | 80754 | -41690 | 0 | 0 | 0 | -5912 | 0 | -47602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47602 | 80754 | 80754 | 0 | 153003 | B0 | ACC - LUMP SUM
2 | T2533 | 43355415201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-06-18 | 8533240 | 8598881 | 9356445 | 65640.9 | 0 | 9207548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9356445 | 9207548 | -148897 | 7794226
2 | T2567 | 43224715201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2015-02-25 | 1013111 | 1368388 | 1368010 | 355277.03 | 0 | 1368010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368010 | 1368010 | 0 | 1004174 | B0 | ACC - LUMP SUM
2 | T2572 | 43061415201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 1990811 | 2002450 | 2059822 | 11638.3 | 0 | 2059822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059822 | 2059822 | 0 | 1508390
2 | T2587 | 43265515201 | F453689782 | SOUTHERN STATES PAVEMENT MARKINGS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 718800 | 718800 | 718800 | 0 | 0 | 718800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718800 | 718800 | 0 | 769167 | B0 | ACC - LUMP SUM
2 | T2594 | 43265415201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2015-09-30 | 475000 | 475000 | 475000 | 0 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000 | 475000 | 0 | 428506 | B0 | ACC - LUMP SUM
2 | T2603 | 43075915201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 521218 | 521218 | 506672 | 0 | 0 | 506672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506672 | 506672 | 0 | 510082
2 | T2608 | 43055825201 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2015-10-28 | 148375 | 148375 | 138616 | 0 | 0 | 138616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138616 | 138616 | 0 | 178082
2 | T9006 | 43675915201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2015-05-20 | 5341287 | 5341287 | 5975297 | 0 | 0 | 5919052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5975297 | 5919052 | -56245 | 5370611
3 | E3K73 | 42693515201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2014-03-13 | 1221881 | 1231781 | 1143560 | 9900 | 0 | 1120620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1143560 | 1120620 | -22940 | 1514949
3 | E3L90 | 42840315201 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2013-06-28 | 24049000 | 24338104 | 24337828 | 289103.75 | 0 | 24337642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24337828 | 24337642 | -186 | 21314872 | A3 | ICC - DESIGN/BUILD - MINOR
3 | E3M17 | 40747845201 | F455085205 | PRINCIPLE PROPERTIES INC. | N/A | N/A | N/A | N/A | 2015-11-20 | 149498 | 149498 | 139613 | 0 | 0 | 139613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139613 | 139613 | 0 | 163264
3 | E3M55 | 42805825201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2014-01-31 | 1540571 | 1579254 | 1571464 | 38682.88 | 0 | 1571464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1571464 | 1571464 | 0 | 1529160 | A3 | ICC - DESIGN/BUILD - MINOR
3 | E3M95 | 41694315201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-07-09 | 2738862 | 3014082 | 3595051 | 275219.9 | 0 | 3484491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3595051 | 3484491 | -110560 | 3204695
3 | E3N17 | 43392715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-10 | 1734968 | 1417537 | 1360898 | -317430.27 | 0 | 1360898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360898 | 1360898 | 0 | 1346664
3 | E3N18 | 43391815201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-10-08 | 1245237 | 1323870 | 1408799 | 78632.64 | 0 | 1408799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1408799 | 1408799 | 0 | 1048525
3 | E3N39 | 43078815201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-05-14 | 3111936 | 3033818 | 2963684 | -78118.45 | -11504 | 2882199 | -11504 | 0 | 0 | 0 | 0 | 0 | -11504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11504 | 2952180 | 2882199 | -69981 | 3291623
3 | E3N74 | 42696915201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-11-20 | 2813937 | 2813937 | 2913809 | 0 | 0 | 2837766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2913809 | 2837766 | -76042 | 3196209
3 | E3N80 | 42577825201 | F208328161 | AN-KAR CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-01-14 | 246955 | 246955 | 248745 | 0 | -7664 | 241081 | -7664 | 0 | 0 | 0 | 0 | 0 | -7664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7664 | 241081 | 241081 | 0 | 183111
3 | E3O47 | 43253815201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-10-15 | 2030029 | 2030029 | 2131829 | 0 | 0 | 2045055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2131829 | 2045055 | -86775 | 2649534
3 | E3O62 | 43079215201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-12-10 | 1298500 | 1382401 | 1347119 | 83901.29 | 0 | 1319720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347119 | 1319720 | -27399 | 1564335 | B0 | ACC - LUMP SUM
3 | E3P32 | 42460825201 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-03-10 | 69197 | 69197 | 67195 | 0 | 0 | 67195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67195 | 67195 | 0 | 143400
3 | T3349 | 22041285201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2010-12-08 | 7357219 | 10528722 | 10638848 | 3171502.78 | -93018 | 10537771 | -93018 | 0 | 0 | 0 | 0 | 0 | -93018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -93018 | 10545830 | 10537771 | -8059 | 7320355 | ARRA | AMERICAN RECOVERY AND REINVEST
3 | T3375 | 42124315201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2012-02-29 | 14736078 | 15035632 | 14669101 | 299554.18 | 0 | 14620764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14669101 | 14620764 | -48338 | 18080147
3 | T3418 | 42551915201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2014-12-03 | 2589441 | 2672648 | 2648983 | 83206.58 | 0 | 2635144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2648983 | 2635144 | -13838 | 2582603
3 | T3427 | 42164415201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2013-07-31 | 11476305 | 11609159 | 11286785 | 132854.22 | -11250 | 10699458 | 0 | 0 | 0 | 0 | 0 | -11250 | -11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11250 | 11275535 | 10699458 | -576077 | 12800390
3 | T3443 | 42693415201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 4037987 | 4183812 | 4167957 | 145824.98 | 0 | 3846478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167957 | 3846478 | -321479 | 4397279
3 | T3482 | 42884515201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-01-28 | 7416925 | 7437265 | 7758460 | 20339.32 | -880 | 7441692 | 0 | 0 | 0 | 0 | 0 | -880 | -880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -880 | 7757580 | 7441692 | -315888 | 8733988
3 | T3495 | 42695615201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-29 | 1619321 | 1619321 | 1588249 | 0 | 0 | 1566711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1588249 | 1566711 | -21538 | 1991520
3 | T3515 | 43090835201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 8076272 | 8066272 | 8349102 | -10000 | 0 | 7667982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8349102 | 7667982 | -681120 | 8827285
3 | T3589 | 43174315201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-03-30 | 169047 | 169047 | 169047 | 0 | 0 | 169047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169047 | 169047 | 0 | 199840 | B0 | ACC - LUMP SUM
3 | T9009 | 43035625201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-06-24 | 1500230 | 1500230 | 1507255 | 0 | 0 | 1507255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507255 | 1507255 | 0 | 1868903
4 | E4P98 | 42605315201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-02-06 | 1670723 | 1694884 | 1701995 | 24161.58 | 0 | 1740331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1701995 | 1740331 | 38336 | 1844041
4 | E4Q70 | 43056615201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2015-04-03 | 594927 | 594927 | 563713 | 0 | 0 | 563713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563713 | 563713 | 0 | 789528
4 | E4R65 | 43538615201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-01-08 | 593859 | 593859 | 535917 | 0 | 0 | 540661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535917 | 540661 | 4743 | 495318
4 | T4341 | 23073015201 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2013-02-06 | 6592014 | 6833204 | 6617553 | 241190.16 | 0 | 6330385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6617553 | 6330385 | -287168 | 7354584
4 | T4389 | 23097825201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2014-04-30 | 15715809 | 15753499 | 15520925 | 37690.07 | 630700 | 14964924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630700 | 0 | 0 | 0 | 0 | 0 | 630700 | 630700 | 16151625 | 14964924 | -1186702 | 15839218 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4402 | 42973715201 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2014-07-30 | 2824000 | 2824000 | 2773850 | 0 | 0 | 2779467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2773850 | 2779467 | 5617 | 3519184 | B0 | ACC - LUMP SUM
4 | T4416 | 43171715201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 1444863 | 1444863 | 1398240 | 0 | 0 | 1398240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398240 | 1398240 | 0 | 1613354
5 | E5W67 | 43198915201 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2014-10-07 | 2340785 | 2247902 | 2197902 | -92883 | -92326 | 2104471 | -92326 | 0 | 0 | 0 | 0 | 0 | -92326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92326 | 2105576 | 2104471 | -1105 | 2486510
5 | E5W83 | 43528215201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-04-07 | 2750721 | 2750721 | 2676098 | 0 | 0 | 2676025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2676098 | 2676025 | -73 | 2985731
5 | E5Y02 | 43705815201 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2015-09-01 | 783941 | 783941 | 744941 | 0 | 0 | 744941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 744941 | 744941 | 0 | 821518
5 | T5496 | 43106615201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-05-21 | 4198661 | 4198661 | 4290920 | 0 | 0 | 4280333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4290920 | 4280333 | -10587 | 5833244
5 | T5497 | 43113915201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-06-18 | 5577400 | 5630674 | 5316503 | 53274.46 | 0 | 5110931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5316503 | 5110931 | -205572 | 5261132 | B0:B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
5 | T5507 | 42908315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-29 | 13950000 | 14304220 | 14416417 | 354219.83 | 0 | 13250583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14416417 | 13250583 | -1165834 | 13411584
5 | T5515 | 43066815201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-02-25 | 1884019 | 1929335 | 1919435 | 45316.44 | 0 | 1875340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919435 | 1875340 | -44095 | 1716624 | B0 | ACC - LUMP SUM
5 | T5528 | 43066915201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2015-05-27 | 2181000 | 2446253 | 2396253 | 265252.96 | 0 | 2380075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2396253 | 2380075 | -16178 | 1883279
5 | T5536 | 43067715201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 2584884 | 2614884 | 2636650 | 30000 | 0 | 2540033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2636650 | 2540033 | -96617 | 2795914
5 | T5537 | 43244215201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-09-30 | 1272760 | 1272760 | 1267646 | 0 | 0 | 1267646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267646 | 1267646 | 0 | 919590 | B0 | ACC - LUMP SUM
6 | T6320 | 42914015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 14295524 | 14692214 | 13690377 | 396690.11 | 245000 | 13056864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 0 | 245000 | 245000 | 13935377 | 13056864 | -878513 | 15289320 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6325 | 25055425201 | F410827177 | JOHNSON BROS. CORPORATION | N/A | N/A | N/A | N/A | 2012-10-31 | 11430054 | 11749528 | 11929942 | 319473.2 | 0 | 11924070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11929942 | 11924070 | -5871 | 12087502
6 | T6373 | 43080915201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-02-25 | 2376742 | 2426742 | 2460615 | 50000 | 0 | 2384892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2460615 | 2384892 | -75723 | 2292102
6 | T6376 | 43081715201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-02-25 | 6621887 | 6805679 | 6261293 | 183792.64 | 470000 | 6082074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 20000 | 0 | 470000 | 470000 | 6731293 | 6082074 | -649219 | 6429680 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6384 | 43350815201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2015-09-30 | 439934 | 439934 | 417205 | 0 | 0 | 417205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417205 | 417205 | 0 | 559680 | B0 | ACC - LUMP SUM
7 | E7I46 | 25633925201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-08-14 | 15944000 | 16474127 | 16294835 | 530127.11 | 0 | 15360010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16294835 | 15360010 | -934824 | 18310419 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
7 | E7J99 | 42715515201 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2015-04-08 | 1844400 | 1881240 | 1852163 | 36840.35 | 0 | 1792416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1852163 | 1792416 | -59746 | 1650000
7 | E7K02 | 43090115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-02-11 | 2683100 | 2806747 | 2817266 | 123647.22 | 0 | 2772695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2817266 | 2772695 | -44571 | 2450000 | B0 | ACC - LUMP SUM
7 | E7K04 | 43066015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-03-11 | 2680382 | 2750471 | 2763085 | 70089.15 | 0 | 2699178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2763085 | 2699178 | -63907 | 2007403 | B0 | ACC - LUMP SUM
7 | E7K05 | 43243225201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2015-03-11 | 1086230 | 1086230 | 1062839 | 0 | 0 | 1062824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062839 | 1062824 | -15 | 1230200
7 | E7K17 | 43094815201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-06-10 | 2888000 | 2888000 | 2727932 | 0 | 0 | 2690622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2727932 | 2690622 | -37311 | 3200000 | B0 | ACC - LUMP SUM
7 | E7K67 | 43149515201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-05-13 | 2794895 | 2964710 | 2918290 | 169814.53 | -7200 | 2905726 | 0 | 0 | 0 | 0 | 0 | -7200 | -7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7200 | 2911090 | 2905726 | -5363 | 1905000
7 | E7K78 | 43080235201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-09-09 | 1271000 | 1271000 | 1221000 | 0 | 0 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221000 | 1221000 | 0 | 2206022 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
7 | E7K80 | 43478115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-12 | 1052289 | 1092289 | 992268 | 40000 | 0 | 991427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992268 | 991427 | -840 | 752249
7 | E7L07 | 43258315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-11-12 | 1115377 | 1115377 | 1056390 | 0 | 0 | 1056390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056390 | 1056390 | 0 | 1450000 | B0 | ACC - LUMP SUM
7 | T7209 | 25841515201 | F263258515 | PCL/ARCHER WESTERN A JOINT VEN | N/A | N/A | N/A | N/A | 2009-09-16 | 389463750 | 430319761 | 437468272 | 40856010.73 | 0 | 439424048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437468272 | 439424048 | 1955776 | 412328910 | ARRA:B2:B5:P:B2 | AMERICAN RECOVERY AND REINVEST:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:PUBLIC PRIVATE PARTNERSHIP:ACC - A+B (COST+TIME BIDDING)
7 | T7236 | 25589325201 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2011-09-28 | 7147510 | 7510715 | 7761739 | 363204.75 | -452520 | 7308427 | -452520 | 0 | 0 | 0 | 0 | 0 | -452520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -452520 | 7309219 | 7308427 | -793 | 8423805
7 | T7362 | 42907725202 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-03-25 | 5709404 | 5709404 | 5625130 | 0 | 0 | 5464793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5625130 | 5464793 | -160337 | 5660000
7 | T7366 | 43113215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-04-29 | 1795000 | 1795000 | 1754140 | 0 | 0 | 1746653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754140 | 1746653 | -7487 | 1415000 | B0 | ACC - LUMP SUM
8 | E8N60 | 41546265201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-05-20 | 10628174 | 10702005 | 10703365 | 73831.12 | -6500 | 10548835 | 0 | 0 | 0 | 0 | 0 | -6500 | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 10696865 | 10548835 | -148030 | 9781121
8 | E8P54 | 43110015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-10-20 | 1369271 | 1355607 | 1258468 | -13663.94 | 0 | 1224485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258468 | 1224485 | -33984 | 1662320
8 | E8P55 | 43561715201 | F203908361 | MIDASCO LLC | N/A | N/A | N/A | N/A | 2015-06-16 | 1736149 | 1766298 | 1678250 | 30148.52 | -26500 | 1651060 | 0 | 0 | 0 | 0 | 0 | -26500 | -26500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26500 | 1651750 | 1651060 | -690 | 1991672

## Detailed Data - PPP
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
[29 empty] | 0% | 0
| Dist 01 - Central Let Contrats SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 01 | E1K48 | 41306615201 | 2012-06-28 | QTR4 | 11/12 | 1 | 5 | 890 | 1143 | 1143 | 104.5% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 71256984.02 | 99.51% | 1 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852 | F454673542 | DE MOYA / LEWARE JV | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 |  | 2015-12-08 | QTR2 | 15/16 | 106 | 80270500 | B8:DBF:P3 | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP
[29 empty] | 0% | 0
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 1 | 1 | 5 | 890 | 1143 | 1143 | 100% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 71256984.02 | 100% | 1 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852
| District 01 Totals |  |  |  |  | 1 | 1 | 5 | 890 | 1143 | 1143 | 100% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 71256984.02 | 100% | 1 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852
[29 empty] | 0% | 1
| Dist 02 Central Let Contract SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 02 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 02 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 03 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 03 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 03 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 04 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 04 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 04 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 05 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 05 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 05 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 06 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 06 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 06 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 07 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 07 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 07 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 08 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide District Let Contracts SubTotal |  |  |  |  | 1 | 1 | 5 | 890 | 1143 | 1143 | 100% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 71256984.02 | 700% | 7 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852
| Statewide Totals |  |  |  |  | 1 | 1 | 5 | 890 | 1143 | 1143 | 100% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 71256984.02 | 1300% | 13 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852

## Sheet1 (hidden)
01CO | 01 | T1417 | 41612015201 | 2011-12-07 | QTR2 | 11/12 | 4 | 6 | 450 | 591 | 790 | -199 | 199 | 0 | 111 | 30 | 12691971 | 121466 | 12570505 | 13256420 | 13055581 | -656700 | 0 | -656700 | 12398881 | 12393005 | -5876 | 564450 | 64 | 10 | 0 | 108668 | 21405 | 20 | 10 | 504186 | 27781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 38852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 653741 | 49186 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2014-06-13 | QTR4 | 13/14 | 115 | 11408241.94 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO | 14 | 01co | 1 | 14
01CO | 01 | T1560 | 42910115201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 250 | 268 | 268 | 0 | 0 | 0 | 18 | 0 | 4883160 | 57482 | 4825678 | 4883160 | 4742567 | 0 | 0 | 0 | 4742567 | 4581604 | -160964 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 118 | 5451824.59 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO | 4 | 01do | 15 | 18
01CO | 01 | T1583 | 42910715201 | 2014-05-21 | QTR4 | 13/14 | 2 | 12 | 365 | 542 | 598 | -56 | 56 | 0 | 106 | 71 | 12221582 | 124617 | 12096965 | 12321397 | 12316064 | -258944 | 0 | -258944 | 12057120 | 11369478 | -687643 | 99815 | 77 | 0 | 55 | 73297 | 0 | 0 | 16 | 102194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 177856 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 108 | 11851721.99 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO | 9 | 02co | 19 | 27
01CO | 01 | T1601 | 42910615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 0 | 180 | 206 | 206 | 0 | 0 | 0 | 26 | 0 | 2560715 | 50000 | 2510715 | 2560715 | 2601322 | 0 | 0 | 0 | 2601322 | 2476584 | -124738 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 108 | 2539521.53 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO | 4 | 02do | 28 | 31
01CO | 01 | T1604 | 43340715201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 130 | 138 | 139 | -1 | 1 | 0 | 11 | -3 | 1272557 | 50000 | 1222557 | 1265786 | 1215247 | 0 | 0 | 0 | 1215247 | 1215247 | 0 | -6770 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -6770 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-20 | QTR4 | 15/16 | 113 | 1175938.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 1 | 0 | -3 | -6770 | 0 |  | CO | 10 | 03co | 32 | 41
01CO | 01 | T1610 | 43337615201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 140 | 157 | 173 | -16 | 16 | 0 | 17 | 0 | 766880 | 38788 | 728092 | 763925 | 702653 | -27872 | 0 | -27872 | 674781 | 674781 | 0 | -2956 | 10 | 0 | 0 | -73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2956 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-28 | QTR4 | 15/16 | 108 | 1032307.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO | 13 | 03do | 42 | 54
01CO | 01 | T1612 | 43539315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 2 | 139 | 163 | 162 | 1 | 0 | 0 | 24 | 0 | 965039 | 0 | 965039 | 965864 | 949501 | 0 | 0 | 0 | 949501 | 941761 | -7741 | 825 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-05 | QTR1 | 16/17 |  | 2016-04-14 | QTR4 | 15/16 | 113 | 968994.66 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 4 | 04co | 55 | 58
01CO | 01 | T1615 | 42950615201 | 2015-06-17 | QTR4 | 14/15 | 2 | 0 | 150 | 184 | 184 | 0 | 0 | 0 | 34 | 0 | 1470894 | 50000 | 1420894 | 1470894 | 1424904 | 0 | 0 | 0 | 1424904 | 1424904 | 0 | 0 | 30 | 0 | 0 | 3080 | 0 | 0 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4010 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-07-05 | QTR1 | 16/17 | 115 | 1441634.98 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO | 3 | 04do | 59 | 61
01CO | 01 | T1617 | 43337515201 | 2015-06-17 | QTR4 | 14/15 | 1 | 2 | 150 | 170 | 169 | 1 | 0 | 0 | 20 | 0 | 1087453 | 50000 | 1037453 | 1211375 | 1165751 | 0 | 0 | 0 | 1165751 | 1165751 | 0 | 123922 | 11 | 0 | 0 | 135887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128298 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 108 | 1092794.1 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 7 | 05co | 62 | 68
01CO | 01 | T1618 | 43340815201 | 2015-06-17 | QTR4 | 14/15 | 2 | 2 | 150 | 185 | 185 | 0 | 0 | 0 | 28 | 7 | 1135821 | 50000 | 1085821 | 1138128 | 1108067 | 0 | 0 | 0 | 1108067 | 1103946 | -4121 | 2307 | 17 | 0 | 4 | 3712 | 0 | 0 | 3 | 18533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 22246 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 108 | 1209049.68 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 7 | 11 | 0 | 0 | 0 | 0 | T | CO | 3 | 05do | 69 | 71
01CO | 01 | T1629 | 43325615201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 85 | 88 | 74 | 14 | 0 | 0 | 3 | 0 | 910000 | 47212 | 862788 | 910000 | 883227 | 0 | 0 | 0 | 883227 | 883227 | 0 | 0 | 3 | 0 | 0 | 13198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13198 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-28 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 115 | 857875.38 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO | 5 | 06co | 72 | 76
01CO | 01 | T1651 | 43134115201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 90 | 91 | 78 | 13 | 0 | 0 | 1 | 0 | 194630 | 9734 | 184896 | 194630 | 184896 | 0 | 0 | 0 | 184896 | 184896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-06-06 | QTR4 | 15/16 | 118 | 236550.37 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 0 | 06do | 77 | 76
01CO | 01 | T1A02 | 42518315201 | 2014-12-03 | QTR2 | 14/15 | 1 | 4 | 250 | 403 | 402 | 1 | 0 | 0 | 75 | 78 | 5396928 | 50000 | 5346928 | 5491707 | 5952983 | 0 | 0 | 0 | 5952983 | 5952455 | -528 | 94779 | 57 | 0 | 75 | 18567 | 0 | 0 | 3 | 122779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 141346 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-05-19 | QTR4 | 15/16 | 115 | 4358786.71 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 4 | 07co | 77 | 80
01CO | 01 | T1A15 | 43325515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 70 | 97 | 97 | 0 | 0 | 0 | 27 | 0 | 219504 | 10504 | 209000 | 219504 | 213917 | 0 | 0 | 0 | 213917 | 213917 | 0 | 0 | 15 | 0 | 0 | 4917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4917 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-02-20 | QTR3 | 15/16 | 106 | 200589.29 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO | 10 | 07do | 81 | 90
01DO | 01 | E1N74 | 42912015201 | 2014-12-18 | QTR2 | 14/15 | 1 | 0 | 185 | 212 | 212 | 0 | 0 | 0 | 27 | 0 | 3107573 | 50000 | 3057573 | 3107573 | 3110593 | 0 | 0 | 0 | 3110593 | 2961957 | -148636 | 0 | 9 | 0 | 0 | 7628 | 0 | 0 | 0 | 8425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16053 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-01-21 | QTR3 | 15/16 | 113 | 3280021.43 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 91 | 90
01DO | 01 | E1N87 | 43120915201 | 2015-02-19 | QTR3 | 14/15 | 1 | 0 | 300 | 336 | 336 | 0 | 0 | 0 | 36 | 0 | 3172000 | 50000 | 3122000 | 3172000 | 3272265 | 0 | 0 | 0 | 3272265 | 3269380 | -2886 | 0 | 24 | 0 | 0 | 7188 | 0 | 0 | 0 | 21276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40644 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-25 | QTR4 | 15/16 | 108 | 3312411.11 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO | 3 | 08do | 91 | 93
01DO | 01 | E1O02 | 43161515201 | 2015-01-15 | QTR3 | 14/15 | 1 | 2 | 290 | 354 | 354 | 0 | 0 | 0 | 34 | 30 | 5445703 | 56538 | 5389165 | 6533716 | 6114803 | 0 | 0 | 0 | 6114803 | 5883385 | -231419 | 1088013 | 19 | 0 | 20 | 396717 | 0 | 0 | 10 | 691296 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1088013 | 691296 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 113 | 4971481.53 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O75 | 43503815201 | 2016-01-21 | QTR3 | 15/16 | 1 | 0 | 60 | 62 | 54 | 8 | 0 | 0 | 2 | 0 | 149955 | 6815 | 143140 | 149955 | 147793 | 0 | 0 | 0 | 147793 | 147793 | 0 | 0 | 1 | 0 | 0 | 6813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6813 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-06-21 | QTR4 | 15/16 | 118 | 157973.52 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2506 | 43040415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 45 | 48 | 103 | -55 | 55 | 0 | 3 | 0 | 136157 | 7800 | 128357 | 136157 | 128357 | -47602 | 0 | -47602 | 80754 | 80754 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-09-14 | QTR1 | 16/17 |  | 2014-05-14 | QTR4 | 13/14 | 208 | 153002.52 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO |  | 0
02CO | 02 | T2533 | 43355415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 3 | 400 | 535 | 535 | 0 | 0 | 0 | 117 | 18 | 8533240 | 72079 | 8461162 | 8598881 | 9356445 | 0 | 0 | 0 | 9356445 | 9207548 | -148897 | 65641 | 58 | 0 | 0 | 229 | 0 | 0 | 18 | 64256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 46705 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 208 | 7794225.55 |  |  | 0 | 59 | 0 | 0 | -19692 | 0 |  | CO
02CO | 02 | T2567 | 43224715201 | 2015-02-25 | QTR3 | 14/15 | 1 | 8 | 135 | 252 | 252 | 0 | 0 | 0 | 79 | 38 | 1013111 | 0 | 1013111 | 1368388 | 1368010 | 0 | 0 | 0 | 1368010 | 1368010 | 0 | 355277 | 46 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-02-01 | QTR3 | 15/16 | 214 | 1004174.39 | B0 | ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2572 | 43061415201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 150 | 191 | 191 | 0 | 0 | 0 | 41 | 0 | 1990811 | 0 | 1990811 | 2002450 | 2059822 | 0 | 0 | 0 | 2059822 | 2059822 | 0 | 11638 | 21 | 0 | 0 | 11638 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 11638 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-07-21 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 214 | 1508389.63 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2587 | 43265515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 120 | 151 | 151 | 0 | 0 | 0 | 31 | 0 | 718800 | 0 | 718800 | 718800 | 718800 | 0 | 0 | 0 | 718800 | 718800 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453689782 | SOUTHERN STATES PAVEMENT MARKINGS INC. | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2016-06-02 | QTR4 | 15/16 | 209 | 769166.88 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2594 | 43265415201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 152 | 152 | 0 | 0 | 0 | 32 | 0 | 475000 | 0 | 475000 | 475000 | 475000 | 0 | 0 | 0 | 475000 | 475000 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-09-30 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 209 | 428505.77 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2603 | 43075915201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 95 | 95 | 0 | 0 | 0 | 6 | 14 | 521218 | 23780 | 497438 | 521218 | 506672 | 0 | 0 | 0 | 506672 | 506672 | 0 | 0 | 3 | 0 | 10 | 1681 | 0 | 0 | 0 | 7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 9235 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-07-01 | QTR1 | 16/17 | 214 | 510081.72 |  |  | 14 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2608 | 43055825201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 84 | 80 | 4 | 0 | 0 | 9 | 0 | 148375 | 8369 | 140006 | 148375 | 138616 | 0 | 0 | 0 | 138616 | 138616 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 209 | 178082.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9006 | 43675915201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 282 | 308 | 281 | 27 | 0 | 0 | 26 | 0 | 5341287 | 51500 | 5289787 | 5341287 | 5975297 | 0 | 0 | 0 | 5975297 | 5919052 | -56245 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 27028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27028 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-06-15 | QTR4 | 15/16 | 209 | 5370611 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2R04 | 21066125201 | 2012-12-12 | QTR2 | 12/13 | 2 | 1 | 90 | 192 | 224 | -32 | 32 | 0 | 32 | 70 | 1430432 | 50000 | 1380432 | 1430840 | 1393606 | -49024 | 0 | -49024 | 1344582 | 1344578 | -4 | 408 | 14 | 3 | 0 | 4074 | 0 | 0 | 70 | 21643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 70 | 25716 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 | 07/17/2014 | 2014-03-07 | QTR3 | 13/14 | 208 | 1293927.32 |  |  | 70 | 15 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R17 | 21237935201 | 2013-06-20 | QTR4 | 12/13 | 5 | 1 | 790 | 846 | 846 | 0 | 0 | 0 | 56 | 0 | 11440230 | 150000 | 11290230 | 11429587 | 11316805 | 0 | 0 | 0 | 11316805 | 11261013 | -55793 | -10643 | 7 | 0 | 0 | -621 | 0 | 0 | 0 | 42964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32321 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2015-12-07 | QTR2 | 15/16 | 208 | 13890662.92 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR | 0 | 49 | 0 | 0 | -11541 | 0 |  | DO
02DO | 02 | E2T70 | 43219415201 | 2015-07-15 | QTR1 | 15/16 | 1 | 0 | 190 | 217 | 214 | 3 | 0 | 0 | 23 | 4 | 741630 | 36943 | 704687 | 741630 | 709180 | 0 | 0 | 0 | 709180 | 709010 | -170 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 214 | 775810 |  |  | 4 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T74 | 42342715201 | 2015-09-16 | QTR1 | 15/16 | 1 | 0 | 135 | 163 | 162 | 1 | 0 | 0 | 28 | 0 | 4336630 | 50000 | 4286630 | 4336630 | 4421132 | 0 | 0 | 0 | 4421132 | 4255700 | -165433 | 0 | 27 | 0 | 0 | 17388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17388 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-28 | QTR1 | 16/17 |  | 2016-06-13 | QTR4 | 15/16 | 209 | 4754490.59 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3349 | 22041285201 | 2010-12-08 | QTR2 | 10/11 | 3 | 28 | 835 | 1802 | 1804 | -2 | 2 | 0 | 381 | 586 | 7357219 | 72479 | 7284740 | 10528722 | 10638848 | -93018 | 0 | -93018 | 10545830 | 10537771 | -8059 | 3171503 | 203 | 0 | 428 | 2195488 | 844067 | 0 | 120 | 436311 | 60348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 81300 | 13615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 365823 | 185379 | 97 | 0 | 126858 | 126858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 586 | 3205779 | 1230267 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-03-11 | QTR3 | 15/16 | 308 | 7320354.71 | ARRA | AMERICAN RECOVERY AND REINVEST | 49 | 81 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3375 | 42124315201 | 2012-02-29 | QTR3 | 11/12 | 3 | 3 | 1194 | 1402 | 1400 | 2 | 0 | 0 | 170 | 38 | 14736078 | 150000 | 14586078 | 15035632 | 14669101 | 0 | 0 | 0 | 14669101 | 14620764 | -48338 | 299554 | 105 | 0 | 38 | 320021 | 0 | 0 | 0 | 102024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59292 | 0 | 0 | 0 | 7231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 371313 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-30 | QTR4 | 15/16 | 308 | 18080147.32 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3418 | 42551915201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 350 | 475 | 472 | 3 | 0 | 0 | 125 | 0 | 2589441 | 50000 | 2539441 | 2672648 | 2648983 | 0 | 0 | 0 | 2648983 | 2635144 | -13838 | 83207 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-07-06 | QTR1 | 16/17 | 308 | 2582602.98 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3427 | 42164415201 | 2013-07-31 | QTR1 | 13/14 | 4 | 2 | 475 | 888 | 888 | 0 | 0 | 0 | 369 | 44 | 11476305 | 126776 | 11349528 | 11609159 | 11286785 | -11250 | 0 | -11250 | 11275535 | 10699458 | -576077 | 132854 | 265 | 0 | 19 | 140137 | 0 | 0 | 15 | 65665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 12852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 44 | 228449 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 308 | 12800389.92 |  |  | 42 | 91 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3443 | 42693415201 | 2014-12-03 | QTR2 | 14/15 | 2 | 1 | 247 | 408 | 408 | 0 | 0 | 0 | 143 | 18 | 4037987 | 50000 | 3987987 | 4183812 | 4167957 | 0 | 0 | 0 | 4167957 | 3846478 | -321479 | 145825 | 106 | 13 | 17 | 28230 | 0 | 3 | 1 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18 | 175160 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 308 | 4397278.78 |  |  | 18 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3482 | 42884515201 | 2015-01-28 | QTR3 | 14/15 | 2 | 1 | 300 | 396 | 388 | 8 | 0 | 0 | 96 | 0 | 7416925 | 85537 | 7331389 | 7437265 | 7758460 | -880 | 0 | -880 | 7757580 | 7441692 | -315888 | 20339 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 27217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30580 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 313 | 8733987.91 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3495 | 42695615201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 90 | 226 | 225 | 1 | 0 | 0 | 136 | 0 | 1619321 | 50000 | 1569321 | 1619321 | 1588249 | 0 | 0 | 0 | 1588249 | 1566711 | -21538 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-05-18 | QTR4 | 15/16 | 321 | 1991519.93 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3515 | 43090835201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 240 | 568 | 567 | 1 | 0 | 0 | 314 | 14 | 8076272 | 85662 | 7990610 | 8066272 | 8349102 | 0 | 0 | 0 | 8349102 | 7667982 | -681120 | -10000 | 119 | 1 | 14 | 68182 | 0 | 0 | 0 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 14 | 58182 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 313 | 8827284.67 |  |  | 14 | 54 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3589 | 43174315201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 120 | 126 | 77 | 49 | 0 | 0 | 6 | 0 | 169047 | 0 | 169047 | 169047 | 169047 | 0 | 0 | 0 | 169047 | 169047 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 321 | 199840.42 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9009 | 43035625201 | 2015-06-24 | QTR4 | 14/15 | 1 | 0 | 240 | 330 | 299 | 31 | 0 | 0 | 90 | 0 | 1500230 | 50000 | 1450230 | 1500230 | 1507255 | 0 | 0 | 0 | 1507255 | 1507255 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 14 | 0 | 29504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 49973 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 314 | 1868902.5 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3K73 | 42693515201 | 2014-03-13 | QTR3 | 13/14 | 2 | 1 | 200 | 344 | 344 | 0 | 0 | 0 | 125 | 19 | 1221881 | 50000 | 1171881 | 1231781 | 1143560 | 0 | 0 | 0 | 1143560 | 1120620 | -22940 | 9900 | 106 | 0 | 0 | 0 | 0 | 0 | 19 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 10560 | 6600 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2015-06-14 | QTR4 | 14/15 | 308 | 1514949.05 |  |  | 19 | 19 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L90 | 42840315201 | 2013-06-28 | QTR4 | 12/13 | 1 | 3 | 534 | 975 | 975 | 0 | 0 | 0 | 304 | 137 | 24049000 | 150000 | 23899000 | 24338104 | 24337828 | 0 | 0 | 0 | 24337828 | 24337642 | -186 | 289104 | 165 | 0 | 0 | 10000 | 0 | 20 | 0 | 59678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 363800 | 298854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 137 | 438828 | 298854 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2016-08-30 | QTR1 | 16/17 |  | 2016-04-26 | QTR4 | 15/16 | 313 | 21314871.51 | A3 | ICC - DESIGN/BUILD - MINOR | 21 | 64 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M17 | 40747845201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 90 | 109 | 107 | 2 | 0 | 0 | 19 | 0 | 149498 | 7779 | 141719 | 149498 | 139613 | 0 | 0 | 0 | 139613 | 139613 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455085205 | PRINCIPLE PROPERTIES INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-06-08 | QTR4 | 15/16 | 308 | 163264.04 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M55 | 42805825201 | 2014-01-31 | QTR3 | 13/14 | 1 | 1 | 265 | 629 | 628 | 1 | 0 | 0 | 211 | 153 | 1540571 | 50000 | 1490571 | 1579254 | 1571464 | 0 | 0 | 0 | 1571464 | 1571464 | 0 | 38683 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-01-19 | QTR3 | 15/16 | 308 | 1529160 | A3 | ICC - DESIGN/BUILD - MINOR | 65 | 20 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M95 | 41694315201 | 2015-07-09 | QTR1 | 15/16 | 1 | 3 | 140 | 240 | 239 | 1 | 0 | 0 | 73 | 27 | 2738862 | 50000 | 2688862 | 3014082 | 3595051 | 0 | 0 | 0 | 3595051 | 3484491 | -110560 | 275220 | 36 | 0 | 0 | 0 | 0 | 0 | 5 | 288220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 12155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 287375 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-19 | QTR1 | 16/17 |  | 2016-06-27 | QTR4 | 15/16 | 314 | 3204695.35 |  |  | 22 | 37 | 0 | 0 | -13000 | 0 |  | DO
03DO | 03 | E3N17 | 43392715201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 65 | 65 | 50 | 15 | 0 | 0 | 2 | -2 | 1734968 | 50000 | 1684968 | 1417537 | 1360898 | 0 | 0 | 0 | 1360898 | 1360898 | 0 | -317430 | 2 | 0 | -2 | -313024 | 0 | 0 | 0 | 4578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | -308196 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-05-23 | QTR4 | 15/16 | 321 | 1346663.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N18 | 43391815201 | 2015-10-08 | QTR2 | 15/16 | 1 | 1 | 65 | 117 | 116 | 1 | 0 | 0 | 31 | 21 | 1245237 | 49942 | 1195296 | 1323870 | 1408799 | 0 | 0 | 0 | 1408799 | 1408799 | 0 | 78633 | 30 | 0 | 21 | 108680 | 16182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 108680 | 16182 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-01 | QTR4 | 15/16 | 308 | 1048525.47 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N39 | 43078815201 | 2015-05-14 | QTR4 | 14/15 | 2 | 2 | 185 | 318 | 294 | 24 | 0 | 0 | 133 | 0 | 3111936 | 50000 | 3061936 | 3033818 | 2963684 | -11504 | 0 | -11504 | 2952180 | 2882199 | -69981 | -78118 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 18424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | -78118 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-20 | QTR4 | 15/16 | 314 | 3291622.83 |  |  | 0 | 41 | 0 | 0 | -96542 | 0 |  | DO
03DO | 03 | E3N74 | 42696915201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 125 | 164 | 164 | 0 | 0 | 0 | 39 | 0 | 2813937 | 50000 | 2763937 | 2813937 | 2913809 | 0 | 0 | 0 | 2913809 | 2837766 | -76042 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 308 | 3196208.79 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N80 | 42577825201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 60 | 79 | 87 | -8 | 8 | 0 | 19 | 0 | 246955 | 8741 | 238214 | 246955 | 248745 | -7664 | 0 | -7664 | 241081 | 241081 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | F208328161 | AN-KAR CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 308 | 183110.5 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O47 | 43253815201 | 2015-10-15 | QTR2 | 15/16 | 1 | 0 | 100 | 128 | 128 | 0 | 0 | 0 | 28 | 0 | 2030029 | 50000 | 1980029 | 2030029 | 2131829 | 0 | 0 | 0 | 2131829 | 2045055 | -86775 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-12 | QTR1 | 16/17 | 321 | 2649534.01 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O62 | 43079215201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 90 | 131 | 129 | 2 | 0 | 0 | 24 | 17 | 1298500 | 50000 | 1248500 | 1382401 | 1347119 | 0 | 0 | 0 | 1347119 | 1319720 | -27399 | 83901 | 17 | 0 | 17 | 83901 | 15601 | 0 | 0 | 3826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 87727 | 15601 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-08 | QTR1 | 16/17 |  | 2016-07-11 | QTR1 | 16/17 | 321 | 1564334.7 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P32 | 42460825201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 40 | 51 | 48 | 3 | 0 | 0 | 11 | 0 | 69197 | 6233 | 62964 | 69197 | 67195 | 0 | 0 | 0 | 67195 | 67195 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-01 | QTR1 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 321 | 143399.73 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4341 | 23073015201 | 2013-02-06 | QTR3 | 12/13 | 2 | 8 | 674 | 896 | 896 | 0 | 0 | 0 | 191 | 31 | 6592014 | 73358 | 6518656 | 6833204 | 6617553 | 0 | 0 | 0 | 6617553 | 6330385 | -287168 | 241190 | 105 | 0 | 31 | 138206 | 0 | 4 | 0 | 108342 | 50933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 43 | 31 | 314541 | 50933 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2016-07-06 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 412 | 7354583.81 |  |  | 14 | 43 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4389 | 23097825201 | 2014-04-30 | QTR4 | 13/14 | 1 | 2 | 750 | 801 | 631 | 170 | 0 | 0 | 51 | 0 | 15715809 | 150000 | 15565809 | 15753499 | 15520925 | 0 | 630700 | 630700 | 16151625 | 14963445 | -1188180 | 37690 | 29 | 0 | 0 | 48793 | 0 | 0 | 0 | 38749 | 2893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66399 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158063 | 2893 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2016-09-12 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 408 | 15839218.13 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4402 | 42973715201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 540 | 577 | 542 | 35 | 0 | 0 | 37 | 0 | 2824000 | 50000 | 2774000 | 2824000 | 2773850 | 0 | 0 | 0 | 2773850 | 2779467 | 5617 | 0 | 15 | 0 | 0 | 8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8687 | 0 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 408 | 3519184.32 | B0 | ACC - LUMP SUM | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4416 | 43171715201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 238 | 268 | 261 | 7 | 0 | 0 | 30 | 0 | 1444863 | 50000 | 1394863 | 1444863 | 1398240 | 0 | 0 | 0 | 1398240 | 1398240 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 412 | 1613353.82 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4P98 | 42605315201 | 2015-02-06 | QTR3 | 14/15 | 2 | 2 | 238 | 283 | 280 | 3 | 0 | 0 | 45 | 0 | 1670723 | 50000 | 1620723 | 1694884 | 1701995 | 0 | 0 | 0 | 1701995 | 1694894 | -7101 | 24162 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 9687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43444 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-02-26 | QTR3 | 15/16 | 409 | 1844040.91 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q70 | 43056615201 | 2015-04-03 | QTR4 | 14/15 | 1 | 0 | 86 | 99 | 99 | 0 | 0 | 0 | 13 | 0 | 594927 | 36890 | 558037 | 594927 | 563713 | 0 | 0 | 0 | 563713 | 563713 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-07-08 | QTR1 | 16/17 | 412 | 789528.37 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R65 | 43538615201 | 2016-01-08 | QTR3 | 15/16 | 2 | 0 | 65 | 92 | 91 | 1 | 0 | 0 | 23 | 4 | 593859 | 24145 | 569714 | 593859 | 535917 | 0 | 0 | 0 | 535917 | 535917 | 0 | 0 | 18 | 0 | 4 | 8796 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9546 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 409 | 495318.22 |  |  | 4 | 4 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5496 | 43106615201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 460 | 684 | 678 | 6 | 0 | 0 | 224 | 0 | 4198661 | 57000 | 4141661 | 4198661 | 4290920 | 0 | 0 | 0 | 4290920 | 4280333 | -10587 | 0 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 514 | 5833243.5 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5497 | 43113915201 | 2014-06-18 | QTR4 | 13/14 | 4 | 2 | 350 | 479 | 448 | 31 | 0 | 0 | 99 | 30 | 5577400 | 50000 | 5527400 | 5630674 | 5316503 | 0 | 0 | 0 | 5316503 | 5110931 | -205572 | 53274 | 72 | 0 | 0 | 16219 | 0 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 62720 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-13 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 514 | 5261131.52 | B0:B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5507 | 42908315201 | 2014-10-29 | QTR2 | 14/15 | 2 | 3 | 352 | 458 | 457 | 1 | 0 | 0 | 85 | 21 | 13950000 | 132000 | 13818000 | 14304220 | 14416417 | 0 | 0 | 0 | 14416417 | 13245104 | -1171314 | 354220 | 70 | 0 | 0 | 36422 | 0 | 0 | 0 | 46490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 308750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 391661 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 512 | 13411584.34 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5515 | 43066815201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 210 | 284 | 284 | 0 | 0 | 0 | 44 | 30 | 1884019 | 50000 | 1834019 | 1929335 | 1919435 | 0 | 0 | 0 | 1919435 | 1870656 | -48780 | 45316 | 30 | 0 | 24 | 59005 | 0 | 0 | 6 | 21372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 80377 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2016-05-05 | QTR4 | 15/16 | 514 | 1716624.23 | B0 | ACC - LUMP SUM | 6 | 12 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5528 | 43066915201 | 2015-05-27 | QTR4 | 14/15 | 1 | 1 | 200 | 245 | 224 | 21 | 0 | 0 | 45 | 0 | 2181000 | 50000 | 2131000 | 2446253 | 2396253 | 0 | 0 | 0 | 2396253 | 2380075 | -16178 | 265253 | 19 | 0 | 0 | 145670 | 0 | 0 | 0 | 119583 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265253 | 508 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-07-01 | QTR1 | 16/17 |  | 2016-04-06 | QTR4 | 15/16 | 507 | 1883279.22 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5536 | 43067715201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 216 | 247 | 233 | 14 | 0 | 0 | 31 | 0 | 2584884 | 50000 | 2534884 | 2614884 | 2636650 | 0 | 0 | 0 | 2636650 | 2540033 | -96617 | 30000 | 12 | 0 | 0 | 15490 | 0 | 0 | 0 | 58864 | 13921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74355 | 13921 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-07-22 | QTR1 | 16/17 | 513 | 2795913.94 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5537 | 43244215201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 110 | 154 | 147 | 7 | 0 | 0 | 24 | 20 | 1272760 | 42000 | 1230760 | 1272760 | 1267646 | 0 | 0 | 0 | 1267646 | 1267646 | 0 | 0 | 9 | 0 | 0 | 615 | 0 | 0 | 20 | 34326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 34941 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-06-10 | QTR4 | 15/16 | 513 | 919590 | B0 | ACC - LUMP SUM | 20 | 15 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W67 | 43198915201 | 2014-10-07 | QTR2 | 14/15 | 1 | 2 | 300 | 340 | 393 | -53 | 53 | 0 | 13 | 27 | 2340785 | 50000 | 2290785 | 2247902 | 2197902 | -92326 | 0 | -92326 | 2105576 | 2104471 | -1105 | -92883 | 6 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | -92883 | 0 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-02-10 | QTR3 | 15/16 | 509 | 2486510 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W83 | 43528215201 | 2015-04-07 | QTR4 | 14/15 | 1 | 0 | 240 | 265 | 264 | 1 | 0 | 0 | 25 | 0 | 2750721 | 50000 | 2700721 | 2750721 | 2676098 | 0 | 0 | 0 | 2676098 | 2676025 | -73 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-07-20 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 513 | 2985731 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y02 | 43705815201 | 2015-09-01 | QTR1 | 15/16 | 1 | 0 | 130 | 134 | 107 | 27 | 0 | 0 | 4 | 0 | 783941 | 39000 | 744941 | 783941 | 744941 | 0 | 0 | 0 | 744941 | 744941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-08-09 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 515 | 821518.11 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6320 | 42914015201 | 2014-06-18 | QTR4 | 13/14 | 3 | 3 | 450 | 503 | 387 | 116 | 0 | 0 | 53 | 0 | 14295524 | 150000 | 14145524 | 14692214 | 13690377 | 0 | 245000 | 245000 | 13935377 | 13056864 | -878513 | 396690 | 43 | 0 | 0 | 18351 | 0 | 0 | 0 | 421570 | 152744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447735 | 152744 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 606 | 15289319.55 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6325 | 25055425201 | 2012-10-31 | QTR2 | 12/13 | 1 | 3 | 700 | 903 | 870 | 33 | 0 | 0 | 197 | 6 | 11430054 | 123500 | 11306554 | 11749528 | 11929942 | 0 | 0 | 0 | 11929942 | 11924070 | -5871 | 319473 | 154 | 2 | 0 | 266319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 63468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 370763 | 0 | F410827177 | JOHNSON BROS. CORPORATION | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 606 | 12087502 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6373 | 43080915201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 230 | 328 | 326 | 2 | 0 | 0 | 98 | 0 | 2376742 | 50130 | 2326612 | 2426742 | 2460615 | 0 | 0 | 0 | 2460615 | 2384892 | -75723 | 50000 | 56 | 31 | 0 | 16266 | 0 | 0 | 0 | 14872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 71617 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-12 | QTR4 | 15/16 | 606 | 2292101.6 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6376 | 43081715201 | 2015-02-25 | QTR3 | 14/15 | 2 | 4 | 435 | 468 | 375 | 93 | 0 | 0 | 33 | 0 | 6621887 | 69750 | 6552137 | 6805679 | 6261293 | 0 | 470000 | 470000 | 6731293 | 6082074 | -649219 | 183793 | 21 | 0 | 0 | 71716 | 0 | 0 | 0 | 115147 | 9450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186863 | 9450 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-27 | QTR1 | 16/17 |  | 2016-05-08 | QTR4 | 15/16 | 606 | 6429680.27 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6384 | 43350815201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 137 | 137 | 0 | 0 | 0 | 17 | 0 | 439934 | 26680 | 413254 | 439934 | 417205 | 0 | 0 | 0 | 417205 | 417205 | 0 | 0 | 16 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 606 | 559680 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7209 | 25841515201 | 2009-09-16 | QTR1 | 09/10 | 7 | 55 | 1065 | 1694 | 1694 | 0 | 0 | 0 | 109 | 520 | 389463750 | 75000 | 389388750 | 430319761 | 437468272 | 0 | 0 | 0 | 437468272 | 439424048 | 1955776 | 40856011 | 52 | 22 | 67 | 10225188 | 4993195 | 1 | 121 | 13703270 | 4748092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 6407054 | 1636245 | 0 | 0 | 10009318 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 173923 | 100951 | 0 | 0 | 210466 | 210466 | 0 | 0 | 3584 | 0 | 0 | 0 | 0 | 0 | 23 | 520 | 40732802 | 11688949 | F263258515 | PCL/ARCHER WESTERN A JOINT VEN | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2014-10-19 | QTR2 | 14/15 | 714 | 412328910.33 | ARRA:B2:B5:P:B2 | AMERICAN RECOVERY AND REINVEST:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:PUBLIC PRIVATE PARTNERSHIP:ACC - A+B (COST+TIME BIDDING) | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7236 | 25589325201 | 2011-09-28 | QTR1 | 11/12 | 2 | 7 | 410 | 560 | 740 | -180 | 180 | 0 | 131 | 19 | 7147510 | 74000 | 7073510 | 7510715 | 7761739 | -452520 | 0 | -452520 | 7309219 | 7308427 | -793 | 363205 | 107 | 0 | 15 | 337971 | 0 | 0 | 4 | 38132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 372176 | 0 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2016-08-10 | QTR1 | 16/17 |  | 2014-06-13 | QTR4 | 13/14 | 717 | 8423805.36 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7362 | 42907725202 | 2015-03-25 | QTR3 | 14/15 | 2 | 0 | 180 | 256 | 256 | 0 | 0 | 0 | 76 | 0 | 5709404 | 50000 | 5659404 | 5709404 | 5625130 | 0 | 0 | 0 | 5625130 | 5464793 | -160337 | 0 | 57 | 0 | 0 | 8822 | 0 | 0 | 0 | 10150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-08-19 | QTR1 | 16/17 |  | 2016-05-16 | QTR4 | 15/16 | 717 | 5660000 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7366 | 43113215201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 150 | 211 | 210 | 1 | 0 | 0 | 61 | 0 | 1795000 | 50000 | 1745000 | 1795000 | 1754140 | 0 | 0 | 0 | 1754140 | 1746653 | -7487 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-19 | QTR1 | 16/17 |  | 2016-03-18 | QTR3 | 15/16 | 717 | 1415000 | B0 | ACC - LUMP SUM | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7I46 | 25633925201 | 2014-08-14 | QTR1 | 14/15 | 1 | 4 | 450 | 623 | 622 | 1 | 0 | 0 | 137 | 36 | 15944000 | 150000 | 15794000 | 16474127 | 16294835 | 0 | 0 | 0 | 16294835 | 15360010 | -934824 | 530127 | 97 | 0 | 0 | 56222 | 0 | 0 | 1 | 186898 | 3530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 346909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 590029 | 3530 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-15 | QTR1 | 16/17 |  | 2016-06-25 | QTR4 | 15/16 | 714 | 18310419.41 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 11 | 40 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7J99 | 42715515201 | 2015-04-08 | QTR4 | 14/15 | 1 | 1 | 199 | 302 | 274 | 28 | 0 | 0 | 103 | 0 | 1844400 | 50000 | 1794400 | 1881240 | 1852163 | 0 | 0 | 0 | 1852163 | 1792416 | -59746 | 36840 | 47 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 |  | 2016-06-28 | QTR4 | 15/16 | 798 | 1650000 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K02 | 43090115201 | 2015-02-11 | QTR3 | 14/15 | 1 | 3 | 125 | 176 | 176 | 0 | 0 | 0 | 39 | 12 | 2683100 | 50000 | 2633100 | 2806747 | 2817266 | 0 | 0 | 0 | 2817266 | 2772695 | -44571 | 123647 | 34 | 0 | 12 | 67604 | 15358 | 0 | 0 | 123204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 173025 | 15358 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-07 | QTR1 | 16/17 |  | 2015-11-30 | QTR2 | 15/16 | 709 | 2450000 | B0 | ACC - LUMP SUM | 12 | 5 | 0 | 0 | -17782 | 0 |  | DO
07DO | 07 | E7K04 | 43066015201 | 2015-03-11 | QTR3 | 14/15 | 1 | 2 | 180 | 281 | 281 | 0 | 0 | 0 | 82 | 19 | 2680382 | 50000 | 2630382 | 2750471 | 2763085 | 0 | 0 | 0 | 2763085 | 2699178 | -63907 | 70089 | 46 | 0 | 0 | 0 | 0 | 0 | 19 | 111980 | 18119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 19 | 114701 | 18119 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-03-14 | QTR3 | 15/16 | 709 | 2007403 | B0 | ACC - LUMP SUM | 19 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K05 | 43243225201 | 2015-03-11 | QTR3 | 14/15 | 1 | 0 | 220 | 262 | 261 | 1 | 0 | 0 | 42 | 0 | 1086230 | 50000 | 1036230 | 1086230 | 1062839 | 0 | 0 | 0 | 1062839 | 1062824 | -15 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2016-09-26 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 717 | 1230200 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K17 | 43094815201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 220 | 258 | 212 | 46 | 0 | 0 | 38 | 0 | 2888000 | 50000 | 2838000 | 2888000 | 2727932 | 0 | 0 | 0 | 2727932 | 2690622 | -37311 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-16 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 798 | 3200000 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K67 | 43149515201 | 2015-05-13 | QTR4 | 14/15 | 1 | 4 | 140 | 178 | 178 | 0 | 0 | 0 | 28 | 10 | 2794895 | 50000 | 2744895 | 2964710 | 2918290 | -7200 | 0 | -7200 | 2911090 | 2905726 | -5363 | 169815 | 17 | 0 | 5 | 49615 | 0 | 0 | 5 | 161418 | 7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 193888 | 7074 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 717 | 1905000 |  |  | 2 | 11 | 0 | 0 | -17145 | 0 |  | DO
07DO | 07 | E7K78 | 43080235201 | 2015-09-09 | QTR1 | 15/16 | 2 | 0 | 206 | 217 | 128 | 89 | 0 | 0 | 11 | 0 | 1271000 | 50000 | 1221000 | 1271000 | 1221000 | 0 | 0 | 0 | 1221000 | 1221000 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-05-10 | QTR4 | 15/16 | 717 | 2206022.47 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K80 | 43478115201 | 2015-08-12 | QTR1 | 15/16 | 2 | 2 | 160 | 203 | 203 | 0 | 0 | 0 | 41 | 2 | 1052289 | 33000 | 1019289 | 1092289 | 992268 | 0 | 0 | 0 | 992268 | 991427 | -840 | 40000 | 21 | 0 | 0 | 7453 | 0 | 0 | 2 | 55456 | 19923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 62908 | 19923 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 717 | 752249.19 |  |  | 2 | 20 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L07 | 43258315201 | 2015-11-12 | QTR2 | 15/16 | 1 | 0 | 80 | 89 | 89 | 0 | 0 | 0 | 5 | 4 | 1115377 | 50000 | 1065377 | 1115377 | 1056390 | 0 | 0 | 0 | 1056390 | 1056390 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 798 | 1450000 | B0 | ACC - LUMP SUM | 4 | 0 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N60 | 41546265201 | 2014-05-20 | QTR4 | 13/14 | 1 | 3 | 475 | 545 | 545 | 0 | 0 | 0 | 70 | 0 | 10628174 | 96840 | 10531334 | 10702005 | 10703365 | -6500 | 0 | -6500 | 10696865 | 10548835 | -148030 | 73831 | 23 | 0 | 0 | 8969 | 0 | 0 | 0 | 107706 | 13562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 117912 | 13562 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-04-12 | QTR4 | 15/16 | 854 | 9781121.21 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P54 | 43110015201 | 2015-10-20 | QTR2 | 15/16 | 1 | 1 | 115 | 121 | 118 | 3 | 0 | 0 | 6 | 0 | 1369271 | 50000 | 1319271 | 1355607 | 1258468 | 0 | 0 | 0 | 1258468 | 1224485 | -33984 | -13664 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-06-24 | QTR4 | 15/16 | 854 | 1662320.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P55 | 43561715201 | 2015-06-16 | QTR4 | 14/15 | 1 | 1 | 140 | 189 | 189 | 0 | 0 | 0 | 45 | 4 | 1736149 | 50000 | 1686149 | 1766298 | 1678250 | -26500 | 0 | -26500 | 1651750 | 1651060 | -690 | 30149 | 29 | 0 | 4 | 30149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 30149 | 0 | F203908361 | MIDASCO LLC | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 854 | 1991671.8 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
01DO | 01 | E1K48 | 41306615201 | 2012-06-28 | QTR4 | 11/12 | 1 | 5 | 890 | 1143 | 1143 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 0 | -71423852 | -187553 | 155 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 12 | -153550 | 12852 | F454673542 | DE MOYA / LEWARE JV | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 | 2015-12-08 | QTR2 | 15/16 | 106 | 80270500 | B8:DBF:P3 | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP | 0 | 58 | 0 | 0 | -339346 | 0 |  | DO | 0 | 01co | 1 | 0
CO | [104 empty] | CO | 1 | 01do | 1 | 1
CO | [104 empty] | CO | 0 | 02co | 2 | 1
CO | [104 empty] | CO | 0 | 02do | 2 | 1
CO | [104 empty] | CO | 0 | 03co | 2 | 1
CO | [104 empty] | CO | 0 | 03do | 2 | 1
CO | [104 empty] | CO | 0 | 04co | 2 | 1
CO | [104 empty] | CO | 0 | 04do | 2 | 1
CO | [104 empty] | CO | 0 | 05co | 2 | 1
CO | [103 empty] | T | CO | 0 | 05do | 2 | 1
CO | [104 empty] | CO | 0 | 06co | 2 | 1
CO | [104 empty] | CO | 0 | 06do | 2 | 1
CO | [104 empty] | CO | 0 | 07co | 2 | 1
CO | [104 empty] | CO | 0 | 07do | 2 | 1
CO | [104 empty] | CO | 0 | 08co | 2 | 1
CO | [104 empty] | CO | 0 | 08do | 2 | 1
CO | [104 empty] | CO
CO | [104 empty] | CO
CO | [104 empty] | CO |  | 0