## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 103505177 | 102450754 | 102361397 | 101907760 | 2200000 | 97719183 | -4.618% | 85.71% | -763250 | -0.745% | -1143780 | -1.105% | 4269 | 795 | 18.62% | 201 | 4.708% | 18 | 0.4216% | 182 | 4.263% | 4469 | 4.685% | 5502 | 5234 | 4238 | -0.7262% | 85.71%
| District Let | 13752434 | 13539081 | 14881421 | 14488884 | 0 | 14084454 | 4.028% | 100% | 1197607 | 8.846% | 1128987 | 8.209% | 995 | 60 | 6.03% | 55 | 5.528% | 0 | 0% | 36 | 3.618% | 1031 | 3.618% | 1146 | 1150 | 1035 | 4.02% | 100%
| All Contracts | 117257611 | 115989835 | 117242818 | 116396644 | 2200000 | 111803637 | -3.609% | 88.46% | 434357 | 0.3745% | -14793 | -0.01262% | 5264 | 855 | 16.24% | 256 | 4.863% | 18 | 0.3419% | 218 | 4.141% | 5500 | 4.483% | 6648 | 6384 | 5273 | 0.171% | 88.46%
2 | Central Let | 38279724 | 37888718 | 39041866 | 40122189 | 0 | 39391627 | 3.967% | 87.5% | 824421 | 2.176% | 762140 | 1.991% | 2679 | 351 | 13.1% | 171 | 6.383% | 24 | 0.8959% | 177 | 6.607% | 2880 | 7.503% | 3434 | 3454 | 2932 | 9.444% | 81.25%
| District Let | 43766946 | 43124504 | 53441794 | 54333034 | 0 | 53265020 | 23.51% | 70% | 9964259 | 23.11% | 9674848 | 22.11% | 2540 | 261 | 10.28% | 187 | 7.362% | 3 | 0.1181% | 849 | 33.43% | 3392 | 33.54% | 3848 | 3996 | 3548 | 39.69% | 60%
| All Contracts | 82046670 | 81013222 | 92483660 | 94455223 | 0 | 92656647 | 14.37% | 80.77% | 10788680 | 13.32% | 10436988 | 12.72% | 5219 | 612 | 11.73% | 358 | 6.86% | 27 | 0.5173% | 1026 | 19.66% | 6272 | 20.18% | 7282 | 7450 | 6480 | 24.16% | 73.08%
3 | Central Let | 84643965 | 83512946 | 89605053 | 89475354 | 0 | 86498744 | 3.575% | 88.89% | 5469795 | 6.55% | 4961086 | 5.861% | 5621 | 1665 | 29.62% | 629 | 11.19% | 582 | 10.35% | 1004 | 17.86% | 7207 | 28.22% | 9501 | 9420 | 7126 | 26.77% | 72.22%
| District Let | 62342380 | 61323349 | 64083222 | 64589096 | 0 | 63773751 | 3.996% | 86.36% | 2102590 | 3.429% | 1740843 | 2.792% | 3449 | 945 | 27.4% | 327 | 9.481% | 199 | 5.77% | 552 | 16% | 4200 | 21.77% | 5472 | 5323 | 4051 | 17.45% | 81.82%
| All Contracts | 146986345 | 144836295 | 153688275 | 154064450 | 0 | 150272495 | 3.753% | 87.5% | 7572385 | 5.228% | 6701929 | 4.56% | 9070 | 2610 | 28.78% | 956 | 10.54% | 781 | 8.611% | 1556 | 17.16% | 11407 | 25.77% | 14973 | 14743 | 11177 | 23.23% | 77.5%
4 | Central Let | 31008831 | 30500454 | 31297836 | 30611487 | 630700 | 29763351 | -2.417% | 100% | 569676 | 1.868% | 289005 | 0.932% | 3001 | 243 | 8.097% | 113 | 3.765% | 61 | 2.033% | 31 | 1.033% | 3093 | 3.066% | 3453 | 3225 | 2869 | -4.399% | 100%
| District Let | 29601464 | 29178240 | 31630233 | 31744124 | 791600 | 31609585 | 8.333% | 85.71% | 2265414 | 7.764% | 2028771 | 6.854% | 1747 | 222 | 12.71% | 75 | 4.293% | 45 | 2.576% | 167 | 9.559% | 1959 | 12.14% | 2272 | 2094 | 1797 | 2.862% | 100%
| All Contracts | 60610295 | 59678694 | 62928069 | 62355611 | 1422300 | 61372936 | 2.839% | 93.33% | 2835090 | 4.751% | 2317776 | 3.824% | 4748 | 465 | 9.794% | 188 | 3.96% | 106 | 2.233% | 198 | 4.17% | 5052 | 6.403% | 5725 | 5319 | 4666 | -1.727% | 100%
5 | Central Let | 76985389 | 76204389 | 80216900 | 79809973 | 0 | 77403268 | 1.573% | 91.67% | 3934829 | 5.164% | 3650457 | 4.742% | 4198 | 625 | 14.89% | 281 | 6.694% | 0 | 0% | 217 | 5.169% | 4415 | 5.169% | 5340 | 5210 | 4304 | 2.525% | 91.67%
| District Let | 8439321 | 8171321 | 8364891 | 8091285 | 0 | 7998356 | -2.117% | 100% | -61589 | -0.7537% | -74430 | -0.8819% | 1325 | 30 | 2.264% | 46 | 3.472% | 0 | 0% | 27 | 2.038% | 1352 | 2.038% | 1453 | 1455 | 1379 | 4.075% | 75%
| All Contracts | 85424710 | 84375710 | 88581791 | 87901258 | 0 | 85401624 | 1.216% | 95% | 3873240 | 4.59% | 3576027 | 4.186% | 5523 | 655 | 11.86% | 327 | 5.921% | 0 | 0% | 244 | 4.418% | 5767 | 4.418% | 6793 | 6665 | 5683 | 2.897% | 85%
6 | Central Let | 123249886 | 122250399 | 125286526 | 124165679 | 1455000 | 122087841 | -0.133% | 100% | 2518816 | 2.06% | 2036640 | 1.652% | 4270 | 626 | 14.66% | 182 | 4.262% | 74 | 1.733% | 6 | 0.1405% | 4350 | 1.874% | 5158 | 4833 | 4025 | -5.738% | 100%
| District Let | 11414599 | 11168053 | 12581141 | 12570276 | 525000 | 12323821 | 10.35% | 75% | 1241840 | 11.12% | 1166542 | 10.22% | 841 | 249 | 29.61% | 48 | 5.707% | 51 | 6.064% | 193 | 22.95% | 1085 | 29.01% | 1382 | 1381 | 1084 | 28.89% | 75%
| All Contracts | 134664485 | 133418452 | 137867667 | 136735955 | 1980000 | 134411662 | 0.7444% | 93.33% | 3760656 | 2.819% | 3203182 | 2.379% | 5111 | 875 | 17.12% | 230 | 4.5% | 125 | 2.446% | 199 | 3.894% | 5435 | 6.339% | 6540 | 6214 | 5109 | -0.03913% | 93.33%
7 | Central Let | 505803656 | 504749656 | 550416088 | 556729934 | 420000 | 556146280 | 10.18% | 92.31% | 44902548 | 8.896% | 44612432 | 8.82% | 5719 | 894 | 15.63% | 366 | 6.4% | 63 | 1.102% | 670 | 11.72% | 6452 | 12.82% | 7712 | 7794 | 6534 | 14.25% | 84.62%
| District Let | 292756531 | 291684406 | 302987492 | 302708590 | 1650000 | 299072674.09 | 2.533% | 94.44% | 10607078 | 3.636% | 10230961 | 3.495% | 4785 | 602 | 12.58% | 300 | 6.27% | 45 | 0.9404% | 112 | 2.341% | 4942 | 3.281% | 5844 | 5448 | 4546 | -4.995% | 100%
| All Contracts | 798560187 | 796434062 | 853403580 | 859438524 | 2070000 | 855218954.09 | 7.381% | 93.55% | 55509626 | 6.97% | 54843393 | 6.868% | 10504 | 1496 | 14.24% | 666 | 6.34% | 108 | 1.028% | 782 | 7.445% | 11394 | 8.473% | 13556 | 13242 | 11080 | 5.484% | 93.55%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 144626351 | 143979511 | 147106087 | 147994161 | 0 | 145636629 | 1.151% | 100% | 2732315 | 1.898% | 2479736 | 1.715% | 3260 | 278 | 8.528% | 181 | 5.552% | 97 | 2.975% | 18 | 0.5521% | 3375 | 3.528% | 3844 | 3840 | 3381 | 3.712% | 0.002321%
| All Contracts | 144626351 | 143979511 | 147106087 | 147994161 | 0 | 145636629 | 1.151% | 100% | 2732315 | 1.898% | 2479736 | 1.715% | 3260 | 278 | 8.528% | 181 | 5.552% | 97 | 2.975% | 18 | 0.5521% | 3375 | 3.528% | 3844 | 3840 | 3381 | 3.712% | 100%
Totals This Qtr | Central Let | 963476628 | 957557316 | 1018225666 | 1022822376 | 4705700 | 1009010294 | 5.373% | 90.91% | 57456835 | 6% | 55167980 | 5.726% | 29757 | 5199 | 17.47% | 1943 | 6.53% | 822 | 2.762% | 2287 | 7.686% | 32866 | 10.45% | 40100 | 39170 | 32028 | 7.632% | 85.86%
| District Let | 606700026 | 602168465 | 635076281 | 636519450 | 2966600 | 627764290.09 | 4.251% | 88.75% | 30049514 | 4.99% | 28376258 | 4.677% | 18942 | 2647 | 13.97% | 1219 | 6.435% | 440 | 2.323% | 1954 | 10.32% | 21336 | 12.64% | 25261 | 24687 | 20821 | 9.92% | 86.25%
| All Contracts | 1570176654 | 1559725781 | 1653301947 | 1659341826 | 7672300 | 1636774584.09 | 4.94% | 89.94% | 87506349 | 5.61% | 83544238 | 5.321% | 48699 | 7846 | 16.11% | 3162 | 6.493% | 1262 | 2.591% | 4241 | 8.709% | 54202 | 11.3% | 65361 | 63857 | 52849 | 8.522% | 86.03%
Totals Previous Quarter | Central Let | 608447202 | 605551466 | 656231079 | 662895010 | 1345700 | 657330468 | 8.551% | 86.54% | 48802480 | 8.059% | 47783875 | 7.853% | 15482 | 2702 | 17.45% | 1067 | 6.892% | 413 | 2.668% | 1600 | 10.33% | 17495 | 13% | 21282 | 20899 | 17130 | 10.64% | 84.62%
| District Let | 127902947 | 125800082 | 130352729 | 129482488 | 0 | 126945988 | 0.9109% | 95% | 3178698 | 2.527% | 2449784 | 1.915% | 7768 | 1156 | 14.88% | 615 | 7.917% | 241 | 3.102% | 594 | 7.647% | 8603 | 10.75% | 10389 | 10221 | 8450 | 8.78% | 87.5%
| All Contracts | 736350149 | 731351548 | 786583808 | 792377498 | 1345700 | 784276456 | 7.237% | 90.22% | 51981178 | 7.108% | 50233659 | 6.822% | 23250 | 3858 | 16.59% | 1682 | 7.234% | 654 | 2.813% | 2194 | 9.437% | 26098 | 12.25% | 31671 | 31120 | 25580 | 10.02% | 85.87%
Totals Fiscal Year 2015/2016 | Central Let | 939392055 | 928183064 | 968008671 | 980536241 | 5086000 | 963305142 | 3.784% | 91.71% | 32914329 | 3.546% | 28616617 | 3.046% | 52868 | 8893 | 16.82% | 3474 | 6.571% | 961 | 1.818% | 3777 | 7.144% | 57606 | 8.962% | 70058 | 70737 | 58370 | 10.41% | 83.9%
| District Let | 984092963 | 976092333 | 1036587854 | 1030584161 | 5781667 | 998653518 | 2.311% | 92.36% | 57365087 | 5.877% | 55188579 | 5.608% | 37490 | 4617 | 12.32% | 2121 | 5.658% | 1331 | 3.55% | 3490 | 9.309% | 42311 | 12.86% | 48945 | 49037 | 42299 | 12.83% | 87.9%
| All Contracts | 1923485018 | 1904275397 | 2004596525 | 2011120402 | 10867667 | 1961958660 | 3.029% | 91.99% | 90279416 | 4.741% | 83805196 | 4.357% | 90358 | 13510 | 14.95% | 5595 | 6.192% | 2292 | 2.537% | 7267 | 8.042% | 99917 | 10.58% | 119003 | 119774 | 100669 | 11.41% | 85.64%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1552 | 40631475201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 164 | 200 | 128% | 0 | -36 | 36 | 0 | 10 | 4 | 2579468 | 50000 | 2529468 | 2579468 | 2493565 | -85464 | 0 | -85464 | 2408101 | 2408101 | 95.2% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2016-12-14 | QTR2 | 16/17 |  | 2014-09-12 | QTR1 | 14/15 | 115 | 3076291.38
| 01 | T1560 | 42910115201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 250 | 268 | 268 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 4883160 | 57482 | 4825678 | 4883160 | 4742567 | 0 | 0 | 0 | 4742567 | 4581604 | 94.94% | 1 | -160964 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 118 | 5451824.59
| 01 | T1583 | 42910715201 | 2014-05-21 | QTR4 | 13/14 | 2 | 12 | 365 | 542 | 598 | 134.8% | 0 | -56 | 56 | 0 | 106 | 71 | 12221582 | 124617 | 12096965 | 12321397 | 12316064 | -258944 | 0 | -258944 | 12057120 | 11369478 | 93.99% | 1 | -687643 | 99815 | 77 | 29 | 0 | 55 | 73297 | 0 | 0 | 16 | 102194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 177856 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 108 | 11851721.99
| 01 | T1587 | 42913115201 | 2014-03-26 | QTR3 | 13/14 | 2 | 7 | 185 | 230 | 226 | 102.7% | 1 | 4 | 0 | 0 | 36 | 9 | 4576900 | 50000 | 4526900 | 4273384 | 4255627 | 0 | 0 | 0 | 4255627 | 4165417 | 92.01% | 1 | -90210 | -303516 | 25 | 11 | 0 | 6 | 199569 | 39215 | 0 | 3 | -504411 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | -277723 | 58709 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-01 | QTR2 | 16/17 |  | 2015-04-29 | QTR4 | 14/15 | 115 | 5166652.25 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1588 | 41304225201 | 2014-06-18 | QTR4 | 13/14 | 2 | 7 | 680 | 710 | 591 | 85.59% | 1 | 119 | 0 | 0 | 46 | -16 | 24169365 | 150000 | 24019365 | 23023182 | 22613781 | 0 | 900000 | 900000 | 23513781 | 20785082 | 86.53% | 1 | -2728699 | -1146183 | 1 | 8 | 0 | -16 | -1426521 | 0 | 0 | 0 | 288694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | -1137827 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 |  | 2016-08-25 | QTR1 | 16/17 | 106 | 29188895.88 | B2:B5:B2 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING)
| 01 | T1595 | 40631345201 | 2015-03-25 | QTR3 | 14/15 | 1 | 6 | 525 | 556 | 395 | 66.29% | 1 | 161 | 0 | 0 | 47 | -16 | 31929262 | 150000 | 31779262 | 31614976 | 31607283 | 0 | 1300000 | 1300000 | 32907283 | 30894410 | 97.22% | 1 | -2012872 | -314286 | 36 | 11 | 0 | -16 | 17006 | 0 | 0 | 0 | 270841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -491717 | 0 | 0 | -16 | -196174 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-10-25 | QTR2 | 16/17 |  | 2016-07-13 | QTR1 | 16/17 | 106 | 30769490.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 01 | T1596 | 43142215201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 250 | 349 | 348 | 109.6% | 1 | 1 | 0 | 0 | 74 | 25 | 5571174 | 56174 | 5515000 | 5623674 | 5636689 | 0 | 0 | 0 | 5636689 | 5437906 | 98.6% | 1 | -198783 | 52500 | 61 | 13 | 0 | 25 | 48439 | 0 | 0 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 100939 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-11-21 | QTR2 | 16/17 |  | 2016-05-28 | QTR4 | 15/16 | 113 | 5411862.18 | B0 | ACC - LUMP SUM
| 01 | T1597 | 43356115201 | 2015-02-25 | QTR3 | 14/15 | 1 | 2 | 115 | 551 | 519 | 92.17% | 1 | 32 | 0 | 0 | 413 | 23 | 737000 | 0 | 737000 | 989001 | 989001 | 0 | 0 | 0 | 989001 | 989001 | 134.2% | 0 | 0 | 252001 | 394 | 19 | 0 | 1 | 3000 | 0 | 0 | 22 | 249001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 252001 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-11-28 | QTR2 | 16/17 |  | 2016-10-25 | QTR2 | 16/17 | 108 | 596982.85 | B0 | ACC - LUMP SUM
| 01 | T1601 | 42910615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 0 | 180 | 206 | 206 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 2560715 | 50000 | 2510715 | 2560715 | 2601322 | 0 | 0 | 0 | 2601322 | 2476584 | 98.64% | 1 | -124738 | 0 | 16 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 108 | 2539521.53
| 01 | T1604 | 43340715201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 130 | 138 | 139 | 98.46% | 1 | -1 | 1 | 0 | 11 | -3 | 1272557 | 50000 | 1222557 | 1265786 | 1215247 | 0 | 0 | 0 | 1215247 | 1215247 | 99.4% | 1 | 0 | -6770 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -6770 | 0 | 0 | -3 | -6770 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-20 | QTR4 | 15/16 | 113 | 1175938.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1610 | 43337615201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 140 | 157 | 173 | 111.4% | 1 | -16 | 16 | 0 | 17 | 0 | 766880 | 38788 | 728092 | 763925 | 702653 | -27872 | 0 | -27872 | 674781 | 674781 | 92.68% | 1 | 0 | -2956 | 10 | 7 | 0 | 0 | -73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2956 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-28 | QTR4 | 15/16 | 108 | 1032307.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1612 | 43539315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 2 | 139 | 163 | 162 | 99.28% | 1 | 1 | 0 | 0 | 24 | 0 | 965039 | 0 | 965039 | 965864 | 949501 | 0 | 0 | 0 | 949501 | 941761 | 97.59% | 1 | -7741 | 825 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-05 | QTR1 | 16/17 |  | 2016-04-14 | QTR4 | 15/16 | 113 | 968994.66
| 01 | T1615 | 42950615201 | 2015-06-17 | QTR4 | 14/15 | 2 | 0 | 150 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1470894 | 50000 | 1420894 | 1470894 | 1424904 | 0 | 0 | 0 | 1424904 | 1424904 | 100.3% | 1 | 0 | 0 | 30 | 4 | 0 | 0 | 3080 | 0 | 0 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4010 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-07-05 | QTR1 | 16/17 | 115 | 1441634.98 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1617 | 43337515201 | 2015-06-17 | QTR4 | 14/15 | 1 | 2 | 150 | 170 | 169 | 99.33% | 1 | 1 | 0 | 0 | 20 | 0 | 1087453 | 50000 | 1037453 | 1211375 | 1165751 | 0 | 0 | 0 | 1165751 | 1165751 | 112.4% | 0 | 0 | 123922 | 11 | 9 | 0 | 0 | 135887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128298 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 108 | 1092794.1 | B0 | ACC - LUMP SUM
| 01 | T1618 | 43340815201 | 2015-06-17 | QTR4 | 14/15 | 2 | 2 | 150 | 185 | 185 | 104.7% | 1 | 0 | 0 | 0 | 28 | 7 | 1135821 | 50000 | 1085821 | 1138128 | 1108067 | 0 | 0 | 0 | 1108067 | 1103946 | 101.7% | 1 | -4121 | 2307 | 17 | 11 | 0 | 4 | 3712 | 0 | 0 | 3 | 18533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 22246 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 108 | 1209049.68 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1619 | 43365815201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 145 | 172 | 171 | 110.3% | 1 | 1 | 0 | 0 | 27 | 0 | 618558 | 0 | 618558 | 622340 | 622340 | 0 | 0 | 0 | 622340 | 622340 | 100.6% | 1 | 0 | 3782 | 7 | 4 | 2 | 0 | 3782 | 3782 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 3782 | 3782 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-10-05 | QTR2 | 16/17 | 108 | 495886.08 | B0 | ACC - LUMP SUM
| 01 | T1629 | 43325615201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 85 | 88 | 74 | 83.53% | 1 | 14 | 0 | 0 | 3 | 0 | 910000 | 47212 | 862788 | 910000 | 883227 | 0 | 0 | 0 | 883227 | 883227 | 102.4% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 13198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13198 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-28 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 115 | 857875.38 | B0 | ACC - LUMP SUM
| 01 | T1651 | 43134115201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 90 | 91 | 78 | 85.56% | 1 | 13 | 0 | 0 | 1 | 0 | 194630 | 9734 | 184896 | 194630 | 184896 | 0 | 0 | 0 | 184896 | 184896 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-06-06 | QTR4 | 15/16 | 118 | 236550.37 | B0 | ACC - LUMP SUM
| 01 | T1659 | 43472815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 70 | 78 | 49 | 58.57% | 1 | 29 | 0 | 0 | 8 | 0 | 238287 | 9912 | 228375 | 238287 | 228375 | 0 | 0 | 0 | 228375 | 228375 | 100% | 1 | 0 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 |  | 2016-10-17 | QTR2 | 16/17 | 115 | 176436.4 | B0 | ACC - LUMP SUM
| 01 | T1A02 | 42518315201 | 2014-12-03 | QTR2 | 14/15 | 1 | 4 | 250 | 403 | 402 | 130.8% | 0 | 1 | 0 | 0 | 75 | 78 | 5396928 | 50000 | 5346928 | 5491707 | 5952983 | 0 | 0 | 0 | 5952983 | 5952455 | 111.3% | 0 | -528 | 94779 | 57 | 18 | 0 | 75 | 18567 | 0 | 0 | 3 | 122779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 141346 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-05-19 | QTR4 | 15/16 | 115 | 4358786.71 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1A15 | 43325515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 70 | 97 | 97 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 219504 | 10504 | 209000 | 219504 | 213917 | 0 | 0 | 0 | 213917 | 213917 | 102.4% | 1 | 0 | 0 | 15 | 12 | 0 | 0 | 4917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4917 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-02-20 | QTR3 | 15/16 | 106 | 200589.29 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 21 | 29 | 49 | 4269 | 5502 | 5234 | 85.71% | 18 | 268 | 109 | 0 | 1051 | 182 | 103505177 | 1054423 | 102450754 | 102361397 | 101907760 | -372280 | 2200000 | 1827720 | 103735480 | 97719183 | 85.71% | 18 | -6016299 | -1143780 | 795 | 201 | 2 | 134 | -902140 | 42997 | 14 | 51 | 610668 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | -6896 | 0 | 0 | 0 | 8532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1529 | 0 | 0 | 0 | 19544 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -498487 | 0 | 18 | 182 | -763250 | 62491
| 01 | E1N36 | 43544915201 | 2014-06-19 | QTR4 | 13/14 | 1 | 2 | 160 | 182 | 194 | 111.2% | 1 | -12 | 12 | 0 | 16 | 6 | 1877203 | 50000 | 1827203 | 1918177 | 1843430 | -20904 | 0 | -20904 | 1822526 | 1821939 | 99.71% | 1 | -587 | 40974 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 6 | 46084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 46084 | 0 | F593586613 | EVANS CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 |  | 2015-05-19 | QTR4 | 14/15 | 108 | 2352808.24
| 01 | E1N74 | 42912015201 | 2014-12-18 | QTR2 | 14/15 | 1 | 0 | 185 | 212 | 212 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 3107573 | 50000 | 3057573 | 3107573 | 3110593 | 0 | 0 | 0 | 3110593 | 2961957 | 96.87% | 1 | -148636 | 0 | 9 | 18 | 0 | 0 | 7628 | 0 | 0 | 0 | 8425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16053 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-01-21 | QTR3 | 15/16 | 113 | 3280021.43
| 01 | E1N87 | 43120915201 | 2015-02-19 | QTR3 | 14/15 | 1 | 0 | 300 | 336 | 336 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 3172000 | 50000 | 3122000 | 3172000 | 3272265 | 0 | 0 | 0 | 3272265 | 3269380 | 104.7% | 1 | -2886 | 0 | 24 | 12 | 0 | 0 | 7188 | 0 | 0 | 0 | 21276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40644 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-25 | QTR4 | 15/16 | 108 | 3312411.11
| 01 | E1O02 | 43161515201 | 2015-01-15 | QTR3 | 14/15 | 1 | 2 | 290 | 354 | 354 | 110.3% | 1 | 0 | 0 | 0 | 34 | 30 | 5445703 | 56538 | 5389165 | 6533716 | 6114803 | 0 | 0 | 0 | 6114803 | 5883385 | 109.2% | 1 | -231419 | 1088013 | 19 | 15 | 0 | 20 | 396717 | 0 | 0 | 10 | 691296 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1088013 | 691296 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 113 | 4971481.53
| 01 | E1O75 | 43503815201 | 2016-01-21 | QTR3 | 15/16 | 1 | 0 | 60 | 62 | 54 | 86.67% | 1 | 8 | 0 | 0 | 2 | 0 | 149955 | 6815 | 143140 | 149955 | 147793 | 0 | 0 | 0 | 147793 | 147793 | 103.3% | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 6813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6813 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-06-21 | QTR4 | 15/16 | 118 | 157973.52
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 5 | 5 | 4 | 995 | 1146 | 1150 | 100% | 5 | -4 | 12 | 0 | 115 | 36 | 13752434 | 213353 | 13539081 | 14881421 | 14488884 | -20904 | 0 | -20904 | 14467980 | 14084454 | 100% | 5 | -383528 | 1128987 | 60 | 55 | 0 | 20 | 418346 | 0 | 0 | 16 | 767081 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1197607 | 691296
| District 01 Totals |  |  |  |  | 26 | 34 | 53 | 5264 | 6648 | 6384 | 88.46% | 23 | 264 | 121 | 0 | 1166 | 218 | 117257611 | 1267776 | 115989835 | 117242818 | 116396644 | -393184 | 2200000 | 1806816 | 118203460 | 111803637 | 88.46% | 23 | -6399827 | -14793 | 855 | 256 | 2 | 154 | -483794 | 42997 | 14 | 67 | 1377749 | 710790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | -3046 | 0 | 0 | 0 | 16863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1529 | 0 | 0 | 0 | 19544 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -498487 | 0 | 18 | 218 | 434357 | 753787
| 02 | T2506 | 43040415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 45 | 48 | 103 | 222.2% | 0 | -55 | 55 | 0 | 3 | 0 | 136157 | 7800 | 128357 | 136157 | 128357 | -47602 | 0 | -47602 | 80754 | 80754 | 62.91% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-09-14 | QTR1 | 16/17 |  | 2014-05-14 | QTR4 | 13/14 | 208 | 153002.52 | B0 | ACC - LUMP SUM
| 02 | T2533 | 43355415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 3 | 400 | 535 | 535 | 104.5% | 1 | 0 | 0 | 0 | 117 | 18 | 8533240 | 72079 | 8461162 | 8598881 | 9356445 | 0 | 0 | 0 | 9356445 | 9207548 | 108.8% | 1 | -148897 | 65641 | 58 | 59 | 0 | 0 | 229 | 0 | 0 | 18 | 64256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19692 | 0 | 0 | 18 | 46705 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 208 | 7794225.55
| 02 | T2538 | 42696315201 | 2014-06-18 | QTR4 | 13/14 | 2 | 0 | 130 | 198 | 198 | 105.4% | 1 | 0 | 0 | 0 | 65 | 3 | 3648202 | 50000 | 3598202 | 3648202 | 3611865 | 0 | 0 | 0 | 3611865 | 3514982 | 97.69% | 1 | -96884 | 0 | 33 | 28 | 4 | 3 | 9477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 9477 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-10-05 | QTR2 | 16/17 |  | 2015-05-28 | QTR4 | 14/15 | 208 | 3330302.73
| 02 | T2541 | 42607315201 | 2014-09-24 | QTR1 | 14/15 | 1 | 1 | 380 | 501 | 501 | 112.1% | 1 | 0 | 0 | 0 | 83 | 38 | 3641891 | 50000 | 3591891 | 3767252 | 4042041 | 0 | 0 | 0 | 4042041 | 3981696 | 110.9% | 0 | -60345 | 125361 | 55 | 20 | 0 | 0 | 0 | 0 | 0 | 38 | 174588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 174588 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-11-14 | QTR2 | 16/17 |  | 2016-05-26 | QTR4 | 15/16 | 209 | 3748196.45
| 02 | T2567 | 43224715201 | 2015-02-25 | QTR3 | 14/15 | 1 | 8 | 135 | 252 | 252 | 141.5% | 0 | 0 | 0 | 0 | 79 | 38 | 1013111 | 0 | 1013111 | 1368388 | 1368010 | 0 | 0 | 0 | 1368010 | 1368010 | 135% | 0 | 0 | 355277 | 46 | 15 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-02-01 | QTR3 | 15/16 | 214 | 1004174.39 | B0 | ACC - LUMP SUM
| 02 | T2572 | 43061415201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 150 | 191 | 191 | 102% | 1 | 0 | 0 | 0 | 41 | 0 | 1990811 | 0 | 1990811 | 2002450 | 2059822 | 0 | 0 | 0 | 2059822 | 2059822 | 103.5% | 1 | 0 | 11638 | 21 | 17 | 0 | 0 | 11638 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 11638 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-07-21 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 214 | 1508389.63
| 02 | T2584 | 43051315201 | 2015-08-26 | QTR1 | 15/16 | 2 | 1 | 150 | 186 | 185 | 114% | 1 | 1 | 0 | 0 | 14 | 22 | 3444187 | 50000 | 3394187 | 3524159 | 3538172 | 0 | 0 | 0 | 3538172 | 3415729 | 100.6% | 1 | -122443 | 79972 | 8 | 6 | 0 | 3 | 2309 | 0 | 0 | 19 | 89994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 92303 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-12-28 | QTR2 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 214 | 3688557.42
| 02 | T2587 | 43265515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 120 | 151 | 151 | 100% | 1 | 0 | 0 | 0 | 31 | 0 | 718800 | 0 | 718800 | 718800 | 718800 | 0 | 0 | 0 | 718800 | 718800 | 100% | 1 | 0 | 0 | 26 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453689782 | SOUTHERN STATES PAVEMENT MARKINGS INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-06-02 | QTR4 | 15/16 | 209 | 769166.88 | B0 | ACC - LUMP SUM
| 02 | T2588 | 21237925201 | 2015-09-30 | QTR1 | 15/16 | 1 | 3 | 170 | 227 | 227 | 130% | 0 | 0 | 0 | 0 | 23 | 34 | 2271500 | 0 | 2271500 | 2329229 | 2340019 | 0 | 0 | 0 | 2340019 | 2337891 | 102.9% | 1 | -2128 | 57729 | 5 | 1 | 4 | 0 | 7981 | 0 | 13 | 5 | 38697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 11052 | 11052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 34 | 57729 | 11052 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-11-29 | QTR2 | 16/17 |  | 2016-08-17 | QTR1 | 16/17 | 208 | 2754838.98 | B0 | ACC - LUMP SUM
| 02 | T2589 | 41525415201 | 2015-12-03 | QTR2 | 15/16 | 2 | 2 | 250 | 256 | 224 | 87.2% | 1 | 32 | 0 | 0 | 6 | 0 | 1503905 | 0 | 1503905 | 1530011 | 1553775 | 0 | 0 | 0 | 1553775 | 1554113 | 103.3% | 1 | 338 | 26105 | 3 | 3 | 0 | 0 | 26105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26105 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 |  | 2016-10-04 | QTR2 | 16/17 | 208 | 1346460.02
| 02 | T2593 | 43051715201 | 2015-09-30 | QTR1 | 15/16 | 3 | 2 | 179 | 211 | 210 | 105% | 1 | 1 | 0 | 0 | 22 | 10 | 1956915 | 0 | 1956915 | 1997332 | 1951682 | 0 | 0 | 0 | 1951682 | 1947009 | 99.49% | 1 | -4672 | 40417 | 19 | 3 | 0 | 10 | 40417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 40417 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-16 | QTR2 | 16/17 |  | 2016-08-01 | QTR1 | 16/17 | 209 | 2334094.44
| 02 | T2594 | 43265415201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 152 | 152 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 475000 | 0 | 475000 | 475000 | 475000 | 0 | 0 | 0 | 475000 | 475000 | 100% | 1 | 0 | 0 | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-09-30 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 209 | 428505.77 | B0 | ACC - LUMP SUM
| 02 | T2602 | 43074515201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 100 | 114 | 113 | 99% | 1 | 1 | 0 | 0 | 14 | 0 | 558858 | 27404 | 531454 | 558858 | 508320 | 0 | 0 | 0 | 508320 | 508320 | 95.65% | 1 | 0 | 0 | 11 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-10-17 | QTR2 | 16/17 | 209 | 579077.38
| 02 | T2603 | 43075915201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 95 | 95 | 118.7% | 1 | 0 | 0 | 0 | 6 | 14 | 521218 | 23780 | 497438 | 521218 | 506672 | 0 | 0 | 0 | 506672 | 506672 | 101.9% | 1 | 0 | 0 | 3 | 3 | 0 | 10 | 1681 | 0 | 0 | 0 | 7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 9235 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-07-01 | QTR1 | 16/17 | 214 | 510081.72
| 02 | T2604 | 43226115201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 200 | 233 | 237 | 105% | 1 | -4 | 4 | 0 | 27 | 6 | 7717554 | 101575 | 7615979 | 7717554 | 7824593 | -15080 | 0 | -15080 | 7809513 | 7576665 | 99.48% | 1 | -232848 | 0 | 24 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-27 | QTR2 | 16/17 |  | 2016-09-07 | QTR1 | 16/17 | 209 | 9660990.21
| 02 | T2608 | 43055825201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 84 | 80 | 94.67% | 1 | 4 | 0 | 0 | 9 | 0 | 148375 | 8369 | 140006 | 148375 | 138616 | 0 | 0 | 0 | 138616 | 138616 | 99.01% | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 209 | 178082.19
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 16 | 21 | 23 | 2679 | 3434 | 3454 | 81.25% | 13 | -20 | 59 | 0 | 572 | 183 | 38279724 | 391007 | 37888718 | 39041866 | 40122189 | -62682 | 0 | -62682 | 40059506 | 39391627 | 87.5% | 14 | -667879 | 762140 | 351 | 171 | 8 | 26 | 99837 | 0 | 16 | 118 | 731312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 11052 | 11052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19692 | 0 | 24 | 177 | 824421 | 11052
| 02 | E2P99 | 21330125201 | 2012-06-29 | QTR4 | 11/12 | 2 | 7 | 615 | 1443 | 1443 | 202% | 0 | 0 | 0 | 0 | 201 | 627 | 17859000 | 150000 | 17709000 | 27306925 | 27318877 | 0 | 0 | 0 | 27318877 | 26689964 | 150.7% | 0 | -628913 | 9447925 | 119 | 82 | 0 | 627 | 9078926 | 2177986 | 0 | 0 | 325187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0 | 0 | 2873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627 | 9579662 | 2177986 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-12-14 | QTR2 | 16/17 |  | 2016-08-09 | QTR1 | 16/17 | 208 | 28650000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2R04 | 21066125201 | 2012-12-12 | QTR2 | 12/13 | 2 | 1 | 90 | 192 | 224 | 216.7% | 0 | -32 | 32 | 0 | 32 | 70 | 1430432 | 50000 | 1380432 | 1430840 | 1393606 | -49024 | 0 | -49024 | 1344582 | 1344578 | 97.4% | 1 | -4 | 408 | 14 | 15 | 3 | 0 | 4074 | 0 | 0 | 70 | 21643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 70 | 25716 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 | 07/17/2014 | 2014-03-07 | QTR3 | 13/14 | 208 | 1293927.32
| 02 | E2R17 | 21237935201 | 2013-06-20 | QTR4 | 12/13 | 5 | 1 | 790 | 846 | 846 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 11440230 | 150000 | 11290230 | 11429587 | 11316805 | 0 | 0 | 0 | 11316805 | 11261013 | 99.74% | 1 | -55793 | -10643 | 7 | 49 | 0 | 0 | -621 | 0 | 0 | 0 | 42964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11541 | 0 | 0 | 0 | 32321 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2015-12-07 | QTR2 | 15/16 | 208 | 13890662.92 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
| 02 | E2T58 | 43226315201 | 2015-11-18 | QTR2 | 15/16 | 1 | 0 | 140 | 181 | 181 | 101.4% | 1 | 0 | 0 | 0 | 41 | 0 | 3757549 | 50000 | 3707549 | 3757549 | 3830766 | 0 | 0 | 0 | 3830766 | 3684887 | 99.39% | 1 | -145879 | 0 | 30 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-10-11 | QTR2 | 16/17 |  | 2016-09-08 | QTR1 | 16/17 | 214 | 4878401.01
| 02 | E2T69 | 43041715201 | 2015-07-15 | QTR1 | 15/16 | 1 | 3 | 210 | 362 | 362 | 161% | 0 | 0 | 0 | 0 | 30 | 122 | 1759555 | 50000 | 1709555 | 1996713 | 2571252 | 0 | 0 | 0 | 2571252 | 2563560 | 150% | 0 | -7693 | 237158 | 11 | 13 | 0 | 18 | 101267 | 0 | 0 | 104 | 148934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 250201 | 0 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 |  | 2016-09-16 | QTR1 | 16/17 | 208 | 1357063.07
| 02 | E2T70 | 43219415201 | 2015-07-15 | QTR1 | 15/16 | 1 | 0 | 190 | 217 | 214 | 100.5% | 1 | 3 | 0 | 0 | 23 | 4 | 741630 | 36943 | 704687 | 741630 | 709180 | 0 | 0 | 0 | 709180 | 709010 | 100.6% | 1 | -170 | 0 | 14 | 9 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 214 | 775810
| 02 | E2T74 | 42342715201 | 2015-09-16 | QTR1 | 15/16 | 1 | 0 | 135 | 163 | 162 | 99.26% | 1 | 1 | 0 | 0 | 28 | 0 | 4336630 | 50000 | 4286630 | 4336630 | 4421132 | 0 | 0 | 0 | 4421132 | 4255700 | 99.28% | 1 | -165433 | 0 | 27 | 1 | 0 | 0 | 17388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17388 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-28 | QTR1 | 16/17 |  | 2016-06-13 | QTR4 | 15/16 | 209 | 4754490.59
| 02 | E2T87 | 20967415201 | 2015-11-18 | QTR2 | 15/16 | 1 | 0 | 140 | 199 | 198 | 117.1% | 1 | 1 | 0 | 0 | 34 | 25 | 1743906 | 50000 | 1693906 | 1743906 | 2125210 | 0 | 0 | 0 | 2125210 | 2124106 | 125.4% | 0 | -1104 | 0 | 30 | 4 | 0 | 0 | 0 | 0 | 0 | 21 | 39680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 41424 | 0 | F205877898 | KIRBY DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 |  | 2016-08-24 | QTR1 | 16/17 | 208 | 1607950.75
| 02 | E2T90 | 20838945201 | 2015-12-16 | QTR2 | 15/16 | 1 | 0 | 185 | 192 | 155 | 80% | 1 | 37 | 0 | 0 | 7 | 0 | 559753 | 48363 | 511389 | 559753 | 512091 | 0 | 0 | 0 | 512091 | 512091 | 100.1% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593285921 | S & D INDUSTRIAL PAINTING INC. | N/A | N/A | N/A | N/A | 2016-11-08 | QTR2 | 16/17 |  | 2016-10-03 | QTR2 | 16/17 | 209 | 1034491.52
| 02 | E2U45 | 42871125201 | 2015-12-16 | QTR2 | 15/16 | 1 | 0 | 45 | 53 | 211 | 453.3% | 0 | -158 | 158 | 0 | 7 | 1 | 138261 | 7135 | 131126 | 138261 | 134115 | -43856 | 0 | -43856 | 90258 | 120111 | 91.6% | 1 | 29853 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2989 | 0 | Z31-0396250 | OHIO CASUALTY INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-21 | QTR2 | 16/17 | 208 | 151023.35 | B0 | ACC - LUMP SUM
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 10 | 16 | 12 | 2540 | 3848 | 3996 | 60% | 6 | -148 | 190 | 0 | 459 | 849 | 43766946 | 642441 | 43124504 | 53441794 | 54333034 | -92880 | 0 | -92880 | 54240153 | 53265020 | 70% | 7 | -975136 | 9674848 | 261 | 187 | 3 | 645 | 9201034 | 2177986 | 0 | 200 | 594692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0 | 0 | 4392 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 132621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11541 | 0 | 3 | 849 | 9964259 | 2177986
| District 02 Totals |  |  |  |  | 26 | 37 | 35 | 5219 | 7282 | 7450 | 73.08% | 19 | -168 | 249 | 0 | 1031 | 1032 | 82046670 | 1033448 | 81013222 | 92483660 | 94455223 | -155562 | 0 | -155562 | 94299659 | 92656647 | 80.77% | 21 | -1643015 | 10436988 | 612 | 358 | 11 | 671 | 9300871 | 2177986 | 16 | 318 | 1326004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0 | 4 | 6304 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 132621 | 0 | 0 | 29 | 11052 | 11052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31233 | 0 | 27 | 1026 | 10788680 | 2189038
| 03 | T3349 | 22041285201 | 2010-12-08 | QTR2 | 10/11 | 3 | 28 | 835 | 1802 | 1804 | 182% | 0 | -2 | 2 | 0 | 381 | 586 | 7357219 | 72479 | 7284740 | 10528722 | 10638848 | -93018 | 0 | -93018 | 10545830 | 10537771 | 144.7% | 0 | -8059 | 3171503 | 203 | 81 | 0 | 428 | 2195488 | 844067 | 0 | 120 | 436311 | 60348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 81300 | 13615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 365823 | 185379 | 97 | 0 | 126858 | 126858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 586 | 3205779 | 1230267 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-03-11 | QTR3 | 15/16 | 308 | 7320354.71 | ARRA | AMERICAN RECOVERY AND REINVEST
| 03 | T3375 | 42124315201 | 2012-02-29 | QTR3 | 11/12 | 3 | 3 | 1194 | 1402 | 1400 | 103% | 1 | 2 | 0 | 0 | 170 | 38 | 14736078 | 150000 | 14586078 | 15035632 | 14669101 | 0 | 0 | 0 | 14669101 | 14620764 | 100.2% | 1 | -48338 | 299554 | 105 | 65 | 0 | 38 | 320021 | 0 | 0 | 0 | 102024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59292 | 0 | 0 | 0 | 7231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 371313 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-30 | QTR4 | 15/16 | 308 | 18080147.32
| 03 | T3398 | 22016225201 | 2013-09-25 | QTR1 | 13/14 | 1 | 4 | 310 | 940 | 940 | 238.1% | 0 | 0 | 0 | 0 | 415 | 215 | 3358717 | 50000 | 3308717 | 4155082 | 4026349 | 0 | 0 | 0 | 4026349 | 3996594 | 120.8% | 0 | -29755 | 796365 | 165 | 37 | 27 | 211 | 787219 | 726197 | 5 | 3 | 10636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 1 | -14634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 215 | 783220 | 726197 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-07 | QTR2 | 16/17 |  | 2016-08-02 | QTR1 | 16/17 | 308 | 2823245.81
| 03 | T3418 | 42551915201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 350 | 475 | 472 | 99.14% | 1 | 3 | 0 | 0 | 125 | 0 | 2589441 | 50000 | 2539441 | 2672648 | 2648983 | 0 | 0 | 0 | 2648983 | 2635144 | 103.8% | 1 | -13838 | 83207 | 114 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-07-06 | QTR1 | 16/17 | 308 | 2582602.98
| 03 | T3427 | 42164415201 | 2013-07-31 | QTR1 | 13/14 | 4 | 2 | 475 | 888 | 888 | 112% | 1 | 0 | 0 | 0 | 369 | 44 | 11476305 | 126776 | 11349528 | 11609159 | 11286785 | -11250 | 0 | -11250 | 11275535 | 10699458 | 94.27% | 1 | -576077 | 132854 | 265 | 91 | 0 | 19 | 140137 | 0 | 0 | 15 | 65665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 12852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 44 | 228449 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 308 | 12800389.92
| 03 | T3433 | 42693025201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 285 | 368 | 375 | 103.5% | 1 | -7 | 7 | 0 | 80 | 3 | 4985043 | 60566 | 4924478 | 5040858 | 4902106 | -20132 | 0 | -20132 | 4881974 | 4555909 | 92.52% | 1 | -326064 | 55814 | 53 | 27 | 0 | 3 | 55814 | 15953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 64944 | 15953 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-24 | QTR2 | 16/17 |  | 2016-05-21 | QTR4 | 15/16 | 321 | 6115127.23
| 03 | T3443 | 42693415201 | 2014-12-03 | QTR2 | 14/15 | 2 | 1 | 247 | 408 | 408 | 113.8% | 1 | 0 | 0 | 0 | 143 | 18 | 4037987 | 50000 | 3987987 | 4183812 | 4167957 | 0 | 0 | 0 | 4167957 | 3846478 | 96.45% | 1 | -321479 | 145825 | 106 | 21 | 13 | 17 | 28230 | 0 | 3 | 1 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18 | 175160 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 308 | 4397278.78
| 03 | T3460 | 42874715201 | 2016-03-30 | QTR3 | 15/16 | 2 | 0 | 120 | 140 | 137 | 98.33% | 1 | 3 | 0 | 0 | 19 | 1 | 1335414 | 50000 | 1285414 | 1335414 | 1301394 | 0 | 0 | 0 | 1301394 | 1295632 | 100.8% | 1 | -5762 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5544 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 |  | 2016-11-04 | QTR2 | 16/17 | 321 | 1593999.48
| 03 | T3482 | 42884515201 | 2015-01-28 | QTR3 | 14/15 | 2 | 1 | 300 | 396 | 388 | 97.33% | 1 | 8 | 0 | 0 | 96 | 0 | 7416925 | 85537 | 7331389 | 7437265 | 7758460 | -880 | 0 | -880 | 7757580 | 7441692 | 101.5% | 1 | -315888 | 20339 | 66 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 27217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30580 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 313 | 8733987.91
| 03 | T3483 | 43077715201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 250 | 386 | 386 | 113.6% | 1 | 0 | 0 | 0 | 115 | 21 | 4039522 | 50000 | 3989522 | 4047995 | 4269663 | 0 | 0 | 0 | 4269663 | 4226492 | 105.9% | 1 | -43171 | 8473 | 57 | 45 | 12 | 10 | 55493 | 0 | 1 | 4 | 4180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30674 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 21 | 28999 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-05 | QTR2 | 16/17 |  | 2016-08-24 | QTR1 | 16/17 | 314 | 3857910.06
| 03 | T3495 | 42695615201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 90 | 226 | 225 | 98.89% | 1 | 1 | 0 | 0 | 136 | 0 | 1619321 | 50000 | 1569321 | 1619321 | 1588249 | 0 | 0 | 0 | 1588249 | 1566711 | 99.83% | 1 | -21538 | 0 | 102 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-05-18 | QTR4 | 15/16 | 321 | 1991519.93
| 03 | T3514 | 43078115201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 175 | 307 | 308 | 100.6% | 1 | -1 | 1 | 0 | 132 | 0 | 3802689 | 50000 | 3752689 | 3802689 | 3624193 | 0 | 0 | 0 | 3624193 | 3479143 | 92.71% | 1 | -145050 | 0 | 90 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 |  | 2016-07-23 | QTR1 | 16/17 | 314 | 4144189.92
| 03 | T3515 | 43090835201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 240 | 568 | 567 | 164.2% | 0 | 1 | 0 | 0 | 314 | 14 | 8076272 | 85662 | 7990610 | 8066272 | 8349102 | 0 | 0 | 0 | 8349102 | 7667982 | 95.96% | 1 | -681120 | -10000 | 119 | 54 | 1 | 14 | 68182 | 0 | 0 | 0 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 14 | 58182 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 313 | 8827284.67
| 03 | T3539 | 22243945201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 90 | 205 | 205 | 167.8% | 0 | 0 | 0 | 0 | 66 | 49 | 1948263 | 50000 | 1898263 | 1965454 | 2004975 | 0 | 0 | 0 | 2004975 | 2004975 | 105.6% | 1 | 0 | 17192 | 50 | 4 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 45708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 49 | 45708 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-07-28 | QTR1 | 16/17 | 308 | 1870760.28
| 03 | T3551 | 42873915201 | 2015-03-25 | QTR3 | 14/15 | 3 | 4 | 175 | 297 | 304 | 125.1% | 0 | -7 | 7 | 0 | 118 | 4 | 2525492 | 50000 | 2475492 | 2696693 | 2810548 | -29132 | 0 | -29132 | 2781416 | 2626488 | 106.1% | 1 | -154929 | 171200 | 58 | 27 | 22 | 0 | 31909 | 0 | 11 | 4 | 152138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 4 | 201162 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-01 | QTR2 | 16/17 |  | 2016-04-10 | QTR4 | 15/16 | 321 | 3044222.49
| 03 | T3552 | 43273715201 | 2015-07-29 | QTR1 | 15/16 | 1 | 1 | 125 | 237 | 237 | 108.8% | 1 | 0 | 0 | 0 | 101 | 11 | 3670000 | 50000 | 3620000 | 3738760 | 3752339 | -5200 | 0 | -5200 | 3747139 | 3621209 | 100% | 1 | -125930 | 68760 | 66 | 35 | 0 | 7 | 27730 | 0 | 0 | 4 | 70531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 98576 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-10 | QTR2 | 16/17 |  | 2016-06-11 | QTR4 | 15/16 | 308 | 4236500
| 03 | T3589 | 43174315201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 120 | 126 | 77 | 59.17% | 1 | 49 | 0 | 0 | 6 | 0 | 169047 | 0 | 169047 | 169047 | 169047 | 0 | 0 | 0 | 169047 | 169047 | 100% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 321 | 199840.42 | B0 | ACC - LUMP SUM
| 03 | T9009 | 43035625201 | 2015-06-24 | QTR4 | 14/15 | 1 | 0 | 240 | 330 | 299 | 105.4% | 1 | 31 | 0 | 0 | 90 | 0 | 1500230 | 50000 | 1450230 | 1500230 | 1507255 | 0 | 0 | 0 | 1507255 | 1507255 | 103.9% | 1 | 0 | 0 | 30 | 16 | 30 | 0 | 0 | 0 | 14 | 0 | 29504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 49973 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 314 | 1868902.5
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 18 | 33 | 51 | 5621 | 9501 | 9420 | 72.22% | 13 | 81 | 17 | 0 | 2876 | 1004 | 84643965 | 1131020 | 83512946 | 89605053 | 89475354 | -159612 | 0 | -159612 | 89315742 | 86498744 | 88.89% | 16 | -2816998 | 4961086 | 1665 | 629 | 105 | 747 | 3710223 | 1586217 | 46 | 152 | 894855 | 60348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316 | 68 | 390526 | 13615 | 0 | 7 | 20478 | 0 | 0 | 0 | -59292 | 0 | 18 | 30 | 386150 | 185379 | 97 | 0 | 126858 | 126858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582 | 1004 | 5469795 | 1972417
| 03 | E3K73 | 42693515201 | 2014-03-13 | QTR3 | 13/14 | 2 | 1 | 200 | 344 | 344 | 109.5% | 1 | 0 | 0 | 0 | 125 | 19 | 1221881 | 50000 | 1171881 | 1231781 | 1143560 | 0 | 0 | 0 | 1143560 | 1120620 | 95.63% | 1 | -22940 | 9900 | 106 | 19 | 0 | 0 | 0 | 0 | 0 | 19 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 10560 | 6600 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2015-06-14 | QTR4 | 14/15 | 308 | 1514949.05
| 03 | E3L90 | 42840315201 | 2013-06-28 | QTR4 | 12/13 | 1 | 3 | 534 | 975 | 975 | 139.7% | 0 | 0 | 0 | 0 | 304 | 137 | 24049000 | 150000 | 23899000 | 24338104 | 24337828 | 0 | 0 | 0 | 24337828 | 24337642 | 101.8% | 1 | -186 | 289104 | 165 | 64 | 0 | 0 | 10000 | 0 | 20 | 0 | 59678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 363800 | 298854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 137 | 438828 | 298854 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2016-08-30 | QTR1 | 16/17 |  | 2016-04-26 | QTR4 | 15/16 | 313 | 21314871.51 | A3 | ICC - DESIGN/BUILD - MINOR
| 03 | E3M17 | 40747845201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 90 | 109 | 107 | 97.78% | 1 | 2 | 0 | 0 | 19 | 0 | 149498 | 7779 | 141719 | 149498 | 139613 | 0 | 0 | 0 | 139613 | 139613 | 98.51% | 1 | 0 | 0 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455085205 | PRINCIPLE PROPERTIES INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-06-08 | QTR4 | 15/16 | 308 | 163264.04
| 03 | E3M30 | 42429125201 | 2015-02-26 | QTR3 | 14/15 | 2 | 1 | 300 | 535 | 534 | 139.7% | 0 | 1 | 0 | 0 | 115 | 120 | 4578636 | 50636 | 4528000 | 5834533 | 5832583 | 0 | 0 | 0 | 5832583 | 5832583 | 128.8% | 0 | 0 | 1255897 | 89 | 26 | 0 | 0 | 0 | 0 | 0 | 120 | 1304583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1304583 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-28 | QTR2 | 16/17 | 308 | 4578636 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| 03 | E3M55 | 42805825201 | 2014-01-31 | QTR3 | 13/14 | 1 | 1 | 265 | 629 | 628 | 198.1% | 0 | 1 | 0 | 0 | 211 | 153 | 1540571 | 50000 | 1490571 | 1579254 | 1571464 | 0 | 0 | 0 | 1571464 | 1571464 | 105.4% | 1 | 0 | 38683 | 83 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-01-19 | QTR3 | 15/16 | 308 | 1529160 | A3 | ICC - DESIGN/BUILD - MINOR
| 03 | E3M95 | 41694315201 | 2015-07-09 | QTR1 | 15/16 | 1 | 3 | 140 | 240 | 239 | 118.6% | 1 | 1 | 0 | 0 | 73 | 27 | 2738862 | 50000 | 2688862 | 3014082 | 3595051 | 0 | 0 | 0 | 3595051 | 3484491 | 129.6% | 0 | -110560 | 275220 | 36 | 37 | 0 | 0 | 0 | 0 | 0 | 5 | 288220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 12155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 27 | 287375 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-19 | QTR1 | 16/17 |  | 2016-06-27 | QTR4 | 15/16 | 314 | 3204695.35
| 03 | E3N17 | 43392715201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 65 | 65 | 50 | 73.85% | 1 | 15 | 0 | 0 | 2 | -2 | 1734968 | 50000 | 1684968 | 1417537 | 1360898 | 0 | 0 | 0 | 1360898 | 1360898 | 80.77% | 1 | 0 | -317430 | 2 | 0 | 0 | -2 | -313024 | 0 | 0 | 0 | 4578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | -308196 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-05-23 | QTR4 | 15/16 | 321 | 1346663.5
| 03 | E3N18 | 43391815201 | 2015-10-08 | QTR2 | 15/16 | 1 | 1 | 65 | 117 | 116 | 130.8% | 0 | 1 | 0 | 0 | 31 | 21 | 1245237 | 49942 | 1195296 | 1323870 | 1408799 | 0 | 0 | 0 | 1408799 | 1408799 | 117.9% | 0 | 0 | 78633 | 30 | 1 | 0 | 21 | 108680 | 16182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 108680 | 16182 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-01 | QTR4 | 15/16 | 308 | 1048525.47
| 03 | E3N27 | 41627215201 | 2015-03-25 | QTR3 | 14/15 | 2 | 2 | 305 | 427 | 427 | 116.4% | 1 | 0 | 0 | 0 | 72 | 50 | 2233345 | 43949 | 2189396 | 2293381 | 2249432 | 0 | 0 | 0 | 2249432 | 2223244 | 101.5% | 1 | -26188 | 60036 | 41 | 31 | 0 | 0 | 0 | 0 | 0 | 50 | 60036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 60036 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 321 | 2172218.95 | A3:LBDB:A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
| 03 | E3N39 | 43078815201 | 2015-05-14 | QTR4 | 14/15 | 2 | 2 | 185 | 318 | 294 | 90.81% | 1 | 24 | 0 | 0 | 133 | 0 | 3111936 | 50000 | 3061936 | 3033818 | 2963684 | -11504 | 0 | -11504 | 2952180 | 2882199 | 94.13% | 1 | -69981 | -78118 | 85 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 18424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -96542 | 0 | 7 | 0 | -78118 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-20 | QTR4 | 15/16 | 314 | 3291622.83
| 03 | E3N42 | 21791185201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 75 | 124 | 107 | 77.33% | 1 | 17 | 0 | 0 | 49 | 0 | 762045 | 50000 | 712045 | 762045 | 712000 | 0 | 0 | 0 | 712000 | 712000 | 99.99% | 1 | 0 | 0 | 36 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 |  | 2016-09-09 | QTR1 | 16/17 | 314 | 1488724.75
| 03 | E3N73 | 43078715201 | 2015-05-14 | QTR4 | 14/15 | 1 | 2 | 245 | 350 | 350 | 103.3% | 1 | 0 | 0 | 0 | 102 | 3 | 4943758 | 50000 | 4893758 | 4974205 | 5018776 | -2400 | 0 | -2400 | 5016376 | 4741701 | 96.89% | 1 | -274675 | 30447 | 76 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 40031 | 29279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 3 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8991 | 0 | 5 | 3 | 34041 | 29279 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 314 | 4773076.33
| 03 | E3N74 | 42696915201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 125 | 164 | 164 | 100% | 1 | 0 | 0 | 0 | 39 | 0 | 2813937 | 50000 | 2763937 | 2813937 | 2913809 | 0 | 0 | 0 | 2913809 | 2837766 | 102.7% | 1 | -76042 | 0 | 28 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 308 | 3196208.79
| 03 | E3N76 | 41557535201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 180 | 207 | 132 | 58.33% | 1 | 75 | 0 | 0 | 27 | 0 | 1819446 | 50000 | 1769446 | 1819446 | 1750296 | 0 | 0 | 0 | 1750296 | 1750297 | 98.92% | 1 | 1 | 0 | 22 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-08-28 | QTR1 | 16/17 | 308 | 1571362.8
| 03 | E3N80 | 42577825201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 60 | 79 | 87 | 116.7% | 1 | -8 | 8 | 0 | 19 | 0 | 246955 | 8741 | 238214 | 246955 | 248745 | -7664 | 0 | -7664 | 241081 | 241081 | 101.2% | 1 | 0 | 0 | 10 | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | F208328161 | AN-KAR CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 308 | 183110.5
| 03 | E3O14 | 41040925201 | 2015-09-24 | QTR1 | 15/16 | 2 | 2 | 180 | 214 | 205 | 100% | 1 | 9 | 0 | 0 | 27 | 7 | 1815481 | 50000 | 1765481 | 1830051 | 1851635 | 0 | 0 | 0 | 1851635 | 1847209 | 104.6% | 1 | -4426 | 14570 | 20 | 5 | 0 | 0 | 4627 | 0 | 0 | 4 | 46652 | 9517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 13292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 64570 | 9517 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-11-16 | QTR2 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 321 | 1670231.68
| 03 | E3O47 | 43253815201 | 2015-10-15 | QTR2 | 15/16 | 1 | 0 | 100 | 128 | 128 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 2030029 | 50000 | 1980029 | 2030029 | 2131829 | 0 | 0 | 0 | 2131829 | 2045055 | 103.3% | 1 | -86775 | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-12 | QTR1 | 16/17 | 321 | 2649534.01
| 03 | E3O53 | 43254815201 | 2015-09-10 | QTR1 | 15/16 | 1 | 0 | 125 | 173 | 173 | 100% | 1 | 0 | 0 | 0 | 48 | 0 | 2754000 | 50000 | 2704000 | 2754000 | 2779810 | 0 | 0 | 0 | 2779810 | 2686704 | 99.36% | 1 | -93106 | 0 | 44 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-24 | QTR2 | 16/17 |  | 2016-06-24 | QTR4 | 15/16 | 314 | 3103650
| 03 | E3O62 | 43079215201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 90 | 131 | 129 | 116.7% | 1 | 2 | 0 | 0 | 24 | 17 | 1298500 | 50000 | 1248500 | 1382401 | 1347119 | 0 | 0 | 0 | 1347119 | 1319720 | 105.7% | 1 | -27399 | 83901 | 17 | 7 | 0 | 17 | 83901 | 15601 | 0 | 0 | 3826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 87727 | 15601 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-08 | QTR1 | 16/17 |  | 2016-07-11 | QTR1 | 16/17 | 321 | 1564334.7 | B0 | ACC - LUMP SUM
| 03 | E3P32 | 42460825201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 40 | 51 | 48 | 92.5% | 1 | 3 | 0 | 0 | 11 | 0 | 69197 | 6233 | 62964 | 69197 | 67195 | 0 | 0 | 0 | 67195 | 67195 | 106.7% | 1 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-01 | QTR1 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 321 | 143399.73
| 03 | E3P60 | 43255315201 | 2016-08-11 | QTR1 | 16/17 | 1 | 0 | 45 | 48 | 43 | 88.89% | 1 | 5 | 0 | 0 | 3 | 0 | 966283 | 42737 | 923546 | 966283 | 955206 | -1500 | 0 | -1500 | 953706 | 953706 | 103.3% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-19 | QTR2 | 16/17 |  | 2016-11-14 | QTR2 | 16/17 | 314 | 939110.13
| 03 | E3P85 | 43627415201 | 2016-04-14 | QTR4 | 15/16 | 1 | 0 | 35 | 44 | 43 | 97.14% | 1 | 1 | 0 | 0 | 9 | 0 | 218815 | 9015 | 209800 | 218815 | 209764 | 0 | 0 | 0 | 209764 | 209764 | 99.98% | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-06 | QTR2 | 16/17 |  | 2016-08-20 | QTR1 | 16/17 | 308 | 189940
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 22 | 27 | 20 | 3449 | 5472 | 5323 | 81.82% | 18 | 149 | 8 | 0 | 1471 | 552 | 62342380 | 1019032 | 61323349 | 64083222 | 64589096 | -23068 | 0 | -23068 | 64566028 | 63773751 | 86.36% | 19 | -792277 | 1740843 | 945 | 327 | 0 | 36 | -105816 | 31783 | 22 | 198 | 1826688 | 38796 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 122 | 291 | 491651 | 305454 | 0 | 3 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -118533 | 0 | 199 | 552 | 2102590 | 376033
| District 03 Totals |  |  |  |  | 40 | 60 | 71 | 9070 | 14973 | 14743 | 77.5% | 31 | 230 | 25 | 0 | 4347 | 1556 | 146986345 | 2150052 | 144836295 | 153688275 | 154064450 | -182680 | 0 | -182680 | 153881770 | 150272495 | 87.5% | 35 | -3609275 | 6701929 | 2610 | 956 | 105 | 783 | 3604407 | 1618000 | 68 | 350 | 2721543 | 99144 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 438 | 359 | 882177 | 319069 | 0 | 10 | 23728 | 0 | 0 | 0 | -59292 | 0 | 18 | 54 | 401250 | 185379 | 97 | 0 | 126858 | 126858 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -118533 | 0 | 781 | 1556 | 7572385 | 2348450
| 04 | T4341 | 23073015201 | 2013-02-06 | QTR3 | 12/13 | 2 | 8 | 674 | 896 | 896 | 111% | 1 | 0 | 0 | 0 | 191 | 31 | 6592014 | 73358 | 6518656 | 6833204 | 6617553 | 0 | 0 | 0 | 6617553 | 6330385 | 97.11% | 1 | -287168 | 241190 | 105 | 43 | 0 | 31 | 138206 | 0 | 4 | 0 | 108342 | 50933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 31 | 314541 | 50933 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2016-07-06 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 412 | 7354583.81
| 04 | T4389 | 23097825201 | 2014-04-30 | QTR4 | 13/14 | 1 | 2 | 750 | 801 | 631 | 77.33% | 1 | 170 | 0 | 0 | 51 | 0 | 15715809 | 150000 | 15565809 | 15753499 | 15520925 | 0 | 630700 | 630700 | 16151625 | 14963445 | 96.13% | 1 | -1188180 | 37690 | 29 | 22 | 0 | 0 | 48793 | 0 | 0 | 0 | 38749 | 2893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66399 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158063 | 2893 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2016-09-12 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 408 | 15839218.13 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4402 | 42973715201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 540 | 577 | 542 | 93.52% | 1 | 35 | 0 | 0 | 37 | 0 | 2824000 | 50000 | 2774000 | 2824000 | 2773850 | 0 | 0 | 0 | 2773850 | 2779467 | 100.2% | 1 | 5617 | 0 | 15 | 22 | 0 | 0 | 8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8687 | 0 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 408 | 3519184.32 | B0 | ACC - LUMP SUM
| 04 | T4411 | 43472615201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 245 | 261 | 254 | 97.14% | 1 | 7 | 0 | 0 | 16 | 0 | 1298981 | 50000 | 1248981 | 1298981 | 1226359 | 0 | 0 | 0 | 1226359 | 1217254 | 97.46% | 1 | -9105 | 0 | 12 | 4 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31566 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-11-01 | QTR2 | 16/17 |  | 2016-09-22 | QTR1 | 16/17 | 412 | 1277354.98
| 04 | T4415 | 43472315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 198 | 219 | 219 | 101.5% | 1 | 0 | 0 | 0 | 21 | 0 | 1247191 | 50000 | 1197191 | 1247191 | 1236940 | 0 | 0 | 0 | 1236940 | 1236940 | 103.3% | 1 | 0 | 0 | 16 | 2 | 0 | 0 | 4774 | 0 | 0 | 0 | 9270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14044 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-08-24 | QTR1 | 16/17 | 409 | 1184118.51
| 04 | T4416 | 43171715201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 238 | 268 | 261 | 97.48% | 1 | 7 | 0 | 0 | 30 | 0 | 1444863 | 50000 | 1394863 | 1444863 | 1398240 | 0 | 0 | 0 | 1398240 | 1398240 | 100.2% | 1 | 0 | 0 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 412 | 1613353.82
| 04 | T4417 | 43400715201 | 2015-05-20 | QTR4 | 14/15 | 1 | 1 | 254 | 270 | 261 | 96.46% | 1 | 9 | 0 | 0 | 16 | 0 | 590398 | 35018 | 555379 | 600523 | 561695 | 0 | 0 | 0 | 561695 | 561695 | 101.1% | 1 | 0 | 10125 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-11-15 | QTR2 | 16/17 |  | 2016-09-27 | QTR1 | 16/17 | 409 | 743747.84
| 04 | T4426 | 43060815201 | 2016-02-24 | QTR3 | 15/16 | 2 | 0 | 102 | 161 | 161 | 117.6% | 1 | 0 | 0 | 0 | 59 | 0 | 1295575 | 50000 | 1245575 | 1295575 | 1275925 | 0 | 0 | 0 | 1275925 | 1275925 | 102.4% | 1 | 0 | 0 | 35 | 6 | 18 | 0 | 15716 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18401 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-19 | QTR2 | 16/17 | 409 | 1142628.19 | B0 | ACC - LUMP SUM
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 8 | 11 | 11 | 3001 | 3453 | 3225 | 100% | 8 | 228 | 0 | 0 | 421 | 31 | 31008831 | 508376 | 30500454 | 31297836 | 30611487 | 0 | 630700 | 630700 | 31242187 | 29763351 | 100% | 8 | -1478836 | 289005 | 243 | 113 | 18 | 31 | 247742 | 0 | 4 | 0 | 168796 | 53826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144179 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 31 | 569676 | 53826
| 04 | E4P79 | 42593515201 | 2014-04-23 | QTR4 | 13/14 | 2 | 2 | 313 | 441 | 441 | 119.5% | 1 | 0 | 0 | 0 | 67 | 61 | 7765532 | 74876 | 7690656 | 7903357 | 8161146 | 0 | 321600 | 321600 | 8482746 | 8149687 | 106% | 1 | -333059 | 137826 | 53 | 14 | 0 | 20 | 14059 | 0 | 0 | 30 | 137826 | 0 | 0 | 11 | 3260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 155145 | 0 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 |  | 2016-03-20 | QTR3 | 15/16 | 412 | 7456671.91 | B3:B5 | ACC - LANE RENTAL:ACC - INCENTIVE/DISINCENTIVE
| 04 | E4P94 | 43368845201 | 2014-05-02 | QTR4 | 13/14 | 1 | 8 | 506 | 648 | 514 | 93.87% | 1 | 134 | 0 | 0 | 40 | 102 | 11791416 | 121557 | 11669859 | 13321296 | 13475252 | 0 | 470000 | 470000 | 13945252 | 13368481 | 114.6% | 0 | -576771 | 1529880 | 25 | 14 | 0 | 102 | 23355 | 0 | 0 | 0 | 1681280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74534 | 0 | 0 | 102 | 1637852 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 |  | 2015-12-23 | QTR2 | 15/16 | 412 | 12152859.28 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 04 | E4P98 | 42605315201 | 2015-02-06 | QTR3 | 14/15 | 2 | 2 | 238 | 283 | 280 | 104.6% | 1 | 3 | 0 | 0 | 45 | 0 | 1670723 | 50000 | 1620723 | 1694884 | 1701995 | 0 | 0 | 0 | 1701995 | 1694894 | 104.6% | 1 | -7101 | 24162 | 17 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 9687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43444 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-02-26 | QTR3 | 15/16 | 409 | 1844040.91
| 04 | E4Q22 | 42990515201 | 2014-12-19 | QTR2 | 14/15 | 1 | 4 | 224 | 359 | 356 | 118.8% | 1 | 3 | 0 | 0 | 135 | 0 | 5750000 | 65756 | 5684244 | 6072503 | 6142459 | 0 | 0 | 0 | 6142459 | 6141649 | 108% | 1 | -810 | 322503 | 75 | 15 | 0 | 0 | 13481 | 0 | 45 | 0 | 372908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 386389 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-09-30 | QTR1 | 16/17 | 412 | 6522411.23 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4Q70 | 43056615201 | 2015-04-03 | QTR4 | 14/15 | 1 | 0 | 86 | 99 | 99 | 100% | 1 | 0 | 0 | 0 | 13 | 0 | 594927 | 36890 | 558037 | 594927 | 563713 | 0 | 0 | 0 | 563713 | 563713 | 101% | 1 | 0 | 0 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-07-08 | QTR1 | 16/17 | 412 | 789528.37
| 04 | E4R08 | 43115215201 | 2015-05-20 | QTR4 | 14/15 | 1 | 1 | 315 | 350 | 313 | 88.25% | 1 | 37 | 0 | 0 | 35 | 0 | 1435007 | 50000 | 1385007 | 1449407 | 1163642 | 0 | 0 | 0 | 1163642 | 1155244 | 83.41% | 1 | -8398 | 14400 | 23 | 12 | 0 | 0 | 3143 | 0 | 0 | 0 | 29620 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33038 | 0 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 408 | 1565107.46
| 04 | E4R65 | 43538615201 | 2016-01-08 | QTR3 | 15/16 | 2 | 0 | 65 | 92 | 91 | 106.2% | 1 | 1 | 0 | 0 | 23 | 4 | 593859 | 24145 | 569714 | 593859 | 535917 | 0 | 0 | 0 | 535917 | 535917 | 94.07% | 1 | 0 | 0 | 18 | 4 | 0 | 4 | 8796 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9546 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 409 | 495318.22
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 7 | 10 | 17 | 1747 | 2272 | 2094 | 100% | 7 | 178 | 0 | 0 | 358 | 167 | 29601464 | 423224 | 29178240 | 31630233 | 31744124 | 0 | 791600 | 791600 | 32535724 | 31609585 | 85.71% | 6 | -926139 | 2028771 | 222 | 75 | 0 | 126 | 62834 | 0 | 45 | 30 | 2232071 | 0 | 0 | 11 | 3535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74534 | 0 | 45 | 167 | 2265414 | 0
| District 04 Totals |  |  |  |  | 15 | 21 | 28 | 4748 | 5725 | 5319 | 100% | 15 | 406 | 0 | 0 | 779 | 198 | 60610295 | 931600 | 59678694 | 62928069 | 62355611 | 0 | 1422300 | 1422300 | 63777911 | 61372936 | 93.33% | 14 | -2404975 | 2317776 | 465 | 188 | 18 | 157 | 310576 | 0 | 49 | 30 | 2400867 | 53826 | 0 | 11 | 3535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185686 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74534 | 0 | 106 | 198 | 2835090 | 53826
| 05 | T5415 | 40735535201 | 2012-05-23 | QTR4 | 11/12 | 6 | 19 | 1100 | 1340 | 1359 | 106% | 1 | -19 | 19 | 0 | 215 | 25 | 32798973 | 150000 | 32648973 | 35176946 | 35231745 | -161575 | 0 | -161575 | 35070170 | 34680971 | 106.2% | 1 | -389199 | 2796919 | 109 | 84 | 0 | 25 | 751698 | 18086 | 0 | 4 | 2213568 | 1011571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57075 | 0 | 0 | 29 | 2908901 | 1029658 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2016-11-18 | QTR2 | 16/17 |  | 2016-06-20 | QTR4 | 15/16 | 513 | 37106689.63
| 05 | T5496 | 43106615201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 460 | 684 | 678 | 97.61% | 1 | 6 | 0 | 0 | 224 | 0 | 4198661 | 57000 | 4141661 | 4198661 | 4290920 | 0 | 0 | 0 | 4290920 | 4280333 | 103.3% | 1 | -10587 | 0 | 199 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 514 | 5833243.5
| 05 | T5497 | 43113915201 | 2014-06-18 | QTR4 | 13/14 | 4 | 2 | 350 | 479 | 448 | 99.71% | 1 | 31 | 0 | 0 | 99 | 30 | 5577400 | 50000 | 5527400 | 5630674 | 5316503 | 0 | 0 | 0 | 5316503 | 5110931 | 92.47% | 1 | -205572 | 53274 | 72 | 27 | 0 | 0 | 16219 | 0 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 62720 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-13 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 514 | 5261131.52 | B0:B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 05 | T5504 | 43326915201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 340 | 414 | 410 | 98.82% | 1 | 4 | 0 | 0 | 74 | 0 | 2791824 | 50000 | 2741824 | 2791824 | 2764770 | 0 | 0 | 0 | 2764770 | 2763716 | 100.8% | 1 | -1054 | 0 | 53 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 |  | 2016-09-09 | QTR1 | 16/17 | 514 | 3681477
| 05 | T5507 | 42908315201 | 2014-10-29 | QTR2 | 14/15 | 2 | 3 | 352 | 458 | 457 | 105.7% | 1 | 1 | 0 | 0 | 85 | 21 | 13950000 | 132000 | 13818000 | 14304220 | 14416417 | 0 | 0 | 0 | 14416417 | 13245104 | 95.85% | 1 | -1171314 | 354220 | 70 | 15 | 0 | 0 | 36422 | 0 | 0 | 0 | 46490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 308750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 391661 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 512 | 13411584.34
| 05 | T5515 | 43066815201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 210 | 284 | 284 | 115.2% | 1 | 0 | 0 | 0 | 44 | 30 | 1884019 | 50000 | 1834019 | 1929335 | 1919435 | 0 | 0 | 0 | 1919435 | 1870656 | 102% | 1 | -48780 | 45316 | 30 | 12 | 0 | 24 | 59005 | 0 | 0 | 6 | 21372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 80377 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2016-05-05 | QTR4 | 15/16 | 514 | 1716624.23 | B0 | ACC - LUMP SUM
| 05 | T5519 | 43066615201 | 2015-07-29 | QTR1 | 15/16 | 2 | 0 | 280 | 323 | 260 | 77.5% | 1 | 63 | 0 | 0 | 43 | 0 | 2698908 | 50000 | 2648908 | 2698908 | 2560594 | 0 | 0 | 0 | 2560594 | 2513289 | 94.88% | 1 | -47305 | 0 | 32 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 3735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11651 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 514 | 2488176
| 05 | T5524 | 43065215201 | 2015-03-25 | QTR3 | 14/15 | 1 | 3 | 270 | 391 | 390 | 132.6% | 0 | 1 | 0 | 0 | 34 | 87 | 4938000 | 50000 | 4888000 | 5043475 | 4946856 | 0 | 0 | 0 | 4946856 | 4688330 | 95.92% | 1 | -258527 | 105475 | 16 | 16 | 0 | 0 | 3176 | 0 | 0 | 36 | 84688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 17106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 104970 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 515 | 4676396.93
| 05 | T5528 | 43066915201 | 2015-05-27 | QTR4 | 14/15 | 1 | 1 | 200 | 245 | 224 | 90.5% | 1 | 21 | 0 | 0 | 45 | 0 | 2181000 | 50000 | 2131000 | 2446253 | 2396253 | 0 | 0 | 0 | 2396253 | 2380075 | 111.7% | 0 | -16178 | 265253 | 19 | 24 | 0 | 0 | 145670 | 0 | 0 | 0 | 119583 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265253 | 508 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-07-01 | QTR1 | 16/17 |  | 2016-04-06 | QTR4 | 15/16 | 507 | 1883279.22
| 05 | T5536 | 43067715201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 216 | 247 | 233 | 93.52% | 1 | 14 | 0 | 0 | 31 | 0 | 2584884 | 50000 | 2534884 | 2614884 | 2636650 | 0 | 0 | 0 | 2636650 | 2540033 | 100.2% | 1 | -96617 | 30000 | 12 | 19 | 0 | 0 | 15490 | 0 | 0 | 0 | 58864 | 13921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74355 | 13921 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-07-22 | QTR1 | 16/17 | 513 | 2795913.94
| 05 | T5537 | 43244215201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 110 | 154 | 147 | 111.8% | 1 | 7 | 0 | 0 | 24 | 20 | 1272760 | 42000 | 1230760 | 1272760 | 1267646 | 0 | 0 | 0 | 1267646 | 1267646 | 103% | 1 | 0 | 0 | 9 | 15 | 0 | 0 | 615 | 0 | 0 | 20 | 34326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 34941 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-06-10 | QTR4 | 15/16 | 513 | 919590 | B0 | ACC - LUMP SUM
| 05 | T5540 | 43544615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 310 | 321 | 320 | 99.68% | 1 | 1 | 0 | 0 | 11 | 0 | 2108960 | 50000 | 2058960 | 2108960 | 2062184 | 0 | 0 | 0 | 2062184 | 2062184 | 100.2% | 1 | 0 | 0 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-12-13 | QTR2 | 16/17 |  | 2016-09-29 | QTR1 | 16/17 | 509 | 2665356.75
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 12 | 23 | 31 | 4198 | 5340 | 5210 | 91.67% | 11 | 130 | 19 | 0 | 929 | 213 | 76985389 | 781000 | 76204389 | 80216900 | 79809973 | -161575 | 0 | -161575 | 79648398 | 77403268 | 91.67% | 11 | -2245133 | 3650457 | 625 | 281 | 0 | 49 | 1028295 | 18086 | 0 | 66 | 2587926 | 1026000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 334482 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57075 | 0 | 0 | 217 | 3934829 | 1044087
| 05 | E5W67 | 43198915201 | 2014-10-07 | QTR2 | 14/15 | 1 | 2 | 300 | 340 | 393 | 126.7% | 0 | -53 | 53 | 0 | 13 | 27 | 2340785 | 50000 | 2290785 | 2247902 | 2197902 | -92326 | 0 | -92326 | 2105576 | 2104471 | 91.87% | 1 | -1105 | -92883 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | -92883 | 0 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-02-10 | QTR3 | 15/16 | 509 | 2486510
| 05 | E5W83 | 43528215201 | 2015-04-07 | QTR4 | 14/15 | 1 | 0 | 240 | 265 | 264 | 99.58% | 1 | 1 | 0 | 0 | 25 | 0 | 2750721 | 50000 | 2700721 | 2750721 | 2676098 | 0 | 0 | 0 | 2676098 | 2676025 | 99.09% | 1 | -73 | 0 | 7 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-07-20 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 513 | 2985731
| 05 | E5W86 | 43488315201 | 2015-06-04 | QTR4 | 14/15 | 1 | 1 | 120 | 131 | 131 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 584110 | 29000 | 555110 | 585291 | 580591 | 0 | 0 | 0 | 580591 | 580591 | 104.6% | 1 | 0 | 1181 | 1 | 10 | 0 | 0 | 478 | 0 | 0 | 0 | 4195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4673 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-11-28 | QTR2 | 16/17 |  | 2016-07-22 | QTR1 | 16/17 | 513 | 623548.95
| 05 | E5Y02 | 43705815201 | 2015-09-01 | QTR1 | 15/16 | 1 | 0 | 130 | 134 | 107 | 79.23% | 1 | 27 | 0 | 0 | 4 | 0 | 783941 | 39000 | 744941 | 783941 | 744941 | 0 | 0 | 0 | 744941 | 744941 | 100% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-08-09 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 515 | 821518.11
| 05 | E5Y03 | 43116415201 | 2016-02-02 | QTR3 | 15/16 | 1 | 0 | 65 | 88 | 83 | 123.1% | 0 | 5 | 0 | 0 | 23 | 0 | 63940 | 5000 | 58940 | 63940 | 58289 | 0 | 0 | 0 | 58289 | 58289 | 98.9% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2016-12-23 | QTR2 | 16/17 |  | 2016-10-20 | QTR2 | 16/17 | 514 | 123170
| 05 | E5Y04 | 43705715201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 210 | 220 | 220 | 100% | 1 | 0 | 0 | 0 | 10 | 0 | 679709 | 43000 | 636709 | 679709 | 640622 | 0 | 0 | 0 | 640622 | 640622 | 100.6% | 1 | 0 | 0 | 9 | 1 | 0 | 0 | 4403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4403 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-12-30 | QTR2 | 16/17 |  | 2016-10-13 | QTR2 | 16/17 | 514 | 911255.5
| 05 | E5Y05 | 43465915201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 100 | 110 | 109 | 104% | 1 | 1 | 0 | 0 | 10 | 0 | 448115 | 19000 | 429115 | 448115 | 434061 | 0 | 0 | 0 | 434061 | 434061 | 101.2% | 1 | 0 | 0 | 3 | 2 | 0 | 0 | 4946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4946 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-10-04 | QTR2 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 514 | 409595.51
| 05 | E5Y18 | 23800235225 | 2016-02-02 | QTR3 | 15/16 | 1 | 1 | 160 | 165 | 148 | 89.38% | 1 | 17 | 0 | 0 | 5 | 0 | 788000 | 33000 | 755000 | 805272 | 758781 | 0 | 0 | 0 | 758781 | 759356 | 100.6% | 1 | 575 | 17272 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 17272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17272 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 |  | 2016-09-26 | QTR1 | 16/17 | 513 | 717565.65
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 8 | 8 | 4 | 1325 | 1453 | 1455 | 75% | 6 | -2 | 53 | 0 | 101 | 27 | 8439321 | 268000 | 8171321 | 8364891 | 8091285 | -92326 | 0 | -92326 | 7998959 | 7998356 | 100% | 8 | -603 | -74430 | 30 | 46 | 0 | 0 | 9827 | 0 | 0 | 27 | 21467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | -61589 | 0
| District 05 Totals |  |  |  |  | 20 | 31 | 35 | 5523 | 6793 | 6665 | 85% | 17 | 128 | 72 | 0 | 1030 | 240 | 85424710 | 1049000 | 84375710 | 88581791 | 87901258 | -253901 | 0 | -253901 | 87647357 | 85401624 | 95% | 19 | -2245736 | 3576027 | 655 | 327 | 0 | 49 | 1038122 | 18086 | 0 | 93 | 2609393 | 1026000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 241599 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57075 | 0 | 0 | 244 | 3873240 | 1044087
| 06 | T6127 | 25118515201 | 2011-09-07 | QTR1 | 11/12 | 3 | 18 | 1250 | 1524 | 1524 | 100% | 1 | 0 | 0 | 0 | 274 | 0 | 58542945 | 268019 | 58274926 | 59378958 | 60313959 | 0 | 0 | 0 | 60313959 | 59721395 | 102.5% | 1 | -592564 | 836013 | 200 | 74 | 0 | 0 | 1336258 | 17957 | 0 | 0 | 533489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -761248 | 0 | 0 | 0 | 1060088 | 17957 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-08-12 | QTR1 | 16/17 | 606 | 67023598.5
| 06 | T6320 | 42914015201 | 2014-06-18 | QTR4 | 13/14 | 3 | 3 | 450 | 503 | 387 | 74.22% | 1 | 116 | 0 | 0 | 53 | 0 | 14295524 | 150000 | 14145524 | 14692214 | 13690377 | 0 | 245000 | 245000 | 13935377 | 13056864 | 92.3% | 1 | -878513 | 396690 | 43 | 10 | 0 | 0 | 18351 | 0 | 0 | 0 | 421570 | 152744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447735 | 152744 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 606 | 15289319.55 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6325 | 25055425201 | 2012-10-31 | QTR2 | 12/13 | 1 | 3 | 700 | 903 | 870 | 96.43% | 1 | 33 | 0 | 0 | 197 | 6 | 11430054 | 123500 | 11306554 | 11749528 | 11929942 | 0 | 0 | 0 | 11929942 | 11924070 | 105.5% | 1 | -5871 | 319473 | 154 | 41 | 2 | 0 | 266319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 63468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 370763 | 0 | F410827177 | JOHNSON BROS. CORPORATION | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 606 | 12087502
| 06 | T6365 | 43274315201 | 2015-08-26 | QTR1 | 15/16 | 2 | 3 | 180 | 208 | 206 | 98.89% | 1 | 2 | 0 | 0 | 28 | 0 | 3849469 | 50000 | 3799469 | 3927103 | 3942847 | 0 | 0 | 0 | 3942847 | 3837692 | 101% | 1 | -105154 | 77634 | 24 | 4 | 0 | 0 | 1963 | 0 | 0 | 0 | 73400 | 3297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4426 | 0 | 0 | 0 | 20491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91428 | 3297 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-08-02 | QTR1 | 16/17 | 606 | 4708187.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6371 | 42913415201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 180 | 212 | 212 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 1483369 | 50000 | 1433369 | 1483369 | 1429074 | 0 | 0 | 0 | 1429074 | 1425704 | 99.47% | 1 | -3370 | 0 | 29 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 35508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42642 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-11-10 | QTR2 | 16/17 |  | 2016-08-09 | QTR1 | 16/17 | 606 | 1435507.6
| 06 | T6373 | 43080915201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 230 | 328 | 326 | 112.6% | 1 | 2 | 0 | 0 | 98 | 0 | 2376742 | 50130 | 2326612 | 2426742 | 2460615 | 0 | 0 | 0 | 2460615 | 2384892 | 102.5% | 1 | -75723 | 50000 | 56 | 11 | 31 | 0 | 16266 | 0 | 0 | 0 | 14872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 71617 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-12 | QTR4 | 15/16 | 606 | 2292101.6
| 06 | T6374 | 43118015201 | 2015-03-25 | QTR3 | 14/15 | 6 | 4 | 210 | 310 | 308 | 118.6% | 1 | 2 | 0 | 0 | 100 | 0 | 5144045 | 52640 | 5091405 | 5317082 | 5198829 | 0 | 0 | 0 | 5198829 | 5112224 | 100.4% | 1 | -86605 | 173037 | 47 | 12 | 29 | 0 | 30730 | 0 | 0 | 0 | 7365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 148657 | 104434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 186752 | 104434 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-02 | QTR2 | 16/17 |  | 2016-07-03 | QTR1 | 16/17 | 606 | 4599362.55
| 06 | T6376 | 43081715201 | 2015-02-25 | QTR3 | 14/15 | 2 | 4 | 435 | 468 | 375 | 78.62% | 1 | 93 | 0 | 0 | 33 | 0 | 6621887 | 69750 | 6552137 | 6805679 | 6261293 | 0 | 470000 | 470000 | 6731293 | 6082074 | 92.83% | 1 | -649219 | 183793 | 21 | 12 | 0 | 0 | 71716 | 0 | 0 | 0 | 115147 | 9450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186863 | 9450 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-27 | QTR1 | 16/17 |  | 2016-05-08 | QTR4 | 15/16 | 606 | 6429680.27 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6384 | 43350815201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 439934 | 26680 | 413254 | 439934 | 417205 | 0 | 0 | 0 | 417205 | 417205 | 101% | 1 | 0 | 0 | 16 | 1 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 606 | 559680 | B0 | ACC - LUMP SUM
| 06 | T6389 | 43481015201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 80 | 96 | 93 | 96.25% | 1 | 3 | 0 | 0 | 16 | 0 | 147742 | 8768 | 138974 | 147742 | 141841 | 0 | 0 | 0 | 141841 | 141841 | 102.1% | 1 | 0 | 0 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | F273954210 | PE-SERVICES L.L.C. | N/A | N/A | N/A | N/A | 2016-11-02 | QTR2 | 16/17 |  | 2016-10-05 | QTR2 | 16/17 | 606 | 180124 | B0 | ACC - LUMP SUM
| 06 | T6394 | 24961575201 | 2015-04-29 | QTR4 | 14/15 | 2 | 1 | 435 | 469 | 395 | 82.99% | 1 | 74 | 0 | 0 | 34 | 0 | 18918175 | 150000 | 18768175 | 18918175 | 18379697 | 0 | 740000 | 740000 | 19119697 | 17983880 | 95.82% | 1 | -1135817 | 0 | 21 | 13 | 0 | 0 | 2262 | 0 | 0 | 0 | 34785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52061 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-11-08 | QTR2 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 606 | 23196102.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 11 | 25 | 37 | 4270 | 5158 | 4833 | 100% | 11 | 325 | 0 | 0 | 882 | 6 | 123249886 | 999487 | 122250399 | 125286526 | 124165679 | 0 | 1455000 | 1455000 | 125620679 | 122087841 | 100% | 11 | -3532836 | 2036640 | 626 | 182 | 62 | 0 | 1749865 | 17957 | 0 | 0 | 1239003 | 165491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 197454 | 104434 | 0 | 0 | 20491 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 73250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -761248 | 0 | 74 | 6 | 2518816 | 287882
| 06 | E6H77 | 41806525201 | 2013-07-16 | QTR1 | 13/14 | 4 | 8 | 381 | 718 | 718 | 150.7% | 0 | 0 | 0 | 0 | 144 | 193 | 6865432 | 95551 | 6769881 | 8047242 | 8106870 | 0 | 525000 | 525000 | 8631870 | 8012338 | 118.4% | 0 | -619532 | 1181810 | 121 | 23 | 0 | 193 | 589219 | 0 | 0 | 0 | 643866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 1240647 | 0 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2016-11-21 | QTR2 | 16/17 |  | 2016-02-25 | QTR3 | 15/16 | 606 | 9650622.75 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 06 | E6I89 | 43117815201 | 2014-10-30 | QTR2 | 14/15 | 2 | 1 | 220 | 378 | 378 | 119.1% | 1 | 0 | 0 | 0 | 158 | 0 | 2097039 | 50575 | 2046464 | 2147039 | 2148203 | 0 | 0 | 0 | 2148203 | 2008021 | 98.12% | 1 | -140182 | 50000 | 100 | 16 | 42 | 0 | 57755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 63544 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2016-10-05 | QTR2 | 16/17 |  | 2016-05-29 | QTR4 | 15/16 | 606 | 2334024.25
| 06 | E6I91 | 42918715201 | 2015-06-11 | QTR4 | 14/15 | 2 | 0 | 150 | 180 | 179 | 105.3% | 1 | 1 | 0 | 0 | 30 | 0 | 1483128 | 50420 | 1432708 | 1483128 | 1441455 | 0 | 0 | 0 | 1441455 | 1430102 | 99.82% | 1 | -11353 | 0 | 14 | 7 | 0 | 0 | 2145 | 0 | 0 | 0 | 772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 2917 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 |  | 2016-09-23 | QTR1 | 16/17 | 606 | 1376235.85
| 06 | E6I98 | 43493065201 | 2016-03-31 | QTR3 | 15/16 | 1 | 1 | 90 | 106 | 106 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 969000 | 50000 | 919000 | 903732 | 873748 | 0 | 0 | 0 | 873748 | 873360 | 95.03% | 1 | -388 | -65268 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65268 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-10-25 | QTR2 | 16/17 |  | 2016-10-02 | QTR2 | 16/17 | 606 | 1134223.3 | B0 | ACC - LUMP SUM
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 4 | 9 | 10 | 841 | 1382 | 1381 | 75% | 3 | 1 | 0 | 0 | 348 | 193 | 11414599 | 246546 | 11168053 | 12581141 | 12570276 | 0 | 525000 | 525000 | 13095276 | 12323821 | 75% | 3 | -771455 | 1166542 | 249 | 48 | 42 | 193 | 649119 | 0 | 0 | 0 | 644638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7561 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 193 | 1241840 | 0
| District 06 Totals |  |  |  |  | 15 | 34 | 47 | 5111 | 6540 | 6214 | 93.33% | 14 | 326 | 0 | 0 | 1230 | 199 | 134664485 | 1246033 | 133418452 | 137867667 | 136735955 | 0 | 1980000 | 1980000 | 138715955 | 134411662 | 93.33% | 14 | -4304291 | 3203182 | 875 | 230 | 104 | 193 | 2398984 | 17957 | 0 | 0 | 1883641 | 165491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 137976 | 104434 | 0 | 0 | 20491 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 80811 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -761248 | 0 | 125 | 199 | 3760656 | 287882
| 07 | T7209 | 25841515201 | 2009-09-16 | QTR1 | 09/10 | 7 | 55 | 1065 | 1694 | 1694 | 151% | 0 | 0 | 0 | 0 | 109 | 520 | 389463750 | 75000 | 389388750 | 430319761 | 437468272 | 0 | 0 | 0 | 437468272 | 439424048 | 112.8% | 0 | 1955776 | 40856011 | 52 | 34 | 22 | 67 | 10225188 | 4993195 | 1 | 121 | 13703270 | 4748092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 6407054 | 1636245 | 0 | 0 | 10009318 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 173923 | 100951 | 0 | 0 | 210466 | 210466 | 0 | 0 | 3584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 520 | 40732802 | 11688949 | F263258515 | PCL/ARCHER WESTERN A JOINT VEN | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2014-10-19 | QTR2 | 14/15 | 714 | 412328910.33 | ARRA:B2:B5:P:B2 | AMERICAN RECOVERY AND REINVEST:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:PUBLIC PRIVATE PARTNERSHIP:ACC - A+B (COST+TIME BIDDING)
| 07 | T7236 | 25589325201 | 2011-09-28 | QTR1 | 11/12 | 2 | 7 | 410 | 560 | 740 | 148.5% | 0 | -180 | 180 | 0 | 131 | 19 | 7147510 | 74000 | 7073510 | 7510715 | 7761739 | -452520 | 0 | -452520 | 7309219 | 7308427 | 103.3% | 1 | -793 | 363205 | 107 | 24 | 0 | 15 | 337971 | 0 | 0 | 4 | 38132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 372176 | 0 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2016-08-10 | QTR1 | 16/17 |  | 2014-06-13 | QTR4 | 13/14 | 717 | 8423805.36
| 07 | T7305 | 41886065201 | 2012-06-20 | QTR4 | 11/12 | 8 | 18 | 740 | 1035 | 1035 | 110% | 1 | 0 | 0 | 0 | 221 | 74 | 27994444 | 135000 | 27859444 | 28571829 | 28922186 | -13000 | 200000 | 187000 | 29109186 | 28487362 | 102.3% | 1 | -621825 | 577385 | 184 | 37 | 0 | 1 | 153865 | 37343 | 0 | 61 | 494365 | 110210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9379 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -1161 | 12265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 637690 | 167258 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 |  | 2015-08-15 | QTR1 | 15/16 | 714 | 26994097.12 | B1 | ACC - NO EXCUSE BONUS
| 07 | T7309 | 25714715201 | 2012-09-26 | QTR1 | 12/13 | 5 | 11 | 1000 | 1141 | 1121 | 98% | 1 | 20 | 0 | 0 | 141 | 0 | 20511016 | 150000 | 20361016 | 21458828 | 20369299 | 0 | 0 | 0 | 20369299 | 20020139 | 98.33% | 1 | -349160 | 947812 | 105 | 36 | 0 | 0 | 754859 | 16651 | 0 | 0 | 284869 | 162142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1086056 | 178793 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-04-25 | QTR4 | 15/16 | 714 | 20045000
| 07 | T7311 | 25579315201 | 2013-05-31 | QTR4 | 12/13 | 3 | 15 | 800 | 990 | 976 | 108.6% | 1 | 14 | 0 | 0 | 147 | 43 | 21435705 | 150000 | 21285705 | 23015417 | 23090810 | -8000 | 0 | -8000 | 23082810 | 22674547 | 106.5% | 1 | -408263 | 1579712 | 74 | 33 | 0 | 37 | 367652 | 256110 | 40 | 0 | 1071146 | 402006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 172463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77446 | 4419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 43 | 1688706 | 662534 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-10-27 | QTR2 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 714 | 21961489.64
| 07 | T7348 | 42907415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 495 | 613 | 579 | 93.13% | 1 | 34 | 0 | 0 | 118 | 0 | 13220362 | 110000 | 13110362 | 13351863 | 13162187 | 0 | 0 | 0 | 13162187 | 12814384 | 97.74% | 1 | -347802 | 131501 | 69 | 49 | 0 | 0 | 10426 | 0 | 0 | 0 | 164259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174685 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 |  | 2016-06-02 | QTR4 | 15/16 | 717 | 12277372.35
| 07 | T7356 | 42905815201 | 2014-12-03 | QTR2 | 14/15 | 1 | 3 | 240 | 337 | 337 | 100% | 1 | 0 | 0 | 0 | 97 | 0 | 6377897 | 60000 | 6317897 | 6518755 | 6488848 | 0 | 0 | 0 | 6488848 | 6241174 | 98.79% | 1 | -247674 | 140858 | 77 | 20 | 0 | 0 | 54833 | 0 | 0 | 0 | 43775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32045 | 0 | 0 | 0 | 4717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143613 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-02-15 | QTR3 | 15/16 | 709 | 6176900
| 07 | T7362 | 42907725202 | 2015-03-25 | QTR3 | 14/15 | 2 | 0 | 180 | 256 | 256 | 100% | 1 | 0 | 0 | 0 | 76 | 0 | 5709404 | 50000 | 5659404 | 5709404 | 5625130 | 0 | 0 | 0 | 5625130 | 5464793 | 96.56% | 1 | -160337 | 0 | 57 | 19 | 0 | 0 | 8822 | 0 | 0 | 0 | 10150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-08-19 | QTR1 | 16/17 |  | 2016-05-16 | QTR4 | 15/16 | 717 | 5660000
| 07 | T7364 | 43311115201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 115 | 141 | 141 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 1656000 | 50000 | 1606000 | 1660046 | 1621270 | 0 | 0 | 0 | 1621270 | 1621270 | 101% | 1 | 0 | 4046 | 14 | 12 | 0 | 0 | 8843 | 0 | 0 | 0 | 6427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15270 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-02-08 | QTR3 | 15/16 | 709 | 1539800 | B0 | ACC - LUMP SUM
| 07 | T7366 | 43113215201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 150 | 211 | 210 | 99.33% | 1 | 1 | 0 | 0 | 61 | 0 | 1795000 | 50000 | 1745000 | 1795000 | 1754140 | 0 | 0 | 0 | 1754140 | 1746653 | 100.1% | 1 | -7487 | 0 | 41 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-19 | QTR1 | 16/17 |  | 2016-03-18 | QTR3 | 15/16 | 717 | 1415000 | B0 | ACC - LUMP SUM
| 07 | T7367 | 42907615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 4 | 250 | 355 | 355 | 105.6% | 1 | 0 | 0 | 0 | 91 | 14 | 3822222 | 50000 | 3772222 | 3834124 | 3855324 | 0 | 0 | 0 | 3855324 | 3731807 | 98.93% | 1 | -123517 | 11902 | 61 | 30 | 0 | 0 | 44654 | 0 | 0 | 14 | 59289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82752 | 0 | 0 | 14 | 24270 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-11-15 | QTR2 | 16/17 |  | 2016-05-27 | QTR4 | 15/16 | 798 | 4100000
| 07 | T7370 | 43251915201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 150 | 240 | 240 | 100% | 1 | 0 | 0 | 0 | 90 | 0 | 3088818 | 50000 | 3038818 | 3088818 | 2944540 | 0 | 0 | 0 | 2944540 | 2940006 | 96.75% | 1 | -4534 | 0 | 44 | 46 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-03 | QTR2 | 16/17 |  | 2016-06-22 | QTR4 | 15/16 | 709 | 3068000
| 07 | T7374 | 43257915201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 124 | 139 | 110 | 76.61% | 1 | 29 | 0 | 0 | 15 | 0 | 3581528 | 50000 | 3531528 | 3581528 | 3666189 | 0 | 220000 | 220000 | 3886189 | 3671670 | 104% | 1 | -214519 | 0 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-09 | QTR2 | 16/17 |  | 2016-08-18 | QTR1 | 16/17 | 717 | 2950000 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 13 | 35 | 116 | 5719 | 7712 | 7794 | 84.62% | 11 | -82 | 180 | 0 | 1323 | 670 | 505803656 | 1054000 | 504749656 | 550416088 | 556729934 | -473520 | 420000 | -53520 | 556676414 | 556146280 | 92.31% | 12 | -530135 | 44612432 | 894 | 366 | 22 | 120 | 11967993 | 5303299 | 41 | 200 | 15875682 | 5422450 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 6599628 | 1643685 | 0 | 0 | 10017115 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 251369 | 105370 | 0 | 0 | 210466 | 210466 | 0 | 10 | 66975 | 12265 | 0 | 0 | 0 | 0 | 0 | 0 | -82752 | 0 | 63 | 670 | 44902548 | 12697534
| 07 | E7F75 | 25839855201 | 2012-05-08 | QTR4 | 11/12 | 2 | 30 | 1445 | 1568 | 1429 | 90.38% | 1 | 139 | 0 | 0 | 123 | 0 | 215400000 | 150000 | 215250000 | 224435209 | 224895976 | 0 | 1650000 | 1650000 | 226545976 | 223875000 | 104% | 1 | -2670976 | 9035209 | 88 | 35 | 0 | 0 | 2771364 | 13903 | 0 | 0 | 5245266 | 459975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22798 | 0 | 0 | 0 | 1015841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9055269 | 473878 | F453806780 | SKANSKA-AJAX PAVING JOINT VENTU | N/A | N/A | N/A | N/A | 2016-12-06 | QTR2 | 16/17 |  | 2016-06-28 | QTR4 | 15/16 | 714 | 213872600 | B11:B12:B8:B:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - DSGN BLD-MAJ/BONUS/WRNTY:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 07 | E7I34 | 41101135201 | 2014-01-23 | QTR3 | 13/14 | 1 | 3 | 750 | 874 | 871 | 99.6% | 1 | 3 | 0 | 0 | 124 | 0 | 35188969 | 150000 | 35038969 | 35441051 | 35414850 | 0 | 0 | 0 | 35414850 | 34061551 | 97.21% | 1 | -1353299 | 252082 | 90 | 34 | 0 | 0 | 47212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31900 | 0 | 0 | 0 | 150744 | 0 | 0 | 0 | 75555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305411 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-23 | QTR2 | 16/17 |  | 2016-11-02 | QTR2 | 16/17 | 714 | 37368154.02 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7I46 | 25633925201 | 2014-08-14 | QTR1 | 14/15 | 1 | 4 | 450 | 623 | 622 | 107.8% | 1 | 1 | 0 | 0 | 137 | 36 | 15944000 | 150000 | 15794000 | 16474127 | 16294835 | 0 | 0 | 0 | 16294835 | 15360010 | 97.25% | 1 | -934824 | 530127 | 97 | 40 | 0 | 0 | 56222 | 0 | 0 | 1 | 186898 | 3530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 346909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 590029 | 3530 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-15 | QTR1 | 16/17 |  | 2016-06-25 | QTR4 | 15/16 | 714 | 18310419.41 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 07 | E7J99 | 42715515201 | 2015-04-08 | QTR4 | 14/15 | 1 | 1 | 199 | 302 | 274 | 101% | 1 | 28 | 0 | 0 | 103 | 0 | 1844400 | 50000 | 1794400 | 1881240 | 1852163 | 0 | 0 | 0 | 1852163 | 1792416 | 99.89% | 1 | -59746 | 36840 | 47 | 26 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 |  | 2016-06-28 | QTR4 | 15/16 | 798 | 1650000
| 07 | E7K02 | 43090115201 | 2015-02-11 | QTR3 | 14/15 | 1 | 3 | 125 | 176 | 176 | 109.6% | 1 | 0 | 0 | 0 | 39 | 12 | 2683100 | 50000 | 2633100 | 2806747 | 2817266 | 0 | 0 | 0 | 2817266 | 2772695 | 105.3% | 1 | -44571 | 123647 | 34 | 5 | 0 | 12 | 67604 | 15358 | 0 | 0 | 123204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17782 | 0 | 0 | 12 | 173025 | 15358 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-07 | QTR1 | 16/17 |  | 2015-11-30 | QTR2 | 15/16 | 709 | 2450000 | B0 | ACC - LUMP SUM
| 07 | E7K04 | 43066015201 | 2015-03-11 | QTR3 | 14/15 | 1 | 2 | 180 | 281 | 281 | 118.9% | 1 | 0 | 0 | 0 | 82 | 19 | 2680382 | 50000 | 2630382 | 2750471 | 2763085 | 0 | 0 | 0 | 2763085 | 2699178 | 102.6% | 1 | -63907 | 70089 | 46 | 21 | 0 | 0 | 0 | 0 | 0 | 19 | 111980 | 18119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 19 | 114701 | 18119 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-03-14 | QTR3 | 15/16 | 709 | 2007403 | B0 | ACC - LUMP SUM
| 07 | E7K05 | 43243225201 | 2015-03-11 | QTR3 | 14/15 | 1 | 0 | 220 | 262 | 261 | 99.55% | 1 | 1 | 0 | 0 | 42 | 0 | 1086230 | 50000 | 1036230 | 1086230 | 1062839 | 0 | 0 | 0 | 1062839 | 1062824 | 102.6% | 1 | -15 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2016-09-26 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 717 | 1230200
| 07 | E7K07 | 43068515201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 105 | 145 | 145 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 1119020 | 42000 | 1077020 | 1119020 | 1092543 | 0 | 0 | 0 | 1092543 | 1092543 | 101.4% | 1 | 0 | 0 | 25 | 15 | 0 | 0 | 3319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3319 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2016-10-27 | QTR2 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 717 | 885300 | B0 | ACC - LUMP SUM
| 07 | E7K17 | 43094815201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 220 | 258 | 212 | 79.09% | 1 | 46 | 0 | 0 | 38 | 0 | 2888000 | 50000 | 2838000 | 2888000 | 2727932 | 0 | 0 | 0 | 2727932 | 2634048.09 | 92.81% | 1 | -37311 | 0 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-16 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 798 | 3200000 | B0 | ACC - LUMP SUM
| 07 | E7K29 | 42550325201 | 2015-05-13 | QTR4 | 14/15 | 1 | 0 | 120 | 183 | 155 | 76.67% | 1 | 28 | 0 | 0 | 63 | 0 | 1984295 | 50000 | 1934295 | 1984295 | 1950400 | 0 | 0 | 0 | 1950400 | 1950400 | 100.8% | 1 | 0 | 0 | 32 | 31 | 0 | 0 | 13191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13191 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-10-10 | QTR2 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 717 | 1727700
| 07 | E7K67 | 43149515201 | 2015-05-13 | QTR4 | 14/15 | 1 | 4 | 140 | 178 | 178 | 107.1% | 1 | 0 | 0 | 0 | 28 | 10 | 2794895 | 50000 | 2744895 | 2964710 | 2918290 | -7200 | 0 | -7200 | 2911090 | 2905726 | 105.9% | 1 | -5363 | 169815 | 17 | 11 | 0 | 5 | 49615 | 0 | 0 | 5 | 161418 | 7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17145 | 0 | 0 | 10 | 193888 | 7074 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 717 | 1905000
| 07 | E7K68 | 43149115201 | 2015-05-13 | QTR4 | 14/15 | 2 | 1 | 200 | 298 | 294 | 112.5% | 1 | 4 | 0 | 0 | 69 | 29 | 4031039 | 50000 | 3981039 | 4044189 | 4055974 | 0 | 0 | 0 | 4055974 | 4004687 | 100.6% | 1 | -51286 | 13150 | 48 | 21 | 0 | 6 | 42639 | 3293 | 0 | 23 | 4531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59544 | 3293 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 709 | 3361350
| 07 | E7K78 | 43080235201 | 2015-09-09 | QTR1 | 15/16 | 2 | 0 | 206 | 217 | 128 | 56.8% | 1 | 89 | 0 | 0 | 11 | 0 | 1271000 | 50000 | 1221000 | 1271000 | 1221000 | 0 | 0 | 0 | 1221000 | 1221000 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-05-10 | QTR4 | 15/16 | 717 | 2206022.47 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 07 | E7K80 | 43478115201 | 2015-08-12 | QTR1 | 15/16 | 2 | 2 | 160 | 203 | 203 | 101.2% | 1 | 0 | 0 | 0 | 41 | 2 | 1052289 | 33000 | 1019289 | 1092289 | 992268 | 0 | 0 | 0 | 992268 | 991427 | 97.27% | 1 | -840 | 40000 | 21 | 20 | 0 | 0 | 7453 | 0 | 0 | 2 | 55456 | 19923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 62908 | 19923 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 717 | 752249.19
| 07 | E7K88 | 43071015201 | 2016-01-13 | QTR3 | 15/16 | 1 | 1 | 75 | 75 | 34 | 45.33% | 1 | 41 | 0 | 0 | 0 | 0 | 716889 | 28000 | 688889 | 655243 | 627243 | 0 | 0 | 0 | 627243 | 627243 | 91.05% | 1 | 0 | -61646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -61646 | 0 | 0 | 0 | -61646 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-27 | QTR2 | 16/17 |  | 2016-08-19 | QTR1 | 16/17 | 717 | 590500 | B0 | ACC - LUMP SUM
| 07 | E7K90 | 43386615201 | 2016-02-10 | QTR3 | 15/16 | 1 | 0 | 60 | 61 | 59 | 96.67% | 1 | 2 | 0 | 0 | 1 | 0 | 795744 | 15000 | 780744 | 795744 | 787111 | 0 | 0 | 0 | 787111 | 787111 | 100.8% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5751 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-10-12 | QTR2 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 717 | 455000 | B0 | ACC - LUMP SUM
| 07 | E7K99 | 43625515201 | 2016-03-09 | QTR3 | 15/16 | 1 | 1 | 50 | 51 | 37 | 72% | 1 | 14 | 0 | 0 | 1 | 0 | 160902 | 4125 | 156777 | 182550 | 178425 | 0 | 0 | 0 | 178425 | 178425 | 113.8% | 0 | 0 | 21648 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 21648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21648 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 717 | 165500 | B0 | ACC - LUMP SUM
| 07 | E7L07 | 43258315201 | 2015-11-12 | QTR2 | 15/16 | 1 | 0 | 80 | 89 | 89 | 105% | 1 | 0 | 0 | 0 | 5 | 4 | 1115377 | 50000 | 1065377 | 1115377 | 1056390 | 0 | 0 | 0 | 1056390 | 1056390 | 99.16% | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 798 | 1450000 | B0 | ACC - LUMP SUM
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 18 | 22 | 52 | 4785 | 5844 | 5448 | 100% | 18 | 396 | 0 | 0 | 947 | 112 | 292756531 | 1072125 | 291684406 | 302987492 | 302708590 | -7200 | 1650000 | 1642800 | 304351390 | 299072674.09 | 94.44% | 17 | -5222138 | 10230961 | 602 | 300 | 0 | 23 | 3058619 | 32554 | 30 | 50 | 5960259 | 508621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54698 | 0 | 15 | 39 | 1554522 | 0 | 0 | 0 | 75555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -96573 | 0 | 45 | 112 | 10607078 | 541175
| District 07 Totals |  |  |  |  | 31 | 57 | 168 | 10504 | 13556 | 13242 | 93.55% | 29 | 314 | 180 | 0 | 2270 | 782 | 798560187 | 2126125 | 796434062 | 853403580 | 859438524 | -480720 | 2070000 | 1589280 | 861027804 | 855218954.09 | 93.55% | 29 | -5752273 | 54843393 | 1496 | 666 | 22 | 143 | 15026612 | 5335853 | 71 | 250 | 21835941 | 5931071 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 54698 | 0 | 15 | 352 | 8154150 | 1643685 | 0 | 0 | 10092670 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 251369 | 105370 | 0 | 0 | 210466 | 210466 | 0 | 10 | 66975 | 12265 | 0 | 0 | 0 | 0 | 0 | 0 | -179325 | 0 | 108 | 782 | 55509626 | 13238709
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8M60 | 43127515201 | 2013-01-22 | QTR3 | 12/13 | 3 | 33 | 1055 | 1167 | 1167 | 100.4% | 1 | -1 | 1 | 0 | 112 | 0 | 56648757 | 150000 | 56498757 | 57438075 | 57810006 | 0 | 0 | 0 | 57810006 | 57069148 | 101% | 1 | -740858 | 789318 | 68 | 40 | 0 | 0 | 324282 | 0 | 0 | 0 | 229213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568192 | 23585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 32879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -311259 | 0 | 4 | 0 | 843308 | 23585 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 |  | 2016-06-30 | QTR4 | 15/16 | 854 | 56376201.62
| 08 | E8M63 | 40615215201 | 2013-02-05 | QTR3 | 12/13 | 3 | 16 | 995 | 1179 | 1179 | 102.1% | 1 | 0 | 0 | 0 | 170 | 14 | 57400000 | 150000 | 57250000 | 57854468 | 58114118 | -10000 | 0 | -10000 | 58104118 | 57193979 | 99.9% | 1 | -910139 | 454468 | 108 | 55 | 0 | 0 | 135877 | 1764 | 7 | 14 | 647998 | 24913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -365840 | 0 | 7 | 14 | 489562 | 26677 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-02 | QTR2 | 16/17 |  | 2016-07-20 | QTR1 | 16/17 | 854 | 59063480.38
| 08 | E8N60 | 41546265201 | 2014-05-20 | QTR4 | 13/14 | 1 | 3 | 475 | 545 | 545 | 100.2% | 1 | 0 | 0 | 0 | 70 | 0 | 10628174 | 96840 | 10531334 | 10702005 | 10703365 | -6500 | 0 | -6500 | 10696865 | 10548835 | 100.2% | 1 | -148030 | 73831 | 23 | 46 | 0 | 0 | 8969 | 0 | 0 | 0 | 107706 | 13562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 117912 | 13562 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-04-12 | QTR4 | 15/16 | 854 | 9781121.21
| 08 | E8N68 | 24301715201 | 2014-06-09 | QTR4 | 13/14 | 2 | 4 | 480 | 643 | 642 | 119.6% | 1 | 1 | 0 | 0 | 163 | 0 | 16844000 | 150000 | 16694000 | 17989634 | 18429954 | -3000 | 0 | -3000 | 18426954 | 17949122 | 107.5% | 1 | -477832 | 1145634 | 44 | 24 | 0 | 0 | 71261 | 0 | 29 | 0 | 246343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 947444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 1265048 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 854 | 15034152.99
| 08 | E8P54 | 43110015201 | 2015-10-20 | QTR2 | 15/16 | 1 | 1 | 115 | 121 | 118 | 97.39% | 1 | 3 | 0 | 0 | 6 | 0 | 1369271 | 50000 | 1319271 | 1355607 | 1258468 | 0 | 0 | 0 | 1258468 | 1224485 | 92.82% | 1 | -33984 | -13664 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-06-24 | QTR4 | 15/16 | 854 | 1662320.12
| 08 | E8P55 | 43561715201 | 2015-06-16 | QTR4 | 14/15 | 1 | 1 | 140 | 189 | 189 | 102.9% | 1 | 0 | 0 | 0 | 45 | 4 | 1736149 | 50000 | 1686149 | 1766298 | 1678250 | -26500 | 0 | -26500 | 1651750 | 1651060 | 97.92% | 1 | -690 | 30149 | 29 | 16 | 0 | 4 | 30149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 30149 | 0 | F203908361 | MIDASCO LLC | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 854 | 1991671.8
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 6 | 11 | 58 | 3260 | 3844 | 3840 | 0.002321% | 6 | 3 | 1 | 0 | 566 | 18 | 144626351 | 646840 | 143979511 | 147106087 | 147994161 | -46000 | 0 | -46000 | 147948161 | 145636629 | 100% | 6 | -2311533 | 2479736 | 278 | 181 | 0 | 4 | 570538 | 1764 | 36 | 14 | 1217596 | 51076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 1582198 | 23585 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 37844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -677099 | 0 | 97 | 18 | 2732315 | 76425
| District 08 Totals |  |  |  |  | 6 | 11 | 58 | 3260 | 3844 | 3840 | 100% | 6 | 3 | 1 | 0 | 566 | 18 | 144626351 | 646840 | 143979511 | 147106087 | 147994161 | -46000 | 0 | -46000 | 147948161 | 145636629 | 100% | 6 | -2311533 | 2479736 | 278 | 181 | 0 | 4 | 570538 | 1764 | 36 | 14 | 1217596 | 51076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 1582198 | 23585 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 37844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -677099 | 0 | 97 | 18 | 2732315 | 76425
| Statewide Central Let Contracts SubTotal |  |  |  |  | 99 | 177 | 318 | 29757 | 40100 | 39170 | 85.86% | 85 | 930 | 384 | 0 | 8054 | 2289 | 963476628 | 5919313 | 957557316 | 1018225666 | 1022822376 | -1229669 | 4705700 | 3476031 | 1026298406 | 1009010294 | 90.91% | 90 | -17288116 | 55167980 | 5199 | 1943 | 217 | 1107 | 17901815 | 6968556 | 121 | 587 | 22108242 | 6747609 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 4000 | 0 | 328 | 457 | 7661285 | 1761734 | 0 | 37 | 10111939 | 0 | 0 | 0 | -59292 | 0 | 18 | 63 | 712298 | 290749 | 97 | 29 | 367920 | 348376 | 41 | 10 | 71812 | 12265 | 0 | 0 | 0 | 0 | 0 | -3 | -1419254 | 0 | 822 | 2287 | 57456835 | 16129289
| Statewide District Let Contracts SubTotal |  |  |  |  | 80 | 108 | 177 | 18942 | 25261 | 24687 | 86.25% | 69 | 573 | 264 | 0 | 4365 | 1954 | 606700026 | 4531561 | 602168465 | 635076281 | 636519450 | -282378 | 2966600 | 2684222 | 639203671 | 627764290.09 | 88.75% | 71 | -11382809 | 28376258 | 2647 | 1219 | 45 | 1047 | 13864501 | 2244087 | 133 | 535 | 13264492 | 1289789 | 0 | 11 | 3535 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 96498 | 0 | 194 | 330 | 3525759 | 329039 | 0 | 3 | 89636 | 0 | 0 | 0 | 0 | 0 | 4 | 28 | 193126 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -978280 | 0 | 440 | 1954 | 30049514 | 3862915
| Statewide Totals |  |  |  |  | 179 | 285 | 495 | 48699 | 65361 | 63857 | 86.03% | 154 | 1503 | 648 | 0 | 12419 | 4243 | 1570176654 | 10450874 | 1559725781 | 1653301947 | 1659341826 | -1512047 | 7672300 | 6160253 | 1665502077 | 1636774584.09 | 89.94% | 161 | -28670925 | 83544238 | 7846 | 3162 | 262 | 2154 | 31766316 | 9212643 | 254 | 1122 | 35372734 | 8037398 | 0 | 11 | 3535 | 0 | 0 | 0 | -13677 | 0 | 0 | 0 | 100498 | 0 | 522 | 787 | 11187044 | 2090773 | 0 | 40 | 10201575 | 0 | 0 | 0 | -59292 | 0 | 22 | 91 | 905424 | 290749 | 97 | 29 | 367920 | 348376 | 105 | 10 | 71812 | 12265 | 0 | 0 | 0 | 0 | 0 | -3 | -2397534 | 0 | 1262 | 4241 | 87506349 | 19992204

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1N36 | 43544915201 | F593586613 | EVANS CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-06-19 | 1877203 | 1918177 | 1843430 | 40974.24 | -20904 | 1821939 | -20904 | 0 | 0 | 0 | 0 | 0 | -20904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20904 | 1822526 | 1821939 | -587 | 2352808
1 | E1N74 | 42912015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-18 | 3107573 | 3107573 | 3110593 | 0 | 0 | 2961957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3110593 | 2961957 | -148636 | 3280021
1 | E1N87 | 43120915201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2015-02-19 | 3172000 | 3172000 | 3272265 | 0 | 0 | 3269380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3272265 | 3269380 | -2886 | 3312411
1 | E1O02 | 43161515201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-01-15 | 5445703 | 6533716 | 6114803 | 1088013.37 | 0 | 5883385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6114803 | 5883385 | -231419 | 4971482
1 | E1O75 | 43503815201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-01-21 | 149955 | 149955 | 147793 | 0 | 0 | 147793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147793 | 147793 | 0 | 157974
1 | T1552 | 40631475201 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2013-09-25 | 2579468 | 2579468 | 2493565 | 0 | -85464 | 2408101 | -85464 | 0 | 0 | 0 | 0 | 0 | -85464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -85464 | 2408101 | 2408101 | 0 | 3076291
1 | T1560 | 42910115201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-08-26 | 4883160 | 4883160 | 4742567 | 0 | 0 | 4581604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4742567 | 4581604 | -160964 | 5451825
1 | T1583 | 42910715201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-05-21 | 12221582 | 12321397 | 12316064 | 99814.55 | -258944 | 11369478 | -258944 | 0 | 0 | 0 | 0 | 0 | -258944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -258944 | 12057120 | 11369478 | -687643 | 11851722
1 | T1587 | 42913115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-03-26 | 4576900 | 4273384 | 4255627 | -303515.58 | 0 | 4165417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4255627 | 4165417 | -90210 | 5166652 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1588 | 41304225201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-06-18 | 24169365 | 23023182 | 22613781 | -1146183.49 | 900000 | 20785082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 900000 | 900000 | 23513781 | 20785082 | -2728699 | 29188896 | B2:B5:B2 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING)
1 | T1595 | 40631345201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-03-25 | 31929262 | 31614976 | 31607283 | -314285.98 | 1300000 | 30894410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 1300000 | 1300000 | 32907283 | 30894410 | -2012872 | 30769491 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
1 | T1596 | 43142215201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-02-25 | 5571174 | 5623674 | 5636689 | 52500 | 0 | 5437906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5636689 | 5437906 | -198783 | 5411862 | B0 | ACC - LUMP SUM
1 | T1597 | 43356115201 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-02-25 | 737000 | 989001 | 989001 | 252000.76 | 0 | 989001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 989001 | 989001 | 0 | 596983 | B0 | ACC - LUMP SUM
1 | T1601 | 42910615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 2560715 | 2560715 | 2601322 | 0 | 0 | 2476584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601322 | 2476584 | -124738 | 2539522
1 | T1604 | 43340715201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1272557 | 1265786 | 1215247 | -6770.49 | 0 | 1215247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215247 | 1215247 | 0 | 1175939 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1610 | 43337615201 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2015-05-20 | 766880 | 763925 | 702653 | -2955.57 | -27872 | 674781 | -27872 | 0 | 0 | 0 | 0 | 0 | -27872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27872 | 674781 | 674781 | 0 | 1032308 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1612 | 43539315201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 965039 | 965864 | 949501 | 824.93 | 0 | 941761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949501 | 941761 | -7741 | 968995
1 | T1615 | 42950615201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1470894 | 1470894 | 1424904 | 0 | 0 | 1424904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424904 | 1424904 | 0 | 1441635 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1617 | 43337515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1087453 | 1211375 | 1165751 | 123921.65 | 0 | 1165751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165751 | 1165751 | 0 | 1092794 | B0 | ACC - LUMP SUM
1 | T1618 | 43340815201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-06-17 | 1135821 | 1138128 | 1108067 | 2307.3 | 0 | 1103946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108067 | 1103946 | -4121 | 1209050 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1619 | 43365815201 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 618558 | 622340 | 622340 | 3781.98 | 0 | 622340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622340 | 622340 | 0 | 495886 | B0 | ACC - LUMP SUM
1 | T1629 | 43325615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-30 | 910000 | 910000 | 883227 | 0 | 0 | 883227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883227 | 883227 | 0 | 857875 | B0 | ACC - LUMP SUM
1 | T1651 | 43134115201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-01-27 | 194630 | 194630 | 184896 | 0 | 0 | 184896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184896 | 184896 | 0 | 236550 | B0 | ACC - LUMP SUM
1 | T1659 | 43472815201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 238287 | 238287 | 228375 | 0 | 0 | 228375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228375 | 228375 | 0 | 176436 | B0 | ACC - LUMP SUM
1 | T1A02 | 42518315201 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 5396928 | 5491707 | 5952983 | 94778.73 | 0 | 5952455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5952983 | 5952455 | -528 | 4358787 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1A15 | 43325515201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 219504 | 219504 | 213917 | 0 | 0 | 213917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213917 | 213917 | 0 | 200589 | B0 | ACC - LUMP SUM
2 | E2P99 | 21330125201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2012-06-29 | 17859000 | 27306925 | 27318877 | 9447924.67 | 0 | 26689964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27318877 | 26689964 | -628913 | 28650000 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2R04 | 21066125201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2012-12-12 | 1430432 | 1430840 | 1393606 | 408.1 | -49024 | 1344578 | -49024 | 0 | 0 | 0 | 0 | 0 | -49024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49024 | 1344582 | 1344578 | -4 | 1293927
2 | E2R17 | 21237935201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2013-06-20 | 11440230 | 11429587 | 11316805 | -10643.03 | 0 | 11261013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11316805 | 11261013 | -55793 | 13890663 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
2 | E2T58 | 43226315201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-11-18 | 3757549 | 3757549 | 3830766 | 0 | 0 | 3684887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3830766 | 3684887 | -145879 | 4878401
2 | E2T69 | 43041715201 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-15 | 1759555 | 1996713 | 2571252 | 237157.84 | 0 | 2563560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571252 | 2563560 | -7693 | 1357063
2 | E2T70 | 43219415201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2015-07-15 | 741630 | 741630 | 709180 | 0 | 0 | 709010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709180 | 709010 | -170 | 775810
2 | E2T74 | 42342715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-09-16 | 4336630 | 4336630 | 4421132 | 0 | 0 | 4255700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4421132 | 4255700 | -165433 | 4754491
2 | E2T87 | 20967415201 | F205877898 | KIRBY DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2015-11-18 | 1743906 | 1743906 | 2125210 | 0 | 0 | 2124106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125210 | 2124106 | -1104 | 1607951
2 | E2T90 | 20838945201 | F593285921 | S & D INDUSTRIAL PAINTING INC. | N/A | N/A | N/A | N/A | 2015-12-16 | 559753 | 559753 | 512091 | 0 | 0 | 512091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512091 | 512091 | 0 | 1034492
2 | E2U45 | 42871125201 | Z31-0396250 | OHIO CASUALTY INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2015-12-16 | 138261 | 138261 | 134115 | 0 | -43856 | 120111 | -43856 | 0 | 0 | 0 | 0 | 0 | -43856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43856 | 90258 | 120111 | 29853 | 151023 | B0 | ACC - LUMP SUM
2 | T2506 | 43040415201 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2013-10-30 | 136157 | 136157 | 128357 | 0 | -47602 | 80754 | -41690 | 0 | 0 | 0 | -5912 | 0 | -47602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47602 | 80754 | 80754 | 0 | 153003 | B0 | ACC - LUMP SUM
2 | T2533 | 43355415201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-06-18 | 8533240 | 8598881 | 9356445 | 65640.9 | 0 | 9207548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9356445 | 9207548 | -148897 | 7794226
2 | T2538 | 42696315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-06-18 | 3648202 | 3648202 | 3611865 | 0 | 0 | 3514982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3611865 | 3514982 | -96884 | 3330303
2 | T2541 | 42607315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-09-24 | 3641891 | 3767252 | 4042041 | 125360.82 | 0 | 3981696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4042041 | 3981696 | -60345 | 3748196
2 | T2567 | 43224715201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2015-02-25 | 1013111 | 1368388 | 1368010 | 355277.03 | 0 | 1368010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368010 | 1368010 | 0 | 1004174 | B0 | ACC - LUMP SUM
2 | T2572 | 43061415201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 1990811 | 2002450 | 2059822 | 11638.3 | 0 | 2059822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059822 | 2059822 | 0 | 1508390
2 | T2584 | 43051315201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 3444187 | 3524159 | 3538172 | 79971.84 | 0 | 3415729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3538172 | 3415729 | -122443 | 3688557
2 | T2587 | 43265515201 | F453689782 | SOUTHERN STATES PAVEMENT MARKINGS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 718800 | 718800 | 718800 | 0 | 0 | 718800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718800 | 718800 | 0 | 769167 | B0 | ACC - LUMP SUM
2 | T2588 | 21237925201 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-09-30 | 2271500 | 2329229 | 2340019 | 57729.21 | 0 | 2337891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340019 | 2337891 | -2128 | 2754839 | B0 | ACC - LUMP SUM
2 | T2589 | 41525415201 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-12-03 | 1503905 | 1530011 | 1553775 | 26105.47 | 0 | 1554113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1553775 | 1554113 | 338 | 1346460
2 | T2593 | 43051715201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-09-30 | 1956915 | 1997332 | 1951682 | 40417.14 | 0 | 1947009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1951682 | 1947009 | -4672 | 2334094
2 | T2594 | 43265415201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2015-09-30 | 475000 | 475000 | 475000 | 0 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000 | 475000 | 0 | 428506 | B0 | ACC - LUMP SUM
2 | T2602 | 43074515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-02-24 | 558858 | 558858 | 508320 | 0 | 0 | 508320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508320 | 508320 | 0 | 579077
2 | T2603 | 43075915201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 521218 | 521218 | 506672 | 0 | 0 | 506672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506672 | 506672 | 0 | 510082
2 | T2604 | 43226115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 7717554 | 7717554 | 7824593 | 0 | -15080 | 7576665 | -15080 | 0 | 0 | 0 | 0 | 0 | -15080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15080 | 7809513 | 7576665 | -232848 | 9660990
2 | T2608 | 43055825201 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2015-10-28 | 148375 | 148375 | 138616 | 0 | 0 | 138616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138616 | 138616 | 0 | 178082
3 | E3K73 | 42693515201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2014-03-13 | 1221881 | 1231781 | 1143560 | 9900 | 0 | 1120620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1143560 | 1120620 | -22940 | 1514949
3 | E3L90 | 42840315201 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2013-06-28 | 24049000 | 24338104 | 24337828 | 289103.75 | 0 | 24337642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24337828 | 24337642 | -186 | 21314872 | A3 | ICC - DESIGN/BUILD - MINOR
3 | E3M17 | 40747845201 | F455085205 | PRINCIPLE PROPERTIES INC. | N/A | N/A | N/A | N/A | 2015-11-20 | 149498 | 149498 | 139613 | 0 | 0 | 139613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139613 | 139613 | 0 | 163264
3 | E3M30 | 42429125201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-02-26 | 4578636 | 5834533 | 5832583 | 1255897.44 | 0 | 5832583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5832583 | 5832583 | 0 | 4578636 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
3 | E3M55 | 42805825201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2014-01-31 | 1540571 | 1579254 | 1571464 | 38682.88 | 0 | 1571464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1571464 | 1571464 | 0 | 1529160 | A3 | ICC - DESIGN/BUILD - MINOR
3 | E3M95 | 41694315201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-07-09 | 2738862 | 3014082 | 3595051 | 275219.9 | 0 | 3484491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3595051 | 3484491 | -110560 | 3204695
3 | E3N17 | 43392715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-10 | 1734968 | 1417537 | 1360898 | -317430.27 | 0 | 1360898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360898 | 1360898 | 0 | 1346664
3 | E3N18 | 43391815201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-10-08 | 1245237 | 1323870 | 1408799 | 78632.64 | 0 | 1408799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1408799 | 1408799 | 0 | 1048525
3 | E3N27 | 41627215201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2015-03-25 | 2233345 | 2293381 | 2249432 | 60035.59 | 0 | 2223244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2249432 | 2223244 | -26188 | 2172219 | A3:LBDB:A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
3 | E3N39 | 43078815201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-05-14 | 3111936 | 3033818 | 2963684 | -78118.45 | -11504 | 2882199 | -11504 | 0 | 0 | 0 | 0 | 0 | -11504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11504 | 2952180 | 2882199 | -69981 | 3291623
3 | E3N42 | 21791185201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-03-10 | 762045 | 762045 | 712000 | 0 | 0 | 712000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712000 | 712000 | 0 | 1488725
3 | E3N73 | 43078715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-05-14 | 4943758 | 4974205 | 5018776 | 30446.86 | -2400 | 4741701 | 0 | 0 | 0 | 0 | 0 | -2400 | -2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2400 | 5016376 | 4741701 | -274675 | 4773076
3 | E3N74 | 42696915201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-11-20 | 2813937 | 2813937 | 2913809 | 0 | 0 | 2837766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2913809 | 2837766 | -76042 | 3196209
3 | E3N76 | 41557535201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-01-14 | 1819446 | 1819446 | 1750296 | 0 | 0 | 1750297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750296 | 1750297 | 1 | 1571363
3 | E3N80 | 42577825201 | F208328161 | AN-KAR CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-01-14 | 246955 | 246955 | 248745 | 0 | -7664 | 241081 | -7664 | 0 | 0 | 0 | 0 | 0 | -7664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7664 | 241081 | 241081 | 0 | 183111
3 | E3O14 | 41040925201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-09-24 | 1815481 | 1830051 | 1851635 | 14570.45 | 0 | 1847209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1851635 | 1847209 | -4426 | 1670232
3 | E3O47 | 43253815201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-10-15 | 2030029 | 2030029 | 2131829 | 0 | 0 | 2045055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2131829 | 2045055 | -86775 | 2649534
3 | E3O53 | 43254815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-09-10 | 2754000 | 2754000 | 2779810 | 0 | 0 | 2686704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2779810 | 2686704 | -93106 | 3103650
3 | E3O62 | 43079215201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-12-10 | 1298500 | 1382401 | 1347119 | 83901.29 | 0 | 1319720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347119 | 1319720 | -27399 | 1564335 | B0 | ACC - LUMP SUM
3 | E3P32 | 42460825201 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-03-10 | 69197 | 69197 | 67195 | 0 | 0 | 67195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67195 | 67195 | 0 | 143400
3 | E3P60 | 43255315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-08-11 | 966283 | 966283 | 955206 | 0 | -1500 | 953706 | 0 | 0 | 0 | 0 | 0 | -1500 | -1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1500 | 953706 | 953706 | 0 | 939110
3 | E3P85 | 43627415201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-04-14 | 218815 | 218815 | 209764 | 0 | 0 | 209764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209764 | 209764 | 0 | 189940
3 | T3349 | 22041285201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2010-12-08 | 7357219 | 10528722 | 10638848 | 3171502.78 | -93018 | 10537771 | -93018 | 0 | 0 | 0 | 0 | 0 | -93018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -93018 | 10545830 | 10537771 | -8059 | 7320355 | ARRA | AMERICAN RECOVERY AND REINVEST
3 | T3375 | 42124315201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2012-02-29 | 14736078 | 15035632 | 14669101 | 299554.18 | 0 | 14620764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14669101 | 14620764 | -48338 | 18080147
3 | T3398 | 22016225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 3358717 | 4155082 | 4026349 | 796365.22 | 0 | 3996594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4026349 | 3996594 | -29755 | 2823246
3 | T3418 | 42551915201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2014-12-03 | 2589441 | 2672648 | 2648983 | 83206.58 | 0 | 2635144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2648983 | 2635144 | -13838 | 2582603
3 | T3427 | 42164415201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2013-07-31 | 11476305 | 11609159 | 11286785 | 132854.22 | -11250 | 10699458 | 0 | 0 | 0 | 0 | 0 | -11250 | -11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11250 | 11275535 | 10699458 | -576077 | 12800390
3 | T3433 | 42693025201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-02-25 | 4985043 | 5040858 | 4902106 | 55814.29 | -20132 | 4555909 | -20132 | 0 | 0 | 0 | 0 | 0 | -20132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20132 | 4881974 | 4555909 | -326064 | 6115127
3 | T3443 | 42693415201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 4037987 | 4183812 | 4167957 | 145824.98 | 0 | 3846478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167957 | 3846478 | -321479 | 4397279
3 | T3460 | 42874715201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-03-30 | 1335414 | 1335414 | 1301394 | 0 | 0 | 1295632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301394 | 1295632 | -5762 | 1593999
3 | T3482 | 42884515201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-01-28 | 7416925 | 7437265 | 7758460 | 20339.32 | -880 | 7441692 | 0 | 0 | 0 | 0 | 0 | -880 | -880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -880 | 7757580 | 7441692 | -315888 | 8733988
3 | T3483 | 43077715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 4039522 | 4047995 | 4269663 | 8472.89 | 0 | 4226492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4269663 | 4226492 | -43171 | 3857910
3 | T3495 | 42695615201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-29 | 1619321 | 1619321 | 1588249 | 0 | 0 | 1566711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1588249 | 1566711 | -21538 | 1991520
3 | T3514 | 43078115201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-29 | 3802689 | 3802689 | 3624193 | 0 | 0 | 3479143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3624193 | 3479143 | -145050 | 4144190
3 | T3515 | 43090835201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 8076272 | 8066272 | 8349102 | -10000 | 0 | 7667982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8349102 | 7667982 | -681120 | 8827285
3 | T3539 | 22243945201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-06-17 | 1948263 | 1965454 | 2004975 | 17191.7 | 0 | 2004975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004975 | 2004975 | 0 | 1870760
3 | T3551 | 42873915201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 2525492 | 2696693 | 2810548 | 171200.34 | -29132 | 2626488 | -20132 | 0 | 0 | 0 | 0 | -9000 | -29132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29132 | 2781416 | 2626488 | -154929 | 3044222
3 | T3552 | 43273715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-07-29 | 3670000 | 3738760 | 3752339 | 68759.59 | -5200 | 3623993 | 0 | 0 | 0 | 0 | 0 | -5200 | -5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5200 | 3747139 | 3623993 | -123146 | 4236500
3 | T3589 | 43174315201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-03-30 | 169047 | 169047 | 169047 | 0 | 0 | 169047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169047 | 169047 | 0 | 199840 | B0 | ACC - LUMP SUM
3 | T9009 | 43035625201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-06-24 | 1500230 | 1500230 | 1507255 | 0 | 0 | 1507255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507255 | 1507255 | 0 | 1868903
4 | E4P79 | 42593515201 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-04-23 | 7765532 | 7903357 | 8161146 | 137825.56 | 321600 | 8149687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 0 | 0 | 0 | 0 | 111600 | 321600 | 321600 | 8482746 | 8149687 | -333059 | 7456672 | B3:B5 | ACC - LANE RENTAL:ACC - INCENTIVE/DISINCENTIVE
4 | E4P94 | 43368845201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2014-05-02 | 11791416 | 13321296 | 13475252 | 1529880.42 | 470000 | 13368481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470000 | 0 | 0 | 0 | 0 | 0 | 470000 | 470000 | 13945252 | 13368481 | -576771 | 12152859 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
4 | E4P98 | 42605315201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-02-06 | 1670723 | 1694884 | 1701995 | 24161.58 | 0 | 1740331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1701995 | 1740331 | 38336 | 1844041
4 | E4Q22 | 42990515201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-19 | 5750000 | 6072503 | 6142459 | 322502.98 | 0 | 6141649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6142459 | 6141649 | -810 | 6522411 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4Q70 | 43056615201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2015-04-03 | 594927 | 594927 | 563713 | 0 | 0 | 563713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563713 | 563713 | 0 | 789528
4 | E4R08 | 43115215201 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 1435007 | 1449407 | 1163642 | 14400 | 0 | 1155244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163642 | 1155244 | -8398 | 1565107
4 | E4R65 | 43538615201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-01-08 | 593859 | 593859 | 535917 | 0 | 0 | 540661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535917 | 540661 | 4743 | 495318
4 | T4341 | 23073015201 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2013-02-06 | 6592014 | 6833204 | 6617553 | 241190.16 | 0 | 6330385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6617553 | 6330385 | -287168 | 7354584
4 | T4389 | 23097825201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2014-04-30 | 15715809 | 15753499 | 15520925 | 37690.07 | 630700 | 14964924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630700 | 0 | 0 | 0 | 0 | 0 | 630700 | 630700 | 16151625 | 14964924 | -1186702 | 15839218 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4402 | 42973715201 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2014-07-30 | 2824000 | 2824000 | 2773850 | 0 | 0 | 2779467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2773850 | 2779467 | 5617 | 3519184 | B0 | ACC - LUMP SUM
4 | T4411 | 43472615201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 1298981 | 1298981 | 1226359 | 0 | 0 | 1217254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226359 | 1217254 | -9105 | 1277355
4 | T4415 | 43472315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 1247191 | 1247191 | 1236940 | 0 | 0 | 1236940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236940 | 1236940 | 0 | 1184119
4 | T4416 | 43171715201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 1444863 | 1444863 | 1398240 | 0 | 0 | 1398240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398240 | 1398240 | 0 | 1613354
4 | T4417 | 43400715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-05-20 | 590398 | 600523 | 561695 | 10124.92 | 0 | 561695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561695 | 561695 | 0 | 743748
4 | T4426 | 43060815201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2016-02-24 | 1295575 | 1295575 | 1275925 | 0 | 0 | 1275925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275925 | 1275925 | 0 | 1142628 | B0 | ACC - LUMP SUM
5 | E5W67 | 43198915201 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2014-10-07 | 2340785 | 2247902 | 2197902 | -92883 | -92326 | 2104471 | -92326 | 0 | 0 | 0 | 0 | 0 | -92326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92326 | 2105576 | 2104471 | -1105 | 2486510
5 | E5W83 | 43528215201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-04-07 | 2750721 | 2750721 | 2676098 | 0 | 0 | 2676025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2676098 | 2676025 | -73 | 2985731
5 | E5W86 | 43488315201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-04 | 584110 | 585291 | 580591 | 1181.19 | 0 | 580591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580591 | 580591 | 0 | 623549
5 | E5Y02 | 43705815201 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2015-09-01 | 783941 | 783941 | 744941 | 0 | 0 | 744941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 744941 | 744941 | 0 | 821518
5 | E5Y03 | 43116415201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2016-02-02 | 63940 | 63940 | 58289 | 0 | 0 | 58289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58289 | 58289 | 0 | 123170
5 | E5Y04 | 43705715201 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-01-05 | 679709 | 679709 | 640622 | 0 | 0 | 640622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640622 | 640622 | 0 | 911256
5 | E5Y05 | 43465915201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-01-05 | 448115 | 448115 | 434061 | 0 | 0 | 434061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434061 | 434061 | 0 | 409596
5 | E5Y18 | 23800235225 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-02-02 | 788000 | 805272 | 758781 | 17271.51 | 0 | 759356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 758781 | 759356 | 575 | 717566
5 | T5415 | 40735535201 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2012-05-23 | 32798973 | 35176946 | 35231745 | 2796919.19 | -161575 | 34680971 | -161575 | 0 | 0 | 0 | 0 | 0 | -161575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -161575 | 35070170 | 34680971 | -389199 | 37106690
5 | T5496 | 43106615201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-05-21 | 4198661 | 4198661 | 4290920 | 0 | 0 | 4280333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4290920 | 4280333 | -10587 | 5833244
5 | T5497 | 43113915201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-06-18 | 5577400 | 5630674 | 5316503 | 53274.46 | 0 | 5110931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5316503 | 5110931 | -205572 | 5261132 | B0:B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
5 | T5504 | 43326915201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-02-25 | 2791824 | 2791824 | 2764770 | 0 | 0 | 2763716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2764770 | 2763716 | -1054 | 3681477
5 | T5507 | 42908315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-29 | 13950000 | 14304220 | 14416417 | 354219.83 | 0 | 13250583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14416417 | 13250583 | -1165834 | 13411584
5 | T5515 | 43066815201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-02-25 | 1884019 | 1929335 | 1919435 | 45316.44 | 0 | 1875340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919435 | 1875340 | -44095 | 1716624 | B0 | ACC - LUMP SUM
5 | T5519 | 43066615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-07-29 | 2698908 | 2698908 | 2560594 | 0 | 0 | 2513289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560594 | 2513289 | -47305 | 2488176
5 | T5524 | 43065215201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 4938000 | 5043475 | 4946856 | 105475.47 | 0 | 4688330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4946856 | 4688330 | -258527 | 4676397
5 | T5528 | 43066915201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2015-05-27 | 2181000 | 2446253 | 2396253 | 265252.96 | 0 | 2380075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2396253 | 2380075 | -16178 | 1883279
5 | T5536 | 43067715201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 2584884 | 2614884 | 2636650 | 30000 | 0 | 2540033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2636650 | 2540033 | -96617 | 2795914
5 | T5537 | 43244215201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-09-30 | 1272760 | 1272760 | 1267646 | 0 | 0 | 1267646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267646 | 1267646 | 0 | 919590 | B0 | ACC - LUMP SUM
5 | T5540 | 43544615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 2108960 | 2108960 | 2062184 | 0 | 0 | 2062184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2062184 | 2062184 | 0 | 2665357
6 | E6H77 | 41806525201 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2013-07-16 | 6865432 | 8047242 | 8106870 | 1181810.07 | 525000 | 8012338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 525000 | 525000 | 8631870 | 8012338 | -619532 | 9650623 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
6 | E6I89 | 43117815201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-10-30 | 2097039 | 2147039 | 2148203 | 50000 | 0 | 2008021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2148203 | 2008021 | -140182 | 2334024
6 | E6I91 | 42918715201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-06-11 | 1483128 | 1483128 | 1441455 | 0 | 0 | 1430102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1441455 | 1430102 | -11353 | 1376236
6 | E6I98 | 43493065201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-03-31 | 969000 | 903732 | 873748 | -65268.21 | 0 | 873360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 873748 | 873360 | -388 | 1134223 | B0 | ACC - LUMP SUM
6 | T6127 | 25118515201 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2011-09-07 | 58542945 | 59378958 | 60313959 | 836012.85 | 0 | 59721395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60313959 | 59721395 | -592564 | 67023599
6 | T6320 | 42914015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 14295524 | 14692214 | 13690377 | 396690.11 | 245000 | 13056864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 0 | 245000 | 245000 | 13935377 | 13056864 | -878513 | 15289320 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6325 | 25055425201 | F410827177 | JOHNSON BROS. CORPORATION | N/A | N/A | N/A | N/A | 2012-10-31 | 11430054 | 11749528 | 11929942 | 319473.2 | 0 | 11924070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11929942 | 11924070 | -5871 | 12087502
6 | T6365 | 43274315201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 3849469 | 3927103 | 3942847 | 77633.87 | 0 | 3837692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3942847 | 3837692 | -105154 | 4708188 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6371 | 42913415201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-04-29 | 1483369 | 1483369 | 1429074 | 0 | 0 | 1425704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429074 | 1425704 | -3370 | 1435508
6 | T6373 | 43080915201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-02-25 | 2376742 | 2426742 | 2460615 | 50000 | 0 | 2384892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2460615 | 2384892 | -75723 | 2292102
6 | T6374 | 43118015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 5144045 | 5317082 | 5198829 | 173037.48 | 0 | 5112224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5198829 | 5112224 | -86605 | 4599363
6 | T6376 | 43081715201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-02-25 | 6621887 | 6805679 | 6261293 | 183792.64 | 470000 | 6082074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 20000 | 0 | 470000 | 470000 | 6731293 | 6082074 | -649219 | 6429680 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6384 | 43350815201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2015-09-30 | 439934 | 439934 | 417205 | 0 | 0 | 417205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417205 | 417205 | 0 | 559680 | B0 | ACC - LUMP SUM
6 | T6389 | 43481015201 | F273954210 | PE-SERVICES L.L.C. | N/A | N/A | N/A | N/A | 2016-01-27 | 147742 | 147742 | 141841 | 0 | 0 | 141841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141841 | 141841 | 0 | 180124 | B0 | ACC - LUMP SUM
6 | T6394 | 24961575201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 18918175 | 18918175 | 18379697 | 0 | 740000 | 17983880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660000 | 0 | 0 | 0 | 80000 | 0 | 740000 | 740000 | 19119697 | 17983880 | -1135817 | 23196102 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
7 | E7F75 | 25839855201 | F453806780 | SKANSKA-AJAX PAVING JOINT VENTU | N/A | N/A | N/A | N/A | 2012-05-08 | 215400000 | 224435209 | 224895976 | 9035209.03 | 1650000 | 223875000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650000 | 0 | 0 | 0 | 1650000 | 1650000 | 226545976 | 223875000 | -2670976 | 213872600 | B11:B12:B8:B:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - DSGN BLD-MAJ/BONUS/WRNTY:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
7 | E7I34 | 41101135201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-01-23 | 35188969 | 35441051 | 35414850 | 252081.91 | 0 | 34061551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35414850 | 34061551 | -1353299 | 37368154 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7I46 | 25633925201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-08-14 | 15944000 | 16474127 | 16294835 | 530127.11 | 0 | 15360010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16294835 | 15360010 | -934824 | 18310419 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
7 | E7J99 | 42715515201 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2015-04-08 | 1844400 | 1881240 | 1852163 | 36840.35 | 0 | 1792416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1852163 | 1792416 | -59746 | 1650000
7 | E7K02 | 43090115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-02-11 | 2683100 | 2806747 | 2817266 | 123647.22 | 0 | 2772695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2817266 | 2772695 | -44571 | 2450000 | B0 | ACC - LUMP SUM
7 | E7K04 | 43066015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-03-11 | 2680382 | 2750471 | 2763085 | 70089.15 | 0 | 2699178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2763085 | 2699178 | -63907 | 2007403 | B0 | ACC - LUMP SUM
7 | E7K05 | 43243225201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2015-03-11 | 1086230 | 1086230 | 1062839 | 0 | 0 | 1062824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062839 | 1062824 | -15 | 1230200
7 | E7K07 | 43068515201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-06-10 | 1119020 | 1119020 | 1092543 | 0 | 0 | 1092543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1092543 | 1092543 | 0 | 885300 | B0 | ACC - LUMP SUM
7 | E7K17 | 43094815201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-06-10 | 2888000 | 2888000 | 2727932 | 0 | 0 | 2690622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2727932 | 2690622 | -37311 | 3200000 | B0 | ACC - LUMP SUM
7 | E7K29 | 42550325201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2015-05-13 | 1984295 | 1984295 | 1950400 | 0 | 0 | 1950400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1950400 | 1950400 | 0 | 1727700
7 | E7K67 | 43149515201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-05-13 | 2794895 | 2964710 | 2918290 | 169814.53 | -7200 | 2905726 | 0 | 0 | 0 | 0 | 0 | -7200 | -7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7200 | 2911090 | 2905726 | -5363 | 1905000
7 | E7K68 | 43149115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-05-13 | 4031039 | 4044189 | 4055974 | 13150.2 | 0 | 4004687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4055974 | 4004687 | -51286 | 3361350
7 | E7K78 | 43080235201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-09-09 | 1271000 | 1271000 | 1221000 | 0 | 0 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221000 | 1221000 | 0 | 2206022 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
7 | E7K80 | 43478115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-12 | 1052289 | 1092289 | 992268 | 40000 | 0 | 991427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992268 | 991427 | -840 | 752249
7 | E7K88 | 43071015201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-01-13 | 716889 | 655243 | 627243 | -61645.9 | 0 | 627243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627243 | 627243 | 0 | 590500 | B0 | ACC - LUMP SUM
7 | E7K90 | 43386615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-02-10 | 795744 | 795744 | 787111 | 0 | 0 | 787111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787111 | 787111 | 0 | 455000 | B0 | ACC - LUMP SUM
7 | E7K99 | 43625515201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-03-09 | 160902 | 182550 | 178425 | 21648 | 0 | 178425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178425 | 178425 | 0 | 165500 | B0 | ACC - LUMP SUM
7 | E7L07 | 43258315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-11-12 | 1115377 | 1115377 | 1056390 | 0 | 0 | 1056390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056390 | 1056390 | 0 | 1450000 | B0 | ACC - LUMP SUM
7 | T7209 | 25841515201 | F263258515 | PCL/ARCHER WESTERN A JOINT VEN | N/A | N/A | N/A | N/A | 2009-09-16 | 389463750 | 430319761 | 437468272 | 40856010.73 | 0 | 439424048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437468272 | 439424048 | 1955776 | 412328910 | ARRA:B2:B5:P:B2 | AMERICAN RECOVERY AND REINVEST:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:PUBLIC PRIVATE PARTNERSHIP:ACC - A+B (COST+TIME BIDDING)
7 | T7236 | 25589325201 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2011-09-28 | 7147510 | 7510715 | 7761739 | 363204.75 | -452520 | 7308427 | -452520 | 0 | 0 | 0 | 0 | 0 | -452520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -452520 | 7309219 | 7308427 | -793 | 8423805
7 | T7305 | 41886065201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2012-06-20 | 27994444 | 28571829 | 28922186 | 577384.54 | 187000 | 28487362 | 0 | 0 | 0 | 0 | 0 | -13000 | -13000 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 187000 | 29109186 | 28487362 | -621825 | 26994097 | B1 | ACC - NO EXCUSE BONUS
7 | T7309 | 25714715201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2012-09-26 | 20511016 | 21458828 | 20369299 | 947812.13 | 0 | 20020139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20369299 | 20020139 | -349160 | 20045000
7 | T7311 | 25579315201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2013-05-31 | 21435705 | 23015417 | 23090810 | 1579712.31 | -8000 | 22674547 | 0 | 0 | 0 | 0 | 0 | -8000 | -8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8000 | 23082810 | 22674547 | -408263 | 21961490
7 | T7348 | 42907415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-06-18 | 13220362 | 13351863 | 13162187 | 131500.82 | 0 | 12814384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13162187 | 12814384 | -347802 | 12277372
7 | T7356 | 42905815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 6377897 | 6518755 | 6488848 | 140857.94 | 0 | 6241174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6488848 | 6241174 | -247674 | 6176900
7 | T7362 | 42907725202 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-03-25 | 5709404 | 5709404 | 5625130 | 0 | 0 | 5464793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5625130 | 5464793 | -160337 | 5660000
7 | T7364 | 43311115201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1656000 | 1660046 | 1621270 | 4045.76 | 0 | 1621270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1621270 | 1621270 | 0 | 1539800 | B0 | ACC - LUMP SUM
7 | T7366 | 43113215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-04-29 | 1795000 | 1795000 | 1754140 | 0 | 0 | 1746653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754140 | 1746653 | -7487 | 1415000 | B0 | ACC - LUMP SUM
7 | T7367 | 42907615201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 3822222 | 3834124 | 3855324 | 11901.75 | 0 | 3731807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3855324 | 3731807 | -123517 | 4100000
7 | T7370 | 43251915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-08-26 | 3088818 | 3088818 | 2944540 | 0 | 0 | 2940006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2944540 | 2940006 | -4534 | 3068000
7 | T7374 | 43257915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 3581528 | 3581528 | 3666189 | 0 | 220000 | 3671670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 220000 | 220000 | 3886189 | 3671670 | -214519 | 2950000 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
8 | E8M60 | 43127515201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2013-01-22 | 56648757 | 57438075 | 57810006 | 789318 | 0 | 57069148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57810006 | 57069148 | -740858 | 56376202
8 | E8M63 | 40615215201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-02-05 | 57400000 | 57854468 | 58114118 | 454468.05 | -10000 | 57193979 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 58104118 | 57193979 | -910139 | 59063480
8 | E8N60 | 41546265201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-05-20 | 10628174 | 10702005 | 10703365 | 73831.12 | -6500 | 10548835 | 0 | 0 | 0 | 0 | 0 | -6500 | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 10696865 | 10548835 | -148030 | 9781121
8 | E8N68 | 24301715201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-06-09 | 16844000 | 17989634 | 18429954 | 1145634.02 | -3000 | 17949122 | 0 | 0 | 0 | 0 | 0 | -3000 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 18426954 | 17949122 | -477832 | 15034153
8 | E8P54 | 43110015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-10-20 | 1369271 | 1355607 | 1258468 | -13663.94 | 0 | 1224485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258468 | 1224485 | -33984 | 1662320
8 | E8P55 | 43561715201 | F203908361 | MIDASCO LLC | N/A | N/A | N/A | N/A | 2015-06-16 | 1736149 | 1766298 | 1678250 | 30148.52 | -26500 | 1651060 | 0 | 0 | 0 | 0 | 0 | -26500 | -26500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26500 | 1651750 | 1651060 | -690 | 1991672

## Detailed Data - PPP
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
[29 empty] | 0% | 1
| Dist 01 - Central Let Contrats SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 01 | E1K48 | 41306615201 | 2012-06-28 | QTR4 | 11/12 | 1 | 5 | 890 | 1143 | 1143 | 104.5% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 0 | 0% | 1 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852 | F454673542 | DE MOYA / LEWARE JV | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 |  | 2015-12-08 | QTR2 | 15/16 | 106 | 80270500 | B8:DBF:P3 | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP
[29 empty] | 0% | 1
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 1 | 1 | 5 | 890 | 1143 | 1143 | 100% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 0 | 200% | 2 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852
| District 01 Totals |  |  |  |  | 1 | 1 | 5 | 890 | 1143 | 1143 | 100% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 0 | 300% | 3 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852
[29 empty] | 0% | 1
| Dist 02 Central Let Contract SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 02 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 02 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 03 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 03 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 03 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 04 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 04 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 04 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 05 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 05 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 05 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 06 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 06 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 06 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 07 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 07 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 07 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 08 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide District Let Contracts SubTotal |  |  |  |  | 1 | 1 | 5 | 890 | 1143 | 1143 | 100% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 0 | 800% | 8 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852
| Statewide Totals |  |  |  |  | 1 | 1 | 5 | 890 | 1143 | 1143 | 100% | 1 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 0 | 1500% | 15 | -71423852 | -187553 | 155 | 58 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339346 | 0 | 28 | 12 | -153550 | 12852

## Sheet1 (hidden)
01CO | 01 | T1552 | 40631475201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 164 | 200 | -36 | 36 | 0 | 10 | 4 | 2579468 | 50000 | 2529468 | 2579468 | 2493565 | -85464 | 0 | -85464 | 2408101 | 2408101 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2016-12-14 | QTR2 | 16/17 |  | 2014-09-12 | QTR1 | 14/15 | 115 | 3076291.38 |  |  | 4 | 3 | 0 | 0 | 0 | 0 |  | CO | 21 | 01co | 1 | 21
01CO | 01 | T1560 | 42910115201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 250 | 268 | 268 | 0 | 0 | 0 | 18 | 0 | 4883160 | 57482 | 4825678 | 4883160 | 4742567 | 0 | 0 | 0 | 4742567 | 4581604 | -160964 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 118 | 5451824.59 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO | 5 | 01do | 22 | 26
01CO | 01 | T1583 | 42910715201 | 2014-05-21 | QTR4 | 13/14 | 2 | 12 | 365 | 542 | 598 | -56 | 56 | 0 | 106 | 71 | 12221582 | 124617 | 12096965 | 12321397 | 12316064 | -258944 | 0 | -258944 | 12057120 | 11369478 | -687643 | 99815 | 77 | 0 | 55 | 73297 | 0 | 0 | 16 | 102194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 177856 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 108 | 11851721.99 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO | 16 | 02co | 27 | 42
01CO | 01 | T1587 | 42913115201 | 2014-03-26 | QTR3 | 13/14 | 2 | 7 | 185 | 230 | 226 | 4 | 0 | 0 | 36 | 9 | 4576900 | 50000 | 4526900 | 4273384 | 4255627 | 0 | 0 | 0 | 4255627 | 4165417 | -90210 | -303516 | 25 | 0 | 6 | 199569 | 39215 | 0 | 3 | -504411 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | -277723 | 58709 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-01 | QTR2 | 16/17 |  | 2015-04-29 | QTR4 | 14/15 | 115 | 5166652.25 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO | 10 | 02do | 43 | 52
01CO | 01 | T1588 | 41304225201 | 2014-06-18 | QTR4 | 13/14 | 2 | 7 | 680 | 710 | 591 | 119 | 0 | 0 | 46 | -16 | 24169365 | 150000 | 24019365 | 23023182 | 22613781 | 0 | 900000 | 900000 | 23513781 | 20785082 | -2728699 | -1146183 | 1 | 0 | -16 | -1426521 | 0 | 0 | 0 | 288694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | -1137827 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 |  | 2016-08-25 | QTR1 | 16/17 | 106 | 29188895.88 | B2:B5:B2 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING) | 0 | 8 | 0 | 0 | 0 | 0 |  | CO | 18 | 03co | 53 | 70
01CO | 01 | T1595 | 40631345201 | 2015-03-25 | QTR3 | 14/15 | 1 | 6 | 525 | 556 | 395 | 161 | 0 | 0 | 47 | -16 | 31929262 | 150000 | 31779262 | 31614976 | 31607283 | 0 | 1300000 | 1300000 | 32907283 | 30894410 | -2012872 | -314286 | 36 | 0 | -16 | 17006 | 0 | 0 | 0 | 270841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | -196174 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-10-25 | QTR2 | 16/17 |  | 2016-07-13 | QTR1 | 16/17 | 106 | 30769490.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | -491717 | 0 |  | CO | 22 | 03do | 71 | 92
01CO | 01 | T1596 | 43142215201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 250 | 349 | 348 | 1 | 0 | 0 | 74 | 25 | 5571174 | 56174 | 5515000 | 5623674 | 5636689 | 0 | 0 | 0 | 5636689 | 5437906 | -198783 | 52500 | 61 | 0 | 25 | 48439 | 0 | 0 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 100939 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-11-21 | QTR2 | 16/17 |  | 2016-05-28 | QTR4 | 15/16 | 113 | 5411862.18 | B0 | ACC - LUMP SUM | 25 | 13 | 0 | 0 | 0 | 0 |  | CO | 8 | 04co | 93 | 100
01CO | 01 | T1597 | 43356115201 | 2015-02-25 | QTR3 | 14/15 | 1 | 2 | 115 | 551 | 519 | 32 | 0 | 0 | 413 | 23 | 737000 | 0 | 737000 | 989001 | 989001 | 0 | 0 | 0 | 989001 | 989001 | 0 | 252001 | 394 | 0 | 1 | 3000 | 0 | 0 | 22 | 249001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 252001 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-11-28 | QTR2 | 16/17 |  | 2016-10-25 | QTR2 | 16/17 | 108 | 596982.85 | B0 | ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 |  | CO | 7 | 04do | 101 | 107
01CO | 01 | T1601 | 42910615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 0 | 180 | 206 | 206 | 0 | 0 | 0 | 26 | 0 | 2560715 | 50000 | 2510715 | 2560715 | 2601322 | 0 | 0 | 0 | 2601322 | 2476584 | -124738 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 108 | 2539521.53 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO | 12 | 05co | 108 | 119
01CO | 01 | T1604 | 43340715201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 130 | 138 | 139 | -1 | 1 | 0 | 11 | -3 | 1272557 | 50000 | 1222557 | 1265786 | 1215247 | 0 | 0 | 0 | 1215247 | 1215247 | 0 | -6770 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -6770 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-20 | QTR4 | 15/16 | 113 | 1175938.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 1 | 0 | -3 | -6770 | 0 | T | CO | 8 | 05do | 120 | 127
01CO | 01 | T1610 | 43337615201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 140 | 157 | 173 | -16 | 16 | 0 | 17 | 0 | 766880 | 38788 | 728092 | 763925 | 702653 | -27872 | 0 | -27872 | 674781 | 674781 | 0 | -2956 | 10 | 0 | 0 | -73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2956 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-28 | QTR4 | 15/16 | 108 | 1032307.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO | 11 | 06co | 128 | 138
01CO | 01 | T1612 | 43539315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 2 | 139 | 163 | 162 | 1 | 0 | 0 | 24 | 0 | 965039 | 0 | 965039 | 965864 | 949501 | 0 | 0 | 0 | 949501 | 941761 | -7741 | 825 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-05 | QTR1 | 16/17 |  | 2016-04-14 | QTR4 | 15/16 | 113 | 968994.66 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 4 | 06do | 139 | 142
01CO | 01 | T1615 | 42950615201 | 2015-06-17 | QTR4 | 14/15 | 2 | 0 | 150 | 184 | 184 | 0 | 0 | 0 | 34 | 0 | 1470894 | 50000 | 1420894 | 1470894 | 1424904 | 0 | 0 | 0 | 1424904 | 1424904 | 0 | 0 | 30 | 0 | 0 | 3080 | 0 | 0 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4010 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-07-05 | QTR1 | 16/17 | 115 | 1441634.98 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO | 13 | 07co | 143 | 155
01CO | 01 | T1617 | 43337515201 | 2015-06-17 | QTR4 | 14/15 | 1 | 2 | 150 | 170 | 169 | 1 | 0 | 0 | 20 | 0 | 1087453 | 50000 | 1037453 | 1211375 | 1165751 | 0 | 0 | 0 | 1165751 | 1165751 | 0 | 123922 | 11 | 0 | 0 | 135887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128298 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 108 | 1092794.1 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 18 | 07do | 156 | 173
01CO | 01 | T1618 | 43340815201 | 2015-06-17 | QTR4 | 14/15 | 2 | 2 | 150 | 185 | 185 | 0 | 0 | 0 | 28 | 7 | 1135821 | 50000 | 1085821 | 1138128 | 1108067 | 0 | 0 | 0 | 1108067 | 1103946 | -4121 | 2307 | 17 | 0 | 4 | 3712 | 0 | 0 | 3 | 18533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 22246 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 108 | 1209049.68 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 7 | 11 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 174 | 173
01CO | 01 | T1619 | 43365815201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 145 | 172 | 171 | 1 | 0 | 0 | 27 | 0 | 618558 | 0 | 618558 | 622340 | 622340 | 0 | 0 | 0 | 622340 | 622340 | 0 | 3782 | 7 | 2 | 0 | 3782 | 3782 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 3782 | 3782 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-10-05 | QTR2 | 16/17 | 108 | 495886.08 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO | 6 | 08do | 174 | 179
01CO | 01 | T1629 | 43325615201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 85 | 88 | 74 | 14 | 0 | 0 | 3 | 0 | 910000 | 47212 | 862788 | 910000 | 883227 | 0 | 0 | 0 | 883227 | 883227 | 0 | 0 | 3 | 0 | 0 | 13198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13198 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-28 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 115 | 857875.38 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1651 | 43134115201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 90 | 91 | 78 | 13 | 0 | 0 | 1 | 0 | 194630 | 9734 | 184896 | 194630 | 184896 | 0 | 0 | 0 | 184896 | 184896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-06-06 | QTR4 | 15/16 | 118 | 236550.37 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1659 | 43472815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 70 | 78 | 49 | 29 | 0 | 0 | 8 | 0 | 238287 | 9912 | 228375 | 238287 | 228375 | 0 | 0 | 0 | 228375 | 228375 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 |  | 2016-10-17 | QTR2 | 16/17 | 115 | 176436.4 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1A02 | 42518315201 | 2014-12-03 | QTR2 | 14/15 | 1 | 4 | 250 | 403 | 402 | 1 | 0 | 0 | 75 | 78 | 5396928 | 50000 | 5346928 | 5491707 | 5952983 | 0 | 0 | 0 | 5952983 | 5952455 | -528 | 94779 | 57 | 0 | 75 | 18567 | 0 | 0 | 3 | 122779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 141346 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-05-19 | QTR4 | 15/16 | 115 | 4358786.71 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A15 | 43325515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 70 | 97 | 97 | 0 | 0 | 0 | 27 | 0 | 219504 | 10504 | 209000 | 219504 | 213917 | 0 | 0 | 0 | 213917 | 213917 | 0 | 0 | 15 | 0 | 0 | 4917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4917 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-02-20 | QTR3 | 15/16 | 106 | 200589.29 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1N36 | 43544915201 | 2014-06-19 | QTR4 | 13/14 | 1 | 2 | 160 | 182 | 194 | -12 | 12 | 0 | 16 | 6 | 1877203 | 50000 | 1827203 | 1918177 | 1843430 | -20904 | 0 | -20904 | 1822526 | 1821939 | -587 | 40974 | 7 | 0 | 0 | 0 | 0 | 0 | 6 | 46084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 46084 | 0 | F593586613 | EVANS CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 |  | 2015-05-19 | QTR4 | 14/15 | 108 | 2352808.24 |  |  | 3 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N74 | 42912015201 | 2014-12-18 | QTR2 | 14/15 | 1 | 0 | 185 | 212 | 212 | 0 | 0 | 0 | 27 | 0 | 3107573 | 50000 | 3057573 | 3107573 | 3110593 | 0 | 0 | 0 | 3110593 | 2961957 | -148636 | 0 | 9 | 0 | 0 | 7628 | 0 | 0 | 0 | 8425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16053 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-01-21 | QTR3 | 15/16 | 113 | 3280021.43 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N87 | 43120915201 | 2015-02-19 | QTR3 | 14/15 | 1 | 0 | 300 | 336 | 336 | 0 | 0 | 0 | 36 | 0 | 3172000 | 50000 | 3122000 | 3172000 | 3272265 | 0 | 0 | 0 | 3272265 | 3269380 | -2886 | 0 | 24 | 0 | 0 | 7188 | 0 | 0 | 0 | 21276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40644 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-25 | QTR4 | 15/16 | 108 | 3312411.11 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O02 | 43161515201 | 2015-01-15 | QTR3 | 14/15 | 1 | 2 | 290 | 354 | 354 | 0 | 0 | 0 | 34 | 30 | 5445703 | 56538 | 5389165 | 6533716 | 6114803 | 0 | 0 | 0 | 6114803 | 5883385 | -231419 | 1088013 | 19 | 0 | 20 | 396717 | 0 | 0 | 10 | 691296 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1088013 | 691296 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 113 | 4971481.53 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O75 | 43503815201 | 2016-01-21 | QTR3 | 15/16 | 1 | 0 | 60 | 62 | 54 | 8 | 0 | 0 | 2 | 0 | 149955 | 6815 | 143140 | 149955 | 147793 | 0 | 0 | 0 | 147793 | 147793 | 0 | 0 | 1 | 0 | 0 | 6813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6813 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-06-21 | QTR4 | 15/16 | 118 | 157973.52 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2506 | 43040415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 45 | 48 | 103 | -55 | 55 | 0 | 3 | 0 | 136157 | 7800 | 128357 | 136157 | 128357 | -47602 | 0 | -47602 | 80754 | 80754 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-09-14 | QTR1 | 16/17 |  | 2014-05-14 | QTR4 | 13/14 | 208 | 153002.52 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2533 | 43355415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 3 | 400 | 535 | 535 | 0 | 0 | 0 | 117 | 18 | 8533240 | 72079 | 8461162 | 8598881 | 9356445 | 0 | 0 | 0 | 9356445 | 9207548 | -148897 | 65641 | 58 | 0 | 0 | 229 | 0 | 0 | 18 | 64256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 46705 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 208 | 7794225.55 |  |  | 0 | 59 | 0 | 0 | -19692 | 0 |  | CO
02CO | 02 | T2538 | 42696315201 | 2014-06-18 | QTR4 | 13/14 | 2 | 0 | 130 | 198 | 198 | 0 | 0 | 0 | 65 | 3 | 3648202 | 50000 | 3598202 | 3648202 | 3611865 | 0 | 0 | 0 | 3611865 | 3514982 | -96884 | 0 | 33 | 4 | 3 | 9477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 9477 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-10-05 | QTR2 | 16/17 |  | 2015-05-28 | QTR4 | 14/15 | 208 | 3330302.73 |  |  | 3 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2541 | 42607315201 | 2014-09-24 | QTR1 | 14/15 | 1 | 1 | 380 | 501 | 501 | 0 | 0 | 0 | 83 | 38 | 3641891 | 50000 | 3591891 | 3767252 | 4042041 | 0 | 0 | 0 | 4042041 | 3981696 | -60345 | 125361 | 55 | 0 | 0 | 0 | 0 | 0 | 38 | 174588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 174588 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-11-14 | QTR2 | 16/17 |  | 2016-05-26 | QTR4 | 15/16 | 209 | 3748196.45 |  |  | 8 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2567 | 43224715201 | 2015-02-25 | QTR3 | 14/15 | 1 | 8 | 135 | 252 | 252 | 0 | 0 | 0 | 79 | 38 | 1013111 | 0 | 1013111 | 1368388 | 1368010 | 0 | 0 | 0 | 1368010 | 1368010 | 0 | 355277 | 46 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-02-01 | QTR3 | 15/16 | 214 | 1004174.39 | B0 | ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2572 | 43061415201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 150 | 191 | 191 | 0 | 0 | 0 | 41 | 0 | 1990811 | 0 | 1990811 | 2002450 | 2059822 | 0 | 0 | 0 | 2059822 | 2059822 | 0 | 11638 | 21 | 0 | 0 | 11638 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 11638 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-07-21 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 214 | 1508389.63 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2584 | 43051315201 | 2015-08-26 | QTR1 | 15/16 | 2 | 1 | 150 | 186 | 185 | 1 | 0 | 0 | 14 | 22 | 3444187 | 50000 | 3394187 | 3524159 | 3538172 | 0 | 0 | 0 | 3538172 | 3415729 | -122443 | 79972 | 8 | 0 | 3 | 2309 | 0 | 0 | 19 | 89994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 92303 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-12-28 | QTR2 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 214 | 3688557.42 |  |  | 17 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2587 | 43265515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 120 | 151 | 151 | 0 | 0 | 0 | 31 | 0 | 718800 | 0 | 718800 | 718800 | 718800 | 0 | 0 | 0 | 718800 | 718800 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453689782 | SOUTHERN STATES PAVEMENT MARKINGS INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-06-02 | QTR4 | 15/16 | 209 | 769166.88 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2588 | 21237925201 | 2015-09-30 | QTR1 | 15/16 | 1 | 3 | 170 | 227 | 227 | 0 | 0 | 0 | 23 | 34 | 2271500 | 0 | 2271500 | 2329229 | 2340019 | 0 | 0 | 0 | 2340019 | 2337891 | -2128 | 57729 | 5 | 4 | 0 | 7981 | 0 | 13 | 5 | 38697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 11052 | 11052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 34 | 57729 | 11052 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-11-29 | QTR2 | 16/17 |  | 2016-08-17 | QTR1 | 16/17 | 208 | 2754838.98 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2589 | 41525415201 | 2015-12-03 | QTR2 | 15/16 | 2 | 2 | 250 | 256 | 224 | 32 | 0 | 0 | 6 | 0 | 1503905 | 0 | 1503905 | 1530011 | 1553775 | 0 | 0 | 0 | 1553775 | 1554113 | 338 | 26105 | 3 | 0 | 0 | 26105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26105 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 |  | 2016-10-04 | QTR2 | 16/17 | 208 | 1346460.02 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2593 | 43051715201 | 2015-09-30 | QTR1 | 15/16 | 3 | 2 | 179 | 211 | 210 | 1 | 0 | 0 | 22 | 10 | 1956915 | 0 | 1956915 | 1997332 | 1951682 | 0 | 0 | 0 | 1951682 | 1947009 | -4672 | 40417 | 19 | 0 | 10 | 40417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 40417 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-16 | QTR2 | 16/17 |  | 2016-08-01 | QTR1 | 16/17 | 209 | 2334094.44 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2594 | 43265415201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 152 | 152 | 0 | 0 | 0 | 32 | 0 | 475000 | 0 | 475000 | 475000 | 475000 | 0 | 0 | 0 | 475000 | 475000 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-09-30 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 209 | 428505.77 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2602 | 43074515201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 100 | 114 | 113 | 1 | 0 | 0 | 14 | 0 | 558858 | 27404 | 531454 | 558858 | 508320 | 0 | 0 | 0 | 508320 | 508320 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-10-17 | QTR2 | 16/17 | 209 | 579077.38 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2603 | 43075915201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 95 | 95 | 0 | 0 | 0 | 6 | 14 | 521218 | 23780 | 497438 | 521218 | 506672 | 0 | 0 | 0 | 506672 | 506672 | 0 | 0 | 3 | 0 | 10 | 1681 | 0 | 0 | 0 | 7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 9235 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-07-01 | QTR1 | 16/17 | 214 | 510081.72 |  |  | 14 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2604 | 43226115201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 200 | 233 | 237 | -4 | 4 | 0 | 27 | 6 | 7717554 | 101575 | 7615979 | 7717554 | 7824593 | -15080 | 0 | -15080 | 7809513 | 7576665 | -232848 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-27 | QTR2 | 16/17 |  | 2016-09-07 | QTR1 | 16/17 | 209 | 9660990.21 |  |  | 6 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2608 | 43055825201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 84 | 80 | 4 | 0 | 0 | 9 | 0 | 148375 | 8369 | 140006 | 148375 | 138616 | 0 | 0 | 0 | 138616 | 138616 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 209 | 178082.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2P99 | 21330125201 | 2012-06-29 | QTR4 | 11/12 | 2 | 7 | 615 | 1443 | 1443 | 0 | 0 | 0 | 201 | 627 | 17859000 | 150000 | 17709000 | 27306925 | 27318877 | 0 | 0 | 0 | 27318877 | 26689964 | -628913 | 9447925 | 119 | 0 | 627 | 9078926 | 2177986 | 0 | 0 | 325187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0 | 0 | 2873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627 | 9579662 | 2177986 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-12-14 | QTR2 | 16/17 |  | 2016-08-09 | QTR1 | 16/17 | 208 | 28650000 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 82 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R04 | 21066125201 | 2012-12-12 | QTR2 | 12/13 | 2 | 1 | 90 | 192 | 224 | -32 | 32 | 0 | 32 | 70 | 1430432 | 50000 | 1380432 | 1430840 | 1393606 | -49024 | 0 | -49024 | 1344582 | 1344578 | -4 | 408 | 14 | 3 | 0 | 4074 | 0 | 0 | 70 | 21643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 70 | 25716 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 | 07/17/2014 | 2014-03-07 | QTR3 | 13/14 | 208 | 1293927.32 |  |  | 70 | 15 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R17 | 21237935201 | 2013-06-20 | QTR4 | 12/13 | 5 | 1 | 790 | 846 | 846 | 0 | 0 | 0 | 56 | 0 | 11440230 | 150000 | 11290230 | 11429587 | 11316805 | 0 | 0 | 0 | 11316805 | 11261013 | -55793 | -10643 | 7 | 0 | 0 | -621 | 0 | 0 | 0 | 42964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32321 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2015-12-07 | QTR2 | 15/16 | 208 | 13890662.92 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR | 0 | 49 | 0 | 0 | -11541 | 0 |  | DO
02DO | 02 | E2T58 | 43226315201 | 2015-11-18 | QTR2 | 15/16 | 1 | 0 | 140 | 181 | 181 | 0 | 0 | 0 | 41 | 0 | 3757549 | 50000 | 3707549 | 3757549 | 3830766 | 0 | 0 | 0 | 3830766 | 3684887 | -145879 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-10-11 | QTR2 | 16/17 |  | 2016-09-08 | QTR1 | 16/17 | 214 | 4878401.01 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T69 | 43041715201 | 2015-07-15 | QTR1 | 15/16 | 1 | 3 | 210 | 362 | 362 | 0 | 0 | 0 | 30 | 122 | 1759555 | 50000 | 1709555 | 1996713 | 2571252 | 0 | 0 | 0 | 2571252 | 2563560 | -7693 | 237158 | 11 | 0 | 18 | 101267 | 0 | 0 | 104 | 148934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 250201 | 0 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 |  | 2016-09-16 | QTR1 | 16/17 | 208 | 1357063.07 |  |  | 29 | 13 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T70 | 43219415201 | 2015-07-15 | QTR1 | 15/16 | 1 | 0 | 190 | 217 | 214 | 3 | 0 | 0 | 23 | 4 | 741630 | 36943 | 704687 | 741630 | 709180 | 0 | 0 | 0 | 709180 | 709010 | -170 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 214 | 775810 |  |  | 4 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T74 | 42342715201 | 2015-09-16 | QTR1 | 15/16 | 1 | 0 | 135 | 163 | 162 | 1 | 0 | 0 | 28 | 0 | 4336630 | 50000 | 4286630 | 4336630 | 4421132 | 0 | 0 | 0 | 4421132 | 4255700 | -165433 | 0 | 27 | 0 | 0 | 17388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17388 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-28 | QTR1 | 16/17 |  | 2016-06-13 | QTR4 | 15/16 | 209 | 4754490.59 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T87 | 20967415201 | 2015-11-18 | QTR2 | 15/16 | 1 | 0 | 140 | 199 | 198 | 1 | 0 | 0 | 34 | 25 | 1743906 | 50000 | 1693906 | 1743906 | 2125210 | 0 | 0 | 0 | 2125210 | 2124106 | -1104 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 21 | 39680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 41424 | 0 | F205877898 | KIRBY DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 |  | 2016-08-24 | QTR1 | 16/17 | 208 | 1607950.75 |  |  | 25 | 4 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T90 | 20838945201 | 2015-12-16 | QTR2 | 15/16 | 1 | 0 | 185 | 192 | 155 | 37 | 0 | 0 | 7 | 0 | 559753 | 48363 | 511389 | 559753 | 512091 | 0 | 0 | 0 | 512091 | 512091 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593285921 | S & D INDUSTRIAL PAINTING INC. | N/A | N/A | N/A | N/A | 2016-11-08 | QTR2 | 16/17 |  | 2016-10-03 | QTR2 | 16/17 | 209 | 1034491.52 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U45 | 42871125201 | 2015-12-16 | QTR2 | 15/16 | 1 | 0 | 45 | 53 | 211 | -158 | 158 | 0 | 7 | 1 | 138261 | 7135 | 131126 | 138261 | 134115 | -43856 | 0 | -43856 | 90258 | 120111 | 29853 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2989 | 0 | Z31-0396250 | OHIO CASUALTY INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-21 | QTR2 | 16/17 | 208 | 151023.35 | B0 | ACC - LUMP SUM | 1 | 2 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3349 | 22041285201 | 2010-12-08 | QTR2 | 10/11 | 3 | 28 | 835 | 1802 | 1804 | -2 | 2 | 0 | 381 | 586 | 7357219 | 72479 | 7284740 | 10528722 | 10638848 | -93018 | 0 | -93018 | 10545830 | 10537771 | -8059 | 3171503 | 203 | 0 | 428 | 2195488 | 844067 | 0 | 120 | 436311 | 60348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 81300 | 13615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 365823 | 185379 | 97 | 0 | 126858 | 126858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 586 | 3205779 | 1230267 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-03-11 | QTR3 | 15/16 | 308 | 7320354.71 | ARRA | AMERICAN RECOVERY AND REINVEST | 49 | 81 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3375 | 42124315201 | 2012-02-29 | QTR3 | 11/12 | 3 | 3 | 1194 | 1402 | 1400 | 2 | 0 | 0 | 170 | 38 | 14736078 | 150000 | 14586078 | 15035632 | 14669101 | 0 | 0 | 0 | 14669101 | 14620764 | -48338 | 299554 | 105 | 0 | 38 | 320021 | 0 | 0 | 0 | 102024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59292 | 0 | 0 | 0 | 7231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 371313 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-30 | QTR4 | 15/16 | 308 | 18080147.32 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3398 | 22016225201 | 2013-09-25 | QTR1 | 13/14 | 1 | 4 | 310 | 940 | 940 | 0 | 0 | 0 | 415 | 215 | 3358717 | 50000 | 3308717 | 4155082 | 4026349 | 0 | 0 | 0 | 4026349 | 3996594 | -29755 | 796365 | 165 | 27 | 211 | 787219 | 726197 | 5 | 3 | 10636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 1 | -14634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 215 | 783220 | 726197 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-07 | QTR2 | 16/17 |  | 2016-08-02 | QTR1 | 16/17 | 308 | 2823245.81 |  |  | 6 | 37 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3418 | 42551915201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 350 | 475 | 472 | 3 | 0 | 0 | 125 | 0 | 2589441 | 50000 | 2539441 | 2672648 | 2648983 | 0 | 0 | 0 | 2648983 | 2635144 | -13838 | 83207 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-07-06 | QTR1 | 16/17 | 308 | 2582602.98 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3427 | 42164415201 | 2013-07-31 | QTR1 | 13/14 | 4 | 2 | 475 | 888 | 888 | 0 | 0 | 0 | 369 | 44 | 11476305 | 126776 | 11349528 | 11609159 | 11286785 | -11250 | 0 | -11250 | 11275535 | 10699458 | -576077 | 132854 | 265 | 0 | 19 | 140137 | 0 | 0 | 15 | 65665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 12852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 44 | 228449 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 308 | 12800389.92 |  |  | 42 | 91 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3433 | 42693025201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 285 | 368 | 375 | -7 | 7 | 0 | 80 | 3 | 4985043 | 60566 | 4924478 | 5040858 | 4902106 | -20132 | 0 | -20132 | 4881974 | 4555909 | -326064 | 55814 | 53 | 0 | 3 | 55814 | 15953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 64944 | 15953 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-24 | QTR2 | 16/17 |  | 2016-05-21 | QTR4 | 15/16 | 321 | 6115127.23 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3443 | 42693415201 | 2014-12-03 | QTR2 | 14/15 | 2 | 1 | 247 | 408 | 408 | 0 | 0 | 0 | 143 | 18 | 4037987 | 50000 | 3987987 | 4183812 | 4167957 | 0 | 0 | 0 | 4167957 | 3846478 | -321479 | 145825 | 106 | 13 | 17 | 28230 | 0 | 3 | 1 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18 | 175160 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 308 | 4397278.78 |  |  | 18 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3460 | 42874715201 | 2016-03-30 | QTR3 | 15/16 | 2 | 0 | 120 | 140 | 137 | 3 | 0 | 0 | 19 | 1 | 1335414 | 50000 | 1285414 | 1335414 | 1301394 | 0 | 0 | 0 | 1301394 | 1295632 | -5762 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 1 | 5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5544 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 |  | 2016-11-04 | QTR2 | 16/17 | 321 | 1593999.48 |  |  | 1 | 5 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3482 | 42884515201 | 2015-01-28 | QTR3 | 14/15 | 2 | 1 | 300 | 396 | 388 | 8 | 0 | 0 | 96 | 0 | 7416925 | 85537 | 7331389 | 7437265 | 7758460 | -880 | 0 | -880 | 7757580 | 7441692 | -315888 | 20339 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 27217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30580 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 313 | 8733987.91 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3483 | 43077715201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 250 | 386 | 386 | 0 | 0 | 0 | 115 | 21 | 4039522 | 50000 | 3989522 | 4047995 | 4269663 | 0 | 0 | 0 | 4269663 | 4226492 | -43171 | 8473 | 57 | 12 | 10 | 55493 | 0 | 1 | 4 | 4180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30674 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 21 | 28999 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-05 | QTR2 | 16/17 |  | 2016-08-24 | QTR1 | 16/17 | 314 | 3857910.06 |  |  | 14 | 45 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3495 | 42695615201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 90 | 226 | 225 | 1 | 0 | 0 | 136 | 0 | 1619321 | 50000 | 1569321 | 1619321 | 1588249 | 0 | 0 | 0 | 1588249 | 1566711 | -21538 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-05-18 | QTR4 | 15/16 | 321 | 1991519.93 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3514 | 43078115201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 175 | 307 | 308 | -1 | 1 | 0 | 132 | 0 | 3802689 | 50000 | 3752689 | 3802689 | 3624193 | 0 | 0 | 0 | 3624193 | 3479143 | -145050 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 |  | 2016-07-23 | QTR1 | 16/17 | 314 | 4144189.92 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3515 | 43090835201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 240 | 568 | 567 | 1 | 0 | 0 | 314 | 14 | 8076272 | 85662 | 7990610 | 8066272 | 8349102 | 0 | 0 | 0 | 8349102 | 7667982 | -681120 | -10000 | 119 | 1 | 14 | 68182 | 0 | 0 | 0 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 14 | 58182 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 313 | 8827284.67 |  |  | 14 | 54 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3539 | 22243945201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 90 | 205 | 205 | 0 | 0 | 0 | 66 | 49 | 1948263 | 50000 | 1898263 | 1965454 | 2004975 | 0 | 0 | 0 | 2004975 | 2004975 | 0 | 17192 | 50 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 45708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 49 | 45708 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-07-28 | QTR1 | 16/17 | 308 | 1870760.28 |  |  | 49 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3551 | 42873915201 | 2015-03-25 | QTR3 | 14/15 | 3 | 4 | 175 | 297 | 304 | -7 | 7 | 0 | 118 | 4 | 2525492 | 50000 | 2475492 | 2696693 | 2810548 | -29132 | 0 | -29132 | 2781416 | 2626488 | -154929 | 171200 | 58 | 22 | 0 | 31909 | 0 | 11 | 4 | 152138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 4 | 201162 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-01 | QTR2 | 16/17 |  | 2016-04-10 | QTR4 | 15/16 | 321 | 3044222.49 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3552 | 43273715201 | 2015-07-29 | QTR1 | 15/16 | 1 | 1 | 125 | 237 | 237 | 0 | 0 | 0 | 101 | 11 | 3670000 | 50000 | 3620000 | 3738760 | 3752339 | -5200 | 0 | -5200 | 3747139 | 3621209 | -125930 | 68760 | 66 | 0 | 7 | 27730 | 0 | 0 | 4 | 70531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 98576 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-10 | QTR2 | 16/17 |  | 2016-06-11 | QTR4 | 15/16 | 308 | 4236500 |  |  | 7 | 35 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3589 | 43174315201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 120 | 126 | 77 | 49 | 0 | 0 | 6 | 0 | 169047 | 0 | 169047 | 169047 | 169047 | 0 | 0 | 0 | 169047 | 169047 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 321 | 199840.42 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9009 | 43035625201 | 2015-06-24 | QTR4 | 14/15 | 1 | 0 | 240 | 330 | 299 | 31 | 0 | 0 | 90 | 0 | 1500230 | 50000 | 1450230 | 1500230 | 1507255 | 0 | 0 | 0 | 1507255 | 1507255 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 14 | 0 | 29504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 49973 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 314 | 1868902.5 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3K73 | 42693515201 | 2014-03-13 | QTR3 | 13/14 | 2 | 1 | 200 | 344 | 344 | 0 | 0 | 0 | 125 | 19 | 1221881 | 50000 | 1171881 | 1231781 | 1143560 | 0 | 0 | 0 | 1143560 | 1120620 | -22940 | 9900 | 106 | 0 | 0 | 0 | 0 | 0 | 19 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 10560 | 6600 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2015-06-14 | QTR4 | 14/15 | 308 | 1514949.05 |  |  | 19 | 19 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L90 | 42840315201 | 2013-06-28 | QTR4 | 12/13 | 1 | 3 | 534 | 975 | 975 | 0 | 0 | 0 | 304 | 137 | 24049000 | 150000 | 23899000 | 24338104 | 24337828 | 0 | 0 | 0 | 24337828 | 24337642 | -186 | 289104 | 165 | 0 | 0 | 10000 | 0 | 20 | 0 | 59678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 363800 | 298854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 137 | 438828 | 298854 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2016-08-30 | QTR1 | 16/17 |  | 2016-04-26 | QTR4 | 15/16 | 313 | 21314871.51 | A3 | ICC - DESIGN/BUILD - MINOR | 21 | 64 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M17 | 40747845201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 90 | 109 | 107 | 2 | 0 | 0 | 19 | 0 | 149498 | 7779 | 141719 | 149498 | 139613 | 0 | 0 | 0 | 139613 | 139613 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455085205 | PRINCIPLE PROPERTIES INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-06-08 | QTR4 | 15/16 | 308 | 163264.04 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M30 | 42429125201 | 2015-02-26 | QTR3 | 14/15 | 2 | 1 | 300 | 535 | 534 | 1 | 0 | 0 | 115 | 120 | 4578636 | 50636 | 4528000 | 5834533 | 5832583 | 0 | 0 | 0 | 5832583 | 5832583 | 0 | 1255897 | 89 | 0 | 0 | 0 | 0 | 0 | 120 | 1304583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1304583 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-28 | QTR2 | 16/17 | 308 | 4578636 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M55 | 42805825201 | 2014-01-31 | QTR3 | 13/14 | 1 | 1 | 265 | 629 | 628 | 1 | 0 | 0 | 211 | 153 | 1540571 | 50000 | 1490571 | 1579254 | 1571464 | 0 | 0 | 0 | 1571464 | 1571464 | 0 | 38683 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-01-19 | QTR3 | 15/16 | 308 | 1529160 | A3 | ICC - DESIGN/BUILD - MINOR | 65 | 20 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M95 | 41694315201 | 2015-07-09 | QTR1 | 15/16 | 1 | 3 | 140 | 240 | 239 | 1 | 0 | 0 | 73 | 27 | 2738862 | 50000 | 2688862 | 3014082 | 3595051 | 0 | 0 | 0 | 3595051 | 3484491 | -110560 | 275220 | 36 | 0 | 0 | 0 | 0 | 0 | 5 | 288220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 12155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 287375 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-19 | QTR1 | 16/17 |  | 2016-06-27 | QTR4 | 15/16 | 314 | 3204695.35 |  |  | 22 | 37 | 0 | 0 | -13000 | 0 |  | DO
03DO | 03 | E3N17 | 43392715201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 65 | 65 | 50 | 15 | 0 | 0 | 2 | -2 | 1734968 | 50000 | 1684968 | 1417537 | 1360898 | 0 | 0 | 0 | 1360898 | 1360898 | 0 | -317430 | 2 | 0 | -2 | -313024 | 0 | 0 | 0 | 4578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | -308196 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-05-23 | QTR4 | 15/16 | 321 | 1346663.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N18 | 43391815201 | 2015-10-08 | QTR2 | 15/16 | 1 | 1 | 65 | 117 | 116 | 1 | 0 | 0 | 31 | 21 | 1245237 | 49942 | 1195296 | 1323870 | 1408799 | 0 | 0 | 0 | 1408799 | 1408799 | 0 | 78633 | 30 | 0 | 21 | 108680 | 16182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 108680 | 16182 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-01 | QTR4 | 15/16 | 308 | 1048525.47 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N27 | 41627215201 | 2015-03-25 | QTR3 | 14/15 | 2 | 2 | 305 | 427 | 427 | 0 | 0 | 0 | 72 | 50 | 2233345 | 43949 | 2189396 | 2293381 | 2249432 | 0 | 0 | 0 | 2249432 | 2223244 | -26188 | 60036 | 41 | 0 | 0 | 0 | 0 | 0 | 50 | 60036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 60036 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 321 | 2172218.95 | A3:LBDB:A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N39 | 43078815201 | 2015-05-14 | QTR4 | 14/15 | 2 | 2 | 185 | 318 | 294 | 24 | 0 | 0 | 133 | 0 | 3111936 | 50000 | 3061936 | 3033818 | 2963684 | -11504 | 0 | -11504 | 2952180 | 2882199 | -69981 | -78118 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 18424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | -78118 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-20 | QTR4 | 15/16 | 314 | 3291622.83 |  |  | 0 | 41 | 0 | 0 | -96542 | 0 |  | DO
03DO | 03 | E3N42 | 21791185201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 75 | 124 | 107 | 17 | 0 | 0 | 49 | 0 | 762045 | 50000 | 712045 | 762045 | 712000 | 0 | 0 | 0 | 712000 | 712000 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 |  | 2016-09-09 | QTR1 | 16/17 | 314 | 1488724.75 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N73 | 43078715201 | 2015-05-14 | QTR4 | 14/15 | 1 | 2 | 245 | 350 | 350 | 0 | 0 | 0 | 102 | 3 | 4943758 | 50000 | 4893758 | 4974205 | 5018776 | -2400 | 0 | -2400 | 5016376 | 4741701 | -274675 | 30447 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 40031 | 29279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 3 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 34041 | 29279 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 314 | 4773076.33 |  |  | 3 | 21 | 0 | 0 | -8991 | 0 |  | DO
03DO | 03 | E3N74 | 42696915201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 125 | 164 | 164 | 0 | 0 | 0 | 39 | 0 | 2813937 | 50000 | 2763937 | 2813937 | 2913809 | 0 | 0 | 0 | 2913809 | 2837766 | -76042 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 308 | 3196208.79 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N76 | 41557535201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 180 | 207 | 132 | 75 | 0 | 0 | 27 | 0 | 1819446 | 50000 | 1769446 | 1819446 | 1750296 | 0 | 0 | 0 | 1750296 | 1750297 | 1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-08-28 | QTR1 | 16/17 | 308 | 1571362.8 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N80 | 42577825201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 60 | 79 | 87 | -8 | 8 | 0 | 19 | 0 | 246955 | 8741 | 238214 | 246955 | 248745 | -7664 | 0 | -7664 | 241081 | 241081 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | F208328161 | AN-KAR CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 308 | 183110.5 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O14 | 41040925201 | 2015-09-24 | QTR1 | 15/16 | 2 | 2 | 180 | 214 | 205 | 9 | 0 | 0 | 27 | 7 | 1815481 | 50000 | 1765481 | 1830051 | 1851635 | 0 | 0 | 0 | 1851635 | 1847209 | -4426 | 14570 | 20 | 0 | 0 | 4627 | 0 | 0 | 4 | 46652 | 9517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 13292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 64570 | 9517 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-11-16 | QTR2 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 321 | 1670231.68 |  |  | 3 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O47 | 43253815201 | 2015-10-15 | QTR2 | 15/16 | 1 | 0 | 100 | 128 | 128 | 0 | 0 | 0 | 28 | 0 | 2030029 | 50000 | 1980029 | 2030029 | 2131829 | 0 | 0 | 0 | 2131829 | 2045055 | -86775 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-12 | QTR1 | 16/17 | 321 | 2649534.01 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O53 | 43254815201 | 2015-09-10 | QTR1 | 15/16 | 1 | 0 | 125 | 173 | 173 | 0 | 0 | 0 | 48 | 0 | 2754000 | 50000 | 2704000 | 2754000 | 2779810 | 0 | 0 | 0 | 2779810 | 2686704 | -93106 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-24 | QTR2 | 16/17 |  | 2016-06-24 | QTR4 | 15/16 | 314 | 3103650 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O62 | 43079215201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 90 | 131 | 129 | 2 | 0 | 0 | 24 | 17 | 1298500 | 50000 | 1248500 | 1382401 | 1347119 | 0 | 0 | 0 | 1347119 | 1319720 | -27399 | 83901 | 17 | 0 | 17 | 83901 | 15601 | 0 | 0 | 3826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 87727 | 15601 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-08 | QTR1 | 16/17 |  | 2016-07-11 | QTR1 | 16/17 | 321 | 1564334.7 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P32 | 42460825201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 40 | 51 | 48 | 3 | 0 | 0 | 11 | 0 | 69197 | 6233 | 62964 | 69197 | 67195 | 0 | 0 | 0 | 67195 | 67195 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-01 | QTR1 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 321 | 143399.73 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P60 | 43255315201 | 2016-08-11 | QTR1 | 16/17 | 1 | 0 | 45 | 48 | 43 | 5 | 0 | 0 | 3 | 0 | 966283 | 42737 | 923546 | 966283 | 955206 | -1500 | 0 | -1500 | 953706 | 953706 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-19 | QTR2 | 16/17 |  | 2016-11-14 | QTR2 | 16/17 | 314 | 939110.13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P85 | 43627415201 | 2016-04-14 | QTR4 | 15/16 | 1 | 0 | 35 | 44 | 43 | 1 | 0 | 0 | 9 | 0 | 218815 | 9015 | 209800 | 218815 | 209764 | 0 | 0 | 0 | 209764 | 209764 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-06 | QTR2 | 16/17 |  | 2016-08-20 | QTR1 | 16/17 | 308 | 189940 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4341 | 23073015201 | 2013-02-06 | QTR3 | 12/13 | 2 | 8 | 674 | 896 | 896 | 0 | 0 | 0 | 191 | 31 | 6592014 | 73358 | 6518656 | 6833204 | 6617553 | 0 | 0 | 0 | 6617553 | 6330385 | -287168 | 241190 | 105 | 0 | 31 | 138206 | 0 | 4 | 0 | 108342 | 50933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 43 | 31 | 314541 | 50933 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2016-07-06 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 412 | 7354583.81 |  |  | 14 | 43 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4389 | 23097825201 | 2014-04-30 | QTR4 | 13/14 | 1 | 2 | 750 | 801 | 631 | 170 | 0 | 0 | 51 | 0 | 15715809 | 150000 | 15565809 | 15753499 | 15520925 | 0 | 630700 | 630700 | 16151625 | 14963445 | -1188180 | 37690 | 29 | 0 | 0 | 48793 | 0 | 0 | 0 | 38749 | 2893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66399 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158063 | 2893 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2016-09-12 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 408 | 15839218.13 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4402 | 42973715201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 540 | 577 | 542 | 35 | 0 | 0 | 37 | 0 | 2824000 | 50000 | 2774000 | 2824000 | 2773850 | 0 | 0 | 0 | 2773850 | 2779467 | 5617 | 0 | 15 | 0 | 0 | 8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8687 | 0 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 408 | 3519184.32 | B0 | ACC - LUMP SUM | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4411 | 43472615201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 245 | 261 | 254 | 7 | 0 | 0 | 16 | 0 | 1298981 | 50000 | 1248981 | 1298981 | 1226359 | 0 | 0 | 0 | 1226359 | 1217254 | -9105 | 0 | 12 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31566 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-11-01 | QTR2 | 16/17 |  | 2016-09-22 | QTR1 | 16/17 | 412 | 1277354.98 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4415 | 43472315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 198 | 219 | 219 | 0 | 0 | 0 | 21 | 0 | 1247191 | 50000 | 1197191 | 1247191 | 1236940 | 0 | 0 | 0 | 1236940 | 1236940 | 0 | 0 | 16 | 0 | 0 | 4774 | 0 | 0 | 0 | 9270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14044 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-08-24 | QTR1 | 16/17 | 409 | 1184118.51 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4416 | 43171715201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 238 | 268 | 261 | 7 | 0 | 0 | 30 | 0 | 1444863 | 50000 | 1394863 | 1444863 | 1398240 | 0 | 0 | 0 | 1398240 | 1398240 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 412 | 1613353.82 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4417 | 43400715201 | 2015-05-20 | QTR4 | 14/15 | 1 | 1 | 254 | 270 | 261 | 9 | 0 | 0 | 16 | 0 | 590398 | 35018 | 555379 | 600523 | 561695 | 0 | 0 | 0 | 561695 | 561695 | 0 | 10125 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-11-15 | QTR2 | 16/17 |  | 2016-09-27 | QTR1 | 16/17 | 409 | 743747.84 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4426 | 43060815201 | 2016-02-24 | QTR3 | 15/16 | 2 | 0 | 102 | 161 | 161 | 0 | 0 | 0 | 59 | 0 | 1295575 | 50000 | 1245575 | 1295575 | 1275925 | 0 | 0 | 0 | 1275925 | 1275925 | 0 | 0 | 35 | 18 | 0 | 15716 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18401 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-19 | QTR2 | 16/17 | 409 | 1142628.19 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4P79 | 42593515201 | 2014-04-23 | QTR4 | 13/14 | 2 | 2 | 313 | 441 | 441 | 0 | 0 | 0 | 67 | 61 | 7765532 | 74876 | 7690656 | 7903357 | 8161146 | 0 | 321600 | 321600 | 8482746 | 8149687 | -333059 | 137826 | 53 | 0 | 20 | 14059 | 0 | 0 | 30 | 137826 | 0 | 0 | 11 | 3260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 155145 | 0 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 |  | 2016-03-20 | QTR3 | 15/16 | 412 | 7456671.91 | B3:B5 | ACC - LANE RENTAL:ACC - INCENTIVE/DISINCENTIVE | 31 | 14 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P94 | 43368845201 | 2014-05-02 | QTR4 | 13/14 | 1 | 8 | 506 | 648 | 514 | 134 | 0 | 0 | 40 | 102 | 11791416 | 121557 | 11669859 | 13321296 | 13475252 | 0 | 470000 | 470000 | 13945252 | 13368481 | -576771 | 1529880 | 25 | 0 | 102 | 23355 | 0 | 0 | 0 | 1681280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1637852 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 |  | 2015-12-23 | QTR2 | 15/16 | 412 | 12152859.28 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 102 | 14 | 0 | 0 | -74534 | 0 |  | DO
04DO | 04 | E4P98 | 42605315201 | 2015-02-06 | QTR3 | 14/15 | 2 | 2 | 238 | 283 | 280 | 3 | 0 | 0 | 45 | 0 | 1670723 | 50000 | 1620723 | 1694884 | 1701995 | 0 | 0 | 0 | 1701995 | 1694894 | -7101 | 24162 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 9687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43444 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-02-26 | QTR3 | 15/16 | 409 | 1844040.91 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q22 | 42990515201 | 2014-12-19 | QTR2 | 14/15 | 1 | 4 | 224 | 359 | 356 | 3 | 0 | 0 | 135 | 0 | 5750000 | 65756 | 5684244 | 6072503 | 6142459 | 0 | 0 | 0 | 6142459 | 6141649 | -810 | 322503 | 75 | 0 | 0 | 13481 | 0 | 45 | 0 | 372908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 386389 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-09-30 | QTR1 | 16/17 | 412 | 6522411.23 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q70 | 43056615201 | 2015-04-03 | QTR4 | 14/15 | 1 | 0 | 86 | 99 | 99 | 0 | 0 | 0 | 13 | 0 | 594927 | 36890 | 558037 | 594927 | 563713 | 0 | 0 | 0 | 563713 | 563713 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-07-08 | QTR1 | 16/17 | 412 | 789528.37 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R08 | 43115215201 | 2015-05-20 | QTR4 | 14/15 | 1 | 1 | 315 | 350 | 313 | 37 | 0 | 0 | 35 | 0 | 1435007 | 50000 | 1385007 | 1449407 | 1163642 | 0 | 0 | 0 | 1163642 | 1155244 | -8398 | 14400 | 23 | 0 | 0 | 3143 | 0 | 0 | 0 | 29620 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33038 | 0 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 408 | 1565107.46 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R65 | 43538615201 | 2016-01-08 | QTR3 | 15/16 | 2 | 0 | 65 | 92 | 91 | 1 | 0 | 0 | 23 | 4 | 593859 | 24145 | 569714 | 593859 | 535917 | 0 | 0 | 0 | 535917 | 535917 | 0 | 0 | 18 | 0 | 4 | 8796 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9546 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 409 | 495318.22 |  |  | 4 | 4 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5415 | 40735535201 | 2012-05-23 | QTR4 | 11/12 | 6 | 19 | 1100 | 1340 | 1359 | -19 | 19 | 0 | 215 | 25 | 32798973 | 150000 | 32648973 | 35176946 | 35231745 | -161575 | 0 | -161575 | 35070170 | 34680971 | -389199 | 2796919 | 109 | 0 | 25 | 751698 | 18086 | 0 | 4 | 2213568 | 1011571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 2908901 | 1029658 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2016-11-18 | QTR2 | 16/17 |  | 2016-06-20 | QTR4 | 15/16 | 513 | 37106689.63 |  |  | 1 | 84 | 0 | 0 | -57075 | 0 |  | CO
05CO | 05 | T5496 | 43106615201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 460 | 684 | 678 | 6 | 0 | 0 | 224 | 0 | 4198661 | 57000 | 4141661 | 4198661 | 4290920 | 0 | 0 | 0 | 4290920 | 4280333 | -10587 | 0 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 514 | 5833243.5 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5497 | 43113915201 | 2014-06-18 | QTR4 | 13/14 | 4 | 2 | 350 | 479 | 448 | 31 | 0 | 0 | 99 | 30 | 5577400 | 50000 | 5527400 | 5630674 | 5316503 | 0 | 0 | 0 | 5316503 | 5110931 | -205572 | 53274 | 72 | 0 | 0 | 16219 | 0 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 62720 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-13 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 514 | 5261131.52 | B0:B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5504 | 43326915201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 340 | 414 | 410 | 4 | 0 | 0 | 74 | 0 | 2791824 | 50000 | 2741824 | 2791824 | 2764770 | 0 | 0 | 0 | 2764770 | 2763716 | -1054 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 |  | 2016-09-09 | QTR1 | 16/17 | 514 | 3681477 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5507 | 42908315201 | 2014-10-29 | QTR2 | 14/15 | 2 | 3 | 352 | 458 | 457 | 1 | 0 | 0 | 85 | 21 | 13950000 | 132000 | 13818000 | 14304220 | 14416417 | 0 | 0 | 0 | 14416417 | 13245104 | -1171314 | 354220 | 70 | 0 | 0 | 36422 | 0 | 0 | 0 | 46490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 308750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 391661 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 512 | 13411584.34 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5515 | 43066815201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 210 | 284 | 284 | 0 | 0 | 0 | 44 | 30 | 1884019 | 50000 | 1834019 | 1929335 | 1919435 | 0 | 0 | 0 | 1919435 | 1870656 | -48780 | 45316 | 30 | 0 | 24 | 59005 | 0 | 0 | 6 | 21372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 80377 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2016-05-05 | QTR4 | 15/16 | 514 | 1716624.23 | B0 | ACC - LUMP SUM | 6 | 12 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5519 | 43066615201 | 2015-07-29 | QTR1 | 15/16 | 2 | 0 | 280 | 323 | 260 | 63 | 0 | 0 | 43 | 0 | 2698908 | 50000 | 2648908 | 2698908 | 2560594 | 0 | 0 | 0 | 2560594 | 2513289 | -47305 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 3735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11651 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 514 | 2488176 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5524 | 43065215201 | 2015-03-25 | QTR3 | 14/15 | 1 | 3 | 270 | 391 | 390 | 1 | 0 | 0 | 34 | 87 | 4938000 | 50000 | 4888000 | 5043475 | 4946856 | 0 | 0 | 0 | 4946856 | 4688330 | -258527 | 105475 | 16 | 0 | 0 | 3176 | 0 | 0 | 36 | 84688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 17106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 104970 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 515 | 4676396.93 |  |  | 23 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5528 | 43066915201 | 2015-05-27 | QTR4 | 14/15 | 1 | 1 | 200 | 245 | 224 | 21 | 0 | 0 | 45 | 0 | 2181000 | 50000 | 2131000 | 2446253 | 2396253 | 0 | 0 | 0 | 2396253 | 2380075 | -16178 | 265253 | 19 | 0 | 0 | 145670 | 0 | 0 | 0 | 119583 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265253 | 508 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-07-01 | QTR1 | 16/17 |  | 2016-04-06 | QTR4 | 15/16 | 507 | 1883279.22 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5536 | 43067715201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 216 | 247 | 233 | 14 | 0 | 0 | 31 | 0 | 2584884 | 50000 | 2534884 | 2614884 | 2636650 | 0 | 0 | 0 | 2636650 | 2540033 | -96617 | 30000 | 12 | 0 | 0 | 15490 | 0 | 0 | 0 | 58864 | 13921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74355 | 13921 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-07-22 | QTR1 | 16/17 | 513 | 2795913.94 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5537 | 43244215201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 110 | 154 | 147 | 7 | 0 | 0 | 24 | 20 | 1272760 | 42000 | 1230760 | 1272760 | 1267646 | 0 | 0 | 0 | 1267646 | 1267646 | 0 | 0 | 9 | 0 | 0 | 615 | 0 | 0 | 20 | 34326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 34941 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-06-10 | QTR4 | 15/16 | 513 | 919590 | B0 | ACC - LUMP SUM | 20 | 15 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5540 | 43544615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 310 | 321 | 320 | 1 | 0 | 0 | 11 | 0 | 2108960 | 50000 | 2058960 | 2108960 | 2062184 | 0 | 0 | 0 | 2062184 | 2062184 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-12-13 | QTR2 | 16/17 |  | 2016-09-29 | QTR1 | 16/17 | 509 | 2665356.75 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W67 | 43198915201 | 2014-10-07 | QTR2 | 14/15 | 1 | 2 | 300 | 340 | 393 | -53 | 53 | 0 | 13 | 27 | 2340785 | 50000 | 2290785 | 2247902 | 2197902 | -92326 | 0 | -92326 | 2105576 | 2104471 | -1105 | -92883 | 6 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | -92883 | 0 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-02-10 | QTR3 | 15/16 | 509 | 2486510 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W83 | 43528215201 | 2015-04-07 | QTR4 | 14/15 | 1 | 0 | 240 | 265 | 264 | 1 | 0 | 0 | 25 | 0 | 2750721 | 50000 | 2700721 | 2750721 | 2676098 | 0 | 0 | 0 | 2676098 | 2676025 | -73 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-07-20 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 513 | 2985731 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W86 | 43488315201 | 2015-06-04 | QTR4 | 14/15 | 1 | 1 | 120 | 131 | 131 | 0 | 0 | 0 | 11 | 0 | 584110 | 29000 | 555110 | 585291 | 580591 | 0 | 0 | 0 | 580591 | 580591 | 0 | 1181 | 1 | 0 | 0 | 478 | 0 | 0 | 0 | 4195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4673 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-11-28 | QTR2 | 16/17 |  | 2016-07-22 | QTR1 | 16/17 | 513 | 623548.95 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y02 | 43705815201 | 2015-09-01 | QTR1 | 15/16 | 1 | 0 | 130 | 134 | 107 | 27 | 0 | 0 | 4 | 0 | 783941 | 39000 | 744941 | 783941 | 744941 | 0 | 0 | 0 | 744941 | 744941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-08-09 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 515 | 821518.11 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y03 | 43116415201 | 2016-02-02 | QTR3 | 15/16 | 1 | 0 | 65 | 88 | 83 | 5 | 0 | 0 | 23 | 0 | 63940 | 5000 | 58940 | 63940 | 58289 | 0 | 0 | 0 | 58289 | 58289 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2016-12-23 | QTR2 | 16/17 |  | 2016-10-20 | QTR2 | 16/17 | 514 | 123170 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y04 | 43705715201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 210 | 220 | 220 | 0 | 0 | 0 | 10 | 0 | 679709 | 43000 | 636709 | 679709 | 640622 | 0 | 0 | 0 | 640622 | 640622 | 0 | 0 | 9 | 0 | 0 | 4403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4403 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-12-30 | QTR2 | 16/17 |  | 2016-10-13 | QTR2 | 16/17 | 514 | 911255.5 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y05 | 43465915201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 100 | 110 | 109 | 1 | 0 | 0 | 10 | 0 | 448115 | 19000 | 429115 | 448115 | 434061 | 0 | 0 | 0 | 434061 | 434061 | 0 | 0 | 3 | 0 | 0 | 4946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4946 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-10-04 | QTR2 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 514 | 409595.51 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y18 | 23800235225 | 2016-02-02 | QTR3 | 15/16 | 1 | 1 | 160 | 165 | 148 | 17 | 0 | 0 | 5 | 0 | 788000 | 33000 | 755000 | 805272 | 758781 | 0 | 0 | 0 | 758781 | 759356 | 575 | 17272 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 17272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17272 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 |  | 2016-09-26 | QTR1 | 16/17 | 513 | 717565.65 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6127 | 25118515201 | 2011-09-07 | QTR1 | 11/12 | 3 | 18 | 1250 | 1524 | 1524 | 0 | 0 | 0 | 274 | 0 | 58542945 | 268019 | 58274926 | 59378958 | 60313959 | 0 | 0 | 0 | 60313959 | 59721395 | -592564 | 836013 | 200 | 0 | 0 | 1336258 | 17957 | 0 | 0 | 533489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060088 | 17957 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-08-12 | QTR1 | 16/17 | 606 | 67023598.5 |  |  | 0 | 74 | 0 | 0 | -761248 | 0 |  | CO
06CO | 06 | T6320 | 42914015201 | 2014-06-18 | QTR4 | 13/14 | 3 | 3 | 450 | 503 | 387 | 116 | 0 | 0 | 53 | 0 | 14295524 | 150000 | 14145524 | 14692214 | 13690377 | 0 | 245000 | 245000 | 13935377 | 13056864 | -878513 | 396690 | 43 | 0 | 0 | 18351 | 0 | 0 | 0 | 421570 | 152744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447735 | 152744 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 606 | 15289319.55 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6325 | 25055425201 | 2012-10-31 | QTR2 | 12/13 | 1 | 3 | 700 | 903 | 870 | 33 | 0 | 0 | 197 | 6 | 11430054 | 123500 | 11306554 | 11749528 | 11929942 | 0 | 0 | 0 | 11929942 | 11924070 | -5871 | 319473 | 154 | 2 | 0 | 266319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 63468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 370763 | 0 | F410827177 | JOHNSON BROS. CORPORATION | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 606 | 12087502 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6365 | 43274315201 | 2015-08-26 | QTR1 | 15/16 | 2 | 3 | 180 | 208 | 206 | 2 | 0 | 0 | 28 | 0 | 3849469 | 50000 | 3799469 | 3927103 | 3942847 | 0 | 0 | 0 | 3942847 | 3837692 | -105154 | 77634 | 24 | 0 | 0 | 1963 | 0 | 0 | 0 | 73400 | 3297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4426 | 0 | 0 | 0 | 20491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91428 | 3297 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-08-02 | QTR1 | 16/17 | 606 | 4708187.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6371 | 42913415201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 180 | 212 | 212 | 0 | 0 | 0 | 32 | 0 | 1483369 | 50000 | 1433369 | 1483369 | 1429074 | 0 | 0 | 0 | 1429074 | 1425704 | -3370 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 35508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42642 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-11-10 | QTR2 | 16/17 |  | 2016-08-09 | QTR1 | 16/17 | 606 | 1435507.6 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6373 | 43080915201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 230 | 328 | 326 | 2 | 0 | 0 | 98 | 0 | 2376742 | 50130 | 2326612 | 2426742 | 2460615 | 0 | 0 | 0 | 2460615 | 2384892 | -75723 | 50000 | 56 | 31 | 0 | 16266 | 0 | 0 | 0 | 14872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 71617 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-12 | QTR4 | 15/16 | 606 | 2292101.6 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6374 | 43118015201 | 2015-03-25 | QTR3 | 14/15 | 6 | 4 | 210 | 310 | 308 | 2 | 0 | 0 | 100 | 0 | 5144045 | 52640 | 5091405 | 5317082 | 5198829 | 0 | 0 | 0 | 5198829 | 5112224 | -86605 | 173037 | 47 | 29 | 0 | 30730 | 0 | 0 | 0 | 7365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 148657 | 104434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 186752 | 104434 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-02 | QTR2 | 16/17 |  | 2016-07-03 | QTR1 | 16/17 | 606 | 4599362.55 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6376 | 43081715201 | 2015-02-25 | QTR3 | 14/15 | 2 | 4 | 435 | 468 | 375 | 93 | 0 | 0 | 33 | 0 | 6621887 | 69750 | 6552137 | 6805679 | 6261293 | 0 | 470000 | 470000 | 6731293 | 6082074 | -649219 | 183793 | 21 | 0 | 0 | 71716 | 0 | 0 | 0 | 115147 | 9450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186863 | 9450 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-27 | QTR1 | 16/17 |  | 2016-05-08 | QTR4 | 15/16 | 606 | 6429680.27 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6384 | 43350815201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 137 | 137 | 0 | 0 | 0 | 17 | 0 | 439934 | 26680 | 413254 | 439934 | 417205 | 0 | 0 | 0 | 417205 | 417205 | 0 | 0 | 16 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 606 | 559680 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6389 | 43481015201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 80 | 96 | 93 | 3 | 0 | 0 | 16 | 0 | 147742 | 8768 | 138974 | 147742 | 141841 | 0 | 0 | 0 | 141841 | 141841 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | F273954210 | PE-SERVICES L.L.C. | N/A | N/A | N/A | N/A | 2016-11-02 | QTR2 | 16/17 |  | 2016-10-05 | QTR2 | 16/17 | 606 | 180124 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6394 | 24961575201 | 2015-04-29 | QTR4 | 14/15 | 2 | 1 | 435 | 469 | 395 | 74 | 0 | 0 | 34 | 0 | 18918175 | 150000 | 18768175 | 18918175 | 18379697 | 0 | 740000 | 740000 | 19119697 | 17983880 | -1135817 | 0 | 21 | 0 | 0 | 2262 | 0 | 0 | 0 | 34785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52061 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-11-08 | QTR2 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 606 | 23196102.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6H77 | 41806525201 | 2013-07-16 | QTR1 | 13/14 | 4 | 8 | 381 | 718 | 718 | 0 | 0 | 0 | 144 | 193 | 6865432 | 95551 | 6769881 | 8047242 | 8106870 | 0 | 525000 | 525000 | 8631870 | 8012338 | -619532 | 1181810 | 121 | 0 | 193 | 589219 | 0 | 0 | 0 | 643866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 1240647 | 0 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2016-11-21 | QTR2 | 16/17 |  | 2016-02-25 | QTR3 | 15/16 | 606 | 9650622.75 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I89 | 43117815201 | 2014-10-30 | QTR2 | 14/15 | 2 | 1 | 220 | 378 | 378 | 0 | 0 | 0 | 158 | 0 | 2097039 | 50575 | 2046464 | 2147039 | 2148203 | 0 | 0 | 0 | 2148203 | 2008021 | -140182 | 50000 | 100 | 42 | 0 | 57755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 63544 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2016-10-05 | QTR2 | 16/17 |  | 2016-05-29 | QTR4 | 15/16 | 606 | 2334024.25 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I91 | 42918715201 | 2015-06-11 | QTR4 | 14/15 | 2 | 0 | 150 | 180 | 179 | 1 | 0 | 0 | 30 | 0 | 1483128 | 50420 | 1432708 | 1483128 | 1441455 | 0 | 0 | 0 | 1441455 | 1430102 | -11353 | 0 | 14 | 0 | 0 | 2145 | 0 | 0 | 0 | 772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 2917 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 |  | 2016-09-23 | QTR1 | 16/17 | 606 | 1376235.85 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I98 | 43493065201 | 2016-03-31 | QTR3 | 15/16 | 1 | 1 | 90 | 106 | 106 | 0 | 0 | 0 | 16 | 0 | 969000 | 50000 | 919000 | 903732 | 873748 | 0 | 0 | 0 | 873748 | 873360 | -388 | -65268 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65268 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-10-25 | QTR2 | 16/17 |  | 2016-10-02 | QTR2 | 16/17 | 606 | 1134223.3 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7209 | 25841515201 | 2009-09-16 | QTR1 | 09/10 | 7 | 55 | 1065 | 1694 | 1694 | 0 | 0 | 0 | 109 | 520 | 389463750 | 75000 | 389388750 | 430319761 | 437468272 | 0 | 0 | 0 | 437468272 | 439424048 | 1955776 | 40856011 | 52 | 22 | 67 | 10225188 | 4993195 | 1 | 121 | 13703270 | 4748092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 6407054 | 1636245 | 0 | 0 | 10009318 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 173923 | 100951 | 0 | 0 | 210466 | 210466 | 0 | 0 | 3584 | 0 | 0 | 0 | 0 | 0 | 23 | 520 | 40732802 | 11688949 | F263258515 | PCL/ARCHER WESTERN A JOINT VEN | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2014-10-19 | QTR2 | 14/15 | 714 | 412328910.33 | ARRA:B2:B5:P:B2 | AMERICAN RECOVERY AND REINVEST:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:PUBLIC PRIVATE PARTNERSHIP:ACC - A+B (COST+TIME BIDDING) | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7236 | 25589325201 | 2011-09-28 | QTR1 | 11/12 | 2 | 7 | 410 | 560 | 740 | -180 | 180 | 0 | 131 | 19 | 7147510 | 74000 | 7073510 | 7510715 | 7761739 | -452520 | 0 | -452520 | 7309219 | 7308427 | -793 | 363205 | 107 | 0 | 15 | 337971 | 0 | 0 | 4 | 38132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 372176 | 0 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2016-08-10 | QTR1 | 16/17 |  | 2014-06-13 | QTR4 | 13/14 | 717 | 8423805.36 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7305 | 41886065201 | 2012-06-20 | QTR4 | 11/12 | 8 | 18 | 740 | 1035 | 1035 | 0 | 0 | 0 | 221 | 74 | 27994444 | 135000 | 27859444 | 28571829 | 28922186 | -13000 | 200000 | 187000 | 29109186 | 28487362 | -621825 | 577385 | 184 | 0 | 1 | 153865 | 37343 | 0 | 61 | 494365 | 110210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9379 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -1161 | 12265 | 0 | 0 | 0 | 0 | 0 | 74 | 637690 | 167258 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 |  | 2015-08-15 | QTR1 | 15/16 | 714 | 26994097.12 | B1 | ACC - NO EXCUSE BONUS | 35 | 37 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7309 | 25714715201 | 2012-09-26 | QTR1 | 12/13 | 5 | 11 | 1000 | 1141 | 1121 | 20 | 0 | 0 | 141 | 0 | 20511016 | 150000 | 20361016 | 21458828 | 20369299 | 0 | 0 | 0 | 20369299 | 20020139 | -349160 | 947812 | 105 | 0 | 0 | 754859 | 16651 | 0 | 0 | 284869 | 162142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1086056 | 178793 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-04-25 | QTR4 | 15/16 | 714 | 20045000 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7311 | 25579315201 | 2013-05-31 | QTR4 | 12/13 | 3 | 15 | 800 | 990 | 976 | 14 | 0 | 0 | 147 | 43 | 21435705 | 150000 | 21285705 | 23015417 | 23090810 | -8000 | 0 | -8000 | 23082810 | 22674547 | -408263 | 1579712 | 74 | 0 | 37 | 367652 | 256110 | 40 | 0 | 1071146 | 402006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 172463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77446 | 4419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 43 | 1688706 | 662534 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-10-27 | QTR2 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 714 | 21961489.64 |  |  | 5 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7348 | 42907415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 495 | 613 | 579 | 34 | 0 | 0 | 118 | 0 | 13220362 | 110000 | 13110362 | 13351863 | 13162187 | 0 | 0 | 0 | 13162187 | 12814384 | -347802 | 131501 | 69 | 0 | 0 | 10426 | 0 | 0 | 0 | 164259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174685 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 |  | 2016-06-02 | QTR4 | 15/16 | 717 | 12277372.35 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7356 | 42905815201 | 2014-12-03 | QTR2 | 14/15 | 1 | 3 | 240 | 337 | 337 | 0 | 0 | 0 | 97 | 0 | 6377897 | 60000 | 6317897 | 6518755 | 6488848 | 0 | 0 | 0 | 6488848 | 6241174 | -247674 | 140858 | 77 | 0 | 0 | 54833 | 0 | 0 | 0 | 43775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32045 | 0 | 0 | 0 | 4717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143613 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-02-15 | QTR3 | 15/16 | 709 | 6176900 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7362 | 42907725202 | 2015-03-25 | QTR3 | 14/15 | 2 | 0 | 180 | 256 | 256 | 0 | 0 | 0 | 76 | 0 | 5709404 | 50000 | 5659404 | 5709404 | 5625130 | 0 | 0 | 0 | 5625130 | 5464793 | -160337 | 0 | 57 | 0 | 0 | 8822 | 0 | 0 | 0 | 10150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-08-19 | QTR1 | 16/17 |  | 2016-05-16 | QTR4 | 15/16 | 717 | 5660000 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7364 | 43311115201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 115 | 141 | 141 | 0 | 0 | 0 | 26 | 0 | 1656000 | 50000 | 1606000 | 1660046 | 1621270 | 0 | 0 | 0 | 1621270 | 1621270 | 0 | 4046 | 14 | 0 | 0 | 8843 | 0 | 0 | 0 | 6427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15270 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-02-08 | QTR3 | 15/16 | 709 | 1539800 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7366 | 43113215201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 150 | 211 | 210 | 1 | 0 | 0 | 61 | 0 | 1795000 | 50000 | 1745000 | 1795000 | 1754140 | 0 | 0 | 0 | 1754140 | 1746653 | -7487 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-19 | QTR1 | 16/17 |  | 2016-03-18 | QTR3 | 15/16 | 717 | 1415000 | B0 | ACC - LUMP SUM | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7367 | 42907615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 4 | 250 | 355 | 355 | 0 | 0 | 0 | 91 | 14 | 3822222 | 50000 | 3772222 | 3834124 | 3855324 | 0 | 0 | 0 | 3855324 | 3731807 | -123517 | 11902 | 61 | 0 | 0 | 44654 | 0 | 0 | 14 | 59289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 24270 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-11-15 | QTR2 | 16/17 |  | 2016-05-27 | QTR4 | 15/16 | 798 | 4100000 |  |  | 14 | 30 | 0 | 0 | -82752 | 0 |  | CO
07CO | 07 | T7370 | 43251915201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 150 | 240 | 240 | 0 | 0 | 0 | 90 | 0 | 3088818 | 50000 | 3038818 | 3088818 | 2944540 | 0 | 0 | 0 | 2944540 | 2940006 | -4534 | 0 | 44 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-03 | QTR2 | 16/17 |  | 2016-06-22 | QTR4 | 15/16 | 709 | 3068000 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7374 | 43257915201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 124 | 139 | 110 | 29 | 0 | 0 | 15 | 0 | 3581528 | 50000 | 3531528 | 3581528 | 3666189 | 0 | 220000 | 220000 | 3886189 | 3671670 | -214519 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-09 | QTR2 | 16/17 |  | 2016-08-18 | QTR1 | 16/17 | 717 | 2950000 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7F75 | 25839855201 | 2012-05-08 | QTR4 | 11/12 | 2 | 30 | 1445 | 1568 | 1429 | 139 | 0 | 0 | 123 | 0 | 215400000 | 150000 | 215250000 | 224435209 | 224895976 | 0 | 1650000 | 1650000 | 226545976 | 223875000 | -2670976 | 9035209 | 88 | 0 | 0 | 2771364 | 13903 | 0 | 0 | 5245266 | 459975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22798 | 0 | 0 | 0 | 1015841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9055269 | 473878 | F453806780 | SKANSKA-AJAX PAVING JOINT VENTU | N/A | N/A | N/A | N/A | 2016-12-06 | QTR2 | 16/17 |  | 2016-06-28 | QTR4 | 15/16 | 714 | 213872600 | B11:B12:B8:B:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - DSGN BLD-MAJ/BONUS/WRNTY:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I34 | 41101135201 | 2014-01-23 | QTR3 | 13/14 | 1 | 3 | 750 | 874 | 871 | 3 | 0 | 0 | 124 | 0 | 35188969 | 150000 | 35038969 | 35441051 | 35414850 | 0 | 0 | 0 | 35414850 | 34061551 | -1353299 | 252082 | 90 | 0 | 0 | 47212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31900 | 0 | 0 | 0 | 150744 | 0 | 0 | 0 | 75555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305411 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-23 | QTR2 | 16/17 |  | 2016-11-02 | QTR2 | 16/17 | 714 | 37368154.02 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I46 | 25633925201 | 2014-08-14 | QTR1 | 14/15 | 1 | 4 | 450 | 623 | 622 | 1 | 0 | 0 | 137 | 36 | 15944000 | 150000 | 15794000 | 16474127 | 16294835 | 0 | 0 | 0 | 16294835 | 15360010 | -934824 | 530127 | 97 | 0 | 0 | 56222 | 0 | 0 | 1 | 186898 | 3530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 346909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 590029 | 3530 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-15 | QTR1 | 16/17 |  | 2016-06-25 | QTR4 | 15/16 | 714 | 18310419.41 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 11 | 40 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7J99 | 42715515201 | 2015-04-08 | QTR4 | 14/15 | 1 | 1 | 199 | 302 | 274 | 28 | 0 | 0 | 103 | 0 | 1844400 | 50000 | 1794400 | 1881240 | 1852163 | 0 | 0 | 0 | 1852163 | 1792416 | -59746 | 36840 | 47 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 |  | 2016-06-28 | QTR4 | 15/16 | 798 | 1650000 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K02 | 43090115201 | 2015-02-11 | QTR3 | 14/15 | 1 | 3 | 125 | 176 | 176 | 0 | 0 | 0 | 39 | 12 | 2683100 | 50000 | 2633100 | 2806747 | 2817266 | 0 | 0 | 0 | 2817266 | 2772695 | -44571 | 123647 | 34 | 0 | 12 | 67604 | 15358 | 0 | 0 | 123204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 173025 | 15358 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-07 | QTR1 | 16/17 |  | 2015-11-30 | QTR2 | 15/16 | 709 | 2450000 | B0 | ACC - LUMP SUM | 12 | 5 | 0 | 0 | -17782 | 0 |  | DO
07DO | 07 | E7K04 | 43066015201 | 2015-03-11 | QTR3 | 14/15 | 1 | 2 | 180 | 281 | 281 | 0 | 0 | 0 | 82 | 19 | 2680382 | 50000 | 2630382 | 2750471 | 2763085 | 0 | 0 | 0 | 2763085 | 2699178 | -63907 | 70089 | 46 | 0 | 0 | 0 | 0 | 0 | 19 | 111980 | 18119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 19 | 114701 | 18119 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-03-14 | QTR3 | 15/16 | 709 | 2007403 | B0 | ACC - LUMP SUM | 19 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K05 | 43243225201 | 2015-03-11 | QTR3 | 14/15 | 1 | 0 | 220 | 262 | 261 | 1 | 0 | 0 | 42 | 0 | 1086230 | 50000 | 1036230 | 1086230 | 1062839 | 0 | 0 | 0 | 1062839 | 1062824 | -15 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2016-09-26 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 717 | 1230200 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K07 | 43068515201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 105 | 145 | 145 | 0 | 0 | 0 | 40 | 0 | 1119020 | 42000 | 1077020 | 1119020 | 1092543 | 0 | 0 | 0 | 1092543 | 1092543 | 0 | 0 | 25 | 0 | 0 | 3319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3319 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2016-10-27 | QTR2 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 717 | 885300 | B0 | ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K17 | 43094815201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 220 | 258 | 212 | 46 | 0 | 0 | 38 | 0 | 2888000 | 50000 | 2838000 | 2888000 | 2727932 | 0 | 0 | 0 | 2727932 | 2690622 | -37311 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-16 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 798 | 3200000 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K29 | 42550325201 | 2015-05-13 | QTR4 | 14/15 | 1 | 0 | 120 | 183 | 155 | 28 | 0 | 0 | 63 | 0 | 1984295 | 50000 | 1934295 | 1984295 | 1950400 | 0 | 0 | 0 | 1950400 | 1950400 | 0 | 0 | 32 | 0 | 0 | 13191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13191 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-10-10 | QTR2 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 717 | 1727700 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K67 | 43149515201 | 2015-05-13 | QTR4 | 14/15 | 1 | 4 | 140 | 178 | 178 | 0 | 0 | 0 | 28 | 10 | 2794895 | 50000 | 2744895 | 2964710 | 2918290 | -7200 | 0 | -7200 | 2911090 | 2905726 | -5363 | 169815 | 17 | 0 | 5 | 49615 | 0 | 0 | 5 | 161418 | 7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 193888 | 7074 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 717 | 1905000 |  |  | 2 | 11 | 0 | 0 | -17145 | 0 |  | DO
07DO | 07 | E7K68 | 43149115201 | 2015-05-13 | QTR4 | 14/15 | 2 | 1 | 200 | 298 | 294 | 4 | 0 | 0 | 69 | 29 | 4031039 | 50000 | 3981039 | 4044189 | 4055974 | 0 | 0 | 0 | 4055974 | 4004687 | -51286 | 13150 | 48 | 0 | 6 | 42639 | 3293 | 0 | 23 | 4531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59544 | 3293 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 709 | 3361350 |  |  | 26 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K78 | 43080235201 | 2015-09-09 | QTR1 | 15/16 | 2 | 0 | 206 | 217 | 128 | 89 | 0 | 0 | 11 | 0 | 1271000 | 50000 | 1221000 | 1271000 | 1221000 | 0 | 0 | 0 | 1221000 | 1221000 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-05-10 | QTR4 | 15/16 | 717 | 2206022.47 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K80 | 43478115201 | 2015-08-12 | QTR1 | 15/16 | 2 | 2 | 160 | 203 | 203 | 0 | 0 | 0 | 41 | 2 | 1052289 | 33000 | 1019289 | 1092289 | 992268 | 0 | 0 | 0 | 992268 | 991427 | -840 | 40000 | 21 | 0 | 0 | 7453 | 0 | 0 | 2 | 55456 | 19923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 62908 | 19923 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 717 | 752249.19 |  |  | 2 | 20 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K88 | 43071015201 | 2016-01-13 | QTR3 | 15/16 | 1 | 1 | 75 | 75 | 34 | 41 | 0 | 0 | 0 | 0 | 716889 | 28000 | 688889 | 655243 | 627243 | 0 | 0 | 0 | 627243 | 627243 | 0 | -61646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -61646 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-27 | QTR2 | 16/17 |  | 2016-08-19 | QTR1 | 16/17 | 717 | 590500 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | -61646 | 0 |  | DO
07DO | 07 | E7K90 | 43386615201 | 2016-02-10 | QTR3 | 15/16 | 1 | 0 | 60 | 61 | 59 | 2 | 0 | 0 | 1 | 0 | 795744 | 15000 | 780744 | 795744 | 787111 | 0 | 0 | 0 | 787111 | 787111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5751 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-10-12 | QTR2 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 717 | 455000 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K99 | 43625515201 | 2016-03-09 | QTR3 | 15/16 | 1 | 1 | 50 | 51 | 37 | 14 | 0 | 0 | 1 | 0 | 160902 | 4125 | 156777 | 182550 | 178425 | 0 | 0 | 0 | 178425 | 178425 | 0 | 21648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21648 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 717 | 165500 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L07 | 43258315201 | 2015-11-12 | QTR2 | 15/16 | 1 | 0 | 80 | 89 | 89 | 0 | 0 | 0 | 5 | 4 | 1115377 | 50000 | 1065377 | 1115377 | 1056390 | 0 | 0 | 0 | 1056390 | 1056390 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 798 | 1450000 | B0 | ACC - LUMP SUM | 4 | 0 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M60 | 43127515201 | 2013-01-22 | QTR3 | 12/13 | 3 | 33 | 1055 | 1167 | 1168 | -1 | 1 | 0 | 112 | 0 | 56648757 | 150000 | 56498757 | 57438075 | 57810006 | 0 | 0 | 0 | 57810006 | 57069148 | -740858 | 789318 | 68 | 0 | 0 | 324282 | 0 | 0 | 0 | 229213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568192 | 23585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 32879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 843308 | 23585 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 |  | 2016-06-30 | QTR4 | 15/16 | 854 | 56376201.62 |  |  | 0 | 40 | 0 | 0 | -311259 | 0 |  | DO
08DO | 08 | E8M63 | 40615215201 | 2013-02-05 | QTR3 | 12/13 | 3 | 16 | 995 | 1179 | 1179 | 0 | 0 | 0 | 170 | 14 | 57400000 | 150000 | 57250000 | 57854468 | 58114118 | -10000 | 0 | -10000 | 58104118 | 57193979 | -910139 | 454468 | 108 | 0 | 0 | 135877 | 1764 | 7 | 14 | 647998 | 24913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 489562 | 26677 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-02 | QTR2 | 16/17 |  | 2016-07-20 | QTR1 | 16/17 | 854 | 59063480.38 |  |  | 0 | 55 | 0 | 0 | -365840 | 0 |  | DO
08DO | 08 | E8N60 | 41546265201 | 2014-05-20 | QTR4 | 13/14 | 1 | 3 | 475 | 545 | 545 | 0 | 0 | 0 | 70 | 0 | 10628174 | 96840 | 10531334 | 10702005 | 10703365 | -6500 | 0 | -6500 | 10696865 | 10548835 | -148030 | 73831 | 23 | 0 | 0 | 8969 | 0 | 0 | 0 | 107706 | 13562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 117912 | 13562 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-04-12 | QTR4 | 15/16 | 854 | 9781121.21 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N68 | 24301715201 | 2014-06-09 | QTR4 | 13/14 | 2 | 4 | 480 | 643 | 642 | 1 | 0 | 0 | 163 | 0 | 16844000 | 150000 | 16694000 | 17989634 | 18429954 | -3000 | 0 | -3000 | 18426954 | 17949122 | -477832 | 1145634 | 44 | 0 | 0 | 71261 | 0 | 29 | 0 | 246343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 947444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 1265048 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 854 | 15034152.99 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P54 | 43110015201 | 2015-10-20 | QTR2 | 15/16 | 1 | 1 | 115 | 121 | 118 | 3 | 0 | 0 | 6 | 0 | 1369271 | 50000 | 1319271 | 1355607 | 1258468 | 0 | 0 | 0 | 1258468 | 1224485 | -33984 | -13664 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-06-24 | QTR4 | 15/16 | 854 | 1662320.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P55 | 43561715201 | 2015-06-16 | QTR4 | 14/15 | 1 | 1 | 140 | 189 | 189 | 0 | 0 | 0 | 45 | 4 | 1736149 | 50000 | 1686149 | 1766298 | 1678250 | -26500 | 0 | -26500 | 1651750 | 1651060 | -690 | 30149 | 29 | 0 | 4 | 30149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 30149 | 0 | F203908361 | MIDASCO LLC | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 854 | 1991671.8 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
01DO | 01 | E1K48 | 41306615201 | 2012-06-28 | QTR4 | 11/12 | 1 | 5 | 890 | 1143 | 1143 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 0 | -71423852 | -187553 | 155 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 12 | -153550 | 12852 | F454673542 | DE MOYA / LEWARE JV | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 | 2015-12-08 | QTR2 | 15/16 | 106 | 80270500 | B8:DBF:P3 | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP | 0 | 58 | 0 | 0 | -339346 | 0 |  | DO | 0 | 01co | 1 | 0
CO | [104 empty] | CO | 1 | 01do | 1 | 1
CO | [104 empty] | CO | 0 | 02co | 2 | 1
CO | [104 empty] | CO | 0 | 02do | 2 | 1
CO | [104 empty] | CO | 0 | 03co | 2 | 1
CO | [104 empty] | CO | 0 | 03do | 2 | 1
CO | [104 empty] | CO | 0 | 04co | 2 | 1
CO | [104 empty] | CO | 0 | 04do | 2 | 1
CO | [104 empty] | CO | 0 | 05co | 2 | 1
CO | [103 empty] | T | CO | 0 | 05do | 2 | 1
CO | [104 empty] | CO | 0 | 06co | 2 | 1
CO | [104 empty] | CO | 0 | 06do | 2 | 1
CO | [104 empty] | CO | 0 | 07co | 2 | 1
CO | [104 empty] | CO | 0 | 07do | 2 | 1
CO | [104 empty] | CO | 0 | 08co | 2 | 1
CO | [104 empty] | CO | 0 | 08do | 2 | 1
CO | [104 empty] | CO
CO | [104 empty] | CO
CO | [104 empty] | CO |  | 0