## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 153027844 | 151365882 | 154467448 | 153493019 | 2592000 | 148637681 | -1.802% | 89.19% | 1923980 | 1.271% | 1439603 | 0.9407% | 7135 | 1223 | 17.14% | 348 | 4.877% | 18 | 0.2523% | 303 | 4.247% | 7456 | 4.499% | 9095 | 8834 | 7263 | 1.794% | 86.49%
| District Let | 63275556 | 62465816 | 65993886 | 64686028 | 0 | 63027509 | 0.8992% | 100% | 2937839 | 4.703% | 2718330 | 4.296% | 3469 | 496 | 14.3% | 234 | 6.745% | 138 | 3.978% | 109 | 3.142% | 3716 | 7.12% | 4447 | 4424 | 3694 | 6.486% | 93.33%
| All Contracts | 216303400 | 213831698 | 220461334 | 218179047 | 2592000 | 211665190 | -1.013% | 92.31% | 4861819 | 2.274% | 4157933 | 1.922% | 10604 | 1719 | 16.21% | 582 | 5.488% | 156 | 1.471% | 412 | 3.885% | 11172 | 5.356% | 13542 | 13258 | 10957 | 3.329% | 88.46%
2 | Central Let | 79570470 | 78698067 | 78630013 | 78849591 | 0 | 77843270 | -1.086% | 92.86% | 1321884 | 1.68% | 1101540 | 1.384% | 5557 | 534 | 9.61% | 353 | 6.352% | 42 | 0.7558% | 266 | 4.787% | 5865 | 5.543% | 6622 | 6636 | 5749 | 3.455% | 82.14%
| District Let | 52749513 | 51885624 | 62459361 | 62820578 | 0 | 61732186 | 18.98% | 81.25% | 10038426 | 19.35% | 9709848 | 18.41% | 3520 | 311 | 8.835% | 250 | 7.102% | 15 | 0.4261% | 868 | 24.66% | 4403 | 25.09% | 4972 | 5062 | 4501 | 27.87% | 75%
| All Contracts | 132319983 | 130583691 | 141089374 | 141670169 | 0 | 139575456 | 6.886% | 88.64% | 11360310 | 8.7% | 10811388 | 8.171% | 9077 | 845 | 9.309% | 603 | 6.643% | 57 | 0.628% | 1134 | 12.49% | 10268 | 13.12% | 11594 | 11698 | 10250 | 12.92% | 79.55%
3 | Central Let | 136059024 | 134182593 | 143363623 | 144110804 | 0 | 139902162 | 4.263% | 91.43% | 8048311 | 5.998% | 7304598 | 5.369% | 8689 | 2339 | 26.92% | 919 | 10.58% | 965 | 11.11% | 1239 | 14.26% | 10893 | 25.37% | 14151 | 14010 | 10752 | 23.74% | 74.29%
| District Let | 72812576 | 71589921 | 74881647 | 75805881 | 0 | 74972299 | 4.725% | 82.14% | 2486716 | 3.474% | 2069073 | 2.842% | 4146 | 1080 | 26.05% | 377 | 9.093% | 200 | 4.824% | 569 | 13.72% | 4915 | 18.55% | 6372 | 6188 | 4731 | 14.11% | 85.71%
| All Contracts | 208871600 | 205772514 | 218245270 | 219916685 | 0 | 214874461 | 4.423% | 87.3% | 10535027 | 5.12% | 9373671 | 4.488% | 12835 | 3419 | 26.64% | 1296 | 10.1% | 1165 | 9.077% | 1808 | 14.09% | 15808 | 23.16% | 20523 | 20198 | 15483 | 20.63% | 79.37%
4 | Central Let | 59367431 | 58378624 | 61309283 | 60400164 | 630700 | 58970678 | 1.014% | 94.74% | 2573373 | 4.408% | 1941850 | 3.271% | 6033 | 761 | 12.61% | 294 | 4.873% | 191 | 3.166% | 146 | 2.42% | 6370 | 5.586% | 7429 | 7180 | 6125 | 1.525% | 94.74%
| District Let | 81974493 | 80923067 | 87634666 | 87279108 | 791600 | 84270792 | 4.137% | 82.35% | 6036281 | 7.459% | 5660176 | 6.905% | 5865 | 731 | 12.46% | 361 | 6.155% | 144 | 2.455% | 770 | 13.13% | 6779 | 15.58% | 7889 | 7655 | 6563 | 11.9% | 82.35%
| All Contracts | 141341924 | 139301691 | 148943949 | 147679272 | 1422300 | 143241470 | 2.828% | 88.89% | 8609654 | 6.181% | 7602026 | 5.378% | 11898 | 1492 | 12.54% | 655 | 5.505% | 335 | 2.816% | 916 | 7.699% | 13149 | 10.51% | 15318 | 14835 | 12688 | 6.64% | 88.89%
5 | Central Let | 113860470 | 112497745 | 117873626 | 117384619 | 0 | 113469442 | 0.8637% | 95.45% | 4962668 | 4.411% | 4432102 | 3.893% | 6673 | 993 | 14.88% | 447 | 6.699% | 0 | 0% | 354 | 5.305% | 7027 | 5.305% | 8499 | 8256 | 6816 | 2.143% | 95.45%
| District Let | 14011323 | 13599323 | 14093618 | 13582224 | 100000 | 13474727 | -0.9162% | 100% | 99716 | 0.7332% | 82295 | 0.5873% | 2171 | 128 | 5.896% | 115 | 5.297% | 0 | 0% | 47 | 2.165% | 2218 | 2.165% | 2489 | 2398 | 2155 | -0.737% | 84.62%
| All Contracts | 127871793 | 126097068 | 131967244 | 130966843 | 100000 | 126944169 | 0.6718% | 97.14% | 5062384 | 4.015% | 4514397 | 3.53% | 8844 | 1121 | 12.68% | 562 | 6.355% | 0 | 0% | 401 | 4.534% | 9245 | 4.534% | 10988 | 10654 | 8971 | 1.436% | 91.43%
6 | Central Let | 231481635 | 229346742 | 240868601 | 238906801 | 6925000 | 235043905 | 2.484% | 95.24% | 10479295 | 4.569% | 9386966 | 4.055% | 7990 | 960 | 12.02% | 367 | 4.593% | 80 | 1.001% | 40 | 0.5006% | 8110 | 1.502% | 9437 | 8853 | 7526 | -5.807% | 100%
| District Let | 26195812 | 25706571 | 27355973 | 27263658 | 625000 | 24014723 | -6.581% | 88.89% | 1271992 | 4.948% | 1160159 | 4.429% | 2261 | 680 | 30.08% | 152 | 6.723% | 110 | 4.865% | 193 | 8.536% | 2564 | 13.4% | 3396 | 3345 | 2513 | 11.15% | 88.89%
| All Contracts | 257677447 | 255053313 | 268224574 | 266170459 | 7550000 | 259058628 | 1.57% | 93.33% | 11751287 | 4.607% | 10547125 | 4.093% | 10251 | 1640 | 16% | 519 | 5.063% | 190 | 1.853% | 233 | 2.273% | 10674 | 4.126% | 12833 | 12198 | 10039 | -2.068% | 96.67%
7 | Central Let | 607994838 | 606097138 | 657549456 | 664039143 | 420000 | 660778935 | 9.022% | 92% | 50116455 | 8.269% | 49554619 | 8.15% | 9319 | 1484 | 15.92% | 647 | 6.943% | 99 | 1.062% | 1029 | 11.04% | 10447 | 12.1% | 12578 | 13144 | 11013 | 18.18% | 84%
| District Let | 380048932 | 378181087 | 393257974 | 392642336 | 1650000 | 386599413 | 2.226% | 97.06% | 13718249 | 3.627% | 13209043 | 3.476% | 8384 | 1243 | 14.83% | 607 | 7.24% | 45 | 0.5367% | 373 | 4.449% | 8802 | 4.986% | 10671 | 10218 | 8368 | -0.1908% | 100%
| All Contracts | 988043770 | 984278225 | 1050807430 | 1056681479 | 2070000 | 1047378348 | 6.411% | 94.92% | 63834704 | 6.485% | 62763662 | 6.352% | 17703 | 2727 | 15.4% | 1254 | 7.084% | 144 | 0.8134% | 1402 | 7.92% | 19249 | 8.733% | 23249 | 23362 | 19381 | 9.479% | 93.22%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 190991286 | 190169031 | 194230313 | 195652475 | 0 | 191899835 | 0.9101% | 100% | 3521326 | 1.852% | 3239028 | 1.696% | 4445 | 420 | 9.449% | 243 | 5.467% | 107 | 2.407% | 130 | 2.925% | 4682 | 5.332% | 5355 | 5207 | 4544 | 2.227% | 0.002321%
| All Contracts | 190991286 | 190169031 | 194230313 | 195652475 | 0 | 191899835 | 0.9101% | 100% | 3521326 | 1.852% | 3239028 | 1.696% | 4445 | 420 | 9.449% | 243 | 5.467% | 107 | 2.407% | 130 | 2.925% | 4682 | 5.332% | 5355 | 5207 | 4544 | 2.227% | 100%
Totals This Qtr | Central Let | 1381361712 | 1370566791 | 1454062050 | 1457184141 | 10567700 | 1434646073 | 4.675% | 92.51% | 79425966 | 5.795% | 75161278 | 5.441% | 51396 | 8294 | 16.14% | 3375 | 6.567% | 1395 | 2.714% | 3377 | 6.571% | 56168 | 9.285% | 67811 | 66913 | 55244 | 7.487% | 86.63%
| District Let | 882059491 | 874520440 | 919907438 | 919732288 | 3166600 | 899991484 | 2.913% | 90.71% | 40110545 | 4.587% | 37847952 | 4.291% | 34261 | 5089 | 14.85% | 2339 | 6.827% | 759 | 2.215% | 3059 | 8.929% | 38079 | 11.14% | 45591 | 44497 | 37069 | 8.196% | 89.29%
| All Contracts | 2263421203 | 2245087231 | 2373969488 | 2376916429 | 13734300 | 2334637557 | 3.989% | 91.74% | 119536511 | 5.324% | 113009230 | 4.993% | 85657 | 13383 | 15.62% | 5714 | 6.671% | 2154 | 2.515% | 6436 | 7.514% | 94247 | 10.03% | 113402 | 111410 | 92313 | 7.771% | 87.77%
Totals Previous Quarter | Central Let | 366812141 | 363322200 | 391791558 | 394582000 | 6114800 | 397147320 | 9.31% | 83.33% | 25965031 | 7.147% | 24967334 | 6.807% | 13122 | 1150 | 8.764% | 464 | 3.536% | 163 | 1.242% | 1629 | 12.41% | 14914 | 13.66% | 16867 | 16130 | 14516 | 10.62% | 85.42%
| District Let | 166347760 | 164757121 | 170581461 | 170154877 | 887500 | 171426463 | 4.048% | 88.24% | 4844362 | 2.94% | 4233700 | 2.545% | 7595 | 643 | 8.466% | 228 | 3.002% | 165 | 2.172% | 392 | 5.161% | 8152 | 7.334% | 9033 | 9067 | 8196 | 7.913% | 85.29%
| All Contracts | 533159901 | 528079321 | 562373019 | 564736877 | 7002300 | 568573783 | 7.668% | 85.37% | 30809393 | 5.834% | 29201034 | 5.477% | 20717 | 1793 | 8.655% | 692 | 3.34% | 328 | 1.583% | 2021 | 9.755% | 23066 | 11.34% | 25900 | 25197 | 22712 | 9.63% | 85.37%
Totals Fiscal Year 2008/2009 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1468 | 19753425201 | 2012-05-23 | QTR4 | 11/12 | 2 | 16 | 650 | 755 | 755 | 103.7% | 1 | 0 | 0 | 0 | 81 | 24 | 14242918 | 150000 | 14092918 | 15688629 | 15514205 | 0 | 0 | 0 | 15514205 | 15463127 | 109.7% | 1 | -51078 | 1445710 | 64 | 17 | 0 | 14 | 850509 | 0 | 0 | 0 | 96860 | 6298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 501609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1450956 | 6298 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-01-03 | QTR3 | 16/17 |  | 2014-10-04 | QTR2 | 14/15 | 108 | 14155367.4
| 01 | T1552 | 40631475201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 164 | 200 | 128% | 0 | -36 | 36 | 0 | 10 | 4 | 2579468 | 50000 | 2529468 | 2579468 | 2493565 | -85464 | 0 | -85464 | 2408101 | 2408101 | 95.2% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2016-12-14 | QTR2 | 16/17 |  | 2014-09-12 | QTR1 | 14/15 | 115 | 3076291.38
| 01 | T1560 | 42910115201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 250 | 268 | 268 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 4883160 | 57482 | 4825678 | 4883160 | 4742567 | 0 | 0 | 0 | 4742567 | 4581604 | 94.94% | 1 | -160964 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 118 | 5451824.59
| 01 | T1577 | 42919915201 | 2013-12-04 | QTR2 | 13/14 | 1 | 2 | 80 | 105 | 214 | 262.5% | 0 | -109 | 109 | 0 | 4 | 21 | 149236 | 0 | 149236 | 153020 | 93123 | 0 | 0 | 0 | 93123 | 87604 | 58.7% | 1 | -5519 | 3784 | 2 | 2 | 0 | 21 | 3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 3784 | 0 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-04-25 | QTR4 | 16/17 |  | 2014-12-04 | QTR2 | 14/15 | 108 | 204084.47 | B0 | ACC - LUMP SUM
| 01 | T1583 | 42910715201 | 2014-05-21 | QTR4 | 13/14 | 2 | 12 | 365 | 542 | 598 | 134.8% | 0 | -56 | 56 | 0 | 106 | 71 | 12221582 | 124617 | 12096965 | 12321397 | 12316064 | -258944 | 0 | -258944 | 12057120 | 11369478 | 93.99% | 1 | -687643 | 99815 | 77 | 29 | 0 | 55 | 73297 | 0 | 0 | 16 | 102194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 177856 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 108 | 11851721.99
| 01 | T1587 | 42913115201 | 2014-03-26 | QTR3 | 13/14 | 2 | 7 | 185 | 230 | 226 | 102.7% | 1 | 4 | 0 | 0 | 36 | 9 | 4576900 | 50000 | 4526900 | 4273384 | 4255627 | 0 | 0 | 0 | 4255627 | 4165417 | 92.01% | 1 | -90210 | -303516 | 25 | 11 | 0 | 6 | 199569 | 39215 | 0 | 3 | -504411 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | -277723 | 58709 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-01 | QTR2 | 16/17 |  | 2015-04-29 | QTR4 | 14/15 | 115 | 5166652.25 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1588 | 41304225201 | 2014-06-18 | QTR4 | 13/14 | 2 | 7 | 680 | 710 | 591 | 85.59% | 1 | 119 | 0 | 0 | 46 | -16 | 24169365 | 150000 | 24019365 | 23023182 | 22613781 | 0 | 900000 | 900000 | 23513781 | 20785082 | 86.53% | 1 | -2728699 | -1146183 | 1 | 8 | 0 | -16 | -1426521 | 0 | 0 | 0 | 288694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | -1137827 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 |  | 2016-08-25 | QTR1 | 16/17 | 106 | 29188895.88 | B2:B5:B2 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING)
| 01 | T1595 | 40631345201 | 2015-03-25 | QTR3 | 14/15 | 1 | 6 | 525 | 556 | 395 | 66.29% | 1 | 161 | 0 | 0 | 47 | -16 | 31929262 | 150000 | 31779262 | 31614976 | 31607283 | 0 | 1300000 | 1300000 | 32907283 | 30894410 | 97.22% | 1 | -2012872 | -314286 | 36 | 11 | 0 | -16 | 17006 | 0 | 0 | 0 | 270841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -491717 | 0 | 0 | -16 | -196174 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-10-25 | QTR2 | 16/17 |  | 2016-07-13 | QTR1 | 16/17 | 106 | 30769490.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 01 | T1596 | 43142215201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 250 | 349 | 348 | 109.6% | 1 | 1 | 0 | 0 | 74 | 25 | 5571174 | 56174 | 5515000 | 5623674 | 5636689 | 0 | 0 | 0 | 5636689 | 5437906 | 98.6% | 1 | -198783 | 52500 | 61 | 13 | 0 | 25 | 48439 | 0 | 0 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 100939 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-11-21 | QTR2 | 16/17 |  | 2016-05-28 | QTR4 | 15/16 | 113 | 5411862.18 | B0 | ACC - LUMP SUM
| 01 | T1597 | 43356115201 | 2015-02-25 | QTR3 | 14/15 | 1 | 2 | 115 | 551 | 519 | 92.17% | 1 | 32 | 0 | 0 | 413 | 23 | 737000 | 0 | 737000 | 989001 | 989001 | 0 | 0 | 0 | 989001 | 989001 | 134.2% | 0 | 0 | 252001 | 394 | 19 | 0 | 1 | 3000 | 0 | 0 | 22 | 249001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 252001 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-11-28 | QTR2 | 16/17 |  | 2016-10-25 | QTR2 | 16/17 | 108 | 596982.85 | B0 | ACC - LUMP SUM
| 01 | T1599 | 42584155201 | 2015-07-29 | QTR1 | 15/16 | 1 | 1 | 325 | 396 | 396 | 109.5% | 1 | 0 | 0 | 0 | 71 | 0 | 7593742 | 79742 | 7514000 | 7718407 | 7550971 | 0 | 0 | 0 | 7550971 | 7299675 | 97.15% | 1 | -251296 | 124665 | 19 | 21 | 0 | 0 | 124665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124665 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 |  | 2016-12-01 | QTR2 | 16/17 | 113 | 8930964.42
| 01 | T1600 | 42811715201 | 2015-05-20 | QTR4 | 14/15 | 1 | 6 | 150 | 348 | 346 | 112% | 1 | 2 | 0 | 0 | 178 | 20 | 2180000 | 0 | 2180000 | 2794372 | 2791154 | 0 | 0 | 0 | 2791154 | 2775457 | 127.3% | 0 | -15697 | 614372 | 166 | 12 | 0 | 0 | 3129 | 0 | 0 | 20 | 611243 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 614372 | 410 | F464740152 | CATHCART CONSTRUCTION COMPANY - FLORIDA | N/A | N/A | N/A | N/A | 2017-04-28 | QTR4 | 16/17 |  | 2016-07-13 | QTR1 | 16/17 | 108 | 2282380.64 | B0 | ACC - LUMP SUM
| 01 | T1601 | 42910615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 0 | 180 | 206 | 206 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 2560715 | 50000 | 2510715 | 2560715 | 2601322 | 0 | 0 | 0 | 2601322 | 2476584 | 98.64% | 1 | -124738 | 0 | 16 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 108 | 2539521.53
| 01 | T1604 | 43340715201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 130 | 138 | 139 | 98.46% | 1 | -1 | 1 | 0 | 11 | -3 | 1272557 | 50000 | 1222557 | 1265786 | 1215247 | 0 | 0 | 0 | 1215247 | 1215247 | 99.4% | 1 | 0 | -6770 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -6770 | 0 | 0 | -3 | -6770 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-20 | QTR4 | 15/16 | 113 | 1175938.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1610 | 43337615201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 140 | 157 | 173 | 111.4% | 1 | -16 | 16 | 0 | 17 | 0 | 766880 | 38788 | 728092 | 763925 | 702653 | -27872 | 0 | -27872 | 674781 | 674781 | 92.68% | 1 | 0 | -2956 | 10 | 7 | 0 | 0 | -73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2956 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-28 | QTR4 | 15/16 | 108 | 1032307.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1612 | 43539315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 2 | 139 | 163 | 162 | 99.28% | 1 | 1 | 0 | 0 | 24 | 0 | 965039 | 0 | 965039 | 965864 | 949501 | 0 | 0 | 0 | 949501 | 941761 | 97.59% | 1 | -7741 | 825 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-05 | QTR1 | 16/17 |  | 2016-04-14 | QTR4 | 15/16 | 113 | 968994.66
| 01 | T1613 | 19611435201 | 2015-06-17 | QTR4 | 14/15 | 2 | 5 | 375 | 386 | 343 | 84.27% | 1 | 43 | 0 | 0 | 27 | -16 | 14129548 | 134625 | 13994923 | 14489220 | 14438239 | 0 | 392000 | 392000 | 14830239 | 14122043 | 100.9% | 1 | -708196 | 359672 | 15 | 12 | 0 | 0 | 3699 | 0 | 0 | -16 | 386161 | 2894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 393707 | 2894 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-03-23 | QTR3 | 16/17 |  | 2016-09-08 | QTR1 | 16/17 | 115 | 13676471.13 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1615 | 42950615201 | 2015-06-17 | QTR4 | 14/15 | 2 | 0 | 150 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1470894 | 50000 | 1420894 | 1470894 | 1424904 | 0 | 0 | 0 | 1424904 | 1424904 | 100.3% | 1 | 0 | 0 | 30 | 4 | 0 | 0 | 3080 | 0 | 0 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4010 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-07-05 | QTR1 | 16/17 | 115 | 1441634.98 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1617 | 43337515201 | 2015-06-17 | QTR4 | 14/15 | 1 | 2 | 150 | 170 | 169 | 99.33% | 1 | 1 | 0 | 0 | 20 | 0 | 1087453 | 50000 | 1037453 | 1211375 | 1165751 | 0 | 0 | 0 | 1165751 | 1165751 | 112.4% | 0 | 0 | 123922 | 11 | 9 | 0 | 0 | 135887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128298 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 108 | 1092794.1 | B0 | ACC - LUMP SUM
| 01 | T1618 | 43340815201 | 2015-06-17 | QTR4 | 14/15 | 2 | 2 | 150 | 185 | 185 | 104.7% | 1 | 0 | 0 | 0 | 28 | 7 | 1135821 | 50000 | 1085821 | 1138128 | 1108067 | 0 | 0 | 0 | 1108067 | 1103946 | 101.7% | 1 | -4121 | 2307 | 17 | 11 | 0 | 4 | 3712 | 0 | 0 | 3 | 18533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 22246 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 108 | 1209049.68 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1619 | 43365815201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 145 | 172 | 171 | 110.3% | 1 | 1 | 0 | 0 | 27 | 0 | 618558 | 0 | 618558 | 622340 | 622340 | 0 | 0 | 0 | 622340 | 622340 | 100.6% | 1 | 0 | 3782 | 7 | 4 | 2 | 0 | 3782 | 3782 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 3782 | 3782 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-10-05 | QTR2 | 16/17 | 108 | 495886.08 | B0 | ACC - LUMP SUM
| 01 | T1629 | 43325615201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 85 | 88 | 74 | 83.53% | 1 | 14 | 0 | 0 | 3 | 0 | 910000 | 47212 | 862788 | 910000 | 883227 | 0 | 0 | 0 | 883227 | 883227 | 102.4% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 13198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13198 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-28 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 115 | 857875.38 | B0 | ACC - LUMP SUM
| 01 | T1633 | 43092415201 | 2016-03-30 | QTR3 | 15/16 | 2 | 1 | 110 | 184 | 178 | 126.4% | 0 | 6 | 0 | 0 | 39 | 35 | 964016 | 0 | 964016 | 968295 | 968295 | 0 | 0 | 0 | 968295 | 968295 | 100.4% | 1 | 0 | 4279 | 27 | 12 | 0 | 0 | 0 | 0 | 0 | 35 | 4279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 4279 | 0 | F592190605 | O-A-K/FLORIDA INC. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 |  | 2016-12-29 | QTR2 | 16/17 | 113 | 965168.46 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1637 | 43359315201 | 2016-01-27 | QTR3 | 15/16 | 2 | 1 | 175 | 208 | 203 | 97.14% | 1 | 5 | 0 | 0 | 33 | 0 | 2282142 | 50000 | 2232142 | 2313043 | 2274863 | 0 | 0 | 0 | 2274863 | 2279204 | 102.1% | 1 | 4342 | 30901 | 25 | 8 | 0 | 0 | 30901 | 0 | 0 | 0 | 15071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45973 | 0 | F381807765 | DOUGLAS N. HIGGINS INC. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 |  | 2016-12-16 | QTR2 | 16/17 | 115 | 2156564.24
| 01 | T1638 | 43450315201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 90 | 100 | 98 | 97.78% | 1 | 2 | 0 | 0 | 10 | 0 | 98907 | 6887 | 92020 | 98907 | 93187 | 0 | 0 | 0 | 93187 | 93187 | 101.3% | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1166 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-02-06 | QTR3 | 16/17 |  | 2016-12-12 | QTR2 | 16/17 | 118 | 117357.81 | B0 | ACC - LUMP SUM
| 01 | T1639 | 43321815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 100 | 124 | 122 | 100% | 1 | 2 | 0 | 0 | 22 | 2 | 484935 | 19525 | 465410 | 484935 | 472783 | 0 | 0 | 0 | 472783 | 472783 | 101.6% | 1 | 0 | 0 | 7 | 15 | 0 | 0 | 0 | 0 | 0 | 2 | 7373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7373 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING O | N/A | N/A | N/A | N/A | 2017-06-05 | QTR4 | 16/17 |  | 2017-02-10 | QTR3 | 16/17 | 113 | 507136.03 | B0 | ACC - LUMP SUM
| 01 | T1645 | 43146115201 | 2016-03-30 | QTR3 | 15/16 | 2 | 0 | 200 | 247 | 265 | 109% | 1 | -18 | 18 | 0 | 47 | 0 | 2749030 | 50000 | 2699030 | 2749030 | 2742983 | -50598 | 0 | -50598 | 2692385 | 2702439 | 100.1% | 1 | 10054 | 0 | 30 | 17 | 0 | 0 | 19807 | 0 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22257 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-05-23 | QTR4 | 16/17 |  | 2017-03-17 | QTR3 | 16/17 | 118 | 2791241.12 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1649 | 43092615201 | 2016-03-30 | QTR3 | 15/16 | 2 | 0 | 105 | 148 | 148 | 105.7% | 1 | 0 | 0 | 0 | 37 | 6 | 1164267 | 0 | 1164267 | 1164267 | 1163985 | 0 | 0 | 0 | 1163985 | 1163985 | 99.98% | 1 | 0 | 0 | 30 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-02-02 | QTR3 | 16/17 |  | 2016-12-19 | QTR2 | 16/17 | 113 | 995954.35 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1651 | 43134115201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 90 | 91 | 78 | 85.56% | 1 | 13 | 0 | 0 | 1 | 0 | 194630 | 9734 | 184896 | 194630 | 184896 | 0 | 0 | 0 | 184896 | 184896 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 |  | 2016-06-06 | QTR4 | 15/16 | 118 | 236550.37 | B0 | ACC - LUMP SUM
| 01 | T1654 | 43448815201 | 2016-05-25 | QTR4 | 15/16 | 1 | 0 | 75 | 82 | 81 | 98.67% | 1 | 1 | 0 | 0 | 7 | 0 | 374353 | 11020 | 363333 | 374353 | 363333 | 0 | 0 | 0 | 363333 | 363333 | 100% | 1 | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2017-02-02 | QTR3 | 16/17 |  | 2016-12-01 | QTR2 | 16/17 | 108 | 331783.25 | B0 | ACC - LUMP SUM
| 01 | T1656 | 43698615201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 60 | 67 | 64 | 95% | 1 | 3 | 0 | 0 | 7 | 0 | 162848 | 7848 | 155000 | 162848 | 155000 | 0 | 0 | 0 | 155000 | 155000 | 100% | 1 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-01-18 | QTR3 | 16/17 |  | 2016-12-13 | QTR2 | 16/17 | 115 | 192823.77 | B0 | ACC - LUMP SUM
| 01 | T1657 | 43131915201 | 2016-02-24 | QTR3 | 15/16 | 3 | 0 | 200 | 270 | 270 | 114.5% | 1 | 0 | 0 | 0 | 41 | 29 | 1914753 | 50000 | 1864753 | 1914753 | 1975777 | 0 | 0 | 0 | 1975777 | 1983617 | 106.4% | 1 | 7841 | 0 | 25 | 16 | 0 | 0 | 0 | 0 | 0 | 29 | 18698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 18698 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-05-16 | QTR4 | 16/17 |  | 2017-03-10 | QTR3 | 16/17 | 118 | 1639168.26
| 01 | T1659 | 43472815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 70 | 78 | 49 | 58.57% | 1 | 29 | 0 | 0 | 8 | 0 | 238287 | 9912 | 228375 | 238287 | 228375 | 0 | 0 | 0 | 228375 | 228375 | 100% | 1 | 0 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 |  | 2016-10-17 | QTR2 | 16/17 | 115 | 176436.4 | B0 | ACC - LUMP SUM
| 01 | T1669 | 43502315201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 150 | 152 | 96 | 62.67% | 1 | 56 | 0 | 0 | 2 | 0 | 917114 | 42067 | 875047 | 917114 | 879919 | 0 | 0 | 0 | 879919 | 881307 | 100.7% | 1 | 1388 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2017-06-08 | QTR4 | 16/17 |  | 2017-04-26 | QTR4 | 16/17 | 113 | 940355.44 | B0 | ACC - LUMP SUM
| 01 | T1684 | 43766015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 21 | 21 | 21 | 100% | 1 | 0 | 0 | 0 | 0 | 0 | 114858 | 5825 | 109033 | 114858 | 107442 | 0 | 0 | 0 | 107442 | 107442 | 98.54% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 |  | 2017-01-23 | QTR3 | 16/17 | 115 | 126526.39
| 01 | T1A02 | 42518315201 | 2014-12-03 | QTR2 | 14/15 | 1 | 4 | 250 | 403 | 402 | 130.8% | 0 | 1 | 0 | 0 | 75 | 78 | 5396928 | 50000 | 5346928 | 5491707 | 5952983 | 0 | 0 | 0 | 5952983 | 5952455 | 111.3% | 0 | -528 | 94779 | 57 | 18 | 0 | 75 | 18567 | 0 | 0 | 3 | 122779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 141346 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 |  | 2016-05-19 | QTR4 | 15/16 | 115 | 4358786.71 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1A15 | 43325515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 70 | 97 | 97 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 219504 | 10504 | 209000 | 219504 | 213917 | 0 | 0 | 0 | 213917 | 213917 | 102.4% | 1 | 0 | 0 | 15 | 12 | 0 | 0 | 4917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4917 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-02-20 | QTR3 | 15/16 | 106 | 200589.29 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 37 | 53 | 81 | 7135 | 9095 | 8834 | 86.49% | 32 | 261 | 236 | 0 | 1657 | 303 | 153027844 | 1661962 | 151365882 | 154467448 | 153493019 | -422878 | 2592000 | 2169122 | 155662141 | 148637681 | 89.19% | 33 | -7024460 | 1439603 | 1223 | 348 | 2 | 169 | 134354 | 42997 | 14 | 121 | 1752803 | 29096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 16 | 495879 | 0 | 0 | 0 | 12379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3507 | 0 | 0 | 0 | 19544 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -498487 | 0 | 18 | 303 | 1923980 | 72093
| 01 | E1L58 | 19753445201 | 2013-01-10 | QTR3 | 12/13 | 3 | 23 | 939 | 1226 | 1226 | 116.9% | 1 | 0 | 0 | 0 | 257 | 30 | 21988997 | 150000 | 21838997 | 23327334 | 23110936 | 0 | 0 | 0 | 23110936 | 22111039 | 101.2% | 1 | -999897 | 1338337 | 81 | 47 | 129 | 30 | 1271226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71910 | 71910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 30 | 1366773 | 71910 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-06-01 | QTR4 | 16/17 |  | 2016-12-01 | QTR2 | 16/17 | 108 | 21988997 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1N36 | 43544915201 | 2014-06-19 | QTR4 | 13/14 | 1 | 2 | 160 | 182 | 194 | 111.2% | 1 | -12 | 12 | 0 | 16 | 6 | 1877203 | 50000 | 1827203 | 1918177 | 1843430 | -20904 | 0 | -20904 | 1822526 | 1821939 | 99.71% | 1 | -587 | 40974 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 6 | 46084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 46084 | 0 | F593586613 | EVANS CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 |  | 2015-05-19 | QTR4 | 14/15 | 108 | 2352808.24
| 01 | E1N74 | 42912015201 | 2014-12-18 | QTR2 | 14/15 | 1 | 0 | 185 | 212 | 212 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 3107573 | 50000 | 3057573 | 3107573 | 3110593 | 0 | 0 | 0 | 3110593 | 2961957 | 96.87% | 1 | -148636 | 0 | 9 | 18 | 0 | 0 | 7628 | 0 | 0 | 0 | 8425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16053 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-01-21 | QTR3 | 15/16 | 113 | 3280021.43
| 01 | E1N87 | 43120915201 | 2015-02-19 | QTR3 | 14/15 | 1 | 0 | 300 | 336 | 336 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 3172000 | 50000 | 3122000 | 3172000 | 3272265 | 0 | 0 | 0 | 3272265 | 3269380 | 104.7% | 1 | -2886 | 0 | 24 | 12 | 0 | 0 | 7188 | 0 | 0 | 0 | 21276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40644 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 |  | 2016-04-25 | QTR4 | 15/16 | 108 | 3312411.11
| 01 | E1O02 | 43161515201 | 2015-01-15 | QTR3 | 14/15 | 1 | 2 | 290 | 354 | 354 | 110.3% | 1 | 0 | 0 | 0 | 34 | 30 | 5445703 | 56538 | 5389165 | 6533716 | 6114803 | 0 | 0 | 0 | 6114803 | 5883385 | 109.2% | 1 | -231419 | 1088013 | 19 | 15 | 0 | 20 | 396717 | 0 | 0 | 10 | 691296 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1088013 | 691296 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 113 | 4971481.53
| 01 | E1O45 | 43160315201 | 2015-11-19 | QTR2 | 15/16 | 2 | 0 | 250 | 280 | 279 | 100% | 1 | 1 | 0 | 0 | 29 | 1 | 5243826 | 73650 | 5170176 | 5243826 | 5060368 | 0 | 0 | 0 | 5060368 | 4915836 | 95.08% | 1 | -144532 | 0 | 13 | 16 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2017-05-01 | QTR4 | 16/17 |  | 2017-01-05 | QTR3 | 16/17 | 118 | 7438831.94
| 01 | E1O48 | 43129415201 | 2015-12-17 | QTR2 | 15/16 | 1 | 2 | 240 | 295 | 295 | 105% | 1 | 0 | 0 | 0 | 53 | 2 | 5895900 | 54282 | 5841618 | 5903041 | 5910137 | 0 | 0 | 0 | 5910137 | 5818680 | 99.61% | 1 | -91457 | 7141 | 26 | 17 | 0 | 2 | 8312 | 0 | 0 | 0 | 40806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 4868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 53985 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-05-23 | QTR4 | 16/17 |  | 2017-02-13 | QTR3 | 16/17 | 108 | 5444557.02 | B0 | ACC - LUMP SUM
| 01 | E1O51 | 43129115201 | 2016-03-17 | QTR3 | 15/16 | 1 | 3 | 200 | 237 | 234 | 98.5% | 1 | 3 | 0 | 0 | 37 | 0 | 6085726 | 74632 | 6011094 | 6210864 | 5926238 | 0 | 0 | 0 | 5926238 | 5952143 | 99.02% | 1 | 25904 | 125138 | 21 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 45051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125138 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-05-23 | QTR4 | 16/17 |  | 2017-03-07 | QTR3 | 16/17 | 108 | 7615266.46
| 01 | E1O52 | 43120615201 | 2015-11-19 | QTR2 | 15/16 | 1 | 2 | 145 | 179 | 179 | 110.3% | 1 | 0 | 0 | 0 | 19 | 15 | 2386060 | 50000 | 2336060 | 2389112 | 2334583 | 0 | 0 | 0 | 2334583 | 2290475 | 98.05% | 1 | -44107 | 3052 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 15 | 31743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 31743 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-01-24 | QTR3 | 16/17 |  | 2016-10-04 | QTR2 | 16/17 | 108 | 2466348.35
| 01 | E1O54 | 43170515201 | 2016-01-21 | QTR3 | 15/16 | 1 | 0 | 130 | 254 | 236 | 86.15% | 1 | 18 | 0 | 0 | 124 | 0 | 960772 | 50000 | 910772 | 960772 | 890253 | 0 | 0 | 0 | 890253 | 890253 | 97.75% | 1 | 0 | 0 | 106 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2017-02-16 | QTR3 | 16/17 |  | 2017-01-13 | QTR3 | 16/17 | 113 | 1095709.39 | B0 | ACC - LUMP SUM
| 01 | E1O75 | 43503815201 | 2016-01-21 | QTR3 | 15/16 | 1 | 0 | 60 | 62 | 54 | 86.67% | 1 | 8 | 0 | 0 | 2 | 0 | 149955 | 6815 | 143140 | 149955 | 147793 | 0 | 0 | 0 | 147793 | 147793 | 103.3% | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 6813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6813 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-06-21 | QTR4 | 15/16 | 118 | 157973.52
| 01 | E1O76 | 43504325201 | 2016-03-17 | QTR3 | 15/16 | 1 | 1 | 85 | 150 | 150 | 124.7% | 0 | 0 | 0 | 0 | 44 | 21 | 889110 | 31776 | 857334 | 947735 | 899072 | 0 | 0 | 0 | 899072 | 899072 | 104.9% | 1 | 0 | 58625 | 26 | 18 | 0 | 0 | 0 | 0 | 0 | 21 | 58625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 58625 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-04-12 | QTR4 | 16/17 |  | 2017-01-04 | QTR3 | 16/17 | 113 | 866149.16
| 01 | E1O79 | 43708215201 | 2015-12-17 | QTR2 | 15/16 | 1 | 2 | 300 | 336 | 333 | 99% | 1 | 3 | 0 | 0 | 36 | 0 | 4699575 | 50000 | 4649575 | 4749575 | 4699575 | 0 | 0 | 0 | 4699575 | 4699575 | 101.1% | 1 | 0 | 50000 | 18 | 18 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-02-22 | QTR3 | 16/17 |  | 2017-01-20 | QTR3 | 16/17 | 115 | 4699575 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1O85 | 42814015201 | 2015-11-19 | QTR2 | 15/16 | 1 | 0 | 100 | 247 | 247 | 104% | 1 | 0 | 0 | 0 | 143 | 4 | 1074449 | 50000 | 1024449 | 1074449 | 1064642 | 0 | 0 | 0 | 1064642 | 1064642 | 103.9% | 1 | 0 | 0 | 131 | 12 | 0 | 2 | 7446 | 0 | 0 | 2 | 31842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 39288 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-01 | QTR4 | 16/17 |  | 2016-12-08 | QTR2 | 16/17 | 113 | 1084852.65 | B0 | ACC - LUMP SUM
| 01 | E1P12 | 43856115201 | 2016-06-09 | QTR4 | 15/16 | 1 | 1 | 85 | 97 | 95 | 97.65% | 1 | 2 | 0 | 0 | 12 | 0 | 298707 | 12047 | 286660 | 305757 | 301340 | 0 | 0 | 0 | 301340 | 301340 | 105.1% | 1 | 0 | 7050 | 0 | 12 | 0 | 0 | 4450 | 0 | 0 | 0 | 10230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14680 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 |  | 2017-01-16 | QTR3 | 16/17 | 108 | 246048.46 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 15 | 18 | 38 | 3469 | 4447 | 4424 | 93.33% | 14 | 23 | 12 | 0 | 869 | 109 | 63275556 | 809740 | 62465816 | 65993886 | 64686028 | -20904 | 0 | -20904 | 64665124 | 63027509 | 100% | 15 | -1637617 | 2718330 | 496 | 234 | 129 | 55 | 1759780 | 0 | 0 | 54 | 985378 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 155847 | 71910 | 0 | 0 | 13199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 109 | 2937839 | 763206
| District 01 Totals |  |  |  |  | 52 | 71 | 119 | 10604 | 13542 | 13258 | 88.46% | 46 | 284 | 248 | 0 | 2526 | 412 | 216303400 | 2471702 | 213831698 | 220461334 | 218179047 | -443782 | 2592000 | 2148218 | 220327265 | 211665190 | 92.31% | 48 | -8662077 | 4157933 | 1719 | 582 | 131 | 224 | 1894134 | 42997 | 14 | 175 | 2738181 | 720392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 9 | 16 | 651726 | 71910 | 0 | 0 | 25578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27144 | 0 | 0 | 0 | 19544 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -498487 | 0 | 156 | 412 | 4861819 | 835299
| 02 | T2473 | 42449415201 | 2013-04-24 | QTR4 | 12/13 | 1 | 1 | 360 | 442 | 442 | 100% | 1 | 0 | 0 | 0 | 82 | 0 | 6447454 | 73390 | 6374065 | 6752983 | 6507167 | 0 | 0 | 0 | 6507167 | 6505012 | 102.1% | 1 | -2155 | 305529 | 54 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 317914 | 18101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348362 | 18101 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-04-06 | QTR4 | 16/17 |  | 2014-10-11 | QTR2 | 14/15 | 208 | 6671609.38
| 02 | T2506 | 43040415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 45 | 48 | 103 | 222.2% | 0 | -55 | 55 | 0 | 3 | 0 | 136157 | 7800 | 128357 | 136157 | 128357 | -47602 | 0 | -47602 | 80754 | 80754 | 62.91% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-09-14 | QTR1 | 16/17 |  | 2014-05-14 | QTR4 | 13/14 | 208 | 153002.52 | B0 | ACC - LUMP SUM
| 02 | T2523 | 43051815201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 90 | 136 | 135 | 138.9% | 0 | 1 | 0 | 0 | 40 | 6 | 212150 | 10702 | 201448 | 212150 | 210626 | -31760 | 0 | -31760 | 178866 | 178866 | 88.79% | 1 | 0 | 0 | 7 | 3 | 0 | 6 | 9178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 9178 | 0 | F753160478 | ENVIRONMENTAL INNOVATIONS INC | N/A | N/A | N/A | N/A | 2017-01-12 | QTR3 | 16/17 |  | 2014-10-20 | QTR2 | 14/15 | 209 | 224301.27 | B0 | ACC - LUMP SUM
| 02 | T2533 | 43355415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 3 | 400 | 535 | 535 | 104.5% | 1 | 0 | 0 | 0 | 117 | 18 | 8533240 | 72079 | 8461162 | 8598881 | 9356445 | 0 | 0 | 0 | 9356445 | 9207548 | 108.8% | 1 | -148897 | 65641 | 58 | 59 | 0 | 0 | 229 | 0 | 0 | 18 | 64256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19692 | 0 | 0 | 18 | 46705 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 208 | 7794225.55
| 02 | T2538 | 42696315201 | 2014-06-18 | QTR4 | 13/14 | 2 | 0 | 130 | 198 | 198 | 105.4% | 1 | 0 | 0 | 0 | 65 | 3 | 3648202 | 50000 | 3598202 | 3648202 | 3611865 | 0 | 0 | 0 | 3611865 | 3514982 | 97.69% | 1 | -96884 | 0 | 33 | 28 | 4 | 3 | 9477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 9477 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-10-05 | QTR2 | 16/17 |  | 2015-05-28 | QTR4 | 14/15 | 208 | 3330302.73
| 02 | T2541 | 42607315201 | 2014-09-24 | QTR1 | 14/15 | 1 | 1 | 380 | 501 | 501 | 112.1% | 1 | 0 | 0 | 0 | 83 | 38 | 3641891 | 50000 | 3591891 | 3767252 | 4042041 | 0 | 0 | 0 | 4042041 | 3981696 | 110.9% | 0 | -60345 | 125361 | 55 | 20 | 0 | 0 | 0 | 0 | 0 | 38 | 174588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 174588 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-11-14 | QTR2 | 16/17 |  | 2016-05-26 | QTR4 | 15/16 | 209 | 3748196.45
| 02 | T2567 | 43224715201 | 2015-02-25 | QTR3 | 14/15 | 1 | 8 | 135 | 252 | 252 | 141.5% | 0 | 0 | 0 | 0 | 79 | 38 | 1013111 | 0 | 1013111 | 1368388 | 1368010 | 0 | 0 | 0 | 1368010 | 1368010 | 135% | 0 | 0 | 355277 | 46 | 15 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-02-01 | QTR3 | 15/16 | 214 | 1004174.39 | B0 | ACC - LUMP SUM
| 02 | T2572 | 43061415201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 150 | 191 | 191 | 102% | 1 | 0 | 0 | 0 | 41 | 0 | 1990811 | 0 | 1990811 | 2002450 | 2059822 | 0 | 0 | 0 | 2059822 | 2059822 | 103.5% | 1 | 0 | 11638 | 21 | 17 | 0 | 0 | 11638 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 11638 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-07-21 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 214 | 1508389.63
| 02 | T2574 | 21325145201 | 2015-03-25 | QTR3 | 14/15 | 1 | 1 | 210 | 311 | 316 | 134.3% | 0 | -5 | 5 | 0 | 39 | 62 | 3292108 | 50000 | 3242108 | 3306325 | 3271355 | -14380 | 0 | -14380 | 3256975 | 3216216 | 99.2% | 1 | -40760 | 14217 | 14 | 20 | 0 | 0 | 0 | 0 | 0 | 14 | 8349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 14217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 22566 | 0 | F592913720 | CALLAWAY CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-03-21 | QTR3 | 16/17 |  | 2016-04-15 | QTR4 | 15/16 | 208 | 3074491.57
| 02 | T2575 | 42747615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 360 | 431 | 424 | 100.6% | 1 | 7 | 0 | 0 | 62 | 9 | 6409349 | 53558 | 6355792 | 6447241 | 6325936 | 0 | 0 | 0 | 6325936 | 6325901 | 99.53% | 1 | -35 | 37891 | 15 | 47 | 0 | 0 | 0 | 0 | 0 | 9 | 41071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 63946 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-05-24 | QTR4 | 16/17 |  | 2017-03-02 | QTR3 | 16/17 | 216 | 5409342.01
| 02 | T2581 | 42747415201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 483 | 519 | 517 | 99.59% | 1 | 2 | 0 | 0 | 36 | 0 | 5752494 | 63821 | 5688673 | 5752494 | 5614852 | 0 | 0 | 0 | 5614852 | 5614852 | 98.7% | 1 | 0 | 0 | 12 | 24 | 0 | 0 | 6927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6927 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-03-31 | QTR3 | 16/17 |  | 2017-02-15 | QTR3 | 16/17 | 214 | 6445947.23
| 02 | T2584 | 43051315201 | 2015-08-26 | QTR1 | 15/16 | 2 | 1 | 150 | 186 | 185 | 114% | 1 | 1 | 0 | 0 | 14 | 22 | 3444187 | 50000 | 3394187 | 3524159 | 3538172 | 0 | 0 | 0 | 3538172 | 3415729 | 100.6% | 1 | -122443 | 79972 | 8 | 6 | 0 | 3 | 2309 | 0 | 0 | 19 | 89994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 92303 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-12-28 | QTR2 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 214 | 3688557.42
| 02 | T2587 | 43265515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 120 | 151 | 151 | 100% | 1 | 0 | 0 | 0 | 31 | 0 | 718800 | 0 | 718800 | 718800 | 718800 | 0 | 0 | 0 | 718800 | 718800 | 100% | 1 | 0 | 0 | 26 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453689782 | SOUTHERN STATES PAVEMENT MARKINGS INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-06-02 | QTR4 | 15/16 | 209 | 769166.88 | B0 | ACC - LUMP SUM
| 02 | T2588 | 21237925201 | 2015-09-30 | QTR1 | 15/16 | 1 | 3 | 170 | 227 | 227 | 130% | 0 | 0 | 0 | 0 | 23 | 34 | 2271500 | 0 | 2271500 | 2329229 | 2340019 | 0 | 0 | 0 | 2340019 | 2337891 | 102.9% | 1 | -2128 | 57729 | 5 | 1 | 4 | 0 | 7981 | 0 | 13 | 5 | 38697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 11052 | 11052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 34 | 57729 | 11052 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-11-29 | QTR2 | 16/17 |  | 2016-08-17 | QTR1 | 16/17 | 208 | 2754838.98 | B0 | ACC - LUMP SUM
| 02 | T2589 | 41525415201 | 2015-12-03 | QTR2 | 15/16 | 2 | 2 | 250 | 256 | 224 | 87.2% | 1 | 32 | 0 | 0 | 6 | 0 | 1503905 | 0 | 1503905 | 1530011 | 1553775 | 0 | 0 | 0 | 1553775 | 1554113 | 103.3% | 1 | 338 | 26105 | 3 | 3 | 0 | 0 | 26105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26105 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 |  | 2016-10-04 | QTR2 | 16/17 | 208 | 1346460.02
| 02 | T2593 | 43051715201 | 2015-09-30 | QTR1 | 15/16 | 3 | 2 | 179 | 211 | 210 | 105% | 1 | 1 | 0 | 0 | 22 | 10 | 1956915 | 0 | 1956915 | 1997332 | 1951682 | 0 | 0 | 0 | 1951682 | 1947009 | 99.49% | 1 | -4672 | 40417 | 19 | 3 | 0 | 10 | 40417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 40417 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-16 | QTR2 | 16/17 |  | 2016-08-01 | QTR1 | 16/17 | 209 | 2334094.44
| 02 | T2594 | 43265415201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 152 | 152 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 475000 | 0 | 475000 | 475000 | 475000 | 0 | 0 | 0 | 475000 | 475000 | 100% | 1 | 0 | 0 | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-09-30 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 209 | 428505.77 | B0 | ACC - LUMP SUM
| 02 | T2598 | 43265915201 | 2015-12-03 | QTR2 | 15/16 | 1 | 0 | 160 | 178 | 189 | 106.9% | 1 | -11 | 11 | 0 | 18 | 0 | 848333 | 43639 | 804695 | 848333 | 798176 | -19162 | 0 | -19162 | 779014 | 774669 | 96.27% | 1 | -4345 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2794 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-04-05 | QTR4 | 16/17 |  | 2016-12-09 | QTR2 | 16/17 | 208 | 911545.64
| 02 | T2602 | 43074515201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 100 | 114 | 113 | 99% | 1 | 1 | 0 | 0 | 14 | 0 | 558858 | 27404 | 531454 | 558858 | 508320 | 0 | 0 | 0 | 508320 | 508320 | 95.65% | 1 | 0 | 0 | 11 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-10-17 | QTR2 | 16/17 | 209 | 579077.38
| 02 | T2603 | 43075915201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 95 | 95 | 118.7% | 1 | 0 | 0 | 0 | 6 | 14 | 521218 | 23780 | 497438 | 521218 | 506672 | 0 | 0 | 0 | 506672 | 506672 | 101.9% | 1 | 0 | 0 | 3 | 3 | 0 | 10 | 1681 | 0 | 0 | 0 | 7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 9235 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-07-01 | QTR1 | 16/17 | 214 | 510081.72
| 02 | T2604 | 43226115201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 200 | 233 | 237 | 105% | 1 | -4 | 4 | 0 | 27 | 6 | 7717554 | 101575 | 7615979 | 7717554 | 7824593 | -15080 | 0 | -15080 | 7809513 | 7576665 | 99.48% | 1 | -232848 | 0 | 24 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-27 | QTR2 | 16/17 |  | 2016-09-07 | QTR1 | 16/17 | 209 | 9660990.21
| 02 | T2605 | 43226415201 | 2016-02-24 | QTR3 | 15/16 | 1 | 1 | 270 | 313 | 312 | 103.3% | 1 | 1 | 0 | 0 | 33 | 10 | 4020836 | 50000 | 3970836 | 4002599 | 3805029 | 0 | 0 | 0 | 3805029 | 3807540 | 95.89% | 1 | 2511 | -18237 | 15 | 18 | 0 | 10 | 38621 | 0 | 0 | 0 | -7854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 30766 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-01 | QTR4 | 16/17 |  | 2017-03-13 | QTR3 | 16/17 | 216 | 4422862.3
| 02 | T2608 | 43055825201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 84 | 80 | 94.67% | 1 | 4 | 0 | 0 | 9 | 0 | 148375 | 8369 | 140006 | 148375 | 138616 | 0 | 0 | 0 | 138616 | 138616 | 99.01% | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 209 | 178082.19
| 02 | T2610 | 41525115201 | 2015-12-09 | QTR2 | 15/16 | 1 | 0 | 270 | 279 | 269 | 97.04% | 1 | 10 | 0 | 0 | 9 | 0 | 1544000 | 0 | 1544000 | 1544000 | 1614197 | 0 | 0 | 0 | 1614197 | 1614952 | 104.6% | 1 | 755 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2017-03-08 | QTR3 | 16/17 |  | 2016-11-18 | QTR2 | 16/17 | 208 | 1676280.55
| 02 | T2613 | 42869615201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 190 | 227 | 227 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 7289393 | 80145 | 7209248 | 7289393 | 7240404 | 0 | 0 | 0 | 7240404 | 7140234 | 99.04% | 1 | -100170 | 0 | 23 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-05-03 | QTR4 | 16/17 |  | 2016-12-09 | QTR2 | 16/17 | 209 | 8014109.84
| 02 | T2626 | 43055215201 | 2015-12-03 | QTR2 | 15/16 | 1 | 0 | 210 | 255 | 255 | 104.8% | 1 | 0 | 0 | 0 | 43 | 2 | 3284461 | 50000 | 3234461 | 3284461 | 3197387 | 0 | 0 | 0 | 3197387 | 3131128 | 96.81% | 1 | -66259 | 0 | 26 | 9 | 0 | 0 | 0 | 0 | 7 | 0 | 10174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 12924 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-26 | QTR3 | 16/17 |  | 2016-11-28 | QTR2 | 16/17 | 216 | 3672060.67
| 02 | T2631 | 43808515201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 75 | 97 | 96 | 113.3% | 1 | 1 | 0 | 0 | 22 | 0 | 148168 | 6145 | 142023 | 148168 | 142273 | 0 | 0 | 0 | 142273 | 142273 | 100.2% | 1 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-22 | QTR4 | 16/17 |  | 2017-04-07 | QTR4 | 16/17 | 214 | 129624.31
| 02 | T2659 | 43432715201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 200 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 2042000 | 0 | 2042000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-06-13 | QTR4 | 16/17 |  |  | QTR2 | 00/01 |  | 2336443.75
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 28 | 34 | 27 | 5557 | 6622 | 6636 | 82.14% | 23 | -14 | 75 | 0 | 993 | 272 | 79570470 | 872407 | 78698067 | 78630013 | 78849591 | -127984 | 0 | -127984 | 78721606 | 77843270 | 92.86% | 26 | -878337 | 1101540 | 534 | 353 | 8 | 42 | 154563 | 0 | 34 | 141 | 1103760 | 18101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 57985 | 0 | 0 | 48 | 14217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 11052 | 11052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19692 | 0 | 42 | 266 | 1321884 | 29153
| 02 | E2P99 | 21330125201 | 2012-06-29 | QTR4 | 11/12 | 2 | 7 | 615 | 1443 | 1443 | 202% | 0 | 0 | 0 | 0 | 201 | 627 | 17859000 | 150000 | 17709000 | 27306925 | 27318877 | 0 | 0 | 0 | 27318877 | 26689964 | 150.7% | 0 | -628913 | 9447925 | 119 | 82 | 0 | 627 | 9078926 | 2177986 | 0 | 0 | 325187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0 | 0 | 2873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627 | 9579662 | 2177986 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-12-14 | QTR2 | 16/17 |  | 2016-08-09 | QTR1 | 16/17 | 208 | 28650000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2R04 | 21066125201 | 2012-12-12 | QTR2 | 12/13 | 2 | 1 | 90 | 192 | 224 | 216.7% | 0 | -32 | 32 | 0 | 32 | 70 | 1430432 | 50000 | 1380432 | 1430840 | 1393606 | -49024 | 0 | -49024 | 1344582 | 1344578 | 97.4% | 1 | -4 | 408 | 14 | 15 | 3 | 0 | 4074 | 0 | 0 | 70 | 21643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 70 | 25716 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2014-03-07 | QTR3 | 13/14 | 208 | 1293927.32
| 02 | E2R17 | 21237935201 | 2013-06-20 | QTR4 | 12/13 | 5 | 1 | 790 | 846 | 846 | 100% | 1 | 0 | 0 | 0 | 56 | 0 | 11440230 | 150000 | 11290230 | 11429587 | 11316805 | 0 | 0 | 0 | 11316805 | 11261013 | 99.74% | 1 | -55793 | -10643 | 7 | 49 | 0 | 0 | -621 | 0 | 0 | 0 | 42964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11541 | 0 | 0 | 0 | 32321 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2015-12-07 | QTR2 | 15/16 | 208 | 13890662.92 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
| 02 | E2T58 | 43226315201 | 2015-11-18 | QTR2 | 15/16 | 1 | 0 | 140 | 181 | 181 | 101.4% | 1 | 0 | 0 | 0 | 41 | 0 | 3757549 | 50000 | 3707549 | 3757549 | 3830766 | 0 | 0 | 0 | 3830766 | 3684887 | 99.39% | 1 | -145879 | 0 | 30 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-10-11 | QTR2 | 16/17 |  | 2016-09-08 | QTR1 | 16/17 | 214 | 4878401.01
| 02 | E2T69 | 43041715201 | 2015-07-15 | QTR1 | 15/16 | 1 | 3 | 210 | 362 | 362 | 161% | 0 | 0 | 0 | 0 | 30 | 122 | 1759555 | 50000 | 1709555 | 1996713 | 2571252 | 0 | 0 | 0 | 2571252 | 2563560 | 150% | 0 | -7693 | 237158 | 11 | 13 | 0 | 18 | 101267 | 0 | 0 | 104 | 148934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 250201 | 0 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 |  | 2016-09-16 | QTR1 | 16/17 | 208 | 1357063.07
| 02 | E2T70 | 43219415201 | 2015-07-15 | QTR1 | 15/16 | 1 | 0 | 190 | 217 | 214 | 100.5% | 1 | 3 | 0 | 0 | 23 | 4 | 741630 | 36943 | 704687 | 741630 | 709180 | 0 | 0 | 0 | 709180 | 709010 | 100.6% | 1 | -170 | 0 | 14 | 9 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 214 | 775810
| 02 | E2T74 | 42342715201 | 2015-09-16 | QTR1 | 15/16 | 1 | 0 | 135 | 163 | 162 | 99.26% | 1 | 1 | 0 | 0 | 28 | 0 | 4336630 | 50000 | 4286630 | 4336630 | 4421132 | 0 | 0 | 0 | 4421132 | 4255700 | 99.28% | 1 | -165433 | 0 | 27 | 1 | 0 | 0 | 17388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17388 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-28 | QTR1 | 16/17 |  | 2016-06-13 | QTR4 | 15/16 | 209 | 4754490.59
| 02 | E2T86 | 20789425201 | 2015-11-18 | QTR2 | 15/16 | 2 | 1 | 250 | 289 | 284 | 102.4% | 1 | 5 | 0 | 0 | 28 | 11 | 825208 | 41817 | 783391 | 860208 | 824755 | 0 | 0 | 0 | 824755 | 824711 | 105.3% | 1 | -44 | 35000 | 10 | 18 | 0 | 0 | 0 | 0 | 0 | 11 | 54666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 54666 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2017-06-12 | QTR4 | 16/17 |  | 2017-02-15 | QTR3 | 16/17 | 209 | 890405.76
| 02 | E2T87 | 20967415201 | 2015-11-18 | QTR2 | 15/16 | 1 | 0 | 140 | 199 | 198 | 117.1% | 1 | 1 | 0 | 0 | 34 | 25 | 1743906 | 50000 | 1693906 | 1743906 | 2125210 | 0 | 0 | 0 | 2125210 | 2124106 | 125.4% | 0 | -1104 | 0 | 30 | 4 | 0 | 0 | 0 | 0 | 0 | 21 | 39680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 41424 | 0 | F205877898 | KIRBY DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 |  | 2016-08-24 | QTR1 | 16/17 | 208 | 1607950.75
| 02 | E2T90 | 20838945201 | 2015-12-16 | QTR2 | 15/16 | 1 | 0 | 185 | 192 | 155 | 80% | 1 | 37 | 0 | 0 | 7 | 0 | 559753 | 48363 | 511389 | 559753 | 512091 | 0 | 0 | 0 | 512091 | 512091 | 100.1% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593285921 | S & D INDUSTRIAL PAINTING INC. | N/A | N/A | N/A | N/A | 2016-11-08 | QTR2 | 16/17 |  | 2016-10-03 | QTR2 | 16/17 | 209 | 1034491.52
| 02 | E2U35 | 43226515201 | 2016-02-24 | QTR3 | 15/16 | 1 | 1 | 280 | 320 | 314 | 97.86% | 1 | 6 | 0 | 0 | 40 | 0 | 5333716 | 66130 | 5267586 | 5333716 | 5070766 | 0 | 0 | 0 | 5070766 | 5049334 | 95.86% | 1 | -21432 | 0 | 22 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-18 | QTR4 | 16/17 |  | 2017-03-13 | QTR3 | 16/17 | 216 | 6137175.52
| 02 | E2U45 | 42871125201 | 2015-12-16 | QTR2 | 15/16 | 1 | 0 | 45 | 53 | 211 | 453.3% | 0 | -158 | 158 | 0 | 7 | 1 | 138261 | 7135 | 131126 | 138261 | 134115 | -43856 | 0 | -43856 | 90258 | 120111 | 91.6% | 1 | 29853 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2989 | 0 | Z31-0396250 | OHIO CASUALTY INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-21 | QTR2 | 16/17 | 208 | 151023.35 | B0 | ACC - LUMP SUM
| 02 | E2U47 | 43226215201 | 2016-04-20 | QTR4 | 15/16 | 1 | 0 | 90 | 97 | 93 | 95.56% | 1 | 4 | 0 | 0 | 7 | 0 | 841047 | 35674 | 805373 | 841047 | 781435 | 0 | 0 | 0 | 781435 | 781435 | 97.03% | 1 | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6444 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-02-07 | QTR3 | 16/17 |  | 2016-10-05 | QTR2 | 16/17 | 209 | 750871.08
| 02 | E2U48 | 40849455201 | 2016-04-20 | QTR4 | 15/16 | 1 | 0 | 120 | 128 | 106 | 81.67% | 1 | 22 | 0 | 0 | 8 | 0 | 293901 | 11791 | 282110 | 293901 | 283652 | 0 | 0 | 0 | 283652 | 284750 | 100.9% | 1 | 1098 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2017-02-02 | QTR3 | 16/17 |  | 2016-10-18 | QTR2 | 16/17 | 208 | 225521.53
| 02 | E2U52 | 43075015201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 120 | 169 | 169 | 116.7% | 1 | 0 | 0 | 0 | 41 | 8 | 1141413 | 45095 | 1096318 | 1141413 | 1057536 | 0 | 0 | 0 | 1057536 | 1057536 | 96.46% | 1 | 0 | 0 | 7 | 22 | 0 | 2 | 5102 | 0 | 12 | 6 | 7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 13057 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-23 | QTR4 | 16/17 |  | 2017-04-26 | QTR4 | 16/17 | 214 | 954138.18
| 02 | E2V32 | 43743115201 | 2016-08-17 | QTR1 | 16/17 | 1 | 0 | 120 | 121 | 100 | 82.5% | 1 | 21 | 0 | 0 | 1 | 0 | 547282 | 20940 | 526342 | 547282 | 469400 | 0 | 0 | 0 | 469400 | 469400 | 89.18% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2017-06-19 | QTR4 | 16/17 |  | 2017-04-12 | QTR4 | 16/17 | 208 | 449347.96
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 16 | 23 | 14 | 3520 | 4972 | 5062 | 75% | 12 | -90 | 190 | 0 | 584 | 868 | 52749513 | 863888 | 51885624 | 62459361 | 62820578 | -92880 | 0 | -92880 | 62727697 | 61732186 | 81.25% | 13 | -995514 | 9709848 | 311 | 250 | 3 | 647 | 9206136 | 2177986 | 12 | 217 | 663757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0 | 0 | 4392 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 132621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11541 | 0 | 15 | 868 | 10038426 | 2177986
| District 02 Totals |  |  |  |  | 44 | 57 | 41 | 9077 | 11594 | 11698 | 79.55% | 35 | -104 | 265 | 0 | 1577 | 1140 | 132319983 | 1736295 | 130583691 | 141089374 | 141670169 | -220864 | 0 | -220864 | 141449303 | 139575456 | 88.64% | 39 | -1873851 | 10811388 | 845 | 603 | 11 | 689 | 9360699 | 2177986 | 46 | 358 | 1767517 | 18101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0 | 6 | 62377 | 0 | 0 | 48 | 15480 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 132621 | 0 | 0 | 29 | 11052 | 11052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31233 | 0 | 57 | 1134 | 11360310 | 2207139
| 03 | T3349 | 22041285201 | 2010-12-08 | QTR2 | 10/11 | 3 | 28 | 835 | 1802 | 1804 | 182% | 0 | -2 | 2 | 0 | 381 | 586 | 7357219 | 72479 | 7284740 | 10528722 | 10638848 | -93018 | 0 | -93018 | 10545830 | 10537771 | 144.7% | 0 | -8059 | 3171503 | 203 | 81 | 0 | 428 | 2195488 | 844067 | 0 | 120 | 436311 | 60348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 81300 | 13615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 365823 | 185379 | 97 | 0 | 126858 | 126858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 586 | 3205779 | 1230267 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-03-11 | QTR3 | 15/16 | 308 | 7320354.71 | ARRA | AMERICAN RECOVERY AND REINVEST
| 03 | T3375 | 42124315201 | 2012-02-29 | QTR3 | 11/12 | 3 | 3 | 1194 | 1402 | 1400 | 103% | 1 | 2 | 0 | 0 | 170 | 38 | 14736078 | 150000 | 14586078 | 15035632 | 14669101 | 0 | 0 | 0 | 14669101 | 14620764 | 100.2% | 1 | -48338 | 299554 | 105 | 65 | 0 | 38 | 320021 | 0 | 0 | 0 | 102024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59292 | 0 | 0 | 0 | 7231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 371313 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-30 | QTR4 | 15/16 | 308 | 18080147.32
| 03 | T3392 | 41694015201 | 2012-03-28 | QTR3 | 11/12 | 6 | 6 | 485 | 764 | 774 | 116.5% | 1 | -10 | 10 | 0 | 209 | 70 | 6759549 | 77577 | 6681973 | 7037952 | 7405140 | -32260 | 0 | -32260 | 7372880 | 7308967 | 109.4% | 1 | -63913 | 278403 | 171 | 38 | 0 | 42 | 141721 | 0 | 0 | 9 | 29158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 110627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 16690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1655 | 0 | 0 | 70 | 296541 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-08 | QTR3 | 16/17 |  | 2014-07-24 | QTR1 | 14/15 | 308 | 7836269.38
| 03 | T3398 | 22016225201 | 2013-09-25 | QTR1 | 13/14 | 1 | 4 | 310 | 940 | 940 | 238.1% | 0 | 0 | 0 | 0 | 415 | 215 | 3358717 | 50000 | 3308717 | 4155082 | 4026349 | 0 | 0 | 0 | 4026349 | 3996594 | 120.8% | 0 | -29755 | 796365 | 165 | 37 | 27 | 211 | 792014 | 726197 | 5 | 3 | 10636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 1 | -14634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 215 | 788016 | 726197 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-07 | QTR2 | 16/17 |  | 2016-08-02 | QTR1 | 16/17 | 308 | 2823245.81
| 03 | T3403 | 42692915201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 100 | 215 | 215 | 142% | 0 | 0 | 0 | 0 | 73 | 42 | 893145 | 39567 | 853578 | 944595 | 853629 | 0 | 0 | 0 | 853629 | 853629 | 100% | 1 | 0 | 51450 | 36 | 37 | 0 | 0 | 0 | 0 | 0 | 42 | 52046 | 18775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 52046 | 18775 | F223711240 | GULF BEACH CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-05-04 | QTR4 | 16/17 |  | 2016-06-11 | QTR4 | 15/16 | 308 | 829904.02
| 03 | T3418 | 42551915201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 350 | 475 | 472 | 99.14% | 1 | 3 | 0 | 0 | 125 | 0 | 2589441 | 50000 | 2539441 | 2672648 | 2648983 | 0 | 0 | 0 | 2648983 | 2635144 | 103.8% | 1 | -13838 | 83207 | 114 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-07-06 | QTR1 | 16/17 | 308 | 2582602.98
| 03 | T3427 | 42164415201 | 2013-07-31 | QTR1 | 13/14 | 4 | 2 | 475 | 888 | 888 | 112% | 1 | 0 | 0 | 0 | 369 | 44 | 11476305 | 126776 | 11349528 | 11609159 | 11286785 | -11250 | 0 | -11250 | 11275535 | 10699458 | 94.27% | 1 | -576077 | 132854 | 265 | 91 | 0 | 19 | 140137 | 0 | 0 | 15 | 65665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 12852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 44 | 228449 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-03-31 | QTR3 | 15/16 | 308 | 12800389.92
| 03 | T3433 | 42693025201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 285 | 368 | 375 | 103.5% | 1 | -7 | 7 | 0 | 80 | 3 | 4985043 | 60566 | 4924478 | 5040858 | 4902106 | -20132 | 0 | -20132 | 4881974 | 4555909 | 92.52% | 1 | -326064 | 55814 | 53 | 27 | 0 | 3 | 55814 | 15953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 64944 | 15953 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-24 | QTR2 | 16/17 |  | 2016-05-21 | QTR4 | 15/16 | 321 | 6115127.23
| 03 | T3435 | 42290715201 | 2013-05-22 | QTR4 | 12/13 | 2 | 19 | 570 | 1008 | 1008 | 142.1% | 0 | 0 | 0 | 0 | 355 | 83 | 6523192 | 66956 | 6456236 | 8090393 | 8420054 | 0 | 0 | 0 | 8420054 | 8335602 | 129.1% | 0 | -84452 | 1567201 | 162 | 36 | 21 | 57 | 608587 | 319691 | 21 | 17 | 178987 | 15099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121332 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228153 | 0 | 0 | 6 | 27967 | 17242 | 115 | 3 | 454135 | 25649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 83 | 1619160 | 381061 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-02-28 | QTR3 | 16/17 |  | 2016-05-12 | QTR4 | 15/16 | 308 | 6744574.73
| 03 | T3443 | 42693415201 | 2014-12-03 | QTR2 | 14/15 | 2 | 1 | 247 | 408 | 408 | 113.8% | 1 | 0 | 0 | 0 | 143 | 18 | 4037987 | 50000 | 3987987 | 4183812 | 4167957 | 0 | 0 | 0 | 4167957 | 3846478 | 96.45% | 1 | -321479 | 145825 | 106 | 21 | 13 | 17 | 28230 | 0 | 3 | 1 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18 | 175160 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-04-07 | QTR4 | 15/16 | 308 | 4397278.78
| 03 | T3460 | 42874715201 | 2016-03-30 | QTR3 | 15/16 | 2 | 0 | 120 | 140 | 137 | 98.33% | 1 | 3 | 0 | 0 | 19 | 1 | 1335414 | 50000 | 1285414 | 1335414 | 1301394 | 0 | 0 | 0 | 1301394 | 1295632 | 100.8% | 1 | -5762 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5544 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 |  | 2016-11-04 | QTR2 | 16/17 | 321 | 1593999.48
| 03 | T3464 | 43000315201 | 2015-03-25 | QTR3 | 14/15 | 2 | 7 | 370 | 548 | 548 | 118.9% | 1 | 0 | 0 | 0 | 154 | 24 | 5476809 | 0 | 5476809 | 5729223 | 5761356 | 0 | 0 | 0 | 5761356 | 5745026 | 104.9% | 1 | -16330 | 252414 | 71 | 37 | 21 | 24 | 101269 | 18627 | 25 | 0 | 93889 | 92391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 24 | 252414 | 111018 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2017-03-15 | QTR3 | 16/17 |  | 2017-01-17 | QTR3 | 16/17 | 308 | 4721318.79
| 03 | T3482 | 42884515201 | 2015-01-28 | QTR3 | 14/15 | 2 | 1 | 300 | 396 | 388 | 97.33% | 1 | 8 | 0 | 0 | 96 | 0 | 7416925 | 85537 | 7331389 | 7437265 | 7758460 | -880 | 0 | -880 | 7757580 | 7441692 | 101.5% | 1 | -315888 | 20339 | 66 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 27217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30580 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 313 | 8733987.91
| 03 | T3483 | 43077715201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 250 | 386 | 386 | 113.6% | 1 | 0 | 0 | 0 | 115 | 21 | 4039522 | 50000 | 3989522 | 4047995 | 4269663 | 0 | 0 | 0 | 4269663 | 4226492 | 105.9% | 1 | -43171 | 8473 | 57 | 45 | 12 | 10 | 55493 | 0 | 1 | 4 | 4180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30674 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 21 | 28999 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-05 | QTR2 | 16/17 |  | 2016-08-24 | QTR1 | 16/17 | 314 | 3857910.06
| 03 | T3491 | 43078015201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 90 | 161 | 159 | 150% | 0 | 2 | 0 | 0 | 71 | 0 | 3493487 | 50000 | 3443487 | 3493487 | 3579235 | 0 | 0 | 0 | 3579235 | 3547935 | 103% | 1 | -31300 | 0 | 15 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 1758 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | QTR3 | 16/17 |  | 2016-10-12 | QTR2 | 16/17 | 314 | 2971789.29
| 03 | T3495 | 42695615201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 90 | 226 | 225 | 98.89% | 1 | 1 | 0 | 0 | 136 | 0 | 1619321 | 50000 | 1569321 | 1619321 | 1588249 | 0 | 0 | 0 | 1588249 | 1566711 | 99.83% | 1 | -21538 | 0 | 102 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-05-18 | QTR4 | 15/16 | 321 | 1991519.93
| 03 | T3497 | 43178715201 | 2016-02-24 | QTR3 | 15/16 | 2 | 1 | 90 | 113 | 113 | 102.2% | 1 | 0 | 0 | 0 | 23 | 0 | 439154 | 18320 | 420833 | 441637 | 406769 | 0 | 0 | 0 | 406769 | 406424 | 96.58% | 1 | -345 | 2483 | 19 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2483 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-03-23 | QTR3 | 16/17 |  | 2016-08-21 | QTR1 | 16/17 | 308 | 385976.74
| 03 | T3513 | 43077815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 80 | 83 | 83 | 100% | 1 | 0 | 0 | 0 | 3 | 0 | 742276 | 35965 | 706312 | 740169 | 725008 | 0 | 0 | 0 | 725008 | 725004 | 102.6% | 1 | -4 | -2107 | 1 | 2 | 0 | 0 | -2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-01-18 | QTR3 | 16/17 |  | 2016-11-27 | QTR2 | 16/17 | 314 | 757261.77
| 03 | T3514 | 43078115201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 175 | 307 | 308 | 100.6% | 1 | -1 | 1 | 0 | 132 | 0 | 3802689 | 50000 | 3752689 | 3802689 | 3624193 | 0 | 0 | 0 | 3624193 | 3479143 | 92.71% | 1 | -145050 | 0 | 90 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 |  | 2016-07-23 | QTR1 | 16/17 | 314 | 4144189.92
| 03 | T3515 | 43090835201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 240 | 568 | 567 | 164.2% | 0 | 1 | 0 | 0 | 314 | 14 | 8076272 | 85662 | 7990610 | 8066272 | 8349102 | 0 | 0 | 0 | 8349102 | 7667982 | 95.96% | 1 | -681120 | -10000 | 119 | 54 | 1 | 14 | 68182 | 0 | 0 | 0 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 14 | 58182 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 313 | 8827284.67
| 03 | T3516 | 42874115201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 70 | 83 | 83 | 100% | 1 | 0 | 0 | 0 | 13 | 0 | 664504 | 28504 | 636000 | 664504 | 636000 | 0 | 0 | 0 | 636000 | 636000 | 100% | 1 | 0 | 0 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-01-30 | QTR3 | 16/17 |  | 2016-09-30 | QTR1 | 16/17 | 308 | 599580.35 | B0 | ACC - LUMP SUM
| 03 | T3519 | 42986115201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 45 | 49 | 40 | 80% | 1 | 9 | 0 | 0 | 4 | 0 | 79117 | 5001 | 74116 | 79117 | 68771 | 0 | 0 | 0 | 68771 | 68771 | 92.79% | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2017-04-19 | QTR4 | 16/17 |  | 2017-03-13 | QTR3 | 16/17 | 321 | 104519.39
| 03 | T3539 | 22243945201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 90 | 205 | 205 | 167.8% | 0 | 0 | 0 | 0 | 66 | 49 | 1948263 | 50000 | 1898263 | 1965454 | 2004975 | 0 | 0 | 0 | 2004975 | 2004975 | 105.6% | 1 | 0 | 17192 | 50 | 4 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 45708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 49 | 45708 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-07-28 | QTR1 | 16/17 | 308 | 1870760.28
| 03 | T3544 | 43090825201 | 2015-03-25 | QTR3 | 14/15 | 1 | 2 | 240 | 490 | 504 | 162.9% | 0 | -14 | 14 | 0 | 244 | 6 | 9957902 | 122790 | 9835112 | 10174090 | 10291533 | -52780 | 0 | -52780 | 10238753 | 9419099 | 95.77% | 1 | -819655 | 216188 | 71 | 42 | 0 | 0 | 0 | 0 | 0 | 4 | 44460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2 | 2689 | 0 | 6 | 0 | 217063 | 217063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 6 | 264212 | 217063 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-20 | QTR3 | 16/17 |  | 2016-11-01 | QTR2 | 16/17 | 313 | 12349086.79
| 03 | T3548 | 43079315201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 90 | 110 | 110 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 1961731 | 50000 | 1911731 | 1961731 | 1976693 | 0 | 0 | 0 | 1976693 | 1976488 | 103.4% | 1 | -205 | 0 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | QTR3 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 314 | 2269437.6
| 03 | T3551 | 42873915201 | 2015-03-25 | QTR3 | 14/15 | 3 | 4 | 175 | 297 | 304 | 125.1% | 0 | -7 | 7 | 0 | 118 | 4 | 2525492 | 50000 | 2475492 | 2696693 | 2810548 | -29132 | 0 | -29132 | 2781416 | 2626488 | 106.1% | 1 | -154929 | 171200 | 58 | 27 | 22 | 0 | 31909 | 0 | 11 | 4 | 152138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 4 | 201162 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-01 | QTR2 | 16/17 |  | 2016-04-10 | QTR4 | 15/16 | 321 | 3044222.49
| 03 | T3552 | 43273715201 | 2015-07-29 | QTR1 | 15/16 | 1 | 1 | 125 | 237 | 237 | 108.8% | 1 | 0 | 0 | 0 | 101 | 11 | 3670000 | 50000 | 3620000 | 3738760 | 3752339 | -5200 | 0 | -5200 | 3747139 | 3621209 | 100% | 1 | -125930 | 68760 | 66 | 35 | 0 | 7 | 27730 | 0 | 0 | 4 | 70531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 98576 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-10 | QTR2 | 16/17 |  | 2016-06-11 | QTR4 | 15/16 | 308 | 4236500
| 03 | T3556 | 43253715201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 205 | 251 | 244 | 100% | 1 | 7 | 0 | 0 | 39 | 7 | 6785910 | 71955 | 6713955 | 6785910 | 7196007 | 0 | 0 | 0 | 7196007 | 7198436 | 107.2% | 1 | 2429 | 0 | 17 | 22 | 0 | 7 | 57129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 64053 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-10 | QTR4 | 16/17 |  | 2017-01-02 | QTR3 | 16/17 | 313 | 7266475.01
| 03 | T3558 | 43274115201 | 2015-09-30 | QTR1 | 15/16 | 2 | 0 | 189 | 216 | 212 | 97.88% | 1 | 4 | 0 | 0 | 27 | 0 | 3745728 | 50000 | 3695728 | 3745728 | 3536653 | 0 | 0 | 0 | 3536653 | 3415843 | 92.43% | 1 | -120811 | 0 | 21 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 9140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9140 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-02-02 | QTR3 | 16/17 |  | 2016-09-28 | QTR1 | 16/17 | 321 | 4720445.88
| 03 | T3560 | 42461815201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 105 | 161 | 161 | 102.9% | 1 | 0 | 0 | 0 | 53 | 3 | 1870023 | 50000 | 1820023 | 1848237 | 1748528 | 0 | 0 | 0 | 1748528 | 1735931 | 95.38% | 1 | -12597 | -21786 | 41 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -21786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -21786 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-01-12 | QTR3 | 16/17 |  | 2016-09-15 | QTR1 | 16/17 | 308 | 2060779.2
| 03 | T3572 | 43014825201 | 2016-05-25 | QTR4 | 15/16 | 1 | 1 | 69 | 95 | 95 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 411660 | 19913 | 391747 | 421660 | 407116 | 0 | 0 | 0 | 407116 | 407116 | 103.9% | 1 | 0 | 10000 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 20458 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20458 | 545 | F593289030 | DOWDY PLUMBING CORPORATION | N/A | N/A | N/A | N/A | 2017-04-25 | QTR4 | 16/17 |  | 2017-02-28 | QTR3 | 16/17 | 321 | 427171.29
| 03 | T3589 | 43174315201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 120 | 126 | 77 | 59.17% | 1 | 49 | 0 | 0 | 6 | 0 | 169047 | 0 | 169047 | 169047 | 169047 | 0 | 0 | 0 | 169047 | 169047 | 100% | 1 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 321 | 199840.42 | B0 | ACC - LUMP SUM
| 03 | T3595 | 43551835201 | 2016-07-27 | QTR1 | 16/17 | 2 | 1 | 90 | 106 | 103 | 96.67% | 1 | 3 | 0 | 0 | 16 | 0 | 513855 | 6584 | 507270 | 503120 | 496536 | 0 | 0 | 0 | 496536 | 496536 | 97.88% | 1 | 0 | -10734 | 3 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10734 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-01 | QTR4 | 16/17 |  | 2017-01-18 | QTR3 | 16/17 | 314 | 447907.33 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 03 | T3606 | 43187515201 | 2016-10-26 | QTR2 | 16/17 | 2 | 1 | 180 | 197 | 138 | 67.22% | 1 | 59 | 0 | 0 | 17 | 0 | 1097017 | 52280 | 1044737 | 1097017 | 1126422 | 0 | 0 | 0 | 1126422 | 1126611 | 107.8% | 1 | 189 | 0 | 6 | 11 | 0 | 0 | 7587 | 0 | 0 | 0 | 12345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23782 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2017-06-14 | QTR4 | 16/17 |  | 2017-04-28 | QTR4 | 16/17 | 321 | 1355921.27
| 03 | T9009 | 43035625201 | 2015-06-24 | QTR4 | 14/15 | 1 | 0 | 240 | 330 | 299 | 105.4% | 1 | 31 | 0 | 0 | 90 | 0 | 1500230 | 50000 | 1450230 | 1500230 | 1507255 | 0 | 0 | 0 | 1507255 | 1507255 | 103.9% | 1 | 0 | 0 | 30 | 16 | 30 | 0 | 0 | 0 | 14 | 0 | 29504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 49973 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-08-08 | QTR1 | 16/17 | 314 | 1868902.5
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 35 | 61 | 92 | 8689 | 14151 | 14010 | 74.29% | 26 | 141 | 41 | 0 | 4223 | 1239 | 136059024 | 1876432 | 134182593 | 143363623 | 144110804 | -244652 | 0 | -244652 | 143866152 | 139902162 | 91.43% | 32 | -3963992 | 7304598 | 2339 | 919 | 147 | 877 | 4629204 | 1924535 | 94 | 224 | 1337096 | 187158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488 | 83 | 658545 | 16995 | 6 | 7 | 244465 | 217063 | 0 | 0 | -59292 | 0 | 18 | 39 | 630993 | 185379 | 97 | 6 | 154825 | 144100 | 115 | 3 | 454135 | 25649 | 0 | 0 | 0 | 0 | 0 | 0 | -1655 | 0 | 965 | 1239 | 8048311 | 2700879
| 03 | E3K73 | 42693515201 | 2014-03-13 | QTR3 | 13/14 | 2 | 1 | 200 | 344 | 344 | 109.5% | 1 | 0 | 0 | 0 | 125 | 19 | 1221881 | 50000 | 1171881 | 1231781 | 1143560 | 0 | 0 | 0 | 1143560 | 1120620 | 95.63% | 1 | -22940 | 9900 | 106 | 19 | 0 | 0 | 0 | 0 | 0 | 19 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 10560 | 6600 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2015-06-14 | QTR4 | 14/15 | 308 | 1514949.05
| 03 | E3L68 | 42874015201 | 2016-01-14 | QTR3 | 15/16 | 1 | 1 | 114 | 163 | 168 | 105.3% | 1 | -5 | 5 | 0 | 49 | 0 | 2387205 | 50000 | 2337205 | 2450930 | 2540774 | -17920 | 0 | -17920 | 2522854 | 2503625 | 107.1% | 1 | -19229 | 63725 | 35 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 63725 | 63725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 63725 | 63725 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2017-01-18 | QTR3 | 16/17 |  | 2016-09-20 | QTR1 | 16/17 | 321 | 3051775.88
| 03 | E3L90 | 42840315201 | 2013-06-28 | QTR4 | 12/13 | 1 | 3 | 534 | 975 | 975 | 139.7% | 0 | 0 | 0 | 0 | 304 | 137 | 24049000 | 150000 | 23899000 | 24338104 | 24337828 | 0 | 0 | 0 | 24337828 | 24337642 | 101.8% | 1 | -186 | 289104 | 165 | 64 | 0 | 0 | 10000 | 0 | 20 | 0 | 59678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 363800 | 298854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 137 | 438828 | 298854 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2016-08-30 | QTR1 | 16/17 |  | 2016-04-26 | QTR4 | 15/16 | 313 | 21314871.51 | A3 | ICC - DESIGN/BUILD - MINOR
| 03 | E3M17 | 40747845201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 90 | 109 | 107 | 97.78% | 1 | 2 | 0 | 0 | 19 | 0 | 149498 | 7779 | 141719 | 149498 | 139613 | 0 | 0 | 0 | 139613 | 139613 | 98.51% | 1 | 0 | 0 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455085205 | PRINCIPLE PROPERTIES INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-06-08 | QTR4 | 15/16 | 308 | 163264.04
| 03 | E3M30 | 42429125201 | 2015-02-26 | QTR3 | 14/15 | 2 | 1 | 300 | 535 | 534 | 139.7% | 0 | 1 | 0 | 0 | 115 | 120 | 4578636 | 50636 | 4528000 | 5834533 | 5832583 | 0 | 0 | 0 | 5832583 | 5832583 | 128.8% | 0 | 0 | 1255897 | 89 | 26 | 0 | 0 | 0 | 0 | 0 | 120 | 1304583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1304583 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-28 | QTR2 | 16/17 | 308 | 4578636 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| 03 | E3M55 | 42805825201 | 2014-01-31 | QTR3 | 13/14 | 1 | 1 | 265 | 629 | 628 | 198.1% | 0 | 1 | 0 | 0 | 211 | 153 | 1540571 | 50000 | 1490571 | 1579254 | 1571464 | 0 | 0 | 0 | 1571464 | 1571464 | 105.4% | 1 | 0 | 38683 | 83 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 |  | 2016-01-19 | QTR3 | 15/16 | 308 | 1529160 | A3 | ICC - DESIGN/BUILD - MINOR
| 03 | E3M95 | 41694315201 | 2015-07-09 | QTR1 | 15/16 | 1 | 3 | 140 | 240 | 239 | 118.6% | 1 | 1 | 0 | 0 | 73 | 27 | 2738862 | 50000 | 2688862 | 3014082 | 3595051 | 0 | 0 | 0 | 3595051 | 3484491 | 129.6% | 0 | -110560 | 275220 | 36 | 37 | 0 | 0 | 0 | 0 | 0 | 5 | 288220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 12155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13000 | 0 | 0 | 27 | 287375 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-19 | QTR1 | 16/17 |  | 2016-06-27 | QTR4 | 15/16 | 314 | 3204695.35
| 03 | E3N17 | 43392715201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 65 | 65 | 50 | 73.85% | 1 | 15 | 0 | 0 | 2 | -2 | 1734968 | 50000 | 1684968 | 1417537 | 1360898 | 0 | 0 | 0 | 1360898 | 1360898 | 80.77% | 1 | 0 | -317430 | 2 | 0 | 0 | -2 | -313024 | 0 | 0 | 0 | 4578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | -308196 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 |  | 2016-05-23 | QTR4 | 15/16 | 321 | 1346663.5
| 03 | E3N18 | 43391815201 | 2015-10-08 | QTR2 | 15/16 | 1 | 1 | 65 | 117 | 116 | 130.8% | 0 | 1 | 0 | 0 | 31 | 21 | 1245237 | 49942 | 1195296 | 1323870 | 1408799 | 0 | 0 | 0 | 1408799 | 1408799 | 117.9% | 0 | 0 | 78633 | 30 | 1 | 0 | 21 | 108680 | 16182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 108680 | 16182 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-01 | QTR4 | 15/16 | 308 | 1048525.47
| 03 | E3N24 | 42884815201 | 2016-03-10 | QTR3 | 15/16 | 1 | 1 | 130 | 153 | 152 | 99.23% | 1 | 1 | 0 | 0 | 23 | 0 | 3543344 | 50000 | 3493344 | 3600105 | 3788222 | 0 | 0 | 0 | 3788222 | 3802308 | 108.8% | 1 | 14086 | 56761 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 61861 | 56761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61861 | 56761 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2017-01-04 | QTR3 | 16/17 |  | 2016-11-02 | QTR2 | 16/17 | 321 | 3817847.54
| 03 | E3N27 | 41627215201 | 2015-03-25 | QTR3 | 14/15 | 2 | 2 | 305 | 427 | 427 | 116.4% | 1 | 0 | 0 | 0 | 72 | 50 | 2233345 | 43949 | 2189396 | 2293381 | 2249432 | 0 | 0 | 0 | 2249432 | 2223244 | 101.5% | 1 | -26188 | 60036 | 41 | 31 | 0 | 0 | 0 | 0 | 0 | 50 | 60036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 60036 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 321 | 2172218.95 | A3:LBDB:A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
| 03 | E3N39 | 43078815201 | 2015-05-14 | QTR4 | 14/15 | 2 | 2 | 185 | 318 | 294 | 90.81% | 1 | 24 | 0 | 0 | 133 | 0 | 3111936 | 50000 | 3061936 | 3033818 | 2963684 | -11504 | 0 | -11504 | 2952180 | 2882199 | 94.13% | 1 | -69981 | -78118 | 85 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 18424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -96542 | 0 | 7 | 0 | -78118 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-20 | QTR4 | 15/16 | 314 | 3291622.83
| 03 | E3N42 | 21791185201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 75 | 124 | 107 | 77.33% | 1 | 17 | 0 | 0 | 49 | 0 | 762045 | 50000 | 712045 | 762045 | 712000 | 0 | 0 | 0 | 712000 | 712000 | 99.99% | 1 | 0 | 0 | 36 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 |  | 2016-09-09 | QTR1 | 16/17 | 314 | 1488724.75
| 03 | E3N48 | 43514815201 | 2016-02-11 | QTR3 | 15/16 | 1 | 1 | 75 | 124 | 124 | 100% | 1 | 0 | 0 | 0 | 49 | 0 | 398651 | 12737 | 385914 | 407027 | 394699 | 0 | 0 | 0 | 394699 | 394699 | 102.3% | 1 | 0 | 8376 | 44 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14166 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2017-03-06 | QTR3 | 16/17 |  | 2016-10-07 | QTR2 | 16/17 | 308 | 275247.5
| 03 | E3N73 | 43078715201 | 2015-05-14 | QTR4 | 14/15 | 1 | 2 | 245 | 350 | 350 | 103.3% | 1 | 0 | 0 | 0 | 102 | 3 | 4943758 | 50000 | 4893758 | 4974205 | 5018776 | -2400 | 0 | -2400 | 5016376 | 4741701 | 96.89% | 1 | -274675 | 30447 | 76 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 40031 | 29279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 3 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8991 | 0 | 5 | 3 | 34041 | 29279 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-08-22 | QTR1 | 16/17 | 314 | 4773076.33
| 03 | E3N74 | 42696915201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 125 | 164 | 164 | 100% | 1 | 0 | 0 | 0 | 39 | 0 | 2813937 | 50000 | 2763937 | 2813937 | 2913809 | 0 | 0 | 0 | 2913809 | 2837766 | 102.7% | 1 | -76042 | 0 | 28 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 308 | 3196208.79
| 03 | E3N76 | 41557535201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 180 | 207 | 132 | 58.33% | 1 | 75 | 0 | 0 | 27 | 0 | 1819446 | 50000 | 1769446 | 1819446 | 1750296 | 0 | 0 | 0 | 1750296 | 1750297 | 98.92% | 1 | 1 | 0 | 22 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-08-28 | QTR1 | 16/17 | 308 | 1571362.8
| 03 | E3N80 | 42577825201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 60 | 79 | 87 | 116.7% | 1 | -8 | 8 | 0 | 19 | 0 | 246955 | 8741 | 238214 | 246955 | 248745 | -7664 | 0 | -7664 | 241081 | 241081 | 101.2% | 1 | 0 | 0 | 10 | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | F208328161 | AN-KAR CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 308 | 183110.5
| 03 | E3O14 | 41040925201 | 2015-09-24 | QTR1 | 15/16 | 2 | 2 | 180 | 214 | 205 | 100% | 1 | 9 | 0 | 0 | 27 | 7 | 1815481 | 50000 | 1765481 | 1830051 | 1851635 | 0 | 0 | 0 | 1851635 | 1847209 | 104.6% | 1 | -4426 | 14570 | 20 | 5 | 0 | 0 | 4627 | 0 | 0 | 4 | 46652 | 9517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 13292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 64570 | 9517 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-11-16 | QTR2 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 321 | 1670231.68
| 03 | E3O47 | 43253815201 | 2015-10-15 | QTR2 | 15/16 | 1 | 0 | 100 | 128 | 128 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 2030029 | 50000 | 1980029 | 2030029 | 2131829 | 0 | 0 | 0 | 2131829 | 2045055 | 103.3% | 1 | -86775 | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 |  | 2016-07-12 | QTR1 | 16/17 | 321 | 2649534.01
| 03 | E3O53 | 43254815201 | 2015-09-10 | QTR1 | 15/16 | 1 | 0 | 125 | 173 | 173 | 100% | 1 | 0 | 0 | 0 | 48 | 0 | 2754000 | 50000 | 2704000 | 2754000 | 2779810 | 0 | 0 | 0 | 2779810 | 2686704 | 99.36% | 1 | -93106 | 0 | 44 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-24 | QTR2 | 16/17 |  | 2016-06-24 | QTR4 | 15/16 | 314 | 3103650
| 03 | E3O62 | 43079215201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 90 | 131 | 129 | 116.7% | 1 | 2 | 0 | 0 | 24 | 17 | 1298500 | 50000 | 1248500 | 1382401 | 1347119 | 0 | 0 | 0 | 1347119 | 1319720 | 105.7% | 1 | -27399 | 83901 | 17 | 7 | 0 | 17 | 83901 | 15601 | 0 | 0 | 3826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 87727 | 15601 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-08 | QTR1 | 16/17 |  | 2016-07-11 | QTR1 | 16/17 | 321 | 1564334.7 | B0 | ACC - LUMP SUM
| 03 | E3O64 | 40946235201 | 2016-09-08 | QTR1 | 16/17 | 1 | 0 | 28 | 33 | 33 | 100% | 1 | 0 | 0 | 0 | 5 | 0 | 76737 | 4830 | 71907 | 76737 | 79842 | 0 | 0 | 0 | 79842 | 79842 | 111% | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2017-04-17 | QTR4 | 16/17 |  | 2017-02-26 | QTR3 | 16/17 | 321 | 102432.1
| 03 | E3P32 | 42460825201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 40 | 51 | 48 | 92.5% | 1 | 3 | 0 | 0 | 11 | 0 | 69197 | 6233 | 62964 | 69197 | 67195 | 0 | 0 | 0 | 67195 | 67195 | 106.7% | 1 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-01 | QTR1 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 321 | 143399.73
| 03 | E3P60 | 43255315201 | 2016-08-11 | QTR1 | 16/17 | 1 | 0 | 45 | 48 | 43 | 88.89% | 1 | 5 | 0 | 0 | 3 | 0 | 966283 | 42737 | 923546 | 966283 | 955206 | -1500 | 0 | -1500 | 953706 | 953706 | 103.3% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-19 | QTR2 | 16/17 |  | 2016-11-14 | QTR2 | 16/17 | 314 | 939110.13
| 03 | E3P65 | 22049555201 | 2016-05-19 | QTR4 | 15/16 | 1 | 2 | 230 | 263 | 226 | 83.91% | 1 | 37 | 0 | 0 | 33 | 0 | 3075201 | 50000 | 3025201 | 3228421 | 3425155 | 0 | 0 | 0 | 3425155 | 3429981 | 113.4% | 0 | 4826 | 153221 | 16 | 17 | 0 | 0 | 880 | 0 | 0 | 0 | 41531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196882 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2017-04-19 | QTR4 | 16/17 |  | 2017-02-24 | QTR3 | 16/17 | 321 | 3871135
| 03 | E3P73 | 22266815201 | 2016-06-09 | QTR4 | 15/16 | 1 | 1 | 120 | 164 | 162 | 112.5% | 1 | 2 | 0 | 0 | 27 | 17 | 989058 | 36057 | 953001 | 1035205 | 988093 | 0 | 0 | 0 | 988093 | 988093 | 103.7% | 1 | 0 | 46147 | 17 | 10 | 0 | 0 | 46147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 47492 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-06-13 | QTR4 | 16/17 |  | 2017-05-08 | QTR4 | 16/17 | 321 | 777198.58
| 03 | E3P85 | 43627415201 | 2016-04-14 | QTR4 | 15/16 | 1 | 0 | 35 | 44 | 43 | 97.14% | 1 | 1 | 0 | 0 | 9 | 0 | 218815 | 9015 | 209800 | 218815 | 209764 | 0 | 0 | 0 | 209764 | 209764 | 99.98% | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-06 | QTR2 | 16/17 |  | 2016-08-20 | QTR1 | 16/17 | 308 | 189940
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 28 | 33 | 26 | 4146 | 6372 | 6188 | 85.71% | 24 | 184 | 13 | 0 | 1657 | 569 | 72812576 | 1222656 | 71589921 | 74881647 | 75805881 | -40988 | 0 | -40988 | 75764893 | 74972299 | 82.14% | 23 | -792594 | 2069073 | 1080 | 377 | 0 | 36 | -58789 | 31783 | 22 | 198 | 1993805 | 159282 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 123 | 308 | 661633 | 305454 | 0 | 3 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -118533 | 0 | 200 | 569 | 2486716 | 496519
| District 03 Totals |  |  |  |  | 63 | 94 | 118 | 12835 | 20523 | 20198 | 79.37% | 50 | 325 | 54 | 0 | 5880 | 1808 | 208871600 | 3099088 | 205772514 | 218245270 | 219916685 | -285640 | 0 | -285640 | 219631045 | 214874461 | 87.3% | 55 | -4756586 | 9373671 | 3419 | 1296 | 147 | 913 | 4570415 | 1956318 | 116 | 422 | 3330901 | 346440 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 611 | 391 | 1320178 | 322449 | 6 | 10 | 247715 | 217063 | 0 | 0 | -59292 | 0 | 18 | 63 | 646093 | 185379 | 97 | 6 | 154825 | 144100 | 170 | 3 | 454135 | 25649 | 0 | 0 | 0 | 0 | 0 | 0 | -120188 | 0 | 1165 | 1808 | 10535027 | 3197398
| 04 | T4341 | 23073015201 | 2013-02-06 | QTR3 | 12/13 | 2 | 8 | 674 | 896 | 896 | 111% | 1 | 0 | 0 | 0 | 191 | 31 | 6592014 | 73358 | 6518656 | 6833204 | 6617553 | 0 | 0 | 0 | 6617553 | 6330385 | 97.11% | 1 | -287168 | 241190 | 105 | 43 | 0 | 31 | 138206 | 0 | 4 | 0 | 108342 | 50933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 31 | 314541 | 50933 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2016-07-06 | QTR1 | 16/17 |  | 2016-04-11 | QTR4 | 15/16 | 412 | 7354583.81
| 04 | T4356 | 42286615201 | 2013-06-19 | QTR4 | 12/13 | 2 | 7 | 810 | 1040 | 1038 | 102% | 1 | 2 | 0 | 0 | 212 | 18 | 9484806 | 99537 | 9385269 | 10082799 | 10383603 | 0 | 0 | 0 | 10383603 | 10314411 | 109.9% | 1 | -69192 | 597992 | 169 | 43 | 0 | 18 | 291301 | 0 | 0 | 0 | 134692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252549 | 97110 | 0 | 0 | 7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 686144 | 97110 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2017-05-18 | QTR4 | 16/17 |  | 2016-09-07 | QTR1 | 16/17 | 412 | 10825487.49
| 04 | T4367 | 23072415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 7 | 353 | 546 | 546 | 126.6% | 0 | 0 | 0 | 0 | 166 | 27 | 3396284 | 50000 | 3346284 | 4218679 | 4018129 | 0 | 0 | 0 | 4018129 | 3882269 | 116% | 0 | -135861 | 822395 | 88 | 11 | 0 | 0 | 111602 | 0 | 0 | 27 | 341937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23868 | 0 | 0 | 0 | 12844 | 12844 | 0 | 0 | 0 | 0 | 0 | 0 | 10820 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 363650 | 363650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 27 | 864722 | 376495 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-31 | QTR3 | 16/17 |  | 2016-08-19 | QTR1 | 16/17 | 412 | 3663891.57
| 04 | T4376 | 42701215201 | 2015-07-29 | QTR1 | 15/16 | 1 | 3 | 336 | 397 | 396 | 105.4% | 1 | 1 | 0 | 0 | 61 | 0 | 4137540 | 50000 | 4087540 | 4285354 | 4224921 | 0 | 0 | 0 | 4224921 | 4063258 | 99.41% | 1 | -161663 | 147813 | 28 | 14 | 8 | 0 | 2200 | 0 | 11 | 0 | 176739 | 6433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 195285 | 6433 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-03 | QTR4 | 16/17 |  | 2016-12-22 | QTR2 | 16/17 | 412 | 4993224.98
| 04 | T4389 | 23097825201 | 2014-04-30 | QTR4 | 13/14 | 1 | 2 | 750 | 801 | 631 | 77.33% | 1 | 170 | 0 | 0 | 51 | 0 | 15715809 | 150000 | 15565809 | 15753499 | 15520925 | 0 | 630700 | 630700 | 16151625 | 14963445 | 96.13% | 1 | -1188180 | 37690 | 29 | 22 | 0 | 0 | 48793 | 0 | 0 | 0 | 38749 | 2893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66399 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158063 | 2893 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2016-09-12 | QTR1 | 16/17 |  | 2016-05-02 | QTR4 | 15/16 | 408 | 15839218.13 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4396 | 42873215201 | 2015-07-29 | QTR1 | 15/16 | 2 | 1 | 233 | 348 | 348 | 118.9% | 1 | 0 | 0 | 0 | 87 | 28 | 3226208 | 50000 | 3176208 | 3268117 | 3297315 | 0 | 0 | 0 | 3297315 | 3205408 | 100.9% | 1 | -91907 | 41909 | 54 | 17 | 0 | 7 | 51755 | 0 | 0 | 21 | 30301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 28 | 82056 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-30 | QTR4 | 16/17 |  | 2017-01-06 | QTR3 | 16/17 | 412 | 3538926.72
| 04 | T4402 | 42973715201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 540 | 577 | 542 | 93.52% | 1 | 35 | 0 | 0 | 37 | 0 | 2824000 | 50000 | 2774000 | 2824000 | 2773850 | 0 | 0 | 0 | 2773850 | 2779467 | 100.2% | 1 | 5617 | 0 | 15 | 22 | 0 | 0 | 8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8687 | 0 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 |  | 2016-04-27 | QTR4 | 15/16 | 408 | 3519184.32 | B0 | ACC - LUMP SUM
| 04 | T4406 | 42872615201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 267 | 355 | 355 | 106.7% | 1 | 0 | 0 | 0 | 88 | 0 | 3869297 | 50000 | 3819297 | 3899697 | 3754820 | 0 | 0 | 0 | 3754820 | 3632165 | 95.1% | 1 | -122655 | 30400 | 56 | 14 | 0 | 0 | 16792 | 0 | 18 | 0 | 39603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 77392 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-01-24 | QTR3 | 16/17 |  | 2016-06-28 | QTR4 | 15/16 | 412 | 3716758.39
| 04 | T4411 | 43472615201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 245 | 261 | 254 | 97.14% | 1 | 7 | 0 | 0 | 16 | 0 | 1298981 | 50000 | 1248981 | 1298981 | 1226359 | 0 | 0 | 0 | 1226359 | 1217254 | 97.46% | 1 | -9105 | 0 | 12 | 4 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31566 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-11-01 | QTR2 | 16/17 |  | 2016-09-22 | QTR1 | 16/17 | 412 | 1277354.98
| 04 | T4415 | 43472315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 198 | 219 | 219 | 101.5% | 1 | 0 | 0 | 0 | 21 | 0 | 1247191 | 50000 | 1197191 | 1247191 | 1236940 | 0 | 0 | 0 | 1236940 | 1236940 | 103.3% | 1 | 0 | 0 | 16 | 2 | 0 | 0 | 4774 | 0 | 0 | 0 | 9270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14044 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-08-24 | QTR1 | 16/17 | 409 | 1184118.51
| 04 | T4416 | 43171715201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 238 | 268 | 261 | 97.48% | 1 | 7 | 0 | 0 | 30 | 0 | 1444863 | 50000 | 1394863 | 1444863 | 1398240 | 0 | 0 | 0 | 1398240 | 1398240 | 100.2% | 1 | 0 | 0 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 412 | 1613353.82
| 04 | T4417 | 43400715201 | 2015-05-20 | QTR4 | 14/15 | 1 | 1 | 254 | 270 | 261 | 96.46% | 1 | 9 | 0 | 0 | 16 | 0 | 590398 | 35018 | 555379 | 600523 | 561695 | 0 | 0 | 0 | 561695 | 561695 | 101.1% | 1 | 0 | 10125 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-11-15 | QTR2 | 16/17 |  | 2016-09-27 | QTR1 | 16/17 | 409 | 743747.84
| 04 | T4420 | 43059515201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 294 | 393 | 392 | 106.5% | 1 | 1 | 0 | 0 | 79 | 20 | 1707658 | 50000 | 1657658 | 1707658 | 1691828 | 0 | 0 | 0 | 1691828 | 1691828 | 102.1% | 1 | 0 | 0 | 53 | 26 | 0 | 10 | 6101 | 0 | 0 | 9 | 22334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40453 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-03-07 | QTR3 | 16/17 |  | 2016-11-10 | QTR2 | 16/17 | 412 | 1786379.26
| 04 | T4421 | 42802415201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 234 | 318 | 318 | 109.4% | 1 | 0 | 0 | 0 | 62 | 22 | 655175 | 33966 | 621209 | 655175 | 640299 | 0 | 0 | 0 | 640299 | 640223 | 103.1% | 1 | -76 | 0 | 44 | 18 | 0 | 14 | 756 | 0 | 0 | 8 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 32782 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-02-14 | QTR3 | 16/17 |  | 2017-01-09 | QTR3 | 16/17 | 412 | 662183.52
| 04 | T4426 | 43060815201 | 2016-02-24 | QTR3 | 15/16 | 2 | 0 | 102 | 161 | 161 | 117.6% | 1 | 0 | 0 | 0 | 59 | 0 | 1295575 | 50000 | 1245575 | 1295575 | 1275925 | 0 | 0 | 0 | 1275925 | 1275925 | 102.4% | 1 | 0 | 0 | 35 | 6 | 18 | 0 | 15716 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18401 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-19 | QTR2 | 16/17 | 409 | 1142628.19 | B0 | ACC - LUMP SUM
| 04 | T4427 | 43490215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 187 | 207 | 193 | 92.51% | 1 | 14 | 0 | 0 | 20 | 0 | 800000 | 46765 | 753235 | 800000 | 773213 | 0 | 0 | 0 | 773213 | 773213 | 102.7% | 1 | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8431 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-05-02 | QTR4 | 16/17 |  | 2017-04-06 | QTR4 | 16/17 | 412 | 918089.86
| 04 | T4430 | 43509615201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 125 | 137 | 134 | 97.6% | 1 | 3 | 0 | 0 | 12 | 0 | 369071 | 19947 | 349124 | 369071 | 326639 | 0 | 0 | 0 | 326639 | 326642 | 93.56% | 1 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2017-05-10 | QTR4 | 16/17 |  | 2017-04-10 | QTR4 | 16/17 | 409 | 392822.92
| 04 | T4431 | 43509315201 | 2016-03-30 | QTR3 | 15/16 | 1 | 1 | 90 | 119 | 119 | 111.1% | 1 | 0 | 0 | 0 | 29 | 0 | 249966 | 10331 | 239635 | 262302 | 239047 | 0 | 0 | 0 | 239047 | 239047 | 99.75% | 1 | 0 | 12336 | 17 | 2 | 0 | 0 | 0 | 0 | 10 | 0 | 12845 | 11486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 13545 | 11486 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2017-01-24 | QTR3 | 16/17 |  | 2016-11-16 | QTR2 | 16/17 | 412 | 216195.57
| 04 | T4432 | 43509115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 103 | 116 | 116 | 100% | 1 | 0 | 0 | 0 | 13 | 0 | 462595 | 19884 | 442711 | 462595 | 438863 | 0 | 0 | 0 | 438863 | 438863 | 99.13% | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 820 | 0 | 0 | 0 | 2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2887 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-03-27 | QTR3 | 16/17 |  | 2017-02-16 | QTR3 | 16/17 | 412 | 406505.19
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 19 | 25 | 31 | 6033 | 7429 | 7180 | 94.74% | 18 | 249 | 0 | 0 | 1250 | 146 | 59367431 | 988806 | 58378624 | 61309283 | 60400164 | 0 | 630700 | 630700 | 61030864 | 58970678 | 94.74% | 18 | -2060187 | 1941850 | 761 | 294 | 26 | 80 | 728249 | 0 | 43 | 65 | 939367 | 71745 | 0 | 0 | 2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 475037 | 97110 | 16 | 0 | 49344 | 12844 | 0 | 0 | 0 | 0 | 0 | 0 | 10820 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 368487 | 363650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 146 | 2573373 | 545350
| 04 | E4N30 | 23071725201 | 2013-02-06 | QTR3 | 12/13 | 9 | 7 | 832 | 1192 | 1192 | 126.7% | 0 | 0 | 0 | 0 | 175 | 185 | 7998765 | 72329 | 7926436 | 10990699 | 10941188 | 0 | 0 | 0 | 10941188 | 10875104 | 137.2% | 0 | -66084 | 2991934 | 66 | 72 | 37 | 176 | 628756 | 26127 | 0 | 41 | 2394421 | 428763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93484 | 93484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32 | -58956 | 0 | 37 | 185 | 3020452 | 548374 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2017-01-04 | QTR3 | 16/17 |  | 2016-08-11 | QTR1 | 16/17 | 412 | 7310236.62 | A3:Y:A:Y::Y::Y::Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
| 04 | E4P11 | 43330115201 | 2014-05-07 | QTR4 | 13/14 | 5 | 3 | 646 | 774 | 773 | 109.3% | 1 | 1 | 0 | 0 | 67 | 61 | 7982486 | 103877 | 7878609 | 8060089 | 7966495 | 0 | 0 | 0 | 7966495 | 7966495 | 101.1% | 1 | 0 | 77603 | 27 | 40 | 0 | 23 | 15186 | 0 | 0 | 0 | 627 | 627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 79421 | 9562 | 0 | 14 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 100531 | 10189 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-01-18 | QTR3 | 16/17 |  | 2016-09-14 | QTR1 | 16/17 | 412 | 10491582.3 | A3:Y:A:Y::Y::Y::Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
| 04 | E4P15 | 43270715201 | 2014-04-30 | QTR4 | 13/14 | 1 | 7 | 550 | 706 | 778 | 119.8% | 1 | -72 | 72 | 0 | 120 | 36 | 6920878 | 73114 | 6847764 | 6931376 | 6809928 | -232272 | 0 | -232272 | 6577656 | 6290830 | 91.87% | 1 | -286826 | 10498 | 83 | 36 | 1 | 5 | 67800 | 0 | 0 | 8 | -59002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 18759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 57507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -98214 | 0 | 1 | 36 | -13151 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-06-08 | QTR4 | 16/17 |  | 2016-08-30 | QTR1 | 16/17 | 408 | 6902573.81 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4P38 | 43270415201 | 2014-05-28 | QTR4 | 13/14 | 2 | 4 | 688 | 944 | 944 | 98.4% | 1 | 0 | 0 | 0 | 272 | -16 | 21920100 | 150000 | 21770100 | 21827650 | 21748676 | 0 | 0 | 0 | 21748676 | 19468244 | 89.43% | 1 | -2280432 | -92450 | 218 | 49 | 0 | 0 | 10743 | 0 | 0 | 16 | 32162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45 | -92450 | 0 | 5 | -16 | -49545 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-06-13 | QTR4 | 16/17 |  | 2017-03-06 | QTR3 | 16/17 | 409 | 20025810 | B8:Y:B:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4P79 | 42593515201 | 2014-04-23 | QTR4 | 13/14 | 2 | 2 | 313 | 441 | 441 | 119.5% | 1 | 0 | 0 | 0 | 67 | 61 | 7765532 | 74876 | 7690656 | 7903357 | 8161146 | 0 | 321600 | 321600 | 8482746 | 8149687 | 106% | 1 | -333059 | 137826 | 53 | 14 | 0 | 20 | 14059 | 0 | 0 | 30 | 137826 | 0 | 0 | 11 | 3260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 155145 | 0 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 |  | 2016-03-20 | QTR3 | 15/16 | 412 | 7456671.91 | B3:B5 | ACC - LANE RENTAL:ACC - INCENTIVE/DISINCENTIVE
| 04 | E4P94 | 43368845201 | 2014-05-02 | QTR4 | 13/14 | 1 | 8 | 506 | 648 | 514 | 93.87% | 1 | 134 | 0 | 0 | 40 | 102 | 11791416 | 121557 | 11669859 | 13321296 | 13475252 | 0 | 470000 | 470000 | 13945252 | 13368481 | 114.6% | 0 | -576771 | 1529880 | 25 | 14 | 0 | 102 | 23355 | 0 | 0 | 0 | 1681280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74534 | 0 | 0 | 102 | 1637852 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 |  | 2015-12-23 | QTR2 | 15/16 | 412 | 12152859.28 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
| 04 | E4P95 | 42131415201 | 2014-07-11 | QTR1 | 14/15 | 1 | 10 | 350 | 753 | 753 | 200% | 0 | 0 | 0 | 0 | 53 | 350 | 1812600 | 50000 | 1762600 | 2451083 | 2583183 | 0 | 0 | 0 | 2583183 | 2583183 | 146.6% | 0 | 0 | 638483 | 28 | 25 | 0 | 0 | 14920 | 0 | 0 | 0 | 271205 | 255634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 380967 | 379225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 667719 | 634859 | F262618462 | COBALT CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2017-06-16 | QTR4 | 16/17 |  | 2016-12-08 | QTR2 | 16/17 | 408 | 1882510.53
| 04 | E4P98 | 42605315201 | 2015-02-06 | QTR3 | 14/15 | 2 | 2 | 238 | 283 | 280 | 104.6% | 1 | 3 | 0 | 0 | 45 | 0 | 1670723 | 50000 | 1620723 | 1694884 | 1701995 | 0 | 0 | 0 | 1701995 | 1694894 | 104.6% | 1 | -7101 | 24162 | 17 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 9687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43444 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 |  | 2016-02-26 | QTR3 | 15/16 | 409 | 1844040.91
| 04 | E4Q22 | 42990515201 | 2014-12-19 | QTR2 | 14/15 | 1 | 4 | 224 | 358 | 356 | 119.2% | 1 | 2 | 0 | 0 | 134 | 0 | 5750000 | 65756 | 5684244 | 6072503 | 6142459 | 0 | 0 | 0 | 6142459 | 6141649 | 108% | 1 | -810 | 322503 | 74 | 15 | 0 | 0 | 13481 | 0 | 45 | 0 | 372908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 386389 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-09-30 | QTR1 | 16/17 | 412 | 6522411.23 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4Q70 | 43056615201 | 2015-04-03 | QTR4 | 14/15 | 1 | 0 | 86 | 99 | 99 | 100% | 1 | 0 | 0 | 0 | 13 | 0 | 594927 | 36890 | 558037 | 594927 | 563713 | 0 | 0 | 0 | 563713 | 563713 | 101% | 1 | 0 | 0 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-07-08 | QTR1 | 16/17 | 412 | 789528.37
| 04 | E4Q82 | 43056715201 | 2015-03-06 | QTR3 | 14/15 | 1 | 2 | 430 | 446 | 410 | 85.12% | 1 | 36 | 0 | 0 | 46 | -30 | 2188629 | 50000 | 2138629 | 2163534 | 2089683 | 0 | 0 | 0 | 2089683 | 2076611 | 97.1% | 1 | -13073 | -25094 | 28 | 16 | 0 | 0 | 10000 | 0 | 0 | 0 | 13423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | -29883 | 0 | 0 | -30 | -5141 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-02-10 | QTR3 | 16/17 |  | 2016-10-15 | QTR2 | 16/17 | 409 | 2260658.05
| 04 | E4R08 | 43115215201 | 2015-05-20 | QTR4 | 14/15 | 1 | 1 | 315 | 350 | 313 | 88.25% | 1 | 37 | 0 | 0 | 35 | 0 | 1435007 | 50000 | 1385007 | 1449407 | 1163642 | 0 | 0 | 0 | 1163642 | 1155244 | 83.41% | 1 | -8398 | 14400 | 23 | 12 | 0 | 0 | 3143 | 0 | 0 | 0 | 29620 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33038 | 0 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 408 | 1565107.46
| 04 | E4R33 | 43059015201 | 2016-03-04 | QTR3 | 15/16 | 1 | 1 | 238 | 246 | 164 | 65.55% | 1 | 82 | 0 | 0 | 8 | 0 | 1637760 | 50000 | 1587760 | 1638489 | 1537659 | 0 | 0 | 0 | 1537659 | 1540807 | 97.04% | 1 | 3148 | 729 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17565 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-10 | QTR3 | 16/17 |  | 2016-11-04 | QTR2 | 16/17 | 412 | 1735050.08
| 04 | E4R44 | 43061715201 | 2016-04-01 | QTR4 | 15/16 | 1 | 2 | 160 | 210 | 205 | 107.5% | 1 | 5 | 0 | 0 | 33 | 17 | 1182414 | 35234 | 1147180 | 1176116 | 1146902 | 0 | 0 | 0 | 1146902 | 1148631 | 100.1% | 1 | 1729 | -6298 | 17 | 16 | 0 | 0 | 0 | 0 | 0 | 17 | -3563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | -3563 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-06-19 | QTR4 | 16/17 |  | 2017-02-21 | QTR3 | 16/17 | 408 | 670122.53
| 04 | E4R47 | 42840015201 | 2015-12-04 | QTR2 | 15/16 | 1 | 0 | 67 | 179 | 179 | 183.6% | 0 | 0 | 0 | 0 | 112 | 0 | 281874 | 13403 | 268471 | 281874 | 265427 | 0 | 0 | 0 | 265427 | 265427 | 98.87% | 1 | 0 | 0 | 29 | 27 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-01-31 | QTR3 | 16/17 |  | 2016-12-06 | QTR2 | 16/17 | 409 | 248191.49
| 04 | E4R52 | 43399815201 | 2015-12-04 | QTR2 | 15/16 | 2 | 1 | 157 | 168 | 163 | 96.82% | 1 | 5 | 0 | 0 | 11 | 0 | 447523 | 30245 | 417278 | 483523 | 445843 | 0 | 0 | 0 | 445843 | 445875 | 106.9% | 1 | 32 | 36000 | 9 | 2 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 0 | F462088820 | INTERSTATE CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-01-24 | QTR3 | 16/17 |  | 2016-08-12 | QTR1 | 16/17 | 412 | 628945.46
| 04 | E4R65 | 43538615201 | 2016-01-08 | QTR3 | 15/16 | 2 | 0 | 65 | 92 | 91 | 106.2% | 1 | 1 | 0 | 0 | 23 | 4 | 593859 | 24145 | 569714 | 593859 | 535917 | 0 | 0 | 0 | 535917 | 535917 | 94.07% | 1 | 0 | 0 | 18 | 4 | 0 | 4 | 8796 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9546 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 |  | 2016-06-29 | QTR4 | 15/16 | 409 | 495318.22
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 17 | 34 | 54 | 5865 | 7889 | 7655 | 82.35% | 14 | 234 | 72 | 0 | 1254 | 770 | 81974493 | 1051426 | 80923067 | 87634666 | 87279108 | -232272 | 791600 | 559328 | 87838436 | 84270792 | 82.35% | 14 | -3567645 | 5660176 | 731 | 361 | 38 | 330 | 846239 | 26127 | 101 | 112 | 4882073 | 685024 | 0 | 11 | 3535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 5 | 387 | 501895 | 388787 | 0 | 16 | 42210 | 0 | 0 | 0 | -40553 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 151618 | 93484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -107 | -354037 | 0 | 144 | 770 | 6036281 | 1193422
| District 04 Totals |  |  |  |  | 36 | 59 | 85 | 11898 | 15318 | 14835 | 88.89% | 32 | 483 | 72 | 0 | 2504 | 916 | 141341924 | 2040232 | 139301691 | 148943949 | 147679272 | -232272 | 1422300 | 1190028 | 148869300 | 143241470 | 88.89% | 32 | -5627832 | 7602026 | 1492 | 655 | 64 | 410 | 1574488 | 26127 | 144 | 177 | 5821440 | 756769 | 0 | 11 | 5602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 5 | 388 | 976932 | 485897 | 16 | 16 | 91554 | 12844 | 0 | 0 | -40553 | 0 | 0 | 0 | 10820 | 0 | 0 | 21 | 151618 | 93484 | 106 | 0 | 368487 | 363650 | 0 | 0 | 0 | 0 | 0 | -107 | -354037 | 0 | 335 | 916 | 8609654 | 1738772
| 05 | T5415 | 40735535201 | 2012-05-23 | QTR4 | 11/12 | 6 | 19 | 1100 | 1340 | 1359 | 106% | 1 | -19 | 19 | 0 | 211 | 29 | 32798973 | 150000 | 32648973 | 35176946 | 35231745 | -161575 | 0 | -161575 | 35070170 | 34680971 | 106.2% | 1 | -389199 | 2796919 | 109 | 84 | 0 | 25 | 751698 | 18086 | 0 | 8 | 2210379 | 1011571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57075 | 0 | 0 | 33 | 2905712 | 1029658 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2016-11-18 | QTR2 | 16/17 |  | 2016-06-20 | QTR4 | 15/16 | 513 | 37106689.63
| 05 | T5486 | 23871915201 | 2014-02-26 | QTR3 | 13/14 | 1 | 8 | 490 | 699 | 671 | 112.7% | 1 | 28 | 0 | 0 | 125 | 84 | 12324444 | 150000 | 12174444 | 12887259 | 13204280 | 0 | 0 | 0 | 13204280 | 11961836 | 98.25% | 1 | -1242443 | 562815 | 92 | 27 | 0 | 0 | 66841 | 7015 | 0 | 75 | 365963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20597 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 265295 | 0 | 0 | 0 | 1516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 679017 | 10770 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-02-06 | QTR3 | 16/17 |  | 2016-04-25 | QTR4 | 15/16 | 512 | 17116714.63 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 05 | T5496 | 43106615201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 460 | 684 | 678 | 97.61% | 1 | 6 | 0 | 0 | 224 | 0 | 4198661 | 57000 | 4141661 | 4198661 | 4290920 | 0 | 0 | 0 | 4290920 | 4280333 | 103.3% | 1 | -10587 | 0 | 199 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-10-12 | QTR2 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 514 | 5833243.5
| 05 | T5497 | 43113915201 | 2014-06-18 | QTR4 | 13/14 | 4 | 2 | 350 | 479 | 448 | 99.71% | 1 | 31 | 0 | 0 | 99 | 30 | 5577400 | 50000 | 5527400 | 5630674 | 5316503 | 0 | 0 | 0 | 5316503 | 5110931 | 92.47% | 1 | -205572 | 53274 | 72 | 27 | 0 | 0 | 16219 | 0 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 62720 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-13 | QTR1 | 16/17 |  | 2016-04-13 | QTR4 | 15/16 | 514 | 5261131.52 | B0:B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 05 | T5504 | 43326915201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 340 | 414 | 410 | 98.82% | 1 | 4 | 0 | 0 | 74 | 0 | 2791824 | 50000 | 2741824 | 2791824 | 2764770 | 0 | 0 | 0 | 2764770 | 2763716 | 100.8% | 1 | -1054 | 0 | 53 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 |  | 2016-09-09 | QTR1 | 16/17 | 514 | 3681477
| 05 | T5507 | 42908315201 | 2014-10-29 | QTR2 | 14/15 | 2 | 3 | 352 | 458 | 457 | 105.7% | 1 | 1 | 0 | 0 | 85 | 21 | 13950000 | 132000 | 13818000 | 14304220 | 14416417 | 0 | 0 | 0 | 14416417 | 13245104 | 95.85% | 1 | -1171314 | 354220 | 70 | 15 | 0 | 0 | 36422 | 0 | 0 | 0 | 46490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 308750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 391661 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 512 | 13411584.34
| 05 | T5515 | 43066815201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 210 | 284 | 284 | 115.2% | 1 | 0 | 0 | 0 | 44 | 30 | 1884019 | 50000 | 1834019 | 1929335 | 1919435 | 0 | 0 | 0 | 1919435 | 1870656 | 102% | 1 | -48780 | 45316 | 30 | 12 | 0 | 24 | 59005 | 0 | 0 | 6 | 21372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 80377 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2016-05-05 | QTR4 | 15/16 | 514 | 1716624.23 | B0 | ACC - LUMP SUM
| 05 | T5519 | 43066615201 | 2015-07-29 | QTR1 | 15/16 | 2 | 0 | 280 | 323 | 260 | 77.5% | 1 | 63 | 0 | 0 | 43 | 0 | 2698908 | 50000 | 2648908 | 2698908 | 2560594 | 0 | 0 | 0 | 2560594 | 2513289 | 94.88% | 1 | -47305 | 0 | 32 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 3735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11651 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 514 | 2488176
| 05 | T5524 | 43065215201 | 2015-03-25 | QTR3 | 14/15 | 1 | 3 | 270 | 391 | 390 | 132.6% | 0 | 1 | 0 | 0 | 34 | 87 | 4938000 | 50000 | 4888000 | 5043475 | 4946856 | 0 | 0 | 0 | 4946856 | 4688330 | 95.92% | 1 | -258527 | 105475 | 16 | 16 | 0 | 0 | 3176 | 0 | 0 | 36 | 84688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 17106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 104970 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 515 | 4676396.93
| 05 | T5528 | 43066915201 | 2015-05-27 | QTR4 | 14/15 | 1 | 1 | 200 | 245 | 224 | 90.5% | 1 | 21 | 0 | 0 | 45 | 0 | 2181000 | 50000 | 2131000 | 2446253 | 2396253 | 0 | 0 | 0 | 2396253 | 2380075 | 111.7% | 0 | -16178 | 265253 | 19 | 24 | 0 | 0 | 145670 | 0 | 0 | 0 | 119583 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265253 | 508 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-07-01 | QTR1 | 16/17 |  | 2016-04-06 | QTR4 | 15/16 | 507 | 1883279.22
| 05 | T5531 | 42821325202 | 2015-06-17 | QTR4 | 14/15 | 1 | 2 | 400 | 442 | 400 | 89.5% | 1 | 42 | 0 | 0 | 42 | 0 | 3499000 | 50000 | 3449000 | 3559000 | 3541158 | 0 | 0 | 0 | 3541158 | 3541158 | 102.7% | 1 | 0 | 60000 | 26 | 16 | 0 | 0 | 5923 | 0 | 0 | 0 | 58348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74271 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-10-19 | QTR2 | 16/17 | 512 | 4392675.67
| 05 | T5536 | 43067715201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 216 | 247 | 233 | 93.52% | 1 | 14 | 0 | 0 | 31 | 0 | 2584884 | 50000 | 2534884 | 2614884 | 2636650 | 0 | 0 | 0 | 2636650 | 2540033 | 100.2% | 1 | -96617 | 30000 | 12 | 19 | 0 | 0 | 15490 | 0 | 0 | 0 | 58864 | 13921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74355 | 13921 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 |  | 2016-07-22 | QTR1 | 16/17 | 513 | 2795913.94
| 05 | T5537 | 43244215201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 110 | 154 | 147 | 111.8% | 1 | 7 | 0 | 0 | 24 | 20 | 1272760 | 42000 | 1230760 | 1272760 | 1267646 | 0 | 0 | 0 | 1267646 | 1267646 | 103% | 1 | 0 | 0 | 9 | 15 | 0 | 0 | 615 | 0 | 0 | 20 | 34326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 34941 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 |  | 2016-06-10 | QTR4 | 15/16 | 513 | 919590 | B0 | ACC - LUMP SUM
| 05 | T5540 | 43544615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 310 | 321 | 320 | 99.68% | 1 | 1 | 0 | 0 | 11 | 0 | 2108960 | 50000 | 2058960 | 2108960 | 2062184 | 0 | 0 | 0 | 2062184 | 2062184 | 100.2% | 1 | 0 | 0 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-12-13 | QTR2 | 16/17 |  | 2016-09-29 | QTR1 | 16/17 | 509 | 2665356.75
| 05 | T5541 | 43241215201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 200 | 241 | 240 | 102% | 1 | 1 | 0 | 0 | 41 | 0 | 894822 | 38000 | 856822 | 894822 | 858557 | 0 | 0 | 0 | 858557 | 860505 | 100.4% | 1 | 1948 | 0 | 27 | 9 | 0 | 0 | 3728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3728 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-03-13 | QTR3 | 16/17 |  | 2016-12-15 | QTR2 | 16/17 | 514 | 813974.1
| 05 | T5542 | 43245515201 | 2015-10-28 | QTR2 | 15/16 | 3 | 5 | 260 | 435 | 434 | 110.8% | 1 | 1 | 0 | 0 | 146 | 29 | 6389000 | 77000 | 6312000 | 6541385 | 6525238 | -8241 | 0 | -8241 | 6516997 | 6292502 | 99.69% | 1 | -224496 | 152385 | 107 | 39 | 0 | 7 | 160572 | 0 | 0 | 22 | 25360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 204141 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-06-29 | QTR4 | 16/17 |  | 2017-05-05 | QTR4 | 16/17 | 513 | 7834175.55
| 05 | T5543 | 43366515201 | 2015-10-28 | QTR2 | 15/16 | 1 | 1 | 120 | 150 | 150 | 113.3% | 1 | 0 | 0 | 0 | 14 | 16 | 408828 | 16725 | 392103 | 408828 | 402408 | 0 | 0 | 0 | 402408 | 402408 | 102.6% | 1 | 0 | 0 | 12 | 2 | 0 | 0 | 3550 | 0 | 0 | 16 | 7612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 11162 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2017-01-20 | QTR3 | 16/17 |  | 2016-07-13 | QTR1 | 16/17 | 512 | 373627.25
| 05 | T5545 | 43065615201 | 2015-10-28 | QTR2 | 15/16 | 1 | 2 | 220 | 237 | 233 | 98.18% | 1 | 4 | 0 | 0 | 17 | 0 | 1793084 | 50000 | 1743084 | 1837115 | 1743748 | 0 | 0 | 0 | 1743748 | 1711189 | 98.17% | 1 | -32559 | 44031 | 13 | 4 | 0 | 0 | 15032 | 0 | 0 | 0 | 26653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71534 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-12-16 | QTR2 | 16/17 |  | 2016-09-27 | QTR1 | 16/17 | 512 | 1806322.05
| 05 | T5550 | 43245315201 | 2016-02-24 | QTR3 | 15/16 | 2 | 2 | 220 | 259 | 232 | 88.18% | 1 | 27 | 0 | 0 | 39 | 0 | 4609815 | 50000 | 4559815 | 4482913 | 4406263 | 0 | 0 | 0 | 4406263 | 4397650 | 96.44% | 1 | -8613 | -126902 | 19 | 19 | 0 | 0 | -129277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129277 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-02-16 | QTR3 | 16/17 |  | 2017-01-04 | QTR3 | 16/17 | 509 | 4516602
| 05 | T5560 | 43244115201 | 2016-04-27 | QTR4 | 15/16 | 3 | 3 | 200 | 246 | 236 | 98.5% | 1 | 10 | 0 | 0 | 42 | 4 | 2552654 | 50000 | 2502654 | 2632050 | 2628965 | 0 | 0 | 0 | 2628965 | 2624607 | 104.9% | 1 | -4358 | 79396 | 19 | 20 | 0 | 0 | 19854 | 0 | 0 | 4 | 79217 | 2968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 99072 | 2968 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-05 | QTR4 | 16/17 |  | 2017-03-10 | QTR3 | 16/17 | 513 | 2570277.16
| 05 | T5561 | 43474115201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 125 | 188 | 188 | 101.6% | 1 | 0 | 0 | 0 | 63 | 0 | 2191000 | 50000 | 2141000 | 2191000 | 2106346 | 0 | 0 | 0 | 2106346 | 2116636 | 98.86% | 1 | 10290 | 0 | 44 | 17 | 0 | 0 | 7460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7460 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-03-16 | QTR3 | 16/17 |  | 2017-01-30 | QTR3 | 16/17 | 514 | 2517053
| 05 | T5577 | 43544615202 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 240 | 262 | 262 | 100% | 1 | 0 | 0 | 0 | 22 | 0 | 2212434 | 50000 | 2162434 | 2222354 | 2157683 | 0 | 0 | 0 | 2157683 | 2157683 | 99.78% | 1 | 0 | 9920 | 9 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 9920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9920 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-03-27 | QTR3 | 16/17 |  | 2017-02-02 | QTR3 | 16/17 | 509 | 2655160.5
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 22 | 38 | 55 | 6673 | 8499 | 8256 | 95.45% | 21 | 243 | 19 | 0 | 1476 | 350 | 113860470 | 1362725 | 112497745 | 117873626 | 117384619 | -169816 | 0 | -169816 | 117214803 | 113469442 | 95.45% | 21 | -3745364 | 4432102 | 993 | 447 | 0 | 56 | 1181978 | 25101 | 0 | 187 | 3157810 | 1028968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 342772 | 3755 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19171 | 0 | 0 | 9 | 275295 | 0 | 0 | 0 | 1516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57075 | 0 | 0 | 354 | 4962668 | 1057825
| 05 | E5W67 | 43198915201 | 2014-10-07 | QTR2 | 14/15 | 1 | 2 | 300 | 340 | 393 | 126.7% | 0 | -53 | 53 | 0 | 13 | 27 | 2340785 | 50000 | 2290785 | 2247902 | 2197902 | -92326 | 0 | -92326 | 2105576 | 2104471 | 91.87% | 1 | -1105 | -92883 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | -92883 | 0 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-02-10 | QTR3 | 15/16 | 509 | 2486510
| 05 | E5W83 | 43528215201 | 2015-04-07 | QTR4 | 14/15 | 1 | 0 | 240 | 265 | 264 | 99.58% | 1 | 1 | 0 | 0 | 25 | 0 | 2750721 | 50000 | 2700721 | 2750721 | 2676098 | 0 | 0 | 0 | 2676098 | 2676025 | 99.09% | 1 | -73 | 0 | 7 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-07-20 | QTR1 | 16/17 |  | 2016-05-06 | QTR4 | 15/16 | 513 | 2985731
| 05 | E5W86 | 43488315201 | 2015-06-04 | QTR4 | 14/15 | 1 | 1 | 120 | 131 | 131 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 584110 | 29000 | 555110 | 585291 | 580591 | 0 | 0 | 0 | 580591 | 580591 | 104.6% | 1 | 0 | 1181 | 1 | 10 | 0 | 0 | 478 | 0 | 0 | 0 | 4195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4673 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-11-28 | QTR2 | 16/17 |  | 2016-07-22 | QTR1 | 16/17 | 513 | 623548.95
| 05 | E5Y02 | 43705815201 | 2015-09-01 | QTR1 | 15/16 | 1 | 0 | 130 | 134 | 107 | 79.23% | 1 | 27 | 0 | 0 | 4 | 0 | 783941 | 39000 | 744941 | 783941 | 744941 | 0 | 0 | 0 | 744941 | 744941 | 100% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-08-09 | QTR1 | 16/17 |  | 2016-07-25 | QTR1 | 16/17 | 515 | 821518.11
| 05 | E5Y03 | 43116415201 | 2016-02-02 | QTR3 | 15/16 | 1 | 0 | 65 | 88 | 83 | 123.1% | 0 | 5 | 0 | 0 | 23 | 0 | 63940 | 5000 | 58940 | 63940 | 58289 | 0 | 0 | 0 | 58289 | 58289 | 98.9% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2016-12-23 | QTR2 | 16/17 |  | 2016-10-20 | QTR2 | 16/17 | 514 | 123170
| 05 | E5Y04 | 43705715201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 210 | 220 | 220 | 100% | 1 | 0 | 0 | 0 | 10 | 0 | 679709 | 43000 | 636709 | 679709 | 640622 | 0 | 0 | 0 | 640622 | 640622 | 100.6% | 1 | 0 | 0 | 9 | 1 | 0 | 0 | 4403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4403 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-12-30 | QTR2 | 16/17 |  | 2016-10-13 | QTR2 | 16/17 | 514 | 911255.5
| 05 | E5Y05 | 43465915201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 100 | 110 | 109 | 104% | 1 | 1 | 0 | 0 | 10 | 0 | 448115 | 19000 | 429115 | 448115 | 434061 | 0 | 0 | 0 | 434061 | 434061 | 101.2% | 1 | 0 | 0 | 3 | 2 | 0 | 0 | 4946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4946 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-10-04 | QTR2 | 16/17 |  | 2016-07-14 | QTR1 | 16/17 | 514 | 409595.51
| 05 | E5Y07 | 43693615201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 300 | 389 | 380 | 98% | 1 | 9 | 0 | 0 | 89 | 0 | 2962958 | 50000 | 2912958 | 2962958 | 2820404 | 0 | 0 | 0 | 2820404 | 2820404 | 96.82% | 1 | 0 | 0 | 64 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-05-26 | QTR4 | 16/17 |  | 2017-03-23 | QTR3 | 16/17 | 514 | 2456435
| 05 | E5Y18 | 23800235225 | 2016-02-02 | QTR3 | 15/16 | 1 | 1 | 160 | 165 | 148 | 89.38% | 1 | 17 | 0 | 0 | 5 | 0 | 788000 | 33000 | 755000 | 805272 | 758781 | 0 | 0 | 0 | 758781 | 759356 | 100.6% | 1 | 575 | 17272 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 17272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17272 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 |  | 2016-09-26 | QTR1 | 16/17 | 513 | 717565.65
| 05 | E5Y28 | 43750125201 | 2016-05-03 | QTR4 | 15/16 | 2 | 0 | 90 | 98 | 97 | 98.89% | 1 | 1 | 0 | 0 | 8 | 0 | 236798 | 15000 | 221798 | 236798 | 194703 | 0 | 0 | 0 | 194703 | 194703 | 87.78% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591625608 | SANTA CRUZ CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 |  | 2016-11-14 | QTR2 | 16/17 | 515 | 335841
| 05 | E5Y38 | 43781715201 | 2016-06-07 | QTR4 | 15/16 | 2 | 1 | 86 | 134 | 134 | 108.1% | 1 | 0 | 0 | 0 | 40 | 8 | 293265 | 19000 | 274265 | 294576 | 286101 | 0 | 0 | 0 | 286101 | 284790 | 103.8% | 1 | -1311 | 1311 | 24 | 17 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-18 | QTR4 | 16/17 |  | 2017-01-28 | QTR3 | 16/17 | 513 | 406745
| 05 | E5Y41 | 43781615201 | 2016-06-07 | QTR4 | 15/16 | 1 | 0 | 120 | 138 | 93 | 62.5% | 1 | 45 | 0 | 0 | 18 | 0 | 151151 | 10000 | 141151 | 151151 | 134927 | 0 | 0 | 0 | 134927 | 134927 | 95.59% | 1 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-04-14 | QTR4 | 16/17 |  | 2017-03-09 | QTR3 | 16/17 | 513 | 237416.1
| 05 | E5Y49 | 43939215201 | 2016-05-25 | QTR4 | 15/16 | 2 | 3 | 250 | 277 | 239 | 90% | 1 | 38 | 0 | 0 | 15 | 12 | 1927830 | 50000 | 1877830 | 2083244 | 2054804 | 0 | 100000 | 100000 | 2154804 | 2041547 | 108.7% | 1 | -113257 | 155414 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 12 | 161305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 161305 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 |  | 2017-02-20 | QTR3 | 16/17 | 513 | 1351307 | A3:B5:LBDB | ICC - DESIGN/BUILD - MINOR:ACC - INCENTIVE/DISINCENTIVE:LOW BID DESIGN BUILD
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 13 | 16 | 8 | 2171 | 2489 | 2398 | 84.62% | 11 | 91 | 53 | 0 | 271 | 47 | 14011323 | 412000 | 13599323 | 14093618 | 13582224 | -92326 | 100000 | 7674 | 13589898 | 13474727 | 100% | 13 | -115171 | 82295 | 128 | 115 | 0 | 0 | 9827 | 0 | 0 | 47 | 182772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 99716 | 0
| District 05 Totals |  |  |  |  | 35 | 54 | 63 | 8844 | 10988 | 10654 | 91.43% | 32 | 334 | 72 | 0 | 1747 | 397 | 127871793 | 1774725 | 126097068 | 131967244 | 130966843 | -262142 | 100000 | -162142 | 130804701 | 126944169 | 97.14% | 34 | -3860535 | 4514397 | 1121 | 562 | 0 | 56 | 1191805 | 25101 | 0 | 234 | 3340582 | 1028968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 249889 | 3755 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19171 | 0 | 0 | 9 | 275295 | 0 | 0 | 0 | 1516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -57075 | 0 | 0 | 401 | 5062384 | 1057825
| 06 | T6127 | 25118515201 | 2011-09-07 | QTR1 | 11/12 | 3 | 18 | 1250 | 1524 | 1524 | 100% | 1 | 0 | 0 | 0 | 274 | 0 | 58542945 | 268019 | 58274926 | 59378958 | 60313959 | 0 | 0 | 0 | 60313959 | 59818042 | 102.6% | 1 | -495917 | 836013 | 200 | 74 | 0 | 0 | 1344690 | 17957 | 0 | 0 | 533489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -761248 | 0 | 0 | 0 | 1068519 | 17957 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 |  | 2016-08-12 | QTR1 | 16/17 | 606 | 67023598.5
| 06 | T6290 | 24991115201 | 2012-12-05 | QTR2 | 12/13 | 5 | 17 | 845 | 1067 | 1067 | 104.7% | 1 | 0 | 0 | 0 | 188 | 34 | 31967610 | 396250 | 31571360 | 38766907 | 37791470 | 0 | 2100000 | 2100000 | 39891470 | 37602287 | 119.1% | 0 | -2289183 | 6799297 | 121 | 61 | 4 | 0 | 1715422 | 4227 | 0 | 0 | 515011 | 5252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 4900006 | 368720 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3982 | 3982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 34 | 7134421 | 382182 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2017-02-21 | QTR3 | 16/17 |  | 2016-03-02 | QTR3 | 15/16 | 606 | 27939576.37 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6320 | 42914015201 | 2014-06-18 | QTR4 | 13/14 | 3 | 3 | 450 | 503 | 387 | 74.22% | 1 | 116 | 0 | 0 | 53 | 0 | 14295524 | 150000 | 14145524 | 14692214 | 13690377 | 0 | 245000 | 245000 | 13935377 | 13056864 | 92.3% | 1 | -878513 | 396690 | 43 | 10 | 0 | 0 | 18351 | 0 | 0 | 0 | 421570 | 152744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447735 | 152744 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-06-14 | QTR4 | 15/16 | 606 | 15289319.55 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6325 | 25055425201 | 2012-10-31 | QTR2 | 12/13 | 1 | 3 | 700 | 903 | 870 | 96.43% | 1 | 33 | 0 | 0 | 197 | 6 | 11430054 | 123500 | 11306554 | 11749528 | 11929942 | 0 | 0 | 0 | 11929942 | 11924070 | 105.5% | 1 | -5871 | 319473 | 154 | 41 | 2 | 0 | 266319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 63468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 370763 | 0 | F410827177 | JOHNSON BROS. CORPORATION | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 606 | 12087502
| 06 | T6328 | 42745215201 | 2014-04-30 | QTR4 | 13/14 | 3 | 4 | 600 | 663 | 663 | 100% | 1 | 0 | 0 | 0 | 63 | 0 | 8067382 | 91797 | 7975585 | 8176995 | 8097390 | 0 | 300000 | 300000 | 8397390 | 7946905 | 99.64% | 1 | -450485 | 109613 | 40 | 23 | 0 | 0 | 99579 | 0 | 0 | 0 | 7266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141770 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-03 | QTR3 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 606 | 8580765.85 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6365 | 43274315201 | 2015-08-26 | QTR1 | 15/16 | 2 | 3 | 180 | 208 | 206 | 98.89% | 1 | 2 | 0 | 0 | 28 | 0 | 3849469 | 50000 | 3799469 | 3927103 | 3942847 | 0 | 0 | 0 | 3942847 | 3837692 | 101% | 1 | -105154 | 77634 | 24 | 4 | 0 | 0 | 1963 | 0 | 0 | 0 | 73400 | 3297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4426 | 0 | 0 | 0 | 20491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91428 | 3297 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-08-02 | QTR1 | 16/17 | 606 | 4708187.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6371 | 42913415201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 180 | 212 | 212 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 1483369 | 50000 | 1433369 | 1483369 | 1429074 | 0 | 0 | 0 | 1429074 | 1425704 | 99.47% | 1 | -3370 | 0 | 29 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 35508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42642 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-11-10 | QTR2 | 16/17 |  | 2016-08-09 | QTR1 | 16/17 | 606 | 1435507.6
| 06 | T6372 | 43345115201 | 2016-01-27 | QTR3 | 15/16 | 4 | 3 | 140 | 182 | 182 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 1089885 | 50425 | 1039460 | 1078983 | 1060465 | 0 | 0 | 0 | 1060465 | 1060465 | 102% | 1 | 0 | -10902 | 35 | 7 | 0 | 0 | -13402 | 0 | 0 | 0 | 16958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18662 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-11 | QTR4 | 16/17 |  | 2016-11-28 | QTR2 | 16/17 | 606 | 1129000.75 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 06 | T6373 | 43080915201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 230 | 328 | 326 | 112.6% | 1 | 2 | 0 | 0 | 98 | 0 | 2376742 | 50130 | 2326612 | 2426742 | 2460615 | 0 | 0 | 0 | 2460615 | 2384892 | 102.5% | 1 | -75723 | 50000 | 56 | 11 | 31 | 0 | 16266 | 0 | 0 | 0 | 14872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 71617 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-05-12 | QTR4 | 15/16 | 606 | 2292101.6
| 06 | T6374 | 43118015201 | 2015-03-25 | QTR3 | 14/15 | 6 | 4 | 210 | 310 | 308 | 118.6% | 1 | 2 | 0 | 0 | 100 | 0 | 5144045 | 52640 | 5091405 | 5317082 | 5198829 | 0 | 0 | 0 | 5198829 | 5112224 | 100.4% | 1 | -86605 | 173037 | 47 | 12 | 29 | 0 | 30730 | 0 | 0 | 0 | 7365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 148657 | 104434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 186752 | 104434 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-02 | QTR2 | 16/17 |  | 2016-07-03 | QTR1 | 16/17 | 606 | 4599362.55
| 06 | T6376 | 43081715201 | 2015-02-25 | QTR3 | 14/15 | 2 | 4 | 435 | 468 | 375 | 78.62% | 1 | 93 | 0 | 0 | 33 | 0 | 6621887 | 69750 | 6552137 | 6805679 | 6261293 | 0 | 470000 | 470000 | 6731293 | 6082074 | 92.83% | 1 | -649219 | 183793 | 21 | 12 | 0 | 0 | 71716 | 0 | 0 | 0 | 115147 | 9450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186863 | 9450 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-27 | QTR1 | 16/17 |  | 2016-05-08 | QTR4 | 15/16 | 606 | 6429680.27 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6379 | 42934515201 | 2016-03-30 | QTR3 | 15/16 | 2 | 2 | 220 | 234 | 192 | 80.91% | 1 | 42 | 0 | 0 | 14 | 0 | 2622038 | 55125 | 2566913 | 2613142 | 2527516 | 0 | 150000 | 150000 | 2677516 | 2524953 | 98.37% | 1 | -152563 | -8896 | 8 | 6 | 0 | 0 | -31036 | 0 | 0 | 0 | 22140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1060 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-03-02 | QTR3 | 16/17 |  | 2016-12-23 | QTR2 | 16/17 | 606 | 3493513.45 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6381 | 43349015201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 140 | 184 | 184 | 100% | 1 | 0 | 0 | 0 | 44 | 0 | 762732 | 41312 | 721420 | 762732 | 718865 | 0 | 0 | 0 | 718865 | 721234 | 99.97% | 1 | 2369 | 0 | 25 | 19 | 0 | 0 | 9499 | 0 | 0 | 0 | 5079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14578 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2017-04-03 | QTR4 | 16/17 |  | 2017-02-06 | QTR3 | 16/17 | 606 | 854446.65
| 06 | T6384 | 43350815201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 439934 | 26680 | 413254 | 439934 | 417205 | 0 | 0 | 0 | 417205 | 417205 | 101% | 1 | 0 | 0 | 16 | 1 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 |  | 2016-06-23 | QTR4 | 15/16 | 606 | 559680 | B0 | ACC - LUMP SUM
| 06 | T6386 | 43349315201 | 2016-01-27 | QTR3 | 15/16 | 2 | 0 | 180 | 206 | 206 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 648209 | 34334 | 613875 | 648209 | 638650 | 0 | 0 | 0 | 638650 | 605828 | 98.69% | 1 | -32822 | 0 | 12 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-29 | QTR4 | 16/17 |  | 2017-02-10 | QTR3 | 16/17 | 606 | 711332.45
| 06 | T6389 | 43481015201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 80 | 96 | 93 | 96.25% | 1 | 3 | 0 | 0 | 16 | 0 | 147742 | 8768 | 138974 | 147742 | 141841 | 0 | 0 | 0 | 141841 | 141841 | 102.1% | 1 | 0 | 0 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | F273954210 | PE-SERVICES L.L.C. | N/A | N/A | N/A | N/A | 2016-11-02 | QTR2 | 16/17 |  | 2016-10-05 | QTR2 | 16/17 | 606 | 180124 | B0 | ACC - LUMP SUM
| 06 | T6393 | 24961585201 | 2015-03-25 | QTR3 | 14/15 | 1 | 0 | 580 | 628 | 550 | 86.55% | 1 | 78 | 0 | 0 | 48 | 0 | 17726000 | 150000 | 17576000 | 17726000 | 17439683 | 0 | 670000 | 670000 | 18109683 | 16969633 | 96.55% | 1 | -1140050 | 0 | 24 | 24 | 0 | 0 | 4522 | 0 | 0 | 0 | 33334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47647 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-10 | QTR3 | 16/17 |  | 2016-12-15 | QTR2 | 16/17 | 606 | 20932157.05 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6394 | 24961575201 | 2015-04-29 | QTR4 | 14/15 | 2 | 1 | 435 | 469 | 395 | 82.99% | 1 | 74 | 0 | 0 | 34 | 0 | 18918175 | 150000 | 18768175 | 18918175 | 18379697 | 0 | 740000 | 740000 | 19119697 | 17983880 | 95.82% | 1 | -1135817 | 0 | 21 | 13 | 0 | 0 | 2262 | 0 | 0 | 0 | 34785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52061 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-11-08 | QTR2 | 16/17 |  | 2016-08-05 | QTR1 | 16/17 | 606 | 23196102.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6395 | 24961555201 | 2015-12-03 | QTR2 | 15/16 | 1 | 2 | 350 | 367 | 311 | 84% | 1 | 56 | 0 | 0 | 17 | 0 | 18870198 | 150000 | 18720198 | 19070198 | 19250284 | 0 | 1120000 | 1120000 | 20370284 | 19024190 | 101.6% | 1 | -1346095 | 200000 | 10 | 7 | 0 | 0 | 205933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251546 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-06-26 | QTR4 | 16/17 |  | 2017-03-01 | QTR3 | 16/17 | 606 | 22322899.05 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6396 | 24961525201 | 2015-05-20 | QTR4 | 14/15 | 4 | 4 | 585 | 641 | 558 | 85.81% | 1 | 83 | 0 | 0 | 56 | 0 | 26227745 | 150000 | 26077745 | 26488959 | 26988041 | 0 | 1130000 | 1130000 | 28118041 | 26175164 | 100.4% | 1 | -1942877 | 261214 | 33 | 23 | 0 | 0 | 217919 | 0 | 0 | 0 | 91807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337759 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-05-08 | QTR4 | 16/17 |  | 2017-02-17 | QTR3 | 16/17 | 606 | 34221350.42 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6402 | 43631315201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 80 | 107 | 107 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 249950 | 16163 | 233787 | 249950 | 228758 | 0 | 0 | 0 | 228758 | 228758 | 97.85% | 1 | 0 | 0 | 26 | 1 | 0 | 0 | 4223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4223 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-07 | QTR3 | 16/17 |  | 2016-11-10 | QTR2 | 16/17 | 606 | 332195.65
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 21 | 50 | 69 | 7990 | 9437 | 8853 | 100% | 21 | 584 | 0 | 0 | 1407 | 40 | 231481635 | 2134893 | 229346742 | 240868601 | 238906801 | 0 | 6925000 | 6925000 | 245831801 | 235043905 | 95.24% | 20 | -10787895 | 9386966 | 960 | 367 | 66 | 0 | 3970956 | 22184 | 0 | 0 | 1930598 | 170743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 34 | 5213232 | 473154 | 2 | 0 | 48525 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 73250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3982 | 3982 | 0 | 0 | 0 | 0 | 0 | 0 | -761248 | 0 | 80 | 40 | 10479295 | 670064
| 06 | E6H77 | 41806525201 | 2013-07-16 | QTR1 | 13/14 | 4 | 8 | 381 | 718 | 718 | 150.7% | 0 | 0 | 0 | 0 | 144 | 193 | 6865432 | 95551 | 6769881 | 8047242 | 8106870 | 0 | 525000 | 525000 | 8631870 | 8012338 | 118.4% | 0 | -619532 | 1181810 | 121 | 23 | 0 | 193 | 589219 | 0 | 0 | 0 | 643866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 1240647 | 0 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2016-11-21 | QTR2 | 16/17 |  | 2016-02-25 | QTR3 | 15/16 | 606 | 9650622.75 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 06 | E6I74 | 43119315201 | 2014-11-20 | QTR2 | 14/15 | 1 | 1 | 330 | 764 | 764 | 117.9% | 1 | 0 | 0 | 0 | 434 | 0 | 3722164 | 50000 | 3672164 | 3772164 | 4008665 | 0 | 0 | 0 | 4008665 | 4008622 | 109.2% | 1 | -43 | 50000 | 333 | 42 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 49781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 49781 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2017-06-05 | QTR4 | 16/17 |  | 2017-03-17 | QTR3 | 16/17 | 606 | 3636115.25
| 06 | E6I84 | 42560065201 | 2015-11-19 | QTR2 | 15/16 | 2 | 1 | 300 | 325 | 280 | 85% | 1 | 45 | 0 | 0 | 25 | 0 | 4769021 | 50000 | 4719021 | 4787530 | 4658702 | 0 | 100000 | 100000 | 4758702 | 4637845 | 98.28% | 1 | -120857 | 18508 | 11 | 14 | 0 | 0 | 697 | 0 | 0 | 0 | 23025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23721 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-23 | QTR3 | 16/17 |  | 2017-01-02 | QTR3 | 16/17 | 606 | 4440861.9 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6I89 | 43117815201 | 2014-10-30 | QTR2 | 14/15 | 2 | 1 | 220 | 378 | 378 | 119.1% | 1 | 0 | 0 | 0 | 158 | 0 | 2097039 | 50575 | 2046464 | 2147039 | 2148203 | 0 | 0 | 0 | 2148203 | 2008021 | 98.12% | 1 | -140182 | 50000 | 100 | 16 | 42 | 0 | 57755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 63544 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2016-10-05 | QTR2 | 16/17 |  | 2016-05-29 | QTR4 | 15/16 | 606 | 2334024.25
| 06 | E6I91 | 42918715201 | 2015-06-11 | QTR4 | 14/15 | 2 | 0 | 150 | 180 | 179 | 105.3% | 1 | 1 | 0 | 0 | 30 | 0 | 1483128 | 50420 | 1432708 | 1483128 | 1441455 | 0 | 0 | 0 | 1441455 | 1430102 | 99.82% | 1 | -11353 | 0 | 14 | 7 | 0 | 0 | 2145 | 0 | 0 | 0 | 772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 2917 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 |  | 2016-09-23 | QTR1 | 16/17 | 606 | 1376235.85
| 06 | E6I96 | 25023475201 | 2015-04-30 | QTR4 | 14/15 | 2 | 0 | 270 | 332 | 327 | 98.15% | 1 | 5 | 0 | 0 | 62 | 0 | 2344175 | 50730 | 2293445 | 2344175 | 2268222 | 0 | 0 | 0 | 2268222 | 2254238 | 98.29% | 1 | -13984 | 0 | 51 | 11 | 0 | 0 | 7412 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9512 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2017-03-14 | QTR3 | 16/17 |  | 2016-08-12 | QTR1 | 16/17 | 606 | 2475261.25
| 06 | E6I98 | 43493065201 | 2016-03-31 | QTR3 | 15/16 | 1 | 1 | 90 | 106 | 106 | 100% | 1 | 0 | 0 | 0 | 16 | 0 | 969000 | 50000 | 919000 | 903732 | 873748 | 0 | 0 | 0 | 873748 | 873360 | 95.03% | 1 | -388 | -65268 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65268 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-10-25 | QTR2 | 16/17 |  | 2016-10-02 | QTR2 | 16/17 | 606 | 1134223.3 | B0 | ACC - LUMP SUM
| 06 | E6J31 | 41247385201 | 2015-10-29 | QTR2 | 15/16 | 2 | 1 | 140 | 170 | 170 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 928836 | 41965 | 886871 | 853946 | 790776 | 0 | 0 | 0 | 790776 | 790197 | 89.1% | 1 | -578 | -74891 | 27 | 3 | 0 | 0 | -67505 | 0 | 0 | 0 | 10856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -52862 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-01-12 | QTR3 | 16/17 |  | 2016-10-11 | QTR2 | 16/17 | 606 | 879055.55
| 06 | E6J90 | 41774089201 | 2015-09-23 | QTR1 | 15/16 | 3 | 0 | 380 | 423 | 423 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 3017017 | 50000 | 2967017 | 3017017 | 2967017 | 0 | 0 | 0 | 2967017 | 0 | 0% | 1 | -2967017 | 0 | 9 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-03-14 | QTR3 | 16/17 |  | 2017-02-09 | QTR3 | 16/17 | 606 | 3290000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 9 | 19 | 13 | 2261 | 3396 | 3345 | 88.89% | 8 | 51 | 0 | 0 | 942 | 193 | 26195812 | 489241 | 25706571 | 27355973 | 27263658 | 0 | 625000 | 625000 | 27888658 | 24014723 | 88.89% | 8 | -3873934 | 1160159 | 680 | 152 | 71 | 193 | 589723 | 0 | 0 | 0 | 680619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | -5909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7561 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 193 | 1271992 | 0
| District 06 Totals |  |  |  |  | 30 | 69 | 82 | 10251 | 12833 | 12198 | 96.67% | 29 | 635 | 0 | 0 | 2349 | 233 | 257677447 | 2624134 | 255053313 | 268224574 | 266170459 | 0 | 7550000 | 7550000 | 273720459 | 259058628 | 93.33% | 28 | -14661829 | 10547125 | 1640 | 519 | 137 | 193 | 4560679 | 22184 | 0 | 0 | 2611217 | 170743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 34 | 5207323 | 473154 | 2 | 0 | 48525 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 80811 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 3982 | 3982 | 0 | 0 | 0 | 0 | 0 | 0 | -761248 | 0 | 190 | 233 | 11751287 | 670064
| 07 | T7209 | 25841515201 | 2009-09-16 | QTR1 | 09/10 | 7 | 55 | 1065 | 1694 | 1694 | 151% | 0 | 0 | 0 | 0 | 109 | 520 | 389463750 | 75000 | 389388750 | 430319761 | 437468272 | 0 | 0 | 0 | 437468272 | 439424048 | 112.8% | 0 | 1955776 | 40856011 | 52 | 34 | 22 | 67 | 10225188 | 4993195 | 1 | 121 | 13703270 | 4748092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 6407054 | 1636245 | 0 | 0 | 10009318 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 173923 | 100951 | 0 | 0 | 210466 | 210466 | 0 | 0 | 3584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 520 | 40732802 | 11688949 | F263258515 | PCL/ARCHER WESTERN A JOINT VEN | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 |  | 2014-10-19 | QTR2 | 14/15 | 714 | 412328910.33 | ARRA:B2:B5:P:B2 | AMERICAN RECOVERY AND REINVEST:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:PUBLIC PRIVATE PARTNERSHIP:ACC - A+B (COST+TIME BIDDING)
| 07 | T7236 | 25589325201 | 2011-09-28 | QTR1 | 11/12 | 2 | 7 | 410 | 560 | 740 | 148.5% | 0 | -180 | 180 | 0 | 131 | 19 | 7147510 | 74000 | 7073510 | 7510715 | 7761739 | -452520 | 0 | -452520 | 7309219 | 7308427 | 103.3% | 1 | -793 | 363205 | 107 | 24 | 0 | 15 | 337971 | 0 | 0 | 4 | 38132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 372176 | 0 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2016-08-10 | QTR1 | 16/17 |  | 2014-06-13 | QTR4 | 13/14 | 717 | 8423805.36
| 07 | T7269 | 40845945201 | 2010-12-08 | QTR2 | 10/11 | 1 | 16 | 565 | 857 | 1355 | 212.7% | 0 | -498 | 498 | 0 | 153 | 139 | 22517641 | 150000 | 22367641 | 23804461 | 24257673 | -2893316 | 0 | -2893316 | 21364357 | 22393675 | 100.1% | 1 | 1029318 | 1286820 | 119 | 34 | 0 | 69 | 626503 | 226978 | 0 | 70 | 754399 | 409500 | 0 | 0 | 0 | 0 | 0 | 0 | -226300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 1166622 | 636478 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2017-04-26 | QTR4 | 16/17 |  | 2014-11-25 | QTR2 | 14/15 | 714 | 23500000
| 07 | T7298 | 25866025201 | 2012-02-08 | QTR3 | 11/12 | 4 | 11 | 750 | 1037 | 1037 | 118% | 1 | 0 | 0 | 0 | 152 | 135 | 29974786 | 150000 | 29824786 | 31148108 | 30989158 | -35000 | 0 | -35000 | 30954158 | 30930903 | 103.7% | 1 | -23256 | 1173322 | 85 | 67 | 0 | 60 | 529216 | 0 | 0 | 75 | 660734 | 406258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6927 | 0 | 0 | 135 | 1269799 | 406258 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-01-25 | QTR3 | 16/17 |  | 2015-04-13 | QTR4 | 14/15 | 714 | 24953779.92
| 07 | T7305 | 41886065201 | 2012-06-20 | QTR4 | 11/12 | 8 | 18 | 740 | 1035 | 1035 | 110% | 1 | 0 | 0 | 0 | 221 | 74 | 27994444 | 135000 | 27859444 | 28571829 | 28922186 | -13000 | 200000 | 187000 | 29109186 | 28487362 | 102.3% | 1 | -621825 | 577385 | 184 | 37 | 0 | 1 | 153865 | 37343 | 0 | 61 | 494365 | 110210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9379 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -1161 | 12265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 637690 | 167258 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 |  | 2015-08-15 | QTR1 | 15/16 | 714 | 26994097.12 | B1 | ACC - NO EXCUSE BONUS
| 07 | T7309 | 25714715201 | 2012-09-26 | QTR1 | 12/13 | 5 | 11 | 1000 | 1141 | 1121 | 98% | 1 | 20 | 0 | 0 | 141 | 0 | 20511016 | 150000 | 20361016 | 21458828 | 20369299 | 0 | 0 | 0 | 20369299 | 20020139 | 98.33% | 1 | -349160 | 947812 | 105 | 36 | 0 | 0 | 754859 | 16651 | 0 | 0 | 284869 | 162142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1086056 | 178793 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-04-25 | QTR4 | 15/16 | 714 | 20045000
| 07 | T7311 | 25579315201 | 2013-05-31 | QTR4 | 12/13 | 3 | 15 | 800 | 990 | 976 | 108.6% | 1 | 14 | 0 | 0 | 147 | 43 | 21435705 | 150000 | 21285705 | 23015417 | 23090810 | -8000 | 0 | -8000 | 23082810 | 22674547 | 106.5% | 1 | -408263 | 1579712 | 74 | 33 | 0 | 37 | 367652 | 256110 | 40 | 0 | 1071146 | 402006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 172463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77446 | 4419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 43 | 1688706 | 662534 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-10-27 | QTR2 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 714 | 21961489.64
| 07 | T7326 | 43304615201 | 2013-06-19 | QTR4 | 12/13 | 4 | 0 | 120 | 145 | 139 | 95% | 1 | 6 | 0 | 0 | 25 | 0 | 259624 | 13300 | 246324 | 259624 | 242742 | 0 | 0 | 0 | 242742 | 242742 | 98.55% | 1 | 0 | 0 | 11 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593374298 | EMPOWER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-05-15 | QTR4 | 16/17 |  | 2014-01-15 | QTR3 | 13/14 | 717 | 272600
| 07 | T7331 | 42896215201 | 2013-09-25 | QTR1 | 13/14 | 4 | 9 | 460 | 543 | 543 | 104.6% | 1 | 0 | 0 | 0 | 62 | 21 | 10973861 | 52500 | 10921361 | 11371382 | 11571904 | 0 | 0 | 0 | 11571904 | 11452952 | 104.9% | 1 | -118952 | 397521 | 35 | 27 | 0 | 21 | 253992 | 0 | 0 | 0 | 113746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 54197 | 54197 | 0 | 0 | 0 | 0 | 0 | 0 | -1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 424813 | 58197 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-06-21 | QTR4 | 16/17 |  | 2015-05-29 | QTR4 | 14/15 | 709 | 9940198.06
| 07 | T7345 | 25699525201 | 2014-04-30 | QTR4 | 13/14 | 2 | 5 | 420 | 541 | 538 | 106.4% | 1 | 3 | 0 | 0 | 91 | 30 | 4872870 | 60000 | 4812870 | 6561188 | 6362566 | 0 | 0 | 0 | 6362566 | 6193892 | 128.7% | 0 | -168674 | 1688319 | 67 | 24 | 0 | 0 | 1670961 | 64925 | 0 | 30 | 69035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1744441 | 64925 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-01-31 | QTR3 | 16/17 |  | 2016-02-02 | QTR3 | 15/16 | 709 | 7433777
| 07 | T7348 | 42907415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 495 | 613 | 579 | 93.13% | 1 | 34 | 0 | 0 | 118 | 0 | 13220362 | 110000 | 13110362 | 13351863 | 13162187 | 0 | 0 | 0 | 13162187 | 12814384 | 97.74% | 1 | -347802 | 131501 | 69 | 49 | 0 | 0 | 10426 | 0 | 0 | 0 | 164259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174685 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 |  | 2016-06-02 | QTR4 | 15/16 | 717 | 12277372.35
| 07 | T7356 | 42905815201 | 2014-12-03 | QTR2 | 14/15 | 1 | 3 | 240 | 337 | 337 | 100% | 1 | 0 | 0 | 0 | 97 | 0 | 6377897 | 60000 | 6317897 | 6518755 | 6488848 | 0 | 0 | 0 | 6488848 | 6241174 | 98.79% | 1 | -247674 | 140858 | 77 | 20 | 0 | 0 | 57588 | 0 | 0 | 0 | 41020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32045 | 0 | 0 | 0 | 4717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143613 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 |  | 2016-02-15 | QTR3 | 15/16 | 709 | 6176900
| 07 | T7362 | 42907725202 | 2015-03-25 | QTR3 | 14/15 | 2 | 0 | 180 | 256 | 256 | 100% | 1 | 0 | 0 | 0 | 76 | 0 | 5709404 | 50000 | 5659404 | 5709404 | 5625130 | 0 | 0 | 0 | 5625130 | 5464793 | 96.56% | 1 | -160337 | 0 | 57 | 19 | 0 | 0 | 8822 | 0 | 0 | 0 | 10150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-08-19 | QTR1 | 16/17 |  | 2016-05-16 | QTR4 | 15/16 | 717 | 5660000
| 07 | T7364 | 43311115201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 115 | 141 | 141 | 100% | 1 | 0 | 0 | 0 | 26 | 0 | 1656000 | 50000 | 1606000 | 1660046 | 1621270 | 0 | 0 | 0 | 1621270 | 1621270 | 101% | 1 | 0 | 4046 | 14 | 12 | 0 | 0 | 8843 | 0 | 0 | 0 | 6427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15270 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 |  | 2016-02-08 | QTR3 | 15/16 | 709 | 1539800 | B0 | ACC - LUMP SUM
| 07 | T7365 | 43090015201 | 2015-05-20 | QTR4 | 14/15 | 2 | 3 | 170 | 272 | 272 | 119.4% | 1 | 0 | 0 | 0 | 69 | 33 | 3669419 | 50000 | 3619419 | 3856675 | 3844686 | 0 | 0 | 0 | 3844686 | 3746837 | 103.5% | 1 | -97849 | 187256 | 47 | 22 | 0 | 33 | 193456 | 188898 | 0 | 0 | 28907 | 12707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 209335 | 201605 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-01-06 | QTR3 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 709 | 3925150 | B0 | ACC - LUMP SUM
| 07 | T7366 | 43113215201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 150 | 211 | 210 | 99.33% | 1 | 1 | 0 | 0 | 61 | 0 | 1795000 | 50000 | 1745000 | 1795000 | 1754140 | 0 | 0 | 0 | 1754140 | 1746653 | 100.1% | 1 | -7487 | 0 | 41 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-19 | QTR1 | 16/17 |  | 2016-03-18 | QTR3 | 15/16 | 717 | 1415000 | B0 | ACC - LUMP SUM
| 07 | T7367 | 42907615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 4 | 250 | 355 | 355 | 105.6% | 1 | 0 | 0 | 0 | 91 | 14 | 3822222 | 50000 | 3772222 | 3834124 | 3855324 | 0 | 0 | 0 | 3855324 | 3731807 | 98.93% | 1 | -123517 | 11902 | 61 | 30 | 0 | 0 | 44654 | 0 | 0 | 14 | 59289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -82752 | 0 | 0 | 14 | 24270 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-11-15 | QTR2 | 16/17 |  | 2016-05-27 | QTR4 | 15/16 | 798 | 4100000
| 07 | T7368 | 42421315201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 310 | 399 | 399 | 100% | 1 | 0 | 0 | 0 | 89 | 0 | 4471471 | 50000 | 4421471 | 4471471 | 4410937 | 0 | 0 | 0 | 4410937 | 4410891 | 99.76% | 1 | -46 | 0 | 68 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 18221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18221 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-01-03 | QTR3 | 16/17 |  | 2016-11-10 | QTR2 | 16/17 | 717 | 5267432
| 07 | T7370 | 43251915201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 150 | 240 | 240 | 100% | 1 | 0 | 0 | 0 | 90 | 0 | 3088818 | 50000 | 3038818 | 3088818 | 2944540 | 0 | 0 | 0 | 2944540 | 2940006 | 96.75% | 1 | -4534 | 0 | 44 | 46 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-03 | QTR2 | 16/17 |  | 2016-06-22 | QTR4 | 15/16 | 709 | 3068000
| 07 | T7371 | 43089915201 | 2015-10-28 | QTR2 | 15/16 | 1 | 4 | 250 | 319 | 319 | 100% | 1 | 0 | 0 | 0 | 69 | 0 | 10094563 | 100000 | 9994563 | 10178653 | 10186112 | 0 | 0 | 0 | 10186112 | 10014564 | 100.2% | 1 | -171548 | 84089 | 42 | 27 | 0 | 0 | -28914 | 5035 | 0 | 0 | 106953 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108605 | 5512 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-06-19 | QTR4 | 16/17 |  | 2017-01-05 | QTR3 | 16/17 | 709 | 10547226.76 | B0 | ACC - LUMP SUM
| 07 | T7372 | 43260715201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 85 | 131 | 128 | 97.65% | 1 | 3 | 0 | 0 | 45 | 1 | 3371083 | 50000 | 3321083 | 3375146 | 3271033 | 0 | 0 | 0 | 3271033 | 3261114 | 98.19% | 1 | -9919 | 4063 | 35 | 10 | 0 | 1 | 29247 | 0 | 0 | 0 | 5018 | 2659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 34265 | 2659 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-06-08 | QTR4 | 16/17 |  | 2016-09-13 | QTR1 | 16/17 | 717 | 2100000 | B0 | ACC - LUMP SUM
| 07 | T7373 | 43131515201 | 2015-09-30 | QTR1 | 15/16 | 1 | 1 | 210 | 251 | 251 | 100% | 1 | 0 | 0 | 0 | 41 | 0 | 6275807 | 75000 | 6200807 | 6350807 | 6400500 | 0 | 0 | 0 | 6400500 | 6232156 | 100.5% | 1 | -168344 | 75000 | 28 | 13 | 0 | 0 | 9469 | 0 | 0 | 0 | 73724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39594 | 0 | 0 | 0 | 1277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124063 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-03-06 | QTR3 | 16/17 |  | 2016-12-07 | QTR2 | 16/17 | 798 | 7740000
| 07 | T7374 | 43257915201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 124 | 139 | 110 | 76.61% | 1 | 29 | 0 | 0 | 15 | 0 | 3581528 | 50000 | 3531528 | 3581528 | 3666189 | 0 | 220000 | 220000 | 3886189 | 3671670 | 104% | 1 | -214519 | 0 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-09 | QTR2 | 16/17 |  | 2016-08-18 | QTR1 | 16/17 | 717 | 2950000 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 07 | T7378 | 43149615201 | 2016-01-27 | QTR3 | 15/16 | 2 | 2 | 125 | 185 | 185 | 100% | 1 | 0 | 0 | 0 | 60 | 0 | 4821342 | 50000 | 4771342 | 4867138 | 4900357 | 0 | 0 | 0 | 4900357 | 4881384 | 102.3% | 1 | -18972 | 45797 | 50 | 10 | 0 | 0 | 62986 | 6831 | 0 | 0 | 17749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80735 | 6831 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-04-24 | QTR4 | 16/17 |  | 2016-11-23 | QTR2 | 16/17 | 709 | 4555000
| 07 | T9014 | 43482515201 | 2016-05-25 | QTR4 | 15/16 | 1 | 0 | 135 | 186 | 184 | 125.2% | 0 | 2 | 0 | 0 | 51 | 0 | 888715 | 42900 | 845815 | 888715 | 871541 | 0 | 0 | 0 | 871541 | 871545 | 103% | 1 | 3 | 0 | 3 | 12 | 15 | 0 | 583 | 0 | 21 | 0 | 32425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 33008 | 0 | F030586197 | R.M. WILLIAMS CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-04-28 | QTR4 | 16/17 |  | 2017-03-21 | QTR3 | 16/17 | 706 | 826928
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 25 | 59 | 168 | 9319 | 12578 | 13144 | 84% | 21 | -566 | 678 | 0 | 2230 | 1029 | 607994838 | 1897700 | 606097138 | 657549456 | 664039143 | -3401836 | 420000 | -2981836 | 661057307 | 660778935 | 92% | 23 | -278374 | 49554619 | 1484 | 647 | 37 | 304 | 15318247 | 5795966 | 62 | 375 | 17753838 | 6254051 | 0 | 0 | 0 | 0 | 0 | 0 | -230227 | 0 | 0 | 0 | 4000 | 4000 | 0 | 313 | 6687210 | 1697882 | 0 | 0 | 10030770 | 0 | 0 | 0 | -1122 | 0 | 0 | 27 | 269557 | 105370 | 0 | 0 | 302442 | 210466 | 0 | 10 | 71420 | 12265 | 0 | 0 | 0 | 0 | 0 | 0 | -89679 | 0 | 99 | 1029 | 50116455 | 14079999
| 07 | E7F75 | 25839855201 | 2012-05-08 | QTR4 | 11/12 | 2 | 30 | 1445 | 1568 | 1429 | 90.38% | 1 | 139 | 0 | 0 | 123 | 0 | 215400000 | 150000 | 215250000 | 224435209 | 224895976 | 0 | 1650000 | 1650000 | 226545976 | 223875000 | 104% | 1 | -2670976 | 9035209 | 88 | 35 | 0 | 0 | 2771364 | 13903 | 0 | 0 | 5245266 | 459975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22798 | 0 | 0 | 0 | 1015841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9055269 | 473878 | F453806780 | SKANSKA-AJAX PAVING JOINT VENTU | N/A | N/A | N/A | N/A | 2016-12-06 | QTR2 | 16/17 |  | 2016-06-28 | QTR4 | 15/16 | 714 | 213872600 | B11:B12:B8:B:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - DSGN BLD-MAJ/BONUS/WRNTY:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 07 | E7I30 | 41101425201 | 2013-10-29 | QTR2 | 13/14 | 1 | 9 | 749 | 941 | 941 | 102.8% | 1 | 0 | 0 | 0 | 171 | 21 | 45811000 | 150000 | 45661000 | 47224425 | 47268962 | 0 | 0 | 0 | 47268962 | 46074212 | 100.9% | 1 | -1194751 | 1413425 | 134 | 37 | 0 | 21 | 545327 | 101855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 0 | 0 | 899849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1481476 | 101855 | F940519552 | GRANITE CONSTRUCTION COMPANY OF CALIFORN | N/A | N/A | N/A | N/A | 2017-05-23 | QTR4 | 16/17 |  | 2016-08-17 | QTR1 | 16/17 | 714 | 47778700 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7I34 | 41101135201 | 2014-01-23 | QTR3 | 13/14 | 1 | 3 | 750 | 874 | 871 | 99.6% | 1 | 3 | 0 | 0 | 124 | 0 | 35188969 | 150000 | 35038969 | 35441051 | 35414850 | 0 | 0 | 0 | 35414850 | 34061551 | 97.21% | 1 | -1353299 | 252082 | 90 | 34 | 0 | 0 | 47212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31900 | 0 | 0 | 0 | 150744 | 0 | 0 | 0 | 75555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305411 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-23 | QTR2 | 16/17 |  | 2016-11-02 | QTR2 | 16/17 | 714 | 37368154.02 | B8 | ACC - DESIGN/BUILD - MAJOR
| 07 | E7I46 | 25633925201 | 2014-08-14 | QTR1 | 14/15 | 1 | 4 | 450 | 623 | 622 | 107.8% | 1 | 1 | 0 | 0 | 137 | 36 | 15944000 | 150000 | 15794000 | 16474127 | 16294835 | 0 | 0 | 0 | 16294835 | 15360010 | 97.25% | 1 | -934824 | 530127 | 97 | 40 | 0 | 0 | 56222 | 0 | 0 | 1 | 186898 | 3530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 346909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 590029 | 3530 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-15 | QTR1 | 16/17 |  | 2016-06-25 | QTR4 | 15/16 | 714 | 18310419.41 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
| 07 | E7I70 | 42550015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 5 | 450 | 694 | 690 | 109.1% | 1 | 4 | 0 | 0 | 199 | 45 | 10449830 | 119000 | 10330830 | 11043877 | 11011337 | 0 | 0 | 0 | 11011337 | 10279911 | 99.51% | 1 | -731426 | 594047 | 156 | 43 | 0 | 34 | 313026 | 0 | 0 | 3 | 96771 | 980 | 0 | 0 | 84213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38377 | 38377 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 532387 | 39357 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-04-05 | QTR4 | 16/17 |  | 2016-09-15 | QTR1 | 16/17 | 717 | 11723000 | B0 | ACC - LUMP SUM
| 07 | E7I76 | 42900015201 | 2014-06-11 | QTR4 | 13/14 | 1 | 8 | 525 | 768 | 768 | 119.4% | 1 | 0 | 0 | 0 | 141 | 102 | 11107156 | 120000 | 10987156 | 11770977 | 11963122 | 0 | 0 | 0 | 11963122 | 11588757 | 105.5% | 1 | -374365 | 663821 | 96 | 45 | 0 | 49 | 373765 | 0 | 0 | 53 | 336731 | 26900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 714298 | 26900 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-03-31 | QTR3 | 16/17 |  | 2016-10-10 | QTR2 | 16/17 | 717 | 11550400
| 07 | E7J99 | 42715515201 | 2015-04-08 | QTR4 | 14/15 | 1 | 1 | 199 | 302 | 274 | 101% | 1 | 28 | 0 | 0 | 103 | 0 | 1844400 | 50000 | 1794400 | 1881240 | 1852163 | 0 | 0 | 0 | 1852163 | 1792416 | 99.89% | 1 | -59746 | 36840 | 47 | 26 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 |  | 2016-06-28 | QTR4 | 15/16 | 798 | 1650000
| 07 | E7K01 | 43070715201 | 2015-02-11 | QTR3 | 14/15 | 1 | 4 | 360 | 510 | 509 | 115.6% | 1 | 1 | 0 | 0 | 93 | 57 | 2815000 | 50000 | 2765000 | 2850595 | 2883182 | 0 | 0 | 0 | 2883182 | 2883115 | 104.3% | 1 | -66 | 35595 | 66 | 27 | 0 | 57 | 50148 | 0 | 0 | 0 | 26437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 76584 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-04-04 | QTR4 | 16/17 |  | 2016-12-05 | QTR2 | 16/17 | 709 | 2338000
| 07 | E7K02 | 43090115201 | 2015-02-11 | QTR3 | 14/15 | 1 | 3 | 125 | 176 | 176 | 109.6% | 1 | 0 | 0 | 0 | 39 | 12 | 2683100 | 50000 | 2633100 | 2806747 | 2817266 | 0 | 0 | 0 | 2817266 | 2772695 | 105.3% | 1 | -44571 | 123647 | 34 | 5 | 0 | 12 | 67604 | 15358 | 0 | 0 | 123204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17782 | 0 | 0 | 12 | 173025 | 15358 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-07 | QTR1 | 16/17 |  | 2015-11-30 | QTR2 | 15/16 | 709 | 2450000 | B0 | ACC - LUMP SUM
| 07 | E7K04 | 43066015201 | 2015-03-11 | QTR3 | 14/15 | 1 | 2 | 180 | 281 | 281 | 118.9% | 1 | 0 | 0 | 0 | 82 | 19 | 2680382 | 50000 | 2630382 | 2750471 | 2763085 | 0 | 0 | 0 | 2763085 | 2699178 | 102.6% | 1 | -63907 | 70089 | 46 | 21 | 0 | 0 | 0 | 0 | 0 | 19 | 111980 | 18119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 19 | 114701 | 18119 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-03-14 | QTR3 | 15/16 | 709 | 2007403 | B0 | ACC - LUMP SUM
| 07 | E7K05 | 43243225201 | 2015-03-11 | QTR3 | 14/15 | 1 | 0 | 220 | 262 | 261 | 99.55% | 1 | 1 | 0 | 0 | 42 | 0 | 1086230 | 50000 | 1036230 | 1086230 | 1062839 | 0 | 0 | 0 | 1062839 | 1062824 | 102.6% | 1 | -15 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2016-09-26 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 717 | 1230200
| 07 | E7K06 | 42905615201 | 2015-06-30 | QTR4 | 14/15 | 1 | 4 | 140 | 215 | 215 | 119.3% | 1 | 0 | 0 | 0 | 48 | 27 | 4138392 | 50000 | 4088392 | 4373349 | 4094400 | 0 | 0 | 0 | 4094400 | 4010129 | 98.09% | 1 | -84271 | 234957 | 28 | 20 | 0 | 27 | 111035 | 0 | 0 | 0 | 106967 | 1662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 218003 | 1662 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-04-18 | QTR4 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 709 | 3911400.01
| 07 | E7K07 | 43068515201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 105 | 145 | 145 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 1119020 | 42000 | 1077020 | 1119020 | 1092543 | 0 | 0 | 0 | 1092543 | 1092543 | 101.4% | 1 | 0 | 0 | 25 | 15 | 0 | 0 | 3319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3319 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2016-10-27 | QTR2 | 16/17 |  | 2016-06-03 | QTR4 | 15/16 | 717 | 885300 | B0 | ACC - LUMP SUM
| 07 | E7K17 | 43094815201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 220 | 258 | 212 | 79.09% | 1 | 46 | 0 | 0 | 38 | 0 | 2888000 | 50000 | 2838000 | 2888000 | 2727932 | 0 | 0 | 0 | 2727932 | 2634048 | 92.81% | 1 | -93884 | 0 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-16 | QTR1 | 16/17 |  | 2016-05-31 | QTR4 | 15/16 | 798 | 3200000 | B0 | ACC - LUMP SUM
| 07 | E7K29 | 42550325201 | 2015-05-13 | QTR4 | 14/15 | 1 | 0 | 120 | 183 | 155 | 76.67% | 1 | 28 | 0 | 0 | 63 | 0 | 1984295 | 50000 | 1934295 | 1984295 | 1950400 | 0 | 0 | 0 | 1950400 | 1950400 | 100.8% | 1 | 0 | 0 | 32 | 31 | 0 | 0 | 13191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13191 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-10-10 | QTR2 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 717 | 1727700
| 07 | E7K67 | 43149515201 | 2015-05-13 | QTR4 | 14/15 | 1 | 4 | 140 | 178 | 178 | 107.1% | 1 | 0 | 0 | 0 | 28 | 10 | 2794895 | 50000 | 2744895 | 2964710 | 2918290 | -7200 | 0 | -7200 | 2911090 | 2905726 | 105.9% | 1 | -5363 | 169815 | 17 | 11 | 0 | 5 | 49615 | 0 | 0 | 5 | 161418 | 7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17145 | 0 | 0 | 10 | 193888 | 7074 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 |  | 2016-05-11 | QTR4 | 15/16 | 717 | 1905000
| 07 | E7K68 | 43149115201 | 2015-05-13 | QTR4 | 14/15 | 2 | 2 | 200 | 298 | 294 | 112.5% | 1 | 4 | 0 | 0 | 69 | 29 | 4031039 | 50000 | 3981039 | 4044189 | 4055974 | 0 | 0 | 0 | 4055974 | 4004687 | 100.6% | 1 | -51286 | 13150 | 48 | 21 | 0 | 6 | 42639 | 3293 | 0 | 23 | 4531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59544 | 3293 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 709 | 3361350
| 07 | E7K76 | 43070625201 | 2015-12-09 | QTR2 | 15/16 | 1 | 0 | 390 | 445 | 409 | 90.77% | 1 | 36 | 0 | 0 | 55 | 0 | 2114910 | 50000 | 2064910 | 2114910 | 2214302 | 0 | 0 | 0 | 2214302 | 2214502 | 107.2% | 1 | 200 | 0 | 37 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 5026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5026 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-05-16 | QTR4 | 16/17 |  | 2017-04-04 | QTR4 | 16/17 | 717 | 2723400
| 07 | E7K78 | 43080235201 | 2015-09-09 | QTR1 | 15/16 | 2 | 0 | 206 | 217 | 128 | 56.8% | 1 | 89 | 0 | 0 | 11 | 0 | 1271000 | 50000 | 1221000 | 1271000 | 1221000 | 0 | 0 | 0 | 1221000 | 1221000 | 100% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 |  | 2016-05-10 | QTR4 | 15/16 | 717 | 2206022.47 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 07 | E7K80 | 43478115201 | 2015-08-12 | QTR1 | 15/16 | 2 | 2 | 160 | 203 | 203 | 101.2% | 1 | 0 | 0 | 0 | 41 | 2 | 1052289 | 33000 | 1019289 | 1092289 | 992268 | 0 | 0 | 0 | 992268 | 991427 | 97.27% | 1 | -840 | 40000 | 21 | 20 | 0 | 0 | 7453 | 0 | 0 | 2 | 55456 | 19923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 62908 | 19923 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 |  | 2016-04-29 | QTR4 | 15/16 | 717 | 752249.19
| 07 | E7K84 | 43070615201 | 2015-10-14 | QTR2 | 15/16 | 1 | 0 | 290 | 347 | 345 | 99.31% | 1 | 2 | 0 | 0 | 57 | 0 | 2060672 | 50000 | 2010672 | 2060672 | 1940979 | 0 | 0 | 0 | 1940979 | 1940979 | 96.53% | 1 | 0 | 0 | 34 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-04-06 | QTR4 | 16/17 |  | 2017-01-30 | QTR3 | 16/17 | 717 | 2481000
| 07 | E7K88 | 43071015201 | 2016-01-13 | QTR3 | 15/16 | 1 | 1 | 75 | 75 | 34 | 45.33% | 1 | 41 | 0 | 0 | 0 | 0 | 716889 | 28000 | 688889 | 655243 | 627243 | 0 | 0 | 0 | 627243 | 627243 | 91.05% | 1 | 0 | -61646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -61646 | 0 | 0 | 0 | -61646 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-27 | QTR2 | 16/17 |  | 2016-08-19 | QTR1 | 16/17 | 717 | 590500 | B0 | ACC - LUMP SUM
| 07 | E7K89 | 42905915201 | 2016-03-09 | QTR3 | 15/16 | 1 | 0 | 90 | 124 | 124 | 104.4% | 1 | 0 | 0 | 0 | 30 | 4 | 2078378 | 50000 | 2028378 | 2078378 | 1941350 | -25400 | 0 | -25400 | 1915950 | 1919022 | 94.61% | 1 | 3072 | 0 | 24 | 6 | 0 | 0 | 0 | 0 | 0 | 4 | 8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9187 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-02-21 | QTR3 | 16/17 |  | 2016-10-21 | QTR2 | 16/17 | 717 | 2100000 | B0 | ACC - LUMP SUM
| 07 | E7K90 | 43386615201 | 2016-02-10 | QTR3 | 15/16 | 1 | 0 | 60 | 61 | 59 | 96.67% | 1 | 2 | 0 | 0 | 1 | 0 | 795744 | 15000 | 780744 | 795744 | 787111 | 0 | 0 | 0 | 787111 | 787111 | 100.8% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5751 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-10-12 | QTR2 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 717 | 455000 | B0 | ACC - LUMP SUM
| 07 | E7K92 | 42749515201 | 2016-06-08 | QTR4 | 15/16 | 1 | 1 | 40 | 49 | 49 | 100% | 1 | 0 | 0 | 0 | 9 | 0 | 377368 | 1590 | 375778 | 396118 | 378995 | 0 | 0 | 0 | 378995 | 378995 | 100.9% | 1 | 0 | 18750 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-04-14 | QTR4 | 16/17 |  | 2017-03-05 | QTR3 | 16/17 | 717 | 201276 | B0 | ACC - LUMP SUM
| 07 | E7K93 | 42749615201 | 2016-01-13 | QTR3 | 15/16 | 1 | 1 | 50 | 63 | 63 | 100% | 1 | 0 | 0 | 0 | 13 | 0 | 429380 | 7100 | 422280 | 432555 | 431202 | 0 | 0 | 0 | 431202 | 431202 | 102.1% | 1 | 0 | 3175 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8922 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-01-06 | QTR3 | 16/17 |  | 2016-07-06 | QTR1 | 16/17 | 709 | 252301.19 | B0 | ACC - LUMP SUM
| 07 | E7K94 | 42750115201 | 2016-02-10 | QTR3 | 15/16 | 1 | 1 | 50 | 60 | 59 | 98% | 1 | 1 | 0 | 0 | 10 | 0 | 652140 | 14000 | 638140 | 665253 | 647487 | 0 | 0 | 0 | 647487 | 647487 | 101.5% | 1 | 0 | 13113 | 6 | 4 | 0 | 0 | 10385 | 0 | 0 | 0 | 2728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13113 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-03-06 | QTR3 | 16/17 |  | 2016-09-14 | QTR1 | 16/17 | 717 | 350000 | B0 | ACC - LUMP SUM
| 07 | E7K96 | 42896915201 | 2016-03-31 | QTR3 | 15/16 | 1 | 1 | 120 | 178 | 178 | 115.8% | 1 | 0 | 0 | 0 | 39 | 19 | 2176471 | 50000 | 2126471 | 2176471 | 2177273 | 0 | 0 | 0 | 2177273 | 2177273 | 102.4% | 1 | 0 | 0 | 18 | 21 | 0 | 0 | 37837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37837 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-06-29 | QTR4 | 16/17 |  | 2017-03-17 | QTR3 | 16/17 | 717 | 1980000 | B0 | ACC - LUMP SUM
| 07 | E7K99 | 43625515201 | 2016-03-09 | QTR3 | 15/16 | 1 | 1 | 50 | 51 | 37 | 72% | 1 | 14 | 0 | 0 | 1 | 0 | 160902 | 4125 | 156777 | 182550 | 178425 | 0 | 0 | 0 | 178425 | 178425 | 113.8% | 0 | 0 | 21648 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 21648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21648 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 |  | 2016-07-26 | QTR1 | 16/17 | 717 | 165500 | B0 | ACC - LUMP SUM
| 07 | E7L02 | 43472915201 | 2016-06-08 | QTR4 | 15/16 | 1 | 0 | 100 | 134 | 132 | 98% | 1 | 2 | 0 | 0 | 34 | 0 | 2090000 | 50000 | 2040000 | 2090000 | 2025548 | 0 | 0 | 0 | 2025548 | 2025548 | 99.29% | 1 | 0 | 0 | 12 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-05-15 | QTR4 | 16/17 |  | 2017-02-25 | QTR3 | 16/17 | 717 | 1628500 | B0 | ACC - LUMP SUM
| 07 | E7L07 | 43258315201 | 2015-11-12 | QTR2 | 15/16 | 1 | 0 | 80 | 89 | 89 | 105% | 1 | 0 | 0 | 0 | 5 | 4 | 1115377 | 50000 | 1065377 | 1115377 | 1056390 | 0 | 0 | 0 | 1056390 | 1056390 | 99.16% | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 |  | 2016-05-03 | QTR4 | 15/16 | 798 | 1450000 | B0 | ACC - LUMP SUM
| 07 | E7L29 | 42717125201 | 2016-06-08 | QTR4 | 15/16 | 1 | 0 | 115 | 145 | 145 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 567079 | 20000 | 547079 | 567079 | 554076 | 0 | 0 | 0 | 554076 | 554076 | 101.3% | 1 | 0 | 0 | 5 | 25 | 0 | 0 | 1851 | 0 | 0 | 0 | 5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6997 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-04-12 | QTR4 | 16/17 |  | 2017-03-10 | QTR3 | 16/17 | 717 | 490000 | B0 | ACC - LUMP SUM
| 07 | E7L38 | 43936215201 | 2016-06-08 | QTR4 | 15/16 | 1 | 2 | 100 | 116 | 105 | 89% | 1 | 11 | 0 | 0 | 16 | 0 | 281697 | 10500 | 271197 | 282895 | 265516 | 0 | 0 | 0 | 265516 | 265516 | 97.91% | 1 | 0 | 1199 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2017-02-14 | QTR3 | 16/17 |  | 2016-12-06 | QTR2 | 16/17 | 709 | 275000
| 07 | E7L40 | 43940015201 | 2016-07-13 | QTR1 | 16/17 | 1 | 0 | 30 | 38 | 38 | 116.7% | 1 | 0 | 0 | 0 | 3 | 5 | 142928 | 3530 | 139398 | 142928 | 136015 | 0 | 0 | 0 | 136015 | 136015 | 97.57% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2967 | 0 | F270559642 | CITY WIDE PAVING LLC | N/A | N/A | N/A | N/A | 2017-03-07 | QTR3 | 16/17 |  | 2016-11-23 | QTR2 | 16/17 | 798 | 150000
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 34 | 38 | 89 | 8384 | 10671 | 10218 | 100% | 34 | 453 | 0 | 0 | 1895 | 392 | 380048932 | 1867845 | 378181087 | 393257974 | 392642336 | -32600 | 1650000 | 1617400 | 394259736 | 386599413 | 97.06% | 33 | -7660318 | 13209043 | 1243 | 607 | 0 | 211 | 4501993 | 134409 | 30 | 115 | 6559986 | 538163 | 0 | 0 | 84213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90998 | 0 | 15 | 39 | 2493947 | 38377 | 0 | 8 | 83688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -96573 | 0 | 45 | 373 | 13718249 | 710949
| District 07 Totals |  |  |  |  | 59 | 97 | 257 | 17703 | 23249 | 23362 | 93.22% | 55 | -113 | 678 | 0 | 4125 | 1421 | 988043770 | 3765545 | 984278225 | 1050807430 | 1056681479 | -3434436 | 2070000 | -1364436 | 1055317043 | 1047378348 | 94.92% | 56 | -7938692 | 62763662 | 2727 | 1254 | 37 | 515 | 19820240 | 5930375 | 92 | 490 | 24313824 | 6792214 | 0 | 0 | 84213 | 0 | 0 | 0 | -230227 | 0 | 0 | 0 | 94998 | 4000 | 15 | 352 | 9181157 | 1736259 | 0 | 8 | 10114458 | 0 | 0 | 0 | -1122 | 0 | 0 | 27 | 269557 | 105370 | 0 | 0 | 302442 | 210466 | 0 | 10 | 71420 | 12265 | 0 | 0 | 0 | 0 | 0 | 0 | -186252 | 0 | 144 | 1402 | 63834704 | 14790948
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8M60 | 43127515201 | 2013-01-22 | QTR3 | 12/13 | 3 | 33 | 1055 | 1167 | 1167 | 100.4% | 1 | 0 | 0 | 0 | 112 | 0 | 56648757 | 150000 | 56498757 | 57438075 | 57810006 | 0 | 0 | 0 | 57810006 | 57069148 | 101% | 1 | -740858 | 789318 | 68 | 40 | 0 | 0 | 324282 | 0 | 0 | 0 | 229213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568192 | 23585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 32879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -311259 | 0 | 4 | 0 | 843308 | 23585 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 |  | 2016-06-30 | QTR4 | 15/16 | 854 | 56376201.62
| 08 | E8M62 | 40615115201 | 2013-02-26 | QTR3 | 12/13 | 2 | 19 | 995 | 1321 | 1336 | 113.8% | 1 | -15 | 15 | 0 | 214 | 112 | 46046392 | 150000 | 45896392 | 46822521 | 47408243 | -137490 | 0 | -137490 | 47270753 | 46013135 | 100.3% | 1 | -1257618 | 776129 | 142 | 62 | 0 | 0 | 162157 | 0 | 10 | 112 | 852634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -210973 | 0 | 10 | 112 | 805848 | 0 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2017-05-31 | QTR4 | 16/17 |  | 2017-01-23 | QTR3 | 16/17 | 854 | 51466143.9 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8M63 | 40615215201 | 2013-02-05 | QTR3 | 12/13 | 3 | 16 | 995 | 1179 | 1179 | 102.1% | 1 | 0 | 0 | 0 | 170 | 14 | 57400000 | 150000 | 57250000 | 57854468 | 58114118 | -10000 | 0 | -10000 | 58104118 | 57193979 | 99.9% | 1 | -910139 | 454468 | 108 | 55 | 0 | 0 | 135877 | 1764 | 7 | 14 | 647998 | 24913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -365840 | 0 | 7 | 14 | 489562 | 26677 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-02 | QTR2 | 16/17 |  | 2016-07-20 | QTR1 | 16/17 | 854 | 59063480.38
| 08 | E8N60 | 41546265201 | 2014-05-20 | QTR4 | 13/14 | 1 | 3 | 475 | 545 | 545 | 100.2% | 1 | 0 | 0 | 0 | 70 | 0 | 10628174 | 96840 | 10531334 | 10702005 | 10703365 | -6500 | 0 | -6500 | 10696865 | 10548835 | 100.2% | 1 | -148030 | 73831 | 23 | 46 | 0 | 0 | 8969 | 0 | 0 | 0 | 107706 | 13562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 117912 | 13562 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 |  | 2016-04-12 | QTR4 | 15/16 | 854 | 9781121.21
| 08 | E8N68 | 24301715201 | 2014-06-09 | QTR4 | 13/14 | 2 | 4 | 480 | 643 | 642 | 119.6% | 1 | 1 | 0 | 0 | 163 | 0 | 16844000 | 150000 | 16694000 | 17989634 | 18429954 | -3000 | 0 | -3000 | 18426954 | 17949122 | 107.5% | 1 | -477832 | 1145634 | 44 | 24 | 0 | 0 | 71261 | 0 | 29 | 0 | 246343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 947444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 1265048 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 |  | 2016-07-29 | QTR1 | 16/17 | 854 | 15034152.99
| 08 | E8P54 | 43110015201 | 2015-10-20 | QTR2 | 15/16 | 1 | 1 | 115 | 121 | 118 | 97.39% | 1 | 3 | 0 | 0 | 6 | 0 | 1369271 | 50000 | 1319271 | 1355607 | 1258468 | 0 | 0 | 0 | 1258468 | 1224485 | 92.82% | 1 | -33984 | -13664 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 |  | 2016-06-24 | QTR4 | 15/16 | 854 | 1662320.12
| 08 | E8P55 | 43561715201 | 2015-06-16 | QTR4 | 14/15 | 1 | 1 | 140 | 189 | 189 | 102.9% | 1 | 0 | 0 | 0 | 45 | 4 | 1736149 | 50000 | 1686149 | 1766298 | 1678250 | -26500 | 0 | -26500 | 1651750 | 1651060 | 97.92% | 1 | -690 | 30149 | 29 | 16 | 0 | 4 | 30149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 30149 | 0 | F203908361 | MIDASCO LLC | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 |  | 2016-05-24 | QTR4 | 15/16 | 854 | 1991671.8
| 08 | E8Q15 | 43753215201 | 2016-10-18 | QTR2 | 16/17 | 1 | 1 | 190 | 190 | 31 | 16.32% | 1 | 159 | 0 | 0 | 0 | 0 | 318543 | 25415 | 293128 | 301705 | 250071 | 0 | 0 | 0 | 250071 | 250071 | 85.31% | 1 | 0 | -16837 | 0 | 0 | 0 | 0 | -16837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16837 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2017-05-31 | QTR4 | 16/17 |  | 2017-03-15 | QTR3 | 16/17 | 854 | 796207.04
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 8 | 14 | 78 | 4445 | 5355 | 5207 | 0.002321% | 8 | 148 | 15 | 0 | 780 | 130 | 190991286 | 822255 | 190169031 | 194230313 | 195652475 | -183490 | 0 | -183490 | 195468985 | 191899835 | 100% | 8 | -3569151 | 3239028 | 420 | 243 | 0 | 4 | 715858 | 1764 | 46 | 126 | 2070230 | 51076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 1584228 | 23585 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 37844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -888072 | 0 | 107 | 130 | 3521326 | 76425
| District 08 Totals |  |  |  |  | 8 | 14 | 78 | 4445 | 5355 | 5207 | 100% | 8 | 148 | 15 | 0 | 780 | 130 | 190991286 | 822255 | 190169031 | 194230313 | 195652475 | -183490 | 0 | -183490 | 195468985 | 191899835 | 100% | 8 | -3569151 | 3239028 | 420 | 243 | 0 | 4 | 715858 | 1764 | 46 | 126 | 2070230 | 51076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 1584228 | 23585 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 37844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -888072 | 0 | 107 | 130 | 3521326 | 76425
| Statewide Central Let Contracts SubTotal |  |  |  |  | 187 | 320 | 523 | 51396 | 67811 | 66913 | 86.63% | 162 | 898 | 1049 | 0 | 13236 | 3379 | 1381361712 | 10794925 | 1370566791 | 1454062050 | 1457184141 | -4367166 | 10567700 | 6200534 | 1463384674 | 1434646073 | 92.51% | 173 | -28738609 | 75161278 | 8294 | 3375 | 286 | 1528 | 26117551 | 7810783 | 247 | 1113 | 27975272 | 7759862 | 0 | 0 | 2067 | 0 | 0 | 0 | -230227 | 0 | 0 | 0 | 8000 | 4000 | 500 | 525 | 13930660 | 2288896 | 24 | 85 | 10440902 | 229907 | 0 | 0 | -60414 | 0 | 18 | 72 | 1007298 | 290749 | 97 | 44 | 763158 | 365618 | 223 | 13 | 899540 | 405546 | 0 | 0 | 0 | 0 | 0 | -3 | -1427836 | 0 | 1395 | 3377 | 79425966 | 19155363
| Statewide District Let Contracts SubTotal |  |  |  |  | 140 | 195 | 320 | 34261 | 45591 | 44497 | 89.29% | 125 | 1094 | 355 | 0 | 8252 | 3078 | 882059491 | 7539051 | 874520440 | 919907438 | 919732288 | -695460 | 3166600 | 2471140 | 922203427 | 899991484 | 90.71% | 127 | -22211944 | 37847952 | 5089 | 2339 | 241 | 1476 | 17570767 | 2372069 | 211 | 869 | 18018620 | 2124841 | 0 | 11 | 87748 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 136098 | 0 | 239 | 734 | 5303150 | 828113 | 0 | 27 | 144847 | 0 | 0 | 0 | -40553 | 0 | 4 | 28 | 216763 | 0 | 0 | 21 | 151618 | 93484 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -107 | -1468756 | 0 | 759 | 3059 | 40110545 | 5418507
| Statewide Totals |  |  |  |  | 327 | 515 | 843 | 85657 | 113402 | 111410 | 87.77% | 287 | 1992 | 1404 | 0 | 21488 | 6457 | 2263421203 | 18333976 | 2245087231 | 2373969488 | 2376916429 | -5062626 | 13734300 | 8671674 | 2385588101 | 2334637557 | 91.74% | 300 | -50950553 | 113009230 | 13383 | 5714 | 527 | 3004 | 43688318 | 10182852 | 458 | 1982 | 45993892 | 9884703 | 0 | 11 | 89815 | 0 | 0 | 0 | -239977 | 0 | 0 | 0 | 144098 | 4000 | 739 | 1259 | 19233810 | 3117009 | 24 | 112 | 10585749 | 229907 | 0 | 0 | -100967 | 0 | 22 | 100 | 1224061 | 290749 | 97 | 65 | 914776 | 459102 | 287 | 13 | 899540 | 405546 | 0 | 0 | 0 | 0 | 0 | -110 | -2896592 | 0 | 2154 | 6436 | 119536511 | 24573870

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1L58 | 19753445201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2013-01-10 | 21988997 | 23327334 | 23110936 | 1338337.31 | 0 | 22111039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23110936 | 22111039 | -999897 | 21988997 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1N36 | 43544915201 | F593586613 | EVANS CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-06-19 | 1877203 | 1918177 | 1843430 | 40974.24 | -20904 | 1821939 | -20904 | 0 | 0 | 0 | 0 | 0 | -20904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20904 | 1822526 | 1821939 | -587 | 2352808
1 | E1N74 | 42912015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-18 | 3107573 | 3107573 | 3110593 | 0 | 0 | 2961957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3110593 | 2961957 | -148636 | 3280021
1 | E1N87 | 43120915201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2015-02-19 | 3172000 | 3172000 | 3272265 | 0 | 0 | 3269380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3272265 | 3269380 | -2886 | 3312411
1 | E1O02 | 43161515201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-01-15 | 5445703 | 6533716 | 6114803 | 1088013.37 | 0 | 5883385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6114803 | 5883385 | -231419 | 4971482
1 | E1O45 | 43160315201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-11-19 | 5243826 | 5243826 | 5060368 | 0 | 0 | 4979207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5060368 | 4979207 | -81161 | 7438832
1 | E1O48 | 43129415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-12-17 | 5895900 | 5903041 | 5910137 | 7140.79 | 0 | 5818680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5910137 | 5818680 | -91457 | 5444557 | B0 | ACC - LUMP SUM
1 | E1O51 | 43129115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-03-17 | 6085726 | 6210864 | 5926238 | 125138.04 | 0 | 5952143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5926238 | 5952143 | 25904 | 7615266
1 | E1O52 | 43120615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-11-19 | 2386060 | 2389112 | 2334583 | 3052.24 | 0 | 2290475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2334583 | 2290475 | -44107 | 2466348
1 | E1O54 | 43170515201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2016-01-21 | 960772 | 960772 | 890253 | 0 | 0 | 890253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890253 | 890253 | 0 | 1095709 | B0 | ACC - LUMP SUM
1 | E1O75 | 43503815201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-01-21 | 149955 | 149955 | 147793 | 0 | 0 | 147793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147793 | 147793 | 0 | 157974
1 | E1O76 | 43504325201 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-03-17 | 889110 | 947735 | 899072 | 58625 | 0 | 899072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899072 | 899072 | 0 | 866149
1 | E1O79 | 43708215201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-12-17 | 4699575 | 4749575 | 4699575 | 50000 | 0 | 4699575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4699575 | 4699575 | 0 | 4699575 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1O85 | 42814015201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-11-19 | 1074449 | 1074449 | 1064642 | 0 | 0 | 1064642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064642 | 1064642 | 0 | 1084853 | B0 | ACC - LUMP SUM
1 | E1P12 | 43856115201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-06-09 | 298707 | 305757 | 301340 | 7050 | 0 | 301340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301340 | 301340 | 0 | 246048 | B0 | ACC - LUMP SUM
1 | T1468 | 19753425201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2012-05-23 | 14242918 | 15688629 | 15514205 | 1445710.21 | 0 | 15463127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15514205 | 15463127 | -51078 | 14155367
1 | T1552 | 40631475201 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2013-09-25 | 2579468 | 2579468 | 2493565 | 0 | -85464 | 2408101 | -85464 | 0 | 0 | 0 | 0 | 0 | -85464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -85464 | 2408101 | 2408101 | 0 | 3076291
1 | T1560 | 42910115201 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2015-08-26 | 4883160 | 4883160 | 4742567 | 0 | 0 | 4581604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4742567 | 4581604 | -160964 | 5451825
1 | T1577 | 42919915201 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2013-12-04 | 149236 | 153020 | 93123 | 3783.95 | 0 | 87604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93123 | 87604 | -5519 | 204084 | B0 | ACC - LUMP SUM
1 | T1583 | 42910715201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-05-21 | 12221582 | 12321397 | 12316064 | 99814.55 | -258944 | 11369478 | -258944 | 0 | 0 | 0 | 0 | 0 | -258944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -258944 | 12057120 | 11369478 | -687643 | 11851722
1 | T1587 | 42913115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-03-26 | 4576900 | 4273384 | 4255627 | -303515.58 | 0 | 4165417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4255627 | 4165417 | -90210 | 5166652 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1588 | 41304225201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-06-18 | 24169365 | 23023182 | 22613781 | -1146183.49 | 900000 | 20785082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 900000 | 900000 | 23513781 | 20785082 | -2728699 | 29188896 | B2:B5:B2 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING)
1 | T1595 | 40631345201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-03-25 | 31929262 | 31614976 | 31607283 | -314285.98 | 1300000 | 30894410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 1300000 | 1300000 | 32907283 | 30894410 | -2012872 | 30769491 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
1 | T1596 | 43142215201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-02-25 | 5571174 | 5623674 | 5636689 | 52500 | 0 | 5437906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5636689 | 5437906 | -198783 | 5411862 | B0 | ACC - LUMP SUM
1 | T1597 | 43356115201 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-02-25 | 737000 | 989001 | 989001 | 252000.76 | 0 | 989001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 989001 | 989001 | 0 | 596983 | B0 | ACC - LUMP SUM
1 | T1599 | 42584155201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-07-29 | 7593742 | 7718407 | 7550971 | 124664.7 | 0 | 7299675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7550971 | 7299675 | -251296 | 8930964
1 | T1600 | 42811715201 | F464740152 | CATHCART CONSTRUCTION COMPANY - FLORIDA | N/A | N/A | N/A | N/A | 2015-05-20 | 2180000 | 2794372 | 2791154 | 614371.62 | 0 | 2775457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2791154 | 2775457 | -15697 | 2282381 | B0 | ACC - LUMP SUM
1 | T1601 | 42910615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 2560715 | 2560715 | 2601322 | 0 | 0 | 2476584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601322 | 2476584 | -124738 | 2539522
1 | T1604 | 43340715201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1272557 | 1265786 | 1215247 | -6770.49 | 0 | 1215247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215247 | 1215247 | 0 | 1175939 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1610 | 43337615201 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2015-05-20 | 766880 | 763925 | 702653 | -2955.57 | -27872 | 674781 | -27872 | 0 | 0 | 0 | 0 | 0 | -27872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27872 | 674781 | 674781 | 0 | 1032308 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1612 | 43539315201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 965039 | 965864 | 949501 | 824.93 | 0 | 941761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949501 | 941761 | -7741 | 968995
1 | T1613 | 19611435201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 14129548 | 14489220 | 14438239 | 359672.31 | 392000 | 14122043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392000 | 0 | 392000 | 392000 | 14830239 | 14122043 | -708196 | 13676471 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1615 | 42950615201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1470894 | 1470894 | 1424904 | 0 | 0 | 1424904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424904 | 1424904 | 0 | 1441635 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1617 | 43337515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1087453 | 1211375 | 1165751 | 123921.65 | 0 | 1165751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165751 | 1165751 | 0 | 1092794 | B0 | ACC - LUMP SUM
1 | T1618 | 43340815201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-06-17 | 1135821 | 1138128 | 1108067 | 2307.3 | 0 | 1103946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108067 | 1103946 | -4121 | 1209050 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1619 | 43365815201 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 618558 | 622340 | 622340 | 3781.98 | 0 | 622340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622340 | 622340 | 0 | 495886 | B0 | ACC - LUMP SUM
1 | T1629 | 43325615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-30 | 910000 | 910000 | 883227 | 0 | 0 | 883227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883227 | 883227 | 0 | 857875 | B0 | ACC - LUMP SUM
1 | T1633 | 43092415201 | F592190605 | O-A-K/FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 964016 | 968295 | 968295 | 4278.93 | 0 | 968295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968295 | 968295 | 0 | 965168 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1637 | 43359315201 | F381807765 | DOUGLAS N. HIGGINS INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 2282142 | 2313043 | 2274863 | 30901.45 | 0 | 2279204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274863 | 2279204 | 4342 | 2156564
1 | T1638 | 43450315201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-04-27 | 98907 | 98907 | 93187 | 0 | 0 | 93187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93187 | 93187 | 0 | 117358 | B0 | ACC - LUMP SUM
1 | T1639 | 43321815201 | F743148751 | ROGAR MANAGEMENT & CONSULTING O | N/A | N/A | N/A | N/A | 2016-06-15 | 484935 | 484935 | 472783 | 0 | 0 | 472783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472783 | 472783 | 0 | 507136 | B0 | ACC - LUMP SUM
1 | T1645 | 43146115201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 2749030 | 2749030 | 2742983 | 0 | -50598 | 2702439 | -50598 | 0 | 0 | 0 | 0 | 0 | -50598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50598 | 2692385 | 2702439 | 10054 | 2791241 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1649 | 43092615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 1164267 | 1164267 | 1163985 | 0 | 0 | 1163985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163985 | 1163985 | 0 | 995954 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1651 | 43134115201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-01-27 | 194630 | 194630 | 184896 | 0 | 0 | 184896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184896 | 184896 | 0 | 236550 | B0 | ACC - LUMP SUM
1 | T1654 | 43448815201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2016-05-25 | 374353 | 374353 | 363333 | 0 | 0 | 363333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363333 | 363333 | 0 | 331783 | B0 | ACC - LUMP SUM
1 | T1656 | 43698615201 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-06-15 | 162848 | 162848 | 155000 | 0 | 0 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 155000 | 0 | 192824 | B0 | ACC - LUMP SUM
1 | T1657 | 43131915201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-02-24 | 1914753 | 1914753 | 1975777 | 0 | 0 | 1983617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975777 | 1983617 | 7841 | 1639168
1 | T1659 | 43472815201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 238287 | 238287 | 228375 | 0 | 0 | 228375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228375 | 228375 | 0 | 176436 | B0 | ACC - LUMP SUM
1 | T1669 | 43502315201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 917114 | 917114 | 879919 | 0 | 0 | 881307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879919 | 881307 | 1388 | 940355 | B0 | ACC - LUMP SUM
1 | T1684 | 43766015201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 114858 | 114858 | 107442 | 0 | 0 | 107442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107442 | 107442 | 0 | 126526
1 | T1A02 | 42518315201 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 5396928 | 5491707 | 5952983 | 94778.73 | 0 | 5952455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5952983 | 5952455 | -528 | 4358787 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1A15 | 43325515201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 219504 | 219504 | 213917 | 0 | 0 | 213917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213917 | 213917 | 0 | 200589 | B0 | ACC - LUMP SUM
2 | E2P99 | 21330125201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2012-06-29 | 17859000 | 27306925 | 27318877 | 9447924.67 | 0 | 26689964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27318877 | 26689964 | -628913 | 28650000 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2R04 | 21066125201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2012-12-12 | 1430432 | 1430840 | 1393606 | 408.1 | -49024 | 1344578 | -49024 | 0 | 0 | 0 | 0 | 0 | -49024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49024 | 1344582 | 1344578 | -4 | 1293927
2 | E2R17 | 21237935201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2013-06-20 | 11440230 | 11429587 | 11316805 | -10643.03 | 0 | 11261013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11316805 | 11261013 | -55793 | 13890663 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR
2 | E2T58 | 43226315201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-11-18 | 3757549 | 3757549 | 3830766 | 0 | 0 | 3684887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3830766 | 3684887 | -145879 | 4878401
2 | E2T69 | 43041715201 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-07-15 | 1759555 | 1996713 | 2571252 | 237157.84 | 0 | 2563560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571252 | 2563560 | -7693 | 1357063
2 | E2T70 | 43219415201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2015-07-15 | 741630 | 741630 | 709180 | 0 | 0 | 709010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709180 | 709010 | -170 | 775810
2 | E2T74 | 42342715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-09-16 | 4336630 | 4336630 | 4421132 | 0 | 0 | 4255700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4421132 | 4255700 | -165433 | 4754491
2 | E2T86 | 20789425201 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2015-11-18 | 825208 | 860208 | 824755 | 35000 | 0 | 824711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824755 | 824711 | -44 | 890406
2 | E2T87 | 20967415201 | F205877898 | KIRBY DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2015-11-18 | 1743906 | 1743906 | 2125210 | 0 | 0 | 2124106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125210 | 2124106 | -1104 | 1607951
2 | E2T90 | 20838945201 | F593285921 | S & D INDUSTRIAL PAINTING INC. | N/A | N/A | N/A | N/A | 2015-12-16 | 559753 | 559753 | 512091 | 0 | 0 | 512091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512091 | 512091 | 0 | 1034492
2 | E2U35 | 43226515201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 5333716 | 5333716 | 5070766 | 0 | 0 | 5049334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5070766 | 5049334 | -21432 | 6137176
2 | E2U45 | 42871125201 | Z31-0396250 | OHIO CASUALTY INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2015-12-16 | 138261 | 138261 | 134115 | 0 | -43856 | 120111 | -43856 | 0 | 0 | 0 | 0 | 0 | -43856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43856 | 90258 | 120111 | 29853 | 151023 | B0 | ACC - LUMP SUM
2 | E2U47 | 43226215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-04-20 | 841047 | 841047 | 781435 | 0 | 0 | 781435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781435 | 781435 | 0 | 750871
2 | E2U48 | 40849455201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-04-20 | 293901 | 293901 | 283652 | 0 | 0 | 284750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283652 | 284750 | 1098 | 225522
2 | E2U52 | 43075015201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-06-14 | 1141413 | 1141413 | 1057536 | 0 | 0 | 1057536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057536 | 1057536 | 0 | 954138
2 | E2V32 | 43743115201 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2016-08-17 | 547282 | 547282 | 469400 | 0 | 0 | 469400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469400 | 469400 | 0 | 449348
2 | T2473 | 42449415201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2013-04-24 | 6447454 | 6752983 | 6507167 | 305529 | 0 | 6505012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6507167 | 6505012 | -2155 | 6671609
2 | T2506 | 43040415201 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2013-10-30 | 136157 | 136157 | 128357 | 0 | -47602 | 80754 | -41690 | 0 | 0 | 0 | -5912 | 0 | -47602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47602 | 80754 | 80754 | 0 | 153003 | B0 | ACC - LUMP SUM
2 | T2523 | 43051815201 | F753160478 | ENVIRONMENTAL INNOVATIONS INC | N/A | N/A | N/A | N/A | 2014-03-26 | 212150 | 212150 | 210626 | 0 | -31760 | 178866 | 0 | 0 | 0 | 0 | -31760 | 0 | -31760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31760 | 178866 | 178866 | 0 | 224301 | B0 | ACC - LUMP SUM
2 | T2533 | 43355415201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-06-18 | 8533240 | 8598881 | 9356445 | 65640.9 | 0 | 9207548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9356445 | 9207548 | -148897 | 7794226
2 | T2538 | 42696315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-06-18 | 3648202 | 3648202 | 3611865 | 0 | 0 | 3514982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3611865 | 3514982 | -96884 | 3330303
2 | T2541 | 42607315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-09-24 | 3641891 | 3767252 | 4042041 | 125360.82 | 0 | 3981696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4042041 | 3981696 | -60345 | 3748196
2 | T2567 | 43224715201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2015-02-25 | 1013111 | 1368388 | 1368010 | 355277.03 | 0 | 1368010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368010 | 1368010 | 0 | 1004174 | B0 | ACC - LUMP SUM
2 | T2572 | 43061415201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 1990811 | 2002450 | 2059822 | 11638.3 | 0 | 2059822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059822 | 2059822 | 0 | 1508390
2 | T2574 | 21325145201 | F592913720 | CALLAWAY CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 3292108 | 3306325 | 3271355 | 14217.43 | -14380 | 3216216 | -14380 | 0 | 0 | 0 | 0 | 0 | -14380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14380 | 3256975 | 3216216 | -40760 | 3074492
2 | T2575 | 42747615201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2015-06-17 | 6409349 | 6447241 | 6325936 | 37891.18 | 0 | 6325901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6325936 | 6325901 | -35 | 5409342
2 | T2581 | 42747415201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 5752494 | 5752494 | 5614852 | 0 | 0 | 5614852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5614852 | 5614852 | 0 | 6445947
2 | T2584 | 43051315201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 3444187 | 3524159 | 3538172 | 79971.84 | 0 | 3415729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3538172 | 3415729 | -122443 | 3688557
2 | T2587 | 43265515201 | F453689782 | SOUTHERN STATES PAVEMENT MARKINGS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 718800 | 718800 | 718800 | 0 | 0 | 718800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718800 | 718800 | 0 | 769167 | B0 | ACC - LUMP SUM
2 | T2588 | 21237925201 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-09-30 | 2271500 | 2329229 | 2340019 | 57729.21 | 0 | 2337891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340019 | 2337891 | -2128 | 2754839 | B0 | ACC - LUMP SUM
2 | T2589 | 41525415201 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2015-12-03 | 1503905 | 1530011 | 1553775 | 26105.47 | 0 | 1554113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1553775 | 1554113 | 338 | 1346460
2 | T2593 | 43051715201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-09-30 | 1956915 | 1997332 | 1951682 | 40417.14 | 0 | 1947009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1951682 | 1947009 | -4672 | 2334094
2 | T2594 | 43265415201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2015-09-30 | 475000 | 475000 | 475000 | 0 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000 | 475000 | 0 | 428506 | B0 | ACC - LUMP SUM
2 | T2598 | 43265915201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 848333 | 848333 | 798176 | 0 | -19162 | 774669 | -19162 | 0 | 0 | 0 | 0 | 0 | -19162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19162 | 779014 | 774669 | -4345 | 911546
2 | T2602 | 43074515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-02-24 | 558858 | 558858 | 508320 | 0 | 0 | 508320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508320 | 508320 | 0 | 579077
2 | T2603 | 43075915201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 521218 | 521218 | 506672 | 0 | 0 | 506672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506672 | 506672 | 0 | 510082
2 | T2604 | 43226115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 7717554 | 7717554 | 7824593 | 0 | -15080 | 7576665 | -15080 | 0 | 0 | 0 | 0 | 0 | -15080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15080 | 7809513 | 7576665 | -232848 | 9660990
2 | T2605 | 43226415201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 4020836 | 4002599 | 3805029 | -18236.68 | 0 | 3807540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3805029 | 3807540 | 2511 | 4422862
2 | T2608 | 43055825201 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2015-10-28 | 148375 | 148375 | 138616 | 0 | 0 | 138616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138616 | 138616 | 0 | 178082
2 | T2610 | 41525115201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2015-12-09 | 1544000 | 1544000 | 1614197 | 0 | 0 | 1614952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1614197 | 1614952 | 755 | 1676281
2 | T2613 | 42869615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 7289393 | 7289393 | 7240404 | 0 | 0 | 7140234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7240404 | 7140234 | -100170 | 8014110
2 | T2626 | 43055215201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 3284461 | 3284461 | 3197387 | 0 | 0 | 3131128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3197387 | 3131128 | -66259 | 3672061
2 | T2631 | 43808515201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 148168 | 148168 | 142273 | 0 | 0 | 142273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142273 | 142273 | 0 | 129624
2 | T2659 | 43432715201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-05-24 | 2042000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2336444
3 | E3K73 | 42693515201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2014-03-13 | 1221881 | 1231781 | 1143560 | 9900 | 0 | 1120620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1143560 | 1120620 | -22940 | 1514949
3 | E3L68 | 42874015201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-01-14 | 2387205 | 2450930 | 2540774 | 63725 | -17920 | 2503625 | -7920 | 0 | 0 | 0 | 0 | -10000 | -17920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17920 | 2522854 | 2503625 | -19229 | 3051776
3 | E3L90 | 42840315201 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2013-06-28 | 24049000 | 24338104 | 24337828 | 289103.75 | 0 | 24337642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24337828 | 24337642 | -186 | 21314872 | A3 | ICC - DESIGN/BUILD - MINOR
3 | E3M17 | 40747845201 | F455085205 | PRINCIPLE PROPERTIES INC. | N/A | N/A | N/A | N/A | 2015-11-20 | 149498 | 149498 | 139613 | 0 | 0 | 139613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139613 | 139613 | 0 | 163264
3 | E3M30 | 42429125201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-02-26 | 4578636 | 5834533 | 5832583 | 1255897.44 | 0 | 5832583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5832583 | 5832583 | 0 | 4578636 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
3 | E3M55 | 42805825201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2014-01-31 | 1540571 | 1579254 | 1571464 | 38682.88 | 0 | 1571464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1571464 | 1571464 | 0 | 1529160 | A3 | ICC - DESIGN/BUILD - MINOR
3 | E3M95 | 41694315201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-07-09 | 2738862 | 3014082 | 3595051 | 275219.9 | 0 | 3484491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3595051 | 3484491 | -110560 | 3204695
3 | E3N17 | 43392715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-12-10 | 1734968 | 1417537 | 1360898 | -317430.27 | 0 | 1360898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360898 | 1360898 | 0 | 1346664
3 | E3N18 | 43391815201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-10-08 | 1245237 | 1323870 | 1408799 | 78632.64 | 0 | 1408799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1408799 | 1408799 | 0 | 1048525
3 | E3N24 | 42884815201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-03-10 | 3543344 | 3600105 | 3788222 | 56761.11 | 0 | 3802308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3788222 | 3802308 | 14086 | 3817848
3 | E3N27 | 41627215201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2015-03-25 | 2233345 | 2293381 | 2249432 | 60035.59 | 0 | 2223244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2249432 | 2223244 | -26188 | 2172219 | A3:LBDB:A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
3 | E3N39 | 43078815201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-05-14 | 3111936 | 3033818 | 2963684 | -78118.45 | -11504 | 2882199 | -11504 | 0 | 0 | 0 | 0 | 0 | -11504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11504 | 2952180 | 2882199 | -69981 | 3291623
3 | E3N42 | 21791185201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-03-10 | 762045 | 762045 | 712000 | 0 | 0 | 712000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712000 | 712000 | 0 | 1488725
3 | E3N48 | 43514815201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-02-11 | 398651 | 407027 | 394699 | 8376.05 | 0 | 394699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394699 | 394699 | 0 | 275248
3 | E3N73 | 43078715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-05-14 | 4943758 | 4974205 | 5018776 | 30446.86 | -2400 | 4741701 | 0 | 0 | 0 | 0 | 0 | -2400 | -2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2400 | 5016376 | 4741701 | -274675 | 4773076
3 | E3N74 | 42696915201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2015-11-20 | 2813937 | 2813937 | 2913809 | 0 | 0 | 2837766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2913809 | 2837766 | -76042 | 3196209
3 | E3N76 | 41557535201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-01-14 | 1819446 | 1819446 | 1750296 | 0 | 0 | 1750297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750296 | 1750297 | 1 | 1571363
3 | E3N80 | 42577825201 | F208328161 | AN-KAR CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-01-14 | 246955 | 246955 | 248745 | 0 | -7664 | 241081 | -7664 | 0 | 0 | 0 | 0 | 0 | -7664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7664 | 241081 | 241081 | 0 | 183111
3 | E3O14 | 41040925201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-09-24 | 1815481 | 1830051 | 1851635 | 14570.45 | 0 | 1847209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1851635 | 1847209 | -4426 | 1670232
3 | E3O47 | 43253815201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-10-15 | 2030029 | 2030029 | 2131829 | 0 | 0 | 2045055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2131829 | 2045055 | -86775 | 2649534
3 | E3O53 | 43254815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-09-10 | 2754000 | 2754000 | 2779810 | 0 | 0 | 2686704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2779810 | 2686704 | -93106 | 3103650
3 | E3O62 | 43079215201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-12-10 | 1298500 | 1382401 | 1347119 | 83901.29 | 0 | 1319720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347119 | 1319720 | -27399 | 1564335 | B0 | ACC - LUMP SUM
3 | E3O64 | 40946235201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2016-09-08 | 76737 | 76737 | 79842 | 0 | 0 | 79842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79842 | 79842 | 0 | 102432
3 | E3P32 | 42460825201 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-03-10 | 69197 | 69197 | 67195 | 0 | 0 | 67195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67195 | 67195 | 0 | 143400
3 | E3P60 | 43255315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-08-11 | 966283 | 966283 | 955206 | 0 | -1500 | 953706 | 0 | 0 | 0 | 0 | 0 | -1500 | -1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1500 | 953706 | 953706 | 0 | 939110
3 | E3P65 | 22049555201 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2016-05-19 | 3075201 | 3228421 | 3425155 | 153220.67 | 0 | 3429981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3425155 | 3429981 | 4826 | 3871135
3 | E3P73 | 22266815201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-06-09 | 989058 | 1035205 | 988093 | 46146.83 | 0 | 988093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988093 | 988093 | 0 | 777199
3 | E3P85 | 43627415201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-04-14 | 218815 | 218815 | 209764 | 0 | 0 | 209764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209764 | 209764 | 0 | 189940
3 | T3349 | 22041285201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2010-12-08 | 7357219 | 10528722 | 10638848 | 3171502.78 | -93018 | 10537771 | -93018 | 0 | 0 | 0 | 0 | 0 | -93018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -93018 | 10545830 | 10537771 | -8059 | 7320355 | ARRA | AMERICAN RECOVERY AND REINVEST
3 | T3375 | 42124315201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2012-02-29 | 14736078 | 15035632 | 14669101 | 299554.18 | 0 | 14620764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14669101 | 14620764 | -48338 | 18080147
3 | T3392 | 41694015201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2012-03-28 | 6759549 | 7037952 | 7405140 | 278402.74 | -32260 | 7308967 | -32260 | 0 | 0 | 0 | 0 | 0 | -32260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32260 | 7372880 | 7308967 | -63913 | 7836269
3 | T3398 | 22016225201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 3358717 | 4155082 | 4026349 | 796365.22 | 0 | 3996594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4026349 | 3996594 | -29755 | 2823246
3 | T3403 | 42692915201 | F223711240 | GULF BEACH CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 893145 | 944595 | 853629 | 51450.21 | 0 | 853629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853629 | 853629 | 0 | 829904
3 | T3418 | 42551915201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2014-12-03 | 2589441 | 2672648 | 2648983 | 83206.58 | 0 | 2635144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2648983 | 2635144 | -13838 | 2582603
3 | T3427 | 42164415201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2013-07-31 | 11476305 | 11609159 | 11286785 | 132854.22 | -11250 | 10699458 | 0 | 0 | 0 | 0 | 0 | -11250 | -11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11250 | 11275535 | 10699458 | -576077 | 12800390
3 | T3433 | 42693025201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-02-25 | 4985043 | 5040858 | 4902106 | 55814.29 | -20132 | 4555909 | -20132 | 0 | 0 | 0 | 0 | 0 | -20132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20132 | 4881974 | 4555909 | -326064 | 6115127
3 | T3435 | 42290715201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2013-05-22 | 6523192 | 8090393 | 8420054 | 1567200.59 | 0 | 8335602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8420054 | 8335602 | -84452 | 6744575
3 | T3443 | 42693415201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 4037987 | 4183812 | 4167957 | 145824.98 | 0 | 3846478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167957 | 3846478 | -321479 | 4397279
3 | T3460 | 42874715201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-03-30 | 1335414 | 1335414 | 1301394 | 0 | 0 | 1295632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301394 | 1295632 | -5762 | 1593999
3 | T3464 | 43000315201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 5476809 | 5729223 | 5761356 | 252414.41 | 0 | 5745026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5761356 | 5745026 | -16330 | 4721319
3 | T3482 | 42884515201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-01-28 | 7416925 | 7437265 | 7758460 | 20339.32 | -880 | 7441692 | 0 | 0 | 0 | 0 | 0 | -880 | -880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -880 | 7757580 | 7441692 | -315888 | 8733988
3 | T3483 | 43077715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 4039522 | 4047995 | 4269663 | 8472.89 | 0 | 4226492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4269663 | 4226492 | -43171 | 3857910
3 | T3491 | 43078015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 3493487 | 3493487 | 3579235 | 0 | 0 | 3547935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3579235 | 3547935 | -31300 | 2971789
3 | T3495 | 42695615201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-29 | 1619321 | 1619321 | 1588249 | 0 | 0 | 1566711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1588249 | 1566711 | -21538 | 1991520
3 | T3497 | 43178715201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-02-24 | 439154 | 441637 | 406769 | 2483.01 | 0 | 406424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406769 | 406424 | -345 | 385977
3 | T3513 | 43077815201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 742276 | 740169 | 725008 | -2107.01 | 0 | 725004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 725008 | 725004 | -4 | 757262
3 | T3514 | 43078115201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-07-29 | 3802689 | 3802689 | 3624193 | 0 | 0 | 3479143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3624193 | 3479143 | -145050 | 4144190
3 | T3515 | 43090835201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2014-08-27 | 8076272 | 8066272 | 8349102 | -10000 | 0 | 7667982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8349102 | 7667982 | -681120 | 8827285
3 | T3516 | 42874115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 664504 | 664504 | 636000 | 0 | 0 | 636000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636000 | 636000 | 0 | 599580 | B0 | ACC - LUMP SUM
3 | T3519 | 42986115201 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2016-12-07 | 79117 | 79117 | 68771 | 0 | 0 | 68771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68771 | 68771 | 0 | 104519
3 | T3539 | 22243945201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-06-17 | 1948263 | 1965454 | 2004975 | 17191.7 | 0 | 2004975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004975 | 2004975 | 0 | 1870760
3 | T3544 | 43090825201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 9957902 | 10174090 | 10291533 | 216187.5 | -52780 | 9419099 | -52780 | 0 | 0 | 0 | 0 | 0 | -52780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -52780 | 10238753 | 9419099 | -819655 | 12349087
3 | T3548 | 43079315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 1961731 | 1961731 | 1976693 | 0 | 0 | 1976488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1976693 | 1976488 | -205 | 2269438
3 | T3551 | 42873915201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 2525492 | 2696693 | 2810548 | 171200.34 | -29132 | 2626488 | -20132 | 0 | 0 | 0 | 0 | -9000 | -29132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29132 | 2781416 | 2626488 | -154929 | 3044222
3 | T3552 | 43273715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-07-29 | 3670000 | 3738760 | 3752339 | 68759.59 | -5200 | 3623993 | 0 | 0 | 0 | 0 | 0 | -5200 | -5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5200 | 3747139 | 3623993 | -123146 | 4236500
3 | T3556 | 43253715201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 6785910 | 6785910 | 7196007 | 0 | 0 | 7198436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7196007 | 7198436 | 2429 | 7266475
3 | T3558 | 43274115201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2015-09-30 | 3745728 | 3745728 | 3536653 | 0 | 0 | 3415843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3536653 | 3415843 | -120811 | 4720446
3 | T3560 | 42461815201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-01-27 | 1870023 | 1848237 | 1748528 | -21786.33 | 0 | 1735931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1748528 | 1735931 | -12597 | 2060779
3 | T3572 | 43014825201 | F593289030 | DOWDY PLUMBING CORPORATION | N/A | N/A | N/A | N/A | 2016-05-25 | 411660 | 421660 | 407116 | 10000 | 0 | 407116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407116 | 407116 | 0 | 427171
3 | T3589 | 43174315201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-03-30 | 169047 | 169047 | 169047 | 0 | 0 | 169047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169047 | 169047 | 0 | 199840 | B0 | ACC - LUMP SUM
3 | T3595 | 43551835201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-07-27 | 513855 | 503120 | 496536 | -10734.35 | 0 | 496536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496536 | 496536 | 0 | 447907 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
3 | T3606 | 43187515201 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 1097017 | 1097017 | 1126422 | 0 | 0 | 1126611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126422 | 1126611 | 189 | 1355921
3 | T9009 | 43035625201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2015-06-24 | 1500230 | 1500230 | 1507255 | 0 | 0 | 1507255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507255 | 1507255 | 0 | 1868903
4 | E4N30 | 23071725201 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2013-02-06 | 7998765 | 10990699 | 10941188 | 2991934.22 | 0 | 10875104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10941188 | 10875104 | -66084 | 7310237 | A3:Y:A:Y::Y::Y::Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
4 | E4P11 | 43330115201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2014-05-07 | 7982486 | 8060089 | 7966495 | 77602.88 | 0 | 7966495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7966495 | 7966495 | 0 | 10491582 | A3:Y:A:Y::Y::Y::Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT
4 | E4P15 | 43270715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2014-04-30 | 6920878 | 6931376 | 6809928 | 10498.44 | -232272 | 6347977 | -232272 | 0 | 0 | 0 | 0 | 0 | -232272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -232272 | 6577656 | 6347977 | -229679 | 6902574 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4P38 | 43270415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-05-28 | 21920100 | 21827650 | 21748676 | -92449.95 | 0 | 19468244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21748676 | 19468244 | -2280432 | 20025810 | B8:Y:B:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4P79 | 42593515201 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-04-23 | 7765532 | 7903357 | 8161146 | 137825.56 | 321600 | 8149687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 0 | 0 | 0 | 0 | 111600 | 321600 | 321600 | 8482746 | 8149687 | -333059 | 7456672 | B3:B5 | ACC - LANE RENTAL:ACC - INCENTIVE/DISINCENTIVE
4 | E4P94 | 43368845201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2014-05-02 | 11791416 | 13321296 | 13475252 | 1529880.42 | 470000 | 13368481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470000 | 0 | 0 | 0 | 0 | 0 | 470000 | 470000 | 13945252 | 13368481 | -576771 | 12152859 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE
4 | E4P95 | 42131415201 | F262618462 | COBALT CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2014-07-11 | 1812600 | 2451083 | 2583183 | 638483.01 | 0 | 2583183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2583183 | 2583183 | 0 | 1882511
4 | E4P98 | 42605315201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-02-06 | 1670723 | 1694884 | 1701995 | 24161.58 | 0 | 1740331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1701995 | 1740331 | 38336 | 1844041
4 | E4Q22 | 42990515201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-12-19 | 5750000 | 6072503 | 6142459 | 322502.98 | 0 | 6141649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6142459 | 6141649 | -810 | 6522411 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4Q70 | 43056615201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2015-04-03 | 594927 | 594927 | 563713 | 0 | 0 | 563713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563713 | 563713 | 0 | 789528
4 | E4Q82 | 43056715201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2015-03-06 | 2188629 | 2163534 | 2089683 | -25094.26 | 0 | 2076611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2089683 | 2076611 | -13073 | 2260658
4 | E4R08 | 43115215201 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 1435007 | 1449407 | 1163642 | 14400 | 0 | 1155244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163642 | 1155244 | -8398 | 1565107
4 | E4R33 | 43059015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-03-04 | 1637760 | 1638489 | 1537659 | 729.3 | 0 | 1540807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1537659 | 1540807 | 3148 | 1735050
4 | E4R44 | 43061715201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2016-04-01 | 1182414 | 1176116 | 1146902 | -6297.56 | 0 | 1148631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146902 | 1148631 | 1729 | 670123
4 | E4R47 | 42840015201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2015-12-04 | 281874 | 281874 | 265427 | 0 | 0 | 265427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265427 | 265427 | 0 | 248191
4 | E4R52 | 43399815201 | F462088820 | INTERSTATE CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-12-04 | 447523 | 483523 | 445843 | 36000 | 0 | 445875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445843 | 445875 | 32 | 628945
4 | E4R65 | 43538615201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-01-08 | 593859 | 593859 | 535917 | 0 | 0 | 540661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535917 | 540661 | 4743 | 495318
4 | T4341 | 23073015201 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2013-02-06 | 6592014 | 6833204 | 6617553 | 241190.16 | 0 | 6330385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6617553 | 6330385 | -287168 | 7354584
4 | T4356 | 42286615201 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 9484806 | 10082799 | 10383603 | 597992.35 | 0 | 10314411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10383603 | 10314411 | -69192 | 10825487
4 | T4367 | 23072415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 3396284 | 4218679 | 4018129 | 822394.66 | 0 | 3882269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4018129 | 3882269 | -135861 | 3663892
4 | T4376 | 42701215201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-07-29 | 4137540 | 4285354 | 4224921 | 147813.49 | 0 | 4063258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4224921 | 4063258 | -161663 | 4993225
4 | T4389 | 23097825201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2014-04-30 | 15715809 | 15753499 | 15520925 | 37690.07 | 630700 | 14964924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630700 | 0 | 0 | 0 | 0 | 0 | 630700 | 630700 | 16151625 | 14964924 | -1186702 | 15839218 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4396 | 42873215201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-07-29 | 3226208 | 3268117 | 3297315 | 41909.23 | 0 | 3205408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3297315 | 3205408 | -91907 | 3538927
4 | T4402 | 42973715201 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2014-07-30 | 2824000 | 2824000 | 2773850 | 0 | 0 | 2779467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2773850 | 2779467 | 5617 | 3519184 | B0 | ACC - LUMP SUM
4 | T4406 | 42872615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-12-03 | 3869297 | 3899697 | 3754820 | 30400 | 0 | 3632165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3754820 | 3632165 | -122655 | 3716758
4 | T4411 | 43472615201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 1298981 | 1298981 | 1226359 | 0 | 0 | 1217254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226359 | 1217254 | -9105 | 1277355
4 | T4415 | 43472315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 1247191 | 1247191 | 1236940 | 0 | 0 | 1236940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236940 | 1236940 | 0 | 1184119
4 | T4416 | 43171715201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 1444863 | 1444863 | 1398240 | 0 | 0 | 1398240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398240 | 1398240 | 0 | 1613354
4 | T4417 | 43400715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2015-05-20 | 590398 | 600523 | 561695 | 10124.92 | 0 | 561695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561695 | 561695 | 0 | 743748
4 | T4420 | 43059515201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-06-17 | 1707658 | 1707658 | 1691828 | 0 | 0 | 1691828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1691828 | 1691828 | 0 | 1786379
4 | T4421 | 42802415201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2015-10-28 | 655175 | 655175 | 640299 | 0 | 0 | 640223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640299 | 640223 | -76 | 662184
4 | T4426 | 43060815201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2016-02-24 | 1295575 | 1295575 | 1275925 | 0 | 0 | 1275925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275925 | 1275925 | 0 | 1142628 | B0 | ACC - LUMP SUM
4 | T4427 | 43490215201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2016-04-27 | 800000 | 800000 | 773213 | 0 | 0 | 773213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773213 | 773213 | 0 | 918090
4 | T4430 | 43509615201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 369071 | 369071 | 326639 | 0 | 0 | 326642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326639 | 326642 | 3 | 392823
4 | T4431 | 43509315201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2016-03-30 | 249966 | 262302 | 239047 | 12335.72 | 0 | 239047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239047 | 239047 | 0 | 216196
4 | T4432 | 43509115201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2016-03-30 | 462595 | 462595 | 438863 | 0 | 0 | 438863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438863 | 438863 | 0 | 406505
5 | E5W67 | 43198915201 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2014-10-07 | 2340785 | 2247902 | 2197902 | -92883 | -92326 | 2104471 | -92326 | 0 | 0 | 0 | 0 | 0 | -92326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92326 | 2105576 | 2104471 | -1105 | 2486510
5 | E5W83 | 43528215201 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-04-07 | 2750721 | 2750721 | 2676098 | 0 | 0 | 2676025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2676098 | 2676025 | -73 | 2985731
5 | E5W86 | 43488315201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-04 | 584110 | 585291 | 580591 | 1181.19 | 0 | 580591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580591 | 580591 | 0 | 623549
5 | E5Y02 | 43705815201 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2015-09-01 | 783941 | 783941 | 744941 | 0 | 0 | 744941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 744941 | 744941 | 0 | 821518
5 | E5Y03 | 43116415201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2016-02-02 | 63940 | 63940 | 58289 | 0 | 0 | 58289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58289 | 58289 | 0 | 123170
5 | E5Y04 | 43705715201 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-01-05 | 679709 | 679709 | 640622 | 0 | 0 | 640622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640622 | 640622 | 0 | 911256
5 | E5Y05 | 43465915201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-01-05 | 448115 | 448115 | 434061 | 0 | 0 | 434061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434061 | 434061 | 0 | 409596
5 | E5Y07 | 43693615201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-01-05 | 2962958 | 2962958 | 2820404 | 0 | 0 | 2820425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2820404 | 2820425 | 21 | 2456435
5 | E5Y18 | 23800235225 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-02-02 | 788000 | 805272 | 758781 | 17271.51 | 0 | 759356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 758781 | 759356 | 575 | 717566
5 | E5Y28 | 43750125201 | F591625608 | SANTA CRUZ CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-05-03 | 236798 | 236798 | 194703 | 0 | 0 | 194703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194703 | 194703 | 0 | 335841
5 | E5Y38 | 43781715201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-06-07 | 293265 | 294576 | 286101 | 1310.87 | 0 | 284790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286101 | 284790 | -1311 | 406745
5 | E5Y41 | 43781615201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-06-07 | 151151 | 151151 | 134927 | 0 | 0 | 134927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134927 | 134927 | 0 | 237416
5 | E5Y49 | 43939215201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-05-25 | 1927830 | 2083244 | 2054804 | 155413.53 | 100000 | 2041547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 2154804 | 2041547 | -113257 | 1351307 | A3:B5:LBDB | ICC - DESIGN/BUILD - MINOR:ACC - INCENTIVE/DISINCENTIVE:LOW BID DESIGN BUILD
5 | T5415 | 40735535201 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2012-05-23 | 32798973 | 35176946 | 35231745 | 2796919.19 | -161575 | 34680971 | -161575 | 0 | 0 | 0 | 0 | 0 | -161575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -161575 | 35070170 | 34680971 | -389199 | 37106690
5 | T5486 | 23871915201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-02-26 | 12324444 | 12887259 | 13204280 | 562814.56 | 0 | 11961836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13204280 | 11961836 | -1242443 | 17116715 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
5 | T5496 | 43106615201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2014-05-21 | 4198661 | 4198661 | 4290920 | 0 | 0 | 4280333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4290920 | 4280333 | -10587 | 5833244
5 | T5497 | 43113915201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2014-06-18 | 5577400 | 5630674 | 5316503 | 53274.46 | 0 | 5110931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5316503 | 5110931 | -205572 | 5261132 | B0:B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
5 | T5504 | 43326915201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-02-25 | 2791824 | 2791824 | 2764770 | 0 | 0 | 2763716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2764770 | 2763716 | -1054 | 3681477
5 | T5507 | 42908315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-10-29 | 13950000 | 14304220 | 14416417 | 354219.83 | 0 | 13250583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14416417 | 13250583 | -1165834 | 13411584
5 | T5515 | 43066815201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-02-25 | 1884019 | 1929335 | 1919435 | 45316.44 | 0 | 1875340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919435 | 1875340 | -44095 | 1716624 | B0 | ACC - LUMP SUM
5 | T5519 | 43066615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-07-29 | 2698908 | 2698908 | 2560594 | 0 | 0 | 2513289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560594 | 2513289 | -47305 | 2488176
5 | T5524 | 43065215201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 4938000 | 5043475 | 4946856 | 105475.47 | 0 | 4688330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4946856 | 4688330 | -258527 | 4676397
5 | T5528 | 43066915201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2015-05-27 | 2181000 | 2446253 | 2396253 | 265252.96 | 0 | 2380075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2396253 | 2380075 | -16178 | 1883279
5 | T5531 | 42821325202 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 3499000 | 3559000 | 3541158 | 60000 | 0 | 3541158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3541158 | 3541158 | 0 | 4392676
5 | T5536 | 43067715201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 2584884 | 2614884 | 2636650 | 30000 | 0 | 2540033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2636650 | 2540033 | -96617 | 2795914
5 | T5537 | 43244215201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2015-09-30 | 1272760 | 1272760 | 1267646 | 0 | 0 | 1267646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267646 | 1267646 | 0 | 919590 | B0 | ACC - LUMP SUM
5 | T5540 | 43544615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 2108960 | 2108960 | 2062184 | 0 | 0 | 2062184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2062184 | 2062184 | 0 | 2665357
5 | T5541 | 43241215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-10-28 | 894822 | 894822 | 858557 | 0 | 0 | 860505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 858557 | 860505 | 1948 | 813974
5 | T5542 | 43245515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 6389000 | 6541385 | 6525238 | 152385.41 | -8241 | 6292502 | 0 | 0 | 0 | 0 | 0 | -8241 | -8241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8241 | 6516997 | 6292502 | -224496 | 7834176
5 | T5543 | 43366515201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2015-10-28 | 408828 | 408828 | 402408 | 0 | 0 | 402408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402408 | 402408 | 0 | 373627
5 | T5545 | 43065615201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-10-28 | 1793084 | 1837115 | 1743748 | 44031.49 | 0 | 1747584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1743748 | 1747584 | 3836 | 1806322
5 | T5550 | 43245315201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-02-24 | 4609815 | 4482913 | 4406263 | -126902.29 | 0 | 4397650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4406263 | 4397650 | -8613 | 4516602
5 | T5560 | 43244115201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 2552654 | 2632050 | 2628965 | 79396.19 | 0 | 2624607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2628965 | 2624607 | -4358 | 2570277
5 | T5561 | 43474115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 2191000 | 2191000 | 2106346 | 0 | 0 | 2116636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2106346 | 2116636 | 10290 | 2517053
5 | T5577 | 43544615202 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 2212434 | 2222354 | 2157683 | 9920 | 0 | 2157683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157683 | 2157683 | 0 | 2655161
6 | E6H77 | 41806525201 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2013-07-16 | 6865432 | 8047242 | 8106870 | 1181810.07 | 525000 | 8012338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 525000 | 525000 | 8631870 | 8012338 | -619532 | 9650623 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
6 | E6I74 | 43119315201 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2014-11-20 | 3722164 | 3772164 | 4008665 | 50000 | 0 | 4008622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4008665 | 4008622 | -43 | 3636115
6 | E6I84 | 42560065201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-11-19 | 4769021 | 4787530 | 4658702 | 18508.49 | 100000 | 4637845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 4758702 | 4637845 | -120857 | 4440862 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6I89 | 43117815201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2014-10-30 | 2097039 | 2147039 | 2148203 | 50000 | 0 | 2008021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2148203 | 2008021 | -140182 | 2334024
6 | E6I91 | 42918715201 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2015-06-11 | 1483128 | 1483128 | 1441455 | 0 | 0 | 1430102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1441455 | 1430102 | -11353 | 1376236
6 | E6I96 | 25023475201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-04-30 | 2344175 | 2344175 | 2268222 | 0 | 0 | 2254238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2268222 | 2254238 | -13984 | 2475261
6 | E6I98 | 43493065201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-03-31 | 969000 | 903732 | 873748 | -65268.21 | 0 | 873360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 873748 | 873360 | -388 | 1134223 | B0 | ACC - LUMP SUM
6 | E6J31 | 41247385201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-10-29 | 928836 | 853946 | 790776 | -74890.65 | 0 | 790197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790776 | 790197 | -578 | 879056
6 | E6J90 | 41774089201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2015-09-23 | 3017017 | 3017017 | 2967017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2967017 | 0 | -2967017 | 3290000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
6 | T6127 | 25118515201 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2011-09-07 | 58542945 | 59378958 | 60313959 | 836012.85 | 0 | 59818042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60313959 | 59818042 | -495917 | 67023599
6 | T6290 | 24991115201 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2012-12-05 | 31967610 | 38766907 | 37791470 | 6799296.61 | 2100000 | 37602287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 0 | 1000000 | 0 | 0 | 0 | 2100000 | 2100000 | 39891470 | 37602287 | -2289183 | 27939576 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6320 | 42914015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 14295524 | 14692214 | 13690377 | 396690.11 | 245000 | 13056864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 0 | 245000 | 245000 | 13935377 | 13056864 | -878513 | 15289320 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6325 | 25055425201 | F410827177 | JOHNSON BROS. CORPORATION | N/A | N/A | N/A | N/A | 2012-10-31 | 11430054 | 11749528 | 11929942 | 319473.2 | 0 | 11924070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11929942 | 11924070 | -5871 | 12087502
6 | T6328 | 42745215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2014-04-30 | 8067382 | 8176995 | 8097390 | 109612.99 | 300000 | 7946905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 8397390 | 7946905 | -450485 | 8580766 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6365 | 43274315201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 3849469 | 3927103 | 3942847 | 77633.87 | 0 | 3837692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3942847 | 3837692 | -105154 | 4708188 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6371 | 42913415201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-04-29 | 1483369 | 1483369 | 1429074 | 0 | 0 | 1425704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429074 | 1425704 | -3370 | 1435508
6 | T6372 | 43345115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 1089885 | 1078983 | 1060465 | -10901.99 | 0 | 1060465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060465 | 1060465 | 0 | 1129001 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
6 | T6373 | 43080915201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-02-25 | 2376742 | 2426742 | 2460615 | 50000 | 0 | 2384892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2460615 | 2384892 | -75723 | 2292102
6 | T6374 | 43118015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 5144045 | 5317082 | 5198829 | 173037.48 | 0 | 5112224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5198829 | 5112224 | -86605 | 4599363
6 | T6376 | 43081715201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-02-25 | 6621887 | 6805679 | 6261293 | 183792.64 | 470000 | 6082074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0 | 20000 | 0 | 470000 | 470000 | 6731293 | 6082074 | -649219 | 6429680 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6379 | 42934515201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 2622038 | 2613142 | 2527516 | -8895.6 | 150000 | 2524953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 2677516 | 2524953 | -152563 | 3493513 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6381 | 43349015201 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 762732 | 762732 | 718865 | 0 | 0 | 721234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718865 | 721234 | 2369 | 854447
6 | T6384 | 43350815201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2015-09-30 | 439934 | 439934 | 417205 | 0 | 0 | 417205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417205 | 417205 | 0 | 559680 | B0 | ACC - LUMP SUM
6 | T6386 | 43349315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 648209 | 648209 | 638650 | 0 | 0 | 605828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638650 | 605828 | -32822 | 711332
6 | T6389 | 43481015201 | F273954210 | PE-SERVICES L.L.C. | N/A | N/A | N/A | N/A | 2016-01-27 | 147742 | 147742 | 141841 | 0 | 0 | 141841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141841 | 141841 | 0 | 180124 | B0 | ACC - LUMP SUM
6 | T6393 | 24961585201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 17726000 | 17726000 | 17439683 | 0 | 670000 | 16969633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 70000 | 0 | 670000 | 670000 | 18109683 | 16969633 | -1140050 | 20932157 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6394 | 24961575201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 18918175 | 18918175 | 18379697 | 0 | 740000 | 17983880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660000 | 0 | 0 | 0 | 80000 | 0 | 740000 | 740000 | 19119697 | 17983880 | -1135817 | 23196102 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6395 | 24961555201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 18870198 | 19070198 | 19250284 | 200000 | 1120000 | 19024190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 120000 | 0 | 1120000 | 1120000 | 20370284 | 19024190 | -1346095 | 22322899 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6396 | 24961525201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-05-20 | 26227745 | 26488959 | 26988041 | 261213.58 | 1130000 | 26175164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020000 | 0 | 0 | 0 | 110000 | 0 | 1130000 | 1130000 | 28118041 | 26175164 | -1942877 | 34221350 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6402 | 43631315201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 249950 | 249950 | 228758 | 0 | 0 | 228758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228758 | 228758 | 0 | 332196
7 | E7F75 | 25839855201 | F453806780 | SKANSKA-AJAX PAVING JOINT VENTU | N/A | N/A | N/A | N/A | 2012-05-08 | 215400000 | 224435209 | 224895976 | 9035209.03 | 1650000 | 223875000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650000 | 0 | 0 | 0 | 1650000 | 1650000 | 226545976 | 223875000 | -2670976 | 213872600 | B11:B12:B8:B:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - DSGN BLD-MAJ/BONUS/WRNTY:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
7 | E7I30 | 41101425201 | F940519552 | GRANITE CONSTRUCTION COMPANY OF CALIFORN | N/A | N/A | N/A | N/A | 2013-10-29 | 45811000 | 47224425 | 47268962 | 1413424.65 | 0 | 46074212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47268962 | 46074212 | -1194751 | 47778700 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7I34 | 41101135201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-01-23 | 35188969 | 35441051 | 35414850 | 252081.91 | 0 | 34061551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35414850 | 34061551 | -1353299 | 37368154 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | E7I46 | 25633925201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-08-14 | 15944000 | 16474127 | 16294835 | 530127.11 | 0 | 15360010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16294835 | 15360010 | -934824 | 18310419 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD
7 | E7I70 | 42550015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-05-14 | 10449830 | 11043877 | 11011337 | 594047.42 | 0 | 10279911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11011337 | 10279911 | -731426 | 11723000 | B0 | ACC - LUMP SUM
7 | E7I76 | 42900015201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-06-11 | 11107156 | 11770977 | 11963122 | 663821.01 | 0 | 11588757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11963122 | 11588757 | -374365 | 11550400
7 | E7J99 | 42715515201 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2015-04-08 | 1844400 | 1881240 | 1852163 | 36840.35 | 0 | 1792416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1852163 | 1792416 | -59746 | 1650000
7 | E7K01 | 43070715201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-02-11 | 2815000 | 2850595 | 2883182 | 35595.29 | 0 | 2883115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2883182 | 2883115 | -66 | 2338000
7 | E7K02 | 43090115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-02-11 | 2683100 | 2806747 | 2817266 | 123647.22 | 0 | 2772695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2817266 | 2772695 | -44571 | 2450000 | B0 | ACC - LUMP SUM
7 | E7K04 | 43066015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-03-11 | 2680382 | 2750471 | 2763085 | 70089.15 | 0 | 2699178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2763085 | 2699178 | -63907 | 2007403 | B0 | ACC - LUMP SUM
7 | E7K05 | 43243225201 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2015-03-11 | 1086230 | 1086230 | 1062839 | 0 | 0 | 1062824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062839 | 1062824 | -15 | 1230200
7 | E7K06 | 42905615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-06-30 | 4138392 | 4373349 | 4094400 | 234956.87 | 0 | 4010129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4094400 | 4010129 | -84271 | 3911400
7 | E7K07 | 43068515201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2015-06-10 | 1119020 | 1119020 | 1092543 | 0 | 0 | 1092543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1092543 | 1092543 | 0 | 885300 | B0 | ACC - LUMP SUM
7 | E7K17 | 43094815201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-06-10 | 2888000 | 2888000 | 2727932 | 0 | 0 | 2690622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2727932 | 2690622 | -37311 | 3200000 | B0 | ACC - LUMP SUM
7 | E7K29 | 42550325201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2015-05-13 | 1984295 | 1984295 | 1950400 | 0 | 0 | 1950400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1950400 | 1950400 | 0 | 1727700
7 | E7K67 | 43149515201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-05-13 | 2794895 | 2964710 | 2918290 | 169814.53 | -7200 | 2905726 | 0 | 0 | 0 | 0 | 0 | -7200 | -7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7200 | 2911090 | 2905726 | -5363 | 1905000
7 | E7K68 | 43149115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-05-13 | 4031039 | 4044189 | 4055974 | 13150.2 | 0 | 4004687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4055974 | 4004687 | -51286 | 3361350
7 | E7K76 | 43070625201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-12-09 | 2114910 | 2114910 | 2214302 | 0 | 0 | 2214502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2214302 | 2214502 | 200 | 2723400
7 | E7K78 | 43080235201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2015-09-09 | 1271000 | 1271000 | 1221000 | 0 | 0 | 1221000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221000 | 1221000 | 0 | 2206022 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
7 | E7K80 | 43478115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-08-12 | 1052289 | 1092289 | 992268 | 40000 | 0 | 991427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992268 | 991427 | -840 | 752249
7 | E7K84 | 43070615201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2015-10-14 | 2060672 | 2060672 | 1940979 | 0 | 0 | 1940979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940979 | 1940979 | 0 | 2481000
7 | E7K88 | 43071015201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-01-13 | 716889 | 655243 | 627243 | -61645.9 | 0 | 627243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627243 | 627243 | 0 | 590500 | B0 | ACC - LUMP SUM
7 | E7K89 | 42905915201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-03-09 | 2078378 | 2078378 | 1941350 | 0 | -25400 | 1919022 | 0 | 0 | 0 | 0 | 0 | -25400 | -25400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25400 | 1915950 | 1919022 | 3072 | 2100000 | B0 | ACC - LUMP SUM
7 | E7K90 | 43386615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-02-10 | 795744 | 795744 | 787111 | 0 | 0 | 787111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787111 | 787111 | 0 | 455000 | B0 | ACC - LUMP SUM
7 | E7K92 | 42749515201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-06-08 | 377368 | 396118 | 378995 | 18750 | 0 | 378995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378995 | 378995 | 0 | 201276 | B0 | ACC - LUMP SUM
7 | E7K93 | 42749615201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-01-13 | 429380 | 432555 | 431202 | 3174.92 | 0 | 431202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431202 | 431202 | 0 | 252301 | B0 | ACC - LUMP SUM
7 | E7K94 | 42750115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-02-10 | 652140 | 665253 | 647487 | 13112.99 | 0 | 647487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647487 | 647487 | 0 | 350000 | B0 | ACC - LUMP SUM
7 | E7K96 | 42896915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-03-31 | 2176471 | 2176471 | 2177273 | 0 | 0 | 2177273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177273 | 2177273 | 0 | 1980000 | B0 | ACC - LUMP SUM
7 | E7K99 | 43625515201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-03-09 | 160902 | 182550 | 178425 | 21648 | 0 | 178425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178425 | 178425 | 0 | 165500 | B0 | ACC - LUMP SUM
7 | E7L02 | 43472915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-06-08 | 2090000 | 2090000 | 2025548 | 0 | 0 | 2025548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025548 | 2025548 | 0 | 1628500 | B0 | ACC - LUMP SUM
7 | E7L07 | 43258315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-11-12 | 1115377 | 1115377 | 1056390 | 0 | 0 | 1056390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056390 | 1056390 | 0 | 1450000 | B0 | ACC - LUMP SUM
7 | E7L29 | 42717125201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-06-08 | 567079 | 567079 | 554076 | 0 | 0 | 554076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554076 | 554076 | 0 | 490000 | B0 | ACC - LUMP SUM
7 | E7L38 | 43936215201 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2016-06-08 | 281697 | 282895 | 265516 | 1198.59 | 0 | 265516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265516 | 265516 | 0 | 275000
7 | E7L40 | 43940015201 | F270559642 | CITY WIDE PAVING LLC | N/A | N/A | N/A | N/A | 2016-07-13 | 142928 | 142928 | 136015 | 0 | 0 | 136015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136015 | 136015 | 0 | 150000
7 | T7209 | 25841515201 | F263258515 | PCL/ARCHER WESTERN A JOINT VEN | N/A | N/A | N/A | N/A | 2009-09-16 | 389463750 | 430319761 | 437468272 | 40856010.73 | 0 | 439424048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437468272 | 439424048 | 1955776 | 412328910 | ARRA:B2:B5:P:B2 | AMERICAN RECOVERY AND REINVEST:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:PUBLIC PRIVATE PARTNERSHIP:ACC - A+B (COST+TIME BIDDING)
7 | T7236 | 25589325201 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2011-09-28 | 7147510 | 7510715 | 7761739 | 363204.75 | -452520 | 7308427 | -452520 | 0 | 0 | 0 | 0 | 0 | -452520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -452520 | 7309219 | 7308427 | -793 | 8423805
7 | T7269 | 40845945201 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2010-12-08 | 22517641 | 23804461 | 24257673 | 1286819.77 | -2893316 | 22393675 | -2893316 | 0 | 0 | 0 | 0 | 0 | -2893316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2893316 | 21364357 | 22393675 | 1029318 | 23500000
7 | T7298 | 25866025201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2012-02-08 | 29974786 | 31148108 | 30989158 | 1173322.09 | -35000 | 30930903 | 0 | 0 | 0 | 0 | 0 | -35000 | -35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35000 | 30954158 | 30930903 | -23256 | 24953780
7 | T7305 | 41886065201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2012-06-20 | 27994444 | 28571829 | 28922186 | 577384.54 | 187000 | 28487362 | 0 | 0 | 0 | 0 | 0 | -13000 | -13000 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 187000 | 29109186 | 28487362 | -621825 | 26994097 | B1 | ACC - NO EXCUSE BONUS
7 | T7309 | 25714715201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2012-09-26 | 20511016 | 21458828 | 20369299 | 947812.13 | 0 | 20020139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20369299 | 20020139 | -349160 | 20045000
7 | T7311 | 25579315201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2013-05-31 | 21435705 | 23015417 | 23090810 | 1579712.31 | -8000 | 22674547 | 0 | 0 | 0 | 0 | 0 | -8000 | -8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8000 | 23082810 | 22674547 | -408263 | 21961490
7 | T7326 | 43304615201 | F593374298 | EMPOWER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 259624 | 259624 | 242742 | 0 | 0 | 242742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242742 | 242742 | 0 | 272600
7 | T7331 | 42896215201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 10973861 | 11371382 | 11571904 | 397520.71 | 0 | 11452952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11571904 | 11452952 | -118952 | 9940198
7 | T7345 | 25699525201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2014-04-30 | 4872870 | 6561188 | 6362566 | 1688318.56 | 0 | 6238967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6362566 | 6238967 | -123598 | 7433777
7 | T7348 | 42907415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2014-06-18 | 13220362 | 13351863 | 13162187 | 131500.82 | 0 | 12814384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13162187 | 12814384 | -347802 | 12277372
7 | T7356 | 42905815201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 6377897 | 6518755 | 6488848 | 140857.94 | 0 | 6241174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6488848 | 6241174 | -247674 | 6176900
7 | T7362 | 42907725202 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2015-03-25 | 5709404 | 5709404 | 5625130 | 0 | 0 | 5464793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5625130 | 5464793 | -160337 | 5660000
7 | T7364 | 43311115201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 1656000 | 1660046 | 1621270 | 4045.76 | 0 | 1621270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1621270 | 1621270 | 0 | 1539800 | B0 | ACC - LUMP SUM
7 | T7365 | 43090015201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2015-05-20 | 3669419 | 3856675 | 3844686 | 187256.11 | 0 | 3746837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3844686 | 3746837 | -97849 | 3925150 | B0 | ACC - LUMP SUM
7 | T7366 | 43113215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-04-29 | 1795000 | 1795000 | 1754140 | 0 | 0 | 1746653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754140 | 1746653 | -7487 | 1415000 | B0 | ACC - LUMP SUM
7 | T7367 | 42907615201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 3822222 | 3834124 | 3855324 | 11901.75 | 0 | 3731807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3855324 | 3731807 | -123517 | 4100000
7 | T7368 | 42421315201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 4471471 | 4471471 | 4410937 | 0 | 0 | 4410891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4410937 | 4410891 | -46 | 5267432
7 | T7370 | 43251915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-08-26 | 3088818 | 3088818 | 2944540 | 0 | 0 | 2940006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2944540 | 2940006 | -4534 | 3068000
7 | T7371 | 43089915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 10094563 | 10178653 | 10186112 | 84089.39 | 0 | 10014564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10186112 | 10014564 | -171548 | 10547227 | B0 | ACC - LUMP SUM
7 | T7372 | 43260715201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-01-27 | 3371083 | 3375146 | 3271033 | 4062.87 | 0 | 3261114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3271033 | 3261114 | -9919 | 2100000 | B0 | ACC - LUMP SUM
7 | T7373 | 43131515201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2015-09-30 | 6275807 | 6350807 | 6400500 | 75000 | 0 | 6232156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400500 | 6232156 | -168344 | 7740000
7 | T7374 | 43257915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 3581528 | 3581528 | 3666189 | 0 | 220000 | 3671670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 220000 | 220000 | 3886189 | 3671670 | -214519 | 2950000 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
7 | T7378 | 43149615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 4821342 | 4867138 | 4900357 | 45796.52 | 0 | 4881384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4900357 | 4881384 | -18972 | 4555000
7 | T9014 | 43482515201 | F030586197 | R.M. WILLIAMS CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 888715 | 888715 | 871541 | 0 | 0 | 871545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 871541 | 871545 | 3 | 826928
8 | E8M60 | 43127515201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2013-01-22 | 56648757 | 57438075 | 57810006 | 789318 | 0 | 57069148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57810006 | 57069148 | -740858 | 56376202
8 | E8M62 | 40615115201 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2013-02-26 | 46046392 | 46822521 | 47408243 | 776128.95 | -137490 | 46013135 | -137490 | 0 | 0 | 0 | 0 | 0 | -137490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -137490 | 47270753 | 46013135 | -1257618 | 51466144 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8M63 | 40615215201 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-02-05 | 57400000 | 57854468 | 58114118 | 454468.05 | -10000 | 57193979 | 0 | 0 | 0 | 0 | 0 | -10000 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 58104118 | 57193979 | -910139 | 59063480
8 | E8N60 | 41546265201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-05-20 | 10628174 | 10702005 | 10703365 | 73831.12 | -6500 | 10548835 | 0 | 0 | 0 | 0 | 0 | -6500 | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 10696865 | 10548835 | -148030 | 9781121
8 | E8N68 | 24301715201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2014-06-09 | 16844000 | 17989634 | 18429954 | 1145634.02 | -3000 | 17949122 | 0 | 0 | 0 | 0 | 0 | -3000 | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 18426954 | 17949122 | -477832 | 15034153
8 | E8P54 | 43110015201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2015-10-20 | 1369271 | 1355607 | 1258468 | -13663.94 | 0 | 1224485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258468 | 1224485 | -33984 | 1662320
8 | E8P55 | 43561715201 | F203908361 | MIDASCO LLC | N/A | N/A | N/A | N/A | 2015-06-16 | 1736149 | 1766298 | 1678250 | 30148.52 | -26500 | 1651060 | 0 | 0 | 0 | 0 | 0 | -26500 | -26500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26500 | 1651750 | 1651060 | -690 | 1991672
8 | E8Q15 | 43753215201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2016-10-18 | 318543 | 301705 | 250071 | -16837.14 | 0 | 250071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250071 | 250071 | 0 | 796207

## Sheet1 (hidden)
01CO | 01 | T1468 | 19753425201 | 2012-05-23 | QTR4 | 11/12 | 2 | 16 | 650 | 755 | 755 | 0 | 0 | 0 | 81 | 24 | 14242918 | 150000 | 14092918 | 15688629 | 15514205 | 0 | 0 | 0 | 15514205 | 15463127 | -51078 | 1445710 | 64 | 0 | 14 | 850509 | 0 | 0 | 0 | 96860 | 6298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 501609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1450956 | 6298 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-01-03 | QTR3 | 16/17 | 2014-10-04 | QTR2 | 14/15 | 108 | 14155367.4 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO | 37 | 01co | 1 | 37
01CO | 01 | T1552 | 40631475201 | 2013-09-25 | QTR1 | 13/14 | 1 | 0 | 150 | 164 | 200 | -36 | 36 | 0 | 10 | 4 | 2579468 | 50000 | 2529468 | 2579468 | 2493565 | -85464 | 0 | -85464 | 2408101 | 2408101 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | F381884765 | CONTI CORPORATION | N/A | N/A | N/A | N/A | 2016-12-14 | QTR2 | 16/17 | 2014-09-12 | QTR1 | 14/15 | 115 | 3076291.38 |  |  | 4 | 3 | 0 | 0 | 0 | 0 |  | CO | 15 | 01do | 38 | 52
01CO | 01 | T1560 | 42910115201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 250 | 268 | 268 | 0 | 0 | 0 | 18 | 0 | 4883160 | 57482 | 4825678 | 4883160 | 4742567 | 0 | 0 | 0 | 4742567 | 4581604 | -160964 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 | 2016-08-08 | QTR1 | 16/17 | 118 | 5451824.59 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO | 28 | 02co | 53 | 80
01CO | 01 | T1577 | 42919915201 | 2013-12-04 | QTR2 | 13/14 | 1 | 2 | 80 | 105 | 214 | -109 | 109 | 0 | 4 | 21 | 149236 | 0 | 149236 | 153020 | 93123 | 0 | 0 | 0 | 93123 | 87604 | -5519 | 3784 | 2 | 0 | 21 | 3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 3784 | 0 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-04-25 | QTR4 | 16/17 | 2014-12-04 | QTR2 | 14/15 | 108 | 204084.47 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO | 16 | 02do | 81 | 96
01CO | 01 | T1583 | 42910715201 | 2014-05-21 | QTR4 | 13/14 | 2 | 12 | 365 | 542 | 598 | -56 | 56 | 0 | 106 | 71 | 12221582 | 124617 | 12096965 | 12321397 | 12316064 | -258944 | 0 | -258944 | 12057120 | 11369478 | -687643 | 99815 | 77 | 0 | 55 | 73297 | 0 | 0 | 16 | 102194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 177856 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 | 2016-04-29 | QTR4 | 15/16 | 108 | 11851721.99 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO | 35 | 03co | 97 | 131
01CO | 01 | T1587 | 42913115201 | 2014-03-26 | QTR3 | 13/14 | 2 | 7 | 185 | 230 | 226 | 4 | 0 | 0 | 36 | 9 | 4576900 | 50000 | 4526900 | 4273384 | 4255627 | 0 | 0 | 0 | 4255627 | 4165417 | -90210 | -303516 | 25 | 0 | 6 | 199569 | 39215 | 0 | 3 | -504411 | 19494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | -277723 | 58709 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-01 | QTR2 | 16/17 | 2015-04-29 | QTR4 | 14/15 | 115 | 5166652.25 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO | 28 | 03do | 132 | 159
01CO | 01 | T1588 | 41304225201 | 2014-06-18 | QTR4 | 13/14 | 2 | 7 | 680 | 710 | 591 | 119 | 0 | 0 | 46 | -16 | 24169365 | 150000 | 24019365 | 23023182 | 22613781 | 0 | 900000 | 900000 | 23513781 | 20785082 | -2728699 | -1146183 | 1 | 0 | -16 | -1426521 | 0 | 0 | 0 | 288694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | -1137827 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 | 2016-08-25 | QTR1 | 16/17 | 106 | 29188895.88 | B2:B5:B2 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING) | 0 | 8 | 0 | 0 | 0 | 0 |  | CO | 19 | 04co | 160 | 178
01CO | 01 | T1595 | 40631345201 | 2015-03-25 | QTR3 | 14/15 | 1 | 6 | 525 | 556 | 395 | 161 | 0 | 0 | 47 | -16 | 31929262 | 150000 | 31779262 | 31614976 | 31607283 | 0 | 1300000 | 1300000 | 32907283 | 30894410 | -2012872 | -314286 | 36 | 0 | -16 | 17006 | 0 | 0 | 0 | 270841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | -196174 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-10-25 | QTR2 | 16/17 | 2016-07-13 | QTR1 | 16/17 | 106 | 30769490.8 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 11 | 0 | 0 | -491717 | 0 |  | CO | 17 | 04do | 179 | 195
01CO | 01 | T1596 | 43142215201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 250 | 349 | 348 | 1 | 0 | 0 | 74 | 25 | 5571174 | 56174 | 5515000 | 5623674 | 5636689 | 0 | 0 | 0 | 5636689 | 5437906 | -198783 | 52500 | 61 | 0 | 25 | 48439 | 0 | 0 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 100939 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-11-21 | QTR2 | 16/17 | 2016-05-28 | QTR4 | 15/16 | 113 | 5411862.18 | B0 | ACC - LUMP SUM | 25 | 13 | 0 | 0 | 0 | 0 |  | CO | 22 | 05co | 196 | 217
01CO | 01 | T1597 | 43356115201 | 2015-02-25 | QTR3 | 14/15 | 1 | 2 | 115 | 551 | 519 | 32 | 0 | 0 | 413 | 23 | 737000 | 0 | 737000 | 989001 | 989001 | 0 | 0 | 0 | 989001 | 989001 | 0 | 252001 | 394 | 0 | 1 | 3000 | 0 | 0 | 22 | 249001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 252001 | 0 | F591939826 | CENTRAL CONCRETE PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-11-28 | QTR2 | 16/17 | 2016-10-25 | QTR2 | 16/17 | 108 | 596982.85 | B0 | ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 | T | CO | 13 | 05do | 218 | 230
01CO | 01 | T1599 | 42584155201 | 2015-07-29 | QTR1 | 15/16 | 1 | 1 | 325 | 396 | 396 | 0 | 0 | 0 | 71 | 0 | 7593742 | 79742 | 7514000 | 7718407 | 7550971 | 0 | 0 | 0 | 7550971 | 7299675 | -251296 | 124665 | 19 | 0 | 0 | 124665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124665 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 | 2016-12-01 | QTR2 | 16/17 | 113 | 8930964.42 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO | 21 | 06co | 231 | 251
01CO | 01 | T1600 | 42811715201 | 2015-05-20 | QTR4 | 14/15 | 1 | 6 | 150 | 348 | 346 | 2 | 0 | 0 | 178 | 20 | 2180000 | 0 | 2180000 | 2794372 | 2791154 | 0 | 0 | 0 | 2791154 | 2775457 | -15697 | 614372 | 166 | 0 | 0 | 3129 | 0 | 0 | 20 | 611243 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 614372 | 410 | F464740152 | CATHCART CONSTRUCTION COMPANY - FLORIDA | N/A | N/A | N/A | N/A | 2017-04-28 | QTR4 | 16/17 | 2016-07-13 | QTR1 | 16/17 | 108 | 2282380.64 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO | 9 | 06do | 252 | 260
01CO | 01 | T1601 | 42910615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 0 | 180 | 206 | 206 | 0 | 0 | 0 | 26 | 0 | 2560715 | 50000 | 2510715 | 2560715 | 2601322 | 0 | 0 | 0 | 2601322 | 2476584 | -124738 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8528 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 | 2016-04-11 | QTR4 | 15/16 | 108 | 2539521.53 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO | 25 | 07co | 261 | 285
01CO | 01 | T1604 | 43340715201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 130 | 138 | 139 | -1 | 1 | 0 | 11 | -3 | 1272557 | 50000 | 1222557 | 1265786 | 1215247 | 0 | 0 | 0 | 1215247 | 1215247 | 0 | -6770 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -6770 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 | 2016-05-20 | QTR4 | 15/16 | 113 | 1175938.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 1 | 0 | -3 | -6770 | 0 |  | CO | 34 | 07do | 286 | 319
01CO | 01 | T1610 | 43337615201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 140 | 157 | 173 | -16 | 16 | 0 | 17 | 0 | 766880 | 38788 | 728092 | 763925 | 702653 | -27872 | 0 | -27872 | 674781 | 674781 | 0 | -2956 | 10 | 0 | 0 | -73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2956 | 0 | F202950491 | NEW FLORIDA INDUSTRIAL ELECTRIC INC. (T | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 | 2016-04-28 | QTR4 | 15/16 | 108 | 1032307.62 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 320 | 319
01CO | 01 | T1612 | 43539315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 2 | 139 | 163 | 162 | 1 | 0 | 0 | 24 | 0 | 965039 | 0 | 965039 | 965864 | 949501 | 0 | 0 | 0 | 949501 | 941761 | -7741 | 825 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-08-05 | QTR1 | 16/17 | 2016-04-14 | QTR4 | 15/16 | 113 | 968994.66 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 8 | 08do | 320 | 327
01CO | 01 | T1613 | 19611435201 | 2015-06-17 | QTR4 | 14/15 | 2 | 5 | 375 | 386 | 343 | 43 | 0 | 0 | 27 | -16 | 14129548 | 134625 | 13994923 | 14489220 | 14438239 | 0 | 392000 | 392000 | 14830239 | 14122043 | -708196 | 359672 | 15 | 0 | 0 | 3699 | 0 | 0 | -16 | 386161 | 2894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 393707 | 2894 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-03-23 | QTR3 | 16/17 | 2016-09-08 | QTR1 | 16/17 | 115 | 13676471.13 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1615 | 42950615201 | 2015-06-17 | QTR4 | 14/15 | 2 | 0 | 150 | 184 | 184 | 0 | 0 | 0 | 34 | 0 | 1470894 | 50000 | 1420894 | 1470894 | 1424904 | 0 | 0 | 0 | 1424904 | 1424904 | 0 | 0 | 30 | 0 | 0 | 3080 | 0 | 0 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4010 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 | 2016-07-05 | QTR1 | 16/17 | 115 | 1441634.98 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1617 | 43337515201 | 2015-06-17 | QTR4 | 14/15 | 1 | 2 | 150 | 170 | 169 | 1 | 0 | 0 | 20 | 0 | 1087453 | 50000 | 1037453 | 1211375 | 1165751 | 0 | 0 | 0 | 1165751 | 1165751 | 0 | 123922 | 11 | 0 | 0 | 135887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128298 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 | 2016-05-03 | QTR4 | 15/16 | 108 | 1092794.1 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1618 | 43340815201 | 2015-06-17 | QTR4 | 14/15 | 2 | 2 | 150 | 185 | 185 | 0 | 0 | 0 | 28 | 7 | 1135821 | 50000 | 1085821 | 1138128 | 1108067 | 0 | 0 | 0 | 1108067 | 1103946 | -4121 | 2307 | 17 | 0 | 4 | 3712 | 0 | 0 | 3 | 18533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 22246 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 | 2016-04-13 | QTR4 | 15/16 | 108 | 1209049.68 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 7 | 11 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1619 | 43365815201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 145 | 172 | 171 | 1 | 0 | 0 | 27 | 0 | 618558 | 0 | 618558 | 622340 | 622340 | 0 | 0 | 0 | 622340 | 622340 | 0 | 3782 | 7 | 2 | 0 | 3782 | 3782 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 3782 | 3782 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 | 2016-10-05 | QTR2 | 16/17 | 108 | 495886.08 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1629 | 43325615201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 85 | 88 | 74 | 14 | 0 | 0 | 3 | 0 | 910000 | 47212 | 862788 | 910000 | 883227 | 0 | 0 | 0 | 883227 | 883227 | 0 | 0 | 3 | 0 | 0 | 13198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13198 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-28 | QTR1 | 16/17 | 2016-05-24 | QTR4 | 15/16 | 115 | 857875.38 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1633 | 43092415201 | 2016-03-30 | QTR3 | 15/16 | 2 | 1 | 110 | 184 | 178 | 6 | 0 | 0 | 39 | 35 | 964016 | 0 | 964016 | 968295 | 968295 | 0 | 0 | 0 | 968295 | 968295 | 0 | 4279 | 27 | 0 | 0 | 0 | 0 | 0 | 35 | 4279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 4279 | 0 | F592190605 | O-A-K/FLORIDA INC. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 | 2016-12-29 | QTR2 | 16/17 | 113 | 965168.46 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1637 | 43359315201 | 2016-01-27 | QTR3 | 15/16 | 2 | 1 | 175 | 208 | 203 | 5 | 0 | 0 | 33 | 0 | 2282142 | 50000 | 2232142 | 2313043 | 2274863 | 0 | 0 | 0 | 2274863 | 2279204 | 4342 | 30901 | 25 | 0 | 0 | 30901 | 0 | 0 | 0 | 15071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45973 | 0 | F381807765 | DOUGLAS N. HIGGINS INC. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 | 2016-12-16 | QTR2 | 16/17 | 115 | 2156564.24 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1638 | 43450315201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 90 | 100 | 98 | 2 | 0 | 0 | 10 | 0 | 98907 | 6887 | 92020 | 98907 | 93187 | 0 | 0 | 0 | 93187 | 93187 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1166 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-02-06 | QTR3 | 16/17 | 2016-12-12 | QTR2 | 16/17 | 118 | 117357.81 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1639 | 43321815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 100 | 124 | 122 | 2 | 0 | 0 | 22 | 2 | 484935 | 19525 | 465410 | 484935 | 472783 | 0 | 0 | 0 | 472783 | 472783 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 2 | 7373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7373 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING O | N/A | N/A | N/A | N/A | 2017-06-05 | QTR4 | 16/17 | 2017-02-10 | QTR3 | 16/17 | 113 | 507136.03 | B0 | ACC - LUMP SUM | 2 | 15 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1645 | 43146115201 | 2016-03-30 | QTR3 | 15/16 | 2 | 0 | 200 | 247 | 265 | -18 | 18 | 0 | 47 | 0 | 2749030 | 50000 | 2699030 | 2749030 | 2742983 | -50598 | 0 | -50598 | 2692385 | 2702439 | 10054 | 0 | 30 | 0 | 0 | 19807 | 0 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22257 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-05-23 | QTR4 | 16/17 | 2017-03-17 | QTR3 | 16/17 | 118 | 2791241.12 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1649 | 43092615201 | 2016-03-30 | QTR3 | 15/16 | 2 | 0 | 105 | 148 | 148 | 0 | 0 | 0 | 37 | 6 | 1164267 | 0 | 1164267 | 1164267 | 1163985 | 0 | 0 | 0 | 1163985 | 1163985 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-02-02 | QTR3 | 16/17 | 2016-12-19 | QTR2 | 16/17 | 113 | 995954.35 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 6 | 7 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1651 | 43134115201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 90 | 91 | 78 | 13 | 0 | 0 | 1 | 0 | 194630 | 9734 | 184896 | 194630 | 184896 | 0 | 0 | 0 | 184896 | 184896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-07-18 | QTR1 | 16/17 | 2016-06-06 | QTR4 | 15/16 | 118 | 236550.37 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1654 | 43448815201 | 2016-05-25 | QTR4 | 15/16 | 1 | 0 | 75 | 82 | 81 | 1 | 0 | 0 | 7 | 0 | 374353 | 11020 | 363333 | 374353 | 363333 | 0 | 0 | 0 | 363333 | 363333 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2017-02-02 | QTR3 | 16/17 | 2016-12-01 | QTR2 | 16/17 | 108 | 331783.25 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1656 | 43698615201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 60 | 67 | 64 | 3 | 0 | 0 | 7 | 0 | 162848 | 7848 | 155000 | 162848 | 155000 | 0 | 0 | 0 | 155000 | 155000 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-01-18 | QTR3 | 16/17 | 2016-12-13 | QTR2 | 16/17 | 115 | 192823.77 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1657 | 43131915201 | 2016-02-24 | QTR3 | 15/16 | 3 | 0 | 200 | 270 | 270 | 0 | 0 | 0 | 41 | 29 | 1914753 | 50000 | 1864753 | 1914753 | 1975777 | 0 | 0 | 0 | 1975777 | 1983617 | 7841 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 29 | 18698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 18698 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-05-16 | QTR4 | 16/17 | 2017-03-10 | QTR3 | 16/17 | 118 | 1639168.26 |  |  | 29 | 16 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1659 | 43472815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 70 | 78 | 49 | 29 | 0 | 0 | 8 | 0 | 238287 | 9912 | 228375 | 238287 | 228375 | 0 | 0 | 0 | 228375 | 228375 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 | 2016-10-17 | QTR2 | 16/17 | 115 | 176436.4 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1669 | 43502315201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 150 | 152 | 96 | 56 | 0 | 0 | 2 | 0 | 917114 | 42067 | 875047 | 917114 | 879919 | 0 | 0 | 0 | 879919 | 881307 | 1388 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2017-06-08 | QTR4 | 16/17 | 2017-04-26 | QTR4 | 16/17 | 113 | 940355.44 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1684 | 43766015201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 114858 | 5825 | 109033 | 114858 | 107442 | 0 | 0 | 0 | 107442 | 107442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 | 2017-01-23 | QTR3 | 16/17 | 115 | 126526.39 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A02 | 42518315201 | 2014-12-03 | QTR2 | 14/15 | 1 | 4 | 250 | 403 | 402 | 1 | 0 | 0 | 75 | 78 | 5396928 | 50000 | 5346928 | 5491707 | 5952983 | 0 | 0 | 0 | 5952983 | 5952455 | -528 | 94779 | 57 | 0 | 75 | 18567 | 0 | 0 | 3 | 122779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 141346 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-21 | QTR1 | 16/17 | 2016-05-19 | QTR4 | 15/16 | 115 | 4358786.71 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A15 | 43325515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 70 | 97 | 97 | 0 | 0 | 0 | 27 | 0 | 219504 | 10504 | 209000 | 219504 | 213917 | 0 | 0 | 0 | 213917 | 213917 | 0 | 0 | 15 | 0 | 0 | 4917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4917 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 | 2016-02-20 | QTR3 | 15/16 | 106 | 200589.29 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1L58 | 19753445201 | 2013-01-10 | QTR3 | 12/13 | 3 | 23 | 939 | 1226 | 1226 | 0 | 0 | 0 | 257 | 30 | 21988997 | 150000 | 21838997 | 23327334 | 23110936 | 0 | 0 | 0 | 23110936 | 22111039 | -999897 | 1338337 | 81 | 129 | 30 | 1271226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71910 | 71910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 30 | 1366773 | 71910 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-06-01 | QTR4 | 16/17 | 2016-12-01 | QTR2 | 16/17 | 108 | 21988997 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N36 | 43544915201 | 2014-06-19 | QTR4 | 13/14 | 1 | 2 | 160 | 182 | 194 | -12 | 12 | 0 | 16 | 6 | 1877203 | 50000 | 1827203 | 1918177 | 1843430 | -20904 | 0 | -20904 | 1822526 | 1821939 | -587 | 40974 | 7 | 0 | 0 | 0 | 0 | 0 | 6 | 46084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 46084 | 0 | F593586613 | EVANS CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 | 2015-05-19 | QTR4 | 14/15 | 108 | 2352808.24 |  |  | 3 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N74 | 42912015201 | 2014-12-18 | QTR2 | 14/15 | 1 | 0 | 185 | 212 | 212 | 0 | 0 | 0 | 27 | 0 | 3107573 | 50000 | 3057573 | 3107573 | 3110593 | 0 | 0 | 0 | 3110593 | 2961957 | -148636 | 0 | 9 | 0 | 0 | 7628 | 0 | 0 | 0 | 8425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16053 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 | 2016-01-21 | QTR3 | 15/16 | 113 | 3280021.43 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N87 | 43120915201 | 2015-02-19 | QTR3 | 14/15 | 1 | 0 | 300 | 336 | 336 | 0 | 0 | 0 | 36 | 0 | 3172000 | 50000 | 3122000 | 3172000 | 3272265 | 0 | 0 | 0 | 3272265 | 3269380 | -2886 | 0 | 24 | 0 | 0 | 7188 | 0 | 0 | 0 | 21276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40644 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-07-05 | QTR1 | 16/17 | 2016-04-25 | QTR4 | 15/16 | 108 | 3312411.11 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O02 | 43161515201 | 2015-01-15 | QTR3 | 14/15 | 1 | 2 | 290 | 354 | 354 | 0 | 0 | 0 | 34 | 30 | 5445703 | 56538 | 5389165 | 6533716 | 6114803 | 0 | 0 | 0 | 6114803 | 5883385 | -231419 | 1088013 | 19 | 0 | 20 | 396717 | 0 | 0 | 10 | 691296 | 691296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1088013 | 691296 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 | 2016-05-02 | QTR4 | 15/16 | 113 | 4971481.53 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O45 | 43160315201 | 2015-11-19 | QTR2 | 15/16 | 2 | 0 | 250 | 280 | 279 | 1 | 0 | 0 | 29 | 1 | 5243826 | 73650 | 5170176 | 5243826 | 5060368 | 0 | 0 | 0 | 5060368 | 4915836 | -144532 | 0 | 13 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | F010807936 | LAWRENCE-LYNCH CORP. | N/A | N/A | N/A | N/A | 2017-05-01 | QTR4 | 16/17 | 2017-01-05 | QTR3 | 16/17 | 118 | 7438831.94 |  |  | 1 | 16 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O48 | 43129415201 | 2015-12-17 | QTR2 | 15/16 | 1 | 2 | 240 | 295 | 295 | 0 | 0 | 0 | 53 | 2 | 5895900 | 54282 | 5841618 | 5903041 | 5910137 | 0 | 0 | 0 | 5910137 | 5818680 | -91457 | 7141 | 26 | 0 | 2 | 8312 | 0 | 0 | 0 | 40806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 4868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 53985 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-05-23 | QTR4 | 16/17 | 2017-02-13 | QTR3 | 16/17 | 108 | 5444557.02 | B0 | ACC - LUMP SUM | 2 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O51 | 43129115201 | 2016-03-17 | QTR3 | 15/16 | 1 | 3 | 200 | 237 | 234 | 3 | 0 | 0 | 37 | 0 | 6085726 | 74632 | 6011094 | 6210864 | 5926238 | 0 | 0 | 0 | 5926238 | 5952143 | 25904 | 125138 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 45051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125138 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-05-23 | QTR4 | 16/17 | 2017-03-07 | QTR3 | 16/17 | 108 | 7615266.46 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O52 | 43120615201 | 2015-11-19 | QTR2 | 15/16 | 1 | 2 | 145 | 179 | 179 | 0 | 0 | 0 | 19 | 15 | 2386060 | 50000 | 2336060 | 2389112 | 2334583 | 0 | 0 | 0 | 2334583 | 2290475 | -44107 | 3052 | 14 | 0 | 0 | 0 | 0 | 0 | 15 | 31743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 31743 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-01-24 | QTR3 | 16/17 | 2016-10-04 | QTR2 | 16/17 | 108 | 2466348.35 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O54 | 43170515201 | 2016-01-21 | QTR3 | 15/16 | 1 | 0 | 130 | 254 | 236 | 18 | 0 | 0 | 124 | 0 | 960772 | 50000 | 910772 | 960772 | 890253 | 0 | 0 | 0 | 890253 | 890253 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2017-02-16 | QTR3 | 16/17 | 2017-01-13 | QTR3 | 16/17 | 113 | 1095709.39 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O75 | 43503815201 | 2016-01-21 | QTR3 | 15/16 | 1 | 0 | 60 | 62 | 54 | 8 | 0 | 0 | 2 | 0 | 149955 | 6815 | 143140 | 149955 | 147793 | 0 | 0 | 0 | 147793 | 147793 | 0 | 0 | 1 | 0 | 0 | 6813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6813 | 0 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 | 2016-06-21 | QTR4 | 15/16 | 118 | 157973.52 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O76 | 43504325201 | 2016-03-17 | QTR3 | 15/16 | 1 | 1 | 85 | 150 | 150 | 0 | 0 | 0 | 44 | 21 | 889110 | 31776 | 857334 | 947735 | 899072 | 0 | 0 | 0 | 899072 | 899072 | 0 | 58625 | 26 | 0 | 0 | 0 | 0 | 0 | 21 | 58625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 58625 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-04-12 | QTR4 | 16/17 | 2017-01-04 | QTR3 | 16/17 | 113 | 866149.16 |  |  | 7 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O79 | 43708215201 | 2015-12-17 | QTR2 | 15/16 | 1 | 2 | 300 | 336 | 333 | 3 | 0 | 0 | 36 | 0 | 4699575 | 50000 | 4649575 | 4749575 | 4699575 | 0 | 0 | 0 | 4699575 | 4699575 | 0 | 50000 | 18 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-02-22 | QTR3 | 16/17 | 2017-01-20 | QTR3 | 16/17 | 115 | 4699575 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O85 | 42814015201 | 2015-11-19 | QTR2 | 15/16 | 1 | 0 | 100 | 247 | 247 | 0 | 0 | 0 | 143 | 4 | 1074449 | 50000 | 1024449 | 1074449 | 1064642 | 0 | 0 | 0 | 1064642 | 1064642 | 0 | 0 | 131 | 0 | 2 | 7446 | 0 | 0 | 2 | 31842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 39288 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-01 | QTR4 | 16/17 | 2016-12-08 | QTR2 | 16/17 | 113 | 1084852.65 | B0 | ACC - LUMP SUM | 4 | 12 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P12 | 43856115201 | 2016-06-09 | QTR4 | 15/16 | 1 | 1 | 85 | 97 | 95 | 2 | 0 | 0 | 12 | 0 | 298707 | 12047 | 286660 | 305757 | 301340 | 0 | 0 | 0 | 301340 | 301340 | 0 | 7050 | 0 | 0 | 0 | 4450 | 0 | 0 | 0 | 10230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14680 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 | 2017-01-16 | QTR3 | 16/17 | 108 | 246048.46 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2473 | 42449415201 | 2013-04-24 | QTR4 | 12/13 | 1 | 1 | 360 | 442 | 442 | 0 | 0 | 0 | 82 | 0 | 6447454 | 73390 | 6374065 | 6752983 | 6507167 | 0 | 0 | 0 | 6507167 | 6505012 | -2155 | 305529 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 317914 | 18101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348362 | 18101 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-04-06 | QTR4 | 16/17 | 2014-10-11 | QTR2 | 14/15 | 208 | 6671609.38 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2506 | 43040415201 | 2013-10-30 | QTR2 | 13/14 | 1 | 0 | 45 | 48 | 103 | -55 | 55 | 0 | 3 | 0 | 136157 | 7800 | 128357 | 136157 | 128357 | -47602 | 0 | -47602 | 80754 | 80754 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F861169576 | PURIFOY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-09-14 | QTR1 | 16/17 | 2014-05-14 | QTR4 | 13/14 | 208 | 153002.52 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2523 | 43051815201 | 2014-03-26 | QTR3 | 13/14 | 1 | 0 | 90 | 136 | 135 | 1 | 0 | 0 | 40 | 6 | 212150 | 10702 | 201448 | 212150 | 210626 | -31760 | 0 | -31760 | 178866 | 178866 | 0 | 0 | 7 | 0 | 6 | 9178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 9178 | 0 | F753160478 | ENVIRONMENTAL INNOVATIONS INC | N/A | N/A | N/A | N/A | 2017-01-12 | QTR3 | 16/17 | 2014-10-20 | QTR2 | 14/15 | 209 | 224301.27 | B0 | ACC - LUMP SUM | 6 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2533 | 43355415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 3 | 400 | 535 | 535 | 0 | 0 | 0 | 117 | 18 | 8533240 | 72079 | 8461162 | 8598881 | 9356445 | 0 | 0 | 0 | 9356445 | 9207548 | -148897 | 65641 | 58 | 0 | 0 | 229 | 0 | 0 | 18 | 64256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 46705 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 | 2016-06-23 | QTR4 | 15/16 | 208 | 7794225.55 |  |  | 0 | 59 | 0 | 0 | -19692 | 0 |  | CO
02CO | 02 | T2538 | 42696315201 | 2014-06-18 | QTR4 | 13/14 | 2 | 0 | 130 | 198 | 198 | 0 | 0 | 0 | 65 | 3 | 3648202 | 50000 | 3598202 | 3648202 | 3611865 | 0 | 0 | 0 | 3611865 | 3514982 | -96884 | 0 | 33 | 4 | 3 | 9477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 9477 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-10-05 | QTR2 | 16/17 | 2015-05-28 | QTR4 | 14/15 | 208 | 3330302.73 |  |  | 3 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2541 | 42607315201 | 2014-09-24 | QTR1 | 14/15 | 1 | 1 | 380 | 501 | 501 | 0 | 0 | 0 | 83 | 38 | 3641891 | 50000 | 3591891 | 3767252 | 4042041 | 0 | 0 | 0 | 4042041 | 3981696 | -60345 | 125361 | 55 | 0 | 0 | 0 | 0 | 0 | 38 | 174588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 174588 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-11-14 | QTR2 | 16/17 | 2016-05-26 | QTR4 | 15/16 | 209 | 3748196.45 |  |  | 8 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2567 | 43224715201 | 2015-02-25 | QTR3 | 14/15 | 1 | 8 | 135 | 252 | 252 | 0 | 0 | 0 | 79 | 38 | 1013111 | 0 | 1013111 | 1368388 | 1368010 | 0 | 0 | 0 | 1368010 | 1368010 | 0 | 355277 | 46 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 355277 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 | 2016-02-01 | QTR3 | 15/16 | 214 | 1004174.39 | B0 | ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2572 | 43061415201 | 2015-05-20 | QTR4 | 14/15 | 1 | 3 | 150 | 191 | 191 | 0 | 0 | 0 | 41 | 0 | 1990811 | 0 | 1990811 | 2002450 | 2059822 | 0 | 0 | 0 | 2059822 | 2059822 | 0 | 11638 | 21 | 0 | 0 | 11638 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 11638 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-07-21 | QTR1 | 16/17 | 2016-03-31 | QTR3 | 15/16 | 214 | 1508389.63 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2574 | 21325145201 | 2015-03-25 | QTR3 | 14/15 | 1 | 1 | 210 | 311 | 316 | -5 | 5 | 0 | 39 | 62 | 3292108 | 50000 | 3242108 | 3306325 | 3271355 | -14380 | 0 | -14380 | 3256975 | 3216216 | -40760 | 14217 | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 8349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 14217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 22566 | 0 | F592913720 | CALLAWAY CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-03-21 | QTR3 | 16/17 | 2016-04-15 | QTR4 | 15/16 | 208 | 3074491.57 |  |  | 14 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2575 | 42747615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 360 | 431 | 424 | 7 | 0 | 0 | 62 | 9 | 6409349 | 53558 | 6355792 | 6447241 | 6325936 | 0 | 0 | 0 | 6325936 | 6325901 | -35 | 37891 | 15 | 0 | 0 | 0 | 0 | 0 | 9 | 41071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 63946 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-05-24 | QTR4 | 16/17 | 2017-03-02 | QTR3 | 16/17 | 216 | 5409342.01 |  |  | 9 | 47 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2581 | 42747415201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 483 | 519 | 517 | 2 | 0 | 0 | 36 | 0 | 5752494 | 63821 | 5688673 | 5752494 | 5614852 | 0 | 0 | 0 | 5614852 | 5614852 | 0 | 0 | 12 | 0 | 0 | 6927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6927 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-03-31 | QTR3 | 16/17 | 2017-02-15 | QTR3 | 16/17 | 214 | 6445947.23 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2584 | 43051315201 | 2015-08-26 | QTR1 | 15/16 | 2 | 1 | 150 | 186 | 185 | 1 | 0 | 0 | 14 | 22 | 3444187 | 50000 | 3394187 | 3524159 | 3538172 | 0 | 0 | 0 | 3538172 | 3415729 | -122443 | 79972 | 8 | 0 | 3 | 2309 | 0 | 0 | 19 | 89994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 92303 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-12-28 | QTR2 | 16/17 | 2016-08-05 | QTR1 | 16/17 | 214 | 3688557.42 |  |  | 17 | 6 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2587 | 43265515201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 120 | 151 | 151 | 0 | 0 | 0 | 31 | 0 | 718800 | 0 | 718800 | 718800 | 718800 | 0 | 0 | 0 | 718800 | 718800 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453689782 | SOUTHERN STATES PAVEMENT MARKINGS INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 | 2016-06-02 | QTR4 | 15/16 | 209 | 769166.88 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2588 | 21237925201 | 2015-09-30 | QTR1 | 15/16 | 1 | 3 | 170 | 227 | 227 | 0 | 0 | 0 | 23 | 34 | 2271500 | 0 | 2271500 | 2329229 | 2340019 | 0 | 0 | 0 | 2340019 | 2337891 | -2128 | 57729 | 5 | 4 | 0 | 7981 | 0 | 13 | 5 | 38697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 11052 | 11052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 34 | 57729 | 11052 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-11-29 | QTR2 | 16/17 | 2016-08-17 | QTR1 | 16/17 | 208 | 2754838.98 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2589 | 41525415201 | 2015-12-03 | QTR2 | 15/16 | 2 | 2 | 250 | 256 | 224 | 32 | 0 | 0 | 6 | 0 | 1503905 | 0 | 1503905 | 1530011 | 1553775 | 0 | 0 | 0 | 1553775 | 1554113 | 338 | 26105 | 3 | 0 | 0 | 26105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26105 | 0 | F593476170 | HAL JONES CONTRACTOR INC | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 | 2016-10-04 | QTR2 | 16/17 | 208 | 1346460.02 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2593 | 43051715201 | 2015-09-30 | QTR1 | 15/16 | 3 | 2 | 179 | 211 | 210 | 1 | 0 | 0 | 22 | 10 | 1956915 | 0 | 1956915 | 1997332 | 1951682 | 0 | 0 | 0 | 1951682 | 1947009 | -4672 | 40417 | 19 | 0 | 10 | 40417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 40417 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-16 | QTR2 | 16/17 | 2016-08-01 | QTR1 | 16/17 | 209 | 2334094.44 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2594 | 43265415201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 152 | 152 | 0 | 0 | 0 | 32 | 0 | 475000 | 0 | 475000 | 475000 | 475000 | 0 | 0 | 0 | 475000 | 475000 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-09-30 | QTR1 | 16/17 | 2016-06-03 | QTR4 | 15/16 | 209 | 428505.77 | B0 | ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2598 | 43265915201 | 2015-12-03 | QTR2 | 15/16 | 1 | 0 | 160 | 178 | 189 | -11 | 11 | 0 | 18 | 0 | 848333 | 43639 | 804695 | 848333 | 798176 | -19162 | 0 | -19162 | 779014 | 774669 | -4345 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2794 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-04-05 | QTR4 | 16/17 | 2016-12-09 | QTR2 | 16/17 | 208 | 911545.64 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2602 | 43074515201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 100 | 114 | 113 | 1 | 0 | 0 | 14 | 0 | 558858 | 27404 | 531454 | 558858 | 508320 | 0 | 0 | 0 | 508320 | 508320 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 | 2016-10-17 | QTR2 | 16/17 | 209 | 579077.38 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2603 | 43075915201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 95 | 95 | 0 | 0 | 0 | 6 | 14 | 521218 | 23780 | 497438 | 521218 | 506672 | 0 | 0 | 0 | 506672 | 506672 | 0 | 0 | 3 | 0 | 10 | 1681 | 0 | 0 | 0 | 7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 9235 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 | 2016-07-01 | QTR1 | 16/17 | 214 | 510081.72 |  |  | 14 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2604 | 43226115201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 200 | 233 | 237 | -4 | 4 | 0 | 27 | 6 | 7717554 | 101575 | 7615979 | 7717554 | 7824593 | -15080 | 0 | -15080 | 7809513 | 7576665 | -232848 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-27 | QTR2 | 16/17 | 2016-09-07 | QTR1 | 16/17 | 209 | 9660990.21 |  |  | 6 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2605 | 43226415201 | 2016-02-24 | QTR3 | 15/16 | 1 | 1 | 270 | 313 | 312 | 1 | 0 | 0 | 33 | 10 | 4020836 | 50000 | 3970836 | 4002599 | 3805029 | 0 | 0 | 0 | 3805029 | 3807540 | 2511 | -18237 | 15 | 0 | 10 | 38621 | 0 | 0 | 0 | -7854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 30766 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-01 | QTR4 | 16/17 | 2017-03-13 | QTR3 | 16/17 | 216 | 4422862.3 |  |  | 10 | 18 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2608 | 43055825201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 75 | 84 | 80 | 4 | 0 | 0 | 9 | 0 | 148375 | 8369 | 140006 | 148375 | 138616 | 0 | 0 | 0 | 138616 | 138616 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 | 2016-04-07 | QTR4 | 15/16 | 209 | 178082.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2610 | 41525115201 | 2015-12-09 | QTR2 | 15/16 | 1 | 0 | 270 | 279 | 269 | 10 | 0 | 0 | 9 | 0 | 1544000 | 0 | 1544000 | 1544000 | 1614197 | 0 | 0 | 0 | 1614197 | 1614952 | 755 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2017-03-08 | QTR3 | 16/17 | 2016-11-18 | QTR2 | 16/17 | 208 | 1676280.55 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2613 | 42869615201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 190 | 227 | 227 | 0 | 0 | 0 | 37 | 0 | 7289393 | 80145 | 7209248 | 7289393 | 7240404 | 0 | 0 | 0 | 7240404 | 7140234 | -100170 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-05-03 | QTR4 | 16/17 | 2016-12-09 | QTR2 | 16/17 | 209 | 8014109.84 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2626 | 43055215201 | 2015-12-03 | QTR2 | 15/16 | 1 | 0 | 210 | 255 | 255 | 0 | 0 | 0 | 43 | 2 | 3284461 | 50000 | 3234461 | 3284461 | 3197387 | 0 | 0 | 0 | 3197387 | 3131128 | -66259 | 0 | 26 | 0 | 0 | 0 | 0 | 7 | 0 | 10174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 12924 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-26 | QTR3 | 16/17 | 2016-11-28 | QTR2 | 16/17 | 216 | 3672060.67 |  |  | 2 | 9 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2631 | 43808515201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 75 | 97 | 96 | 1 | 0 | 0 | 22 | 0 | 148168 | 6145 | 142023 | 148168 | 142273 | 0 | 0 | 0 | 142273 | 142273 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-22 | QTR4 | 16/17 | 2017-04-07 | QTR4 | 16/17 | 214 | 129624.31 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2659 | 43432715201 | 2017-05-24 | QTR4 | 16/17 | 2 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042000 | 0 | 2042000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-06-13 | QTR4 | 16/17 |  | QTR2 | 00/01 |  | 2336443.75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2P99 | 21330125201 | 2012-06-29 | QTR4 | 11/12 | 2 | 7 | 615 | 1443 | 1443 | 0 | 0 | 0 | 201 | 627 | 17859000 | 150000 | 17709000 | 27306925 | 27318877 | 0 | 0 | 0 | 27318877 | 26689964 | -628913 | 9447925 | 119 | 0 | 627 | 9078926 | 2177986 | 0 | 0 | 325187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0 | 0 | 2873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627 | 9579662 | 2177986 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-12-14 | QTR2 | 16/17 | 2016-08-09 | QTR1 | 16/17 | 208 | 28650000 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 82 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R04 | 21066125201 | 2012-12-12 | QTR2 | 12/13 | 2 | 1 | 90 | 192 | 224 | -32 | 32 | 0 | 32 | 70 | 1430432 | 50000 | 1380432 | 1430840 | 1393606 | -49024 | 0 | -49024 | 1344582 | 1344578 | -4 | 408 | 14 | 3 | 0 | 4074 | 0 | 0 | 70 | 21643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 70 | 25716 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 | 2014-03-07 | QTR3 | 13/14 | 208 | 1293927.32 |  |  | 70 | 15 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R17 | 21237935201 | 2013-06-20 | QTR4 | 12/13 | 5 | 1 | 790 | 846 | 846 | 0 | 0 | 0 | 56 | 0 | 11440230 | 150000 | 11290230 | 11429587 | 11316805 | 0 | 0 | 0 | 11316805 | 11261013 | -55793 | -10643 | 7 | 0 | 0 | -621 | 0 | 0 | 0 | 42964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32321 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 | 2015-12-07 | QTR2 | 15/16 | 208 | 13890662.92 | B8:A3 | ACC - DESIGN/BUILD - MAJOR:ICC - DESIGN/BUILD - MINOR | 0 | 49 | 0 | 0 | -11541 | 0 |  | DO
02DO | 02 | E2T58 | 43226315201 | 2015-11-18 | QTR2 | 15/16 | 1 | 0 | 140 | 181 | 181 | 0 | 0 | 0 | 41 | 0 | 3757549 | 50000 | 3707549 | 3757549 | 3830766 | 0 | 0 | 0 | 3830766 | 3684887 | -145879 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-10-11 | QTR2 | 16/17 | 2016-09-08 | QTR1 | 16/17 | 214 | 4878401.01 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T69 | 43041715201 | 2015-07-15 | QTR1 | 15/16 | 1 | 3 | 210 | 362 | 362 | 0 | 0 | 0 | 30 | 122 | 1759555 | 50000 | 1709555 | 1996713 | 2571252 | 0 | 0 | 0 | 2571252 | 2563560 | -7693 | 237158 | 11 | 0 | 18 | 101267 | 0 | 0 | 104 | 148934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 250201 | 0 | F352517594 | BROTHERS' CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 | 2016-09-16 | QTR1 | 16/17 | 208 | 1357063.07 |  |  | 29 | 13 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T70 | 43219415201 | 2015-07-15 | QTR1 | 15/16 | 1 | 0 | 190 | 217 | 214 | 3 | 0 | 0 | 23 | 4 | 741630 | 36943 | 704687 | 741630 | 709180 | 0 | 0 | 0 | 709180 | 709010 | -170 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13295 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 | 2016-06-29 | QTR4 | 15/16 | 214 | 775810 |  |  | 4 | 9 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T74 | 42342715201 | 2015-09-16 | QTR1 | 15/16 | 1 | 0 | 135 | 163 | 162 | 1 | 0 | 0 | 28 | 0 | 4336630 | 50000 | 4286630 | 4336630 | 4421132 | 0 | 0 | 0 | 4421132 | 4255700 | -165433 | 0 | 27 | 0 | 0 | 17388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17388 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-28 | QTR1 | 16/17 | 2016-06-13 | QTR4 | 15/16 | 209 | 4754490.59 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T86 | 20789425201 | 2015-11-18 | QTR2 | 15/16 | 2 | 1 | 250 | 289 | 284 | 5 | 0 | 0 | 28 | 11 | 825208 | 41817 | 783391 | 860208 | 824755 | 0 | 0 | 0 | 824755 | 824711 | -44 | 35000 | 10 | 0 | 0 | 0 | 0 | 0 | 11 | 54666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 54666 | 0 | F205269497 | PROSHOT CONCRETE INC. | N/A | N/A | N/A | N/A | 2017-06-12 | QTR4 | 16/17 | 2017-02-15 | QTR3 | 16/17 | 209 | 890405.76 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T87 | 20967415201 | 2015-11-18 | QTR2 | 15/16 | 1 | 0 | 140 | 199 | 198 | 1 | 0 | 0 | 34 | 25 | 1743906 | 50000 | 1693906 | 1743906 | 2125210 | 0 | 0 | 0 | 2125210 | 2124106 | -1104 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 21 | 39680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 41424 | 0 | F205877898 | KIRBY DEVELOPMENT INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 | 2016-08-24 | QTR1 | 16/17 | 208 | 1607950.75 |  |  | 25 | 4 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T90 | 20838945201 | 2015-12-16 | QTR2 | 15/16 | 1 | 0 | 185 | 192 | 155 | 37 | 0 | 0 | 7 | 0 | 559753 | 48363 | 511389 | 559753 | 512091 | 0 | 0 | 0 | 512091 | 512091 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593285921 | S & D INDUSTRIAL PAINTING INC. | N/A | N/A | N/A | N/A | 2016-11-08 | QTR2 | 16/17 | 2016-10-03 | QTR2 | 16/17 | 209 | 1034491.52 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U35 | 43226515201 | 2016-02-24 | QTR3 | 15/16 | 1 | 1 | 280 | 320 | 314 | 6 | 0 | 0 | 40 | 0 | 5333716 | 66130 | 5267586 | 5333716 | 5070766 | 0 | 0 | 0 | 5070766 | 5049334 | -21432 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-18 | QTR4 | 16/17 | 2017-03-13 | QTR3 | 16/17 | 216 | 6137175.52 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U45 | 42871125201 | 2015-12-16 | QTR2 | 15/16 | 1 | 0 | 45 | 53 | 211 | -158 | 158 | 0 | 7 | 1 | 138261 | 7135 | 131126 | 138261 | 134115 | -43856 | 0 | -43856 | 90258 | 120111 | 29853 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2989 | 0 | Z31-0396250 | OHIO CASUALTY INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 | 2016-10-21 | QTR2 | 16/17 | 208 | 151023.35 | B0 | ACC - LUMP SUM | 1 | 2 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U47 | 43226215201 | 2016-04-20 | QTR4 | 15/16 | 1 | 0 | 90 | 97 | 93 | 4 | 0 | 0 | 7 | 0 | 841047 | 35674 | 805373 | 841047 | 781435 | 0 | 0 | 0 | 781435 | 781435 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6444 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-02-07 | QTR3 | 16/17 | 2016-10-05 | QTR2 | 16/17 | 209 | 750871.08 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U48 | 40849455201 | 2016-04-20 | QTR4 | 15/16 | 1 | 0 | 120 | 128 | 106 | 22 | 0 | 0 | 8 | 0 | 293901 | 11791 | 282110 | 293901 | 283652 | 0 | 0 | 0 | 283652 | 284750 | 1098 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2017-02-02 | QTR3 | 16/17 | 2016-10-18 | QTR2 | 16/17 | 208 | 225521.53 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U52 | 43075015201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 120 | 169 | 169 | 0 | 0 | 0 | 41 | 8 | 1141413 | 45095 | 1096318 | 1141413 | 1057536 | 0 | 0 | 0 | 1057536 | 1057536 | 0 | 0 | 7 | 0 | 2 | 5102 | 0 | 12 | 6 | 7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 13057 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-06-23 | QTR4 | 16/17 | 2017-04-26 | QTR4 | 16/17 | 214 | 954138.18 |  |  | 8 | 22 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V32 | 43743115201 | 2016-08-17 | QTR1 | 16/17 | 1 | 0 | 120 | 121 | 100 | 21 | 0 | 0 | 1 | 0 | 547282 | 20940 | 526342 | 547282 | 469400 | 0 | 0 | 0 | 469400 | 469400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2017-06-19 | QTR4 | 16/17 | 2017-04-12 | QTR4 | 16/17 | 208 | 449347.96 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3349 | 22041285201 | 2010-12-08 | QTR2 | 10/11 | 3 | 28 | 835 | 1802 | 1804 | -2 | 2 | 0 | 381 | 586 | 7357219 | 72479 | 7284740 | 10528722 | 10638848 | -93018 | 0 | -93018 | 10545830 | 10537771 | -8059 | 3171503 | 203 | 0 | 428 | 2195488 | 844067 | 0 | 120 | 436311 | 60348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 81300 | 13615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 365823 | 185379 | 97 | 0 | 126858 | 126858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 586 | 3205779 | 1230267 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 | 2016-03-11 | QTR3 | 15/16 | 308 | 7320354.71 | ARRA | AMERICAN RECOVERY AND REINVEST | 49 | 81 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3375 | 42124315201 | 2012-02-29 | QTR3 | 11/12 | 3 | 3 | 1194 | 1402 | 1400 | 2 | 0 | 0 | 170 | 38 | 14736078 | 150000 | 14586078 | 15035632 | 14669101 | 0 | 0 | 0 | 14669101 | 14620764 | -48338 | 299554 | 105 | 0 | 38 | 320021 | 0 | 0 | 0 | 102024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59292 | 0 | 0 | 0 | 7231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 371313 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 | 2016-04-30 | QTR4 | 15/16 | 308 | 18080147.32 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3392 | 41694015201 | 2012-03-28 | QTR3 | 11/12 | 6 | 6 | 485 | 764 | 774 | -10 | 10 | 0 | 209 | 70 | 6759549 | 77577 | 6681973 | 7037952 | 7405140 | -32260 | 0 | -32260 | 7372880 | 7308967 | -63913 | 278403 | 171 | 0 | 42 | 141721 | 0 | 0 | 9 | 29158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 110627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 16690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 296541 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-08 | QTR3 | 16/17 | 2014-07-24 | QTR1 | 14/15 | 308 | 7836269.38 |  |  | 22 | 38 | 0 | 0 | -1655 | 0 |  | CO
03CO | 03 | T3398 | 22016225201 | 2013-09-25 | QTR1 | 13/14 | 1 | 4 | 310 | 940 | 940 | 0 | 0 | 0 | 415 | 215 | 3358717 | 50000 | 3308717 | 4155082 | 4026349 | 0 | 0 | 0 | 4026349 | 3996594 | -29755 | 796365 | 165 | 27 | 211 | 792014 | 726197 | 5 | 3 | 10636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 1 | -14634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 215 | 788016 | 726197 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-07 | QTR2 | 16/17 | 2016-08-02 | QTR1 | 16/17 | 308 | 2823245.81 |  |  | 6 | 37 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3403 | 42692915201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 100 | 215 | 215 | 0 | 0 | 0 | 73 | 42 | 893145 | 39567 | 853578 | 944595 | 853629 | 0 | 0 | 0 | 853629 | 853629 | 0 | 51450 | 36 | 0 | 0 | 0 | 0 | 0 | 42 | 52046 | 18775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 52046 | 18775 | F223711240 | GULF BEACH CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-05-04 | QTR4 | 16/17 | 2016-06-11 | QTR4 | 15/16 | 308 | 829904.02 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3418 | 42551915201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 350 | 475 | 472 | 3 | 0 | 0 | 125 | 0 | 2589441 | 50000 | 2539441 | 2672648 | 2648983 | 0 | 0 | 0 | 2648983 | 2635144 | -13838 | 83207 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122206 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 | 2016-07-06 | QTR1 | 16/17 | 308 | 2582602.98 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3427 | 42164415201 | 2013-07-31 | QTR1 | 13/14 | 4 | 2 | 475 | 888 | 888 | 0 | 0 | 0 | 369 | 44 | 11476305 | 126776 | 11349528 | 11609159 | 11286785 | -11250 | 0 | -11250 | 11275535 | 10699458 | -576077 | 132854 | 265 | 0 | 19 | 140137 | 0 | 0 | 15 | 65665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 12852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 44 | 228449 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 | 2016-03-31 | QTR3 | 15/16 | 308 | 12800389.92 |  |  | 42 | 91 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3433 | 42693025201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 285 | 368 | 375 | -7 | 7 | 0 | 80 | 3 | 4985043 | 60566 | 4924478 | 5040858 | 4902106 | -20132 | 0 | -20132 | 4881974 | 4555909 | -326064 | 55814 | 53 | 0 | 3 | 55814 | 15953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 64944 | 15953 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-24 | QTR2 | 16/17 | 2016-05-21 | QTR4 | 15/16 | 321 | 6115127.23 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3435 | 42290715201 | 2013-05-22 | QTR4 | 12/13 | 2 | 19 | 570 | 1008 | 1008 | 0 | 0 | 0 | 355 | 83 | 6523192 | 66956 | 6456236 | 8090393 | 8420054 | 0 | 0 | 0 | 8420054 | 8335602 | -84452 | 1567201 | 162 | 21 | 57 | 608587 | 319691 | 21 | 17 | 178987 | 15099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121332 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228153 | 0 | 0 | 6 | 27967 | 17242 | 115 | 3 | 454135 | 25649 | 0 | 0 | 0 | 0 | 157 | 83 | 1619160 | 381061 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-02-28 | QTR3 | 16/17 | 2016-05-12 | QTR4 | 15/16 | 308 | 6744574.73 |  |  | 5 | 36 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3443 | 42693415201 | 2014-12-03 | QTR2 | 14/15 | 2 | 1 | 247 | 408 | 408 | 0 | 0 | 0 | 143 | 18 | 4037987 | 50000 | 3987987 | 4183812 | 4167957 | 0 | 0 | 0 | 4167957 | 3846478 | -321479 | 145825 | 106 | 13 | 17 | 28230 | 0 | 3 | 1 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18 | 175160 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 | 2016-04-07 | QTR4 | 15/16 | 308 | 4397278.78 |  |  | 18 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3460 | 42874715201 | 2016-03-30 | QTR3 | 15/16 | 2 | 0 | 120 | 140 | 137 | 3 | 0 | 0 | 19 | 1 | 1335414 | 50000 | 1285414 | 1335414 | 1301394 | 0 | 0 | 0 | 1301394 | 1295632 | -5762 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 1 | 5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5544 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 | 2016-11-04 | QTR2 | 16/17 | 321 | 1593999.48 |  |  | 1 | 5 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3464 | 43000315201 | 2015-03-25 | QTR3 | 14/15 | 2 | 7 | 370 | 548 | 548 | 0 | 0 | 0 | 154 | 24 | 5476809 | 0 | 5476809 | 5729223 | 5761356 | 0 | 0 | 0 | 5761356 | 5745026 | -16330 | 252414 | 71 | 21 | 24 | 101269 | 18627 | 25 | 0 | 93889 | 92391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 24 | 252414 | 111018 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2017-03-15 | QTR3 | 16/17 | 2017-01-17 | QTR3 | 16/17 | 308 | 4721318.79 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3482 | 42884515201 | 2015-01-28 | QTR3 | 14/15 | 2 | 1 | 300 | 396 | 388 | 8 | 0 | 0 | 96 | 0 | 7416925 | 85537 | 7331389 | 7437265 | 7758460 | -880 | 0 | -880 | 7757580 | 7441692 | -315888 | 20339 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 27217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30580 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 | 2016-04-27 | QTR4 | 15/16 | 313 | 8733987.91 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3483 | 43077715201 | 2015-05-20 | QTR4 | 14/15 | 2 | 2 | 250 | 386 | 386 | 0 | 0 | 0 | 115 | 21 | 4039522 | 50000 | 3989522 | 4047995 | 4269663 | 0 | 0 | 0 | 4269663 | 4226492 | -43171 | 8473 | 57 | 12 | 10 | 55493 | 0 | 1 | 4 | 4180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30674 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 21 | 28999 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-05 | QTR2 | 16/17 | 2016-08-24 | QTR1 | 16/17 | 314 | 3857910.06 |  |  | 14 | 45 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3491 | 43078015201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 90 | 161 | 159 | 2 | 0 | 0 | 71 | 0 | 3493487 | 50000 | 3443487 | 3493487 | 3579235 | 0 | 0 | 0 | 3579235 | 3547935 | -31300 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 1758 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | QTR3 | 16/17 | 2016-10-12 | QTR2 | 16/17 | 314 | 2971789.29 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3495 | 42695615201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 90 | 226 | 225 | 1 | 0 | 0 | 136 | 0 | 1619321 | 50000 | 1569321 | 1619321 | 1588249 | 0 | 0 | 0 | 1588249 | 1566711 | -21538 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 | 2016-05-18 | QTR4 | 15/16 | 321 | 1991519.93 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3497 | 43178715201 | 2016-02-24 | QTR3 | 15/16 | 2 | 1 | 90 | 113 | 113 | 0 | 0 | 0 | 23 | 0 | 439154 | 18320 | 420833 | 441637 | 406769 | 0 | 0 | 0 | 406769 | 406424 | -345 | 2483 | 19 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2483 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-03-23 | QTR3 | 16/17 | 2016-08-21 | QTR1 | 16/17 | 308 | 385976.74 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3513 | 43077815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 80 | 83 | 83 | 0 | 0 | 0 | 3 | 0 | 742276 | 35965 | 706312 | 740169 | 725008 | 0 | 0 | 0 | 725008 | 725004 | -4 | -2107 | 1 | 0 | 0 | -2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-01-18 | QTR3 | 16/17 | 2016-11-27 | QTR2 | 16/17 | 314 | 757261.77 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3514 | 43078115201 | 2015-07-29 | QTR1 | 15/16 | 1 | 0 | 175 | 307 | 308 | -1 | 1 | 0 | 132 | 0 | 3802689 | 50000 | 3752689 | 3802689 | 3624193 | 0 | 0 | 0 | 3624193 | 3479143 | -145050 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 | 2016-07-23 | QTR1 | 16/17 | 314 | 4144189.92 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3515 | 43090835201 | 2014-08-27 | QTR1 | 14/15 | 1 | 1 | 240 | 568 | 567 | 1 | 0 | 0 | 314 | 14 | 8076272 | 85662 | 7990610 | 8066272 | 8349102 | 0 | 0 | 0 | 8349102 | 7667982 | -681120 | -10000 | 119 | 1 | 14 | 68182 | 0 | 0 | 0 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 14 | 58182 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 | 2016-06-03 | QTR4 | 15/16 | 313 | 8827284.67 |  |  | 14 | 54 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3516 | 42874115201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 70 | 83 | 83 | 0 | 0 | 0 | 13 | 0 | 664504 | 28504 | 636000 | 664504 | 636000 | 0 | 0 | 0 | 636000 | 636000 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-01-30 | QTR3 | 16/17 | 2016-09-30 | QTR1 | 16/17 | 308 | 599580.35 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3519 | 42986115201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 45 | 49 | 40 | 9 | 0 | 0 | 4 | 0 | 79117 | 5001 | 74116 | 79117 | 68771 | 0 | 0 | 0 | 68771 | 68771 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F470999979 | BURNETT CIVIL CONTRACTING OF FL | N/A | N/A | N/A | N/A | 2017-04-19 | QTR4 | 16/17 | 2017-03-13 | QTR3 | 16/17 | 321 | 104519.39 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3539 | 22243945201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 90 | 205 | 205 | 0 | 0 | 0 | 66 | 49 | 1948263 | 50000 | 1898263 | 1965454 | 2004975 | 0 | 0 | 0 | 2004975 | 2004975 | 0 | 17192 | 50 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 45708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 49 | 45708 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 | 2016-07-28 | QTR1 | 16/17 | 308 | 1870760.28 |  |  | 49 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3544 | 43090825201 | 2015-03-25 | QTR3 | 14/15 | 1 | 2 | 240 | 490 | 504 | -14 | 14 | 0 | 244 | 6 | 9957902 | 122790 | 9835112 | 10174090 | 10291533 | -52780 | 0 | -52780 | 10238753 | 9419099 | -819655 | 216188 | 71 | 0 | 0 | 0 | 0 | 0 | 4 | 44460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2 | 2689 | 0 | 6 | 0 | 217063 | 217063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 6 | 264212 | 217063 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-20 | QTR3 | 16/17 | 2016-11-01 | QTR2 | 16/17 | 313 | 12349086.79 |  |  | 6 | 42 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3548 | 43079315201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 90 | 110 | 110 | 0 | 0 | 0 | 20 | 0 | 1961731 | 50000 | 1911731 | 1961731 | 1976693 | 0 | 0 | 0 | 1976693 | 1976488 | -205 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-22 | QTR3 | 16/17 | 2016-07-29 | QTR1 | 16/17 | 314 | 2269437.6 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3551 | 42873915201 | 2015-03-25 | QTR3 | 14/15 | 3 | 4 | 175 | 297 | 304 | -7 | 7 | 0 | 118 | 4 | 2525492 | 50000 | 2475492 | 2696693 | 2810548 | -29132 | 0 | -29132 | 2781416 | 2626488 | -154929 | 171200 | 58 | 22 | 0 | 31909 | 0 | 11 | 4 | 152138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 4 | 201162 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-01 | QTR2 | 16/17 | 2016-04-10 | QTR4 | 15/16 | 321 | 3044222.49 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3552 | 43273715201 | 2015-07-29 | QTR1 | 15/16 | 1 | 1 | 125 | 237 | 237 | 0 | 0 | 0 | 101 | 11 | 3670000 | 50000 | 3620000 | 3738760 | 3752339 | -5200 | 0 | -5200 | 3747139 | 3621209 | -125930 | 68760 | 66 | 0 | 7 | 27730 | 0 | 0 | 4 | 70531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 98576 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-10 | QTR2 | 16/17 | 2016-06-11 | QTR4 | 15/16 | 308 | 4236500 |  |  | 7 | 35 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3556 | 43253715201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 205 | 251 | 244 | 7 | 0 | 0 | 39 | 7 | 6785910 | 71955 | 6713955 | 6785910 | 7196007 | 0 | 0 | 0 | 7196007 | 7198436 | 2429 | 0 | 17 | 0 | 7 | 57129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 64053 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-10 | QTR4 | 16/17 | 2017-01-02 | QTR3 | 16/17 | 313 | 7266475.01 |  |  | 7 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3558 | 43274115201 | 2015-09-30 | QTR1 | 15/16 | 2 | 0 | 189 | 216 | 212 | 4 | 0 | 0 | 27 | 0 | 3745728 | 50000 | 3695728 | 3745728 | 3536653 | 0 | 0 | 0 | 3536653 | 3415843 | -120811 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 9140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9140 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-02-02 | QTR3 | 16/17 | 2016-09-28 | QTR1 | 16/17 | 321 | 4720445.88 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3560 | 42461815201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 105 | 161 | 161 | 0 | 0 | 0 | 53 | 3 | 1870023 | 50000 | 1820023 | 1848237 | 1748528 | 0 | 0 | 0 | 1748528 | 1735931 | -12597 | -21786 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -21786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | -21786 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-01-12 | QTR3 | 16/17 | 2016-09-15 | QTR1 | 16/17 | 308 | 2060779.2 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3572 | 43014825201 | 2016-05-25 | QTR4 | 15/16 | 1 | 1 | 69 | 95 | 95 | 0 | 0 | 0 | 26 | 0 | 411660 | 19913 | 391747 | 421660 | 407116 | 0 | 0 | 0 | 407116 | 407116 | 0 | 10000 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 20458 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20458 | 545 | F593289030 | DOWDY PLUMBING CORPORATION | N/A | N/A | N/A | N/A | 2017-04-25 | QTR4 | 16/17 | 2017-02-28 | QTR3 | 16/17 | 321 | 427171.29 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3589 | 43174315201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 120 | 126 | 77 | 49 | 0 | 0 | 6 | 0 | 169047 | 0 | 169047 | 169047 | 169047 | 0 | 0 | 0 | 169047 | 169047 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 | 2016-08-22 | QTR1 | 16/17 | 321 | 199840.42 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3595 | 43551835201 | 2016-07-27 | QTR1 | 16/17 | 2 | 1 | 90 | 106 | 103 | 3 | 0 | 0 | 16 | 0 | 513855 | 6584 | 507270 | 503120 | 496536 | 0 | 0 | 0 | 496536 | 496536 | 0 | -10734 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10734 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-01 | QTR4 | 16/17 | 2017-01-18 | QTR3 | 16/17 | 314 | 447907.33 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3606 | 43187515201 | 2016-10-26 | QTR2 | 16/17 | 2 | 1 | 180 | 197 | 138 | 59 | 0 | 0 | 17 | 0 | 1097017 | 52280 | 1044737 | 1097017 | 1126422 | 0 | 0 | 0 | 1126422 | 1126611 | 189 | 0 | 6 | 0 | 0 | 7587 | 0 | 0 | 0 | 12345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23782 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2017-06-14 | QTR4 | 16/17 | 2017-04-28 | QTR4 | 16/17 | 321 | 1355921.27 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9009 | 43035625201 | 2015-06-24 | QTR4 | 14/15 | 1 | 0 | 240 | 330 | 299 | 31 | 0 | 0 | 90 | 0 | 1500230 | 50000 | 1450230 | 1500230 | 1507255 | 0 | 0 | 0 | 1507255 | 1507255 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 14 | 0 | 29504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 49973 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 | 2016-08-08 | QTR1 | 16/17 | 314 | 1868902.5 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3K73 | 42693515201 | 2014-03-13 | QTR3 | 13/14 | 2 | 1 | 200 | 344 | 344 | 0 | 0 | 0 | 125 | 19 | 1221881 | 50000 | 1171881 | 1231781 | 1143560 | 0 | 0 | 0 | 1143560 | 1120620 | -22940 | 9900 | 106 | 0 | 0 | 0 | 0 | 0 | 19 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 10560 | 6600 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 | 2015-06-14 | QTR4 | 14/15 | 308 | 1514949.05 |  |  | 19 | 19 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L68 | 42874015201 | 2016-01-14 | QTR3 | 15/16 | 1 | 1 | 114 | 163 | 168 | -5 | 5 | 0 | 49 | 0 | 2387205 | 50000 | 2337205 | 2450930 | 2540774 | -17920 | 0 | -17920 | 2522854 | 2503625 | -19229 | 63725 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 63725 | 63725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 63725 | 63725 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2017-01-18 | QTR3 | 16/17 | 2016-09-20 | QTR1 | 16/17 | 321 | 3051775.88 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3L90 | 42840315201 | 2013-06-28 | QTR4 | 12/13 | 1 | 3 | 534 | 975 | 975 | 0 | 0 | 0 | 304 | 137 | 24049000 | 150000 | 23899000 | 24338104 | 24337828 | 0 | 0 | 0 | 24337828 | 24337642 | -186 | 289104 | 165 | 0 | 0 | 10000 | 0 | 20 | 0 | 59678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9750 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 363800 | 298854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 15100 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 137 | 438828 | 298854 | F582354516 | WORLD FIBER TECHNOLOGIES INC. | N/A | N/A | N/A | N/A | 2016-08-30 | QTR1 | 16/17 | 2016-04-26 | QTR4 | 15/16 | 313 | 21314871.51 | A3 | ICC - DESIGN/BUILD - MINOR | 21 | 64 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M17 | 40747845201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 90 | 109 | 107 | 2 | 0 | 0 | 19 | 0 | 149498 | 7779 | 141719 | 149498 | 139613 | 0 | 0 | 0 | 139613 | 139613 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455085205 | PRINCIPLE PROPERTIES INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 | 2016-06-08 | QTR4 | 15/16 | 308 | 163264.04 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M30 | 42429125201 | 2015-02-26 | QTR3 | 14/15 | 2 | 1 | 300 | 535 | 534 | 1 | 0 | 0 | 115 | 120 | 4578636 | 50636 | 4528000 | 5834533 | 5832583 | 0 | 0 | 0 | 5832583 | 5832583 | 0 | 1255897 | 89 | 0 | 0 | 0 | 0 | 0 | 120 | 1304583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1304583 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 | 2016-10-28 | QTR2 | 16/17 | 308 | 4578636 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M55 | 42805825201 | 2014-01-31 | QTR3 | 13/14 | 1 | 1 | 265 | 629 | 628 | 1 | 0 | 0 | 211 | 153 | 1540571 | 50000 | 1490571 | 1579254 | 1571464 | 0 | 0 | 0 | 1571464 | 1571464 | 0 | 38683 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 153 | 80893 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-08-16 | QTR1 | 16/17 | 2016-01-19 | QTR3 | 15/16 | 308 | 1529160 | A3 | ICC - DESIGN/BUILD - MINOR | 65 | 20 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3M95 | 41694315201 | 2015-07-09 | QTR1 | 15/16 | 1 | 3 | 140 | 240 | 239 | 1 | 0 | 0 | 73 | 27 | 2738862 | 50000 | 2688862 | 3014082 | 3595051 | 0 | 0 | 0 | 3595051 | 3484491 | -110560 | 275220 | 36 | 0 | 0 | 0 | 0 | 0 | 5 | 288220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 12155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 287375 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-09-19 | QTR1 | 16/17 | 2016-06-27 | QTR4 | 15/16 | 314 | 3204695.35 |  |  | 22 | 37 | 0 | 0 | -13000 | 0 |  | DO
03DO | 03 | E3N17 | 43392715201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 65 | 65 | 50 | 15 | 0 | 0 | 2 | -2 | 1734968 | 50000 | 1684968 | 1417537 | 1360898 | 0 | 0 | 0 | 1360898 | 1360898 | 0 | -317430 | 2 | 0 | -2 | -313024 | 0 | 0 | 0 | 4578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | -308196 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-09-22 | QTR1 | 16/17 | 2016-05-23 | QTR4 | 15/16 | 321 | 1346663.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N18 | 43391815201 | 2015-10-08 | QTR2 | 15/16 | 1 | 1 | 65 | 117 | 116 | 1 | 0 | 0 | 31 | 21 | 1245237 | 49942 | 1195296 | 1323870 | 1408799 | 0 | 0 | 0 | 1408799 | 1408799 | 0 | 78633 | 30 | 0 | 21 | 108680 | 16182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 108680 | 16182 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 | 2016-05-01 | QTR4 | 15/16 | 308 | 1048525.47 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N24 | 42884815201 | 2016-03-10 | QTR3 | 15/16 | 1 | 1 | 130 | 153 | 152 | 1 | 0 | 0 | 23 | 0 | 3543344 | 50000 | 3493344 | 3600105 | 3788222 | 0 | 0 | 0 | 3788222 | 3802308 | 14086 | 56761 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 61861 | 56761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61861 | 56761 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2017-01-04 | QTR3 | 16/17 | 2016-11-02 | QTR2 | 16/17 | 321 | 3817847.54 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N27 | 41627215201 | 2015-03-25 | QTR3 | 14/15 | 2 | 2 | 305 | 427 | 427 | 0 | 0 | 0 | 72 | 50 | 2233345 | 43949 | 2189396 | 2293381 | 2249432 | 0 | 0 | 0 | 2249432 | 2223244 | -26188 | 60036 | 41 | 0 | 0 | 0 | 0 | 0 | 50 | 60036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 60036 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 | 2016-08-22 | QTR1 | 16/17 | 321 | 2172218.95 | A3:LBDB:A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD:ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N39 | 43078815201 | 2015-05-14 | QTR4 | 14/15 | 2 | 2 | 185 | 318 | 294 | 24 | 0 | 0 | 133 | 0 | 3111936 | 50000 | 3061936 | 3033818 | 2963684 | -11504 | 0 | -11504 | 2952180 | 2882199 | -69981 | -78118 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 18424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | -78118 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 | 2016-06-20 | QTR4 | 15/16 | 314 | 3291622.83 |  |  | 0 | 41 | 0 | 0 | -96542 | 0 |  | DO
03DO | 03 | E3N42 | 21791185201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 75 | 124 | 107 | 17 | 0 | 0 | 49 | 0 | 762045 | 50000 | 712045 | 762045 | 712000 | 0 | 0 | 0 | 712000 | 712000 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-11-09 | QTR2 | 16/17 | 2016-09-09 | QTR1 | 16/17 | 314 | 1488724.75 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N48 | 43514815201 | 2016-02-11 | QTR3 | 15/16 | 1 | 1 | 75 | 124 | 124 | 0 | 0 | 0 | 49 | 0 | 398651 | 12737 | 385914 | 407027 | 394699 | 0 | 0 | 0 | 394699 | 394699 | 0 | 8376 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14166 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2017-03-06 | QTR3 | 16/17 | 2016-10-07 | QTR2 | 16/17 | 308 | 275247.5 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N73 | 43078715201 | 2015-05-14 | QTR4 | 14/15 | 1 | 2 | 245 | 350 | 350 | 0 | 0 | 0 | 102 | 3 | 4943758 | 50000 | 4893758 | 4974205 | 5018776 | -2400 | 0 | -2400 | 5016376 | 4741701 | -274675 | 30447 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 40031 | 29279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 3 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 34041 | 29279 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 | 2016-08-22 | QTR1 | 16/17 | 314 | 4773076.33 |  |  | 3 | 21 | 0 | 0 | -8991 | 0 |  | DO
03DO | 03 | E3N74 | 42696915201 | 2015-11-20 | QTR2 | 15/16 | 1 | 0 | 125 | 164 | 164 | 0 | 0 | 0 | 39 | 0 | 2813937 | 50000 | 2763937 | 2813937 | 2913809 | 0 | 0 | 0 | 2913809 | 2837766 | -76042 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 | 2016-07-25 | QTR1 | 16/17 | 308 | 3196208.79 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N76 | 41557535201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 180 | 207 | 132 | 75 | 0 | 0 | 27 | 0 | 1819446 | 50000 | 1769446 | 1819446 | 1750296 | 0 | 0 | 0 | 1750296 | 1750297 | 1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 | 2016-08-28 | QTR1 | 16/17 | 308 | 1571362.8 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N80 | 42577825201 | 2016-01-14 | QTR3 | 15/16 | 1 | 0 | 60 | 79 | 87 | -8 | 8 | 0 | 19 | 0 | 246955 | 8741 | 238214 | 246955 | 248745 | -7664 | 0 | -7664 | 241081 | 241081 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | F208328161 | AN-KAR CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 | 2016-07-14 | QTR1 | 16/17 | 308 | 183110.5 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O14 | 41040925201 | 2015-09-24 | QTR1 | 15/16 | 2 | 2 | 180 | 214 | 205 | 9 | 0 | 0 | 27 | 7 | 1815481 | 50000 | 1765481 | 1830051 | 1851635 | 0 | 0 | 0 | 1851635 | 1847209 | -4426 | 14570 | 20 | 0 | 0 | 4627 | 0 | 0 | 4 | 46652 | 9517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 13292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 64570 | 9517 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-11-16 | QTR2 | 16/17 | 2016-07-26 | QTR1 | 16/17 | 321 | 1670231.68 |  |  | 3 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O47 | 43253815201 | 2015-10-15 | QTR2 | 15/16 | 1 | 0 | 100 | 128 | 128 | 0 | 0 | 0 | 28 | 0 | 2030029 | 50000 | 1980029 | 2030029 | 2131829 | 0 | 0 | 0 | 2131829 | 2045055 | -86775 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2016-09-07 | QTR1 | 16/17 | 2016-07-12 | QTR1 | 16/17 | 321 | 2649534.01 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O53 | 43254815201 | 2015-09-10 | QTR1 | 15/16 | 1 | 0 | 125 | 173 | 173 | 0 | 0 | 0 | 48 | 0 | 2754000 | 50000 | 2704000 | 2754000 | 2779810 | 0 | 0 | 0 | 2779810 | 2686704 | -93106 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-24 | QTR2 | 16/17 | 2016-06-24 | QTR4 | 15/16 | 314 | 3103650 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O62 | 43079215201 | 2015-12-10 | QTR2 | 15/16 | 1 | 1 | 90 | 131 | 129 | 2 | 0 | 0 | 24 | 17 | 1298500 | 50000 | 1248500 | 1382401 | 1347119 | 0 | 0 | 0 | 1347119 | 1319720 | -27399 | 83901 | 17 | 0 | 17 | 83901 | 15601 | 0 | 0 | 3826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 87727 | 15601 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-08 | QTR1 | 16/17 | 2016-07-11 | QTR1 | 16/17 | 321 | 1564334.7 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O64 | 40946235201 | 2016-09-08 | QTR1 | 16/17 | 1 | 0 | 28 | 33 | 33 | 0 | 0 | 0 | 5 | 0 | 76737 | 4830 | 71907 | 76737 | 79842 | 0 | 0 | 0 | 79842 | 79842 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2017-04-17 | QTR4 | 16/17 | 2017-02-26 | QTR3 | 16/17 | 321 | 102432.1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P32 | 42460825201 | 2016-03-10 | QTR3 | 15/16 | 1 | 0 | 40 | 51 | 48 | 3 | 0 | 0 | 11 | 0 | 69197 | 6233 | 62964 | 69197 | 67195 | 0 | 0 | 0 | 67195 | 67195 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F582427024 | DAVID TAYLOR CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-09-01 | QTR1 | 16/17 | 2016-07-26 | QTR1 | 16/17 | 321 | 143399.73 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P60 | 43255315201 | 2016-08-11 | QTR1 | 16/17 | 1 | 0 | 45 | 48 | 43 | 5 | 0 | 0 | 3 | 0 | 966283 | 42737 | 923546 | 966283 | 955206 | -1500 | 0 | -1500 | 953706 | 953706 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-19 | QTR2 | 16/17 | 2016-11-14 | QTR2 | 16/17 | 314 | 939110.13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P65 | 22049555201 | 2016-05-19 | QTR4 | 15/16 | 1 | 2 | 230 | 263 | 226 | 37 | 0 | 0 | 33 | 0 | 3075201 | 50000 | 3025201 | 3228421 | 3425155 | 0 | 0 | 0 | 3425155 | 3429981 | 4826 | 153221 | 16 | 0 | 0 | 880 | 0 | 0 | 0 | 41531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196882 | 0 | F592280870 | M OF TALLAHASSEE INC. | N/A | N/A | N/A | N/A | 2017-04-19 | QTR4 | 16/17 | 2017-02-24 | QTR3 | 16/17 | 321 | 3871135 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P73 | 22266815201 | 2016-06-09 | QTR4 | 15/16 | 1 | 1 | 120 | 164 | 162 | 2 | 0 | 0 | 27 | 17 | 989058 | 36057 | 953001 | 1035205 | 988093 | 0 | 0 | 0 | 988093 | 988093 | 0 | 46147 | 17 | 0 | 0 | 46147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 47492 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-06-13 | QTR4 | 16/17 | 2017-05-08 | QTR4 | 16/17 | 321 | 777198.58 |  |  | 17 | 10 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P85 | 43627415201 | 2016-04-14 | QTR4 | 15/16 | 1 | 0 | 35 | 44 | 43 | 1 | 0 | 0 | 9 | 0 | 218815 | 9015 | 209800 | 218815 | 209764 | 0 | 0 | 0 | 209764 | 209764 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-06 | QTR2 | 16/17 | 2016-08-20 | QTR1 | 16/17 | 308 | 189940 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4341 | 23073015201 | 2013-02-06 | QTR3 | 12/13 | 2 | 8 | 674 | 896 | 896 | 0 | 0 | 0 | 191 | 31 | 6592014 | 73358 | 6518656 | 6833204 | 6617553 | 0 | 0 | 0 | 6617553 | 6330385 | -287168 | 241190 | 105 | 0 | 31 | 138206 | 0 | 4 | 0 | 108342 | 50933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 4837 | 0 | 0 | 0 | 0 | 0 | 43 | 31 | 314541 | 50933 | F592691292 | MARKS BROTHERS INC. | N/A | N/A | N/A | N/A | 2016-07-06 | QTR1 | 16/17 | 2016-04-11 | QTR4 | 15/16 | 412 | 7354583.81 |  |  | 14 | 43 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4356 | 42286615201 | 2013-06-19 | QTR4 | 12/13 | 2 | 7 | 810 | 1040 | 1038 | 2 | 0 | 0 | 212 | 18 | 9484806 | 99537 | 9385269 | 10082799 | 10383603 | 0 | 0 | 0 | 10383603 | 10314411 | -69192 | 597992 | 169 | 0 | 18 | 291301 | 0 | 0 | 0 | 134692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252549 | 97110 | 0 | 0 | 7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 686144 | 97110 | F203902316 | DRAGADOS USA INC. | N/A | N/A | N/A | N/A | 2017-05-18 | QTR4 | 16/17 | 2016-09-07 | QTR1 | 16/17 | 412 | 10825487.49 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4367 | 23072415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 7 | 353 | 546 | 546 | 0 | 0 | 0 | 166 | 27 | 3396284 | 50000 | 3346284 | 4218679 | 4018129 | 0 | 0 | 0 | 4018129 | 3882269 | -135861 | 822395 | 88 | 0 | 0 | 111602 | 0 | 0 | 27 | 341937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23868 | 0 | 0 | 0 | 12844 | 12844 | 0 | 0 | 0 | 0 | 0 | 0 | 10820 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 363650 | 363650 | 0 | 0 | 0 | 0 | 67 | 27 | 864722 | 376495 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-31 | QTR3 | 16/17 | 2016-08-19 | QTR1 | 16/17 | 412 | 3663891.57 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4376 | 42701215201 | 2015-07-29 | QTR1 | 15/16 | 1 | 3 | 336 | 397 | 396 | 1 | 0 | 0 | 61 | 0 | 4137540 | 50000 | 4087540 | 4285354 | 4224921 | 0 | 0 | 0 | 4224921 | 4063258 | -161663 | 147813 | 28 | 8 | 0 | 2200 | 0 | 11 | 0 | 176739 | 6433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 195285 | 6433 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-03 | QTR4 | 16/17 | 2016-12-22 | QTR2 | 16/17 | 412 | 4993224.98 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4389 | 23097825201 | 2014-04-30 | QTR4 | 13/14 | 1 | 2 | 750 | 801 | 631 | 170 | 0 | 0 | 51 | 0 | 15715809 | 150000 | 15565809 | 15753499 | 15520925 | 0 | 630700 | 630700 | 16151625 | 14963445 | -1188180 | 37690 | 29 | 0 | 0 | 48793 | 0 | 0 | 0 | 38749 | 2893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66399 | 0 | 0 | 0 | 4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158063 | 2893 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2016-09-12 | QTR1 | 16/17 | 2016-05-02 | QTR4 | 15/16 | 408 | 15839218.13 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4396 | 42873215201 | 2015-07-29 | QTR1 | 15/16 | 2 | 1 | 233 | 348 | 348 | 0 | 0 | 0 | 87 | 28 | 3226208 | 50000 | 3176208 | 3268117 | 3297315 | 0 | 0 | 0 | 3297315 | 3205408 | -91907 | 41909 | 54 | 0 | 7 | 51755 | 0 | 0 | 21 | 30301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 28 | 82056 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-05-30 | QTR4 | 16/17 | 2017-01-06 | QTR3 | 16/17 | 412 | 3538926.72 |  |  | 21 | 17 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4402 | 42973715201 | 2014-07-30 | QTR1 | 14/15 | 1 | 0 | 540 | 577 | 542 | 35 | 0 | 0 | 37 | 0 | 2824000 | 50000 | 2774000 | 2824000 | 2773850 | 0 | 0 | 0 | 2773850 | 2779467 | 5617 | 0 | 15 | 0 | 0 | 8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8687 | 0 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2016-09-20 | QTR1 | 16/17 | 2016-04-27 | QTR4 | 15/16 | 408 | 3519184.32 | B0 | ACC - LUMP SUM | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4406 | 42872615201 | 2014-12-03 | QTR2 | 14/15 | 1 | 1 | 267 | 355 | 355 | 0 | 0 | 0 | 88 | 0 | 3869297 | 50000 | 3819297 | 3899697 | 3754820 | 0 | 0 | 0 | 3754820 | 3632165 | -122655 | 30400 | 56 | 0 | 0 | 16792 | 0 | 18 | 0 | 39603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 77392 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-01-24 | QTR3 | 16/17 | 2016-06-28 | QTR4 | 15/16 | 412 | 3716758.39 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4411 | 43472615201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 245 | 261 | 254 | 7 | 0 | 0 | 16 | 0 | 1298981 | 50000 | 1248981 | 1298981 | 1226359 | 0 | 0 | 0 | 1226359 | 1217254 | -9105 | 0 | 12 | 0 | 0 | 31566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31566 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-11-01 | QTR2 | 16/17 | 2016-09-22 | QTR1 | 16/17 | 412 | 1277354.98 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4415 | 43472315201 | 2015-05-20 | QTR4 | 14/15 | 1 | 0 | 198 | 219 | 219 | 0 | 0 | 0 | 21 | 0 | 1247191 | 50000 | 1197191 | 1247191 | 1236940 | 0 | 0 | 0 | 1236940 | 1236940 | 0 | 0 | 16 | 0 | 0 | 4774 | 0 | 0 | 0 | 9270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14044 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 | 2016-08-24 | QTR1 | 16/17 | 409 | 1184118.51 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4416 | 43171715201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 238 | 268 | 261 | 7 | 0 | 0 | 30 | 0 | 1444863 | 50000 | 1394863 | 1444863 | 1398240 | 0 | 0 | 0 | 1398240 | 1398240 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14249 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 | 2016-06-14 | QTR4 | 15/16 | 412 | 1613353.82 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4417 | 43400715201 | 2015-05-20 | QTR4 | 14/15 | 1 | 1 | 254 | 270 | 261 | 9 | 0 | 0 | 16 | 0 | 590398 | 35018 | 555379 | 600523 | 561695 | 0 | 0 | 0 | 561695 | 561695 | 0 | 10125 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-11-15 | QTR2 | 16/17 | 2016-09-27 | QTR1 | 16/17 | 409 | 743747.84 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4420 | 43059515201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 294 | 393 | 392 | 1 | 0 | 0 | 79 | 20 | 1707658 | 50000 | 1657658 | 1707658 | 1691828 | 0 | 0 | 0 | 1691828 | 1691828 | 0 | 0 | 53 | 0 | 10 | 6101 | 0 | 0 | 9 | 22334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40453 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-03-07 | QTR3 | 16/17 | 2016-11-10 | QTR2 | 16/17 | 412 | 1786379.26 |  |  | 20 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4421 | 42802415201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 234 | 318 | 318 | 0 | 0 | 0 | 62 | 22 | 655175 | 33966 | 621209 | 655175 | 640299 | 0 | 0 | 0 | 640299 | 640223 | -76 | 0 | 44 | 0 | 14 | 756 | 0 | 0 | 8 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 32782 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-02-14 | QTR3 | 16/17 | 2017-01-09 | QTR3 | 16/17 | 412 | 662183.52 |  |  | 22 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4426 | 43060815201 | 2016-02-24 | QTR3 | 15/16 | 2 | 0 | 102 | 161 | 161 | 0 | 0 | 0 | 59 | 0 | 1295575 | 50000 | 1245575 | 1295575 | 1275925 | 0 | 0 | 0 | 1275925 | 1275925 | 0 | 0 | 35 | 18 | 0 | 15716 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18401 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 | 2016-10-19 | QTR2 | 16/17 | 409 | 1142628.19 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4427 | 43490215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 187 | 207 | 193 | 14 | 0 | 0 | 20 | 0 | 800000 | 46765 | 753235 | 800000 | 773213 | 0 | 0 | 0 | 773213 | 773213 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8431 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-05-02 | QTR4 | 16/17 | 2017-04-06 | QTR4 | 16/17 | 412 | 918089.86 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4430 | 43509615201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 125 | 137 | 134 | 3 | 0 | 0 | 12 | 0 | 369071 | 19947 | 349124 | 369071 | 326639 | 0 | 0 | 0 | 326639 | 326642 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2017-05-10 | QTR4 | 16/17 | 2017-04-10 | QTR4 | 16/17 | 409 | 392822.92 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4431 | 43509315201 | 2016-03-30 | QTR3 | 15/16 | 1 | 1 | 90 | 119 | 119 | 0 | 0 | 0 | 29 | 0 | 249966 | 10331 | 239635 | 262302 | 239047 | 0 | 0 | 0 | 239047 | 239047 | 0 | 12336 | 17 | 0 | 0 | 0 | 0 | 10 | 0 | 12845 | 11486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 13545 | 11486 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2017-01-24 | QTR3 | 16/17 | 2016-11-16 | QTR2 | 16/17 | 412 | 216195.57 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4432 | 43509115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 0 | 103 | 116 | 116 | 0 | 0 | 0 | 13 | 0 | 462595 | 19884 | 442711 | 462595 | 438863 | 0 | 0 | 0 | 438863 | 438863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820 | 0 | 0 | 0 | 2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2887 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-03-27 | QTR3 | 16/17 | 2017-02-16 | QTR3 | 16/17 | 412 | 406505.19 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4N30 | 23071725201 | 2013-02-06 | QTR3 | 12/13 | 9 | 7 | 832 | 1192 | 1192 | 0 | 0 | 0 | 175 | 185 | 7998765 | 72329 | 7926436 | 10990699 | 10941188 | 0 | 0 | 0 | 10941188 | 10875104 | -66084 | 2991934 | 66 | 37 | 176 | 628756 | 26127 | 0 | 41 | 2394421 | 428763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93484 | 93484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 185 | 3020452 | 548374 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2017-01-04 | QTR3 | 16/17 | 2016-08-11 | QTR1 | 16/17 | 412 | 7310236.62 | A3:Y:A:Y::Y::Y::Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT | 0 | 72 | 0 | -32 | -58956 | 0 |  | DO
04DO | 04 | E4P11 | 43330115201 | 2014-05-07 | QTR4 | 13/14 | 5 | 3 | 646 | 774 | 773 | 1 | 0 | 0 | 67 | 61 | 7982486 | 103877 | 7878609 | 8060089 | 7966495 | 0 | 0 | 0 | 7966495 | 7966495 | 0 | 77603 | 27 | 0 | 23 | 15186 | 0 | 0 | 0 | 627 | 627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 79421 | 9562 | 0 | 14 | 5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 100531 | 10189 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-01-18 | QTR3 | 16/17 | 2016-09-14 | QTR1 | 16/17 | 412 | 10491582.3 | A3:Y:A:Y::Y::Y::Y | ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT:ICC - DESIGN/BUILD - MINOR:DESIGN/BUILD PROJECT | 1 | 40 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P15 | 43270715201 | 2014-04-30 | QTR4 | 13/14 | 1 | 7 | 550 | 706 | 778 | -72 | 72 | 0 | 120 | 36 | 6920878 | 73114 | 6847764 | 6931376 | 6809928 | -232272 | 0 | -232272 | 6577656 | 6290830 | -286826 | 10498 | 83 | 1 | 5 | 67800 | 0 | 0 | 8 | -59002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 18759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 57507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 36 | -13151 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-06-08 | QTR4 | 16/17 | 2016-08-30 | QTR1 | 16/17 | 408 | 6902573.81 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 7 | 36 | 0 | 0 | -98214 | 0 |  | DO
04DO | 04 | E4P38 | 43270415201 | 2014-05-28 | QTR4 | 13/14 | 2 | 4 | 688 | 944 | 944 | 0 | 0 | 0 | 272 | -16 | 21920100 | 150000 | 21770100 | 21827650 | 21748676 | 0 | 0 | 0 | 21748676 | 19468244 | -2280432 | -92450 | 218 | 0 | 0 | 10743 | 0 | 0 | 16 | 32162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | -16 | -49545 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-06-13 | QTR4 | 16/17 | 2017-03-06 | QTR3 | 16/17 | 409 | 20025810 | B8:Y:B:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 16 | 49 | 0 | -45 | -92450 | 0 |  | DO
04DO | 04 | E4P79 | 42593515201 | 2014-04-23 | QTR4 | 13/14 | 2 | 2 | 313 | 441 | 441 | 0 | 0 | 0 | 67 | 61 | 7765532 | 74876 | 7690656 | 7903357 | 8161146 | 0 | 321600 | 321600 | 8482746 | 8149687 | -333059 | 137826 | 53 | 0 | 20 | 14059 | 0 | 0 | 30 | 137826 | 0 | 0 | 11 | 3260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 155145 | 0 | F840915605 | PCL CIVIL CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 | 2016-03-20 | QTR3 | 15/16 | 412 | 7456671.91 | B3:B5 | ACC - LANE RENTAL:ACC - INCENTIVE/DISINCENTIVE | 31 | 14 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P94 | 43368845201 | 2014-05-02 | QTR4 | 13/14 | 1 | 8 | 506 | 648 | 514 | 134 | 0 | 0 | 40 | 102 | 11791416 | 121557 | 11669859 | 13321296 | 13475252 | 0 | 470000 | 470000 | 13945252 | 13368481 | -576771 | 1529880 | 25 | 0 | 102 | 23355 | 0 | 0 | 0 | 1681280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1637852 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 | 2015-12-23 | QTR2 | 15/16 | 412 | 12152859.28 | B10:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - INCENTIVE/DISINCENTIVE | 102 | 14 | 0 | 0 | -74534 | 0 |  | DO
04DO | 04 | E4P95 | 42131415201 | 2014-07-11 | QTR1 | 14/15 | 1 | 10 | 350 | 753 | 753 | 0 | 0 | 0 | 53 | 350 | 1812600 | 50000 | 1762600 | 2451083 | 2583183 | 0 | 0 | 0 | 2583183 | 2583183 | 0 | 638483 | 28 | 0 | 0 | 14920 | 0 | 0 | 0 | 271205 | 255634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 380967 | 379225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 667719 | 634859 | F262618462 | COBALT CONSTRUCTION GROUP LLC | N/A | N/A | N/A | N/A | 2017-06-16 | QTR4 | 16/17 | 2016-12-08 | QTR2 | 16/17 | 408 | 1882510.53 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4P98 | 42605315201 | 2015-02-06 | QTR3 | 14/15 | 2 | 2 | 238 | 283 | 280 | 3 | 0 | 0 | 45 | 0 | 1670723 | 50000 | 1620723 | 1694884 | 1701995 | 0 | 0 | 0 | 1701995 | 1694894 | -7101 | 24162 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 9687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43444 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-03 | QTR1 | 16/17 | 2016-02-26 | QTR3 | 15/16 | 409 | 1844040.91 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q22 | 42990515201 | 2014-12-19 | QTR2 | 14/15 | 1 | 4 | 224 | 358 | 356 | 2 | 0 | 0 | 134 | 0 | 5750000 | 65756 | 5684244 | 6072503 | 6142459 | 0 | 0 | 0 | 6142459 | 6141649 | -810 | 322503 | 74 | 0 | 0 | 13481 | 0 | 45 | 0 | 372908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 386389 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 | 2016-09-30 | QTR1 | 16/17 | 412 | 6522411.23 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q70 | 43056615201 | 2015-04-03 | QTR4 | 14/15 | 1 | 0 | 86 | 99 | 99 | 0 | 0 | 0 | 13 | 0 | 594927 | 36890 | 558037 | 594927 | 563713 | 0 | 0 | 0 | 563713 | 563713 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 | 2016-07-08 | QTR1 | 16/17 | 412 | 789528.37 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q82 | 43056715201 | 2015-03-06 | QTR3 | 14/15 | 1 | 2 | 430 | 446 | 410 | 36 | 0 | 0 | 46 | -30 | 2188629 | 50000 | 2138629 | 2163534 | 2089683 | 0 | 0 | 0 | 2089683 | 2076611 | -13073 | -25094 | 28 | 0 | 0 | 10000 | 0 | 0 | 0 | 13423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | -5141 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-02-10 | QTR3 | 16/17 | 2016-10-15 | QTR2 | 16/17 | 409 | 2260658.05 |  |  | 0 | 16 | 0 | -30 | -29883 | 0 |  | DO
04DO | 04 | E4R08 | 43115215201 | 2015-05-20 | QTR4 | 14/15 | 1 | 1 | 315 | 350 | 313 | 37 | 0 | 0 | 35 | 0 | 1435007 | 50000 | 1385007 | 1449407 | 1163642 | 0 | 0 | 0 | 1163642 | 1155244 | -8398 | 14400 | 23 | 0 | 0 | 3143 | 0 | 0 | 0 | 29620 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33038 | 0 | F561327509 | DICKERSON FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-10-18 | QTR2 | 16/17 | 2016-06-29 | QTR4 | 15/16 | 408 | 1565107.46 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R33 | 43059015201 | 2016-03-04 | QTR3 | 15/16 | 1 | 1 | 238 | 246 | 164 | 82 | 0 | 0 | 8 | 0 | 1637760 | 50000 | 1587760 | 1638489 | 1537659 | 0 | 0 | 0 | 1537659 | 1540807 | 3148 | 729 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17565 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-10 | QTR3 | 16/17 | 2016-11-04 | QTR2 | 16/17 | 412 | 1735050.08 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R44 | 43061715201 | 2016-04-01 | QTR4 | 15/16 | 1 | 2 | 160 | 210 | 205 | 5 | 0 | 0 | 33 | 17 | 1182414 | 35234 | 1147180 | 1176116 | 1146902 | 0 | 0 | 0 | 1146902 | 1148631 | 1729 | -6298 | 17 | 0 | 0 | 0 | 0 | 0 | 17 | -3563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | -3563 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-06-19 | QTR4 | 16/17 | 2017-02-21 | QTR3 | 16/17 | 408 | 670122.53 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R47 | 42840015201 | 2015-12-04 | QTR2 | 15/16 | 1 | 0 | 67 | 179 | 179 | 0 | 0 | 0 | 112 | 0 | 281874 | 13403 | 268471 | 281874 | 265427 | 0 | 0 | 0 | 265427 | 265427 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-01-31 | QTR3 | 16/17 | 2016-12-06 | QTR2 | 16/17 | 409 | 248191.49 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R52 | 43399815201 | 2015-12-04 | QTR2 | 15/16 | 2 | 1 | 157 | 168 | 163 | 5 | 0 | 0 | 11 | 0 | 447523 | 30245 | 417278 | 483523 | 445843 | 0 | 0 | 0 | 445843 | 445875 | 32 | 36000 | 9 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 0 | F462088820 | INTERSTATE CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-01-24 | QTR3 | 16/17 | 2016-08-12 | QTR1 | 16/17 | 412 | 628945.46 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R65 | 43538615201 | 2016-01-08 | QTR3 | 15/16 | 2 | 0 | 65 | 92 | 91 | 1 | 0 | 0 | 23 | 4 | 593859 | 24145 | 569714 | 593859 | 535917 | 0 | 0 | 0 | 535917 | 535917 | 0 | 0 | 18 | 0 | 4 | 8796 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9546 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-08-25 | QTR1 | 16/17 | 2016-06-29 | QTR4 | 15/16 | 409 | 495318.22 |  |  | 4 | 4 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5415 | 40735535201 | 2012-05-23 | QTR4 | 11/12 | 6 | 19 | 1100 | 1340 | 1359 | -19 | 19 | 0 | 211 | 29 | 32798973 | 150000 | 32648973 | 35176946 | 35231745 | -161575 | 0 | -161575 | 35070170 | 34680971 | -389199 | 2796919 | 109 | 0 | 25 | 751698 | 18086 | 0 | 8 | 2210379 | 1011571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 2905712 | 1029658 | F570677291 | UNITED INFRASTRUCTURE GROUP INC. | N/A | N/A | N/A | N/A | 2016-11-18 | QTR2 | 16/17 | 2016-06-20 | QTR4 | 15/16 | 513 | 37106689.63 |  |  | 9 | 84 | 0 | 0 | -57075 | 0 |  | CO
05CO | 05 | T5486 | 23871915201 | 2014-02-26 | QTR3 | 13/14 | 1 | 8 | 490 | 699 | 671 | 28 | 0 | 0 | 125 | 84 | 12324444 | 150000 | 12174444 | 12887259 | 13204280 | 0 | 0 | 0 | 13204280 | 11961836 | -1242443 | 562815 | 92 | 0 | 0 | 66841 | 7015 | 0 | 75 | 365963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20597 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 265295 | 0 | 0 | 0 | 1516 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 679017 | 10770 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-02-06 | QTR3 | 16/17 | 2016-04-25 | QTR4 | 15/16 | 512 | 17116714.63 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5496 | 43106615201 | 2014-05-21 | QTR4 | 13/14 | 1 | 0 | 460 | 684 | 678 | 6 | 0 | 0 | 224 | 0 | 4198661 | 57000 | 4141661 | 4198661 | 4290920 | 0 | 0 | 0 | 4290920 | 4280333 | -10587 | 0 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-10-12 | QTR2 | 16/17 | 2016-08-05 | QTR1 | 16/17 | 514 | 5833243.5 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5497 | 43113915201 | 2014-06-18 | QTR4 | 13/14 | 4 | 2 | 350 | 479 | 448 | 31 | 0 | 0 | 99 | 30 | 5577400 | 50000 | 5527400 | 5630674 | 5316503 | 0 | 0 | 0 | 5316503 | 5110931 | -205572 | 53274 | 72 | 0 | 0 | 16219 | 0 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 41202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 62720 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-13 | QTR1 | 16/17 | 2016-04-13 | QTR4 | 15/16 | 514 | 5261131.52 | B0:B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5504 | 43326915201 | 2015-02-25 | QTR3 | 14/15 | 1 | 0 | 340 | 414 | 410 | 4 | 0 | 0 | 74 | 0 | 2791824 | 50000 | 2741824 | 2791824 | 2764770 | 0 | 0 | 0 | 2764770 | 2763716 | -1054 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 | 2016-09-09 | QTR1 | 16/17 | 514 | 3681477 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5507 | 42908315201 | 2014-10-29 | QTR2 | 14/15 | 2 | 3 | 352 | 458 | 457 | 1 | 0 | 0 | 85 | 21 | 13950000 | 132000 | 13818000 | 14304220 | 14416417 | 0 | 0 | 0 | 14416417 | 13245104 | -1171314 | 354220 | 70 | 0 | 0 | 36422 | 0 | 0 | 0 | 46490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 308750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 391661 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-08-22 | QTR1 | 16/17 | 2016-05-06 | QTR4 | 15/16 | 512 | 13411584.34 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5515 | 43066815201 | 2015-02-25 | QTR3 | 14/15 | 2 | 2 | 210 | 284 | 284 | 0 | 0 | 0 | 44 | 30 | 1884019 | 50000 | 1834019 | 1929335 | 1919435 | 0 | 0 | 0 | 1919435 | 1870656 | -48780 | 45316 | 30 | 0 | 24 | 59005 | 0 | 0 | 6 | 21372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 80377 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 | 2016-05-05 | QTR4 | 15/16 | 514 | 1716624.23 | B0 | ACC - LUMP SUM | 6 | 12 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5519 | 43066615201 | 2015-07-29 | QTR1 | 15/16 | 2 | 0 | 280 | 323 | 260 | 63 | 0 | 0 | 43 | 0 | 2698908 | 50000 | 2648908 | 2698908 | 2560594 | 0 | 0 | 0 | 2560594 | 2513289 | -47305 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 3735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11651 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 | 2016-07-14 | QTR1 | 16/17 | 514 | 2488176 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5524 | 43065215201 | 2015-03-25 | QTR3 | 14/15 | 1 | 3 | 270 | 391 | 390 | 1 | 0 | 0 | 34 | 87 | 4938000 | 50000 | 4888000 | 5043475 | 4946856 | 0 | 0 | 0 | 4946856 | 4688330 | -258527 | 105475 | 16 | 0 | 0 | 3176 | 0 | 0 | 36 | 84688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 17106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 104970 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 | 2016-07-29 | QTR1 | 16/17 | 515 | 4676396.93 |  |  | 23 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5528 | 43066915201 | 2015-05-27 | QTR4 | 14/15 | 1 | 1 | 200 | 245 | 224 | 21 | 0 | 0 | 45 | 0 | 2181000 | 50000 | 2131000 | 2446253 | 2396253 | 0 | 0 | 0 | 2396253 | 2380075 | -16178 | 265253 | 19 | 0 | 0 | 145670 | 0 | 0 | 0 | 119583 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265253 | 508 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2016-07-01 | QTR1 | 16/17 | 2016-04-06 | QTR4 | 15/16 | 507 | 1883279.22 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5531 | 42821325202 | 2015-06-17 | QTR4 | 14/15 | 1 | 2 | 400 | 442 | 400 | 42 | 0 | 0 | 42 | 0 | 3499000 | 50000 | 3449000 | 3559000 | 3541158 | 0 | 0 | 0 | 3541158 | 3541158 | 0 | 60000 | 26 | 0 | 0 | 5923 | 0 | 0 | 0 | 58348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74271 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 | 2016-10-19 | QTR2 | 16/17 | 512 | 4392675.67 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5536 | 43067715201 | 2015-08-26 | QTR1 | 15/16 | 1 | 1 | 216 | 247 | 233 | 14 | 0 | 0 | 31 | 0 | 2584884 | 50000 | 2534884 | 2614884 | 2636650 | 0 | 0 | 0 | 2636650 | 2540033 | -96617 | 30000 | 12 | 0 | 0 | 15490 | 0 | 0 | 0 | 58864 | 13921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74355 | 13921 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-09-27 | QTR1 | 16/17 | 2016-07-22 | QTR1 | 16/17 | 513 | 2795913.94 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5537 | 43244215201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 110 | 154 | 147 | 7 | 0 | 0 | 24 | 20 | 1272760 | 42000 | 1230760 | 1272760 | 1267646 | 0 | 0 | 0 | 1267646 | 1267646 | 0 | 0 | 9 | 0 | 0 | 615 | 0 | 0 | 20 | 34326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 34941 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-07-26 | QTR1 | 16/17 | 2016-06-10 | QTR4 | 15/16 | 513 | 919590 | B0 | ACC - LUMP SUM | 20 | 15 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5540 | 43544615201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 310 | 321 | 320 | 1 | 0 | 0 | 11 | 0 | 2108960 | 50000 | 2058960 | 2108960 | 2062184 | 0 | 0 | 0 | 2062184 | 2062184 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-12-13 | QTR2 | 16/17 | 2016-09-29 | QTR1 | 16/17 | 509 | 2665356.75 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5541 | 43241215201 | 2015-10-28 | QTR2 | 15/16 | 1 | 0 | 200 | 241 | 240 | 1 | 0 | 0 | 41 | 0 | 894822 | 38000 | 856822 | 894822 | 858557 | 0 | 0 | 0 | 858557 | 860505 | 1948 | 0 | 27 | 0 | 0 | 3728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3728 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-03-13 | QTR3 | 16/17 | 2016-12-15 | QTR2 | 16/17 | 514 | 813974.1 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5542 | 43245515201 | 2015-10-28 | QTR2 | 15/16 | 3 | 5 | 260 | 435 | 434 | 1 | 0 | 0 | 146 | 29 | 6389000 | 77000 | 6312000 | 6541385 | 6525238 | -8241 | 0 | -8241 | 6516997 | 6292502 | -224496 | 152385 | 107 | 0 | 7 | 160572 | 0 | 0 | 22 | 25360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 204141 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-06-29 | QTR4 | 16/17 | 2017-05-05 | QTR4 | 16/17 | 513 | 7834175.55 |  |  | 2 | 39 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5543 | 43366515201 | 2015-10-28 | QTR2 | 15/16 | 1 | 1 | 120 | 150 | 150 | 0 | 0 | 0 | 14 | 16 | 408828 | 16725 | 392103 | 408828 | 402408 | 0 | 0 | 0 | 402408 | 402408 | 0 | 0 | 12 | 0 | 0 | 3550 | 0 | 0 | 16 | 7612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 11162 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2017-01-20 | QTR3 | 16/17 | 2016-07-13 | QTR1 | 16/17 | 512 | 373627.25 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5545 | 43065615201 | 2015-10-28 | QTR2 | 15/16 | 1 | 2 | 220 | 237 | 233 | 4 | 0 | 0 | 17 | 0 | 1793084 | 50000 | 1743084 | 1837115 | 1743748 | 0 | 0 | 0 | 1743748 | 1711189 | -32559 | 44031 | 13 | 0 | 0 | 15032 | 0 | 0 | 0 | 26653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71534 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-12-16 | QTR2 | 16/17 | 2016-09-27 | QTR1 | 16/17 | 512 | 1806322.05 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5550 | 43245315201 | 2016-02-24 | QTR3 | 15/16 | 2 | 2 | 220 | 259 | 232 | 27 | 0 | 0 | 39 | 0 | 4609815 | 50000 | 4559815 | 4482913 | 4406263 | 0 | 0 | 0 | 4406263 | 4397650 | -8613 | -126902 | 19 | 0 | 0 | -129277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -129277 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-02-16 | QTR3 | 16/17 | 2017-01-04 | QTR3 | 16/17 | 509 | 4516602 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5560 | 43244115201 | 2016-04-27 | QTR4 | 15/16 | 3 | 3 | 200 | 246 | 236 | 10 | 0 | 0 | 42 | 4 | 2552654 | 50000 | 2502654 | 2632050 | 2628965 | 0 | 0 | 0 | 2628965 | 2624607 | -4358 | 79396 | 19 | 0 | 0 | 19854 | 0 | 0 | 4 | 79217 | 2968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 99072 | 2968 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-05 | QTR4 | 16/17 | 2017-03-10 | QTR3 | 16/17 | 513 | 2570277.16 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5561 | 43474115201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 125 | 188 | 188 | 0 | 0 | 0 | 63 | 0 | 2191000 | 50000 | 2141000 | 2191000 | 2106346 | 0 | 0 | 0 | 2106346 | 2116636 | 10290 | 0 | 44 | 0 | 0 | 7460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7460 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-03-16 | QTR3 | 16/17 | 2017-01-30 | QTR3 | 16/17 | 514 | 2517053 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5577 | 43544615202 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 240 | 262 | 262 | 0 | 0 | 0 | 22 | 0 | 2212434 | 50000 | 2162434 | 2222354 | 2157683 | 0 | 0 | 0 | 2157683 | 2157683 | 0 | 9920 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9920 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-03-27 | QTR3 | 16/17 | 2017-02-02 | QTR3 | 16/17 | 509 | 2655160.5 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5W67 | 43198915201 | 2014-10-07 | QTR2 | 14/15 | 1 | 2 | 300 | 340 | 393 | -53 | 53 | 0 | 13 | 27 | 2340785 | 50000 | 2290785 | 2247902 | 2197902 | -92326 | 0 | -92326 | 2105576 | 2104471 | -1105 | -92883 | 6 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -92883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | -92883 | 0 | F201309732 | RIC-MAN CONSTRUCTION FLORIDA INC. | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 | 2016-02-10 | QTR3 | 15/16 | 509 | 2486510 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W83 | 43528215201 | 2015-04-07 | QTR4 | 14/15 | 1 | 0 | 240 | 265 | 264 | 1 | 0 | 0 | 25 | 0 | 2750721 | 50000 | 2700721 | 2750721 | 2676098 | 0 | 0 | 0 | 2676098 | 2676025 | -73 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591158596 | ORION MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-07-20 | QTR1 | 16/17 | 2016-05-06 | QTR4 | 15/16 | 513 | 2985731 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5W86 | 43488315201 | 2015-06-04 | QTR4 | 14/15 | 1 | 1 | 120 | 131 | 131 | 0 | 0 | 0 | 11 | 0 | 584110 | 29000 | 555110 | 585291 | 580591 | 0 | 0 | 0 | 580591 | 580591 | 0 | 1181 | 1 | 0 | 0 | 478 | 0 | 0 | 0 | 4195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4673 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-11-28 | QTR2 | 16/17 | 2016-07-22 | QTR1 | 16/17 | 513 | 623548.95 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y02 | 43705815201 | 2015-09-01 | QTR1 | 15/16 | 1 | 0 | 130 | 134 | 107 | 27 | 0 | 0 | 4 | 0 | 783941 | 39000 | 744941 | 783941 | 744941 | 0 | 0 | 0 | 744941 | 744941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-08-09 | QTR1 | 16/17 | 2016-07-25 | QTR1 | 16/17 | 515 | 821518.11 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y03 | 43116415201 | 2016-02-02 | QTR3 | 15/16 | 1 | 0 | 65 | 88 | 83 | 5 | 0 | 0 | 23 | 0 | 63940 | 5000 | 58940 | 63940 | 58289 | 0 | 0 | 0 | 58289 | 58289 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2016-12-23 | QTR2 | 16/17 | 2016-10-20 | QTR2 | 16/17 | 514 | 123170 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y04 | 43705715201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 210 | 220 | 220 | 0 | 0 | 0 | 10 | 0 | 679709 | 43000 | 636709 | 679709 | 640622 | 0 | 0 | 0 | 640622 | 640622 | 0 | 0 | 9 | 0 | 0 | 4403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4403 | 0 | F463021209 | SHEN-LINE LLC | N/A | N/A | N/A | N/A | 2016-12-30 | QTR2 | 16/17 | 2016-10-13 | QTR2 | 16/17 | 514 | 911255.5 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y05 | 43465915201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 100 | 110 | 109 | 1 | 0 | 0 | 10 | 0 | 448115 | 19000 | 429115 | 448115 | 434061 | 0 | 0 | 0 | 434061 | 434061 | 0 | 0 | 3 | 0 | 0 | 4946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4946 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-10-04 | QTR2 | 16/17 | 2016-07-14 | QTR1 | 16/17 | 514 | 409595.51 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y07 | 43693615201 | 2016-01-05 | QTR3 | 15/16 | 1 | 0 | 300 | 389 | 380 | 9 | 0 | 0 | 89 | 0 | 2962958 | 50000 | 2912958 | 2962958 | 2820404 | 0 | 0 | 0 | 2820404 | 2820404 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-05-26 | QTR4 | 16/17 | 2017-03-23 | QTR3 | 16/17 | 514 | 2456435 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y18 | 23800235225 | 2016-02-02 | QTR3 | 15/16 | 1 | 1 | 160 | 165 | 148 | 17 | 0 | 0 | 5 | 0 | 788000 | 33000 | 755000 | 805272 | 758781 | 0 | 0 | 0 | 758781 | 759356 | 575 | 17272 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 17272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17272 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 | 2016-09-26 | QTR1 | 16/17 | 513 | 717565.65 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y28 | 43750125201 | 2016-05-03 | QTR4 | 15/16 | 2 | 0 | 90 | 98 | 97 | 1 | 0 | 0 | 8 | 0 | 236798 | 15000 | 221798 | 236798 | 194703 | 0 | 0 | 0 | 194703 | 194703 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591625608 | SANTA CRUZ CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-29 | QTR2 | 16/17 | 2016-11-14 | QTR2 | 16/17 | 515 | 335841 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y38 | 43781715201 | 2016-06-07 | QTR4 | 15/16 | 2 | 1 | 86 | 134 | 134 | 0 | 0 | 0 | 40 | 8 | 293265 | 19000 | 274265 | 294576 | 286101 | 0 | 0 | 0 | 286101 | 284790 | -1311 | 1311 | 24 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-18 | QTR4 | 16/17 | 2017-01-28 | QTR3 | 16/17 | 513 | 406745 |  |  | 8 | 17 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y41 | 43781615201 | 2016-06-07 | QTR4 | 15/16 | 1 | 0 | 120 | 138 | 93 | 45 | 0 | 0 | 18 | 0 | 151151 | 10000 | 141151 | 151151 | 134927 | 0 | 0 | 0 | 134927 | 134927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-04-14 | QTR4 | 16/17 | 2017-03-09 | QTR3 | 16/17 | 513 | 237416.1 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y49 | 43939215201 | 2016-05-25 | QTR4 | 15/16 | 2 | 3 | 250 | 277 | 239 | 38 | 0 | 0 | 15 | 12 | 1927830 | 50000 | 1877830 | 2083244 | 2054804 | 0 | 100000 | 100000 | 2154804 | 2041547 | -113257 | 155414 | 5 | 0 | 0 | 0 | 0 | 0 | 12 | 161305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 161305 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-03-30 | QTR3 | 16/17 | 2017-02-20 | QTR3 | 16/17 | 513 | 1351307 | A3:B5:LBDB | ICC - DESIGN/BUILD - MINOR:ACC - INCENTIVE/DISINCENTIVE:LOW BID DESIGN BUILD | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6127 | 25118515201 | 2011-09-07 | QTR1 | 11/12 | 3 | 18 | 1250 | 1524 | 1524 | 0 | 0 | 0 | 274 | 0 | 58542945 | 268019 | 58274926 | 59378958 | 60313959 | 0 | 0 | 0 | 60313959 | 59818042 | -495917 | 836013 | 200 | 0 | 0 | 1344690 | 17957 | 0 | 0 | 533489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1068519 | 17957 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2016-12-20 | QTR2 | 16/17 | 2016-08-12 | QTR1 | 16/17 | 606 | 67023598.5 |  |  | 0 | 74 | 0 | 0 | -761248 | 0 |  | CO
06CO | 06 | T6290 | 24991115201 | 2012-12-05 | QTR2 | 12/13 | 5 | 17 | 845 | 1067 | 1067 | 0 | 0 | 0 | 188 | 34 | 31967610 | 396250 | 31571360 | 38766907 | 37791470 | 0 | 2100000 | 2100000 | 39891470 | 37602287 | -2289183 | 6799297 | 121 | 4 | 0 | 1715422 | 4227 | 0 | 0 | 515011 | 5252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 4900006 | 368720 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3982 | 3982 | 0 | 0 | 0 | 0 | 6 | 34 | 7134421 | 382182 | F591104806 | BERGERON LAND DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2017-02-21 | QTR3 | 16/17 | 2016-03-02 | QTR3 | 15/16 | 606 | 27939576.37 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 61 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6320 | 42914015201 | 2014-06-18 | QTR4 | 13/14 | 3 | 3 | 450 | 503 | 387 | 116 | 0 | 0 | 53 | 0 | 14295524 | 150000 | 14145524 | 14692214 | 13690377 | 0 | 245000 | 245000 | 13935377 | 13056864 | -878513 | 396690 | 43 | 0 | 0 | 18351 | 0 | 0 | 0 | 421570 | 152744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447735 | 152744 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 | 2016-06-14 | QTR4 | 15/16 | 606 | 15289319.55 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6325 | 25055425201 | 2012-10-31 | QTR2 | 12/13 | 1 | 3 | 700 | 903 | 870 | 33 | 0 | 0 | 197 | 6 | 11430054 | 123500 | 11306554 | 11749528 | 11929942 | 0 | 0 | 0 | 11929942 | 11924070 | -5871 | 319473 | 154 | 2 | 0 | 266319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 63468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 370763 | 0 | F410827177 | JOHNSON BROS. CORPORATION | N/A | N/A | N/A | N/A | 2016-07-11 | QTR1 | 16/17 | 2016-05-31 | QTR4 | 15/16 | 606 | 12087502 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6328 | 42745215201 | 2014-04-30 | QTR4 | 13/14 | 3 | 4 | 600 | 663 | 663 | 0 | 0 | 0 | 63 | 0 | 8067382 | 91797 | 7975585 | 8176995 | 8097390 | 0 | 300000 | 300000 | 8397390 | 7946905 | -450485 | 109613 | 40 | 0 | 0 | 99579 | 0 | 0 | 0 | 7266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141770 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-01-03 | QTR3 | 16/17 | 2016-08-05 | QTR1 | 16/17 | 606 | 8580765.85 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6365 | 43274315201 | 2015-08-26 | QTR1 | 15/16 | 2 | 3 | 180 | 208 | 206 | 2 | 0 | 0 | 28 | 0 | 3849469 | 50000 | 3799469 | 3927103 | 3942847 | 0 | 0 | 0 | 3942847 | 3837692 | -105154 | 77634 | 24 | 0 | 0 | 1963 | 0 | 0 | 0 | 73400 | 3297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4426 | 0 | 0 | 0 | 20491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91428 | 3297 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 | 2016-08-02 | QTR1 | 16/17 | 606 | 4708187.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6371 | 42913415201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 180 | 212 | 212 | 0 | 0 | 0 | 32 | 0 | 1483369 | 50000 | 1433369 | 1483369 | 1429074 | 0 | 0 | 0 | 1429074 | 1425704 | -3370 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 35508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42642 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-11-10 | QTR2 | 16/17 | 2016-08-09 | QTR1 | 16/17 | 606 | 1435507.6 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6372 | 43345115201 | 2016-01-27 | QTR3 | 15/16 | 4 | 3 | 140 | 182 | 182 | 0 | 0 | 0 | 42 | 0 | 1089885 | 50425 | 1039460 | 1078983 | 1060465 | 0 | 0 | 0 | 1060465 | 1060465 | 0 | -10902 | 35 | 0 | 0 | -13402 | 0 | 0 | 0 | 16958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18662 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-04-11 | QTR4 | 16/17 | 2016-11-28 | QTR2 | 16/17 | 606 | 1129000.75 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6373 | 43080915201 | 2015-02-25 | QTR3 | 14/15 | 2 | 1 | 230 | 328 | 326 | 2 | 0 | 0 | 98 | 0 | 2376742 | 50130 | 2326612 | 2426742 | 2460615 | 0 | 0 | 0 | 2460615 | 2384892 | -75723 | 50000 | 56 | 31 | 0 | 16266 | 0 | 0 | 0 | 14872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 71617 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 | 2016-05-12 | QTR4 | 15/16 | 606 | 2292101.6 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6374 | 43118015201 | 2015-03-25 | QTR3 | 14/15 | 6 | 4 | 210 | 310 | 308 | 2 | 0 | 0 | 100 | 0 | 5144045 | 52640 | 5091405 | 5317082 | 5198829 | 0 | 0 | 0 | 5198829 | 5112224 | -86605 | 173037 | 47 | 29 | 0 | 30730 | 0 | 0 | 0 | 7365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 148657 | 104434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 186752 | 104434 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-12-02 | QTR2 | 16/17 | 2016-07-03 | QTR1 | 16/17 | 606 | 4599362.55 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6376 | 43081715201 | 2015-02-25 | QTR3 | 14/15 | 2 | 4 | 435 | 468 | 375 | 93 | 0 | 0 | 33 | 0 | 6621887 | 69750 | 6552137 | 6805679 | 6261293 | 0 | 470000 | 470000 | 6731293 | 6082074 | -649219 | 183793 | 21 | 0 | 0 | 71716 | 0 | 0 | 0 | 115147 | 9450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186863 | 9450 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-07-27 | QTR1 | 16/17 | 2016-05-08 | QTR4 | 15/16 | 606 | 6429680.27 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6379 | 42934515201 | 2016-03-30 | QTR3 | 15/16 | 2 | 2 | 220 | 234 | 192 | 42 | 0 | 0 | 14 | 0 | 2622038 | 55125 | 2566913 | 2613142 | 2527516 | 0 | 150000 | 150000 | 2677516 | 2524953 | -152563 | -8896 | 8 | 0 | 0 | -31036 | 0 | 0 | 0 | 22140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1060 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-03-02 | QTR3 | 16/17 | 2016-12-23 | QTR2 | 16/17 | 606 | 3493513.45 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6381 | 43349015201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 140 | 184 | 184 | 0 | 0 | 0 | 44 | 0 | 762732 | 41312 | 721420 | 762732 | 718865 | 0 | 0 | 0 | 718865 | 721234 | 2369 | 0 | 25 | 0 | 0 | 9499 | 0 | 0 | 0 | 5079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14578 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2017-04-03 | QTR4 | 16/17 | 2017-02-06 | QTR3 | 16/17 | 606 | 854446.65 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6384 | 43350815201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 120 | 137 | 137 | 0 | 0 | 0 | 17 | 0 | 439934 | 26680 | 413254 | 439934 | 417205 | 0 | 0 | 0 | 417205 | 417205 | 0 | 0 | 16 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-08-18 | QTR1 | 16/17 | 2016-06-23 | QTR4 | 15/16 | 606 | 559680 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6386 | 43349315201 | 2016-01-27 | QTR3 | 15/16 | 2 | 0 | 180 | 206 | 206 | 0 | 0 | 0 | 26 | 0 | 648209 | 34334 | 613875 | 648209 | 638650 | 0 | 0 | 0 | 638650 | 605828 | -32822 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-29 | QTR4 | 16/17 | 2017-02-10 | QTR3 | 16/17 | 606 | 711332.45 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6389 | 43481015201 | 2016-01-27 | QTR3 | 15/16 | 1 | 0 | 80 | 96 | 93 | 3 | 0 | 0 | 16 | 0 | 147742 | 8768 | 138974 | 147742 | 141841 | 0 | 0 | 0 | 141841 | 141841 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | F273954210 | PE-SERVICES L.L.C. | N/A | N/A | N/A | N/A | 2016-11-02 | QTR2 | 16/17 | 2016-10-05 | QTR2 | 16/17 | 606 | 180124 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6393 | 24961585201 | 2015-03-25 | QTR3 | 14/15 | 1 | 0 | 580 | 628 | 550 | 78 | 0 | 0 | 48 | 0 | 17726000 | 150000 | 17576000 | 17726000 | 17439683 | 0 | 670000 | 670000 | 18109683 | 16969633 | -1140050 | 0 | 24 | 0 | 0 | 4522 | 0 | 0 | 0 | 33334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47647 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-10 | QTR3 | 16/17 | 2016-12-15 | QTR2 | 16/17 | 606 | 20932157.05 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6394 | 24961575201 | 2015-04-29 | QTR4 | 14/15 | 2 | 1 | 435 | 469 | 395 | 74 | 0 | 0 | 34 | 0 | 18918175 | 150000 | 18768175 | 18918175 | 18379697 | 0 | 740000 | 740000 | 19119697 | 17983880 | -1135817 | 0 | 21 | 0 | 0 | 2262 | 0 | 0 | 0 | 34785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52061 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-11-08 | QTR2 | 16/17 | 2016-08-05 | QTR1 | 16/17 | 606 | 23196102.49 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6395 | 24961555201 | 2015-12-03 | QTR2 | 15/16 | 1 | 2 | 350 | 367 | 311 | 56 | 0 | 0 | 17 | 0 | 18870198 | 150000 | 18720198 | 19070198 | 19250284 | 0 | 1120000 | 1120000 | 20370284 | 19024190 | -1346095 | 200000 | 10 | 0 | 0 | 205933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251546 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-06-26 | QTR4 | 16/17 | 2017-03-01 | QTR3 | 16/17 | 606 | 22322899.05 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6396 | 24961525201 | 2015-05-20 | QTR4 | 14/15 | 4 | 4 | 585 | 641 | 558 | 83 | 0 | 0 | 56 | 0 | 26227745 | 150000 | 26077745 | 26488959 | 26988041 | 0 | 1130000 | 1130000 | 28118041 | 26175164 | -1942877 | 261214 | 33 | 0 | 0 | 217919 | 0 | 0 | 0 | 91807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337759 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-05-08 | QTR4 | 16/17 | 2017-02-17 | QTR3 | 16/17 | 606 | 34221350.42 | B2:B5:B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6402 | 43631315201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 80 | 107 | 107 | 0 | 0 | 0 | 27 | 0 | 249950 | 16163 | 233787 | 249950 | 228758 | 0 | 0 | 0 | 228758 | 228758 | 0 | 0 | 26 | 0 | 0 | 4223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4223 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-07 | QTR3 | 16/17 | 2016-11-10 | QTR2 | 16/17 | 606 | 332195.65 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6H77 | 41806525201 | 2013-07-16 | QTR1 | 13/14 | 4 | 8 | 381 | 718 | 718 | 0 | 0 | 0 | 144 | 193 | 6865432 | 95551 | 6769881 | 8047242 | 8106870 | 0 | 525000 | 525000 | 8631870 | 8012338 | -619532 | 1181810 | 121 | 0 | 193 | 589219 | 0 | 0 | 0 | 643866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 1240647 | 0 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2016-11-21 | QTR2 | 16/17 | 2016-02-25 | QTR3 | 15/16 | 606 | 9650622.75 | B5:B8:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I74 | 43119315201 | 2014-11-20 | QTR2 | 14/15 | 1 | 1 | 330 | 764 | 764 | 0 | 0 | 0 | 434 | 0 | 3722164 | 50000 | 3672164 | 3772164 | 4008665 | 0 | 0 | 0 | 4008665 | 4008622 | -43 | 50000 | 333 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 49781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 49781 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2017-06-05 | QTR4 | 16/17 | 2017-03-17 | QTR3 | 16/17 | 606 | 3636115.25 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I84 | 42560065201 | 2015-11-19 | QTR2 | 15/16 | 2 | 1 | 300 | 325 | 280 | 45 | 0 | 0 | 25 | 0 | 4769021 | 50000 | 4719021 | 4787530 | 4658702 | 0 | 100000 | 100000 | 4758702 | 4637845 | -120857 | 18508 | 11 | 0 | 0 | 697 | 0 | 0 | 0 | 23025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23721 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-02-23 | QTR3 | 16/17 | 2017-01-02 | QTR3 | 16/17 | 606 | 4440861.9 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I89 | 43117815201 | 2014-10-30 | QTR2 | 14/15 | 2 | 1 | 220 | 378 | 378 | 0 | 0 | 0 | 158 | 0 | 2097039 | 50575 | 2046464 | 2147039 | 2148203 | 0 | 0 | 0 | 2148203 | 2008021 | -140182 | 50000 | 100 | 42 | 0 | 57755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 63544 | 0 | F650024320 | H & J ASPHALT INC. | N/A | N/A | N/A | N/A | 2016-10-05 | QTR2 | 16/17 | 2016-05-29 | QTR4 | 15/16 | 606 | 2334024.25 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I91 | 42918715201 | 2015-06-11 | QTR4 | 14/15 | 2 | 0 | 150 | 180 | 179 | 1 | 0 | 0 | 30 | 0 | 1483128 | 50420 | 1432708 | 1483128 | 1441455 | 0 | 0 | 0 | 1441455 | 1430102 | -11353 | 0 | 14 | 0 | 0 | 2145 | 0 | 0 | 0 | 772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 2917 | 0 | F592629362 | DE MOYA GROUP INC. (THE) | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 | 2016-09-23 | QTR1 | 16/17 | 606 | 1376235.85 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I96 | 25023475201 | 2015-04-30 | QTR4 | 14/15 | 2 | 0 | 270 | 332 | 327 | 5 | 0 | 0 | 62 | 0 | 2344175 | 50730 | 2293445 | 2344175 | 2268222 | 0 | 0 | 0 | 2268222 | 2254238 | -13984 | 0 | 51 | 0 | 0 | 7412 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9512 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2017-03-14 | QTR3 | 16/17 | 2016-08-12 | QTR1 | 16/17 | 606 | 2475261.25 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6I98 | 43493065201 | 2016-03-31 | QTR3 | 15/16 | 1 | 1 | 90 | 106 | 106 | 0 | 0 | 0 | 16 | 0 | 969000 | 50000 | 919000 | 903732 | 873748 | 0 | 0 | 0 | 873748 | 873360 | -388 | -65268 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65268 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-10-25 | QTR2 | 16/17 | 2016-10-02 | QTR2 | 16/17 | 606 | 1134223.3 | B0 | ACC - LUMP SUM | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J31 | 41247385201 | 2015-10-29 | QTR2 | 15/16 | 2 | 1 | 140 | 170 | 170 | 0 | 0 | 0 | 30 | 0 | 928836 | 41965 | 886871 | 853946 | 790776 | 0 | 0 | 0 | 790776 | 790197 | -578 | -74891 | 27 | 0 | 0 | -67505 | 0 | 0 | 0 | 10856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -52862 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-01-12 | QTR3 | 16/17 | 2016-10-11 | QTR2 | 16/17 | 606 | 879055.55 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J90 | 41774089201 | 2015-09-23 | QTR1 | 15/16 | 3 | 0 | 380 | 423 | 423 | 0 | 0 | 0 | 43 | 0 | 3017017 | 50000 | 2967017 | 3017017 | 2967017 | 0 | 0 | 0 | 2967017 | 0 | -2967017 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-03-14 | QTR3 | 16/17 | 2017-02-09 | QTR3 | 16/17 | 606 | 3290000 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7209 | 25841515201 | 2009-09-16 | QTR1 | 09/10 | 7 | 55 | 1065 | 1694 | 1694 | 0 | 0 | 0 | 109 | 520 | 389463750 | 75000 | 389388750 | 430319761 | 437468272 | 0 | 0 | 0 | 437468272 | 439424048 | 1955776 | 40856011 | 52 | 22 | 67 | 10225188 | 4993195 | 1 | 121 | 13703270 | 4748092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 6407054 | 1636245 | 0 | 0 | 10009318 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 173923 | 100951 | 0 | 0 | 210466 | 210466 | 0 | 0 | 3584 | 0 | 0 | 0 | 0 | 0 | 23 | 520 | 40732802 | 11688949 | F263258515 | PCL/ARCHER WESTERN A JOINT VEN | N/A | N/A | N/A | N/A | 2016-09-06 | QTR1 | 16/17 | 2014-10-19 | QTR2 | 14/15 | 714 | 412328910.33 | ARRA:B2:B5:P:B2 | AMERICAN RECOVERY AND REINVEST:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:PUBLIC PRIVATE PARTNERSHIP:ACC - A+B (COST+TIME BIDDING) | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7236 | 25589325201 | 2011-09-28 | QTR1 | 11/12 | 2 | 7 | 410 | 560 | 740 | -180 | 180 | 0 | 131 | 19 | 7147510 | 74000 | 7073510 | 7510715 | 7761739 | -452520 | 0 | -452520 | 7309219 | 7308427 | -793 | 363205 | 107 | 0 | 15 | 337971 | 0 | 0 | 4 | 38132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 372176 | 0 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2016-08-10 | QTR1 | 16/17 | 2014-06-13 | QTR4 | 13/14 | 717 | 8423805.36 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7269 | 40845945201 | 2010-12-08 | QTR2 | 10/11 | 1 | 16 | 565 | 857 | 1355 | -498 | 498 | 0 | 153 | 139 | 22517641 | 150000 | 22367641 | 23804461 | 24257673 | -2893316 | 0 | -2893316 | 21364357 | 22393675 | 1029318 | 1286820 | 119 | 0 | 69 | 626503 | 226978 | 0 | 70 | 754399 | 409500 | 0 | 0 | 0 | 0 | 0 | 0 | -226300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 1166622 | 636478 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2017-04-26 | QTR4 | 16/17 | 2014-11-25 | QTR2 | 14/15 | 714 | 23500000 |  |  | 31 | 34 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7298 | 25866025201 | 2012-02-08 | QTR3 | 11/12 | 4 | 11 | 750 | 1037 | 1037 | 0 | 0 | 0 | 152 | 135 | 29974786 | 150000 | 29824786 | 31148108 | 30989158 | -35000 | 0 | -35000 | 30954158 | 30930903 | -23256 | 1173322 | 85 | 0 | 60 | 529216 | 0 | 0 | 75 | 660734 | 406258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 1269799 | 406258 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-01-25 | QTR3 | 16/17 | 2015-04-13 | QTR4 | 14/15 | 714 | 24953779.92 |  |  | 0 | 67 | 0 | 0 | -6927 | 0 |  | CO
07CO | 07 | T7305 | 41886065201 | 2012-06-20 | QTR4 | 11/12 | 8 | 18 | 740 | 1035 | 1035 | 0 | 0 | 0 | 221 | 74 | 27994444 | 135000 | 27859444 | 28571829 | 28922186 | -13000 | 200000 | 187000 | 29109186 | 28487362 | -621825 | 577385 | 184 | 0 | 1 | 153865 | 37343 | 0 | 61 | 494365 | 110210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9379 | 7440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -1161 | 12265 | 0 | 0 | 0 | 0 | 0 | 74 | 637690 | 167258 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-10-14 | QTR2 | 16/17 | 2015-08-15 | QTR1 | 15/16 | 714 | 26994097.12 | B1 | ACC - NO EXCUSE BONUS | 35 | 37 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7309 | 25714715201 | 2012-09-26 | QTR1 | 12/13 | 5 | 11 | 1000 | 1141 | 1121 | 20 | 0 | 0 | 141 | 0 | 20511016 | 150000 | 20361016 | 21458828 | 20369299 | 0 | 0 | 0 | 20369299 | 20020139 | -349160 | 947812 | 105 | 0 | 0 | 754859 | 16651 | 0 | 0 | 284869 | 162142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1086056 | 178793 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 | 2016-04-25 | QTR4 | 15/16 | 714 | 20045000 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7311 | 25579315201 | 2013-05-31 | QTR4 | 12/13 | 3 | 15 | 800 | 990 | 976 | 14 | 0 | 0 | 147 | 43 | 21435705 | 150000 | 21285705 | 23015417 | 23090810 | -8000 | 0 | -8000 | 23082810 | 22674547 | -408263 | 1579712 | 74 | 0 | 37 | 367652 | 256110 | 40 | 0 | 1071146 | 402006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 172463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77446 | 4419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 43 | 1688706 | 662534 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-10-27 | QTR2 | 16/17 | 2016-05-11 | QTR4 | 15/16 | 714 | 21961489.64 |  |  | 5 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7326 | 43304615201 | 2013-06-19 | QTR4 | 12/13 | 4 | 0 | 120 | 145 | 139 | 6 | 0 | 0 | 25 | 0 | 259624 | 13300 | 246324 | 259624 | 242742 | 0 | 0 | 0 | 242742 | 242742 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593374298 | EMPOWER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-05-15 | QTR4 | 16/17 | 2014-01-15 | QTR3 | 13/14 | 717 | 272600 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7331 | 42896215201 | 2013-09-25 | QTR1 | 13/14 | 4 | 9 | 460 | 543 | 543 | 0 | 0 | 0 | 62 | 21 | 10973861 | 52500 | 10921361 | 11371382 | 11571904 | 0 | 0 | 0 | 11571904 | 11452952 | -118952 | 397521 | 35 | 0 | 21 | 253992 | 0 | 0 | 0 | 113746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 54197 | 54197 | 0 | 0 | 0 | 0 | 0 | 0 | -1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 424813 | 58197 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-06-21 | QTR4 | 16/17 | 2015-05-29 | QTR4 | 14/15 | 709 | 9940198.06 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7345 | 25699525201 | 2014-04-30 | QTR4 | 13/14 | 2 | 5 | 420 | 541 | 538 | 3 | 0 | 0 | 91 | 30 | 4872870 | 60000 | 4812870 | 6561188 | 6362566 | 0 | 0 | 0 | 6362566 | 6193892 | -168674 | 1688319 | 67 | 0 | 0 | 1670961 | 64925 | 0 | 30 | 69035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4445 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1744441 | 64925 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-01-31 | QTR3 | 16/17 | 2016-02-02 | QTR3 | 15/16 | 709 | 7433777 |  |  | 30 | 24 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7348 | 42907415201 | 2014-06-18 | QTR4 | 13/14 | 1 | 1 | 495 | 613 | 579 | 34 | 0 | 0 | 118 | 0 | 13220362 | 110000 | 13110362 | 13351863 | 13162187 | 0 | 0 | 0 | 13162187 | 12814384 | -347802 | 131501 | 69 | 0 | 0 | 10426 | 0 | 0 | 0 | 164259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174685 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-10-26 | QTR2 | 16/17 | 2016-06-02 | QTR4 | 15/16 | 717 | 12277372.35 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7356 | 42905815201 | 2014-12-03 | QTR2 | 14/15 | 1 | 3 | 240 | 337 | 337 | 0 | 0 | 0 | 97 | 0 | 6377897 | 60000 | 6317897 | 6518755 | 6488848 | 0 | 0 | 0 | 6488848 | 6241174 | -247674 | 140858 | 77 | 0 | 0 | 57588 | 0 | 0 | 0 | 41020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32045 | 0 | 0 | 0 | 4717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143613 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-12-08 | QTR2 | 16/17 | 2016-02-15 | QTR3 | 15/16 | 709 | 6176900 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7362 | 42907725202 | 2015-03-25 | QTR3 | 14/15 | 2 | 0 | 180 | 256 | 256 | 0 | 0 | 0 | 76 | 0 | 5709404 | 50000 | 5659404 | 5709404 | 5625130 | 0 | 0 | 0 | 5625130 | 5464793 | -160337 | 0 | 57 | 0 | 0 | 8822 | 0 | 0 | 0 | 10150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-08-19 | QTR1 | 16/17 | 2016-05-16 | QTR4 | 15/16 | 717 | 5660000 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7364 | 43311115201 | 2015-06-17 | QTR4 | 14/15 | 1 | 1 | 115 | 141 | 141 | 0 | 0 | 0 | 26 | 0 | 1656000 | 50000 | 1606000 | 1660046 | 1621270 | 0 | 0 | 0 | 1621270 | 1621270 | 0 | 4046 | 14 | 0 | 0 | 8843 | 0 | 0 | 0 | 6427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15270 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2016-10-20 | QTR2 | 16/17 | 2016-02-08 | QTR3 | 15/16 | 709 | 1539800 | B0 | ACC - LUMP SUM | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7365 | 43090015201 | 2015-05-20 | QTR4 | 14/15 | 2 | 3 | 170 | 272 | 272 | 0 | 0 | 0 | 69 | 33 | 3669419 | 50000 | 3619419 | 3856675 | 3844686 | 0 | 0 | 0 | 3844686 | 3746837 | -97849 | 187256 | 47 | 0 | 33 | 193456 | 188898 | 0 | 0 | 28907 | 12707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 209335 | 201605 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-01-06 | QTR3 | 16/17 | 2016-06-03 | QTR4 | 15/16 | 709 | 3925150 | B0 | ACC - LUMP SUM | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7366 | 43113215201 | 2015-04-29 | QTR4 | 14/15 | 2 | 0 | 150 | 211 | 210 | 1 | 0 | 0 | 61 | 0 | 1795000 | 50000 | 1745000 | 1795000 | 1754140 | 0 | 0 | 0 | 1754140 | 1746653 | -7487 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-19 | QTR1 | 16/17 | 2016-03-18 | QTR3 | 15/16 | 717 | 1415000 | B0 | ACC - LUMP SUM | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7367 | 42907615201 | 2015-03-25 | QTR3 | 14/15 | 1 | 4 | 250 | 355 | 355 | 0 | 0 | 0 | 91 | 14 | 3822222 | 50000 | 3772222 | 3834124 | 3855324 | 0 | 0 | 0 | 3855324 | 3731807 | -123517 | 11902 | 61 | 0 | 0 | 44654 | 0 | 0 | 14 | 59289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 24270 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-11-15 | QTR2 | 16/17 | 2016-05-27 | QTR4 | 15/16 | 798 | 4100000 |  |  | 14 | 30 | 0 | 0 | -82752 | 0 |  | CO
07CO | 07 | T7368 | 42421315201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 310 | 399 | 399 | 0 | 0 | 0 | 89 | 0 | 4471471 | 50000 | 4421471 | 4471471 | 4410937 | 0 | 0 | 0 | 4410937 | 4410891 | -46 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 18221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18221 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-01-03 | QTR3 | 16/17 | 2016-11-10 | QTR2 | 16/17 | 717 | 5267432 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7370 | 43251915201 | 2015-08-26 | QTR1 | 15/16 | 1 | 0 | 150 | 240 | 240 | 0 | 0 | 0 | 90 | 0 | 3088818 | 50000 | 3038818 | 3088818 | 2944540 | 0 | 0 | 0 | 2944540 | 2940006 | -4534 | 0 | 44 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-03 | QTR2 | 16/17 | 2016-06-22 | QTR4 | 15/16 | 709 | 3068000 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7371 | 43089915201 | 2015-10-28 | QTR2 | 15/16 | 1 | 4 | 250 | 319 | 319 | 0 | 0 | 0 | 69 | 0 | 10094563 | 100000 | 9994563 | 10178653 | 10186112 | 0 | 0 | 0 | 10186112 | 10014564 | -171548 | 84089 | 42 | 0 | 0 | -28914 | 5035 | 0 | 0 | 106953 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108605 | 5512 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-06-19 | QTR4 | 16/17 | 2017-01-05 | QTR3 | 16/17 | 709 | 10547226.76 | B0 | ACC - LUMP SUM | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7372 | 43260715201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 85 | 131 | 128 | 3 | 0 | 0 | 45 | 1 | 3371083 | 50000 | 3321083 | 3375146 | 3271033 | 0 | 0 | 0 | 3271033 | 3261114 | -9919 | 4063 | 35 | 0 | 1 | 29247 | 0 | 0 | 0 | 5018 | 2659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 34265 | 2659 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-06-08 | QTR4 | 16/17 | 2016-09-13 | QTR1 | 16/17 | 717 | 2100000 | B0 | ACC - LUMP SUM | 1 | 10 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7373 | 43131515201 | 2015-09-30 | QTR1 | 15/16 | 1 | 1 | 210 | 251 | 251 | 0 | 0 | 0 | 41 | 0 | 6275807 | 75000 | 6200807 | 6350807 | 6400500 | 0 | 0 | 0 | 6400500 | 6232156 | -168344 | 75000 | 28 | 0 | 0 | 9469 | 0 | 0 | 0 | 73724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39594 | 0 | 0 | 0 | 1277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124063 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-03-06 | QTR3 | 16/17 | 2016-12-07 | QTR2 | 16/17 | 798 | 7740000 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7374 | 43257915201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 124 | 139 | 110 | 29 | 0 | 0 | 15 | 0 | 3581528 | 50000 | 3531528 | 3581528 | 3666189 | 0 | 220000 | 220000 | 3886189 | 3671670 | -214519 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-09 | QTR2 | 16/17 | 2016-08-18 | QTR1 | 16/17 | 717 | 2950000 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7378 | 43149615201 | 2016-01-27 | QTR3 | 15/16 | 2 | 2 | 125 | 185 | 185 | 0 | 0 | 0 | 60 | 0 | 4821342 | 50000 | 4771342 | 4867138 | 4900357 | 0 | 0 | 0 | 4900357 | 4881384 | -18972 | 45797 | 50 | 0 | 0 | 62986 | 6831 | 0 | 0 | 17749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80735 | 6831 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-04-24 | QTR4 | 16/17 | 2016-11-23 | QTR2 | 16/17 | 709 | 4555000 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T9014 | 43482515201 | 2016-05-25 | QTR4 | 15/16 | 1 | 0 | 135 | 186 | 184 | 2 | 0 | 0 | 51 | 0 | 888715 | 42900 | 845815 | 888715 | 871541 | 0 | 0 | 0 | 871541 | 871545 | 3 | 0 | 3 | 15 | 0 | 583 | 0 | 21 | 0 | 32425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 33008 | 0 | F030586197 | R.M. WILLIAMS CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-04-28 | QTR4 | 16/17 | 2017-03-21 | QTR3 | 16/17 | 706 | 826928 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7F75 | 25839855201 | 2012-05-08 | QTR4 | 11/12 | 2 | 30 | 1445 | 1568 | 1429 | 139 | 0 | 0 | 123 | 0 | 215400000 | 150000 | 215250000 | 224435209 | 224895976 | 0 | 1650000 | 1650000 | 226545976 | 223875000 | -2670976 | 9035209 | 88 | 0 | 0 | 2771364 | 13903 | 0 | 0 | 5245266 | 459975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22798 | 0 | 0 | 0 | 1015841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9055269 | 473878 | F453806780 | SKANSKA-AJAX PAVING JOINT VENTU | N/A | N/A | N/A | N/A | 2016-12-06 | QTR2 | 16/17 | 2016-06-28 | QTR4 | 15/16 | 714 | 213872600 | B11:B12:B8:B:B8 | ACC - DESIGN BUILD-MAJOR/BONUS:ACC - DSGN BLD-MAJ/BONUS/WRNTY:ACC - DESIGN/BUILD - MAJOR:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I30 | 41101425201 | 2013-10-29 | QTR2 | 13/14 | 1 | 9 | 749 | 941 | 941 | 0 | 0 | 0 | 171 | 21 | 45811000 | 150000 | 45661000 | 47224425 | 47268962 | 0 | 0 | 0 | 47268962 | 46074212 | -1194751 | 1413425 | 134 | 0 | 21 | 545327 | 101855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 0 | 0 | 899849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1481476 | 101855 | F940519552 | GRANITE CONSTRUCTION COMPANY OF CALIFORN | N/A | N/A | N/A | N/A | 2017-05-23 | QTR4 | 16/17 | 2016-08-17 | QTR1 | 16/17 | 714 | 47778700 | B8 | ACC - DESIGN/BUILD - MAJOR | 21 | 37 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I34 | 41101135201 | 2014-01-23 | QTR3 | 13/14 | 1 | 3 | 750 | 874 | 871 | 3 | 0 | 0 | 124 | 0 | 35188969 | 150000 | 35038969 | 35441051 | 35414850 | 0 | 0 | 0 | 35414850 | 34061551 | -1353299 | 252082 | 90 | 0 | 0 | 47212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31900 | 0 | 0 | 0 | 150744 | 0 | 0 | 0 | 75555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305411 | 0 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-12-23 | QTR2 | 16/17 | 2016-11-02 | QTR2 | 16/17 | 714 | 37368154.02 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I46 | 25633925201 | 2014-08-14 | QTR1 | 14/15 | 1 | 4 | 450 | 623 | 622 | 1 | 0 | 0 | 137 | 36 | 15944000 | 150000 | 15794000 | 16474127 | 16294835 | 0 | 0 | 0 | 16294835 | 15360010 | -934824 | 530127 | 97 | 0 | 0 | 56222 | 0 | 0 | 1 | 186898 | 3530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 346909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 590029 | 3530 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-09-15 | QTR1 | 16/17 | 2016-06-25 | QTR4 | 15/16 | 714 | 18310419.41 | B8:LBDB | ACC - DESIGN/BUILD - MAJOR:LOW BID DESIGN BUILD | 11 | 40 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I70 | 42550015201 | 2014-05-14 | QTR4 | 13/14 | 1 | 5 | 450 | 694 | 690 | 4 | 0 | 0 | 199 | 45 | 10449830 | 119000 | 10330830 | 11043877 | 11011337 | 0 | 0 | 0 | 11011337 | 10279911 | -731426 | 594047 | 156 | 0 | 34 | 313026 | 0 | 0 | 3 | 96771 | 980 | 0 | 0 | 84213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38377 | 38377 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 532387 | 39357 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-04-05 | QTR4 | 16/17 | 2016-09-15 | QTR1 | 16/17 | 717 | 11723000 | B0 | ACC - LUMP SUM | 45 | 43 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7I76 | 42900015201 | 2014-06-11 | QTR4 | 13/14 | 1 | 8 | 525 | 768 | 768 | 0 | 0 | 0 | 141 | 102 | 11107156 | 120000 | 10987156 | 11770977 | 11963122 | 0 | 0 | 0 | 11963122 | 11588757 | -374365 | 663821 | 96 | 0 | 49 | 373765 | 0 | 0 | 53 | 336731 | 26900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 714298 | 26900 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-03-31 | QTR3 | 16/17 | 2016-10-10 | QTR2 | 16/17 | 717 | 11550400 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7J99 | 42715515201 | 2015-04-08 | QTR4 | 14/15 | 1 | 1 | 199 | 302 | 274 | 28 | 0 | 0 | 103 | 0 | 1844400 | 50000 | 1794400 | 1881240 | 1852163 | 0 | 0 | 0 | 1852163 | 1792416 | -59746 | 36840 | 47 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 37425 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 | 2016-06-28 | QTR4 | 15/16 | 798 | 1650000 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K01 | 43070715201 | 2015-02-11 | QTR3 | 14/15 | 1 | 4 | 360 | 510 | 509 | 1 | 0 | 0 | 93 | 57 | 2815000 | 50000 | 2765000 | 2850595 | 2883182 | 0 | 0 | 0 | 2883182 | 2883115 | -66 | 35595 | 66 | 0 | 57 | 50148 | 0 | 0 | 0 | 26437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 76584 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-04-04 | QTR4 | 16/17 | 2016-12-05 | QTR2 | 16/17 | 709 | 2338000 |  |  | 57 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K02 | 43090115201 | 2015-02-11 | QTR3 | 14/15 | 1 | 3 | 125 | 176 | 176 | 0 | 0 | 0 | 39 | 12 | 2683100 | 50000 | 2633100 | 2806747 | 2817266 | 0 | 0 | 0 | 2817266 | 2772695 | -44571 | 123647 | 34 | 0 | 12 | 67604 | 15358 | 0 | 0 | 123204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 173025 | 15358 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-07-07 | QTR1 | 16/17 | 2015-11-30 | QTR2 | 15/16 | 709 | 2450000 | B0 | ACC - LUMP SUM | 12 | 5 | 0 | 0 | -17782 | 0 |  | DO
07DO | 07 | E7K04 | 43066015201 | 2015-03-11 | QTR3 | 14/15 | 1 | 2 | 180 | 281 | 281 | 0 | 0 | 0 | 82 | 19 | 2680382 | 50000 | 2630382 | 2750471 | 2763085 | 0 | 0 | 0 | 2763085 | 2699178 | -63907 | 70089 | 46 | 0 | 0 | 0 | 0 | 0 | 19 | 111980 | 18119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 19 | 114701 | 18119 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 | 2016-03-14 | QTR3 | 15/16 | 709 | 2007403 | B0 | ACC - LUMP SUM | 19 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K05 | 43243225201 | 2015-03-11 | QTR3 | 14/15 | 1 | 0 | 220 | 262 | 261 | 1 | 0 | 0 | 42 | 0 | 1086230 | 50000 | 1036230 | 1086230 | 1062839 | 0 | 0 | 0 | 1062839 | 1062824 | -15 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591146125 | SIEG & AMBACHTSHEER INC. | N/A | N/A | N/A | N/A | 2016-09-26 | QTR1 | 16/17 | 2016-05-03 | QTR4 | 15/16 | 717 | 1230200 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K06 | 42905615201 | 2015-06-30 | QTR4 | 14/15 | 1 | 4 | 140 | 215 | 215 | 0 | 0 | 0 | 48 | 27 | 4138392 | 50000 | 4088392 | 4373349 | 4094400 | 0 | 0 | 0 | 4094400 | 4010129 | -84271 | 234957 | 28 | 0 | 27 | 111035 | 0 | 0 | 0 | 106967 | 1662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 218003 | 1662 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-04-18 | QTR4 | 16/17 | 2016-06-03 | QTR4 | 15/16 | 709 | 3911400.01 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K07 | 43068515201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 105 | 145 | 145 | 0 | 0 | 0 | 40 | 0 | 1119020 | 42000 | 1077020 | 1119020 | 1092543 | 0 | 0 | 0 | 1092543 | 1092543 | 0 | 0 | 25 | 0 | 0 | 3319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3319 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION INC | N/A | N/A | N/A | N/A | 2016-10-27 | QTR2 | 16/17 | 2016-06-03 | QTR4 | 15/16 | 717 | 885300 | B0 | ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K17 | 43094815201 | 2015-06-10 | QTR4 | 14/15 | 1 | 0 | 220 | 258 | 212 | 46 | 0 | 0 | 38 | 0 | 2888000 | 50000 | 2838000 | 2888000 | 2727932 | 0 | 0 | 0 | 2727932 | 2634048 | -93884 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6682 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-16 | QTR1 | 16/17 | 2016-05-31 | QTR4 | 15/16 | 798 | 3200000 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K29 | 42550325201 | 2015-05-13 | QTR4 | 14/15 | 1 | 0 | 120 | 183 | 155 | 28 | 0 | 0 | 63 | 0 | 1984295 | 50000 | 1934295 | 1984295 | 1950400 | 0 | 0 | 0 | 1950400 | 1950400 | 0 | 0 | 32 | 0 | 0 | 13191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13191 | 0 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2016-10-10 | QTR2 | 16/17 | 2016-05-11 | QTR4 | 15/16 | 717 | 1727700 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K67 | 43149515201 | 2015-05-13 | QTR4 | 14/15 | 1 | 4 | 140 | 178 | 178 | 0 | 0 | 0 | 28 | 10 | 2794895 | 50000 | 2744895 | 2964710 | 2918290 | -7200 | 0 | -7200 | 2911090 | 2905726 | -5363 | 169815 | 17 | 0 | 5 | 49615 | 0 | 0 | 5 | 161418 | 7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 193888 | 7074 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-09-13 | QTR1 | 16/17 | 2016-05-11 | QTR4 | 15/16 | 717 | 1905000 |  |  | 2 | 11 | 0 | 0 | -17145 | 0 |  | DO
07DO | 07 | E7K68 | 43149115201 | 2015-05-13 | QTR4 | 14/15 | 2 | 2 | 200 | 298 | 294 | 4 | 0 | 0 | 69 | 29 | 4031039 | 50000 | 3981039 | 4044189 | 4055974 | 0 | 0 | 0 | 4055974 | 4004687 | -51286 | 13150 | 48 | 0 | 6 | 42639 | 3293 | 0 | 23 | 4531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 59544 | 3293 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 | 2016-07-26 | QTR1 | 16/17 | 709 | 3361350 |  |  | 26 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K76 | 43070625201 | 2015-12-09 | QTR2 | 15/16 | 1 | 0 | 390 | 445 | 409 | 36 | 0 | 0 | 55 | 0 | 2114910 | 50000 | 2064910 | 2114910 | 2214302 | 0 | 0 | 0 | 2214302 | 2214502 | 200 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 5026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5026 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-05-16 | QTR4 | 16/17 | 2017-04-04 | QTR4 | 16/17 | 717 | 2723400 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K78 | 43080235201 | 2015-09-09 | QTR1 | 15/16 | 2 | 0 | 206 | 217 | 128 | 89 | 0 | 0 | 11 | 0 | 1271000 | 50000 | 1221000 | 1271000 | 1221000 | 0 | 0 | 0 | 1221000 | 1221000 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2016-07-12 | QTR1 | 16/17 | 2016-05-10 | QTR4 | 15/16 | 717 | 2206022.47 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K80 | 43478115201 | 2015-08-12 | QTR1 | 15/16 | 2 | 2 | 160 | 203 | 203 | 0 | 0 | 0 | 41 | 2 | 1052289 | 33000 | 1019289 | 1092289 | 992268 | 0 | 0 | 0 | 992268 | 991427 | -840 | 40000 | 21 | 0 | 0 | 7453 | 0 | 0 | 2 | 55456 | 19923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 62908 | 19923 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-24 | QTR1 | 16/17 | 2016-04-29 | QTR4 | 15/16 | 717 | 752249.19 |  |  | 2 | 20 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K84 | 43070615201 | 2015-10-14 | QTR2 | 15/16 | 1 | 0 | 290 | 347 | 345 | 2 | 0 | 0 | 57 | 0 | 2060672 | 50000 | 2010672 | 2060672 | 1940979 | 0 | 0 | 0 | 1940979 | 1940979 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-04-06 | QTR4 | 16/17 | 2017-01-30 | QTR3 | 16/17 | 717 | 2481000 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K88 | 43071015201 | 2016-01-13 | QTR3 | 15/16 | 1 | 1 | 75 | 75 | 34 | 41 | 0 | 0 | 0 | 0 | 716889 | 28000 | 688889 | 655243 | 627243 | 0 | 0 | 0 | 627243 | 627243 | 0 | -61646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -61646 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-12-27 | QTR2 | 16/17 | 2016-08-19 | QTR1 | 16/17 | 717 | 590500 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | -61646 | 0 |  | DO
07DO | 07 | E7K89 | 42905915201 | 2016-03-09 | QTR3 | 15/16 | 1 | 0 | 90 | 124 | 124 | 0 | 0 | 0 | 30 | 4 | 2078378 | 50000 | 2028378 | 2078378 | 1941350 | -25400 | 0 | -25400 | 1915950 | 1919022 | 3072 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 4 | 8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9187 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-02-21 | QTR3 | 16/17 | 2016-10-21 | QTR2 | 16/17 | 717 | 2100000 | B0 | ACC - LUMP SUM | 4 | 6 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K90 | 43386615201 | 2016-02-10 | QTR3 | 15/16 | 1 | 0 | 60 | 61 | 59 | 2 | 0 | 0 | 1 | 0 | 795744 | 15000 | 780744 | 795744 | 787111 | 0 | 0 | 0 | 787111 | 787111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5751 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-10-12 | QTR2 | 16/17 | 2016-07-29 | QTR1 | 16/17 | 717 | 455000 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K92 | 42749515201 | 2016-06-08 | QTR4 | 15/16 | 1 | 1 | 40 | 49 | 49 | 0 | 0 | 0 | 9 | 0 | 377368 | 1590 | 375778 | 396118 | 378995 | 0 | 0 | 0 | 378995 | 378995 | 0 | 18750 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 3175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-04-14 | QTR4 | 16/17 | 2017-03-05 | QTR3 | 16/17 | 717 | 201276 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K93 | 42749615201 | 2016-01-13 | QTR3 | 15/16 | 1 | 1 | 50 | 63 | 63 | 0 | 0 | 0 | 13 | 0 | 429380 | 7100 | 422280 | 432555 | 431202 | 0 | 0 | 0 | 431202 | 431202 | 0 | 3175 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8922 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-01-06 | QTR3 | 16/17 | 2016-07-06 | QTR1 | 16/17 | 709 | 252301.19 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K94 | 42750115201 | 2016-02-10 | QTR3 | 15/16 | 1 | 1 | 50 | 60 | 59 | 1 | 0 | 0 | 10 | 0 | 652140 | 14000 | 638140 | 665253 | 647487 | 0 | 0 | 0 | 647487 | 647487 | 0 | 13113 | 6 | 0 | 0 | 10385 | 0 | 0 | 0 | 2728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13113 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-03-06 | QTR3 | 16/17 | 2016-09-14 | QTR1 | 16/17 | 717 | 350000 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K96 | 42896915201 | 2016-03-31 | QTR3 | 15/16 | 1 | 1 | 120 | 178 | 178 | 0 | 0 | 0 | 39 | 19 | 2176471 | 50000 | 2126471 | 2176471 | 2177273 | 0 | 0 | 0 | 2177273 | 2177273 | 0 | 0 | 18 | 0 | 0 | 37837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37837 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-06-29 | QTR4 | 16/17 | 2017-03-17 | QTR3 | 16/17 | 717 | 1980000 | B0 | ACC - LUMP SUM | 19 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K99 | 43625515201 | 2016-03-09 | QTR3 | 15/16 | 1 | 1 | 50 | 51 | 37 | 14 | 0 | 0 | 1 | 0 | 160902 | 4125 | 156777 | 182550 | 178425 | 0 | 0 | 0 | 178425 | 178425 | 0 | 21648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21648 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-10-31 | QTR2 | 16/17 | 2016-07-26 | QTR1 | 16/17 | 717 | 165500 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L02 | 43472915201 | 2016-06-08 | QTR4 | 15/16 | 1 | 0 | 100 | 134 | 132 | 2 | 0 | 0 | 34 | 0 | 2090000 | 50000 | 2040000 | 2090000 | 2025548 | 0 | 0 | 0 | 2025548 | 2025548 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-05-15 | QTR4 | 16/17 | 2017-02-25 | QTR3 | 16/17 | 717 | 1628500 | B0 | ACC - LUMP SUM | 0 | 22 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L07 | 43258315201 | 2015-11-12 | QTR2 | 15/16 | 1 | 0 | 80 | 89 | 89 | 0 | 0 | 0 | 5 | 4 | 1115377 | 50000 | 1065377 | 1115377 | 1056390 | 0 | 0 | 0 | 1056390 | 1056390 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25933 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-07-22 | QTR1 | 16/17 | 2016-05-03 | QTR4 | 15/16 | 798 | 1450000 | B0 | ACC - LUMP SUM | 4 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L29 | 42717125201 | 2016-06-08 | QTR4 | 15/16 | 1 | 0 | 115 | 145 | 145 | 0 | 0 | 0 | 30 | 0 | 567079 | 20000 | 547079 | 567079 | 554076 | 0 | 0 | 0 | 554076 | 554076 | 0 | 0 | 5 | 0 | 0 | 1851 | 0 | 0 | 0 | 5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6997 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-04-12 | QTR4 | 16/17 | 2017-03-10 | QTR3 | 16/17 | 717 | 490000 | B0 | ACC - LUMP SUM | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L38 | 43936215201 | 2016-06-08 | QTR4 | 15/16 | 1 | 2 | 100 | 116 | 105 | 11 | 0 | 0 | 16 | 0 | 281697 | 10500 | 271197 | 282895 | 265516 | 0 | 0 | 0 | 265516 | 265516 | 0 | 1199 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2017-02-14 | QTR3 | 16/17 | 2016-12-06 | QTR2 | 16/17 | 709 | 275000 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L40 | 43940015201 | 2016-07-13 | QTR1 | 16/17 | 1 | 0 | 30 | 38 | 38 | 0 | 0 | 0 | 3 | 5 | 142928 | 3530 | 139398 | 142928 | 136015 | 0 | 0 | 0 | 136015 | 136015 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 2967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2967 | 0 | F270559642 | CITY WIDE PAVING LLC | N/A | N/A | N/A | N/A | 2017-03-07 | QTR3 | 16/17 | 2016-11-23 | QTR2 | 16/17 | 798 | 150000 |  |  | 5 | 0 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M60 | 43127515201 | 2013-01-22 | QTR3 | 12/13 | 3 | 33 | 1055 | 1167 | 1167 | 0 | 0 | 0 | 112 | 0 | 56648757 | 150000 | 56498757 | 57438075 | 57810006 | 0 | 0 | 0 | 57810006 | 57069148 | -740858 | 789318 | 68 | 0 | 0 | 324282 | 0 | 0 | 0 | 229213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568192 | 23585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 32879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 843308 | 23585 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2016-11-30 | QTR2 | 16/17 | 2016-06-30 | QTR4 | 15/16 | 854 | 56376201.62 |  |  | 0 | 40 | 0 | 0 | -311259 | 0 |  | DO
08DO | 08 | E8M62 | 40615115201 | 2013-02-26 | QTR3 | 12/13 | 2 | 19 | 995 | 1321 | 1336 | -15 | 15 | 0 | 214 | 112 | 46046392 | 150000 | 45896392 | 46822521 | 47408243 | -137490 | 0 | -137490 | 47270753 | 46013135 | -1257618 | 776129 | 142 | 0 | 0 | 162157 | 0 | 10 | 112 | 852634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 112 | 805848 | 0 | F650143860 | ASTALDI CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2017-05-31 | QTR4 | 16/17 | 2017-01-23 | QTR3 | 16/17 | 854 | 51466143.9 | B5 | ACC - INCENTIVE/DISINCENTIVE | 53 | 62 | 0 | 0 | -210973 | 0 |  | DO
08DO | 08 | E8M63 | 40615215201 | 2013-02-05 | QTR3 | 12/13 | 3 | 16 | 995 | 1179 | 1179 | 0 | 0 | 0 | 170 | 14 | 57400000 | 150000 | 57250000 | 57854468 | 58114118 | -10000 | 0 | -10000 | 58104118 | 57193979 | -910139 | 454468 | 108 | 0 | 0 | 135877 | 1764 | 7 | 14 | 647998 | 24913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 489562 | 26677 | F841163868 | SEMA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-02 | QTR2 | 16/17 | 2016-07-20 | QTR1 | 16/17 | 854 | 59063480.38 |  |  | 0 | 55 | 0 | 0 | -365840 | 0 |  | DO
08DO | 08 | E8N60 | 41546265201 | 2014-05-20 | QTR4 | 13/14 | 1 | 3 | 475 | 545 | 545 | 0 | 0 | 0 | 70 | 0 | 10628174 | 96840 | 10531334 | 10702005 | 10703365 | -6500 | 0 | -6500 | 10696865 | 10548835 | -148030 | 73831 | 23 | 0 | 0 | 8969 | 0 | 0 | 0 | 107706 | 13562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 117912 | 13562 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-29 | QTR1 | 16/17 | 2016-04-12 | QTR4 | 15/16 | 854 | 9781121.21 |  |  | 0 | 46 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N68 | 24301715201 | 2014-06-09 | QTR4 | 13/14 | 2 | 4 | 480 | 643 | 642 | 1 | 0 | 0 | 163 | 0 | 16844000 | 150000 | 16694000 | 17989634 | 18429954 | -3000 | 0 | -3000 | 18426954 | 17949122 | -477832 | 1145634 | 44 | 0 | 0 | 71261 | 0 | 29 | 0 | 246343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 947444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 1265048 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-12 | QTR2 | 16/17 | 2016-07-29 | QTR1 | 16/17 | 854 | 15034152.99 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P54 | 43110015201 | 2015-10-20 | QTR2 | 15/16 | 1 | 1 | 115 | 121 | 118 | 3 | 0 | 0 | 6 | 0 | 1369271 | 50000 | 1319271 | 1355607 | 1258468 | 0 | 0 | 0 | 1258468 | 1224485 | -33984 | -13664 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13664 | 12601 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-08-04 | QTR1 | 16/17 | 2016-06-24 | QTR4 | 15/16 | 854 | 1662320.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P55 | 43561715201 | 2015-06-16 | QTR4 | 14/15 | 1 | 1 | 140 | 189 | 189 | 0 | 0 | 0 | 45 | 4 | 1736149 | 50000 | 1686149 | 1766298 | 1678250 | -26500 | 0 | -26500 | 1651750 | 1651060 | -690 | 30149 | 29 | 0 | 4 | 30149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 30149 | 0 | F203908361 | MIDASCO LLC | N/A | N/A | N/A | N/A | 2016-08-02 | QTR1 | 16/17 | 2016-05-24 | QTR4 | 15/16 | 854 | 1991671.8 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q15 | 43753215201 | 2016-10-18 | QTR2 | 16/17 | 1 | 1 | 190 | 190 | 31 | 159 | 0 | 0 | 0 | 0 | 318543 | 25415 | 293128 | 301705 | 250071 | 0 | 0 | 0 | 250071 | 250071 | 0 | -16837 | 0 | 0 | 0 | -16837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16837 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2017-05-31 | QTR4 | 16/17 | 2017-03-15 | QTR3 | 16/17 | 854 | 796207.04 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
01DO | 01 | E1K48 | 41306615201 | 2012-06-28 | QTR4 | 11/12 | 1 | 5 | 890 | 1143 | 1143 | 0 | 0 | 0 | 241 | 12 | 71757500 | 150000 | 71607500 | 71569947 | 71423852 | 0 | 0 | 0 | 71423852 | 0 | -71423852 | -187553 | 155 | 28 | 12 | 180991 | 12852 | 0 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 12 | -153550 | 12852 | F454673542 | DE MOYA / LEWARE JV | N/A | N/A | N/A | N/A | 2016-08-08 | QTR1 | 16/17 | 2015-12-08 | QTR2 | 15/16 | 106 | 80270500 | B8:DBF:P3 | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP | 0 | 58 | 0 | 0 | -339346 | 0 |  | DO | 0 | 01co | 1 | 0
07CO | 07 | T7213 | 25688115201 | 2009-08-05 | QTR1 | 09/10 | 18 | 82 | 1665 | 2466 | 2466 | 0 | 0 | 0 | 339 | 462 | 109468948 | 150000 | 109318948 | 122321407 | 123527139 | -40000 | 0 | -40000 | 123487139 | 121727984 | -1759155 | 12852459 | 226 | 0 | 395 | 10043878 | 374564 | 0 | 12 | 2039723 | 251127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 0 | 0 | 126912 | 15529 | 0 | 0 | 1785 | 1785 | 0 | 0 | 0 | 0 | 0 | 0 | 4858 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 405345 | 405345 | 0 | 0 | 0 | 0 | 0 | 462 | 12838502 | 1048350 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-06-05 | QTR4 | 16/17 | 2016-08-30 | QTR1 | 16/17 | 714 | 131526034.82 | ARRA:B1:P3:B:B:B5 | AMERICAN RECOVERY AND REINVEST:ACC - NO EXCUSE BONUS:PUBLIC PRIVATE PARTNERSHIP:ACC - NO EXCUSE BONUS:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 113 | 0 | 0 | 0 | 0 |  | CO | 1 | 01do | 1 | 1
CO | [104 empty] | CO | 0 | 02co | 2 | 1
CO | [104 empty] | CO | 0 | 02do | 2 | 1
CO | [104 empty] | CO | 0 | 03co | 2 | 1
CO | [104 empty] | CO | 0 | 03do | 2 | 1
CO | [104 empty] | CO | 0 | 04co | 2 | 1
CO | [104 empty] | CO | 0 | 04do | 2 | 1
CO | [104 empty] | CO | 0 | 05co | 2 | 1
CO | [103 empty] | T | CO | 0 | 05do | 2 | 1
CO | [104 empty] | CO | 0 | 06co | 2 | 1
CO | [104 empty] | CO | 0 | 06do | 2 | 1
CO | [104 empty] | CO | 1 | 07co | 2 | 2
CO | [104 empty] | CO | 0 | 07do | 3 | 2
CO | [104 empty] | CO | 0 | 08co | 3 | 2
CO | [104 empty] | CO | 0 | 08do | 3 | 2
CO | [104 empty] | CO
CO | [104 empty] | CO
CO | [104 empty] | CO |  | 0