## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 11002672 | 10740095 | 11098761 | 10797871 | 0 | 10793117 | 0.4937% | 100% | 145213 | 1.352% | 96089 | 0.8733% | 890 | 56 | 6.292% | 75 | 8.427% | 14 | 1.573% | 36 | 4.045% | 940 | 5.618% | 1076 | 1074 | 943 | 5.955% | 100%
| District Let | 5276221 | 5134491 | 5320448 | 5245832 | 0 | 5247102 | 2.193% | 100% | 88109 | 1.716% | 44227 | 0.8382% | 485 | 12 | 2.474% | 17 | 3.505% | 14 | 2.887% | 0 | 0% | 499 | 2.887% | 528 | 503 | 474 | -2.268% | 100%
| All Contracts | 16278893 | 15874586 | 16419209 | 16043703 | 0 | 16040219 | 1.043% | 100% | 233322 | 1.47% | 140316 | 0.862% | 1375 | 68 | 4.945% | 92 | 6.691% | 28 | 2.036% | 36 | 2.618% | 1439 | 4.655% | 1604 | 1577 | 1417 | 3.055% | 100%
2 | Central Let | 27220013 | 26835846 | 27482269 | 27527584 | 0 | 26508965 | -1.218% | 100% | 372010 | 1.386% | 262256 | 0.9635% | 2080 | 245 | 11.78% | 149 | 7.163% | 0 | 0% | 76 | 3.654% | 2156 | 3.654% | 2550 | 2542 | 2148 | 3.269% | 87.5%
| District Let | 51606714 | 51264421 | 51945624 | 51310160 | 0 | 50768684 | -0.967% | 75% | 519194 | 1.013% | 338910 | 0.6567% | 1356 | 172 | 12.68% | 154 | 11.36% | 61 | 4.499% | 127 | 9.366% | 1544 | 13.86% | 1870 | 1863 | 1537 | 13.35% | 100%
| All Contracts | 78826727 | 78100267 | 79427893 | 78837744 | 0 | 77277649 | -1.053% | 91.67% | 891204 | 1.141% | 601166 | 0.7626% | 3436 | 417 | 12.14% | 303 | 8.818% | 61 | 1.775% | 203 | 5.908% | 3700 | 7.683% | 4420 | 4405 | 3685 | 7.247% | 91.67%
3 | Central Let | 54995108 | 54494752 | 57762308 | 57826987 | 0 | 56566212 | 3.801% | 92.31% | 3496369 | 6.416% | 2767201 | 5.032% | 2610 | 824 | 31.57% | 260 | 9.962% | 351 | 13.45% | 311 | 11.92% | 3272 | 25.36% | 4334 | 4279 | 3195 | 22.41% | 76.92%
| District Let | 13488001 | 13202446 | 13594576 | 13583823 | 0 | 13598458 | 3% | 100% | 133803 | 1.013% | 106575 | 0.7901% | 805 | 115 | 14.29% | 75 | 9.317% | 145 | 18.01% | 0 | 0% | 950 | 18.01% | 1140 | 1143 | 953 | 18.39% | 71.43%
| All Contracts | 68483109 | 67697198 | 71356884 | 71410810 | 0 | 70164670 | 3.645% | 95% | 3630172 | 5.362% | 2873776 | 4.196% | 3415 | 939 | 27.5% | 335 | 9.81% | 496 | 14.52% | 311 | 9.107% | 4222 | 23.63% | 5474 | 5422 | 4148 | 21.46% | 75%
4 | Central Let | 10134705 | 9898403 | 10274062 | 10074440 | 50000 | 9977687 | 0.801% | 80% | 193344 | 1.953% | 139357 | 1.375% | 1168 | 172 | 14.73% | 58 | 4.966% | 0 | 0% | 34 | 2.911% | 1202 | 2.911% | 1432 | 1352 | 1122 | -3.938% | 100%
| District Let | 2174636 | 2097848 | 2174636 | 2041048 | 0 | 2040933 | -2.713% | 100% | 19200 | 0.9152% | 0 | 0% | 385 | 39 | 10.13% | 24 | 6.234% | 0 | 0% | 0 | 0% | 385 | 0% | 448 | 442 | 379 | -1.558% | 100%
| All Contracts | 12309341 | 11996251 | 12448698 | 12115488 | 50000 | 12018620 | 0.1865% | 87.5% | 212544 | 1.772% | 139357 | 1.132% | 1553 | 211 | 13.59% | 82 | 5.28% | 0 | 0% | 34 | 2.189% | 1587 | 2.189% | 1880 | 1794 | 1501 | -3.348% | 100%
5 | Central Let | 26947347 | 26547347 | 27358053 | 27199241 | 0 | 26799003 | 0.948% | 100% | 488878 | 1.842% | 410706 | 1.524% | 1435 | 96 | 6.69% | 108 | 7.526% | 0 | 0% | 178 | 12.4% | 1613 | 12.4% | 1843 | 1869 | 1665 | 16.03% | 66.67%
| District Let | 2189577 | 2098577 | 2195324 | 2053959 | 0 | 2028746 | -3.328% | 100% | 5747 | 0.2739% | 5747 | 0.2625% | 320 | 48 | 15% | 45 | 14.06% | 0 | 0% | 8 | 2.5% | 328 | 2.5% | 423 | 427 | 334 | 4.375% | 66.67%
| All Contracts | 29136924 | 28645924 | 29553377 | 29253200 | 0 | 28827749 | 0.6347% | 100% | 494625 | 1.727% | 416453 | 1.429% | 1755 | 144 | 8.205% | 153 | 8.718% | 0 | 0% | 186 | 10.6% | 1941 | 10.6% | 2266 | 2296 | 1999 | 13.9% | 66.67%
6 | Central Let | 31259268 | 30363247 | 31531115 | 30408106 | 1016000 | 29943724 | -1.382% | 100% | 516266 | 1.7% | 271848 | 0.8697% | 1820 | 203 | 11.15% | 91 | 5% | 40 | 2.198% | 34 | 1.868% | 1894 | 4.066% | 2188 | 2013 | 1719 | -5.549% | 100%
| District Let | 5756716 | 5452282 | 5564978 | 5177545 | 0 | 5178497 | -5.021% | 100% | -146383 | -2.685% | -191738 | -3.331% | 2115 | 277 | 13.1% | 70 | 3.31% | 0 | 0% | 0 | 0% | 2115 | 0% | 2462 | 2278 | 1931 | -8.7% | 100%
| All Contracts | 37015984 | 35815529 | 37096093 | 35585651 | 1016000 | 35122221 | -1.936% | 100% | 369883 | 1.033% | 80110 | 0.2164% | 3935 | 480 | 12.2% | 161 | 4.091% | 40 | 1.017% | 34 | 0.864% | 4009 | 1.881% | 4650 | 4291 | 3650 | -7.243% | 100%
7 | Central Let | 121108174 | 120672174 | 125975177 | 129579326 | 0 | 127514497 | 5.67% | 100% | 4751768 | 3.938% | 4867001 | 4.019% | 2750 | 522 | 18.98% | 184 | 6.691% | 6 | 0.2182% | 163 | 5.927% | 2919 | 6.145% | 3625 | 3623 | 2917 | 6.073% | 100%
| District Let | 10378889 | 10278889 | 10378889 | 10405733 | 0 | 10354211 | 0.7328% | 100% | 42916 | 0.4175% | 0 | 0% | 680 | 97 | 14.26% | 51 | 7.5% | 12 | 1.765% | 73 | 10.74% | 765 | 12.5% | 913 | 913 | 765 | 12.5% | 100%
| All Contracts | 131487063 | 130951063 | 136354066 | 139985059 | 0 | 137868708 | 5.283% | 100% | 4794684 | 3.661% | 4867001 | 3.702% | 3430 | 619 | 18.05% | 235 | 6.851% | 18 | 0.5248% | 236 | 6.88% | 3684 | 7.405% | 4538 | 4536 | 3682 | 7.347% | 100%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 4130517 | 3985054 | 4122888 | 3961484 | 0 | 3988430 | 0.08472% | 100% | 70821 | 1.777% | -7629 | -0.1847% | 545 | 19 | 3.486% | 51 | 9.358% | 0 | 0% | 14 | 2.569% | 559 | 2.569% | 629 | 627 | 557 | 2.202% | 100%
| All Contracts | 4130517 | 3985054 | 4122888 | 3961484 | 0 | 3988430 | 0.08472% | 100% | 70821 | 1.777% | -7629 | -0.1847% | 545 | 19 | 3.486% | 51 | 9.358% | 0 | 0% | 14 | 2.569% | 559 | 2.569% | 629 | 627 | 557 | 2.202% | 100%
Totals This Qtr | Central Let | 282667287 | 279551864 | 291481745 | 293413555 | 1066000 | 288103205 | 3.059% | 95.92% | 9963848 | 3.564% | 8814458 | 3.118% | 12753 | 2118 | 16.61% | 925 | 7.253% | 411 | 3.223% | 832 | 6.524% | 13996 | 9.747% | 17048 | 16752 | 13709 | 7.496% | 87.76%
| District Let | 95001271 | 93514008 | 95297363 | 93779584 | 0 | 93205061 | -0.3304% | 97.06% | 733407 | 0.7843% | 296092 | 0.3117% | 6691 | 779 | 11.64% | 487 | 7.278% | 232 | 3.467% | 222 | 3.318% | 7145 | 6.785% | 8413 | 8196 | 6930 | 3.572% | 91.18%
| All Contracts | 377668558 | 373065872 | 386779108 | 387193139 | 1066000 | 381308266 | 2.209% | 96.39% | 10697255 | 2.867% | 9110550 | 2.412% | 19444 | 2897 | 14.9% | 1412 | 7.262% | 643 | 3.307% | 1054 | 5.421% | 21141 | 8.728% | 25461 | 24948 | 20639 | 6.146% | 89.16%
Totals Previous Quarter | Central Let
District Let
All Contracts
Totals Fiscal Year 2016/2017 | Central Let | 1381361712 | 1370566791 | 1454062050 | 1457184141 | 10567700 | 1434646073 | 4.675% | 92.51% | 79425966 | 5.795% | 75161278 | 5.441% | 51396 | 8294 | 16.14% | 3375 | 6.567% | 1395 | 2.714% | 3377 | 6.571% | 56168 | 9.285% | 67811 | 66913 | 55244 | 7.487% | 86.63%
| District Let | 882059491 | 874520440 | 919907438 | 919732288 | 3166600 | 899991484 | 2.913% | 90.71% | 40110545 | 4.587% | 37847952 | 4.291% | 34261 | 5089 | 14.85% | 2339 | 6.827% | 759 | 2.215% | 3059 | 8.929% | 38079 | 11.14% | 45591 | 44497 | 37069 | 8.196% | 89.29%
| All Contracts | 2263421203 | 2245087231 | 2373969488 | 2376916429 | 13734300 | 2334637557 | 3.989% | 91.74% | 119536511 | 5.324% | 113009230 | 4.993% | 85657 | 13383 | 15.62% | 5714 | 6.671% | 2154 | 2.515% | 6436 | 7.514% | 94247 | 10.03% | 113402 | 111410 | 92313 | 7.771% | 87.77%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1625 | 42988315201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 150 | 198 | 198 | 114.7% | 1 | 0 | 0 | 0 | 40 | 8 | 1852000 | 50000 | 1802000 | 1866275 | 1867608 | 0 | 0 | 0 | 1867608 | 1867700 | 103.6% | 1 | 92 | 14275 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 8 | 26881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8 | 26881 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-04-11 | QTR4 | 16/17 | 108 | 2064220.28
| 01 | T1628 | 43011915201 | 2016-01-27 | QTR3 | 15/16 | 2 | 3 | 250 | 289 | 289 | 101.2% | 1 | 0 | 0 | 0 | 36 | 3 | 5092548 | 54005 | 5038543 | 5147816 | 5084411 | 0 | 0 | 0 | 5084411 | 5074685 | 100.7% | 1 | -9725 | 55268 | 16 | 20 | 0 | 0 | 9739 | 0 | 0 | 3 | 56544 | 5272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 66284 | 5272 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-27 | QTR1 | 17/18 |  | 2017-04-05 | QTR4 | 16/17 | 113 | 5336136.69
| 01 | T1658 | 43902815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 175 | 214 | 210 | 103.4% | 1 | 4 | 0 | 0 | 29 | 10 | 2041864 | 54329 | 1987535 | 2041864 | 1925079 | 0 | 0 | 0 | 1925079 | 1925198 | 96.86% | 1 | 118 | 0 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 10 | 16588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 16588 | 0 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-06-12 | QTR4 | 16/17 | 113 | 4696299.51
| 01 | T1662 | 43132515201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 75 | 90 | 97 | 109.3% | 1 | -7 | 7 | 0 | 15 | 0 | 150000 | 7492 | 142508 | 150000 | 141366 | -6706 | 0 | -6706 | 134660 | 134660 | 94.49% | 1 | 0 | 0 | 4 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452357137 | YD WEST COAST HOME INC | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-03-03 | QTR3 | 16/17 | 118 | 195237.61 | B0 | ACC - LUMP SUM
| 01 | T1668 | 43450715201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 100 | 104 | 99 | 95% | 1 | 5 | 0 | 0 | 4 | 0 | 860000 | 50000 | 810000 | 860000 | 810000 | 0 | 0 | 0 | 810000 | 810000 | 100% | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-07-17 | QTR1 | 17/18 |  | 2017-04-25 | QTR4 | 16/17 | 108 | 1005379.75 | B0 | ACC - LUMP SUM
| 01 | T1A01 | 43134015201 | 2016-07-27 | QTR1 | 16/17 | 2 | 1 | 140 | 181 | 181 | 114.3% | 1 | 0 | 0 | 0 | 26 | 15 | 1006260 | 46751 | 959509 | 1032806 | 969407 | 0 | 0 | 0 | 969407 | 980874 | 102.2% | 1 | 11467 | 26546 | 7 | 14 | 0 | 15 | 35460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 35460 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-08-04 | QTR1 | 17/18 |  | 2017-06-03 | QTR4 | 16/17 | 118 | 1134236.85
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 6 | 8 | 7 | 890 | 1076 | 1074 | 100% | 6 | 2 | 7 | 0 | 150 | 36 | 11002672 | 262577 | 10740095 | 11098761 | 10797871 | -6706 | 0 | -6706 | 10791165 | 10793117 | 100% | 6 | 1952 | 96089 | 56 | 75 | 0 | 15 | 45199 | 0 | 0 | 21 | 100013 | 5272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 36 | 145213 | 5272
| 01 | E1O50 | 43121215201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 160 | 168 | 145 | 85.62% | 1 | 23 | 0 | 0 | 8 | 0 | 2473492 | 50000 | 2423492 | 2473492 | 2430162 | 0 | 0 | 0 | 2430162 | 2431258 | 100.3% | 1 | 1097 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-06-02 | QTR4 | 16/17 | 115 | 2383341.22 | B0 | ACC - LUMP SUM
| 01 | E1O53 | 43486515201 | 2015-12-17 | QTR2 | 15/16 | 1 | 3 | 245 | 278 | 278 | 105.7% | 1 | 0 | 0 | 0 | 33 | 0 | 1972999 | 50000 | 1922999 | 2017226 | 2027670 | 0 | 0 | 0 | 2027670 | 2027844 | 105.5% | 1 | 174 | 44227 | 5 | 14 | 14 | 0 | 37826 | 0 | 0 | 0 | 38283 | 12197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 88109 | 12197 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-10 | QTR1 | 17/18 |  | 2017-05-26 | QTR4 | 16/17 | 115 | 1579998.38
| 01 | E1P64 | 43172315201 | 2016-08-18 | QTR1 | 16/17 | 1 | 0 | 80 | 82 | 80 | 97.5% | 1 | 2 | 0 | 0 | 2 | 0 | 829730 | 41730 | 788000 | 829730 | 788000 | 0 | 0 | 0 | 788000 | 788000 | 100% | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 |  | 2017-05-31 | QTR4 | 16/17 | 118 | 915006.57 | B0 | ACC - LUMP SUM
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 3 | 3 | 3 | 485 | 528 | 503 | 100% | 3 | 25 | 0 | 0 | 43 | 0 | 5276221 | 141730 | 5134491 | 5320448 | 5245832 | 0 | 0 | 0 | 5245832 | 5247102 | 100% | 3 | 1271 | 44227 | 12 | 17 | 14 | 0 | 37826 | 0 | 0 | 0 | 38283 | 12197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 88109 | 12197
| District 01 Totals |  |  |  |  | 9 | 11 | 10 | 1375 | 1604 | 1577 | 100% | 9 | 27 | 7 | 0 | 193 | 36 | 16278893 | 404307 | 15874586 | 16419209 | 16043703 | -6706 | 0 | -6706 | 16036997 | 16040219 | 100% | 9 | 3223 | 140316 | 68 | 92 | 14 | 15 | 83025 | 0 | 0 | 21 | 138296 | 17469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 36 | 233322 | 17469
| 02 | T2548 | 20939965201 | 2014-08-27 | QTR1 | 14/15 | 2 | 2 | 770 | 923 | 919 | 99.48% | 1 | 4 | 0 | 0 | 153 | 0 | 14832876 | 150000 | 14682876 | 14931694 | 15170352 | 0 | 0 | 0 | 15170352 | 14252602 | 97.07% | 1 | -917750 | 98818 | 93 | 60 | 0 | 0 | 40183 | 0 | 0 | 0 | 37352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149669 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 |  | 2017-05-19 | QTR4 | 16/17 | 208 | 15494259.21
| 02 | T2599 | 43726615201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 180 | 213 | 213 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 1048048 | 50000 | 998048 | 1048048 | 985628 | 0 | 0 | 0 | 985628 | 985628 | 98.76% | 1 | 0 | 0 | 13 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-07-14 | QTR1 | 17/18 |  | 2017-02-21 | QTR3 | 16/17 | 216 | 1120328.18
| 02 | T2601 | 21166315201 | 2015-10-28 | QTR2 | 15/16 | 1 | 1 | 400 | 443 | 440 | 100% | 1 | 3 | 0 | 0 | 40 | 3 | 3712278 | 0 | 3712278 | 3713235 | 3797768 | 0 | 0 | 0 | 3797768 | 3782265 | 101.9% | 1 | -15503 | 957 | 23 | 17 | 0 | 3 | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 957 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 |  | 2017-04-13 | QTR4 | 16/17 | 209 | 4020991.68
| 02 | T2619 | 43265715201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 150 | 164 | 160 | 97.33% | 1 | 4 | 0 | 0 | 14 | 0 | 985253 | 39196 | 946057 | 985253 | 900611 | 0 | 0 | 0 | 900611 | 903976 | 95.55% | 1 | 3365 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-04 | QTR1 | 17/18 |  | 2016-12-28 | QTR2 | 16/17 | 209 | 823384.31
| 02 | T2629 | 43056215201 | 2015-12-03 | QTR2 | 15/16 | 4 | 1 | 175 | 283 | 298 | 128.6% | 0 | -15 | 15 | 0 | 73 | 35 | 3955571 | 57673 | 3897898 | 4118052 | 4040559 | -43140 | 0 | -43140 | 3997419 | 3949454 | 101.3% | 1 | -47965 | 162481 | 57 | 16 | 0 | 35 | 162481 | 0 | 0 | 0 | 26106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 188587 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 |  | 2017-01-05 | QTR3 | 16/17 | 208 | 3564631.32
| 02 | T2635 | 42470035201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 75 | 140 | 135 | 104% | 1 | 5 | 0 | 0 | 57 | 8 | 348154 | 16878 | 331276 | 348154 | 353179 | 0 | 0 | 0 | 353179 | 353179 | 106.6% | 1 | 0 | 0 | 45 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11425 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-09-26 | QTR1 | 17/18 |  | 2017-07-11 | QTR1 | 17/18 | 208 | 330103.8
| 02 | T2644 | 43429515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 90 | 93 | 86 | 92.22% | 1 | 7 | 0 | 0 | 3 | 0 | 1424722 | 50000 | 1374722 | 1424722 | 1389257 | 0 | 0 | 0 | 1389257 | 1391632 | 101.2% | 1 | 2374 | 0 | 3 | 0 | 0 | 0 | 547 | 0 | 0 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 |  | 2017-04-12 | QTR4 | 16/17 | 209 | 1869641.02
| 02 | T9015 | 43475815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 240 | 291 | 291 | 112.5% | 1 | 0 | 0 | 0 | 21 | 30 | 913111 | 20420 | 892691 | 913111 | 890230 | 0 | 0 | 0 | 890230 | 890229 | 99.72% | 1 | -1 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 30 | 20420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20420 | 0 | F593504786 | ANGLIN CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-08-08 | QTR1 | 17/18 |  | 2017-06-28 | QTR4 | 16/17 | 209 | 612984.42
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 8 | 12 | 5 | 2080 | 2550 | 2542 | 87.5% | 7 | 8 | 15 | 0 | 394 | 76 | 27220013 | 384167 | 26835846 | 27482269 | 27527584 | -43140 | 0 | -43140 | 27484444 | 26508965 | 100% | 8 | -975480 | 262256 | 245 | 149 | 0 | 38 | 204168 | 0 | 0 | 30 | 84283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 14016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 372010 | 0
| 02 | E2R19 | 20960715201 | 2013-12-12 | QTR2 | 13/14 | 1 | 2 | 800 | 1141 | 1139 | 118.3% | 1 | 2 | 0 | 0 | 254 | 87 | 44244000 | 150000 | 44094000 | 44497660 | 44485464 | 0 | 0 | 0 | 44485464 | 43929908 | 99.63% | 1 | -555556 | 253660 | 105 | 88 | 61 | 87 | 261680 | 29435 | 0 | 0 | 49212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 87 | 367067 | 29435 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2017-08-17 | QTR1 | 17/18 |  | 2017-03-27 | QTR3 | 16/17 | 208 | 49888540.47 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 112.2% | 1 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 110.4% | 0 | 11678 | 85250 | 19 | 18 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 |  | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91
| 02 | E2U92 | 43015715201 | 2016-03-16 | QTR3 | 15/16 | 1 | 0 | 200 | 277 | 277 | 105% | 1 | 0 | 0 | 0 | 67 | 10 | 4567769 | 50000 | 4517769 | 4567769 | 4034344 | 0 | 0 | 0 | 4034344 | 4034680 | 89.31% | 1 | 336 | 0 | 29 | 38 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 |  | 2017-05-19 | QTR4 | 16/17 | 208 | 3766652.07
| 02 | E2V03 | 43242015201 | 2016-05-18 | QTR4 | 15/16 | 1 | 0 | 126 | 155 | 152 | 97.62% | 1 | 3 | 0 | 0 | 29 | 0 | 1065911 | 42293 | 1023618 | 1065911 | 1003076 | 0 | 0 | 0 | 1003076 | 1005142 | 98.2% | 1 | 2066 | 0 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 |  | 2017-04-28 | QTR4 | 16/17 | 209 | 900493.11
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 4 | 5 | 4 | 1356 | 1870 | 1863 | 100% | 4 | 7 | 0 | 0 | 387 | 127 | 51606714 | 342293 | 51264421 | 51945624 | 51310160 | 0 | 0 | 0 | 51310160 | 50768684 | 75% | 3 | -541476 | 338910 | 172 | 154 | 61 | 93 | 392364 | 29435 | 0 | 34 | 70656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 127 | 519194 | 29435
| District 02 Totals |  |  |  |  | 12 | 17 | 9 | 3436 | 4420 | 4405 | 91.67% | 11 | 15 | 15 | 0 | 781 | 203 | 78826727 | 726460 | 78100267 | 79427893 | 78837744 | -43140 | 0 | -43140 | 78794604 | 77277649 | 91.67% | 11 | -1516956 | 601166 | 417 | 303 | 61 | 131 | 596532 | 29435 | 0 | 64 | 154939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39600 | 0 | 0 | 8 | 14016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 203 | 891204 | 29435
| 03 | T3380 | 22067915201 | 2012-05-23 | QTR4 | 11/12 | 2 | 16 | 955 | 1636 | 1636 | 128.7% | 0 | 0 | 0 | 0 | 456 | 225 | 27973197 | 150000 | 27823197 | 28765517 | 28817877 | 0 | 0 | 0 | 28817877 | 27757494 | 99.76% | 1 | -1060383 | 792320 | 319 | 88 | 5 | 0 | 135159 | 0 | 37 | 70 | 1137365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 177 | 426650 | 213490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -797630 | 0 | 49 | 247 | 1502304 | 213490 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-07-31 | QTR1 | 17/18 |  | 2017-03-03 | QTR3 | 16/17 | 313 | 27697061.12
| 03 | T3484 | 43000215201 | 2015-02-25 | QTR3 | 14/15 | 3 | 14 | 300 | 644 | 600 | 159.3% | 0 | 44 | 0 | 0 | 315 | 29 | 4296119 | 0 | 4296119 | 6114814 | 6340441 | 0 | 0 | 0 | 6340441 | 6332694 | 147.4% | 0 | -7747 | 1818695 | 99 | 23 | 0 | 1 | 6824 | 0 | 0 | 7 | 1522085 | 1237952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 7 | 245665 | 82769 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 44120 | 44120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 29 | 1818695 | 1364841 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-05-05 | QTR4 | 16/17 | 308 | 3303857.17
| 03 | T3521 | 43078515201 | 2015-12-03 | QTR2 | 15/16 | 3 | 2 | 200 | 397 | 409 | 148.5% | 0 | -12 | 12 | 0 | 196 | 1 | 2580711 | 50000 | 2530711 | 2556235 | 2428112 | -31636 | 0 | -31636 | 2396476 | 2365069 | 93.45% | 1 | -31407 | -24476 | 75 | 37 | 8 | 1 | 1155 | 0 | 73 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | -20162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1 | -15973 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 |  | 2017-03-31 | QTR3 | 16/17 | 308 | 2532090.83
| 03 | T3528 | 22281815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 120 | 139 | 138 | 106.7% | 1 | 1 | 0 | 0 | 19 | 0 | 931084 | 33811 | 897273 | 988106 | 921773 | 0 | 0 | 0 | 921773 | 921773 | 102.7% | 1 | 0 | 57022 | 9 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 57022 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-07-27 | QTR1 | 17/18 |  | 2017-05-20 | QTR4 | 16/17 | 313 | 926503.43
| 03 | T3550 | 43257015201 | 2015-12-03 | QTR2 | 15/16 | 1 | 0 | 195 | 323 | 318 | 97.44% | 1 | 5 | 0 | 0 | 128 | 0 | 9008956 | 100031 | 8908925 | 9008956 | 9058480 | 0 | 0 | 0 | 9058480 | 8913154 | 100% | 1 | -145326 | 0 | 107 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 7180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7180 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 |  | 2017-03-01 | QTR3 | 16/17 | 321 | 9047924.85
| 03 | T3553 | 43273915201 | 2016-04-27 | QTR4 | 15/16 | 1 | 2 | 180 | 231 | 229 | 100% | 1 | 2 | 0 | 0 | 49 | 2 | 5112998 | 56886 | 5056112 | 5217096 | 5197254 | -15000 | 0 | -15000 | 5182254 | 5211856 | 103.1% | 1 | 29602 | 104098 | 31 | 18 | 0 | 2 | 49607 | 0 | 0 | 0 | 47212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 99339 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-03-10 | QTR3 | 16/17 | 321 | 5858555.67
| 03 | T3574 | 43047115201 | 2016-08-31 | QTR1 | 16/17 | 1 | 0 | 125 | 166 | 172 | 104.8% | 1 | -6 | 6 | 0 | 41 | 0 | 710702 | 0 | 710702 | 710702 | 703481 | -9504 | 0 | -9504 | 693977 | 696276 | 97.97% | 1 | 2299 | 0 | 30 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-04-21 | QTR4 | 16/17 | 308 | 765580.95
| 03 | T3575 | 43079115201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 65 | 72 | 72 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 1223500 | 50000 | 1173500 | 1223500 | 1204340 | 0 | 0 | 0 | 1204340 | 1216824 | 103.7% | 1 | 12484 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-16 | QTR1 | 17/18 |  | 2017-04-18 | QTR4 | 16/17 | 313 | 1644576.72 | B0 | ACC - LUMP SUM
| 03 | T3576 | 42857615201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 120 | 191 | 191 | 115% | 1 | 0 | 0 | 0 | 53 | 18 | 455335 | 0 | 455335 | 461101 | 462306 | 0 | 0 | 0 | 462306 | 462306 | 101.5% | 1 | 0 | 5766 | 40 | 13 | 0 | 0 | 0 | 0 | 0 | 18 | 5766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 5766 | 0 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-05-20 | QTR4 | 16/17 | 313 | 517906.59
| 03 | T3599 | 42820835201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 90 | 92 | 83 | 90% | 1 | 9 | 0 | 0 | 2 | 0 | 311313 | 9628 | 301685 | 311313 | 302309 | 0 | 0 | 0 | 302309 | 302309 | 100.2% | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-02 | QTR1 | 17/18 |  | 2017-03-31 | QTR3 | 16/17 | 308 | 204199 | B0 | ACC - LUMP SUM
| 03 | T3600 | 42695115201 | 2016-02-24 | QTR3 | 15/16 | 1 | 1 | 155 | 299 | 299 | 118.7% | 1 | 0 | 0 | 0 | 130 | 14 | 2196017 | 50000 | 2146017 | 2209792 | 2194453 | 0 | 0 | 0 | 2194453 | 2190296 | 102.1% | 1 | -4157 | 13776 | 80 | 35 | 0 | 0 | 0 | 0 | 15 | 14 | 16901 | 13776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14 | 21411 | 13776 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-08-16 | QTR1 | 17/18 |  | 2017-03-29 | QTR3 | 16/17 | 308 | 2203713.84
| 03 | T3616 | 43662215201 | 2017-03-29 | QTR3 | 16/17 | 1 | 0 | 60 | 75 | 63 | 80% | 1 | 12 | 0 | 0 | 15 | 0 | 96639 | 0 | 96639 | 96639 | 100978 | 0 | 0 | 0 | 100978 | 100978 | 104.5% | 1 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | QTR1 | 17/18 |  | 2017-08-02 | QTR1 | 17/18 | 321 | 113500
| 03 | T3620 | 43278725201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 45 | 69 | 69 | 102.2% | 1 | 0 | 0 | 0 | 24 | 0 | 98537 | 0 | 98537 | 98537 | 95183 | 0 | 0 | 0 | 95183 | 95183 | 96.6% | 1 | 0 | 0 | 15 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 |  | 2017-07-12 | QTR1 | 17/18 | 321 | 131241.78
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 13 | 18 | 37 | 2610 | 4334 | 4279 | 76.92% | 10 | 55 | 18 | 0 | 1435 | 289 | 54995108 | 500356 | 54494752 | 57762308 | 57826987 | -56140 | 0 | -56140 | 57770847 | 56566212 | 92.31% | 12 | -1204635 | 2767201 | 824 | 260 | 14 | 4 | 192745 | 0 | 134 | 109 | 2739543 | 1251728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 184 | 716830 | 296259 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600760 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 44120 | 44120 | 0 | 0 | 0 | 0 | 0 | 0 | -797630 | 0 | 351 | 311 | 3496369 | 1592107
| 03 | E3N84 | 21876225201 | 2016-07-14 | QTR1 | 16/17 | 1 | 0 | 120 | 179 | 190 | 138.3% | 0 | -11 | 11 | 0 | 59 | 0 | 531067 | 36301 | 494766 | 531067 | 486082 | -17424 | 0 | -17424 | 468658 | 468658 | 94.72% | 1 | 0 | 0 | 11 | 13 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | F592982651 | WILLIAMS INDUSTRIAL & MARINE INC | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-05-01 | QTR4 | 16/17 | 321 | 761742
| 03 | E3P11 | 43257215201 | 2016-04-14 | QTR4 | 15/16 | 1 | 0 | 210 | 314 | 313 | 102.9% | 1 | 1 | 0 | 0 | 104 | 0 | 6922953 | 61524 | 6861429 | 6922953 | 6941583 | 0 | 0 | 0 | 6941583 | 6966761 | 101.5% | 1 | 25178 | 0 | 60 | 37 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-29 | QTR1 | 17/18 |  | 2017-05-18 | QTR4 | 16/17 | 314 | 6237409.01
| 03 | E3P12 | 43255515201 | 2016-11-10 | QTR2 | 16/17 | 1 | 1 | 90 | 105 | 105 | 115.6% | 1 | 0 | 0 | 0 | 15 | 0 | 751984 | 39984 | 712000 | 801537 | 761553 | 0 | 0 | 0 | 761553 | 761553 | 107% | 1 | 0 | 49553 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 49553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 49553 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-09-14 | QTR1 | 17/18 |  | 2017-05-26 | QTR4 | 16/17 | 308 | 851593.48 | B0 | ACC - LUMP SUM
| 03 | E3P15 | 43255015201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 90 | 95 | 88 | 92.22% | 1 | 7 | 0 | 0 | 5 | 0 | 1296000 | 50000 | 1246000 | 1296000 | 1281750 | 0 | 0 | 0 | 1281750 | 1293176 | 103.8% | 1 | 11426 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2017-08-28 | QTR1 | 17/18 |  | 2017-04-30 | QTR4 | 16/17 | 321 | 1595361.1 | B0 | ACC - LUMP SUM
| 03 | E3P74 | 22271315201 | 2016-06-09 | QTR4 | 15/16 | 1 | 1 | 120 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 916620 | 32497 | 884123 | 973642 | 931184 | 0 | 0 | 0 | 931184 | 931184 | 105.3% | 1 | 0 | 57022 | 9 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-05-12 | QTR4 | 16/17 | 308 | 702427.14
| 03 | E3P75 | 43078615201 | 2016-07-14 | QTR1 | 16/17 | 2 | 0 | 100 | 210 | 210 | 177% | 0 | 0 | 0 | 0 | 110 | 0 | 2702301 | 50119 | 2652182 | 2702301 | 2824495 | 0 | 0 | 0 | 2824495 | 2819950 | 106.3% | 1 | -4545 | 0 | 17 | 16 | 73 | 0 | 5732 | 0 | 4 | 0 | 14182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 19914 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 |  | 2017-04-27 | QTR4 | 16/17 | 308 | 2591912.99
| 03 | E3P91 | 43460615201 | 2016-10-13 | QTR2 | 16/17 | 1 | 0 | 75 | 100 | 100 | 116% | 1 | 0 | 0 | 0 | 25 | 0 | 367076 | 15130 | 351946 | 367076 | 357176 | 0 | 0 | 0 | 357176 | 357176 | 101.5% | 1 | 0 | 0 | 12 | 1 | 0 | 0 | 5230 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 5230 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 |  | 2017-04-22 | QTR4 | 16/17 | 308 | 306636.35 | B0 | ACC - LUMP SUM
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 7 | 8 | 2 | 805 | 1140 | 1143 | 71.43% | 5 | -3 | 11 | 0 | 335 | 0 | 13488001 | 285555 | 13202446 | 13594576 | 13583823 | -17424 | 0 | -17424 | 13566399 | 13598458 | 100% | 7 | 32059 | 106575 | 115 | 75 | 108 | 0 | 10962 | 0 | 37 | 0 | 65819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 133803 | 0
| District 03 Totals |  |  |  |  | 20 | 26 | 39 | 3415 | 5474 | 5422 | 75% | 15 | 52 | 29 | 0 | 1770 | 289 | 68483109 | 785911 | 67697198 | 71356884 | 71410810 | -73564 | 0 | -73564 | 71337246 | 70164670 | 95% | 19 | -1172576 | 2873776 | 939 | 335 | 122 | 4 | 203707 | 0 | 171 | 109 | 2805362 | 1251728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 184 | 773852 | 296259 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600760 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 44120 | 44120 | 0 | 0 | 0 | 0 | 0 | 0 | -797630 | 0 | 496 | 311 | 3630172 | 1592107
| 04 | T4408 | 42898415201 | 2015-04-29 | QTR4 | 14/15 | 2 | 7 | 590 | 716 | 711 | 99.15% | 1 | 5 | 0 | 0 | 126 | 0 | 5457914 | 59401 | 5398513 | 5501915 | 5476312 | 0 | 0 | 0 | 5476312 | 5355390 | 99.2% | 1 | -120921 | 44001 | 96 | 30 | 0 | 0 | 8201 | 0 | 0 | 0 | 99691 | 4389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -77463 | 0 | 0 | 0 | 75511 | 4389 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-08-11 | QTR1 | 17/18 |  | 2017-06-23 | QTR4 | 16/17 | 408 | 6001634.3
| 04 | T4429 | 43320715201 | 2016-02-24 | QTR3 | 15/16 | 2 | 2 | 276 | 345 | 344 | 108.7% | 1 | 1 | 0 | 0 | 44 | 25 | 1817368 | 50000 | 1767368 | 1866868 | 1820548 | 0 | 0 | 0 | 1820548 | 1828664 | 103.5% | 1 | 8115 | 49500 | 31 | 13 | 0 | 0 | 23754 | 0 | 0 | 25 | 41825 | 27746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 65579 | 27746 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-28 | QTR1 | 17/18 |  | 2017-06-27 | QTR4 | 16/17 | 412 | 1805872.62
| 04 | T4437 | 43510215201 | 2016-03-30 | QTR3 | 15/16 | 1 | 3 | 48 | 104 | 104 | 118.8% | 1 | 0 | 0 | 0 | 47 | 9 | 647604 | 27717 | 619887 | 693460 | 677812 | 0 | 0 | 0 | 677812 | 686116 | 110.7% | 0 | 8304 | 45856 | 45 | 2 | 0 | 0 | 0 | 0 | 0 | 9 | 29362 | 34197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10791 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 51453 | 44988 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2017-08-08 | QTR1 | 17/18 |  | 2016-11-07 | QTR2 | 16/17 | 409 | 572056.26
| 04 | T4441 | 43799415201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 134 | 136 | 62 | 44.78% | 1 | 74 | 0 | 0 | 2 | 0 | 899605 | 49184 | 850421 | 899605 | 846333 | 0 | 50000 | 50000 | 896333 | 846333 | 99.52% | 1 | -50000 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-09-25 | QTR1 | 17/18 |  | 2017-08-15 | QTR1 | 17/18 | 412 | 1032154.5 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4443 | 43427515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 120 | 131 | 131 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 1312214 | 50000 | 1262214 | 1312214 | 1253435 | 0 | 0 | 0 | 1253435 | 1261184 | 99.92% | 1 | 7749 | 0 | 0 | 11 | 0 | 0 | 801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2017-08-07 | QTR1 | 17/18 |  | 2017-04-21 | QTR4 | 16/17 | 408 | 1458806.8
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 5 | 7 | 12 | 1168 | 1432 | 1352 | 100% | 5 | 80 | 0 | 0 | 230 | 34 | 10134705 | 236302 | 9898403 | 10274062 | 10074440 | 0 | 50000 | 50000 | 10124440 | 9977687 | 80% | 4 | -146753 | 139357 | 172 | 58 | 0 | 0 | 32756 | 0 | 0 | 34 | 170878 | 66332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 45081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10791 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -77463 | 0 | 0 | 34 | 193344 | 77123
| 04 | E4R04 | 43062515201 | 2015-06-12 | QTR4 | 14/15 | 1 | 0 | 255 | 296 | 293 | 98.82% | 1 | 3 | 0 | 0 | 41 | 0 | 1604618 | 50000 | 1554618 | 1604618 | 1554867 | 0 | 0 | 0 | 1554867 | 1554752 | 100% | 1 | -115 | 0 | 23 | 18 | 0 | 0 | 6891 | 0 | 0 | 0 | 1506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8397 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-07 | QTR1 | 17/18 |  | 2017-06-28 | QTR4 | 16/17 | 412 | 1736394.32 | B0 | ACC - LUMP SUM
| 04 | E4S04 | 43110715201 | 2016-10-14 | QTR2 | 16/17 | 1 | 0 | 102 | 118 | 116 | 98.04% | 1 | 2 | 0 | 0 | 16 | 0 | 289809 | 14415 | 275394 | 289809 | 270949 | 0 | 0 | 0 | 270949 | 270949 | 98.39% | 1 | 0 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2017-08-23 | QTR1 | 17/18 |  | 2017-06-09 | QTR4 | 16/17 | 412 | 303225.64
| 04 | E4S17 | 43397715201 | 2017-01-06 | QTR3 | 16/17 | 1 | 0 | 28 | 34 | 33 | 96.43% | 1 | 1 | 0 | 0 | 6 | 0 | 280209 | 12373 | 267836 | 280209 | 215232 | 0 | 0 | 0 | 215232 | 215232 | 80.36% | 1 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 10803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10803 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-09-20 | QTR1 | 17/18 |  | 2017-07-20 | QTR1 | 17/18 | 412 | 253963.62
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 3 | 3 | 0 | 385 | 448 | 442 | 100% | 3 | 6 | 0 | 0 | 63 | 0 | 2174636 | 76788 | 2097848 | 2174636 | 2041048 | 0 | 0 | 0 | 2041048 | 2040933 | 100% | 3 | -115 | 0 | 39 | 24 | 0 | 0 | 6891 | 0 | 0 | 0 | 12309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0
| District 04 Totals |  |  |  |  | 8 | 10 | 12 | 1553 | 1880 | 1794 | 100% | 8 | 86 | 0 | 0 | 293 | 34 | 12309341 | 313090 | 11996251 | 12448698 | 12115488 | 0 | 50000 | 50000 | 12165488 | 12018620 | 87.5% | 7 | -146868 | 139357 | 211 | 82 | 0 | 0 | 39647 | 0 | 0 | 34 | 183187 | 66332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 45081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10791 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -77463 | 0 | 0 | 34 | 212544 | 77123
| 05 | BE035 | 43387415201 | 2015-08-10 | QTR1 | 15/16 | 1 | 6 | 345 | 494 | 495 | 133.3% | 0 | -1 | 1 | 0 | 40 | 109 | 8947000 | 150000 | 8797000 | 9057405 | 9057405 | 0 | 0 | 0 | 9057405 | 9057101 | 103% | 1 | -304 | 110405 | 14 | 21 | 0 | 55 | 165982 | 14523 | 0 | 54 | -39561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 110405 | 14523 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-05-05 | QTR4 | 16/17 | 509 | 8947000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | BE227 | 43029015201 | 2016-04-22 | QTR4 | 15/16 | 1 | 5 | 220 | 244 | 243 | 106.4% | 1 | 1 | 0 | 0 | 24 | 0 | 1697000 | 50000 | 1647000 | 1771015 | 1771015 | 0 | 0 | 0 | 1771015 | 1771300 | 107.5% | 1 | 285 | 74015 | 4 | 5 | 0 | 0 | 62930 | 0 | 0 | 0 | 11085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74015 | 0 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-05-12 | QTR4 | 16/17 | 513 | 1668323.35
| 05 | T5533 | 42728015201 | 2015-07-29 | QTR1 | 15/16 | 2 | 9 | 340 | 466 | 494 | 127.6% | 0 | -28 | 28 | 0 | 65 | 61 | 8422850 | 50000 | 8372850 | 8665412 | 8608390 | -105560 | 0 | -105560 | 8502830 | 8174179 | 97.63% | 1 | -328651 | 242562 | 28 | 32 | 0 | 0 | 4603 | 0 | 0 | 46 | 107535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 176219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 288356 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-09-05 | QTR1 | 17/18 |  | 2017-04-04 | QTR4 | 16/17 | 512 | 8647534.74
| 05 | T5553 | 43242115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 1 | 150 | 171 | 169 | 98.67% | 1 | 2 | 0 | 0 | 21 | 0 | 1085604 | 50000 | 1035604 | 1087044 | 1021639 | -6360 | 0 | -6360 | 1015279 | 1026222 | 99.09% | 1 | 10943 | 1440 | 7 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 6692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6692 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-07-13 | QTR1 | 17/18 |  | 2017-04-24 | QTR4 | 16/17 | 595 | 1163003.22
| 05 | T5565 | 43065715201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 230 | 273 | 273 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 3028041 | 50000 | 2978041 | 3028041 | 2950282 | 0 | 0 | 0 | 2950282 | 2950886 | 99.09% | 1 | 604 | 0 | 24 | 19 | 0 | 0 | 5094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5094 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-08 | QTR1 | 17/18 |  | 2017-07-21 | QTR1 | 17/18 | 514 | 3357586 | B0 | ACC - LUMP SUM
| 05 | T5566 | 43243715201 | 2016-07-27 | QTR1 | 16/17 | 1 | 2 | 150 | 195 | 195 | 106% | 1 | 0 | 0 | 0 | 37 | 8 | 3766852 | 50000 | 3716852 | 3749136 | 3790510 | 0 | 0 | 0 | 3790510 | 3819315 | 102.8% | 1 | 28805 | -17716 | 19 | 17 | 0 | 0 | -8096 | 0 | 0 | 8 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4316 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-09-08 | QTR1 | 17/18 |  | 2017-05-08 | QTR4 | 16/17 | 514 | 4106500.86
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 6 | 7 | 23 | 1435 | 1843 | 1869 | 66.67% | 4 | -26 | 29 | 0 | 230 | 178 | 26947347 | 400000 | 26547347 | 27358053 | 27199241 | -111920 | 0 | -111920 | 27087321 | 26799003 | 100% | 6 | -288318 | 410706 | 96 | 108 | 0 | 55 | 230513 | 14523 | 0 | 108 | 98163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 160203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 488878 | 14523
| 05 | E5Y32 | 43445515201 | 2016-08-02 | QTR1 | 16/17 | 1 | 0 | 120 | 189 | 177 | 90% | 1 | 12 | 0 | 0 | 69 | 0 | 622133 | 26000 | 596133 | 622133 | 564614 | 0 | 0 | 0 | 564614 | 564745 | 94.73% | 1 | 131 | 0 | 38 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2017-09-06 | QTR1 | 17/18 |  | 2017-04-28 | QTR4 | 16/17 | 513 | 567682.87
| 05 | E5Y36 | 43445615201 | 2016-10-04 | QTR2 | 16/17 | 1 | 0 | 110 | 118 | 118 | 101.8% | 1 | 0 | 0 | 0 | 8 | 0 | 704674 | 32000 | 672674 | 704674 | 672674 | 0 | 0 | 0 | 672674 | 672674 | 100% | 1 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 |  | 2017-05-05 | QTR4 | 16/17 | 515 | 684419.55
| 05 | E5Y63 | 43234615201 | 2016-10-04 | QTR2 | 16/17 | 1 | 1 | 90 | 116 | 132 | 126.7% | 0 | -16 | 16 | 0 | 18 | 8 | 862770 | 33000 | 829770 | 868517 | 816671 | -25344 | 0 | -25344 | 791327 | 791327 | 95.37% | 1 | 0 | 5747 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 |  | 2017-05-15 | QTR4 | 16/17 | 513 | 776696.15
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 3 | 3 | 1 | 320 | 423 | 427 | 66.67% | 2 | -4 | 16 | 0 | 95 | 8 | 2189577 | 91000 | 2098577 | 2195324 | 2053959 | -25344 | 0 | -25344 | 2028615 | 2028746 | 100% | 3 | 131 | 5747 | 48 | 45 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0
| District 05 Totals |  |  |  |  | 9 | 10 | 24 | 1755 | 2266 | 2296 | 66.67% | 6 | -30 | 45 | 0 | 325 | 186 | 29136924 | 491000 | 28645924 | 29553377 | 29253200 | -137264 | 0 | -137264 | 29115936 | 28827749 | 100% | 9 | -288187 | 416453 | 144 | 153 | 0 | 55 | 230513 | 14523 | 0 | 116 | 103910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 160203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 494625 | 14523
| 06 | T6345 | 24994165201 | 2014-06-25 | QTR4 | 13/14 | 2 | 5 | 780 | 859 | 754 | 87.69% | 1 | 105 | 0 | 0 | 70 | 9 | 20210987 | 648000 | 19562987 | 20241085 | 19700200 | 0 | 800000 | 800000 | 20500200 | 19298493 | 98.65% | 1 | -1201707 | 30098 | 51 | 19 | 0 | 0 | 325806 | 0 | 0 | 0 | 277026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5947 | 0 | 0 | 0 | 8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -422785 | 0 | 0 | 9 | 196909 | 0 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2017-09-19 | QTR1 | 17/18 |  | 2017-01-27 | QTR3 | 16/17 | 606 | 19907818.44 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6349 | 42916225201 | 2016-04-27 | QTR4 | 15/16 | 2 | 7 | 240 | 263 | 195 | 71.67% | 1 | 68 | 0 | 0 | 23 | 0 | 4178283 | 50000 | 4128283 | 4236996 | 3850525 | 0 | 160000 | 160000 | 4010525 | 3858312 | 93.46% | 1 | -152213 | 58713 | 14 | 9 | 0 | 0 | 24297 | 0 | 0 | 0 | 74263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9298 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91182 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-02-24 | QTR3 | 16/17 | 606 | 5124941.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6380 | 41462435201 | 2015-06-17 | QTR4 | 14/15 | 3 | 3 | 280 | 383 | 382 | 113.9% | 1 | 1 | 0 | 0 | 103 | 0 | 3520907 | 50505 | 3470402 | 3612854 | 3575998 | 0 | 56000 | 56000 | 3631998 | 3498466 | 100.8% | 1 | -133532 | 91947 | 47 | 16 | 0 | 0 | 1588 | 0 | 40 | 0 | 82138 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 83726 | 8200 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 |  | 2017-01-20 | QTR3 | 16/17 | 606 | 3771064.2 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6385 | 43326415201 | 2016-01-27 | QTR3 | 15/16 | 2 | 1 | 180 | 259 | 259 | 113.9% | 1 | 0 | 0 | 0 | 54 | 25 | 1122164 | 50070 | 1072094 | 1210753 | 1131145 | 0 | 0 | 0 | 1131145 | 1133153 | 105.7% | 1 | 2007 | 88590 | 37 | 17 | 0 | 0 | 17204 | 0 | 0 | 25 | 90738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 107942 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-04-04 | QTR4 | 16/17 | 606 | 1217718.2
| 06 | T6391 | 43349215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 180 | 208 | 208 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 1155673 | 47446 | 1108227 | 1155673 | 1091324 | 0 | 0 | 0 | 1091324 | 1092555 | 98.59% | 1 | 1230 | 0 | 11 | 17 | 0 | 0 | 12008 | 0 | 0 | 0 | 2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21825 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 |  | 2017-05-21 | QTR4 | 16/17 | 606 | 983083.6
| 06 | T6405 | 42934625201 | 2016-03-30 | QTR3 | 15/16 | 3 | 1 | 160 | 216 | 215 | 99.38% | 1 | 1 | 0 | 0 | 56 | 0 | 1071254 | 50000 | 1021254 | 1073754 | 1058914 | 0 | 0 | 0 | 1058914 | 1062745 | 104.1% | 1 | 3831 | 2500 | 43 | 13 | 0 | 0 | 3296 | 0 | 0 | 0 | 3287 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5133 | 0 | 0 | 0 | 2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14682 | 787 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 |  | 2017-04-28 | QTR4 | 16/17 | 606 | 1077071.2
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 6 | 14 | 17 | 1820 | 2188 | 2013 | 100% | 6 | 175 | 0 | 0 | 334 | 34 | 31259268 | 896021 | 30363247 | 31531115 | 30408106 | 0 | 1016000 | 1016000 | 31424106 | 29943724 | 100% | 6 | -1480384 | 271848 | 203 | 91 | 0 | 0 | 384199 | 0 | 40 | 25 | 529860 | 8987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9191 | 0 | 0 | 0 | 12918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -422785 | 0 | 40 | 34 | 516266 | 8987
| 06 | E6J00 | 43540715201 | 2015-01-29 | QTR3 | 14/15 | 1 | 0 | 790 | 794 | 791 | 99.62% | 1 | 3 | 0 | 0 | 4 | 0 | 204491 | 11179 | 193312 | 204491 | 200808 | 0 | 0 | 0 | 200808 | 200808 | 103.9% | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | F650817669 | FLORIDA TURF AND LANDSCAPE HORTICULTURE | N/A | N/A | N/A | N/A | 2017-08-17 | QTR1 | 17/18 |  | 2017-07-24 | QTR1 | 17/18 | 606 | 234759 | B0 | ACC - LUMP SUM
| 06 | E6J27 | 43325415201 | 2015-10-29 | QTR2 | 15/16 | 1 | 1 | 240 | 364 | 364 | 100% | 1 | 0 | 0 | 0 | 124 | 0 | 874736 | 43765 | 830971 | 839120 | 814919 | 0 | 0 | 0 | 814919 | 814919 | 98.07% | 1 | 0 | -35616 | 105 | 19 | 0 | 0 | 10698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35616 | 0 | 0 | 0 | -24918 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2017-07-18 | QTR1 | 17/18 |  | 2017-04-26 | QTR4 | 16/17 | 606 | 895054.75
| 06 | E6J41 | 43444315201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 70 | 77 | 77 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 220419 | 11619 | 208800 | 220419 | 208800 | 0 | 0 | 0 | 208800 | 208800 | 100% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2017-09-06 | QTR1 | 17/18 |  | 2017-04-23 | QTR4 | 16/17 | 606 | 249619 | B0 | ACC - LUMP SUM
| 06 | E6J44 | 43468115201 | 2016-05-26 | QTR4 | 15/16 | 1 | 1 | 240 | 317 | 257 | 75% | 1 | 60 | 0 | 0 | 77 | 0 | 979602 | 50000 | 929602 | 823480 | 746877 | 0 | 0 | 0 | 746877 | 746877 | 80.34% | 1 | 0 | -156122 | 57 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | -156122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -156122 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 |  | 2017-06-09 | QTR4 | 16/17 | 606 | 1105870
| 06 | E6J75 | 43652815201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 215 | 220 | 132 | 59.07% | 1 | 88 | 0 | 0 | 5 | 0 | 847200 | 50000 | 797200 | 847200 | 789681 | 0 | 0 | 0 | 789681 | 789681 | 99.06% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-08-15 | QTR1 | 17/18 |  | 2017-06-20 | QTR4 | 16/17 | 606 | 1102468.5
| 06 | E6J76 | 43652915201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 180 | 234 | 220 | 92.22% | 1 | 14 | 0 | 0 | 54 | 0 | 588728 | 36323 | 552405 | 588728 | 477515 | 0 | 0 | 0 | 477515 | 477515 | 86.44% | 1 | 0 | 0 | 37 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-05-08 | QTR4 | 16/17 | 606 | 756279.75
| 06 | E6K21 | 42914635201 | 2016-07-28 | QTR1 | 16/17 | 1 | 0 | 100 | 107 | 105 | 98% | 1 | 2 | 0 | 0 | 7 | 0 | 177943 | 9346 | 168597 | 177943 | 173203 | 0 | 0 | 0 | 173203 | 173203 | 102.7% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2017-07-13 | QTR1 | 17/18 |  | 2017-06-12 | QTR4 | 16/17 | 606 | 196223.5
| 06 | E6K31 | 42934635201 | 2016-08-25 | QTR1 | 16/17 | 1 | 0 | 140 | 162 | 145 | 87.86% | 1 | 17 | 0 | 0 | 22 | 0 | 999395 | 50000 | 949395 | 999395 | 975146 | 0 | 0 | 0 | 975146 | 975806 | 102.8% | 1 | 660 | 0 | 19 | 3 | 0 | 0 | 9015 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31215 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 |  | 2017-06-30 | QTR4 | 16/17 | 606 | 1051398.75
| 06 | E6K49 | 43058825201 | 2016-09-29 | QTR1 | 16/17 | 2 | 0 | 140 | 187 | 187 | 100% | 1 | 0 | 0 | 0 | 47 | 0 | 864202 | 42202 | 822000 | 864202 | 790596 | 0 | 0 | 0 | 790596 | 790888 | 96.22% | 1 | 292 | 0 | 42 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2017-09-18 | QTR1 | 17/18 |  | 2017-07-28 | QTR1 | 17/18 | 606 | 885402 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 9 | 10 | 2 | 2115 | 2462 | 2278 | 100% | 9 | 184 | 0 | 0 | 347 | 0 | 5756716 | 304434 | 5452282 | 5564978 | 5177545 | 0 | 0 | 0 | 5177545 | 5178497 | 100% | 9 | 952 | -191738 | 277 | 70 | 0 | 0 | 19713 | 0 | 0 | 0 | -135572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35616 | 0 | 0 | 0 | -146383 | 0
| District 06 Totals |  |  |  |  | 15 | 24 | 19 | 3935 | 4650 | 4291 | 100% | 15 | 359 | 0 | 0 | 681 | 34 | 37015984 | 1200455 | 35815529 | 37096093 | 35585651 | 0 | 1016000 | 1016000 | 36601651 | 35122221 | 100% | 15 | -1479432 | 80110 | 480 | 161 | 0 | 0 | 403912 | 0 | 40 | 25 | 394288 | 8987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14283 | 0 | 0 | 0 | 12918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -458401 | 0 | 40 | 34 | 369883 | 8987
| 07 | T7220 | 40845925201 | 2011-06-29 | QTR4 | 10/11 | 6 | 63 | 1500 | 1779 | 1779 | 102.8% | 1 | 0 | 0 | 0 | 237 | 42 | 94696203 | 150000 | 94546203 | 99221504 | 102513161 | -176000 | 0 | -176000 | 102337161 | 101320385 | 107.2% | 1 | -1016777 | 4525301 | 164 | 73 | 0 | 0 | 1140417 | 444656 | 0 | 0 | 638567 | 94458 | 0 | 0 | 0 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2636702 | 157507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347209 | 54885 | 0 | 0 | 0 | 0 | 0 | 0 | 4136 | 4136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 4335071 | 755643 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-07-07 | QTR1 | 17/18 |  | 2016-08-26 | QTR1 | 16/17 | 714 | 107019759.03
| 07 | T7346 | 43089815201 | 2014-07-30 | QTR1 | 14/15 | 1 | 5 | 390 | 599 | 599 | 110% | 1 | 0 | 0 | 0 | 170 | 39 | 6794444 | 62000 | 6732444 | 6864518 | 7093818 | 0 | 0 | 0 | 7093818 | 6785751 | 100.8% | 1 | -308067 | 70073 | 144 | 26 | 0 | 17 | 18684 | 0 | 0 | 22 | 128610 | 6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 112644 | 6122 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2016-08-25 | QTR1 | 16/17 | 717 | 6553700
| 07 | T7349 | 43124315201 | 2014-06-18 | QTR4 | 13/14 | 2 | 5 | 400 | 654 | 652 | 113.8% | 1 | 2 | 0 | 0 | 203 | 51 | 12544444 | 119000 | 12425444 | 12706570 | 13012776 | 0 | 0 | 0 | 13012776 | 12421061 | 99.96% | 1 | -591715 | 162125 | 167 | 30 | 6 | 11 | 89297 | 0 | 0 | 40 | 77646 | 16339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15383 | 15383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 51 | 182326 | 31722 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-31 | QTR1 | 17/18 |  | 2016-10-25 | QTR2 | 16/17 | 798 | 12199500
| 07 | T7377 | 42453295201 | 2016-02-24 | QTR3 | 15/16 | 3 | 6 | 260 | 309 | 309 | 101.2% | 1 | 0 | 0 | 0 | 46 | 3 | 2482901 | 50000 | 2432901 | 2542403 | 2373194 | 0 | 0 | 0 | 2373194 | 2384196 | 98% | 1 | 11002 | 59502 | 25 | 21 | 0 | 3 | 56002 | 0 | 0 | 0 | 8532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 64535 | 0 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-07-25 | QTR1 | 17/18 |  | 2017-05-17 | QTR4 | 16/17 | 709 | 2246000
| 07 | T7381 | 25589335201 | 2016-05-25 | QTR4 | 15/16 | 2 | 1 | 200 | 284 | 284 | 114% | 1 | 0 | 0 | 0 | 56 | 28 | 4590182 | 55000 | 4535182 | 4640182 | 4586377 | 0 | 0 | 0 | 4586377 | 4603104 | 101.5% | 1 | 16727 | 50000 | 22 | 34 | 0 | 7 | 26821 | 0 | 0 | 0 | 14230 | 1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 57192 | 1901 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-09-27 | QTR1 | 17/18 |  | 2017-05-31 | QTR4 | 16/17 | 717 | 7190840.88
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 5 | 14 | 80 | 2750 | 3625 | 3623 | 100% | 5 | 2 | 0 | 0 | 712 | 163 | 121108174 | 436000 | 120672174 | 125975177 | 129579326 | -176000 | 0 | -176000 | 129403326 | 127514497 | 100% | 5 | -1888830 | 4867001 | 522 | 184 | 6 | 38 | 1331221 | 444656 | 0 | 62 | 867585 | 118820 | 0 | 0 | 0 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2618194 | 157507 | 0 | 0 | 15383 | 15383 | 0 | 0 | 0 | 0 | 0 | 0 | 347209 | 54885 | 0 | 0 | 0 | 0 | 0 | 21 | 4136 | 4136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 163 | 4751768 | 795388
| 07 | E7K09 | 43376015201 | 2016-03-09 | QTR3 | 15/16 | 1 | 0 | 165 | 235 | 235 | 107.3% | 1 | 0 | 0 | 0 | 70 | 0 | 4858889 | 50000 | 4808889 | 4858889 | 4889946 | 0 | 0 | 0 | 4889946 | 4892719 | 101.7% | 1 | 2773 | 0 | 37 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-01-20 | QTR3 | 16/17 | 798 | 4975480
| 07 | E7K14 | 43571815201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 515 | 678 | 678 | 114.2% | 1 | 0 | 0 | 0 | 90 | 73 | 5520000 | 50000 | 5470000 | 5520000 | 5515787 | 0 | 0 | 0 | 5515787 | 5461492 | 99.84% | 1 | -54295 | 0 | 60 | 30 | 0 | 0 | 0 | 0 | 0 | 73 | 42916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 42916 | 0 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-08-23 | QTR1 | 17/18 |  | 2017-07-10 | QTR1 | 17/18 | 709 | 5318312 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 2 | 2 | 0 | 680 | 913 | 913 | 100% | 2 | 0 | 0 | 0 | 160 | 73 | 10378889 | 100000 | 10278889 | 10378889 | 10405733 | 0 | 0 | 0 | 10405733 | 10354211 | 100% | 2 | -51522 | 0 | 97 | 51 | 0 | 0 | 0 | 0 | 0 | 73 | 42916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 73 | 42916 | 0
| District 07 Totals |  |  |  |  | 7 | 16 | 80 | 3430 | 4538 | 4536 | 100% | 7 | 2 | 0 | 0 | 872 | 236 | 131487063 | 536000 | 130951063 | 136354066 | 139985059 | -176000 | 0 | -176000 | 139809059 | 137868708 | 100% | 7 | -1940352 | 4867001 | 619 | 235 | 6 | 38 | 1331221 | 444656 | 0 | 135 | 910501 | 118820 | 0 | 0 | 0 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 0 | 0 | 12 | 42 | 2618194 | 157507 | 0 | 0 | 15383 | 15383 | 0 | 0 | 0 | 0 | 0 | 0 | 347209 | 54885 | 0 | 0 | 0 | 0 | 0 | 21 | 4136 | 4136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 236 | 4794684 | 795388
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8P84 | 43560415201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 215 | 250 | 251 | 107% | 1 | -1 | 1 | 0 | 21 | 14 | 1564634 | 50000 | 1514634 | 1564634 | 1570658 | 0 | 0 | 0 | 1570658 | 1593989 | 105.2% | 1 | 23332 | 0 | 4 | 17 | 0 | 0 | 8912 | 0 | 0 | 14 | 23635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 32548 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-25 | QTR1 | 17/18 |  | 2017-05-24 | QTR4 | 16/17 | 854 | 1798899.5
| 08 | E8P93 | 42933415201 | 2016-04-12 | QTR4 | 15/16 | 2 | 1 | 155 | 189 | 189 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1627383 | 48815 | 1578568 | 1619754 | 1562111 | 0 | 0 | 0 | 1562111 | 1565726 | 99.19% | 1 | 3615 | -7629 | 14 | 20 | 0 | 0 | -1000 | 0 | 0 | 0 | 16722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18273 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-07 | QTR1 | 17/18 |  | 2017-04-05 | QTR4 | 16/17 | 854 | 1804452.94
| 08 | E8P96 | 43494625201 | 2016-05-24 | QTR4 | 15/16 | 3 | 1 | 175 | 190 | 187 | 98.29% | 1 | 3 | 0 | 0 | 15 | 0 | 938500 | 46648 | 891852 | 938500 | 828715 | 0 | 0 | 0 | 828715 | 828715 | 92.92% | 1 | 0 | 0 | 1 | 14 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 |  | 2017-05-12 | QTR4 | 16/17 | 854 | 988989.54
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 3 | 6 | 2 | 545 | 629 | 627 | 100% | 3 | 2 | 1 | 0 | 70 | 14 | 4130517 | 145463 | 3985054 | 4122888 | 3961484 | 0 | 0 | 0 | 3961484 | 3988430 | 100% | 3 | 26947 | -7629 | 19 | 51 | 0 | 0 | 15912 | 0 | 0 | 14 | 40357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 70821 | 0
| District 08 Totals |  |  |  |  | 3 | 6 | 2 | 545 | 629 | 627 | 100% | 3 | 2 | 1 | 0 | 70 | 14 | 4130517 | 145463 | 3985054 | 4122888 | 3961484 | 0 | 0 | 0 | 3961484 | 3988430 | 100% | 3 | 26947 | -7629 | 19 | 51 | 0 | 0 | 15912 | 0 | 0 | 14 | 40357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 70821 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 49 | 80 | 181 | 12753 | 17048 | 16752 | 87.76% | 43 | 296 | 69 | 0 | 3485 | 810 | 282667287 | 3115423 | 279551864 | 291481745 | 293413555 | -393906 | 1066000 | 672094 | 294085649 | 288103205 | 95.92% | 47 | -5982448 | 8814458 | 2118 | 925 | 20 | 150 | 2420801 | 459179 | 174 | 389 | 4590325 | 1451139 | 0 | 0 | 0 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 11300 | 0 | 112 | 249 | 3563515 | 453766 | 105 | 0 | 28301 | 15383 | 0 | 0 | 0 | 0 | 0 | 0 | 1017512 | 54885 | 0 | 0 | 10791 | 10791 | 0 | 44 | 51138 | 48256 | 0 | 0 | 0 | 0 | 0 | 0 | -1297878 | 0 | 411 | 832 | 9963848 | 2493400
| Statewide District Let Contracts SubTotal |  |  |  |  | 34 | 40 | 14 | 6691 | 8413 | 8196 | 91.18% | 31 | 217 | 28 | 0 | 1500 | 222 | 95001271 | 1487263 | 93514008 | 95297363 | 93779584 | -42768 | 0 | -42768 | 93736816 | 93205061 | 97.06% | 33 | -531753 | 296092 | 779 | 487 | 183 | 93 | 483668 | 29435 | 37 | 129 | 140515 | 12197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39600 | 0 | 12 | 0 | 81258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35616 | 0 | 232 | 222 | 733407 | 41632
| Statewide Totals |  |  |  |  | 83 | 120 | 195 | 19444 | 25461 | 24948 | 89.16% | 74 | 513 | 97 | 0 | 4985 | 1032 | 377668558 | 4602686 | 373065872 | 386779108 | 387193139 | -436674 | 1066000 | 629326 | 387822465 | 381308266 | 96.39% | 80 | -6514201 | 9110550 | 2897 | 1412 | 203 | 243 | 2904469 | 488614 | 211 | 518 | 4730840 | 1463336 | 0 | 0 | 0 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 50900 | 0 | 124 | 249 | 3644773 | 453766 | 105 | 0 | 28301 | 15383 | 0 | 0 | 0 | 0 | 0 | 0 | 1038943 | 54885 | 0 | 0 | 10791 | 10791 | 0 | 44 | 53689 | 48256 | 0 | 0 | 0 | 0 | 0 | 0 | -1333494 | 0 | 643 | 1054 | 10697255 | 2535032

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1O50 | 43121215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-06-14 | 2473492 | 2473492 | 2430162 | 0 | 0 | 2431258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430162 | 2431258 | 1097 | 2383341 | B0 | ACC - LUMP SUM
1 | E1O53 | 43486515201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-12-17 | 1972999 | 2017226 | 2027670 | 44227.39 | 0 | 2027844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027670 | 2027844 | 174 | 1579998
1 | E1P64 | 43172315201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-08-18 | 829730 | 829730 | 788000 | 0 | 0 | 788000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788000 | 788000 | 0 | 915007 | B0 | ACC - LUMP SUM
1 | T1625 | 42988315201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-06-15 | 1852000 | 1866275 | 1867608 | 14275 | 0 | 1867700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1867608 | 1867700 | 92 | 2064220
1 | T1628 | 43011915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-01-27 | 5092548 | 5147816 | 5084411 | 55268.23 | 0 | 5074685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5084411 | 5074685 | -9725 | 5336137
1 | T1658 | 43902815201 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2016-06-15 | 2041864 | 2041864 | 1925079 | 0 | 0 | 1925198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925079 | 1925198 | 118 | 4696300
1 | T1662 | 43132515201 | F452357137 | YD WEST COAST HOME INC | N/A | N/A | N/A | N/A | 2016-07-27 | 150000 | 150000 | 141366 | 0 | -6706 | 134660 | -6706 | 0 | 0 | 0 | 0 | 0 | -6706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6706 | 134660 | 134660 | 0 | 195238 | B0 | ACC - LUMP SUM
1 | T1668 | 43450715201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 860000 | 860000 | 810000 | 0 | 0 | 810000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810000 | 810000 | 0 | 1005380 | B0 | ACC - LUMP SUM
1 | T1A01 | 43134015201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-07-27 | 1006260 | 1032806 | 969407 | 26545.55 | 0 | 980874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969407 | 980874 | 11467 | 1134237
2 | E2R19 | 20960715201 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2013-12-12 | 44244000 | 44497660 | 44485464 | 253660.05 | 0 | 43929908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44485464 | 43929908 | -555556 | 49888540 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2U38 | 43226615201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-03-16 | 1729034 | 1814284 | 1787276 | 85250 | 0 | 1798954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 2261729
2 | E2U92 | 43015715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-03-16 | 4567769 | 4567769 | 4034344 | 0 | 0 | 4034680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4034344 | 4034680 | 336 | 3766652
2 | E2V03 | 43242015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-05-18 | 1065911 | 1065911 | 1003076 | 0 | 0 | 1005142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1003076 | 1005142 | 2066 | 900493
2 | T2548 | 20939965201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-08-27 | 14832876 | 14931694 | 15170352 | 98818.4 | 0 | 14252602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15170352 | 14252602 | -917750 | 15494259
2 | T2599 | 43726615201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 1048048 | 1048048 | 985628 | 0 | 0 | 985628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985628 | 985628 | 0 | 1120328
2 | T2601 | 21166315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 3712278 | 3713235 | 3797768 | 956.68 | 0 | 3782265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3797768 | 3782265 | -15503 | 4020992
2 | T2619 | 43265715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 985253 | 985253 | 900611 | 0 | 0 | 903976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900611 | 903976 | 3365 | 823384
2 | T2629 | 43056215201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 3955571 | 4118052 | 4040559 | 162481 | -43140 | 3949454 | -43140 | 0 | 0 | 0 | 0 | 0 | -43140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43140 | 3997419 | 3949454 | -47965 | 3564631
2 | T2635 | 42470035201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 348154 | 348154 | 353179 | 0 | 0 | 353179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353179 | 353179 | 0 | 330104
2 | T2644 | 43429515201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 1424722 | 1424722 | 1389257 | 0 | 0 | 1391632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1389257 | 1391632 | 2374 | 1869641
2 | T9015 | 43475815201 | F593504786 | ANGLIN CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-06-15 | 913111 | 913111 | 890230 | 0 | 0 | 890229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890230 | 890229 | -1 | 612984
3 | E3N84 | 21876225201 | F592982651 | WILLIAMS INDUSTRIAL & MARINE INC | N/A | N/A | N/A | N/A | 2016-07-14 | 531067 | 531067 | 486082 | 0 | -17424 | 468658 | -17424 | 0 | 0 | 0 | 0 | 0 | -17424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17424 | 468658 | 468658 | 0 | 761742
3 | E3P11 | 43257215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-04-14 | 6922953 | 6922953 | 6941583 | 0 | 0 | 6966761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6941583 | 6966761 | 25178 | 6237409
3 | E3P12 | 43255515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-11-10 | 751984 | 801537 | 761553 | 49553.08 | 0 | 761553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 761553 | 761553 | 0 | 851593 | B0 | ACC - LUMP SUM
3 | E3P15 | 43255015201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-11-17 | 1296000 | 1296000 | 1281750 | 0 | 0 | 1293176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1281750 | 1293176 | 11426 | 1595361 | B0 | ACC - LUMP SUM
3 | E3P74 | 22271315201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-06-09 | 916620 | 973642 | 931184 | 57021.58 | 0 | 931184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931184 | 931184 | 0 | 702427
3 | E3P75 | 43078615201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-07-14 | 2702301 | 2702301 | 2824495 | 0 | 0 | 2819950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2824495 | 2819950 | -4545 | 2591913
3 | E3P91 | 43460615201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-10-13 | 367076 | 367076 | 357176 | 0 | 0 | 357176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357176 | 357176 | 0 | 306636 | B0 | ACC - LUMP SUM
3 | T3380 | 22067915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2012-05-23 | 27973197 | 28765517 | 28817877 | 792320.21 | 0 | 27757494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28817877 | 27757494 | -1060383 | 27697061
3 | T3484 | 43000215201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-02-25 | 4296119 | 6114814 | 6340441 | 1818694.53 | 0 | 6332694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6340441 | 6332694 | -7747 | 3303857
3 | T3521 | 43078515201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-12-03 | 2580711 | 2556235 | 2428112 | -24475.9 | -31636 | 2365069 | -31636 | 0 | 0 | 0 | 0 | 0 | -31636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31636 | 2396476 | 2365069 | -31407 | 2532091
3 | T3528 | 22281815201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 931084 | 988106 | 921773 | 57021.56 | 0 | 921773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921773 | 921773 | 0 | 926503
3 | T3550 | 43257015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 9008956 | 9008956 | 9058480 | 0 | 0 | 8913154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9058480 | 8913154 | -145326 | 9047925
3 | T3553 | 43273915201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 5112998 | 5217096 | 5197254 | 104097.95 | -15000 | 5211856 | 0 | 0 | 0 | 0 | 0 | -15000 | -15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15000 | 5182254 | 5211856 | 29602 | 5858556
3 | T3574 | 43047115201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-08-31 | 710702 | 710702 | 703481 | 0 | -9504 | 696276 | -9504 | 0 | 0 | 0 | 0 | 0 | -9504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9504 | 693977 | 696276 | 2299 | 765581
3 | T3575 | 43079115201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 1223500 | 1223500 | 1204340 | 0 | 0 | 1216824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1204340 | 1216824 | 12484 | 1644577 | B0 | ACC - LUMP SUM
3 | T3576 | 42857615201 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-08-31 | 455335 | 461101 | 462306 | 5766.1 | 0 | 462306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462306 | 462306 | 0 | 517907
3 | T3599 | 42820835201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 311313 | 311313 | 302309 | 0 | 0 | 302309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302309 | 302309 | 0 | 204199 | B0 | ACC - LUMP SUM
3 | T3600 | 42695115201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-02-24 | 2196017 | 2209792 | 2194453 | 13775.67 | 0 | 2190296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2194453 | 2190296 | -4157 | 2203714
3 | T3616 | 43662215201 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 96639 | 96639 | 100978 | 0 | 0 | 100978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100978 | 100978 | 0 | 113500
3 | T3620 | 43278725201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2017-02-22 | 98537 | 98537 | 95183 | 0 | 0 | 95183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95183 | 95183 | 0 | 131242
4 | E4R04 | 43062515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-06-12 | 1604618 | 1604618 | 1554867 | 0 | 0 | 1554752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1554867 | 1554752 | -115 | 1736394 | B0 | ACC - LUMP SUM
4 | E4S04 | 43110715201 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2016-10-14 | 289809 | 289809 | 270949 | 0 | 0 | 270949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270949 | 270949 | 0 | 303226
4 | E4S17 | 43397715201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-01-06 | 280209 | 280209 | 215232 | 0 | 0 | 215232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215232 | 215232 | 0 | 253964
4 | T4408 | 42898415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 5457914 | 5501915 | 5476312 | 44001.24 | 0 | 5355390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5476312 | 5355390 | -120921 | 6001634
4 | T4429 | 43320715201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 1817368 | 1866868 | 1820548 | 49500 | 0 | 1828664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1820548 | 1828664 | 8115 | 1805873
4 | T4437 | 43510215201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-03-30 | 647604 | 693460 | 677812 | 45855.69 | 0 | 686116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677812 | 686116 | 8304 | 572056
4 | T4441 | 43799415201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 899605 | 899605 | 846333 | 0 | 50000 | 846333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 896333 | 846333 | -50000 | 1032155 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4443 | 43427515201 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2016-09-28 | 1312214 | 1312214 | 1253435 | 0 | 0 | 1261184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1253435 | 1261184 | 7749 | 1458807
5 | BE035 | 43387415201 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2015-08-10 | 8947000 | 9057405 | 9057405 | 110405 | 0 | 9057101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9057405 | 9057101 | -304 | 8947000 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | BE227 | 43029015201 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2016-04-22 | 1697000 | 1771015 | 1771015 | 74015 | 0 | 1771300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1771015 | 1771300 | 285 | 1668323
5 | E5Y32 | 43445515201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2016-08-02 | 622133 | 622133 | 564614 | 0 | 0 | 564745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564614 | 564745 | 131 | 567683
5 | E5Y36 | 43445615201 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2016-10-04 | 704674 | 704674 | 672674 | 0 | 0 | 672674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672674 | 672674 | 0 | 684420
5 | E5Y63 | 43234615201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-10-04 | 862770 | 868517 | 816671 | 5746.5 | -25344 | 791327 | -25344 | 0 | 0 | 0 | 0 | 0 | -25344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25344 | 791327 | 791327 | 0 | 776696
5 | T5533 | 42728015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-07-29 | 8422850 | 8665412 | 8608390 | 242561.74 | -105560 | 8174179 | -105560 | 0 | 0 | 0 | 0 | 0 | -105560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105560 | 8502830 | 8174179 | -328651 | 8647535
5 | T5553 | 43242115201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-03-30 | 1085604 | 1087044 | 1021639 | 1440 | -6360 | 1026222 | 0 | 0 | 0 | 0 | 0 | -6360 | -6360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6360 | 1015279 | 1026222 | 10943 | 1163003
5 | T5565 | 43065715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-27 | 3028041 | 3028041 | 2950282 | 0 | 0 | 2950886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950282 | 2950886 | 604 | 3357586 | B0 | ACC - LUMP SUM
5 | T5566 | 43243715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-07-27 | 3766852 | 3749136 | 3790510 | -17715.85 | 0 | 3819315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3790510 | 3819315 | 28805 | 4106501
6 | E6J00 | 43540715201 | F650817669 | FLORIDA TURF AND LANDSCAPE HORTICULTURE | N/A | N/A | N/A | N/A | 2015-01-29 | 204491 | 204491 | 200808 | 0 | 0 | 200808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200808 | 200808 | 0 | 234759 | B0 | ACC - LUMP SUM
6 | E6J27 | 43325415201 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2015-10-29 | 874736 | 839120 | 814919 | -35615.78 | 0 | 814919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 814919 | 814919 | 0 | 895055
6 | E6J41 | 43444315201 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2016-11-17 | 220419 | 220419 | 208800 | 0 | 0 | 208800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208800 | 208800 | 0 | 249619 | B0 | ACC - LUMP SUM
6 | E6J44 | 43468115201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-05-26 | 979602 | 823480 | 746877 | -156121.9 | 0 | 746877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 746877 | 746877 | 0 | 1105870
6 | E6J75 | 43652815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-06-09 | 847200 | 847200 | 789681 | 0 | 0 | 789681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789681 | 789681 | 0 | 1102469
6 | E6J76 | 43652915201 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2016-06-09 | 588728 | 588728 | 477515 | 0 | 0 | 477515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477515 | 477515 | 0 | 756280
6 | E6K21 | 42914635201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2016-07-28 | 177943 | 177943 | 173203 | 0 | 0 | 173203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173203 | 173203 | 0 | 196224
6 | E6K31 | 42934635201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-25 | 999395 | 999395 | 975146 | 0 | 0 | 975806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975146 | 975806 | 660 | 1051399
6 | E6K49 | 43058825201 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2016-09-29 | 864202 | 864202 | 790596 | 0 | 0 | 790888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790596 | 790888 | 292 | 885402 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
6 | T6345 | 24994165201 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2014-06-25 | 20210987 | 20241085 | 19700200 | 30097.79 | 800000 | 19298493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 20500200 | 19298493 | -1201707 | 19907818 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6349 | 42916225201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 4178283 | 4236996 | 3850525 | 58712.87 | 160000 | 3858312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 160000 | 160000 | 4010525 | 3858312 | -152213 | 5124942 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6380 | 41462435201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 3520907 | 3612854 | 3575998 | 91946.73 | 56000 | 3498466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 56000 | 56000 | 3631998 | 3498466 | -133532 | 3771064 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6385 | 43326415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 1122164 | 1210753 | 1131145 | 88589.58 | 0 | 1133153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1131145 | 1133153 | 2007 | 1217718
6 | T6391 | 43349215201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2016-04-27 | 1155673 | 1155673 | 1091324 | 0 | 0 | 1092555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1091324 | 1092555 | 1230 | 983084
6 | T6405 | 42934625201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-03-30 | 1071254 | 1073754 | 1058914 | 2500 | 0 | 1062745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058914 | 1062745 | 3831 | 1077071
7 | E7K09 | 43376015201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-03-09 | 4858889 | 4858889 | 4889946 | 0 | 0 | 4892719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889946 | 4892719 | 2773 | 4975480
7 | E7K14 | 43571815201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2015-06-23 | 5520000 | 5520000 | 5515787 | 0 | 0 | 5461492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5515787 | 5461492 | -54295 | 5318312 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
7 | T7220 | 40845925201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2011-06-29 | 94696203 | 99221504 | 102513161 | 4525301.07 | -176000 | 101320385 | 0 | 0 | 0 | 0 | 0 | -176000 | -176000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -176000 | 102337161 | 101320385 | -1016777 | 107019759
7 | T7346 | 43089815201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 6794444 | 6864518 | 7093818 | 70073.29 | 0 | 6785751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7093818 | 6785751 | -308067 | 6553700
7 | T7349 | 43124315201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 12544444 | 12706570 | 13012776 | 162125.3 | 0 | 12421061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13012776 | 12421061 | -591715 | 12199500
7 | T7377 | 42453295201 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-02-24 | 2482901 | 2542403 | 2373194 | 59502.28 | 0 | 2384196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373194 | 2384196 | 11002 | 2246000
7 | T7381 | 25589335201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 4590182 | 4640182 | 4586377 | 50000 | 0 | 4603104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4586377 | 4603104 | 16727 | 7190841
8 | E8P84 | 43560415201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-06-14 | 1564634 | 1564634 | 1570658 | 0 | 0 | 1593989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570658 | 1593989 | 23332 | 1798900
8 | E8P93 | 42933415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-04-12 | 1627383 | 1619754 | 1562111 | -7628.64 | 0 | 1565726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1562111 | 1565726 | 3615 | 1804453
8 | E8P96 | 43494625201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2016-05-24 | 938500 | 938500 | 828715 | 0 | 0 | 828715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 828715 | 828715 | 0 | 988990

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [7 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total
1 |  |  | 0 |  |  |  | 0 |  | 16278893 | 0% | 0
01 |  | 23626.41 |  | 1275.98 |  | 0 | 24902.39 |  | 78826727 | 0.03159% | 24902.39
02 |  |  |  | 24940 |  | 40322.9 | 65262.9 |  | 68483109 | 0.03642% | 24940
03 |  | 28522.03 |  |  | 961548.45 | 607036.08 | 1597106.56 |  | 12309341 | 8.043% | 990070.48
04 |  | 46166.52 |  |  |  | 46030.53 | 92197.05 |  | 29136924 | 0.1584% | 46166.52
05 |  | 2981.58 |  | 0 | 0 | 14523 | 17504.58 |  | 37015984 | 0.008055% | 2981.58
06 | 0 | 14445.35 |  |  | 0 | 0 | 14445.35 |  | 131487063 | 0.01099% | 14445.35
07 |  | 106724.57 |  | 23865.91 | 126179.53 | 576506.61 | 833276.62 |  | 4130517 | 6.216% | 256770.01
08 |  | 8022.37 |  |  |  | 974.3 | 8996.67 |  | 377668558 | 0.002124% | 8022.37
Grand Total | 0 | 230488.83 | 0 | 50081.89 | 1087727.98 | 1285393.42 | 2653692.12
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days SA
01 |  | 8 |  | 10 |  | 18 | 36 |  | 18
02 |  |  |  | 0 |  | 203 | 203 |  | 0
03 |  | 21 |  |  | 14 | 254 | 289 |  | 35
04 |  | 25 |  |  |  | 9 | 34 |  | 25
05 |  | 43 |  | 0 | 0 | 143 | 186 |  | 43
06 | 0 | 0 |  |  | 9 | 25 | 34 |  | 9
07 |  | 22 |  | 40 | 7 | 167 | 236 |  | 69
08 |  | 14 |  |  |  | 0 | 14 |  | 14
1 |  |  | 0 |  |  |  | 0 |  | 0
Grand Total | 0 | 133 | 0 | 50 | 30 | 819 | 1032
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
1 | 0 |  | 0 | 0 |  |  | 0 | 0 | 18 | 1375 | 1.309%
4 |  |  |  | 0 |  |  | 0 | 0 | 0 | 3436 | 0%
5 |  |  |  |  | 0 |  | 0 | 0 | 35 | 3415 | 1.025%
8 | [5 empty] | 0 | 0 | 0 | 25 | 1553 | 1.61%
01 |  | 14 |  |  |  | 14 | 28 | 14 | 57 | 1755 | 3.248%
02 | [5 empty] | 61 | 61 | 0 | 9 | 3935 | 0.2287%
03 |  | 58 |  |  | 121 | 317 | 496 | 179 | 248 | 3430 | 7.23%
06 |  | 40 |  |  |  |  | 40 | 40 | 54 | 545 | 9.908%
07 |  | 6 |  |  |  | 12 | 18 | 6 | 6 | 19444 | 0.03086%
Grand Total | 0 | 118 | 0 | 0 | 121 | 404 | 643

## Detailed Data - PPP
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
[29 empty] | 0% | 1
| Dist 01 - Central Let Contrats SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 01 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 01 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 02 Central Let Contract SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | E2Q62 | 20929495201 | 2012-07-17 | QTR1 | 12/13 | 2 | 2 | 1100 | 1382 | 1382 | 103.8% | 1 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | 0% | 1 | -95132842 | 102106 | 152 | 88 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849 | F900869955 | INFRASTRUCTURE DEV PARTNERS | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 |  | 2016-07-16 | QTR1 | 16/17 | 216 | 104626299 | B8:DBF:P3 | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP
[29 empty] | 0% | 1
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 1 | 2 | 2 | 1100 | 1382 | 1382 | 100% | 1 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | 200% | 2 | -95132842 | 102106 | 152 | 88 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849
| District 02 Totals |  |  |  |  | 1 | 2 | 2 | 1100 | 1382 | 1382 | 100% | 1 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | 300% | 3 | -95132842 | 102106 | 152 | 88 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849
[29 empty] | 0% | 1
| Dist 03 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 03 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 03 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 04 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 04 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 04 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 05 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 05 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 05 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 06 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 06 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 06 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 07 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 07 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 07 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 08 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide District Let Contracts SubTotal |  |  |  |  | 1 | 2 | 2 | 1100 | 1382 | 1382 | 100% | 1 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | 800% | 8 | -95132842 | 102106 | 152 | 88 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849
| Statewide Totals |  |  |  |  | 1 | 2 | 2 | 1100 | 1382 | 1382 | 100% | 1 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | 1500% | 15 | -95132842 | 102106 | 152 | 88 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849

## Sheet1 (hidden)
01CO | 01 | T1625 | 42988315201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 150 | 198 | 198 | 0 | 0 | 0 | 40 | 8 | 1852000 | 50000 | 1802000 | 1866275 | 1867608 | 0 | 0 | 0 | 1867608 | 1867700 | 92 | 14275 | 13 | 0 | 0 | 0 | 0 | 0 | 8 | 26881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8 | 26881 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-04-11 | QTR4 | 16/17 | 108 | 2064220.28 |  |  | 8 | 13 | 0 | 0 | 0 | 0 |  | CO | 6 | 01co | 1 | 6
01CO | 01 | T1628 | 43011915201 | 2016-01-27 | QTR3 | 15/16 | 2 | 3 | 250 | 289 | 289 | 0 | 0 | 0 | 36 | 3 | 5092548 | 54005 | 5038543 | 5147816 | 5084411 | 0 | 0 | 0 | 5084411 | 5074685 | -9725 | 55268 | 16 | 0 | 0 | 9739 | 0 | 0 | 3 | 56544 | 5272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 66284 | 5272 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-27 | QTR1 | 17/18 | 2017-04-05 | QTR4 | 16/17 | 113 | 5336136.69 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO | 3 | 01do | 7 | 9
01CO | 01 | T1658 | 43902815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 175 | 214 | 210 | 4 | 0 | 0 | 29 | 10 | 2041864 | 54329 | 1987535 | 2041864 | 1925079 | 0 | 0 | 0 | 1925079 | 1925198 | 118 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 10 | 16588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 16588 | 0 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-06-12 | QTR4 | 16/17 | 113 | 4696299.51 |  |  | 10 | 17 | 0 | 0 | 0 | 0 |  | CO | 8 | 02co | 10 | 17
01CO | 01 | T1662 | 43132515201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 75 | 90 | 97 | -7 | 7 | 0 | 15 | 0 | 150000 | 7492 | 142508 | 150000 | 141366 | -6706 | 0 | -6706 | 134660 | 134660 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452357137 | YD WEST COAST HOME INC | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-03-03 | QTR3 | 16/17 | 118 | 195237.61 | B0 | ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO | 4 | 02do | 18 | 21
01CO | 01 | T1668 | 43450715201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 100 | 104 | 99 | 5 | 0 | 0 | 4 | 0 | 860000 | 50000 | 810000 | 860000 | 810000 | 0 | 0 | 0 | 810000 | 810000 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-07-17 | QTR1 | 17/18 | 2017-04-25 | QTR4 | 16/17 | 108 | 1005379.75 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO | 13 | 03co | 22 | 34
01CO | 01 | T1A01 | 43134015201 | 2016-07-27 | QTR1 | 16/17 | 2 | 1 | 140 | 181 | 181 | 0 | 0 | 0 | 26 | 15 | 1006260 | 46751 | 959509 | 1032806 | 969407 | 0 | 0 | 0 | 969407 | 980874 | 11467 | 26546 | 7 | 0 | 15 | 35460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 35460 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-08-04 | QTR1 | 17/18 | 2017-06-03 | QTR4 | 16/17 | 118 | 1134236.85 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO | 7 | 03do | 35 | 41
01DO | 01 | E1O50 | 43121215201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 160 | 168 | 145 | 23 | 0 | 0 | 8 | 0 | 2473492 | 50000 | 2423492 | 2473492 | 2430162 | 0 | 0 | 0 | 2430162 | 2431258 | 1097 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-06-02 | QTR4 | 16/17 | 115 | 2383341.22 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | DO | 5 | 04co | 42 | 46
01DO | 01 | E1O53 | 43486515201 | 2015-12-17 | QTR2 | 15/16 | 1 | 3 | 245 | 278 | 278 | 0 | 0 | 0 | 33 | 0 | 1972999 | 50000 | 1922999 | 2017226 | 2027670 | 0 | 0 | 0 | 2027670 | 2027844 | 174 | 44227 | 5 | 14 | 0 | 37826 | 0 | 0 | 0 | 38283 | 12197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 88109 | 12197 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-10 | QTR1 | 17/18 | 2017-05-26 | QTR4 | 16/17 | 115 | 1579998.38 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO | 3 | 04do | 47 | 49
01DO | 01 | E1P64 | 43172315201 | 2016-08-18 | QTR1 | 16/17 | 1 | 0 | 80 | 82 | 80 | 2 | 0 | 0 | 2 | 0 | 829730 | 41730 | 788000 | 829730 | 788000 | 0 | 0 | 0 | 788000 | 788000 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 | 2017-05-31 | QTR4 | 16/17 | 118 | 915006.57 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO | 6 | 05co | 50 | 55
02CO | 02 | T2548 | 20939965201 | 2014-08-27 | QTR1 | 14/15 | 2 | 2 | 770 | 923 | 919 | 4 | 0 | 0 | 153 | 0 | 14832876 | 150000 | 14682876 | 14931694 | 15170352 | 0 | 0 | 0 | 15170352 | 14252602 | -917750 | 98818 | 93 | 0 | 0 | 40183 | 0 | 0 | 0 | 37352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149669 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 | 2017-05-19 | QTR4 | 16/17 | 208 | 15494259.21 |  |  | 0 | 60 | 0 | 0 | 0 | 0 | T | CO | 3 | 05do | 56 | 58
02CO | 02 | T2599 | 43726615201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 180 | 213 | 213 | 0 | 0 | 0 | 33 | 0 | 1048048 | 50000 | 998048 | 1048048 | 985628 | 0 | 0 | 0 | 985628 | 985628 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-07-14 | QTR1 | 17/18 | 2017-02-21 | QTR3 | 16/17 | 216 | 1120328.18 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO | 6 | 06co | 59 | 64
02CO | 02 | T2601 | 21166315201 | 2015-10-28 | QTR2 | 15/16 | 1 | 1 | 400 | 443 | 440 | 3 | 0 | 0 | 40 | 3 | 3712278 | 0 | 3712278 | 3713235 | 3797768 | 0 | 0 | 0 | 3797768 | 3782265 | -15503 | 957 | 23 | 0 | 3 | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 957 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 | 2017-04-13 | QTR4 | 16/17 | 209 | 4020991.68 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO | 9 | 06do | 65 | 73
02CO | 02 | T2619 | 43265715201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 150 | 164 | 160 | 4 | 0 | 0 | 14 | 0 | 985253 | 39196 | 946057 | 985253 | 900611 | 0 | 0 | 0 | 900611 | 903976 | 3365 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-04 | QTR1 | 17/18 | 2016-12-28 | QTR2 | 16/17 | 209 | 823384.31 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO | 5 | 07co | 74 | 78
02CO | 02 | T2629 | 43056215201 | 2015-12-03 | QTR2 | 15/16 | 4 | 1 | 175 | 283 | 298 | -15 | 15 | 0 | 73 | 35 | 3955571 | 57673 | 3897898 | 4118052 | 4040559 | -43140 | 0 | -43140 | 3997419 | 3949454 | -47965 | 162481 | 57 | 0 | 35 | 162481 | 0 | 0 | 0 | 26106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 188587 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 | 2017-01-05 | QTR3 | 16/17 | 208 | 3564631.32 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 2 | 07do | 79 | 80
02CO | 02 | T2635 | 42470035201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 75 | 140 | 135 | 5 | 0 | 0 | 57 | 8 | 348154 | 16878 | 331276 | 348154 | 353179 | 0 | 0 | 0 | 353179 | 353179 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11425 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-09-26 | QTR1 | 17/18 | 2017-07-11 | QTR1 | 17/18 | 208 | 330103.8 |  |  | 8 | 12 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 81 | 80
02CO | 02 | T2644 | 43429515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 90 | 93 | 86 | 7 | 0 | 0 | 3 | 0 | 1424722 | 50000 | 1374722 | 1424722 | 1389257 | 0 | 0 | 0 | 1389257 | 1391632 | 2374 | 0 | 3 | 0 | 0 | 547 | 0 | 0 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 | 2017-04-12 | QTR4 | 16/17 | 209 | 1869641.02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO | 3 | 08do | 81 | 83
02CO | 02 | T9015 | 43475815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 240 | 291 | 291 | 0 | 0 | 0 | 21 | 30 | 913111 | 20420 | 892691 | 913111 | 890230 | 0 | 0 | 0 | 890230 | 890229 | -1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 30 | 20420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20420 | 0 | F593504786 | ANGLIN CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-08-08 | QTR1 | 17/18 | 2017-06-28 | QTR4 | 16/17 | 209 | 612984.42 |  |  | 30 | 17 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2R19 | 20960715201 | 2013-12-12 | QTR2 | 13/14 | 1 | 2 | 800 | 1141 | 1139 | 2 | 0 | 0 | 254 | 87 | 44244000 | 150000 | 44094000 | 44497660 | 44485464 | 0 | 0 | 0 | 44485464 | 43929908 | -555556 | 253660 | 105 | 61 | 87 | 261680 | 29435 | 0 | 0 | 49212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 87 | 367067 | 29435 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2017-08-17 | QTR1 | 17/18 | 2017-03-27 | QTR3 | 16/17 | 208 | 49888540.47 | B8 | ACC - DESIGN/BUILD - MAJOR | 87 | 88 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 85250 | 19 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91 |  |  | 30 | 18 | 0 | 0 | 0 | 0 |  | DO |  | 0
02DO | 02 | E2U92 | 43015715201 | 2016-03-16 | QTR3 | 15/16 | 1 | 0 | 200 | 277 | 277 | 0 | 0 | 0 | 67 | 10 | 4567769 | 50000 | 4517769 | 4567769 | 4034344 | 0 | 0 | 0 | 4034344 | 4034680 | 336 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 | 2017-05-19 | QTR4 | 16/17 | 208 | 3766652.07 |  |  | 10 | 38 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V03 | 43242015201 | 2016-05-18 | QTR4 | 15/16 | 1 | 0 | 126 | 155 | 152 | 3 | 0 | 0 | 29 | 0 | 1065911 | 42293 | 1023618 | 1065911 | 1003076 | 0 | 0 | 0 | 1003076 | 1005142 | 2066 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 | 2017-04-28 | QTR4 | 16/17 | 209 | 900493.11 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3380 | 22067915201 | 2012-05-23 | QTR4 | 11/12 | 2 | 16 | 955 | 1636 | 1636 | 0 | 0 | 0 | 456 | 225 | 27973197 | 150000 | 27823197 | 28765517 | 28817877 | 0 | 0 | 0 | 28817877 | 27757494 | -1060383 | 792320 | 319 | 5 | 0 | 135159 | 0 | 37 | 70 | 1137365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 177 | 426650 | 213490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 247 | 1502304 | 213490 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-07-31 | QTR1 | 17/18 | 2017-03-03 | QTR3 | 16/17 | 313 | 27697061.12 |  |  | 5 | 88 | 0 | 0 | -797630 | 0 |  | CO
03CO | 03 | T3484 | 43000215201 | 2015-02-25 | QTR3 | 14/15 | 3 | 14 | 300 | 644 | 600 | 44 | 0 | 0 | 315 | 29 | 4296119 | 0 | 4296119 | 6114814 | 6340441 | 0 | 0 | 0 | 6340441 | 6332694 | -7747 | 1818695 | 99 | 0 | 1 | 6824 | 0 | 0 | 7 | 1522085 | 1237952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 7 | 245665 | 82769 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 44120 | 44120 | 0 | 0 | 0 | 0 | 193 | 29 | 1818695 | 1364841 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-05-05 | QTR4 | 16/17 | 308 | 3303857.17 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3521 | 43078515201 | 2015-12-03 | QTR2 | 15/16 | 3 | 2 | 200 | 397 | 409 | -12 | 12 | 0 | 196 | 1 | 2580711 | 50000 | 2530711 | 2556235 | 2428112 | -31636 | 0 | -31636 | 2396476 | 2365069 | -31407 | -24476 | 75 | 8 | 1 | 1155 | 0 | 73 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | -20162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1 | -15973 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 | 2017-03-31 | QTR3 | 16/17 | 308 | 2532090.83 |  |  | 1 | 37 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3528 | 22281815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 120 | 139 | 138 | 1 | 0 | 0 | 19 | 0 | 931084 | 33811 | 897273 | 988106 | 921773 | 0 | 0 | 0 | 921773 | 921773 | 0 | 57022 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 57022 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-07-27 | QTR1 | 17/18 | 2017-05-20 | QTR4 | 16/17 | 313 | 926503.43 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3550 | 43257015201 | 2015-12-03 | QTR2 | 15/16 | 1 | 0 | 195 | 323 | 318 | 5 | 0 | 0 | 128 | 0 | 9008956 | 100031 | 8908925 | 9008956 | 9058480 | 0 | 0 | 0 | 9058480 | 8913154 | -145326 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 7180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7180 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 | 2017-03-01 | QTR3 | 16/17 | 321 | 9047924.85 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3553 | 43273915201 | 2016-04-27 | QTR4 | 15/16 | 1 | 2 | 180 | 231 | 229 | 2 | 0 | 0 | 49 | 2 | 5112998 | 56886 | 5056112 | 5217096 | 5197254 | -15000 | 0 | -15000 | 5182254 | 5211856 | 29602 | 104098 | 31 | 0 | 2 | 49607 | 0 | 0 | 0 | 47212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 99339 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-03-10 | QTR3 | 16/17 | 321 | 5858555.67 |  |  | 2 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3574 | 43047115201 | 2016-08-31 | QTR1 | 16/17 | 1 | 0 | 125 | 166 | 172 | -6 | 6 | 0 | 41 | 0 | 710702 | 0 | 710702 | 710702 | 703481 | -9504 | 0 | -9504 | 693977 | 696276 | 2299 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-04-21 | QTR4 | 16/17 | 308 | 765580.95 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3575 | 43079115201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 65 | 72 | 72 | 0 | 0 | 0 | 7 | 0 | 1223500 | 50000 | 1173500 | 1223500 | 1204340 | 0 | 0 | 0 | 1204340 | 1216824 | 12484 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-16 | QTR1 | 17/18 | 2017-04-18 | QTR4 | 16/17 | 313 | 1644576.72 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3576 | 42857615201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 120 | 191 | 191 | 0 | 0 | 0 | 53 | 18 | 455335 | 0 | 455335 | 461101 | 462306 | 0 | 0 | 0 | 462306 | 462306 | 0 | 5766 | 40 | 0 | 0 | 0 | 0 | 0 | 18 | 5766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 5766 | 0 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-05-20 | QTR4 | 16/17 | 313 | 517906.59 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3599 | 42820835201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 90 | 92 | 83 | 9 | 0 | 0 | 2 | 0 | 311313 | 9628 | 301685 | 311313 | 302309 | 0 | 0 | 0 | 302309 | 302309 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-02 | QTR1 | 17/18 | 2017-03-31 | QTR3 | 16/17 | 308 | 204199 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3600 | 42695115201 | 2016-02-24 | QTR3 | 15/16 | 1 | 1 | 155 | 299 | 299 | 0 | 0 | 0 | 130 | 14 | 2196017 | 50000 | 2146017 | 2209792 | 2194453 | 0 | 0 | 0 | 2194453 | 2190296 | -4157 | 13776 | 80 | 0 | 0 | 0 | 0 | 15 | 14 | 16901 | 13776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14 | 21411 | 13776 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-08-16 | QTR1 | 17/18 | 2017-03-29 | QTR3 | 16/17 | 308 | 2203713.84 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3616 | 43662215201 | 2017-03-29 | QTR3 | 16/17 | 1 | 0 | 60 | 75 | 63 | 12 | 0 | 0 | 15 | 0 | 96639 | 0 | 96639 | 96639 | 100978 | 0 | 0 | 0 | 100978 | 100978 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | ROBERTS C.W. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | QTR1 | 17/18 | 2017-08-02 | QTR1 | 17/18 | 321 | 113500 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3620 | 43278725201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 45 | 69 | 69 | 0 | 0 | 0 | 24 | 0 | 98537 | 0 | 98537 | 98537 | 95183 | 0 | 0 | 0 | 95183 | 95183 | 0 | 0 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 | 2017-07-12 | QTR1 | 17/18 | 321 | 131241.78 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3N84 | 21876225201 | 2016-07-14 | QTR1 | 16/17 | 1 | 0 | 120 | 179 | 190 | -11 | 11 | 0 | 59 | 0 | 531067 | 36301 | 494766 | 531067 | 486082 | -17424 | 0 | -17424 | 468658 | 468658 | 0 | 0 | 11 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | F592982651 | WILLIAMS INDUSTRIAL & MARINE INC | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-05-01 | QTR4 | 16/17 | 321 | 761742 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P11 | 43257215201 | 2016-04-14 | QTR4 | 15/16 | 1 | 0 | 210 | 314 | 313 | 1 | 0 | 0 | 104 | 0 | 6922953 | 61524 | 6861429 | 6922953 | 6941583 | 0 | 0 | 0 | 6941583 | 6966761 | 25178 | 0 | 60 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-29 | QTR1 | 17/18 | 2017-05-18 | QTR4 | 16/17 | 314 | 6237409.01 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P12 | 43255515201 | 2016-11-10 | QTR2 | 16/17 | 1 | 1 | 90 | 105 | 105 | 0 | 0 | 0 | 15 | 0 | 751984 | 39984 | 712000 | 801537 | 761553 | 0 | 0 | 0 | 761553 | 761553 | 0 | 49553 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 49553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 49553 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-09-14 | QTR1 | 17/18 | 2017-05-26 | QTR4 | 16/17 | 308 | 851593.48 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P15 | 43255015201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 90 | 95 | 88 | 7 | 0 | 0 | 5 | 0 | 1296000 | 50000 | 1246000 | 1296000 | 1281750 | 0 | 0 | 0 | 1281750 | 1293176 | 11426 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2017-08-28 | QTR1 | 17/18 | 2017-04-30 | QTR4 | 16/17 | 321 | 1595361.1 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P74 | 22271315201 | 2016-06-09 | QTR4 | 15/16 | 1 | 1 | 120 | 137 | 137 | 0 | 0 | 0 | 17 | 0 | 916620 | 32497 | 884123 | 973642 | 931184 | 0 | 0 | 0 | 931184 | 931184 | 0 | 57022 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-05-12 | QTR4 | 16/17 | 308 | 702427.14 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P75 | 43078615201 | 2016-07-14 | QTR1 | 16/17 | 2 | 0 | 100 | 210 | 210 | 0 | 0 | 0 | 110 | 0 | 2702301 | 50119 | 2652182 | 2702301 | 2824495 | 0 | 0 | 0 | 2824495 | 2819950 | -4545 | 0 | 17 | 73 | 0 | 5732 | 0 | 4 | 0 | 14182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 19914 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 | 2017-04-27 | QTR4 | 16/17 | 308 | 2591912.99 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P91 | 43460615201 | 2016-10-13 | QTR2 | 16/17 | 1 | 0 | 75 | 100 | 100 | 0 | 0 | 0 | 25 | 0 | 367076 | 15130 | 351946 | 367076 | 357176 | 0 | 0 | 0 | 357176 | 357176 | 0 | 0 | 12 | 0 | 0 | 5230 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 5230 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 | 2017-04-22 | QTR4 | 16/17 | 308 | 306636.35 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4408 | 42898415201 | 2015-04-29 | QTR4 | 14/15 | 2 | 7 | 590 | 716 | 711 | 5 | 0 | 0 | 126 | 0 | 5457914 | 59401 | 5398513 | 5501915 | 5476312 | 0 | 0 | 0 | 5476312 | 5355390 | -120921 | 44001 | 96 | 0 | 0 | 8201 | 0 | 0 | 0 | 99691 | 4389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75511 | 4389 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-08-11 | QTR1 | 17/18 | 2017-06-23 | QTR4 | 16/17 | 408 | 6001634.3 |  |  | 0 | 30 | 0 | 0 | -77463 | 0 |  | CO
04CO | 04 | T4429 | 43320715201 | 2016-02-24 | QTR3 | 15/16 | 2 | 2 | 276 | 345 | 344 | 1 | 0 | 0 | 44 | 25 | 1817368 | 50000 | 1767368 | 1866868 | 1820548 | 0 | 0 | 0 | 1820548 | 1828664 | 8115 | 49500 | 31 | 0 | 0 | 23754 | 0 | 0 | 25 | 41825 | 27746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 65579 | 27746 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-28 | QTR1 | 17/18 | 2017-06-27 | QTR4 | 16/17 | 412 | 1805872.62 |  |  | 25 | 13 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4437 | 43510215201 | 2016-03-30 | QTR3 | 15/16 | 1 | 3 | 48 | 104 | 104 | 0 | 0 | 0 | 47 | 9 | 647604 | 27717 | 619887 | 693460 | 677812 | 0 | 0 | 0 | 677812 | 686116 | 8304 | 45856 | 45 | 0 | 0 | 0 | 0 | 0 | 9 | 29362 | 34197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10791 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 51453 | 44988 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2017-08-08 | QTR1 | 17/18 | 2016-11-07 | QTR2 | 16/17 | 409 | 572056.26 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4441 | 43799415201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 134 | 136 | 62 | 74 | 0 | 0 | 2 | 0 | 899605 | 49184 | 850421 | 899605 | 846333 | 0 | 50000 | 50000 | 896333 | 846333 | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-09-25 | QTR1 | 17/18 | 2017-08-15 | QTR1 | 17/18 | 412 | 1032154.5 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4443 | 43427515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 120 | 131 | 131 | 0 | 0 | 0 | 11 | 0 | 1312214 | 50000 | 1262214 | 1312214 | 1253435 | 0 | 0 | 0 | 1253435 | 1261184 | 7749 | 0 | 0 | 0 | 0 | 801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2017-08-07 | QTR1 | 17/18 | 2017-04-21 | QTR4 | 16/17 | 408 | 1458806.8 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4R04 | 43062515201 | 2015-06-12 | QTR4 | 14/15 | 1 | 0 | 255 | 296 | 293 | 3 | 0 | 0 | 41 | 0 | 1604618 | 50000 | 1554618 | 1604618 | 1554867 | 0 | 0 | 0 | 1554867 | 1554752 | -115 | 0 | 23 | 0 | 0 | 6891 | 0 | 0 | 0 | 1506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8397 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-07 | QTR1 | 17/18 | 2017-06-28 | QTR4 | 16/17 | 412 | 1736394.32 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S04 | 43110715201 | 2016-10-14 | QTR2 | 16/17 | 1 | 0 | 102 | 118 | 116 | 2 | 0 | 0 | 16 | 0 | 289809 | 14415 | 275394 | 289809 | 270949 | 0 | 0 | 0 | 270949 | 270949 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2017-08-23 | QTR1 | 17/18 | 2017-06-09 | QTR4 | 16/17 | 412 | 303225.64 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S17 | 43397715201 | 2017-01-06 | QTR3 | 16/17 | 1 | 0 | 28 | 34 | 33 | 1 | 0 | 0 | 6 | 0 | 280209 | 12373 | 267836 | 280209 | 215232 | 0 | 0 | 0 | 215232 | 215232 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10803 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-09-20 | QTR1 | 17/18 | 2017-07-20 | QTR1 | 17/18 | 412 | 253963.62 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | BE035 | 43387415201 | 2015-08-10 | QTR1 | 15/16 | 1 | 6 | 345 | 494 | 495 | -1 | 1 | 0 | 40 | 109 | 8947000 | 150000 | 8797000 | 9057405 | 9057405 | 0 | 0 | 0 | 9057405 | 9057101 | -304 | 110405 | 14 | 0 | 55 | 165982 | 14523 | 0 | 54 | -39561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 110405 | 14523 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-05-05 | QTR4 | 16/17 | 509 | 8947000 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | BE227 | 43029015201 | 2016-04-22 | QTR4 | 15/16 | 1 | 5 | 220 | 244 | 243 | 1 | 0 | 0 | 24 | 0 | 1697000 | 50000 | 1647000 | 1771015 | 1771015 | 0 | 0 | 0 | 1771015 | 1771300 | 285 | 74015 | 4 | 0 | 0 | 62930 | 0 | 0 | 0 | 11085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74015 | 0 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-05-12 | QTR4 | 16/17 | 513 | 1668323.35 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5533 | 42728015201 | 2015-07-29 | QTR1 | 15/16 | 2 | 9 | 340 | 466 | 494 | -28 | 28 | 0 | 65 | 61 | 8422850 | 50000 | 8372850 | 8665412 | 8608390 | -105560 | 0 | -105560 | 8502830 | 8174179 | -328651 | 242562 | 28 | 0 | 0 | 4603 | 0 | 0 | 46 | 107535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 176219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 288356 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-09-05 | QTR1 | 17/18 | 2017-04-04 | QTR4 | 16/17 | 512 | 8647534.74 |  |  | 39 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5553 | 43242115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 1 | 150 | 171 | 169 | 2 | 0 | 0 | 21 | 0 | 1085604 | 50000 | 1035604 | 1087044 | 1021639 | -6360 | 0 | -6360 | 1015279 | 1026222 | 10943 | 1440 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 6692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6692 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-07-13 | QTR1 | 17/18 | 2017-04-24 | QTR4 | 16/17 | 595 | 1163003.22 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5565 | 43065715201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 230 | 273 | 273 | 0 | 0 | 0 | 43 | 0 | 3028041 | 50000 | 2978041 | 3028041 | 2950282 | 0 | 0 | 0 | 2950282 | 2950886 | 604 | 0 | 24 | 0 | 0 | 5094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5094 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-08 | QTR1 | 17/18 | 2017-07-21 | QTR1 | 17/18 | 514 | 3357586 | B0 | ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5566 | 43243715201 | 2016-07-27 | QTR1 | 16/17 | 1 | 2 | 150 | 195 | 195 | 0 | 0 | 0 | 37 | 8 | 3766852 | 50000 | 3716852 | 3749136 | 3790510 | 0 | 0 | 0 | 3790510 | 3819315 | 28805 | -17716 | 19 | 0 | 0 | -8096 | 0 | 0 | 8 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4316 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-09-08 | QTR1 | 17/18 | 2017-05-08 | QTR4 | 16/17 | 514 | 4106500.86 |  |  | 8 | 17 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5Y32 | 43445515201 | 2016-08-02 | QTR1 | 16/17 | 1 | 0 | 120 | 189 | 177 | 12 | 0 | 0 | 69 | 0 | 622133 | 26000 | 596133 | 622133 | 564614 | 0 | 0 | 0 | 564614 | 564745 | 131 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2017-09-06 | QTR1 | 17/18 | 2017-04-28 | QTR4 | 16/17 | 513 | 567682.87 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y36 | 43445615201 | 2016-10-04 | QTR2 | 16/17 | 1 | 0 | 110 | 118 | 118 | 0 | 0 | 0 | 8 | 0 | 704674 | 32000 | 672674 | 704674 | 672674 | 0 | 0 | 0 | 672674 | 672674 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 | 2017-05-05 | QTR4 | 16/17 | 515 | 684419.55 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y63 | 43234615201 | 2016-10-04 | QTR2 | 16/17 | 1 | 1 | 90 | 116 | 132 | -16 | 16 | 0 | 18 | 8 | 862770 | 33000 | 829770 | 868517 | 816671 | -25344 | 0 | -25344 | 791327 | 791327 | 0 | 5747 | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 | 2017-05-15 | QTR4 | 16/17 | 513 | 776696.15 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6345 | 24994165201 | 2014-06-25 | QTR4 | 13/14 | 2 | 5 | 780 | 859 | 754 | 105 | 0 | 0 | 70 | 9 | 20210987 | 648000 | 19562987 | 20241085 | 19700200 | 0 | 800000 | 800000 | 20500200 | 19298493 | -1201707 | 30098 | 51 | 0 | 0 | 325806 | 0 | 0 | 0 | 277026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5947 | 0 | 0 | 0 | 8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2882 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 196909 | 0 | F592373403 | MUNILLA CONSTRUCTION MANAGEMENT LLC D/B/ | N/A | N/A | N/A | N/A | 2017-09-19 | QTR1 | 17/18 | 2017-01-27 | QTR3 | 16/17 | 606 | 19907818.44 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 19 | 0 | 0 | -422785 | 0 |  | CO
06CO | 06 | T6349 | 42916225201 | 2016-04-27 | QTR4 | 15/16 | 2 | 7 | 240 | 263 | 195 | 68 | 0 | 0 | 23 | 0 | 4178283 | 50000 | 4128283 | 4236996 | 3850525 | 0 | 160000 | 160000 | 4010525 | 3858312 | -152213 | 58713 | 14 | 0 | 0 | 24297 | 0 | 0 | 0 | 74263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9298 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91182 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-02-24 | QTR3 | 16/17 | 606 | 5124941.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6380 | 41462435201 | 2015-06-17 | QTR4 | 14/15 | 3 | 3 | 280 | 383 | 382 | 1 | 0 | 0 | 103 | 0 | 3520907 | 50505 | 3470402 | 3612854 | 3575998 | 0 | 56000 | 56000 | 3631998 | 3498466 | -133532 | 91947 | 47 | 0 | 0 | 1588 | 0 | 40 | 0 | 82138 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 83726 | 8200 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 | 2017-01-20 | QTR3 | 16/17 | 606 | 3771064.2 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6385 | 43326415201 | 2016-01-27 | QTR3 | 15/16 | 2 | 1 | 180 | 259 | 259 | 0 | 0 | 0 | 54 | 25 | 1122164 | 50070 | 1072094 | 1210753 | 1131145 | 0 | 0 | 0 | 1131145 | 1133153 | 2007 | 88590 | 37 | 0 | 0 | 17204 | 0 | 0 | 25 | 90738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 107942 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-04-04 | QTR4 | 16/17 | 606 | 1217718.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6391 | 43349215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 180 | 208 | 208 | 0 | 0 | 0 | 28 | 0 | 1155673 | 47446 | 1108227 | 1155673 | 1091324 | 0 | 0 | 0 | 1091324 | 1092555 | 1230 | 0 | 11 | 0 | 0 | 12008 | 0 | 0 | 0 | 2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21825 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 | 2017-05-21 | QTR4 | 16/17 | 606 | 983083.6 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6405 | 42934625201 | 2016-03-30 | QTR3 | 15/16 | 3 | 1 | 160 | 216 | 215 | 1 | 0 | 0 | 56 | 0 | 1071254 | 50000 | 1021254 | 1073754 | 1058914 | 0 | 0 | 0 | 1058914 | 1062745 | 3831 | 2500 | 43 | 0 | 0 | 3296 | 0 | 0 | 0 | 3287 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5133 | 0 | 0 | 0 | 2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14682 | 787 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 | 2017-04-28 | QTR4 | 16/17 | 606 | 1077071.2 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J00 | 43540715201 | 2015-01-29 | QTR3 | 14/15 | 1 | 0 | 790 | 794 | 791 | 3 | 0 | 0 | 4 | 0 | 204491 | 11179 | 193312 | 204491 | 200808 | 0 | 0 | 0 | 200808 | 200808 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | F650817669 | FLORIDA TURF AND LANDSCAPE HORTICULTURE | N/A | N/A | N/A | N/A | 2017-08-17 | QTR1 | 17/18 | 2017-07-24 | QTR1 | 17/18 | 606 | 234759 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J27 | 43325415201 | 2015-10-29 | QTR2 | 15/16 | 1 | 1 | 240 | 364 | 364 | 0 | 0 | 0 | 124 | 0 | 874736 | 43765 | 830971 | 839120 | 814919 | 0 | 0 | 0 | 814919 | 814919 | 0 | -35616 | 105 | 0 | 0 | 10698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24918 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2017-07-18 | QTR1 | 17/18 | 2017-04-26 | QTR4 | 16/17 | 606 | 895054.75 |  |  | 0 | 19 | 0 | 0 | -35616 | 0 |  | DO
06DO | 06 | E6J41 | 43444315201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 70 | 77 | 77 | 0 | 0 | 0 | 7 | 0 | 220419 | 11619 | 208800 | 220419 | 208800 | 0 | 0 | 0 | 208800 | 208800 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2017-09-06 | QTR1 | 17/18 | 2017-04-23 | QTR4 | 16/17 | 606 | 249619 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J44 | 43468115201 | 2016-05-26 | QTR4 | 15/16 | 1 | 1 | 240 | 317 | 257 | 60 | 0 | 0 | 77 | 0 | 979602 | 50000 | 929602 | 823480 | 746877 | 0 | 0 | 0 | 746877 | 746877 | 0 | -156122 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | -156122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -156122 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 | 2017-06-09 | QTR4 | 16/17 | 606 | 1105870 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J75 | 43652815201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 215 | 220 | 132 | 88 | 0 | 0 | 5 | 0 | 847200 | 50000 | 797200 | 847200 | 789681 | 0 | 0 | 0 | 789681 | 789681 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-08-15 | QTR1 | 17/18 | 2017-06-20 | QTR4 | 16/17 | 606 | 1102468.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J76 | 43652915201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 180 | 234 | 220 | 14 | 0 | 0 | 54 | 0 | 588728 | 36323 | 552405 | 588728 | 477515 | 0 | 0 | 0 | 477515 | 477515 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-05-08 | QTR4 | 16/17 | 606 | 756279.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K21 | 42914635201 | 2016-07-28 | QTR1 | 16/17 | 1 | 0 | 100 | 107 | 105 | 2 | 0 | 0 | 7 | 0 | 177943 | 9346 | 168597 | 177943 | 173203 | 0 | 0 | 0 | 173203 | 173203 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2017-07-13 | QTR1 | 17/18 | 2017-06-12 | QTR4 | 16/17 | 606 | 196223.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K31 | 42934635201 | 2016-08-25 | QTR1 | 16/17 | 1 | 0 | 140 | 162 | 145 | 17 | 0 | 0 | 22 | 0 | 999395 | 50000 | 949395 | 999395 | 975146 | 0 | 0 | 0 | 975146 | 975806 | 660 | 0 | 19 | 0 | 0 | 9015 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31215 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 | 2017-06-30 | QTR4 | 16/17 | 606 | 1051398.75 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K49 | 43058825201 | 2016-09-29 | QTR1 | 16/17 | 2 | 0 | 140 | 187 | 187 | 0 | 0 | 0 | 47 | 0 | 864202 | 42202 | 822000 | 864202 | 790596 | 0 | 0 | 0 | 790596 | 790888 | 292 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2017-09-18 | QTR1 | 17/18 | 2017-07-28 | QTR1 | 17/18 | 606 | 885402 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7220 | 40845925201 | 2011-06-29 | QTR4 | 10/11 | 6 | 63 | 1500 | 1779 | 1779 | 0 | 0 | 0 | 237 | 42 | 94696203 | 150000 | 94546203 | 99221504 | 102513161 | -176000 | 0 | -176000 | 102337161 | 101320385 | -1016777 | 4525301 | 164 | 0 | 0 | 1140417 | 444656 | 0 | 0 | 638567 | 94458 | 0 | 0 | 0 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2636702 | 157507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347209 | 54885 | 0 | 0 | 0 | 0 | 0 | 0 | 4136 | 4136 | 0 | 0 | 0 | 0 | 0 | 42 | 4335071 | 755643 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-07-07 | QTR1 | 17/18 | 2016-08-26 | QTR1 | 16/17 | 714 | 107019759.03 |  |  | 42 | 73 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7346 | 43089815201 | 2014-07-30 | QTR1 | 14/15 | 1 | 5 | 390 | 599 | 599 | 0 | 0 | 0 | 170 | 39 | 6794444 | 62000 | 6732444 | 6864518 | 7093818 | 0 | 0 | 0 | 7093818 | 6785751 | -308067 | 70073 | 144 | 0 | 17 | 18684 | 0 | 0 | 22 | 128610 | 6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 112644 | 6122 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2016-08-25 | QTR1 | 16/17 | 717 | 6553700 |  |  | 39 | 26 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7349 | 43124315201 | 2014-06-18 | QTR4 | 13/14 | 2 | 5 | 400 | 654 | 652 | 2 | 0 | 0 | 203 | 51 | 12544444 | 119000 | 12425444 | 12706570 | 13012776 | 0 | 0 | 0 | 13012776 | 12421061 | -591715 | 162125 | 167 | 6 | 11 | 89297 | 0 | 0 | 40 | 77646 | 16339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15383 | 15383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 51 | 182326 | 31722 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-31 | QTR1 | 17/18 | 2016-10-25 | QTR2 | 16/17 | 798 | 12199500 |  |  | 45 | 30 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7377 | 42453295201 | 2016-02-24 | QTR3 | 15/16 | 3 | 6 | 260 | 309 | 309 | 0 | 0 | 0 | 46 | 3 | 2482901 | 50000 | 2432901 | 2542403 | 2373194 | 0 | 0 | 0 | 2373194 | 2384196 | 11002 | 59502 | 25 | 0 | 3 | 56002 | 0 | 0 | 0 | 8532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 64535 | 0 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-07-25 | QTR1 | 17/18 | 2017-05-17 | QTR4 | 16/17 | 709 | 2246000 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7381 | 25589335201 | 2016-05-25 | QTR4 | 15/16 | 2 | 1 | 200 | 284 | 284 | 0 | 0 | 0 | 56 | 28 | 4590182 | 55000 | 4535182 | 4640182 | 4586377 | 0 | 0 | 0 | 4586377 | 4603104 | 16727 | 50000 | 22 | 0 | 7 | 26821 | 0 | 0 | 0 | 14230 | 1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 57192 | 1901 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-09-27 | QTR1 | 17/18 | 2017-05-31 | QTR4 | 16/17 | 717 | 7190840.88 |  |  | 28 | 34 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7K09 | 43376015201 | 2016-03-09 | QTR3 | 15/16 | 1 | 0 | 165 | 235 | 235 | 0 | 0 | 0 | 70 | 0 | 4858889 | 50000 | 4808889 | 4858889 | 4889946 | 0 | 0 | 0 | 4889946 | 4892719 | 2773 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-01-20 | QTR3 | 16/17 | 798 | 4975480 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K14 | 43571815201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 515 | 678 | 678 | 0 | 0 | 0 | 90 | 73 | 5520000 | 50000 | 5470000 | 5520000 | 5515787 | 0 | 0 | 0 | 5515787 | 5461492 | -54295 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 73 | 42916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 42916 | 0 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-08-23 | QTR1 | 17/18 | 2017-07-10 | QTR1 | 17/18 | 709 | 5318312 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD | 73 | 30 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P84 | 43560415201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 215 | 250 | 251 | -1 | 1 | 0 | 21 | 14 | 1564634 | 50000 | 1514634 | 1564634 | 1570658 | 0 | 0 | 0 | 1570658 | 1593989 | 23332 | 0 | 4 | 0 | 0 | 8912 | 0 | 0 | 14 | 23635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 32548 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-25 | QTR1 | 17/18 | 2017-05-24 | QTR4 | 16/17 | 854 | 1798899.5 |  |  | 14 | 17 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P93 | 42933415201 | 2016-04-12 | QTR4 | 15/16 | 2 | 1 | 155 | 189 | 189 | 0 | 0 | 0 | 34 | 0 | 1627383 | 48815 | 1578568 | 1619754 | 1562111 | 0 | 0 | 0 | 1562111 | 1565726 | 3615 | -7629 | 14 | 0 | 0 | -1000 | 0 | 0 | 0 | 16722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18273 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-07 | QTR1 | 17/18 | 2017-04-05 | QTR4 | 16/17 | 854 | 1804452.94 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P96 | 43494625201 | 2016-05-24 | QTR4 | 15/16 | 3 | 1 | 175 | 190 | 187 | 3 | 0 | 0 | 15 | 0 | 938500 | 46648 | 891852 | 938500 | 828715 | 0 | 0 | 0 | 828715 | 828715 | 0 | 0 | 1 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 | 2017-05-12 | QTR4 | 16/17 | 854 | 988989.54 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
02DO | 02 | E2Q62 | 20929495201 | 2012-07-17 | QTR1 | 12/13 | 2 | 2 | 1100 | 1382 | 1382 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | -95132842 | 102106 | 152 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849 | F900869955 | INFRASTRUCTURE DEV PARTNERS | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 | 2016-07-16 | QTR1 | 16/17 | 216 | 104626299 | B8:DBF:P3 | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP | 0 | 88 | 0 | 0 | 0 | 0 |  | DO | 0 | 01co | 1 | 0
CO | [104 empty] | CO | 0 | 01do | 1 | 0
CO | [104 empty] | CO | 0 | 02co | 1 | 0
CO | [104 empty] | CO | 1 | 02do | 1 | 1
CO | [104 empty] | CO | 0 | 03co | 2 | 1
CO | [104 empty] | CO | 0 | 03do | 2 | 1
CO | [104 empty] | CO | 0 | 04co | 2 | 1
CO | [104 empty] | CO | 0 | 04do | 2 | 1
CO | [104 empty] | CO | 0 | 05co | 2 | 1
CO | [103 empty] | T | CO | 0 | 05do | 2 | 1
CO | [104 empty] | CO | 0 | 06co | 2 | 1
CO | [104 empty] | CO | 0 | 06do | 2 | 1
CO | [104 empty] | CO | 0 | 07co | 2 | 1
CO | [104 empty] | CO | 0 | 07do | 2 | 1
CO | [104 empty] | CO | 0 | 08co | 2 | 1
CO | [104 empty] | CO | 0 | 08do | 2 | 1
CO | [104 empty] | CO
CO | [104 empty] | CO
CO | [104 empty] | CO |  | 0