## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 187593921 | 186157777 | 192639791 | 190033736 | 3500000 | 185291277 | -0.4655% | 96.43% | 5333696 | 2.865% | 4988713 | 2.659% | 6528 | 860 | 13.17% | 433 | 6.633% | 121 | 1.854% | 387 | 5.928% | 7036 | 7.782% | 8329 | 8315 | 7022 | 7.567% | 89.29%
| District Let | 61251660 | 60155874 | 63161559 | 61293239 | 1341000 | 61140478 | 1.637% | 90.91% | 1819259 | 3.024% | 1909900 | 3.118% | 4220 | 561 | 13.29% | 247 | 5.853% | 50 | 1.185% | 339 | 8.033% | 4609 | 9.218% | 5436 | 5385 | 4577 | 8.46% | 86.36%
| All Contracts | 248845581 | 246313651 | 255801350 | 251326975 | 4841000 | 246431755 | 0.04795% | 94% | 7152955 | 2.904% | 6898613 | 2.772% | 10748 | 1421 | 13.22% | 680 | 6.327% | 171 | 1.591% | 726 | 6.755% | 11645 | 8.346% | 13765 | 13700 | 11599 | 7.918% | 88%
2 | Central Let | 195302600 | 192843354 | 197562989 | 197996186 | 150000 | 188806771 | -2.093% | 94.12% | 3110294 | 1.613% | 2258040 | 1.156% | 9765 | 1951 | 19.98% | 848 | 8.684% | 109 | 1.116% | 377 | 3.861% | 10251 | 4.977% | 13070 | 14180 | 11381 | 16.55% | 85.29%
| District Let | 96972480 | 95925202 | 99217392 | 98289393 | 0 | 96261114 | 0.3502% | 94.74% | 2485413 | 2.591% | 2243411 | 2.313% | 4031 | 607 | 15.06% | 431 | 10.69% | 190 | 4.713% | 374 | 9.278% | 4595 | 13.99% | 5654 | 5810 | 4772 | 18.38% | 68.42%
| All Contracts | 292275080 | 288768556 | 296780381 | 296285579 | 150000 | 285067885 | -1.282% | 94.34% | 5595707 | 1.938% | 4501451 | 1.54% | 13796 | 2558 | 18.54% | 1279 | 9.271% | 299 | 2.167% | 751 | 5.444% | 14846 | 7.611% | 18724 | 19990 | 16153 | 17.08% | 79.25%
3 | Central Let | 168503946 | 166809869 | 178880679 | 180786993 | 0 | 177294802 | 6.286% | 90.48% | 11373721 | 6.818% | 10371940 | 6.155% | 8428 | 2636 | 31.28% | 925 | 10.98% | 833 | 9.884% | 696 | 8.258% | 9957 | 18.14% | 13499 | 13366 | 9805 | 16.34% | 83.33%
| District Let | 41645875 | 40876581 | 42342155 | 42082127 | 0 | 41848223 | 2.377% | 93.75% | 904174 | 2.212% | 667482 | 1.603% | 2450 | 641 | 26.16% | 319 | 13.02% | 301 | 12.29% | 84 | 3.429% | 2835 | 15.71% | 3795 | 3715 | 2755 | 12.45% | 75%
| All Contracts | 210149821 | 207686450 | 221222834 | 222869120 | 0 | 219143025 | 5.516% | 91.38% | 12277895 | 5.912% | 11039422 | 5.253% | 10878 | 3277 | 30.13% | 1244 | 11.44% | 1134 | 10.42% | 780 | 7.17% | 12792 | 17.6% | 17294 | 17081 | 12560 | 15.46% | 81.03%
4 | Central Let | 70435628 | 69551128 | 73435952 | 72007714 | 194900 | 70879234 | 1.91% | 100% | 3262844 | 4.691% | 3000325 | 4.26% | 4126 | 772 | 18.71% | 253 | 6.132% | 108 | 2.618% | 203 | 4.92% | 4437 | 7.538% | 5462 | 5375 | 4350 | 5.429% | 93.75%
| District Let | 114435245 | 113793532 | 158718598 | 158092992 | 548500 | 157063429 | 38.02% | 91.67% | 44495569 | 39.1% | 44266932 | 38.68% | 3259 | 559 | 17.15% | 195 | 5.983% | 0 | 0% | 743 | 22.8% | 4002 | 22.8% | 4756 | 4653 | 3899 | 19.64% | 91.67%
| All Contracts | 184870873 | 183344660 | 232154550 | 230100706 | 743400 | 227942663 | 24.32% | 96.43% | 47758413 | 26.05% | 47267257 | 25.57% | 7385 | 1331 | 18.02% | 448 | 6.066% | 108 | 1.462% | 946 | 12.81% | 8439 | 14.27% | 10218 | 10028 | 8249 | 11.7% | 92.86%
5 | Central Let | 126471560 | 124623660 | 128274016 | 127463203 | 316000 | 123336902 | -1.033% | 97.06% | 2076251 | 1.666% | 1778453 | 1.406% | 7691 | 1265 | 16.45% | 632 | 8.217% | 22 | 0.286% | 331 | 4.304% | 8044 | 4.59% | 9941 | 9958 | 8061 | 4.811% | 88.24%
| District Let | 225645085 | 224830085 | 236072794 | 236081533 | 500000 | 227803441 | 1.322% | 100% | 10487238 | 4.665% | 10427710 | 4.621% | 3669 | 717 | 19.54% | 377 | 10.28% | 33 | 0.8994% | 746 | 20.33% | 4448 | 21.23% | 5629 | 5408 | 4314 | 17.58% | 75%
| All Contracts | 352116645 | 349453745 | 364346810 | 363544736 | 816000 | 351140343 | 0.4826% | 98% | 12563489 | 3.595% | 12206163 | 3.467% | 11360 | 1982 | 17.45% | 1009 | 8.882% | 55 | 0.4842% | 1077 | 9.481% | 12492 | 9.965% | 15570 | 15366 | 12375 | 8.935% | 84%
6 | Central Let | 50640903 | 49428988 | 51302536 | 49839845 | 1256000 | 49100798 | -0.664% | 100% | 866326 | 1.753% | 563445 | 1.113% | 3070 | 329 | 10.72% | 148 | 4.821% | 70 | 2.28% | 34 | 1.107% | 3174 | 3.388% | 3651 | 3336 | 2859 | -6.873% | 100%
| District Let | 12529258 | 12061908 | 12903461 | 12413284 | 0 | 8485222 | -29.65% | 92.31% | 451070 | 3.74% | 374203 | 2.987% | 3165 | 557 | 17.6% | 176 | 5.561% | 0 | 0% | 30 | 0.9479% | 3195 | 0.9479% | 3928 | 3712 | 2979 | -5.877% | 100%
| All Contracts | 63170161 | 61490896 | 64205997 | 62253129 | 1256000 | 57586020 | -6.35% | 96% | 1317396 | 2.142% | 937648 | 1.484% | 6235 | 886 | 14.21% | 324 | 5.196% | 70 | 1.123% | 64 | 1.026% | 6369 | 2.149% | 7579 | 7048 | 5838 | -6.367% | 100%
7 | Central Let | 123324366 | 122786513 | 128220239 | 131747723 | 0 | 129157816 | 5.189% | 87.5% | 4788886 | 3.9% | 4895871 | 3.97% | 3150 | 687 | 21.81% | 217 | 6.889% | 12 | 0.381% | 197 | 6.254% | 3359 | 6.635% | 4263 | 4547 | 3643 | 15.65% | 87.5%
| District Let | 45466076 | 44821576 | 46371197 | 46892080 | 0 | 46757236 | 4.319% | 92.86% | 1117772 | 2.494% | 905121 | 1.991% | 3189 | 985 | 30.89% | 303 | 9.501% | 12 | 0.3763% | 180 | 5.644% | 3381 | 6.021% | 4669 | 4638 | 3350 | 5.049% | 100%
| All Contracts | 168790442 | 167608089 | 174591436 | 178639803 | 0 | 175915052 | 4.956% | 90.91% | 5906658 | 3.524% | 5800992 | 3.437% | 6339 | 1672 | 26.38% | 520 | 8.203% | 24 | 0.3786% | 377 | 5.947% | 6740 | 6.326% | 8932 | 9185 | 6993 | 10.32% | 95.45%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 83977792 | 83121413 | 86893404 | 86391205 | 300000 | 85594776.61 | 2.976% | 80% | 3247085 | 3.906% | 2915612 | 3.472% | 3820 | 332 | 8.691% | 286 | 7.487% | 109 | 2.853% | 105 | 2.749% | 4034 | 5.602% | 4652 | 4569 | 3951 | 3.429% | 0.002302%
| All Contracts | 83977792 | 83121413 | 86893404 | 86391205 | 300000 | 85594776.61 | 2.976% | 80% | 3247085 | 3.906% | 2915612 | 3.472% | 3820 | 332 | 8.691% | 286 | 7.487% | 109 | 2.853% | 105 | 2.749% | 4034 | 5.602% | 4652 | 4569 | 3951 | 3.429% | 100%
Totals This Qtr | Central Let | 922272924 | 912201289 | 950316202 | 949875400 | 5416900 | 923867600 | 1.279% | 94.83% | 30812018 | 3.378% | 27856787 | 3.02% | 42758 | 8500 | 19.88% | 3456 | 8.083% | 1275 | 2.982% | 2225 | 5.204% | 46258 | 8.186% | 58215 | 59077 | 47121 | 10.2% | 87.93%
| District Let | 681923471 | 675586171 | 745680560 | 741535853 | 2689500 | 724953919.61 | 7.307% | 92.62% | 65007580 | 9.622% | 63710371 | 9.343% | 27803 | 4959 | 17.84% | 2334 | 8.395% | 695 | 2.5% | 2601 | 9.355% | 31099 | 11.85% | 38519 | 37890 | 30597 | 10.05% | 85.25%
| All Contracts | 1604196395 | 1587787460 | 1695996762 | 1691411253 | 8106400 | 1648821519.61 | 3.844% | 93.92% | 95819598 | 6.035% | 91567158 | 5.708% | 70561 | 13459 | 19.07% | 5790 | 8.206% | 1970 | 2.792% | 4826 | 6.839% | 77357 | 9.631% | 96734 | 96967 | 77718 | 10.14% | 86.82%
Totals Previous Quarter | Central Let | 614177658 | 606871231 | 632923799 | 632195826 | 1676900 | 616170455 | 1.532% | 95.93% | 20890611 | 3.442% | 18656145 | 3.038% | 29986 | 5850 | 19.51% | 2256 | 7.524% | 861 | 2.871% | 1520 | 5.069% | 32367 | 7.94% | 40451 | 40186 | 32080 | 6.983% | 89.43%
| District Let | 485918976 | 481027608 | 538157371 | 534856019 | 2689500 | 522212315 | 8.562% | 94.68% | 53464678 | 11.11% | 52191676 | 10.74% | 21670 | 3629 | 16.75% | 1581 | 7.296% | 492 | 2.27% | 1621 | 7.48% | 23783 | 9.751% | 29007 | 28344 | 23134 | 6.756% | 87.23%
| All Contracts | 1100096634 | 1087898839 | 1171081170 | 1167051845 | 4366400 | 1138382770 | 4.64% | 95.39% | 74355289 | 6.835% | 70847821 | 6.44% | 51656 | 9479 | 18.35% | 3837 | 7.428% | 1353 | 2.619% | 3141 | 6.081% | 56150 | 8.7% | 69458 | 68530 | 55214 | 6.888% | 88.48%
Totals Fiscal Year 2008/2009 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1330 | 19571825201 | 2012-06-20 | QTR4 | 11/12 | 6 | 8 | 750 | 1067 | 1067 | 118.8% | 1 | 0 | 0 | 0 | 176 | 141 | 22148030 | 150000 | 21998030 | 24020348 | 23810851 | 0 | 0 | 0 | 23810851 | 23564595 | 107.1% | 1 | -246257 | 1872318 | 139 | 37 | 0 | 80 | 1993803 | 247057 | 0 | -30 | 163045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -278762 | 0 | 0 | 141 | 1925001 | 247057 | F272587735 | CONALVIAS USA LLC | N/A | N/A | N/A | N/A | 2018-03-09 | QTR3 | 17/18 |  | 2015-12-09 | QTR2 | 15/16 | 113 | 21275691.37
| 01 | T1417 | 41612015201 | 2011-12-07 | QTR2 | 11/12 | 4 | 6 | 450 | 591 | 790 | 157.6% | 0 | -199 | 199 | 0 | 111 | 30 | 12691971 | 121466 | 12570505 | 13256420 | 13055581 | -656700 | 0 | -656700 | 12398881 | 12393005 | 98.59% | 1 | -5876 | 564450 | 64 | 17 | 10 | 0 | 108668 | 21405 | 20 | 10 | 504186 | 27781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 38852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 653741 | 49186 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2017-11-21 | QTR2 | 17/18 |  | 2014-06-13 | QTR4 | 13/14 | 115 | 11408241.94
| 01 | T1598 | 41304425201 | 2015-07-29 | QTR1 | 15/16 | 3 | 17 | 668 | 722 | 698 | 95.81% | 1 | 24 | 0 | 0 | 58 | -4 | 72913523 | 150000 | 72763523 | 73524079 | 72400941 | -52000 | 3500000 | 3448000 | 75848941 | 70273740 | 96.58% | 1 | -5529824 | 610556 | 38 | 20 | 0 | -16 | 375892 | 55875 | 0 | 0 | 747621 | 285223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -453111 | 0 | 0 | -4 | 661423 | 341098 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2018-05-30 | QTR4 | 17/18 |  | 2017-11-30 | QTR2 | 17/18 | 106 | 87450436.24 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 01 | T1625 | 42988315201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 150 | 198 | 198 | 114.7% | 1 | 0 | 0 | 0 | 40 | 8 | 1852000 | 50000 | 1802000 | 1866275 | 1867608 | 0 | 0 | 0 | 1867608 | 1867700 | 103.6% | 1 | 92 | 14275 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 8 | 26881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8 | 26881 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-04-11 | QTR4 | 16/17 | 108 | 2064220.28
| 01 | T1628 | 43011915201 | 2016-01-27 | QTR3 | 15/16 | 2 | 3 | 250 | 289 | 289 | 101.2% | 1 | 0 | 0 | 0 | 36 | 3 | 5092548 | 54005 | 5038543 | 5147816 | 5084411 | 0 | 0 | 0 | 5084411 | 5074685 | 100.7% | 1 | -9725 | 55268 | 16 | 20 | 0 | 0 | 9739 | 0 | 0 | 3 | 56544 | 5272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 66284 | 5272 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-27 | QTR1 | 17/18 |  | 2017-04-05 | QTR4 | 16/17 | 113 | 5336136.69
| 01 | T1631 | 43327215201 | 2016-04-27 | QTR4 | 15/16 | 1 | 3 | 100 | 208 | 208 | 151% | 0 | 0 | 0 | 0 | 108 | 0 | 1451189 | 0 | 1451189 | 1460304 | 1516711 | 0 | 0 | 0 | 1516711 | 1516711 | 104.5% | 1 | 0 | 9115 | 38 | 19 | 0 | 0 | 24623 | 0 | 34 | 0 | -15508 | 1870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 9115 | 1870 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-10-05 | QTR2 | 17/18 |  | 2017-07-14 | QTR1 | 17/18 | 108 | 1389366.28
| 01 | T1647 | 43131615201 | 2016-02-24 | QTR3 | 15/16 | 5 | 15 | 475 | 631 | 631 | 104.8% | 1 | 0 | 0 | 0 | 133 | 23 | 14344879 | 150000 | 14194879 | 14807906 | 14762958 | 0 | 0 | 0 | 14762958 | 14811081 | 104.3% | 1 | 105279 | 405870 | 85 | 48 | 0 | 20 | 179164 | 0 | 0 | 0 | 33291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125250 | 0 | 0 | 3 | 56309 | 56309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22560 | 22560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 416573 | 78868 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-05-14 | QTR4 | 17/18 |  | 2018-01-22 | QTR3 | 17/18 | 113 | 14324215.64
| 01 | T1648 | 43448915201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 85 | 113 | 113 | 118.8% | 1 | 0 | 0 | 0 | 12 | 16 | 910955 | 0 | 910955 | 949740 | 949740 | 0 | 0 | 0 | 949740 | 949740 | 104.3% | 1 | 0 | 38784 | 11 | 1 | 0 | 6 | 15433 | 0 | 0 | 10 | 23352 | 4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 38784 | 4641 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2017-10-26 | QTR2 | 17/18 |  | 2017-04-25 | QTR4 | 16/17 | 108 | 910039.59 | B0 | ACC - LUMP SUM
| 01 | T1652 | 43356215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 250 | 279 | 278 | 99.6% | 1 | 1 | 0 | 0 | 29 | 0 | 1849592 | 50000 | 1799592 | 1849592 | 1707344 | 0 | 0 | 0 | 1707344 | 1709115 | 94.97% | 1 | 1771 | 0 | 11 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 5795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5795 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-11-08 | QTR2 | 17/18 |  | 2017-07-07 | QTR1 | 17/18 | 115 | 1373813.46
| 01 | T1655 | 43507515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 1 | 250 | 300 | 279 | 91.6% | 1 | 21 | 0 | 0 | 50 | 0 | 4645998 | 59238 | 4586760 | 4644998 | 4654697 | 0 | 0 | 0 | 4654697 | 4670541 | 101.8% | 1 | 15844 | -1000 | 31 | 19 | 0 | 0 | 9206 | 0 | 0 | 0 | 17333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28684 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-10-27 | QTR2 | 17/18 |  | 2017-07-28 | QTR1 | 17/18 | 108 | 4668696.06 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1658 | 43902815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 175 | 214 | 210 | 103.4% | 1 | 4 | 0 | 0 | 29 | 10 | 2041864 | 54329 | 1987535 | 2041864 | 1925079 | 0 | 0 | 0 | 1925079 | 1925198 | 96.86% | 1 | 118 | 0 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 10 | 16588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 16588 | 0 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-06-12 | QTR4 | 16/17 | 113 | 4696299.51
| 01 | T1661 | 43450815201 | 2017-02-22 | QTR3 | 16/17 | 3 | 1 | 110 | 157 | 152 | 95.45% | 1 | 5 | 0 | 0 | 47 | 0 | 1347647 | 0 | 1347647 | 1408422 | 1434774 | 0 | 0 | 0 | 1434774 | 1313225 | 97.45% | 1 | -60775 | 60775 | 41 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-20 | QTR3 | 17/18 |  | 2017-11-21 | QTR2 | 17/18 | 108 | 1203312.27
| 01 | T1662 | 43132515201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 75 | 90 | 97 | 109.3% | 1 | -7 | 7 | 0 | 15 | 0 | 150000 | 7492 | 142508 | 150000 | 141366 | -6706 | 0 | -6706 | 134660 | 134660 | 94.49% | 1 | 0 | 0 | 4 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452357137 | YD WEST COAST HOME INC | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-03-03 | QTR3 | 16/17 | 118 | 195237.61 | B0 | ACC - LUMP SUM
| 01 | T1663 | 43502515201 | 2016-08-31 | QTR1 | 16/17 | 3 | 3 | 200 | 333 | 333 | 136% | 0 | 0 | 0 | 0 | 61 | 72 | 2395063 | 50000 | 2345063 | 2800850 | 2741389 | 0 | 0 | 0 | 2741389 | 2747244 | 117.2% | 0 | 10825 | 405787 | 46 | 15 | 0 | 0 | 1766 | 0 | 0 | 72 | 406947 | 400817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 408713 | 400817 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-05-15 | QTR4 | 17/18 |  | 2017-12-01 | QTR2 | 17/18 | 113 | 2399072.74 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1668 | 43450715201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 100 | 104 | 99 | 95% | 1 | 5 | 0 | 0 | 4 | 0 | 860000 | 50000 | 810000 | 860000 | 810000 | 0 | 0 | 0 | 810000 | 810000 | 100% | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-07-17 | QTR1 | 17/18 |  | 2017-04-25 | QTR4 | 16/17 | 108 | 1005379.75 | B0 | ACC - LUMP SUM
| 01 | T1677 | 43450615201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 130 | 169 | 166 | 97.69% | 1 | 3 | 0 | 0 | 39 | 0 | 681681 | 39099 | 642582 | 697653 | 645164 | 0 | 0 | 0 | 645164 | 630209 | 98.07% | 1 | 0 | 15972 | 19 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-03-01 | QTR3 | 17/18 |  | 2018-01-05 | QTR3 | 17/18 | 108 | 692725.22 | B0 | ACC - LUMP SUM
| 01 | T1679 | 43660115201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 175 | 209 | 209 | 104.6% | 1 | 0 | 0 | 0 | 26 | 8 | 2015831 | 50000 | 1965831 | 2015831 | 1984899 | 0 | 0 | 0 | 1984899 | 2016886 | 102.6% | 1 | 31987 | 0 | 9 | 17 | 0 | 1 | 3158 | 0 | 0 | 7 | 15910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 19068 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-06-12 | QTR4 | 17/18 |  | 2018-05-05 | QTR4 | 17/18 | 108 | 1987460.72 | B0 | ACC - LUMP SUM
| 01 | T1680 | 43092215201 | 2017-03-29 | QTR3 | 16/17 | 1 | 0 | 70 | 76 | 50 | 62.86% | 1 | 26 | 0 | 0 | 6 | 0 | 206428 | 0 | 206428 | 206428 | 206428 | 0 | 0 | 0 | 206428 | 206428 | 100% | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-02-15 | QTR3 | 17/18 |  | 2017-12-18 | QTR2 | 17/18 | 113 | 236686.57 | B0 | ACC - LUMP SUM
| 01 | T1681 | 43318115201 | 2017-03-29 | QTR3 | 16/17 | 2 | 0 | 160 | 212 | 131 | 48.75% | 1 | 81 | 0 | 0 | 53 | -1 | 427415 | 0 | 427415 | 427415 | 422004 | 0 | 0 | 0 | 422004 | 422004 | 98.73% | 1 | 0 | 0 | 47 | 6 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-11-06 | QTR2 | 17/18 |  | 2017-10-13 | QTR2 | 17/18 | 113 | 348089.37 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 01 | T1682 | 43496215201 | 2017-05-24 | QTR4 | 16/17 | 1 | 1 | 150 | 190 | 190 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 1775437 | 50000 | 1725437 | 1781028 | 1655773 | 0 | 0 | 0 | 1655773 | 1656969 | 96.03% | 1 | 6786 | 5591 | 21 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-04-20 | QTR4 | 17/18 |  | 2018-02-07 | QTR3 | 17/18 | 118 | 1722624.26
| 01 | T1689 | 43470715201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 100 | 108 | 92 | 84% | 1 | 16 | 0 | 0 | 8 | 0 | 553926 | 25801 | 528125 | 553926 | 528125 | 0 | 0 | 0 | 528125 | 528125 | 100% | 1 | 0 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2018-05-08 | QTR4 | 17/18 |  | 2018-04-09 | QTR4 | 17/18 | 113 | 582898.39 | B0 | ACC - LUMP SUM
| 01 | T1691 | 43654615201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 65 | 76 | 71 | 92.31% | 1 | 5 | 0 | 0 | 11 | 0 | 153287 | 6065 | 147222 | 153287 | 147222 | 0 | 0 | 0 | 147222 | 147222 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-04-12 | QTR4 | 17/18 |  | 2018-02-05 | QTR3 | 17/18 | 115 | 115131.87 | B0 | ACC - LUMP SUM
| 01 | T1695 | 43320115201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 85 | 87 | 78 | 89.41% | 1 | 9 | 0 | 0 | 2 | 0 | 324149 | 16622 | 307527 | 324149 | 315985 | 0 | 0 | 0 | 315985 | 315985 | 102.8% | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 8458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8458 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-05-09 | QTR4 | 17/18 |  | 2018-03-26 | QTR3 | 17/18 | 108 | 310285.33 | B0 | ACC - LUMP SUM
| 01 | T1696 | 43668115201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 90 | 86 | 94.67% | 1 | 4 | 0 | 0 | 15 | 0 | 117983 | 5276 | 112707 | 117983 | 110528 | 0 | 0 | 0 | 110528 | 110528 | 98.07% | 1 | 0 | 0 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-06-04 | QTR4 | 17/18 |  | 2018-03-29 | QTR3 | 17/18 | 108 | 105146.26
| 01 | T1998 | 42271025201 | 2014-07-30 | QTR1 | 14/15 | 2 | 27 | 850 | 1090 | 1090 | 104.9% | 1 | 0 | 0 | 0 | 198 | 42 | 31131016 | 150000 | 30981016 | 31906922 | 31516260 | 0 | 0 | 0 | 31516260 | 29926809 | 96.6% | 1 | -1576116 | 775906 | 145 | 53 | 0 | 35 | 459658 | 0 | 0 | 7 | 328072 | 64792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26606 | 0 | 0 | 0 | 995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 815331 | 64792 | F650507332 | GUYMANN CONSTRUCTION OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2018-06-19 | QTR4 | 17/18 |  | 2018-01-22 | QTR3 | 17/18 | 113 | 37523290.44 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 01 | T1A01 | 43134015201 | 2016-07-27 | QTR1 | 16/17 | 2 | 1 | 140 | 181 | 181 | 110.7% | 1 | 0 | 0 | 0 | 26 | 15 | 1006260 | 46751 | 959509 | 1032806 | 969407 | 0 | 0 | 0 | 969407 | 980874 | 102.2% | 1 | 11467 | 26546 | 12 | 14 | 0 | 15 | 35922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 36986 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-08-04 | QTR1 | 17/18 |  | 2017-06-03 | QTR4 | 16/17 | 118 | 1134236.85
| 01 | T1A06 | 42910315201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 170 | 206 | 206 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 2539891 | 50000 | 2489891 | 2539891 | 2578009 | 0 | 0 | 0 | 2578009 | 2497434 | 100.3% | 1 | -80575 | 0 | 31 | 5 | 0 | 0 | 746 | 0 | 0 | 0 | 15007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15754 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-12-28 | QTR2 | 17/18 |  | 2015-09-14 | QTR1 | 15/16 | 108 | 2442140.29
| 01 | T9013 | 43700115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 3 | 270 | 339 | 323 | 112.6% | 1 | 16 | 0 | 0 | 45 | 24 | 1965358 | 50000 | 1915358 | 2093858 | 2090482 | 0 | 0 | 0 | 2090482 | 2090564 | 109.1% | 1 | 83 | 128500 | 0 | 19 | 0 | 0 | 387 | 0 | 26 | 24 | 156842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 24 | 178500 | 0 | F030586197 | R.M. WILLIAMS CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-12-12 | QTR2 | 17/18 |  | 2017-08-21 | QTR1 | 17/18 | 113 | 2398810.5
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 28 | 52 | 95 | 6528 | 8329 | 8315 | 89.29% | 25 | 14 | 206 | 0 | 1414 | 387 | 187593921 | 1436144 | 186157777 | 192639791 | 190033736 | -715406 | 3500000 | 2784594 | 192818330 | 185291277 | 96.43% | 27 | -7324896 | 4988713 | 860 | 433 | 10 | 140 | 3226623 | 324337 | 80 | 121 | 2502906 | 790396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 20 | 231851 | 0 | 0 | 3 | 79592 | 56309 | 0 | 0 | 0 | 0 | 0 | 12 | 2035 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 22560 | 22560 | 0 | 0 | 0 | 0 | 0 | 91 | -731873 | 0 | 121 | 387 | 5333696 | 1193601
| 01 | E1L76 | 43193815201 | 2013-03-21 | QTR3 | 12/13 | 1 | 0 | 100 | 185 | 493 | 408% | 0 | -308 | 308 | 0 | 85 | 0 | 775601 | 38617 | 736984 | 775601 | 267269 | -89053 | 0 | -89053 | 178216 | 256487 | 34.8% | 1 | 78271 | 0 | 67 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593374298 | EMPOWER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-03 | QTR4 | 17/18 |  | 2014-11-14 | QTR2 | 14/15 | 118 | 826590.47 | B0 | ACC - LUMP SUM
| 01 | E1N91 | 43526915201 | 2015-04-16 | QTR4 | 14/15 | 4 | 5 | 175 | 464 | 459 | 249.1% | 0 | 5 | 0 | 0 | 44 | 245 | 1423170 | 29305 | 1393865 | 2060086 | 1941361 | 0 | 0 | 0 | 1941361 | 1938507 | 139.1% | 0 | -2854 | 636916 | 7 | 16 | 0 | 61 | 572771 | 0 | 21 | 171 | 64145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 240 | 636916 | 0 | F381807765 | DOUGLAS N. HIGGINS INC. | N/A | N/A | N/A | N/A | 2018-06-21 | QTR4 | 17/18 |  | 2017-01-05 | QTR3 | 16/17 | 118 | 875885.34
| 01 | E1O46 | 43654515201 | 2015-11-19 | QTR2 | 15/16 | 1 | 2 | 115 | 164 | 164 | 122.6% | 0 | 0 | 0 | 0 | 37 | 12 | 704333 | 30651 | 673682 | 763036 | 748922 | 0 | 0 | 0 | 748922 | 748922 | 111.2% | 0 | 0 | 58703 | 15 | 8 | 0 | 12 | 30084 | 0 | 0 | 0 | 28619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 12 | 58703 | 0 | F730764097 | MANHATTAN ROAD & BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2017-11-28 | QTR2 | 17/18 |  | 2016-09-14 | QTR1 | 16/17 | 115 | 529268.14
| 01 | E1O47 | 43170315201 | 2016-01-28 | QTR3 | 15/16 | 2 | 0 | 160 | 276 | 276 | 118.8% | 1 | 0 | 0 | 0 | 86 | 30 | 2080080 | 50000 | 2030080 | 2080080 | 2081575 | 0 | 0 | 0 | 2081575 | 2082167 | 102.6% | 1 | 592 | 0 | 65 | 21 | 0 | 30 | 6976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 6976 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2017-10-02 | QTR2 | 17/18 |  | 2017-02-23 | QTR3 | 16/17 | 113 | 2823450.85
| 01 | E1O50 | 43121215201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 160 | 168 | 145 | 85.62% | 1 | 23 | 0 | 0 | 8 | 0 | 2473492 | 50000 | 2423492 | 2473492 | 2430162 | 0 | 0 | 0 | 2430162 | 2431258 | 100.3% | 1 | 1097 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-06-02 | QTR4 | 16/17 | 115 | 2383341.22 | B0 | ACC - LUMP SUM
| 01 | E1O53 | 43486515201 | 2015-12-17 | QTR2 | 15/16 | 1 | 3 | 245 | 278 | 278 | 105.7% | 1 | 0 | 0 | 0 | 33 | 0 | 1972999 | 50000 | 1922999 | 2017226 | 2027670 | 0 | 0 | 0 | 2027670 | 2027844 | 105.5% | 1 | 174 | 44227 | 5 | 14 | 14 | 0 | 37826 | 0 | 0 | 0 | 38283 | 12197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 88109 | 12197 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-10 | QTR1 | 17/18 |  | 2017-05-26 | QTR4 | 16/17 | 115 | 1579998.38
| 01 | E1O56 | 42799515201 | 2015-05-21 | QTR4 | 14/15 | 2 | 9 | 350 | 432 | 422 | 101.7% | 1 | 10 | 0 | 0 | 66 | 16 | 6985880 | 68645 | 6917235 | 7218308 | 7107622 | 0 | 0 | 0 | 7107622 | 6945376 | 100.4% | 1 | -162246 | 232428 | 48 | 18 | 0 | 5 | 167389 | 18637 | 0 | 11 | 38597 | 16457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 235986 | 65094 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2017-11-21 | QTR2 | 17/18 |  | 2016-11-02 | QTR2 | 16/17 | 115 | 7866883.02 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1O77 | 43120815201 | 2016-05-19 | QTR4 | 15/16 | 2 | 6 | 355 | 393 | 307 | 79.15% | 1 | 86 | 0 | 0 | 26 | 12 | 5170633 | 87166 | 5083467 | 5203293 | 5192938 | 0 | 366000 | 366000 | 5558938 | 5199260 | 102.3% | 1 | -359678 | 32660 | 12 | 14 | 0 | 0 | 9159 | 9159 | 0 | 0 | 30936 | 5390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10463 | 0 | 0 | 0 | 4218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 56787 | 16559 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2017-10-26 | QTR2 | 17/18 |  | 2017-06-13 | QTR4 | 16/17 | 108 | 7193789.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1O89 | 42731525201 | 2016-04-01 | QTR4 | 15/16 | 1 | 1 | 450 | 539 | 538 | 99.78% | 1 | 1 | 0 | 0 | 89 | 0 | 2744297 | 50000 | 2694297 | 2808760 | 2758760 | 0 | 0 | 0 | 2758760 | 2694297 | 100% | 1 | 0 | 64463 | 59 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2018-04-11 | QTR4 | 17/18 |  | 2017-11-29 | QTR2 | 17/18 | 108 | 2744297 | B8 | ACC - DESIGN/BUILD - MAJOR
| 01 | E1P55 | 43476215201 | 2016-04-21 | QTR4 | 15/16 | 2 | 10 | 600 | 664 | 516 | 76.33% | 1 | 148 | 0 | 0 | 58 | 6 | 16187341 | 150000 | 16037341 | 16450162 | 16170719 | 0 | 950000 | 950000 | 17120719 | 16200920 | 101% | 1 | -872739 | 262821 | 35 | 23 | 0 | 0 | 25554 | 0 | 0 | 0 | 171431 | 4377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186439 | 4377 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2018-03-14 | QTR3 | 17/18 |  | 2017-12-15 | QTR2 | 17/18 | 108 | 17171779.98 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1P64 | 43172315201 | 2016-08-18 | QTR1 | 16/17 | 1 | 0 | 80 | 82 | 80 | 97.5% | 1 | 2 | 0 | 0 | 2 | 0 | 829730 | 41730 | 788000 | 829730 | 788000 | 0 | 0 | 0 | 788000 | 788000 | 100% | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 |  | 2017-05-31 | QTR4 | 16/17 | 118 | 915006.57 | B0 | ACC - LUMP SUM
| 01 | E1P83 | 43496015201 | 2017-01-19 | QTR3 | 16/17 | 1 | 0 | 100 | 120 | 120 | 100% | 1 | 0 | 0 | 0 | 20 | 0 | 884000 | 46833 | 837167 | 884000 | 845823 | 0 | 0 | 0 | 845823 | 845823 | 101% | 1 | 0 | 0 | 17 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1234 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-04-06 | QTR4 | 17/18 |  | 2017-08-18 | QTR1 | 17/18 | 118 | 915851.72 | B0 | ACC - LUMP SUM
| 01 | E1P84 | 43494015201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 180 | 192 | 183 | 95% | 1 | 9 | 0 | 0 | 12 | 0 | 2940436 | 50000 | 2890436 | 2940436 | 2909678 | 0 | 0 | 0 | 2909678 | 2924839 | 101.2% | 1 | 15161 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-03-01 | QTR3 | 17/18 |  | 2017-08-24 | QTR1 | 17/18 | 118 | 3425094.3
| 01 | E1P85 | 43507115201 | 2016-11-17 | QTR2 | 16/17 | 1 | 1 | 150 | 196 | 196 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 1782010 | 50000 | 1732010 | 1785646 | 1738365 | 0 | 0 | 0 | 1738365 | 1738373 | 100.4% | 1 | 3643 | 3636 | 35 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 3671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3671 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-01-26 | QTR3 | 17/18 |  | 2017-11-22 | QTR2 | 17/18 | 108 | 1557493.63 | B0 | ACC - LUMP SUM
| 01 | E1P86 | 43496115201 | 2016-12-15 | QTR2 | 16/17 | 1 | 1 | 130 | 176 | 176 | 106.2% | 1 | 0 | 0 | 0 | 39 | 7 | 1418298 | 50000 | 1368298 | 1437032 | 1407750 | 0 | 0 | 0 | 1407750 | 1407687 | 102.9% | 1 | -63 | 18735 | 29 | 9 | 0 | 7 | 39864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 58599 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-02-23 | QTR3 | 17/18 |  | 2017-09-25 | QTR1 | 17/18 | 115 | 1330643 | B0 | ACC - LUMP SUM
| 01 | E1P88 | 43486015201 | 2017-01-31 | QTR3 | 16/17 | 1 | 1 | 105 | 135 | 135 | 100% | 1 | 0 | 0 | 0 | 30 | 0 | 2696196 | 50000 | 2646196 | 2716814 | 2562828 | 0 | 0 | 0 | 2562828 | 2545217 | 96.18% | 1 | 3007 | 20618 | 26 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 16342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16342 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2018-04-11 | QTR4 | 17/18 |  | 2017-11-16 | QTR2 | 17/18 | 115 | 3341250.31 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1P89 | 43692015201 | 2016-12-15 | QTR2 | 16/17 | 1 | 2 | 250 | 362 | 357 | 110% | 1 | 5 | 0 | 0 | 82 | 30 | 5605151 | 64174 | 5540977 | 6085870 | 5887019 | 0 | 0 | 0 | 5887019 | 5929757 | 107% | 1 | 103551 | 480719 | 59 | 23 | 0 | 0 | 0 | 0 | 0 | 30 | 425993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 425993 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-22 | QTR4 | 17/18 |  | 2018-03-14 | QTR3 | 17/18 | 118 | 6393089.14
| 01 | E1P93 | 43663815201 | 2017-01-19 | QTR3 | 16/17 | 1 | 3 | 150 | 192 | 192 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 2271296 | 50000 | 2221296 | 2325270 | 2285617 | 0 | 0 | 0 | 2285617 | 2291460 | 103.2% | 1 | 19656 | 53974 | 33 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40160 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-03-15 | QTR3 | 17/18 |  | 2017-11-08 | QTR2 | 17/18 | 113 | 2620650.05 | B0 | ACC - LUMP SUM
| 01 | E1Q60 | 43614515201 | 2017-06-15 | QTR4 | 16/17 | 1 | 0 | 225 | 251 | 219 | 85.78% | 1 | 32 | 0 | 0 | 26 | 0 | 1652714 | 50000 | 1602714 | 1652714 | 1595287 | 0 | 0 | 0 | 1595287 | 1594960 | 99.52% | 1 | -327 | 0 | 11 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464740152 | CATHCART CONSTRUCTION COMPANY - FLORIDA | N/A | N/A | N/A | N/A | 2018-05-21 | QTR4 | 17/18 |  | 2018-04-11 | QTR4 | 17/18 | 108 | 874718.37
| 01 | E1Q63 | 44095315201 | 2017-04-20 | QTR4 | 16/17 | 1 | 0 | 30 | 49 | 48 | 96.67% | 1 | 1 | 0 | 0 | 19 | 0 | 110918 | 9596 | 101322 | 110918 | 101322 | 0 | 0 | 0 | 101322 | 101322 | 100% | 1 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2017-11-09 | QTR2 | 17/18 |  | 2017-08-24 | QTR1 | 17/18 | 113 | 179085.79 | B0 | ACC - LUMP SUM
| 01 | E1Q84 | 43861715201 | 2017-06-15 | QTR4 | 16/17 | 1 | 0 | 70 | 77 | 56 | 70% | 1 | 21 | 0 | 0 | 7 | 0 | 325029 | 11099 | 313930 | 325029 | 252626 | 0 | 0 | 0 | 252626 | 256076 | 81.57% | 1 | 3450 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2018-05-01 | QTR4 | 17/18 |  | 2017-12-17 | QTR2 | 17/18 | 113 | 138637.23 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | E1Q92 | 43495715201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 40 | 41 | 25 | 60% | 1 | 16 | 0 | 0 | 1 | 0 | 218056 | 17970 | 200086 | 218056 | 191926 | 0 | 25000 | 25000 | 216926 | 191926 | 95.92% | 1 | -25000 | 0 | 1 | 0 | 0 | 0 | 3344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3344 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-10-13 | QTR2 | 17/18 |  | 2017-08-17 | QTR1 | 17/18 | 118 | 167846.6 | B1 | ACC - NO EXCUSE BONUS
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 22 | 29 | 44 | 4220 | 5436 | 5385 | 86.36% | 19 | 51 | 308 | 0 | 858 | 358 | 61251660 | 1095786 | 60155874 | 63161559 | 61293239 | -89053 | 1341000 | 1251947 | 62545186 | 61140478 | 90.91% | 20 | -1194305 | 1909900 | 561 | 247 | 14 | 115 | 892967 | 27796 | 21 | 212 | 819251 | 38421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 7062 | 0 | 14 | 0 | 63113 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4856 | 0 | 0 | 0 | 32010 | 32010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 339 | 1819259 | 98227
| District 01 Totals |  |  |  |  | 50 | 81 | 139 | 10748 | 13765 | 13700 | 88% | 44 | 65 | 514 | 0 | 2272 | 745 | 248845581 | 2531930 | 246313651 | 255801350 | 251326975 | -804459 | 4841000 | 4036541 | 255363516 | 246431755 | 94% | 47 | -8519201 | 6898613 | 1421 | 680 | 24 | 255 | 4119590 | 352133 | 101 | 333 | 3322157 | 828817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 24 | 238913 | 0 | 14 | 3 | 142705 | 56309 | 0 | 0 | 0 | 0 | 0 | 20 | 6891 | 0 | 0 | 0 | 32010 | 32010 | 17 | 0 | 22560 | 22560 | 0 | 0 | 0 | 0 | 0 | 91 | -731873 | 0 | 171 | 726 | 7152955 | 1291828
| 02 | T2426 | 20837325201 | 2012-06-20 | QTR4 | 11/12 | 1 | 2 | 550 | 646 | 1412 | 247.8% | 0 | -766 | 766 | 0 | 75 | 21 | 10147516 | 118589 | 10028927 | 10201629 | 10315106 | -1110928 | 0 | -1110928 | 9204178 | 8737450 | 87.12% | 1 | -466728 | 54113 | 27 | 22 | 0 | 3 | 105503 | 16666 | 0 | 18 | 63011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 21 | 168514 | 16666 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2018-05-23 | QTR4 | 17/18 |  | 2016-11-18 | QTR2 | 16/17 | 209 | 12049132.99
| 02 | T2482 | 20916875201 | 2013-06-19 | QTR4 | 12/13 | 1 | 5 | 900 | 1011 | 1011 | 103.3% | 1 | 0 | 0 | 0 | 81 | 30 | 20538005 | 150000 | 20388005 | 21074264 | 21550372 | 0 | 0 | 0 | 21550372 | 21142359 | 103.7% | 1 | -408013 | 536259 | 39 | 42 | 0 | 30 | 693596 | 0 | 0 | 0 | 379915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -399145 | 0 | 0 | 30 | 674366 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-05-14 | QTR4 | 17/18 |  | 2016-08-07 | QTR1 | 16/17 | 208 | 20493068.45
| 02 | T2484 | 21086545201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 365 | 496 | 496 | 108.5% | 1 | 0 | 0 | 0 | 100 | 31 | 2500683 | 50000 | 2450683 | 2484554 | 2410530 | 0 | 0 | 0 | 2410530 | 2388453 | 97.46% | 1 | -22077 | -16129 | 76 | 24 | 0 | 8 | 28138 | 0 | 0 | 1 | 3731 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -16129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 16497 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-01-04 | QTR3 | 17/18 |  | 2015-05-16 | QTR4 | 14/15 | 209 | 2639633.26
| 02 | T2515 | 21325915201 | 2014-05-07 | QTR4 | 13/14 | 1 | 7 | 550 | 768 | 768 | 115.8% | 1 | 0 | 0 | 0 | 146 | 72 | 10022616 | 100668 | 9921947 | 10748841 | 11713560 | 0 | 0 | 0 | 11713560 | 10970371 | 110.6% | 0 | -743189 | 726225 | 78 | 53 | 1 | 72 | 355716 | 232777 | 14 | 0 | 398545 | 2171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4334 | 0 | 0 | 0 | 10693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 72 | 769289 | 234949 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-05-14 | QTR4 | 17/18 |  | 2016-12-07 | QTR2 | 16/17 | 208 | 10434763.41
| 02 | T2531 | 21308255201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 180 | 235 | 331 | 157.2% | 0 | -96 | 96 | 0 | 48 | 7 | 2996901 | 50000 | 2946901 | 2996901 | 3018348 | -276096 | 0 | -276096 | 2742252 | 2600555 | 88.25% | 1 | -141696 | 0 | 43 | 5 | 0 | 0 | 0 | 0 | 0 | 7 | 13966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13966 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-09 | QTR4 | 17/18 |  | 2015-12-01 | QTR2 | 15/16 | 209 | 2497599.17
| 02 | T2548 | 20939965201 | 2014-08-27 | QTR1 | 14/15 | 2 | 2 | 770 | 923 | 919 | 99.48% | 1 | 4 | 0 | 0 | 153 | 0 | 14832876 | 150000 | 14682876 | 14931694 | 15170352 | 0 | 0 | 0 | 15170352 | 14252602 | 97.07% | 1 | -917750 | 98818 | 93 | 60 | 0 | 0 | 40183 | 0 | 0 | 0 | 37352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149669 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 |  | 2017-05-19 | QTR4 | 16/17 | 208 | 15494259.21
| 02 | T2558 | 42880215201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 365 | 530 | 530 | 101.1% | 1 | 0 | 0 | 0 | 161 | 4 | 11419267 | 135449 | 11283818 | 11419267 | 11519213 | 0 | 0 | 0 | 11519213 | 9884932 | 87.6% | 1 | -1634281 | 0 | 122 | 39 | 0 | 4 | 78371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 78371 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-12 | QTR3 | 17/18 |  | 2016-06-17 | QTR4 | 15/16 | 214 | 11862914.12
| 02 | T2571 | 42307115201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 420 | 755 | 755 | 101.4% | 1 | 0 | 0 | 0 | 329 | 6 | 23206023 | 150000 | 23056023 | 23352096 | 23326424 | 0 | 0 | 0 | 23326424 | 22086601 | 95.8% | 1 | -1239823 | 146073 | 267 | 62 | 0 | 5 | 56142 | 0 | 0 | 1 | 165467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2783 | 0 | 0 | 0 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 224790 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-05-15 | QTR4 | 17/18 |  | 2017-10-11 | QTR2 | 17/18 | 214 | 22349692.01
| 02 | T2578 | 43054215201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 300 | 447 | 446 | 99.67% | 1 | 1 | 0 | 0 | 147 | 0 | 6197496 | 54454 | 6143043 | 6197496 | 6219729 | 0 | 0 | 0 | 6219729 | 5902734 | 96.09% | 1 | -316995 | 0 | 99 | 48 | 0 | 0 | 4070 | 0 | 0 | 0 | 22507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26577 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-10-10 | QTR2 | 17/18 |  | 2017-03-24 | QTR3 | 16/17 | 214 | 5697731.43
| 02 | T2583 | 21311345201 | 2015-06-17 | QTR4 | 14/15 | 2 | 8 | 350 | 523 | 901 | 222.3% | 0 | -378 | 378 | 0 | 123 | 50 | 6310104 | 56792 | 6253313 | 6241152 | 6008764 | -1425060 | 0 | -1425060 | 4583704 | 4934012 | 78.9% | 1 | 365795 | -68953 | 91 | 32 | 0 | 45 | 131732 | 0 | 0 | 5 | -234003 | 4811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | -102271 | 4811 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-15 | QTR4 | 17/18 |  | 2018-02-19 | QTR3 | 17/18 | 208 | 5828458.9
| 02 | T2590 | 42880515201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 340 | 577 | 577 | 119.1% | 1 | 0 | 0 | 0 | 232 | 5 | 12627578 | 150000 | 12477578 | 12627578 | 13136952 | 0 | 0 | 0 | 13136952 | 12671855 | 101.6% | 1 | -465097 | 0 | 125 | 47 | 60 | 5 | 39332 | 0 | 0 | 0 | 24651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 5 | 63984 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-03-01 | QTR3 | 17/18 |  | 2017-10-03 | QTR2 | 17/18 | 214 | 13903210.66
| 02 | T2595 | 43273315201 | 2015-08-26 | QTR1 | 15/16 | 1 | 3 | 365 | 575 | 575 | 100% | 1 | 0 | 0 | 0 | 210 | 0 | 14598877 | 142235 | 14456642 | 14676873 | 13917260 | 0 | 0 | 0 | 13917260 | 13357978 | 92.4% | 1 | -559281 | 77996 | 183 | 27 | 0 | 0 | 49500 | 0 | 0 | 0 | 47996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97496 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-16 | QTR3 | 17/18 |  | 2017-07-31 | QTR1 | 17/18 | 209 | 14373836.6
| 02 | T2599 | 43726615201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 180 | 213 | 213 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 1048048 | 50000 | 998048 | 1048048 | 985628 | 0 | 0 | 0 | 985628 | 985628 | 98.76% | 1 | 0 | 0 | 13 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-07-14 | QTR1 | 17/18 |  | 2017-02-21 | QTR3 | 16/17 | 216 | 1120328.18
| 02 | T2601 | 21166315201 | 2015-10-28 | QTR2 | 15/16 | 1 | 1 | 400 | 443 | 440 | 100% | 1 | 3 | 0 | 0 | 40 | 3 | 3712278 | 0 | 3712278 | 3713235 | 3797768 | 0 | 0 | 0 | 3797768 | 3782265 | 101.9% | 1 | -15503 | 957 | 23 | 17 | 0 | 3 | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 957 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 |  | 2017-04-13 | QTR4 | 16/17 | 209 | 4020991.68
| 02 | T2607 | 43265615201 | 2015-10-28 | QTR2 | 15/16 | 2 | 8 | 280 | 493 | 493 | 106.1% | 1 | 0 | 0 | 0 | 196 | 17 | 3726163 | 50000 | 3676163 | 3942398 | 4032657 | 0 | 0 | 0 | 4032657 | 3977766 | 108.2% | 1 | -54891 | 216235 | 149 | 47 | 0 | 12 | 139025 | 0 | 0 | 5 | 82451 | 10617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 238797 | 10617 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-12-26 | QTR2 | 17/18 |  | 2017-05-31 | QTR4 | 16/17 | 216 | 4078236.5
| 02 | T2615 | 43316425201 | 2016-04-27 | QTR4 | 15/16 | 1 | 2 | 230 | 244 | 229 | 93.48% | 1 | 15 | 0 | 0 | 14 | 0 | 1867840 | 50000 | 1817840 | 1917840 | 1853345 | 0 | 150000 | 150000 | 2003345 | 1860008 | 102.3% | 1 | -143337 | 50000 | 3 | 11 | 0 | 0 | 35081 | 0 | 0 | 0 | 35033 | 0 | 0 | 0 | 2457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76376 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-10-24 | QTR2 | 17/18 |  | 2017-07-17 | QTR1 | 17/18 | 208 | 2133960.64
| 02 | T2619 | 43265715201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 150 | 164 | 160 | 97.33% | 1 | 4 | 0 | 0 | 14 | 0 | 985253 | 39196 | 946057 | 985253 | 900611 | 0 | 0 | 0 | 900611 | 903976 | 95.55% | 1 | 3365 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-04 | QTR1 | 17/18 |  | 2016-12-28 | QTR2 | 16/17 | 209 | 823384.31
| 02 | T2629 | 43056215201 | 2015-12-03 | QTR2 | 15/16 | 4 | 1 | 175 | 283 | 298 | 128.6% | 0 | -15 | 15 | 0 | 73 | 35 | 3955571 | 57673 | 3897898 | 4118052 | 4040559 | -43140 | 0 | -43140 | 3997419 | 3949454 | 101.3% | 1 | -47965 | 162481 | 57 | 16 | 0 | 35 | 162481 | 0 | 0 | 0 | 26106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 188587 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 |  | 2017-01-05 | QTR3 | 16/17 | 208 | 3564631.32
| 02 | T2634 | 43225615201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 190 | 249 | 267 | 129.5% | 0 | -18 | 18 | 0 | 49 | 10 | 956123 | 50000 | 906123 | 956123 | 910673 | -28512 | 0 | -28512 | 882161 | 882485 | 97.39% | 1 | 323 | 0 | 5 | 16 | 13 | 9 | 0 | 0 | 8 | 1 | 15330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 10 | 15330 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-02-21 | QTR3 | 17/18 |  | 2017-07-17 | QTR1 | 17/18 | 216 | 1019427.54
| 02 | T2635 | 42470035201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 75 | 140 | 135 | 104% | 1 | 5 | 0 | 0 | 57 | 8 | 348154 | 16878 | 331276 | 348154 | 353179 | 0 | 0 | 0 | 353179 | 353179 | 106.6% | 1 | 0 | 0 | 45 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11425 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-09-26 | QTR1 | 17/18 |  | 2017-07-11 | QTR1 | 17/18 | 208 | 330103.8
| 02 | T2638 | 43500515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 158 | 202 | 199 | 98.1% | 1 | 3 | 0 | 0 | 44 | 0 | 1148616 | 49816 | 1098801 | 1148616 | 1092502 | 0 | 0 | 0 | 1092502 | 1092502 | 99.43% | 1 | 0 | 0 | 33 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1706 | 0 | F030527982 | J D HINSON COMPANY | N/A | N/A | N/A | N/A | 2017-12-29 | QTR2 | 17/18 |  | 2017-10-20 | QTR2 | 17/18 | 208 | 1088824.29
| 02 | T2639 | 41142415201 | 2016-10-26 | QTR2 | 16/17 | 2 | 4 | 260 | 311 | 304 | 101.2% | 1 | 7 | 0 | 0 | 41 | 10 | 2159445 | 120 | 2159325 | 2188557 | 2084623 | 0 | 0 | 0 | 2084623 | 2081632 | 96.4% | 1 | -643 | 26764 | 25 | 16 | 0 | 10 | 43759 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28343 | 0 | 0 | 10 | 24416 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-04 | QTR4 | 17/18 |  | 2017-12-20 | QTR2 | 17/18 | 209 | 2356414.98
| 02 | T2640 | 43231315201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 145 | 181 | 179 | 98.62% | 1 | 2 | 0 | 0 | 36 | 0 | 2804745 | 50000 | 2754745 | 2804745 | 2745654 | 0 | 0 | 0 | 2745654 | 2752258 | 99.91% | 1 | 6604 | 0 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-05-07 | QTR4 | 17/18 |  | 2017-07-11 | QTR1 | 17/18 | 216 | 2903614.64
| 02 | T2642 | 43430215201 | 2016-10-26 | QTR2 | 16/17 | 2 | 0 | 200 | 281 | 281 | 104.5% | 1 | 0 | 0 | 0 | 72 | 9 | 3380793 | 206100 | 3174693 | 3380793 | 3079001 | 0 | 0 | 0 | 3079001 | 3097527 | 97.57% | 1 | 18526 | 0 | 51 | 21 | 0 | 9 | 15861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 22462 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-02-23 | QTR3 | 17/18 |  | 2017-10-24 | QTR2 | 17/18 | 208 | 3680245.83
| 02 | T2644 | 43429515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 90 | 93 | 86 | 92.22% | 1 | 7 | 0 | 0 | 3 | 0 | 1424722 | 50000 | 1374722 | 1424722 | 1389257 | 0 | 0 | 0 | 1389257 | 1391632 | 101.2% | 1 | 2374 | 0 | 3 | 0 | 0 | 0 | 547 | 0 | 0 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 |  | 2017-04-12 | QTR4 | 16/17 | 209 | 1869641.02
| 02 | T2645 | 43429915201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 150 | 223 | 222 | 100.7% | 1 | 1 | 0 | 0 | 71 | 2 | 1921891 | 50000 | 1871891 | 1921891 | 1921001 | 0 | 0 | 0 | 1921001 | 1933245 | 103.3% | 1 | 12244 | 0 | 60 | 11 | 0 | 2 | 7194 | 0 | 0 | 0 | 5606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12800 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-01-25 | QTR3 | 17/18 |  | 2017-10-05 | QTR2 | 17/18 | 208 | 1970515.95
| 02 | T2646 | 43231515201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 180 | 220 | 220 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 4589348 | 50987 | 4538362 | 4589348 | 4544001 | 0 | 0 | 0 | 4544001 | 4607510 | 101.5% | 1 | 63509 | 0 | 29 | 11 | 0 | 0 | 4648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4648 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-16 | QTR3 | 17/18 |  | 2017-10-31 | QTR2 | 17/18 | 214 | 5170519.43
| 02 | T2649 | 43231115201 | 2016-12-07 | QTR2 | 16/17 | 1 | 1 | 180 | 256 | 223 | 91.11% | 1 | 33 | 0 | 0 | 59 | 17 | 3476169 | 50000 | 3426169 | 3576658 | 3781425 | 0 | 0 | 0 | 3781425 | 3833191 | 111.9% | 0 | 51766 | 100489 | 44 | 15 | 0 | 0 | 1208 | 0 | 0 | 17 | 116876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 130357 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-01-12 | QTR3 | 17/18 |  | 2017-10-04 | QTR2 | 17/18 | 214 | 4220270.07
| 02 | T2651 | 43226915201 | 2017-01-25 | QTR3 | 16/17 | 1 | 1 | 197 | 265 | 265 | 100% | 1 | 0 | 0 | 0 | 68 | 0 | 5097026 | 57071 | 5039956 | 5193738 | 5154184 | 0 | 0 | 0 | 5154184 | 5199723 | 103.2% | 1 | 45540 | 96712 | 43 | 25 | 0 | 0 | 89004 | 0 | 0 | 0 | 7708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96712 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | QTR4 | 17/18 |  | 2018-01-19 | QTR3 | 17/18 | 216 | 5759394.65
| 02 | T2652 | 43226815201 | 2017-01-25 | QTR3 | 16/17 | 1 | 1 | 150 | 212 | 183 | 87.33% | 1 | 29 | 0 | 0 | 52 | 10 | 1128456 | 50000 | 1078456 | 1178456 | 1132814 | 0 | 0 | 0 | 1132814 | 1135885 | 105.3% | 1 | 3071 | 50000 | 33 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 39274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 47573 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-04-19 | QTR4 | 17/18 |  | 2017-12-04 | QTR2 | 17/18 | 208 | 1228718.9
| 02 | T2653 | 43431815201 | 2017-01-25 | QTR3 | 16/17 | 1 | 0 | 210 | 256 | 216 | 80.95% | 1 | 40 | 0 | 0 | 46 | 0 | 5848696 | 70923 | 5777773 | 5848696 | 5842884 | 0 | 0 | 0 | 5842884 | 5902466 | 102.2% | 1 | 59582 | 0 | 16 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-04-04 | QTR4 | 17/18 |  | 2017-11-30 | QTR2 | 17/18 | 214 | 7299512.23
| 02 | T2663 | 43431915201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 270 | 324 | 315 | 96.67% | 1 | 9 | 0 | 0 | 54 | 0 | 7359482 | 81879 | 7277603 | 7359482 | 7148275 | 0 | 0 | 0 | 7148275 | 7267943 | 99.87% | 1 | 119668 | 0 | 28 | 26 | 0 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16795 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-29 | QTR4 | 17/18 |  | 2018-02-01 | QTR3 | 17/18 | 214 | 8368235.32
| 02 | T2664 | 43433015201 | 2017-03-29 | QTR3 | 16/17 | 2 | 0 | 200 | 240 | 240 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 2052728 | 50000 | 2002728 | 2052728 | 2009305 | 0 | 0 | 0 | 2009305 | 1996365 | 99.68% | 1 | -12939 | 0 | 18 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 17653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17653 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-06-27 | QTR4 | 17/18 |  | 2018-03-01 | QTR3 | 17/18 | 208 | 2080962
| 02 | T9015 | 43475815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 240 | 291 | 291 | 112.5% | 1 | 0 | 0 | 0 | 21 | 30 | 913111 | 20420 | 892691 | 913111 | 890230 | 0 | 0 | 0 | 890230 | 890229 | 99.72% | 1 | -1 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 30 | 20420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20420 | 0 | F593504786 | ANGLIN CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-08-08 | QTR1 | 17/18 |  | 2017-06-28 | QTR4 | 16/17 | 209 | 612984.42
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 34 | 44 | 49 | 9765 | 13070 | 14180 | 85.29% | 29 | -1110 | 1273 | 0 | 2928 | 377 | 195302600 | 2459250 | 192843354 | 197562989 | 197996186 | -2883736 | 150000 | -2733736 | 195262450 | 188806771 | 94.12% | 32 | -6437842 | 2258040 | 1951 | 848 | 74 | 252 | 2098843 | 249443 | 22 | 85 | 1301786 | 17599 | 0 | 0 | 2457 | 0 | 0 | 22 | -16129 | 0 | 0 | 0 | 0 | 0 | 7 | 18 | 47510 | 0 | 0 | 0 | 11464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91848 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -427488 | 0 | 109 | 377 | 3110294 | 267043
| 02 | E2R19 | 20960715201 | 2013-12-12 | QTR2 | 13/14 | 1 | 2 | 800 | 1141 | 1139 | 118.3% | 1 | 2 | 0 | 0 | 254 | 87 | 44244000 | 150000 | 44094000 | 44497660 | 44485464 | 0 | 0 | 0 | 44485464 | 43904176 | 99.57% | 1 | -555556 | 253660 | 105 | 88 | 61 | 87 | 261680 | 29435 | 0 | 0 | 49212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 87 | 367067 | 29435 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2017-08-17 | QTR1 | 17/18 |  | 2017-03-27 | QTR3 | 16/17 | 208 | 49888540.47 | B8 | ACC - DESIGN/BUILD - MAJOR
| 02 | E2R22 | 43264115201 | 2013-04-25 | QTR4 | 12/13 | 1 | 1 | 520 | 709 | 728 | 120.6% | 0 | -19 | 19 | 0 | 101 | 88 | 23839013 | 150000 | 23689013 | 25517586 | 25531336 | -153064 | 0 | -153064 | 25378272 | 24766329 | 104.5% | 1 | -611943 | 1678573 | 71 | 30 | 0 | 88 | 1684540 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 1684540 | 22000 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-01-04 | QTR3 | 17/18 |  | 2015-07-02 | QTR1 | 15/16 | 209 | 22387890.4 | LBDB | LOW BID DESIGN BUILD
| 02 | E2R95 | 42889935201 | 2013-06-19 | QTR4 | 12/13 | 1 | 0 | 200 | 258 | 609 | 275.5% | 0 | -351 | 351 | 0 | 58 | 0 | 483500 | 0 | 483500 | 483500 | 483510 | -134757 | 0 | -134757 | 348753 | 348753 | 72.13% | 1 | 0 | 0 | 46 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F161659018 | CORE CONSTRUCTION COMPANY OF JA | N/A | N/A | N/A | N/A | 2017-11-01 | QTR2 | 17/18 |  | 2015-05-14 | QTR4 | 14/15 | 209 | 448242.4 | A3 | ICC - DESIGN/BUILD - MINOR
| 02 | E2T29 | 43055915201 | 2014-11-13 | QTR2 | 14/15 | 1 | 0 | 130 | 139 | 178 | 130% | 0 | -39 | 39 | 0 | 9 | 0 | 4199999 | 50000 | 4149999 | 4199999 | 4314349 | -112164 | 0 | -112164 | 4202185 | 3826662 | 92.21% | 1 | -375523 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-01-17 | QTR3 | 17/18 |  | 2015-08-28 | QTR1 | 15/16 | 209 | 4057259.23
| 02 | E2T50 | 43044915201 | 2017-03-15 | QTR3 | 16/17 | 2 | 1 | 270 | 298 | 140 | 41.48% | 1 | 158 | 0 | 0 | 28 | 0 | 606000 | 30541 | 575459 | 609005 | 554175 | 0 | 0 | 0 | 554175 | 551170 | 95.78% | 1 | -1503 | 1503 | 17 | 11 | 0 | 0 | -986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8822 | 0 | F593114052 | K.V.K. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-09 | QTR3 | 17/18 |  | 2017-11-27 | QTR2 | 17/18 | 216 | 649753.12 | B3 | ACC - LANE RENTAL
| 02 | E2U33 | 43195815201 | 2015-06-30 | QTR4 | 14/15 | 1 | 1 | 300 | 454 | 454 | 110% | 1 | 0 | 0 | 0 | 124 | 30 | 3436656 | 50000 | 3386656 | 3327571 | 3278414 | 0 | 0 | 0 | 3278414 | 3274966 | 96.7% | 1 | -3448 | -109085 | 102 | 22 | 0 | 15 | 7337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -109085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 30 | -101748 | 0 | F591809068 | WEST CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-11-28 | QTR2 | 17/18 |  | 2017-04-01 | QTR4 | 16/17 | 209 | 3590759.86
| 02 | E2U37 | 43075615201 | 2016-03-16 | QTR3 | 15/16 | 1 | 1 | 120 | 248 | 248 | 176.7% | 0 | 0 | 0 | 0 | 36 | 92 | 1152620 | 49250 | 1103370 | 1152620 | 1092925 | 0 | 0 | 0 | 1092925 | 1092925 | 99.05% | 1 | 0 | 0 | 5 | 31 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-02-19 | QTR3 | 17/18 |  | 2017-08-03 | QTR1 | 17/18 | 208 | 1021841.84
| 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 112.2% | 1 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 110.4% | 0 | 11678 | 85250 | 19 | 18 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 |  | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91
| 02 | E2U50 | 20968615201 | 2016-05-18 | QTR4 | 15/16 | 1 | 0 | 145 | 304 | 304 | 189% | 0 | 0 | 0 | 0 | 159 | 0 | 1697762 | 50000 | 1647762 | 1697762 | 1628431 | 0 | 0 | 0 | 1628431 | 1628433 | 98.83% | 1 | 2 | 0 | 7 | 23 | 21 | 0 | 743 | 0 | 101 | 0 | 31423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1929 | 0 | 6 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 34575 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-05-10 | QTR4 | 17/18 |  | 2017-08-16 | QTR1 | 17/18 | 208 | 1682496.79
| 02 | E2U92 | 43015715201 | 2016-03-16 | QTR3 | 15/16 | 1 | 0 | 200 | 277 | 277 | 105% | 1 | 0 | 0 | 0 | 67 | 10 | 4567769 | 50000 | 4517769 | 4567769 | 4034344 | 0 | 0 | 0 | 4034344 | 4034680 | 89.31% | 1 | 336 | 0 | 29 | 38 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 |  | 2017-05-19 | QTR4 | 16/17 | 208 | 3766652.07
| 02 | E2V03 | 43242015201 | 2016-05-18 | QTR4 | 15/16 | 1 | 0 | 126 | 155 | 152 | 97.62% | 1 | 3 | 0 | 0 | 29 | 0 | 1065911 | 42293 | 1023618 | 1065911 | 1003076 | 0 | 0 | 0 | 1003076 | 1005142 | 98.2% | 1 | 2066 | 0 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 |  | 2017-04-28 | QTR4 | 16/17 | 209 | 900493.11
| 02 | E2V25 | 43432015201 | 2016-11-29 | QTR2 | 16/17 | 3 | 1 | 135 | 157 | 174 | 113.3% | 1 | -17 | 17 | 0 | 21 | 1 | 2345000 | 50000 | 2295000 | 2419896 | 2450882 | -26928 | 0 | -26928 | 2423954 | 2449808 | 106.7% | 1 | 25854 | 74896 | 11 | 10 | 0 | 1 | 626 | 0 | 0 | 0 | 75816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76442 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-01-16 | QTR3 | 17/18 |  | 2017-08-08 | QTR1 | 17/18 | 214 | 2443365.36
| 02 | E2V31 | 43434115201 | 2016-11-29 | QTR2 | 16/17 | 1 | 0 | 60 | 63 | 65 | 103.3% | 1 | -2 | 2 | 0 | 3 | 0 | 203115 | 9466 | 193650 | 203115 | 185168 | -1916 | 0 | -1916 | 183252 | 183252 | 94.63% | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-02-26 | QTR3 | 17/18 |  | 2017-05-02 | QTR4 | 16/17 | 208 | 215268.19
| 02 | E2V33 | 43430115201 | 2016-12-21 | QTR2 | 16/17 | 1 | 1 | 120 | 207 | 207 | 115.8% | 1 | 0 | 0 | 0 | 68 | 19 | 2694175 | 50000 | 2644175 | 2863300 | 2867453 | 0 | 0 | 0 | 2867453 | 2906553 | 109.9% | 1 | 39100 | 169126 | 47 | 21 | 0 | 19 | 169126 | 0 | 0 | 0 | 14573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 183698 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-02-28 | QTR3 | 17/18 |  | 2017-10-17 | QTR2 | 17/18 | 208 | 2907209.99
| 02 | E2V45 | 43526815201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 135 | 281 | 281 | 128.1% | 0 | 0 | 0 | 0 | 108 | 38 | 1232900 | 46700 | 1186200 | 1315355 | 1289463 | 0 | 0 | 0 | 1289463 | 1160707 | 97.85% | 1 | -62998 | 82455 | 75 | 33 | 0 | 0 | 9223 | 0 | 0 | 17 | 28282 | 16696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 37505 | 16696 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-06-07 | QTR4 | 17/18 |  | 2018-04-17 | QTR4 | 17/18 | 208 | 1032476.16 | B0 | ACC - LUMP SUM
| 02 | E2V61 | 43860215201 | 2017-02-15 | QTR3 | 16/17 | 4 | 1 | 180 | 212 | 210 | 98.89% | 1 | 2 | 0 | 0 | 32 | 0 | 763644 | 36425 | 727219 | 770677 | 746279 | 0 | 0 | 0 | 746279 | 746279 | 102.6% | 1 | 0 | 7033 | 12 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 19060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19060 | 0 | F650213904 | CEDARS ELECTRO-MECHANICAL INC. | N/A | N/A | N/A | N/A | 2018-04-17 | QTR4 | 17/18 |  | 2018-03-02 | QTR3 | 17/18 | 209 | 765325
| 02 | E2V68 | 43231415201 | 2017-05-17 | QTR4 | 16/17 | 1 | 0 | 140 | 167 | 103 | 54.29% | 1 | 64 | 0 | 0 | 27 | 0 | 949302 | 50000 | 899302 | 949302 | 919773 | 0 | 0 | 0 | 919773 | 926046 | 103% | 1 | 6273 | 0 | 9 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 17219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17219 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-04-12 | QTR4 | 17/18 |  | 2018-02-09 | QTR3 | 17/18 | 214 | 1080181.65
| 02 | E2W54 | 43617115201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 120 | 180 | 139 | 65.83% | 1 | 41 | 0 | 0 | 60 | 0 | 1207306 | 50000 | 1157306 | 1207306 | 1108761 | 0 | 0 | 0 | 1108761 | 1126368 | 97.33% | 1 | 17607 | 0 | 16 | 44 | 0 | 0 | 4688 | 0 | 0 | 0 | 1418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6106 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-06-15 | QTR4 | 17/18 |  | 2018-03-23 | QTR3 | 17/18 | 208 | 1296537.47
| 02 | E2W83 | 43617715201 | 2017-10-18 | QTR2 | 17/18 | 1 | 0 | 100 | 107 | 107 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 554774 | 32604 | 522170 | 554774 | 528314 | 0 | 0 | 0 | 528314 | 529911 | 101.5% | 1 | 1597 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-06-29 | QTR4 | 17/18 |  | 2018-05-11 | QTR4 | 17/18 | 208 | 689013.27
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 19 | 27 | 13 | 4031 | 5654 | 5810 | 68.42% | 13 | -156 | 428 | 0 | 1228 | 395 | 96972480 | 1047279 | 95925202 | 99217392 | 98289393 | -428829 | 0 | -428829 | 97860564 | 96261114 | 94.74% | 18 | -1506458 | 2243411 | 607 | 431 | 82 | 216 | 2267661 | 51435 | 101 | 143 | 258447 | 16696 | 0 | 0 | 0 | 0 | 0 | 0 | -109085 | 0 | 0 | 0 | 39600 | 0 | 1 | 0 | 11737 | 0 | 6 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 190 | 374 | 2485413 | 68131
| District 02 Totals |  |  |  |  | 53 | 71 | 62 | 13796 | 18724 | 19990 | 79.25% | 42 | -1266 | 1701 | 0 | 4156 | 772 | 292275080 | 3506529 | 288768556 | 296780381 | 296285579 | -3312565 | 150000 | -3162565 | 293123014 | 285067885 | 94.34% | 50 | -7944300 | 4501451 | 2558 | 1279 | 156 | 468 | 4366504 | 300878 | 123 | 228 | 1560233 | 34295 | 0 | 0 | 2457 | 0 | 0 | 22 | -125214 | 0 | 0 | 0 | 39600 | 0 | 8 | 18 | 59247 | 0 | 6 | 0 | 11944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108423 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -427488 | 0 | 299 | 751 | 5595707 | 335174
| 03 | T3350 | 40716815201 | 2013-03-27 | QTR3 | 12/13 | 1 | 2 | 430 | 854 | 897 | 140.2% | 0 | -43 | 43 | 0 | 386 | 38 | 5692603 | 50656 | 5641947 | 5867358 | 5901155 | -138718 | 0 | -138718 | 5762437 | 5819943 | 103.2% | 1 | 57505 | 174754 | 245 | 49 | 0 | 29 | 93987 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 85667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 38 | 179654 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2018-06-25 | QTR4 | 17/18 |  | 2015-11-23 | QTR2 | 15/16 | 314 | 5114304.52
| 03 | T3380 | 22067915201 | 2012-05-23 | QTR4 | 11/12 | 2 | 16 | 955 | 1636 | 1636 | 128.7% | 0 | 0 | 0 | 0 | 456 | 225 | 27973197 | 150000 | 27823197 | 28765517 | 28817877 | 0 | 0 | 0 | 28817877 | 27757494 | 99.76% | 1 | -1060383 | 792320 | 319 | 88 | 5 | 0 | 135159 | 0 | 37 | 70 | 1137365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 177 | 426650 | 213490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -797630 | 0 | 49 | 247 | 1502304 | 213490 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-07-31 | QTR1 | 17/18 |  | 2017-03-03 | QTR3 | 16/17 | 313 | 27697061.12
| 03 | T3400 | 22247715201 | 2013-08-28 | QTR1 | 13/14 | 3 | 43 | 850 | 1574 | 1539 | 136% | 0 | 35 | 0 | 0 | 561 | 163 | 43091371 | 150000 | 42941371 | 47509716 | 49630327 | -24000 | 0 | -24000 | 49606327 | 47713281 | 111.1% | 0 | -1893046 | 4418345 | 273 | 110 | 0 | 47 | 2284506 | 956120 | 178 | 78 | 1025524 | 25541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1050648 | 13331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114517 | 0 | 0 | 0 | 28390 | 28390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 163 | 4503584 | 1023381 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2018-06-07 | QTR4 | 17/18 |  | 2018-03-07 | QTR3 | 17/18 | 308 | 39882529.44
| 03 | T3406 | 42693215201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 166 | 247 | 253 | 113.3% | 1 | -6 | 6 | 0 | 81 | 0 | 2166253 | 50000 | 2116253 | 2166253 | 2369003 | -9504 | 0 | -9504 | 2359499 | 2363042 | 111.7% | 0 | 3543 | 0 | 29 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-19 | QTR2 | 17/18 |  | 2017-05-12 | QTR4 | 16/17 | 308 | 2386446.01
| 03 | T3416 | 42450815201 | 2014-05-07 | QTR4 | 13/14 | 1 | 5 | 555 | 860 | 860 | 115.9% | 1 | 0 | 0 | 0 | 225 | 80 | 13977555 | 143973 | 13833583 | 15548700 | 15324392 | 0 | 0 | 0 | 15324392 | 15062237 | 108.9% | 1 | -262156 | 1571145 | 167 | 50 | 0 | 26 | 895372 | 207942 | 0 | 0 | 23976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82180 | 51052 | 0 | 54 | 529058 | 102561 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 80 | 1595061 | 361555 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2018-01-10 | QTR3 | 17/18 |  | 2016-12-09 | QTR2 | 16/17 | 308 | 14671971.16
| 03 | T3484 | 43000215201 | 2015-02-25 | QTR3 | 14/15 | 3 | 14 | 300 | 644 | 600 | 159.3% | 0 | 44 | 0 | 0 | 315 | 29 | 4296119 | 0 | 4296119 | 6114814 | 6340441 | 0 | 0 | 0 | 6340441 | 6332694 | 147.4% | 0 | -7747 | 1818695 | 99 | 23 | 0 | 1 | 6824 | 0 | 0 | 7 | 1522085 | 1237952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 7 | 245665 | 82769 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 44120 | 44120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 29 | 1818695 | 1364841 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-05-05 | QTR4 | 16/17 | 308 | 3303857.17
| 03 | T3521 | 43078515201 | 2015-12-03 | QTR2 | 15/16 | 3 | 2 | 200 | 397 | 409 | 148.5% | 0 | -12 | 12 | 0 | 196 | 1 | 2580711 | 50000 | 2530711 | 2556235 | 2428112 | -31636 | 0 | -31636 | 2396476 | 2365069 | 93.45% | 1 | -31407 | -24476 | 75 | 37 | 8 | 1 | 1155 | 0 | 73 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | -20162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1 | -15973 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 |  | 2017-03-31 | QTR3 | 16/17 | 308 | 2532090.83
| 03 | T3524 | 22251815201 | 2016-06-15 | QTR4 | 15/16 | 2 | 1 | 240 | 317 | 317 | 104.6% | 1 | 0 | 0 | 0 | 77 | 0 | 2046734 | 50000 | 1996734 | 2173323 | 2073501 | 0 | 0 | 0 | 2073501 | 2070847 | 103.7% | 1 | -2655 | 126589 | 43 | 23 | 0 | 0 | 126589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 126589 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-12-12 | QTR2 | 17/18 |  | 2017-10-24 | QTR2 | 17/18 | 321 | 2321587.69
| 03 | T3528 | 22281815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 120 | 139 | 138 | 106.7% | 1 | 1 | 0 | 0 | 19 | 0 | 931084 | 33811 | 897273 | 988106 | 921773 | 0 | 0 | 0 | 921773 | 921773 | 102.7% | 1 | 0 | 57022 | 9 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 57022 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-07-27 | QTR1 | 17/18 |  | 2017-05-20 | QTR4 | 16/17 | 313 | 926503.43
| 03 | T3531 | 43078415201 | 2016-01-27 | QTR3 | 15/16 | 4 | 3 | 230 | 338 | 341 | 114.3% | 1 | -3 | 3 | 0 | 78 | 30 | 4796511 | 50000 | 4746511 | 5842667 | 5869213 | -10128 | 0 | -10128 | 5859085 | 5851868 | 123.3% | 0 | -7217 | 1046156 | 58 | 20 | 0 | 0 | 0 | 0 | 0 | 30 | 596890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1046753 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-11-08 | QTR2 | 17/18 |  | 2017-05-19 | QTR4 | 16/17 | 321 | 4833815.48
| 03 | T3541 | 43046715201 | 2017-02-22 | QTR3 | 16/17 | 2 | 3 | 160 | 264 | 264 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 762396 | 0 | 762396 | 768113 | 740975 | 0 | 0 | 0 | 740975 | 741383 | 97.24% | 1 | 407 | 5717 | 81 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 4927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4927 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-06-27 | QTR4 | 17/18 |  | 2018-03-30 | QTR3 | 17/18 | 308 | 751000
| 03 | T3550 | 43257015201 | 2015-12-03 | QTR2 | 15/16 | 1 | 0 | 195 | 323 | 318 | 97.44% | 1 | 5 | 0 | 0 | 128 | 0 | 9008956 | 100031 | 8908925 | 9008956 | 9058480 | 0 | 0 | 0 | 9058480 | 8913154 | 100% | 1 | -145326 | 0 | 107 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 7180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7180 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 |  | 2017-03-01 | QTR3 | 16/17 | 321 | 9047924.85
| 03 | T3553 | 43273915201 | 2016-04-27 | QTR4 | 15/16 | 1 | 2 | 180 | 231 | 229 | 100% | 1 | 2 | 0 | 0 | 49 | 2 | 5112998 | 56886 | 5056112 | 5217096 | 5197254 | -15000 | 0 | -15000 | 5182254 | 5211856 | 103.1% | 1 | 29602 | 104098 | 31 | 18 | 0 | 2 | 49607 | 0 | 0 | 0 | 47212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 99339 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-03-10 | QTR3 | 16/17 | 321 | 5858555.67
| 03 | T3557 | 43047215201 | 2016-10-26 | QTR2 | 16/17 | 3 | 3 | 325 | 475 | 476 | 116.9% | 1 | -1 | 1 | 0 | 150 | 0 | 3101706 | 21426 | 3080281 | 3159561 | 3107062 | -3800 | 0 | -3800 | 3103262 | 3079745 | 99.98% | 1 | -8031 | 57855 | 73 | 23 | 49 | 0 | 38972 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 42369 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-06-25 | QTR4 | 17/18 |  | 2018-05-02 | QTR4 | 17/18 | 308 | 3337302.14
| 03 | T3563 | 43344815201 | 2017-03-29 | QTR3 | 16/17 | 1 | 2 | 150 | 201 | 189 | 94.67% | 1 | 12 | 0 | 0 | 47 | 4 | 434900 | 16291 | 418609 | 486505 | 459662 | 0 | 0 | 0 | 459662 | 460414 | 110% | 1 | 752 | 51605 | 36 | 11 | 0 | 4 | 26560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25045 | 25045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 51605 | 25045 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 |  | 2017-12-20 | QTR2 | 17/18 | 308 | 347118.69
| 03 | T3564 | 43273615201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 260 | 476 | 476 | 100% | 1 | 0 | 0 | 0 | 216 | 0 | 8987040 | 99047 | 8887993 | 9020160 | 9114270 | -36735 | 0 | -36735 | 9077535 | 9043937 | 101.8% | 1 | -33598 | 33120 | 166 | 50 | 0 | 0 | 33120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107965 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-04 | QTR2 | 17/18 |  | 2017-08-02 | QTR1 | 17/18 | 308 | 10170399.14
| 03 | T3566 | 43047015201 | 2017-02-22 | QTR3 | 16/17 | 2 | 2 | 135 | 182 | 181 | 99.26% | 1 | 1 | 0 | 0 | 47 | 0 | 740057 | 0 | 740057 | 740736 | 741918 | 0 | 0 | 0 | 741918 | 741816 | 100.2% | 1 | -102 | 679 | 40 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-03-26 | QTR3 | 17/18 |  | 2017-11-08 | QTR2 | 17/18 | 308 | 733082.39
| 03 | T3574 | 43047115201 | 2016-08-31 | QTR1 | 16/17 | 1 | 0 | 125 | 166 | 172 | 104.8% | 1 | -6 | 6 | 0 | 41 | 0 | 710702 | 0 | 710702 | 710702 | 703481 | -9504 | 0 | -9504 | 693977 | 696276 | 97.97% | 1 | 2299 | 0 | 30 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-04-21 | QTR4 | 16/17 | 308 | 765580.95
| 03 | T3575 | 43079115201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 65 | 72 | 72 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 1223500 | 50000 | 1173500 | 1223500 | 1204340 | 0 | 0 | 0 | 1204340 | 1216824 | 103.7% | 1 | 12484 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-16 | QTR1 | 17/18 |  | 2017-04-18 | QTR4 | 16/17 | 313 | 1644576.72 | B0 | ACC - LUMP SUM
| 03 | T3576 | 42857615201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 120 | 191 | 191 | 115% | 1 | 0 | 0 | 0 | 53 | 18 | 455335 | 0 | 455335 | 461101 | 462306 | 0 | 0 | 0 | 462306 | 462306 | 101.5% | 1 | 0 | 5766 | 40 | 13 | 0 | 0 | 0 | 0 | 0 | 18 | 5766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 5766 | 0 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-05-20 | QTR4 | 16/17 | 313 | 517906.59
| 03 | T3577 | 43047515201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 145 | 221 | 214 | 107.6% | 1 | 7 | 0 | 0 | 76 | 0 | 777422 | 0 | 777422 | 777422 | 756968 | 0 | 0 | 0 | 756968 | 757588 | 97.45% | 1 | 619 | 0 | 34 | 24 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 |  | 2018-01-08 | QTR3 | 17/18 | 313 | 827647.36
| 03 | T3583 | 43047415201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 120 | 181 | 181 | 117.5% | 1 | 0 | 0 | 0 | 61 | 0 | 450844 | 0 | 450844 | 450844 | 461793 | 0 | 0 | 0 | 461793 | 461793 | 102.4% | 1 | 0 | 0 | 28 | 12 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-12-12 | QTR2 | 17/18 |  | 2017-11-01 | QTR2 | 17/18 | 313 | 501000
| 03 | T3588 | 43390415201 | 2016-10-26 | QTR2 | 16/17 | 1 | 2 | 265 | 354 | 353 | 104.9% | 1 | 1 | 0 | 0 | 89 | 0 | 1128303 | 0 | 1128303 | 1129920 | 1176298 | 0 | 0 | 0 | 1176298 | 1177731 | 104.4% | 1 | 1433 | 1617 | 60 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 1617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 1617 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2018-05-01 | QTR4 | 17/18 |  | 2017-12-21 | QTR2 | 17/18 | 308 | 1069862.79
| 03 | T3590 | 43273815201 | 2016-03-30 | QTR3 | 15/16 | 3 | 2 | 265 | 456 | 456 | 120% | 1 | 0 | 0 | 0 | 141 | 50 | 8979888 | 97111 | 8882777 | 9089938 | 8804885 | -11500 | 0 | -11500 | 8793385 | 8851032 | 99.64% | 1 | 57647 | 105256 | 107 | 31 | 0 | 0 | 0 | 0 | 0 | 50 | 122455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 122455 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2018-04-17 | QTR4 | 17/18 |  | 2017-09-29 | QTR1 | 17/18 | 313 | 9805557.62
| 03 | T3591 | 43047815201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 125 | 198 | 198 | 114.4% | 1 | 0 | 0 | 0 | 73 | 0 | 755934 | 0 | 755934 | 755934 | 764661 | 0 | 0 | 0 | 764661 | 765293 | 101.2% | 1 | 632 | 0 | 38 | 17 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-01-24 | QTR3 | 17/18 |  | 2017-12-05 | QTR2 | 17/18 | 313 | 728590.2
| 03 | T3592 | 43466715201 | 2016-12-07 | QTR2 | 16/17 | 2 | 0 | 150 | 227 | 225 | 110.7% | 1 | 2 | 0 | 0 | 73 | 4 | 2446453 | 51160 | 2395293 | 2446453 | 2415161 | 0 | 0 | 0 | 2415161 | 2432529 | 101.6% | 1 | 17369 | 0 | 42 | 17 | 14 | 0 | 2420 | 0 | 0 | 4 | 14826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 4 | 17246 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 |  | 2017-10-05 | QTR2 | 17/18 | 313 | 2770764.29
| 03 | T3593 | 43356915201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 132 | 203 | 207 | 126.5% | 0 | -4 | 4 | 0 | 57 | 14 | 1110799 | 50000 | 1060799 | 1110799 | 1075584 | -6336 | 0 | -6336 | 1069248 | 1069297 | 100.8% | 1 | 48 | 0 | 32 | 8 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 14 | 15186 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-10-30 | QTR2 | 17/18 |  | 2017-08-22 | QTR1 | 17/18 | 314 | 1069165.29
| 03 | T3599 | 42820835201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 90 | 92 | 83 | 90% | 1 | 9 | 0 | 0 | 2 | 0 | 311313 | 9628 | 301685 | 311313 | 302309 | 0 | 0 | 0 | 302309 | 302309 | 100.2% | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-02 | QTR1 | 17/18 |  | 2017-03-31 | QTR3 | 16/17 | 308 | 204199 | B0 | ACC - LUMP SUM
| 03 | T3600 | 42695115201 | 2016-02-24 | QTR3 | 15/16 | 1 | 1 | 155 | 299 | 299 | 118.7% | 1 | 0 | 0 | 0 | 130 | 14 | 2196017 | 50000 | 2146017 | 2209792 | 2194453 | 0 | 0 | 0 | 2194453 | 2190296 | 102.1% | 1 | -4157 | 13776 | 80 | 35 | 0 | 0 | 0 | 0 | 15 | 14 | 16901 | 13776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14 | 21411 | 13776 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-08-16 | QTR1 | 17/18 |  | 2017-03-29 | QTR3 | 16/17 | 308 | 2203713.84
| 03 | T3601 | 43046315201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 150 | 225 | 224 | 99.33% | 1 | 1 | 0 | 0 | 75 | 0 | 937429 | 0 | 937429 | 937429 | 948863 | 0 | 0 | 0 | 948863 | 948876 | 101.2% | 1 | 13 | 0 | 67 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2017-12-19 | QTR2 | 17/18 |  | 2017-08-21 | QTR1 | 17/18 | 314 | 1073431.03
| 03 | T3608 | 43356815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 0 | 125 | 193 | 192 | 99.2% | 1 | 1 | 0 | 0 | 68 | 0 | 535448 | 29005 | 506444 | 535448 | 538259 | 0 | 0 | 0 | 538259 | 543732 | 107.4% | 1 | 5474 | 0 | 30 | 38 | 0 | 0 | 27200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27200 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-05-30 | QTR4 | 17/18 |  | 2018-04-19 | QTR4 | 17/18 | 321 | 646015.19
| 03 | T3610 | 43255615201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 120 | 137 | 101 | 70% | 1 | 36 | 0 | 0 | 17 | 0 | 1354302 | 50000 | 1304302 | 1354302 | 1333996 | 0 | 0 | 0 | 1333996 | 1333996 | 102.3% | 1 | 0 | 0 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-11-30 | QTR2 | 17/18 |  | 2017-10-26 | QTR2 | 17/18 | 313 | 1817291.75 | B0 | ACC - LUMP SUM
| 03 | T3611 | 43256715201 | 2017-01-25 | QTR3 | 16/17 | 1 | 0 | 120 | 145 | 134 | 90.83% | 1 | 11 | 0 | 0 | 25 | 0 | 933656 | 41797 | 891860 | 933656 | 847331 | 0 | 0 | 0 | 847331 | 849907 | 95.3% | 1 | 2576 | 0 | 17 | 8 | 0 | 0 | 8236 | 0 | 0 | 0 | 2394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21880 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-12-04 | QTR2 | 17/18 |  | 2017-08-15 | QTR1 | 17/18 | 308 | 1051000
| 03 | T3613 | 21995025202 | 2016-12-07 | QTR2 | 16/17 | 4 | 3 | 195 | 244 | 243 | 99.49% | 1 | 1 | 0 | 0 | 49 | 0 | 5413721 | 92895 | 5320825 | 5421436 | 5717509 | 0 | 0 | 0 | 5717509 | 5805268 | 109.1% | 1 | 87758 | 7716 | 37 | 12 | 0 | 0 | 3816 | 3816 | 0 | 0 | 4227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8042 | 3816 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-02-15 | QTR3 | 17/18 |  | 2017-10-20 | QTR2 | 17/18 | 321 | 6943781.15
| 03 | T3616 | 43662215201 | 2017-03-29 | QTR3 | 16/17 | 1 | 0 | 60 | 75 | 63 | 80% | 1 | 12 | 0 | 0 | 15 | 0 | 96639 | 0 | 96639 | 96639 | 100978 | 0 | 0 | 0 | 100978 | 100978 | 104.5% | 1 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | QTR1 | 17/18 |  | 2017-08-02 | QTR1 | 17/18 | 321 | 113500
| 03 | T3620 | 43278725201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 45 | 69 | 69 | 102.2% | 1 | 0 | 0 | 0 | 24 | 0 | 98537 | 0 | 98537 | 98537 | 95183 | 0 | 0 | 0 | 95183 | 95183 | 96.6% | 1 | 0 | 0 | 15 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 |  | 2017-07-12 | QTR1 | 17/18 | 321 | 131241.78
| 03 | T3625 | 43188315201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 75 | 140 | 140 | 130.7% | 0 | 0 | 0 | 0 | 63 | 2 | 966793 | 39222 | 927571 | 970978 | 923813 | 0 | 0 | 0 | 923813 | 919628 | 99.14% | 1 | -4185 | 4185 | 34 | 8 | 0 | 2 | 5219 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 2 | 5219 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-21 | QTR3 | 17/18 |  | 2017-11-07 | QTR2 | 17/18 | 308 | 827500
| 03 | T3628 | 43626415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 60 | 85 | 81 | 93.33% | 1 | 4 | 0 | 0 | 25 | 0 | 798080 | 50000 | 748080 | 798080 | 766495 | 0 | 0 | 0 | 766495 | 766495 | 102.5% | 1 | 0 | 0 | 9 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-26 | QTR3 | 17/18 |  | 2018-02-01 | QTR3 | 17/18 | 313 | 1010000 | B0 | ACC - LUMP SUM
| 03 | T3631 | 43827525201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 90 | 120 | 105 | 83.33% | 1 | 15 | 0 | 0 | 30 | 0 | 140958 | 6321 | 134637 | 140958 | 128843 | 0 | 0 | 0 | 128843 | 128843 | 95.7% | 1 | 0 | 0 | 17 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F203990573 | MURDOCK INVESTMENTS LLC | N/A | N/A | N/A | N/A | 2018-05-30 | QTR4 | 17/18 |  | 2018-03-20 | QTR3 | 17/18 | 314 | 138259.04
| 03 | T3643 | 43626215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 0 | 60 | 62 | 55 | 88.33% | 1 | 7 | 0 | 0 | 2 | 0 | 550118 | 35866 | 514252 | 550118 | 526409 | 0 | 0 | 0 | 526409 | 526409 | 102.4% | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-06-04 | QTR4 | 17/18 |  | 2018-03-30 | QTR3 | 17/18 | 321 | 755612.66
| 03 | T3654 | 43827615201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 45 | 69 | 68 | 97.78% | 1 | 1 | 0 | 0 | 24 | 0 | 40030 | 1983 | 38047 | 40030 | 37300 | 0 | 0 | 0 | 37300 | 37300 | 98.04% | 1 | 0 | 0 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-11-08 | QTR2 | 17/18 |  | 2017-10-09 | QTR2 | 17/18 | 308 | 43000.39
| 03 | T3657 | 40980195201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 117 | 117 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 391534 | 16972 | 374563 | 391534 | 404360 | 0 | 0 | 0 | 404360 | 404360 | 108% | 1 | 0 | 0 | 13 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2018-04-25 | QTR4 | 17/18 |  | 2018-03-31 | QTR3 | 17/18 | 314 | 349936.25
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 42 | 65 | 111 | 8428 | 13499 | 13366 | 83.33% | 35 | 133 | 75 | 0 | 4397 | 674 | 168503946 | 1694081 | 166809869 | 178880679 | 180786993 | -296861 | 0 | -296861 | 180490132 | 177294802 | 90.48% | 38 | -3179849 | 10371940 | 2636 | 925 | 115 | 112 | 3738742 | 1167878 | 451 | 271 | 4534762 | 1277269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 245 | 2498823 | 334635 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 797457 | 51052 | 0 | 54 | 557448 | 130951 | 8 | 14 | 44120 | 44120 | 0 | 0 | 0 | 0 | 0 | 0 | -797630 | 0 | 833 | 696 | 11373721 | 3005904
| 03 | E3N16 | 42902475201 | 2014-12-19 | QTR2 | 14/15 | 2 | 6 | 560 | 901 | 893 | 118.4% | 1 | 8 | 0 | 0 | 284 | 57 | 16475693 | 150000 | 16325693 | 16845905 | 16848483 | 0 | 0 | 0 | 16848483 | 16712396 | 102.4% | 1 | -136087 | 370212 | 178 | 52 | 54 | 25 | 169404 | 31240 | 0 | 42 | 298911 | 57695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 51119 | 20267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 57 | 519434 | 109202 | F590840493 | GAC CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-01-04 | QTR3 | 17/18 |  | 2017-08-25 | QTR1 | 17/18 | 306 | 16475693 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
| 03 | E3N84 | 21876225201 | 2016-07-14 | QTR1 | 16/17 | 1 | 0 | 120 | 179 | 190 | 138.3% | 0 | -11 | 11 | 0 | 59 | 0 | 531067 | 36301 | 494766 | 531067 | 486082 | -17424 | 0 | -17424 | 468658 | 468658 | 94.72% | 1 | 0 | 0 | 11 | 13 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | F592982651 | WILLIAMS INDUSTRIAL & MARINE I | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-05-01 | QTR4 | 16/17 | 321 | 761742
| 03 | E3O04 | 41768345201 | 2016-07-14 | QTR1 | 16/17 | 1 | 0 | 105 | 221 | 278 | 222.9% | 0 | -57 | 57 | 0 | 116 | 0 | 565668 | 27463 | 538205 | 565668 | 550555 | -90288 | 0 | -90288 | 460267 | 489412 | 90.93% | 1 | 29145 | 0 | 17 | 27 | 21 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 12350 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 |  | 2017-07-25 | QTR1 | 17/18 | 308 | 576618
| 03 | E3O86 | 43255215201 | 2017-02-09 | QTR3 | 16/17 | 3 | 2 | 290 | 351 | 238 | 61.03% | 1 | 113 | 0 | 0 | 61 | 0 | 3759171 | 50000 | 3709171 | 3953037 | 3874241 | 0 | 0 | 0 | 3874241 | 3841980 | 103.6% | 1 | -3461 | 165067 | 40 | 21 | 0 | 0 | 9875 | 0 | 0 | 0 | 6740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159424 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-14 | QTR3 | 17/18 |  | 2017-12-22 | QTR2 | 17/18 | 321 | 4804332.83
| 03 | E3P09 | 41767745201 | 2016-07-14 | QTR1 | 16/17 | 1 | 0 | 180 | 407 | 405 | 130.6% | 0 | 2 | 0 | 0 | 200 | 27 | 1746205 | 50000 | 1696205 | 1746205 | 1870829 | 0 | 0 | 0 | 1870829 | 1871101 | 110.3% | 0 | 272 | 0 | 123 | 47 | 30 | 5 | 25895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 24100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 27 | 49995 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2018-01-10 | QTR3 | 17/18 |  | 2017-11-21 | QTR2 | 17/18 | 314 | 1884982.7
| 03 | E3P11 | 43257215201 | 2016-04-14 | QTR4 | 15/16 | 1 | 0 | 210 | 314 | 313 | 102.9% | 1 | 1 | 0 | 0 | 104 | 0 | 6922953 | 61524 | 6861429 | 6922953 | 6941583 | 0 | 0 | 0 | 6941583 | 6966761 | 101.5% | 1 | 25178 | 0 | 60 | 37 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-29 | QTR1 | 17/18 |  | 2017-05-18 | QTR4 | 16/17 | 314 | 6237409.01
| 03 | E3P12 | 43255515201 | 2016-11-10 | QTR2 | 16/17 | 1 | 1 | 90 | 105 | 105 | 115.6% | 1 | 0 | 0 | 0 | 15 | 0 | 751984 | 39984 | 712000 | 801537 | 761553 | 0 | 0 | 0 | 761553 | 761553 | 107% | 1 | 0 | 49553 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 49553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 49553 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-09-14 | QTR1 | 17/18 |  | 2017-05-26 | QTR4 | 16/17 | 308 | 851593.48 | B0 | ACC - LUMP SUM
| 03 | E3P15 | 43255015201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 90 | 95 | 88 | 92.22% | 1 | 7 | 0 | 0 | 5 | 0 | 1296000 | 50000 | 1246000 | 1296000 | 1281750 | 0 | 0 | 0 | 1281750 | 1293176 | 103.8% | 1 | 11426 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2017-08-28 | QTR1 | 17/18 |  | 2017-04-30 | QTR4 | 16/17 | 321 | 1595361.1 | B0 | ACC - LUMP SUM
| 03 | E3P36 | 42358935201 | 2017-02-09 | QTR3 | 16/17 | 1 | 2 | 150 | 195 | 187 | 94.67% | 1 | 8 | 0 | 0 | 45 | 0 | 2450599 | 50000 | 2400599 | 2476226 | 2317426 | 0 | 0 | 0 | 2317426 | 2305202 | 96.03% | 1 | 604 | 25628 | 26 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12800 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-06-05 | QTR4 | 17/18 |  | 2018-02-13 | QTR3 | 17/18 | 321 | 1549641.5
| 03 | E3P46 | 43466815201 | 2017-06-08 | QTR4 | 16/17 | 1 | 0 | 90 | 152 | 148 | 95.56% | 1 | 4 | 0 | 0 | 62 | 0 | 557062 | 27215 | 529848 | 557062 | 546186 | -8400 | 0 | -8400 | 537786 | 537786 | 101.5% | 1 | 0 | 0 | 47 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 16368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16368 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2018-05-01 | QTR4 | 17/18 |  | 2018-01-26 | QTR3 | 17/18 | 308 | 571964.36 | B0 | ACC - LUMP SUM
| 03 | E3P62 | 21787925201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 130 | 214 | 210 | 96.92% | 1 | 4 | 0 | 0 | 84 | 0 | 1094282 | 48440 | 1045842 | 1094282 | 1014445 | 0 | 0 | 0 | 1014445 | 1015749 | 97.12% | 1 | 1305 | 0 | 43 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-10-30 | QTR2 | 17/18 |  | 2017-07-19 | QTR1 | 17/18 | 314 | 1020236.95
| 03 | E3P74 | 22271315201 | 2016-06-09 | QTR4 | 15/16 | 1 | 1 | 120 | 137 | 137 | 100% | 1 | 0 | 0 | 0 | 17 | 0 | 916620 | 32497 | 884123 | 973642 | 931184 | 0 | 0 | 0 | 931184 | 931184 | 105.3% | 1 | 0 | 57022 | 9 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-05-12 | QTR4 | 16/17 | 308 | 702427.14
| 03 | E3P75 | 43078615201 | 2016-07-14 | QTR1 | 16/17 | 2 | 0 | 100 | 210 | 210 | 177% | 0 | 0 | 0 | 0 | 110 | 0 | 2702301 | 50119 | 2652182 | 2702301 | 2824495 | 0 | 0 | 0 | 2824495 | 2819950 | 106.3% | 1 | -4545 | 0 | 17 | 16 | 73 | 0 | 5732 | 0 | 4 | 0 | 14182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 19914 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 |  | 2017-04-27 | QTR4 | 16/17 | 308 | 2591912.99
| 03 | E3P91 | 43460615201 | 2016-10-13 | QTR2 | 16/17 | 1 | 0 | 75 | 100 | 100 | 116% | 1 | 0 | 0 | 0 | 25 | 0 | 367076 | 15130 | 351946 | 367076 | 357176 | 0 | 0 | 0 | 357176 | 357176 | 101.5% | 1 | 0 | 0 | 12 | 1 | 0 | 0 | 5230 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 5230 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 |  | 2017-04-22 | QTR4 | 16/17 | 308 | 306636.35 | B0 | ACC - LUMP SUM
| 03 | E3Q09 | 43749615201 | 2017-01-12 | QTR3 | 16/17 | 1 | 0 | 50 | 89 | 88 | 98% | 1 | 1 | 0 | 0 | 39 | 0 | 360470 | 29511 | 330959 | 360470 | 302941 | 0 | 0 | 0 | 302941 | 302941 | 91.53% | 1 | 0 | 0 | 35 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-11-15 | QTR2 | 17/18 |  | 2017-08-30 | QTR1 | 17/18 | 321 | 618734.99
| 03 | E3Q27 | 43626315201 | 2017-07-13 | QTR1 | 17/18 | 2 | 0 | 90 | 125 | 125 | 100% | 1 | 0 | 0 | 0 | 35 | 0 | 1148724 | 51111 | 1097613 | 1148724 | 1173198 | 0 | 0 | 0 | 1173198 | 1173198 | 106.9% | 1 | 0 | 0 | 17 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-15 | QTR3 | 17/18 |  | 2018-01-30 | QTR3 | 17/18 | 314 | 1210000
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 16 | 21 | 12 | 2450 | 3795 | 3715 | 75% | 12 | 80 | 68 | 0 | 1261 | 84 | 41645875 | 769295 | 40876581 | 42342155 | 42082127 | -116112 | 0 | -116112 | 41966015 | 41848223 | 93.75% | 15 | -76163 | 667482 | 641 | 319 | 213 | 30 | 216136 | 31240 | 88 | 42 | 400638 | 57695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 263300 | 20267 | 0 | 22 | 24100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301 | 84 | 904174 | 109202
| District 03 Totals |  |  |  |  | 58 | 86 | 123 | 10878 | 17294 | 17081 | 81.03% | 47 | 213 | 143 | 0 | 5658 | 758 | 210149821 | 2463376 | 207686450 | 221222834 | 222869120 | -412973 | 0 | -412973 | 222456147 | 219143025 | 91.38% | 53 | -3256012 | 11039422 | 3277 | 1244 | 328 | 142 | 3954878 | 1199118 | 539 | 313 | 4935400 | 1334964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 235 | 2762123 | 354902 | 105 | 22 | 24100 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 797457 | 51052 | 0 | 54 | 557448 | 130951 | 8 | 14 | 44120 | 44120 | 0 | 0 | 0 | 0 | 0 | 0 | -797630 | 0 | 1134 | 780 | 12277895 | 3115106
| 04 | T4360 | 40691915201 | 2013-06-19 | QTR4 | 12/13 | 2 | 10 | 919 | 1391 | 1391 | 119.9% | 1 | 0 | 0 | 0 | 358 | 114 | 22198458 | 150000 | 22048458 | 24242652 | 24231373 | 0 | 0 | 0 | 24231373 | 24184321 | 109.7% | 1 | -47051 | 2044194 | 228 | 61 | 35 | 84 | 1056338 | 304013 | 0 | 0 | 416860 | 27507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 30 | 614810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 114 | 2088008 | 331520 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2018-03-05 | QTR3 | 17/18 |  | 2017-08-18 | QTR1 | 17/18 | 412 | 25330673.92
| 04 | T4387 | 42924625201 | 2014-04-30 | QTR4 | 13/14 | 2 | 2 | 460 | 621 | 621 | 108% | 1 | 0 | 0 | 0 | 158 | 3 | 20572640 | 150000 | 20422640 | 20874760 | 20200080 | 0 | 0 | 0 | 20200080 | 19403592 | 95.01% | 1 | -796488 | 302120 | 97 | 27 | 0 | 0 | 41914 | 0 | 0 | 3 | 55774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 266000 | 266000 | 34 | 0 | 20558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 3 | 392245 | 266000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-11 | QTR2 | 17/18 |  | 2016-04-06 | QTR4 | 15/16 | 409 | 23230743.39
| 04 | T4392 | 42873115201 | 2016-08-31 | QTR1 | 16/17 | 3 | 0 | 146 | 158 | 157 | 99.32% | 1 | 1 | 0 | 0 | 12 | 0 | 1894496 | 50000 | 1844496 | 1894496 | 1876142 | 0 | 0 | 0 | 1876142 | 1885605 | 102.2% | 1 | 9463 | 0 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 6357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14601 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-12-15 | QTR2 | 17/18 |  | 2017-06-08 | QTR4 | 16/17 | 412 | 2046919.21 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 04 | T4393 | 42872215201 | 2015-10-28 | QTR2 | 15/16 | 2 | 3 | 228 | 398 | 402 | 126.8% | 0 | -4 | 4 | 0 | 118 | 52 | 7257569 | 84109 | 7173460 | 7675751 | 7429380 | -15080 | 0 | -15080 | 7414300 | 7264049 | 101.3% | 1 | -150251 | 418182 | 90 | 23 | 5 | 15 | 182656 | 0 | 0 | 15 | 262907 | 1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 6909 | 0 | 0 | 0 | 18227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 52 | 470700 | 1463 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-05-21 | QTR4 | 17/18 |  | 2017-03-01 | QTR3 | 16/17 | 409 | 7461270.16
| 04 | T4407 | 43060115201 | 2015-12-03 | QTR2 | 15/16 | 2 | 2 | 333 | 412 | 411 | 99.7% | 1 | 1 | 0 | 0 | 79 | 0 | 4429693 | 50000 | 4379693 | 4522960 | 4441417 | 0 | 144900 | 144900 | 4586317 | 4419287 | 100.9% | 1 | -167030 | 93267 | 48 | 31 | 0 | 0 | 59120 | 0 | 0 | 0 | 18567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78567 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-09 | QTR2 | 17/18 |  | 2017-06-02 | QTR4 | 16/17 | 412 | 4059381.95 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4408 | 42898415201 | 2015-04-29 | QTR4 | 14/15 | 2 | 7 | 590 | 716 | 711 | 99.15% | 1 | 5 | 0 | 0 | 126 | 0 | 5457914 | 59401 | 5398513 | 5501915 | 5476312 | 0 | 0 | 0 | 5476312 | 5355390 | 99.2% | 1 | -120921 | 44001 | 96 | 30 | 0 | 0 | 8201 | 0 | 0 | 0 | 99691 | 4389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -77463 | 0 | 0 | 0 | 75511 | 4389 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-08-11 | QTR1 | 17/18 |  | 2017-06-23 | QTR4 | 16/17 | 408 | 6001634.3
| 04 | T4428 | 43175715201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 185 | 197 | 197 | 100% | 1 | 0 | 0 | 0 | 12 | 0 | 1321404 | 50000 | 1271404 | 1321404 | 1261612 | 0 | 0 | 0 | 1261612 | 1264590 | 99.46% | 1 | 2978 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 9018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9018 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-08 | QTR3 | 17/18 |  | 2017-05-06 | QTR4 | 16/17 | 412 | 1395149.88
| 04 | T4429 | 43320715201 | 2016-02-24 | QTR3 | 15/16 | 2 | 2 | 276 | 345 | 344 | 108.7% | 1 | 1 | 0 | 0 | 44 | 25 | 1817368 | 50000 | 1767368 | 1866868 | 1820548 | 0 | 0 | 0 | 1820548 | 1828664 | 103.5% | 1 | 8115 | 49500 | 31 | 13 | 0 | 0 | 23754 | 0 | 0 | 25 | 41825 | 27746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 65579 | 27746 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-28 | QTR1 | 17/18 |  | 2017-06-27 | QTR4 | 16/17 | 412 | 1805872.62
| 04 | T4436 | 43515915201 | 2017-02-22 | QTR3 | 16/17 | 2 | 0 | 74 | 95 | 94 | 98.65% | 1 | 1 | 0 | 0 | 21 | 0 | 363409 | 19053 | 344357 | 363409 | 342509 | 0 | 0 | 0 | 342509 | 342509 | 99.46% | 1 | 0 | 0 | 16 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 |  | 2017-09-06 | QTR1 | 17/18 | 409 | 390893.72
| 04 | T4437 | 43510215201 | 2016-03-30 | QTR3 | 15/16 | 1 | 3 | 48 | 104 | 104 | 118.8% | 1 | 0 | 0 | 0 | 47 | 9 | 647604 | 27717 | 619887 | 693460 | 677812 | 0 | 0 | 0 | 677812 | 677812 | 109.3% | 1 | 0 | 45856 | 45 | 2 | 0 | 0 | 0 | 0 | 0 | 9 | 29362 | 34197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10791 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 51453 | 44988 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2017-08-08 | QTR1 | 17/18 |  | 2016-11-07 | QTR2 | 16/17 | 409 | 572056.26
| 04 | T4440 | 43512215201 | 2016-05-25 | QTR4 | 15/16 | 1 | 0 | 237 | 272 | 267 | 97.89% | 1 | 5 | 0 | 0 | 35 | 0 | 1336353 | 50000 | 1286353 | 1336353 | 1276103 | 0 | 0 | 0 | 1276103 | 1277493 | 99.31% | 1 | 1390 | 0 | 16 | 19 | 0 | 0 | 3339 | 0 | 0 | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-17 | QTR2 | 17/18 |  | 2017-08-10 | QTR1 | 17/18 | 409 | 1362625.9
| 04 | T4441 | 43799415201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 134 | 136 | 62 | 44.78% | 1 | 74 | 0 | 0 | 2 | 0 | 899605 | 49184 | 850421 | 899605 | 846333 | 0 | 50000 | 50000 | 896333 | 846333 | 99.52% | 1 | -50000 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-09-25 | QTR1 | 17/18 |  | 2017-08-15 | QTR1 | 17/18 | 412 | 1032154.5 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | T4442 | 43444915201 | 2016-08-31 | QTR1 | 16/17 | 1 | 0 | 169 | 212 | 210 | 98.82% | 1 | 2 | 0 | 0 | 43 | 0 | 413333 | 18532 | 394801 | 413333 | 384378 | 0 | 0 | 0 | 384378 | 384534 | 97.4% | 1 | 156 | 0 | 34 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 4513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4513 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-10-30 | QTR2 | 17/18 |  | 2017-09-25 | QTR1 | 17/18 | 412 | 393421.68
| 04 | T4443 | 43427515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 120 | 131 | 131 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 1312214 | 50000 | 1262214 | 1312214 | 1253435 | 0 | 0 | 0 | 1253435 | 1261184 | 99.92% | 1 | 7749 | 0 | 0 | 11 | 0 | 0 | 801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2017-08-07 | QTR1 | 17/18 |  | 2017-04-21 | QTR4 | 16/17 | 408 | 1458806.8
| 04 | T4448 | 43786515201 | 2017-02-22 | QTR3 | 16/17 | 2 | 1 | 119 | 157 | 157 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 279149 | 13386 | 265763 | 282353 | 271123 | 0 | 0 | 0 | 271123 | 264714 | 99.61% | 1 | -3205 | 3205 | 33 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 6026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6026 | 0 | F650861113 | I & C EARTHMOVERS CORP. | N/A | N/A | N/A | N/A | 2018-02-14 | QTR3 | 17/18 |  | 2017-11-08 | QTR2 | 17/18 | 412 | 272833.13
| 04 | T4458 | 43168715201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 88 | 117 | 116 | 98.86% | 1 | 1 | 0 | 0 | 29 | 0 | 234419 | 13120 | 221300 | 234419 | 219157 | 0 | 0 | 0 | 219157 | 219157 | 99.03% | 1 | 0 | 0 | 25 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2017-10-06 | QTR2 | 17/18 |  | 2017-08-28 | QTR1 | 17/18 | 412 | 262846.25
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 16 | 26 | 30 | 4126 | 5462 | 5375 | 93.75% | 15 | 87 | 4 | 0 | 1133 | 203 | 70435628 | 884502 | 69551128 | 73435952 | 72007714 | -15080 | 194900 | 179820 | 72187534 | 70879234 | 100% | 16 | -1305095 | 3000325 | 772 | 253 | 40 | 99 | 1376123 | 304013 | 0 | 52 | 951458 | 95302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19300 | 0 | 34 | 52 | 942969 | 266000 | 34 | 0 | 39665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10791 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -77463 | 0 | 108 | 203 | 3262844 | 676106
| 04 | E4K49 | 42279615201 | 2010-12-03 | QTR2 | 10/11 | 4 | 17 | 770 | 1766 | 1894 | 217% | 0 | -128 | 128 | 0 | 223 | 773 | 84027062 | 150000 | 83877062 | 128024336 | 127605903 | -1137325 | 0 | -1137325 | 126468579 | 126905951 | 151.3% | 0 | 437373 | 43997274 | 178 | 45 | 0 | 105 | 962107 | 0 | 0 | 335 | 30312020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 12553147 | 0 | 0 | 0 | 259786 | 0 | 0 | 0 | -162117 | 0 | 0 | 0 | 153417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773 | 44078361 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-01-10 | QTR3 | 17/18 |  | 2017-02-02 | QTR3 | 16/17 | 412 | 102208657 | ARRA:B8:Y:ARR::Y | AMERICAN RECOVERY AND REINVEST:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:AMERICAN RECOVERY AND REINVEST:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4Q43 | 22939625201 | 2015-04-15 | QTR4 | 14/15 | 1 | 0 | 450 | 613 | 613 | 100.9% | 1 | 0 | 0 | 0 | 159 | 4 | 9189394 | 64394 | 9125000 | 9189394 | 9232946 | 0 | 148500 | 148500 | 9381446 | 8920506 | 97.76% | 1 | -460940 | 0 | 118 | 41 | 0 | 0 | 13790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 16262 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-30 | QTR2 | 17/18 |  | 2017-02-20 | QTR3 | 16/17 | 409 | 6467904.26 | A3:B5:Y | ICC - DESIGN/BUILD - MINOR:ACC - INCENTIVE/DISINCENTIVE:DESIGN/BUILD PROJECT
| 04 | E4R04 | 43062515201 | 2015-06-12 | QTR4 | 14/15 | 1 | 0 | 255 | 296 | 293 | 98.82% | 1 | 3 | 0 | 0 | 41 | 0 | 1604618 | 50000 | 1554618 | 1604618 | 1554867 | 0 | 0 | 0 | 1554867 | 1554752 | 100% | 1 | -115 | 0 | 23 | 18 | 0 | 0 | 6891 | 0 | 0 | 0 | 1506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8397 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-07 | QTR1 | 17/18 |  | 2017-06-28 | QTR4 | 16/17 | 412 | 1736394.32 | B0 | ACC - LUMP SUM
| 04 | E4R64 | 43664615201 | 2016-03-04 | QTR3 | 15/16 | 1 | 1 | 458 | 520 | 412 | 76.42% | 1 | 108 | 0 | 0 | 62 | 0 | 8161674 | 109400 | 8052274 | 8192052 | 8168056 | 0 | 300000 | 300000 | 8468056 | 8188367 | 101.7% | 1 | -279689 | 30378 | 47 | 15 | 0 | 0 | 5673 | 0 | 0 | 0 | 31277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30378 | 0 | 0 | 0 | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67882 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-12-21 | QTR2 | 17/18 |  | 2017-07-22 | QTR1 | 17/18 | 408 | 11010250.52 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4R66 | 42872725201 | 2016-03-04 | QTR3 | 15/16 | 1 | 1 | 293 | 331 | 331 | 100% | 1 | 0 | 0 | 0 | 38 | 0 | 2866096 | 50000 | 2816096 | 3030096 | 3026692 | 0 | 0 | 0 | 3026692 | 3026963 | 107.5% | 1 | 272 | 164000 | 21 | 17 | 0 | 0 | 167040 | 30703 | 0 | 0 | 17339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197428 | 30703 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 |  | 2017-06-30 | QTR4 | 16/17 | 412 | 1839665.45
| 04 | E4R68 | 43750315201 | 2016-07-01 | QTR1 | 16/17 | 1 | 2 | 252 | 272 | 213 | 76.59% | 1 | 59 | 0 | 0 | 20 | 0 | 4071704 | 50278 | 4021426 | 4123622 | 4162840 | 0 | 100000 | 100000 | 4262840 | 4159065 | 103.4% | 1 | -103775 | 51918 | 10 | 10 | 0 | 0 | 22683 | 0 | 0 | 0 | 28003 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90643 | 153 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-11-29 | QTR2 | 17/18 |  | 2017-04-12 | QTR4 | 16/17 | 406 | 5128284.05 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4R80 | 43232615201 | 2016-12-02 | QTR2 | 16/17 | 1 | 0 | 190 | 241 | 241 | 100% | 1 | 0 | 0 | 0 | 51 | 0 | 2142842 | 50000 | 2092842 | 2142842 | 2107961 | 0 | 0 | 0 | 2107961 | 2118375 | 101.2% | 1 | 10414 | 0 | 42 | 9 | 0 | 0 | 3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3701 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-02-08 | QTR3 | 17/18 |  | 2017-10-23 | QTR2 | 17/18 | 408 | 2054272.34
| 04 | E4S04 | 43110715201 | 2016-10-14 | QTR2 | 16/17 | 1 | 0 | 102 | 118 | 116 | 98.04% | 1 | 2 | 0 | 0 | 16 | 0 | 289809 | 14415 | 275394 | 289809 | 270949 | 0 | 0 | 0 | 270949 | 270949 | 98.39% | 1 | 0 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2017-08-23 | QTR1 | 17/18 |  | 2017-06-09 | QTR4 | 16/17 | 412 | 303225.64
| 04 | E4S17 | 43397715201 | 2017-01-06 | QTR3 | 16/17 | 1 | 0 | 28 | 34 | 33 | 96.43% | 1 | 1 | 0 | 0 | 6 | 0 | 280209 | 12373 | 267836 | 280209 | 215232 | 0 | 0 | 0 | 215232 | 215232 | 80.36% | 1 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 10803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10803 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-09-20 | QTR1 | 17/18 |  | 2017-07-20 | QTR1 | 17/18 | 412 | 253963.62
| 04 | E4S18 | 43110615201 | 2017-01-06 | QTR3 | 16/17 | 3 | 2 | 154 | 181 | 180 | 77.27% | 1 | 1 | 0 | 0 | 61 | -34 | 1025128 | 50000 | 975128 | 1057971 | 1006759 | 0 | 0 | 0 | 1006759 | 973916 | 99.88% | 1 | -16422 | 16422 | 52 | 9 | 0 | 0 | 9460 | 0 | 0 | -34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34 | 9460 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 |  | 2017-10-20 | QTR2 | 17/18 | 409 | 3357102.02
| 04 | E4S28 | 43793415201 | 2017-03-03 | QTR3 | 16/17 | 2 | 1 | 169 | 204 | 147 | 66.27% | 1 | 57 | 0 | 0 | 35 | 0 | 316709 | 17954 | 298755 | 319147 | 303591 | 0 | 0 | 0 | 303591 | 298717 | 99.99% | 1 | -2437 | 2437 | 31 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473077227 | TADEOS ENGINEERING LLC | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 |  | 2017-10-23 | QTR2 | 17/18 | 412 | 371789.25
| 04 | E4S33 | 43334915201 | 2017-04-07 | QTR4 | 16/17 | 4 | 1 | 138 | 180 | 180 | 100% | 1 | 0 | 0 | 0 | 42 | 0 | 460000 | 22899 | 437101 | 464502 | 437196 | 0 | 0 | 0 | 437196 | 430636 | 98.52% | 1 | -2057 | 4503 | 21 | 21 | 0 | 0 | 6568 | 0 | 0 | 0 | 6064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12632 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-05-08 | QTR4 | 17/18 |  | 2018-02-06 | QTR3 | 17/18 | 408 | 473230.59
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 12 | 21 | 25 | 3259 | 4756 | 4653 | 91.67% | 11 | 103 | 128 | 0 | 754 | 743 | 114435245 | 641713 | 113793532 | 158718598 | 158092992 | -1137325 | 548500 | -588825 | 157504168 | 157063429 | 91.67% | 11 | -417376 | 44266932 | 559 | 195 | 0 | 105 | 1197913 | 30703 | 0 | 301 | 30407012 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 12596575 | 0 | 0 | 0 | 260340 | 0 | 0 | 0 | -162117 | 0 | 0 | 4 | 155889 | 0 | 0 | 0 | 39957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743 | 44495569 | 30856
| District 04 Totals |  |  |  |  | 28 | 47 | 55 | 7385 | 10218 | 10028 | 92.86% | 26 | 190 | 132 | 0 | 1887 | 946 | 184870873 | 1526215 | 183344660 | 232154550 | 230100706 | -1152405 | 743400 | -409005 | 229691702 | 227942663 | 96.43% | 27 | -1722471 | 47267257 | 1331 | 448 | 40 | 204 | 2574036 | 334716 | 0 | 353 | 31358470 | 95455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19300 | 0 | 34 | 385 | 13539544 | 266000 | 34 | 0 | 300005 | 0 | 0 | 0 | -162117 | 0 | 0 | 4 | 155889 | 0 | 0 | 0 | 50748 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -77463 | 0 | 108 | 946 | 47758413 | 706962
| 05 | BE035 | 43387415201 | 2015-08-10 | QTR1 | 15/16 | 1 | 6 | 345 | 494 | 495 | 131.9% | 0 | -1 | 1 | 0 | 40 | 109 | 8947000 | 150000 | 8797000 | 9057405 | 9057405 | 0 | 0 | 0 | 9057405 | 9057101 | 103% | 1 | -304 | 110405 | 19 | 21 | 0 | 55 | 165982 | 14523 | 0 | 54 | -39561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 110405 | 14523 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-05-05 | QTR4 | 16/17 | 509 | 8947000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | BE042 | 43643615201 | 2015-07-20 | QTR1 | 15/16 | 1 | 4 | 527 | 552 | 552 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 4349110 | 150000 | 4199110 | 4305862 | 4305862 | 0 | 0 | 0 | 4305862 | 4305862 | 102.5% | 1 | 0 | -43247 | 6 | 19 | 0 | 0 | 84597 | 0 | 0 | 0 | -150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43247 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2017-10-11 | QTR2 | 17/18 |  | 2017-08-03 | QTR1 | 17/18 | 509 | 2601707 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | BE227 | 43029015201 | 2016-04-22 | QTR4 | 15/16 | 1 | 5 | 220 | 244 | 243 | 99.55% | 1 | 1 | 0 | 0 | 24 | 0 | 1697000 | 50000 | 1647000 | 1771015 | 1771015 | 0 | 0 | 0 | 1771015 | 1771300 | 107.5% | 1 | 285 | 74015 | 19 | 5 | 0 | 0 | 62930 | 0 | 0 | 0 | 11085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74015 | 0 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-05-12 | QTR4 | 16/17 | 513 | 1668323.35
| 05 | T5466 | 43066525201 | 2013-07-31 | QTR1 | 13/14 | 2 | 1 | 109 | 136 | 410 | 351.4% | 0 | -274 | 274 | 0 | 27 | 0 | 650999 | 38000 | 612999 | 630759 | 395792 | 0 | 0 | 0 | 395792 | 395792 | 64.57% | 1 | 0 | -20240 | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20240 | 0 | Z59-1673015 | BANKERS INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-06-13 | QTR4 | 17/18 |  | 2014-12-08 | QTR2 | 14/15 | 515 | 828132.5 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 05 | T5468 | 42887615201 | 2013-12-04 | QTR2 | 13/14 | 1 | 2 | 300 | 436 | 455 | 108% | 1 | -19 | 19 | 0 | 131 | 5 | 5811896 | 62000 | 5749896 | 5828065 | 5929467 | -61294 | 0 | -61294 | 5868173 | 5738344 | 99.8% | 1 | -129829 | 16169 | 104 | 27 | 0 | 5 | 45612 | 0 | 0 | 0 | 19937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 76906 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-06 | QTR2 | 17/18 |  | 2015-06-24 | QTR4 | 14/15 | 514 | 6328169.8 | B0 | ACC - LUMP SUM
| 05 | T5514 | 43065815201 | 2015-06-17 | QTR4 | 14/15 | 2 | 4 | 300 | 466 | 466 | 116.3% | 1 | 0 | 0 | 0 | 119 | 47 | 2758832 | 50000 | 2708832 | 3022207 | 3025677 | 0 | 0 | 0 | 3025677 | 2881446 | 106.4% | 1 | -115108 | 263375 | 92 | 25 | 0 | 0 | 0 | 0 | 2 | 0 | 40418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 205488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 47 | 245906 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-27 | QTR2 | 17/18 |  | 2017-03-16 | QTR3 | 16/17 | 514 | 2936599.78
| 05 | T5516 | 23968315201 | 2015-03-25 | QTR3 | 14/15 | 3 | 9 | 750 | 686 | 606 | 73.33% | 1 | 80 | 0 | 0 | 56 | -120 | 16187452 | 150000 | 16037452 | 16131784 | 15468614 | 0 | 316000 | 316000 | 15784614 | 14731955 | 91.86% | 1 | -991289 | -55668 | 29 | 27 | 0 | 0 | 78814 | 0 | 0 | 0 | 220522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | -340989 | 0 | 0 | -120 | -4653 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-10-13 | QTR2 | 17/18 |  | 2017-06-01 | QTR4 | 16/17 | 509 | 16443271.05 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 05 | T5523 | 43064315201 | 2015-03-25 | QTR3 | 14/15 | 1 | 2 | 520 | 767 | 788 | 107.3% | 1 | -21 | 21 | 0 | 230 | 17 | 26022554 | 150000 | 25872554 | 26092001 | 26837874 | -244771 | 0 | -244771 | 26593103 | 24360936 | 94.16% | 1 | -2232167 | 69447 | 185 | 45 | 0 | 17 | 76392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 76392 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-08 | QTR2 | 17/18 |  | 2017-08-22 | QTR1 | 17/18 | 512 | 32995661.17
| 05 | T5533 | 42728015201 | 2015-07-29 | QTR1 | 15/16 | 2 | 9 | 340 | 466 | 494 | 126.2% | 0 | -28 | 28 | 0 | 65 | 61 | 8422850 | 50000 | 8372850 | 8665412 | 8608390 | -105560 | 0 | -105560 | 8502830 | 8174179 | 97.63% | 1 | -328651 | 242562 | 33 | 32 | 0 | 0 | 4603 | 0 | 0 | 46 | 107535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 176219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 288356 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-09-05 | QTR1 | 17/18 |  | 2017-04-04 | QTR4 | 16/17 | 512 | 8647534.74
| 05 | T5546 | 43234215201 | 2016-06-15 | QTR4 | 15/16 | 2 | 1 | 230 | 376 | 373 | 108.3% | 1 | 3 | 0 | 0 | 144 | 2 | 2075235 | 50000 | 2025235 | 2088068 | 2079010 | 0 | 0 | 0 | 2079010 | 2057061 | 101.6% | 1 | -9116 | 12833 | 86 | 38 | 0 | 0 | 0 | 0 | 20 | 2 | 23721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2 | 23721 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-28 | QTR4 | 17/18 |  | 2017-12-07 | QTR2 | 17/18 | 514 | 1799214
| 05 | T5547 | 43240715201 | 2016-01-27 | QTR3 | 15/16 | 3 | 5 | 370 | 396 | 395 | 99.73% | 1 | 1 | 0 | 0 | 26 | 0 | 5090422 | 50000 | 5040422 | 5188654 | 5185897 | 0 | 0 | 0 | 5185897 | 5163808 | 102.4% | 1 | -19514 | 98232 | 12 | 14 | 0 | 0 | 14392 | 0 | 0 | 0 | 96878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114283 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-03-01 | QTR3 | 17/18 |  | 2017-05-26 | QTR4 | 16/17 | 509 | 4488965.86
| 05 | T5549 | 43240215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 4 | 250 | 367 | 367 | 100% | 1 | 0 | 0 | 0 | 117 | 0 | 4288764 | 50000 | 4238764 | 4479588 | 4434500 | 0 | 0 | 0 | 4434499 | 4445448 | 104.9% | 1 | 17674 | 207821 | 96 | 21 | 0 | 0 | 16197 | 0 | 0 | 0 | 88205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203911 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-04-18 | QTR4 | 17/18 |  | 2017-07-29 | QTR1 | 17/18 | 509 | 4897477.97 | B0 | ACC - LUMP SUM
| 05 | T5553 | 43242115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 1 | 150 | 171 | 169 | 98.67% | 1 | 2 | 0 | 0 | 21 | 0 | 1085604 | 50000 | 1035604 | 1087044 | 1021639 | -6360 | 0 | -6360 | 1015279 | 1026222 | 99.09% | 1 | 10943 | 1440 | 7 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 6692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6692 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-07-13 | QTR1 | 17/18 |  | 2017-04-24 | QTR4 | 16/17 | 595 | 1163003.22
| 05 | T5554 | 43066715202 | 2016-06-15 | QTR4 | 15/16 | 6 | 3 | 320 | 457 | 455 | 102.8% | 1 | 2 | 0 | 0 | 126 | 11 | 5357590 | 61400 | 5296190 | 5415657 | 5363913 | 0 | 0 | 0 | 5363913 | 5291189 | 99.91% | 1 | -8188 | 58067 | 100 | 26 | 0 | 8 | 31331 | 0 | 0 | 0 | -6469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 27077 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-05-15 | QTR4 | 17/18 |  | 2017-12-08 | QTR2 | 17/18 | 514 | 6206642.55 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| 05 | T5563 | 43067815201 | 2016-06-15 | QTR4 | 15/16 | 3 | 6 | 480 | 590 | 564 | 96.04% | 1 | 26 | 0 | 0 | 103 | 7 | 10074300 | 133000 | 9941300 | 10356846 | 10457771 | 0 | 0 | 0 | 10457771 | 10390989 | 104.5% | 1 | -11520 | 282546 | 55 | 48 | 0 | 0 | 18240 | 0 | 0 | 0 | 44935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 292360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 355535 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-06-28 | QTR4 | 17/18 |  | 2018-03-01 | QTR3 | 17/18 | 513 | 13456513.9
| 05 | T5565 | 43065715201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 230 | 273 | 273 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 3028041 | 50000 | 2978041 | 3028041 | 2950282 | 0 | 0 | 0 | 2950282 | 2950886 | 99.09% | 1 | 604 | 0 | 24 | 19 | 0 | 0 | 5094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5094 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-08 | QTR1 | 17/18 |  | 2017-07-21 | QTR1 | 17/18 | 514 | 3357586 | B0 | ACC - LUMP SUM
| 05 | T5566 | 43243715201 | 2016-07-27 | QTR1 | 16/17 | 1 | 2 | 150 | 195 | 195 | 105.3% | 1 | 0 | 0 | 0 | 37 | 8 | 3766852 | 50000 | 3716852 | 3749136 | 3790510 | 0 | 0 | 0 | 3790510 | 3819315 | 102.8% | 1 | 28805 | -17716 | 20 | 17 | 0 | 0 | -8096 | 0 | 0 | 8 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4316 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-09-08 | QTR1 | 17/18 |  | 2017-05-08 | QTR4 | 16/17 | 514 | 4106500.86
| 05 | T5567 | 43442415201 | 2016-07-27 | QTR1 | 16/17 | 1 | 1 | 120 | 243 | 264 | 197.5% | 0 | -21 | 21 | 0 | 27 | 96 | 1345000 | 50000 | 1295000 | 1345000 | 1239674 | 0 | 0 | 0 | 1239674 | 1239674 | 95.73% | 1 | 0 | 0 | 11 | 16 | 0 | 0 | 0 | 0 | 0 | 5 | 7372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 7372 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2018-02-15 | QTR3 | 17/18 |  | 2017-07-17 | QTR1 | 17/18 | 509 | 1380185.4 | B0 | ACC - LUMP SUM
| 05 | T5568 | 43442515201 | 2016-07-27 | QTR1 | 16/17 | 2 | 1 | 130 | 160 | 158 | 98.46% | 1 | 2 | 0 | 0 | 30 | 0 | 1275035 | 50000 | 1225035 | 1276035 | 1191362 | 0 | 0 | 0 | 1191362 | 1191683 | 97.28% | 1 | 320 | 1000 | 27 | 3 | 0 | 0 | 4775 | 0 | 0 | 0 | 5034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9809 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-03-08 | QTR3 | 17/18 |  | 2017-06-30 | QTR4 | 16/17 | 509 | 1313711
| 05 | T5574 | 43241615201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 170 | 232 | 230 | 110.6% | 1 | 2 | 0 | 0 | 42 | 20 | 3274900 | 36000 | 3238900 | 3420024 | 3368050 | 0 | 0 | 0 | 3368050 | 3391256 | 104.7% | 1 | 23206 | 145124 | 26 | 16 | 0 | 20 | 145124 | 0 | 0 | 0 | 3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 167246 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-10-31 | QTR2 | 17/18 |  | 2017-07-14 | QTR1 | 17/18 | 509 | 3753389.85 | B0 | ACC - LUMP SUM
| 05 | T5576 | 41503055201 | 2016-06-15 | QTR4 | 15/16 | 4 | 5 | 320 | 481 | 480 | 117.8% | 1 | 1 | 0 | 0 | 103 | 58 | 5373132 | 61500 | 5311632 | 5659631 | 5489222 | 0 | 0 | 0 | 5489222 | 5482158 | 103.2% | 1 | 31462 | 245499 | 78 | 25 | 0 | 18 | 147936 | 0 | 0 | 40 | 83427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 231363 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-28 | QTR4 | 17/18 |  | 2018-04-28 | QTR4 | 17/18 | 507 | 6329513.9
| 05 | T5581 | 43304015201 | 2016-12-07 | QTR2 | 16/17 | 4 | 2 | 230 | 277 | 277 | 100% | 1 | 0 | 0 | 0 | 47 | 0 | 1118456 | 50000 | 1068456 | 1151446 | 1116798 | 0 | 0 | 0 | 1116798 | 1116571 | 104.5% | 1 | 1214 | 32989 | 22 | 25 | 0 | 0 | 3707 | 0 | 0 | 0 | 11645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46901 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-03-29 | QTR3 | 17/18 |  | 2018-02-07 | QTR3 | 17/18 | 507 | 1259440.1
| 05 | T5583 | 43505215201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 160 | 168 | 159 | 94.38% | 1 | 9 | 0 | 0 | 8 | 0 | 990233 | 50000 | 940233 | 990233 | 940233 | 0 | 0 | 0 | 940233 | 940251 | 100% | 1 | 18 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 |  | 2017-08-18 | QTR1 | 17/18 | 509 | 1091962.75 | B0 | ACC - LUMP SUM
| 05 | T5586 | 43469415201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 80 | 132 | 132 | 108.7% | 1 | 0 | 0 | 0 | 45 | 7 | 727458 | 30000 | 697458 | 768228 | 756229 | 0 | 0 | 0 | 756229 | 735459 | 105.4% | 1 | 0 | 40770 | 39 | 6 | 0 | 0 | 0 | 0 | 0 | 7 | 38001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 38001 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-04-05 | QTR4 | 17/18 |  | 2017-11-14 | QTR2 | 17/18 | 509 | 645877.5
| 05 | T5593 | 43635615201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 90 | 97 | 41 | 37.78% | 1 | 56 | 0 | 0 | 7 | 0 | 264250 | 24250 | 240000 | 264250 | 240000 | 0 | 0 | 0 | 240000 | 240000 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2018-03-21 | QTR3 | 17/18 |  | 2017-12-04 | QTR2 | 17/18 | 515 | 541050 | B0 | ACC - LUMP SUM
| 05 | T5594 | 43636415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 140 | 151 | 98 | 62.14% | 1 | 53 | 0 | 0 | 11 | 0 | 452000 | 30000 | 422000 | 452000 | 422000 | 0 | 0 | 0 | 422000 | 422000 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2018-05-30 | QTR4 | 17/18 |  | 2018-03-14 | QTR3 | 17/18 | 509 | 653172.35
| 05 | T5595 | 43623615201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 60 | 79 | 73 | 90% | 1 | 6 | 0 | 0 | 19 | 0 | 325875 | 18000 | 307875 | 325875 | 307875 | 0 | 0 | 0 | 307875 | 307875 | 100% | 1 | 0 | 0 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-03-19 | QTR3 | 17/18 |  | 2018-02-13 | QTR3 | 17/18 | 514 | 393057.85
| 05 | T5596 | 43637115201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 60 | 67 | 56 | 81.67% | 1 | 11 | 0 | 0 | 7 | 0 | 148500 | 6500 | 142000 | 148500 | 142000 | 0 | 0 | 0 | 142000 | 142000 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2018-05-03 | QTR4 | 17/18 |  | 2017-12-19 | QTR2 | 17/18 | 512 | 188225
| 05 | T5599 | 43623515201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 80 | 110 | 108 | 101.2% | 1 | 2 | 0 | 0 | 27 | 3 | 456461 | 27000 | 429461 | 456461 | 456461 | 0 | 0 | 0 | 456461 | 456461 | 106.3% | 1 | 0 | 0 | 11 | 16 | 0 | 3 | 14438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27000 | 0 | F341233573 | OGLESBY CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-03-19 | QTR3 | 17/18 |  | 2018-02-09 | QTR3 | 17/18 | 513 | 580001
| 05 | T5603 | 43440815201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 90 | 121 | 103 | 80% | 1 | 18 | 0 | 0 | 31 | 0 | 413889 | 25000 | 388889 | 413889 | 405966 | 0 | 0 | 0 | 405966 | 405966 | 104.4% | 1 | 0 | 0 | 11 | 20 | 0 | 0 | 3265 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4090 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-05-08 | QTR4 | 17/18 |  | 2018-03-21 | QTR3 | 17/18 | 512 | 623229.4
| 05 | T5610 | 44113015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 81 | 21 | 14.29% | 1 | 60 | 0 | 0 | 11 | 0 | 67500 | 5000 | 62500 | 67500 | 63500 | 0 | 0 | 0 | 63500 | 63500 | 101.6% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-01-30 | QTR3 | 17/18 |  | 2017-09-25 | QTR1 | 17/18 | 514 | 112350
| 05 | T5611 | 44113025201 | 2017-06-14 | QTR4 | 16/17 | 4 | 1 | 90 | 102 | 91 | 87.78% | 1 | 11 | 0 | 0 | 12 | 0 | 332500 | 21850 | 310650 | 345530 | 326210 | 0 | 0 | 0 | 326210 | 326210 | 105% | 1 | 0 | 13030 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-03-30 | QTR3 | 17/18 |  | 2017-12-19 | QTR2 | 17/18 | 514 | 569600
| 05 | T5613 | 44113045201 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 130 | 183 | 182 | 99.23% | 1 | 1 | 0 | 0 | 53 | 0 | 184425 | 10900 | 173525 | 184425 | 206750 | 0 | 0 | 0 | 206750 | 206750 | 119.1% | 0 | 0 | 0 | 36 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F462078794 | CWA ENVIRONMENTAL SERVICES LLC | N/A | N/A | N/A | N/A | 2018-04-17 | QTR4 | 17/18 |  | 2018-02-28 | QTR3 | 17/18 | 514 | 249956.54
| 05 | T5614 | 44113055201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 80 | 185 | 185 | 100% | 1 | 0 | 0 | 0 | 105 | 0 | 107445 | 7500 | 99945 | 107445 | 107255 | 0 | 0 | 0 | 107255 | 107255 | 107.3% | 1 | 0 | 0 | 75 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-05-22 | QTR4 | 17/18 |  | 2018-04-17 | QTR4 | 17/18 | 514 | 168140
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 34 | 62 | 77 | 7691 | 9941 | 9958 | 88.24% | 30 | -17 | 364 | 0 | 1919 | 331 | 126471560 | 1847900 | 124623660 | 128274016 | 127463203 | -417985 | 316000 | -101985 | 127361217 | 123336902 | 97.06% | 33 | -3731155 | 1778453 | 1265 | 632 | 0 | 126 | 915333 | 14523 | 22 | 162 | 625992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 834507 | 0 | 0 | 0 | 18744 | 0 | 0 | 0 | -20240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 42906 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | -340989 | 0 | 22 | 331 | 2076251 | 14523
| 05 | E5R16 | 40846415201 | 2012-02-03 | QTR3 | 11/12 | 2 | 14 | 900 | 1825 | 1825 | 142.4% | 0 | 0 | 0 | 0 | 544 | 381 | 134462000 | 150000 | 134312000 | 142782598 | 143964934 | -226500 | 0 | -226500 | 143738434 | 140483406 | 104.6% | 1 | -3054710 | 8320598 | 400 | 143 | 0 | 62 | -391641 | 0 | 0 | 267 | 9075569 | 3527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 82418 | 3383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -497895 | 0 | 1 | 329 | 8268451 | 6910 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2018-06-27 | QTR4 | 17/18 |  | 2017-05-07 | QTR4 | 16/17 | 513 | 134462000 | B8 | ACC - DESIGN/BUILD - MAJOR
| 05 | E5W10 | 24262625201 | 2014-06-25 | QTR4 | 13/14 | 2 | 13 | 800 | 1027 | 960 | 97.12% | 1 | 67 | 0 | 0 | 215 | 12 | 76960400 | 150000 | 76810400 | 78949466 | 78905602 | -2960 | 500000 | 497040 | 79402642 | 74147945 | 96.53% | 1 | -5253206 | 1989066 | 129 | 54 | 0 | 12 | 1372538 | 271485 | 32 | 0 | 139811 | 64469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208829 | 0 | 0 | 0 | 394803 | 223994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 12 | 2115980 | 559948 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-10-02 | QTR2 | 17/18 |  | 2017-04-21 | QTR4 | 16/17 | 515 | 74117581 | B2:B5:B8 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 05 | E5Y06 | 43544325201 | 2016-03-29 | QTR3 | 15/16 | 1 | 1 | 225 | 508 | 518 | 224.4% | 0 | -10 | 10 | 0 | 48 | 235 | 1130290 | 50000 | 1080290 | 1130290 | 958974 | 0 | 0 | 0 | 958974 | 958974 | 88.77% | 1 | 0 | 0 | 2 | 11 | 0 | 28 | 0 | 0 | 0 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2018-05-15 | QTR4 | 17/18 |  | 2017-11-17 | QTR2 | 17/18 | 594 | 1120522.5
| 05 | E5Y27 | 43750115201 | 2016-05-03 | QTR4 | 15/16 | 2 | 0 | 170 | 361 | 359 | 194.1% | 0 | 2 | 0 | 0 | 29 | 162 | 1337625 | 56000 | 1281625 | 1337625 | 1189585 | 0 | 0 | 0 | 1189585 | 1190243 | 92.87% | 1 | 659 | 0 | 13 | 16 | 0 | 0 | 1786 | 0 | 0 | 162 | 2956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 4742 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-12-29 | QTR2 | 17/18 |  | 2017-08-30 | QTR1 | 17/18 | 515 | 1320391
| 05 | E5Y32 | 43445515201 | 2016-08-02 | QTR1 | 16/17 | 1 | 0 | 120 | 189 | 177 | 90% | 1 | 12 | 0 | 0 | 69 | 0 | 622133 | 26000 | 596133 | 622133 | 564614 | 0 | 0 | 0 | 564614 | 564745 | 94.73% | 1 | 131 | 0 | 38 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2017-09-06 | QTR1 | 17/18 |  | 2017-04-28 | QTR4 | 16/17 | 513 | 567682.87
| 05 | E5Y34 | 43744415201 | 2016-09-07 | QTR1 | 16/17 | 1 | 0 | 140 | 153 | 152 | 99.29% | 1 | 1 | 0 | 0 | 13 | 0 | 793972 | 40000 | 753972 | 793972 | 619065 | 0 | 0 | 0 | 619065 | 621005 | 82.36% | 1 | 1940 | 0 | 3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-10-16 | QTR2 | 17/18 |  | 2017-05-14 | QTR4 | 16/17 | 509 | 843684
| 05 | E5Y35 | 42302915201 | 2016-10-04 | QTR2 | 16/17 | 2 | 1 | 90 | 118 | 116 | 97.78% | 1 | 2 | 0 | 0 | 28 | 0 | 900963 | 36000 | 864963 | 905489 | 870490 | 0 | 0 | 0 | 870490 | 870490 | 100.6% | 1 | 0 | 4526 | 25 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5527 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-03-16 | QTR3 | 17/18 |  | 2017-06-29 | QTR4 | 16/17 | 509 | 774382.55
| 05 | E5Y36 | 43445615201 | 2016-10-04 | QTR2 | 16/17 | 1 | 0 | 110 | 118 | 118 | 100% | 1 | 0 | 0 | 0 | 8 | 0 | 704674 | 32000 | 672674 | 704674 | 672674 | 0 | 0 | 0 | 672674 | 672674 | 100% | 1 | 0 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 |  | 2017-05-05 | QTR4 | 16/17 | 515 | 684419.55
| 05 | E5Y37 | 43744815201 | 2016-12-06 | QTR2 | 16/17 | 1 | 1 | 85 | 103 | 100 | 96.47% | 1 | 3 | 0 | 0 | 18 | 0 | 339868 | 17000 | 322868 | 339868 | 258858 | 0 | 0 | 0 | 258858 | 258860 | 80.18% | 1 | 2 | 0 | 2 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC | N/A | N/A | N/A | N/A | 2017-11-17 | QTR2 | 17/18 |  | 2017-05-25 | QTR4 | 16/17 | 513 | 388062
| 05 | E5Y53 | 24021675201 | 2017-05-02 | QTR4 | 16/17 | 1 | 0 | 150 | 206 | 195 | 92.67% | 1 | 11 | 0 | 0 | 56 | 0 | 1488299 | 50000 | 1438299 | 1488299 | 1438708 | 0 | 0 | 0 | 1438708 | 1450820 | 100.9% | 1 | 12112 | 0 | 36 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-20 | QTR3 | 17/18 |  | 2018-02-15 | QTR3 | 17/18 | 507 | 1582604.35
| 05 | E5Y58 | 43744615201 | 2017-03-07 | QTR3 | 16/17 | 1 | 1 | 159 | 183 | 182 | 99.37% | 1 | 1 | 0 | 0 | 24 | 0 | 498196 | 35000 | 463196 | 498012 | 443118 | 0 | 0 | 0 | 443118 | 443118 | 95.67% | 1 | 0 | -184 | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | -184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -184 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-02-27 | QTR3 | 17/18 |  | 2018-01-22 | QTR3 | 17/18 | 513 | 954404
| 05 | E5Y59 | 43709215201 | 2016-12-06 | QTR2 | 16/17 | 1 | 0 | 220 | 225 | 167 | 73.64% | 1 | 58 | 0 | 0 | 5 | 0 | 524644 | 24000 | 500644 | 524644 | 497252 | 0 | 0 | 0 | 497252 | 497252 | 99.32% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-11-21 | QTR2 | 17/18 |  | 2017-08-25 | QTR1 | 17/18 | 514 | 584577
| 05 | E5Y63 | 43234615201 | 2016-10-04 | QTR2 | 16/17 | 1 | 1 | 90 | 116 | 132 | 126.7% | 0 | -16 | 16 | 0 | 18 | 8 | 862770 | 33000 | 829770 | 868517 | 816671 | -25344 | 0 | -25344 | 791327 | 791327 | 95.37% | 1 | 0 | 5747 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 |  | 2017-05-15 | QTR4 | 16/17 | 513 | 776696.15
| 05 | E5Y76 | 43566215201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 180 | 199 | 95 | 42.22% | 1 | 104 | 0 | 0 | 19 | 0 | 3490230 | 50000 | 3440230 | 3490230 | 3483913 | 0 | 0 | 0 | 3483913 | 3496667 | 101.6% | 1 | 12754 | 0 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-04 | QTR4 | 17/18 |  | 2018-01-08 | QTR3 | 17/18 | 515 | 4898413
| 05 | E5Y79 | 43544335201 | 2017-03-07 | QTR3 | 16/17 | 2 | 2 | 140 | 172 | 172 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 1179059 | 50000 | 1129059 | 1271899 | 1054894 | 0 | 0 | 0 | 1054894 | 1044236 | 92.49% | 1 | 0 | 92840 | 19 | 13 | 0 | 0 | 4792 | 0 | 0 | 0 | 82183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86975 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-06-26 | QTR4 | 17/18 |  | 2017-12-09 | QTR2 | 17/18 | 509 | 1499217.1
| 05 | E5Y85 | 43465815201 | 2017-04-04 | QTR4 | 16/17 | 2 | 1 | 90 | 126 | 140 | 115.6% | 1 | -14 | 14 | 0 | 36 | 0 | 349962 | 16000 | 333962 | 365078 | 342181 | -15386 | 0 | -15386 | 326795 | 311679 | 93.33% | 1 | 0 | 15117 | 34 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-03-08 | QTR3 | 17/18 |  | 2017-11-21 | QTR2 | 17/18 | 515 | 361362.3
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 16 | 22 | 35 | 3669 | 5629 | 5408 | 75% | 12 | 221 | 40 | 0 | 1162 | 798 | 225645085 | 815000 | 224830085 | 236072794 | 236081533 | -270190 | 500000 | 229810 | 236311343 | 227803441 | 100% | 16 | -8280318 | 10427710 | 717 | 377 | 0 | 102 | 987475 | 271485 | 32 | 644 | 9307082 | 67996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 291247 | 3383 | 0 | 0 | 394803 | 223994 | 0 | 0 | 0 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -497895 | 0 | 33 | 746 | 10487238 | 566858
| District 05 Totals |  |  |  |  | 50 | 84 | 112 | 11360 | 15570 | 15366 | 84% | 42 | 204 | 404 | 0 | 3081 | 1129 | 352116645 | 2662900 | 349453745 | 364346810 | 363544736 | -688175 | 816000 | 127825 | 363672560 | 351140343 | 98% | 49 | -12011473 | 12206163 | 1982 | 1009 | 0 | 228 | 1902808 | 286008 | 54 | 806 | 9933074 | 67996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 72 | 1125754 | 3383 | 0 | 0 | 413547 | 223994 | 0 | 0 | -20240 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 42906 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | -838884 | 0 | 55 | 1077 | 12563489 | 581381
| 06 | T6345 | 24994165201 | 2014-06-25 | QTR4 | 13/14 | 2 | 5 | 780 | 859 | 754 | 87.69% | 1 | 105 | 0 | 0 | 70 | 9 | 20210987 | 648000 | 19562987 | 20241085 | 19700200 | 0 | 800000 | 800000 | 20500200 | 19298493 | 98.65% | 1 | -1201707 | 30098 | 51 | 19 | 0 | 0 | 325806 | 0 | 0 | 0 | 277026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5947 | 0 | 0 | 0 | 8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -422785 | 0 | 0 | 9 | 196909 | 0 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2017-09-19 | QTR1 | 17/18 |  | 2017-01-27 | QTR3 | 16/17 | 606 | 19907818.44 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6349 | 42916225201 | 2016-04-27 | QTR4 | 15/16 | 2 | 7 | 240 | 263 | 195 | 71.67% | 1 | 68 | 0 | 0 | 23 | 0 | 4178283 | 50000 | 4128283 | 4236996 | 3850525 | 0 | 160000 | 160000 | 4010525 | 3858312 | 93.46% | 1 | -152213 | 58713 | 14 | 9 | 0 | 0 | 24297 | 0 | 0 | 0 | 74263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9298 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91182 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 |  | 2017-02-24 | QTR3 | 16/17 | 606 | 5124941.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6350 | 43080315201 | 2016-06-15 | QTR4 | 15/16 | 4 | 4 | 300 | 421 | 418 | 109% | 1 | 3 | 0 | 0 | 121 | 0 | 3626400 | 52820 | 3573580 | 3770876 | 3752395 | 0 | 0 | 0 | 3752395 | 3703553 | 103.6% | 1 | 11155 | 144476 | 63 | 28 | 30 | 0 | -6590 | 0 | 0 | 0 | 9941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53152 | 0 | 0 | 0 | 60998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 117500 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-06-01 | QTR4 | 17/18 |  | 2017-12-08 | QTR2 | 17/18 | 606 | 4489026.25
| 06 | T6375 | 43274325201 | 2015-10-28 | QTR2 | 15/16 | 4 | 3 | 350 | 402 | 390 | 96.57% | 1 | 12 | 0 | 0 | 52 | 0 | 9111715 | 113088 | 8998627 | 9340645 | 9186004 | 0 | 0 | 0 | 9186004 | 8941564 | 99.37% | 1 | -244440 | 138931 | 33 | 19 | 0 | 0 | 70119 | 0 | 0 | 0 | 14883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91211 | 0 | 0 | 0 | 2258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178471 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-11-17 | QTR2 | 17/18 |  | 2017-03-20 | QTR3 | 16/17 | 606 | 10922672.4 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6378 | 43080815201 | 2016-05-25 | QTR4 | 15/16 | 4 | 1 | 380 | 398 | 285 | 70.26% | 1 | 113 | 0 | 0 | 18 | 0 | 4890784 | 61235 | 4829549 | 4907164 | 4857632 | 0 | 240000 | 240000 | 5097632 | 4876249 | 101% | 1 | -221383 | 8190 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 15244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28308 | 0 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44872 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-03 | QTR4 | 17/18 |  | 2017-10-19 | QTR2 | 17/18 | 606 | 6041431.47 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6380 | 41462435201 | 2015-06-17 | QTR4 | 14/15 | 3 | 3 | 280 | 383 | 382 | 113.9% | 1 | 1 | 0 | 0 | 103 | 0 | 3520907 | 50505 | 3470402 | 3612854 | 3575998 | 0 | 56000 | 56000 | 3631998 | 3498466 | 100.8% | 1 | -133532 | 91947 | 47 | 16 | 0 | 0 | 1588 | 0 | 40 | 0 | 82138 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 83726 | 8200 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 |  | 2017-01-20 | QTR3 | 16/17 | 606 | 3771064.2 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6385 | 43326415201 | 2016-01-27 | QTR3 | 15/16 | 2 | 1 | 180 | 259 | 259 | 113.9% | 1 | 0 | 0 | 0 | 54 | 25 | 1122164 | 50070 | 1072094 | 1210753 | 1131145 | 0 | 0 | 0 | 1131145 | 1133153 | 105.7% | 1 | 2007 | 88590 | 37 | 17 | 0 | 0 | 17204 | 0 | 0 | 25 | 90738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 107942 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-04-04 | QTR4 | 16/17 | 606 | 1217718.2
| 06 | T6387 | 43477215201 | 2016-12-07 | QTR2 | 16/17 | 4 | 0 | 100 | 112 | 100 | 88% | 1 | 12 | 0 | 0 | 12 | 0 | 397288 | 22666 | 374622 | 397288 | 368073 | 0 | 0 | 0 | 368073 | 368073 | 98.25% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5157 | 0 | 0 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9217 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-10-03 | QTR2 | 17/18 |  | 2017-08-08 | QTR1 | 17/18 | 606 | 422434
| 06 | T6391 | 43349215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 180 | 208 | 208 | 100% | 1 | 0 | 0 | 0 | 28 | 0 | 1155673 | 47446 | 1108227 | 1155673 | 1091324 | 0 | 0 | 0 | 1091324 | 1092555 | 98.59% | 1 | 1230 | 0 | 11 | 17 | 0 | 0 | 12008 | 0 | 0 | 0 | 2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21825 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 |  | 2017-05-21 | QTR4 | 16/17 | 606 | 983083.6
| 06 | T6405 | 42934625201 | 2016-03-30 | QTR3 | 15/16 | 3 | 1 | 160 | 216 | 215 | 99.38% | 1 | 1 | 0 | 0 | 56 | 0 | 1071254 | 50000 | 1021254 | 1073754 | 1058914 | 0 | 0 | 0 | 1058914 | 1062745 | 104.1% | 1 | 3831 | 2500 | 43 | 13 | 0 | 0 | 3296 | 0 | 0 | 0 | 3287 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5133 | 0 | 0 | 0 | 2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14682 | 787 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 |  | 2017-04-28 | QTR4 | 16/17 | 606 | 1077071.2
| 06 | T6439 | 43476615201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 70 | 79 | 79 | 100% | 1 | 0 | 0 | 0 | 9 | 0 | 230856 | 17085 | 213771 | 230856 | 202885 | 0 | 0 | 0 | 202885 | 202885 | 94.91% | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-05-24 | QTR4 | 17/18 |  | 2018-04-04 | QTR4 | 17/18 | 606 | 346258.1
| 06 | T9018 | 43676425201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 50 | 51 | 51 | 100% | 1 | 0 | 0 | 0 | 1 | 0 | 1124592 | 49000 | 1075592 | 1124592 | 1064750 | 0 | 0 | 0 | 1064750 | 1064750 | 98.99% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-06-08 | QTR4 | 17/18 |  | 2018-02-27 | QTR3 | 17/18 | 606 | 1110084.56
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 12 | 32 | 25 | 3070 | 3651 | 3336 | 100% | 12 | 315 | 0 | 0 | 547 | 34 | 50640903 | 1211915 | 49428988 | 51302536 | 49839845 | 0 | 1256000 | 1256000 | 51095845 | 49100798 | 100% | 12 | -1935052 | 563445 | 329 | 148 | 30 | 0 | 447728 | 0 | 40 | 25 | 573397 | 8987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187019 | 0 | 0 | 0 | 78085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -422785 | 0 | 70 | 34 | 866326 | 8987
| 06 | E6J00 | 43540715201 | 2015-01-29 | QTR3 | 14/15 | 1 | 0 | 790 | 794 | 791 | 99.62% | 1 | 3 | 0 | 0 | 4 | 0 | 204491 | 11179 | 193312 | 204491 | 200808 | 0 | 0 | 0 | 200808 | 200808 | 103.9% | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | F650817669 | FLORIDA TURF AND LANDSCAPE HORTICULTURE | N/A | N/A | N/A | N/A | 2017-08-17 | QTR1 | 17/18 |  | 2017-07-24 | QTR1 | 17/18 | 606 | 234759 | B0 | ACC - LUMP SUM
| 06 | E6J27 | 43325415201 | 2015-10-29 | QTR2 | 15/16 | 1 | 1 | 240 | 364 | 364 | 100% | 1 | 0 | 0 | 0 | 124 | 0 | 874736 | 43765 | 830971 | 839120 | 814919 | 0 | 0 | 0 | 814919 | 814919 | 98.07% | 1 | 0 | -35616 | 105 | 19 | 0 | 0 | 10698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35616 | 0 | 0 | 0 | -24918 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2017-07-18 | QTR1 | 17/18 |  | 2017-04-26 | QTR4 | 16/17 | 606 | 895054.75
| 06 | E6J41 | 43444315201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 70 | 77 | 77 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 220419 | 11619 | 208800 | 220419 | 208800 | 0 | 0 | 0 | 208800 | 208800 | 100% | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2017-09-06 | QTR1 | 17/18 |  | 2017-04-23 | QTR4 | 16/17 | 606 | 249619 | B0 | ACC - LUMP SUM
| 06 | E6J44 | 43468115201 | 2016-05-26 | QTR4 | 15/16 | 1 | 1 | 240 | 317 | 257 | 75% | 1 | 60 | 0 | 0 | 77 | 0 | 979602 | 50000 | 929602 | 823480 | 746877 | 0 | 0 | 0 | 746877 | 746877 | 80.34% | 1 | 0 | -156122 | 57 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | -156122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -156122 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 |  | 2017-06-09 | QTR4 | 16/17 | 606 | 1105870
| 06 | E6J47 | 43471015201 | 2016-03-31 | QTR3 | 15/16 | 2 | 2 | 300 | 503 | 493 | 106.7% | 1 | 10 | 0 | 0 | 173 | 30 | 1421464 | 50000 | 1371464 | 1931498 | 1949242 | 0 | 0 | 0 | 1949242 | 1896702 | 138.3% | 0 | 0 | 510034 | 138 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 457493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 457493 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2018-05-10 | QTR4 | 17/18 |  | 2017-12-06 | QTR2 | 17/18 | 606 | 1476116
| 06 | E6J56 | 43550619201 | 2015-12-02 | QTR2 | 15/16 | 1 | 1 | 460 | 512 | 502 | 97.83% | 1 | 10 | 0 | 0 | 52 | 0 | 3827963 | 50000 | 3777963 | 3877963 | 3862070 | 0 | 0 | 0 | 3862070 | 0 | 0% | 1 | -3862070 | 50000 | 29 | 23 | 0 | 0 | 49710 | 19018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3878 | 0 | 0 | 0 | 7133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99707 | 19018 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-01-26 | QTR3 | 17/18 |  | 2017-06-30 | QTR4 | 16/17 | 606 | 3497921 | A3 | ICC - DESIGN/BUILD - MINOR
| 06 | E6J75 | 43652815201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 215 | 220 | 132 | 59.07% | 1 | 88 | 0 | 0 | 5 | 0 | 847200 | 50000 | 797200 | 847200 | 789681 | 0 | 0 | 0 | 789681 | 789681 | 99.06% | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-08-15 | QTR1 | 17/18 |  | 2017-06-20 | QTR4 | 16/17 | 606 | 1102468.5
| 06 | E6J76 | 43652915201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 180 | 234 | 220 | 92.22% | 1 | 14 | 0 | 0 | 54 | 0 | 588728 | 36323 | 552405 | 588728 | 477515 | 0 | 0 | 0 | 477515 | 477515 | 86.44% | 1 | 0 | 0 | 37 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2017-05-08 | QTR4 | 16/17 | 606 | 756279.75
| 06 | E6K21 | 42914635201 | 2016-07-28 | QTR1 | 16/17 | 1 | 0 | 100 | 107 | 105 | 98% | 1 | 2 | 0 | 0 | 7 | 0 | 177943 | 9346 | 168597 | 177943 | 173203 | 0 | 0 | 0 | 173203 | 173203 | 102.7% | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2017-07-13 | QTR1 | 17/18 |  | 2017-06-12 | QTR4 | 16/17 | 606 | 196223.5
| 06 | E6K22 | 42521625201 | 2016-07-28 | QTR1 | 16/17 | 3 | 3 | 210 | 315 | 305 | 95.24% | 1 | 10 | 0 | 0 | 105 | 0 | 1343144 | 50000 | 1293144 | 1349051 | 1259511 | 0 | 0 | 0 | 1259511 | 1245107 | 96.29% | 1 | -6083 | 5907 | 75 | 30 | 0 | 0 | -2413 | 0 | 0 | 0 | 26451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40253 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-06-04 | QTR4 | 17/18 |  | 2018-01-25 | QTR3 | 17/18 | 606 | 1605334.2
| 06 | E6K28 | 42563735201 | 2017-03-30 | QTR3 | 16/17 | 2 | 0 | 80 | 136 | 134 | 97.5% | 1 | 2 | 0 | 0 | 56 | 0 | 179971 | 12916 | 167055 | 179971 | 164916 | 0 | 0 | 0 | 164916 | 164916 | 98.72% | 1 | 0 | 0 | 38 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-30 | QTR3 | 17/18 |  | 2018-01-16 | QTR3 | 17/18 | 606 | 267547.25
| 06 | E6K31 | 42934635201 | 2016-08-25 | QTR1 | 16/17 | 1 | 0 | 140 | 162 | 145 | 87.86% | 1 | 17 | 0 | 0 | 22 | 0 | 999395 | 50000 | 949395 | 999395 | 975146 | 0 | 0 | 0 | 975146 | 975806 | 102.8% | 1 | 660 | 0 | 19 | 3 | 0 | 0 | 9015 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31215 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 |  | 2017-06-30 | QTR4 | 16/17 | 606 | 1051398.75
| 06 | E6K49 | 43058825201 | 2016-09-29 | QTR1 | 16/17 | 2 | 0 | 140 | 187 | 187 | 100% | 1 | 0 | 0 | 0 | 47 | 0 | 864202 | 42202 | 822000 | 864202 | 790596 | 0 | 0 | 0 | 790596 | 790888 | 96.22% | 1 | 292 | 0 | 42 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2017-09-18 | QTR1 | 17/18 |  | 2017-07-28 | QTR1 | 17/18 | 606 | 885402 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 13 | 18 | 8 | 3165 | 3928 | 3712 | 100% | 13 | 216 | 0 | 0 | 733 | 30 | 12529258 | 467350 | 12061908 | 12903461 | 12413284 | 0 | 0 | 0 | 12413284 | 8485222 | 92.31% | 12 | -3867201 | 374203 | 557 | 176 | 0 | 0 | 67010 | 19018 | 0 | 0 | -109121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25186 | 0 | 0 | 30 | 464626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35616 | 0 | 0 | 30 | 451070 | 19018
| District 06 Totals |  |  |  |  | 25 | 50 | 33 | 6235 | 7579 | 7048 | 100% | 25 | 531 | 0 | 0 | 1280 | 64 | 63170161 | 1679265 | 61490896 | 64205997 | 62253129 | 0 | 1256000 | 1256000 | 63509129 | 57586020 | 96% | 24 | -5802253 | 937648 | 886 | 324 | 30 | 0 | 514738 | 19018 | 40 | 25 | 464276 | 8987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212205 | 0 | 0 | 30 | 542711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38988 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -458401 | 0 | 70 | 64 | 1317396 | 28005
| 07 | T7220 | 40845925201 | 2011-06-29 | QTR4 | 10/11 | 6 | 63 | 1500 | 1779 | 1779 | 102.8% | 1 | 0 | 0 | 0 | 237 | 42 | 94696203 | 150000 | 94546203 | 99221504 | 102513161 | -176000 | 0 | -176000 | 102337161 | 101152204 | 107% | 1 | -1016777 | 4525301 | 164 | 73 | 0 | 0 | 1140417 | 444656 | 0 | 0 | 638567 | 94458 | 0 | 0 | 0 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2636702 | 157507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347209 | 54885 | 0 | 0 | 0 | 0 | 0 | 0 | 4136 | 4136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 4335071 | 755643 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-07-07 | QTR1 | 17/18 |  | 2016-08-26 | QTR1 | 16/17 | 714 | 107019759.03
| 07 | T7322 | 42292925201 | 2013-06-19 | QTR4 | 12/13 | 1 | 0 | 153 | 321 | 607 | 301.3% | 0 | -286 | 286 | 0 | 146 | 22 | 756468 | 47620 | 708848 | 756468 | 713772 | -356956 | 0 | -356956 | 356816 | 356816 | 50.34% | 1 | 0 | 0 | 137 | 9 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 11372 | 0 | F331064425 | CIVIL SITE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-02-13 | QTR3 | 17/18 |  | 2015-09-04 | QTR1 | 15/16 | 717 | 983979
| 07 | T7346 | 43089815201 | 2014-07-30 | QTR1 | 14/15 | 1 | 5 | 390 | 599 | 599 | 110% | 1 | 0 | 0 | 0 | 170 | 39 | 6794444 | 62000 | 6732444 | 6864518 | 7093818 | 0 | 0 | 0 | 7093818 | 6785751 | 100.8% | 1 | -308067 | 70073 | 144 | 26 | 0 | 17 | 18684 | 0 | 0 | 22 | 128610 | 6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 112644 | 6122 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 |  | 2016-08-25 | QTR1 | 16/17 | 717 | 6553700
| 07 | T7349 | 43124315201 | 2014-06-18 | QTR4 | 13/14 | 2 | 5 | 400 | 654 | 652 | 113.8% | 1 | 2 | 0 | 0 | 203 | 51 | 12544444 | 119000 | 12425444 | 12706570 | 13012776 | 0 | 0 | 0 | 13012776 | 12421061 | 99.96% | 1 | -591715 | 162125 | 167 | 30 | 6 | 11 | 89297 | 0 | 0 | 40 | 77646 | 16339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15383 | 15383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 51 | 182326 | 31722 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-31 | QTR1 | 17/18 |  | 2016-10-25 | QTR2 | 16/17 | 798 | 12199500
| 07 | T7377 | 42453295201 | 2016-02-24 | QTR3 | 15/16 | 3 | 6 | 260 | 309 | 309 | 101.2% | 1 | 0 | 0 | 0 | 46 | 3 | 2482901 | 50000 | 2432901 | 2542403 | 2373194 | 0 | 0 | 0 | 2373194 | 2384196 | 98% | 1 | 11002 | 59502 | 25 | 21 | 0 | 3 | 56002 | 0 | 0 | 0 | 8532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 64535 | 0 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-07-25 | QTR1 | 17/18 |  | 2017-05-17 | QTR4 | 16/17 | 709 | 2246000
| 07 | T7381 | 25589335201 | 2016-05-25 | QTR4 | 15/16 | 2 | 1 | 200 | 284 | 284 | 114% | 1 | 0 | 0 | 0 | 56 | 28 | 4590182 | 55000 | 4535182 | 4640182 | 4586377 | 0 | 0 | 0 | 4586377 | 4603104 | 101.5% | 1 | 16727 | 50000 | 22 | 34 | 0 | 7 | 26821 | 0 | 0 | 0 | 14230 | 1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 57192 | 1901 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-09-27 | QTR1 | 17/18 |  | 2017-05-31 | QTR4 | 16/17 | 717 | 7190840.88
| 07 | T7397 | 43768715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 205 | 252 | 252 | 105.9% | 1 | 0 | 0 | 0 | 35 | 12 | 1352726 | 50000 | 1302726 | 1363694 | 1329902 | 0 | 0 | 0 | 1329902 | 1329961 | 102.1% | 1 | 11027 | 10968 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 12 | 3644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3644 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-05-17 | QTR4 | 17/18 |  | 2018-05-01 | QTR4 | 17/18 | 796 | 1620000
| 07 | T9019 | 44030915201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 42 | 65 | 65 | 114.3% | 1 | 0 | 0 | 0 | 23 | 0 | 106998 | 4233 | 102765 | 124900 | 124723 | 0 | 0 | 0 | 124723 | 124723 | 121.4% | 0 | 0 | 17902 | 13 | 4 | 0 | 0 | 0 | 0 | 6 | 0 | 9550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 22102 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-01-22 | QTR3 | 17/18 |  | 2017-10-10 | QTR2 | 17/18 | 706 | 105779.7
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 8 | 17 | 83 | 3150 | 4263 | 4547 | 87.5% | 7 | -284 | 286 | 0 | 916 | 197 | 123324366 | 537853 | 122786513 | 128220239 | 131747723 | -532956 | 0 | -532956 | 131214767 | 129157816 | 87.5% | 7 | -1877803 | 4895871 | 687 | 217 | 6 | 38 | 1331221 | 444656 | 6 | 96 | 880779 | 118820 | 0 | 0 | 0 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2618194 | 157507 | 0 | 0 | 27935 | 15383 | 0 | 0 | 0 | 0 | 0 | 0 | 358581 | 54885 | 0 | 0 | 0 | 0 | 0 | 21 | 4136 | 4136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 197 | 4788886 | 795388
| 07 | E7I69 | 41868515201 | 2014-06-11 | QTR4 | 13/14 | 2 | 16 | 500 | 714 | 714 | 119.8% | 1 | 0 | 0 | 0 | 115 | 99 | 8338093 | 57000 | 8281093 | 9034910 | 9761980 | 0 | 0 | 0 | 9761980 | 9649830 | 116.5% | 0 | -112150 | 696817 | 41 | 74 | 0 | 99 | 441414 | 190338 | 0 | 0 | 344754 | 73724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45110 | 0 | 0 | 0 | 9744 | 4974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006 | 3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 753808 | 272042 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-05-29 | QTR4 | 17/18 |  | 2016-12-08 | QTR2 | 16/17 | 717 | 6938454.99
| 07 | E7J74 | 42347415201 | 2014-08-13 | QTR1 | 14/15 | 1 | 3 | 450 | 654 | 653 | 99.78% | 1 | 1 | 0 | 0 | 204 | 0 | 5011920 | 50000 | 4961920 | 5193391 | 5076829 | 0 | 0 | 0 | 5076829 | 5076829 | 102.3% | 1 | 0 | 181471 | 160 | 44 | 0 | 0 | 12562 | 0 | 0 | 0 | 136458 | 0 | 0 | 0 | 32450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194400 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2018-03-02 | QTR3 | 17/18 |  | 2017-01-23 | QTR3 | 16/17 | 709 | 4749400
| 07 | E7J76 | 43075115201 | 2014-12-10 | QTR2 | 14/15 | 1 | 1 | 150 | 160 | 156 | 97.33% | 1 | 4 | 0 | 0 | 10 | 0 | 743784 | 39000 | 704784 | 740664 | 652729 | 0 | 0 | 0 | 652729 | 652689 | 92.61% | 1 | -40 | -3120 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3120 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2018-03-15 | QTR3 | 17/18 |  | 2015-08-18 | QTR1 | 15/16 | 709 | 860120
| 07 | E7K09 | 43376015201 | 2016-03-09 | QTR3 | 15/16 | 1 | 0 | 165 | 235 | 235 | 107.3% | 1 | 0 | 0 | 0 | 70 | 0 | 4858889 | 50000 | 4808889 | 4858889 | 4889946 | 0 | 0 | 0 | 4889946 | 4892719 | 101.7% | 1 | 2773 | 0 | 37 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 |  | 2017-01-20 | QTR3 | 16/17 | 798 | 4975480
| 07 | E7K13 | 43175035201 | 2014-11-26 | QTR2 | 14/15 | 2 | 0 | 360 | 765 | 765 | 100% | 1 | 0 | 0 | 0 | 405 | 0 | 5076080 | 55000 | 5021080 | 5076080 | 5350308 | 0 | 0 | 0 | 5350308 | 5348564 | 106.5% | 1 | -1744 | 0 | 358 | 47 | 0 | 0 | 13591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16458 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2017-10-24 | QTR2 | 17/18 |  | 2017-06-20 | QTR4 | 16/17 | 709 | 5778800
| 07 | E7K14 | 43571815201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 515 | 678 | 678 | 114.2% | 1 | 0 | 0 | 0 | 90 | 73 | 5520000 | 50000 | 5470000 | 5520000 | 5515787 | 0 | 0 | 0 | 5515787 | 5461492 | 99.84% | 1 | -54295 | 0 | 60 | 30 | 0 | 0 | 0 | 0 | 0 | 73 | 42916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 42916 | 0 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-08-23 | QTR1 | 17/18 |  | 2017-07-10 | QTR1 | 17/18 | 709 | 5318312 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
| 07 | E7K95 | 43655215201 | 2016-03-09 | QTR3 | 15/16 | 1 | 0 | 129 | 175 | 134 | 68.22% | 1 | 41 | 0 | 0 | 46 | 0 | 1999499 | 50000 | 1949499 | 1999499 | 1965163 | 0 | 0 | 0 | 1965163 | 1965188 | 100.8% | 1 | 25 | 0 | 42 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 27547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27547 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2017-11-13 | QTR2 | 17/18 |  | 2017-09-20 | QTR1 | 17/18 | 717 | 2583470
| 07 | E7K97 | 43149215201 | 2016-06-08 | QTR4 | 15/16 | 1 | 0 | 210 | 294 | 289 | 97.62% | 1 | 5 | 0 | 0 | 84 | 0 | 5498000 | 50000 | 5448000 | 5498000 | 5479166 | 0 | 0 | 0 | 5479166 | 5486336 | 100.7% | 1 | 7170 | 0 | 58 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-10-31 | QTR2 | 17/18 |  | 2017-08-31 | QTR1 | 17/18 | 717 | 5955000 | B0 | ACC - LUMP SUM
| 07 | E7L41 | 42550315201 | 2016-09-14 | QTR1 | 16/17 | 1 | 0 | 95 | 117 | 116 | 98.95% | 1 | 1 | 0 | 0 | 22 | 0 | 1429757 | 50000 | 1379757 | 1429757 | 1357101 | 0 | 0 | 0 | 1357101 | 1357101 | 98.36% | 1 | 0 | 0 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6201 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-10-27 | QTR2 | 17/18 |  | 2017-07-13 | QTR1 | 17/18 | 717 | 1539689.27
| 07 | E7L44 | 43269915201 | 2016-10-12 | QTR2 | 16/17 | 1 | 1 | 170 | 206 | 206 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 2181247 | 50000 | 2131247 | 2181247 | 2114949 | 0 | 0 | 0 | 2114949 | 2122813 | 99.6% | 1 | 7864 | 0 | 27 | 9 | 0 | 0 | 4670 | 0 | 0 | 0 | 1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5935 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-12-20 | QTR2 | 17/18 |  | 2017-09-22 | QTR1 | 17/18 | 709 | 2450000.36 | B0 | ACC - LUMP SUM
| 07 | E7L46 | 43473615201 | 2016-12-14 | QTR2 | 16/17 | 1 | 0 | 140 | 251 | 278 | 119.3% | 1 | -27 | 27 | 0 | 111 | 0 | 2644431 | 50000 | 2594431 | 2644431 | 2652518 | -75897 | 0 | -75897 | 2576621 | 2683911 | 103.4% | 1 | 107290 | 0 | 83 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 6922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6922 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-06-26 | QTR4 | 17/18 |  | 2018-02-23 | QTR3 | 17/18 | 717 | 3002164
| 07 | E7L48 | 43243215201 | 2017-01-11 | QTR3 | 16/17 | 1 | 1 | 120 | 211 | 221 | 114.2% | 1 | -10 | 10 | 0 | 84 | 7 | 658045 | 35000 | 623045 | 681845 | 622321 | -15840 | 0 | -15840 | 606481 | 606481 | 97.34% | 1 | 0 | 23800 | 76 | 8 | 0 | 7 | 44560 | 0 | 0 | 0 | 10563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 32843 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-03-28 | QTR3 | 17/18 |  | 2017-11-17 | QTR2 | 17/18 | 709 | 825000
| 07 | E7L57 | 43386515201 | 2017-03-08 | QTR3 | 16/17 | 1 | 0 | 65 | 65 | 49 | 75.38% | 1 | 16 | 0 | 0 | 0 | 0 | 284040 | 13500 | 270540 | 284040 | 270466 | 0 | 0 | 0 | 270466 | 270466 | 99.97% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2139 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-10-31 | QTR2 | 17/18 |  | 2017-09-21 | QTR1 | 17/18 | 717 | 320000 | B0 | ACC - LUMP SUM
| 07 | E7L63 | 43794015201 | 2017-03-08 | QTR3 | 16/17 | 1 | 1 | 120 | 144 | 144 | 100.8% | 1 | 0 | 0 | 0 | 23 | 1 | 1222291 | 45000 | 1177291 | 1228444 | 1182817 | 0 | 0 | 0 | 1182817 | 1182817 | 100.5% | 1 | 0 | 6153 | 20 | 3 | 0 | 1 | 4327 | 0 | 0 | 0 | 9637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 21223 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2017-12-27 | QTR2 | 17/18 |  | 2017-11-29 | QTR2 | 17/18 | 709 | 1198576.7
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 14 | 16 | 23 | 3189 | 4669 | 4638 | 100% | 14 | 31 | 37 | 0 | 1300 | 180 | 45466076 | 644500 | 44821576 | 46371197 | 46892080 | -91737 | 0 | -91737 | 46800343 | 46757236 | 92.86% | 13 | -43107 | 905121 | 985 | 303 | 0 | 107 | 523263 | 190338 | 0 | 73 | 596763 | 73724 | 0 | 0 | 32450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | -25174 | 0 | 0 | 0 | 9744 | 4974 | 0 | 0 | -22280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006 | 3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 180 | 1117772 | 272042
| District 07 Totals |  |  |  |  | 22 | 33 | 106 | 6339 | 8932 | 9185 | 95.45% | 21 | -253 | 323 | 0 | 2216 | 377 | 168790442 | 1182353 | 167608089 | 174591436 | 178639803 | -624693 | 0 | -624693 | 178015110 | 175915052 | 90.91% | 20 | -1920910 | 5800992 | 1672 | 520 | 6 | 145 | 1854484 | 634994 | 6 | 169 | 1477542 | 192544 | 0 | 0 | 32450 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 0 | 0 | 12 | 42 | 2593020 | 157507 | 0 | 0 | 37679 | 20357 | 0 | 0 | -22280 | 0 | 0 | 0 | 358581 | 54885 | 0 | 0 | 0 | 0 | 0 | 21 | 7142 | 7142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 377 | 5906658 | 1067430
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8M76 | 41548815201 | 2013-04-09 | QTR4 | 12/13 | 1 | 17 | 1035 | 1333 | 1333 | 112.9% | 1 | 0 | 0 | 0 | 221 | 77 | 40893455 | 100000 | 40793455 | 42793440 | 43780119 | 0 | 0 | 0 | 43780119 | 42891163 | 105.1% | 1 | -888956 | 1899985 | 111 | 53 | 0 | 4 | 388093 | 93242 | 21 | 73 | 1171105 | 320036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 425486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 77 | 1986212 | 413278 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2017-12-20 | QTR2 | 17/18 |  | 2017-04-14 | QTR4 | 16/17 | 854 | 44448235.6 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8N90 | 42815425201 | 2014-10-14 | QTR2 | 14/15 | 2 | 2 | 845 | 960 | 915 | 96.33% | 1 | 45 | 0 | 0 | 101 | 14 | 8152113 | 150000 | 8002113 | 8219090 | 7569664 | 0 | 0 | 0 | 7569664 | 7559469 | 94.47% | 1 | -10195 | 66977 | 48 | 53 | 0 | 14 | 96833 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | -15815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 90818 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-11-15 | QTR2 | 17/18 |  | 2017-08-04 | QTR1 | 17/18 | 854 | 10548406
| 08 | E8P07 | 43560915201 | 2016-05-10 | QTR4 | 15/16 | 1 | 5 | 310 | 394 | 394 | 111.3% | 1 | 0 | 0 | 0 | 84 | 0 | 3499824 | 50000 | 3449824 | 3949117 | 3984741 | 0 | 0 | 0 | 3984741 | 3986085 | 115.5% | 0 | 1344 | 449293 | 21 | 28 | 0 | 0 | 398537 | 0 | 0 | 0 | -23329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 109120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 484328 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-22 | QTR4 | 17/18 |  | 2018-01-31 | QTR3 | 17/18 | 854 | 3565669.46
| 08 | E8P83 | 43282615201 | 2016-03-22 | QTR3 | 15/16 | 2 | 1 | 250 | 312 | 312 | 100% | 1 | 0 | 0 | 0 | 62 | 0 | 12114000 | 150000 | 11964000 | 12052537 | 12086406 | 0 | 0 | 0 | 12086406 | 12136961 | 101.4% | 1 | 50556 | -61463 | 30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | -56714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40594 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-11-15 | QTR2 | 17/18 |  | 2017-05-08 | QTR4 | 16/17 | 854 | 13714087.19
| 08 | E8P84 | 43560415201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 215 | 250 | 250 | 106.5% | 1 | 0 | 0 | 0 | 21 | 14 | 1564634 | 50000 | 1514634 | 1564634 | 1570658 | 0 | 0 | 0 | 1570658 | 1593989 | 105.2% | 1 | 23332 | 0 | 4 | 17 | 0 | 0 | 8912 | 0 | 0 | 14 | 23635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 32548 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-25 | QTR1 | 17/18 |  | 2017-05-24 | QTR4 | 16/17 | 854 | 1798899.5
| 08 | E8P93 | 42933415201 | 2016-04-12 | QTR4 | 15/16 | 2 | 1 | 155 | 189 | 189 | 100% | 1 | 0 | 0 | 0 | 34 | 0 | 1627383 | 48815 | 1578568 | 1619754 | 1562111 | 0 | 0 | 0 | 1562111 | 1565726 | 99.19% | 1 | 3615 | -7629 | 14 | 20 | 0 | 0 | -1000 | 0 | 0 | 0 | 16722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18273 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-07 | QTR1 | 17/18 |  | 2017-04-05 | QTR4 | 16/17 | 854 | 1804452.94
| 08 | E8P94 | 43282715201 | 2016-05-24 | QTR4 | 15/16 | 5 | 2 | 425 | 523 | 519 | 99.06% | 1 | 4 | 0 | 0 | 98 | 0 | 11866804 | 150000 | 11716804 | 11967156 | 11316560 | -6500 | 0 | -6500 | 11310060 | 11338372.61 | 96.77% | 1 | 28313 | 100351 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 108976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5076 | 0 | 0 | 0 | 73350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187402 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2018-06-28 | QTR4 | 17/18 |  | 2018-02-08 | QTR3 | 17/18 | 854 | 13286145.15
| 08 | E8P96 | 43494625201 | 2016-05-24 | QTR4 | 15/16 | 3 | 1 | 175 | 190 | 187 | 98.29% | 1 | 3 | 0 | 0 | 15 | 0 | 938500 | 46648 | 891852 | 938500 | 828715 | 0 | 0 | 0 | 828715 | 828715 | 92.92% | 1 | 0 | 0 | 1 | 14 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 |  | 2017-05-12 | QTR4 | 16/17 | 854 | 988989.54
| 08 | E8Q16 | 43540615201 | 2016-10-18 | QTR2 | 16/17 | 1 | 1 | 280 | 304 | 273 | 88.93% | 1 | 31 | 0 | 0 | 24 | 0 | 2671430 | 77853 | 2593576 | 3119007 | 3032466 | 0 | 300000 | 300000 | 3332466 | 3032466 | 116.9% | 0 | -300000 | 447578 | 21 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447578 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-12-27 | QTR2 | 17/18 |  | 2017-11-02 | QTR2 | 17/18 | 854 | 8220798.85 | B10 | ACC - BONUS/INCENT/DISINCENT
| 08 | E8Q55 | 43914515201 | 2017-04-11 | QTR4 | 16/17 | 1 | 1 | 130 | 197 | 197 | 113.1% | 1 | 0 | 0 | 0 | 67 | 0 | 649649 | 33062 | 616587 | 670169 | 659765 | 0 | 0 | 0 | 659765 | 661830 | 107.3% | 1 | 2065 | 20520 | 33 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 20520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 20520 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2018-03-14 | QTR3 | 17/18 |  | 2018-01-17 | QTR3 | 17/18 | 854 | 849412.2
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 10 | 19 | 31 | 3820 | 4652 | 4569 | 0.002302% | 10 | 83 | 0 | 0 | 727 | 105 | 83977792 | 856378 | 83121413 | 86893404 | 86391205 | -6500 | 300000 | 293500 | 86684705 | 85594776.61 | 80% | 8 | -1089926 | 2915612 | 332 | 286 | 0 | 18 | 899375 | 93242 | 21 | 87 | 1267515 | 320036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 88 | 0 | 999565 | 0 | 0 | 0 | 73350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 105 | 3247085 | 413278
| District 08 Totals |  |  |  |  | 10 | 19 | 31 | 3820 | 4652 | 4569 | 100% | 10 | 83 | 0 | 0 | 727 | 105 | 83977792 | 856378 | 83121413 | 86893404 | 86391205 | -6500 | 300000 | 293500 | 86684705 | 85594776.61 | 80% | 8 | -1089926 | 2915612 | 332 | 286 | 0 | 18 | 899375 | 93242 | 21 | 87 | 1267515 | 320036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 88 | 0 | 999565 | 0 | 0 | 0 | 73350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 105 | 3247085 | 413278
| Statewide Central Let Contracts SubTotal |  |  |  |  | 174 | 298 | 470 | 42758 | 58215 | 59077 | 87.93% | 153 | -862 | 2208 | 0 | 13254 | 2203 | 922272924 | 10071645 | 912201289 | 950316202 | 949875400 | -4862024 | 5416900 | 554876 | 950430275 | 923867600 | 94.83% | 165 | -25791692 | 27856787 | 8500 | 3456 | 275 | 767 | 13134613 | 2504850 | 621 | 812 | 11371080 | 2308373 | 0 | 0 | 2457 | 0 | 0 | 22 | -448089 | 0 | 0 | 0 | 19300 | 0 | 198 | 449 | 7360873 | 758142 | 139 | 3 | 255485 | 71692 | 0 | 0 | -20240 | 0 | 11 | 12 | 1249921 | 105937 | 0 | 54 | 568239 | 141742 | 31 | 135 | 116604 | 70816 | 0 | 0 | 0 | 0 | 0 | -29 | -2798228 | 0 | 1275 | 2225 | 30812018 | 5961552
| Statewide District Let Contracts SubTotal |  |  |  |  | 122 | 173 | 191 | 27803 | 38519 | 37890 | 85.25% | 104 | 629 | 1009 | 0 | 8023 | 2693 | 681923471 | 6337301 | 675586171 | 745680560 | 741535853 | -2139746 | 2689500 | 549754 | 742085608 | 724953919.61 | 92.62% | 113 | -16474854 | 63710371 | 4959 | 2334 | 309 | 693 | 7051800 | 715257 | 263 | 1502 | 42947587 | 574721 | 0 | 0 | 32450 | 0 | 0 | 0 | -109085 | 0 | 0 | 0 | 42800 | 0 | 103 | 327 | 14169498 | 23650 | 20 | 52 | 1290556 | 228968 | 0 | 0 | -184397 | 0 | 0 | 12 | 222362 | 0 | 0 | 0 | 71967 | 32010 | 0 | 0 | 5557 | 3006 | 0 | 0 | 0 | 0 | 0 | 15 | -533511 | 0 | 695 | 2601 | 65007580 | 1577612
| Statewide Totals |  |  |  |  | 296 | 471 | 661 | 70561 | 96734 | 96967 | 86.82% | 257 | -233 | 3217 | 0 | 21277 | 4896 | 1604196395 | 16408946 | 1587787460 | 1695996762 | 1691411253 | -7001770 | 8106400 | 1104630 | 1692515883 | 1648821519.61 | 93.92% | 278 | -42266546 | 91567158 | 13459 | 5790 | 584 | 1460 | 20186413 | 3220107 | 884 | 2314 | 54318667 | 2883094 | 0 | 0 | 34907 | 0 | 0 | 22 | -557174 | 0 | 0 | 0 | 62100 | 0 | 301 | 776 | 21530371 | 781792 | 159 | 55 | 1546041 | 300660 | 0 | 0 | -204637 | 0 | 11 | 24 | 1472283 | 105937 | 0 | 54 | 640206 | 173752 | 31 | 135 | 122161 | 73822 | 0 | 0 | 0 | 0 | 0 | -14 | -3331739 | 0 | 1970 | 4826 | 95819598 | 7539164

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1L76 | 43193815201 | F593374298 | EMPOWER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2013-03-21 | 775601 | 775601 | 267269 | 0 | -89053 | 256487 | 0 | 0 | -89053 | 0 | 0 | 0 | -89053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -89053 | 178216 | 256487 | 78271 | 826590 | B0 | ACC - LUMP SUM
1 | E1N91 | 43526915201 | F381807765 | DOUGLAS N. HIGGINS INC. | N/A | N/A | N/A | N/A | 2015-04-16 | 1423170 | 2060086 | 1941361 | 636916.13 | 0 | 1938507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1941361 | 1938507 | -2854 | 875885
1 | E1O46 | 43654515201 | F730764097 | MANHATTAN ROAD & BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2015-11-19 | 704333 | 763036 | 748922 | 58702.5 | 0 | 748922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748922 | 748922 | 0 | 529268
1 | E1O47 | 43170315201 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2016-01-28 | 2080080 | 2080080 | 2081575 | 0 | 0 | 2082167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081575 | 2082167 | 592 | 2823451
1 | E1O50 | 43121215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-06-14 | 2473492 | 2473492 | 2430162 | 0 | 0 | 2431258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430162 | 2431258 | 1097 | 2383341 | B0 | ACC - LUMP SUM
1 | E1O53 | 43486515201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-12-17 | 1972999 | 2017226 | 2027670 | 44227.39 | 0 | 2027844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027670 | 2027844 | 174 | 1579998
1 | E1O56 | 42799515201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2015-05-21 | 6985880 | 7218308 | 7107622 | 232428.02 | 0 | 6945376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7107622 | 6945376 | -162246 | 7866883 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1O77 | 43120815201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2016-05-19 | 5170633 | 5203293 | 5192938 | 32660 | 366000 | 5199260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366000 | 0 | 366000 | 366000 | 5558938 | 5199260 | -359678 | 7193789 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1O89 | 42731525201 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2016-04-01 | 2744297 | 2808760 | 2758760 | 64463.19 | 0 | 2758760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2758760 | 2758760 | 0 | 2744297 | B8 | ACC - DESIGN/BUILD - MAJOR
1 | E1P55 | 43476215201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2016-04-21 | 16187341 | 16450162 | 16170719 | 262820.98 | 950000 | 16247980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 0 | 950000 | 950000 | 17120719 | 16247980 | -872739 | 17171780 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1P64 | 43172315201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-08-18 | 829730 | 829730 | 788000 | 0 | 0 | 788000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788000 | 788000 | 0 | 915007 | B0 | ACC - LUMP SUM
1 | E1P83 | 43496015201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-01-19 | 884000 | 884000 | 845823 | 0 | 0 | 845823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 845823 | 845823 | 0 | 915852 | B0 | ACC - LUMP SUM
1 | E1P84 | 43494015201 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2016-11-17 | 2940436 | 2940436 | 2909678 | 0 | 0 | 2924839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909678 | 2924839 | 15161 | 3425094
1 | E1P85 | 43507115201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-11-17 | 1782010 | 1785646 | 1738365 | 3635.58 | 0 | 1742008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738365 | 1742008 | 3643 | 1557494 | B0 | ACC - LUMP SUM
1 | E1P86 | 43496115201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-12-15 | 1418298 | 1437032 | 1407750 | 18734.8 | 0 | 1407687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1407750 | 1407687 | -63 | 1330643 | B0 | ACC - LUMP SUM
1 | E1P88 | 43486015201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-01-31 | 2696196 | 2716814 | 2562828 | 20617.93 | 0 | 2565835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2562828 | 2565835 | 3007 | 3341250 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1P89 | 43692015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-12-15 | 5605151 | 6085870 | 5887019 | 480718.61 | 0 | 5990570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5887019 | 5990570 | 103551 | 6393089
1 | E1P93 | 43663815201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-01-19 | 2271296 | 2325270 | 2285617 | 53974.26 | 0 | 2305274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2285617 | 2305274 | 19656 | 2620650 | B0 | ACC - LUMP SUM
1 | E1Q60 | 43614515201 | F464740152 | CATHCART CONSTRUCTION COMPANY - FLORIDA | N/A | N/A | N/A | N/A | 2017-06-15 | 1652714 | 1652714 | 1595287 | 0 | 0 | 1598410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1595287 | 1598410 | 3123 | 874718
1 | E1Q63 | 44095315201 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2017-04-20 | 110918 | 110918 | 101322 | 0 | 0 | 101322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101322 | 101322 | 0 | 179086 | B0 | ACC - LUMP SUM
1 | E1Q84 | 43861715201 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2017-06-15 | 325029 | 325029 | 252626 | 0 | 0 | 256076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252626 | 256076 | 3450 | 138637 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | E1Q92 | 43495715201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-05-18 | 218056 | 218056 | 191926 | 0 | 25000 | 191926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 25000 | 216926 | 191926 | -25000 | 167847 | B1 | ACC - NO EXCUSE BONUS
1 | T1330 | 19571825201 | F272587735 | CONALVIAS USA LLC | N/A | N/A | N/A | N/A | 2012-06-20 | 22148030 | 24020348 | 23810851 | 1872318.48 | 0 | 23564595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23810851 | 23564595 | -246257 | 21275691
1 | T1417 | 41612015201 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2011-12-07 | 12691971 | 13256420 | 13055581 | 564449.7 | -656700 | 12402265 | -656700 | 0 | 0 | 0 | 0 | 0 | -656700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -656700 | 12398881 | 12402265 | 3384 | 11408242
1 | T1598 | 41304425201 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2015-07-29 | 72913523 | 73524079 | 72400941 | 610555.91 | 3448000 | 70319117 | 0 | 0 | 0 | 0 | 0 | -52000 | -52000 | 3500000 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3448000 | 75848941 | 70319117 | -5529824 | 87450436 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
1 | T1625 | 42988315201 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2016-06-15 | 1852000 | 1866275 | 1867608 | 14275 | 0 | 1867700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1867608 | 1867700 | 92 | 2064220
1 | T1628 | 43011915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-01-27 | 5092548 | 5147816 | 5084411 | 55268.23 | 0 | 5074685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5084411 | 5074685 | -9725 | 5336137
1 | T1631 | 43327215201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2016-04-27 | 1451189 | 1460304 | 1516711 | 9115.24 | 0 | 1516711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1516711 | 1516711 | 0 | 1389366
1 | T1647 | 43131615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-02-24 | 14344879 | 14807906 | 14762958 | 405870.1 | 0 | 14868237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14762958 | 14868237 | 105279 | 14324216
1 | T1648 | 43448915201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2016-08-31 | 910955 | 949740 | 949740 | 38784.28 | 0 | 949740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949740 | 949740 | 0 | 910040 | B0 | ACC - LUMP SUM
1 | T1652 | 43356215201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 1849592 | 1849592 | 1707344 | 0 | 0 | 1709115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1707344 | 1709115 | 1771 | 1373813
1 | T1655 | 43507515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 4645998 | 4644998 | 4654697 | -1000 | 0 | 4670541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4654697 | 4670541 | 15844 | 4668696 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1658 | 43902815201 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2016-06-15 | 2041864 | 2041864 | 1925079 | 0 | 0 | 1925198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925079 | 1925198 | 118 | 4696300
1 | T1661 | 43450815201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 1347647 | 1408422 | 1434774 | 60774.74 | 0 | 1373999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1434774 | 1373999 | -60775 | 1203312
1 | T1662 | 43132515201 | F452357137 | YD WEST COAST HOME INC | N/A | N/A | N/A | N/A | 2016-07-27 | 150000 | 150000 | 141366 | 0 | -6706 | 134660 | -6706 | 0 | 0 | 0 | 0 | 0 | -6706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6706 | 134660 | 134660 | 0 | 195238 | B0 | ACC - LUMP SUM
1 | T1663 | 43502515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-31 | 2395063 | 2800850 | 2741389 | 405786.69 | 0 | 2752214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2741389 | 2752214 | 10825 | 2399073 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
1 | T1668 | 43450715201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 860000 | 860000 | 810000 | 0 | 0 | 810000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810000 | 810000 | 0 | 1005380 | B0 | ACC - LUMP SUM
1 | T1677 | 43450615201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 681681 | 697653 | 645164 | 15971.92 | 0 | 645164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645164 | 645164 | 0 | 692725 | B0 | ACC - LUMP SUM
1 | T1679 | 43660115201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-05-24 | 2015831 | 2015831 | 1984899 | 0 | 0 | 2016886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1984899 | 2016886 | 31987 | 1987461 | B0 | ACC - LUMP SUM
1 | T1680 | 43092215201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-03-29 | 206428 | 206428 | 206428 | 0 | 0 | 206428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206428 | 206428 | 0 | 236687 | B0 | ACC - LUMP SUM
1 | T1681 | 43318115201 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-03-29 | 427415 | 427415 | 422004 | 0 | 0 | 422004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422004 | 422004 | 0 | 348089 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
1 | T1682 | 43496215201 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2017-05-24 | 1775437 | 1781028 | 1655773 | 5590.99 | 0 | 1662560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1655773 | 1662560 | 6786 | 1722624
1 | T1689 | 43470715201 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2017-09-27 | 553926 | 553926 | 528125 | 0 | 0 | 528125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528125 | 528125 | 0 | 582898 | B0 | ACC - LUMP SUM
1 | T1691 | 43654615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-26 | 153287 | 153287 | 147222 | 0 | 0 | 147222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147222 | 147222 | 0 | 115132 | B0 | ACC - LUMP SUM
1 | T1695 | 43320115201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 324149 | 324149 | 315985 | 0 | 0 | 315985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315985 | 315985 | 0 | 310285 | B0 | ACC - LUMP SUM
1 | T1696 | 43668115201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2017-08-30 | 117983 | 117983 | 110528 | 0 | 0 | 110528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110528 | 110528 | 0 | 105146
1 | T1998 | 42271025201 | F650507332 | GUYMANN CONSTRUCTION OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 31131016 | 31906922 | 31516260 | 775905.76 | 0 | 29940144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31516260 | 29940144 | -1576116 | 37523290 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
1 | T1A01 | 43134015201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2016-07-27 | 1006260 | 1032806 | 969407 | 26545.55 | 0 | 980874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969407 | 980874 | 11467 | 1134237
1 | T1A06 | 42910315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2014-12-03 | 2539891 | 2539891 | 2578009 | 0 | 0 | 2497434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2578009 | 2497434 | -80575 | 2442140
1 | T9013 | 43700115201 | F030586197 | R.M. WILLIAMS CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 1965358 | 2093858 | 2090482 | 128500 | 0 | 2090564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2090482 | 2090564 | 83 | 2398811
2 | E2R19 | 20960715201 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2013-12-12 | 44244000 | 44497660 | 44485464 | 253660.05 | 0 | 43929908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44485464 | 43929908 | -555556 | 49888540 | B8 | ACC - DESIGN/BUILD - MAJOR
2 | E2R22 | 43264115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-04-25 | 23839013 | 25517586 | 25531336 | 1678573.06 | -153064 | 24766329 | -153064 | 0 | 0 | 0 | 0 | 0 | -153064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -153064 | 25378272 | 24766329 | -611943 | 22387890 | LBDB | LOW BID DESIGN BUILD
2 | E2R95 | 42889935201 | F161659018 | CORE CONSTRUCTION COMPANY OF JA | N/A | N/A | N/A | N/A | 2013-06-19 | 483500 | 483500 | 483510 | 0 | -134757 | 348753 | -134757 | 0 | 0 | 0 | 0 | 0 | -134757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -134757 | 348753 | 348753 | 0 | 448242 | A3 | ICC - DESIGN/BUILD - MINOR
2 | E2T29 | 43055915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-11-13 | 4199999 | 4199999 | 4314349 | 0 | -112164 | 3826662 | -112164 | 0 | 0 | 0 | 0 | 0 | -112164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -112164 | 4202185 | 3826662 | -375523 | 4057259
2 | E2T50 | 43044915201 | F593114052 | K.V.K. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-03-15 | 606000 | 609005 | 554175 | 1502.64 | 0 | 552672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554175 | 552672 | -1503 | 649753 | B3 | ACC - LANE RENTAL
2 | E2U33 | 43195815201 | F591809068 | WEST CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2015-06-30 | 3436656 | 3327571 | 3278414 | -109085.45 | 0 | 3274966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3278414 | 3274966 | -3448 | 3590760
2 | E2U37 | 43075615201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-03-16 | 1152620 | 1152620 | 1092925 | 0 | 0 | 1092925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1092925 | 1092925 | 0 | 1021842
2 | E2U38 | 43226615201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-03-16 | 1729034 | 1814284 | 1787276 | 85250 | 0 | 1798954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 2261729
2 | E2U50 | 20968615201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2016-05-18 | 1697762 | 1697762 | 1628431 | 0 | 0 | 1628433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628431 | 1628433 | 2 | 1682497
2 | E2U92 | 43015715201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2016-03-16 | 4567769 | 4567769 | 4034344 | 0 | 0 | 4034680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4034344 | 4034680 | 336 | 3766652
2 | E2V03 | 43242015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-05-18 | 1065911 | 1065911 | 1003076 | 0 | 0 | 1005142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1003076 | 1005142 | 2066 | 900493
2 | E2V25 | 43432015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-11-29 | 2345000 | 2419896 | 2450882 | 74895.65 | -26928 | 2449808 | -26928 | 0 | 0 | 0 | 0 | 0 | -26928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26928 | 2423954 | 2449808 | 25854 | 2443365
2 | E2V31 | 43434115201 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2016-11-29 | 203115 | 203115 | 185168 | 0 | -1916 | 183252 | -1916 | 0 | 0 | 0 | 0 | 0 | -1916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1916 | 183252 | 183252 | 0 | 215268
2 | E2V33 | 43430115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-12-21 | 2694175 | 2863300 | 2867453 | 169125.76 | 0 | 2906553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867453 | 2906553 | 39100 | 2907210
2 | E2V45 | 43526815201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-04-19 | 1232900 | 1315355 | 1289463 | 82454.78 | 0 | 1226466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1289463 | 1226466 | -62998 | 1032476 | B0 | ACC - LUMP SUM
2 | E2V61 | 43860215201 | F650213904 | CEDARS ELECTRO-MECHANICAL INC. | N/A | N/A | N/A | N/A | 2017-02-15 | 763644 | 770677 | 746279 | 7032.89 | 0 | 746279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 746279 | 746279 | 0 | 765325
2 | E2V68 | 43231415201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2017-05-17 | 949302 | 949302 | 919773 | 0 | 0 | 926046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 919773 | 926046 | 6273 | 1080182
2 | E2W54 | 43617115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-08-16 | 1207306 | 1207306 | 1108761 | 0 | 0 | 1126368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108761 | 1126368 | 17607 | 1296537
2 | E2W83 | 43617715201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-10-18 | 554774 | 554774 | 528314 | 0 | 0 | 529911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528314 | 529911 | 1597 | 689013
2 | T2426 | 20837325201 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2012-06-20 | 10147516 | 10201629 | 10315106 | 54112.5 | -1110928 | 8737450 | -1110928 | 0 | 0 | 0 | 0 | 0 | -1110928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1110928 | 9204178 | 8737450 | -466728 | 12049133
2 | T2482 | 20916875201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2013-06-19 | 20538005 | 21074264 | 21550372 | 536259.18 | 0 | 21142359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21550372 | 21142359 | -408013 | 20493068
2 | T2484 | 21086545201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2013-09-25 | 2500683 | 2484554 | 2410530 | -16129.13 | 0 | 2388453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2410530 | 2388453 | -22077 | 2639633
2 | T2515 | 21325915201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-05-07 | 10022616 | 10748841 | 11713560 | 726224.89 | 0 | 10970371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11713560 | 10970371 | -743189 | 10434763
2 | T2531 | 21308255201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 2996901 | 2996901 | 3018348 | 0 | -276096 | 2600555 | -276096 | 0 | 0 | 0 | 0 | 0 | -276096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -276096 | 2742252 | 2600555 | -141696 | 2497599
2 | T2548 | 20939965201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2014-08-27 | 14832876 | 14931694 | 15170352 | 98818.4 | 0 | 14252602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15170352 | 14252602 | -917750 | 15494259
2 | T2558 | 42880215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2014-09-24 | 11419267 | 11419267 | 11519213 | 0 | 0 | 9884932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11519213 | 9884932 | -1634281 | 11862914
2 | T2571 | 42307115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 23206023 | 23352096 | 23326424 | 146072.98 | 0 | 22086601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23326424 | 22086601 | -1239823 | 22349692
2 | T2578 | 43054215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 6197496 | 6197496 | 6219729 | 0 | 0 | 5902734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6219729 | 5902734 | -316995 | 5697731
2 | T2583 | 21311345201 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-06-17 | 6310104 | 6241152 | 6008764 | -68952.85 | -1425060 | 4949499 | -1425060 | 0 | 0 | 0 | 0 | 0 | -1425060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1425060 | 4583704 | 4949499 | 365795 | 5828459
2 | T2590 | 42880515201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-09-30 | 12627578 | 12627578 | 13136952 | 0 | 0 | 12671855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13136952 | 12671855 | -465097 | 13903211
2 | T2595 | 43273315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-08-26 | 14598877 | 14676873 | 13917260 | 77995.66 | 0 | 13357978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13917260 | 13357978 | -559281 | 14373837
2 | T2599 | 43726615201 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 1048048 | 1048048 | 985628 | 0 | 0 | 985628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985628 | 985628 | 0 | 1120328
2 | T2601 | 21166315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-10-28 | 3712278 | 3713235 | 3797768 | 956.68 | 0 | 3782265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3797768 | 3782265 | -15503 | 4020992
2 | T2607 | 43265615201 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2015-10-28 | 3726163 | 3942398 | 4032657 | 216234.8 | 0 | 3977766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4032657 | 3977766 | -54891 | 4078237
2 | T2615 | 43316425201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2016-04-27 | 1867840 | 1917840 | 1853345 | 50000 | 150000 | 1860008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000 | 150000 | 2003345 | 1860008 | -143337 | 2133961
2 | T2619 | 43265715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 985253 | 985253 | 900611 | 0 | 0 | 903976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900611 | 903976 | 3365 | 823384
2 | T2629 | 43056215201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 3955571 | 4118052 | 4040559 | 162481 | -43140 | 3949454 | -43140 | 0 | 0 | 0 | 0 | 0 | -43140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43140 | 3997419 | 3949454 | -47965 | 3564631
2 | T2634 | 43225615201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-07-27 | 956123 | 956123 | 910673 | 0 | -28512 | 882485 | -28512 | 0 | 0 | 0 | 0 | 0 | -28512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28512 | 882161 | 882485 | 323 | 1019428
2 | T2635 | 42470035201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 348154 | 348154 | 353179 | 0 | 0 | 353179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353179 | 353179 | 0 | 330104
2 | T2638 | 43500515201 | F030527982 | J D HINSON COMPANY | N/A | N/A | N/A | N/A | 2016-09-28 | 1148616 | 1148616 | 1092502 | 0 | 0 | 1092502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1092502 | 1092502 | 0 | 1088824
2 | T2639 | 41142415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 2159445 | 2188557 | 2084623 | 26764.02 | 0 | 2083980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084623 | 2083980 | -643 | 2356415
2 | T2640 | 43231315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-10-26 | 2804745 | 2804745 | 2745654 | 0 | 0 | 2752258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2745654 | 2752258 | 6604 | 2903615
2 | T2642 | 43430215201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 3380793 | 3380793 | 3079001 | 0 | 0 | 3097527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3079001 | 3097527 | 18526 | 3680246
2 | T2644 | 43429515201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 1424722 | 1424722 | 1389257 | 0 | 0 | 1391632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1389257 | 1391632 | 2374 | 1869641
2 | T2645 | 43429915201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 1921891 | 1921891 | 1921001 | 0 | 0 | 1933245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1921001 | 1933245 | 12244 | 1970516
2 | T2646 | 43231515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 4589348 | 4589348 | 4544001 | 0 | 0 | 4607510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4544001 | 4607510 | 63509 | 5170519
2 | T2649 | 43231115201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 3476169 | 3576658 | 3781425 | 100488.71 | 0 | 3833191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3781425 | 3833191 | 51766 | 4220270
2 | T2651 | 43226915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 5097026 | 5193738 | 5154184 | 96712.05 | 0 | 5199723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5154184 | 5199723 | 45540 | 5759395
2 | T2652 | 43226815201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 1128456 | 1178456 | 1132814 | 50000 | 0 | 1135885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1132814 | 1135885 | 3071 | 1228719
2 | T2653 | 43431815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 5848696 | 5848696 | 5842884 | 0 | 0 | 5902466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5842884 | 5902466 | 59582 | 7299512
2 | T2663 | 43431915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 7359482 | 7359482 | 7148275 | 0 | 0 | 7267943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7148275 | 7267943 | 119668 | 8368235
2 | T2664 | 43433015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-03-29 | 2052728 | 2052728 | 2009305 | 0 | 0 | 1996365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009305 | 1996365 | -12939 | 2080962
2 | T9015 | 43475815201 | F593504786 | ANGLIN CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-06-15 | 913111 | 913111 | 890230 | 0 | 0 | 890229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890230 | 890229 | -1 | 612984
3 | E3N16 | 42902475201 | F590840493 | GAC CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2014-12-19 | 16475693 | 16845905 | 16848483 | 370211.56 | 0 | 16712396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16848483 | 16712396 | -136086 | 16475693 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR
3 | E3N84 | 21876225201 | F592982651 | WILLIAMS INDUSTRIAL & MARINE I | N/A | N/A | N/A | N/A | 2016-07-14 | 531067 | 531067 | 486082 | 0 | -17424 | 468658 | -17424 | 0 | 0 | 0 | 0 | 0 | -17424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17424 | 468658 | 468658 | 0 | 761742
3 | E3O04 | 41768345201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-07-14 | 565668 | 565668 | 550555 | 0 | -90288 | 489412 | -90288 | 0 | 0 | 0 | 0 | 0 | -90288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -90288 | 460267 | 489412 | 29145 | 576618
3 | E3O86 | 43255215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-02-09 | 3759171 | 3953037 | 3874241 | 165066.59 | 0 | 3870780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3874241 | 3870780 | -3461 | 4804333
3 | E3P09 | 41767745201 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2016-07-14 | 1746205 | 1746205 | 1870829 | 0 | 0 | 1871101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1870829 | 1871101 | 272 | 1884983
3 | E3P11 | 43257215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-04-14 | 6922953 | 6922953 | 6941583 | 0 | 0 | 6966761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6941583 | 6966761 | 25178 | 6237409
3 | E3P12 | 43255515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-11-10 | 751984 | 801537 | 761553 | 49553.08 | 0 | 761553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 761553 | 761553 | 0 | 851593 | B0 | ACC - LUMP SUM
3 | E3P15 | 43255015201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2016-11-17 | 1296000 | 1296000 | 1281750 | 0 | 0 | 1293176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1281750 | 1293176 | 11426 | 1595361 | B0 | ACC - LUMP SUM
3 | E3P36 | 42358935201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-02-09 | 2450599 | 2476226 | 2317426 | 25627.51 | 0 | 2318029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2317426 | 2318029 | 604 | 1549642
3 | E3P46 | 43466815201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2017-06-08 | 557062 | 557062 | 546186 | 0 | -8400 | 537786 | 0 | 0 | 0 | 0 | 0 | -8400 | -8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8400 | 537786 | 537786 | 0 | 571964 | B0 | ACC - LUMP SUM
3 | E3P62 | 21787925201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-06-09 | 1094282 | 1094282 | 1014445 | 0 | 0 | 1015749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1014445 | 1015749 | 1305 | 1020237
3 | E3P74 | 22271315201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-06-09 | 916620 | 973642 | 931184 | 57021.58 | 0 | 931184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931184 | 931184 | 0 | 702427
3 | E3P75 | 43078615201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2016-07-14 | 2702301 | 2702301 | 2824495 | 0 | 0 | 2819950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2824495 | 2819950 | -4545 | 2591913
3 | E3P91 | 43460615201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-10-13 | 367076 | 367076 | 357176 | 0 | 0 | 357176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357176 | 357176 | 0 | 306636 | B0 | ACC - LUMP SUM
3 | E3Q09 | 43749615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-01-12 | 360470 | 360470 | 302941 | 0 | 0 | 302941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302941 | 302941 | 0 | 618735
3 | E3Q27 | 43626315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-07-13 | 1148724 | 1148724 | 1173198 | 0 | 0 | 1173198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1173198 | 1173198 | 0 | 1210000
3 | T3350 | 40716815201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2013-03-27 | 5692603 | 5867358 | 5901155 | 174754.38 | -138718 | 5819943 | -138718 | 0 | 0 | 0 | 0 | 0 | -138718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -138718 | 5762437 | 5819943 | 57505 | 5114305
3 | T3380 | 22067915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2012-05-23 | 27973197 | 28765517 | 28817877 | 792320.21 | 0 | 27757494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28817877 | 27757494 | -1060383 | 27697061
3 | T3400 | 22247715201 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2013-08-28 | 43091371 | 47509716 | 49630327 | 4418345.22 | -24000 | 47713281 | 0 | 0 | 0 | 0 | 0 | -24000 | -24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24000 | 49606327 | 47713281 | -1893046 | 39882529
3 | T3406 | 42693215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 2166253 | 2166253 | 2369003 | 0 | -9504 | 2363042 | -9504 | 0 | 0 | 0 | 0 | 0 | -9504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9504 | 2359499 | 2363042 | 3543 | 2386446
3 | T3416 | 42450815201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2014-05-07 | 13977555 | 15548700 | 15324392 | 1571145.12 | 0 | 15062237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15324392 | 15062237 | -262156 | 14671971
3 | T3484 | 43000215201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2015-02-25 | 4296119 | 6114814 | 6340441 | 1818694.53 | 0 | 6332694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6340441 | 6332694 | -7747 | 3303857
3 | T3521 | 43078515201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2015-12-03 | 2580711 | 2556235 | 2428112 | -24475.9 | -31636 | 2365069 | -31636 | 0 | 0 | 0 | 0 | 0 | -31636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31636 | 2396476 | 2365069 | -31407 | 2532091
3 | T3524 | 22251815201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 2046734 | 2173323 | 2073501 | 126589.28 | 0 | 2070847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2073501 | 2070847 | -2655 | 2321588
3 | T3528 | 22281815201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 931084 | 988106 | 921773 | 57021.56 | 0 | 921773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921773 | 921773 | 0 | 926503
3 | T3531 | 43078415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 4796511 | 5842667 | 5869213 | 1046155.82 | -10128 | 5851868 | -8628 | 0 | 0 | 0 | 0 | -1500 | -10128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10128 | 5859085 | 5851868 | -7217 | 4833815
3 | T3541 | 43046715201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2017-02-22 | 762396 | 768113 | 740975 | 5716.56 | 0 | 741383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740975 | 741383 | 407 | 751000
3 | T3550 | 43257015201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 9008956 | 9008956 | 9058480 | 0 | 0 | 8913154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9058480 | 8913154 | -145326 | 9047925
3 | T3553 | 43273915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 5112998 | 5217096 | 5197254 | 104097.95 | -15000 | 5211856 | 0 | 0 | 0 | 0 | 0 | -15000 | -15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15000 | 5182254 | 5211856 | 29602 | 5858556
3 | T3557 | 43047215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 3101706 | 3159561 | 3107062 | 57854.95 | -3800 | 3095231 | 0 | 0 | 0 | 0 | 0 | -3800 | -3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3800 | 3103262 | 3095231 | -8031 | 3337302
3 | T3563 | 43344815201 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 434900 | 486505 | 459662 | 51605.15 | 0 | 460414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459662 | 460414 | 752 | 347119
3 | T3564 | 43273615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 8987040 | 9020160 | 9114270 | 33119.65 | -36735 | 9043937 | 0 | 0 | 0 | 0 | -395 | -36340 | -36735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36735 | 9077535 | 9043937 | -33598 | 10170399
3 | T3566 | 43047015201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2017-02-22 | 740057 | 740736 | 741918 | 679 | 0 | 741816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741918 | 741816 | -102 | 733082
3 | T3574 | 43047115201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2016-08-31 | 710702 | 710702 | 703481 | 0 | -9504 | 696276 | -9504 | 0 | 0 | 0 | 0 | 0 | -9504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9504 | 693977 | 696276 | 2299 | 765581
3 | T3575 | 43079115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 1223500 | 1223500 | 1204340 | 0 | 0 | 1216824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1204340 | 1216824 | 12484 | 1644577 | B0 | ACC - LUMP SUM
3 | T3576 | 42857615201 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-08-31 | 455335 | 461101 | 462306 | 5766.1 | 0 | 462306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462306 | 462306 | 0 | 517907
3 | T3577 | 43047515201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2017-02-22 | 777422 | 777422 | 756968 | 0 | 0 | 757588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756968 | 757588 | 619 | 827647
3 | T3583 | 43047415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 450844 | 450844 | 461793 | 0 | 0 | 461793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461793 | 461793 | 0 | 501000
3 | T3588 | 43390415201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 1128303 | 1129920 | 1176298 | 1617 | 0 | 1177731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1176298 | 1177731 | 1433 | 1069863
3 | T3590 | 43273815201 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2016-03-30 | 8979888 | 9089938 | 8804885 | 105255.89 | -11500 | 8851032 | 0 | 0 | 0 | 0 | 0 | -11500 | -11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11500 | 8793385 | 8851032 | 57647 | 9805558
3 | T3591 | 43047815201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2017-02-22 | 755934 | 755934 | 764661 | 0 | 0 | 765293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764661 | 765293 | 632 | 728590
3 | T3592 | 43466715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 2446453 | 2446453 | 2415161 | 0 | 0 | 2432529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2415161 | 2432529 | 17369 | 2770764
3 | T3593 | 43356915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 1110799 | 1110799 | 1075584 | 0 | -6336 | 1069297 | -6336 | 0 | 0 | 0 | 0 | 0 | -6336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6336 | 1069248 | 1069297 | 48 | 1069165
3 | T3599 | 42820835201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 311313 | 311313 | 302309 | 0 | 0 | 302309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302309 | 302309 | 0 | 204199 | B0 | ACC - LUMP SUM
3 | T3600 | 42695115201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-02-24 | 2196017 | 2209792 | 2194453 | 13775.67 | 0 | 2190296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2194453 | 2190296 | -4157 | 2203714
3 | T3601 | 43046315201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2016-10-26 | 937429 | 937429 | 948863 | 0 | 0 | 948876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948863 | 948876 | 13 | 1073431
3 | T3608 | 43356815201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 535448 | 535448 | 538259 | 0 | 0 | 543732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538259 | 543732 | 5474 | 646015
3 | T3610 | 43255615201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 1354302 | 1354302 | 1333996 | 0 | 0 | 1333996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1333996 | 1333996 | 0 | 1817292 | B0 | ACC - LUMP SUM
3 | T3611 | 43256715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-01-25 | 933656 | 933656 | 847331 | 0 | 0 | 849907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847331 | 849907 | 2576 | 1051000
3 | T3613 | 21995025202 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 5413721 | 5421436 | 5717509 | 7715.63 | 0 | 5805268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5717509 | 5805268 | 87758 | 6943781
3 | T3616 | 43662215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 96639 | 96639 | 100978 | 0 | 0 | 100978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100978 | 100978 | 0 | 113500
3 | T3620 | 43278725201 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2017-02-22 | 98537 | 98537 | 95183 | 0 | 0 | 95183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95183 | 95183 | 0 | 131242
3 | T3625 | 43188315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-03-29 | 966793 | 970978 | 923813 | 4184.96 | 0 | 919628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 923813 | 919628 | -4185 | 827500
3 | T3628 | 43626415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 798080 | 798080 | 766495 | 0 | 0 | 766495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766495 | 766495 | 0 | 1010000 | B0 | ACC - LUMP SUM
3 | T3631 | 43827525201 | F203990573 | MURDOCK INVESTMENTS LLC | N/A | N/A | N/A | N/A | 2017-06-14 | 140958 | 140958 | 128843 | 0 | 0 | 128843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128843 | 128843 | 0 | 138259
3 | T3643 | 43626215201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-12-06 | 550118 | 550118 | 526409 | 0 | 0 | 526409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526409 | 526409 | 0 | 755613
3 | T3654 | 43827615201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 40030 | 40030 | 37300 | 0 | 0 | 37300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37300 | 37300 | 0 | 43000
3 | T3657 | 40980195201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2017-08-30 | 391534 | 391534 | 404360 | 0 | 0 | 404360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404360 | 404360 | 0 | 349936
4 | E4K49 | 42279615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2010-12-03 | 84027062 | 128024336 | 127605903 | 43997273.79 | -1137325 | 126905951 | -1137325 | 0 | 0 | 0 | 0 | 0 | -1137325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1137325 | 126468579 | 126905951 | 437373 | 102208657 | ARRA:B8:Y:ARR::Y | AMERICAN RECOVERY AND REINVEST:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:AMERICAN RECOVERY AND REINVEST:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4Q43 | 22939625201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-04-15 | 9189394 | 9189394 | 9232946 | 0 | 148500 | 8922257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148500 | 148500 | 148500 | 9381446 | 8922257 | -459189 | 6467904 | A3:B5:Y | ICC - DESIGN/BUILD - MINOR:ACC - INCENTIVE/DISINCENTIVE:DESIGN/BUILD PROJECT
4 | E4R04 | 43062515201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2015-06-12 | 1604618 | 1604618 | 1554867 | 0 | 0 | 1554752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1554867 | 1554752 | -115 | 1736394 | B0 | ACC - LUMP SUM
4 | E4R64 | 43664615201 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2016-03-04 | 8161674 | 8192052 | 8168056 | 30378 | 300000 | 8188367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 8468056 | 8188367 | -279689 | 11010251 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4R66 | 42872725201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-03-04 | 2866096 | 3030096 | 3026692 | 164000 | 0 | 3026963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3026692 | 3026963 | 272 | 1839665
4 | E4R68 | 43750315201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-07-01 | 4071704 | 4123622 | 4162840 | 51917.6 | 100000 | 4159065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 20000 | 0 | 0 | 0 | 100000 | 100000 | 4262840 | 4159065 | -103775 | 5128284 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4R80 | 43232615201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-12-02 | 2142842 | 2142842 | 2107961 | 0 | 0 | 2118375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107961 | 2118375 | 10414 | 2054272
4 | E4S04 | 43110715201 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2016-10-14 | 289809 | 289809 | 270949 | 0 | 0 | 270949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270949 | 270949 | 0 | 303226
4 | E4S17 | 43397715201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-01-06 | 280209 | 280209 | 215232 | 0 | 0 | 215232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215232 | 215232 | 0 | 253964
4 | E4S18 | 43110615201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-01-06 | 1025128 | 1057971 | 1006759 | 16421.75 | 0 | 990337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006759 | 990337 | -16422 | 3357102
4 | E4S28 | 43793415201 | F473077227 | TADEOS ENGINEERING LLC | N/A | N/A | N/A | N/A | 2017-03-03 | 316709 | 319147 | 303591 | 2437.19 | 0 | 301154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303591 | 301154 | -2437 | 371789
4 | E4S33 | 43334915201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-04-07 | 460000 | 464502 | 437196 | 4502.69 | 0 | 435139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437196 | 435139 | -2057 | 473231
4 | T4360 | 40691915201 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2013-06-19 | 22198458 | 24242652 | 24231373 | 2044193.81 | 0 | 24184321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24231373 | 24184321 | -47051 | 25330674
4 | T4387 | 42924625201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2014-04-30 | 20572640 | 20874760 | 20200080 | 302119.96 | 0 | 19403592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20200080 | 19403592 | -796488 | 23230743
4 | T4392 | 42873115201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-08-31 | 1894496 | 1894496 | 1876142 | 0 | 0 | 1885605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1876142 | 1885605 | 9463 | 2046919 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
4 | T4393 | 42872215201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-10-28 | 7257569 | 7675751 | 7429380 | 418182 | -15080 | 7264049 | -15080 | 0 | 0 | 0 | 0 | 0 | -15080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15080 | 7414300 | 7264049 | -150251 | 7461270
4 | T4407 | 43060115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-12-03 | 4429693 | 4522960 | 4441417 | 93267.11 | 144900 | 4419287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144900 | 144900 | 144900 | 4586317 | 4419287 | -167030 | 4059382 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4408 | 42898415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-04-29 | 5457914 | 5501915 | 5476312 | 44001.24 | 0 | 5355390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5476312 | 5355390 | -120921 | 6001634
4 | T4428 | 43175715201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 1321404 | 1321404 | 1261612 | 0 | 0 | 1264590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1261612 | 1264590 | 2978 | 1395150
4 | T4429 | 43320715201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-02-24 | 1817368 | 1866868 | 1820548 | 49500 | 0 | 1828664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1820548 | 1828664 | 8115 | 1805873
4 | T4436 | 43515915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-02-22 | 363409 | 363409 | 342509 | 0 | 0 | 342509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342509 | 342509 | 0 | 390894
4 | T4437 | 43510215201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2016-03-30 | 647604 | 693460 | 677812 | 45855.69 | 0 | 686116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677812 | 686116 | 8304 | 572056
4 | T4440 | 43512215201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 1336353 | 1336353 | 1276103 | 0 | 0 | 1277493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276103 | 1277493 | 1390 | 1362626
4 | T4441 | 43799415201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-12-07 | 899605 | 899605 | 846333 | 0 | 50000 | 846333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 896333 | 846333 | -50000 | 1032155 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4442 | 43444915201 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2016-08-31 | 413333 | 413333 | 384378 | 0 | 0 | 384534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384378 | 384534 | 156 | 393422
4 | T4443 | 43427515201 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2016-09-28 | 1312214 | 1312214 | 1253435 | 0 | 0 | 1261184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1253435 | 1261184 | 7749 | 1458807
4 | T4448 | 43786515201 | F650861113 | I & C EARTHMOVERS CORP. | N/A | N/A | N/A | N/A | 2017-02-22 | 279149 | 282353 | 271123 | 3204.56 | 0 | 267918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271123 | 267918 | -3205 | 272833
4 | T4458 | 43168715201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2017-02-22 | 234419 | 234419 | 219157 | 0 | 0 | 219157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219157 | 219157 | 0 | 262846
5 | BE035 | 43387415201 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2015-08-10 | 8947000 | 9057405 | 9057405 | 110405 | 0 | 9057101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9057405 | 9057101 | -304 | 8947000 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | BE042 | 43643615201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2015-07-20 | 4349110 | 4305862 | 4305862 | -43247.09 | 0 | 4305862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4305862 | 4305862 | 0 | 2601707 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | BE227 | 43029015201 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2016-04-22 | 1697000 | 1771015 | 1771015 | 74015 | 0 | 1771300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1771015 | 1771300 | 285 | 1668323
5 | E5R16 | 40846415201 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2012-02-03 | 134462000 | 142782598 | 143964934 | 8320597.66 | -226500 | 140683724 | 0 | 0 | 0 | 0 | 0 | -226500 | -226500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -226500 | 143738434 | 140683724 | -3054710 | 134462000 | B8 | ACC - DESIGN/BUILD - MAJOR
5 | E5W10 | 24262625201 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2014-06-25 | 76960400 | 78949466 | 78905602 | 1989066.06 | 497040 | 74149436 | 0 | 0 | 0 | 0 | 0 | -2960 | -2960 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 497040 | 79402642 | 74149436 | -5253206 | 74117581 | B2:B5:B8 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
5 | E5Y06 | 43544325201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2016-03-29 | 1130290 | 1130290 | 958974 | 0 | 0 | 958974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958974 | 958974 | 0 | 1120523
5 | E5Y27 | 43750115201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2016-05-03 | 1337625 | 1337625 | 1189585 | 0 | 0 | 1190243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189585 | 1190243 | 659 | 1320391
5 | E5Y32 | 43445515201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2016-08-02 | 622133 | 622133 | 564614 | 0 | 0 | 564745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564614 | 564745 | 131 | 567683
5 | E5Y34 | 43744415201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2016-09-07 | 793972 | 793972 | 619065 | 0 | 0 | 621005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619065 | 621005 | 1940 | 843684
5 | E5Y35 | 42302915201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-10-04 | 900963 | 905489 | 870490 | 4526.18 | 0 | 870490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 870490 | 870490 | 0 | 774383
5 | E5Y36 | 43445615201 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2016-10-04 | 704674 | 704674 | 672674 | 0 | 0 | 672674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672674 | 672674 | 0 | 684420
5 | E5Y37 | 43744815201 | F273238420 | OCEANEER CONSULTING LLC | N/A | N/A | N/A | N/A | 2016-12-06 | 339868 | 339868 | 258858 | 0 | 0 | 258860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258858 | 258860 | 2 | 388062
5 | E5Y53 | 24021675201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2017-05-02 | 1488299 | 1488299 | 1438708 | 0 | 0 | 1450820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438708 | 1450820 | 12112 | 1582604
5 | E5Y58 | 43744615201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-03-07 | 498196 | 498012 | 443118 | -184 | 0 | 443118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443118 | 443118 | 0 | 954404
5 | E5Y59 | 43709215201 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2016-12-06 | 524644 | 524644 | 497252 | 0 | 0 | 497252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497252 | 497252 | 0 | 584577
5 | E5Y63 | 43234615201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-10-04 | 862770 | 868517 | 816671 | 5746.5 | -25344 | 791327 | -25344 | 0 | 0 | 0 | 0 | 0 | -25344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25344 | 791327 | 791327 | 0 | 776696
5 | E5Y76 | 43566215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-01 | 3490230 | 3490230 | 3483913 | 0 | 0 | 3496667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3483913 | 3496667 | 12754 | 4898413
5 | E5Y79 | 43544335201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-03-07 | 1179059 | 1271899 | 1054894 | 92840.01 | 0 | 1054894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054894 | 1054894 | 0 | 1499217
5 | E5Y85 | 43465815201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-04-04 | 349962 | 365078 | 342181 | 15116.53 | -15386 | 326795 | -15386 | 0 | 0 | 0 | 0 | 0 | -15386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15386 | 326795 | 326795 | 0 | 361362
5 | T5466 | 43066525201 | Z59-1673015 | BANKERS INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2013-07-31 | 650999 | 630759 | 395792 | -20240 | 0 | 395792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395792 | 395792 | 0 | 828133 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
5 | T5468 | 42887615201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2013-12-04 | 5811896 | 5828065 | 5929467 | 16169.2 | -61294 | 5738344 | -61294 | 0 | 0 | 0 | 0 | 0 | -61294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -61294 | 5868173 | 5738344 | -129829 | 6328170 | B0 | ACC - LUMP SUM
5 | T5514 | 43065815201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 2758832 | 3022207 | 3025677 | 263375.47 | 0 | 2910569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3025677 | 2910569 | -115108 | 2936600
5 | T5516 | 23968315201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 16187452 | 16131784 | 15468614 | -55668.27 | 316000 | 14793325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316000 | 0 | 0 | 0 | 0 | 0 | 316000 | 316000 | 15784614 | 14793325 | -991289 | 16443271 | B5 | ACC - INCENTIVE/DISINCENTIVE
5 | T5523 | 43064315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-03-25 | 26022554 | 26092001 | 26837874 | 69447.03 | -244771 | 24360936 | -211869 | 0 | 0 | 0 | 0 | -32902 | -244771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -244771 | 26593103 | 24360936 | -2232167 | 32995661
5 | T5533 | 42728015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2015-07-29 | 8422850 | 8665412 | 8608390 | 242561.74 | -105560 | 8174179 | -105560 | 0 | 0 | 0 | 0 | 0 | -105560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105560 | 8502830 | 8174179 | -328651 | 8647535
5 | T5546 | 43234215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-06-15 | 2075235 | 2088068 | 2079010 | 12832.64 | 0 | 2069893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2079010 | 2069893 | -9116 | 1799214
5 | T5547 | 43240715201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-01-27 | 5090422 | 5188654 | 5185897 | 98232.45 | 0 | 5166489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5185897 | 5166489 | -19408 | 4488966
5 | T5549 | 43240215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-04-27 | 4288764 | 4479588 | 4434500 | 207821.02 | 0 | 4452174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4434499 | 4452174 | 17674 | 4897478 | B0 | ACC - LUMP SUM
5 | T5553 | 43242115201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-03-30 | 1085604 | 1087044 | 1021639 | 1440 | -6360 | 1026222 | 0 | 0 | 0 | 0 | 0 | -6360 | -6360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6360 | 1015279 | 1026222 | 10943 | 1163003
5 | T5554 | 43066715202 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-06-15 | 5357590 | 5415657 | 5363913 | 58066.87 | 0 | 5355725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5363913 | 5355725 | -8188 | 6206643 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
5 | T5563 | 43067815201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 10074300 | 10356846 | 10457771 | 282546.27 | 0 | 10446251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10457771 | 10446251 | -11520 | 13456514
5 | T5565 | 43065715201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-07-27 | 3028041 | 3028041 | 2950282 | 0 | 0 | 2950886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950282 | 2950886 | 604 | 3357586 | B0 | ACC - LUMP SUM
5 | T5566 | 43243715201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-07-27 | 3766852 | 3749136 | 3790510 | -17715.85 | 0 | 3819315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3790510 | 3819315 | 28805 | 4106501
5 | T5567 | 43442415201 | F453608140 | VALENCIA CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2016-07-27 | 1345000 | 1345000 | 1239674 | 0 | 0 | 1239674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239674 | 1239674 | 0 | 1380185 | B0 | ACC - LUMP SUM
5 | T5568 | 43442515201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-07-27 | 1275035 | 1276035 | 1191362 | 1000 | 0 | 1191683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1191362 | 1191683 | 320 | 1313711
5 | T5574 | 43241615201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2016-08-31 | 3274900 | 3420024 | 3368050 | 145123.82 | 0 | 3391256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3368050 | 3391256 | 23206 | 3753390 | B0 | ACC - LUMP SUM
5 | T5576 | 41503055201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-06-15 | 5373132 | 5659631 | 5489222 | 245498.71 | 0 | 5520684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5489222 | 5520684 | 31462 | 6329514
5 | T5581 | 43304015201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2016-12-07 | 1118456 | 1151446 | 1116798 | 32989.48 | 0 | 1118012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116798 | 1118012 | 1214 | 1259440
5 | T5583 | 43505215201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2016-09-28 | 990233 | 990233 | 940233 | 0 | 0 | 940251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940233 | 940251 | 18 | 1091963 | B0 | ACC - LUMP SUM
5 | T5586 | 43469415201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2017-03-29 | 727458 | 768228 | 756229 | 40770.06 | 0 | 756229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756229 | 756229 | 0 | 645878
5 | T5593 | 43635615201 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 264250 | 264250 | 240000 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000 | 0 | 541050 | B0 | ACC - LUMP SUM
5 | T5594 | 43636415201 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 452000 | 452000 | 422000 | 0 | 0 | 422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422000 | 422000 | 0 | 653172
5 | T5595 | 43623615201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 325875 | 325875 | 307875 | 0 | 0 | 307875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307875 | 307875 | 0 | 393058
5 | T5596 | 43637115201 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 148500 | 148500 | 142000 | 0 | 0 | 142000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142000 | 142000 | 0 | 188225
5 | T5599 | 43623515201 | F341233573 | OGLESBY CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-07-26 | 456461 | 456461 | 456461 | 0 | 0 | 456461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456461 | 456461 | 0 | 580001
5 | T5603 | 43440815201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 413889 | 413889 | 405966 | 0 | 0 | 405966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405966 | 405966 | 0 | 623229
5 | T5610 | 44113015201 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 67500 | 67500 | 63500 | 0 | 0 | 63500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63500 | 63500 | 0 | 112350
5 | T5611 | 44113025201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2017-06-14 | 332500 | 345530 | 326210 | 13030 | 0 | 326210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326210 | 326210 | 0 | 569600
5 | T5613 | 44113045201 | F462078794 | CWA ENVIRONMENTAL SERVICES LLC | N/A | N/A | N/A | N/A | 2017-06-14 | 184425 | 184425 | 206750 | 0 | 0 | 206750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206750 | 206750 | 0 | 249957
5 | T5614 | 44113055201 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2017-06-14 | 107445 | 107445 | 107255 | 0 | 0 | 107255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107255 | 107255 | 0 | 168140
5 | T9017 | 43730315201 | F030586197 | R.M. WILLIAMS CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-04-26 | 749800 | 824780 | 791911 | 74980 | 0 | 791926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791911 | 791926 | 15 | 478765
6 | E6J00 | 43540715201 | F650817669 | FLORIDA TURF AND LANDSCAPE HORTICULTURE | N/A | N/A | N/A | N/A | 2015-01-29 | 204491 | 204491 | 200808 | 0 | 0 | 200808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200808 | 200808 | 0 | 234759 | B0 | ACC - LUMP SUM
6 | E6J27 | 43325415201 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2015-10-29 | 874736 | 839120 | 814919 | -35615.78 | 0 | 814919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 814919 | 814919 | 0 | 895055
6 | E6J41 | 43444315201 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2016-11-17 | 220419 | 220419 | 208800 | 0 | 0 | 208800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208800 | 208800 | 0 | 249619 | B0 | ACC - LUMP SUM
6 | E6J44 | 43468115201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-05-26 | 979602 | 823480 | 746877 | -156121.9 | 0 | 746877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 746877 | 746877 | 0 | 1105870
6 | E6J47 | 43471015201 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2016-03-31 | 1421464 | 1931498 | 1949242 | 510033.53 | 0 | 1949242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1949242 | 1949242 | 0 | 1476116
6 | E6J56 | 43550619201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2015-12-02 | 3827963 | 3877963 | 3862070 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3862070 | 0 | -3862070 | 3497921 | A3 | ICC - DESIGN/BUILD - MINOR
6 | E6J75 | 43652815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-06-09 | 847200 | 847200 | 789681 | 0 | 0 | 789681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789681 | 789681 | 0 | 1102469
6 | E6J76 | 43652915201 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2016-06-09 | 588728 | 588728 | 477515 | 0 | 0 | 477515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477515 | 477515 | 0 | 756280
6 | E6K21 | 42914635201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2016-07-28 | 177943 | 177943 | 173203 | 0 | 0 | 173203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173203 | 173203 | 0 | 196224
6 | E6K22 | 42521625201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2016-07-28 | 1343144 | 1349051 | 1259511 | 5907.39 | 0 | 1253427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259511 | 1253427 | -6083 | 1605334
6 | E6K28 | 42563735201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-03-30 | 179971 | 179971 | 164916 | 0 | 0 | 164916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164916 | 164916 | 0 | 267547
6 | E6K31 | 42934635201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-08-25 | 999395 | 999395 | 975146 | 0 | 0 | 975806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975146 | 975806 | 660 | 1051399
6 | E6K49 | 43058825201 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2016-09-29 | 864202 | 864202 | 790596 | 0 | 0 | 790888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790596 | 790888 | 292 | 885402 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM
6 | T6345 | 24994165201 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2014-06-25 | 20210987 | 20241085 | 19700200 | 30097.79 | 800000 | 19298493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 20500200 | 19298493 | -1201707 | 19907818 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6349 | 42916225201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2016-04-27 | 4178283 | 4236996 | 3850525 | 58712.87 | 160000 | 3858312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 160000 | 160000 | 4010525 | 3858312 | -152213 | 5124942 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6350 | 43080315201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2016-06-15 | 3626400 | 3770876 | 3752395 | 144475.59 | 0 | 3763550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3752395 | 3763550 | 11155 | 4489026
6 | T6375 | 43274325201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2015-10-28 | 9111715 | 9340645 | 9186004 | 138930.74 | 0 | 8941564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9186004 | 8941564 | -244440 | 10922672 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6378 | 43080815201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 4890784 | 4907164 | 4857632 | 8190 | 240000 | 4876249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000 | 5097632 | 4876249 | -221383 | 6041431 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6380 | 41462435201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2015-06-17 | 3520907 | 3612854 | 3575998 | 91946.73 | 56000 | 3498466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 56000 | 56000 | 3631998 | 3498466 | -133532 | 3771064 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6385 | 43326415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-01-27 | 1122164 | 1210753 | 1131145 | 88589.58 | 0 | 1133153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1131145 | 1133153 | 2007 | 1217718
6 | T6387 | 43477215201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2016-12-07 | 397288 | 397288 | 368073 | 0 | 0 | 368073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368073 | 368073 | 0 | 422434
6 | T6391 | 43349215201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2016-04-27 | 1155673 | 1155673 | 1091324 | 0 | 0 | 1092555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1091324 | 1092555 | 1230 | 983084
6 | T6405 | 42934625201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2016-03-30 | 1071254 | 1073754 | 1058914 | 2500 | 0 | 1062745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058914 | 1062745 | 3831 | 1077071
6 | T6439 | 43476615201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | 230856 | 230856 | 202885 | 0 | 0 | 202885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202885 | 202885 | 0 | 346258
6 | T9018 | 43676425201 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 1124592 | 1124592 | 1064750 | 0 | 0 | 1064750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064750 | 1064750 | 0 | 1110085
7 | E7I69 | 41868515201 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2014-06-11 | 8338093 | 9034910 | 9761980 | 696817.36 | 0 | 9649830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9761980 | 9649830 | -112150 | 6938455
7 | E7J74 | 42347415201 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2014-08-13 | 5011920 | 5193391 | 5076829 | 181470.54 | 0 | 5076829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5076829 | 5076829 | 0 | 4749400
7 | E7J76 | 43075115201 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2014-12-10 | 743784 | 740664 | 652729 | -3120 | 0 | 652689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652729 | 652689 | -40 | 860120
7 | E7K09 | 43376015201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2016-03-09 | 4858889 | 4858889 | 4889946 | 0 | 0 | 4892719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889946 | 4892719 | 2773 | 4975480
7 | E7K13 | 43175035201 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2014-11-26 | 5076080 | 5076080 | 5350308 | 0 | 0 | 5348564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5350308 | 5348564 | -1744 | 5778800
7 | E7K14 | 43571815201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2015-06-23 | 5520000 | 5520000 | 5515787 | 0 | 0 | 5461492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5515787 | 5461492 | -54295 | 5318312 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD
7 | E7K95 | 43655215201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2016-03-09 | 1999499 | 1999499 | 1965163 | 0 | 0 | 1965188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1965163 | 1965188 | 25 | 2583470
7 | E7K97 | 43149215201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2016-06-08 | 5498000 | 5498000 | 5479166 | 0 | 0 | 5486336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5479166 | 5486336 | 7170 | 5955000 | B0 | ACC - LUMP SUM
7 | E7L41 | 42550315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-09-14 | 1429757 | 1429757 | 1357101 | 0 | 0 | 1357101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357101 | 1357101 | 0 | 1539689
7 | E7L44 | 43269915201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-10-12 | 2181247 | 2181247 | 2114949 | 0 | 0 | 2122813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114949 | 2122813 | 7864 | 2450000 | B0 | ACC - LUMP SUM
7 | E7L46 | 43473615201 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2016-12-14 | 2644431 | 2644431 | 2652518 | 0 | -75897 | 2683911 | -75897 | 0 | 0 | 0 | 0 | 0 | -75897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75897 | 2576621 | 2683911 | 107290 | 3002164
7 | E7L48 | 43243215201 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-01-11 | 658045 | 681845 | 622321 | 23800 | -15840 | 606481 | -15840 | 0 | 0 | 0 | 0 | 0 | -15840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15840 | 606481 | 606481 | 0 | 825000
7 | E7L57 | 43386515201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-03-08 | 284040 | 284040 | 270466 | 0 | 0 | 270466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270466 | 270466 | 0 | 320000 | B0 | ACC - LUMP SUM
7 | E7L63 | 43794015201 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2017-03-08 | 1222291 | 1228444 | 1182817 | 6152.5 | 0 | 1182817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1182817 | 1182817 | 0 | 1198577
7 | T7220 | 40845925201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2011-06-29 | 94696203 | 99221504 | 102513161 | 4525301.07 | -176000 | 101320385 | 0 | 0 | 0 | 0 | 0 | -176000 | -176000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -176000 | 102337161 | 101320385 | -1016777 | 107019759
7 | T7322 | 42292925201 | F331064425 | CIVIL SITE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2013-06-19 | 756468 | 756468 | 713772 | 0 | -356956 | 356816 | -356956 | 0 | 0 | 0 | 0 | 0 | -356956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -356956 | 356816 | 356816 | 0 | 983979
7 | T7346 | 43089815201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-07-30 | 6794444 | 6864518 | 7093818 | 70073.29 | 0 | 6785751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7093818 | 6785751 | -308067 | 6553700
7 | T7349 | 43124315201 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2014-06-18 | 12544444 | 12706570 | 13012776 | 162125.3 | 0 | 12421061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13012776 | 12421061 | -591715 | 12199500
7 | T7377 | 42453295201 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2016-02-24 | 2482901 | 2542403 | 2373194 | 59502.28 | 0 | 2384196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373194 | 2384196 | 11002 | 2246000
7 | T7381 | 25589335201 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2016-05-25 | 4590182 | 4640182 | 4586377 | 50000 | 0 | 4603104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4586377 | 4603104 | 16727 | 7190841
7 | T7397 | 43768715201 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-06-14 | 1352726 | 1363694 | 1329902 | 10968.33 | 0 | 1340929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329902 | 1340929 | 11027 | 1620000
7 | T9019 | 44030915201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2017-04-26 | 106998 | 124900 | 124723 | 17902.24 | 0 | 124723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124723 | 124723 | 0 | 105780
8 | E8M76 | 41548815201 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2013-04-09 | 40893455 | 42793440 | 43780119 | 1899985.04 | 0 | 42891163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43780119 | 42891163 | -888956 | 44448236 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8N90 | 42815425201 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2014-10-14 | 8152113 | 8219090 | 7569664 | 66977.25 | 0 | 7559469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7569664 | 7559469 | -10195 | 10548406
8 | E8P07 | 43560915201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2016-05-10 | 3499824 | 3949117 | 3984741 | 449293.04 | 0 | 3986085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3984741 | 3986085 | 1344 | 3565669
8 | E8P83 | 43282615201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2016-03-22 | 12114000 | 12052537 | 12086406 | -61462.58 | 0 | 12136961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12086406 | 12136961 | 50556 | 13714087
8 | E8P84 | 43560415201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2016-06-14 | 1564634 | 1564634 | 1570658 | 0 | 0 | 1593989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570658 | 1593989 | 23332 | 1798900
8 | E8P93 | 42933415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2016-04-12 | 1627383 | 1619754 | 1562111 | -7628.64 | 0 | 1565726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1562111 | 1565726 | 3615 | 1804453
8 | E8P94 | 43282715201 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2016-05-24 | 11866804 | 11967156 | 11316560 | 100351.4 | -6500 | 11338373 | 0 | 0 | 0 | 0 | 0 | -6500 | -6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6500 | 11310060 | 11338373 | 28313 | 13286145
8 | E8P96 | 43494625201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2016-05-24 | 938500 | 938500 | 828715 | 0 | 0 | 828715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 828715 | 828715 | 0 | 988990
8 | E8Q16 | 43540615201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2016-10-18 | 2671430 | 3119007 | 3032466 | 447577.92 | 300000 | 3032466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 3332466 | 3032466 | -300000 | 8220799 | B10 | ACC - BONUS/INCENT/DISINCENT
8 | E8Q55 | 43914515201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-04-11 | 649649 | 670169 | 659765 | 20520 | 0 | 661830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659765 | 661830 | 2065 | 849412

## Detailed Data - PPP
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
[29 empty] | 0% | 1
| Dist 01 - Central Let Contrats SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 01 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 01 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 02 Central Let Contract SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | E2Q62 | 20929495201 | 2012-07-17 | QTR1 | 12/13 | 2 | 2 | 1100 | 1382 | 1382 | 103.8% | 1 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | 0% | 1 | -95132842 | 102106 | 152 | 88 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849 | F900869955 | INFRASTRUCTURE DEV PARTNERS | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 |  | 2016-07-16 | QTR1 | 16/17 | 216 | 104626299 | B8:DBF:P3 | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP
[29 empty] | 0% | 1
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 1 | 2 | 2 | 1100 | 1382 | 1382 | 100% | 1 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | 200% | 2 | -95132842 | 102106 | 152 | 88 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849
| District 02 Totals |  |  |  |  | 1 | 2 | 2 | 1100 | 1382 | 1382 | 100% | 1 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | 300% | 3 | -95132842 | 102106 | 152 | 88 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849
[29 empty] | 0% | 1
| Dist 03 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 03 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 03 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 04 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 04 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 04 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 05 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 05 | E5R39 | 40686985201 | 2012-04-19 | QTR4 | 11/12 | 1 | 12 | 1330 | 1397 | 1396 | 90.98% | 1 | 1 | 0 | 0 | 186 | -119 | 118370000 | 150000 | 118220000 | 127761416 | 127692104 | -26000 | 989593 | 963593 | 128655697 | 0 | 0% | 1 | -128655697 | 9391416 | 137 | 49 | 0 | -119 | 7073 | 0 | 0 | 0 | 36081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -119 | 2812039 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-12-01 | QTR2 | 17/18 |  | 2016-07-27 | QTR1 | 16/17 | 514 | 128150810 | B1:B11:B8:DB:P3 | ACC - NO EXCUSE BONUS:ACC - DESIGN BUILD-MAJOR/BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP
[29 empty] | 0% | 1
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 1 | 1 | 12 | 1330 | 1397 | 1396 | 100% | 1 | 1 | 0 | 0 | 186 | -119 | 118370000 | 150000 | 118220000 | 127761416 | 127692104 | -26000 | 989593 | 963593 | 128655697 | 0 | 200% | 2 | -128655697 | 9391416 | 137 | 49 | 0 | -119 | 7073 | 0 | 0 | 0 | 36081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -119 | 2812039 | 0
| District 05 Totals |  |  |  |  | 1 | 1 | 12 | 1330 | 1397 | 1396 | 100% | 1 | 1 | 0 | 0 | 186 | -119 | 118370000 | 150000 | 118220000 | 127761416 | 127692104 | -26000 | 989593 | 963593 | 128655697 | 0 | 300% | 3 | -128655697 | 9391416 | 137 | 49 | 0 | -119 | 7073 | 0 | 0 | 0 | 36081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -119 | 2812039 | 0
[29 empty] | 0% | 1
| Dist 06 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06 | E6F61 | 24958115201 | 2009-08-31 | QTR1 | 09/10 | 5 | 34 | 1825 | 2495 | 2494 | 103.3% | 1 | 1 | 0 | 0 | 670 | 0 | 558880178 | 150000 | 558730178 | 562612213 | 563638617 | 0 | 0 | 0 | 563638617 | 567488387 | 101.6% | 1 | 3849771 | 3732035 | 472 | 136 | 4 | 0 | 1284972 | 0 | 0 | 0 | 1625269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50600 | 0 | 58 | 0 | 803680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 3764521 | 0 | F371585067 | COMMUNITY CONDOTTE DE MOYA JV | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 |  | 2016-09-27 | QTR1 | 16/17 | 606 | 559310206 | ARRA:B8:DBF:P3 | AMERICAN RECOVERY AND REINVEST:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP
[29 empty] | 0% | 1
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 1 | 5 | 34 | 1825 | 2495 | 2494 | 100% | 1 | 1 | 0 | 0 | 670 | 0 | 558880178 | 150000 | 558730178 | 562612213 | 563638617 | 0 | 0 | 0 | 563638617 | 567488387 | 200% | 2 | 3849771 | 3732035 | 472 | 136 | 4 | 0 | 1284972 | 0 | 0 | 0 | 1625269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50600 | 0 | 58 | 0 | 803680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 3764521 | 0
| District 06 Totals |  |  |  |  | 1 | 5 | 34 | 1825 | 2495 | 2494 | 100% | 1 | 1 | 0 | 0 | 670 | 0 | 558880178 | 150000 | 558730178 | 562612213 | 563638617 | 0 | 0 | 0 | 563638617 | 567488387 | 300% | 3 | 3849771 | 3732035 | 472 | 136 | 4 | 0 | 1284972 | 0 | 0 | 0 | 1625269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50600 | 0 | 58 | 0 | 803680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 3764521 | 0
[29 empty] | 0% | 1
| Dist 07 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 07 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 07 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 08 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide District Let Contracts SubTotal |  |  |  |  | 3 | 8 | 48 | 4255 | 5274 | 5272 | 100% | 3 | 2 | 0 | 0 | 1134 | -115 | 772151478 | 450000 | 771701478 | 785377035 | 786463563 | -26000 | 989593 | 963593 | 787427156 | 567488387 | 333.3% | 10 | -219938768 | 13225557 | 761 | 273 | 35 | -119 | 1384120 | 0 | 0 | 4 | 1762288 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104500 | 0 | 65 | 0 | 3327479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -115 | 6827162 | 84849
| Statewide Totals |  |  |  |  | 3 | 8 | 48 | 4255 | 5274 | 5272 | 100% | 3 | 2 | 0 | 0 | 1134 | -115 | 772151478 | 450000 | 771701478 | 785377035 | 786463563 | -26000 | 989593 | 963593 | 787427156 | 567488387 | 566.7% | 17 | -219938768 | 13225557 | 761 | 273 | 35 | -119 | 1384120 | 0 | 0 | 4 | 1762288 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104500 | 0 | 65 | 0 | 3327479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -115 | 6827162 | 84849

## Sheet1 (hidden)
01CO | 01 | T1330 | 19571825201 | 2012-06-20 | QTR4 | 11/12 | 6 | 8 | 750 | 1067 | 1067 | 0 | 0 | 0 | 176 | 141 | 22148030 | 150000 | 21998030 | 24020348 | 23810851 | 0 | 0 | 0 | 23810851 | 23564595 | -246257 | 1872318 | 139 | 0 | 80 | 1993803 | 247057 | 0 | -30 | 163045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 1925001 | 247057 | F272587735 | CONALVIAS USA LLC | N/A | N/A | N/A | N/A | 2018-03-09 | QTR3 | 17/18 | 2015-12-09 | QTR2 | 15/16 | 113 | 21275691.37 |  |  | 0 | 37 | 0 | 91 | -278762 | 0 |  | CO | 28 | 01co | 1 | 28
01CO | 01 | T1417 | 41612015201 | 2011-12-07 | QTR2 | 11/12 | 4 | 6 | 450 | 591 | 790 | -199 | 199 | 0 | 111 | 30 | 12691971 | 121466 | 12570505 | 13256420 | 13055581 | -656700 | 0 | -656700 | 12398881 | 12393005 | -5876 | 564450 | 64 | 10 | 0 | 108668 | 21405 | 20 | 10 | 504186 | 27781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 38852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 653741 | 49186 | F592319514 | BETTER ROADS INC. | N/A | N/A | N/A | N/A | 2017-11-21 | QTR2 | 17/18 | 2014-06-13 | QTR4 | 13/14 | 115 | 11408241.94 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO | 22 | 01do | 29 | 50
01CO | 01 | T1598 | 41304425201 | 2015-07-29 | QTR1 | 15/16 | 3 | 17 | 668 | 722 | 698 | 24 | 0 | 0 | 58 | -4 | 72913523 | 150000 | 72763523 | 73524079 | 72400941 | -52000 | 3500000 | 3448000 | 75848941 | 70273740 | -5529824 | 610556 | 38 | 0 | -16 | 375892 | 55875 | 0 | 0 | 747621 | 285223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | 661423 | 341098 | F650143860 | ASTALDI CONSTRUCTION CORP. | N/A | N/A | N/A | N/A | 2018-05-30 | QTR4 | 17/18 | 2017-11-30 | QTR2 | 17/18 | 106 | 87450436.24 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | -453111 | 0 |  | CO | 34 | 02co | 51 | 84
01CO | 01 | T1625 | 42988315201 | 2016-06-15 | QTR4 | 15/16 | 1 | 3 | 150 | 198 | 198 | 0 | 0 | 0 | 40 | 8 | 1852000 | 50000 | 1802000 | 1866275 | 1867608 | 0 | 0 | 0 | 1867608 | 1867700 | 92 | 14275 | 13 | 0 | 0 | 0 | 0 | 0 | 8 | 26881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8 | 26881 | 0 | F592903287 | LEWARE CONSTRUCTION COMPANY OF FLORIDA | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-04-11 | QTR4 | 16/17 | 108 | 2064220.28 |  |  | 8 | 13 | 0 | 0 | 0 | 0 |  | CO | 19 | 02do | 85 | 103
01CO | 01 | T1628 | 43011915201 | 2016-01-27 | QTR3 | 15/16 | 2 | 3 | 250 | 289 | 289 | 0 | 0 | 0 | 36 | 3 | 5092548 | 54005 | 5038543 | 5147816 | 5084411 | 0 | 0 | 0 | 5084411 | 5074685 | -9725 | 55268 | 16 | 0 | 0 | 9739 | 0 | 0 | 3 | 56544 | 5272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 66284 | 5272 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-27 | QTR1 | 17/18 | 2017-04-05 | QTR4 | 16/17 | 113 | 5336136.69 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO | 42 | 03co | 104 | 145
01CO | 01 | T1631 | 43327215201 | 2016-04-27 | QTR4 | 15/16 | 1 | 3 | 100 | 208 | 208 | 0 | 0 | 0 | 108 | 0 | 1451189 | 0 | 1451189 | 1460304 | 1516711 | 0 | 0 | 0 | 1516711 | 1516711 | 0 | 9115 | 38 | 0 | 0 | 24623 | 0 | 34 | 0 | -15508 | 1870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 9115 | 1870 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-10-05 | QTR2 | 17/18 | 2017-07-14 | QTR1 | 17/18 | 108 | 1389366.28 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO | 16 | 03do | 146 | 161
01CO | 01 | T1647 | 43131615201 | 2016-02-24 | QTR3 | 15/16 | 5 | 15 | 475 | 631 | 631 | 0 | 0 | 0 | 133 | 23 | 14344879 | 150000 | 14194879 | 14807906 | 14762958 | 0 | 0 | 0 | 14762958 | 14811081 | 105279 | 405870 | 85 | 0 | 20 | 179164 | 0 | 0 | 0 | 33291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125250 | 0 | 0 | 3 | 56309 | 56309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22560 | 22560 | 0 | 0 | 0 | 0 | 0 | 23 | 416573 | 78868 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-05-14 | QTR4 | 17/18 | 2018-01-22 | QTR3 | 17/18 | 113 | 14324215.64 |  |  | 20 | 48 | 0 | 0 | 0 | 0 |  | CO | 16 | 04co | 162 | 177
01CO | 01 | T1648 | 43448915201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 85 | 113 | 113 | 0 | 0 | 0 | 12 | 16 | 910955 | 0 | 910955 | 949740 | 949740 | 0 | 0 | 0 | 949740 | 949740 | 0 | 38784 | 11 | 0 | 6 | 15433 | 0 | 0 | 10 | 23352 | 4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 38784 | 4641 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2017-10-26 | QTR2 | 17/18 | 2017-04-25 | QTR4 | 16/17 | 108 | 910039.59 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 12 | 04do | 178 | 189
01CO | 01 | T1652 | 43356215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 250 | 279 | 278 | 1 | 0 | 0 | 29 | 0 | 1849592 | 50000 | 1799592 | 1849592 | 1707344 | 0 | 0 | 0 | 1707344 | 1709115 | 1771 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 5795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5795 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-11-08 | QTR2 | 17/18 | 2017-07-07 | QTR1 | 17/18 | 115 | 1373813.46 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 35 | 05co | 190 | 224
01CO | 01 | T1655 | 43507515201 | 2016-05-25 | QTR4 | 15/16 | 2 | 1 | 250 | 300 | 279 | 21 | 0 | 0 | 50 | 0 | 4645998 | 59238 | 4586760 | 4644998 | 4654697 | 0 | 0 | 0 | 4654697 | 4670541 | 15844 | -1000 | 31 | 0 | 0 | 9206 | 0 | 0 | 0 | 17333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28684 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-10-27 | QTR2 | 17/18 | 2017-07-28 | QTR1 | 17/18 | 108 | 4668696.06 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 | T | CO | 16 | 05do | 225 | 240
01CO | 01 | T1658 | 43902815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 175 | 214 | 210 | 4 | 0 | 0 | 29 | 10 | 2041864 | 54329 | 1987535 | 2041864 | 1925079 | 0 | 0 | 0 | 1925079 | 1925198 | 118 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 10 | 16588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 16588 | 0 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-06-12 | QTR4 | 16/17 | 113 | 4696299.51 |  |  | 10 | 17 | 0 | 0 | 0 | 0 |  | CO | 12 | 06co | 241 | 252
01CO | 01 | T1661 | 43450815201 | 2017-02-22 | QTR3 | 16/17 | 3 | 1 | 110 | 157 | 152 | 5 | 0 | 0 | 47 | 0 | 1347647 | 0 | 1347647 | 1408422 | 1434774 | 0 | 0 | 0 | 1434774 | 1313225 | -60775 | 60775 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-03-20 | QTR3 | 17/18 | 2017-11-21 | QTR2 | 17/18 | 108 | 1203312.27 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO | 13 | 06do | 253 | 265
01CO | 01 | T1662 | 43132515201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 75 | 90 | 97 | -7 | 7 | 0 | 15 | 0 | 150000 | 7492 | 142508 | 150000 | 141366 | -6706 | 0 | -6706 | 134660 | 134660 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452357137 | YD WEST COAST HOME INC | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-03-03 | QTR3 | 16/17 | 118 | 195237.61 | B0 | ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO | 8 | 07co | 266 | 273
01CO | 01 | T1663 | 43502515201 | 2016-08-31 | QTR1 | 16/17 | 3 | 3 | 200 | 333 | 333 | 0 | 0 | 0 | 61 | 72 | 2395063 | 50000 | 2345063 | 2800850 | 2741389 | 0 | 0 | 0 | 2741389 | 2747244 | 10825 | 405787 | 46 | 0 | 0 | 1766 | 0 | 0 | 72 | 406947 | 400817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 408713 | 400817 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-05-15 | QTR4 | 17/18 | 2017-12-01 | QTR2 | 17/18 | 113 | 2399072.74 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | CO | 14 | 07do | 274 | 287
01CO | 01 | T1668 | 43450715201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 100 | 104 | 99 | 5 | 0 | 0 | 4 | 0 | 860000 | 50000 | 810000 | 860000 | 810000 | 0 | 0 | 0 | 810000 | 810000 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2017-07-17 | QTR1 | 17/18 | 2017-04-25 | QTR4 | 16/17 | 108 | 1005379.75 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 288 | 287
01CO | 01 | T1677 | 43450615201 | 2017-02-22 | QTR3 | 16/17 | 1 | 2 | 130 | 169 | 166 | 3 | 0 | 0 | 39 | 0 | 681681 | 39099 | 642582 | 697653 | 645164 | 0 | 0 | 0 | 645164 | 630209 | 0 | 15972 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2018-03-01 | QTR3 | 17/18 | 2018-01-05 | QTR3 | 17/18 | 108 | 692725.22 | B0 | ACC - LUMP SUM | 0 | 20 | 0 | 0 | 0 | 0 |  | CO | 10 | 08do | 288 | 297
01CO | 01 | T1679 | 43660115201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 175 | 209 | 209 | 0 | 0 | 0 | 26 | 8 | 2015831 | 50000 | 1965831 | 2015831 | 1984899 | 0 | 0 | 0 | 1984899 | 2016886 | 31987 | 0 | 9 | 0 | 1 | 3158 | 0 | 0 | 7 | 15910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 19068 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-06-12 | QTR4 | 17/18 | 2018-05-05 | QTR4 | 17/18 | 108 | 1987460.72 | B0 | ACC - LUMP SUM | 8 | 17 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1680 | 43092215201 | 2017-03-29 | QTR3 | 16/17 | 1 | 0 | 70 | 76 | 50 | 26 | 0 | 0 | 6 | 0 | 206428 | 0 | 206428 | 206428 | 206428 | 0 | 0 | 0 | 206428 | 206428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2018-02-15 | QTR3 | 17/18 | 2017-12-18 | QTR2 | 17/18 | 113 | 236686.57 | B0 | ACC - LUMP SUM | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1681 | 43318115201 | 2017-03-29 | QTR3 | 16/17 | 2 | 0 | 160 | 212 | 131 | 81 | 0 | 0 | 53 | -1 | 427415 | 0 | 427415 | 427415 | 422004 | 0 | 0 | 0 | 422004 | 422004 | 0 | 0 | 47 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | F593691269 | L-J CONSTRCTN CO OF CRL FL | N/A | N/A | N/A | N/A | 2017-11-06 | QTR2 | 17/18 | 2017-10-13 | QTR2 | 17/18 | 113 | 348089.37 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | -1 | 6 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1682 | 43496215201 | 2017-05-24 | QTR4 | 16/17 | 1 | 1 | 150 | 190 | 190 | 0 | 0 | 0 | 40 | 0 | 1775437 | 50000 | 1725437 | 1781028 | 1655773 | 0 | 0 | 0 | 1655773 | 1656969 | 6786 | 5591 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-04-20 | QTR4 | 17/18 | 2018-02-07 | QTR3 | 17/18 | 118 | 1722624.26 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1689 | 43470715201 | 2017-09-27 | QTR1 | 17/18 | 1 | 0 | 100 | 108 | 92 | 16 | 0 | 0 | 8 | 0 | 553926 | 25801 | 528125 | 553926 | 528125 | 0 | 0 | 0 | 528125 | 528125 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F202246559 | WRIGHT CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2018-05-08 | QTR4 | 17/18 | 2018-04-09 | QTR4 | 17/18 | 113 | 582898.39 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1691 | 43654615201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 65 | 76 | 71 | 5 | 0 | 0 | 11 | 0 | 153287 | 6065 | 147222 | 153287 | 147222 | 0 | 0 | 0 | 147222 | 147222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-04-12 | QTR4 | 17/18 | 2018-02-05 | QTR3 | 17/18 | 115 | 115131.87 | B0 | ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1695 | 43320115201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 85 | 87 | 78 | 9 | 0 | 0 | 2 | 0 | 324149 | 16622 | 307527 | 324149 | 315985 | 0 | 0 | 0 | 315985 | 315985 | 0 | 0 | 2 | 0 | 0 | 8458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8458 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-05-09 | QTR4 | 17/18 | 2018-03-26 | QTR3 | 17/18 | 108 | 310285.33 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1696 | 43668115201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 90 | 86 | 4 | 0 | 0 | 15 | 0 | 117983 | 5276 | 112707 | 117983 | 110528 | 0 | 0 | 0 | 110528 | 110528 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-06-04 | QTR4 | 17/18 | 2018-03-29 | QTR3 | 17/18 | 108 | 105146.26 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1998 | 42271025201 | 2014-07-30 | QTR1 | 14/15 | 2 | 27 | 850 | 1090 | 1090 | 0 | 0 | 0 | 198 | 42 | 31131016 | 150000 | 30981016 | 31906922 | 31516260 | 0 | 0 | 0 | 31516260 | 29926809 | -1576116 | 775906 | 145 | 0 | 35 | 459658 | 0 | 0 | 7 | 328072 | 64792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26606 | 0 | 0 | 0 | 995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 815331 | 64792 | F650507332 | GUYMANN CONSTRUCTION OF FLORIDA INC. | N/A | N/A | N/A | N/A | 2018-06-19 | QTR4 | 17/18 | 2018-01-22 | QTR3 | 17/18 | 113 | 37523290.44 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 53 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A01 | 43134015201 | 2016-07-27 | QTR1 | 16/17 | 2 | 1 | 140 | 181 | 181 | 0 | 0 | 0 | 26 | 15 | 1006260 | 46751 | 959509 | 1032806 | 969407 | 0 | 0 | 0 | 969407 | 980874 | 11467 | 26546 | 12 | 0 | 15 | 35922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 36986 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-08-04 | QTR1 | 17/18 | 2017-06-03 | QTR4 | 16/17 | 118 | 1134236.85 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1A06 | 42910315201 | 2014-12-03 | QTR2 | 14/15 | 1 | 0 | 170 | 206 | 206 | 0 | 0 | 0 | 36 | 0 | 2539891 | 50000 | 2489891 | 2539891 | 2578009 | 0 | 0 | 0 | 2578009 | 2497434 | -80575 | 0 | 31 | 0 | 0 | 746 | 0 | 0 | 0 | 15007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15754 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-12-28 | QTR2 | 17/18 | 2015-09-14 | QTR1 | 15/16 | 108 | 2442140.29 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T9013 | 43700115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 3 | 270 | 339 | 323 | 16 | 0 | 0 | 45 | 24 | 1965358 | 50000 | 1915358 | 2093858 | 2090482 | 0 | 0 | 0 | 2090482 | 2090564 | 83 | 128500 | 0 | 0 | 0 | 387 | 0 | 26 | 24 | 156842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 24 | 178500 | 0 | F030586197 | R.M. WILLIAMS CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-12-12 | QTR2 | 17/18 | 2017-08-21 | QTR1 | 17/18 | 113 | 2398810.5 |  |  | 24 | 19 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1L76 | 43193815201 | 2013-03-21 | QTR3 | 12/13 | 1 | 0 | 100 | 185 | 493 | -308 | 308 | 0 | 85 | 0 | 775601 | 38617 | 736984 | 775601 | 267269 | -89053 | 0 | -89053 | 178216 | 256487 | 78271 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593374298 | EMPOWER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-04-03 | QTR4 | 17/18 | 2014-11-14 | QTR2 | 14/15 | 118 | 826590.47 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1N91 | 43526915201 | 2015-04-16 | QTR4 | 14/15 | 4 | 5 | 175 | 464 | 459 | 5 | 0 | 0 | 44 | 245 | 1423170 | 29305 | 1393865 | 2060086 | 1941361 | 0 | 0 | 0 | 1941361 | 1938507 | -2854 | 636916 | 7 | 0 | 61 | 572771 | 0 | 21 | 171 | 64145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 240 | 636916 | 0 | F381807765 | DOUGLAS N. HIGGINS INC. | N/A | N/A | N/A | N/A | 2018-06-21 | QTR4 | 17/18 | 2017-01-05 | QTR3 | 16/17 | 118 | 875885.34 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O46 | 43654515201 | 2015-11-19 | QTR2 | 15/16 | 1 | 2 | 115 | 164 | 164 | 0 | 0 | 0 | 37 | 12 | 704333 | 30651 | 673682 | 763036 | 748922 | 0 | 0 | 0 | 748922 | 748922 | 0 | 58703 | 15 | 0 | 12 | 30084 | 0 | 0 | 0 | 28619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 12 | 58703 | 0 | F730764097 | MANHATTAN ROAD & BRIDGE COMPANY | N/A | N/A | N/A | N/A | 2017-11-28 | QTR2 | 17/18 | 2016-09-14 | QTR1 | 16/17 | 115 | 529268.14 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O47 | 43170315201 | 2016-01-28 | QTR3 | 15/16 | 2 | 0 | 160 | 276 | 276 | 0 | 0 | 0 | 86 | 30 | 2080080 | 50000 | 2030080 | 2080080 | 2081575 | 0 | 0 | 0 | 2081575 | 2082167 | 592 | 0 | 65 | 0 | 30 | 6976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 6976 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2017-10-02 | QTR2 | 17/18 | 2017-02-23 | QTR3 | 16/17 | 113 | 2823450.85 |  |  | 30 | 21 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O50 | 43121215201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 160 | 168 | 145 | 23 | 0 | 0 | 8 | 0 | 2473492 | 50000 | 2423492 | 2473492 | 2430162 | 0 | 0 | 0 | 2430162 | 2431258 | 1097 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-06-02 | QTR4 | 16/17 | 115 | 2383341.22 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O53 | 43486515201 | 2015-12-17 | QTR2 | 15/16 | 1 | 3 | 245 | 278 | 278 | 0 | 0 | 0 | 33 | 0 | 1972999 | 50000 | 1922999 | 2017226 | 2027670 | 0 | 0 | 0 | 2027670 | 2027844 | 174 | 44227 | 5 | 14 | 0 | 37826 | 0 | 0 | 0 | 38283 | 12197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 88109 | 12197 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-08-10 | QTR1 | 17/18 | 2017-05-26 | QTR4 | 16/17 | 115 | 1579998.38 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O56 | 42799515201 | 2015-05-21 | QTR4 | 14/15 | 2 | 9 | 350 | 432 | 422 | 10 | 0 | 0 | 66 | 16 | 6985880 | 68645 | 6917235 | 7218308 | 7107622 | 0 | 0 | 0 | 7107622 | 6945376 | -162246 | 232428 | 48 | 0 | 5 | 167389 | 18637 | 0 | 11 | 38597 | 16457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 235986 | 65094 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2017-11-21 | QTR2 | 17/18 | 2016-11-02 | QTR2 | 16/17 | 115 | 7866883.02 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O77 | 43120815201 | 2016-05-19 | QTR4 | 15/16 | 2 | 6 | 355 | 393 | 307 | 86 | 0 | 0 | 26 | 12 | 5170633 | 87166 | 5083467 | 5203293 | 5192938 | 0 | 366000 | 366000 | 5558938 | 5199260 | -359678 | 32660 | 12 | 0 | 0 | 9159 | 9159 | 0 | 0 | 30936 | 5390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10463 | 0 | 0 | 0 | 4218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 56787 | 16559 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2017-10-26 | QTR2 | 17/18 | 2017-06-13 | QTR4 | 16/17 | 108 | 7193789.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 4 | 14 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1O89 | 42731525201 | 2016-04-01 | QTR4 | 15/16 | 1 | 1 | 450 | 539 | 538 | 1 | 0 | 0 | 89 | 0 | 2744297 | 50000 | 2694297 | 2808760 | 2758760 | 0 | 0 | 0 | 2758760 | 2694297 | 0 | 64463 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F943198006 | TRANSCORE ITS LLC. | N/A | N/A | N/A | N/A | 2018-04-11 | QTR4 | 17/18 | 2017-11-29 | QTR2 | 17/18 | 108 | 2744297 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P55 | 43476215201 | 2016-04-21 | QTR4 | 15/16 | 2 | 10 | 600 | 664 | 516 | 148 | 0 | 0 | 58 | 6 | 16187341 | 150000 | 16037341 | 16450162 | 16170719 | 0 | 950000 | 950000 | 17120719 | 16200920 | -872739 | 262821 | 35 | 0 | 0 | 25554 | 0 | 0 | 0 | 171431 | 4377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186439 | 4377 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2018-03-14 | QTR3 | 17/18 | 2017-12-15 | QTR2 | 17/18 | 108 | 17171779.98 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P64 | 43172315201 | 2016-08-18 | QTR1 | 16/17 | 1 | 0 | 80 | 82 | 80 | 2 | 0 | 0 | 2 | 0 | 829730 | 41730 | 788000 | 829730 | 788000 | 0 | 0 | 0 | 788000 | 788000 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 | 2017-05-31 | QTR4 | 16/17 | 118 | 915006.57 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P83 | 43496015201 | 2017-01-19 | QTR3 | 16/17 | 1 | 0 | 100 | 120 | 120 | 0 | 0 | 0 | 20 | 0 | 884000 | 46833 | 837167 | 884000 | 845823 | 0 | 0 | 0 | 845823 | 845823 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 1234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1234 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-04-06 | QTR4 | 17/18 | 2017-08-18 | QTR1 | 17/18 | 118 | 915851.72 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P84 | 43494015201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 180 | 192 | 183 | 9 | 0 | 0 | 12 | 0 | 2940436 | 50000 | 2890436 | 2940436 | 2909678 | 0 | 0 | 0 | 2909678 | 2924839 | 15161 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2018-03-01 | QTR3 | 17/18 | 2017-08-24 | QTR1 | 17/18 | 118 | 3425094.3 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P85 | 43507115201 | 2016-11-17 | QTR2 | 16/17 | 1 | 1 | 150 | 196 | 196 | 0 | 0 | 0 | 46 | 0 | 1782010 | 50000 | 1732010 | 1785646 | 1738365 | 0 | 0 | 0 | 1738365 | 1738373 | 3643 | 3636 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 3671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3671 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-01-26 | QTR3 | 17/18 | 2017-11-22 | QTR2 | 17/18 | 108 | 1557493.63 | B0 | ACC - LUMP SUM | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P86 | 43496115201 | 2016-12-15 | QTR2 | 16/17 | 1 | 1 | 130 | 176 | 176 | 0 | 0 | 0 | 39 | 7 | 1418298 | 50000 | 1368298 | 1437032 | 1407750 | 0 | 0 | 0 | 1407750 | 1407687 | -63 | 18735 | 29 | 0 | 7 | 39864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 58599 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-02-23 | QTR3 | 17/18 | 2017-09-25 | QTR1 | 17/18 | 115 | 1330643 | B0 | ACC - LUMP SUM | 7 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P88 | 43486015201 | 2017-01-31 | QTR3 | 16/17 | 1 | 1 | 105 | 135 | 135 | 0 | 0 | 0 | 30 | 0 | 2696196 | 50000 | 2646196 | 2716814 | 2562828 | 0 | 0 | 0 | 2562828 | 2545217 | 3007 | 20618 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 16342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16342 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2018-04-11 | QTR4 | 17/18 | 2017-11-16 | QTR2 | 17/18 | 115 | 3341250.31 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P89 | 43692015201 | 2016-12-15 | QTR2 | 16/17 | 1 | 2 | 250 | 362 | 357 | 5 | 0 | 0 | 82 | 30 | 5605151 | 64174 | 5540977 | 6085870 | 5887019 | 0 | 0 | 0 | 5887019 | 5929757 | 103551 | 480719 | 59 | 0 | 0 | 0 | 0 | 0 | 30 | 425993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 425993 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-22 | QTR4 | 17/18 | 2018-03-14 | QTR3 | 17/18 | 118 | 6393089.14 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1P93 | 43663815201 | 2017-01-19 | QTR3 | 16/17 | 1 | 3 | 150 | 192 | 192 | 0 | 0 | 0 | 42 | 0 | 2271296 | 50000 | 2221296 | 2325270 | 2285617 | 0 | 0 | 0 | 2285617 | 2291460 | 19656 | 53974 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40160 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-03-15 | QTR3 | 17/18 | 2017-11-08 | QTR2 | 17/18 | 113 | 2620650.05 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q60 | 43614515201 | 2017-06-15 | QTR4 | 16/17 | 1 | 0 | 225 | 251 | 219 | 32 | 0 | 0 | 26 | 0 | 1652714 | 50000 | 1602714 | 1652714 | 1595287 | 0 | 0 | 0 | 1595287 | 1594960 | -327 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F464740152 | CATHCART CONSTRUCTION COMPANY - FLORIDA | N/A | N/A | N/A | N/A | 2018-05-21 | QTR4 | 17/18 | 2018-04-11 | QTR4 | 17/18 | 108 | 874718.37 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q63 | 44095315201 | 2017-04-20 | QTR4 | 16/17 | 1 | 0 | 30 | 49 | 48 | 1 | 0 | 0 | 19 | 0 | 110918 | 9596 | 101322 | 110918 | 101322 | 0 | 0 | 0 | 101322 | 101322 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F264642586 | MCSHEA CONTRACTING LLC | N/A | N/A | N/A | N/A | 2017-11-09 | QTR2 | 17/18 | 2017-08-24 | QTR1 | 17/18 | 113 | 179085.79 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q84 | 43861715201 | 2017-06-15 | QTR4 | 16/17 | 1 | 0 | 70 | 77 | 56 | 21 | 0 | 0 | 7 | 0 | 325029 | 11099 | 313930 | 325029 | 252626 | 0 | 0 | 0 | 252626 | 256076 | 3450 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593713459 | MIDWESTERN CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2018-05-01 | QTR4 | 17/18 | 2017-12-17 | QTR2 | 17/18 | 113 | 138637.23 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1Q92 | 43495715201 | 2017-05-18 | QTR4 | 16/17 | 1 | 0 | 40 | 41 | 25 | 16 | 0 | 0 | 1 | 0 | 218056 | 17970 | 200086 | 218056 | 191926 | 0 | 25000 | 25000 | 216926 | 191926 | -25000 | 0 | 1 | 0 | 0 | 3344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3344 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-10-13 | QTR2 | 17/18 | 2017-08-17 | QTR1 | 17/18 | 118 | 167846.6 | B1 | ACC - NO EXCUSE BONUS | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2426 | 20837325201 | 2012-06-20 | QTR4 | 11/12 | 1 | 2 | 550 | 646 | 1412 | -766 | 766 | 0 | 75 | 21 | 10147516 | 118589 | 10028927 | 10201629 | 10315106 | -1110928 | 0 | -1110928 | 9204178 | 8737450 | -466728 | 54113 | 27 | 0 | 3 | 105503 | 16666 | 0 | 18 | 63011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 21 | 168514 | 16666 | Z13-3046577 | FIDELITY AND DEPOSIT COMPANY OF MARYLAND | N/A | N/A | N/A | N/A | 2018-05-23 | QTR4 | 17/18 | 2016-11-18 | QTR2 | 16/17 | 209 | 12049132.99 |  |  | 21 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2482 | 20916875201 | 2013-06-19 | QTR4 | 12/13 | 1 | 5 | 900 | 1011 | 1011 | 0 | 0 | 0 | 81 | 30 | 20538005 | 150000 | 20388005 | 21074264 | 21550372 | 0 | 0 | 0 | 21550372 | 21142359 | -408013 | 536259 | 39 | 0 | 30 | 693596 | 0 | 0 | 0 | 379915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 674366 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-05-14 | QTR4 | 17/18 | 2016-08-07 | QTR1 | 16/17 | 208 | 20493068.45 |  |  | 0 | 42 | 0 | 0 | -399145 | 0 |  | CO
02CO | 02 | T2484 | 21086545201 | 2013-09-25 | QTR1 | 13/14 | 1 | 1 | 365 | 496 | 496 | 0 | 0 | 0 | 100 | 31 | 2500683 | 50000 | 2450683 | 2484554 | 2410530 | 0 | 0 | 0 | 2410530 | 2388453 | -22077 | -16129 | 76 | 0 | 8 | 28138 | 0 | 0 | 1 | 3731 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | -16129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 16497 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-01-04 | QTR3 | 17/18 | 2015-05-16 | QTR4 | 14/15 | 209 | 2639633.26 |  |  | 9 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2515 | 21325915201 | 2014-05-07 | QTR4 | 13/14 | 1 | 7 | 550 | 768 | 768 | 0 | 0 | 0 | 146 | 72 | 10022616 | 100668 | 9921947 | 10748841 | 11713560 | 0 | 0 | 0 | 11713560 | 10970371 | -743189 | 726225 | 78 | 1 | 72 | 355716 | 232777 | 14 | 0 | 398545 | 2171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4334 | 0 | 0 | 0 | 10693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 72 | 769289 | 234949 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-05-14 | QTR4 | 17/18 | 2016-12-07 | QTR2 | 16/17 | 208 | 10434763.41 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2531 | 21308255201 | 2014-06-18 | QTR4 | 13/14 | 1 | 0 | 180 | 235 | 331 | -96 | 96 | 0 | 48 | 7 | 2996901 | 50000 | 2946901 | 2996901 | 3018348 | -276096 | 0 | -276096 | 2742252 | 2600555 | -141696 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 7 | 13966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13966 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-09 | QTR4 | 17/18 | 2015-12-01 | QTR2 | 15/16 | 209 | 2497599.17 |  |  | 7 | 5 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2548 | 20939965201 | 2014-08-27 | QTR1 | 14/15 | 2 | 2 | 770 | 923 | 919 | 4 | 0 | 0 | 153 | 0 | 14832876 | 150000 | 14682876 | 14931694 | 15170352 | 0 | 0 | 0 | 15170352 | 14252602 | -917750 | 98818 | 93 | 0 | 0 | 40183 | 0 | 0 | 0 | 37352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149669 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 | 2017-05-19 | QTR4 | 16/17 | 208 | 15494259.21 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2558 | 42880215201 | 2014-09-24 | QTR1 | 14/15 | 1 | 0 | 365 | 530 | 530 | 0 | 0 | 0 | 161 | 4 | 11419267 | 135449 | 11283818 | 11419267 | 11519213 | 0 | 0 | 0 | 11519213 | 9884932 | -1634281 | 0 | 122 | 0 | 4 | 78371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 78371 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-12 | QTR3 | 17/18 | 2016-06-17 | QTR4 | 15/16 | 214 | 11862914.12 |  |  | 4 | 39 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2571 | 42307115201 | 2015-06-17 | QTR4 | 14/15 | 2 | 1 | 420 | 755 | 755 | 0 | 0 | 0 | 329 | 6 | 23206023 | 150000 | 23056023 | 23352096 | 23326424 | 0 | 0 | 0 | 23326424 | 22086601 | -1239823 | 146073 | 267 | 0 | 5 | 56142 | 0 | 0 | 1 | 165467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2783 | 0 | 0 | 0 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 224790 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-05-15 | QTR4 | 17/18 | 2017-10-11 | QTR2 | 17/18 | 214 | 22349692.01 |  |  | 6 | 62 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2578 | 43054215201 | 2015-06-17 | QTR4 | 14/15 | 1 | 0 | 300 | 447 | 446 | 1 | 0 | 0 | 147 | 0 | 6197496 | 54454 | 6143043 | 6197496 | 6219729 | 0 | 0 | 0 | 6219729 | 5902734 | -316995 | 0 | 99 | 0 | 0 | 4070 | 0 | 0 | 0 | 22507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26577 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-10-10 | QTR2 | 17/18 | 2017-03-24 | QTR3 | 16/17 | 214 | 5697731.43 |  |  | 0 | 48 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2583 | 21311345201 | 2015-06-17 | QTR4 | 14/15 | 2 | 8 | 350 | 523 | 901 | -378 | 378 | 0 | 123 | 50 | 6310104 | 56792 | 6253313 | 6241152 | 6008764 | -1425060 | 0 | -1425060 | 4583704 | 4934012 | 365795 | -68953 | 91 | 0 | 45 | 131732 | 0 | 0 | 5 | -234003 | 4811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | -102271 | 4811 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-15 | QTR4 | 17/18 | 2018-02-19 | QTR3 | 17/18 | 208 | 5828458.9 |  |  | 12 | 32 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2590 | 42880515201 | 2015-09-30 | QTR1 | 15/16 | 1 | 0 | 340 | 577 | 577 | 0 | 0 | 0 | 232 | 5 | 12627578 | 150000 | 12477578 | 12627578 | 13136952 | 0 | 0 | 0 | 13136952 | 12671855 | -465097 | 0 | 125 | 60 | 5 | 39332 | 0 | 0 | 0 | 24651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 5 | 63984 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-03-01 | QTR3 | 17/18 | 2017-10-03 | QTR2 | 17/18 | 214 | 13903210.66 |  |  | 5 | 47 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2595 | 43273315201 | 2015-08-26 | QTR1 | 15/16 | 1 | 3 | 365 | 575 | 575 | 0 | 0 | 0 | 210 | 0 | 14598877 | 142235 | 14456642 | 14676873 | 13917260 | 0 | 0 | 0 | 13917260 | 13357978 | -559281 | 77996 | 183 | 0 | 0 | 49500 | 0 | 0 | 0 | 47996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97496 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-16 | QTR3 | 17/18 | 2017-07-31 | QTR1 | 17/18 | 209 | 14373836.6 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2599 | 43726615201 | 2016-02-24 | QTR3 | 15/16 | 1 | 0 | 180 | 213 | 213 | 0 | 0 | 0 | 33 | 0 | 1048048 | 50000 | 998048 | 1048048 | 985628 | 0 | 0 | 0 | 985628 | 985628 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES INC. | N/A | N/A | N/A | N/A | 2017-07-14 | QTR1 | 17/18 | 2017-02-21 | QTR3 | 16/17 | 216 | 1120328.18 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2601 | 21166315201 | 2015-10-28 | QTR2 | 15/16 | 1 | 1 | 400 | 443 | 440 | 3 | 0 | 0 | 40 | 3 | 3712278 | 0 | 3712278 | 3713235 | 3797768 | 0 | 0 | 0 | 3797768 | 3782265 | -15503 | 957 | 23 | 0 | 3 | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 957 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 | 2017-04-13 | QTR4 | 16/17 | 209 | 4020991.68 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2607 | 43265615201 | 2015-10-28 | QTR2 | 15/16 | 2 | 8 | 280 | 493 | 493 | 0 | 0 | 0 | 196 | 17 | 3726163 | 50000 | 3676163 | 3942398 | 4032657 | 0 | 0 | 0 | 4032657 | 3977766 | -54891 | 216235 | 149 | 0 | 12 | 139025 | 0 | 0 | 5 | 82451 | 10617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 238797 | 10617 | F261293750 | PETTICOAT-SCHMITT CIVIL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-12-26 | QTR2 | 17/18 | 2017-05-31 | QTR4 | 16/17 | 216 | 4078236.5 |  |  | 12 | 47 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2615 | 43316425201 | 2016-04-27 | QTR4 | 15/16 | 1 | 2 | 230 | 244 | 229 | 15 | 0 | 0 | 14 | 0 | 1867840 | 50000 | 1817840 | 1917840 | 1853345 | 0 | 150000 | 150000 | 2003345 | 1860008 | -143337 | 50000 | 3 | 0 | 0 | 35081 | 0 | 0 | 0 | 35033 | 0 | 0 | 0 | 2457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76376 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-10-24 | QTR2 | 17/18 | 2017-07-17 | QTR1 | 17/18 | 208 | 2133960.64 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2619 | 43265715201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 150 | 164 | 160 | 4 | 0 | 0 | 14 | 0 | 985253 | 39196 | 946057 | 985253 | 900611 | 0 | 0 | 0 | 900611 | 903976 | 3365 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-04 | QTR1 | 17/18 | 2016-12-28 | QTR2 | 16/17 | 209 | 823384.31 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2629 | 43056215201 | 2015-12-03 | QTR2 | 15/16 | 4 | 1 | 175 | 283 | 298 | -15 | 15 | 0 | 73 | 35 | 3955571 | 57673 | 3897898 | 4118052 | 4040559 | -43140 | 0 | -43140 | 3997419 | 3949454 | -47965 | 162481 | 57 | 0 | 35 | 162481 | 0 | 0 | 0 | 26106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 188587 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 | 2017-01-05 | QTR3 | 16/17 | 208 | 3564631.32 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2634 | 43225615201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 190 | 249 | 267 | -18 | 18 | 0 | 49 | 10 | 956123 | 50000 | 906123 | 956123 | 910673 | -28512 | 0 | -28512 | 882161 | 882485 | 323 | 0 | 5 | 13 | 9 | 0 | 0 | 8 | 1 | 15330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 10 | 15330 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-02-21 | QTR3 | 17/18 | 2017-07-17 | QTR1 | 17/18 | 216 | 1019427.54 |  |  | 10 | 16 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2635 | 42470035201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 75 | 140 | 135 | 5 | 0 | 0 | 57 | 8 | 348154 | 16878 | 331276 | 348154 | 353179 | 0 | 0 | 0 | 353179 | 353179 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11425 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-09-26 | QTR1 | 17/18 | 2017-07-11 | QTR1 | 17/18 | 208 | 330103.8 |  |  | 8 | 12 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2638 | 43500515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 158 | 202 | 199 | 3 | 0 | 0 | 44 | 0 | 1148616 | 49816 | 1098801 | 1148616 | 1092502 | 0 | 0 | 0 | 1092502 | 1092502 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 1706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1706 | 0 | F030527982 | J D HINSON COMPANY | N/A | N/A | N/A | N/A | 2017-12-29 | QTR2 | 17/18 | 2017-10-20 | QTR2 | 17/18 | 208 | 1088824.29 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2639 | 41142415201 | 2016-10-26 | QTR2 | 16/17 | 2 | 4 | 260 | 311 | 304 | 7 | 0 | 0 | 41 | 10 | 2159445 | 120 | 2159325 | 2188557 | 2084623 | 0 | 0 | 0 | 2084623 | 2081632 | -643 | 26764 | 25 | 0 | 10 | 43759 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 24416 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-04 | QTR4 | 17/18 | 2017-12-20 | QTR2 | 17/18 | 209 | 2356414.98 |  |  | 0 | 16 | 0 | 0 | -28343 | 0 |  | CO
02CO | 02 | T2640 | 43231315201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 145 | 181 | 179 | 2 | 0 | 0 | 36 | 0 | 2804745 | 50000 | 2754745 | 2804745 | 2745654 | 0 | 0 | 0 | 2745654 | 2752258 | 6604 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-05-07 | QTR4 | 17/18 | 2017-07-11 | QTR1 | 17/18 | 216 | 2903614.64 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2642 | 43430215201 | 2016-10-26 | QTR2 | 16/17 | 2 | 0 | 200 | 281 | 281 | 0 | 0 | 0 | 72 | 9 | 3380793 | 206100 | 3174693 | 3380793 | 3079001 | 0 | 0 | 0 | 3079001 | 3097527 | 18526 | 0 | 51 | 0 | 9 | 15861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 22462 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-02-23 | QTR3 | 17/18 | 2017-10-24 | QTR2 | 17/18 | 208 | 3680245.83 |  |  | 9 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2644 | 43429515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 90 | 93 | 86 | 7 | 0 | 0 | 3 | 0 | 1424722 | 50000 | 1374722 | 1424722 | 1389257 | 0 | 0 | 0 | 1389257 | 1391632 | 2374 | 0 | 3 | 0 | 0 | 547 | 0 | 0 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 | 2017-04-12 | QTR4 | 16/17 | 209 | 1869641.02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2645 | 43429915201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 150 | 223 | 222 | 1 | 0 | 0 | 71 | 2 | 1921891 | 50000 | 1871891 | 1921891 | 1921001 | 0 | 0 | 0 | 1921001 | 1933245 | 12244 | 0 | 60 | 0 | 2 | 7194 | 0 | 0 | 0 | 5606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12800 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-01-25 | QTR3 | 17/18 | 2017-10-05 | QTR2 | 17/18 | 208 | 1970515.95 |  |  | 2 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2646 | 43231515201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 180 | 220 | 220 | 0 | 0 | 0 | 40 | 0 | 4589348 | 50987 | 4538362 | 4589348 | 4544001 | 0 | 0 | 0 | 4544001 | 4607510 | 63509 | 0 | 29 | 0 | 0 | 4648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4648 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-16 | QTR3 | 17/18 | 2017-10-31 | QTR2 | 17/18 | 214 | 5170519.43 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2649 | 43231115201 | 2016-12-07 | QTR2 | 16/17 | 1 | 1 | 180 | 256 | 223 | 33 | 0 | 0 | 59 | 17 | 3476169 | 50000 | 3426169 | 3576658 | 3781425 | 0 | 0 | 0 | 3781425 | 3833191 | 51766 | 100489 | 44 | 0 | 0 | 1208 | 0 | 0 | 17 | 116876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 130357 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-01-12 | QTR3 | 17/18 | 2017-10-04 | QTR2 | 17/18 | 214 | 4220270.07 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2651 | 43226915201 | 2017-01-25 | QTR3 | 16/17 | 1 | 1 | 197 | 265 | 265 | 0 | 0 | 0 | 68 | 0 | 5097026 | 57071 | 5039956 | 5193738 | 5154184 | 0 | 0 | 0 | 5154184 | 5199723 | 45540 | 96712 | 43 | 0 | 0 | 89004 | 0 | 0 | 0 | 7708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96712 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | QTR4 | 17/18 | 2018-01-19 | QTR3 | 17/18 | 216 | 5759394.65 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2652 | 43226815201 | 2017-01-25 | QTR3 | 16/17 | 1 | 1 | 150 | 212 | 183 | 29 | 0 | 0 | 52 | 10 | 1128456 | 50000 | 1078456 | 1178456 | 1132814 | 0 | 0 | 0 | 1132814 | 1135885 | 3071 | 50000 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 39274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 47573 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-04-19 | QTR4 | 17/18 | 2017-12-04 | QTR2 | 17/18 | 208 | 1228718.9 |  |  | 10 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2653 | 43431815201 | 2017-01-25 | QTR3 | 16/17 | 1 | 0 | 210 | 256 | 216 | 40 | 0 | 0 | 46 | 0 | 5848696 | 70923 | 5777773 | 5848696 | 5842884 | 0 | 0 | 0 | 5842884 | 5902466 | 59582 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-04-04 | QTR4 | 17/18 | 2017-11-30 | QTR2 | 17/18 | 214 | 7299512.23 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2663 | 43431915201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 270 | 324 | 315 | 9 | 0 | 0 | 54 | 0 | 7359482 | 81879 | 7277603 | 7359482 | 7148275 | 0 | 0 | 0 | 7148275 | 7267943 | 119668 | 0 | 28 | 0 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16795 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-29 | QTR4 | 17/18 | 2018-02-01 | QTR3 | 17/18 | 214 | 8368235.32 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2664 | 43433015201 | 2017-03-29 | QTR3 | 16/17 | 2 | 0 | 200 | 240 | 240 | 0 | 0 | 0 | 40 | 0 | 2052728 | 50000 | 2002728 | 2052728 | 2009305 | 0 | 0 | 0 | 2009305 | 1996365 | -12939 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 17653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17653 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-06-27 | QTR4 | 17/18 | 2018-03-01 | QTR3 | 17/18 | 208 | 2080962 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9015 | 43475815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 240 | 291 | 291 | 0 | 0 | 0 | 21 | 30 | 913111 | 20420 | 892691 | 913111 | 890230 | 0 | 0 | 0 | 890230 | 890229 | -1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 30 | 20420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20420 | 0 | F593504786 | ANGLIN CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-08-08 | QTR1 | 17/18 | 2017-06-28 | QTR4 | 16/17 | 209 | 612984.42 |  |  | 30 | 17 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2R19 | 20960715201 | 2013-12-12 | QTR2 | 13/14 | 1 | 2 | 800 | 1141 | 1139 | 2 | 0 | 0 | 254 | 87 | 44244000 | 150000 | 44094000 | 44497660 | 44485464 | 0 | 0 | 0 | 44485464 | 43904176 | -555556 | 253660 | 105 | 61 | 87 | 261680 | 29435 | 0 | 0 | 49212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 87 | 367067 | 29435 | F363286318 | ARCHER WESTERN CONTRACTORS LLC. | N/A | N/A | N/A | N/A | 2017-08-17 | QTR1 | 17/18 | 2017-03-27 | QTR3 | 16/17 | 208 | 49888540.47 | B8 | ACC - DESIGN/BUILD - MAJOR | 87 | 88 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R22 | 43264115201 | 2013-04-25 | QTR4 | 12/13 | 1 | 1 | 520 | 709 | 728 | -19 | 19 | 0 | 101 | 88 | 23839013 | 150000 | 23689013 | 25517586 | 25531336 | -153064 | 0 | -153064 | 25378272 | 24766329 | -611943 | 1678573 | 71 | 0 | 88 | 1684540 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 1684540 | 22000 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-01-04 | QTR3 | 17/18 | 2015-07-02 | QTR1 | 15/16 | 209 | 22387890.4 | LBDB | LOW BID DESIGN BUILD | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2R95 | 42889935201 | 2013-06-19 | QTR4 | 12/13 | 1 | 0 | 200 | 258 | 609 | -351 | 351 | 0 | 58 | 0 | 483500 | 0 | 483500 | 483500 | 483510 | -134757 | 0 | -134757 | 348753 | 348753 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F161659018 | CORE CONSTRUCTION COMPANY OF JA | N/A | N/A | N/A | N/A | 2017-11-01 | QTR2 | 17/18 | 2015-05-14 | QTR4 | 14/15 | 209 | 448242.4 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 12 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T29 | 43055915201 | 2014-11-13 | QTR2 | 14/15 | 1 | 0 | 130 | 139 | 178 | -39 | 39 | 0 | 9 | 0 | 4199999 | 50000 | 4149999 | 4199999 | 4314349 | -112164 | 0 | -112164 | 4202185 | 3826662 | -375523 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-01-17 | QTR3 | 17/18 | 2015-08-28 | QTR1 | 15/16 | 209 | 4057259.23 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2T50 | 43044915201 | 2017-03-15 | QTR3 | 16/17 | 2 | 1 | 270 | 298 | 140 | 158 | 0 | 0 | 28 | 0 | 606000 | 30541 | 575459 | 609005 | 554175 | 0 | 0 | 0 | 554175 | 551170 | -1503 | 1503 | 17 | 0 | 0 | -986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8822 | 0 | F593114052 | K.V.K. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-09 | QTR3 | 17/18 | 2017-11-27 | QTR2 | 17/18 | 216 | 649753.12 | B3 | ACC - LANE RENTAL | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U33 | 43195815201 | 2015-06-30 | QTR4 | 14/15 | 1 | 1 | 300 | 454 | 454 | 0 | 0 | 0 | 124 | 30 | 3436656 | 50000 | 3386656 | 3327571 | 3278414 | 0 | 0 | 0 | 3278414 | 3274966 | -3448 | -109085 | 102 | 0 | 15 | 7337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -109085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | -101748 | 0 | F591809068 | WEST CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-11-28 | QTR2 | 17/18 | 2017-04-01 | QTR4 | 16/17 | 209 | 3590759.86 |  |  | 30 | 22 | 0 | 15 | 0 | 0 |  | DO
02DO | 02 | E2U37 | 43075615201 | 2016-03-16 | QTR3 | 15/16 | 1 | 1 | 120 | 248 | 248 | 0 | 0 | 0 | 36 | 92 | 1152620 | 49250 | 1103370 | 1152620 | 1092925 | 0 | 0 | 0 | 1092925 | 1092925 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-02-19 | QTR3 | 17/18 | 2017-08-03 | QTR1 | 17/18 | 208 | 1021841.84 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U38 | 43226615201 | 2016-03-16 | QTR3 | 15/16 | 2 | 2 | 230 | 297 | 295 | 2 | 0 | 0 | 37 | 30 | 1729034 | 100000 | 1629034 | 1814284 | 1787276 | 0 | 0 | 0 | 1787276 | 1798954 | 11678 | 85250 | 19 | 0 | 6 | 130684 | 0 | 0 | 24 | 21444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 152127 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 | 2017-04-06 | QTR4 | 16/17 | 208 | 2261728.91 |  |  | 30 | 18 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U50 | 20968615201 | 2016-05-18 | QTR4 | 15/16 | 1 | 0 | 145 | 304 | 304 | 0 | 0 | 0 | 159 | 0 | 1697762 | 50000 | 1647762 | 1697762 | 1628431 | 0 | 0 | 0 | 1628431 | 1628433 | 2 | 0 | 7 | 21 | 0 | 743 | 0 | 101 | 0 | 31423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1929 | 0 | 6 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 34575 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-05-10 | QTR4 | 17/18 | 2017-08-16 | QTR1 | 17/18 | 208 | 1682496.79 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2U92 | 43015715201 | 2016-03-16 | QTR3 | 15/16 | 1 | 0 | 200 | 277 | 277 | 0 | 0 | 0 | 67 | 10 | 4567769 | 50000 | 4517769 | 4567769 | 4034344 | 0 | 0 | 0 | 4034344 | 4034680 | 336 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2017-07-24 | QTR1 | 17/18 | 2017-05-19 | QTR4 | 16/17 | 208 | 3766652.07 |  |  | 10 | 38 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V03 | 43242015201 | 2016-05-18 | QTR4 | 15/16 | 1 | 0 | 126 | 155 | 152 | 3 | 0 | 0 | 29 | 0 | 1065911 | 42293 | 1023618 | 1065911 | 1003076 | 0 | 0 | 0 | 1003076 | 1005142 | 2066 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 | 2017-04-28 | QTR4 | 16/17 | 209 | 900493.11 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V25 | 43432015201 | 2016-11-29 | QTR2 | 16/17 | 3 | 1 | 135 | 157 | 174 | -17 | 17 | 0 | 21 | 1 | 2345000 | 50000 | 2295000 | 2419896 | 2450882 | -26928 | 0 | -26928 | 2423954 | 2449808 | 25854 | 74896 | 11 | 0 | 1 | 626 | 0 | 0 | 0 | 75816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 76442 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-01-16 | QTR3 | 17/18 | 2017-08-08 | QTR1 | 17/18 | 214 | 2443365.36 |  |  | 1 | 10 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V31 | 43434115201 | 2016-11-29 | QTR2 | 16/17 | 1 | 0 | 60 | 63 | 65 | -2 | 2 | 0 | 3 | 0 | 203115 | 9466 | 193650 | 203115 | 185168 | -1916 | 0 | -1916 | 183252 | 183252 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274354795 | MAER HOMES LLC | N/A | N/A | N/A | N/A | 2018-02-26 | QTR3 | 17/18 | 2017-05-02 | QTR4 | 16/17 | 208 | 215268.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V33 | 43430115201 | 2016-12-21 | QTR2 | 16/17 | 1 | 1 | 120 | 207 | 207 | 0 | 0 | 0 | 68 | 19 | 2694175 | 50000 | 2644175 | 2863300 | 2867453 | 0 | 0 | 0 | 2867453 | 2906553 | 39100 | 169126 | 47 | 0 | 19 | 169126 | 0 | 0 | 0 | 14573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 183698 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-02-28 | QTR3 | 17/18 | 2017-10-17 | QTR2 | 17/18 | 208 | 2907209.99 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V45 | 43526815201 | 2017-04-19 | QTR4 | 16/17 | 2 | 2 | 135 | 281 | 281 | 0 | 0 | 0 | 108 | 38 | 1232900 | 46700 | 1186200 | 1315355 | 1289463 | 0 | 0 | 0 | 1289463 | 1160707 | -62998 | 82455 | 75 | 0 | 0 | 9223 | 0 | 0 | 17 | 28282 | 16696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 37505 | 16696 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-06-07 | QTR4 | 17/18 | 2018-04-17 | QTR4 | 17/18 | 208 | 1032476.16 | B0 | ACC - LUMP SUM | 4 | 33 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V61 | 43860215201 | 2017-02-15 | QTR3 | 16/17 | 4 | 1 | 180 | 212 | 210 | 2 | 0 | 0 | 32 | 0 | 763644 | 36425 | 727219 | 770677 | 746279 | 0 | 0 | 0 | 746279 | 746279 | 0 | 7033 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 19060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19060 | 0 | F650213904 | CEDARS ELECTRO-MECHANICAL INC. | N/A | N/A | N/A | N/A | 2018-04-17 | QTR4 | 17/18 | 2018-03-02 | QTR3 | 17/18 | 209 | 765325 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V68 | 43231415201 | 2017-05-17 | QTR4 | 16/17 | 1 | 0 | 140 | 167 | 103 | 64 | 0 | 0 | 27 | 0 | 949302 | 50000 | 899302 | 949302 | 919773 | 0 | 0 | 0 | 919773 | 926046 | 6273 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 17219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17219 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2018-04-12 | QTR4 | 17/18 | 2018-02-09 | QTR3 | 17/18 | 214 | 1080181.65 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W54 | 43617115201 | 2017-08-16 | QTR1 | 17/18 | 1 | 0 | 120 | 180 | 139 | 41 | 0 | 0 | 60 | 0 | 1207306 | 50000 | 1157306 | 1207306 | 1108761 | 0 | 0 | 0 | 1108761 | 1126368 | 17607 | 0 | 16 | 0 | 0 | 4688 | 0 | 0 | 0 | 1418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6106 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2018-06-15 | QTR4 | 17/18 | 2018-03-23 | QTR3 | 17/18 | 208 | 1296537.47 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2W83 | 43617715201 | 2017-10-18 | QTR2 | 17/18 | 1 | 0 | 100 | 107 | 107 | 0 | 0 | 0 | 7 | 0 | 554774 | 32604 | 522170 | 554774 | 528314 | 0 | 0 | 0 | 528314 | 529911 | 1597 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2018-06-29 | QTR4 | 17/18 | 2018-05-11 | QTR4 | 17/18 | 208 | 689013.27 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3350 | 40716815201 | 2013-03-27 | QTR3 | 12/13 | 1 | 2 | 430 | 854 | 897 | -43 | 43 | 0 | 386 | 38 | 5692603 | 50656 | 5641947 | 5867358 | 5901155 | -138718 | 0 | -138718 | 5762437 | 5819943 | 57505 | 174754 | 245 | 0 | 29 | 93987 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 85667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 38 | 179654 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2018-06-25 | QTR4 | 17/18 | 2015-11-23 | QTR2 | 15/16 | 314 | 5114304.52 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3380 | 22067915201 | 2012-05-23 | QTR4 | 11/12 | 2 | 16 | 955 | 1636 | 1636 | 0 | 0 | 0 | 456 | 225 | 27973197 | 150000 | 27823197 | 28765517 | 28817877 | 0 | 0 | 0 | 28817877 | 27757494 | -1060383 | 792320 | 319 | 5 | 0 | 135159 | 0 | 37 | 70 | 1137365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 177 | 426650 | 213490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 247 | 1502304 | 213490 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-07-31 | QTR1 | 17/18 | 2017-03-03 | QTR3 | 16/17 | 313 | 27697061.12 |  |  | 5 | 88 | 0 | 0 | -797630 | 0 |  | CO
03CO | 03 | T3400 | 22247715201 | 2013-08-28 | QTR1 | 13/14 | 3 | 43 | 850 | 1574 | 1539 | 35 | 0 | 0 | 561 | 163 | 43091371 | 150000 | 42941371 | 47509716 | 49630327 | -24000 | 0 | -24000 | 49606327 | 47713281 | -1893046 | 4418345 | 273 | 0 | 47 | 2284506 | 956120 | 178 | 78 | 1025524 | 25541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1050648 | 13331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114517 | 0 | 0 | 0 | 28390 | 28390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 163 | 4503584 | 1023381 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2018-06-07 | QTR4 | 17/18 | 2018-03-07 | QTR3 | 17/18 | 308 | 39882529.44 |  |  | 10 | 110 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3406 | 42693215201 | 2016-06-15 | QTR4 | 15/16 | 1 | 0 | 166 | 247 | 253 | -6 | 6 | 0 | 81 | 0 | 2166253 | 50000 | 2116253 | 2166253 | 2369003 | -9504 | 0 | -9504 | 2359499 | 2363042 | 3543 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-19 | QTR2 | 17/18 | 2017-05-12 | QTR4 | 16/17 | 308 | 2386446.01 |  |  | 0 | 36 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3416 | 42450815201 | 2014-05-07 | QTR4 | 13/14 | 1 | 5 | 555 | 860 | 860 | 0 | 0 | 0 | 225 | 80 | 13977555 | 143973 | 13833583 | 15548700 | 15324392 | 0 | 0 | 0 | 15324392 | 15062237 | -262156 | 1571145 | 167 | 0 | 26 | 895372 | 207942 | 0 | 0 | 23976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82180 | 51052 | 0 | 54 | 529058 | 102561 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 80 | 1595061 | 361555 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2018-01-10 | QTR3 | 17/18 | 2016-12-09 | QTR2 | 16/17 | 308 | 14671971.16 |  |  | 13 | 50 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3484 | 43000215201 | 2015-02-25 | QTR3 | 14/15 | 3 | 14 | 300 | 644 | 600 | 44 | 0 | 0 | 315 | 29 | 4296119 | 0 | 4296119 | 6114814 | 6340441 | 0 | 0 | 0 | 6340441 | 6332694 | -7747 | 1818695 | 99 | 0 | 1 | 6824 | 0 | 0 | 7 | 1522085 | 1237952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 7 | 245665 | 82769 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 44120 | 44120 | 0 | 0 | 0 | 0 | 193 | 29 | 1818695 | 1364841 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-05-05 | QTR4 | 16/17 | 308 | 3303857.17 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3521 | 43078515201 | 2015-12-03 | QTR2 | 15/16 | 3 | 2 | 200 | 397 | 409 | -12 | 12 | 0 | 196 | 1 | 2580711 | 50000 | 2530711 | 2556235 | 2428112 | -31636 | 0 | -31636 | 2396476 | 2365069 | -31407 | -24476 | 75 | 8 | 1 | 1155 | 0 | 73 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | -20162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1 | -15973 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 | 2017-03-31 | QTR3 | 16/17 | 308 | 2532090.83 |  |  | 1 | 37 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3524 | 22251815201 | 2016-06-15 | QTR4 | 15/16 | 2 | 1 | 240 | 317 | 317 | 0 | 0 | 0 | 77 | 0 | 2046734 | 50000 | 1996734 | 2173323 | 2073501 | 0 | 0 | 0 | 2073501 | 2070847 | -2655 | 126589 | 43 | 0 | 0 | 126589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 126589 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-12-12 | QTR2 | 17/18 | 2017-10-24 | QTR2 | 17/18 | 321 | 2321587.69 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3528 | 22281815201 | 2016-06-15 | QTR4 | 15/16 | 1 | 1 | 120 | 139 | 138 | 1 | 0 | 0 | 19 | 0 | 931084 | 33811 | 897273 | 988106 | 921773 | 0 | 0 | 0 | 921773 | 921773 | 0 | 57022 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 57022 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-07-27 | QTR1 | 17/18 | 2017-05-20 | QTR4 | 16/17 | 313 | 926503.43 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3531 | 43078415201 | 2016-01-27 | QTR3 | 15/16 | 4 | 3 | 230 | 338 | 341 | -3 | 3 | 0 | 78 | 30 | 4796511 | 50000 | 4746511 | 5842667 | 5869213 | -10128 | 0 | -10128 | 5859085 | 5851868 | -7217 | 1046156 | 58 | 0 | 0 | 0 | 0 | 0 | 30 | 596890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1046753 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-11-08 | QTR2 | 17/18 | 2017-05-19 | QTR4 | 16/17 | 321 | 4833815.48 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3541 | 43046715201 | 2017-02-22 | QTR3 | 16/17 | 2 | 3 | 160 | 264 | 264 | 0 | 0 | 0 | 104 | 0 | 762396 | 0 | 762396 | 768113 | 740975 | 0 | 0 | 0 | 740975 | 741383 | 407 | 5717 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 4927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4927 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-06-27 | QTR4 | 17/18 | 2018-03-30 | QTR3 | 17/18 | 308 | 751000 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3550 | 43257015201 | 2015-12-03 | QTR2 | 15/16 | 1 | 0 | 195 | 323 | 318 | 5 | 0 | 0 | 128 | 0 | 9008956 | 100031 | 8908925 | 9008956 | 9058480 | 0 | 0 | 0 | 9058480 | 8913154 | -145326 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 7180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7180 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 | 2017-03-01 | QTR3 | 16/17 | 321 | 9047924.85 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3553 | 43273915201 | 2016-04-27 | QTR4 | 15/16 | 1 | 2 | 180 | 231 | 229 | 2 | 0 | 0 | 49 | 2 | 5112998 | 56886 | 5056112 | 5217096 | 5197254 | -15000 | 0 | -15000 | 5182254 | 5211856 | 29602 | 104098 | 31 | 0 | 2 | 49607 | 0 | 0 | 0 | 47212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 99339 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-03-10 | QTR3 | 16/17 | 321 | 5858555.67 |  |  | 2 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3557 | 43047215201 | 2016-10-26 | QTR2 | 16/17 | 3 | 3 | 325 | 475 | 476 | -1 | 1 | 0 | 150 | 0 | 3101706 | 21426 | 3080281 | 3159561 | 3107062 | -3800 | 0 | -3800 | 3103262 | 3079745 | -8031 | 57855 | 73 | 49 | 0 | 38972 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 42369 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-06-25 | QTR4 | 17/18 | 2018-05-02 | QTR4 | 17/18 | 308 | 3337302.14 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3563 | 43344815201 | 2017-03-29 | QTR3 | 16/17 | 1 | 2 | 150 | 201 | 189 | 12 | 0 | 0 | 47 | 4 | 434900 | 16291 | 418609 | 486505 | 459662 | 0 | 0 | 0 | 459662 | 460414 | 752 | 51605 | 36 | 0 | 4 | 26560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25045 | 25045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 51605 | 25045 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 | 2017-12-20 | QTR2 | 17/18 | 308 | 347118.69 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3564 | 43273615201 | 2016-01-27 | QTR3 | 15/16 | 1 | 1 | 260 | 476 | 476 | 0 | 0 | 0 | 216 | 0 | 8987040 | 99047 | 8887993 | 9020160 | 9114270 | -36735 | 0 | -36735 | 9077535 | 9043937 | -33598 | 33120 | 166 | 0 | 0 | 33120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107965 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-04 | QTR2 | 17/18 | 2017-08-02 | QTR1 | 17/18 | 308 | 10170399.14 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3566 | 43047015201 | 2017-02-22 | QTR3 | 16/17 | 2 | 2 | 135 | 182 | 181 | 1 | 0 | 0 | 47 | 0 | 740057 | 0 | 740057 | 740736 | 741918 | 0 | 0 | 0 | 741918 | 741816 | -102 | 679 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-03-26 | QTR3 | 17/18 | 2017-11-08 | QTR2 | 17/18 | 308 | 733082.39 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3574 | 43047115201 | 2016-08-31 | QTR1 | 16/17 | 1 | 0 | 125 | 166 | 172 | -6 | 6 | 0 | 41 | 0 | 710702 | 0 | 710702 | 710702 | 703481 | -9504 | 0 | -9504 | 693977 | 696276 | 2299 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-04-21 | QTR4 | 16/17 | 308 | 765580.95 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3575 | 43079115201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 65 | 72 | 72 | 0 | 0 | 0 | 7 | 0 | 1223500 | 50000 | 1173500 | 1223500 | 1204340 | 0 | 0 | 0 | 1204340 | 1216824 | 12484 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-16 | QTR1 | 17/18 | 2017-04-18 | QTR4 | 16/17 | 313 | 1644576.72 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3576 | 42857615201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 120 | 191 | 191 | 0 | 0 | 0 | 53 | 18 | 455335 | 0 | 455335 | 461101 | 462306 | 0 | 0 | 0 | 462306 | 462306 | 0 | 5766 | 40 | 0 | 0 | 0 | 0 | 0 | 18 | 5766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 5766 | 0 | F592664214 | NORTH FLORIDA CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-05-20 | QTR4 | 16/17 | 313 | 517906.59 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3577 | 43047515201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 145 | 221 | 214 | 7 | 0 | 0 | 76 | 0 | 777422 | 0 | 777422 | 777422 | 756968 | 0 | 0 | 0 | 756968 | 757588 | 619 | 0 | 34 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 | 2018-01-08 | QTR3 | 17/18 | 313 | 827647.36 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3583 | 43047415201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 120 | 181 | 181 | 0 | 0 | 0 | 61 | 0 | 450844 | 0 | 450844 | 450844 | 461793 | 0 | 0 | 0 | 461793 | 461793 | 0 | 0 | 28 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-12-12 | QTR2 | 17/18 | 2017-11-01 | QTR2 | 17/18 | 313 | 501000 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3588 | 43390415201 | 2016-10-26 | QTR2 | 16/17 | 1 | 2 | 265 | 354 | 353 | 1 | 0 | 0 | 89 | 0 | 1128303 | 0 | 1128303 | 1129920 | 1176298 | 0 | 0 | 0 | 1176298 | 1177731 | 1433 | 1617 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 1617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 1617 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2018-05-01 | QTR4 | 17/18 | 2017-12-21 | QTR2 | 17/18 | 308 | 1069862.79 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3590 | 43273815201 | 2016-03-30 | QTR3 | 15/16 | 3 | 2 | 265 | 456 | 456 | 0 | 0 | 0 | 141 | 50 | 8979888 | 97111 | 8882777 | 9089938 | 8804885 | -11500 | 0 | -11500 | 8793385 | 8851032 | 57647 | 105256 | 107 | 0 | 0 | 0 | 0 | 0 | 50 | 122455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 122455 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2018-04-17 | QTR4 | 17/18 | 2017-09-29 | QTR1 | 17/18 | 313 | 9805557.62 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3591 | 43047815201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 125 | 198 | 198 | 0 | 0 | 0 | 73 | 0 | 755934 | 0 | 755934 | 755934 | 764661 | 0 | 0 | 0 | 764661 | 765293 | 632 | 0 | 38 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2018-01-24 | QTR3 | 17/18 | 2017-12-05 | QTR2 | 17/18 | 313 | 728590.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3592 | 43466715201 | 2016-12-07 | QTR2 | 16/17 | 2 | 0 | 150 | 227 | 225 | 2 | 0 | 0 | 73 | 4 | 2446453 | 51160 | 2395293 | 2446453 | 2415161 | 0 | 0 | 0 | 2415161 | 2432529 | 17369 | 0 | 42 | 14 | 0 | 2420 | 0 | 0 | 4 | 14826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 4 | 17246 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 | 2017-10-05 | QTR2 | 17/18 | 313 | 2770764.29 |  |  | 4 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3593 | 43356915201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 132 | 203 | 207 | -4 | 4 | 0 | 57 | 14 | 1110799 | 50000 | 1060799 | 1110799 | 1075584 | -6336 | 0 | -6336 | 1069248 | 1069297 | 48 | 0 | 32 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 14 | 15186 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-10-30 | QTR2 | 17/18 | 2017-08-22 | QTR1 | 17/18 | 314 | 1069165.29 |  |  | 14 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3599 | 42820835201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 90 | 92 | 83 | 9 | 0 | 0 | 2 | 0 | 311313 | 9628 | 301685 | 311313 | 302309 | 0 | 0 | 0 | 302309 | 302309 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-02 | QTR1 | 17/18 | 2017-03-31 | QTR3 | 16/17 | 308 | 204199 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3600 | 42695115201 | 2016-02-24 | QTR3 | 15/16 | 1 | 1 | 155 | 299 | 299 | 0 | 0 | 0 | 130 | 14 | 2196017 | 50000 | 2146017 | 2209792 | 2194453 | 0 | 0 | 0 | 2194453 | 2190296 | -4157 | 13776 | 80 | 0 | 0 | 0 | 0 | 15 | 14 | 16901 | 13776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14 | 21411 | 13776 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2017-08-16 | QTR1 | 17/18 | 2017-03-29 | QTR3 | 16/17 | 308 | 2203713.84 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3601 | 43046315201 | 2016-10-26 | QTR2 | 16/17 | 1 | 0 | 150 | 225 | 224 | 1 | 0 | 0 | 75 | 0 | 937429 | 0 | 937429 | 937429 | 948863 | 0 | 0 | 0 | 948863 | 948876 | 13 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2017-12-19 | QTR2 | 17/18 | 2017-08-21 | QTR1 | 17/18 | 314 | 1073431.03 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3608 | 43356815201 | 2017-07-26 | QTR1 | 17/18 | 2 | 0 | 125 | 193 | 192 | 1 | 0 | 0 | 68 | 0 | 535448 | 29005 | 506444 | 535448 | 538259 | 0 | 0 | 0 | 538259 | 543732 | 5474 | 0 | 30 | 0 | 0 | 27200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27200 | 0 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-05-30 | QTR4 | 17/18 | 2018-04-19 | QTR4 | 17/18 | 321 | 646015.19 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3610 | 43255615201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 120 | 137 | 101 | 36 | 0 | 0 | 17 | 0 | 1354302 | 50000 | 1304302 | 1354302 | 1333996 | 0 | 0 | 0 | 1333996 | 1333996 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-11-30 | QTR2 | 17/18 | 2017-10-26 | QTR2 | 17/18 | 313 | 1817291.75 | B0 | ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3611 | 43256715201 | 2017-01-25 | QTR3 | 16/17 | 1 | 0 | 120 | 145 | 134 | 11 | 0 | 0 | 25 | 0 | 933656 | 41797 | 891860 | 933656 | 847331 | 0 | 0 | 0 | 847331 | 849907 | 2576 | 0 | 17 | 0 | 0 | 8236 | 0 | 0 | 0 | 2394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21880 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-12-04 | QTR2 | 17/18 | 2017-08-15 | QTR1 | 17/18 | 308 | 1051000 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3613 | 21995025202 | 2016-12-07 | QTR2 | 16/17 | 4 | 3 | 195 | 244 | 243 | 1 | 0 | 0 | 49 | 0 | 5413721 | 92895 | 5320825 | 5421436 | 5717509 | 0 | 0 | 0 | 5717509 | 5805268 | 87758 | 7716 | 37 | 0 | 0 | 3816 | 3816 | 0 | 0 | 4227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8042 | 3816 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2018-02-15 | QTR3 | 17/18 | 2017-10-20 | QTR2 | 17/18 | 321 | 6943781.15 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3616 | 43662215201 | 2017-03-29 | QTR3 | 16/17 | 1 | 0 | 60 | 75 | 63 | 12 | 0 | 0 | 15 | 0 | 96639 | 0 | 96639 | 96639 | 100978 | 0 | 0 | 0 | 100978 | 100978 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-08-30 | QTR1 | 17/18 | 2017-08-02 | QTR1 | 17/18 | 321 | 113500 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3620 | 43278725201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 45 | 69 | 69 | 0 | 0 | 0 | 24 | 0 | 98537 | 0 | 98537 | 98537 | 95183 | 0 | 0 | 0 | 95183 | 95183 | 0 | 0 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | F464149175 | CONCEPT CONSTRUCTION AND DEMOLI | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 | 2017-07-12 | QTR1 | 17/18 | 321 | 131241.78 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3625 | 43188315201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 75 | 140 | 140 | 0 | 0 | 0 | 63 | 2 | 966793 | 39222 | 927571 | 970978 | 923813 | 0 | 0 | 0 | 923813 | 919628 | -4185 | 4185 | 34 | 0 | 2 | 5219 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 2 | 5219 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-03-21 | QTR3 | 17/18 | 2017-11-07 | QTR2 | 17/18 | 308 | 827500 |  |  | 2 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3628 | 43626415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 60 | 85 | 81 | 4 | 0 | 0 | 25 | 0 | 798080 | 50000 | 748080 | 798080 | 766495 | 0 | 0 | 0 | 766495 | 766495 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-26 | QTR3 | 17/18 | 2018-02-01 | QTR3 | 17/18 | 313 | 1010000 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3631 | 43827525201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 90 | 120 | 105 | 15 | 0 | 0 | 30 | 0 | 140958 | 6321 | 134637 | 140958 | 128843 | 0 | 0 | 0 | 128843 | 128843 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F203990573 | MURDOCK INVESTMENTS LLC | N/A | N/A | N/A | N/A | 2018-05-30 | QTR4 | 17/18 | 2018-03-20 | QTR3 | 17/18 | 314 | 138259.04 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3643 | 43626215201 | 2017-12-06 | QTR2 | 17/18 | 1 | 0 | 60 | 62 | 55 | 7 | 0 | 0 | 2 | 0 | 550118 | 35866 | 514252 | 550118 | 526409 | 0 | 0 | 0 | 526409 | 526409 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-06-04 | QTR4 | 17/18 | 2018-03-30 | QTR3 | 17/18 | 321 | 755612.66 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3654 | 43827615201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 45 | 69 | 68 | 1 | 0 | 0 | 24 | 0 | 40030 | 1983 | 38047 | 40030 | 37300 | 0 | 0 | 0 | 37300 | 37300 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-11-08 | QTR2 | 17/18 | 2017-10-09 | QTR2 | 17/18 | 308 | 43000.39 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3657 | 40980195201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 75 | 117 | 117 | 0 | 0 | 0 | 42 | 0 | 391534 | 16972 | 374563 | 391534 | 404360 | 0 | 0 | 0 | 404360 | 404360 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2018-04-25 | QTR4 | 17/18 | 2018-03-31 | QTR3 | 17/18 | 314 | 349936.25 |  |  | 0 | 29 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3N16 | 42902475201 | 2014-12-19 | QTR2 | 14/15 | 2 | 6 | 560 | 901 | 893 | 8 | 0 | 0 | 284 | 57 | 16475693 | 150000 | 16325693 | 16845905 | 16848483 | 0 | 0 | 0 | 16848483 | 16712396 | -136087 | 370212 | 178 | 54 | 25 | 169404 | 31240 | 0 | 42 | 298911 | 57695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 51119 | 20267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 57 | 519434 | 109202 | F590840493 | GAC CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-01-04 | QTR3 | 17/18 | 2017-08-25 | QTR1 | 17/18 | 306 | 16475693 | B8:B8 | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR | -10 | 52 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3N84 | 21876225201 | 2016-07-14 | QTR1 | 16/17 | 1 | 0 | 120 | 179 | 190 | -11 | 11 | 0 | 59 | 0 | 531067 | 36301 | 494766 | 531067 | 486082 | -17424 | 0 | -17424 | 468658 | 468658 | 0 | 0 | 11 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | F592982651 | WILLIAMS INDUSTRIAL & MARINE I | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-05-01 | QTR4 | 16/17 | 321 | 761742 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O04 | 41768345201 | 2016-07-14 | QTR1 | 16/17 | 1 | 0 | 105 | 221 | 278 | -57 | 57 | 0 | 116 | 0 | 565668 | 27463 | 538205 | 565668 | 550555 | -90288 | 0 | -90288 | 460267 | 489412 | 29145 | 0 | 17 | 21 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 12350 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 | 2017-07-25 | QTR1 | 17/18 | 308 | 576618 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3O86 | 43255215201 | 2017-02-09 | QTR3 | 16/17 | 3 | 2 | 290 | 351 | 238 | 113 | 0 | 0 | 61 | 0 | 3759171 | 50000 | 3709171 | 3953037 | 3874241 | 0 | 0 | 0 | 3874241 | 3841980 | -3461 | 165067 | 40 | 0 | 0 | 9875 | 0 | 0 | 0 | 6740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159424 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-14 | QTR3 | 17/18 | 2017-12-22 | QTR2 | 17/18 | 321 | 4804332.83 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P09 | 41767745201 | 2016-07-14 | QTR1 | 16/17 | 1 | 0 | 180 | 407 | 405 | 2 | 0 | 0 | 200 | 27 | 1746205 | 50000 | 1696205 | 1746205 | 1870829 | 0 | 0 | 0 | 1870829 | 1871101 | 272 | 0 | 123 | 30 | 5 | 25895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 24100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 27 | 49995 | 0 | F590670218 | H. G. HARDERS & SON INC. | N/A | N/A | N/A | N/A | 2018-01-10 | QTR3 | 17/18 | 2017-11-21 | QTR2 | 17/18 | 314 | 1884982.7 |  |  | 27 | 47 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P11 | 43257215201 | 2016-04-14 | QTR4 | 15/16 | 1 | 0 | 210 | 314 | 313 | 1 | 0 | 0 | 104 | 0 | 6922953 | 61524 | 6861429 | 6922953 | 6941583 | 0 | 0 | 0 | 6941583 | 6966761 | 25178 | 0 | 60 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-08-29 | QTR1 | 17/18 | 2017-05-18 | QTR4 | 16/17 | 314 | 6237409.01 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P12 | 43255515201 | 2016-11-10 | QTR2 | 16/17 | 1 | 1 | 90 | 105 | 105 | 0 | 0 | 0 | 15 | 0 | 751984 | 39984 | 712000 | 801537 | 761553 | 0 | 0 | 0 | 761553 | 761553 | 0 | 49553 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 49553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 49553 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-09-14 | QTR1 | 17/18 | 2017-05-26 | QTR4 | 16/17 | 308 | 851593.48 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P15 | 43255015201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 90 | 95 | 88 | 7 | 0 | 0 | 5 | 0 | 1296000 | 50000 | 1246000 | 1296000 | 1281750 | 0 | 0 | 0 | 1281750 | 1293176 | 11426 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2017-08-28 | QTR1 | 17/18 | 2017-04-30 | QTR4 | 16/17 | 321 | 1595361.1 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P36 | 42358935201 | 2017-02-09 | QTR3 | 16/17 | 1 | 2 | 150 | 195 | 187 | 8 | 0 | 0 | 45 | 0 | 2450599 | 50000 | 2400599 | 2476226 | 2317426 | 0 | 0 | 0 | 2317426 | 2305202 | 604 | 25628 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12800 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-06-05 | QTR4 | 17/18 | 2018-02-13 | QTR3 | 17/18 | 321 | 1549641.5 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P46 | 43466815201 | 2017-06-08 | QTR4 | 16/17 | 1 | 0 | 90 | 152 | 148 | 4 | 0 | 0 | 62 | 0 | 557062 | 27215 | 529848 | 557062 | 546186 | -8400 | 0 | -8400 | 537786 | 537786 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 16368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16368 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2018-05-01 | QTR4 | 17/18 | 2018-01-26 | QTR3 | 17/18 | 308 | 571964.36 | B0 | ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P62 | 21787925201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 130 | 214 | 210 | 4 | 0 | 0 | 84 | 0 | 1094282 | 48440 | 1045842 | 1094282 | 1014445 | 0 | 0 | 0 | 1014445 | 1015749 | 1305 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-10-30 | QTR2 | 17/18 | 2017-07-19 | QTR1 | 17/18 | 314 | 1020236.95 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P74 | 22271315201 | 2016-06-09 | QTR4 | 15/16 | 1 | 1 | 120 | 137 | 137 | 0 | 0 | 0 | 17 | 0 | 916620 | 32497 | 884123 | 973642 | 931184 | 0 | 0 | 0 | 931184 | 931184 | 0 | 57022 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57022 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-05-12 | QTR4 | 16/17 | 308 | 702427.14 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P75 | 43078615201 | 2016-07-14 | QTR1 | 16/17 | 2 | 0 | 100 | 210 | 210 | 0 | 0 | 0 | 110 | 0 | 2702301 | 50119 | 2652182 | 2702301 | 2824495 | 0 | 0 | 0 | 2824495 | 2819950 | -4545 | 0 | 17 | 73 | 0 | 5732 | 0 | 4 | 0 | 14182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 19914 | 0 | F591879185 | PANHANDLE GRADING & PAVING INC. | N/A | N/A | N/A | N/A | 2017-08-03 | QTR1 | 17/18 | 2017-04-27 | QTR4 | 16/17 | 308 | 2591912.99 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3P91 | 43460615201 | 2016-10-13 | QTR2 | 16/17 | 1 | 0 | 75 | 100 | 100 | 0 | 0 | 0 | 25 | 0 | 367076 | 15130 | 351946 | 367076 | 357176 | 0 | 0 | 0 | 357176 | 357176 | 0 | 0 | 12 | 0 | 0 | 5230 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 5230 | 0 | F010692695 | MIDSOUTH PAVING INC. | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 | 2017-04-22 | QTR4 | 16/17 | 308 | 306636.35 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q09 | 43749615201 | 2017-01-12 | QTR3 | 16/17 | 1 | 0 | 50 | 89 | 88 | 1 | 0 | 0 | 39 | 0 | 360470 | 29511 | 330959 | 360470 | 302941 | 0 | 0 | 0 | 302941 | 302941 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2017-11-15 | QTR2 | 17/18 | 2017-08-30 | QTR1 | 17/18 | 321 | 618734.99 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3Q27 | 43626315201 | 2017-07-13 | QTR1 | 17/18 | 2 | 0 | 90 | 125 | 125 | 0 | 0 | 0 | 35 | 0 | 1148724 | 51111 | 1097613 | 1148724 | 1173198 | 0 | 0 | 0 | 1173198 | 1173198 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2018-03-15 | QTR3 | 17/18 | 2018-01-30 | QTR3 | 17/18 | 314 | 1210000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4360 | 40691915201 | 2013-06-19 | QTR4 | 12/13 | 2 | 10 | 919 | 1391 | 1391 | 0 | 0 | 0 | 358 | 114 | 22198458 | 150000 | 22048458 | 24242652 | 24231373 | 0 | 0 | 0 | 24231373 | 24184321 | -47051 | 2044194 | 228 | 35 | 84 | 1056338 | 304013 | 0 | 0 | 416860 | 27507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 30 | 614810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 114 | 2088008 | 331520 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2018-03-05 | QTR3 | 17/18 | 2017-08-18 | QTR1 | 17/18 | 412 | 25330673.92 |  |  | 4 | 61 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4387 | 42924625201 | 2014-04-30 | QTR4 | 13/14 | 2 | 2 | 460 | 621 | 621 | 0 | 0 | 0 | 158 | 3 | 20572640 | 150000 | 20422640 | 20874760 | 20200080 | 0 | 0 | 0 | 20200080 | 19403592 | -796488 | 302120 | 97 | 0 | 0 | 41914 | 0 | 0 | 3 | 55774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 266000 | 266000 | 34 | 0 | 20558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 3 | 392245 | 266000 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-11 | QTR2 | 17/18 | 2016-04-06 | QTR4 | 15/16 | 409 | 23230743.39 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4392 | 42873115201 | 2016-08-31 | QTR1 | 16/17 | 3 | 0 | 146 | 158 | 157 | 1 | 0 | 0 | 12 | 0 | 1894496 | 50000 | 1844496 | 1894496 | 1876142 | 0 | 0 | 0 | 1876142 | 1885605 | 9463 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 6357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14601 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-12-15 | QTR2 | 17/18 | 2017-06-08 | QTR4 | 16/17 | 412 | 2046919.21 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4393 | 42872215201 | 2015-10-28 | QTR2 | 15/16 | 2 | 3 | 228 | 398 | 402 | -4 | 4 | 0 | 118 | 52 | 7257569 | 84109 | 7173460 | 7675751 | 7429380 | -15080 | 0 | -15080 | 7414300 | 7264049 | -150251 | 418182 | 90 | 5 | 15 | 182656 | 0 | 0 | 15 | 262907 | 1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 6909 | 0 | 0 | 0 | 18227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 52 | 470700 | 1463 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2018-05-21 | QTR4 | 17/18 | 2017-03-01 | QTR3 | 16/17 | 409 | 7461270.16 |  |  | 14 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4407 | 43060115201 | 2015-12-03 | QTR2 | 15/16 | 2 | 2 | 333 | 412 | 411 | 1 | 0 | 0 | 79 | 0 | 4429693 | 50000 | 4379693 | 4522960 | 4441417 | 0 | 144900 | 144900 | 4586317 | 4419287 | -167030 | 93267 | 48 | 0 | 0 | 59120 | 0 | 0 | 0 | 18567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78567 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-09 | QTR2 | 17/18 | 2017-06-02 | QTR4 | 16/17 | 412 | 4059381.95 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4408 | 42898415201 | 2015-04-29 | QTR4 | 14/15 | 2 | 7 | 590 | 716 | 711 | 5 | 0 | 0 | 126 | 0 | 5457914 | 59401 | 5398513 | 5501915 | 5476312 | 0 | 0 | 0 | 5476312 | 5355390 | -120921 | 44001 | 96 | 0 | 0 | 8201 | 0 | 0 | 0 | 99691 | 4389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75511 | 4389 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-08-11 | QTR1 | 17/18 | 2017-06-23 | QTR4 | 16/17 | 408 | 6001634.3 |  |  | 0 | 30 | 0 | 0 | -77463 | 0 |  | CO
04CO | 04 | T4428 | 43175715201 | 2016-04-27 | QTR4 | 15/16 | 1 | 0 | 185 | 197 | 197 | 0 | 0 | 0 | 12 | 0 | 1321404 | 50000 | 1271404 | 1321404 | 1261612 | 0 | 0 | 0 | 1261612 | 1264590 | 2978 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 9018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9018 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-01-08 | QTR3 | 17/18 | 2017-05-06 | QTR4 | 16/17 | 412 | 1395149.88 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4429 | 43320715201 | 2016-02-24 | QTR3 | 15/16 | 2 | 2 | 276 | 345 | 344 | 1 | 0 | 0 | 44 | 25 | 1817368 | 50000 | 1767368 | 1866868 | 1820548 | 0 | 0 | 0 | 1820548 | 1828664 | 8115 | 49500 | 31 | 0 | 0 | 23754 | 0 | 0 | 25 | 41825 | 27746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 65579 | 27746 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-09-28 | QTR1 | 17/18 | 2017-06-27 | QTR4 | 16/17 | 412 | 1805872.62 |  |  | 25 | 13 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4436 | 43515915201 | 2017-02-22 | QTR3 | 16/17 | 2 | 0 | 74 | 95 | 94 | 1 | 0 | 0 | 21 | 0 | 363409 | 19053 | 344357 | 363409 | 342509 | 0 | 0 | 0 | 342509 | 342509 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 | 2017-09-06 | QTR1 | 17/18 | 409 | 390893.72 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4437 | 43510215201 | 2016-03-30 | QTR3 | 15/16 | 1 | 3 | 48 | 104 | 104 | 0 | 0 | 0 | 47 | 9 | 647604 | 27717 | 619887 | 693460 | 677812 | 0 | 0 | 0 | 677812 | 677812 | 0 | 45856 | 45 | 0 | 0 | 0 | 0 | 0 | 9 | 29362 | 34197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10791 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 51453 | 44988 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2017-08-08 | QTR1 | 17/18 | 2016-11-07 | QTR2 | 16/17 | 409 | 572056.26 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4440 | 43512215201 | 2016-05-25 | QTR4 | 15/16 | 1 | 0 | 237 | 272 | 267 | 5 | 0 | 0 | 35 | 0 | 1336353 | 50000 | 1286353 | 1336353 | 1276103 | 0 | 0 | 0 | 1276103 | 1277493 | 1390 | 0 | 16 | 0 | 0 | 3339 | 0 | 0 | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-17 | QTR2 | 17/18 | 2017-08-10 | QTR1 | 17/18 | 409 | 1362625.9 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4441 | 43799415201 | 2016-12-07 | QTR2 | 16/17 | 1 | 0 | 134 | 136 | 62 | 74 | 0 | 0 | 2 | 0 | 899605 | 49184 | 850421 | 899605 | 846333 | 0 | 50000 | 50000 | 896333 | 846333 | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2017-09-25 | QTR1 | 17/18 | 2017-08-15 | QTR1 | 17/18 | 412 | 1032154.5 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 2 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4442 | 43444915201 | 2016-08-31 | QTR1 | 16/17 | 1 | 0 | 169 | 212 | 210 | 2 | 0 | 0 | 43 | 0 | 413333 | 18532 | 394801 | 413333 | 384378 | 0 | 0 | 0 | 384378 | 384534 | 156 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 4513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4513 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2017-10-30 | QTR2 | 17/18 | 2017-09-25 | QTR1 | 17/18 | 412 | 393421.68 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4443 | 43427515201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 120 | 131 | 131 | 0 | 0 | 0 | 11 | 0 | 1312214 | 50000 | 1262214 | 1312214 | 1253435 | 0 | 0 | 0 | 1253435 | 1261184 | 7749 | 0 | 0 | 0 | 0 | 801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801 | 0 | F208610437 | LYNCH PAVING & CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2017-08-07 | QTR1 | 17/18 | 2017-04-21 | QTR4 | 16/17 | 408 | 1458806.8 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4448 | 43786515201 | 2017-02-22 | QTR3 | 16/17 | 2 | 1 | 119 | 157 | 157 | 0 | 0 | 0 | 38 | 0 | 279149 | 13386 | 265763 | 282353 | 271123 | 0 | 0 | 0 | 271123 | 264714 | -3205 | 3205 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 6026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6026 | 0 | F650861113 | I & C EARTHMOVERS CORP. | N/A | N/A | N/A | N/A | 2018-02-14 | QTR3 | 17/18 | 2017-11-08 | QTR2 | 17/18 | 412 | 272833.13 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4458 | 43168715201 | 2017-02-22 | QTR3 | 16/17 | 1 | 0 | 88 | 117 | 116 | 1 | 0 | 0 | 29 | 0 | 234419 | 13120 | 221300 | 234419 | 219157 | 0 | 0 | 0 | 219157 | 219157 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2017-10-06 | QTR2 | 17/18 | 2017-08-28 | QTR1 | 17/18 | 412 | 262846.25 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4K49 | 42279615201 | 2010-12-03 | QTR2 | 10/11 | 4 | 17 | 770 | 1766 | 1894 | -128 | 128 | 0 | 223 | 773 | 84027062 | 150000 | 83877062 | 128024336 | 127605903 | -1137325 | 0 | -1137325 | 126468579 | 126905951 | 437373 | 43997274 | 178 | 0 | 105 | 962107 | 0 | 0 | 335 | 30312020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 12553147 | 0 | 0 | 0 | 259786 | 0 | 0 | 0 | -162117 | 0 | 0 | 0 | 153417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773 | 44078361 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-01-10 | QTR3 | 17/18 | 2017-02-02 | QTR3 | 16/17 | 412 | 102208657 | ARRA:B8:Y:ARR::Y | AMERICAN RECOVERY AND REINVEST:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:AMERICAN RECOVERY AND REINVEST:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 45 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4Q43 | 22939625201 | 2015-04-15 | QTR4 | 14/15 | 1 | 0 | 450 | 613 | 613 | 0 | 0 | 0 | 159 | 4 | 9189394 | 64394 | 9125000 | 9189394 | 9232946 | 0 | 148500 | 148500 | 9381446 | 8920506 | -460940 | 0 | 118 | 0 | 0 | 13790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 16262 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-30 | QTR2 | 17/18 | 2017-02-20 | QTR3 | 16/17 | 409 | 6467904.26 | A3:B5:Y | ICC - DESIGN/BUILD - MINOR:ACC - INCENTIVE/DISINCENTIVE:DESIGN/BUILD PROJECT | 4 | 41 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R04 | 43062515201 | 2015-06-12 | QTR4 | 14/15 | 1 | 0 | 255 | 296 | 293 | 3 | 0 | 0 | 41 | 0 | 1604618 | 50000 | 1554618 | 1604618 | 1554867 | 0 | 0 | 0 | 1554867 | 1554752 | -115 | 0 | 23 | 0 | 0 | 6891 | 0 | 0 | 0 | 1506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8397 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-07 | QTR1 | 17/18 | 2017-06-28 | QTR4 | 16/17 | 412 | 1736394.32 | B0 | ACC - LUMP SUM | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R64 | 43664615201 | 2016-03-04 | QTR3 | 15/16 | 1 | 1 | 458 | 520 | 412 | 108 | 0 | 0 | 62 | 0 | 8161674 | 109400 | 8052274 | 8192052 | 8168056 | 0 | 300000 | 300000 | 8468056 | 8188367 | -279689 | 30378 | 47 | 0 | 0 | 5673 | 0 | 0 | 0 | 31277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30378 | 0 | 0 | 0 | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67882 | 0 | F471114933 | MORRISON - COBALT JV | N/A | N/A | N/A | N/A | 2017-12-21 | QTR2 | 17/18 | 2017-07-22 | QTR1 | 17/18 | 408 | 11010250.52 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R66 | 42872725201 | 2016-03-04 | QTR3 | 15/16 | 1 | 1 | 293 | 331 | 331 | 0 | 0 | 0 | 38 | 0 | 2866096 | 50000 | 2816096 | 3030096 | 3026692 | 0 | 0 | 0 | 3026692 | 3026963 | 272 | 164000 | 21 | 0 | 0 | 167040 | 30703 | 0 | 0 | 17339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197428 | 30703 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 | 2017-06-30 | QTR4 | 16/17 | 412 | 1839665.45 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R68 | 43750315201 | 2016-07-01 | QTR1 | 16/17 | 1 | 2 | 252 | 272 | 213 | 59 | 0 | 0 | 20 | 0 | 4071704 | 50278 | 4021426 | 4123622 | 4162840 | 0 | 100000 | 100000 | 4262840 | 4159065 | -103775 | 51918 | 10 | 0 | 0 | 22683 | 0 | 0 | 0 | 28003 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90643 | 153 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-11-29 | QTR2 | 17/18 | 2017-04-12 | QTR4 | 16/17 | 406 | 5128284.05 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4R80 | 43232615201 | 2016-12-02 | QTR2 | 16/17 | 1 | 0 | 190 | 241 | 241 | 0 | 0 | 0 | 51 | 0 | 2142842 | 50000 | 2092842 | 2142842 | 2107961 | 0 | 0 | 0 | 2107961 | 2118375 | 10414 | 0 | 42 | 0 | 0 | 3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3701 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-02-08 | QTR3 | 17/18 | 2017-10-23 | QTR2 | 17/18 | 408 | 2054272.34 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S04 | 43110715201 | 2016-10-14 | QTR2 | 16/17 | 1 | 0 | 102 | 118 | 116 | 2 | 0 | 0 | 16 | 0 | 289809 | 14415 | 275394 | 289809 | 270949 | 0 | 0 | 0 | 270949 | 270949 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F631232066 | CONCRETE SERVICES LLC | N/A | N/A | N/A | N/A | 2017-08-23 | QTR1 | 17/18 | 2017-06-09 | QTR4 | 16/17 | 412 | 303225.64 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S17 | 43397715201 | 2017-01-06 | QTR3 | 16/17 | 1 | 0 | 28 | 34 | 33 | 1 | 0 | 0 | 6 | 0 | 280209 | 12373 | 267836 | 280209 | 215232 | 0 | 0 | 0 | 215232 | 215232 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10803 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-09-20 | QTR1 | 17/18 | 2017-07-20 | QTR1 | 17/18 | 412 | 253963.62 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S18 | 43110615201 | 2017-01-06 | QTR3 | 16/17 | 3 | 2 | 154 | 181 | 180 | 1 | 0 | 0 | 61 | -34 | 1025128 | 50000 | 975128 | 1057971 | 1006759 | 0 | 0 | 0 | 1006759 | 973916 | -16422 | 16422 | 52 | 0 | 0 | 9460 | 0 | 0 | -34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34 | 9460 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 | 2017-10-20 | QTR2 | 17/18 | 409 | 3357102.02 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S28 | 43793415201 | 2017-03-03 | QTR3 | 16/17 | 2 | 1 | 169 | 204 | 147 | 57 | 0 | 0 | 35 | 0 | 316709 | 17954 | 298755 | 319147 | 303591 | 0 | 0 | 0 | 303591 | 298717 | -2437 | 2437 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F473077227 | TADEOS ENGINEERING LLC | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 | 2017-10-23 | QTR2 | 17/18 | 412 | 371789.25 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4S33 | 43334915201 | 2017-04-07 | QTR4 | 16/17 | 4 | 1 | 138 | 180 | 180 | 0 | 0 | 0 | 42 | 0 | 460000 | 22899 | 437101 | 464502 | 437196 | 0 | 0 | 0 | 437196 | 430636 | -2057 | 4503 | 21 | 0 | 0 | 6568 | 0 | 0 | 0 | 6064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12632 | 0 | F650503073 | ARC ELECTRIC INC | N/A | N/A | N/A | N/A | 2018-05-08 | QTR4 | 17/18 | 2018-02-06 | QTR3 | 17/18 | 408 | 473230.59 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | BE035 | 43387415201 | 2015-08-10 | QTR1 | 15/16 | 1 | 6 | 345 | 494 | 495 | -1 | 1 | 0 | 40 | 109 | 8947000 | 150000 | 8797000 | 9057405 | 9057405 | 0 | 0 | 0 | 9057405 | 9057101 | -304 | 110405 | 19 | 0 | 55 | 165982 | 14523 | 0 | 54 | -39561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 110405 | 14523 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-05-05 | QTR4 | 16/17 | 509 | 8947000 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | BE042 | 43643615201 | 2015-07-20 | QTR1 | 15/16 | 1 | 4 | 527 | 552 | 552 | 0 | 0 | 0 | 25 | 0 | 4349110 | 150000 | 4199110 | 4305862 | 4305862 | 0 | 0 | 0 | 4305862 | 4305862 | 0 | -43247 | 6 | 0 | 0 | 84597 | 0 | 0 | 0 | -150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43247 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2017-10-11 | QTR2 | 17/18 | 2017-08-03 | QTR1 | 17/18 | 509 | 2601707 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | BE227 | 43029015201 | 2016-04-22 | QTR4 | 15/16 | 1 | 5 | 220 | 244 | 243 | 1 | 0 | 0 | 24 | 0 | 1697000 | 50000 | 1647000 | 1771015 | 1771015 | 0 | 0 | 0 | 1771015 | 1771300 | 285 | 74015 | 19 | 0 | 0 | 62930 | 0 | 0 | 0 | 11085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74015 | 0 | F592143889 | COLLAGE DESIGN AND CONSTRUCTION GROUP I | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-05-12 | QTR4 | 16/17 | 513 | 1668323.35 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5466 | 43066525201 | 2013-07-31 | QTR1 | 13/14 | 2 | 1 | 109 | 136 | 410 | -274 | 274 | 0 | 27 | 0 | 650999 | 38000 | 612999 | 630759 | 395792 | 0 | 0 | 0 | 395792 | 395792 | 0 | -20240 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20240 | 0 | Z59-1673015 | BANKERS INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2018-06-13 | QTR4 | 17/18 | 2014-12-08 | QTR2 | 14/15 | 515 | 828132.5 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5468 | 42887615201 | 2013-12-04 | QTR2 | 13/14 | 1 | 2 | 300 | 436 | 455 | -19 | 19 | 0 | 131 | 5 | 5811896 | 62000 | 5749896 | 5828065 | 5929467 | -61294 | 0 | -61294 | 5868173 | 5738344 | -129829 | 16169 | 104 | 0 | 5 | 45612 | 0 | 0 | 0 | 19937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11357 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 76906 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2017-10-06 | QTR2 | 17/18 | 2015-06-24 | QTR4 | 14/15 | 514 | 6328169.8 | B0 | ACC - LUMP SUM | 3 | 27 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5514 | 43065815201 | 2015-06-17 | QTR4 | 14/15 | 2 | 4 | 300 | 466 | 466 | 0 | 0 | 0 | 119 | 47 | 2758832 | 50000 | 2708832 | 3022207 | 3025677 | 0 | 0 | 0 | 3025677 | 2881446 | -115108 | 263375 | 92 | 0 | 0 | 0 | 0 | 2 | 0 | 40418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 205488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 47 | 245906 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-10-27 | QTR2 | 17/18 | 2017-03-16 | QTR3 | 16/17 | 514 | 2936599.78 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5516 | 23968315201 | 2015-03-25 | QTR3 | 14/15 | 3 | 9 | 750 | 686 | 606 | 80 | 0 | 0 | 56 | -120 | 16187452 | 150000 | 16037452 | 16131784 | 15468614 | 0 | 316000 | 316000 | 15784614 | 14731955 | -991289 | -55668 | 29 | 0 | 0 | 78814 | 0 | 0 | 0 | 220522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -120 | -4653 | 0 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-10-13 | QTR2 | 17/18 | 2017-06-01 | QTR4 | 16/17 | 509 | 16443271.05 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 27 | 0 | -120 | -340989 | 0 |  | CO
05CO | 05 | T5523 | 43064315201 | 2015-03-25 | QTR3 | 14/15 | 1 | 2 | 520 | 767 | 788 | -21 | 21 | 0 | 230 | 17 | 26022554 | 150000 | 25872554 | 26092001 | 26837874 | -244771 | 0 | -244771 | 26593103 | 24360936 | -2232167 | 69447 | 185 | 0 | 17 | 76392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 76392 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-12-08 | QTR2 | 17/18 | 2017-08-22 | QTR1 | 17/18 | 512 | 32995661.17 |  |  | 2 | 45 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5533 | 42728015201 | 2015-07-29 | QTR1 | 15/16 | 2 | 9 | 340 | 466 | 494 | -28 | 28 | 0 | 65 | 61 | 8422850 | 50000 | 8372850 | 8665412 | 8608390 | -105560 | 0 | -105560 | 8502830 | 8174179 | -328651 | 242562 | 33 | 0 | 0 | 4603 | 0 | 0 | 46 | 107535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 176219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 288356 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2017-09-05 | QTR1 | 17/18 | 2017-04-04 | QTR4 | 16/17 | 512 | 8647534.74 |  |  | 39 | 32 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5546 | 43234215201 | 2016-06-15 | QTR4 | 15/16 | 2 | 1 | 230 | 376 | 373 | 3 | 0 | 0 | 144 | 2 | 2075235 | 50000 | 2025235 | 2088068 | 2079010 | 0 | 0 | 0 | 2079010 | 2057061 | -9116 | 12833 | 86 | 0 | 0 | 0 | 0 | 20 | 2 | 23721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2 | 23721 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-28 | QTR4 | 17/18 | 2017-12-07 | QTR2 | 17/18 | 514 | 1799214 |  |  | 2 | 38 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5547 | 43240715201 | 2016-01-27 | QTR3 | 15/16 | 3 | 5 | 370 | 396 | 395 | 1 | 0 | 0 | 26 | 0 | 5090422 | 50000 | 5040422 | 5188654 | 5185897 | 0 | 0 | 0 | 5185897 | 5163808 | -19514 | 98232 | 12 | 0 | 0 | 14392 | 0 | 0 | 0 | 96878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114283 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-03-01 | QTR3 | 17/18 | 2017-05-26 | QTR4 | 16/17 | 509 | 4488965.86 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5549 | 43240215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 4 | 250 | 367 | 367 | 0 | 0 | 0 | 117 | 0 | 4288764 | 50000 | 4238764 | 4479588 | 4434500 | 0 | 0 | 0 | 4434499 | 4445448 | 17674 | 207821 | 96 | 0 | 0 | 16197 | 0 | 0 | 0 | 88205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203911 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2018-04-18 | QTR4 | 17/18 | 2017-07-29 | QTR1 | 17/18 | 509 | 4897477.97 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5553 | 43242115201 | 2016-03-30 | QTR3 | 15/16 | 1 | 1 | 150 | 171 | 169 | 2 | 0 | 0 | 21 | 0 | 1085604 | 50000 | 1035604 | 1087044 | 1021639 | -6360 | 0 | -6360 | 1015279 | 1026222 | 10943 | 1440 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 6692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6692 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-07-13 | QTR1 | 17/18 | 2017-04-24 | QTR4 | 16/17 | 595 | 1163003.22 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5554 | 43066715202 | 2016-06-15 | QTR4 | 15/16 | 6 | 3 | 320 | 457 | 455 | 2 | 0 | 0 | 126 | 11 | 5357590 | 61400 | 5296190 | 5415657 | 5363913 | 0 | 0 | 0 | 5363913 | 5291189 | -8188 | 58067 | 100 | 0 | 8 | 31331 | 0 | 0 | 0 | -6469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 27077 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-05-15 | QTR4 | 17/18 | 2017-12-08 | QTR2 | 17/18 | 514 | 6206642.55 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 11 | 26 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5563 | 43067815201 | 2016-06-15 | QTR4 | 15/16 | 3 | 6 | 480 | 590 | 564 | 26 | 0 | 0 | 103 | 7 | 10074300 | 133000 | 9941300 | 10356846 | 10457771 | 0 | 0 | 0 | 10457771 | 10390989 | -11520 | 282546 | 55 | 0 | 0 | 18240 | 0 | 0 | 0 | 44935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 292360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 355535 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2018-06-28 | QTR4 | 17/18 | 2018-03-01 | QTR3 | 17/18 | 513 | 13456513.9 |  |  | 0 | 48 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5565 | 43065715201 | 2016-07-27 | QTR1 | 16/17 | 1 | 0 | 230 | 273 | 273 | 0 | 0 | 0 | 43 | 0 | 3028041 | 50000 | 2978041 | 3028041 | 2950282 | 0 | 0 | 0 | 2950282 | 2950886 | 604 | 0 | 24 | 0 | 0 | 5094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5094 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-09-08 | QTR1 | 17/18 | 2017-07-21 | QTR1 | 17/18 | 514 | 3357586 | B0 | ACC - LUMP SUM | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5566 | 43243715201 | 2016-07-27 | QTR1 | 16/17 | 1 | 2 | 150 | 195 | 195 | 0 | 0 | 0 | 37 | 8 | 3766852 | 50000 | 3716852 | 3749136 | 3790510 | 0 | 0 | 0 | 3790510 | 3819315 | 28805 | -17716 | 20 | 0 | 0 | -8096 | 0 | 0 | 8 | 12412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4316 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-09-08 | QTR1 | 17/18 | 2017-05-08 | QTR4 | 16/17 | 514 | 4106500.86 |  |  | 8 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5567 | 43442415201 | 2016-07-27 | QTR1 | 16/17 | 1 | 1 | 120 | 243 | 264 | -21 | 21 | 0 | 27 | 96 | 1345000 | 50000 | 1295000 | 1345000 | 1239674 | 0 | 0 | 0 | 1239674 | 1239674 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 5 | 7372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 7372 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2018-02-15 | QTR3 | 17/18 | 2017-07-17 | QTR1 | 17/18 | 509 | 1380185.4 | B0 | ACC - LUMP SUM | 5 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5568 | 43442515201 | 2016-07-27 | QTR1 | 16/17 | 2 | 1 | 130 | 160 | 158 | 2 | 0 | 0 | 30 | 0 | 1275035 | 50000 | 1225035 | 1276035 | 1191362 | 0 | 0 | 0 | 1191362 | 1191683 | 320 | 1000 | 27 | 0 | 0 | 4775 | 0 | 0 | 0 | 5034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9809 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-03-08 | QTR3 | 17/18 | 2017-06-30 | QTR4 | 16/17 | 509 | 1313711 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5574 | 43241615201 | 2016-08-31 | QTR1 | 16/17 | 1 | 1 | 170 | 232 | 230 | 2 | 0 | 0 | 42 | 20 | 3274900 | 36000 | 3238900 | 3420024 | 3368050 | 0 | 0 | 0 | 3368050 | 3391256 | 23206 | 145124 | 26 | 0 | 20 | 145124 | 0 | 0 | 0 | 3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 167246 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2017-10-31 | QTR2 | 17/18 | 2017-07-14 | QTR1 | 17/18 | 509 | 3753389.85 | B0 | ACC - LUMP SUM | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5576 | 41503055201 | 2016-06-15 | QTR4 | 15/16 | 4 | 5 | 320 | 481 | 480 | 1 | 0 | 0 | 103 | 58 | 5373132 | 61500 | 5311632 | 5659631 | 5489222 | 0 | 0 | 0 | 5489222 | 5482158 | 31462 | 245499 | 78 | 0 | 18 | 147936 | 0 | 0 | 40 | 83427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 231363 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2018-06-28 | QTR4 | 17/18 | 2018-04-28 | QTR4 | 17/18 | 507 | 6329513.9 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5581 | 43304015201 | 2016-12-07 | QTR2 | 16/17 | 4 | 2 | 230 | 277 | 277 | 0 | 0 | 0 | 47 | 0 | 1118456 | 50000 | 1068456 | 1151446 | 1116798 | 0 | 0 | 0 | 1116798 | 1116571 | 1214 | 32989 | 22 | 0 | 0 | 3707 | 0 | 0 | 0 | 11645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46901 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-03-29 | QTR3 | 17/18 | 2018-02-07 | QTR3 | 17/18 | 507 | 1259440.1 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5583 | 43505215201 | 2016-09-28 | QTR1 | 16/17 | 1 | 0 | 160 | 168 | 159 | 9 | 0 | 0 | 8 | 0 | 990233 | 50000 | 940233 | 990233 | 940233 | 0 | 0 | 0 | 940233 | 940251 | 18 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2017-12-11 | QTR2 | 17/18 | 2017-08-18 | QTR1 | 17/18 | 509 | 1091962.75 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5586 | 43469415201 | 2017-03-29 | QTR3 | 16/17 | 2 | 2 | 80 | 132 | 132 | 0 | 0 | 0 | 45 | 7 | 727458 | 30000 | 697458 | 768228 | 756229 | 0 | 0 | 0 | 756229 | 735459 | 0 | 40770 | 39 | 0 | 0 | 0 | 0 | 0 | 7 | 38001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 38001 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-04-05 | QTR4 | 17/18 | 2017-11-14 | QTR2 | 17/18 | 509 | 645877.5 |  |  | 7 | 6 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5593 | 43635615201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 90 | 97 | 41 | 56 | 0 | 0 | 7 | 0 | 264250 | 24250 | 240000 | 264250 | 240000 | 0 | 0 | 0 | 240000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2018-03-21 | QTR3 | 17/18 | 2017-12-04 | QTR2 | 17/18 | 515 | 541050 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5594 | 43636415201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 140 | 151 | 98 | 53 | 0 | 0 | 11 | 0 | 452000 | 30000 | 422000 | 452000 | 422000 | 0 | 0 | 0 | 422000 | 422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2018-05-30 | QTR4 | 17/18 | 2018-03-14 | QTR3 | 17/18 | 509 | 653172.35 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5595 | 43623615201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 60 | 79 | 73 | 6 | 0 | 0 | 19 | 0 | 325875 | 18000 | 307875 | 325875 | 307875 | 0 | 0 | 0 | 307875 | 307875 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2018-03-19 | QTR3 | 17/18 | 2018-02-13 | QTR3 | 17/18 | 514 | 393057.85 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5596 | 43637115201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 60 | 67 | 56 | 11 | 0 | 0 | 7 | 0 | 148500 | 6500 | 142000 | 148500 | 142000 | 0 | 0 | 0 | 142000 | 142000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F341337287 | AKCA INC. | N/A | N/A | N/A | N/A | 2018-05-03 | QTR4 | 17/18 | 2017-12-19 | QTR2 | 17/18 | 512 | 188225 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5599 | 43623515201 | 2017-07-26 | QTR1 | 17/18 | 1 | 0 | 80 | 110 | 108 | 2 | 0 | 0 | 27 | 3 | 456461 | 27000 | 429461 | 456461 | 456461 | 0 | 0 | 0 | 456461 | 456461 | 0 | 0 | 11 | 0 | 3 | 14438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 27000 | 0 | F341233573 | OGLESBY CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-03-19 | QTR3 | 17/18 | 2018-02-09 | QTR3 | 17/18 | 513 | 580001 |  |  | 3 | 16 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5603 | 43440815201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 90 | 121 | 103 | 18 | 0 | 0 | 31 | 0 | 413889 | 25000 | 388889 | 413889 | 405966 | 0 | 0 | 0 | 405966 | 405966 | 0 | 0 | 11 | 0 | 0 | 3265 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4090 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-05-08 | QTR4 | 17/18 | 2018-03-21 | QTR3 | 17/18 | 512 | 623229.4 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5610 | 44113015201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 70 | 81 | 21 | 60 | 0 | 0 | 11 | 0 | 67500 | 5000 | 62500 | 67500 | 63500 | 0 | 0 | 0 | 63500 | 63500 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591669706 | COASTAL MARINE CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-01-30 | QTR3 | 17/18 | 2017-09-25 | QTR1 | 17/18 | 514 | 112350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5611 | 44113025201 | 2017-06-14 | QTR4 | 16/17 | 4 | 1 | 90 | 102 | 91 | 11 | 0 | 0 | 12 | 0 | 332500 | 21850 | 310650 | 345530 | 326210 | 0 | 0 | 0 | 326210 | 326210 | 0 | 13030 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2018-03-30 | QTR3 | 17/18 | 2017-12-19 | QTR2 | 17/18 | 514 | 569600 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5613 | 44113045201 | 2017-06-14 | QTR4 | 16/17 | 2 | 0 | 130 | 183 | 182 | 1 | 0 | 0 | 53 | 0 | 184425 | 10900 | 173525 | 184425 | 206750 | 0 | 0 | 0 | 206750 | 206750 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F462078794 | CWA ENVIRONMENTAL SERVICES LLC | N/A | N/A | N/A | N/A | 2018-04-17 | QTR4 | 17/18 | 2018-02-28 | QTR3 | 17/18 | 514 | 249956.54 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5614 | 44113055201 | 2017-06-14 | QTR4 | 16/17 | 1 | 0 | 80 | 185 | 185 | 0 | 0 | 0 | 105 | 0 | 107445 | 7500 | 99945 | 107445 | 107255 | 0 | 0 | 0 | 107255 | 107255 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593146076 | POWERCORE INC. | N/A | N/A | N/A | N/A | 2018-05-22 | QTR4 | 17/18 | 2018-04-17 | QTR4 | 17/18 | 514 | 168140 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T9017 | 43730315201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 135 | 196 | 196 | 0 | 0 | 0 | 54 | 7 | 749800 | 0 | 749800 | 824780 | 791911 | 0 | 0 | 0 | 791911 | 791926 | 15 | 74980 | 15 | 0 | 0 | 0 | 0 | 23 | 7 | 86923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 7 | 88179 | 0 | F030586197 | R.M. WILLIAMS CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-05-29 | QTR4 | 17/18 | 2018-03-19 | QTR3 | 17/18 | 513 | 478764.76 |  |  | 7 | 16 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E5R16 | 40846415201 | 2012-02-03 | QTR3 | 11/12 | 2 | 14 | 900 | 1825 | 1825 | 0 | 0 | 0 | 544 | 381 | 134462000 | 150000 | 134312000 | 142782598 | 143964934 | -226500 | 0 | -226500 | 143738434 | 140483406 | -3054710 | 8320598 | 400 | 0 | 62 | -391641 | 0 | 0 | 267 | 9075569 | 3527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 82418 | 3383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 329 | 8268451 | 6910 | F030569589 | CONDOTTE/DE MOYA JV LLC | N/A | N/A | N/A | N/A | 2018-06-27 | QTR4 | 17/18 | 2017-05-07 | QTR4 | 16/17 | 513 | 134462000 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 143 | 0 | 0 | -497895 | 0 |  | DO
05DO | 05 | E5W10 | 24262625201 | 2014-06-25 | QTR4 | 13/14 | 2 | 13 | 800 | 1027 | 960 | 67 | 0 | 0 | 215 | 12 | 76960400 | 150000 | 76810400 | 78949466 | 78905602 | -2960 | 500000 | 497040 | 79402642 | 74147945 | -5253206 | 1989066 | 129 | 0 | 12 | 1372538 | 271485 | 32 | 0 | 139811 | 64469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208829 | 0 | 0 | 0 | 394803 | 223994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 12 | 2115980 | 559948 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-10-02 | QTR2 | 17/18 | 2017-04-21 | QTR4 | 16/17 | 515 | 74117581 | B2:B5:B8 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 0 | 54 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y06 | 43544325201 | 2016-03-29 | QTR3 | 15/16 | 1 | 1 | 225 | 508 | 518 | -10 | 10 | 0 | 48 | 235 | 1130290 | 50000 | 1080290 | 1130290 | 958974 | 0 | 0 | 0 | 958974 | 958974 | 0 | 0 | 2 | 0 | 28 | 0 | 0 | 0 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2018-05-15 | QTR4 | 17/18 | 2017-11-17 | QTR2 | 17/18 | 594 | 1120522.5 |  |  | 28 | 11 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y27 | 43750115201 | 2016-05-03 | QTR4 | 15/16 | 2 | 0 | 170 | 361 | 359 | 2 | 0 | 0 | 29 | 162 | 1337625 | 56000 | 1281625 | 1337625 | 1189585 | 0 | 0 | 0 | 1189585 | 1190243 | 659 | 0 | 13 | 0 | 0 | 1786 | 0 | 0 | 162 | 2956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 4742 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2017-12-29 | QTR2 | 17/18 | 2017-08-30 | QTR1 | 17/18 | 515 | 1320391 |  |  | 162 | 16 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y32 | 43445515201 | 2016-08-02 | QTR1 | 16/17 | 1 | 0 | 120 | 189 | 177 | 12 | 0 | 0 | 69 | 0 | 622133 | 26000 | 596133 | 622133 | 564614 | 0 | 0 | 0 | 564614 | 564745 | 131 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2017-09-06 | QTR1 | 17/18 | 2017-04-28 | QTR4 | 16/17 | 513 | 567682.87 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y34 | 43744415201 | 2016-09-07 | QTR1 | 16/17 | 1 | 0 | 140 | 153 | 152 | 1 | 0 | 0 | 13 | 0 | 793972 | 40000 | 753972 | 793972 | 619065 | 0 | 0 | 0 | 619065 | 621005 | 1940 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2017-10-16 | QTR2 | 17/18 | 2017-05-14 | QTR4 | 16/17 | 509 | 843684 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y35 | 42302915201 | 2016-10-04 | QTR2 | 16/17 | 2 | 1 | 90 | 118 | 116 | 2 | 0 | 0 | 28 | 0 | 900963 | 36000 | 864963 | 905489 | 870490 | 0 | 0 | 0 | 870490 | 870490 | 0 | 4526 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5527 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2018-03-16 | QTR3 | 17/18 | 2017-06-29 | QTR4 | 16/17 | 509 | 774382.55 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y36 | 43445615201 | 2016-10-04 | QTR2 | 16/17 | 1 | 0 | 110 | 118 | 118 | 0 | 0 | 0 | 8 | 0 | 704674 | 32000 | 672674 | 704674 | 672674 | 0 | 0 | 0 | 672674 | 672674 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592992809 | PAVE-RITE INC. | N/A | N/A | N/A | N/A | 2017-08-14 | QTR1 | 17/18 | 2017-05-05 | QTR4 | 16/17 | 515 | 684419.55 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y37 | 43744815201 | 2016-12-06 | QTR2 | 16/17 | 1 | 1 | 85 | 103 | 100 | 3 | 0 | 0 | 18 | 0 | 339868 | 17000 | 322868 | 339868 | 258858 | 0 | 0 | 0 | 258858 | 258860 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273238420 | OCEANEER CONSULTING LLC | N/A | N/A | N/A | N/A | 2017-11-17 | QTR2 | 17/18 | 2017-05-25 | QTR4 | 16/17 | 513 | 388062 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y53 | 24021675201 | 2017-05-02 | QTR4 | 16/17 | 1 | 0 | 150 | 206 | 195 | 11 | 0 | 0 | 56 | 0 | 1488299 | 50000 | 1438299 | 1488299 | 1438708 | 0 | 0 | 0 | 1438708 | 1450820 | 12112 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-20 | QTR3 | 17/18 | 2018-02-15 | QTR3 | 17/18 | 507 | 1582604.35 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y58 | 43744615201 | 2017-03-07 | QTR3 | 16/17 | 1 | 1 | 159 | 183 | 182 | 1 | 0 | 0 | 24 | 0 | 498196 | 35000 | 463196 | 498012 | 443118 | 0 | 0 | 0 | 443118 | 443118 | 0 | -184 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -184 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2018-02-27 | QTR3 | 17/18 | 2018-01-22 | QTR3 | 17/18 | 513 | 954404 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y59 | 43709215201 | 2016-12-06 | QTR2 | 16/17 | 1 | 0 | 220 | 225 | 167 | 58 | 0 | 0 | 5 | 0 | 524644 | 24000 | 500644 | 524644 | 497252 | 0 | 0 | 0 | 497252 | 497252 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2017-11-21 | QTR2 | 17/18 | 2017-08-25 | QTR1 | 17/18 | 514 | 584577 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y63 | 43234615201 | 2016-10-04 | QTR2 | 16/17 | 1 | 1 | 90 | 116 | 132 | -16 | 16 | 0 | 18 | 8 | 862770 | 33000 | 829770 | 868517 | 816671 | -25344 | 0 | -25344 | 791327 | 791327 | 0 | 5747 | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5747 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 | 2017-05-15 | QTR4 | 16/17 | 513 | 776696.15 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y76 | 43566215201 | 2017-08-01 | QTR1 | 17/18 | 1 | 0 | 180 | 199 | 95 | 104 | 0 | 0 | 19 | 0 | 3490230 | 50000 | 3440230 | 3490230 | 3483913 | 0 | 0 | 0 | 3483913 | 3496667 | 12754 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-04 | QTR4 | 17/18 | 2018-01-08 | QTR3 | 17/18 | 515 | 4898413 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y79 | 43544335201 | 2017-03-07 | QTR3 | 16/17 | 2 | 2 | 140 | 172 | 172 | 0 | 0 | 0 | 32 | 0 | 1179059 | 50000 | 1129059 | 1271899 | 1054894 | 0 | 0 | 0 | 1054894 | 1044236 | 0 | 92840 | 19 | 0 | 0 | 4792 | 0 | 0 | 0 | 82183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86975 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-06-26 | QTR4 | 17/18 | 2017-12-09 | QTR2 | 17/18 | 509 | 1499217.1 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Y85 | 43465815201 | 2017-04-04 | QTR4 | 16/17 | 2 | 1 | 90 | 126 | 140 | -14 | 14 | 0 | 36 | 0 | 349962 | 16000 | 333962 | 365078 | 342181 | -15386 | 0 | -15386 | 326795 | 311679 | 0 | 15117 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-03-08 | QTR3 | 17/18 | 2017-11-21 | QTR2 | 17/18 | 515 | 361362.3 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6345 | 24994165201 | 2014-06-25 | QTR4 | 13/14 | 2 | 5 | 780 | 859 | 754 | 105 | 0 | 0 | 70 | 9 | 20210987 | 648000 | 19562987 | 20241085 | 19700200 | 0 | 800000 | 800000 | 20500200 | 19298493 | -1201707 | 30098 | 51 | 0 | 0 | 325806 | 0 | 0 | 0 | 277026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5947 | 0 | 0 | 0 | 8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2882 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 196909 | 0 | F592373403 | MCM CORP. | N/A | N/A | N/A | N/A | 2017-09-19 | QTR1 | 17/18 | 2017-01-27 | QTR3 | 16/17 | 606 | 19907818.44 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 19 | 0 | 0 | -422785 | 0 |  | CO
06CO | 06 | T6349 | 42916225201 | 2016-04-27 | QTR4 | 15/16 | 2 | 7 | 240 | 263 | 195 | 68 | 0 | 0 | 23 | 0 | 4178283 | 50000 | 4128283 | 4236996 | 3850525 | 0 | 160000 | 160000 | 4010525 | 3858312 | -152213 | 58713 | 14 | 0 | 0 | 24297 | 0 | 0 | 0 | 74263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9298 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91182 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2017-07-06 | QTR1 | 17/18 | 2017-02-24 | QTR3 | 16/17 | 606 | 5124941.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6350 | 43080315201 | 2016-06-15 | QTR4 | 15/16 | 4 | 4 | 300 | 421 | 418 | 3 | 0 | 0 | 121 | 0 | 3626400 | 52820 | 3573580 | 3770876 | 3752395 | 0 | 0 | 0 | 3752395 | 3703553 | 11155 | 144476 | 63 | 30 | 0 | -6590 | 0 | 0 | 0 | 9941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53152 | 0 | 0 | 0 | 60998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 117500 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-06-01 | QTR4 | 17/18 | 2017-12-08 | QTR2 | 17/18 | 606 | 4489026.25 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6375 | 43274325201 | 2015-10-28 | QTR2 | 15/16 | 4 | 3 | 350 | 402 | 390 | 12 | 0 | 0 | 52 | 0 | 9111715 | 113088 | 8998627 | 9340645 | 9186004 | 0 | 0 | 0 | 9186004 | 8941564 | -244440 | 138931 | 33 | 0 | 0 | 70119 | 0 | 0 | 0 | 14883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91211 | 0 | 0 | 0 | 2258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178471 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-11-17 | QTR2 | 17/18 | 2017-03-20 | QTR3 | 16/17 | 606 | 10922672.4 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6378 | 43080815201 | 2016-05-25 | QTR4 | 15/16 | 4 | 1 | 380 | 398 | 285 | 113 | 0 | 0 | 18 | 0 | 4890784 | 61235 | 4829549 | 4907164 | 4857632 | 0 | 240000 | 240000 | 5097632 | 4876249 | -221383 | 8190 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 15244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28308 | 0 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44872 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2018-05-03 | QTR4 | 17/18 | 2017-10-19 | QTR2 | 17/18 | 606 | 6041431.47 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6380 | 41462435201 | 2015-06-17 | QTR4 | 14/15 | 3 | 3 | 280 | 383 | 382 | 1 | 0 | 0 | 103 | 0 | 3520907 | 50505 | 3470402 | 3612854 | 3575998 | 0 | 56000 | 56000 | 3631998 | 3498466 | -133532 | 91947 | 47 | 0 | 0 | 1588 | 0 | 40 | 0 | 82138 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 83726 | 8200 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 | 2017-01-20 | QTR3 | 16/17 | 606 | 3771064.2 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6385 | 43326415201 | 2016-01-27 | QTR3 | 15/16 | 2 | 1 | 180 | 259 | 259 | 0 | 0 | 0 | 54 | 25 | 1122164 | 50070 | 1072094 | 1210753 | 1131145 | 0 | 0 | 0 | 1131145 | 1133153 | 2007 | 88590 | 37 | 0 | 0 | 17204 | 0 | 0 | 25 | 90738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 107942 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-04-04 | QTR4 | 16/17 | 606 | 1217718.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6387 | 43477215201 | 2016-12-07 | QTR2 | 16/17 | 4 | 0 | 100 | 112 | 100 | 12 | 0 | 0 | 12 | 0 | 397288 | 22666 | 374622 | 397288 | 368073 | 0 | 0 | 0 | 368073 | 368073 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5157 | 0 | 0 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9217 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-10-03 | QTR2 | 17/18 | 2017-08-08 | QTR1 | 17/18 | 606 | 422434 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6391 | 43349215201 | 2016-04-27 | QTR4 | 15/16 | 2 | 0 | 180 | 208 | 208 | 0 | 0 | 0 | 28 | 0 | 1155673 | 47446 | 1108227 | 1155673 | 1091324 | 0 | 0 | 0 | 1091324 | 1092555 | 1230 | 0 | 11 | 0 | 0 | 12008 | 0 | 0 | 0 | 2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21825 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 | 2017-05-21 | QTR4 | 16/17 | 606 | 983083.6 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6405 | 42934625201 | 2016-03-30 | QTR3 | 15/16 | 3 | 1 | 160 | 216 | 215 | 1 | 0 | 0 | 56 | 0 | 1071254 | 50000 | 1021254 | 1073754 | 1058914 | 0 | 0 | 0 | 1058914 | 1062745 | 3831 | 2500 | 43 | 0 | 0 | 3296 | 0 | 0 | 0 | 3287 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5133 | 0 | 0 | 0 | 2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14682 | 787 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 | 2017-04-28 | QTR4 | 16/17 | 606 | 1077071.2 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6439 | 43476615201 | 2017-08-30 | QTR1 | 17/18 | 1 | 0 | 70 | 79 | 79 | 0 | 0 | 0 | 9 | 0 | 230856 | 17085 | 213771 | 230856 | 202885 | 0 | 0 | 0 | 202885 | 202885 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2018-05-24 | QTR4 | 17/18 | 2018-04-04 | QTR4 | 17/18 | 606 | 346258.1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T9018 | 43676425201 | 2017-05-24 | QTR4 | 16/17 | 1 | 0 | 50 | 51 | 51 | 0 | 0 | 0 | 1 | 0 | 1124592 | 49000 | 1075592 | 1124592 | 1064750 | 0 | 0 | 0 | 1064750 | 1064750 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-06-08 | QTR4 | 17/18 | 2018-02-27 | QTR3 | 17/18 | 606 | 1110084.56 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6J00 | 43540715201 | 2015-01-29 | QTR3 | 14/15 | 1 | 0 | 790 | 794 | 791 | 3 | 0 | 0 | 4 | 0 | 204491 | 11179 | 193312 | 204491 | 200808 | 0 | 0 | 0 | 200808 | 200808 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | F650817669 | FLORIDA TURF AND LANDSCAPE HORTICULTURE | N/A | N/A | N/A | N/A | 2017-08-17 | QTR1 | 17/18 | 2017-07-24 | QTR1 | 17/18 | 606 | 234759 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J27 | 43325415201 | 2015-10-29 | QTR2 | 15/16 | 1 | 1 | 240 | 364 | 364 | 0 | 0 | 0 | 124 | 0 | 874736 | 43765 | 830971 | 839120 | 814919 | 0 | 0 | 0 | 814919 | 814919 | 0 | -35616 | 105 | 0 | 0 | 10698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24918 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2017-07-18 | QTR1 | 17/18 | 2017-04-26 | QTR4 | 16/17 | 606 | 895054.75 |  |  | 0 | 19 | 0 | 0 | -35616 | 0 |  | DO
06DO | 06 | E6J41 | 43444315201 | 2016-11-17 | QTR2 | 16/17 | 1 | 0 | 70 | 77 | 77 | 0 | 0 | 0 | 7 | 0 | 220419 | 11619 | 208800 | 220419 | 208800 | 0 | 0 | 0 | 208800 | 208800 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2017-09-06 | QTR1 | 17/18 | 2017-04-23 | QTR4 | 16/17 | 606 | 249619 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J44 | 43468115201 | 2016-05-26 | QTR4 | 15/16 | 1 | 1 | 240 | 317 | 257 | 60 | 0 | 0 | 77 | 0 | 979602 | 50000 | 929602 | 823480 | 746877 | 0 | 0 | 0 | 746877 | 746877 | 0 | -156122 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | -156122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -156122 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-08-24 | QTR1 | 17/18 | 2017-06-09 | QTR4 | 16/17 | 606 | 1105870 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J47 | 43471015201 | 2016-03-31 | QTR3 | 15/16 | 2 | 2 | 300 | 503 | 493 | 10 | 0 | 0 | 173 | 30 | 1421464 | 50000 | 1371464 | 1931498 | 1949242 | 0 | 0 | 0 | 1949242 | 1896702 | 0 | 510034 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 457493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 457493 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2018-05-10 | QTR4 | 17/18 | 2017-12-06 | QTR2 | 17/18 | 606 | 1476116 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J56 | 43550619201 | 2015-12-02 | QTR2 | 15/16 | 1 | 1 | 460 | 512 | 502 | 10 | 0 | 0 | 52 | 0 | 3827963 | 50000 | 3777963 | 3877963 | 3862070 | 0 | 0 | 0 | 3862070 | 0 | -3862070 | 50000 | 29 | 0 | 0 | 49710 | 19018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3878 | 0 | 0 | 0 | 7133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99707 | 19018 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2018-01-26 | QTR3 | 17/18 | 2017-06-30 | QTR4 | 16/17 | 606 | 3497921 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J75 | 43652815201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 215 | 220 | 132 | 88 | 0 | 0 | 5 | 0 | 847200 | 50000 | 797200 | 847200 | 789681 | 0 | 0 | 0 | 789681 | 789681 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2017-08-15 | QTR1 | 17/18 | 2017-06-20 | QTR4 | 16/17 | 606 | 1102468.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6J76 | 43652915201 | 2016-06-09 | QTR4 | 15/16 | 1 | 0 | 180 | 234 | 220 | 14 | 0 | 0 | 54 | 0 | 588728 | 36323 | 552405 | 588728 | 477515 | 0 | 0 | 0 | 477515 | 477515 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593595777 | ROYAL BRIDGE INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2017-05-08 | QTR4 | 16/17 | 606 | 756279.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K21 | 42914635201 | 2016-07-28 | QTR1 | 16/17 | 1 | 0 | 100 | 107 | 105 | 2 | 0 | 0 | 7 | 0 | 177943 | 9346 | 168597 | 177943 | 173203 | 0 | 0 | 0 | 173203 | 173203 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2017-07-13 | QTR1 | 17/18 | 2017-06-12 | QTR4 | 16/17 | 606 | 196223.5 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K22 | 42521625201 | 2016-07-28 | QTR1 | 16/17 | 3 | 3 | 210 | 315 | 305 | 10 | 0 | 0 | 105 | 0 | 1343144 | 50000 | 1293144 | 1349051 | 1259511 | 0 | 0 | 0 | 1259511 | 1245107 | -6083 | 5907 | 75 | 0 | 0 | -2413 | 0 | 0 | 0 | 26451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40253 | 0 | F591115297 | GENERAL ASPHALT CO. INC. | N/A | N/A | N/A | N/A | 2018-06-04 | QTR4 | 17/18 | 2018-01-25 | QTR3 | 17/18 | 606 | 1605334.2 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K28 | 42563735201 | 2017-03-30 | QTR3 | 16/17 | 2 | 0 | 80 | 136 | 134 | 2 | 0 | 0 | 56 | 0 | 179971 | 12916 | 167055 | 179971 | 164916 | 0 | 0 | 0 | 164916 | 164916 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2018-03-30 | QTR3 | 17/18 | 2018-01-16 | QTR3 | 17/18 | 606 | 267547.25 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K31 | 42934635201 | 2016-08-25 | QTR1 | 16/17 | 1 | 0 | 140 | 162 | 145 | 17 | 0 | 0 | 22 | 0 | 999395 | 50000 | 949395 | 999395 | 975146 | 0 | 0 | 0 | 975146 | 975806 | 660 | 0 | 19 | 0 | 0 | 9015 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31215 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-31 | QTR1 | 17/18 | 2017-06-30 | QTR4 | 16/17 | 606 | 1051398.75 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6K49 | 43058825201 | 2016-09-29 | QTR1 | 16/17 | 2 | 0 | 140 | 187 | 187 | 0 | 0 | 0 | 47 | 0 | 864202 | 42202 | 822000 | 864202 | 790596 | 0 | 0 | 0 | 790596 | 790888 | 292 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | F800744096 | IMECO INC. | N/A | N/A | N/A | N/A | 2017-09-18 | QTR1 | 17/18 | 2017-07-28 | QTR1 | 17/18 | 606 | 885402 | B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7220 | 40845925201 | 2011-06-29 | QTR4 | 10/11 | 6 | 63 | 1500 | 1779 | 1779 | 0 | 0 | 0 | 237 | 42 | 94696203 | 150000 | 94546203 | 99221504 | 102513161 | -176000 | 0 | -176000 | 102337161 | 101152204 | -1016777 | 4525301 | 164 | 0 | 0 | 1140417 | 444656 | 0 | 0 | 638567 | 94458 | 0 | 0 | 0 | 0 | 0 | 0 | -431960 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2636702 | 157507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347209 | 54885 | 0 | 0 | 0 | 0 | 0 | 0 | 4136 | 4136 | 0 | 0 | 0 | 0 | 0 | 42 | 4335071 | 755643 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-07-07 | QTR1 | 17/18 | 2016-08-26 | QTR1 | 16/17 | 714 | 107019759.03 |  |  | 42 | 73 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7322 | 42292925201 | 2013-06-19 | QTR4 | 12/13 | 1 | 0 | 153 | 321 | 607 | -286 | 286 | 0 | 146 | 22 | 756468 | 47620 | 708848 | 756468 | 713772 | -356956 | 0 | -356956 | 356816 | 356816 | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 11372 | 0 | F331064425 | CIVIL SITE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2018-02-13 | QTR3 | 17/18 | 2015-09-04 | QTR1 | 15/16 | 717 | 983979 |  |  | 22 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7346 | 43089815201 | 2014-07-30 | QTR1 | 14/15 | 1 | 5 | 390 | 599 | 599 | 0 | 0 | 0 | 170 | 39 | 6794444 | 62000 | 6732444 | 6864518 | 7093818 | 0 | 0 | 0 | 7093818 | 6785751 | -308067 | 70073 | 144 | 0 | 17 | 18684 | 0 | 0 | 22 | 128610 | 6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 112644 | 6122 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-10 | QTR1 | 17/18 | 2016-08-25 | QTR1 | 16/17 | 717 | 6553700 |  |  | 39 | 26 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7349 | 43124315201 | 2014-06-18 | QTR4 | 13/14 | 2 | 5 | 400 | 654 | 652 | 2 | 0 | 0 | 203 | 51 | 12544444 | 119000 | 12425444 | 12706570 | 13012776 | 0 | 0 | 0 | 13012776 | 12421061 | -591715 | 162125 | 167 | 6 | 11 | 89297 | 0 | 0 | 40 | 77646 | 16339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15383 | 15383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 51 | 182326 | 31722 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-31 | QTR1 | 17/18 | 2016-10-25 | QTR2 | 16/17 | 798 | 12199500 |  |  | 45 | 30 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7377 | 42453295201 | 2016-02-24 | QTR3 | 15/16 | 3 | 6 | 260 | 309 | 309 | 0 | 0 | 0 | 46 | 3 | 2482901 | 50000 | 2432901 | 2542403 | 2373194 | 0 | 0 | 0 | 2373194 | 2384196 | 11002 | 59502 | 25 | 0 | 3 | 56002 | 0 | 0 | 0 | 8532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 64535 | 0 | F591724558 | MTM CONTRACTORS INC | N/A | N/A | N/A | N/A | 2017-07-25 | QTR1 | 17/18 | 2017-05-17 | QTR4 | 16/17 | 709 | 2246000 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7381 | 25589335201 | 2016-05-25 | QTR4 | 15/16 | 2 | 1 | 200 | 284 | 284 | 0 | 0 | 0 | 56 | 28 | 4590182 | 55000 | 4535182 | 4640182 | 4586377 | 0 | 0 | 0 | 4586377 | 4603104 | 16727 | 50000 | 22 | 0 | 7 | 26821 | 0 | 0 | 0 | 14230 | 1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 57192 | 1901 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-09-27 | QTR1 | 17/18 | 2017-05-31 | QTR4 | 16/17 | 717 | 7190840.88 |  |  | 28 | 34 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7397 | 43768715201 | 2017-06-14 | QTR4 | 16/17 | 1 | 1 | 205 | 252 | 252 | 0 | 0 | 0 | 35 | 12 | 1352726 | 50000 | 1302726 | 1363694 | 1329902 | 0 | 0 | 0 | 1329902 | 1329961 | 11027 | 10968 | 15 | 0 | 0 | 0 | 0 | 0 | 12 | 3644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3644 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2018-05-17 | QTR4 | 17/18 | 2018-05-01 | QTR4 | 17/18 | 796 | 1620000 |  |  | 12 | 20 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T9019 | 44030915201 | 2017-04-26 | QTR4 | 16/17 | 1 | 2 | 42 | 65 | 65 | 0 | 0 | 0 | 23 | 0 | 106998 | 4233 | 102765 | 124900 | 124723 | 0 | 0 | 0 | 124723 | 124723 | 0 | 17902 | 13 | 0 | 0 | 0 | 0 | 6 | 0 | 9550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 22102 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2018-01-22 | QTR3 | 17/18 | 2017-10-10 | QTR2 | 17/18 | 706 | 105779.7 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7I69 | 41868515201 | 2014-06-11 | QTR4 | 13/14 | 2 | 16 | 500 | 714 | 714 | 0 | 0 | 0 | 115 | 99 | 8338093 | 57000 | 8281093 | 9034910 | 9761980 | 0 | 0 | 0 | 9761980 | 9649830 | -112150 | 696817 | 41 | 0 | 99 | 441414 | 190338 | 0 | 0 | 344754 | 73724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45110 | 0 | 0 | 0 | 9744 | 4974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006 | 3006 | 0 | 0 | 0 | 0 | 0 | 99 | 753808 | 272042 | F593026022 | GIBBS & REGISTER INC. | N/A | N/A | N/A | N/A | 2018-05-29 | QTR4 | 17/18 | 2016-12-08 | QTR2 | 16/17 | 717 | 6938454.99 |  |  | 0 | 74 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7J74 | 42347415201 | 2014-08-13 | QTR1 | 14/15 | 1 | 3 | 450 | 654 | 653 | 1 | 0 | 0 | 204 | 0 | 5011920 | 50000 | 4961920 | 5193391 | 5076829 | 0 | 0 | 0 | 5076829 | 5076829 | 0 | 181471 | 160 | 0 | 0 | 12562 | 0 | 0 | 0 | 136458 | 0 | 0 | 0 | 32450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194400 | 0 | F650240625 | CMA CORPORATION | N/A | N/A | N/A | N/A | 2018-03-02 | QTR3 | 17/18 | 2017-01-23 | QTR3 | 16/17 | 709 | 4749400 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7J76 | 43075115201 | 2014-12-10 | QTR2 | 14/15 | 1 | 1 | 150 | 160 | 156 | 4 | 0 | 0 | 10 | 0 | 743784 | 39000 | 704784 | 740664 | 652729 | 0 | 0 | 0 | 652729 | 652689 | -40 | -3120 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3120 | 0 | F630796723 | PNEUMATIC CONCRETE CO. INC. | N/A | N/A | N/A | N/A | 2018-03-15 | QTR3 | 17/18 | 2015-08-18 | QTR1 | 15/16 | 709 | 860120 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K09 | 43376015201 | 2016-03-09 | QTR3 | 15/16 | 1 | 0 | 165 | 235 | 235 | 0 | 0 | 0 | 70 | 0 | 4858889 | 50000 | 4808889 | 4858889 | 4889946 | 0 | 0 | 0 | 4889946 | 4892719 | 2773 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | F650026542 | D.A.B. CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2017-07-05 | QTR1 | 17/18 | 2017-01-20 | QTR3 | 16/17 | 798 | 4975480 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K13 | 43175035201 | 2014-11-26 | QTR2 | 14/15 | 2 | 0 | 360 | 765 | 765 | 0 | 0 | 0 | 405 | 0 | 5076080 | 55000 | 5021080 | 5076080 | 5350308 | 0 | 0 | 0 | 5350308 | 5348564 | -1744 | 0 | 358 | 0 | 0 | 13591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16458 | 0 | F593273147 | INLAND CONSTRUCTION AND ENGINEERING INC | N/A | N/A | N/A | N/A | 2017-10-24 | QTR2 | 17/18 | 2017-06-20 | QTR4 | 16/17 | 709 | 5778800 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K14 | 43571815201 | 2015-06-23 | QTR4 | 14/15 | 1 | 0 | 515 | 678 | 678 | 0 | 0 | 0 | 90 | 73 | 5520000 | 50000 | 5470000 | 5520000 | 5515787 | 0 | 0 | 0 | 5515787 | 5461492 | -54295 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 73 | 42916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 42916 | 0 | F593221511 | PEPPER CONTRACTING SERVICES INC. | N/A | N/A | N/A | N/A | 2017-08-23 | QTR1 | 17/18 | 2017-07-10 | QTR1 | 17/18 | 709 | 5318312 | A3:LBDB | ICC - DESIGN/BUILD - MINOR:LOW BID DESIGN BUILD | 73 | 30 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K95 | 43655215201 | 2016-03-09 | QTR3 | 15/16 | 1 | 0 | 129 | 175 | 134 | 41 | 0 | 0 | 46 | 0 | 1999499 | 50000 | 1949499 | 1999499 | 1965163 | 0 | 0 | 0 | 1965163 | 1965188 | 25 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 27547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27547 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2017-11-13 | QTR2 | 17/18 | 2017-09-20 | QTR1 | 17/18 | 717 | 2583470 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7K97 | 43149215201 | 2016-06-08 | QTR4 | 15/16 | 1 | 0 | 210 | 294 | 289 | 5 | 0 | 0 | 84 | 0 | 5498000 | 50000 | 5448000 | 5498000 | 5479166 | 0 | 0 | 0 | 5479166 | 5486336 | 7170 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2017-10-31 | QTR2 | 17/18 | 2017-08-31 | QTR1 | 17/18 | 717 | 5955000 | B0 | ACC - LUMP SUM | 0 | 26 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L41 | 42550315201 | 2016-09-14 | QTR1 | 16/17 | 1 | 0 | 95 | 117 | 116 | 1 | 0 | 0 | 22 | 0 | 1429757 | 50000 | 1379757 | 1429757 | 1357101 | 0 | 0 | 0 | 1357101 | 1357101 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6201 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-10-27 | QTR2 | 17/18 | 2017-07-13 | QTR1 | 17/18 | 717 | 1539689.27 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L44 | 43269915201 | 2016-10-12 | QTR2 | 16/17 | 1 | 1 | 170 | 206 | 206 | 0 | 0 | 0 | 36 | 0 | 2181247 | 50000 | 2131247 | 2181247 | 2114949 | 0 | 0 | 0 | 2114949 | 2122813 | 7864 | 0 | 27 | 0 | 0 | 4670 | 0 | 0 | 0 | 1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5935 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-12-20 | QTR2 | 17/18 | 2017-09-22 | QTR1 | 17/18 | 709 | 2450000.36 | B0 | ACC - LUMP SUM | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L46 | 43473615201 | 2016-12-14 | QTR2 | 16/17 | 1 | 0 | 140 | 251 | 278 | -27 | 27 | 0 | 111 | 0 | 2644431 | 50000 | 2594431 | 2644431 | 2652518 | -75897 | 0 | -75897 | 2576621 | 2683911 | 107290 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 6922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6922 | 0 | F593759317 | CHEYENNE ASSOCIATES INC. | N/A | N/A | N/A | N/A | 2018-06-26 | QTR4 | 17/18 | 2018-02-23 | QTR3 | 17/18 | 717 | 3002164 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L48 | 43243215201 | 2017-01-11 | QTR3 | 16/17 | 1 | 1 | 120 | 211 | 221 | -10 | 10 | 0 | 84 | 7 | 658045 | 35000 | 623045 | 681845 | 622321 | -15840 | 0 | -15840 | 606481 | 606481 | 0 | 23800 | 76 | 0 | 7 | 44560 | 0 | 0 | 0 | 10563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 32843 | 0 | F593339339 | ESTEP CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2018-03-28 | QTR3 | 17/18 | 2017-11-17 | QTR2 | 17/18 | 709 | 825000 |  |  | 7 | 8 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L57 | 43386515201 | 2017-03-08 | QTR3 | 16/17 | 1 | 0 | 65 | 65 | 49 | 16 | 0 | 0 | 0 | 0 | 284040 | 13500 | 270540 | 284040 | 270466 | 0 | 0 | 0 | 270466 | 270466 | 0 | 0 | 0 | 0 | 0 | 2139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2139 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-10-31 | QTR2 | 17/18 | 2017-09-21 | QTR1 | 17/18 | 717 | 320000 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7L63 | 43794015201 | 2017-03-08 | QTR3 | 16/17 | 1 | 1 | 120 | 144 | 144 | 0 | 0 | 0 | 23 | 1 | 1222291 | 45000 | 1177291 | 1228444 | 1182817 | 0 | 0 | 0 | 1182817 | 1182817 | 0 | 6153 | 20 | 0 | 1 | 4327 | 0 | 0 | 0 | 9637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 21223 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2017-12-27 | QTR2 | 17/18 | 2017-11-29 | QTR2 | 17/18 | 709 | 1198576.7 |  |  | 1 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8M76 | 41548815201 | 2013-04-09 | QTR4 | 12/13 | 1 | 17 | 1035 | 1333 | 1333 | 0 | 0 | 0 | 221 | 77 | 40893455 | 100000 | 40793455 | 42793440 | 43780119 | 0 | 0 | 0 | 43780119 | 42891163 | -888956 | 1899985 | 111 | 0 | 4 | 388093 | 93242 | 21 | 73 | 1171105 | 320036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 425486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 77 | 1986212 | 413278 | F650012669 | CONDOTTE AMERICA INC. | N/A | N/A | N/A | N/A | 2017-12-20 | QTR2 | 17/18 | 2017-04-14 | QTR4 | 16/17 | 854 | 44448235.6 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 53 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8N90 | 42815425201 | 2014-10-14 | QTR2 | 14/15 | 2 | 2 | 845 | 960 | 915 | 45 | 0 | 0 | 101 | 14 | 8152113 | 150000 | 8002113 | 8219090 | 7569664 | 0 | 0 | 0 | 7569664 | 7559469 | -10195 | 66977 | 48 | 0 | 14 | 96833 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | -15815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 90818 | 0 | F223334957 | FERREIRA CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2017-11-15 | QTR2 | 17/18 | 2017-08-04 | QTR1 | 17/18 | 854 | 10548406 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P07 | 43560915201 | 2016-05-10 | QTR4 | 15/16 | 1 | 5 | 310 | 394 | 394 | 0 | 0 | 0 | 84 | 0 | 3499824 | 50000 | 3449824 | 3949117 | 3984741 | 0 | 0 | 0 | 3984741 | 3986085 | 1344 | 449293 | 21 | 0 | 0 | 398537 | 0 | 0 | 0 | -23329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 109120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 484328 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2018-06-22 | QTR4 | 17/18 | 2018-01-31 | QTR3 | 17/18 | 854 | 3565669.46 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P83 | 43282615201 | 2016-03-22 | QTR3 | 15/16 | 2 | 1 | 250 | 312 | 312 | 0 | 0 | 0 | 62 | 0 | 12114000 | 150000 | 11964000 | 12052537 | 12086406 | 0 | 0 | 0 | 12086406 | 12136961 | 50556 | -61463 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | -56714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40594 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2017-11-15 | QTR2 | 17/18 | 2017-05-08 | QTR4 | 16/17 | 854 | 13714087.19 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P84 | 43560415201 | 2016-06-14 | QTR4 | 15/16 | 1 | 0 | 215 | 250 | 250 | 0 | 0 | 0 | 21 | 14 | 1564634 | 50000 | 1514634 | 1564634 | 1570658 | 0 | 0 | 0 | 1570658 | 1593989 | 23332 | 0 | 4 | 0 | 0 | 8912 | 0 | 0 | 14 | 23635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 32548 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2017-08-25 | QTR1 | 17/18 | 2017-05-24 | QTR4 | 16/17 | 854 | 1798899.5 |  |  | 14 | 17 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P93 | 42933415201 | 2016-04-12 | QTR4 | 15/16 | 2 | 1 | 155 | 189 | 189 | 0 | 0 | 0 | 34 | 0 | 1627383 | 48815 | 1578568 | 1619754 | 1562111 | 0 | 0 | 0 | 1562111 | 1565726 | 3615 | -7629 | 14 | 0 | 0 | -1000 | 0 | 0 | 0 | 16722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18273 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2017-07-07 | QTR1 | 17/18 | 2017-04-05 | QTR4 | 16/17 | 854 | 1804452.94 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P94 | 43282715201 | 2016-05-24 | QTR4 | 15/16 | 5 | 2 | 425 | 523 | 519 | 4 | 0 | 0 | 98 | 0 | 11866804 | 150000 | 11716804 | 11967156 | 11316560 | -6500 | 0 | -6500 | 11310060 | 11306292 | 28313 | 100351 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 108976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5076 | 0 | 0 | 0 | 73350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187402 | 0 | F461625297 | MIDDLESEX PAVING LLC | N/A | N/A | N/A | N/A | 2018-06-28 | QTR4 | 17/18 | 2018-02-08 | QTR3 | 17/18 | 854 | 13286145.15 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8P96 | 43494625201 | 2016-05-24 | QTR4 | 15/16 | 3 | 1 | 175 | 190 | 187 | 3 | 0 | 0 | 15 | 0 | 938500 | 46648 | 891852 | 938500 | 828715 | 0 | 0 | 0 | 828715 | 828715 | 0 | 0 | 1 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2017-08-01 | QTR1 | 17/18 | 2017-05-12 | QTR4 | 16/17 | 854 | 988989.54 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q16 | 43540615201 | 2016-10-18 | QTR2 | 16/17 | 1 | 1 | 280 | 304 | 273 | 31 | 0 | 0 | 24 | 0 | 2671430 | 77853 | 2593576 | 3119007 | 3032466 | 0 | 300000 | 300000 | 3332466 | 3032466 | -300000 | 447578 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447578 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2017-12-27 | QTR2 | 17/18 | 2017-11-02 | QTR2 | 17/18 | 854 | 8220798.85 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q55 | 43914515201 | 2017-04-11 | QTR4 | 16/17 | 1 | 1 | 130 | 197 | 197 | 0 | 0 | 0 | 67 | 0 | 649649 | 33062 | 616587 | 670169 | 659765 | 0 | 0 | 0 | 659765 | 661830 | 2065 | 20520 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 20520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 20520 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2018-03-14 | QTR3 | 17/18 | 2018-01-17 | QTR3 | 17/18 | 854 | 849412.2 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
02DO | 02 | E2Q62 | 20929495201 | 2012-07-17 | QTR1 | 12/13 | 2 | 2 | 1100 | 1382 | 1382 | 0 | 0 | 0 | 278 | 4 | 94901300 | 150000 | 94751300 | 95003406 | 95132842 | 0 | 0 | 0 | 95132842 | 0 | -95132842 | 102106 | 152 | 31 | 0 | 92075 | 0 | 0 | 4 | 100938 | 84849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53900 | 0 | 7 | 0 | 3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 4 | 250602 | 84849 | F900869955 | INFRASTRUCTURE DEV PARTNERS | N/A | N/A | N/A | N/A | 2017-07-12 | QTR1 | 17/18 | 2016-07-16 | QTR1 | 16/17 | 216 | 104626299 | B8:DBF:P3 | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP | 0 | 88 | 0 | 0 | 0 | 0 |  | DO | 0 | 01co | 1 | 0
05DO | 05 | E5R39 | 40686985201 | 2012-04-19 | QTR4 | 11/12 | 1 | 12 | 1330 | 1397 | 1396 | 1 | 0 | 0 | 186 | -119 | 118370000 | 150000 | 118220000 | 127761416 | 127692104 | -26000 | 989593 | 963593 | 128655697 | 0 | -128655697 | 9391416 | 137 | 0 | -119 | 7073 | 0 | 0 | 0 | 36081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248774 | 0 | 0 | 0 | 0 | 0 | 0 | -119 | 2812039 | 0 | F060421150 | LANE CONSTRUCTION CORPORATION (THE) | N/A | N/A | N/A | N/A | 2017-12-01 | QTR2 | 17/18 | 2016-07-27 | QTR1 | 16/17 | 514 | 128150810 | B1:B11:B8:DB:P3 | ACC - NO EXCUSE BONUS:ACC - DESIGN BUILD-MAJOR/BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP | 0 | 49 | 0 | 0 | 0 | 0 |  | DO | 0 | 01do | 1 | 0
06DO | 06 | E6F61 | 24958115201 | 2009-08-31 | QTR1 | 09/10 | 5 | 34 | 1825 | 2495 | 2494 | 1 | 0 | 0 | 670 | 0 | 558880178 | 150000 | 558730178 | 562612213 | 563638617 | 0 | 0 | 0 | 563638617 | 567488387 | 3849771 | 3732035 | 472 | 4 | 0 | 1284972 | 0 | 0 | 0 | 1625269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50600 | 0 | 58 | 0 | 803680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 3764521 | 0 | F371585067 | COMMUNITY CONDOTTE DE MOYA JV | N/A | N/A | N/A | N/A | 2018-02-12 | QTR3 | 17/18 | 2016-09-27 | QTR1 | 16/17 | 606 | 559310206 | ARRA:B8:DBF:P3 | AMERICAN RECOVERY AND REINVEST:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP | 0 | 136 | 0 | 0 | 0 | 0 |  | DO | 0 | 02co | 1 | 0
CO | [104 empty] | CO | 1 | 02do | 1 | 1
CO | [104 empty] | CO | 0 | 03co | 2 | 1
CO | [104 empty] | CO | 0 | 03do | 2 | 1
CO | [104 empty] | CO | 0 | 04co | 2 | 1
CO | [104 empty] | CO | 0 | 04do | 2 | 1
CO | [104 empty] | CO | 0 | 05co | 2 | 1
CO | [103 empty] | T | CO | 1 | 05do | 2 | 2
CO | [104 empty] | CO | 0 | 06co | 3 | 2
CO | [104 empty] | CO | 1 | 06do | 3 | 3
CO | [104 empty] | CO | 0 | 07co | 4 | 3
CO | [104 empty] | CO | 0 | 07do | 4 | 3
CO | [104 empty] | CO | 0 | 08co | 4 | 3
CO | [104 empty] | CO | 0 | 08do | 4 | 3
CO | [104 empty] | CO
CO | [104 empty] | CO
CO | [104 empty] | CO |  | 0