## ORALS-ELORS PLAN (hidden)
Attached is our Consultant Acquisition Plan for FY 12/13. Please advise if the below advertisement type is acceptable.
Group Advertisement Type Ph 52 (M) Ph 62 (M) Work Type_______________
1 Expanded Letter $ 3,151 $ 410 Overhead Signing
2 Expanded Letter $ 3,141 $ 599 Bridge Rehabilitation, Intersection Improvement
3 Oral Presentation $10,787 $1,635 Add Lanes & Reconstruct, Resurfacing, Lighting
4 Expanded Letter $10,663 $1,168 Resurfacing, Rail Safety, Sidewalk, Intersection
Improvement
5 Expanded Letter $ 6,548 $ 655 Resurfacing, Overhead Signing
6 Oral Presentation $14,228 $2,021 Add Lanes & Reconstruct
7 Expanded Letter $12,775 $1,914 Resurfacing, Intersection Improvement,
Rail Safety
8 Expanded Letter $ 7,675 $1,080 Rail Safety, Resurfacing, Intersection
Improvement, Bridge Replacement
9 Expanded Letter $ 8,892 $ 989 Resurfacing, Intersection Improvement,
Drainage Improvements
10 Expanded Letter $ 150 District Wide Contract $1.5(M) for 5years

## FY 2026-2027 CAP PLAN
DRAFT Consultant CEI Acquisition Plan - FY26/27 | [31 empty] | LEGEND:
District One Construction
[32 empty] | CS = | Continuing Services
[32 empty] | DBR = | District Bridge Contract
[32 empty] | DW = | District Wide Contract
[32 empty] | F = | Full CEI Contract
[32 empty] | H = | Hybrid Project
[32 empty] | LOA = | Letter of Authorization
[32 empty] | SA = | Supplemental Amendment
[9 empty] | Position | Person | Office Phone | Secondary Phone
Location | Address | Phone | Fax | [5 empty] | District Secretary: | Jamie Driggers Jr. | (386) 758-3722 | (863) 519-1902
District 1 Construction | 801 N. Broadway, Bartow, FL 33830 | (863) 519-2300 | (863) 534-0071 | [5 empty] | Operations Director: | Keith Slater | (863) 519-2202 | (863) 534-7265
Ft. Myers Ops Center | 2981 N.E. Pine Island Rd., Cape Coral, FL 33909 | (239) 985-7800 | (239) 656-7742 | [5 empty] | District Construction Eng: | Amarilys Alonso-Perez | (863) 519-2223 | (863) 534-0071
Manatee Ops Center | 14000 SR 64 East, Bradenton, FL 34212 | (941) 708-4400 | (941) 708-4494 | [5 empty] | Ass't Constr. Engineer: | Brian Blair | (863) 519-2224 | (863) 534-0071
Bartow Ops Center | 2730 S.R. 60 West, Bartow, FL 33830 | (863) 519-4100 | (863) 519-7924 | [5 empty] | District CEI Manager: | Anita Michael | (863) 519-2232 | (863) 534-0071
Heartland Ops Center | 4730 Kenilworth Blvd., Sebring, FL 33870 | (863) 471-4848 | (863) 386-6116 | [5 empty] | CEI Contract Administrator: | Jennifer Roberson | (863) 519-2256 | (863) 534-0071
Seq. | Financial Project ID/(Fund) | [10 empty] | Design Project Manager/Phone No./Fax No. | [11 empty] | Event | Event | Event | Event | Event | Event | Event | Event | Event | Event | Event
No. |  | WPI No.(Old)/SPN(Old) | [10 empty] | Resident Construction Office/Resident Engineer | [10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  |  | Federal Project (WP21) | [10 empty] | Construction Project Manager/Phone No./Fax No. | [9 empty] | 1: (Note: Scheduled Date-Proposed is subject to change/approval by Professional Services Administrator.)
|  |  |  | Project Name | [10 empty] | Type Project/English-Metric
[5 empty] | Limit-From | [10 empty] | Number of Bridges/Alt. Contract
[6 empty] | Limit -To | [10 empty] | Letting Date (Mo-Year)/Construction Time (Days) | [6 empty] | 6: Oral/; 9: Scope
[7 empty] | Dist.(Mi.)/Prop. X- Sect. | [10 empty] | Ph 52 Budget $ |  | (% of CEI FY Total Ph 52) |  |  |  | Scope |  | Long | Short | Scope | Written | Consult. | Proposal | Clarif. | Negot. | Agree,
[8 empty] | County | [9 empty] | Ph 62 Budget $ (% of Ph 52) | [5 empty] | Due | Advert | List | List | Meeting | Present. | Select. | Review | Meeting | Meeting | Execution
1Fa | 433183-4-62-05 | [10 empty] | Anita Michael (863) 519-2256 | [9 empty] | Schedule Date-Prop. |  |  | 46080 | 46111 | 46119 | N/A | N/A | 46140 | 46164 | N/A | 46178 | 46234
|  | DS | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
|  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: DA, LE, RB,
|  |  |  | CEI (INSPECTION) HEA | [10 empty] | INSPECT CONSTRUCTION PROJS. | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | RTLAND OPERATIONS CENTER | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | - CSC | [10 empty] | July 16, 2026 | [5 empty] | Contact: | 7: date: July 2026; 9: Funds Encumb. Date:
[7 empty] | 0 | [11 empty] | ( | 0 | ) |  | Phone: | 9: Marketing Date:; 11: 46069
|  | RKS-BMB-EJT | [5 empty] | DIST/ST-WIDE | [9 empty] | 200000 | ( |  | ) |  | Fax: | 9: CEI Contract #:; 11: 27110
2Fa | 417540-5-62-01 | [10 empty] | Sean T. Pugh (239) 225-1925 | [9 empty] | Schedule Date-Prop. |  |  | 46171 | 46202 | 46210 | N/A | N/A | 46224 | 46251 | N/A | 46258 | 46326
|  | FINC | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
Grouped 417540-6 |  |  | N/A | [10 empty] | James Heffelfinger (239) 985-7869 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: JB, JM, RH (JH-PM)
|  |  |  | SR 29 FROM CR 846 E | [10 empty] | NEW ROAD CONSTRUCTION | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | TO N OF NEW MARKET ROAD W |  |  | 0 | [15 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | October 15, 2026 (1000) | [5 empty] | Contact: | 7: date: October 2026; 9: Funds Encumb. Date:
[7 empty] | 1.15 | [10 empty] | 63354242 | ( | 0.13081 | ) |  | Phone: | 9: Marketing Date:; 11: 46149
|  | NEM-BCC-STP | [5 empty] | COLLIER | [9 empty] | 8843343 | ( | 0.13959 | ) |  | Fax: | 9: CEI Contract #:; 11: 27115
2Fb | 417540-6-62-01 | [10 empty] | Christopher B. Speese (239) 225-1973 | [9 empty] | Schedule Date-Prop. |  |  | 46171 | 46202 | 46210 | N/A | N/A | 46224 | 46251 | N/A | 46258 | 46326
|  | FINC | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
Grouped 417540-5 |  |  | N/A | [10 empty] | James Heffelfinger (239) 985-7869 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: JB, JM, RH (JH-PM)
|  |  |  | SR 29 FROM N OF NEW | [10 empty] | ADD LANES & RECONSTRUCT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | MARKET RD TO SR 82 | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | October 15, 2026 (850) | [5 empty] | Contact: | 7: date: October 2026; 9: Funds Encumb. Date:
[7 empty] | 1.15 | [10 empty] | 51087794 | ( | 0.10549 | ) |  | Phone: | 9: Marketing Date:; 11: 46149
|  | NEM-STP-CBS | [5 empty] | COLLIER | [9 empty] | 6036753 | ( | 0.11816 | ) |  | Fax: | 9: CEI Contract #:; 11: 27115
3Fa | 441512-1-62-01 | [10 empty] | David J. Agacinski (239) 225-1924 | [9 empty] | Schedule Date-Prop. |  |  | 46290 | 46323 | 46329 | N/A | N/A | 46343 | 46370 | N/A | 46377 | 46446
|  | ACSA | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 446451-1 |  |  | N/A | [10 empty] | James Heffelfinger (239) 985-7869 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: CB, MS, RH
|  |  |  | SR 45 (US 41) FROM N | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OF OLD US 41 TO S OF GUL | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | F PARK DR | [10 empty] | February 24, 2027 (400) | [5 empty] | Contact: | 7: date: February 2027; 9: Funds Encumb. Date:
[7 empty] | 4.707 | [10 empty] | 20252960 | ( | 0.041818 | ) |  | Phone: | 9: Marketing Date:
Grouped 446451-1 |  | NEM-STP-DJA | [5 empty] | COLLIER | [9 empty] | 2288011 | ( | 0.11297 | ) |  | Fax: | 9: CEI Contract #:; 11: 27118
3Fb | 446451-1-62-01 | [10 empty] | Jeffrey M. Jones (239)-225-1920 | [9 empty] | Schedule Date-Prop. |  |  | 46290 | 46323 | 46329 | N/A | N/A | 46343 | 46370 | N/A | 46377 | 46507
|  | ACSU | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 441512-1 |  |  | N/A | [10 empty] | James Heffelfinger (239) 985-7869 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: CB, MS, RH
|  |  |  | SR 45 (US 41) AT CR | [10 empty] | INTERSECTION IMPROVEMENT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | 886 (GOLDEN GATE PKWY) | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | April 28, 2027 (125) | [5 empty] | Contact: | 7: date: February 2027; 9: Funds Encumb. Date:
[7 empty] | 0.006 | [10 empty] | 1646827 | ( | 0.0034003 | ) |  | Phone: | 9: Marketing Date:
Grouped 441512-1 |  | NEM-STP-JMJ | [5 empty] | COLLIER | [9 empty] | 181152 | ( | 0.11 | ) |  | Fax: | 9: CEI Contract #:; 11: 27118
4Fa | 445460-1-62-01 | [10 empty] | Jeffrey M. Jones (239)-225-1920 | [9 empty] | Schedule Date-Prop. |  |  | 46290 | 46321 | 46329 | N/A | N/A | 46343 | 46367 | N/A | 46374 | 46446
|  | LF | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
|  |  | N/A | [10 empty] | James Heffelfinger (239) 985-7869 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: CM, JH, RH / MD (PM)
|  |  |  | CAXAMBAS COURT / ROB | [10 empty] | BRIDGE REPLACEMENT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | ERTS BAY REPLACEMENT STRU | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | CTURE #034112 | [10 empty] | February 24, 2027 (375) | [5 empty] | Contact: | 7: date: February 2027; 9: Funds Encumb. Date:
[7 empty] | 0.76 | [10 empty] | 11245107 | ( | 0.023219 | ) |  | Phone: | 9: Marketing Date:; 11: 46268
|  | NEM-STP-JMJ | [5 empty] | COLLIER | [9 empty] | 1349414 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: 27119
5Fa | 452171-1-62-01 | [10 empty] | Michael Rima L. (813) 612-3374 | [9 empty] | Schedule Date-Prop. |  |  | 46136 | 46169 | 46175 | N/A | N/A | 46189 | 46216 | N/A | 46224 | 46295
|  | BRRP | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 452172-1 grouped with 453730-1 |  |  | N/A | [10 empty] | Juan Carrillo (941) 708-1129 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: CM. JC, LP
|  |  |  | LONGBOAT KEY DRAWBRI | [10 empty] | BRIDGE-REPAIR/REHABILITATION | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | DGE SUBMARINE CABLE REPLA | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | CEMENT | [10 empty] | September 17, 2026 (125) | [5 empty] | Contact: | 7: date: September 2026; 9: Funds Encumb. Date:
[7 empty] | 0.405 | [10 empty] | 1044228 | ( | 0.0021561 | ) |  | Phone: | 9: Marketing Date:; 11: 46086
|  | NEM-DBA-MLR | [5 empty] | MANATEE | [9 empty] | 156634 | ( | 0.15 | ) |  | Fax: | 9: CEI Contract #:; 11: 27114
5Fb | 452172-1-62-01 | [10 empty] | Michael Rima L. (813) 612-3374 | [9 empty] | Schedule Date-Prop. |  |  | 46136 | 46169 | 46175 | N/A | N/A | 46189 | 46216 | N/A | 46224 | 46295
|  | BRRP | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 452171-1 grouped with 453730-1 |  |  | N/A | [10 empty] | Juan Carrillo (941) 708-1129 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: CM. JC, LP
|  |  |  | SARASOTA COUNTY SUBM | [10 empty] | BRIDGE-REPAIR/REHABILITATION | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | ARINE CABLE REPLACEMENT | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | September 17, 2026 (175) | [5 empty] | Contact: | 7: date: September 2026; 9: Funds Encumb. Date:
[7 empty] | 0.363 | [10 empty] | 3697568 | ( | 0.0076347 | ) |  | Phone: | 9: Marketing Date:; 11: 46086
|  | NEM-DBA-MLR | [5 empty] | SARASOTA | [9 empty] | 739515 | ( | 0.2 | ) |  | Fax: | 9: CEI Contract #:; 11: 27114
5Fc | 453730-1-62-01 | [10 empty] | Joel Hobbs (863) 519-2376 | [9 empty] | Schedule Date-Prop. |  |  | 46136 | 46169 | 46175 | N/A | N/A | 46189 | 46216 | N/A | 46224 | 46295
|  | LF | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 452171-1 grouped with 452172-1 |  |  | N/A | [10 empty] | Juan Carrillo (941) 708-1129 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: CM. JC, LP
|  |  |  | SR 789 GULF OF MEXIC | [10 empty] | ROUNDABOUT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | O DRIVE ROUNDABOUT AT BRO | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | ADWAY | [10 empty] | September 30, 2026 (450) | [5 empty] | Contact: | 7: date: September 2026; 9: Funds Encumb. Date:
[7 empty] | 0.35 | [10 empty] | 6556100 | ( | 0.013537 | ) |  | Phone: | 9: Marketing Date:; 11: 46086
|  | NEM-BCC-JBH | [5 empty] | MANATEE | [9 empty] | 589136 | ( | 0.089861 | ) |  | Fax: | 9: CEI Contract #:; 11: 27114
6Fa | 451480-1-62-01 | [10 empty] | Randy S. Lachler (863) 519-2745 | [9 empty] | Schedule Date-Prop. |  |  | 46147 | 46195 | 46203 | N/A | N/A | 46224 | 46251 | N/A | 46259 | 46326
|  | DS | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 449737-1 grouped with 451481-1 |  |  | N/A | [10 empty] | Kirby Radford (863)519-4107 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: TP, KR, GF
|  |  |  | SR 35 (US 98) FROM N | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OF SR 546 TO S OF GRIFFI | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | N RD | [10 empty] | October 15, 2026 (150) | [5 empty] | Contact: | 7: date: October 2026; 9: Funds Encumb. Date:
[7 empty] | 1.723 | [10 empty] | 4015547 | ( | 0.0082912 | ) |  | Phone: | 9: Marketing Date:; 11: 46121
|  | NEM-KFS-RSL | [5 empty] | POLK | [9 empty] | 509235 | ( | 0.12682 | ) |  | Fax: | 9: CEI Contract #:; 11: 27117
6Fb | 451481-1-62-01 | [10 empty] | Richard W. "Mose" Howard (863) 519-2374 | [9 empty] | Schedule Date-Prop. |  |  | 46147 | 46195 | 46203 | N/A | N/A | 46224 | 46251 | N/A | 46259 | 46387
|  | DDR | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 449737-1 grouped with 451480-1 |  |  | N/A | [10 empty] | Kirby Radford (863)519-4107 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: TP, KR, GF
|  |  |  | SR 35 (US 98) FROM S | [10 empty] | FLEXIBLE PAVEMENT RECONSTRUCT. | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | HARON DR TO N OF NORTON R | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | D | [10 empty] | December 4, 2026 (350) | [5 empty] | Contact: | 7: date: October 2026; 9: Funds Encumb. Date:
[7 empty] | 2.52 | [10 empty] | 16349101 | ( | 0.033757 | ) |  | Phone: | 9: Contractor Award Date:; 11: 46121
|  | NEM-JLM-RWH | [5 empty] | POLK | [9 empty] | 1961892 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: 27117
7Fa | 440342-2-62-01 | [10 empty] | Douglas J. "Doug" Burkhart (863) 533-6209 | [9 empty] | Schedule Date-Prop. |  |  | 46353 | 46392 | 46399 | N/A | N/A | 46413 | 46740 | N/A | 46447 | 46477
|  | ACSA | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
|  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: DA, RH, JW
|  |  |  | KINGS HIGHWAY FROM C | [10 empty] | ADD LANES & RECONSTRUCT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | HARLOTTE COUNTY LINE TO S | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | W GLENADINE AVE | [10 empty] | March 31, 2027 (650) | [5 empty] | Contact: | 7: date: April 2027; 9: Funds Encumb. Date:
[7 empty] | 1.04 | [10 empty] | 21139725 | ( | 0.043649 | ) |  | Phone: | 9: Marketing Date:
|  | NEM-AEB-DJB | [5 empty] | DESOTO | [9 empty] | 2445342 | ( | 0.11568 | ) |  | Fax: | 9: CEI Contract #:; 11: 27120
8Fa | 448928-1-62-01 | [10 empty] | Joel Sevilla (863) 519-2424 | [9 empty] | Schedule Date-Prop. |  |  | 46087 | 46120 | 46126 | N/A | N/A | 46140 | 46163 | N/A | 46171 | 46234
|  | ACSA | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
BDI |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: SH, DD, XY
|  |  |  | SR 25 (US 27) FROM S | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OF WAYMAN RD TO N OF FI | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | SH EATING CREEK | [10 empty] | July 29, 2026 (425) | [5 empty] | Contact: | 7: date July 2026; 9: Funds Encumb. Date:
[7 empty] | 10.466 | [10 empty] | 22283037 | ( | 0.04601 | ) |  | Phone: | 9: Marketing Date:; 11: 46055
|  | NEM-KFS-JDS | [5 empty] | GLADES | [9 empty] | 3566832 | ( | 0.16007 | ) |  | Fax: | 9: CEI Contract #:; 11: 27111
9Fa | 414511-3-62-01 | [10 empty] | Ahmed Abdellatif (863) 519-2834 | [9 empty] | Schedule Date-Prop. |  |  | 46171 | 46204 | 46210 | N/A | N/A | 46224 | 46252 | N/A | 46260 | 46326
|  | DS | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
GW 439750-2 |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: SH, DD, JT
|  |  |  | SR 700 (US 98) FROM | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | E OF SR 25 (US 27) TO E O | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | F FLORAL DR | [10 empty] | October 28, 2026 (175) | [5 empty] | Contact: | 7: date: October 2026; 9: Funds Encumb. Date:
[7 empty] | 4.577 | [10 empty] | 5374698 | ( | 0.011098 | ) |  | Phone: | 9: Marketing Date:; 11: 46139
|  | NEM-AEB-AAA | [5 empty] | HIGHLANDS | [9 empty] | 537470 | ( | 0.1 | ) |  | Fax: | 9: CEI Contract #:; 11: 27116
9Fb | 439750-2-62-01 | [10 empty] | Ahmed Abdellatif (863) 519-2834 | [9 empty] | Schedule Date-Prop. |  |  | 46171 | 46204 | 46210 | N/A | N/A | 46224 | 46252 | N/A | 46260 | 46326
|  | ACSA | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
GW 414511-3 |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: SH, DD, JT
|  |  |  | SR 25 (US 27) FROM S | [10 empty] | RIGID PAVEMENT RECONSTRUCTION | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OUTH OF SR 66 TO NORTH OF | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | SR 66 | [10 empty] | October 28, 2026 (425) | [5 empty] | Contact: | 7: date: October 2026; 9: Funds Encumb. Date:
[7 empty] | 0.518 | [10 empty] | 15331915 | ( | 0.031657 | ) |  | Phone: | 9: Marketing Date:; 11: 46139
|  | NEM-AEB-AAA | [5 empty] | HIGHLANDS | [9 empty] | 2018881 | ( | 0.13168 | ) |  | Fax: | 9: CEI Contract #:; 11: 27116
11Fa | 451270-1-62-01 | [10 empty] | Ahmed Abdellatif (863) 519-2834 | [9 empty] | Schedule Date-Prop. |  |  | 46108 | 46141 | 46147 | N/A | N/A | 45796 | 46185 | N/A | 46192 | 46260
|  | DS | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
goes with 451361-1 goes with 451362-1 goes with 452621-1 goes with 455182-1 |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: DA, DR, TP
|  |  |  | SR 25 (US 27) FROM N | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OF PONCE DE LEON BLVD TO | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | N OF LAKE ISIS AVE | [10 empty] | August 26, 2026 (275) | [5 empty] | Contact: | 7: date: August 2026; 9: Funds Encumb. Date:
[7 empty] | 4.385 | [10 empty] | 6887949 | ( | 0.014222 | ) |  | Phone: | 9: Marketing Date:; 11: 46065
|  | NEM-AEB-AAA | [5 empty] | HIGHLANDS | [9 empty] | 1016094 | ( | 0.14752 | ) |  | Fax: | 9: CEI Contract #:; 11: 27112
11Fb | 451361-1-62-01 | [10 empty] | Ulises Valles (863) 519-2482 | [9 empty] | Schedule Date-Prop. |  |  | 46108 | 46141 | 46147 | N/A | N/A | 45796 | 46185 | N/A | 46192 | 46265
|  | ACSS | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
goes with 451362-1 goes with 452621-1 goes with 455182-1 goes with 451270-1 |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: DA, DR, TP
|  |  |  | US 27 AT SR 17 / SR | [10 empty] | INTERSECTION IMPROVEMENT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | 64 | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | August 26, 2026 (125) | [5 empty] | Contact: | 7: date: August 2026; 9: Funds Encumb. Date:
[7 empty] | 0.22 | [10 empty] | 976979 | ( | 0.0020173 | ) |  | Phone: | 9: Marketing Date:; 11: 46065
|  | NEM-AEB-UVV | [5 empty] | HIGHLANDS | [9 empty] | 145444 | ( | 0.14887 | ) |  | Fax: | 9: CEI Contract #:; 11: 27112
11Fc | 451362-1-62-01 | [10 empty] | Ulises Valles (863) 519-2482 | [9 empty] | Schedule Date-Prop. |  |  | 46108 | 46141 | 46147 | N/A | N/A | 45796 | 46185 | N/A | 46192 | 46265
|  | ACSS | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
goes with 452621-1 goes with 455182-1 goes with 451270-1 goes with 451361-1 |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: DA, DR, TP
|  |  |  | US 27 AT SEBRING PKW | [10 empty] | INTERSECTION IMPROVEMENT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | Y | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | August 26, 2026 (125) | [5 empty] | Contact: | 7: date: August 2026; 9: Funds Encumb. Date:
[7 empty] | 0.285 | [10 empty] | 1429873 | ( | 0.0029524 | ) |  | Phone: | 9: Marketing Date:; 11: 46065
|  | NEM-AEB-UVV | [5 empty] | HIGHLANDS | [9 empty] | 175723 | ( | 0.12289 | ) |  | Fax: | 9: CEI Contract #:; 11: 27112
11Fd | 452621-1-62-01 | [10 empty] | Sam St. Hilaire (863) 519-2554 | [9 empty] | Schedule Date-Prop. |  |  | 46108 | 46141 | 46147 | N/A | N/A | 45796 | 46185 | N/A | 46192 | 46265
|  | DDR | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
goes with 455182-1 goes with 451270-1 goes with 451361-1 goes with 451362-1 |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: DA, DR, TP
|  |  |  | SR25(US27) FROM N OF | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | SANTA MARIA WAY TO N OF | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | PONCE DE LEON | [10 empty] | August 26, 2026 (300) | [5 empty] | Contact: | 7: date: August 2026; 9: Funds Encumb. Date:
[7 empty] | 4.801 | [10 empty] | 11170682 | ( | 0.023065 | ) |  | Phone: | 9: Marketing Date:; 11: 46065
|  | NEM-KFS-SSH | [5 empty] | HIGHLANDS | [9 empty] | 1433236 | ( | 0.1283 | ) |  | Fax: | 9: CEI Contract #:; 11: 27112
11Fe | 455182-1-62-01 | [10 empty] | Randy S. Lachler (863) 519-2745 | [9 empty] | Schedule Date-Prop. |  |  | 46108 | 46141 | 46147 | N/A | N/A | 45796 | 46185 | N/A | 46192 | 46265
|  | ACSS | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
goes with 452621-1 goes with 451270-1 goes with 451361-1 goes with 451362-1 |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: DA, DR, TP
|  |  |  | SR 25 (US 27) FROM W | [10 empty] | SAFETY PROJECT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | HISPER LAKE CIRCLE TO PON | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | CE DE LEON BLVD | [10 empty] | August 26, 2026 (100) | [5 empty] | Contact: | 7: date: August 2026; 9: Funds Encumb. Date:
[7 empty] | 11.548 | [10 empty] | 961959 | ( | 0.0019862 | ) |  | Phone: | 9: Marketing Date:; 11: 46065
|  | NEM-KFS-RSL | [5 empty] | HIGHLANDS | [9 empty] | 115435 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: 27112
12Fa | 452793-1-62-01 | [10 empty] | Christopher B. Speese (239) 225-1973 | [9 empty] | Schedule Date-Prop. |  |  | 46143 | 46176 | 46182 | N/A | N/A | 46196 | 46223 | N/A | 46230 | 46326
|  | ACNP | [10 empty] | Melissa Slater, P.E. (863) 519-2590 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 452794-1 |  |  | N/A | [10 empty] | Alex Ruiz (941) 708-4419 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: JA, AR, RH
|  |  |  | I-75 FROM N OF ALICO | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | RD TO S OF DANIELS PKWY | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | October 28, 2026 (350) | [5 empty] | Contact: | 7: date: September 2026; 9: Funds Encumb. Date:
[7 empty] | 5.515 | [10 empty] | 15883146 | ( | 0.032795 | ) |  | Phone: | 9: Marketing Date:; 11: 46126
|  | NEM-STP-CBS | [5 empty] | LEE | [9 empty] | 1905978 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: 27113
12Fb | 452794-1-62-01 | [10 empty] | Phil Menke (863) 519-2803 | [9 empty] | Schedule Date-Prop. |  |  | 46143 | 46176 | 46182 | N/A | N/A | 46196 | 46223 | N/A | 46230 | 46295
|  | ACNP | [10 empty] | Melissa Slater, P.E. (863) 519-2590 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 452793-1 |  |  | N/A | [10 empty] | Alex Ruiz (941) 708-4419 | [7 empty] | Shortlisted | Name: | 9: Comments:; 11: JA, AR, RH
|  |  |  | I-75 FROM N OF US 30 | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | 1 TO N OF I-275 | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | September 30, 2026 (400) | [5 empty] | Contact: | 7: date: September 2026; 9: Funds Encumb. Date:
[7 empty] | 10.479 | [10 empty] | 20505956 | ( | 0.04234 | ) |  | Phone: | 9: Marketing Date:; 11: 46126
|  | NEM-JBH-PJM | [5 empty] | MANATEE | [9 empty] | 2726242 | ( | 0.13295 | ) |  | Fax: | 9: CEI Contract #:; 11: 27113
13Fa | 410028-1-62-06 | [20 empty] | Schedule Date-Prop. |  |  | 46087 | 46121 | 46133 | N/A | N/A | 46147 | 46176 | N/A | N/A | 46234
|  | DS | [19 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A; 10: N/A
|  |  | N/A | [18 empty] | Shortlisted | Name: | 9: Comments:
|  |  |  | CONSTRUCTION CEI SUP | [10 empty] | INSPECT CONSTRUCTION PROJS. | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | PORT FOR PLAN AND CLAIM R | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | EVIEW #2 - DISTRICT WIDE | [16 empty] | Contact: | 7: date:; 9: Funds Encumb. Date:
[7 empty] | 0 | [11 empty] | ( | 0 | ) |  | Phone: | 9: Contractor Award Date:
|  | JMK-BMB-AMS | [5 empty] | DIST/ST-WIDE | [9 empty] | 200000 | ( |  | ) |  | Fax: | 9: CEI Contract #:; 11: 27127
Full | 198284-1-62-08 | [10 empty] | Jon Sands (863) 519-2223 | [9 empty] | Schedule Date-Prop. |  | 11: 46234
|  | DS | [10 empty] | Brian Blair (863) 519-2676 | [8 empty] | Actual Date
Contractual Services |  |  | N/A | [10 empty] | Anita Michael (863) 519-2256 | [7 empty] | Shortlisted | Name: | 9: Comments:
|  |  |  | CONSTRUCTION ENVIRONMENTAL MITIGATION | [17 empty] | Consultant | Address: | 1: Sara; 9: Project Info:
[5 empty] | CEI CONSULTANT-DISTRICT WIDE | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | July 16, 2026 | [5 empty] | Contact: | 7: date; 9: Funds Encumb. Date:
[19 empty] | ( | 0 | ) |  | Phone: | 9: Contractor Award Date:
|  | JMK-JMS-AM | [5 empty] | DIST/ ST-WIDE | [9 empty] | 60000 | ( |  | ) |  | Fax: | 9: CEI Contract #:; 11: NEW
5Fd | 438067-1-62-01 | [10 empty] | David Agacinski (239)-225-1924 | [9 empty] | Schedule Date-Prop. |  | 11: 46295
|  | ACSM | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date
grouped with 447878-1 grouped with 447287-1 grouped with 453401-1 grouped with 447238-1 grouped with 448030-1 ¦¦ Lump Sum |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 1: SA to 26111; 9: Comments:
|  |  |  | FT THOMPSON AVE FROM SR | [10 empty] | SIDEWALK | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | 29/BRIDGE ST TO SR 80/HICKPOCHEE AVE | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | September 30, 2026 (225) | [5 empty] | Contact: | 7: date; 9: Funds Encumb. Date:
[18 empty] | 2475770 | ( | 0.0051119 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-STP-DJA | [5 empty] | HENDRY | [9 empty] | 463448 | ( | 0.18719 | ) |  | Fax: | 9: CEI Contract #:; 11: 26111
5Fe | 447238-1-62-01 | [10 empty] | Jeffrey M. Jones (239)-225-1920 | [9 empty] | Schedule Date-Prop. |  | 11: 46295
|  | GFBR | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date
Grouped With 447878-1 grouped with 447287-1 grouped with 453401-1 grouped with 438067-1 grouped with 448030-1 |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 1: SA to 26111; 9: Comments:
|  |  |  | HOMESTEAD AVENUE OVE | [10 empty] | BRIDGE REPLACEMENT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | R MARSH CREEK BRIDGE #074 | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | 026 | [10 empty] | September 30, 2026 (135) | [5 empty] | Contact: | 7: date; 9: Funds Encumb. Date:
[7 empty] | 0.36 | [10 empty] | 1915451 | ( | 0.003955 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-STP-JMJ | [5 empty] | HENDRY | [9 empty] | 229854 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: 26111
5Ff | 448030-1-62-01 | [10 empty] | Jacques J. Louis (239)-225-1914 | [9 empty] | Schedule Date-Prop. |  | 11: 46323
|  | ACSA | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date
Grouped With 447878-1 grouped with 447287-1 grouped with 453401-1 grouped with 438067-1 grouped with 447238-1 ¦¦ Lump Sum |  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 1: SA to 26111; 9: Comments:
|  |  |  | CENTRAL ELEMENTARY - | [10 empty] | SIDEWALK | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | SRTS | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[17 empty] | October 28, 2026 (125) | [5 empty] | Contact: | 7: date; 9: Funds Encumb. Date:
[7 empty] | 0.745 | [10 empty] | 1123040 | ( | 0.0023188 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-STP-JJL | [5 empty] | HENDRY | [9 empty] | 174905 | ( | 0.15574 | ) |  | Fax: | 9: CEI Contract #:; 11: 26111
C/S | 413065-2-62-01 | [10 empty] | Darryl T. Richard (863) 519-2266 | [9 empty] | Schedule Date-Prop. |  | 11: 46326
|  | DS | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | I-75 (SR 93) AT COLONIAL BLVD | [10 empty] | LANDSCAPING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | (SR884) INTERCHANGE | [18 empty] | 9: Funds Encumbered:
[17 empty] | October 15, 2026 | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 2644530 | ( | 0.0054604 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-SEF-DTR | [5 empty] | LEE | [9 empty] | 254668 | ( | 0.0963 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 425843-3-62-01 | [10 empty] | Darryl T. Richard (863) 519-2266 | [9 empty] | Schedule Date-Prop. |  | 11: 46356
|  | DS | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | I-75 (SR 93) AT SR 9 | [10 empty] | LANDSCAPING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | 51 (COLLIER BLVD INTERCHA | [18 empty] | 9: Funds Encumbered:
[6 empty] | NGE) | [10 empty] | November 5, 2026 (100) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.733 | [10 empty] | 1234800 | ( | 0.0025496 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-SEF-DTR | [5 empty] | COLLIER | [9 empty] | 148176 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 433592-5-62-01 | [10 empty] | Amy E. Blair (863) 519-2272 | [9 empty] | Schedule Date-Prop. |  | 11: 46477
|  | ACSU | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
GW 455644-1 GW 449653-1 GW 451026-1 |  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #MOC C/S #8; 8: Lockdown; 9: Comments:
|  |  |  | SR 45 (US 41) FROM 6 | [10 empty] | SIDEWALK | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | 9TH AVE (BAY DR) TO 63RD | [18 empty] | 9: Funds Encumbered:
[6 empty] | AVE | [10 empty] | March 31, 2027 (175) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.758 | [10 empty] | 3139909 | ( | 0.0064832 | ) |  | Phone: | 9: Contractor Award Date:
|  | JMK-BCC-AEB | [5 empty] | MANATEE | [9 empty] | 349639 | ( | 0.11135 | ) |  | Fax: | 9: CEI Contract #:; 11: MOC C/S #8
C/S | 433726-3-62-01 | [10 empty] | Darryl T. Richard (863) 519-2266 | [9 empty] | Schedule Date-Prop. |  | 11: 46326
|  | DS | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | SR 865 (SAN CARLOS) FROM ESTERO | [10 empty] | LANDSCAPING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | BLVD TO MAIN ST | [18 empty] | 9: Funds Encumbered:
[17 empty] | October 15, 2026 (100) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 668850 | ( | 0.001381 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-SEF-DTR | [5 empty] | LEE | [9 empty] | 80262 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 438262-1-62-01 | [10 empty] | Jacques J. Louis (239)-225-1914 | [9 empty] | Schedule Date-Prop. |  | 11: 46446
|  | TALT | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | SR 45 (US 41) TAMIAM | [10 empty] | SIDEWALK | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | I TRAIL FROM CONWAY BLVD | [18 empty] | 9: Funds Encumbered:
[6 empty] | TO MIDWAY BLVD | [10 empty] | February 24, 2027 (350) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 2.136 | [10 empty] | 8713615 | ( | 0.017992 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-STP-JJL | [5 empty] | CHARLOTTE | [9 empty] | 660164 | ( | 0.075762 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 444807-2-62-01 | [10 empty] | Richard W. "Mose" Howard (863) 519-2374 | [9 empty] | Schedule Date-Prop. |  | 11: 46538
|  | ACSU | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; 8: Lockdown; 9: Comments:
|  |  |  | US 41 FROM 10TH AVE | [10 empty] | TRAFFIC OPS IMPROVEMENT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | TO MANATEE AVE E | [18 empty] | 9: Funds Encumbered:
[17 empty] | May 26, 2027 (200) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 1.35 | [10 empty] | 3392847 | ( | 0.0070055 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JLM-RWH | [5 empty] | MANATEE | [9 empty] | 441071 | ( | 0.13 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ61
C/S | 444807-6-62-01 | [10 empty] | Richard W. "Mose" Howard (863) 519-2374 | [9 empty] | Schedule Date-Prop. |  | 11: 46538
|  | ACSU | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAK10; 8: Lockdown; 9: Comments:
|  |  |  | 3RD ST E AND 3RD ST | [10 empty] | TRAFFIC OPS IMPROVEMENT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | W ONE-WAY PAIR | [18 empty] | 9: Funds Encumbered:
[17 empty] | May 26, 2027 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 1.35 | [10 empty] | 1945174 | ( | 0.0040164 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JLM-RWH | [5 empty] | MANATEE | [9 empty] | 252642 | ( | 0.12988 | ) |  | Fax: | 9: CEI Contract #:; 11: CAK10
C/S | 444904-1-62-01 | [10 empty] | Xiaoxue peng (863) 519-2368 | [9 empty] | Schedule Date-Prop. |  | 11: 46538
|  | TALU | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; 8: Lockdown; 9: Comments:
|  |  |  | SR 45 (USB 41) 8TH A | [10 empty] | SAFETY PROJECT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | VE W PEDESTRIAN MIDBLOCK | [18 empty] | 9: Funds Encumbered:
[6 empty] | CROSSINGS | [10 empty] | May 26, 2027 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.188 | [10 empty] | 1306828 | ( | 0.0026983 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-SEF-XP | [5 empty] | MANATEE | [9 empty] | 196025 | ( | 0.15 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ61
C/S | 445296-4-62-01 | [10 empty] | Darryl T. Richard (863) 519-2266 | [9 empty] | Schedule Date-Prop. |  | 11: 46446
|  | DS | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | SR93 AT PINE RIDGE RD | [10 empty] | LANDSCAPING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | INTERCHANGE | [18 empty] | 9: Funds Encumbered:
[17 empty] | February 18, 2027 (110) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 1440600 | ( | 0.0029745 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-KSI-DTR | [5 empty] | COLLIER | [9 empty] | 168000 | ( | 0.11662 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 446204-1-62-01 | [10 empty] | Sam St. Hilaire (863) 519-2554 | [9 empty] | Schedule Date-Prop. |  | 11: 46326
|  | DDR | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #HOC C/S #5; 8: Lockdown; 9: Comments:
|  |  |  | SR 35 (US 17) FROM S | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OF HEARTLAND WAY TO N OF | [18 empty] | 9: Funds Encumbered:
[6 empty] | HILTON RD | [10 empty] | October 28, 2026 (350) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 7.831 | [10 empty] | 12714412 | ( | 0.026253 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-KFS-SSH | [5 empty] | HARDEE | [9 empty] | 1826779 | ( | 0.14368 | ) |  | Fax: | 9: CEI Contract #:; 11: HOC C/S #5
C/S | 446205-1-62-01 | [10 empty] | C. Scott McCall (863) 519-2277 | [9 empty] | Schedule Date-Prop. |  | 11: 46323
|  | ACSA | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #HOC C/S #5; 8: Lockdown; 9: Comments:
|  |  |  | SR 35 (US 17) FROM N | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OF SR 64 TO BELL ST | [18 empty] | 9: Funds Encumbered:
[17 empty] | October 28, 2026 (400) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 8.09 | [10 empty] | 15596202 | ( | 0.032203 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JBH-CSM | [5 empty] | HARDEE | [9 empty] | 1877543 | ( | 0.12038 | ) |  | Fax: | 9: CEI Contract #:; 11: HOC C/S #5
C/S | 446274-1-62-01 | [10 empty] | Ahmed Abdellatif (863) 519-2834 | [9 empty] | Schedule Date-Prop. |  | 11: 46358
|  | ACSS | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
Goes with 451469-1 |  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 563 AT PEAR ST / | [10 empty] | MEDIAN MODIFICATION | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | PARKER ST | [18 empty] | 9: Funds Encumbered:
[17 empty] | December 2, 2026 (100) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.1 | [10 empty] | 413696 | ( | 0.00085419 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-AEB-AAA | [5 empty] | POLK | [9 empty] | 69972 | ( | 0.16914 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 448964-1-62-01 | [10 empty] | Ulises Valles (863-519-2482 | [9 empty] | Schedule Date-Prop. |  | 11: 46533
|  | ACBZ | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #HOC C/S #5; 8: Lockdown; 9: Comments:
|  |  |  | OAK HILL CEMETERY RD | [10 empty] | BRIDGE REPLACEMENT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OVER BONES CREEK BRIDGE | [18 empty] | 9: Funds Encumbered:
[6 empty] | #044040 | [10 empty] | May 26, 2027 (200) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 1.004 | [10 empty] | 2960226 | ( | 0.0061122 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-MLP-UVV | [5 empty] | DESOTO | [9 empty] | 334635 | ( | 0.11304 | ) |  | Fax: | 9: CEI Contract #:; 11: HOC C/S #5
C/S | 449652-1-62-01 | [10 empty] | Ulises Valles (863-519-2482 | [9 empty] | Schedule Date-Prop. |  | 11: 46477
|  | ACSS | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
gw 451105-1 |  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | SR 776 FROM MERCHANT | [10 empty] | SAFETY PROJECT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | S CROSSING TO SARASOTA CO | [18 empty] | 9: Funds Encumbered:
[6 empty] | UNTY LINE | [10 empty] | March 31, 2027 (175) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 1.02 | [10 empty] | 3121543 | ( | 0.0064453 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-AEB-UVV | [5 empty] | CHARLOTTE | [9 empty] | 250507 | ( | 0.080251 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 449653-1-62-01 | [10 empty] | Marie Carvajal (863) 519-2669 | [9 empty] | Schedule Date-Prop. |  | 11: 46477
|  | ACSS | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
GW 451026-1 GW 455644-1 GW 433592-5 |  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; 8: Lockdown; 9: Comments:
|  |  |  | US 41 FROM MAGELLAN | [10 empty] | SAFETY PROJECT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | DR TO 63RD AVE | [18 empty] | 9: Funds Encumbered:
[17 empty] | March 31, 2027 (100) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.871 | [10 empty] | 2489007 | ( | 0.0051393 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JBH-MMC | [5 empty] | MANATEE | [9 empty] | 69093 | ( | 0.027759 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ61
C/S | 449681-1-62-01 | [10 empty] | Jacques J. Louis (239)-225-1914 | [9 empty] | Schedule Date-Prop. |  | 11: 46418
|  | TALU | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
goes with 449683-1 ¦¦ BDI |  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | VIA COCONUT POINT RO | [10 empty] | SIDEWALK | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | UNDABOUT FROM COCONUT RD | [18 empty] | 9: Funds Encumbered:
[6 empty] | TO CORKSCREW RD | [10 empty] | January 27, 2027 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.176 | [10 empty] | 1713191 | ( | 0.0035374 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-STP-JJL | [5 empty] | LEE | [9 empty] | 198460 | ( | 0.11584 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 449683-1-62-01 | [10 empty] | Jacques J. Louis (239)-225-1914 | [9 empty] | Schedule Date-Prop. |  | 11: 46418
|  | TALU | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
goes with 449681-1 ¦¦ BDI |  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | COCONUT RD SIDEWALK | [10 empty] | SIDEWALK | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | FROM OAKWILD TO VIA COCON | [18 empty] | 9: Funds Encumbered:
[6 empty] | UT POINT | [10 empty] | January 27, 2027 (100) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.423 | [10 empty] | 736320 | ( | 0.0015203 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-STP-JJL | [5 empty] | LEE | [9 empty] | 74055 | ( | 0.10057 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 450876-1-62-01 | [10 empty] | Ammber Albritton (863) 519-2253 | [9 empty] | Schedule Date-Prop. |  | 11: 46356
|  | DDR | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 600 (US 92/US 17) | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | FROM S OF SOUTH BLVD TO | [18 empty] | 9: Funds Encumbered:
[6 empty] | N OF NORTH BLVD | [10 empty] | November 5, 2026 (100) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 1.055 | [10 empty] | 907369 | ( | 0.0018735 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JBH-AMA | [5 empty] | POLK | [9 empty] | 131038 | ( | 0.14442 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 450877-1-62-01 | [10 empty] | Jennifer Freeman (863) 519-2543 | [9 empty] | Schedule Date-Prop. |  | 11: 46446
|  | DS | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
goes with 457732-1 |  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 35/700 (US 98) FR | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OM S OF SR 540 (WINTER LA | [18 empty] | 9: Funds Encumbered:
[6 empty] | KE RD) TO N OF BROOKS ST | [10 empty] | February 18, 2027 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 1.176 | [10 empty] | 2880301 | ( | 0.0059472 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-AEB-AAA | [5 empty] | POLK | [9 empty] | 345636 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 450883-1-62-01 | [10 empty] | Jennifer Freeman (863) 519-2543 | [9 empty] | Schedule Date-Prop. |  | 11: 46234
|  | DDR | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 17 FROM NORTH OF | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OLD SCENIC HWY TO LAKE MA | [18 empty] | 9: Funds Encumbered:
[6 empty] | RION RD / SR 544 | [10 empty] | July 16, 2026 (150) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 5.315 | [10 empty] | 4059117 | ( | 0.0083812 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-KSJ-JLF | [5 empty] | POLK | [9 empty] | 416465 | ( | 0.1026 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 451013-1-62-01 | [10 empty] | Jennifer Freeman (863) 519-2543 | [9 empty] | Schedule Date-Prop. |  | 11: 09/31/26
|  | DDR | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #MOC C/S #8; 8: Lockdown; 9: Comments:
|  |  |  | SR 789 FROM LONGBOAT | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | CLUB RD TO MANATEE CO LI | [18 empty] | 9: Funds Encumbered:
[6 empty] | NE | [10 empty] | September 17, 2026 (200) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 5.106 | [10 empty] | 5694393 | ( | 0.011758 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-KSJ-JLF | [5 empty] | SARASOTA | [9 empty] | 557086 | ( | 0.097831 | ) |  | Fax: | 9: CEI Contract #:; 11: MOC C/S #8
C/S | 451020-1-62-01 | [10 empty] | C. Scott McCall (863) 519-2277 | [9 empty] | Schedule Date-Prop. |  | 11: 46234
|  | ACSA | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; 8: Lockdown; 9: Comments:
|  |  |  | SR 64 FROM W OF CR 6 | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | 75 TO WINGATE ROAD | [18 empty] | 9: Funds Encumbered:
[17 empty] | July 29, 2026 (300) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 10.852 | [10 empty] | 12599852 | ( | 0.026016 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JBH-CSM | [5 empty] | MANATEE | [9 empty] | 2202285 | ( | 0.17479 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ61
C/S | 451026-1-62-01 | [10 empty] | Marie Carvajal (863) 519-2669 | [9 empty] | Schedule Date-Prop. |  | 11: 46477
|  | ACSA | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
GW 449653-1 GW 455644-1 GW 433592-5 |  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAK10; 8: Lockdown; 9: Comments:
|  |  |  | SR 45 (US 41) FROM N | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | OF MAGELLAN DR TO N OF 6 | [18 empty] | 9: Funds Encumbered:
[6 empty] | 3RD AVE W | [10 empty] | March 31, 2027 (150) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.922 | [10 empty] | 3871418 | ( | 0.0079936 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JBH-MMC | [5 empty] | MANATEE | [9 empty] | 546495 | ( | 0.14116 | ) |  | Fax: | 9: CEI Contract #:; 11: CAK10
C/S | 451101-1-62-01 | [10 empty] | Ulises Valles (863-519-2482 | [9 empty] | Schedule Date-Prop. |  | 11: 46234
|  | DDR | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #FMOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 45 (US41) FROM S OF AQUI ESTA | [17 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | DR TO S OF CARMALITA ST | [18 empty] | 9: Funds Encumbered:
[17 empty] | July 16, 2026 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 3163383 | ( | 0.0065317 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-AEB-UVV | [5 empty] | CHARLOTTE | [9 empty] | 282632 | ( | 0.089345 | ) |  | Fax: | 9: CEI Contract #:; 11: FMOC C/S #7
C/S | 451103-1-62-01 | [10 empty] | Kellie F. Spurgeon (863) 519-2654 | [9 empty] | Schedule Date-Prop. |  | 11: 46387
|  | DDR | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #FMOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 31 FROM N OF CR 7 | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | 4 TO DESOTO COUNTY LINE | [18 empty] | 9: Funds Encumbered:
[17 empty] | December 3, 2026 (200) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 5.965 | [10 empty] | 6388426 | ( | 0.013191 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-SEF-KFS | [5 empty] | CHARLOTTE | [9 empty] | 607800 | ( | 0.095141 | ) |  | Fax: | 9: CEI Contract #:; 11: FMOC C/S #7
C/S | 451105-1-62-01 | [10 empty] | Ulises Valles (863-519-2482 | [9 empty] | Schedule Date-Prop. |  | 11: 46477
|  | DS | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
goes with 449652-1 |  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #FMOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 776 FROM N OF PIN | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | E ST TO SARASOTA COUNTY L | [18 empty] | 9: Funds Encumbered:
[6 empty] | INE | [10 empty] | March 31, 2027 (265) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 2.088 | [10 empty] | 7996376 | ( | 0.016511 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-AEB-UVV | [5 empty] | CHARLOTTE | [9 empty] | 789568 | ( | 0.098741 | ) |  | Fax: | 9: CEI Contract #:; 11: FMOC C/S #7
C/S | 451106-1-62-01 | [10 empty] | Sam St. Hilaire (863) 519-2554 | [9 empty] | Schedule Date-Prop. |  | 11: 46356
|  | DS | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #HOC C/S #5; 8: Lockdown; 9: Comments:
|  |  |  | SR 710 FROM SR 70 TO | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | N. OF INTERCEPTOR CREEK | [18 empty] | 9: Funds Encumbered:
[6 empty] | BRIDGE #910065 | [10 empty] | November 5, 2026 (100) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 1.101 | [10 empty] | 1401443 | ( | 0.0028937 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-KFS-SSH | [5 empty] | OKEECHOBEE | [9 empty] | 182882 | ( | 0.1305 | ) |  | Fax: | 9: CEI Contract #:; 11: HOC C/S #5
C/S | 451108-1-62-01 | [10 empty] | Phil Menke (863) 519-2803 | [9 empty] | Schedule Date-Prop. |  | 11: 46414
|  | ACSA | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #HOC C/S #5; 8: Lockdown; 9: Comments:
|  |  |  | SR 700 (US 98) FROM | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | BRIDGE #090016 TO BRIDGE | [18 empty] | 9: Funds Encumbered:
[6 empty] | #910090 | [10 empty] | January 27, 2027 (175) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 4.711 | [10 empty] | 5823436 | ( | 0.012024 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JLM-PJM | [5 empty] | OKEECHOBEE | [9 empty] | 698812 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: HOC C/S #5
C/S | 451276-1-62-01 | [10 empty] | C. Scott McCall (863) 519-2277 | [9 empty] | Schedule Date-Prop. |  | 11: 46234
|  | DDR | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
goes with 451275-1 |  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | SR 29 FROM S OF I-75 | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | TO N OF BRIDGE NO 030298 | [18 empty] | 9: Funds Encumbered:
[17 empty] | July 16, 2026 (150) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 4.725 | [10 empty] | 4711194 | ( | 0.0097276 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JBH-CSM | [5 empty] | COLLIER | [9 empty] | 485403 | ( | 0.10303 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 451277-1-62-01 | [10 empty] | C. Scott McCall (863) 519-2277 | [9 empty] | Schedule Date-Prop. |  | 11: 46264
|  | DDR | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
goes with 456577-1 |  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | SR29 FROM N OF OIL WELL | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | RD (CR858) TO N OF BRIDGE #030304 | [18 empty] | 9: Funds Encumbered:
[17 empty] | August 26, 2026 (150) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 4745565 | ( | 0.0097986 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JBH-CSM | [5 empty] | COLLIER | [9 empty] | 559697 | ( | 0.11794 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 451360-1-62-01 | [10 empty] | Sam St. Hilaire (863) 519-2554 | [9 empty] | Schedule Date-Prop. |  | 11: 46234
|  | ACSS | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #FMOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 776 AT OCEANSPRAY | [10 empty] | MEDIAN MODIFICATION | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | BLVD | [18 empty] | 9: Funds Encumbered:
[17 empty] | July 29, 2026 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.636 | [10 empty] | 1212661 | ( | 0.0025039 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-KFS-SSH | [5 empty] | CHARLOTTE | [9 empty] | 121932 | ( | 0.10055 | ) |  | Fax: | 9: CEI Contract #:; 11: FMOC C/S #7
C/S | 451469-1-62-01 | [10 empty] | Kimberly Abate ( 863) 519-2424 | [9 empty] | Schedule Date-Prop. |  | 11: 46358
|  | DS | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
Goes with 446274-1 |  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 563 FROM S OF SR | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | 539 (KATHLEEN RD) TO S OF | [18 empty] | 9: Funds Encumbered:
[6 empty] | SR 546 (US 92) | [10 empty] | December 2, 2026 (100) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.766 | [10 empty] | 1200034 | ( | 0.0024778 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-KFS-JDS | [5 empty] | POLK | [9 empty] | 157154 | ( | 0.13096 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 451470-1-62-01 | [10 empty] | Kellie F. Spurgeon (863) 519-2654 | [9 empty] | Schedule Date-Prop. |  | 11: 46234
|  | DS | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 539 FROM N OF ELL | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | IOT ST TO N OF I-4 | [18 empty] | 9: Funds Encumbered:
[17 empty] | July 16, 2026 (100) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.373 | [10 empty] | 740069 | ( | 0.0015281 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-SEF-KFS | [5 empty] | POLK | [9 empty] | 113217 | ( | 0.15298 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 451473-1-62-01 | [10 empty] | Kimberly Abate ( 863) 519-2424 | [9 empty] | Schedule Date-Prop. |  | 11: 46356
|  | DS | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
goes with 457272-1 |  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 8: Lockdown; 9: Comments:
|  |  |  | SR 600 (US 92) FROM | [10 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | COUNTY LINE RD TO E OF CH | [18 empty] | 9: Funds Encumbered:
[6 empty] | URCHILL AVE | [10 empty] | November 5, 2026 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 2.446 | [10 empty] | 3221610 | ( | 0.0066519 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-KFS-JDS | [5 empty] | POLK | [9 empty] | 338830 | ( | 0.10517 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 453538-1-62-01 | [10 empty] | Cassie Lee (863) 519-2342 | [9 empty] | Schedule Date-Prop. |  | 11: 46418
|  | ACSU | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #MOC C/S #8; 8: Lockdown; 9: Comments:
|  |  |  | US41(SR45) GOLF GATE DR | [10 empty] | ATMS - ARTERIAL TRAFFIC MGMT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | TO GLENGARY ST ATSPM/CV UPGRADE | [18 empty] | 9: Funds Encumbered:
[17 empty] | January 27, 2027 (200) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 3755574 | ( | 0.0077544 | ) |  | Phone: | 9: Contractor Award Date:
|  | JMK-SAD-CAL | [5 empty] | SARASOTA | [9 empty] | 519120 | ( | 0.13823 | ) |  | Fax: | 9: CEI Contract #:; 11: MOC C/S #8
C/S | 453561-1-62-01 | [10 empty] | Phil Menke (863) 519-2803 | [9 empty] | Schedule Date-Prop. |  | 11: 46295
|  | ACNP | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; 8: Lockdown; 9: Comments:
|  |  |  | I-275 FROM S OF US19 | [10 empty] | RESURFACING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | TO N OF US 19 | [18 empty] | 9: Funds Encumbered:
[17 empty] | September 30, 2026 (175) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 3.029 | [10 empty] | 4777942 | ( | 0.0098654 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JLM-PJM | [5 empty] | MANATEE | [9 empty] | 525574 | ( | 0.11 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ61
C/S | 455644-1-62-01 | [10 empty] | Rob R. Swann (813) 435-8877 | [9 empty] | Schedule Date-Prop. |  | 11: 46477
|  | ACSS | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
GW 433592-5 GW 449653-1 GW 451025-1 |  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #MOC C/S #8; 8: Lockdown; 9: Comments:
|  |  |  | US41 (TAMIAMI TRAIL) | [10 empty] | LIGHTING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | FROM N OF MAGELLEN DR. T | [18 empty] | 9: Funds Encumbered:
[6 empty] | O 69TH AVE/BAY DR | [10 empty] | March 31, 2027 (75) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 0.193 | [10 empty] | 187407 | ( | 0.00038695 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JPK-RRS | [5 empty] | MANATEE | [9 empty] | 39102 | ( | 0.20865 | ) |  | Fax: | 9: CEI Contract #:; 11: MOC C/S #8
C/S | 455933-1-62-01 | [10 empty] | Darryl T. Richard (863) 519-2266 | [9 empty] | Schedule Date-Prop. |  | 11: 46476
|  | DS | [10 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #HOC C/S #5; 8: Lockdown; 9: Comments:
|  |  |  | SR25(US27) N OF VISI | [10 empty] | LANDSCAPING | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | ON ST TO TOMOKA BLVD | [18 empty] | 9: Funds Encumbered:
[17 empty] | November 5, 2026 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[7 empty] | 3.168 | [10 empty] | 1804866 | ( | 0.0037267 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-KSI-DTR | [5 empty] | HIGHLANDS | [9 empty] | 226380 | ( | 0.12543 | ) |  | Fax: | 9: CEI Contract #:; 11: HOC C/S #5
C/S | 456577-1-62-01 | [10 empty] | C. Scott McCall (863) 519-2277 | [9 empty] | Schedule Date-Prop. |  | 11: 46265
|  | ACSS | [10 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
goes with 451277-1 |  |  | N/A | [10 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; 8: Lockdown; 9: Comments:
|  |  |  | SR 29 AT OIL WELL ROAD | [10 empty] | LIGHTING | [6 empty] | Consultant | Address: | 9: Project Info:
Funds Encumbered:
[17 empty] | August 26, 2026 (150) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 513141 | ( | 0.0010595 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-JBH-CSM | [5 empty] | COLLIER | [9 empty] | 84378 | ( | 0.16443 | ) |  | Fax: | 9: CEI Contract #:; 11: CAQ65
C/S | 457242-1-62-01 | [10 empty] | Amanda Albritton (863) 519-2253 | [9 empty] | Schedule Date-Prop. |  | 11: 46538
|  | ACSA | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #MOC C/S #8; 8: Lockdown; 9: Comments:
|  |  |  | US41 & PINEY POINT AND US 41 & DOCK | [10 empty] | INTERSECTION IMPROVEMENT | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | STREET INTERSECTION | [18 empty] | 9: Funds Encumbered:
[17 empty] | May 26, 2027 (175) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 3895526 | ( | 0.0080434 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-WHB-AMA | [5 empty] | MANATEE | [9 empty] | 407484 | ( | 0.1046 | ) |  | Fax: | 9: CEI Contract #:; 11: MOC C/S #8
C/S | 457272-1-62-01 | [10 empty] | Karina Della Sera (863) 519-2750 | [9 empty] | Schedule Date-Prop. |  | 11: 46356
|  | DDR | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
goes with 451473-1 |  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 9: Comments:
|  |  |  | US92 FROM CLARK RD TO GLADES AVE | [10 empty] | DRAINAGE IMPROVEMENTS | [6 empty] | Consultant | Address: | 9: Project Info:
Funds Encumbered:
[17 empty] | November 5, 2026 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 2668627 | ( | 0.0055101 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-BJS-KDS | [5 empty] | POLK | [9 empty] | 320235 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 457280-1-62-01 | [10 empty] | Samuel Berkman ( 863) 519-2317 | [9 empty] | Schedule Date-Prop. |  | 11: 46477
|  | ACSS | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 9: Comments:
|  |  |  | US 27 AT SOUTH BLVD | [10 empty] | TRAFFIC SIGNALS | [6 empty] | Consultant | Address: | 9: Project Info:
Funds Encumbered:
[17 empty] | March 31, 2027 | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 1783184 | ( | 0.0036819 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-WHB-SFB | [5 empty] | POLK | [9 empty] | 267477 | ( | 0.15 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 457732-1-62-01 | [10 empty] | Kellie F. Spurgeon (863) 519-2654 | [9 empty] | Schedule Date-Prop. |  | 11: 45716
|  | FC5 | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
goes with 450877-1 |  |  | N/A | [10 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #BOC C/S #7; 9: Comments:
|  |  |  | SR35 (US98) FROM SR540A TO SOUTH OF BONNEY PARK | [10 empty] | RESURFSCING | [6 empty] | Consultant | Address: | 9: Project Info:
Funds Encumbered:
[17 empty] | February 18, 2027 (150) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 7676546 | ( | 0.01585 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-SEF-KFS | [5 empty] | POLK | [9 empty] | 308700 | ( | 0.040213 | ) |  | Fax: | 9: CEI Contract #:; 11: BOC C/S #7
C/S | 457879-1-62-01 | [10 empty] | Michael Rima (863) 612-3373 | [9 empty] | Schedule Date-Prop. |  | 11: 46418
|  | BRRP | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #MOC C/S #8; 9: Comments:
|  |  |  | HERNANDO DESOTO BRIDGE 130053 | [10 empty] | BRIDGE-REPAIR/REHABILITATION | [6 empty] | Consultant | Address: | 9: Project Info:
Funds Encumbered:
[17 empty] | January 21, 2027 (250) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 4569922 | ( | 0.0094359 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-DBA-MLR | [5 empty] | MANATEE | [9 empty] | 685489 | ( | 0.15 | ) |  | Fax: | 9: CEI Contract #:; 11: MOC C/S #8
C/S | 457881-1-62-01 | [10 empty] | Michael Rima (863) 612-3373 | [9 empty] | Schedule Date-Prop. |  | 11: 46387
|  | DS | [10 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [10 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | 1: - CONTINUING SERVICES (CS) CONTRACT #MOC C/S #8; 9: Comments:
|  |  |  | US41 SB OVER SOUTH CREEK | [10 empty] | BRIDGE-REPAIR/REHABILITATION | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | BRIDGE #170014 | [18 empty] | 9: Funds Encumbered:
[17 empty] | December 3, 2026 (125) | [5 empty] | Contact: | 9: Funds Encumb. Date:
[18 empty] | 1149806 | ( | 0.0023741 | ) |  | Phone: | 9: Contractor Award Date:
|  | NEM-DBA-MLR | [5 empty] | SARASOTA | [9 empty] | 137977 | ( | 0.12 | ) |  | Fax: | 9: CEI Contract #:; 11: MOC C/S #8
SA | 449737-1-62-01 | [10 empty] | Amy E. Blair (863) 519-2272 | [9 empty] | Schedule Date-Prop. |  |  | 46147 | 46195 | 46203 | N/A | N/A | 46224 | 46251 | N/A | 46259 | 46446
|  | ACFP | [10 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | 5: N/A; 6: N/A; 9: N/A
grouped with 451480-1 grouped with 451481-1 |  |  | N/A | [10 empty] | Kirby Radford (863)519-4107 | [7 empty] | Shortlisted | Name: | 1: SA to 27117; 9: Comments:; 11: TP, KR, GF
|  |  |  | I-4 REST AREAS IN PO | [10 empty] | PARKING FACILITY | [6 empty] | Consultant | Address: | 9: Project Info:
[5 empty] | LK COUNTY - ADDITIONAL TR | [18 empty] | 7: report card/ lockdown; 9: Funds Encumbered:
[6 empty] | UCK PARKING | [10 empty] | February 24, 2027 (400) | [5 empty] | Contact: | 7: date: October 2026; 9: Funds Encumb. Date:
[7 empty] | 0.85 | [10 empty] | 9971663 | ( | 0.020589 | ) |  | Phone: | 9: Marketing Date:
|  | NEM-BCC-AEB | [5 empty] | POLK | [9 empty] | 1096883 | ( | 0.11 | ) |  | Fax: | 9: CEI Contract #:; 11: 27117
|  | CEI FY 26/27 Total Phase 52 | [15 empty] | 484312255 | ( | 1 | )
|  | CEI FY 26/27 Total Phase 62 | [15 empty] | 60477391 | ( | 0.12487 | )

## Sheet1 (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38