## Slide 1: Stockpile in PrC
Help!!!!!!!

## Slide 2: Stockpile
  Standard Specification and Settings in PrC
  Fields
  Pay Item Numbers
      Contract Item Number
      Project Item Number
  Item Recovery Percentage
  Recovery Date
  Pause
  Transaction Types and what triggers them (DWR)
  Correcting entries
      Item not posted on DWR
      Item posted on DWR
  Reference Material

## Slide 4: Stockpile Percentages…
PrC Error: when the Stockpile Amount is greater than 85% of the unpaid balance on a project item number
Percentage of the bid price is calculated manually for entry into PrC
  Structural steel, ITS, and precast prestressed items not to exceed 85%
  Other items should not exceed 75%
  Standard Specifications 9-5.5.2
  Not the “Recovery Percentage”
PrC can't send an error for the 75% max. Ensure the allowable spec percentage is not exceeded
Notes: If the bid amount is $100,000 and $50,000 has been posted or paid, only 75% or 85% of the balance is permitted to be stockpiled in PrC ($37,500 – 75%)
Tip: Use the Estimate Detail Report to calculate the percentage of the unpaid amount on the item. If you still get an error, check to see if a quantity has been posted on a DWR but not yet paid.

## Slide 5: Stockpile Fields…
Hover over any field name for a definition of the corresponding field entry
If set to 100%, Stockpile is fully recovered once Item is 100% completed
Date stockpile will begin recovering once item is posted on a DWR
Contract Item Number
Project Item Number(s)
If set to 75%, Stockpile is fully recovered once Item is 75% completed
  When deselected, PrC Recovers for ALL PAUSED months on the NEXT Estimate
  Pauses Recovery Adjustments while selected
Notes: Push the recovery date back, if the stockpiled items will not install for a few months
The Pause button will pause system generated recovery adjustments (negative adjustments) on estimates when the item is posted on a DWR. When the Pause is deselected, PrC will automatically recover everything during the paused period on the next estimate. PrC does not recalculate the recovery among the future estimate periods. This will cause a large negative adjustment in one estimate period. Do not select pause unless there is a real need. Remember to unpause to avoid an overpayment at contract completion.

## Slide 6: Stockpile Fields – Pay Item Numbers
Project Item Distribution:
  Project Item Line Number – Financial Project – Category ID
      For Structures, each Bridge will have a different Category ID
  Selected when adding money to the stockpile transaction
Contract Item Number:
  Can have multiple Project Item Numbers tied to it
  Selected when the new stockpile record is created
Ensure the stockpile amount is being applied to the correct project(s). One or more projects can be entered on the same Stockpile.
Remember:
Notes: Tip: Use the Estimate Detail Report to calculate the percentage of the unpaid amount on the project item number. If you still get an error, check to see if a quantity has been posted on a DWR but not yet paid.

## Slide 7: Stockpile Fields – Pay Item Numbers
Tip: Use the Item History To Date Report from PrC
Contract Progress > Items > General > Row Action Menu next to the Contract Item > Reports > Item History to Date Report

## Slide 8: Stockpile Fields – Pay Item Numbers

## Slide 9
System Generated Adjustments in PrC
INV: Triggers the Initial Payment (STMI)
STMA: Positive pay item posting on a DWR triggers Recovery (negative STMA)
STMA: Negative pay item posting on a DWR triggers reversal of recovery (positive STMA)
STMC: Closes stockpile once contract is 100% complete
Stockpile Transaction Types

## Slide 10
Correcting Stockpile
Initial Stockpile Transaction hasn’t posted to an estimate
Open stockpile record and edit as necessary
Stockpile records and transactions can be corrected in multiple ways, and will depend on…
if a stockpile adjustment has been posted/paid on an estimate and/or
if an item quantity has posted to a DWR
Situations and Examples are provided below and on the next 3 slides.

## Slide 11
Initial Stockpile paid on an estimate and Initial Stockpile Payment was too high or too low
Open Stockpile Record and Add a new transaction for STMI and add negative or positive amount to correct the payment
      Example 1: Original SP = $10,000 and should have been $15,000.00
      Add a new STMI Transaction and Enter $5,000.00
      System will generate a STMI for $5,000.00 on the next estimate
      Example 2: Original SP = $10,000 and should have been $5,000.00
      Add a new STMI Transaction and Enter -$5,000.00
      System will generate a STMI for -$5,000.00 on the next estimate
Correcting Stockpile

## Slide 12
      Example1: $14,000 was placed in a stockpile record under Contract Line Number 0025 and Project Line Number 0185 (Bridge 350001). It should have been placed under Project Line Number 0020 (Bridge 350053)
      Add a new STMI Transaction for Project Line Number 0185 for -$14,000
      Creates a Negative STMI for -$14,000
      Add a new INV Transaction for Project Line Number 0020 for $14,000
      Creates a Positive STMI for $14,000
      New Estimate will have a Negative STMI and Positive STMI = $0.00
      ($0.00 estimate can be run for correction prior to next estimate period)
Incorrect Contract or Project Line Number used for Stockpile and estimate has been approved
Negate the incorrect transaction with a new transaction (bringing balance to $0)
Contract Line Number and Project Number is wrong?
  Create a New Stockpile Record under the correct Contract Line Number
Only the Project Number is wrong?
  Add a positive INV Transaction for the correct Project Number
      Example 2: $14,000 was placed in a stockpile record under Contract Line Number 0020 and Project Line Number 0123 (Bridge 25001).
      It should have been placed under Contract Line Number 0025 and Project Line Number 0020 (Bridge 350053)
      Add a new STMI Transaction for Project Line Number 0123 for -$14,000
      Creates a Negative STMI for -$14,000 and
      Closes out the stockpile record for Contract Line Number 0123
      NEXT:
      Create a new Stockpile Record for Contract Line Number 0025
      Add a new INV Transaction for Project Line Number 0185 for $14,000
      Creates a Positive STMI for $14,000
      New Estimate will have a Negative STMI and Positive STMI = $0.00
      ($0.00 estimate can be run for correction prior to next estimate period)
Correcting Stockpile

## Slide 13
Item quantity posted to a DWR was for the incorrect line item OR quantity posted is too high or too low
Correct the item quantity on a DWR (+ or -)
The system will generate a positive or negative STMA to correspond with the new posted installed percentage for the pay item
      Example: Error in quantity was posted to a DWR.
      50% of the pay item quantity/amount has posted on a DWR, but only 25% is currently installed
      Create DWR for -25% of the quantity/amount for the pay item
      System will generate a STMA for -25% of the stockpiled amount
A negative or positive Posting on a DWR will trigger an automatic positive or negative STMA on the next estimate
Correcting Stockpile

## Slide 14
Closing Stockpile
Automatically closes when Contract completion = 100%
Close Manually when 100% of the stockpile has recovered
If a pay item is not 100% installed at the end of the contract, open stockpile record and create a new transaction using STMI
  Enter the negative amount for the balance of the stockpile
  The System will generate a STMI for a negative adjustment on the next estimate
  Manually close the stockpile
  Construction Stockpile Overview > Click Row Action Button for the corresponding Stockpile row> select Close Stockpile

## Slide 15: Stockpile Resources
CPAM 5.11.5
Spec 9-5.5
Resource Links in PrC and on SCO Website
PrC System Test – Test in PrC
https://www.fdot.gov/construction/trnsport.shtm

## Slide 16
      I was today years old when I learned…
      Stockpile in PrC is (fairly) Easy!!
      Need more help?
      Contact…
      Your District PrC Coordinators
      SCO Systems Section
      SCO Final Estimates Office