## Slide 1: I-95 at Glades Road Diverging Diamond Interchange (DDI)
FDOT District IV and WSP USA Inc.
Vanita Saini, PE - Daniel Smith, PMP -
Yamila Hernandez, PE

## Slide 2: Objectives
Best Practices and Lessons Learned
  Design
  Construction
  Implementation

## Slide 3: About the Project
PROJECT LOCATION:
SR 9/I-95 at Glades Road interchange, Palm Beach County, Florida (City of Boca Raton)
SCOPE:
Interchange reconfiguration and roadway improvements along Glades Road from Butts Road to West University Drive

## Slide 4
Reconfigure Glades Road Interchange to improve traffic operations, reduce congestion, and increase safety
Implement interchange design to address traffic spillback onto I-95
Alleviate existing and future traffic congestion thereby improving safety at the interchange
Project Purpose and Need
Source: 2018 I-95 at Glades Road approved IMR

## Slide 5
I-95 PD&E Study from south of Glades Road to north of Yamato Road. Location Design and Concept Acceptance (LDCA) in 2006
I-95 PD&E Study from south of Glades Road to south of Linton Blvd. Location Design and Concept Acceptance (LDCA) in 2010
I-95 at Glades Road (SR 808) Interchange Modification Report (IMR) Approval in 2018
I-95 at Glades Road (SR 808) Interchange Reevaluation Concurrence in 2021
Project Background

## Slide 6: Glades Interchange Concept
Single-point entrances added to address weaving and to pull Interstate commuters from the arterial onto C-D roads.
Additional lane(s) proposed at I-95 exit ramps.
Grade-separated flyover bridge allowing I-95 commuters to bypass the Glades Road / NW 15th Avenue / Airport Road Intersection. I-95 commuters traveling NB along NW 15th Avenue would be required to cross Glades Road and enter the Interstate via a left-turn entrance at a new signalized intersection located along Airport Road.

## Slide 7: Glades Interchange Concept
Projected 2040 Peak Hour Volumes for Interchange Concept
NB I-95 on-ramp
NW 15th Ave
Airport Rd
SB I-95 off-ramp
NB I-95 off-ramp
SB I-95 on-ramp
(1140) 1590
(2015) 1320
1405 (2575)
1020 (1095)
1260 (560)
(1700) 2850
(670) 605
(910) 1160
965 (1815)
800 (1905)
675
(1390)
(280) 195
(2005) 3125
(325) 690
(235) 180
(400) 365
(110) 270
65 (60)
550 (1505)
140 (50)
55 (145)
185 (135)
95 (105)
(260) 215
(455) 390
70 (165)
350 (410)
520
(1020)
445
(795)

## Slide 8: Glades Interchange Concept
to NB I-95
on-ramp
4
Airport Rd
0.5/A
6.2/A
32.9/C
38.2/D
3
Glades Rd
Airport Rd
58.1/E
23.9/C
49.8/D
23.8/C
68.5/E
67.5/E
50.6/D
43.5/D
NB I-95
off-ramp
2
Glades Rd
29.7/C
25.4/C
59.8/E
56.8/E
17.6/B
12.0/B
SB I-95
off-ramp
1
Glades Rd
10.0/A
31.1/C
22.1/C
41.1/D
19.5/B
13.4/B
Interchange Concept (2040)
(Lane configuration, Delay and LOS)
AM Delay / LOS
PM Delay / LOS
A
B
C
D
E
F
Level Of Service
2
4
58.1/E
31.3/C
37.7/D
30.0/C
18.1/B
30.4/C
1
3
12.1/B
17.4/B
Military Trai
SFRC
SB I-95
off-ramp
NB I-95
Off-ramp
Airport Rd
NW 15th Ave
Glades Rd

## Slide 9: Alternative Technical Concept Design Change
  Description:
  Proposed Alternative Technical Concept (ATC) changed the I-95 (SR 9)/Glades Road interchange from a modified existing partial cloverleaf (ParClo) interchange, as identified in the SR 9 (I-95) Interchange Modification Report (IMR) for Glades Road (SR 808) Interchange for the 2040 recommended build alternative, to a DDI.
  Benefits:
  Reduced impacts to existing infrastructure
    Eliminated ramp flyover bridge over Airport Road
    Eliminated bridge widening for Glades Road EB & WB bridges over I-95 and EB bridge over Military Trail / SFRC
    Reduced bride widening for Glades Road WB bridge over Military Trail / SFRC
    Eliminated 0.38 Acres of R/W acquisition from the Boca Raton Water Treatment Plant Property
    Enhanced safety and fewer crashes due to reduction of conflict points. Proposed DDI 14 Conflict Points vs. FDOT Concept Modified ParClo Design 18 Conflict Points.
    Optimized 2-phase signal operations at intersections within the interchange

## Slide 10: Glades Interchange ATC
Enhanced motorist/pedestrian/bicyclist safety and reduction of overall conflict points.
Elimination of auxiliary lane widening along I-95 Mainline beneath Glades Road due to the elimination of proposed loop ramps from RFP Concept.
Reduction of signal phases at ramp terminal intersections. Crossover intersections allow motorists to enter Interstate via free-flow movements.
Comprehensive pavement marking and signage plan to ensure all users understand proper lane guidance in advance of the required movement(s).

## Slide 11: Glades Interchange ATC
Projected 2040 Peak Hour Volumes for DDI Concept
NW 15th Ave
Airport Rd
605
(670)
1160
(910)
2435 (2410)
475 (905)
1405 (2575)
445 (795)
845 (1110)
2850 (1860)
520 (1020)
1245 (2700)
1020
(1095)
1260
(560)
520
(1020)
845
(1110)
445
(795)
475
(905)
SB I-95 off-ramp
SB I-95 on-ramp
(280) 195
(2165) 3125
(325) 690
(495) 395
(140) 150
(110) 270
65 (60)
1245 (2895)
140 (50)
125 (310)
185 (135)
95 (105)
I-95 NB Off-Ramp
NB I-95 on-ramp
11
(32)

## Slide 12: Glades Interchange ATC
AM Delay / LOS
PM Delay / LOS
A
B
C
D
E
F
Level Of Service
1
2
3
41.4 D
33.3 C
22.3 C
28.2 C
Military Trail
SFRC
SB I-95
off-ramp
NB I-95
Off-ramp
Airport Rd
NW 15th Ave
Glades Rd
21.6/C
9.9/A
DDI Concept (2040)
(Lane configuration, Delay and LOS)
Glades Rd
Glades Rd
Glades Rd
SB I-95
off-ramp
1
NB I-95
off-ramp
2
Airport Rd
3
37.1/D
11.6/B
21.6/C
8.6/A
21.5/C
37.8/D
21.6/C
12.1/B
28.9/C
1.0/A
23.3/C
61.1/E
26.5/C
20.3/C
29.4/C
26.7/C
91.9/F
89.8/F
23.4/C
37.7/D
81.0/F
77.1/E
19.8/B
18.1/B

## Slide 13: Diverging Diamond Interchange Defined
Glades Rd.
A Diverging Diamond Interchange is a form of diamond interchange that allows the two directions of traffic on the crossroad to temporarily divide and cross to the opposite side of the road to provide easier left-turns to and from the freeway.

## Slide 14: Diverging Diamond Interchange Advantages
Conflict Points in a
Conventional Diamond
Conflict Points in a
DDI
Fewer conflict points (14 for DDI, 26 for conventional diamond)
Improved intersection sight distance
Pedestrian crossings are shorter
  “Free flow” or simple left and right turns from freeway
  Increases left turn lane capacity without needing additional lanes
  Only two phases needed for traffic signals, shorter cycle length
Bridge widening is reduced
Construction time is reduced

## Slide 15: Glades Diverging Diamond Interchange
Alternative | AM Peak |  |  | PM Peak |  | 
 | Southbound Interchange | Northbound Interchange | Airport Road | Southbound Interchange | Northbound Interchange | Airport Road
Concept |  |  |  |  |  | 
DDI |  |  |  |  |  | 
LEGEND | Level of Service (LOS) | 
 |  | LOS E; Severe Congestion
 |  | LOS D; Moderate Congestion
 |  | LOS C; Some Congestion
 |  | LOS B or Better; Best Traffic Conditions

## Slide 16: Glades DDI Design
Eyebrow
Eyebrow geometry that minimizes likelihood of wrong-way movements
East Crossover Intersection
West Crossover Intersection
30°
30°
Geometric Design that complies with 2018 AASHTO A Policy on Geometric Design of Highways and Streets
Crossover angle of 30 degrees (angle between tangent segment of EB & WB alignments) that accommodates geometric parameters such as normal crown cross slope

## Slide 17: Glades DDI Design
Supplemental signs and pavement markings providing lane guidance in advanced of decision points.

## Slide 18: Glades DDI Design
Enhanced safety for bicycles and pedestrians with a seven-foot buffered bicycle lane and a new 10-foot shared use path for pedestrians and recreational cyclists through the interchange

## Slide 19: Glades DDI Design

## Slide 20: Glades DDI Stakeholder Outreach
Boca Raton High School
Palm Beach County School Board
FAU Research Park
FAU
Public Meeting/Open House
City of Boca
Palm Beach State college
FAU Stadium
Boca Raton Airport
Boca Raton Utilities
University Commons Shopping Plaza
Boca Raton Homeowner’s Association
Palm Beach Traffic Incident Management
Palm Beach County TPA, TAC
Palm Beach County TPA CAC
PALM BEACH COUNTY TPA Bicycle, Trailways, Pedestrian Advisory Committee
Whole Foods University Commons

## Slide 21: Glades DDI Stakeholder Outreach-Strategies
Mobile Billboards
PSA at FAU Stadium, Field, and Gym Sporting Events
In-person presentations for FAU, St. Andrews School and Boca Raton High School
Attend the Mayor’s Town Forum
Bi-monthly Coffee with the Contractor
Regularly meetings with business owners
Social Media Campaign and Updates
Staffed Boca Traffic Management Center (TMC) [300+ signal timing tweaks over 8 weeks]

## Slide 22: Glades DDI Temporary Traffic Control

## Slide 23: Glades DDI Temporary Traffic Control

## Slide 24: Glades DDI Construction

## Slide 25: Glades DDI Construction

## Slide 26: Glades DDI Construction

## Slide 27: Glades DDI Construction

## Slide 28: Glades DDI Construction

## Slide 29: Glades DDI Temporary Traffic Control-Change

## Slide 30: Glades DDI Temporary Traffic Control-Change
One Weekend Closure Detour VS Four Weekend Closures

## Slide 31: Glades DDI Construction-Weekend Closure

## Slide 32: Glades DDI Construction-Weekend Closure

## Slide 33: Glades DDI Construction-Weekend Closure

## Slide 34: Glades DDI Construction

## Slide 35: Glades DDI Final

## Slide 36: Glades DDI Final (east crossover)

## Slide 37: Glades DDI Final (west crossover)

## Slide 38: Glades DDI Smart Work Zone (SWZ) Overview
What is the District Four SWZ Process?
Technology + People + Relationships + A Plan
Smart Devices
People
Relationships
A Plan
Work Zones
Detour Routes
Area of Influence
Deploy
Monitoring
Plan Implementation
Improved Safety and Mobility
What is a Smart Work Zone?

## Slide 39: Stakeholder Communication Ecosystem
Project Overview
  Roles each stakeholder needs to fulfill
  Considerations to improve DDI operation
Education
  Assist the public with understanding the new layout, allowing them to meet the team and asks questions
Smart Work Zone Elements
  Feedback from the public, monitoring, data collection, and weekly briefings.
Monitoring DDI Implementation
Observed Queuing In NBL on Airport Road: Out of Place Drum
Coordination with Contractor
Results
Contractor Fixed Drum Issue
Contact CEI
SWZ Consultant:
SWZ Consultant:
CEI:
Contractor:

## Slide 40: Glades DDI Operations Lessons Learned
Stop Bar Compliance
Observed sneakers and creepers.
Recommendations of:
  “Stop Here On Red” signs.
Pedestrian crossing signs.
Robust striping.
Team verifying stop bar locations.
Old MOT faded striping – drivers need clean message.
Thermo-plastic vs. paint for temporary MOT

## Slide 41: Glades DDI Operations Lessons Learned
Conflict Points SBL Movement, Weaving
EBT sneakers are creating conflict with SBL movement as they don’t have time to get in the line of sight of SBL turning vehicles.
Since all lanes are not yet available, all departure lanes don’t have a receiving lane causing weaving.

## Slide 42: Glades DDI Operations Lessons Learned
Signalization: Traffic Signal System
Highly Recommend a “single traffic controller”
  Glades Road running two controllers. (1 might be better)
  Run the system in “Overlap” and other technology solutions
Be cautious of standard “phasing and timing” in design
  This is not a standard signal
  Must be field adjusted due to dynamic nature of Freeway demand. (Hint, driver behavior)

## Slide 43: Safety Reminder

## Slide 44: Contact Us
Vanita Saini, P.E.
Project Manager
Florida Department of
Transportation, District Four
3400 West Commercial Boulevard
Fort Lauderdale, FL 33309
Phone: 954-777-4468
Toll Free: 866-336-8435, ext. 4468
Email:
vanita.saini@dot.state.fl.us

## Slide 45: Thank You / Questions