## Slide 1
Value Engineering
Bobby Bull, P.E.
State Value Engineer
2024 South Florida Symposium

## Slide 2: Objectives
Why, When, What, & How to VE?
References
What is VE?
Background

## Slide 3: Background
1947 VE Process Established
1954 Adopted by US Navy
1959 SAVE International
1970 Highway Act
1978 FDOT VE Program
1995 National Highway Systems Act
1997 Federal Regulation (23 CFR 627)
2005 SAFETEA-LU
2012 Updated Federal Regulation
2012 MAP-21
2014 Updated Federal Regulation

## Slide 4
Background
  NHS Federal-Aid projects
  $50 million projects
  $40 million bridge projects
  Federal-Aid Major project on or off the NHS
  Not Design Build
  Any project FHWA determines appropriate
FHWA Requirements – 23CFR 627

## Slide 5
Value Engineering is the systematic application of function-oriented techniques by a multi-disciplined team to analyze and improve the value of a product, process or service.
It is not cost reduction!!!
What is Value Engineering?

## Slide 6
Value Engineering is the systematic application of function-oriented techniques by a multi-disciplined team to analyze and improve the value of a product, process or service.
It is not cost reduction!!!
What is Value Engineering?

## Slide 7
Shrinking Resources
  Do More with Less
  Put more product on the street
Bold, Innovative & Inspirational
Why use VE?

## Slide 8: Why use VE?
Improve Constructability
Resolve Stakeholder Issues
Reduce Overall Project Costs
Improve Project Schedule
Reduce Operating Costs
Mitigate Risks
Introduce Innovation

## Slide 9
When to apply VE
VE Study
Project Life Cycle
Scope/Concept
Development
Design
Construction
Operation &
Maintenance
Opportunity for
Change

## Slide 10
Traffic Information
Aerial Photo
ROW Information
Preferred Alternative
Typical Information Required :
When to apply VE
Planning

## Slide 11
Construction Cost Estimates
ROW Cost Estimates
Business Damage Estimates
Traffic Analysis
Preliminary Plans
Environmental Impact Analysis
Summary of public Involvement
Project Development & Environmental
Typical Information Required :
When to apply VE

## Slide 12
Drainage Information
Typical Sections
Plan & Profile
Intersection & Interchange Layouts
PD&E Commitments
Cross Sections
Structure Info.
Traffic Control Plans
Preliminary Cost Estimate
Design
Typical Information Required :
When to apply VE

## Slide 13
Design/Build Projects
23 CFR 627.9 - Conducted prior to release of RFP document
23 CFR 627.5 – FHWA Encourages
Typical Information Required :
RFP Package
When to apply VE

## Slide 14
VE Job Plan
Project Selection
Team Selection
Pre-Study
Implementation
Post-Study
Report Results
Information Phase
Creative
Function Analysis
Evaluation
Development
VE Team Study
Presentation
How is VE Done?

## Slide 15
All projects over $50/$40 million
Major Bridges
Large Right-of-Way Purchases
Complex Projects
Large Corridor & Multi-modal Projects
Project Manager Requests
Projects Selected for VE (What)

## Slide 16
Consultant
In-house
Design
Team Leader
Maintenance
Construction
Specialized Expertise
Team Selection (Who)

## Slide 17
Consultant
In-house
Design
Team Leader
Maintenance
Construction
Specialized Expertise
Team Selection (Who)

## Slide 18
Pre-Study Activities
Team Notifications
Schedule room/platform
Distribute study material
Review study material
Develop project cost model/pareto chart
Reserve van/vehicles if performing field review
Schedule Design Team for presentation
Supplies (in person)– flipcharts, markers, post-its, masking tape
Virtual – templates.

## Slide 19
VE Job Plan
Implementation
Post-Study
Report Results
Information Phase
Creative
Function Analysis
Evaluation
Development
Project Selection
Team Selection
Pre-Study
VE Team Study
Presentation
How is VE Done?

## Slide 20: 5 QUESTIONS
ASK DURING THE VE STUDY:
What is it?
What does it do?
What does it cost?
What else can do it?
What does that cost?

## Slide 21
Stage 1: Forming - Monday
Stage 2: Storming - Tuesday
Stage 3: Norming - Wednesday
Stage 4: Performing – Thursday/Friday
Stages of Team Development
Form
Storm
Norm
Perform

## Slide 22
Review Project Information
  Discuss Design/Estimate
  Develop Questions for Design Team
    Constraints ?
    Major issues?
    What keeps you up at night?
    Significant Risks?
  Identify any missing information
Team Briefing – Design Team contact info
Information Phase

## Slide 23
Site Visit
  Meet at site and walk the site as a team
  Record any observations
  Take Pictures
Post Site Visit
  Collect group observations
  Review Cost Model
  Areas of Review
Information Phase

## Slide 24
20% of functions contain 80% of cost
Chart: Cost Model
| Right-of Way | Roadway | Project Unknowns | Bridges | MOT | Lighting | Mobilization | Earthwork | Median | Drainage | Shoulder | Landscaping | Signalization | Signing | Stipend
 | 10885900 | 6828047.46 | 6410193.34 | 5841935.85 | 4946136.84 | 3552196.78 | 2374145.68 | 2294952.89 | 2033379.28 | 1765668.8 | 1267312.09 | 545000 | 406089.84 | 196101.2 | 150000
Cost Model Pareto

## Slide 25
Intent or purpose that a product or service is expected to perform.
Expressed in 2 words, active verb and measurable noun.
WHAT DOES IT DO?
What is Function?
WHAT DOES IT DO IT TO?
Function Analysis

## Slide 26
Function Analysis
Calling ‘timeout’ in football results in various actions.

## Slide 27
Function Analysis
Time out
How many reasons (Functions) are behind any timeout call by either player, coach or officials?

## Slide 28
Function Analysis
Conserve Time
Convey Strategy
Avoid Errors
Modify Strategy
Stop Clock
Substitute Players Change Play
ACTION VS. FUNCTION

## Slide 29
ITEM | VERB | NOUN
Guardrail |  | 
Door |  | 
Electric Switch |  | 
Screwdriver |  | 
Column |  | 
Light |  | 
Fence |  | 
Landscaping |  | 
Re-direct
Vehicle
Random Function Generation
Function Analysis
Transfer
Load
Illuminate
Area
Enclose
Area
Improve
Appearance
Transmit
Torque
Interrupt
Current
Control
Access

## Slide 30
What is the function of this pencil?
“make marks”
Eraser:
Barrel:
Band:
Paint:
Secure Eraser
Support Lead, Accommodate Grip, Transmit Force
Remove Marks
Protect Wood, Improve Appearance
Graphite:
Make Marks
Function Analysis

## Slide 31
Function Analysis System Technique (FAST)
HOW
WHY
HIGHEST ORDER FUNCTION
LOWEST ORDER FUNCTION
BASIC FUNCTION
SECONDARY FUNCTION
SECONDARY FUNCTION
SECONDARY FUNCTION
SECONDARY FUNCTION
SECONDARY FUNCTION
ALL THE TIME FUNCTIONS
SCOPE OF PROBLEM UNDER STUDY
PROJECT OBJECTIVES
Function Analysis

## Slide 32
Function Analysis System Technique (FAST)
HOW
WHY
RECORD INFORMATION
APPLY FORCE
TRANSMIT FORCE
SCOPE OF PROBLEM UNDER STUDY
Function Analysis
MAKE MARKS
REMOVE MARKS
IMPROVE APPEARANCE
PROTECT WOOD
SECURE ERASER
SUPPORT LEAD
ACCOMMODATE GRIP
Pencil

## Slide 33
A technique to get bigger and better ideas
Free flow of creative ideas not bound by barriers
Challenges traditional thinking
Brainstorming
WHAT ELSE CAN DO IT?
Creative Phase

## Slide 34
Ideas flow freely
No debating or evaluating ideas
Build on other ideas
Think of new ways
Be humorous and creative
Everyone participates
There are no bad ideas
Creative Phase

## Slide 35
Eliminate ideas
Combine ideas
Evaluate remaining ideas
  Weighted Matrix
  Multi-Voting
  Team Consensus
Evaluation Phase

## Slide 36
What is an Evaluation Matrix?
Matrix used to evaluate ideas against the proposed design using the same criteria.
Evaluation Phase

## Slide 37
Evaluation Phase
Determine Evaluation Criteria
Use paired comparison to weight criteria.
Evaluate each alternative/idea based on criteria

## Slide 38
Typical Criteria:
  Costs
  Operations
  Constructability
  Maintenance
  Environmental
  Aesthetics
Evaluation Phase

## Slide 39
Evaluation Phase
Paired Comparison
Costs
(A)
Operations
(B)
Constructability
(C)
Maintenance
(D)
Aesthetics
(E)
(B)
(C)
(A)
(A)
(B)
(B)
(B)
(C)
(C)
(D)
Costs
(A)
Operations
(B)
Constructability
(C)
Maintenance
(D)
Aesthetics
(E)

## Slide 40
Evaluation Phase
Criteria Weightings
Costs (A)
3 = (2)
Operations (B)
5 = (4)
Constructability (C)
4 = (3)
Maintenance (D)
2 = (1)
Aesthetics (E)
1 = (0)

## Slide 41
RATINGS: EXCELLENT – 4 GOOD - 3 FAIR – 2 POOR - 1 | COSTS |  | OPERATIONS |  | CONSTRUCTABILITY |  | MAINTNANCE |  | AESTHETICS |  | TOTALS
ALTERNATIVES/ WEIGHTING | 3 |  | 5 |  | 4 |  | 2 |  | 1 |  | 
AS PROPOSED | 4 | 12 | 3 | 15 | 2 | 8 | 1 | 2 | 5 | 5 | 42
VE ALTERNATIVE 1 | 3 | 9 | 5 | 25 | 2 | 8 | 3 | 6 | 2 | 2 | 50
Evaluation Phase
Weighted Matrix

## Slide 42
What is it?
  A decision-making tool that enables a team to reduce a long list of ideas to a manageable number of ideas.
Evaluation Phase
Multi-Voting

## Slide 43
What is it?
  As a group decide:
    Which ideas to move forward for development
    Which ideas to combine
    Which ideas to eliminate
Evaluation Phase
Team Consensus

## Slide 44
Descriptions
Sketches
Calculations
Advantages & Disadvantages
Cost Analysis (Life Cycle Costs)
Development Phase
Write-up Ideas

## Slide 45
Descriptions
Sketches
Calculations
Advantages & Disadvantages
Cost Analysis (Life Cycle Costs)
Development Phase
Clear Descriptions of both the proposed design and the VE alternative
Write-up Ideas

## Slide 46
Descriptions
Sketches
Calculations
Advantages & Disadvantages
Cost Analysis (Life Cycle Costs)
Development Phase
Sketches to help visualize the VE alternative that is being presented
Write-up Ideas

## Slide 47
Descriptions
Sketches
Calculations
Advantages & Disadvantages
Cost Analysis (Life Cycle Costs)
Development Phase
Calculations that help support the VE Alternative
Write-up Ideas

## Slide 48
Descriptions
Sketches
Calculations
Advantages & Disadvantages
Cost Analysis (Life Cycle Costs)
Development Phase
Advantages and Disadvantages of the VE Alternative
Write-up Ideas

## Slide 49
Descriptions
Sketches
Calculations
Advantages & Disadvantages
Cost Analysis (Life Cycle Costs)
Write-up Ideas
Development Phase
Life Cycle Cost Analysis

## Slide 50
Development Phase
What is Life Cycle Cost Analysis?
A tool to determine the most cost-effective option among different competing alternatives to purchase, own, operate, maintain and finally dispose of an object when each is equally appropriate to be implemented. All the costs are typically discounted to Net Present Value (NPV).

## Slide 51
Present results to management
Either last day of study or scheduled separately by District VE coordinator.
Multiple presenters
Dress rehearsal
Presentation Phase

## Slide 52
Report Results
Team Leader responsible for developing and distributing report.
Collect write-ups from team members.
Include presentation, agenda & sign-in sheets in appendices.
Distribute draft report to team for comments.
PE sign & seal final report.

## Slide 53
Report Results
Results are reported quarterly at the Performance Meeting
Results are reported on an Annual Basis to FHWA

## Slide 54
Cost Risk Analysis & Value Engineering
CRA Process & VE Process are complimentary
  Use the VE process to develop risk response strategies
  Use the CRA process on the VE recommendations to evaluate the risks and their impact on the cost & schedule

## Slide 55
FDOT Value Engineering web site
FDOT Value Engineering Procedure 625-030-002
FHWA Value Engineering web site
SAVE International web site
References

## Slide 56
Questions

## Slide 57
Thank you
Bobby Bull, P.E.
State Value Engineer
Bobby.Bull@dot.state.fl.us
(850) 414-4348