| 971130 | PD&E Pass the Torch Meeting / Begin CAP |
| --- | --- |
| 359040 | Contact Local Agency |
| 900030 | Local Agency Scope Coordination (for Resurfacing and Miscellaneous Projects) |
| 164010 | Stage I Scope Development |
| 230130 | Stage II Scope Evaluation |
| 231010 | Submit Advertisement Package to PSU |
| 230140 | Stage III (Final) Scope Development |
| 900020 | Finalize Scope/Preliminary Units Meeting |
| 164030 | Negotiate Staff Hours |
| 233020 | Encumber Phase 32 Funds For Design |
| 233010 | PE Contract Executed/PE Begin |
| 263020 | LDCA Approved |
| 900010 | Build Schedule |
| 233030 | Encumber Phase 32 Funds For S/A (Plans Update) |
| 250010 | Project Kickoff Meeting |
| 298000 | Right of Way Kickoff Meeting |
| 367010 | Exceptions/Variations (Including Utilities) |
| 106010 | Design Survey |
| 325020 | TIITF Determination |
| 106210 | Survey Alignment |
| 170010 | R/W Survey |
| 170050 | PNC Coordinates |
| 298010 | R/W Estimate - Scope |
| 900070 | Stakeholders Meeting |
| 925010 | Pond Notification Letter - Initial |
| 271010 | Draft Pond Site Report |
| 256010 | Order Design Traffic |
| 304010 | Coring |
| 170250 | PNC Database |
| 109110 | Drainage Kickoff Meeting |
| 106310 | Survey Alignment Review |
| 257010 | Design Traffic Received |
| 925020 | Pond Notification Letter - Second |
| 271110 | Review Draft Pond Site Report |
| 272020 | Permit Coordination Meeting |
| 272030 | Update Permits |
| 170150 | 30% Control Map |
| 313010 | Pavement Data Received |
| 271020 | Final Pond Site Report |
| 925030 | Pond Notification Letter - Final |
| 315020 | 30% Control Map Review |
| 271120 | Review Final Pond Site Report |
| 367020 | Approved Exceptions/Variations (Including Utilities) |
| 106110 | Mainline Design Survey Database Submittal |
| 315120 | 60% Control Map |
| 113010 | Line & Grade (Phase I) |
| 265010 | Initial Utility Design Conference (aka Pre-Design Conference, Utility Design Conference, 30% Utility Meeting) |
| 114010 | Bridge Hydraulics Report (BHR) |
| 221010 | Review Access Management Report |
| 133020 | Geotech Foundations Report for BDR |
| 133010 | Pre BDR Meeting |
| 271030 | Signed Sealed Pond Site Report |
| 197010 | Pavement Design |
| 115010 | BDR |
| 260010 | Typical Section Approved |
| 900060 | Interactive Project Update Meeting (for Minor Projects) |
| 301010 | Line & Grade Meeting (Phase I) |
| 339010 | VE Study |
| 109010 | Drainage Design |
| 113020 | Initial Roadway Plans (Phase II) |
| 131010 | Phase II Soils Report (Initial) |
| 298030 | R/W Estimate - Line & Grade Completion |
| 372010 | Submit Pavement Type Report 30% (Phase I) |
| 315030 | 60% Control Map Review |
| 197020 | Constructability & MOT Review Meeting |
| 315140 | 90% Control Map |
| 146010 | Title Search Work |
| 315040 | 90% Control Map Review |
| 138010 | 30% R/W Map (includes TOPO) |
| 311010 | Structural Review BDR |
| 900040 | Initial Design Team Meeting (Phase II) |
| 183020 | Load Rating Report |
| 115030 | 30% Structure Plans |
| 133030 | 30% Geotech Foundations Report |
| 302010 | Initial Plans Review (Phase II) |
| 106020 | Updated Design Survey Database Submittal |
| 140010 | 30% R/W Map Review |
| 302030 | Respond to Comments - Phase II Plans |
| 302040 | Incorporate Phase II Review Comments |
| 900090 | Pre-Parcel Review Meeting |
| 264010 | Utility Contact (for minor project) |
| 373010 | Submit Pavement Type Report 60% (Phase II) |
| 138030 | R/W Impact Revisions |
| 131020 | Phase III Soils Report |
| 145010 | Permits Package |
| 359010 | Confirm Local Support for Initial Plans |
| 329010 | Request Environmental Review |
| 307010 | Review 30% Structure Plans |
| 322020 | Final R/W Require & LOC to S&M |
| 113030 | Final Roadway Plans (Phase III) |
| 139010 | 60% R/W Map |
| 238010 | Phase I Evaluation of Consultant |
| 238020 | Phase II Evaluation of Consultant |
| 238030 | Phase III Evaluation of Consultant |
| 238040 | Plans Update Evaluation of Consultant |
| 900050 | 60% Mapping Team Meeting (Parcel by Parcel) |
| 133040 | 60% Geotech Foundations Report |
| 115040 | 60% Structure Plans |
| 272010 | Permit Process |
| 298060 | R/W Estimate - Initial Plans Completion |
| 308010 | Review 60% Structure Plans |
| 140020 | 60% R/W Map Review |
| 133050 | 90% Geotech Foundations Report |
| 115050 | 90% Structure Plans |
| 315050 | R/W Control Map Complete |
| 325010 | Prepare TIITF Package |
| 139020 | 90% R/W Map |
| 146110 | Title Search Update |
| 140030 | 90% R/W Map Review |
| 971010 | Assemble R/W Team |
| 264040 | District Utility Review (RGB)(for major projects, no UWS) |
| 303010 | Final Plans Review (Phase III) |
| 184010 | Submit Load Rating Report |
| 308020 | Review 90% Structure Plans |
| 139030 | 100% R/W Map |
| 303030 | Respond to Comments - Final Plans (Phase III) |
| 140040 | 100% R/W Map Review |
| 115060 | 100% Structure Plans |
| 113040 | 100% Roadway Plans |
| 359020 | Confirm Local Support For Final Plans/Update CAP |
| 157010 | R/W Map Complete |
| 144010 | Instrument Prep |
| 133060 | Signed Sealed Geotech Foundations Report |
| 310050 | 100% Plans Coordination |
| 131030 | Signed Sealed Soils Report |
| 201010 | Plans Completed |
| 201020 | Certified Design Survey Deliverables |
| 298090 | R/W Estimate - Final Plans Completion |
| 268010 | Documents to R/W |
| 208010 | Appraisal Contract |
| 222010 | All Permits Clear |
| 120010 | Appraisals |
| 143010 | Appraisal Review |
| 121010 | Negotiation |
| 359050 | Initial Annual Local Agency Update |
| 240010 | Complete Suit Data |
| 273010 | Final R/W Order of Taking |
| 125010 | R/W Demo & Clear Work |
| 359051 | 2nd Annual Local Agency Update |
| 255010 | R/W Certified |
| 933010 | Complete Package to DCPME |
| 310020 | Pre-Spec Meeting (Useful Information) |
| 204010 | Production Date (PID) |
| 226010 | PS&E Submittal(s) |
| 242010 | PS&E Review(s) |
| 359025 | Local Agency Contact Prior to Plans Update |
| 220010 | Plans Update Design Team Meeting |
| 164020 | S/A for Plans Update |
| 220020 | Plans Update |
| 220030 | Review Updated Plans |
| 139060 | Update Survey |
| 139070 | Update R/W Map |
| 125030 | Update R/W Demo & Clear |
| 272040 | Update Permit Status |
| 264020 | District / Resident Utility Review (for minor / major projects. Includes UWS) |
| 264030 | Utility Contact (for major projects - RGB) |
| 264050 | Utility Contact (for major projects - UWS) |
| 173010 | Railroad Contact |
| 359030 | Confirm Local Support for Updated Plans |
| 222020 | Updated Permits Clear |
| 310010 | 100% Plans Update Coordination |
| 266010 | Utilities Certified |
| 201050 | Plans Complete |
| 279010 | Railroad Clear Memo |
| 359052 | 3rd Annual Local Agency Update |
| 212010 | Transmit PS&E Package (Central Office) |
| 370010 | Transmit PS&E Package (District) |
| 359060 | Local Agency Letting Update |
| 280010 | Letting Date |
| 236010 | Final Evaluation of Consultant |
| 171010 | Set Contract Time |