## EMO PSM Codes - Nov 2016
Environmental Management PSM Codes
NOTES:
Primavera Activities - for each tracked PSM code below, primavera MUST use EITHER the PSM code followed by all zeros (705000000) or the PSM code followed by 10,000 (705010000)
Reports displaying Projected Finish vs. Actual Finish are always looking at the completion date for the PSM activity or milestone (even if it represents a start date [SEIR START]) - in Primavera, these are Early Finish and Actual Finish for the corresponding primavera activity
Required by COA?
PSM Code | Abbreviated Description | Activity to Track | Description | CE 2 | EA | EIS | SEIR
PLANNING/PRE-PD&E ACTIVITY CODES
746 | SWAT PLANNING MEETING | SWAT PLANNING MEETING | Date of SWAT Planning Meeting | Yes | Yes | Yes | Yes
747 | SWAT KICKOFF MEETING | SWAT KICKOFF MEETING | Date of SWAT Kick-Off Meeting | Yes | Yes | Yes | Yes
700 | ETDM/ETAT PROG. SCREEN START | ETDM/ETAT PROGRAMMING SCREEN START | Enter Date when the Programming Screen is submitted to ETAT for review. | Yes | Yes | Yes | Yes
701 | ETDM PROG PRELIM SUM REP PUB | ETDM PROGRAMMING PRELIMINARY SUMMARY REPORT PUBLISHED | Enter Date when the Preliminary Programming Summary Report is published and FDOT has addressed all the comments received. Class of Action has not been assigned. | Yes | Yes | Yes | Yes
702 | ETDM PROG FINAL SUM REP PUB | ETDM PROGRAMMING FINAL SUMMARY REPORT PUBLISHED | Enter Date when the Final Programming Summary Report is published, The Programming Screen Summary is considered Final when Class of Action is assigned and accepted. | Yes | Yes | Yes | Yes
703 | PD&E SCOPE AND SCHEDULE COMPL | PD&E SCOPE AND SCHEDULE COMPLETION | Date PD&E Scope and Schedule is completed | Yes | Yes | Yes | Yes
704 | ASSIGN PD&E PROJECT MANAGER | ASSIGN PD&E PROJECT MANAGER | Date PD&E Manager is assigned | Yes | Yes | Yes | Yes
705 | PD&E ADVERTISEMENT | PD&E ADVERTISEMENT | Date PD&E Project is advertised | Yes | Yes | Yes | Yes
PD&E PSM CODES
224 | ADVANCE NOTIFICATION | ADVANCE NOTIFICATION | Date AN sent (can be same as Programming Screen Start if AN sent as part of Programming Screen) | Yes | Yes | Yes | Yes
706 | TYPE 2 CE START | TYPE 2 CE START | Start Date for Type 2 CE | Yes
707 | EA START | EA START | Start Date for EA |  | Yes
708 | NOI - EIS START | NOI - EIS START | Date of Notice of Intent Publication in Federal Register. Start of EIS. |  |  | Yes
709 | SEIR START | SEIR START | Start Date for SEIR |  |  |  | Yes
710 | PLANNING CONSISTENCY COMPL | PLANNING CONSISTENCY COMPLETION | Date when Planning Consistency is Complete | Yes | Yes | Yes
712 | ALTERNATIVES DEVELOPMENT COMPL | ALTERNATIVES DEVELOPMENT COMPLETE | Date Alternatives Concept identified for LDCA | Yes | Yes | Yes | Yes
713 | DISTRICT QC OF DRAFT ENV DOC | DISTRICT QC OF DRAFT ENVIRONMENTAL DOCUMENT | Date District completed QC of Draft Environmental Documents (Environmental Documents are Type 2 CE, EA, EIS and SEIR) | Yes | Yes | Yes | Yes
714 | DEIS TO OEM | DEIS TO OEM | Date Draft EIS is submitted to OEM |  |  | Yes
715 | DEIS OEM APPROVAL | DEIS OEM APPROVAL | Date OEM approves DEIS |  |  | Yes
716 | DEIS TO FHWA | DEIS TO FHWA | Date DEIS is submitted to FHWA |  |  | Yes
717 | DEIS FHWA APPROVAL | DEIS FHWA APPROVAL | Date FHWA Approves DEIS |  |  | Yes
718 | EA TO OEM | EA TO OEM | Date EA is submitted to OEM |  | Yes
719 | EA APPROVED OEM | EA APPROVED OEM | Date OEM approves EA |  | Yes
720 | EA TO FHWA | EA TO FHWA | Date EA is submitted to FHWA |  | Yes
721 | EA APPROVED FHWA | EA APPROVED FHWA | Date FHWA Approves FHWA |  | Yes
722 | TYPE 2 TO FHWA | TYPE 2 TO FHWA | Date Type 2 CE is approved to FHWA | Yes
723 | OEM - NOI REVIEW | REVIEW of NOI BY OEM | Date of Notice of Intent Publication in Federal Register. Review of NOI |  |  | Yes
724 | FEIS TO OEM | FEIS TO OEM | Date FEIS is submitted to OEM |  |  | Yes
725 | FEIS OEM APPROVED | FEIS OEM APPROVED | Date OEM Approves FEIS |  |  | Yes
726 | FEIS TO FHWA | FEIS TO FHWA | Date FEIS is submitted to FHWA |  |  | Yes
727 | FEIS FHWA APPROVED | FEIS FHWA APPROVED | Date FHWA approves FEIS |  |  | Yes
728 | FEIS/ROD TO OEM APPROVED | FEIS/ROD TO OEM APPROVED | Date OEM approves FEIS/ROD |  |  | Yes
729 | FEIS/ROD TO FHWA APPROVED | FEIS/ROD TO FHWA APPROVED | Date FHWA approves FEIS/ROD |  |  | Yes
730 | ROD TO OEM APPROVED | ROD TO OEM APPROVED | Date OEM approves ROD |  |  | Yes
731 | ROD TO FHWA APPROVED | ROD TO FHWA APPROVED | Date FHWA approves ROD |  |  | Yes
732 | FONSI TO OEM APPROVED | FONSI TO OEM APPROVED | Date FONSI is approved by OEM |  | Yes
733 | FONSI TO FHWA APPROVED | FONSI TO FHWA APPROVED | Date FONSI is approved by FHWA |  | Yes
734 | SEIR APPROVED | SEIR APPROVED | Date SEIR is approved |  |  |  | Yes
735 | CO-LEGAL SUFFICIENCY REVIEW | CO-LEGAL SUFFICIENCY REVIEW | Date Legal Sufficiency Review by FDOT CO Legal Staff is complete |  | Yes | Yes
263 | LDCA | LDCA | Date of Location Design Concept Approval | Yes | Yes | Yes | Yes
736 | LDCA PUBLIC NOTICE | LDCA PUBLIC NOTICE | Date of LDCA Public Notice | Yes | Yes | Yes | Yes
738 | FEDERAL REGISTER NOTICE | FEDERAL REGISTER NOTICE | Date Notice is printed in Federal Register |  | Yes | Yes
749 | TYPE 1 CE APPROVAL | TYPE 1 CE APPROVAL | Date of Type 1 CE Approval
RE-EVALUATION PSM CODES
737 | ENV DOC REEVALUATIONS - PE | PREPARE ENVIRONMENTAL DOCUMENT REEVALUATIONS | Date Re-evaluation is completed for Preliminary Engineering | Yes | Yes | Yes | Yes
739 | ENV DOC REEVALUATIONS - R/W | PREPARE ENVIRONMENTAL DOCUMENT REEVALUATIONS | Date Re-evaluation is completed for Right-of-Way | Yes | Yes | Yes | Yes
741 | ENV DOC REEVAL - DESIGN CHANGE | ENV DOC REEVAL - DESIGN CHANGE | Date Re-evaluation is completed for Design | Yes | Yes | Yes | Yes
748 | ENV DOC REEVAL- CONST ADVERTSMT | ENV DOC REEVAL- CONSTRUCTION ADVERTISEMENT | Date Re-evaluation is completed for Construction Advertisement | Yes | Yes | Yes | Yes
PSM CODES WHEN COA IS UNKNOWN OR IF CHANGE IN COA
135 | E.M.O. STUDY | E.M.O. STUDY | General EMO Work. | Yes | Yes | Yes | Yes
740 | NEPA COA UNKNOWN | NEPA COA UNKNOWN | Use when COA is unknown. | Yes | Yes | Yes
742 | EA COA CHANGE | EA COA CHANGE | Use to document shift to EIS. Enter date when it is decided that COA is an EIS. |  | Yes
743 | ON HOLD | ON HOLD | Use if the project is stopped. Use date the project was stopped. | Yes | Yes | Yes | Yes
744 | FEDERAL / STATE CHANGE | FEDERAL / STATE CHANGE | Enter Date when project is changed from Federal to State Process | Yes | Yes | Yes | Yes
745 | OFF HOLD | OFF HOLD | Date project is taken off hold | Yes | Yes | Yes | Yes
USE WHEN PART OF YOUR PROJECT
333 | CULTURAL RESOURCES ASSESSMENT SURVEY | CULTURAL RESOURCES ASSESSMENT SURVEY | Date Cultural Resources Assessment Survey is completed | Yes | Yes | Yes | Yes
335 | PD&E FINAL NOISE STUDY | PD&E FINAL NOISE STUDY | Date Final Noise Study Report is completed | Yes | Yes | Yes | Yes
750 | WETLAND REPORT | WETLAND REPORT | Date Wetland Evaluation Report is complete | Yes | Yes | Yes | Yes
751 | SECTION 4(F) | SECTION 4(F) | Date Section 4(f) is complete | Yes | Yes | Yes
752 | INFORMAL USFWS CONSLT COMP | INFORMAL USFWS CONSULTATION COMPLETE | Date Informal USFWS Consultation is complete. Usually date of letter from USFWS. | Yes | Yes | Yes | Yes
753 | FORMAL USFWS CONSULT COMP | FORMAL USFWS CONSULTATION COMPLETE | Date Formal USFWS Consultation is complete. Allow 135 days to complete. | Yes | Yes | Yes | Yes
756 | 267 F.S. EFFECTS COMPLET | DHR CONSULTATION, 267 F.S. | Date of DHR Letter concurring with FDOT findings |  |  |  | Yes
757 | TRAFFIC ANALYSIS/REPORT | TRAFFIC ANALYSIS/REPORT | Date Traffic Analysis/Report is completed | Yes | Yes | Yes | Yes
758 | CORRIDOR ANALYSIS | CORRIDOR ANALYSIS | Date of Corridor Analysis Report is completed | Yes | Yes | Yes | Yes
759 | TYPICAL SECTION SELECTION | TYPICAL SECTION SELECTION | Date Typical Section Package is signed | Yes | Yes | Yes | Yes
760 | PRELIMINARY ENGINEERING REPORT | PRELIMINARY ENGINEERING REPORT | Date Preliminary Engineering Report is complete, signed and sealed. | Yes | Yes | Yes | Yes
761 | NATURAL RESOURCE EVALUATION | NATURAL RESOURCE EVALUATION | Date Natural Resource Evaluation Report is finalized | Yes | Yes | Yes | Yes
762 | SECTION 106 EFFECTS COMPLETE | SHPO CONSULTATION, SECTION 106 CONSULTATION | Date of SHPO Letter concurring with FDOT findings | Yes | Yes | Yes
763 | NMFS INFORMAL CONSULT COMP | NMFS INFORMAL CONSULTATION COMPLETE | Date of NMFS Letter concurring with FDOT Determination for Informal Consultation | Yes | Yes | Yes | Yes
764 | NMFS FORMAL CONSULT COMP | NMFS FORMAL CONSULTATION COMPLETE | Date Formal NMFS Consultation is complete. Allow 135 days to complete. | Yes | Yes | Yes | Yes
765 | INTERCHANGE ACCESS REPORT | INTERCHANGE ACCESS REPORT | Date of Interchange Access Report Approval | Yes | Yes | Yes | Yes
PUBLIC INVOLVEMENT PSM CODES
365 | PREPARE FOR PUBLIC MEETING | PREPARE FOR PUBLIC MEETING | Date you start Preparing for Public Information Meeting. This could include date of site review, newsletter, etc. | Yes | Yes | Yes | Yes
292 | PUBLIC INFO MEETING | PUBLIC INFORMATION MEETING | Date of Public Information Meeting | Yes | Yes | Yes | Yes
711 | ALTERNATIVES WORKSHOP | ALTERNATIVES WORKSHOP | Date of Alternatives Workshop | Yes | Yes | Yes | Yes
366 | PREPARE FOR PUBLIC HEARING | PREPARE FOR PUBLIC HEARING | Date you start Preparing for Public Hearing. This could include date of site review, newsletter, etc. | Yes | Yes | Yes | Yes
262 | PUBLIC HEARING | PUBLIC HEARING | Date Public Hearing is Held | Yes | Yes | Yes | Yes
ACRONYMS |  | COA = Class of Action
CE 2 = Type 2 Categorical Exclusion
EA = Environmental Assessment
EIS = Environmental Impact Statement
ETDM = Efficient Transportation Decision Making
FHWA = Federal Highway Administration
FONSI = Finding of No Significant Impact
NOI = Notice of Intent
PD&E = Project Development and Environment
ROD = Record of Decision
SEIR = State Environmental Impact Report
OEM = Office of Environmental Management
DHR= Division of Historic Resources