## Design Confidence
DESIGN CONFIDENCE REPORT
Project Name: ________________________________________________________________
Project Phase: _____________________ |  |  | Date: _______________________________
Instructions: The purpose of this report is to convey the engineer of record's level of confidence that all project quantities have been captured in the project documents (reports, plans, etc.) and included in the Engineer's Project Cost. The Engineer of Record (EOR) must avoid optimism bias when reporting their level of confidence. The information presented herein will be used by FDOT and the Independent Project Cost (IPC) Team to inform their assessment of design development risk. The EOR should insert rows as necessary to report on additional project components or to segment project components with varying degrees of design confidence. A comprehensive, but not exhaustive, list of considerations for thoroughly capturing the project scope are provided to the right of the table to help the EOR assess how well defined the project scope is and how comprehensive the Engineer's Project Cost is at the time of reporting. The Project Cost Checklist should also be referred to for additional prompts.
Project Component | What is your level of confidence that the design quantities have captured ALL of the project cost? | Are the project quantities reported on the Engineer's Project Cost supported with information contained in the plans and/or reports. | How much conservatism is incorporated into the design that is, therefore, reported in the quantities? | Additional Information and Clarifications | Project scoping considerations
Project limits |  |  |  |  | Project limits: Project transitions, local roads improvements, temporary widenings, ponds, ADA/intersection upgrades, etc. considered to define project scope and limits of work
Construction sequencing |  |  |  |  | Construction sequencing: Early works identified, temporary traffic control requirements documented or plan prepared
Temporary improvements |  |  |  |  | Temporary improvements: Temporary widening, transitions, cross-overs, temporary drainage, temporary walls, temporary signals/ITS, and temporary bridges identified
Earthwork volumes |  |  |  |  | Earthwork: Based on models or approximation, ponds sized and located, clearing & grubbing limits set, unsuitable materials accounted for, soil stabilization needed
Walls |  |  |  |  | Walls: Noise wall locations identified, Retaining wall location & type identified, Details provided.
Paving sections |  |  |  |  | Pavements: Pavement design prepared, reconstruct vs. widen/overlay, geometric layout finalized, superelevation or cross-slope corrections anticipated, black base required
Drainage systems |  |  |  |  | Drainage & stormwater: Collection system designed vs. approximated, culverts designed vs. approximated, culvert structural integrity assessed for replacement
Permanent barriers |  |  |  |  | Permanent barriers: Location & type identified along roads, stormwater basins, clear zone encroachments, etc.
Foundations |  |  |  |  | Foundations: Foundation type, size, depth, and count/locations, based on project-specific geotechnical information or historical information
Substructures |  |  |  |  | Substructures: Column & cap dimensions & reinforcement, straddle bents required and details provided
Superstructures |  |  |  |  | Superstructure: Girder type & size, deck thickness and reinforcement, barrier type, special means & methods required, approach slabs required
Traffic Signals & ITS |  |  |  |  | Traffic Signals & ITS: New, removed, upgraded; including pedestrian, school zone, signalized crossings, non-standard equipment identified, interconnect type
Overhead signage |  |  |  |  | Overhead signage: Location, standard drawings, square footage estimated
Lighting |  |  |  |  | Lighting: High-mast lighting identified; Corridor, bridge, intersection, and/or aesthetic lighting identified; New, replace, or upgrade requirements specified
Tollway Coordination |  |  |  |  | Tollway coordination: Toll plaza buildings or toll gantries, Park & Ride facilities, Bus stops
Erosion control |  |  |  |  | Erosion & sediment control: Discharge points identified, embankment/fill areas identified, sensitive waters identified, BMPs identified on plans or approximated in quantities
Landscaping |  |  |  |  | Landscaping: Minimum investment established; Limits/locations of landscaping identified, outdoor furnishings identified.
Aesthetics |  |  |  |  | Aesthetics: Bridge aesthetics included, Retaining Wall aesthetics, Other aesthetic commitments?
Environmental |  |  |  |  | Environmental: Wetland impacts (both temporary and permanent), Hazardous/contaminated materials identified, wildlife requirements/restrictions, etc.
Utilities |  |  |  |  | Utilities: Relocations, connections, adjustments identified; Responsible party identified to make clear whether contractor is responsible for coordination or performance of the work
Other 3rd Party coordination |  |  |  |  | Third-Party requirements: Have all project commitments been incorporated into the project scope or definition? Has Railroad coordination occurred and requirements incorporated? Has local coordination occurred and requirements incorporated?
Entries
| 15% or less | Yes | 0-5%
| 15-30% | No | 5-10%
| 30-50% |  | 10-20%
| 50-75% |  | 20-30%
| 75-90% |  | 30-40%
| 100% |  | 40-50%
50+%