## Risk Register
IPC RISK REGISTER | [5 empty] | PROJECT UNKNOWNS: |  |  | 0
[6 empty] | CONTACTOR-OWNED RISK |  |  | 0
PROJECT NAME:
[6 empty] | TIME IMPACTS: |  | 0 | Days |  | DATE:
RISK # | RISK CATEGORY | RISK EVENT | DETAILED DESCRIPTION | RISK TRIGGER | Project Unknown or Contractor-owned Risk | STATUS (Active or Retired) | PROBABILITY (0-100%) | COST IMPACT | WEIGHTED COST (Probability x Weighted Cost) | TIME IMPACT | WEIGHTED TIME (Time Impact x Probability) | PRIORITY (1=High 3=Low) | ASSUMPTIONS / BASIS FOR COST IMPACTS | MITIGATION STRATEGY
RISKS ADDRESSED IN SPECIFICATIONS
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
OTHER RISKS (SEE RISK EVENT LIST)
0
0
0
0
0
0
0

## Risk Event List
Risk Events to be considered for the Risk Register
RISK CATEGORY | RISK EVENT
Community Outreach | Late scope changes are requested
Community Outreach | Lack of community support
Community Outreach | New concerns emerge
Community Outreach | Uncertain political and public support
Community Outreach | Unresolved community outreach issues
Community Outreach | Concerns about viewshed revises design
Community Outreach | Could request a different more costly design
Construction | Third-party delays during construction
Construction | Problem with construction sequencing/staging/phasing
Construction | Supply chain material procurement issues/Materials availability
Construction | Material and subcontractor price escalation for extended contract time due to delays
Construction | Longer than anticipated haul routes
Construction | Project location is difficult to access
Construction | Extensive temporary drainage is required
Construction | Vibration monitoring required
Construction | Specifications all quantity overages without additional approvals
Construction | Throw away work due to adjacent corridor projects
Construction | Additional temporary asphalt anticipated
Construction | Road user claims - vehicular damage - guardrail damage etc.
Construction | Off system road detour causes accelerated degradation of the roadway surface
Construction | Non critical temporary walls anticipated
Construction | MOT pay items not included in base estimate
Construction | (Multiple) stipends required due to DB or PDB
Construction | Constructability issues due to constrained areas etc.
Construction | Time work restrictions for pile driving
Construction | Temporary wire walls are needed
Construction | Marine construction equipment/methods are required
Construction | Temporary bridge is required during construction
Construction | Early works items create throw away work
Construction | Complex MOT to maintain local access
Construction | Anticipated ATC Alternative Technical Concept submittals by contractor
Construction | Temporary barrier is required
Construction | Unanticipated weather delays
Construction | Insufficient or limited construction or staging areas
Construction | Work done using barge/crane
Construction | Material shortages anticipated
Construction | Work height clearances due to nearby airport
Construction | Contractor is required to maintain roadway corridor for an extended period
Construction | Unidentified geotechnical conditions may delay the schedule and require additional supervision and work
Construction | Existing field conditions differ from contract documents, potentially causing delays or additional costs
Construction | Site requires maintenance that is more than standard projects
Contracting & Procurement | Key staff change/substitution
Contracting & Procurement | No or low staff redundancy
Contracting & Procurement | Scope creep/changes
Contracting & Procurement | Scope with low detail on complex project
Contracting & Procurement | Low number of bidders
Contracting & Procurement | Delivery and procurement approach
Contracting & Procurement | Ambiguous contract provisions
Contracting & Procurement | Contract document conflicts
Contracting & Procurement | Staff has conflicting priorities/overworked
Contracting & Procurement | Workforce turnover issues
Contracting & Procurement | Unknown/unidentified project scope. (i.e. Bridge joints/bearings/drainage/signing/striping/lighting/ITS/specialty coatings/railings)
Contracting & Procurement | Increased lettings lead to reduced competition
Contracting & Procurement | Workforce development issues
Contracting & Procurement | Potential lawsuit contributes to project changes
Contracting & Procurement | Unrealistic schedule
Contracting & Procurement | Potential for award to be protested
Design | New alignment is required
Design | Limited/outdated survey data
Design | Change in earthwork design
Design | Project commitments
Design | Reconstruction of concrete pavement due to substandard thickness for widening project
Design | Additional lighting is required
Design | Design is not to FDOT standards
Design | Value Engineering Opportunities
Design | Inaccurate assumptions during the planning phase
Design | Design concept only (Alternative Contracting Methods) may require accelerated construction costs to maintain schedule
Design | Changes in design criteria/requirements
Design | Additional signage requiring structural design is required
Design | Pavement overbuild required (For alternative contracting, additional temporary asphalt overbuild is required if the existing roadway survey is not accurate.)
Design | Maintain ITS facilities during construction
Design | Exceptions/Variations not approved
Design | ITS technology advancements included in project
Design | Existing number of lanes must be maintained throughout construction
Design | Riparian/littoral rights
Design | Pavement type selection is undecided and higher cost is used
Drainage | Change in conveyance size requirements
Drainage | Additional impervious area is needed over what was permitted
Drainage | Pipe size/diameter changes
Drainage | Pipe length changes
Drainage | Pond design updated additional earthwork required
Drainage | Fence is required
Drainage | Ponds drain to an impaired water body
Drainage | New joint use pond location
Drainage | Additional turf/sod required
Environmental | Delay in permitting approval (WMD, USACE, FDEP, etc.) For alternative bidding, additional costs include but are not limited to mobilization, extended overhead, etc.
Environmental | Difficulty in obtaining environmental data and/or delineation approvals
Environmental | Hazardous waste or contamination within project limits
Environmental | Regulatory agency updated or created new rules
Environmental | Environmental document requires updates
Environmental | New environmental document is required
Environmental | Archeological sensitive area
Environmental | Historical structures in project corridor or construction limits
Environmental | Noise walls anticipated
Environmental | 4(f) impacts
Environmental | Project within the Coastal Construction Control Line
Environmental | Project near an OFW Outstanding Florida Water
Environmental | Project impacts a floodplain area
Environmental | Insufficient wetland mitigation credits
Environmental | Nearby airport
Environmental | Additional wetland impacts anticipated
Environmental | Endangered species on project corridor. Mitigation or relocations required.
Environmental | Additional environmental analysis/update is required
Environmental | Lead and/or asbestos found onsite
Geotechnical | Structural foundation/material changes required
Geotechnical | Adverse groundwater conditions (pavement base/pond elevations)
Geotechnical | High water table
Geotechnical | Unsuitable material removal (muck/organics/plastic/clay etc.)
Geotechnical | Geogrid/geosynthetic material/soil stabilization is required
Geotechnical | Limited geotechnical information available
Geotechnical | Black base required
Geotechnical | Surcharging is required
Geotechnical | Hard layer different than anticipated for structural piling
Geotechnical | Excavated material cannot be used for earthwork balancing
Govt and NGO Coordination | Transfer maintenance agreements
Govt and NGO Coordination | Joint Use agreement different than anticipated
Govt and NGO Coordination | Reimbursement agreements
Govt and NGO Coordination | Requested changes to project
Govt and NGO Coordination | Community redevelopment planning requests
Govt and NGO Coordination | Local funding agreements with/without conditions
Govt and NGO Coordination | Local government planning
Govt and NGO Coordination | Transportation Planning Organization priorities change
Govt and NGO Coordination | Non governmental organization requests
Govt and NGO Coordination | Temporary transfer of right of way agreements
Govt and NGO Coordination | Construction maintenance agreements
Govt and NGO Coordination | Lighting/Landscaping agreements different than anticipated
Landscaping | Aesthetics/Hardscape (2%-4% of structural/wall/bridge cost)
Landscaping | Landscaping not previously included (1.5% of project total)
Landscaping | Protection of existing trees
Management / Funding | Coordination with adjacent projects
Management / Funding | Poor communication with project team
Management / Funding | Project schedule/quality issues
Management / Funding | Appropriate staff not assigned to project
Management / Funding | Project placed on the APP list (Advance Production Potential)
Management / Funding | Project is not fully funded
Management / Funding | Priorities change within FDOT departments
Management / Funding | Accelerated schedule reduces planning phase and creates uncertainty
Management / Funding | Requested schedule change
Management / Funding | Limited budget restricts scope additions
Management / Funding | Market conditions/inflation
Management / Funding | New funding source is available
Management / Funding | Original funding source is no longer viable
Political | Coordination with commercial interests
Political | Public commitments from politics/leadership
Political | Political support for project changes
Rail | Work adjacent to or within railroad right of way (rail involvement)
Rail | Railroad policy change requires plan updates
Rail | Shortage of rail flaggers
Rail | Number of trains at crossings increase (could decrease productivity and increase construction time)
Rail | Unforeseen rail involvement
Rail | Bridge replacement over rail right of way is subject to new requirements
Rail | Additional drainage facilities are required due to rail involvement
Rail | Rail owner requires unexpected changes during construction
Rail | Additional trains rerouted to adjacent railroad
Rail | Commitment to construct addition provisions for commuter rail within the project limits
Rail | Rail requirements not identified during planning/design
Rail | Special provision for increased insurance is required
Rail | Increased train movements result in delay and productivity loss
Rail | Crash walls required
Rail | Reduced/no flagger availability from 2nd week in November to 1st week in January
Rail | Changes to footprint within rail right of way necessitates a new easement
Right of Way | Accelerating pace of development in project corridor
Right of Way | Interagency Right of Way transfers are delayed
Right of Way | Right of Way is acquired after construction start for alternative contracting projects
Right of Way | Right of Way is too constrained for planned construction activities/constructability
Right of Way | Additional acquisitions required due to design changes
Right of Way | Removal of private construction withing FDOT Right of Way
Right of Way | Right of Way acquisition not completed on time
Structural | Bridge redesign/analysis
Structural | Change in wall height/length
Structural | Pier protection required
Structural | Widened roadway necessitates a grade separated pedestrian crossing
Structural | Revised bridge hydraulic report
Structural | Bridge clearance issues
Structural | Bridge approach cost not included
Structural | Additional walls other than at bridges anticipated (e.g. cut/MSE)
Structural | Changes in design (girder type, steel vs concrete, pile count, girder count, span length, beams per span, web depth, bridge length/width, footer column & cap type/dimensions)
Structural | Conservative wall design
Structural | Pedestrian over/under pass replaced
Structural | LRE used per SF pricing that is too low
Structural | Bridge culvert needs to be extended/replaced
Structural | Scour issues anticipated
Structural | Removal of existing structures
Structural | Conservative bridge design
Structural | Complex construction methods (e.g. top down construction)
Structural | Existing structures settle during construction requiring additional precautions delaying the project
Tolls | Update in number of gantries required
Tolls | Potential changes in technology
Tolls | Upgraded measures to prevent unauthorized access to express lanes
Tolls | Additional plaza is needed
Utilities | Utility owner delays during design
Utilities | Unknown/unclaimed utility encountered during construction
Utilities | Local government delays utility relocation due to financial hardships
Utilities | Reconstruction of utilities by third party contractor
Utilities | Relocation of existing FDOT owned utilities is required
Utilities | Utility owner delays during construction
Utilities | Bridge widening/replacement requires relocation of utilities
Utilities | Utility does not have as-built data and cannot provide markups
Utilities | Utility does not have tracer wire and cannot be located
Utilities | Utility work by permit is installed after design but prior to construction
Utilities | Design cannot avoid reimbursable utilities
Utilities | Major utility relocations are required
Utilities | Electrical utility cannot de-energize
Utilities | Utility offset requirements cannot be accommodated
Utilities | Existing utility is in an easement
Utilities | Existing utility is in a duct bank
Utilities | Utility owner does not abide by the Utility Owners Agreement
Utilities | Funding change from state to federal makes utilities reimbursable
Utilities | Distance to needed utilities different than anticipated, e.g. electrical, water, sewer, etc.
Utilities | Cost for electrical connections higher/lower than typical
Utilities | Change in project alignment or other design features requires utility relocations
Utilities | Sub-aqueous utility lines present within construction limits