## Project Cost Checklist
Project Cost Checklist
The prompts below should be used by the Engineer of Record to help them provide a comprehensive set of project quantities for the scope of construction or document project elements that must be accounted for in Project Unknowns.
No. | Categories | Prompts for Project Cost
1 | Architectural | All features such as picnic tables, flagpoles, trash receptacles, shelters, bike racks and furniture included?
2 | Architectural | Toll plaza buildings are included
3 | Architectural | Picnic pavilions have been added. Ensure appropriate ADA accommodations are included and at the correct ratio. (ped signals, curb ramps, detectable warning surfaces)
4 | Bridges | Quantities for bridges are provided instead of using lump sum or per unit pricing?
5 | Bridges | Is removal of existing structures included?
6 | Bridges | Is the bridge estimate provided with supporting files? This would be needed at early planning phases too.
7 | Bridges | All bridges are independently estimated and priced based on location and individual site difficulties?
8 | Bridges | If per square foot costing was used to determine overall bridge cost, independently verify results with anticipated quantities and construction method costs.
9 | Bridges | Are any temporary structures required? Temporary bridge?
10 | Bridges | Monitor existing structures?
11 | Bridges | Wildlife crossing/shelf?
12 | Bridges | Restrictions on piling operations that could increase unit costs?
13 | Bridges | Was historical geotechnical data used to determine pile depths?
14 | Bridges | Anticipated steel type?
15 | Bridges | Was latest industry pricing used for bridge items? How is that different from the Structures Design Guide (SDG)?
16 | Bridges | Do bridges meet height clearance requirements?
17 | Bridges | Will anticipated construction methods increase cost. e.g. top down construction, over water, over rail, etc.?
18 | Bridges | Verify pile lengths were determined using current or historical geotechnical data when available.
19 | Bridges | Pile counts and lengths provided
20 | Bridges | Girder type, count and lengths provided
21 | Bridges | Anticipated footing column and cap dimensions provided
22 | Bridges | Span lengths provided
23 | Bridges | Web depth provided
24 | Bridges | Number of spans provided
25 | Bridges | Bridge length provided
26 | Bridges | Bridge width provided
27 | Bridges | Reseal slab joints?
28 | Bridges | Bridge railing/barrier upgrades?
29 | Bridges | Approach slab settlement or repairs required?
30 | Bridges | Increased bridge complexity necessitates higher unit costs?
31 | Bridges | Boardwalk on project?
32 | Bridges | Pedestrian bridge repair/replacement?
33 | Bridges | Aesthetics required? Estimate 2% - 4% of the bridge cost.
34 | Bridges | Pedestrian features on bridge?
35 | Clearing and Grubbing | Is the appropriate amount of clearing and grubbing included?
36 | Drainage | Are all conveyance items included? Closed system, driveway culverts, inlets, pipes, underdrain, ditch lining, end treatments, rubble or bedding stone for erosion, etc.?
37 | Drainage | Are all stormwater management facilities accounted for?
38 | Drainage | Plugging water wells
39 | Drainage | Temporary drainage required?
40 | Drainage | Will dewatering be required? If so, this will increase costs.
41 | Drainage | Will additional box culvert cells be required for design flow or maintenance of traffic (MOT)?
42 | Drainage | Will flowable fill, bedding material or rip rap will be needed to expedite construction in an area to help maintain traffic flow?
43 | Drainage | Stormwater earthwork accounted for?
44 | Drainage | Have drainage pipes been roughly sized? Longer conveyance distances may require larger diameters.
45 | Drainage | Are any cross drains to be extended? Will a hydraulic analysis be required?
46 | Drainage | Will high water tables change pavement design, pond design, or construction methods?
47 | Drainage | Temporary wetland impacts? Construction methods and materials for these impacts?
48 | Earthwork | If there is limited geotechnical data, was historic or USDA web soil survey data provided?
49 | Earthwork | Is earthwork using a built in LRE template or independently verified? Confirm/verify any assumptions
50 | Earthwork | Is unsuitable material within project limits? Assume some amount based on geotechnical analysis, web based soils data, or wetland data
51 | Earthwork | Is temporary earthwork required?
52 | Earthwork | Contamination removal?
53 | Erosion Control | Are erosion & sediment control measures accounted for?
54 | Erosion Control | Erosion control measures provided for slopes, inlets and waterbodies
55 | Intelligent Traffic System (ITS) | Quantities for ITS are provided instead of using lump sum or per unit pricing
56 | Intelligent Traffic System (ITS) | Relocation costs for FDOT ITS utilities/facilities are included
57 | Intelligent Traffic System (ITS) | Will temporary intelligent transportation system (ITS) items be required?
58 | Intelligent Traffic System (ITS) | All cabinets, Bluetooth, dynamic message signs, cameras etc. have been included.
59 | Landscaping | Coordinate with district on landscape needs
60 | Landscaping | Aesthetics items included? This would be outside of bridge or wall cost estimates.
61 | Lighting | Quantities for lighting are provided instead of using lump sum or per unit pricing
62 | Lighting | Relocation costs for FDOT lighting utilities/facilities are included
63 | Lighting | Intersection lighting included?
64 | Lighting | Corridor lighting included?
65 | Lighting | Park and ride lighting included?
66 | Lighting | Will temporary lighting be required?
67 | Lighting | Interchange and ramp lighting included?
68 | Lighting | Upgrading to LED?
69 | Lighting | Pedestrian lighting at signalized intersections and mid block crossings included?
70 | Lighting | Lighting at bus stops included?
71 | Miscellaneous | Field office needed?
72 | Miscellaneous | All rail work is included?
73 | Miscellaneous | Have wildlife crossing requirements been incorporated and additional pay items (fencing as example) included?
74 | Project Level | List of assumptions provided for unique or major quantities (e.g. asphalt, concrete, steel, earthwork etc.)
75 | Project Level | Justification provided for percent item Maintenance of Traffic (MOT) - Should not include MOT items that have separate pay items; greenfield work should decrease MOT
76 | Project Level | Justification provided for percent item Mobilization (MOB) - Difficult to access or specialty equipment etc.
77 | Project Level | Justification provided for percent item Project Unknowns - Should include a discussion of the risk assessment
78 | Project Level | Justification provided for percent item Design Build (DB) - e.g. Modified Phased Design Build (MPDB) would have up to three engineering teams
79 | Project Level | Qualitative & Quantitate risk register provided from the Engineer of Record (EOR) or Cost and Schedule Risk Assessment (CSRA) process
80 | Project Level | Projects in planning or early phase development will still need independently verified and thorough quantities
81 | Project Level | If per unit costs are in the Long Range Estimate (LRE), provide a separate spreadsheet with quantities independently verified
82 | Project Level | Verify project length matches Project Suite Enterprise Edition (PSEE) - Update PSEE/Work Program as needed
83 | Project Level | Are all anticipated plan components covered in the Long Range Estimate (LRE) system?
84 | Project Level | List of all project commitments provided including PD&E, community outreach, Value Engineering (VE) studies, or public/political announcements
85 | Project Level | Have all non bid items that would impact cost been considered. (e.g. contractor walls, dewatering etc.)
86 | Project Level | Has the Long Range Estimate (LRE) or Design Quantities and Estimates (DQE) been reconciled with the IPC?
87 | Project Level | Does the final Design Quantities and Estimates (DQE) match the Independent Project Cost (IPC)?
88 | Project Level | Change documents provided with appropriate scope change approvals
89 | Project Level | Is a comparison of the pay items used against the master pay item list available?
90 | Project Level | Verify costs are not duplicated in the LRE, IPC, DQE for adjacent projects etc.
91 | Project Level | Explanation provided for significant changes in unit costs at next phase submittal
92 | Project Level | Will an early works project increase throwaway work or Mobilization (MOB)
93 | Project Level | List provided of scope/quantity changes between project phases?
94 | Project Level | Risk is included in Project Unknowns or Design Quantities and Estimates (DQE)
95 | Project Level | Were specification allowed overages included in the risk register?
96 | Project Level | Is there any future Local Agency work within or adjacent to the project?
97 | Project Level | Add non-bid items such as; 999-16 (Partnering); 999-20-A Dispute Review Board Meeting & Hearing; and 999-25 (Initial Contingency Amount) as required
98 | Project Level | Description of what was used to set unit costs. Were unique factors or similar bid quantities etc. used to create unit costs?
99 | Project Level | Was a separate engineer's opinion of probable construction cost created in spreadsheet form?
100 | Project Level | Each LRE sequence adequately describes what is included
101 | Project Level | Assumptions should list any goes with or adjacent projects.
102 | Retaining Walls | Is the wall planned for a constrained area that may increase unit cost? Appropriate wall type selected?
103 | Retaining Walls | Noise, retaining, and/or gravity walls included?
104 | Retaining Walls | Are there any non critical contractor walls? (Walls that aren’t CTW’s but are still needed for construction.)
105 | Retaining Walls | Will specialized footers/foundations be required?
106 | Retaining Walls | Were all walls included in the estimate. Where are walls anticipated?
107 | Retaining Walls | Will Mechanically Stabilized Earth (MSE) walls be used along the project or at bridge abutments?
108 | Retaining Walls | Aesthetics required for noise, MSE wall etc.? Include a separate percentage cost for this work in the LRE.
109 | Roadway | Delivery of salvageable material to the department
110 | Roadway | Verify lane widths match plan documents
111 | Roadway | Verify LRE pavement design matches plan documents and the approved pavement design package
112 | Roadway | Is superelevation correction quantified?
113 | Roadway | Quantities for all anticipated turn lanes, bike key hole lanes, side streets and turnouts are provided and independently verified
114 | Roadway | Cross slope correction if any is quantified
115 | Roadway | Are significant saw cuts anticipated?
116 | Roadway | If a temporary diversion is needed, is temporary pavement and earthwork added?
117 | Roadway | Temporary asphalt etc. needed for roundabout construction.
118 | Roadway | Pavement markings are included.
119 | Roadway | Maintenance of Traffic phasing is quantified and provided.
120 | Roadway | Throw away work is quantified including any asphalt transitions for new traffic lanes.
121 | Roadway | Traffic control officers required?
122 | Roadway | Temporary ramps required?
123 | Roadway | Temporary concrete traffic barriers should be quantified separately from percentage items.
124 | Roadway | MOT items such as arrow boards, work zone signs, PCMS, etc. should be quantified separate from percentage items.
125 | Roadway | All paving items included for concrete pavement operations including edge drains, grinding etc.
126 | Roadway | Black base required?
127 | Roadway | What are the temporary pavement design thicknesses?
128 | Roadway | Specialty pavement markings accounted for including Railroad Dynamic Envelope (RDE) for at-grade crossings
129 | Roadway | Soil stabilization issues requiring Stress Absorbing Membrane (SAM) interlayer installation, grout columns, or geotextiles.?
130 | Roadway | Median opening construction
131 | Roadway | Is there a park and ride or other parking onsite? Is it accounted for in the quantities?
132 | Shoulder/Median | Removal of existing concrete included?
133 | Shoulder/Median | Verify shoulder width matches plan documents
134 | Shoulder/Median | Verify LRE shoulder pavement design matches plan documents and the approved pavement design package
135 | Shoulder/Median | Sidewalks and shared use paths are included per plan documents
136 | Shoulder/Median | Are concrete items such as curbing, gutter, medians, separators, etc. included?
137 | Shoulder/Median | Are all ADA upgrades included?
138 | Shoulder/Median | Is handrail included where needed?
139 | Shoulder/Median | Are guardrail replacement, end treatments, bridge anchorage assemblies, crash cushions, etc. included?
140 | Shoulder/Median | Fencing included along Right of Way as needed?
141 | Shoulder/Median | Fencing included at stormwater basins as needed?
142 | Shoulder/Median | Mailboxes included
143 | Shoulder/Median | Turf items included?
144 | Shoulder/Median | Will pier protection be required?
145 | Shoulder/Median | Delineators are included?
146 | Shoulder/Median | Mowing and litter removal is included
147 | Shoulder/Median | Rumble strips including audible and vibratory treatments added as needed.
148 | Shoulder/Median | Sidewalk gaps are filled in
149 | Shoulder/Median | Are bus bay improvements included? (Benches and shelters are paid by the local transit authority.)
150 | Shoulder/Median | Water bodies along roadway that should be shielded with guardrail?
151 | Shoulder/Median | Is context sensative design accounted for if applicable?
152 | Shoulder/Median | Include litter removal and mowing.
153 | Signalizations | Are temporary signals needed?
154 | Signalizations | Are proposed signals/removals included?
155 | Signalizations | Traffic Monitoring Site replacement?
156 | Signalizations | Upgrade signal heads, wiring and vehicle detection devices including addition of backplates.
157 | Signalizations | Upgrade pedestrian signals to current standards and ADA.
158 | Signalizations | Are signals within 10 miles of the coast? Upgrade to mast arms?
159 | Signalizations | Upgrade School Zones
160 | Signalizations | Fiber interconnect or cellular modem for connectivity?
161 | Signalizations | Toll Gantries
162 | Signalizations | Signal designs were selected based on standards and local agency input?
163 | Signalizations | Are Pan Tilt Zoom (PTZ) cameras required?
164 | Signalizations | Are illuminated signs needed?
165 | Signalizations | Is signal preemption needed?
166 | Signalizations | Signalized mid block crossings?
167 | Signing | Are multi-post, bridge mounted, or overhead signs being installed or replaced on the project?
168 | Signing | Replace existing signs.
169 | Turnouts/Crossovers | Quantities of turnouts/crossovers are independently verified.
170 | Utilities | Anticipated utility relocations are identified?
171 | Utilities | Project required utility connections or extensions are included (e.g. electrical service and water/wastewater connections etc.)
172 | Utilities | Are utilities reimbursable?
173 | Utilities | Manhole/valve adjusts?