## All
District 4 Local Program GAP Checklist
GAP Checklist
Agency:
FM Number:
Description:
LAP Certifications | Upload By | Locations | Responsible
Local Agency Program Certification Tool | Initial Phase Submittal | Organization Details/Required Docs | Organization
Sub Recipient Compliance Assessment Tool(SCAT) | Initial Phase Submittal | Organization Details/Required Docs | Organization
Title VI /Nondiscrimination Assurance | Initial Phase Submittal | Organization Details/Required Docs | Organization
Title VI Plan | Initial Phase Submittal | Organization Details/Required Docs | Organization
ADA Policy Statement | Initial Phase Submittal | Organization Details/Required Docs | Organization
ADA Transition Plan, if available. | Initial Phase Submittal | Organization Details/Required Docs | Organization
Financial Risk Assessment Matrix | Initial Phase Submittal | Organization Details/Required Docs | FDOT
Financial Risk Assessment | Initial Phase Submittal | Organization Details/Required Docs | FDOT
Organization Chart | Initial Phase Submittal | Organization Details/Required Docs | Organization
Resumes (Agency LAP Team including Consultant support) | Initial Phase Submittal | Organization Details/Required Docs | Organization
Computer Base Training (CBT's) | Initial Phase Submittal | Organization Details/Required Docs | Organization
Approved LAP Certification Package & Letter | Production | Organization Details/Required Docs | FDOT
Phase 38- Professional Services - Items to Upload | Upload By | Locations | Responsible
Local Agency Program (LAP) Checklist for Design (38)-Federal Funded Professional Services - Executed | Approval of RFP | Tracking | FDOT
Final Approved RFP for Design with all required federal forms | Approval of RFP | Tracking | FDOT
Executed Local Agency Program (LAP) Agreement (Phase 38) | Prior to Advertisment | Tracking | FDOT
Encumbrance (38) | Upon receipt | Tracking | FDOT
FDOT NTP for Advertisement | Prior to issuance of contract | Tracking | Organization
Truth in Negotiations form# 375-030-30 | Prior to issuance of contract | Tracking | Organization
Local Agency Compliance Forms Conflict of Interest and Confidentialy | Prior to issuance of contract | Tracking | Organization
FDOT of Final Approved Professional Service Contract with all forms | Prior to NTP for Design | Tracking | Organization
Local Agency Program (LAP) Checklist for Design (38)-Federal Funded Professional Services - Executed | Approval of RFP | Tracking | FDOT
Final Approved RFP for Design with all required federal forms | Approval of RFP | Tracking | Organization
Executed Local Agency Program (LAP) Agreement (Phase 38) | Prior to Advertisment | Tracking | Organization
FDOT NTP for Advertisement | Prior to issuance of contract | Tracking | Organization
Public Advertisement | Prior to Advertisment | Tracking | Organization
Concurrence to Advertise | Prior to Advertisment | Tracking | FDOT
Final Request for Qualifications/Request for Proposal Package as Advertised | Prior to Advertisment | Tracking | Organization
Addenda to the RFQ/RFP | Prior to Publication | Tracking | Organization
Concurrence with Addenda to Advertisement | Prior to Publication | Tracking | FDOT
Vendor Eligibility Verification | Prior to Award | Tracking | Organization
Truth in Negotiations form# 375-030-30 | Prior to Award | Tracking | Organization
Conflict of Interest Form signed by Selection Committee | Prior to Award | Tracking | Organization
Conflict of Interest Form signed by respondants | Prior to Award | Tracking | Organization
Certification Regarding Debarment, Suspension, Ineligibility and Voluntary Exclusion for Federal Aid Contracts | Prior to Award | Tracking | Organization
Certification for Disclosure of Lobbying Activities on Federal Aid Contracts | Prior to Award | Tracking | Organization
Standard Form -LLL, Disclosure of Lobbying Activities | Prior to Award | Tracking | Organization
Short List of Consultant Firms | Prior to Award | Tracking | Organization
Approval to Move Forward with Less than 3 Responses | Prior to Award | Tracking | FDOT
Independent Man/Staff Hour Estimate prepared by LA | Prior to Award | Tracking | Organization
Score Sheets (includes raw, summary, technical, and presentations as applicable) | Prior to Award | Tracking | Organization
Concurrence to Negotiate | Prior to Award | Tracking | FDOT
Selection Committee Meeting Minutes or Recording | Prior to Award | Tracking | Organization
Negotiations Documentation | Prior to Award | Tracking | Organization
LA Notice of Intent to Award | Prior to Award | Tracking | Organization
Draft Professional Services Contract | Prior to Award | Tracking | Organization
Concurrence with Professional Services Contract Award | Prior to Award | Tracking | FDOT
Professional Services Consultant Contract | Upon execution | Tracking | Organization
LAP Professional Services Checklist executed | Upon execution | Tracking | Organization
Consultant Notice to Proceed- Professional Services | Upon execution | Tracking | Organization
Consultant Contract Amendments | Upon execution | Tracking | Organization
Concurrence with Professional Services Contract Amendment(s) | Upon execution | Tracking | FDOT
Task Work Order (Continuing Contracts only) | Upon execution | Tracking | Organization:
Concurrence with Professional Services Task Order Award | Upon execution | Tracking | FDOT
Consultant Performance Evaluation | Upon Completion | Tracking | Organization
Proof of Insurance | Upon Award | Tracking | Organization
Phase 58- Items to Upload | Upload By | Locations | Responsible
Executed Local Agency Program (LAP) Agreement (Phase 58) | Upon execution | Tracking | Organization
Encumbrance (58) | Upon receipt | Tracking | FDOT
Environmental Certification | Production | Tracking | FDOT
Right of Way Certification | Production | Tracking | FDOT
Final Approved PS&E Package | FDOT | Tracking | FDOT
Final Approved Construction Checklist | Upon issuance | Tracking | FDOT
FDOT Notice to Proceed to Advertise | Upon issuance | Tracking | FDOT
Final Approved BID Docs for Construction with all required federal forms | Approval of RFP | Tracking | Organization
FDOT Bid Concurrence to Local Agency | Upon issuance | Tracking | FDOT
Construction Phase - Bid : 58-01 | Upload By | Locations | Responsible
Executed Local Agency Program (LAP) Supplemental Agreement (Phase 58) | Upon execution | Tracking | Organization
FDOT Notice to Proceed to Advertise | Upon issuance | Tracking | FDOT
Executed Contract by LA and Contractor | Prior to Pre-Construction Meeting | Tracking | Organization
Final Signed and Sealed Plans | Prior to Pre-Construction Meeting | Tracking | Organization
Pre-construction Meeting Minutes | After meeting | Tracking | Organization
Progress Meetings Minutes | After each meeting | Documents | Organization
Contractor’s Baseline Construction Schedule(s) | Prior to Pre-Construction Meeting and after Progress Meetings | Documents | Organization
LA Notice to Proceed to Contractor | Upon issuance | Tracking | Organization
Each Change Order with concurrence | As each change order is executed | Documents | Organization
Buy America Certification (if applicable) | Prior to completion of project | Tracking | Organization
ALL Shop Drawings – Approved | As a complete pdf file | Tracking | Organization
Time File / Cal File (After Final Acceptance) | Upon approval or acceptance by LA | Tracking | Organization
QC Plan | Upon approval or acceptance by LA | Tracking | Organization
Permits | As the final permits have been received | Tracking | Organization
Drill Shaft Installation Plan, Pile Driving Plan, Mix Design | Upon approval or acceptance by LA | Tracking | Organization
Final Request for Reimbursement Invoice with backup | Upon Approval by FDOT | Tracking | Organization
All Project Monthly Status Reports (PMSRs) (Scanned to one) | Before Final Audit | Documents | Organization
All Certification of Payments (700-010-38) (Scanned to one) | Before Final Audit | Documents | Organization
All Final Release of Liens | Before Final Audit | Documents | Organization
Materials Certification Letter from Local Agency | Before Final Audit | Tracking | Organization
Contractors Affidavit and Surety Consent (700-050-21) | Before Final Audit | Documents | Organization
LAP Oversight: Construction Compliance Audit | Upon Completion of Project | Tracking | FDOT
Performance Evaluation LAP Oversight | Upon Completion of Project | Tracking | FDOT
Project Photos LAP Oversignt | Upon Completion of Project | Tracking | FDOT
For Project Closeout with Local Agency
Record of Final Plans and Documents (525-010-47) | Before Final Audit | Tracking | Organization
Over-run Underrun calculations (if not shown on record of Final Plans) | Before Final Audit | Tracking | Organization
Time/Day Counts (spreadsheet/form) | Before Final Audit | Tracking | Organization
Final Reimbursement* | Before Final Audit | Tracking | Organization
Performance Evaluation Fully Executed | Before Final Audit | Tracking | Organization
Final Inspection and Acceptance (525-010-42) | Before Final Audit | Tracking | Organization
Materials Certification Statement | Before Final Audit | Tracking | Organization
Certified As-built Plans | Before Final Audit | Tracking | Organization
Material Tests (Not in LIMS) (as a single file) | Before Final Audit | Tracking | Organization
The Quantities (Plan vs. Actual) for Asphalt, Concrete, and Earthwork materials used. | Before Final Audit | Documents | Organization
Copies of the Tests Data | Before Final Audit | Documents | Organization
Copies of Delivery tickets for Asphalt, Concrete, and Base materials | Before Final Audit | Documents | Organization
Any failing material left in place? How much? | Before Final Audit | Documents | Organization
Corrective Action and Disposition of failing materials. | Before Final Audit | Documents | Organization
Phase 54- Items to Upload -Before and During Construction | Upload By | Locations | Responsible
Executed State Grant Agreement (Phase 54) | Upon execution | Tracking | Organization
Executed State Grant Supplemental Agreement (Phase 54) | Upon execution | Tracking | Organization
FDOT Notice to Proceed to Advertise | Upon issuance | Tracking | FDOT
FDOT Concurrence BID Package to Local Agency | Upon issuance | Tracking | FDOT
Final Contract Package executed by LA andCEI Consultant | Prior to Pre-Construction Meeting | Tracking | Organization
Final Signed and Sealed Plans | Prior to Pre-Construction Meeting | Tracking | Organization
Pre-construction Meeting Minutes | After meeting | Tracking | Organization
Progress Meetings Minutes | After each meeting | Documents | Organization
Contractor’s Baseline Construction Schedule(s) | Prior to Pre-Construction Meeting and after Progress Meetings | Documents | Organization
LA Notice to Proceed to Contractor | Upon issuance | Tracking | Organization
Each Change Order with concurrence | As each change order is executed | Documents | Organization
ALL Shop Drawings – Approved | As a complete pdf file | Tracking | Organization
Time File / Cal File (After Final Acceptance) | Upon approval or acceptance by LA | Tracking | Organization
QC Plan | Upon approval or acceptance by LA | Tracking | Organization
Permits | As the final permits have been received | Tracking | Organization
Drill Shaft Installation Plan, Pile Driving Plan, Mix Design | Upon approval or acceptance by LA | Tracking | Organization
Final Request for Reimbursement Invoice with backup | Upon Approval by FDOT | Tracking | Organization
All Project Monthly Status Reports (PMSRs) (Scanned to one) | Before Final Audit | Documents | Organization
All Certification of Payments (700-010-38) (Scanned to one) | Before Final Audit | Tracking | Organization
All Final Release of Liens | Before Final Audit | Tracking | Organization
Materials Certification Letter from Local Agency | Before Final Audit | Tracking | Organization
Contractors Affidavit and Surety Consent (700-050-21) | Before Final Audit | Tracking | Organization
For Project Closeout with Local Agency
Over-run Underrun calculations (if not shown on record of Final Plans) | Before Final Audit | Tracking | Organization
Time/Day Counts (spreadsheet/form) | Before Final Audit | Tracking | Organization
Final Reimbursement* | Before Final Audit | Tracking | Organization
Final Inspection and Acceptance (525-010-42) | Before Final Audit | Tracking | Organization
Engineers Certification of Compliance | Before Final Audit | Tracking | Organization
Materials Certification Statement | Before Final Audit | Tracking | Organization
Certified As-built Plans | Before Final Audit | Tracking | Organization
Material Tests (Not in LIMS) (as a single file) | Before Final Audit | Tracking | Organization
The Quantities (Plan vs. Actual) for Asphalt, Concrete, and Earthwork materials used. | Before Final Audit | Documents | Organization
Copies of the Tests Data | Before Final Audit | Documents | Organization
Copies of Delivery tickets for Asphalt, Concrete, and Base materials | Before Final Audit | Documents | Organization
Any failing material left in place? How much? | Before Final Audit | Documents | Organization
Corrective Action and Disposition of failing materials. | Before Final Audit | Documents | Organization
Phase 68- Items to Upload -Before and During Construction | Upload By | Locations | Responsible
Executed Local Agency Program (LAP) Agreement (Phase 68) | Upon execution | Tracking | Organization
Executed Local Agency Program (LAP) Supplemental Agreement (Phase 68) | Upon execution | Tracking | Organization
FDOT Notice to Proceed to Advertise | Upon issuance | Tracking | FDOT
FDOT RFQ Concurrence to Local Agency | Upon issuance | Tracking | FDOT
Final Contract Package executed by LA andCEI Consultant | Prior to Pre-Construction Meeting | Tracking | Organization
Final Signed and Sealed Plans | Prior to Pre-Construction Meeting | Tracking | Organization
Pre-construction Meeting Minutes | After meeting | Tracking | Organization
Progress Meetings Minutes | After each meeting | Documents | Organization
Contractor’s Baseline Construction Schedule(s) | Prior to Pre-Construction Meeting and after Progress Meetings | Documents | Organization
LA Notice to Proceed to Contractor | Upon issuance | Tracking | Organization
Each Change Order with concurrence | As each change order is executed | Documents | Organization
Buy America Certification (if applicable) | Prior to completion of project | Tracking | Organization
ALL Shop Drawings – Approved | As a complete pdf file | Tracking | Organization
Time File / Cal File (After Final Acceptance) | Upon approval or acceptance by LA | Tracking | Organization
QC Plan | Upon approval or acceptance by LA | Tracking | Organization
Permits | As the final permits have been received | Tracking | Organization
Drill Shaft Installation Plan, Pile Driving Plan, Mix Design | Upon approval or acceptance by LA | Tracking | Organization
Final Request for Reimbursement Invoice with backup | Upon Approval by FDOT | Tracking | Organization
All Project Monthly Status Reports (PMSRs) (Scanned to one) | Before Final Audit | Tracking | Organization
All Certification of Payments (700-010-38) (Scanned to one) | Before Final Audit | Tracking | Organization
All Final Release of Liens | Before Final Audit | Tracking | Organization
Materials Certification Letter from Local Agency | Before Final Audit | Tracking | Organization
Contractors Affidavit and Surety Consent (700-050-21) | Before Final Audit | Tracking | Organization
LAP Oversight: Construction Compliance Audit | Upon Completion of Project | Tracking | FDOT
Performance Evaluation LAP Oversight | Upon Completion of Project | Tracking | FDOT
Project Photos LAP Oversignt | Upon Completion of Project | Tracking | FDOT
For Project Closeout with Local Agency
Record of Final Plans and Documents (525-010-47) | Before Final Audit | Tracking | Organization
Over-run Underrun calculations (if not shown on record of Final Plans) | Before Final Audit | Tracking | Organization
Time/Day Counts (spreadsheet/form) | Before Final Audit | Tracking | Organization
Final Reimbursement* | Before Final Audit | Tracking | Organization
Performance Evaluation Fully Executed | Before Final Audit | Tracking | Organization
Final Inspection and Acceptance (525-010-42) | Before Final Audit | Tracking | Organization
Materials Certification Statement | Before Final Audit | Tracking | Organization
Certified As-built Plans | Before Final Audit | Tracking | Organization
Material Tests (Not in LIMS) (as a single file) | Before Final Audit | Tracking | Organization
The Quantities (Plan vs. Actual) for Asphalt, Concrete, and Earthwork materials used. | Before Final Audit | Documents | Organization
Copies of the Tests Data | Before Final Audit | Documents | Organization
Copies of Delivery tickets for Asphalt, Concrete, and Base materials | Before Final Audit | Documents | Organization
Any failing material left in place? How much? | Before Final Audit | Documents | Organization
Corrective Action and Disposition of failing materials. | Before Final Audit | Documents | Organization
INVOICES | Upload By | Locations | Responsible
Advertisement Invoice | With in 90 Days of Issuance of NTP to Advertise | Invoices | Organization
Invoices | With in 90 Days of previously submitted invoices | Invoices | Organization
DOCUMENTS | Upload By | Locations | Responsible
Progress Meetings Minutes | Monthly - Life of project | Documents | Organization
Contractor’s Baseline Construction Schedule(s) | Prior to Pre-Construction Meeting and after Progress Meetings | Documents | Organization
Each Change Order with concurrence | As each change order is executed | Documents | Organization
The Quantities (Plan vs. Actual) for Asphalt, Concrete, and Earthwork materials used. | Before Final Audit | Documents | Organization
Copies of the Tests Data | Before Final Audit | Documents | Organization
Copies of Delivery tickets for Asphalt, Concrete, and Base materials | Before Final Audit | Documents | Organization
Any failing material left in place? How much? | Before Final Audit | Documents | Organization
Corrective Action and Disposition of failing materials. | Before Final Audit | Documents | Organization
Jobsite Bulletin Board (monthly) | Monthly - Life of project | Documents | Organization
Progress Monthly Summary Report | Monthly - Life of project | Documents | Organization
Subcontractor(s) Contracts/Purchase Orders/Rental Agreements | Prior to start of work | Documents | Organization
Commerical Useful Function (CUFS) | Monthly -(first 3 months of active work) | Documents | Organization
July Reorts | Before Final Audit | Documents | Organization
Daily Work Reports | Monthly - Life of project | Documents | Organization

## LAP CERT
District 4 Local Program GAP Checklist
GAP Checklist
Agency:
FM Number:
Description:
LAP Certifications | Upload By | Locations | Responsible
Local Agency Program Certification Tool | Initial Phase Submittal | Organization Details/Required Docs | Organization
Sub Recipient Compliance Assessment Tool(SCAT) | Initial Phase Submittal | Organization Details/Required Docs | Organization
Title VI /Nondiscrimination Assurance | Initial Phase Submittal | Organization Details/Required Docs | Organization
Title VI Plan | Initial Phase Submittal | Organization Details/Required Docs | Organization
ADA Policy Statement | Initial Phase Submittal | Organization Details/Required Docs | Organization
ADA Transition Plan, if available. | Initial Phase Submittal | Organization Details/Required Docs | Organization
Financial Risk Assessment Matrix | Initial Phase Submittal | Organization Details/Required Docs | FDOT
Financial Risk Assessment | Initial Phase Submittal | Organization Details/Required Docs | FDOT
Organization Chart | Initial Phase Submittal | Organization Details/Required Docs | Organization
Resumes (Agency LAP Team including Consultant support) | Initial Phase Submittal | Organization Details/Required Docs | Organization
Computer Base Training (CBT's) | Initial Phase Submittal | Organization Details/Required Docs | Organization
Approved LAP Certification Package & Letter | Production | Organization Details/Required Docs | FDOT

## PROF SERV PH 38
District 4 Local Program GAP Checklist
GAP Checklist
Agency:
FM Number:
Description:
Phase 38- Professional Services - Items to Upload | Upload By | Locations | Responsible
Local Agency Program (LAP) Checklist for Design (38)-Federal Funded Professional Services - Executed | Approval of RFP | Tracking | FDOT
Final Approved RFP for Design with all required federal forms | Approval of RFP | Tracking | Organization
Executed Local Agency Program (LAP) Agreement (Phase 38) | Prior to Advertisment | Tracking | Organization
FDOT NTP for Advertisement | Prior to issuance of contract | Tracking | Organization
Public Advertisement | Prior to Advertisment | Tracking | Organization
Concurrence to Advertise | Prior to Advertisment | Tracking | FDOT
Final Request for Qualifications/Request for Proposal Package as Advertised | Prior to Advertisment | Tracking | Organization
Addenda to the RFQ/RFP | Prior to Publication | Tracking | Organization
Concurrence with Addenda to Advertisement | Prior to Publication | Tracking | FDOT
Vendor Eligibility Verification | Prior to Award | Tracking | Organization
Truth in Negotiations form# 375-030-30 | Prior to Award | Tracking | Organization
Conflict of Interest Form signed by Selection Committee | Prior to Award | Tracking | Organization
Conflict of Interest Form signed by respondants | Prior to Award | Tracking | Organization
Certification Regarding Debarment, Suspension, Ineligibility and Voluntary Exclusion for Federal Aid Contracts | Prior to Award | Tracking | Organization
Certification for Disclosure of Lobbying Activities on Federal Aid Contracts | Prior to Award | Tracking | Organization
Standard Form -LLL, Disclosure of Lobbying Activities | Prior to Award | Tracking | Organization
Short List of Consultant Firms | Prior to Award | Tracking | Organization
Approval to Move Forward with Less than 3 Responses | Prior to Award | Tracking | FDOT
Independent Man/Staff Hour Estimate prepared by LA | Prior to Award | Tracking | Organization
Score Sheets (includes raw, summary, technical, and presentations as applicable) | Prior to Award | Tracking | Organization
Concurrence to Negotiate | Prior to Award | Tracking | FDOT
Selection Committee Meeting Minutes or Recording | Prior to Award | Tracking | Organization
Negotiations Documentation | Prior to Award | Tracking | Organization
LA Notice of Intent to Award | Prior to Award | Tracking | Organization
Draft Professional Services Contract | Prior to Award | Tracking | Organization
Concurrence with Professional Services Contract Award | Prior to Award | Tracking | FDOT
Professional Services Consultant Contract | Upon execution | Tracking | Organization
LAP Professional Services Checklist executed | Upon execution | Tracking | Organization
Consultant Notice to Proceed- Professional Services | Upon execution | Tracking | Organization
Consultant Contract Amendments | Upon execution | Tracking | Organization
Concurrence with Professional Services Contract Amendment(s) | Upon execution | Tracking | FDOT
Task Work Order (Continuing Contracts only) | Upon execution | Tracking | Organization:
Concurrence with Professional Services Task Order Award | Upon execution | Tracking | FDOT
Consultant Performance Evaluation | Upon Completion | Tracking | Organization
Proof of Insurance | Upon Award | Tracking | Organization

## PHASE 58
District 4 Local Program GAP Checklist
GAP Checklist
Agency:
FM Number:
Description:
Phase 58- Items to Upload | Upload By | Locations | Responsible
Executed Local Agency Program (LAP) Agreement (Phase 58) | Upon execution | Tracking | Organization
Encumbrance (58) | Upon receipt | Tracking | FDOT
Environmental Certification | Production | Tracking | FDOT
Right of Way Certification | Production | Tracking | FDOT
Final Approved PS&E Package | FDOT | Tracking | FDOT
Final Approved Construction Checklist | Upon issuance | Tracking | FDOT
FDOT Notice to Proceed to Advertise | Upon issuance | Tracking | FDOT
Final Approved BID Docs for Construction with all required federal forms | Approval of RFP | Tracking | Organization
FDOT Bid Concurrence to Local Agency | Upon issuance | Tracking | FDOT
Construction Phase - Bid : 58-01 | Upload By | Locations | Responsible
Executed Local Agency Program (LAP) Supplemental Agreement (Phase 58) | Upon execution | Tracking | Organization
FDOT Notice to Proceed to Advertise | Upon issuance | Tracking | FDOT
Executed Contract by LA and Contractor | Prior to Pre-Construction Meeting | Tracking | Organization
Final Signed and Sealed Plans | Prior to Pre-Construction Meeting | Tracking | Organization
Pre-construction Meeting Minutes | After meeting | Tracking | Organization
Progress Meetings Minutes | After each meeting | Documents | Organization
Contractor’s Baseline Construction Schedule(s) | Prior to Pre-Construction Meeting and after Progress Meetings | Documents | Organization
LA Notice to Proceed to Contractor | Upon issuance | Tracking | Organization
Each Change Order with concurrence | As each change order is executed | Documents | Organization
Buy America Certification (if applicable) | Prior to completion of project | Tracking | Organization
ALL Shop Drawings – Approved | As a complete pdf file | Tracking | Organization
Time File / Cal File (After Final Acceptance) | Upon approval or acceptance by LA | Tracking | Organization
QC Plan | Upon approval or acceptance by LA | Tracking | Organization
Permits | As the final permits have been received | Tracking | Organization
Drill Shaft Installation Plan, Pile Driving Plan, Mix Design | Upon approval or acceptance by LA | Tracking | Organization
Final Request for Reimbursement Invoice with backup | Upon Approval by FDOT | Tracking | Organization
All Project Monthly Status Reports (PMSRs) (Scanned to one) | Before Final Audit | Documents | Organization
All Certification of Payments (700-010-38) (Scanned to one) | Before Final Audit | Documents | Organization
All Final Release of Liens | Before Final Audit | Documents | Organization
Materials Certification Letter from Local Agency | Before Final Audit | Tracking | Organization
Contractors Affidavit and Surety Consent (700-050-21) | Before Final Audit | Documents | Organization
LAP Oversight: Construction Compliance Audit | Upon Completion of Project | Tracking | FDOT
Performance Evaluation LAP Oversight | Upon Completion of Project | Tracking | FDOT
Project Photos LAP Oversignt | Upon Completion of Project | Tracking | FDOT
For Project Closeout with Local Agency
Record of Final Plans and Documents (525-010-47) | Before Final Audit | Tracking | Organization
Over-run Underrun calculations (if not shown on record of Final Plans) | Before Final Audit | Tracking | Organization
Time/Day Counts (spreadsheet/form) | Before Final Audit | Tracking | Organization
Final Reimbursement* | Before Final Audit | Tracking | Organization
Performance Evaluation Fully Executed | Before Final Audit | Tracking | Organization
Final Inspection and Acceptance (525-010-42) | Before Final Audit | Tracking | Organization
Materials Certification Statement | Before Final Audit | Tracking | Organization
Certified As-built Plans | Before Final Audit | Tracking | Organization
Material Tests (Not in LIMS) (as a single file) | Before Final Audit | Tracking | Organization
The Quantities (Plan vs. Actual) for Asphalt, Concrete, and Earthwork materials used. | Before Final Audit | Documents | Organization
Copies of the Tests Data | Before Final Audit | Documents | Organization
Copies of Delivery tickets for Asphalt, Concrete, and Base materials | Before Final Audit | Documents | Organization
Any failing material left in place? How much? | Before Final Audit | Documents | Organization
Corrective Action and Disposition of failing materials. | Before Final Audit | Documents | Organization

## PHASE 54
District 4 Local Program GAP Checklist
GAP Checklist
Agency:
FM Number:
Description:
Phase 54- Items to Upload -Before and During Construction | Upload By | Locations | Responsible
Executed State Grant Agreement (Phase 54) | Upon execution | Tracking | Organization
Executed State Grant Supplemental Agreement (Phase 54) | Upon execution | Tracking | Organization
FDOT Notice to Proceed to Advertise | Upon issuance | Tracking | FDOT
FDOT Concurrence BID Package to Local Agency | Upon issuance | Tracking | FDOT
Final Contract Package executed by LA andCEI Consultant | Prior to Pre-Construction Meeting | Tracking | Organization
Final Signed and Sealed Plans | Prior to Pre-Construction Meeting | Tracking | Organization
Pre-construction Meeting Minutes | After meeting | Tracking | Organization
Progress Meetings Minutes | After each meeting | Documents | Organization
Contractor’s Baseline Construction Schedule(s) | Prior to Pre-Construction Meeting and after Progress Meetings | Documents | Organization
LA Notice to Proceed to Contractor | Upon issuance | Tracking | Organization
Each Change Order with concurrence | As each change order is executed | Documents | Organization
ALL Shop Drawings – Approved | As a complete pdf file | Tracking | Organization
Time File / Cal File (After Final Acceptance) | Upon approval or acceptance by LA | Tracking | Organization
QC Plan | Upon approval or acceptance by LA | Tracking | Organization
Permits | As the final permits have been received | Tracking | Organization
Drill Shaft Installation Plan, Pile Driving Plan, Mix Design | Upon approval or acceptance by LA | Tracking | Organization
Final Request for Reimbursement Invoice with backup | Upon Approval by FDOT | Tracking | Organization
All Project Monthly Status Reports (PMSRs) (Scanned to one) | Before Final Audit | Documents | Organization
All Certification of Payments (700-010-38) (Scanned to one) | Before Final Audit | Documents | Organization
All Final Release of Liens | Before Final Audit | Documents | Organization
Materials Certification Letter from Local Agency | Before Final Audit | Tracking | Organization
Contractors Affidavit and Surety Consent (700-050-21) | Before Final Audit | Documents | Organization
For Project Closeout with Local Agency
Over-run Underrun calculations (if not shown on record of Final Plans) | Before Final Audit | Tracking | Organization
Time/Day Counts (spreadsheet/form) | Before Final Audit | Tracking | Organization
Final Reimbursement* | Before Final Audit | Tracking | Organization
Final Inspection and Acceptance (525-010-42) | Before Final Audit | Tracking | Organization
Engineers Certification of Compliance | Before Final Audit | Tracking | Organization
Materials Certification Statement | Before Final Audit | Tracking | Organization
Certified As-built Plans | Before Final Audit | Tracking | Organization
Material Tests (Not in LIMS) (as a single file) | Before Final Audit | Tracking | Organization
The Quantities (Plan vs. Actual) for Asphalt, Concrete, and Earthwork materials used. | Before Final Audit | Documents | Organization
Copies of the Tests Data | Before Final Audit | Documents | Organization
Copies of Delivery tickets for Asphalt, Concrete, and Base materials | Before Final Audit | Documents | Organization
Any failing material left in place? How much? | Before Final Audit | Documents | Organization
Corrective Action and Disposition of failing materials. | Before Final Audit | Documents | Organization
* Draft Copy of Final Reimbursement must include - Contractor's Affidavit and Surety Consent, Final Release of Lien, All Monthly Progress Reports

## Construction PH 68
District 4 Local Program GAP Checklist
GAP Checklist
Agency:
FM Number:
Description:
Phase 68- Items to Upload -Before and During Construction | Upload By | Locations | Responsible
Executed Local Agency Program (LAP) Agreement (Phase 68) | Upon execution | Tracking | Organization
Executed Local Agency Program (LAP) Supplemental Agreement (Phase 68) | Upon execution | Tracking | Organization
FDOT Notice to Proceed to Advertise | Upon issuance | Tracking | FDOT
FDOT RFQ Concurrence to Local Agency | Upon issuance | Tracking | FDOT
Final Contract Package executed by LA andCEI Consultant | Prior to Pre-Construction Meeting | Tracking | Organization
Final Signed and Sealed Plans | Prior to Pre-Construction Meeting | Tracking | Organization
Pre-construction Meeting Minutes | After meeting | Tracking | Organization
Progress Meetings Minutes | After each meeting | Documents | Organization
Contractor’s Baseline Construction Schedule(s) | Prior to Pre-Construction Meeting and after Progress Meetings | Documents | Organization
LA Notice to Proceed to Contractor | Upon issuance | Tracking | Organization
Each Change Order with concurrence | As each change order is executed | Documents | Organization
Buy America Certification (if applicable) | Prior to completion of project | Tracking | Organization
ALL Shop Drawings – Approved | As a complete pdf file | Tracking | Organization
Time File / Cal File (After Final Acceptance) | Upon approval or acceptance by LA | Tracking | Organization
QC Plan | Upon approval or acceptance by LA | Tracking | Organization
Permits | As the final permits have been received | Tracking | Organization
Drill Shaft Installation Plan, Pile Driving Plan, Mix Design | Upon approval or acceptance by LA | Tracking | Organization
Final Request for Reimbursement Invoice with backup | Upon Approval by FDOT | Tracking | Organization
All Project Monthly Status Reports (PMSRs) (Scanned to one) | Before Final Audit | Documents | Organization
All Certification of Payments (700-010-38) (Scanned to one) | Before Final Audit | Documents | Organization
All Final Release of Liens | Before Final Audit | Documents | Organization
Materials Certification Letter from Local Agency | Before Final Audit | Tracking | Organization
Contractors Affidavit and Surety Consent (700-050-21) | Before Final Audit | Documents | Organization
LAP Oversight: Construction Compliance Audit | Upon Completion of Project | Tracking | FDOT
Performance Evaluation LAP Oversight | Upon Completion of Project | Tracking | FDOT
Project Photos LAP Oversignt | Upon Completion of Project | Tracking | FDOT
For Project Closeout with Local Agency
Record of Final Plans and Documents (525-010-47) | Before Final Audit | Tracking | Organization
Over-run Underrun calculations (if not shown on record of Final Plans) | Before Final Audit | Tracking | Organization
Time/Day Counts (spreadsheet/form) | Before Final Audit | Tracking | Organization
Final Reimbursement* | Before Final Audit | Tracking | Organization
Performance Evaluation Fully Executed | Before Final Audit | Tracking | Organization
Final Inspection and Acceptance (525-010-42) | Before Final Audit | Tracking | Organization
Materials Certification Statement | Before Final Audit | Tracking | Organization
Certified As-built Plans | Before Final Audit | Tracking | Organization
Material Tests (Not in LIMS) (as a single file) | Before Final Audit | Tracking | Organization
The Quantities (Plan vs. Actual) for Asphalt, Concrete, and Earthwork materials used. | Before Final Audit | Documents | Organization
Copies of the Tests Data | Before Final Audit | Documents | Organization
Copies of Delivery tickets for Asphalt, Concrete, and Base materials | Before Final Audit | Documents | Organization
Any failing material left in place? How much? | Before Final Audit | Documents | Organization
Corrective Action and Disposition of failing materials. | Before Final Audit | Documents | Organization
* Draft Copy of Final Reimbursement must include - Contractor's Affidavit and Surety Consent, Final Release of Lien, All Monthly Progress Reports

## Invoices
District 4 Local Program GAP Checklist
GAP Checklist
Agency:
FM Number:
Description:
INVOICES | Upload By | Locations | Responsible
Advertisement Invoice | With in 90 Days of Issuance of NTP to Advertise | Invoices | Organization
Invoices | With in 90 Days of previously submitted invoices | Invoices | Organization

## Documents
District 4 Local Program GAP Checklist
GAP Checklist
Agency:
FM Number:
Description:
DOCUMENTS | Upload By | Locations | Responsible
Progress Meetings Minutes | Monthly - Life of project | Documents | Organization
Contractor’s Baseline Construction Schedule(s) | Prior to Pre-Construction Meeting and after Progress Meetings | Documents | Organization
Each Change Order with concurrence | As each change order is executed | Documents | Organization
The Quantities (Plan vs. Actual) for Asphalt, Concrete, and Earthwork materials used. | Before Final Audit | Documents | Organization
Copies of the Tests Data | Before Final Audit | Documents | Organization
Copies of Delivery tickets for Asphalt, Concrete, and Base materials | Before Final Audit | Documents | Organization
Any failing material left in place? How much? | Before Final Audit | Documents | Organization
Corrective Action and Disposition of failing materials. | Before Final Audit | Documents | Organization
Jobsite Bulletin Board (as per requested by RCS, no less than quarterly) | Monthly - Life of project | Documents | Organization
Progress Monthly Summary Report | Monthly - Life of project | Documents | Organization
Subcontractor(s) Contracts/Purchase Orders/Rental Agreements | Prior to start of work | Documents | Organization
Commerical Useful Function (CUFS) | Monthly -(first 3 months of active work) | Documents | Organization
July Reorts | Before Final Audit | Documents | Organization
Daily Work Reports | Monthly - Life of project | Documents | Organization