## Project Specific Monitoring
Local Agency Program (LAP) Risk Assessment
Subrecipient Monitoring Details
Entity Name:
Project Description: | N/A |  | Current or Estimated Project Funding: | N/A
FPID / Contract No. | N/A |  | Current or Estimated Department Funds Received (all grant programs): | N/A
FAP No. | N/A |  | Fiscal Year(s) of Project Delivery: | N/A
Current Subrecipient Risk Level:
Date of Review:
|  |  | RISK LEVEL | RISK LEVEL
|  |  | (Project Assigned Frequency) | (Minimum Frequency)
# | Monitoring Activities | Description of Activity | (INSERT CURRENT RISK LEVEL)
1 | Invoice Review | Verify that all requested costs identified on the "Local Programs Invoicing Template" have supporting documentation and have been paid for by the Subrecipient. If issues are detected in the randomly selected invoice that are significant, then a site visit may be scheduled to resolve the matter in person. If issues are not adequately resolved, expand invoice review sample to next risk level frequency. Invoicing reviews occurring more often than quarterly will need to be defined in Exhibit A of the LAP Agreement.
2 | Audit Review | Single Audit: Review Subrecipient's single audits (as applicable) in areas such as compliance, financial stability, disclosures of related party transactions, etc. for each year the project remains active.
Period of Performance Date Monitoring: In addition, FDOT may focus on the area of “End Date Monitoring” to help improve project spending by target FHWA end dates.
3 | Review of Programmatic, Performance and Quality Assurance Reports | Review reports submitted by the Subrecipient for programmatic, performance and financial progress and compliance. This will be accounted for in the Subrecipient’s “Project Monitoring Status Report”. Report template will be provided by FDOT.
Review quality assurance reviews, compliance assessments, and other reports performed by external entities for programmatic compliance .
4 | Technical / Training Assistance Requirement | On question #4 of the “LAP Certification Tool”, the Subrecipient agrees to mandatory training requirements for staff performing LAP project delivery.
The Subrecipient may request additional training from FDOT as needed, or when new staff are hired.
At the discretion of the District LAP Administrator and based on prior results, training may also be needed for activities like: how to properly submit an invoice, providing required documentation, delivering proof of payment or understanding eligibility instructions. For SCAT deficiencies, the Subrecipient or the District may request onsite technical assistance by the SCAT Team.
5 | Other Remedies | Identify additional monitoring activities may be performed to ensure compliance. (e.g., in-person interviews, site visits, coordination meetings) Incorporate activities into project agreement as needed.

## Minimum Project Monitoring
Local Agency Program (LAP) Risk Assessment
Subrecipient Monitoring Minimums
*Note: Each activity described below represents a minimum frequency based on risk level and may be required at more frequent intervals at the District LAP Administrator's discretion.
RISK LEVEL
(Minimum Frequency)
# | Monitoring Activities | Description of Activity | Low | Moderate | Elevated | High
1 | Invoice Review | Verify that all requested costs identified on the "Local Programs Invoicing Template" have supporting documentation and have been paid for by the Subrecipient. If issues are detected in the randomly selected invoice that are significant, then a site visit may be scheduled to resolve the matter in person. If issues are not adequately resolved, expand invoice review sample to next risk level frequency. Invoicing reviews occurring more often than quarterly will need to be defined in Exhibit A of the LAP Agreement. | (Annually) | (Quarterly) | (Quartely) | (Monthly)
2 | Audit Review | Single Audit: Review Subrecipient's single audits (as applicable) in areas such as compliance, financial stability, disclosures of related party transactions, etc. for each year the project remains active. | (Annually) | (Annually) | (Annually) | (Annually)
|  | Period of Performance Date Monitoring: In addition, FDOT may focus on the area of “End Date Monitoring” to help improve project spending by target FHWA end dates. | (Bi-annually) | (Quarterly) | (Quarterly) | (Monthly)
3 | Review of Programmatic, Performance and Quality Assurance Reports | Review reports submitted by the Subrecipient for programmatic, performance and financial progress and compliance. This will be accounted for in the Subrecipient’s “Project Monitoring Status Report”. Report template will be provided by FDOT. | (Annually) | (Quarterly) | (Monthly) | (Monthly)
|  | Review quality assurance reviews, compliance assessments, and other reports performed by external entities for programmatic compliance . | As Needed | As Needed | As Needed | As Needed
4 | Technical / Training Assistance Requirement | On question #4 of the “LAP Certification Tool”, the Subrecipient agrees to mandatory training requirements for staff performing LAP project delivery. | Annually | Annually | Annually | Annually
|  | The Subrecipient may request additional training from FDOT as needed, or when new staff are hired. | As Needed | As Needed | As Needed | As Needed
|  | At the discretion of the District LAP Administrator and based on prior results, training may also be needed for activities like: how to properly submit an invoice, providing required documentation, delivering proof of payment or understanding eligibility instructions. | As Needed | As Needed | As Needed | As Needed
5 | Other Remedies | Additional monitoring activities may be performed to ensure compliance. (e.g., in-person interviews, site visits, coordination meetings) | As Needed | As Needed | As Needed | As Needed

## LAP RA Programmatic Calculator
Local Agency Program (LAP) Risk Assessment
Fiscal Year Auditee Summary by Risk Level
Single Audit | 0 |  | High (15-20 points) | Each high risk criterion is equivalent to 4 points.
Program | 0 |  | Elevated (10-15 points) | Each elevated risk criterion is equivalent to 3 points.
Staffing | 0 |  | Moderate (5-10 points) | Each moderate risk criterion is equivalent to 2 points.
Training | 0 |  | Low (0-5 points) | Each low risk criterion is equivalent to 1 point.
SCAT | 0
TOTAL | 0
RISK LEVEL
Instructions: Enter the numerical value (1, 2, 3, or 4) for each category of risk. Points can only be entered for one criterion under each category of risk. Leave those criteria that are not applicable under each category blank
Category | Criteria | Points | Related Tools
Single Audit | 1 point - Clean audit with no findings. FDOT funding was audited as a major program. No prior year items that result in carryforward risk points. |  | FDOT Single Audit Reporting Application (SARA) LAP Certification Tool LAP Invoices
2 points - Prior year management decision. Audit Submitted Late. Biennial auditee. FDOT funding was not audited as a major program. Listed as 'High Risk' by auditor. Findings unrelated to FDOT funding. Unresolved or repeat finding(s) unrelated to FDOT funding. Finding(s) provided in Management Letter related to FDOT funding.
3 points - Exempt from Single Audit Reporting requirements. Federal and/or State financial assistance less than $750,000.
4 points - Non-Compliant auditee in current or prior year. Prior year enforcement action. Going concern identified by the auditor. Finding(s) identified that relate to FDOT funding. A management decision required for these findings. Unresolved or repeat finding(s) related to FDOT funding. *May Include Combinations of Moderate Criteria*
Program | 1 point - Agency delivered a LAP project in the previous three years. Project performance evaluations are above satisfactory (includes invoicing accuracy and frequency). Agency has been subject to a quality assurance review(s) by an external entity in the past three years and was found in compliance with program requirements. |  | LAP Certification Tool LAP Performance Evaluations Quality Assurance Reviews and Reports (FDOT, FHWA, DOJ, etc.)
2 points - Agency delivered a LAP project in the previous three years. Project performance evaluations are satisfactory (includes invoicing accuracy and frequency). Agency has been subject to a quality assurance review(s) by an external entity in the past three years and was found in substantial compliance with program requirements.
3 points - Project performance evaluations are satisfactory, but may be unsatisfactory in 1-2 categories (includes invoicing accuracy and frequency). There is no project history in LAP, but recipient has received other federal funds from the Department (FTA, FAA, etc.) to deliver projects in the last three years. Agency has not been subject to a quality assurance review(s) by an external entity in the past three years.
4 points - Project performance evaluations are unsatisfactory in multiple categories (includes invoicing accuracy and frequency). Agency has not participated in federal programs with the department in the previous three years. Agency has been subject to a quality assurance review(s) by an external entity in the past three years and was found in substantial non-compliance with program requirements and/or funding was removed from past sub-recipient grants awarded by the department.
Staffing | 1 point - Agency has adequate staff, a responsible charge, and sufficient controls for project delivery. |  | SARA LAP Certification Tool LAP Performance Evaluations LAP Invoices LAP Training Certificates Adopted Work Program (project delivery may be considered across all projects funded by the department at the time of assessment)
2 points - Agency staffing may be limited or experiencing recent staff turnover, agency responsible charge is new or inexperienced, but controls for project delivery are sufficient.
3 points - Agency staffing may be limited or lacks LAP project experience, agency responsible charge is new or inexperienced, controls for project delivery are difficult to assess due to lack of program participation.
4 points - Agency staffing is limited and lacks federal project experience, agency responsible charge is new or inexperienced, controls for project delivery are lacking due to absence of program participation or as evidenced by the past project performance evaluation(s).
Training | 1 point - Agency staff attends mandatory training and proactively seeks training for new staff. |  | LAP Certification Tool LAP Sub-recipient Compliance Assessment Tool (SCAT) LAP Performance Evaluations LAP Training Certificates
2 points - Current agency staff attends mandatory training, but new staff requires training.
3 points - Limited staff has attended mandatory training, new staff has not been trained, lack of program participation means staff requires training.
4 points - Limited or no staff has attended mandatory training, new staff has not been trained, agency will not meet the training requirements prior to certification. (Note: training requirements may be fulfilled as courses come available annually or bi-annually. It is not possible to attend all courses required if the agency does not plan ahead for project delivery.)
Subrecipient Compliance Assessment (SCAT - Title VI and ADA) | 1 Point - Agency is "green" and found substantially compliant with ADA, Title VI and other Nondiscrimination Programs. |  | LAP Certification Tool LAP Sub-recipient Compliance Assessment Tool (SCAT) LAP Training Certificates
2 points - Agency is "green" or "yellow" and found substantially compliant with ADA, Title VI and other Nondiscrimination Programs. Yellow rating only requires minor changes to Title VI program for compliance, agency is actively updating information.
3 points - Agency is "yellow". Yellow rating requires changes to Title VI program for compliance. Agency lacks an ADA Transition Plan or has an outdated draft.
4 points - Agency is "yellow". Yellow rating requires major changes to Title VI program for compliance. Agency lacks an ADA Transition Plan and is not actively working on a draft.

## LAP RA Programmatic
Local Agency Program (LAP) Risk Assessment
Assign Risk Level by Cumulative Points
High (15-20 points)
Elevated (10-15 points)
Moderate (5-10 points)
Low (0-5 points)
Risk Level | Criteria | Related Tools
Low 0-5 *Each criterion is equivalent to 1 point | Single Audit: Clean audit with no findings. FDOT funding was audited as a major program. No prior year items that result in carryforward risk points. Program: Agency delivered a LAP project in the previous three years. Project performance evaluations are above satisfactory (includes invoicing accuracy and frequency). Staffing: Agency has adequate staff, a responsible charge, and sufficient controls for project delivery. Training: Agency staff attends mandatory training and proactively seeks training for new staff. SCAT Assessment: Agency is "green" and found substantially compliant with ADA, Title VI and other Nondiscrimination Programs. | SARA LAP Certification Tool LAP Sub-recipient Compliance Assessment Tool (SCAT) LAP Performance Evaluations LAP Invoices LAP Training Certificates
Moderate 5-10 *Each criterion is equivalent to 2 points | Single Audit: Prior year management decision. Audit Submitted Late. Biennial auditee. FDOT funding was not audited as a major program. Listed as 'High Risk' by auditor. Findings unrelated to FDOT funding. Unresolved or repeat finding(s) unrelated to FDOT funding. Finding(s) provided in Management Letter related to FDOT funding. Program: Agency delivered a LAP project in the previous three years. Project performance evaluations are above satisfactory and satisfactory (includes invoicing accuracy and frequency). Staffing: Agency staffing may be limited or experiencing recent staff turnover, agency responsible charge is new or inexperienced, but controls for project delivery are sufficient. Training: Current agency staff attends mandatory training, but new staff requires training. SCAT Assessment: Agency is "green" or "yellow" and found substantially compliant with ADA, Title VI and other Nondiscrimination Programs. Yellow rating only requires minor changes to Title VI program for compliance, agency is actively updating information. | SARA LAP Certification Tool LAP Sub-recipient Compliance Assessment Tool (SCAT) LAP Performance Evaluations LAP Invoices LAP Training Certificates
Elevated 10-15 *Each criterion is equivalent to 3 points | Program: Exempt from Single Audit Reporting requirements. Federal and/or State financial assistance less than $750,000. Program: Project performance evaluations are satisfactory, but may be unsatisfactory in 1-2 categories (includes invoicing accuracy and frequency). There is no project history in LAP, but recipient has received other federal funds from the Department (FTA, FAA, etc.) to deliver projects in the last three years. Staffing: Agency staffing may be limited or lacks LAP project experience, agency responsible charge is new or inexperienced, controls for project delivery are difficult to assess due to lack of program participation. Training: Limited staff has attended mandatory training, new staff has not been trained, lack of program participation means staff requires training. SCAT Assessment: Agency is "yellow". Yellow rating requires changes to Title VI program for compliance. Agency lacks an ADA Transition Plan or has an outdated draft. | SARA LAP Certification Tool LAP Sub-recipient Compliance Assessment Tool (SCAT) LAP Performance Evaluations LAP Invoices LAP Training Certificates
High 15-20 *Each criterion is equivalent to 4 points | Single Audit: Non-Compliant auditee in current or prior year. Prior year enforcement action. Going concern identified by the auditor. Finding(s) identified that relate to FDOT funding. A management decision required for these findings. Unresolved or repeat finding(s) related to FDOT funding. *May Include Combinations of Moderate Criteria* Program: Project performance evaluations are unsatisfactory in multiple categories (includes invoicing accuracy and frequency). Agency has not participated in federal programs with the department in the previous three years. Staffing: Agency staffing is limited and lacks federal project experience, agency responsible charge is new or inexperienced, controls for project delivery are lacking due to absence of program participation or as evidenced by the past project performance evaluation(s). Training: Limited or no staff has attended mandatory training, new staff has not been trained, agency will not meet the training requirements prior to certification. (Note: training requirements may be fulfilled as courses come available annually or bi-annually. It is not possible to attend all courses required if the agency does not plan ahead for project delivery.) SCAT Assessment: Agency is "yellow". Yellow rating requires major changes to Title VI program for compliance. Agency lacks an ADA Transition Plan and is not actively working on a draft. | SARA LAP Certification Tool LAP Sub-recipient Compliance Assessment Tool (SCAT) LAP Performance Evaluations LAP Invoices LAP Training Certificates

## Audit Risk Comptroller
Single Audit Reporting Application (SARA) Risk Assessment
Risk Level | Criteria | Related Checklist Question/Trigger
Low 0 | - Clean audit with no findings. - FDOT funding was audited as a major program. - No prior year items that result in carryforward risk points. | - Questions 14-17, 19 - Question 12 - Determined by the previous year's results.
Moderate 2-12 | - Prior year management decision. - Audit Submitted Late - Biennial auditee - FDOT funding was not audited as a major program. - Listed as 'High Risk' by auditor. - Findings unrelated to FDOT funding. - Unresolved or repeat finding(s) unrelated to FDOT funding. - Finding(s) provided in Management Letter related to FDOT funding. | - Determined by the previous year's results. - Audit received past the 9 month due date. - Auditee Type on checklist. - Question 12 - Question 13 - Questions 14-17,19 - Questions 17, 19 - Question 21
Elevated (Exempt) | - Exempt from Single Audit Reporting requirements. Federal and/or State financial assistance less than $750,000. | - Recipient must submit a Single audit Exemption Letter.
High 14+ | - Non-Compliant auditee in current or prior year. - Prior year enforcement action. - Going concern identified by the auditor. - Finding(s) identified that relate to FDOT funding. A management decision required for these findings. - Unresolved or repeat finding(s) related to FDOT funding. *May Include Combinations of Moderate Criteria* | - Determined by 'Action Type' on profile page. - Question on prior year profile page. - Question 4 - Questions 14-17, 19 - Questions 17, 19
2016 Auditee Summary by Risk Level
High | 77
Moderate | 99
Exempt | 176
Low | 60
2015 Auditee Summary by Risk Level
High | 64
Moderate | 109
Exempt | 114
Low | 73
2014 Auditee Summary by Risk Level
High | 67
Moderate | 85
Exempt | 79
Low | 81

## Major Program Testing By Year
2016 Major Programs Tested
State Program | Number of Occurrences | Federal Program | Number of Occurrences
55.001 - CTD TRIP and Equipment Grant Program | 19 | 20.205 - Local Agency Program (LAP) or Metropolitan Planning Organization (MPO) | 49
55.004 - Aviation Development Grants | 36 | 20.500 - Federal Transit Capital Investment Grants | 5
55.005 - Seaport Grant Program | 4 | 20.505 - Metropolitan Transportation Planning Program | 1
55.007 - Commuter Assistance/Rideshare Grants | 2 | 20.509 - Rural Area Program | 8
55.008 - County Incentive Grant Program (CIGP) | 10 | 20.513 - Enhanced Mobility of Seniors and Individuals with Disabilities | 9
55.009 - Small County Outreach Program (SCOP) | 22 | 20.516 - Job Access and Reverse Commute Program | 3
55.010 - Public Transit Block Grant Program | 15 | 20.521 - New Freedom Program | 1
55.012 - Public Transit Service Development Program | 8 | 20.526 - Bus And Bus Facilities | 9
55.013 - Transit Corridor Program | 5
55.014 - Intermodal Grant Programs | 8
55.016 - Small County Road Assistance Program (SCRAP) | 15
55.020 - State Infrastructure Bank (SIB) | 7
55.021 - Rail Programs: Passenger Development, Capacity or Crossing | 1
55.023 - Florida Landscape Beautification Program | 1
55.026 - Transportation Regional Incentive Program (TRIP) | 13
55.032 - Economic Development Transportation Fund (EDTF) | 6
55.033 - Intermodal Logistics Center Infrastructure Support Program | 1
55.034 - Seaport Investment Program | 2
55.037 - Spaceport Improvement Program | 1
2015 Major Programs Tested
State Program | Number of Occurrences | Federal Program | Number of Occurrences
55.001 - CTD TRIP and Equipment Grant Program | 23 | 20.205 - Local Agency Program (LAP) or Metropolitan Planning Organization (MPO) | 51
55.003 - Keep Florida Beautiful | 1 | 20.500 - Federal Transit Capital Investment Grants | 2
55.004 - Aviation Development Grants | 35 | 20.505 - Metropolitan Transportation Planning Program | 4
55.005 - Seaport Grant Program | 7 | 20.507 - Federal Transit Formula Grant Program | 2
55.007 - Commuter Assistance/Rideshare Grants | 3 | 20.509 - Rural Area Program | 7
55.008 - County Incentive Grant Program (CIGP) | 12 | 20.513 - Enhanced Mobility of Seniors and Individuals with Disabilities | 7
55.009 - Small County Outreach Program (SCOP) | 23 | 20.516 - Job Access and Reverse Commute Program | 3
55.010 - Public Transit Block Grant Program | 18 | 20.521 - New Freedom Program | 4
55.011 - Park and Ride Lot Program | 2 | 20.526 - Bus And Bus Facilities | 4
55.012 - Public Transit Service Development Program | 7 | 20.616 - National Priority Safety Program | 3
55.013 - Transit Corridor Program | 8
55.014 - Intermodal Grant Programs | 5
55.016 - Small County Road Assistance Program (SCRAP) | 18
55.017 - New Starts Transit Program (Rescinded) | 1
55.018 - SFRTA Operating Assistance Program | 1
55.020 - State Infrastructure Bank (SIB) | 6
55.021 - Rail Programs: Passenger Development, Capacity or Crossing | 3
55.023 - Florida Landscape Beautification Program | 3
55.026 - Transportation Regional Incentive Program (TRIP) | 11
55.029 - Transportation Infrastructure Pilot Program | 1
55.032 - Economic Development Transportation Fund (EDTF) | 8
55.033 - Intermodal Logistics Center Infrastructure Support Program | 2
55.034 - Seaport Investment Program | 2
55.036 - Alligator Alley Mile Marker 63 Fire Station | 1
2014 Major Programs Tested
State Program | Occurrences | Federal Program | Occurrences
55.001 - CTD TRIP and Equipment Grant Program | 23 | 20.106 - Airport Improvement Program | 1
55.003 - Keep Florida Beautiful | 1 | 20.205 - Local Agency Program (LAP) or Metropolitan Planning Organization (MPO) | 58
55.004 - Aviation Development Grants | 34 | 20.505 - Metropolitan Transportation Planning Program | 4
55.005 - Seaport Grant Program | 9 | 20.509 - Rural Area Program | 9
55.007 - Commuter Assistance/Rideshare Grants | 2 | 20.513 - Enhanced Mobility of Seniors and Individuals with Disabilities | 4
55.008 - County Incentive Grant Program (CIGP) | 12 | 20.516 - Job Access and Reverse Commute Program | 4
55.009 - Small County Outreach Program (SCOP) | 20 | 20.521 - New Freedom Program | 2
55.010 - Public Transit Block Grant Program | 21 | 20.616 - National Priority Safety Program | 1
55.012 - Public Transit Service Development Program | 5
55.013 - Transit Corridor Program | 7
55.014 - Intermodal Grant Program | 4
55.016 - Small County Road Assistance Program (SCRAP) | 16
55.017 - New Starts Transit Program (Rescinded) | 1
55.018 - SFRTA Operating Assistance Program | 1
55.020 - State Infrastructure Bank (SIB) | 6
55.021 - Rail Programs: Passenger Development, Capacity or Crossing | 1
55.023 - Florida Landscape Beautification Program | 3
55.026 - Transportation Regional Incentive Program (TRIP) | 9
55.029 - Transportation Infrastructure Pilot Program | 2
55.030 - Gainesville RTS Comprehensive Operational Analysis | 1
55.031 - Mitigation Water Management Districts | 1
55.032 - Economic Development Transportation Fund (EDTF) | 9
55.033 - Intermodal Logistics Center Infrastructure Support Program | 1
55.034 - Seaport Investment Program | 5

## Alerts
Single Audit Reporting Application (SARA) Alerts
Prior Year Risks Alerts | Risk Points
Prior Year Exemption/Audit Report Received Late | 0
Prior Year Management Decision Issued | 0
Prior Year Recommended Enforcement Action | 0
Prior Year FDOT Funding Not Audited as Major Program/Project | 0
Current Year Risks Alerts
Exemption/Audit Report Received Late
Current Year Findings and/or Questioned Costs Recorded
Management Decision Required

## Guiding Statutes
2 CFR Section § 200.518 Major program determination. (FEDERAL)
Total Federal awards expended | Type A/B threshold
Equal to or exceed $750,000 but less than or equal to $25 million. | 750000
Exceed $25 million but less than or equal to $100 million. | Total Federal awards expended times .03.
Exceed $100 million but less than or equal to $1 billion. | $3 million.
Exceed $1 billion but less than or equal to $10 billion. | Total Federal awards expended times .003.
Exceed $10 billion but less than or equal to $20 billion. | $30 million.
Exceed $20 billion ................. | Total Federal awards expended times .0015.
2 CFR Section § 200.520 Criteria for a low-risk auditee.
An auditee that meets all of the following conditions for each of the preceding two audit periods must qualify as a low-risk auditee and be eligible for reduced audit coverage in accordance with §200.518 Major program determination. (a) Single audits were performed on an annual basis in accordance with the provisions of this Subpart, including submitting the data collection form and the reporting package to the FAC within the timeframe specified in §200.512 Report submission. A non-Federal entity that has biennial audits does not qualify as a low-risk auditee. (b) The auditor’s opinion on whether the financial statements were prepared in accordance with GAAP, or a basis of accounting required by state law, and the auditor’s in relation to opinion on the schedule of expenditures of Federal awards were unmodified. (c) There were no deficiencies in internal control which were identified as material weaknesses under the requirements of GAGAS. (d) The auditor did not report a substantial doubt about the auditee’s ability to continue as a going concern. (e) None of the Federal programs had audit findings from any of the following in either of the preceding two audit periods in which they were classified as Type A programs: (1) Internal control deficiencies that were identified as material weaknesses in the auditor’s report on internal control for major programs as required under §200.515 Audit reporting, paragraph (c); (2) A modified opinion on a major program in the auditor’s report on major programs as required under §200.515 Audit reporting, paragraph (c); or (3) Known or likely questioned costs that exceeded five percent of the total Federal awards expended for a Type A program during the audit period.
DFS Rule 69I-5.008 Criteria for Identifying Major State Projects
Total State awards expended | Type A/B threshold
For auditees with expenditures of state awards between $300,000 and $1,000,000 | the larger of $100,000 or thirty percent (30%) of total state awards expended
For auditees with expenditures of state awards exceeding $1,000,000 | the larger of $300,000 or three percent (3%) of total state awards expended
(1) The independent auditor shall use a risk-based approach to determine which state projects are major state projects. This risk-based approach shall include consideration of the amount of state project expenditures and the inherent risk of the state project. The process enumerated in subsections (2) through (6) shall be followed. (2) The independent auditor shall identify the larger state projects as Type A Projects according to the following criteria: (a) For auditees with expenditures of state awards between $300,000 and $1,000,000, Type A Projects are defined as the larger of $100,000 or thirty percent (30%) of total state awards expended. (b) For auditees with expenditures of state awards exceeding $1,000,000, Type A Projects are defined as the larger of $300,000 or three percent (3%) of total state awards expended. (3) State projects not identified as Type A Projects shall be considered Type B Projects. (4) The independent auditor shall identify Type A Projects which are low-risk. For a Type A Project to be considered low-risk, it should have been audited as a major state project in at least one of the two most recent audit periods and, in the most recent audit period, it should have had no reportable audit findings. The auditor shall consider the criteria enumerated in Rule 69I-5.009, F.A.C., the results of audit follow-up, and any significant changes in personnel or systems affecting a Type A Project, in applying professional judgment in determining whether a Type A Project is low-risk. (5) The independent auditor shall identify Type B Projects which are high-risk. The auditor shall consider the criteria enumerated in Rule 69I-5.009, F.A.C., in applying professional judgment in determining whether a Type B Project is high-risk. However, the independent auditor is not expected to perform risk assessments on relatively small state projects. Therefore, the auditor is only required to perform risk assessments on Type B Projects as follows: (a) For auditees with expenditures of state awards of $300,000 to $1,000,000, risk assessments shall be required for Type B Projects that exceed the larger of $50,000 or ten percent (10%) of total state awards expended. (b) For auditees with expenditures of state awards that exceed $1,000,000, risk assessments shall be required for Type B Projects that exceed the larger of $100,000 or one percent (1%) of total state awards expended. (6) At a minimum, the independent auditor shall audit all of the following as major projects: (a) All Type A Projects, except the auditor may exclude any low-risk Type A Projects. (b) At least one half of the Type B Projects identified as high-risk, except the auditor is not required to audit more high-risk Type B Projects than the number of low-risk Type A Projects; or one high-risk Type B Project for each low-risk Type A Project identified. The auditor is encouraged to use an approach which provides an opportunity for different high-risk Type B Projects to be audited as a major project over a period of time. (c) Additional projects as may be necessary to provide audit coverage of at least fifty percent (50%) of the auditee’s expenditures of state awards. Wherever practicable, additional projects should be selected in accordance with the criteria enumerated in Rule 69I-5.009, F.A.C.
DFS Rule 69I-5.009 Criteria for Selecting State Projects for Audits Based on Inherent Risk
(1) The independent auditor’s selection of state projects for audit shall be based on an overall analysis and evaluation of the risk of noncompliance occurring which could be material to the state project. The auditor shall use professional judgment and consider criteria, such as described in subsections (2) through (4) below, to identify risk in state projects. Also, as part of the risk analysis, the auditor may wish to discuss a particular state project with auditee management and the awarding state agency. (2) The independent auditor shall consider current and prior audit experience. (a) Weakness in internal controls over state financial assistance would indicate higher risk. Consideration should be given to the control environment over state financial assistance and such factors as the expectation of management’s adherence to applicable laws, rules, and contract/grant provisions, and the competence and experience of personnel who administer the state financial assistance project. (b) Prior audit findings would indicate higher risk, particularly when situations identified in the audit finding could have a significant impact on state financial assistance or have not been corrected. (c) State projects not recently audited as major state projects may be of higher risk than state projects recently audited as major state projects without audit findings. (3) The independent auditor shall consider the extent of any oversight exercised by the state agencies and the results of any monitoring performed. (4) When evaluating state projects, independent auditors shall consider the inherent risk of the project, which includes the following: (a) The nature of the project. This includes, for example, a project’s complexity, the presence of third parties, and the type of costs involved. (b) The phase of the project in its life cycle at the state agency. A new project may not be as time-tested and, therefore, may present higher risk. The state agency’s monitoring procedures may not yet be implemented or effectively in place. Significant changes in the program, laws, rules, or contracts or grant agreements may also increase risk. (c) The phase of the project in its life cycle at the auditee. If a project is new to the auditee, there may be higher risk simply because a learning curve may be present. During the first and last years that an auditee participates in a state project, the risk may be higher due to start-up or closeout of program activities and staff. (d) Type B Projects with larger expenditures. Projects with larger amounts of expenditures would be of higher risk than projects with substantially smaller expenditures. (5) The independent auditor shall document in the working papers the risk analysis process used in determining major projects. State agencies may provide auditors guidance about the risk of a particular state project and the auditor shall consider this guidance in determining major projects in audits not yet substantially completed.