## DROP DOWN (hidden)
Project Type
SELECT
Off SHS
On SHS
Critial Project (Structural Elements)
Select Status
Completed
Pending
N/A
Select Project Type
Class A – On the SHS or NHS
Class B – Off the SHS and NHS with an estimated construction value of $10 million or greater.
Class C – Off the SHS and NHS and includes structural components inclusive of a vehicular bridge, a pedestrian bridge over a roadway, or a box culvert that meets the definition of a bridge.
Class D – Off the SHS and NHS; may include structural components inclusive of pedestrian bridges not over a roadway, bridges on multi-use paths not over a roadway, and box culverts that do not meet the definition of a bridge.
Select Type
In-House
Consultant

## PHASE CHECKLIST
LAP MASTER PHASE SUBMITTAL CHECKLIST FDOT District Four |  |  |  |  | Instructions of use: The Phase Checklist tab is the Dashboard for all phase submittal checklist. This tab has resource links that will assist in completing the phase submittals on the other tabs. -Phase Checklist Dashboard- Complete the sections highlighted in yellow. -Preliminary, Initial, Constructability Checklists - Use the dropdown to select status of items being submitted and complete any sections highlighted in yellow, as requiered. -Production Checklist- Use the dropdown to select status of items being submitted and provide dates of submitted items. Upons completion of all phase submittals the Local Programs Coordinator will provice a signed approval of the accepted submittals. Per the Schedule below, please complete each phase submittal tab, save file and submit with required documents for each applicable phase. Upon completion of production the phase checklists will be approved and returned to the agency for its records (pdf version). Upon Completion of the phase submittal form, please contact your Local Program Coordinator to provide a link to FDOT's FTP Site to upload all document for the phase submittal and the checklist.
Financial Project No: |  |  | Type Project Number in yellow box è
Project Description: |  |  | Type Project Number in yello box è
Project Type (select in drop down) |  |  |  | SELECT
Submitted Date |  | 0 | Status | Resources / Instructions | Activity Name | Duration | Scheduled Submittal Date | Actual Submitted Date
Preliminary Phase Submittal | Requirements |  |  |  | Agency Submits Preliminary Phase
| Project Scope |  | Select Status | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/designsupport/districts/d4lap/projectmanagementanddistrictresources/scope-of-work.pdf? | FDOT Kickoff meeting to discuss Environmental and/or ROW requirements for this project only (optional meeting)
| Project Class (Reference Local Program Manual / 17.4 PRELIMINARY ENGINEERING DESIGN) |  | Select Status | https://www.fdot.gov/programmanagement/lap/lap-toc.shtm | Agency Submits Initial Phase
| Location Map |  | Select Status | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/designsupport/districts/d4lap/projectmanagementanddistrictresources/location-map-example.pdf? | Agency Submits Environmental Draft Documents
| Preliminary Engineer's Estimate (Reference Local Program Manual / 20.4 ESTIMATES) |  | Select Status | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/designsupport/districts/d4lap/projectmanagementanddistrictresources/engineers-cost-estimate-template-01-13-16.pdf? | Agency Submits Constructability Phase
|  |  |  | https://www.fdot.gov/programmanagement/lap/lap-toc.shtm | Agency Submits Production Phase
| Engineer's Estimate Required Signatures |  | Select Status | Must be signed & sealed, dated for preparation, review and approval (Agency Responsible Charge). | FDOT Sends LAP Agreement to Agency
| Design - In house or consultant |  | Select Status | Select Type | Agency returns LAP Agreement for execution
| CEI - In house or consultant |  | Select Status | Reimbursed- CEI Services (in house or Consultant) must provide man-hour estimate | FDOT Encumbrance (LAP Commitment)
| Environmental Consultant |  | Select Status | Date acquired _________________________ | FDOT Issues NTP to Agency
| LAP Certification |  | Select Status | https://www.fdot.gov/designsupport/districts/d4lap/resources
Date Uploaded to GAP ______________________
Submitted Date |  | 0 | Status | Resources / Instructions Click on Links
Initial Phase Submittal | Requirements
| Initial Plans (30%) Florida Design Manual Florida Greenbook- |  | Select Status | https://www.fdot.gov/roadway/fdm/2021-FDM.shtm
https://www.fdot.gov/roadway/floridagreenbook/fgb.shtm
| Proprietary Products |  | Select Status | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/programmanagement/packagepreparation/writingaids/proprietaryproductcertificationdocument.pdf?sfvrsn=c7e00c5f_2
https://transportationsymposium.fdot.gov/User/ClassPresentation?classFileName=2019%20Symposium%20-%20ByramMoyle%20-%20PropProducts.pdf
| Engineer’s Estimate (30%) |  | Select Status | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/designsupport/districts/d4lap/projectmanagementanddistrictresources/engineers-cost-estimate-template-01-13-16.pdf?
https://www.fdot.gov/programmanagement/lap/lap-toc.shtm
| Environmental |  | Select Status | D4 LAP Resources (fdot.gov)
| Right of Way |  | Select Status | D4 LAP Resources (fdot.gov)
Submitted Date |  | 0 | Status | Resources / Instructions
Constructability Phase Submittal | Requirements
| Constructability Plans (90%) Florida Design Manual Florida Greenbook- |  | Select Status | https://www.fdot.gov/roadway/fdm/2021-FDM.shtm
|  |  | Select Status | https://www.fdot.gov/roadway/floridagreenbook/fgb.shtm
| Proprietary Products |  | Select Status | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/programmanagement/packagepreparation/writingaids/proprietaryproductcertificationdocument.pdf?sfvrsn=c7e00c5f_2
https://fdotwp1.dot.state.fl.us/ApprovedProductList/Specifications
| Engineer’s Estimate (100%) |  | Select Status | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/designsupport/districts/d4lap/projectmanagementanddistrictresources/engineers-cost-estimate-template-01-13-16.pdf?
| *Environmental |  | Select Status | D4 LAP Resources (fdot.gov)
| Right of Way |  | Select Status | D4 LAP Resources (fdot.gov)
| 100% Bid/Contract Document with Federal Provisions |  | Select Status | SAM.gov ¦ Home
| Design Reports (On System Only) 'FDM, Chapter 306 Rigid and Flexible Pavement Design Manuals. LP Manual, Chapter 17.5 FDM, Chapter 122 LP Manual, Chapter 17.5 FDM, Chapter 122 |  | Select Status | https://www.fdot.gov/programmanagement/lap/lap-toc.shtm
https://www.fdot.gov/roadway/fdm/2021-FDM.shtm
https://www.fdot.gov/roadway/floridagreenbook/fgb.shtm
| Design Exceptions/Variations -LP Manual, Chapter 17.5 - FDM, Chapter 122 |  | Select Status | https://www.fdot.gov/programmanagement/lap/lap-toc.shtm
2022fdm122varexcept.pdf (windows.net)
| Utilities Documentation of Utility Coordination |  | Select Status | LAP Forms (fdot.gov)
| Railroad |  | Select Status | LAP Forms (fdot.gov)
| Signal Interconnect Coordination (BROWARD COUNTY ONLY) |  | Select Status | n/a
| Bridge Plans (if applicable) 'FDOT Structures Manual, Vol 1, Structures Design Guidelines Chapter 8.3 Bridge Hydraulics Report/Bridge Development Report FDOT Structures Manual, Vol 1, Structures Design Guidelines Chapter 3.2 Soils & Foundations Handbook. FDOT Bridge Load Rating Manual Manual for Condition Evaluation and Load and Resistance Factor Rating (LRFR) of Highway Bridges |  | Select Status | https://www.fdot.gov/structures/docsandpubs.shtm
|  |  | Select Status | https://www.fdot.gov/materials/administration/resources/library/publications/materialsmanual/default.shtm
|  |  | Select Status | https://www.fdot.gov/maintenance/loadrating.shtm
|  |  | Select Status | https://www.fdot.gov/roadway/drainage/design-guide
Submitted Date |  | 0 | Status | Date Approved
Production Phase Submittal | Requirements
| Final Construction Plans (Signed and Sealed ) |  | Select Status | 0
| Proprietary Products (Approved) |  | Select Status | 0
| Final Engineer’s Estimate (Signed and Sealed ) |  | Select Status | 0
| Technical Specifications (Signed and Sealed) |  | Select Status | 0
| Right of Way Approved - FDOT ROW No Additional ROW Certification Form Approved - FDOT ROW Certification Form |  | Select Status | 0
| Approved Applicable Permits( Use Agency Letterhead) Railroad Clear letter Environmental No Permits or Permits Obtained Letter Utilities Clear Letter |  | Select Status | 0
| Environmental Approved Environmental Checklist and Memo Approved Permits, Survey's (If applicable) |  | Select Status | 0
| Outdoor Advertisement Clear letter (project on SHS) |  | Select Status | 0
| Approved Typical Section Package (project on the SHS) |  | Select Status | 0
| ERC Comments addressed/closed |  | Select Status | 0
| FDOT Coordinator Signature |  |  | DATE


## Preliminary
LAP PRELIMINARY PHASE SUBMITTAL CHECKLIST
FDOT District Four
Financial Project No: |  |  | 0
Project Description: |  |  | 0
Project Type |  |  | SELECT
Preliminary Phase Submittal | Requirements | Status | Notes
| Project Scope | Select Status
| Project Class - Select | Select Status | Select Project Type
| Location Map | Select Status
| Preliminary Engineer's Estimate | Select Status
| Engineer's Estimate Required Signatures | Select Status
| Design- In house or consultant | Select Status | Select Type
| CEI - In house or consultant Reimbursed- CEI Services (in house or Consultant) must provide man-hour estimate | Select Status | Select Type
| Environmental in house or Consultant | Select Status | Date acquired _________________________
| LAP Certification | Select Status | FDOT Sub-Recipient Compliance Assessment Certification Tool Title VI Non-Discrimination Assurance Title VI Policy & Plan Organizational Chart Resumes Computer Based Training
* According to Adopted Project Schedule
Upon Completion of form, please contact your Local Program Coordinator to provide link to FDOT's FTP Site to upload all document for the phase submittal and checklist
Name of Agency Responsible Charge |  |  | Submittal Date
FDOT Coordinator Signature |  |  | Coord. Approval Date

## Initial
LAP INITAL PHASE SUBMITTAL CHECKLIST
FDOT District Four
Financial Project No: |  |  | 0
Project Description: |  |  | 0
Project Type |  |  | SELECT
Initial Phase Submittal | Requirements |  | Notes:
| Initial Plans 30% | Select Status | ON –SHS: Comply with FDOT Design Manual & FDOT Standard Plans for Road and Bridge Construction Bridge projects, include BDR/30% Structural Plans per FDM Chapter 120 Landscaping project use FDM Chapter 228 Transit facilities projects: Use FDOT District 4 Transit Facilities Design Guidelines. OFF – SHS (Local Roads): Florida Greenbook Required for all Plans Submittals: Include FM # on Key Sheet Design Speed on Typical Section. ROW line to labeled on all plan sheets.
| Proprietary Products | Select Status | List if Applicable:
| *Engineer’s Estimate (30%) | Select Status | FDOT recommendation to use Department pay items REQUIRED Signatures on bottom right of Engineer’s Cost Estimate must be signed and dated for: 1) Preparation 2) Review 3) Approval (Agency Responsible Charge)
| *Environmental | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Include FM Number and Project Name on Report Cover.
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Cultural Resource Assessment Survey (CRAS) Report, Ensure the CRAS checklist is completed as well
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress Wildlife Study Report or Natural Resource Evaluation (NRE)
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Wetland Survey Report or NRE (can include Bonneted Bat Survey results)
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Section 4(f) Forms (No Use, Exception/Exemption)
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Bridge Asbestos Report/Lead Based Paint Report
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Include Level I and II Contamination Assessment Report
|  | Select Status | Acknowledgement that the LAP Environmental Request for Review Memo was provided to both the LAP agency and Design Consultant. CE1 Memo provided to LA on : ______________________________
|  | Select Status | Acknowledgement that the Public has been notified of the project - What methods of communication was used?________________________
| Right of Way | Select Status | LAP Manual, Chapter 12 Make sure ROW is labeled on plans ROW Documents to be signed by Department Head or other higher-level agency official who has authority to obligate and bind the Agency
* According to Adopted Project Schedule
Upon Completion of form, please contact your Local Program Coordinator to provide link to FDOT's FTP Site to upload all document for the phase submittal and checklist
Name of Agency Responsible Charge |  |  | Submittal Date
FDOT Coordinator Signature |  |  | Coord. Approval Date

## Constructability
LAP CONSTRUCTABILITY PHASE SUBMITTAL CHECKLIST
FDOT District Four
Financial Project No: |  |  | 0
Project Description: |  |  | 0
Project Type |  |  | SELECT
Constuctability Phase Submittal | Requirements | Status | Notes
| Constructability Plans 90% | Select Status | ON –SHS: Comply with FDOT Design Manual & FDOT Standard Plans for Road and Bridge Construction For landscaping projects: Use FDM Chapter 228 Transit facilities projects: Use FDOT District 4 Transit Facilities Design Guidelines. ALL projects : See LP Manual, Chapter 17.4 for other Design Criteria and Manuals. See FDM, Chapter 301 for plans submittal requirements. Include FM # on Key Sheet and year of design standards used. Include backup quantities Traffic Control Plans (TCP) SUE’s (If Applicable) add the following notes to the General Notes: Contamination notes (located in the LAP Environmental Request for Review Memo) All work for this project will be completed within and from the existing right of way.
| Proprietary Products | Select Status | List if Applicable:
| *Engineer’s Estimate (100%) | Select Status | FDOT recommendation to use Department pay items REQUIRED Signatures on bottom right of Engineer’s Cost Estimate must be sealed and dated for: 1) Preparation 2) Review 3) Approval (Agency Responsible Charge)
| *Environmental | Select Status | Refer to the D4 LAP Website and the LAP Environmental Request for Review Memorandum for additional guidance on the Type I CE checklist and Back-up Memorandum including supplemental documents that have been approved by external agencies (as attachments). (See Phase Checklist for Links to Resources)
|  | Select Status | Acknowledgement that the LAP Environmental Request for Review Memo was provided to both the LAP agency and Design Consultant. CE1 Memo provided to LA on ____________
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Cultural Resource Assessment Survey (CRAS) Report
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress Wildlife Study Report or Natural Resource Evaluation (NRE)
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Wetland Survey Report or NRE (can include Bonneted Bat Survey results)
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Section 4(f) Forms (No Use, Exception/Exemption)
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Bridge Asbestos Report/Lead Based Paint Report
|  | Select Status | Select Staus for document(s) provided with submittal, or document progress made on report(s) preparation): Include Level I and II Contamination Assessment Report
|  | Select Status | Clear Letters - Permits Required or No Permits Required Draft Letter
| 100% Bid/Contract Document with Federal Provisions | Select Status | ON SHS/ Critical Projects: FDOT will prepare Division 2 and 3 of contract documents. The Agency can use its own Division I; some required language must be included. On-System LAP Specifications Guidelines OFF SHS Agency can use their own technical specifications but must include: Earthwork, Concrete, and Asphalt (LAP BIG 3). Bid Tab and label Bid/Contract documents Include the Federal Required Contract Provisions Searchable PDF Document Updated Wage Rate Tables Retainage: 5% Requirement (Refer to Fed Provision) Signed Federal Requirements LAP Checklist for Construction Contracts (LP Manual, Chapter 21 Include page numbers under “Requirement Location” for reference in checklist).
| Right of Way | Select Status | LAP Manual, Chapter 19 Make sure ROW is labeled on plans ROW Documents to be signed by Department Head or other higher-level agency official who has authority to obligate and bind the Agency LAP/FDOT No Additional Right of Way Certification Form & LAP/FDOT Right of Way Certification Form (Form # 575-095-05c)
| Design Reports On System Projects Only | Select Status | Typical Section Package - FDM, Chapter 306
|  | Select Status | Pavement Design Package - Rigid and Flexible Pavement Design Manuals.
|  | Select Status | Access Management Plan - The Median Handbook / Driveway Handbook
|  | Select Status | Roadway Lighting Justification Report - AASHTO Roadway Lighting Design Guide / FDM, Chapter 231.4
| Design Exceptions/Variations | Select Status | Design Exceptions/Variations - LP Manual, Chapter 17.5, FDM, Chapter 122
| Utilities Documentation of Utility Coordination | Select Status | Correspondence with Utility Agency. Approved Utility Exceptions (If Applicable) Clear Letter - Utilities
| Railroad | Select Status | This project crosses or is adjacent to RR Right-of-Way Correspondence with Railroad Company or FDOT Rail Coordinator. Clear Letter- Railroad
| Signal Interconnect Coordination | Select Status | Applies to Agencies in Broward County: Coordination with Broward County Traffic Engineering Division required for signal interconnects.
| Bridge Plans (if applicable) | Select Status | Design Calculations FDOT Structures Manual, Vol 1, Structures Design Guidelines Chapter 8.3
|  | Select Status | BHR/BDR Bridge Hydraulics Report/Bridge Development Report
|  | Select Status | Soil or foundation Reports FDOT Structures Manual, Vol 1, Structures Design Guidelines Chapter 3.2 Soils & Foundations Handbook.
|  | Select Status | Bridge Load Rating FDOT Bridge Load Rating Manual Manual for Condition Evaluation and Load and Resistance Factor Rating (LRFR) of Highway Bridges
* According to Adopted Project Schedule
Upon Completion of form, please contact your Local Program Coordinator to provide link to FDOT's FTP Site to upload all document for the phase submittal and checklist
Name of Agency Responsible Charge |  |  | Submittal Date
FDOT Coordinator Signature |  |  | Coord. Approval Date

## Production
LAP PRODUCTION PHASE SUBMITTAL CHECKLIST
FDOT District Four
Financial Project No: |  | 0
Project Description: |  | 0
Project Type |  |  | SELECT
Production Phase Submittal | Requirements | Date Recieved | Status | Date Approved
| Final Construction Plans (Signed and Sealed ) |  | Select Status
| Proprietary Products (Approved) |  | Select Status
| Final Engineer’s Estimate (Signed and Sealed ) |  | Select Status
| Technical Specifications (Signed and Sealed) |  | Select Status
| Right of Way Approved - FDOT ROW No Additional ROW Certification Form Approved - FDOT ROW Certification Form |  | Select Status
| Approved Applicable Permits( Use Agency Letterhead) Railroad Clearletter Environmental No Permits or Permits Obtained Letter Utilities Clear Letter |  | Select Status
| Environmental Approved Environmental Checklist and Memo Approved Permits, Survey's (If applicable) |  | Select Status
| Outdoor Advertisement Clear letter (project on SHS) |  | Select Status
| Approved Typical Section Package (project on the SHS) |  | Select Status
| ERC Comments addressed/closed |  | Select Status
Upon Completion of form, please contact your Local Program Coordinator to provide link to FDOT's FTP Site to upload all document for the phase submittal and checklist.
Agency Responsible Charge Signature |  |  | Submittal Date
FDOT Coordinator Signature |  |  | Coord. Approval Date