## Complexity Guidelines
DRIVE COMPLEXITY GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual tasks on typical projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project. Hours below or above the presented ranges may be applicable based on the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiating hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
The following are general examples of the types of projects within the different complexity levels. This list is not all-inclusive, or always exact, but will provide the basis for beginning estimation and negotiation of staff hours for a project.
Simple Projects
· Rural 2-lane resurfacing (with no 3R improvements).
· Sidewalk project with no utility involvement.
· Minor bridge repair projects (painting or caulking) with no utility involvement.
· Multi-lane limited access resurfacing (no interchange involvement).
· Rural 3R (minor safety improvements)
· Rural Signalization
· Multi-lane limited access resurfacing (safety, earthwork, and minor intersection involvement).
· Intersection improvements without lane additions or signalization
Standard Projects
· Rural 3R (major safety, minor earthwork, realigning ditches).
· Urban 3R (safety, no change to profile grade line, utility exception granted).
· Rural widening/resurfacing (minor ROW and earthwork).
· Urban Signalization with utility impact.
· Intersection improvements with lane additions and signalization.
Complex Projects
· Urban 3R (major safety, extensive above ground feature relocation).
· Rural 2-lane new construction (new alignment, ROW, and earthwork).
· Rural 2-lane to urban multi-lane reconstruction (ROW and intersection involvement).
· Rural or urban 4-lane to 6-lane widening/resurfacing (widening in median, minor ROW, earthwork, and intersection involvement).
· Urban Multi-intersection Signalization with utility impact.
· Rural multi-lane new construction (new alignment, ROW, earthwork and intersection involvement).
· Rural 2-lane to 4-lane (major ROW and earthwork).
· Multi-lane limited access reconstruction (ROW and interchange involvement).
· Multi-lane rural limited access new construction (new alignment, ROW and interchange construction).
· Urban multi-lane new construction (new alignment, ROW and intersection construction).
· Multi-lane limited access, urban reconstruction or new alignment with major interchange involvement (major ROW and interchange
construction, major access management impacts).
· Multi-lane Urban limited access new construction (new alignment, major ROW and, major interchange involvement).

## DRIVE
|  |  | DRIVE D/C Team A TWO Staff Hour Estimation Worksheet | [6 empty] | Enter project name & description
|  |  | Print Name | [6 empty] | Signature / Date
FDOT District
Consultant Name
FPID #
Contract #
TWO #
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Guidelines | Comments | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated |  | Provide documentation when negotiated hours differ from the calculated hours. |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
What is the overall project complexity?
DRN02-001 | 1.1 | DRIVE D/C Cost Savings Strategies Review | Review EA | 1 |  | 0 | 0 | 0 | 0 | Based on 15 to 25 hours per review. 1.1.1.1. Collaborate with District and Team B for cost-savings strategies and data 1.1.1.2. Evaluate existing scope of services and project details. 1.1.1.3. Evaluate and review costs-savings strategies. 1.1.1.4. Independently validate the cost-savings strategies. 1.1.1.5. Document any discrepancies with the proposed savings. 1.1.1.6. Summarize and recommend cost saving strategies to be incorporated in final project scope. |  | 1.1 | [5 empty] | 15 | 20 | 25
|  |  | Report EA | 1 |  | 0 | 0 | 0 | 0 | Based on 6 to 14 hours per report. 1.1.2.1. A comprehensive summary of cost-savings strategies, including any identified special requirements. 1.1.2.2. Documentation of discrepancies. | [7 empty] | 6 | 10 | 14
DRN02-002 | 1.2 | Establish the Baseline | Meeting EA | 1 |  | 0 | 0 | 0 | 0 | Based on 15 to 25 hours per meeting. 1.2.1.1. Facilitation and coordination of DRIVE-D/C Partnership meeting with District and Team B. 1.2.1.2. Document meeting discussion and decisions. 1.2.1.3. Assess modifications to determine project feasibility. 1.2.1.4. Coordinate follow-up meetings, if needed. 1.2.1.5. Memorialize project Baseline (scope and project cost). |  | 1.2 | [5 empty] | 15 | 20 | 25
|  |  | Report EA | 1 |  | 0 | 0 | 0 | 0 | Based on 6 to 14 hours per report. 1.2.2.1 Final Documentation to memorialize the Baseline (scope and project cost) Note: Send to Forecasting and Performance Office | [7 empty] | 6 | 10 | 14
DRN02-003 | 1.3 | Baseline Management | Meeting EA | 3 |  | 24 | 0 | 0 | 0 | Based on 8 hours per meeting. (Typically 3 milestone meetings.) 1.3.1.1. Facilitation and coordination of DRIVE-D/C meeting with District and Team B at project milestones. 1.3.1.2. Evaluate additional innovations and cost savings strategies developed by teams. 1.3.1.3. Document meeting discussion and decisions. 1.3.1.4. Document Baseline modifications. |  | 1.3 | [8 empty] | 8
DRN02-004 |  |  | Report EA | 1 |  | 0 | 0 | 0 | 0 | Based on 2 to 6 hours per report 1.3.2.1. Summary of Innovations and cost savings Strategies. 1.3.2.2. Baseline Modification Report. Note: Send Baseline Modification Report to Forecasting and Performance Office | [7 empty] | 2 | 4 | 6
| 1.4 | Baseline Comparison | Evaluation EA | 1 |  | 0 | 0 | 0 | 0 | Based on 10 to 30 hours per evaluation. 1.4.1.1. Document market conditions and inflation. 1.4.1.2. Summarize reasons for pass/fail rating (bid review summary). 1.4.1.3. Facilitation and Coordination of Drive-D/C meeting with District and Team B. |  | 1.4 | [5 empty] | 10 | 20 | 30
|  |  | Summary EA | 1 |  | 0 | 0 | 0 | 0 | Based on 6 to 14 hours per summary. 1.4.2.1 Bid Review Summary. Note: Send Summary to Forecasting and Performance Office | [7 empty] | 6 | 10 | 14
DRN02-005 | 1.5 | Trend Review | Review EA | 1 |  | 0 | 0 | 0 | 0 | Based on 6 to 12 hours per review. 1.5.1.1. Collaborate with the District and Team B for lessons learned. 1.5.1.2. Document any unknowns or discrepancies that were omitted. 1.5.1.3. Summarize Trend findings. |  | 1.5 | [5 empty] | 6 | 10 | 12
DRN02-006 |  |  | Summary EA | 1 |  | 0 | 0 | 0 | 0 | Based on 2 to 6 hours per summary. 1.5.2.1 Trend Summary to include: • Why did a Trend of not meeting the final Baseline develop? • What will be done to avoid future occurrences of not meeting the final baseline?. • What are lessons learned? Note: Send Summary to Forecasting and Performance Office | [7 empty] | 2 | 4 | 6
| DRIVE Technical Hours Subtotal |  |  |  |  | 24 | 0 | 0 | 0
DRN02-013 | 1.6 | Quality Assurance/Quality Control | % | 1 | 5% | 2 | 0 | 0 | 0 | Based on 5% of the technical subtotal. |  | 1.6
| DRIVE Hours Total |  |  |  |  | 26 | 0 | 0 | 0
Note on G13: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H13: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I13: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J13: Final negotiated staff hours for the project.
Note on E26: Is QA/QC required for Drainage Plans? Yes=1 No=0
Note on F26: 5% of the technical subtotal.

## Attachment B Team A Home
Sheet 1 of 1
A-T-T-A-C-H-M-E-N-T "B"
LIMITING FEE ESTIMATE - GENERAL CONSULTANT SERVICES
WORK ASSIGNMENT NO.
TWO xx
DESCRIPTION
QA/QC Guidelines
DATE
dd/mm/yyyy
STATE PROJECT NUMBER
C12345
| F.E.I.D | FINANCIAL PROJECT ID
| F123456789-000 | 123456-1-32-01
NAME OF CONSULTANT
Team A
TEAM A HOME OFFICE
| JOB CLASSIFICATION | STAFF HOURS | RATE | TOTAL SALARIES
| CADD/COMPUTER TECHNICIAN | 1 | 0 | 0
| SECRETARY/CLERICAL | 1 | 0 | 0
| ENGINEERING INTERN | 1 | 0 | 0
| ENGINEERING TECHNICIAN | 1 | 0 | 0
| DESIGNER | 1 | 0 | 0
| PLANNER | 1 | 0 | 0
| SENIOR DESIGNER | 1 | 0 | 0
| ENGINEER | 1 | 0 | 0
| PROJECT ENGINEER | 1 | 0 | 0
| SENIOR PLANNER | 1 | 0 | 0
| SENIOR PROJECT ENGINEER | 1 | 0 | 0
| PROJECT ENGINEER | 1 | 0 | 0
| SENIOR SPECIALIST | 1 | 0 | 0
| PROJECT MANAGER | 1 | 0 | 0
| SENIOR ENGINEER | 1 | 0 | 0
106 |  | 15 | 0 | 0
107 | LIMITING FEE ESTIMATE (Computations)
| Total Raw Salary Costs (Estimated) |  |  | 0
| (a) Home Office Overhead : | 100 |  | 0
| Subtotal (Salaries Plus Overhead) |  |  | 0
112 | (b) Operating Margin: | 40 |  | 0
113 | Subtotal (Estimated Salary Related Costs) |  |  | 0
114 | (c) FCCM (N/A% of Total Raw Labor) | 0 |  | 0
115 | Subtotal (Burdened Salary) | 0 |  | 0
121 | (d) Expenses (Home Office Expense) | 10 |  | 0
122
123 |  | TOTAL LIMITING FEE ESTIMATE TEAM A HOME OFFICE LA3 |  | 0
FEE SUMMARY:
|  | TOTAL LIMITING FEE ESTIMATE TEAM A HOME OFFICE LA3 |  | 0
|  | TOTAL LIMITING FEE ESTIMATE |  | 0
COMMENTS: