## Title
FDOT STAFF HOUR ESTIMATION
WORKSHEET PACKAGE
October 2026
File Version: 2026.01.1

## TOC
INTRODUCTION |  | SIGNALIZATION
| Disclaimer |  | Signalization Guidelines
| Project Information | 21. | Signalization Analysis
PROJECT GENERAL TASKS |  | 22. | Signalization Plans
3. | Project Common and Project General Tasks | LIGHTING
ROADWAY ANALYSIS |  |  | Lighting Guidelines
| Selective Clearing and Grubbing Guidelines | 23. | Lighting Analysis
| Roadway Guidelines | 24. | Lighting Plans
4. | Roadway Analysis | LANDSCAPE ARCHITECTURE
5. | Roadway Plans |  | Landscape Guidelines
DRAINAGE ANALYSIS |  | 25. | Landscape Analysis
6a. | Drainage Analysis | 26. | Landscape Plans
6b. | Drainage Plans | SURVEY
SELECTIVE CLEARING & GRUBBING |  |  | Survey Guidelines
| Selective C&G Guidelines | 27. | Survey
6c. | Selective C&G | PHOTOGRAMMETRY
UTILITIES |  | 28. | Photogrammetry
| Utilities Guidelines | MAPPING
7. | Utilities | 29. | Mapping
ENVIRONMENTAL PERMITS |  | TERRESTRIAL MOBILE LiDAR
| Environmental Permits Guidelines | 30. | Terrestrial Mobile LiDAR
8. | Environmental Permits and Environmental Clearances | ARCHITECTURE
STRUCTURES |  |  | Architecture Guidelines
| Structures Guidelines | 31. | Architecture Development
9. | Summary and Miscellaneous Tasks & Drawings | 31T. | Toll Facility Development
10. | Bridge Development Report | NOISE BARRIERS
11. | Temporary Bridge |  | Noise Guidelines
12. | Short Span Concrete Bridge | 32. | Noise Barriers Impact Design Assessment in the Design Phase
13. | Medium Span Concrete Bridge | INTELLIGENT TRANSPORTATION SYSTEMS (ITS)
14. | Structural Steel Bridge |  | ITS Guidelines
15. | Segmental Concrete Bridge | 33. | ITS Analysis
16. | Movable Span | 34. | ITS Plans
17. | Retaining Walls | GEOTECHNICAL
18. | Miscellaneous |  | Geotechnical Guidelines
SIGNING & PAVEMENT MARKINGS |  | 35. | Geotechnical
Signing & Pavement Markings Guidelines
19. | Signing & Pavement Markings Analysis
20. | Signing & Pavement Markings Plans

## Disclaimer
FDOT Staff Hour Worksheet Package
The staff hour ranges presented on the following sheets represent the work effort that may be expected for each specific task on typical projects. These hourly ranges vary from a simple project (lower end of range) to a complicated project (upper end of range). The ranges represent neither the minimum nor maximum hours that may be negotiated for a particular task on a project. Hours below or above these ranges may be applicable based upon constraints and requirements that are specific to the project.

## Spreadsheet instructions
Subconsultant Instructions for Submittal of Staffhours for a Technical Proposal
1 | In spreadsheet tab "Project Information" - add as much information as possible; minimum data is FPID, Federal Aid No., Project Name, name of consultant and county name.
2 | In spreadsheet tab "Staff Hour Summary--Grand Total" - add staff classifications in columns C through N, row 10 (for example Project Manager, Chief Engineer, Landscape Architect, Technician, etc.)
3 | In tab "Summary" - enter name of firm in cell C4.
4 | Complete appropriate staff hour sheets for work being performed in individual discipline sheets (tabs 3 through 35). Add name of estimator to the top of each sheet.
5 | In tab "Staff Hour Summary - Firm" - enter distribution of hours by classification for each task in rows 64 through 100.
Subconsultant Instructions for Submittal of Staffhours for a Fee Proposal
1 | Complete the information in Steps 1 - 5 above.
2 | In tab "Fee Sheet - Sub" - enter rates for employee classifications in row 9; subconsultants project number in cell O4; and name of estimator in cell O6.
3 | Also in "Fee Sheet - Sub" - enter Overhead Rate in cell N50, Operating Margin in N51, and FCCM in N52.
4 | Add an EXPENSE sheet to this workbook (this sheet is not included in spreadsheet). Reference expense amount into "Fee Sheet - Sub" cell N53.
Prime Consultant Instructions for Submittal of Staffhours for a Technical Proposal
1 | In spreadsheet tab "Project Information" - add as much information as possible; minimum data is FPID, Federal Aid No., Project Name, name of consultant and county name.
2 | In tab "Staff Hour Summary--Grand Total" - add staff classifications in columns C through N, row 10 (for example Project Manager, Chief Engineer, Landscape Architect, Technician, etc.). After classifications are added for prime, add in all other classifications from Subconsultants. Additional columns may be required if over 12 classifications are used.
3 | In tab "Summary" - enter name of prime firm in cell C4. Add names of subconsultants. Add hours from each subconsultant in respective disciplines.
4 | Complete appropriate staff hour sheets for work being performed in individual discipline sheets (tabs 3 through 35). Add name of estimator to the top of each sheet.
5 | In tab "Staff Hour Summary - Firm" - enter distribution of hours by classification for each task in rows 64 through 100.
6 | In tab "Staff Hour Summary -- Grand Total" - enter distribution of hours by classification for each task in rows 66 through 101. Use distributions provided by subconsultants for tasks being done solely by subconsultant. For tasks with both prime and subconsultant hours - use either a blended percent distribution or just the primes distribution.
Prime Consultant Instructions for Submittal of Staffhours for a Fee Proposal
1 | Complete the information in Steps 1 - 6 above.
2 | In tab "Fee Sheet - Prime" - enter rates for employee classifications in row 9; prime consultant project number in cell O4; and name of estimator in cell O6. Also add fees for each subconsultant in cells Q56-Q67.
3 | Also in "Fee Sheet - Prime" - enter Overhead Rate in cell N50, Operating Margin in N51, and FCCM in N52.
4 | Add an EXPENSE sheet to this workbook. Reference expense amount into "Fee Sheet - Prime" cell N53.
5 | Add subconsultant staff hours to "CITS".
Spreadsheets to be Submitted with Technical Proposals
1 | Requirements will vary by District. A typical submittal would be the "Summary", "Staff Hour Summary -- Grand Total" and "Staff Hour Summary-Firm" completed by the prime consultant along with the "Staff Hour Summary - Firm" completed by each subconsultant.

## Project Information
Financial Project Identification Number: | 999999-1-32-01 |  |  |  |  | Federal Aid Project Identification Number: |  |  |  |  | 54321
Name of Prime / Subconsultant: | Enter name of prime or subconsultant | [8 empty] | County: | enter name of county
Project Description: | Enter project name & description
Begin Milepost: |  |  | End Milepost: |  |  |  | Project Length: |  |  | Miles
Number of Lanes: |  |  | Typical Section: |  |  |  | (Urban / Rural / Int.) |  |  | Lane Configuration: |  | (Divided / Undivided)
Project Type: |  | (Minor / Major) |  | Access Management Classification: | [5 empty] | Roadway Classification: |  | (NHS/FIHS/Off Sys.)
CAP Level: |  |  |  | TTCP Level: |  |  |  |  | Survey Level:
Design Variations: | 1. |  |  |  | Design Exceptions: |  |  | 1.
| 2. | [6 empty] | 2.
| 3. | [6 empty] | 3.
| 4. | [6 empty] | 4.
| 5. | [6 empty] | 5.
Proposed Design Contract Time: |  | months/days |  |  |  | Date of Negotiation: |  |  | Context Classification:
Project Activity: | Estimated By: | [6 empty] | Negotiated By: (name - firm)
| Consultant |  |  |  | FDOT |  |  | Consultant |  |  | FDOT
3. Project Common & Project General Tasks | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
4. Roadway Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
5. Roadway Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
6a. Drainage Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
6b. Drainage Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
6c. Selective C&G | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
7. Utilities | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
8. Environmental Permits and Env. Clearances | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
9. Structures Summary | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
10. Structures - Bridge Development Report | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
11. Structures - Temporary Bridge | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
12. Structures - Short Span Concrete | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
13. Structures - Medium Span Concrete | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
14. Structures - Structural Steel | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
15. Structures - Segmental Concrete | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
16. Structures - Movable Span | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
17. Structures - Retaining Walls | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
18. Structures - Miscellaneous | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
19. Signing and Pavement Marking Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
20. Signing and Pavement Marking Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
21. Signalization Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
22. Signalization Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
23. Lighting Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
24. Lighting Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
25. Landscape Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
26. Landscape Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
27. Survey | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
28. Photogrammetry | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
29. Mapping | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
30. Terrestrial Mobile LiDAR | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
31. Architecture Development | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
31T. Toll Facilities Development | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
32. Noise Barriers Impact Design Assessment | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
33. Intelligent Transportation Systems Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
34. Intelligent Transportation Systems Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
35. Geotechnical | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office

## Summary
Name of Consultant: |  | Enter name of prime or subconsultant | [8 empty] | Enter project name & description
999999-1-32-01
Project Staff Hours
Activity No. | Activity | Enter Firm Name | Enter Name Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6 | Sub 7 | Sub 8 | Sub 9 | Sub 10 | Sub 11 | Sub 12 | Total Hours
3 | Project Common and General Tasks | 0 | [12 empty] | 0
4 | Roadway Analysis | 0 | [12 empty] | 0
5 | Roadway Plans | 0 | [12 empty] | 0
6a | Drainage Analysis | 0 | [12 empty] | 0
6b | Drainage Plans | 0 | [12 empty] | 0
6c | Selective C&G | 0 | [12 empty] | 0
7 | Utilities | 0 | [12 empty] | 0
8 | Env. Permits and Env. Clearances | 0 | [12 empty] | 0
9 | Structures - Summary, Misc. Tasks, Dwgs. | 0 | [12 empty] | 0
10 | BDR | 0 | [12 empty] | 0
11 | Temporary Bridge | 0 | [12 empty] | 0
12 | Short Span Concrete Bridge | 0 | [12 empty] | 0
13 | Medium Span Concrete Bridge | 0 | [12 empty] | 0
14 | Structural Steel Bridge | 0 | [12 empty] | 0
15 | Segmental Concrete Bridge | 0 | [12 empty] | 0
16 | Movable Span | 0 | [12 empty] | 0
17 | Retaining Walls | 0 | [12 empty] | 0
18 | Miscellaneous Structures | 0 | [12 empty] | 0
19 | Signing & Pavement Marking Analysis | 0 | [12 empty] | 0
20 | Signing & Pavement Marking Plans | 0 | [12 empty] | 0
21 | Signalization Analysis | 0 | [12 empty] | 0
22 | Signalization Plans | 0 | [12 empty] | 0
23 | Lighting Analysis | 0 | [12 empty] | 0
24 | Lighting Plans | 0 | [12 empty] | 0
25 | Landscape Analysis | 0 | [12 empty] | 0
26 | Landscape Plans | 0 | [12 empty] | 0
27 | Survey - Field and Office Support | 0 | [12 empty] | 0
28 | Photogrammetry | 0 | [12 empty] | 0
29 | Mapping | 0 | [12 empty] | 0
30 | Terrestrial Mobile LiDAR | 0 | [12 empty] | 0
31 | Architecture Development | 0 | [12 empty] | 0
31T | Toll Facility Development | 0 | [12 empty] | 0
32 | Noise Barriers Impact Design Assessment | 0 | [12 empty] | 0
33 | ITS Analysis | 0 | [12 empty] | 0
34 | ITS Plans | 0 | [12 empty] | 0 | check
35 | Geotechnical | 0 | [12 empty] | 0
Project Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Survey Field Crew Days | 0 | [12 empty] | 0
Notes: | 1. Staff hours for prime consultant come directly from each discipline's worksheet.
2. Staff hours for subconsultants are to be entered manually into columns D through O.
3. For workbooks prepared by subconsultants, their project hours will be totaled in column C.

## Staff Hour Summary--Grand Total
ESTIMATE OF WORK EFFORT FOR TECHNICAL PROPOSALS - GRAND TOTAL
Financial Project Number: | 999999-1-32-01 | [10 empty] | Project Name: | Enter project name & description
FAP Number: | 54321 | [7 empty] | Date: | 2026-10-27 |  | Name of Consultant: | Enter name of prime or subconsultant
WORK ACTIVITY | Hours from "Summary" sheet
[7 empty] | EMPLOYEE CLASSIFICATION | [6 empty] | TOTAL
[14 empty] | STAFF HOURS |  | ON CADD
| Grand Total | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | RANGE
| Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  |  | PERCENT
3. Project Common and Project General Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Roadway Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. Roadway Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6a. Drainage Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6b. Drainage Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6c. Selective C&G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. Environmental Permits and Env. Clearances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. Structures - Bridge Development Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11. Structures - Temporary Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12. Structures - Short Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13. Structures - Medium Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14. Structures - Structural Steel Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15. Structures - Segmental Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16. Structures - Movable Span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17. Structures - Retaining Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18. Structures - Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19. Signing & Pavement Marking Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20. Signing & Pavement Marking Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21. Signalization Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22. Signalization Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23. Lighting Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24. Lighting Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25. Landscape Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26. Landscape Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27. Survey (Field & Office Support) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28. Photogrammetry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29. Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30. Terrestrial Mobile LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31. Architecture Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31T. Toll Facility Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32. Noise Barriers Impact Design Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33. Intelligent Transportation Systems Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34. Intelligent Transportation Systems Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35. Geotechnical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Field Survey Estimate:
Notes: | [8 empty] | 0 | 4-person crew days |  | (Prime Consultant) |  | 0 | 0
1. This worksheet provides the distribution of the grand total staff hours for a project.
2. Percentages for staff hour distribution by classification are entered below in rows 65 to 99 of this sheet.
3. Total Staff Hours (column O) may not match staff hours from Summary worksheet (column B) due to rounding. Staff hours calculated for employee classifications are to be adjusted so totals in columns B and O match.
4. Formulas under "Total Staff Hours Range" (columns O & P) may be adjusted to provide desired range.
5. This spreadsheet to be provided in Technical Proposals for Districts that require a breakdown of hours by classification.
ESTIMATE OF WORK EFFORT FOR TECHNICAL PROPOSALS - GRAND TOTAL
Financial Project Number: | 999999-1-32-01 | [11 empty] | Project Name: | Enter project name & description
FAP Number: | 54321 | [7 empty] | Date: | 2026-10-27 |  |  | Name of Consultant: | Enter name of prime or subconsultant
Staff Hour Distribution Percentages - Grand Total
| Hours from "Summary" sheet Grand Total | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | Total
3. Project Common and Project General Tasks | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4. Roadway Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5. Roadway Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6a. Drainage Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6b. Drainage Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6c. Selective C&G | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7. Utilities | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8. Environmental Permits and Env. Clearances | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10. Structures - Bridge Development Report | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11. Structures - Temporary Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12. Structures - Short Span Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13. Structures - Medium Span Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14. Structures - Structural Steel Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15. Structures - Segmental Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16. Structures - Movable Span | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17. Structures - Retaining Walls | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18. Structures - Miscellaneous | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
19. Signing & Pavement Marking Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
20. Signing & Pavement Marking Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
21. Signalization Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
22. Signalization Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
23. Lighting Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
24. Lighting Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
25. Landscape Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
26. Landscape Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
27. Survey (Field & Office Support) | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
28. Photogrammetry | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
29. Mapping | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30. Terrestrial Mobile LiDAR | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31. Architecture Development | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31T. Toll Facility Development | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
32. Noise Barriers Impact Design Assessment | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
33. Intelligent Transportation Systems Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
34. Intelligent Transportation Systems Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
35. Geotechnical | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Note: | This spreadsheet to be used in Technical Proposal for Districts requiring the Grand Total hours be provided along with percentage distribution by classification.

## Staff Hour Summary - Firm
ESTIMATE OF WORK EFFORT FOR TECHNICAL PROPOSALS - FIRM TOTAL
Financial Project Number: | 999999-1-32-01 | [11 empty] | Project Name: | Enter project name & description
FAP Number: | 54321 | [7 empty] | Date: | 2026-10-27 |  |  | Name of Consultant: | Enter name of prime or subconsultant
Hours from "Summary" sheet
WORK | [6 empty] | EMPLOYEE CLASSIFICATION | [6 empty] | TOTAL
ACTIVITY | [13 empty] | STAFF HOURS |  | ON CADD
| Firm Total | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | RANGE
| Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  |  | PERCENT
3. Project Common and Project General Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Roadway Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. Roadway Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6a. Drainage Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6b. Drainage Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6c. Selective C&G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. Environmental Permits,and Env. Clearances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. Structures - Bridge Development Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11. Structures - Temporary Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12. Structures - Short Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13. Structures - Medium Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14. Structures - Structural Steel Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15. Structures - Segmental Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16. Structures - Movable Span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17. Structures - Retaining Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18. Structures - Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19. Signing & Pavement Marking Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20. Signing & Pavement Marking Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21. Signalization Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22. Signalization Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23. Lighting Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24. Lighting Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25. Landscape Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26. Landscape Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27. Survey (Field & Office Support) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28. Photogrammetry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29. Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30. Terrestrial Mobile LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31. Architecture Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31T. Toll Facility Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32. Noise Barriers Impact Design Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33. Intelligent Transportation Systems Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34. Intelligent Transportation Systems Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35. Geotechnical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Field Survey Estimate:
Notes: | [8 empty] | 0 | 4-person crew days |  | FIRM TOTAL |  | 0 | 0
1. This worksheet provides the distribution of a firm's total staff hours for a project.
2. Percentages for staff hour distribution by classification are entered below in rows 64 to 98 of this sheet.
3. Total Staff Hours (column O) may not match staff hours from Summary worksheet (column B) due to rounding. Staff hours calculated for employee classifications are to be adjusted so totals in columns B and O match.
4. Formulas under "Total Staff Hours Range" (columns O & P) may be adjusted to provide desired range.
ESTIMATE OF WORK EFFORT FOR TECHNICAL PROPOSALS - FIRM TOTAL
Financial Project Number: | 999999-1-32-01 | [11 empty] | Project Name: | Enter project name & description
FAP Number: | 54321 | [7 empty] | Date: | 2026-10-27 |  |  | Name of Consultant: | Enter name of prime or subconsultant
Staff Hour Distribution Percentages - Firm Total
| Hours from "Summary" sheet Firm Total | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | Total
3. Project Common and Project General Tasks | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4. Roadway Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5. Roadway Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6a. Drainage Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6b. Drainage Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6c. Selective C&G | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7. Utilities | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8. Environmental Permits,and Env. Clearances | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10. Structures - Bridge Development Report | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11. Structures - Temporary Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12. Structures - Short Span Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13. Structures - Medium Span Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14. Structures - Structural Steel Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15. Structures - Segmental Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16. Structures - Movable Span | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17. Structures - Retaining Walls | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18. Structures - Miscellaneous | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
19. Signing & Pavement Marking Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
20. Signing & Pavement Marking Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
21. Signalization Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
22. Signalization Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
23. Lighting Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
24. Lighting Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
25. Landscape Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
26. Landscape Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
27. Survey (Field & Office Support) | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
28. Photogrammetry | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
29. Mapping | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30. Terrestrial Mobile LiDAR | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31. Architecture Development | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31T. Toll Facility Development | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
32. Noise Barriers Impact Design Assessment | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
33. Intelligent Transportation Systems Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
34. Intelligent Transportation Systems Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
35. Geotechnical | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Fee Sheet - Prime
ESTIMATE OF WORK EFFORT AND COST - PRIME CONSULTANT
Name of Project: | Enter project name & description | [11 empty] | Consultant Name: | Enter name of prime or subconsultant
County: | enter name of county | [11 empty] | Consultant No.: | enter consultants proj. number
FPN: | 999999-1-32-01 | [11 empty] | Date: | 2026-10-27
FAP No.: | 54321 | [11 empty] | Estimator: | insert name
Staff Classification | Total Staff Hours From "SH Summary - Firm" | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | SH | Salary | Average
[14 empty] | By | Cost By | Rate Per
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Activity | Activity | Task
3. Project Common and Project General Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
4. Roadway Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
5. Roadway Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6a. Drainage Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6b. Drainage Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6c. Selective C&G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
7. Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
8. Environmental Permits,and Env. Clearances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
10. Structures - Bridge Development Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
11. Structures - Temporary Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
12. Structures - Short Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
13. Structures - Medium Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
14. Structures - Structural Steel Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
15. Structures - Segmental Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
16. Structures - Movable Span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
17. Structures - Retaining Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
18. Structures - Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
19. Signing & Pavement Marking Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
20. Signing & Pavement Marking Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
21. Signalization Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
22. Signalization Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
23. Lighting Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
24. Lighting Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
25. Landscape Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
26. Landscape Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
27. Survey (Field & Office Support) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
28. Photogrammetry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
29. Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30. Terrestrial Mobile LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
31. Architecture Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
31T. Toll Facility Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
32. Noise Barriers Impact Design Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
33. Intelligent Transportation Systems Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
34. Intelligent Transportation Systems Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
35. Geotechnical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Staff Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Staff Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
[14 empty] | Check = | 0
[6 empty] | Survey Field Days by Subconsultant |  |  |  | SALARY RELATED COSTS: | [5 empty] | 0
[6 empty] | 4 - Person Crew: |  |  |  | OVERHEAD: |  |  | 0% |  |  | 0
[10 empty] | OPERATING MARGIN: |  |  | 0% |  |  | 0
| Notes: | [8 empty] | FCCM (Facilities Capital Cost Money): |  |  | 0% |  |  | 0
| 1. This sheet to be used by Prime Consultant to calculate the Grand Total fee. | [8 empty] | EXPENSES: |  |  | 0% |  |  | 0
| 2. Manually enter fee from each subconsultant. Unused subconsultant rows may be hidden. | [8 empty] | Survey (Field - if by Prime) |  | 0 | 4-person crew days @ | 0 | / day | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Subconsultant: | Enter Name Sub 1 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 2 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 3 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 4 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 5 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 6 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 7 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 8 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 9 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 10 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 11 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 12 |  |  |  |  | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Geotechnical Field and Lab Testing | [5 empty] | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Optional Services | [5 empty] | 0
[10 empty] | GRAND TOTAL ESTIMATED FEE: | [5 empty] | 0

## Fee Sheet - Sub
ESTIMATE OF WORK EFFORT AND COST - SUBCONSULTANT
Name of Project: | Enter project name & description | [11 empty] | Consultant Name: | Enter name of prime or subconsultant
County: | enter name of county | [11 empty] | Consultant No.: | enter consultants proj. number
FPN: | 999999-1-32-01 | [11 empty] | Date: | 2026-10-27
FAP No.: | 54321 | [11 empty] | Estimator: | insert name
Staff Classification | Total Staff Hours From "SH Summary - Firm" | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | SH | Salary | Average
[14 empty] | By | Cost By | Rate Per
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Activity | Activity | Task
3. Project Common and Project General Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
4. Roadway Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
5. Roadway Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6a. Drainage Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6b. Drainage Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6c. Selective C&G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
7. Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
8. Environmental Permits,and Env. Clearances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
10. Structures - Bridge Development Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
11. Structures - Temporary Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
12. Structures - Short Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
13. Structures - Medium Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
14. Structures - Structural Steel Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
15. Structures - Segmental Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
16. Structures - Movable Span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
17. Structures - Retaining Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
18. Structures - Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
19. Signing & Pavement Marking Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
20. Signing & Pavement Marking Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
21. Signalization Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
22. Signalization Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
23. Lighting Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
24. Lighting Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
25. Landscape Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
26. Landscape Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
27. Survey (Field & Office Support) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
28. Photogrammetry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
29. Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30. Terrestrial Mobile LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
31. Architecture Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
31T. Toll Facility Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
32. Noise Barriers Impact Design Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
33. Intelligent Transportation Systems Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
34. Intelligent Transportation Systems Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
35. Geotechnical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Staff Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Staff Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
[14 empty] | Check = | 0
[10 empty] | SALARY RELATED COSTS: | [5 empty] | 0
[10 empty] | OVERHEAD: |  |  | 0% |  |  | 0
[10 empty] | OPERATING MARGIN: |  |  | 0% |  |  | 0
| Notes: | [8 empty] | FCCM (Facilities Capital Cost Money): |  |  | 0% |  |  | 0
| 1. This sheet to be used by Subconsultant to calculate its fee. | [8 empty] | EXPENSES: |  |  | 0% |  |  | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Survey (Field) |  | 0 | 4-person crew days @ | 0 | / day | 0
[10 empty] | Geotechnical Field and Lab Testing | [5 empty] | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Optional Services | [5 empty] | 0
[10 empty] | GRAND TOTAL ESTIMATED FEE: | [5 empty] | 0

## 3. Project General Tasks
Estimator: | [5 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
3.1 | Public Involvement
3.1.1 | Community Awareness Plan | LS | 1 | 0 | 0
3.1.2 | Notifications | LS | 1 | 0 | 0
3.1.3 | Preparing Mailing Lists | LS | 1 | 0 | 0
3.1.4 | Median Modification Letters | LS | 1 | 0 | 0
3.1.5 | Driveway Modification Letters | LS | 1 | 0 | 0
3.1.6 | Newsletters | LS | 1 | 0 | 0
3.1.7 | Renderings and Fly Throughs | LS | 1 | 0 | 0
3.1.8 | PowerPoint Presentation | LS | 1 | 0 | 0
3.1.9 | Public Meeting Preparations | LS | 1 | 0 | 0
3.1.10 | Public Meeting Attendance/Followup | LS | 1 | 0 | 0
3.1.11 | Other Agency Meetings | LS | 1 | 0 | 0
3.1.12 | Web Site | LS | 1 | 0 | 0
3.1 Public Involvement Subtotal |  |  |  |  | 0
3.2 | Joint Project Agreements | EA | 0 | 0 | 0
3.3 | Specifications & Project Cost
3.3.1 | Specifications Package Preparation | LS | 1 | 0 | 0
3.3.2 | Estimated Quantities Report Preparation | Report | 0 | Calculated Hours | 0
|  | Components | 0 | 0 |  |  | 16 | 2
3.3.3 | Engineer's Project Cost
3.3.3.1 | Project Cost Checklist | LS | 1 | 0 | 0
3.3.3.2 | Risk Register | LS | 1 | 0 | 0
3.3.3.3 | Design Confidence Report | LS | 1 | 0 | 0
3.3.3.4 | Project Document Memorandum (IPC) | LS | 1 | 0 | 0
3.3.3.5 | Project Document Checklist (IPC) | LS | 1 | 0 | 0
3.4 | Contract Maintenance and Project Documentation | LS | 1 | 0 | 0
3.5 | Value Engineering (Multi-Discipline Team) Review | LS | 1 | 0 | 0
3.6 | Prime Consultant Project Manager Meetings | LS | 1 | 0 | 0 | See listing below
3.7 | Plans Update | LS | 1 | 0 | 0
3.8 | Post Design Services | LS | 1 | 0 | 0
3.9 | Digital Delivery | LS | 1 | 0 | 0
3.1 | Risk Assessment Workshop | LS | 1 | 0 | 0
3.11 | Railroad, Transit, and/or Airport Coordination | LS | 1 | 0 | 0
3.11.1 | Aeronautical Evaluation | LS | 1 | 0 | 0
3.12 | Landscape and Existing Vegetation Coordination | LS | 1 | 0 | 0
3.13 | Other Project General Tasks | LS | 1 | 0 | 0
3. Project Common and Project General Tasks Total |  |  |  |  | 0
3.6 - List of Project Manager Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments
Roadway Analysis |  | EA | 0 | 0 | 0
Drainage |  | EA | 0 | 0 | 0
Selective C&G |  | EA | 0 | 0 | 0
Utilities |  | EA | 0 | 0 | 0
Environmental |  | EA | 0 | 0 | 0
Structures |  | EA | 0 | 0 | 0
Signing & Pavement Marking |  | EA | 0 | 0 | 0
Signalization |  | EA | 0 | 0 | 0
Lighting |  | EA | 0 | 0 | 0
Landscape Architecture |  | EA | 0 | 0 | 0
Survey |  | EA | 0 | 0 | 0
Photogrammetry |  | EA | 0 | 0 | 0
ROW & Mapping |  | EA | 0 | 0 | 0
Terrestrial Mobile LiDAR |  | EA | 0 | 0 | 0
Architecture |  | EA | 0 | 0 | 0
Toll Facility Development |  | EA | 0 | 0 | 0
Noise Barriers |  | EA | 0 | 0 | 0
ITS Analysis |  | EA | 0 | 0 | 0
Geotechnical |  | EA | 0 | 0 | 0
Progress Meetings |  | EA | 0 | 0 | 0
Phase Reviews |  | EA | 0 | 0 | 0
Field Reviews |  | EA | 0 | 0 | 0
Total Project Manager Meetings |  |  | 0 |  | 0 | Total PM Meeting Hours carries to Task 3.6 above
Notes:
1. If the hours per meeting vary in length (hours) enter the average in the hour/unit column.
2. Do not double count agency meetings between permitting agencies.
3. Project manager meetings are calculated in each discipline sheet and brought forward to Column D.
Note on D27: Is an EQ Report required for this project? Yes=1 No=0
Note on E27: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on D28: # of components for the EQ Report.
Note on E28: Consider adding 4 hours to the calculated hours when required to include EQ Report with Phase II Submittal.

## Roadway Guidelines
ROADWAY GUIDELINES FOR DETERMINING PROJECT COMPLEXITY
Below (very low) Complexity Projects
2-Lane | Flush Shoulder or Curbed | RRR | No improvements, or cross slope correction
All Roadway Types | Flush Shoulder or Curbed | Safety Improvement or Sidewalk Projects | Calculated earthwork quantities
Low Complexity Projects
2-Lane or Multi-Lane | Flush Shoulder or Curbed | RRR | Minimal safety enhancements, turnout improvements, and minimal cross slope correction
All Roadway Types | Limited Access | Resurfacing | Minimal safety enhancements, cross slope correction, and interchange involvement
Mid Complexity Projects
2-Lane or Multi-Lane | Flush Shoulder | RRR or Widening/Resurfacing | Safety enhancements, turnout improvements, intersection improvements, and cross slope correction
2-Lane or Multi-Lane | Flush Shoulder | New Construction | Minimal utility impacts, intersection involvement, and R/W involvement
2-Lane or Multi-Lane | Curbed | RRR | Safety & Bike/Ped enhancements, ADA improvements, intersection improvements, and cross slope correction
Multi-Lane | Limited Access | Resurfacing or Widening/Resurfacing | Safety enhancements, interchange involvement, and cross slope correction
Upper Complexity Projects
All Roadway Types | Flush Shoulder or Curbed | New Innovative Intersections | Utility impacts, driveway connections, and possible R/W involvement
2-Lane or Multi-Lane | Flush Shoulder | Reconstruction or Widening/Resurfacing | Utility impacts, driveway connections, intersection improvements, and possible R/W involvement
2-Lane | Curbed | Reconstruction | Utility impacts, driveway connections, intersection improvements, and R/W involvement/constraints
2-Lane or Multi-Lane | Curbed | New Construction or Widening/Resurfacing | Utility impacts, driveway connections, intersection improvements, and possible R/W involvement
Multi-Lane | Limited Access | Widening/Resurfacing | Minimal utility, R/W, and intersection involvement, closed median/barrier wall, and includes interchange ramps
Multi-Lane | Limited Access | New Construction or Reconstruction | Minimal utility involvement, interchange/intersection improvements, and possible R/W involvement
Above (very high) Complexity Projects
Multi-Lane | Curbed | Reconstruction | Utility impacts, driveway connections, intersection improvements, and R/W involvement/constraints
Multi-Lane | Limited Access | New Multi-level Interchange | Utility impacts and R/W involvement/constraints

## Roadway 3D Modeling Guidelines
Model Element Name | LOD | 2D or 3D | [5 empty] | Element Data Attributes | [8 empty] | Modeling Effort |  | Element Data Attributes
|  |  | Developed BIM Uses | Legal Document? Yes Contract / No FIO | Professional of Record | Source CADD File | Source CADD Layer | Pay Item No. Quantity & Unit | Location Data |  |  | FDOT Specification | Limitations | Required Reports | Documents Attached? Y/N | Comments | 2D Design File | 3D Model Development | Pay Item No. Quantity & Unit | Location Data
[8 empty] | Pay item Data: Number, Quantity and Unit | Location Data: Alignment, Station Offset | GIS Data Portal | Updated by DAB | [7 empty] | Pay item Data: Number, Quantity and Unit | Location Data: Alignment, Station Offset
Survey Elements
SURVRD | 300 | 3D |  | YES | Surveyor | SURVRD |  | No |  | Yes | Yes | [7 empty] | No
Terrain | 300 | 3D |  | YES | Surveyor | SURVRD |  | No |  | Yes | Yes | [7 empty] | No
Existing Elements
Pavement | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | Cores |  |  | 2D | 3D w/ assumed depth | No
Shoulders | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | Cores |  |  | 2D | 3D w/ assumed depth | No
Curbs | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | n/a |  |  | 2D | 3D w/ assumed depth | No
Islands/Medians | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | n/a |  |  | 2D | 3D w/ assumed depth | No
Sidewalks/ADA Ramps | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | n/a |  |  | 2D | 3D w/ assumed depth | No
Other Concrete Pads | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | n/a |  |  | 2D | 3D w/ assumed depth | No
Slope Pavement | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | n/a |  |  | 2D | 3D w/ assumed depth | No
Ditch Pavement | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | n/a |  |  | 2D | 3D w/ assumed depth | No
Driveways | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | n/a |  |  | 2D | 3D w/ assumed depth | No
Traffic Separators | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | n/a |  |  | 2D | 3D w/ assumed depth | No
Utilities | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths | VVH |  |  | 2D | 3D w/ assumed depth | No
Drainage | 200 | Both | 200 | No | N/A | MODLEX |  | No |  | Yes | Yes |  | assumed depths |  |  |  | 2D | 3D w/ assumed depth | No
Geotech Data | 200 | Both | 200 | No | N/A | ABORRD |  | No |  | Yes | Yes |  | assumed depths | Geotech Report |  |  | 2D | 2D or 3D | No
Unsuitable Soil | 200 | Both | 200 | No | N/A | MODLRD |  | No |  | Yes | Yes | [5 empty] | 2D | 3D | No
Bridge Super Structures | 200 | Both |  | No | N/A | BR#MODLBR_EX |  | When removed |  | Yes | Yes | [5 empty] | 2D | 2D | When removed
Bridge Sub Structures | 200 | Both |  | No | N/A | BR#MODLBR_EX |  | When removed |  | Yes | Yes | [5 empty] | 2D | 2D | When removed
Bridge Misc. Structures (RipRap, Approach Slabs) | 200 | Both |  | No | N/A | MISCSTR |  | When removed |  | Yes | Yes | [5 empty] | 2D | 2D | When removed
Misc. Structures(Signs, Signals, Light Poles,ITS) | 200 | Both |  | No | N/A | BR#MODLBR_EX |  | When removed |  | Yes | Yes | [5 empty] | 2D | 2D | When removed
Walls: MSE, Noise, Retaining, Sheet Pile, etc. | 200 | Both |  | No | N/A | MODLEX |  | When removed |  | Yes | Yes | [5 empty] | 2D | 2D | When removed
Controlling Alignments
Existing Horizontal and Vertical Alignments | 300 | Both |  | Yes | Roadway | ALGNRD |  | No | Alignment Name | Yes | No | N/A |  | HA Report |  |  | 3D | 3D | No | Alignment Name
Proposed Horizontal and Vertical Alignments | 300 | Both |  | Yes | Roadway | ALGNRD |  | No | Alignment Name | Yes | No | N/A |  | HA Report |  |  | 2D or 3D | 3D | No | Alignment Name
Survey Control Points (reference pts & bench marks) | 200 | 2D |  | Yes | Roadway | CTLSRD |  | No | Point Name, NE | Yes | No | N/A |  | Survey Control Report |  |  | 3D | 3D | No | Point Name, NE
Superelevation Model - Roadway | 300 | 2D |  | No | Roadway | ALGNRD |  | No | Alignment Name | No | No | N/A |  | SE Report |  |  | 2D or 3D | 3D | No | Alignment Name
Baselines and profiles - Ramps, sidewalks | 300 | Both |  | Yes | Roadway | ALGNRD |  | No | Alignment Name | Yes | No | N/A |  | HA Report |  |  | 2D or 3D | 3D | No | Alignment Name
Other Baselines and profiles -Sidewalks | 300 | Both |  | Yes | Roadway | MODLRD |  | No | Alignment Name | Yes | No | N/A |  | HA Report |  |  | 2D or 3D | 3D | No | Alignment Name
Baselines and profiles -Walls, Ditches, Bridges | 300 | Both |  | Yes | Roadway | RetaingWall |  | No | Alignment Name | Yes | No | N/A |  | HA Report |  |  | 2D or 3D | 3D | No | Alignment Name
Other Baselines and profiles - Ditches | 300 | Both |  | Yes | Drainiage | DRPRRD |  | No | Alignment Name | Yes | No | N/A |  | HA Report |  |  | 2D or 3D | 2D or 3D | No | Alignment Name
Other Baselines and profiles - Bridge | 300 | Both |  | Yes | Structures | BR#ALGNBR |  | No | Alignment Name | Yes | No | N/A |  | HA Report |  |  | 2D or 3D | 2D or 3D | No | Alignment Name
Right of Way Geometry
Existing Right-of-Way Lines | 200 | Both |  | No | Roadway | RWDTRD |  | No | N/A | Yes, Owner Info | No | N/A |  | Signed Survey |  |  | 2D | 3D (Draping) | No | N/A
Property Lines | 200 | Both |  | No | Roadway | RWDTRD |  | No | N/A | Yes, Owner Info | No | N/A |  | Signed Survey |  |  | 2D | 3D (Draping) | No | N/A
Other Boundaries (Wetland Limits) | 200 | Both |  | No | Roadway | RWDTRD |  | No | N/A | Yes, Owner Info | No | N/A |  | Signed Survey |  |  | 2D | 3D (Draping) | No | N/A
Proposed Right-of-Way Lines | 200 | Both |  | No | Roadway | RWDTRD |  | No | N/A | Yes, Owner Info | No | N/A |  | Signed Survey |  |  | 2D | 3D (Draping) | No | N/A
Permanent Easement Lines | 200 | Both |  | No | Roadway | RWDTRD |  | No | N/A | Yes, Owner Info | No | N/A |  | Signed Survey |  |  | 2D | 3D (Draping) | No | N/A
Temporary Easement Lines | 200 | Both |  | No | Roadway | RWDTRD |  | No | N/A | Yes, Owner Info | No | N/A |  | Signed Survey |  |  | 2D | 3D (Draping) | No | N/A
Earthwork
Excavation | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A |  | not for AMG | Use EAV Report |  |  | 2D | 3D | Yes | Yes
Embankment | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A |  | not for AMG | Use EAV Report |  |  | 2D | 3D | Yes | Yes
Embankment for Bridge | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A | [5 empty] | 2D | 3D | Yes | Yes
Excavation for Bridge | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A | [5 empty] | 2D | 3D | Yes | Yes
Subsoil Excavation | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A | [5 empty] | 2D | 3D | Yes | Yes
add other pay items for excavation | [9 empty] | No | N/A
Terrain
Existing | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A |  | not for AMG | Use EAV Report |  |  | N/A | 3D | Yes | Yes
Proposed | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A |  | not for AMG | Use EAV Report |  |  | N/A | 3D | Yes | Yes
Finished Subgrade | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A | [5 empty] | N/A | 3D | Yes | Yes
Subsoil | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A | [5 empty] | N/A | 3D | Yes | Yes
Existing Subgrade | 300 | 3D |  | NO | N/A | MODLRD |  | Yes | Yes | No | N/A | [5 empty] | N/A | 3D | Yes | Yes
Pavement Roadway & Shoulders
Stabilization | 200 | 2D |  | No | N/A | QTDSRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 2D or 3D | Yes | Yes
Base Course | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Stuctural Course Asphalt | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
FC Asphalt Pavement | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Concrete Pavement | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Pavement Milling | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Pavement Overbuild | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Pavement Overlay | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Shoulder Pavement
Stabilization | 200 | 2D |  | No | N/A | QTDSRD |  | Yes | Yes | Yes | Yes | [7 empty] | Yes | Yes
Base Course | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [7 empty] | Yes | Yes
Stuctural Course Asphalt | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [7 empty] | Yes | Yes
FC Asphalt Pavement | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [7 empty] | Yes | Yes
Concrete Pavement | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [7 empty] | Yes | Yes
Pavement Milling | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [7 empty] | Yes | Yes
Pavement Overbuild | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [7 empty] | Yes | Yes
Pavement Overlay | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [7 empty] | Yes | Yes
Concrete
Ditch Pavement | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Concrete Sidewalk | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Concrete Pads | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Curb and Gutter | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Curb and Gutter Flare Outs | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Shoulder Gutter | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Roundabout Apron | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Traffic Separator | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Concrete Flared Driveway | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Sidewalk Curb Ramps | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Detectable Warnings at Ramps | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 2D | Yes | Yes
Pedestrian Channelization Barriers/Islands | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Misc. Roadside
Rural Driveways | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Meadian Cross Over | 301 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Shoulder Sodding and Turf | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D (Sloped Line) | Yes | Yes
Permanent Erosion Control Sod | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D (Sloped Line) | Yes | Yes
Fencing | 300 | Both |  | No | N/A | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Fence Gates | 300 | Both |  | No | N/A | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 2D | Yes | Yes
Guardrail | 300 | Both |  | No | N/A | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Crash Cushions | 200 | 2D |  | No | N/A | DSGNRD |  | Yes | Yes | Yes | Yes |  |  |  | from APL |  | 2D | 2D | Yes | Yes
Concrete Barrier | 300 | Both |  | Yes | Roadway | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
High Tension Cable Barrier | 300 | Both |  | No | N/A | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Ped/Bicycle Railing | 300 | Both |  | No | N/A | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Pipe Guiderail | 300 | Both |  | No | N/A | MODLRD |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Walls
Gravity Wall | 300 | Both |  | Yes | Structures | MODLRD |  | Yes | Yes | Yes | Yes |  |  |  |  | Rebar detail from standards | 2D | 3D | Yes | Yes
MSE Walls | 300 | Both |  | Yes | Structures | MSEWall |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Noise Walls | 300 | Both |  | Yes | Structures | NoiseWall |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Perimeter Walls | 300 | Both |  | Yes | Structures | RetainingWall |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Canitlever Wall | 400 | Both |  | Yes | Structures | RetainingWall |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Concrete Sheet Pile Wall | 300 | Both |  | Yes | Structures | SheetPileWall |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Steel Sheet Pile Wall | 300 | Both |  | Yes | Structures | SheetPileWall |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes
Temp. Steel Sheet Pile Wall | 300 | Both |  | Yes | Structures | SheetPileWall |  | Yes | Yes | Yes | Yes | [5 empty] | 2D | 3D | Yes | Yes

## 4. Roadway Analysis
| Estimator: |  | 4. Roadway Analysis Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Base |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
What is the overall project complexity? (See Roadway Guidelines)
RDY01-001 | 4.1 | Typical Section Package | Cover | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 4.1 | [8 empty] | 6
RDY01-002 |  |  | Typical | 0 | 2-Lane FS & Ramps | 0 | 0 | 0 | 0 | [8 empty] | 6
RDY01-003 |  |  | Typical | 0 | 2-Lane C & Multi-Lane FS | 0 | 0 | 0 | 0 | [9 empty] | 8
RDY01-004 |  |  | Typical | 0 | LA w/ Barrier & Multi-Lane C | 0 | 0 | 0 | 0 | [10 empty] | 10
RDY01-005 | 4.2 | Pavement Type Selection Report | Report | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.2 | [5 empty] | 8 | 40 | 50
RDY01-006 | 4.3 | Pavement Design Package | Report & Assembly | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.3 | 16 | 24 | 32 | 40 | 48
RDY01-007 |  |  | Pavt Designs | 0 | Travel/Aux. Lanes | 0 | 0 | 0 | 0 | [11 empty] | 8
RDY01-008 |  |  | Pavt Designs | 0 | Other Roads & Shoulders | 0 | 0 | 0 | 0 | [11 empty] | 4
RDY01-009 | 4.4 | Cross Slope Analysis (lanes and shoulders) | X-Slope Assessment | 0 | Undivided Roadway | 0 | 0 | 0 | 0 |  |  | 4.4 | [8 empty] | 1.5
RDY01-010 |  |  | X-Slope Assessment | 0 | Divided Roadway | 0 | 0 | 0 | 0 | [11 empty] | 2.5
RDY01-011 |  |  | Concepts for Corrections | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 6
RDY01-012 | 4.5 | Safety Analysis | HSM Assessment | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.5 | [5 empty] | 40 | 50 | 60
RDY01-013 |  |  | Crash Analysis | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 8 | 24 | 40
RDY01-014 | 4.6 | Design Analysis | Monitor Exist. Structures | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.6 | 4 | 4 | 8 | 12 | 16
RDY01-015 |  |  | Access Management | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 2 | 4 | 8 | 10 | 14
RDY01-016 | 4.7 | Operational Analysis | Roundabout | 0 | 1x1 Roundabout | 0 | 0 | 0 | 0 |  |  | 4.7 | [5 empty] | 40
RDY01-017 |  |  | Roundabout | 0 | 1x2 Roundabout | 0 | 0 | 0 | 0 | [9 empty] | 60
RDY01-018 |  |  | Roundabout | 0 | 2x2 Roundabout | 0 | 0 | 0 | 0 | [10 empty] | 80
RDY01-019 | 4.8 | Design Reports | RRR | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.8 | [5 empty] | 40 | 60 | 80
|  |  | Other Reports |  |  | 0 | 0 | 0 | 0
RDY01-020 | 4.9 | Design Variations and Exceptions | Variation Memo | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.9 | [8 empty] | 8 | 2
RDY01-021 |  |  | Formal Variation | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 24
RDY01-022 |  |  | Design Exception | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 40
RDY01-023 | 4.1 | Master Design File Setup & Maintenance, Model Management Plan | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.1 | 20 | 30 | 40 | 50 | 50
RDY01-024 | 4.11 | Horizontal /Vertical Master Design Files | Mainline | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.11 | 120 | 175 | 215 | 260 | 300
RDY01-025 |  |  | Side Road & Ramps | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 120 | 175 | 215 | 260 | 300
RDY01-026 |  |  | Frontage Road | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 60 | 90 | 120 | 135 | 150
RDY01-027 |  | 3D Modeling Development | Mainline | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 60 | 87.5 | 107.5 | 130 | 150
RDY01-028 |  |  | Side Road & Ramps | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 60 | 87.5 | 107.5 | 130 | 150
RDY01-029 |  |  | Frontage Road | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 30 | 45 | 60 | 67.5 | 75
RDY01-030 |  |  | AMG Files | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 10 | 15 | 20 | 30 | 40
RDY01-031 | 4.12 | TTCP Analysis | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.12 | 10 | 20 | 40 | 100 | 160
|  | Detour Tolls Analysis Memo (DTAM) | LS | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 8 | 16 | 24
RDY01-032 |  | TTCP Master Design Files | Length (Phase-Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 32 | 40 | 48
RDY01-033 |  |  | Pedestrian | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 24 | 32 | 40
RDY01-034 |  | TTCP 3D Modeling (Isolated Locations) | Locations | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 8 | 16 | 24
RDY01-035 | 4.13 | Utility Data Collection & Analysis | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.13 | 2 | 6 | 12 | 18 | 24
RDY01-036 | 4.14 | Roadway Quantities for EQ Report | Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.14 | 2 | 6 | 10 | 14 | 18
RDY01-037 |  |  | Interchanges Rest Areas | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
RDY01-038 |  |  | Validation | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 32 | 36 | 40 | 44 | 48
RDY01-039 |  | TTCP Quantities for EQ Report | Major Phases | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 6 | 9 | 12
RDY01-040 | 4.15 | Project Cost | Engineer's Project Cost | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.15 | 8 | 10 | 12 | 14 | 16
RDY01-041 |  |  | LRE Updates | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 4 | 5 | 6 | 7 | 8
RDY01-042 | 4.16 | Technical or Modified Special Provisions | TSPs & MSPs | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.16 | [8 empty] | 6
RDY01-043 | 4.17 | Other Roadway Tasks | Other Analysis |  |  | 0 | 0 | 0 | 0 |  |  | 4.17
| Roadway Analysis Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
RDY01-044 | 4.18 | Quality Assurance/Quality Control | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 4.18
RDY01-045 | 4.19 | Supervision | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 4.19
RDY01-046 | 4.2 | Roadway Meetings (listed below) | Meetings | 0 |  | 0 | 0 | 0 | 0 |  |  | 4.2 | [8 empty] | 2
RDY01-047 |  |  | Travel Time |  |  | 0 | 0 | 0 | 0
RDY01-048 | 4.21 | Field Reviews (listed below) | LS |  |  | 0 | 0 | 0 | 0 |  |  | 4.21
| Roadway Analysis Non-Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0
RDY01-049 | 4.22 | Coordination | LS | 1 | 3% | 0 | 0 | 0 | 0 |  |  | 4.22
| 4. Roadway Analysis Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
|  | Technical Meetings | # Meetings Designer | Travel Time (Hours) | # Meetings PM | Documentation
|  | Typical Section | 0 | 0 | 0
|  | Pavement Design | 0 | 0 | 0
|  | Access Management / Driveways | 0 | 0 | 0
|  | 15% Line and Grade | 0 | 0 | 0
|  | RRR / ECAR Resolution | 0 | 0 | 0
|  | Local Governments (cities, counties, MPO) | 0 | 0 | 0
|  | Work Zone Traffic Control | 0 | 0 | 0
|  | 30/60/90/100% Comment Review Meetings | 0 | 0 | 0
|  | Utility Coordination | 0 | 0 | 0
|  | Risk Register | 0 | 0 | 0
|  | Indpendent Project Cost | 0 | 0 | 0
|  | Other Meetings | 0 | 0 | 0
|  | Subtotal Technical Meetings | 0 | 0 | 0
|  | Progress Meetings (if required by FDOT) | 0 | 0
|  | Phase Review Meetings | 0 | 0
|  | Total Roadway Meetings | 0 | 0
|  | Field Reviews | # of Staff | Site Time (per staff) | Travel Time (per staff) | Total Hours
|  | Field Review #1 | 0 | 0 | 0 | 0
|  | Field Review #2 | 0 | 0 | 0 | 0
|  | Field Review #3 | 0 | 0 | 0 | 0
|  | Field Review #4 | 0 | 0 | 0 | 0
|  | Plans-in-hand Field Review | 0 | 0 | 0 | 0
|  | Total Field Review Hours |  |  |  | 0
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E13: Estimated # of simple typical sections (2-lane flush shoulder or ramps)
Note on E14: Estimated # of standard typical sections (2-lane curbed or multi-lane flush shoulder)
Note on E15: Estimated # of complex typical sections (limited access or multi-lane curbed)
Note on E18: Number of pavement designs
Note on E19: Number of pavement designs
Note on E20: Length of project (miles) to be evaluated.
Note on E21: Length of project (miles) to be evaluated.
Note on E22: Number of concepts to address cross slope correction.
Note on E26: Length of project (miles) to be evaluated.
Note on E27: Number of 1x1 roundabout designs
Note on E28: Number of 1x2 roundabout designs
Note on E29: Number of 2x2 roundabout designs
Note on E32: Estimated # of design elements contained in the Variation Memos
Note on E33: Estimated # of design elements contained in the Formal Variation Memos
Note on E34: Estimated # of design elements contained in the Design Exceptions
Note on E35: Is Design File Setup required? Yes=1 No=0
Note on E36: Length of mainline roadway in miles.
Note on E37: Length of side road or ramps in miles.
Note on E38: Length of frontage road in miles.
Note on E39: Length of mainline roadway in miles.
Note on E40: Length of side road or frontage road in miles.
Note on E41: Length of side road or frontage road in miles.
Note on D42: Driveways, curb ramps, roundabouts,
Note on E43: Is TTCP required? Yes=1 No=0
Note on E44: Is DTAM required? Yes=1 No=0
Note on E45: Total length of project that requires Level II TTCP x number of major phases (total length) to be contained in the design file. Example: 4.00 miles x 3 major phases = 12.00 phase-miles Note: If the project complexity is "Low" or "Below", the recommended hours will be zero. It is assumed that Level I TTCP will be used and TTCP Plans will not be required.
Note on E46: Is Pedestrian TTCP required? Yes=1 No=0
Note on E47: Estimated # of locations requiring TTCP 3D modeling over all phases. 3D model development intended for design clarification.
Note on E48: Is Utility Data Collection & Analysis required? Includes UWS review if necessary. Yes=1 No=0
Note on E49: Length of project in miles. The "Begin Project" and "End Project" mileposts are the basis for computing the project length. Adding additional hours may be considered for side streets when continuous work along the side street exceeds one-quarter mile from the project corridor.
Note on E50: # of Interchanges or Rest Areas.
Note on E51: Is an EQ Report required? Includes setting up report and validating quantities. Yes=1 No=0
Note on E52: Estimated # of phases required: Simple=1 Standard=2-3 Complex=3-4
Note on E53: Estimated number of Engineer Project Cost submittals.
Note on E54: Estimated number of LRE Updates: typically at Phase II, but sometimes for Phase I as well.
Note on E55: Estimated # of TSPs and MSPs.
Note on E58: Is QA/QC required? Yes=1 No=0
Note on F58: Enter % between 5% and 10%
Note on E59: Is Supervision required? Yes=1 No=0
Note on F59: % of technical subtotal.
Note on E60: Estimated # of meetings listed below
Note on F64: % of technical & non-technical subtotal.
Note on E68: Total hours of travel time required for in person meetings.

## 5. Roadway Plans
| Estimator: |  | 5. Roadway Plans Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task |  | Complexity |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
What is the overall project complexity? (See Roadway Guidelines)
RDY02-001 | 5.1 | Key Sheet |  | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 5.1 | [8 empty] | 4
RDY02-002 |  | Signature Sheet |  | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
RDY02-003 | 5.2 | Typical Section Sheets | Typical Sections w/ CADD | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.2 | [8 empty] | 4
RDY02-004 |  |  | Typical Sections w/o CADD | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 10
RDY02-005 |  |  | Partial Sections | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 3
RDY02-006 | 5.3 | Cross Slope Correction Details | Pavement Segments | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.3 | [8 empty] | 8
RDY02-007 | 5.4 | General Notes/Pay Item Notes |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.4 | [5 empty] | 6 | 9 | 12
RDY02-008 | 5.5 | Model Management |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.5 | [5 empty] | 6 | 10 | 14
|  | Project Layout |  | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 6
RDY02-009 | 5.6 | Plan View (Plan Sheets) | Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.6 | 2 | 3 | 4 | 5 | 6
RDY02-010 |  |  | Interchange | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
RDY02-011 |  |  | Roundabout | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
RDY02-012 | 5.7 | Profile View (Plan/Profile Sheets) | Sheet(s) | 0 | Flush Shoulder | 0 | 0 | 0 | 0 |  |  | 5.7 | [8 empty] | 3
RDY02-013 |  |  | Sheet(s) | 0 | Curbed | 0 | 0 | 0 | 0 | [11 empty] | 5
RDY02-014 | 5.8 | Special Profiles | Driveway Curb Return | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.8 | [8 empty] | 2
RDY02-015 |  |  | Intersection RR Xing | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
RDY02-016 | 5.9 | Sidewalk Profiles | Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.9 | [5 empty] | 6 | 12 | 18
RDY02-017 | 5.1 | Interchange Layout Sheet | Interchange | 0 | Standard 2 Levels | 0 | 0 | 0 | 0 |  |  | 5.1 | [8 empty] | 18
RDY02-018 |  |  |  | 0 | Complex 3+ Levels | 0 | 0 | 0 | 0 | [11 empty] | 24
RDY02-019 | 5.11 | Details | Ramp Terminal | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.11 | [8 empty] | 10
RDY02-020 |  |  | Intersection Layout | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 12
RDY02-021 |  |  | Special | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 10
RDY02-022 | 5.12 | Soil Survey Sheets |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.12 | [8 empty] | 2
RDY02-023 | 5.13 | Cross Sections |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.13 | 0.25 | 0.3 | 0.35 | 0.4 | 0.45
RDY02-024 | 5.14 | Temporary Traffic Control Plan | TTC Notes | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.14 | [8 empty] | 2
|  |  | Phasing Notes & Typicals Sheet(s) | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
RDY02-025 |  |  | TTC Plan Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 2 | 4 | 6
RDY02-026 |  |  | Critical Cross Sections | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
RDY02-027 |  |  | TTC Details | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
RDY02-028 | 5.15 | Utility Adjustment Sheets | Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.15 | [5 empty] | 3 | 6 | 9
RDY02-029 | 5.16 | Project Control Sheets |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.16 | [8 empty] | 4
RDY02-030 | 5.17 | Utility Verification Data (SUE) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 5.17 | [8 empty] | 4
| Roadway Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
RDY02-031 | 5.18 | Quality Assurance/Quality Control | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 5.18
RDY02-032 | 5.19 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 5.19
| Roadway Plans Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E12: Is a Key sheet required? Yes=1 No=0
Note on E13: Is a signature sheet required? If Key Sheet is not required, then no hours will be given for the signature sheet. Yes=1 No=0
Note on E14: Estimated # of typical sections needed for project when the CADD files used to create the typical sections are available for use. Includes standard details (e.g., shoulder pavement details or asphalt base curb pad details)
Note on E15: Estimated # of typical sections needed for project when the CADD files used to create typical sections are NOT available for use. Includes standard details (e.g., shoulder pavement details or asphalt base curb pad details)
Note on E16: Estimated # of partial sections. Use partial sections in lieu of creating another full typical section.
Note on E17: Estimated # of roadway segments (areas) requiring cross slope correction details (e.g., typical sections, notes, tables).
Note on E18: Is a general notes/pay item notes sheet required? Yes=1 No=0
Note on E19: Is a model management sheet required? Yes=1 No=0
Note on E20: Is a project layout sheet required? Should be used only when necessary (complex projects or multiple work location projects). Yes=1 No=0
Note on E21: Estimated number of sheets for the plan view.
Note on E22: Estimated # of interchanges located within the project.
Note on E23: Estimated # of roundabouts located within the project.
Note on E24: Estimated number of sheets for the profile view with flush shoulder roadway.
Note on E25: Estimated number of sheets for the profile view with curbed roadway.
Note on E26: Estimated # of driveway or curb return special profiles.
Note on E27: Estimated # of intersection or railroad crossing special profiles.
Note on E28: Estimated number of sheets for the sidewalk profiles.
Note on E29: Estimated # of 2-level Interchanges to be shown on layout sheets.
Note on E30: Estimated # of multi-level Interchanges to be shown on layout sheets.
Note on E31: Estimated # of ramp terminal details to be shown in plans.
Note on E32: Estimated # of intersection layout details to be shown in plans.
Note on E33: Estimated # of special details to be shown in plans.
Note on E34: Is a Soil Survey Sheet required? Yes=1 No=0
Note on E35: Estimated number of cross sections.
Note on E36: Are TTC notes required? Most projects should indicate "Yes". Yes=1 No=0
Note on E37: Estimated number of sheets for phasing notes and phasing typical sections?
Note on E38: Estimated number of sheets for TTC plan. Note: If the project complexity is "Low" or "Below", the recommended hours will be zero. It is assumed that Level I TTCP will be used and TTCP Plans will not be required.
Note on E39: Estimated # of complex critical cross sections (sectional views) to be shown in plans.
Note on E40: Estimated # of TTC Details to be shown in plans.
Note on E41: Estimated number of sheets for the Utility Adjustment Sheets.
Note on E42: Is a Project Control Sheet required? Yes=1 No=0
Note on E43: Is a Utility Verification Sheet required? Yes=1 No=0
Note on E45: Is QA/QC required? Yes=1 No=0
Note on F45: Enter % between 5% and 10%
Note on E46: Is Supervision required? Yes=1 No=0
Note on F46: % of technical subtotal.

## 6a. Drainage Analysis
| Estimator: |  | 6a. Drainage Analysis Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
DRN01-001 | 6a.1 | Base Clearance Analysis | Locations | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 6a.1 | [5 empty] | 4 | 8 | 12
DRN01-002 |  |  | Report | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 8 | 24 | 40
DRN01-003 | 6a.2 | Hydroplaning Analysis | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.2 | [5 empty] | 8 | 24 | 40
DRN01-004 | 6a.3 | Existing Permit Analysis | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.3 | [5 empty] | 4 | 12 | 20
DRN01-005 | 6a.4 | Utility Conflict Matrix (for drainage structures) | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.4 | [5 empty] | 4 | 8 | 16
DRN01-006 | 6a.5 | Noise Barrier Drainage Analysis | Wall Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.5 | [5 empty] | 4 | 8 | 12
DRN01-007 | 6a.6 | Temporary Drainage Analysis | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.6 | [5 empty] | 4 | 20 | 40
DRN01-008 | 6a.7 | Pond Siting Analysis and Report | Basins | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.7 | [5 empty] | 24 | 42 | 60
DRN01-009 |  |  | Report | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 8 | 12 | 16
DRN01-010 | 6a.8 | Analysis of Pipe Video Inspection Report | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.8 | [5 empty] | 8 | 16 | 24
DRN01-011 | 6a.9 | Bridge Hydraulic Report (Canal Crossing or Ped Bridge) | Canal Xing or Ped Bridge | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.9 | [5 empty] | 60 | 80 | 100
DRN01-012 |  | Bridge Hydraulic Report (Main Bridge, Non-Tidal) | w/o Relief Bridges | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 120 | 200 | 300
DRN01-013 |  |  | With Relief Bridges | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 220 | 300 | 400
DRN01-014 |  |  | No-Rise | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 80
DRN01-015 |  | Bridge Hydraulic Report (Main Bridge, Tidal) | w/o Relief Bridges | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 128 | 208 | 308
DRN01-016 |  |  | With Relief Bridges | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 228 | 308 | 408
DRN01-017 |  |  | No-Rise | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 80
DRN01-018 |  | Wave Modeling | Wave Modeling | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 20 | 40 | 60
DRN01-019 | 6a.10 | Design of Minor Cross Drains | Cross Drains | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 6a.10 | [5 empty] | 7
DRN01-020 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 9
DRN01-021 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 11
DRN01-022 |  | Design of Major Cross Drains | Cross Drains | 0 | Simple | 0 | 0 | 0 | 0 | [8 empty] | 14
DRN01-023 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 24
DRN01-024 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 34
DRN01-025 | 6a.11 | Design of Ditches and Side Drains | Ditches (Miles) | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 6a.11 | [5 empty] | 14
DRN01-026 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 20
DRN01-027 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 26
DRN01-028 |  |  | Side Drains | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
DRN01-029 | 6a.12 | Design of Stormwater Management Facility | Ponds | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 6a.12 | [5 empty] | 50
DRN01-030 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 75
DRN01-031 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 100
DRN01-032 |  |  | Cells | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 12 | 16 | 20
DRN01-033 | 6a.13 | Design of Floodplain Compensation | Basins | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.13 | [5 empty] | 36 | 52 | 68
DRN01-034 | 6a.14 | Design of Storm Drains | Drainage Structures | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.14 | [5 empty] | 3 | 3.5 | 4
DRN01-035 |  |  | Non-Standard Structures | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 3
DRN01-036 | 6a.15 | Optional Culvert Material | Drainage Pipes | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.15 | [5 empty] | 0.15 | 0.2 | 0.25 | 2
DRN01-037 | 6a.16 | Design of Trench Drains | Each | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.16 | [5 empty] | 2 | 2.5 | 3
DRN01-038 | 6a.17 | Design of French Drain Systems | Cell | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.17 | [5 empty] | 12 | 16 | 20
DRN01-039 |  | Evaluation of Existing French Drain Systems | Cell | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 2 | 3 | 4
DRN01-040 | 6a.18 | Design of Drainage Wells | Wells | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.18 | [5 empty] | 8 | 10 | 12
DRN01-041 | 6a.19 | Stormwater Runoff Control Concept | Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.19 | [5 empty] | 2 | 4 | 6
DRN01-042 | 6a.20 | Other Drainage Tasks | LS |  |  | 0 | 0 | 0 | 0 |  |  | 6a.20
DRN01-043 | 6a.21 | Drainage Design Documentation Report | Report | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.21 | [5 empty] | 8 | 40 | 80
DRN01-044 |  |  | Exhibits | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
DRN01-045 | 6a.22 | Drainage Quantities for EQ Report | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.22 | [5 empty] | 20 | 30 | 40
DRN01-046 | 6a.23 | Project Cost | Engineer's Project Cost | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.23 | [5 empty] | 2 | 5 | 8
DRN01-047 |  |  | LRE Updates | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 2 | 4 | 6
DRN01-048 | 6a.24 | Technical or Modified Special Provisions | TSPs & MSPs | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.24 | [8 empty] | 6
| Drainage Analysis Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
DRN01-049 | 6a.25 | Quality Assurance/Quality Control | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 6a.25
DRN01-050 | 6a.26 | Supervision | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 6a.26
DRN01-051 | 6a.27 | Drainage Meetings (listed below) | Meetings | 0 |  | 0 | 0 | 0 | 0 |  |  | 6a.27 | [8 empty] | 2
DRN01-052 |  |  | Travel Time |  |  | 0 | 0 | 0 | 0
DRN01-053 | 6a.28 | Field Reviews (listed below) | LS |  |  | 0 | 0 | 0 | 0 |  |  | 6a.28
| Drainage Analysis Non-Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0
DRN01-054 | 6a.29 | Coordination | % | 1 | 3% | 0 | 0 | 0 | 0 |  |  | 6a.29
| Drainage Analysis Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
|  | Technical Meetings | # Meetings Designer | Travel Time (Hours) | # Meetings PM | Documentation
|  | Base Clearance Water Elevation | 0 | 0 | 0
|  | Pond Siting | 0 | 0 | 0
|  | Agency | 0 | 0 | 0
|  | Local Governments (cities, counties) | 0 | 0 | 0
|  | FDOT Drainage | 0 | 0 | 0
|  | Utility Coordination | 0 | 0 | 0
|  | Engineer's Project Cost | 0 | 0 | 0
|  | Indpendent Project Cost | 0 | 0 | 0
|  | Other Meetings | 0 | 0 | 0
|  | Subtotal Technical Meetings | 0 | 0 | 0
|  | Progress Meetings (if required by FDOT) | 0 | 0
|  | Phase Review Meetings | 0 | 0
|  | Total Drainage Meetings | 0 | 0
|  | Field Reviews | # of Staff | Site Time (per staff) | Travel Time (per staff) | Total Hours
|  | Field Review #1 | 0 | 0 | 0 | 0
|  | Field Review #2 | 0 | 0 | 0 | 0
|  | Field Review #3 | 0 | 0 | 0 | 0
|  | Field Review #4 | 0 | 0 | 0 | 0
|  | Plans-in-hand Field Review | 0 | 0 | 0 | 0
|  | Total Field Review Hours |  |  |  | 0
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E11: # of locations
Note on E12: Is a base clearance report required? Yes=1 No=0
Note on E13: Is a hydroplane analysis required? Yes=1 No=0
Note on E14: Is an existing permit analysis required? Yes=1 No=0
Note on E15: Is an Utility Conflict Matrix (for drainage structures) required? Yes=1 No=0
Note on E16: Estimates total length of proposed noise walls.
Note on E17: Is temporary drainage required? Yes=1 No=0
Note on E18: # of basins (based on three ponds per basin)
Note on E19: Is report required? Yes=1 No=0
Note on E20: Is analysis of a pipe video inspection report required? Yes=1 No=0
Note on E21: # of bridges
Note on E22: # of bridges (one bridge per channel)
Note on E23: # of bridges (one bridge per channel)
Note on E24: # of bridge requiring a FEMA "No Rise".
Note on E25: # of bridges (one bridge per channel)
Note on E26: # of bridges (one bridge per channel)
Note on E27: # of bridge requiring a FEMA "No Rise".
Note on E28: # bridges requiring wave calculations and modeling.
Note on E29: # of Simple, Minor Cross Drains Culverts extended a small amount to meet clear zone requirements where Q is estimated by Q= Area x Velocity (4 FPS)
Note on E30: # of Standard, Minor Cross Drains
Note on E31: # of Complex, Minor Cross Drains Identically replaced culverts due to structural problems, with minimal lengthening to meet clear zone requirements. Rational method is used on an easily defined basin.
Note on E32: # of Simple, Major Cross Drains Culvert replaced due significant lengthening for added travel lanes or culvert realignment or both. Rational method is used. No known flooding or scour problems.
Note on E33: # of Standard, Major Cross Drains. Analysis of several alternatives of size and configuration. Drainage basin difficult to define because of flat terrain, drainage basin is larger than appropriate for the Rational Method, but ungaged. Flooding or scour problems are known.
Note on E34: # of Complex, Major Cross Drains. Analysis of several alternatives of size and configuration that are complicated by the need to model basin overtopping, or model more than one culvert location draining the area. Activities above the range may include complex modeling and routing of the drainage area. Includes necessary downstream tailwater determination.
Note on E35: Length of simple ditches in miles. Simple ditches: Normal roadside and median ditches defined by the typical roadway section.
Note on E36: Length of standard ditches in miles. Standard ditches: Special ditches (varying width, depth, and profile). Large offsite areas contributing to roadside ditches.
Note on E37: Length of complex ditches in miles. Complex ditches: Ditches with constrained/variable R/W.
Note on E38: # of Side Drains to be modeled in 3D.
Note on E39: # of Ponds
Note on E40: # of Ponds
Note on E41: # of Ponds
Note on E42: # of cells
Note on E43: # of basins
Note on E44: # of drainage structures
Note on E45: # of Non-Standard Drainage Structures to be modeled in 3D.
Note on E46: # of drainage pipes
Note on E47: # of trench drains
Note on E48: # of cells
Note on E49: # of cells
Note on E50: # of drainage wells
Note on E51: Length of drainage map in miles.
Note on E53: Is drainage documentation report required? Yes=1 No=0
Note on E54: Estimated # of major exhibits, such as drainage delineation, hydrology, and other special exhibits required.
Note on E55: Is an EQR required for the project? Yes=1 No=0
Note on E56: Estimated number of Engineer Project Cost submittals.
Note on E57: Estimated number of LRE Updates: typically at Phase II, but sometimes for Phase I as well.
Note on E58: Estimated # of TSPs and MSPs
Note on E60: Is QA/QC required for Drainage Plans? Yes=1 No=0
Note on F60: Enter % between 5% and 10%
Note on E61: Is Supervision required for Drainage Plans?? Yes=1 No=0
Note on F61: % of technical subtotal.
Note on E66: Is Coordination required? Yes=1 No=0
Note on F66: % of technical subtotal.
Note on E70: Total hours of travel time required for in person meetings.

## 6b. Drainage Plans
| Estimator: |  | 6b. Drainage Plans Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
DRN02-001 | 6b.1 | Drainage Map (Including Interchanges) | Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 6b.1 | [5 empty] | 16 | 32 | 48
DRN02-002 | 6b.2 | Bridge Hydraulics Recommendation Sheets | Bridges | 0 |  | 0 | 0 | 0 | 0 |  |  | 6b.2 | [8 empty] | 32
DRN02-003 | 6b.3 | Drainage Structures | Drainage Structures | 0 |  | 0 | 0 | 0 | 0 |  |  | 6b.3 | [8 empty] | 16 |  |  | 1.25
DRN02-004 |  |  | Details | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 3
DRN02-005 | 6b.4 | Lateral Ditches | Ditches | 0 | Standard | 0 | 0 | 0 | 0 |  |  | 6b.4 | [6 empty] | 8
DRN02-006 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 12
DRN02-007 |  |  | Cross Section Alignments | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
DRN02-008 | 6b.5 | Retention/Detention/Floodplain Compensation Ponds | Ponds | 0 | Standard | 0 | 0 | 0 | 0 |  |  | 6b.5 | [6 empty] | 24
DRN02-009 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 32
DRN02-010 |  |  | Cross Section Alignments | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
| Drainage Plans Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
DRN02-013 | 6b.6 | Quality Assurance/Quality Control | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 6b.6
DRN02-014 | 6b.7 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 6b.7
| Drainage Plans Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E11: # of sheets for Drainage Map.
Note on E12: # of bridges. Multiple matching parallel bridges count as one bridge.
Note on E13: Estimated # of drainage structures. Includes Drainage Plan View, Drainage Profiles, Drainage Cross Sections, Drainage Tabular Information, and Optional Materials Tabulation.
Note on E14: Estimated # of drainage special details. Includes any associated notes.
Note on E15: Estimated # of standard ditches that require plan and profile to be shown in plans.
Note on E16: Estimated # of complex ditches (Hoz. & Vert complex geometry) that require plan and profile to be shown in plans.
Note on E17: Estimated # of ditch alignments that require cross sections.
Note on E18: # of standard ponds.
Note on E19: # of complex ponds.
Note on E20: # of pond alignments that require cross sections.
Note on E22: Is QA/QC required for Drainage Plans? Yes=1 No=0
Note on F22: Enter % between 5% and 10%
Note on E23: Is Supervision required for Drainage Plans?? Yes=1 No=0
Note on F23: % of technical subtotal.

## Selective C&G Guidelines
SELECTIVE CLEARING AND GRUBBING GUIDELINES
The following matrix was developed to determine the overall level of complexity of a Selective Clearing and Grubbing analysis and plan development.
Element | Complexity Guidance |  | Complexity | Rating | Comments |  | N/A | Simple | Standard | Complex
Complexity of ROW | N/A: | No screening or buffering impacts |  | 0
| Simple: | Minor screening or buffering impacts
| Standard: | Significant screening or buffering impacts
| Complex: | Commitments/Stakeholders involved
Roadway Type | N/A: | No Roadway (pond, rest area) |  | 0
| Simple: | Existing Roadway
| Standard: | Roadway Widening
| Complex: | New Roadway Alignment
Roadway Elements | N/A: | No Intersections |  | 0
| Simple: | Minor Intersections
| Standard: | Standard intersections and Interchanges
| Complex: | Complex intersections and Multiple-Level Interchanges
Utility, and Local and State Agency Coordination | N/A: | No coordination |  | 0
| Simple: | Minimum - 2 or less utilities and agencies
| Standard: | Moderate - 3 to 5 utilities and agencies
| Complex: | Extensive - 6 or more utilities and agencies
Number of Species to Eradicate/Preserve | N/A: | None |  | 0
| Simple: | 1-3 Plant Species, 1 Method
| Standard: | 1-6 Plant Species, 1-2 Methods
| Complex: | 7+ Plant Species or 3+ Methods
Sensitive Sites (Wetlands, Submerged, Dune, Sensitive Vegetation, Environmental Permits Required) | N/A: | No sensitive sites involvement |  | 0
| Simple: | Minimal sensitive sites involvement
| Standard: | Part of the project site is sensitive
| Complex: | A large majority of the project site is sensitive
Number of Trees to be Inventoried | N/A: | None |  | 0
| Simple: | 1-20 Trees
| Standard: | 21-50 Trees
| Complex: | 51+ Trees
Number of Trees to be Root or Branch Pruned | N/A: | None |  | 0
| Simple: | 1 to 3 Trees
| Standard: | 4 to 10 Trees
| Complex: | 11 Trees
Tree/Palm Relocation | N/A: | None |  | 0
| Simple: | 1-10 Trees
| Standard: | 11 - 20 Trees
| Complex: | 21+ Trees
Adjacent Property Screening Concerns | N/A: | None |  | 0
| Simple: | Minimum
| Standard: | Moderate
| Complex: | Extensive
Total Points: |  |  |  | 0 | Overall Complexity: | N/A
[5 empty] | Total Points 9 or less: | Simple
[5 empty] | Total Points 10 to 20: | Standard
[5 empty] | Total Points 21 or more: | Complex

## 6c. Selective C&G
| Estimator: |  | 6c. Selective Clearing and Grubbing Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
What is the overall project complexity? (See Selective C&G Guidelines)
SCG01-001 | 6c.1 | Data Collection and Inventory | Roadway Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 6c.1 | [5 empty] | 8 | 12 | 16
SCG01-002 |  |  | Interchanges Rest Areas | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 4 | 6 | 8
SCG01-003 | 6c.2 | Assessment and Disposition Determination |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 6c.2 | [5 empty] | 16 | 24 | 32
SCG01-004 | 6c.3 | Selective C&G Maintenance Report | Report | 0 |  | 0 | 0 | 0 | 0 |  |  | 6c.3 | [8 empty] | 12
SCG01-005 | 6c.4 | Selective C&G Plan | Roadway Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 6c.4 | [5 empty] | 8 | 10 | 12
SCG01-006 |  |  | Interchanges Rest Areas | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 4 | 6 | 8
SCG01-007 |  |  | Details | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
SCG01-008 | 6c.5 | Selective C&G Quantities for EQ Report |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 6c.5 | [5 empty] | 8 | 12 | 16
SCG01-009 | 6c.6 | Project Cost |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 6c.6 | [5 empty] | 3 | 6 | 9
| Selective C&G Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
SCG01-010 | 6c.7 | Quality Assurance/Quality Control | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 6c.7
SCG01-011 | 6c.8 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 6c.8
SCG01-012 | 6c.9 | Selective C&G Meetings (listed below) | Meetings | 0 |  | 0 | 0 | 0 | 0 |  |  | 6c.9 | [8 empty] | 2
SCG01-013 |  |  | Travel Time |  |  | 0 | 0 | 0 | 0
SCG01-014 | 6c.10 | Field Reviews (listed below) | LS |  |  | 0 | 0 | 0 | 0 |  |  | 6c.10
| Selective C&G Non-Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0
SCG01-015 | 6c.11 | Coordination | % | 1 | 3% | 0 | 0 | 0 | 0 |  |  | 6c.11
| Selective C&G Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
|  | Technical Meetings | # Meetings Designer | Travel Time (Hours) | # Meetings PM | Documentation
|  | Local Governments (cities, counties, MPO) | 0 | 0 | 0
|  | 30/60/90/100% Comment Review Meetings | 0 | 0 | 0
|  | Utility Coordination | 0 | 0 | 0
|  | Risk Register | 0 | 0 | 0
|  | Indpendent Project Cost | 0 | 0 | 0
|  | Other Meetings | 0 | 0 | 0
|  | Subtotal Technical Meetings | 0 | 0 | 0
|  | Progress Meetings (if required by FDOT) | 0 | 0
|  | Phase Review Meetings | 0 | 0
|  | Total Meetings | 0 | 0
|  | Field Reviews | # of Staff | Site Time (per staff) | Travel Time (per staff) | Total Hours
|  | Field Review #1 | 0 | 0 | 0 | 0
|  | Field Review #2 | 0 | 0 | 0 | 0
|  | Field Review #3 | 0 | 0 | 0 | 0
|  | Field Review #4 | 0 | 0 | 0 | 0
|  | Plans-in-hand Field Review | 0 | 0 | 0 | 0
|  | Total Field Review Hours |  |  |  | 0
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E12: Length of roadway in miles.
Note on E13: # of Interchanges, rest areas, or similar areas.
Note on E14: Is Assesment and Disposition Table required? 1=yes 0=no
Note on E15: Is a SC&G Maintenance Report required? 1=yes 0=no
Note on E16: Length of roadway in miles.
Note on E17: # of Interchanges, rest areas, or similar areas.
Note on E18: Estimated # of details. This task includes any required notes. The Disposition Chart is considered a detail.
Note on E19: Are quantities required? Yes=1 No=0
Note on E20: Is a Project Cost required? Yes=1 No=0
Note on E22: Is QA/QC required? Yes=1 No=0
Note on F22: Enter % between 5% and 10%
Note on E23: Is Supervision required? Yes=1 No=0
Note on F23: % of technical subtotal.
Note on E24: Estimated # of meeting listed below
Note on E32: Total hours of travel time required for in person meetings.

## Utility Guidelines
UTILITY GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual tasks on typical roadway projects, ranging from a standard 2-lane rural resurfacing project (lower end of range) to a complicated urban reconstruction project (upper end of range). The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual utility tasks. Hours below or above the presented ranges may be applicable based on the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiating hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
Any Verified Vertical Elevation and Horizontal Locaiton (Vvh; SUE) information is addressed in the Survey activity.
The following are general examples of the types of projects which would contain work effort from below the staff hour ranges contained in this handbook to above the ranges. This list is not inclusive, or always exact, but will provide the basis for beginning estimation and negotiation of staff hours for a project.
Low Range Projects
· Rural 2-lane resurfacing (with no 3R improvements).
· Sidewalk project with no utility involvement.
· Minor bridge repair projects (painting or caulking) with no utility involvement.
· Multi-lane limited access resurfacing (no interchange involvement).
· Rural 3R (minor safety improvements)
· Rural Signalization
· Multi-lane limited access resurfacing (safety, earthwork, and minor intersection involvement).
· Intersection improvements without lane additions or signalization
Middle of Range Projects
· Rural 3R (major safety, minor earthwork, realigning ditches).
· Urban 3R (safety, no change to profile grade line, utility exception granted).
· Highway lighting (FDOT Installed).
· Rural widening/resurfacing (minor ROW and earthwork).
· Urban Signalization with utility impact.
· Intersection improvements with lane additions and signalization.
Upper End of Range
· Urban 3R (major safety, extensive above ground feature relocation).
· Rural 2-lane new construction (new alignment, ROW, and earthwork).
· Rural 2-lane to urban multi-lane reconstruction (ROW and intersection involvement).
· Rural or urban 4-lane to 6-lane widening/resurfacing (widening in median, minor ROW, earthwork, and intersection involvement).
· Urban Multi-intersection Signalization with utility impact.
· Rural multi-lane new construction (new alignment, ROW, earthwork and intersection involvement).
· Rural 2-lane to 4-lane (major ROW and earthwork).
· Multi-lane limited access reconstruction (ROW and interchange involvement).
· Multi-lane rural limited access new construction (new alignment, ROW and interchange construction).
· Urban multi-lane new construction (new alignment, ROW and intersection construction).
· Multi-lane limited access, urban reconstruction or new alignment with major interchange involvement (major ROW and interchange
construction, major access management impacts).
· Multi-lane Urban limited access new construction (new alignment, major ROW and, major interchange involvement).

## 7. Utilities
Estimator: |  | 7. Utility Coordination | [7 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
Representing |  | Print Name | [7 empty] | Signature / Date | Video Tutorial - A short webinar for the Utility Plans tab
FDOT District | [10 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Task Parameter |  |  |  | Staff Hours |  |  |  | Comments |  | Task | Task Complexity |  |  | Basis |  |  | Other
|  | Description | Units | Complexity | No. of Submittals | Calculated | Department | Consultant | Negotiated | Provide comments when negotiated hours differ from the calculated hours. |  |  | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
7.1 | Utility Kickoff Meeting (Preparation, Travel, and Attendance) | LS | 0 |  |  | 0 | 0 | 0 | 0 | Note: Refer to Table 7.1 below | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Task Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 7.1
7.2 | Identify Existing Utility Agency Owners (UAOs) (Office hrs only. Field time under Field Reviews) | UAO | 0 |  |  | 0 | 0 | 0 | 0 | Note: Refer to the Guidelines Tab for minimum hour guideline. |  | 7.2 |  |  |  | 1
7.3 | Utility Contacts | UAO | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 7.3 | 1 | 2 | 2
7.4 | Utility Design Alternative | LS | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 7.4 | 2 | 3 | 5
7.5 | Preliminary Utility Meeting (Preparation, Travel, Attendance and Minutes) | LS | 0 |  |  | 0 | 0 | 0 | 0 | Note: Refer to Table 7.5 below |  | 7.5
7.6 | Individual Meetings (Preparation, Travel, Attendance and Minutes) | LS | 0 |  |  | 0 | 0 | 0 | 0 | Note: Refer to Table 7.6 below |  | 7.6
7.7 | Collect and Review Plans and Data from UAO(s) | UAO | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 7.7 | 1 | 2 | 4
7.8 | Subordination of Easements Coordination | Subordination Agreement | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 7.8 |  |  |  | 8
7.9 | Utility Design Meeting (Preparation, Travel, Attendance and Minutes) | LS | 0 |  |  | 0 | 0 | 0 | 0 | Note: Refer to Table 7.9 below |  | 7.9
7.1 | Review Utility Markups & Work Schedules | UAO | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 7.1 | 2 | 5 | 8
7.11 | Processing of Agreements other than UWHCA | UAO | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 7.11 | 2 | 5 | 8
7.12 | Utility Coordination / Follow-up | UAO | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 7.12 | 2 | 5 | 8
7.13 | Utility Constructability Review | UAO | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 7.13 | 2 | 5 | 8
7.14 | Processing Utility Work by Highway Contractor (UWHC) | UAO | 0 | Simple |  | 0 | 0 | 0 | 0 |  |  | 7.14 | 24
|  | UAO | 0 | Standard |  | 0 | 0 | 0 | 0 |  |  |  |  | 40
|  | UAO | 0 | Complex |  | 0 | 0 | 0 | 0 | [5 empty] | 55
7.15 | Contract Plans to UAO(s) | UAO | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 7.15 |  |  |  | 1
7.16 | Certification/Close-Out | UAO | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 7.16 | 1 | 2 | 2
7.17 | Other Utilities Tasks - Meetings |  |  |  |  | 0 | 0 | 0 | 0 | Note: Add any additional hours for scope items to the total number of hours listed below for the 7.17 Other Utility Task Meetings Table below |  | 7.17
Utilities Technical Subtotal | [5 empty] | 0 | 0 | 0 | 0
7.18 | Field Reviews (listed below) | LS |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346 | 7.18
Utilities Non-Technical Subtotal | [5 empty] | 0 | 0 | 0 | 0
7.19 | Interdisciplinary Coordination | % | 1 | 3% |  | 0 | 0 | 0 | 0 |  |  | 7.19
7.2 | Quality Assurance / Quality Control | % | 1 | 5% |  | 0 | 0 | 0 | 0 |  |  | 7.2
Utilities Total | [5 empty] | 0 | 0 | 0 | 0
| 7.1 Utility Kickoff Meeting | # Meetings | # of Staff | Travel Time (Hours) | Mtg Time (Hours) | Prep (Hours) | Totals | # Meetings PM |  | Comments
| Utility Kickoff Meeting | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Utility Kickoff Meeting | [5 empty] | 0 | 0
| 7.5 Preliminary Utility Meeting | # Meetings | # of Staff | Travel Time (Hours) | Mtg Time (Hours) | Prep and Minutes (Hours) | Totals | # Meetings PM |  | Comments
| Preliminary Utility Meeting | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Preliminary Utility Meeting | [5 empty] | 0 | 0
| 7.6 Individual Meetings | # Meetings | # of Staff | Travel Time (Hours) | Mtg Time (Hours) | Prep and Minutes (Hours) | Totals | # Meetings PM |  | Comments
| Individual Meeting #1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Individual Meeting #1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Individual Meeting #1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Individual Meeting #2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Individual Meeting #3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Individual Meetings | [5 empty] | 0 | 0
| 7.9 Utility Design Meeting | # Meetings | # of Staff | Travel Time (Hours) | Mtg Time (Hours) | Prep and Minutes (Hours) | Totals | # Meetings PM |  | Comments
| Utility Design Meeting | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Preliminary Utility Meeting | [5 empty] | 0 | 0
| 7.17 Other Utility Tasks - Meetings | # Meetings | # of Staff | Travel Time (Hours) | Mtg Time (Hours) | Prep and Minutes (Hours) | Totals | # Meetings PM |  | Comments
| Other Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Other Meetings | [5 empty] | 0 | 0
| Progress Meetings (if required by FDOT) | 0 | 0 | 0 | 0 | 0 | 0
| Phase Review Meetings | 0 | 0 | 0 | 0 | 0 | 0
| Total Other Utility Tasks - Meetings | [5 empty] | 0 | 0
| 7.18 Field Reviews |  | # of Staff | Travel Time (per staff) | Field Time (per staff) | Follow-up Time (per Staff) | Total Hours | # Meetings PM |  | Comments
| Field Review #1 as part 7.2 |  | 0 | 0 | 0 | 0 | 0 | 0
| Field Review #2 |  | 0 | 0 | 0 | 0 | 0 | 0
| Plans-in-hand Field Review |  | 0 | 0 | 0 | 0 | 0 | 0
| Total Field Review Hours | [5 empty] | 0 | 0
|  |  | Total # of Meetings for the PM to be transferred to Tab 3 |  |  |  |  | 0
Note on H10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on I10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on K10: Final negotiated staff hours for the project.
Note on E11: Is Kickoff Meeting required? Yes=1 No=0
Note on E12: Estimated # of UAOs
Note on E13: Estimated # of UAOs
Note on G13: Estimated Number of Submittals
Note on E14: Estimated # of Design Alternatives
Note on E15: Is Preliminary Utility Meeting required? Yes=1 No=0
Note on E16: Are Individual Meetings required? Yes=1 No=0
Note on E17: Estimated # of UAOs
Note on G17: Estimated Number of Submittals
Note on E18: Estimated # of Subordination Agreements
Note on E19: Is Design Meeting required? Yes=1 No=0
Note on E20: Estimated # of UAOs
Note on G20: Estimated Number of Submittals
Note on E21: Estimated # of UAOs
Note on E22: Estimated # of UAOs
Note on G22: Estimated Number of Submittals
Note on E23: Estimated # of UAOs
Note on E24: Estimated # of UAOs
Note on E25: Estimated # of UAOs
Note on E26: Estimated # of UAOs
Note on E27: Estimated # of UAOs
Note on E28: Estimated # of UAOs
Note on E33: Is Interdisciplinary Coordination required? Yes=1 No=0
Note on F33: % of technical subtotal.
Note on E34: Is QA / QC required? Yes=1 No=0
Note on F34: Enter % between 5% and 10%
Note on E37: # of staff attending meeting
Note on F37: Total hours of travel time required if the meeting is being held in person.
Note on G37: Total time required for meetings.
Note on E41: # of staff attending meeting
Note on F41: Total hours of travel time required if the meeting is being held in person.
Note on G41: Total time required for meetings.
Note on E45: # of staff attending meeting
Note on F45: Total hours of travel time required if the meeting is being held in person.
Note on G45: Total time required for meetings.
Note on E53: # of staff attending meeting
Note on F53: Total hours of travel time required if the meeting is being held in person.
Note on G53: Total time required for meetings.
Note on E58: # of staff attending meeting
Note on F58: Total hours of travel time required if an in person meeting.
Note on G58: Total time required for meetings.

## Environmental Permit Guidelines
ENVIRONMENTAL PERMITS and ENVIRONMENTAL CLEARANCES GUIDELINES
An effective permitting program is based on a commitment to close coordination and documentation among the CONSULTANT, the Department’s District Permit Coordinator, the Department's Environmental Management Office, the Department’s Project Manager, and regulatory agencies. The CONSULTANT shall meet with the District Permit Coordinator and the Department’s Project Manager prior to developing and submitting all permit application packages to ensure District policies regarding acquisition of environmental permits have been adequately addressed. The Consultant shall meet with the Permit Coordinator and the Environmental Management Office to determine the level of work required for reevaluations and environmental clearances. The CONSULTANT shall proceed with the development and submittal of permit application packages and acquisition of permits based upon the general guidelines provided by the DEPARTMENT. The Environmental Permits Task is generally considered complete once all applicable environmental permits have been obtained.
The CONSULTANT, the Department's Permit Coordinator and the Department's Environmental Management Office will fully review the project's PD&E documents to determine any special requirements or commitments. The Department's staff and the CONSULTANT will also review the regulating agencies requirements for any species issues to fully understand surveying and permitting.
Below is a brief description of a typical low-range project, a typical mid-range project, and a typical high-range project, with examples of each. Some projects, even typical ones, may not fall neatly into one of these categories. Thus, the descriptions and lists below should be used only as a general guide and should never be used in lieu of close coordination among the CONSULTANT, the Department’s District Permit Coordinator, the Department's Environmental Management Office and the Department’s Project Manager.
Typical Low-Range Project- A low-range project will typically not include additional travel lanes, but may include minor wetland or surface water impacts not requiring mitigation. Low-range projects do not typically require authorization for use of Sovereign Submerged Lands and have no involvement with Threatened or Endangered Species. Examples of typical low-range projects may include permitting for:
· Minor intersection improvements
· Culvert extensions
· Bridge replacement (in-kind or rehabilitation)
· Shoulder widening
· Rehabilitation, Resurfacing, and Restoration
· Sidewalks
Permits may be issued from the following agencies:
· DEP/WMD (General Permit)
· USACE (Nationwide)
· USCG (Advanced Approval)
· EPA and/or DEP [National Pollutant Discharge Elimination System (NPDES) Construction General Permit]
· DEP (Coastal Construction Control Line (CCCL) permit)
· Local Government
Typical Mid-range Project - A mid-range project will typically include additional travel lanes, may include wetland or surface water impacts of less than one half acre and may require mitigation. Mid-range projects may require authorization for use of Sovereign Submerged Lands and may have involvement with Threatened or Endangered Species. Examples of typical mid-range projects may include permitting for:
· Multi-lane reconstruction
· Add lane and resurfacing
· Bridge widening or replacement (not in-kind)
· Minor activities waterward of the Coastal Construction Control Line (CCCL)
· Minor activities within Water Management District or local drainage district lands
· Trails
Permits may be issued from the following agencies:
· DEP/WMD (Individual Permit)
· WMD Right of Way Occupancy Permit
· USACE (Nationwide, or Letter of Permission)
· USCG (bridge permit issued by USCG District)
· EPA and/or FDEP [National Pollutant Discharge Elimination System (NPDES) Construction General Permit]
· Department of Environmental Protection (CCCL permit)
· Local Government
· Local Water Control District Right of Way Occupancy Permit
· FDEP Class V deep well permit
Typical High-Range Project – A high-range project will typically include additional travel lanes, wetland or surface water impacts of one half acre or greater, and require mitigation. High-range projects may require authorization for use of Sovereign Submerged Lands and may have involvement with Threatened or Endangered Species. Examples of typical high-range projects may include permitting for:
· New road construction
· New bridge construction
· Multi-lane reconstruction
· Adding lanes and resurfacing
· Bridge widening or replacement (not in-kind)
· Major activities waterward of the CCCL
Permits may be issued from the following agencies:
· DEP/WMD (Individual Permit)
· WMD Right of Way Occupancy Permit
· USACE (Individual Permit or Regional General Permit)
· USCG (bridge permit issued by USCG Headquarters, Washington, D.C.)
· EPA and/or DEP [National Pollutant Discharge Elimination System (NPDES) Construction General Permit]
· DEP (CCCL permit)
· Local Government
· Local Water Control District Right of Way Occupancy Permit
· DEP Class V Deep Well Permit

## 8. Env. Permits and Clearances
Estimator: | [7 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
Environmental Permits and Environmental Clearances
8.1 | Preliminary Project Research | LS | 1 | 0 | 0
Permits
8.2 | Field Work
8.2.1 | Pond Site Alternatives | per pond site | 0 | 0 | 0
8.2.2 | Establish Wetland Jurisdictional Lines and Assessments | LS | 1 | 0 | 0
8.2.3 | Species Surveys | LS | 1 | 0 | 0
8.3 | Agency Verification of Wetland Data | LS | 1 | 0 | 0
8.4 | Complete And Submit All Required Permit Applications
8.4.1 | Complete and Submit All Required Wetland Permit Applications | LS | 1 | 0 | 0
8.4.2 | Complete and Submit All Required Species Permit Applications | LS | 1 | 0 | 0
8.5 | Coordinate and Review Dredge and Fill Sketches | LS | 1 | 0 | 0
8.6 | Complete and Submit Documentation for Coordination and/or USCG Bridge Permit Application
8.6.1 | Prepare and submit required documents for USCG coordination | LS | 1 | 0 | 0
8.6.2 | Complete and submit USCG Bridge Application | LS | 1 | 0 | 0
8.7 | Prepare Water Management District or Local Water Control District Right of Way Occupancy Permit Application | LS | 1 | 0 | 0
8.8 | Prepare Coastal Construction Control Line (CCCL) Permit Application | LS | 1 | 0 | 0
8.9 | Prepare USACE Section 408 Application to Alter a Civil Works Project | LS | 1 | 0 | 0
8.10 | Compensatory Mitigation Plan | LS | 1 | 0 | 0
8.11 | Mitigation Coordination and Meetings | LS | 1 | 0 | 0
8.12 | Regulatory Agency Support | LS | 1 | 0 | 0
8.13 | Other Environmental Permits | LS | 1 | 0 | 0
Environmental Clearances, Reevaluations, and Technical Support
8.14 | Technical support to the Department for Environmental Clearances and Reevaluations (use when consultant provides technical support only)
8.14.1 | NEPA or SEIR Reevaluation | LS | 1 | 0 | 0
8.14.2 | Archaeological and Historical Resources | LS | 1 | 0 | 0
8.14.3 | Section 4(f), 6(f), and ARC | LS | 1 | 0 | 0
8.14.4 | Wetland Impact Analysis | LS | 1 | 0 | 0
8.14.5 | Essential Fish Habitat Impact Analysis | LS | 1 | 0 | 0
8.14.6 | Protected Species and Habitat Impact Analysis | LS | 1 | 0 | 0
8.15 | Preparation of Environmental Clearances and Reevaluations (use when consultant prepares all documents associated with reevaluation)
8.15.1 | NEPA or SEIR Reevaluation | LS | 1 | 0 | 0
8.15.2 | Archaeological and Historical Resources | LS | 1 | 0 | 0
8.15.3 | Section 4(f), 6(f), and ARC | LS | 1 | 0 | 0
8.15.4 | Wetland Impact Analysis | LS | 1 | 0 | 0
8.15.5 | Essential Fish Habitat Impact Analysis | LS | 1 | 0 | 0
8.15.6 | Protected Species and Habitat Impact Analysis | LS | 1 | 0 | 0
Contamination Analysis
8.16 | Contamination Impact Analysis | LS | 1 | 0 | 0
8.17 | Asbestos Survey | LS | 1 | 0 | 0
Environmental Permits and Environmental Clearances/Reevaluations Technical Subtotal |  |  |  |  | 0
8.18 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
8.19 | Quality Assurance/Quality Control | LS | % | 0% | 0
8.20 | Supervision | LS | % | 0% | 0
Environmental Permits and Environmental Clearances Nontechnical Subtotal |  |  |  |  | 0
8.21 | Coordination | LS | % | 0% | 0
8. Environmental Permits and Environmental Clearances Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
WMD |  | EA | 0 | 0 | 0 |  |  | 0
NMFS |  | EA | 0 | 0 | 0 |  |  | 0
USACE |  | EA | 0 | 0 | 0 |  |  | 0
USCG |  | EA | 0 | 0 | 0 |  |  | 0
USFWS |  | EA | 0 | 0 | 0 |  |  | 0
FFWCC |  | EA | 0 | 0 | 0 |  |  | 0
FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 |  | PM attendance at Progress Meetings is manually entered on General Task 3 | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 |  | PM attendance at Phase Review Meetings is manually entered on General Task 3 | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 8.18 |  |  | Carries to Tab 3

## Structures-Guidelines
STRUCTURES GUIDELINES
The staff hour workbook for structural design efforts, the staff hour worksheets, and the typical ranges and descriptions of each task were developed by a committee consisting of individuals from the FDOT and the consulting industry.
It is intended that individuals negotiating work efforts for both the FDOT and the Consultant be experienced structural engineers knowledgeable of the work effort to complete each task. The worksheets are intended to guide negotiators who have hands on experience designing multiple similar projects.
These worksheets are intended to accommodate approximately 90% of the structures being designed. Staff hour ranges are for new, replacement and widened bridges, rural and urban grade separation, interchange bridges, typical trestle and high level water crossings, retaining walls, box culverts, overhead signs, and other miscellaneous structures. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual task. Specific aspects of each individual project should be considered in negotiating hours for each individual task.
Worksheets and ranges have not been developed for rehabilitation or repair projects or exceptionally complex projects (Skyway) or tunnels. It is anticipated that approximately 10% of structure task efforts will fall outside the ranges, either above or below the maximum and minimum values given, respectively.
Activity worksheets have been developed for the different work elements and bridge structure types normally encountered within FDOT projects. Only the Activity worksheets required should be included in the final workbook. Where more than one bridge is included within the project, individual worksheets shall be replicated for each bridge, such as Activity 10 BDR and other bridge task sheets as required. Each of these worksheets will have to be individually linked to the Activity 9 Structures Summary worksheet. It is the Consultant's responsibility to ensure the accuracy of the formulas.
There are many cases where individual tasks included within these activity worksheets are not required. In such cases, the number of units shall be indicated as zero. Individual line items shall not be deleted, nor inserted.
The following Activity worksheets are provided:
· Activity 9 is a summary of the General Tasks, Bridge Development Report, Bridge Design and Production, Retaining Wall Design and Production and Miscellaneous Structure Design and Production activities within the project. The general tasks address the technical tasks associated with the development of the project-based key sheet/index of drawings, general notes, cost estimates and Technical Special Provisions. This worksheet also addresses non-technical tasks such as field reviews, technical meetings and coordination. This Activity worksheet also addresses Quality Assurance/Quality Control, Independent Peer Review and Supervision activities.
Activity 10 addresses Bridge Development Report tasks. The staff hour ranges were developed for general geometric requirements, statical systems, superstructures alternates, substructure alternatives, foundation alternates, vessel collision, scour, precast bridge options, moveable spans, temporary traffic control, constructability requirements, bridge security, retaining wall, quantities, cost estimates and aesthetics consideration. Report preparation including conclusions and recommendations, development of exhibits and supporting documentation are to be included. The option to include Preliminary Plans is also available.
· Activity 11 addresses Temporary Bridge tasks. The staff hour ranges were developed for an ACROW bridge superstructure with layout of substructure and possibly special design of substructure for longer spans or taller substructures than allowed by the Standard Drawings.
· Activity 12 addresses Short Span Concrete bridge tasks. The staff hour ranges were developed for precast and cast-in-place slab type bridges, inverted T and other slab type bridges. Use either Cast-in-Place Bridge or Prestressed Slab Unit Bridge depending on the anticipated structure type.
· Activity 13 addresses Medium Span Concrete bridge tasks. The staff hour ranges were developed for precast, prestressed concrete beam bridges designed as simply supported or continuous over intermediate supports. Use either Simple Span Concrete Design or Continuous Concrete Girder Design depending on the anticipated structure type, unless both systems are used in the same bridge.
· Activity 14 addresses Structural Steel bridge tasks. The staff hour ranges were developed for all steel girder superstructure types, including steel plates, standard rolled shapes, box girders, simple and continuous configurations. The forms were not intended to cover steel frames or trusses. Use either Structural Steel Plate Girder Design or Structural Steel Box Girder Design depending on the anticipated structure type.
· Activity 15 addresses Segmental Concrete bridge tasks. The staff hour ranges were developed for precast, cast-in-place, span-by-span, balanced cantilever, single or multi-celled box, multiple box.
· Activity 16 addresses Bascule bridge tasks. The staff hour ranges were developed for the bascule pier, rest pier, movable span, electrical, mechanical & control house. The worksheet does not cover approach spans. Account for approach spans by adding worksheets for Activity 12, 13, 14 or 15, as applicable. The following task clarifications are provided for Activity 16:
Task 16.23 Stringer Design: This task is only used if deck stringers are anticipated in the design as is typical for steel grid deck bridges where the deck spans transversely between stringers. If a deck system that spans longitudinally between floorbeams is used, this task is not used.
Task 16.27 Sidewalk Bracket Design: This task only used on bridges with sidewalks.
Task 16.28 Roadway Bracket Design: This task is used when cantilever brackets are used to support the deck outside of the main girders as is the most common case.
Task 16.31 Trunnion Girder Design: This task only used for Hopkins (cantilever) trunnion arrangements.
Task 16.39 Bascule GP&E: This task is only used if the bridge length prohibits providing a scale for the overall bridge GP&E that is appropriate for detailing of the movable span (clearances, subcable location, etc.)
Task 16.49 Trunnion Girder: This task only used for Hopkins (cantilever) trunnion arrangements.
Task 16.50 Cylinder Girder: This task only used for hydraulic cylinder driven bascule bridges incorporating independent cylinder girders.
Task 16.55 Pedestrian Rail and Support Details: Use only if bridge has a pedestrian rail.
Task 16.56 Curb and Sidewalk Details: Use only if bridge has a raised curb or sidewalk decking that differs from the roadway deck.
Task 16.64, 16.65, 16.66, 16.67: Mechanical Drive Design: Use tasks 16.64, 16.65, 16.66, & 16.67 for bridges utilizing an electric motor or hydraulic motor drive train with a rack and pinion. If a hydraulic motor is used use these tasks with Task 16.68, Hydraulic Drive Design.
Task 16.68 Hydraulic Drive Design: Use if hydraulic cylinder or hydraulic motor drive is employed in the design. If a hydraulic motor drive is employed, use this task with appropriate tasks from 16.64, 16.65, 16.66, & 16.67.
Task 16.89 PLC Logic: Use only for bridges with Programmable Logic Controllers.
· Activity 17 addresses Retaining Wall tasks. The staff hour ranges were developed for permanent and temporary proprietary walls, cast-in-place retaining walls and other retaining walls.
· Activity 18 addresses Miscellaneous structure tasks. The staff hour ranges were developed for concrete box culverts, strain poles, mast arms, overhead and cantilever sign structures, high mast light foundations, noise barrier walls and special structures.

## 9. Structures Summary
Estimator: | [10 empty] | Enter project name & description |  |  |  | Phase 2
[11 empty] | 999999-1-32-01 |  |  |  | 4
0
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | Design and Production Staffhours |  |  |  | Comments
|  |  | No. of Units | Hours per Unit | No. of Sheets | Total
General Drawings
9.1 | Key Sheet and Index of Drawings | Sheet | 0 | 0 | 0 | 0
9.2 | Project Layout | Sheet | 0 | 0 | 0 | 0
9.3 | General Notes and Bid Item Notes | Sheet | 0 | 0 | 0 | 0
9.4 | Miscellaneous Common Details | Sheet | 0 | 0 | 0 | 0
9.5 | Incorporate Report of Core Borings | Sheet | 0 | 0 | 0 | 0
9.6 | Standard Plans- Bridges | LS | 1 | 0 |  | 0 | [5 empty] | # Bridges
9.7 | Existing Bridge Plans | LS | 1 | 0 |  | 0 | [5 empty] | 0
9.8 | Structures Quantites for EQ Report | Bridges | 0 | Calculated Hours |  | 0 | [5 empty] | Base for 1st bridge | Bridges 2-6 | Bridges > 7 | Subtotal | Walls | Box Culverts
|  | Walls | 0 | [8 empty] | 16 | 12 | 8 | 0 | 2 | 2 | Total
|  | Box Culverts | 0 | 0 | [9 empty] | Subtotal | 0 | 0 | 0 | 0
9.9 | Project Cost | LS | 1 | 0 |  | 0
9.10' | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 |  | 0
Structures - Summary and Miscellaneous Tasks and Drawings Subtotal |  |  |  |  | 0 | 0
Task No. | Task | Total | Task 10 | Task 11 | Task 12 | Task 13 | Task 14 | Task 15 | Task 16 | Task 17 | Task 18
10-16 | Bridge 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-16 | Bridge 2 | 0
10-16 | Bridge 3 | 0
10-16 | Bridge 4 | 0
10-16 | Bridge 5 | 0
10-16 | Bridge 6 | 0
10-16 | Bridge 7 | 0
10-16 | Bridge 8 | 0
10-16 | Bridge 9 | 0
10-16 | Bridge 10 | 0
17 | Retaining Walls | 0 | [7 empty] | 0
18 | Miscellaneous Structures | 0 | [8 empty] | 0
Structures Technical Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task No. | Task | Units | No. of Units | Hours per Unit | Total | Comments
9.11 | Field Reviews | LS | 1 | 0 | 0
9.12 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
9.13 | Quality Assurance/Quality Control | LS | % | 0% | 0
9.14 | Independent Peer Review | LS | 1 | 0 | 0
9.15 | Supervision | LS | % | 0% | 0
Structures Nontechnical Subtotal |  |  |  |  | 0
9.16 | Coordination | LS | 1 | 0 | 0
9. Structures - Summary and Miscellaneous Tasks and Drawings Nontechnical and Coordination Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments |  |  |  | PM Attendance at Meeting Required? | Number
BDR Coordination/Review |  | EA | 0 | 0 | 0 | [5 empty] | 0
90/100% Comment Review |  | EA | 0 | 0 | 0 | [5 empty] | 0
Aesthetics Coordination |  | EA | 0 | 0 | 0 | [5 empty] | 0
Regulatory Agency |  | EA | 0 | 0 | 0 | [5 empty] | 0
Local Governments (cities, counties) |  | EA | 0 | 0 | 0 | [5 empty] | 0
Utility Companies |  | EA | 0 | 0 | 0 | [5 empty] | 0
Risk Register |  | EA | 0 | 0 | 0 | [5 empty] | 0
Independent Project Cost |  | EA | 0 | 0 | 0 | [5 empty] | 0
Other Meetings |  | EA | 0 | 0 | 0 | [5 empty] | 0
Subtotal Technical Meetings |  |  |  |  | 0 | [5 empty] | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  |  |  |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  |  |  |  | - -
Total Meetings |  |  |  |  | 0 | Total Project Manager Meetings (carries to Tab 3) |  |  |  |  | 0
[5 empty] | Carries to 9.12 | [5 empty] | Carries to Tab 3
Note on D19: # of bridges.
Note on E19: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on D20: # of wall segments.
Note on D21: # of box culverts.
Note on E21: Consider adding 4 hours to the calculated hours when required to include EQ Report with Phase II Submittal.

## 10. Structures-BDR
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Requirement
10.1 | Bridge Geometry | LS | 1 | 0 |  | 0
10.2 | Ship Impact Data Collection | LS | 1 | 0 |  | 0
10.3 | Ship Impact Criteria | EA | 0 | 0 |  | 0
Superstructure Alternatives
10.4 | Short Span Concrete Bridge | EA ALT | 0 | 0 |  | 0
10.5 | Medium Span Concrete Bridge | EA ALT | 0 | 0 |  | 0
10.6 | Long Span Concrete Bridge | EA ALT | 0 | 0 |  | 0
10.7 | Structural Steel Bridge | EA ALT | 0 | 0 |  | 0
Foundation & Substructure Alternatives
10.8 | Pier/Bent | EA Type | 0 | 0 |  | 0
10.9 | Shallow Foundations / GRS Abutments | EA Type | 0 | 0 |  | 0
10.1 | Deep Foundations | EA Foundation Evaluated | 0 | 0 |  | 0
Movable Span
10.11 | Data Collection and Design Criteria | LS | 1 | 0 |  | 0
10.12 | Movable Span Geometrics and Clearances | LS | 1 | 0 |  | 0
10.13 | Deck System Evaluation | LS | 1 | 0 |  | 0
10.14 | Framing Plan Development | LS | 1 | 0 |  | 0
10.15 | Main Girder Preliminary Design | LS | 1 | 0 |  | 0
10.16 | Conceptual Span Balance/Counterweight | LS | 1 | 0 |  | 0
10.17 | Support System Development | LS | 1 | 0 |  | 0
10.18 | Drive Power Calculations | LS | 1 | 0 |  | 0
10.19 | Drive System Development | LS | 1 | 0 |  | 0
10.2 | Power and Control Development | LS | 1 | 0 |  | 0
10.21 | Conceptual Pier Design | LS | 1 | 0 |  | 0
10.22 | Foundation Analysis (FL PIER) | LS | 1 | 0 |  | 0
10.23 | Tender Visibility Study | LS | 1 | 0 |  | 0
Other BDR Issues
10.24 | Aesthetics | LS | 1 | 0 |  | 0
10.25 | TTCP/Staged Construction Requirements | LS | 1 | 0 |  | 0
10.26 | Constructibility Requirements | LS | 1 | 0 |  | 0
10.27 | Load Rating for damaged/widened structures | EA Unit | 1 | 0 |  | 0
10.28 | Quantity and Cost Estimates | EA ALT | 0 | 0 |  | 0
10.29 | Quantity and Cost Estimates - Movable Span | LS | 1 | 0 |  | 0
10.3 | Wall Type Justification | LS | 1 | 0 |  | 0
Report Preparation
10.31 | Exhibits | EA SHEET | 0 | 0 |  | 0
10.32 | Exhibits - Movable Span | EA SHEET | 0 | 0 |  | 0
10.33 | Report Preparation | LS | 1 | 0 |  | 0
10.34 | Report Preparation - Movable Span | LS | 1 | 0 |  | 0
10.35 | BDR Submittal Package | LS | 1 | 0 |  | 0
10. Structures - Bridge Development Report Total | [5 empty] | 0
When ONLY 30% plans are final deliverable, use Task Nos. as shown for applicable bridge types for project Activities 12 thru 16. Staffhours to be negotiated and scaled appropriately.

## 11. Temporary Bridge
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans [Tasks under Activity 11 are for Prefabricated Temporary Bridges only]
11.1 | Overall Bridge Final Geometry | LS | 1 | 0 |  | 0
11.2 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
11.3 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
End Bent Design and Plans
11.4 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
11.5 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Intermediate Bent Design and Plans
11.6 | Intermediate Bent Structural Design | EA Design | 0 | 0 |  | 0
11.7 | Intermediate Bent Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
11.8 | Foundation Layout | EA | 0 | 0 |  | 0
11. Temporary Bridge Total |  |  |  |  | 0 | 0

## 12. Short Span Concrete
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans
12.1 | Overall Bridge Final Geometry | LS | 1 | 0 |  | 0
12.2 | Expansion/Contraction Analysis | EA Unit | 0 | 0 |  | 0
12.3 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
12.4 | Construction Staging | Sheet | 0 | 0 | 0 | 0
12.5 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0 | 0
12.6 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
End Bent Design and Plans
12.7 | End Bent Geometry | EA End Bent | 0 | 0 |  | 0
12.8 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
12.9 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
12.1 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Intermediate Bent Design and Plans
12.11 | Bent Geometry | EA Bent | 0 | 0 |  | 0
12.12 | Bent Stability Analysis | EA Analysis | 0 | 0 |  | 0
12.13 | Bent Structural Design | EA Design | 0 | 0 |  | 0
12.14 | Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
12.15 | Bent Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
12.16 | Foundation Layout | Sheet | 0 | 0 | 0 | 0
Miscellaneous Superstructure Design and Plans
12.17 | Finish Grade Elevation Calculation | LS | 1 | 0 |  | 0
12.18 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
Cast-in-Place Slab Bridges
12.19 | Bridge Deck Design | EA Unit | 0 | 0 |  | 0
12.2 | Superstructure Plan | Sheet | 0 | 0 | 0 | 0
12.21 | Superstructure Sections and Details | Sheet | 0 | 0 | 0 | 0
Prestressed Slab Unit Bridges
12.22 | Prestressed Slab Unit Design | EA Design | 0 | 0 |  | 0
12.23 | Prestressed Slab Unit Layout | Sheet | 0 | 0 | 0 | 0
12.24 | Prestressed Slab Unit Details and Schedule | Sheet | 0 | 0 | 0 | 0
12.25 | Deck Topping Reinforcing Layout | Sheet | 0 | 0 | 0 | 0
12.26 | Superstructure Sections and Details | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar List
12.27 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Load Rating
12.28 | Load Ratings | EA Unit | 0 | 0 |  | 0
12. Structures - Short Span Concrete Bridge Total |  |  |  |  | 0 | 0

## 13. Medium Span Concrete
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans
13.1 | Overall Bridge Final Geometry | LS | 1 | 0 |  | 0
13.2 | Expansion/Contraction Analysis | EA Unit | 0 | 0 |  | 0
13.3 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
13.4 | Construction Staging | Sheet | 0 | 0 | 0 | 0
13.5 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0 | 0
13.6 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
End Bent Design and Plans
13.7 | End Bent Geometry | EA End Bent | 0 | 0 |  | 0
13.8 | Wingwall Design and Geometry | EA End Bent | 0 | 0 |  | 0
13.9 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
13.1 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
13.11 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Intermediate Bent Design and Plans
13.12 | Bent Geometry | EA Bent | 0 | 0 |  | 0
13.13 | Bent Stability Analysis | EA Design | 0 | 0 |  | 0
13.14 | Bent Structural Design | EA Design | 0 | 0 |  | 0
13.15 | Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
13.16 | Bent Details | Sheet | 0 | 0 | 0 | 0
Pier Design and Plans
13.17 | Pier Geometry | EA Pier | 0 | 0 |  | 0
13.18 | Pier Stability Analysis | EA Design | 0 | 0 |  | 0
13.19 | Pier Structural Design | EA Design | 0 | 0 |  | 0
13.2 | Pier Plan and Elevation | Sheet | 0 | 0 | 0 | 0
13.21 | Pier Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
13.22 | Foundation Layout | Sheet | 0 | 0 | 0 | 0
Superstructure Deck Design and Plans
13.23 | Finish Grade Elevation (FGE) Calculation | LS | 1 | 0 |  | 0
13.24 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
13.25 | Bridge Deck Design | EA Section | 0 | 0 |  | 0
13.26 | Bridge Deck Reinforcing and Concrete Quantities | EA Unit | 0 | 0 |  | 0
13.27 | Diaphragm Design | EA Section | 0 | 0 |  | 0
13.28 | Superstructure Plan | Sheet | 0 | 0 | 0 | 0
13.29 | Superstructure Section | Sheet | 0 | 0 | 0 | 0
13.3 | Miscellaneous Superstructure Details | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar Lists
13.31 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Continuous Concrete Girder Design
13.32 | Section Properties | LS | 1 | 0 |  | 0
13.33 | Material Properties | LS | 1 | 0 |  | 0
13.34 | Construction Sequence | EA Unit | 0 | 0 |  | 0
13.35 | Tendon Layouts | EA Unit | 0 | 0 |  | 0
13.36 | Live Load Analysis | EA Unit | 0 | 0 |  | 0
13.37 | Temperature Gradient | EA Unit | 0 | 0 |  | 0
13.38 | Time Dependent Analysis | EA Unit | 0 | 0 |  | 0
13.39 | Stress Summary | EA Unit | 0 | 0 |  | 0
13.4 | Ultimate Moments | EA Unit | 0 | 0 |  | 0
13.41 | Ultimate Shear | EA Unit | 0 | 0 |  | 0
13.42 | Construction Loading | EA Unit | 0 | 0 |  | 0
13.43 | Framing Plan | Sheet | 0 | 0 | 0 | 0
13.44 | Girder Elevation, including Grouting Plan and Vent Locations | Sheet | 0 | 0 | 0 | 0
13.45 | Girder Details | Sheet | 0 | 0 | 0 | 0
13.46 | Erection Sequence | Sheet | 0 | 0 | 0 | 0
13.47 | Splice Details | Sheet | 0 | 0 | 0 | 0
13.48 | Girder Deflections and Camber | Sheet | 0 | 0 | 0 | 0
Simple Span Concrete Design
13.49 | Prestressed Beam | EA Design | 0 | 0 |  | 0
13.5 | Prestressed Beam Schedules | Sheet | 0 | 0 | 0 | 0
13.51 | Framing Plan | Sheet | 0 | 0 | 0 | 0
Beam Stability
13.52 | Beam/girder stability | EA Unit | 0 | 0 |  | 0
Bearing
13.53 | Bearing pad and bearing plate design | Type/ Span | 0 | 0 |  | 0
13.54 | Bearing pad and bearing plate details | Sheet | 0 | 0 | 0 | 0
Load Rating
13.55 | Load Ratings | Per Beam | 0 | 0 |  | 0
13. Structures - Medium Span Concrete Bridge Total |  |  |  |  | 0 | 0

## 14. Structures-Structural Steel
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans
14.1 | Overall Bridge Final Geometry | LS | 1 | 0 |  | 0
14.2 | Expansion/Contraction Analysis | EA Unit | 0 | 0 |  | 0
14.3 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
14.4 | Construction Staging | Sheet | 0 | 0 | 0 | 0
14.5 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0 | 0
14.6 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
End Bent Design and Plans
14.7 | End Bent Geometry | EA Bent | 0 | 0 |  | 0
14.8 | Wingwall Design and Geometry | EA Bent | 0 | 0 |  | 0
14.9 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
14.1 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
14.11 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Intermediate Bent Design and Plans
14.12 | Bent Geometry | EA bent | 0 | 0 |  | 0
14.13 | Bent Stability Analysis | EA design | 0 | 0 |  | 0
14.14 | Bent Structural Design | EA design | 0 | 0 |  | 0
14.15 | Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
14.16 | Bent Details | Sheet | 0 | 0 | 0 | 0
Pier Design and Plans
14.17 | Pier Geometry | EA pier | 0 | 0 |  | 0
14.18 | Pier Stability Analysis | EA design | 0 | 0 |  | 0
14.19 | Pier Structural Design | EA design | 0 | 0 |  | 0
14.2 | Pier Plan and Elevation | Sheet | 0 | 0 | 0 | 0
14.21 | Pier Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
14.22 | Foundation Layout | Sheet | 0 | 0 | 0 | 0
Superstructure Deck Design and Plans
14.23 | Finish Grade Elevation (FGE) Calculation | LS | 1 | 0 |  | 0
14.24 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
14.25 | Bridge Deck Design | EA section | 0 | 0 |  | 0
14.26 | Bridge Deck Reinforcing and Concrete Quantities | EA Unit | 0 | 0 |  | 0
14.27 | Superstructure Plan | Sheet | 0 | 0 | 0 | 0
14.28 | Superstructure Section | Sheet | 0 | 0 | 0 | 0
14.29 | Miscellaneous Bridge Deck Details | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar Lists
14.3 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Structural Steel Plate Girder Design
14.31 | Unit Modeling | EA Unit | 0 | 0 |  | 0
14.32 | Section Design | EA Unit | 0 | 0 |  | 0
14.33 | Stiffener Design and Locations | EA Unit | 0 | 0 |  | 0
14.34 | Cross-Frame Design | EA Unit | 0 | 0 |  | 0
14.35 | Connections | EA Unit | 0 | 0 |  | 0
14.36 | Bearing Assembly Design and Detailing (with Jacking Analysis) | EA Unit | 0 | 0 |  | 0
14.37 | Splice Design | EA Unit | 0 | 0 |  | 0
14.38 | Shear Stud Connectors | EA Unit | 0 | 0 |  | 0
14.39 | Deflection Analysis | EA Unit | 0 | 0 |  | 0
14.4 | Framing Plan | Sheet | 0 | 0 | 0 | 0
14.41 | Girder Elevation | Sheet | 0 | 0 | 0 | 0
14.42 | Structural Steel Details | Sheet | 0 | 0 | 0 | 0
14.43 | Splice Details | Sheet | 0 | 0 | 0 | 0
14.44 | Girder Deflections and Camber | Sheet | 0 | 0 | 0 | 0
Structural Steel Box Girder Design
14.45 | Unit Modeling | EA Unit | 0 | 0 |  | 0
14.46 | Section Design | EA Unit | 0 | 0 |  | 0
14.47 | Stiffener Design and Locations | EA Unit | 0 | 0 |  | 0
14.48 | Interior Cross-Frame Design | EA Unit | 0 | 0 |  | 0
14.49 | Exterior Cross-Frame Design | EA Unit | 0 | 0 |  | 0
14.5 | Connections | EA Unit | 0 | 0 |  | 0
14.51 | Bearing Assembly Design and Detailing (with Jacking Analysis) | EA Unit | 0 | 0 |  | 0
14.52 | Splice Design | EA Unit | 0 | 0 |  | 0
14.53 | Shear Stud Connectors | EA Unit | 0 | 0 |  | 0
14.54 | Deflection Analysis | EA Unit | 0 | 0 |  | 0
14.55 | Framing Plan | Sheet | 0 | 0 | 0 | 0
14.56 | Girder Elevation | Sheet | 0 | 0 | 0 | 0
14.57 | Structural Steel Details | Sheet | 0 | 0 | 0 | 0
14.58 | Splice Details | Sheet | 0 | 0 | 0 | 0
14.59 | Girder Deflections and Camber | Sheet | 0 | 0 | 0 | 0
Erection Scheme
14.6 | Erection scheme analysis | EA Critical Stage | 0 | 0 |  | 0
14.61 | Erection scheme | Sheet | 0 | 0 | 0 | 0
Load Rating
14.62 | Load Rating | EA Unit | 0 | 0 |  | 0
14. Structures - Structural Steel Bridge Total |  |  |  |  | 0 | 0

## 15.Str.-Segmental Concrete
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans
15.1 | Final Bridge Geometry | LS | 1 | 0 |  | 0
15.2 | Casting Geometry Calculation | LS | 1 | 0 |  | 0
15.3 | Finish Grade Geometry Calculation | LS | 1 | 0 |  | 0
15.4 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
15.5 | Construction Schedule | LS | 1 | 0 |  | 0
15.6 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
15.7 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0 | 0
15.8 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
15.9 | Existing Bridge Plans | LS | 1 | 0 |  | 0
End Bent Design and Plans
15.1 | End Bent Geometry | EA Bent | 0 | 0 |  | 0
15.11 | Wingwall Geometry and Design | EA Bent | 0 | 0 |  | 0
15.12 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
15.13 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
15.14 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Pier Design and Plans
15.15 | Pier Geometry | EA Pier | 0 | 0 |  | 0
15.16 | Pier Stability Analysis | EA Analysis | 0 | 0 |  | 0
15.17 | Pier Construction Loads | EA Design | 0 | 0 |  | 0
15.18 | Pier Structural Design | EA Design | 0 | 0 |  | 0
15.19 | Pier Plan and Elevation | Sheet | 0 | 0 | 0 | 0
15.2 | Pier Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
15.21 | Foundation Layout | Sheet | 0 | 0 | 0 | 0
Longitudinal Analysis
15.22 | Section Properties | LS | 1 | 0 |  | 0
15.23 | Material Properties | LS | 1 | 0 |  | 0
15.24 | Superimposed Dead Loads | LS | 1 | 0 |  | 0
15.25 | Construction Sequence | EA Unit | 0 | 0 |  | 0
15.26 | Tendon Layouts | EA Unit | 0 | 0 |  | 0
15.27 | Live Load Analysis | EA Unit | 0 | 0 |  | 0
15.28 | Temperature Gradient | EA Unit | 0 | 0 |  | 0
15.29 | Time Dependent Analysis | EA Unit | 0 | 0 |  | 0
15.3 | Stress Summary | EA Unit | 0 | 0 |  | 0
15.31 | Ultimate Moments | EA Unit | 0 | 0 |  | 0
15.32 | Ultimate Shear | EA Unit | 0 | 0 |  | 0
15.33 | Construction Loading | EA Unit | 0 | 0 |  | 0
Transverse Analysis
15.34 | Time Dependent Analysis | EA Typ. Section | 0 | 0 |  | 0
15.35 | Live Load Analysis | EA Typ. Section | 0 | 0 |  | 0
15.36 | Temperature Gradient | EA Typ. Section | 0 | 0 |  | 0
15.37 | Stress Summary | EA Typ. Section | 0 | 0 |  | 0
15.38 | Ultimate Moments | EA Typ. Section | 0 | 0 |  | 0
15.39 | Construction Loading | EA Typ. Section | 0 | 0 |  | 0
Superstructure Design
15.4 | Typical Segment | LS | 1 | 0 |  | 0
15.41 | Pier Segment | EA Type | 0 | 0 |  | 0
15.42 | Expansion Joint Segment | EA Type | 0 | 0 |  | 0
15.43 | Blister Details | EA Type | 0 | 0 |  | 0
15.44 | Deviator Blocks | EA Type | 0 | 0 |  | 0
15.45 | Bearings | LS | 1 | 0 |  | 0
15.46 | Expansion Joints | EA Design | 0 | 0 |  | 0
15.47 | Special Analysis | EA Case | 0 | 0 |  | 0
Superstructure Plans
15.48 | Typical Sections | Sheet | 0 | 0 | 0 | 0
15.49 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
15.5 | Segment Layout/Designations | Sheet | 0 | 0 | 0 | 0
15.51 | Typical Segments | Sheet | 0 | 0 | 0 | 0
15.52 | Variable Depth Segments | Sheet | 0 | 0 | 0 | 0
15.53 | Pier Segments | Sheet | 0 | 0 | 0 | 0
15.54 | Expansion Joint Segments | Sheet | 0 | 0 | 0 | 0
15.55 | CIP Closure Joint Details | Sheet | 0 | 0 | 0 | 0
15.56 | Casting Geometry | Sheet | 0 | 0 | 0 | 0
15.57 | Integrated 3D Drawings | Sheet | 0 | 0 | 0 | 0
Post-Tensioning Details
15.58 | Bulkhead Details | Sheet | 0 | 0 | 0 | 0
15.59 | Transverse Tendon Layout | Sheet | 0 | 0 | 0 | 0
15.6 | Longitudinal Tendon Layout | Sheet | 0 | 0 | 0 | 0
15.61 | Temporary Post-Tensioning | Sheet | 0 | 0 | 0 | 0
15.62 | Quantities and Stressing Schedule | Sheet | 0 | 0 | 0 | 0
15.63 | Future Post-Tensioning | Sheet | 0 | 0 | 0 | 0
15.64 | Anchorage Blisters | Sheet | 0 | 0 | 0 | 0
15.65 | Deviation Blocks | Sheet | 0 | 0 | 0 | 0
15.66 | PT Grouting Plan Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Details
15.67 | Erection Sequence and Details | Sheet | 0 | 0 | 0 | 0
15.68 | Access Opening Details | Sheet | 0 | 0 | 0 | 0
15.69 | Bearings | Sheet | 0 | 0 | 0 | 0
15.7 | Expansion Joints | Sheet | 0 | 0 | 0 | 0
15.71 | Vermin Screen Details | Sheet | 0 | 0 | 0 | 0
15.72 | Railing Details | Sheet | 0 | 0 | 0 | 0
15.73 | Lighting and Luminaries | Sheet | 0 | 0 | 0 | 0
15.74 | Architectural Details | Sheet | 0 | 0 | 0 | 0
15.75 | Special Systems | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar Lists
15.76 | Preparation of Reinforcing Bar Lists | Sheet | 0 | 0 | 0 | 0
Load Rating
15.77 | Load Ratings (LRFR) | EA Unit | 0 | 0 |  | 0
| 15. Structures - Segmental Concrete Bridge Total |  |  |  | 0 | 0

## 16. Structures-Movable Span
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
Final Design Bascule Pier
16.1 | Pier Deck | LS | 1 | 0 |  | 0
16.2 | Leaf/Pier Clearance Diagrams | EA Diagram | 0 | 0 |  | 0
16.3 | Load Shoe Columns | LS | 1 | 0 |  | 0
16.4 | Trunnion Columns | LS | 1 | 0 |  | 0
16.5 | Foundations | LS | 1 | 0 |  | 0
16.6 | Footing | LS | 1 | 0 |  | 0
16.7 | Seal | LS | 1 | 0 |  | 0
16.8 | Back Wall (Approach Span Bearings) Closed Piers Only | LS | 1 | 0 |  | 0
16.9 | Bascule Pier Deck Elevations | EA Pier | 0 | 0 |  | 0
Bascule Pier Dimensions - Detailing
16.1 | Pier Plan Views | Sheet | 0 | 0 | 0 | 0
16.11 | Pier Elevation Views | Sheet | 0 | 0 | 0 | 0
16.12 | Pier Sections | Sheet | 0 | 0 | 0 | 0
Bascule Pier Reinforcing Details
16.13 | Pier Reinforcing | Sheet | 0 | 0 | 0 | 0
Bascule Pier Miscellaneous Details
16.14 | Pier Barrier Details | Sheet | 0 | 0 | 0 | 0
16.15 | Stair Details | Sheet | 0 | 0 | 0 | 0
16.16 | Handrail Details | Sheet | 0 | 0 | 0 | 0
16.17 | Ladder and Hatch Details | Sheet | 0 | 0 | 0 | 0
16.18 | Pier Equipment | Sheet | 0 | 0 | 0 | 0
16.19 | Bascule Pier Notes and Summary of Quantities | Sheet | 0 | 0 | 0 | 0
16.2 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
Bascule Leaf Design
16.21 | Deck Design | LS | 1 | 0 |  | 0
16.22 | Sidewalk Design | LS | 1 | 0 |  | 0
16.23 | Stringer Design | LS | 1 | 0 |  | 0
16.24 | Typical Floorbeam Design | LS | 1 | 0 |  | 0
16.25 | End Floorbeam Design | LS | 1 | 0 |  | 0
16.26 | Deep Floorbeam Design | LS | 1 | 0 |  | 0
16.27 | Sidewalk Bracket Design | LS | 1 | 0 |  | 0
16.28 | Roadway Bracket Design | LS | 1 | 0 |  | 0
16.29 | Main Girder Influence Lines | LS | 1 | 0 |  | 0
16.3 | Main Girder Design | LS | 1 | 0 |  | 0
16.31 | Trunnion Girder Design | LS | 1 | 0 |  | 0
16.32 | Main Girder Camber Data | LS | 1 | 0 |  | 0
16.33 | Leaf Lateral Bracing Design | LS | 1 | 0 |  | 0
16.34 | Counterweight Design | LS | 1 | 0 |  | 0
16.35 | Live Load Shoe Design | LS | 1 | 0 |  | 0
16.36 | Barrier Design | LS | 1 | 0 |  | 0
16.37 | Deck Elevations | LS | 1 | 0 |  | 0
16.38 | Balance Calculations | LS | 1 | 0 |  | 0
Bascule Leaf Detailing
16.39 | Bascule GP&E | Sheet | 0 | 0 | 0 | 0
16.4 | Bascule Leaf Notes | Sheet | 0 | 0 | 0 | 0
16.41 | Framing Plan | Sheet | 0 | 0 | 0 | 0
16.42 | Flooring Plan and Details | Sheet | 0 | 0 | 0 | 0
16.43 | Typical Section and Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
16.44 | Girder Elevation | Sheet | 0 | 0 | 0 | 0
16.45 | Girder Details | Sheet | 0 | 0 | 0 | 0
16.46 | Camber Layout | Sheet | 0 | 0 | 0 | 0
16.47 | Floor Beams | Sheet | 0 | 0 | 0 | 0
16.48 | Counterweight Girder/Box | Sheet | 0 | 0 | 0 | 0
16.49 | Trunnion Girder | Sheet | 0 | 0 | 0 | 0
16.5 | Cylinder Girder | Sheet | 0 | 0 | 0 | 0
16.51 | Lateral Bracing Details | Sheet | 0 | 0 | 0 | 0
16.52 | Counterweight Bracing Details | Sheet | 0 | 0 | 0 | 0
16.53 | Joint Details | Sheet | 0 | 0 | 0 | 0
16.54 | Traffic Barrier Details | Sheet | 0 | 0 | 0 | 0
16.55 | Pedestrian Rail and Support Details | Sheet | 0 | 0 | 0 | 0
16.56 | Curb and Sidewalk Details | Sheet | 0 | 0 | 0 | 0
16.57 | Barrier and Sidewalk Bracket Details | Sheet | 0 | 0 | 0 | 0
16.58 | Counterweight Details | Sheet | 0 | 0 | 0 | 0
16.59 | Stress Table or Influence Lines | Sheet | 0 | 0 | 0 | 0
Mechanical Design
16.6 | Final Power Requirements | LS | 1 | 0 |  | 0
16.61 | Trunnion Assembly | LS | 1 | 0 |  | 0
16.62 | Span Locks | LS | 1 | 0 |  | 0
16.63 | Sump Pumps | LS | 1 | 0 |  | 0
Mechanical Drive Design
16.64 | Drive Shafts, Couplings, Keys, Bearings and Supports | LS | 1 | 0 |  | 0
16.65 | Rack & Pinion, Bearings and Supports | LS | 1 | 0 |  | 0
16.66 | Drive Train | LS | 1 | 0 |  | 0
16.67 | Motor Brakes & Machinery Brakes | LS | 1 | 0 |  | 0
Hydraulic Drive Design
16.68 | Hydraulic Drive | LS | 1 | 0 |  | 0
Machinery Detailing
16.69 | Machinery Layout | Sheet | 0 | 0 | 0 | 0
16.7 | Machinery Elevation | Sheet | 0 | 0 | 0 | 0
16.71 | Machinery Section | Sheet | 0 | 0 | 0 | 0
16.72 | Trunnion Assembly | Sheet | 0 | 0 | 0 | 0
16.73 | Drive Details | Sheet | 0 | 0 | 0 | 0
16.74 | Span Locks | Sheet | 0 | 0 | 0 | 0
Electrical Design
16.75 | Load Analysis | LS | 1 | 0 |  | 0
16.76 | Power Distribution | LS | 1 | 0 |  | 0
16.77 | Drive Equipment | LS | 1 | 0 |  | 0
16.78 | Bridge Controls | LS | 1 | 0 |  | 0
16.79 | Grounding | LS | 1 | 0 |  | 0
16.8 | Lightning and Surge Suppression | LS | 1 | 0 |  | 0
16.81 | Pier Lighting | LS | 1 | 0 |  | 0
Electrical Detailing
16.82 | Electrical Plan and Elevation | Sheet | 0 | 0 | 0 | 0
16.83 | Electrical Symbols and Abbreviations | Sheet | 0 | 0 | 0 | 0
16.84 | Single/Three Line Diagram | Sheet | 0 | 0 | 0 | 0
16.85 | Panelboard and Light Fixture Schedules | Sheet | 0 | 0 | 0 | 0
16.86 | Wire and Conduit Schedules and Diagrams | Sheet | 0 | 0 | 0 | 0
16.87 | Control Desk/Panel Layout | Sheet | 0 | 0 | 0 | 0
16.88 | Control Schematics | Sheet | 0 | 0 | 0 | 0
16.89 | PLC Logic | Sheet | 0 | 0 | 0 | 0
16.9 | Communication System | Sheet | 0 | 0 | 0 | 0
16.91 | Navigation Lighting Details | Sheet | 0 | 0 | 0 | 0
16.92 | Pedestrian Gate, Traffic Gate and Barrier Details | Sheet | 0 | 0 | 0 | 0
16.93 | Submarine Cable | Sheet | 0 | 0 | 0 | 0
16.94 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
Control House
16.95 | Architectural Design | LS | 1 | 0 |  | 0
16.96 | Architectural Details | Sheet | 0 | 0 | 0 | 0
16.97 | Structural Design | LS | 1 | 0 |  | 0
16.98 | Structural Details | Sheet | 0 | 0 | 0 | 0
16.99 | HVAC/Plumbing Design | LS | 1 | 0 |  | 0
16.1 | HVAC/Plumbing/Electrical Cables | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar Lists
16.101 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Load Rating
16.102 | Load Ratings | LS | 1 | 0 |  | 0
16. Structures - Movable Span Total |  |  |  |  | 0 | 0

## 17. Str-Retaining Walls
Estimator: | [6 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Requirements
17.1 | Key Sheet | Sheet | 0 | 0 | 0 | 0
17.2 | Horizontal Wall Geometry | Per Wall | 0 | 0 |  | 0
Permanent Proprietary Walls
17.3 | Vertical Wall Geometry | Per Wall | 0 | 0 |  | 0
17.4 | Semi-Standard Drawings | Sheet | 0 | 0 | 0 | 0
17.5 | Wall Plan and Elevations (Control Drawings) | Sheet | 0 | 0 | 0 | 0
17.6 | Details | Sheet | 0 | 0 | 0 | 0
Temporary Proprietary Walls
17.7 | Vertical Wall Geometry | Per Wall | 0 | 0 |  | 0
17.8 | Semi-Standard Drawings | Sheet | 0 | 0 | 0 | 0
17.9 | Wall Plan and Elevations (Control Drawings) | Sheet | 0 | 0 | 0 | 0
17.1 | Details | Sheet | 0 | 0 | 0 | 0
Cast-in-Place Retaining Walls
17.11 | Design | EA Design | 0 | 0 |  | 0
17.12 | Vertical Wall Geometry | EA Wall | 0 | 0 |  | 0
17.13 | General Notes | Sheet | 0 | 0 | 0 | 0
17.14 | Wall Plan and Elevations (Control Drawings) | Sheet | 0 | 0 | 0 | 0
17.15 | Sections and Details | Sheet | 0 | 0 | 0 | 0
17.16 | Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Other Retaining Walls and Bulkheads
17.17 | Design | EA Design | 0 | 0 |  | 0
17.18 | Vertical Wall Geometry | EA Wall | 0 | 0 |  | 0
17.19 | General Notes, Tables and Misc. Details | Sheet | 0 | 0 | 0 | 0
17.2 | Wall Plan and Elevations | Sheet | 0 | 0 | 0 | 0
17.21 | Details | Sheet | 0 | 0 | 0 | 0
17. Structures - Retaining Walls Total |  |  |  |  | 0 | 0

## 18. Structures-Miscellaneous
Estimator: | [6 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
Concrete Box Culvert
18.1 | Concrete Box Culverts | EA | 0 | 0 |  | 0
18.2 | Concrete Box Culverts Extensions | EA Extension | 0 | 0 |  | 0
18.3 | Concrete Box Culvert Data Table Plan Sheets | Sheet | 0 | 0 | 0 | 0
18.4 | Concrete Box Culvert Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
Strain Poles
18.5 | Steel Strain Poles | Initial Config | 0 | 0 |  | 0
|  | EA Add'l Config | 0 | 0 |  | 0
18.6 | Concrete Strain Poles | Initial Config | 0 | 0 |  | 0
|  | EA Add'l Config | 0 | 0 |  | 0
18.7 | Strain Pole Data Table Plan Sheets | Sheet | 0 | 0 | 0 | 0
18.8 | Strain Pole Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
Mast Arms
18.9 | Mast Arms | EA Design | 0 | 0 |  | 0
18.1 | Mast Arms Data Table Plan Sheets | Sheet | 0 | 0 | 0 | 0
18.11 | Mast Arm Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
Overhead/Cantilever Sign Structures
18.12 | Cantilever Sign Structures | EA Design | 0 | 0 |  | 0
18.13 | Overhead Span Sign Structures | EA Design | 0 | 0 |  | 0
18.14 | Special (Long Span) Overhead Span Sign Structures | EA Design | 0 | 0 |  | 0
18.15 | Monotube Overhead Sign Structure | EA Design | 0 | 0 |  | 0
18.16 | Bridge Mounted Signs (Attached to Superstr.) | EA Design | 0 | 0 |  | 0
18.17 | Overhead and Cantilever Sign Structures Data Table Plan Sheets | Sheet | 0 | 0 | 0 | 0
18.18 | Overhead and Cantilever Sign Structures Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
High Mast Lighting
18.19 | Non-Standard High Mast Lighting Structures | EA Design | 0 | 0 |  | 0
18.2 | High Mast Lighting Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
Noise Barrier Walls (Ground Mount)
18.21 | Horizontal Wall Geometry | EA Wall | 0 | 0 |  | 0
18.22 | Vertical Wall Geometry | EA Wall | 0 | 0 |  | 0
18.23 | Summary of Quantities - Aesthetic Requirements | Sheet | 0 | 0 | 0 | 0
18.24 | Control Drawings | Sheet | 0 | 0 | 0 | 0
18.25 | Design of Noise Barrier Walls Covered by Standards | EA Design | 0 | 0 |  | 0
18.26 | Design of Noise Barrier Walls Not Covered by Standards | EA Design | 0 | 0 |  | 0
18.27 | Aesthetic Details | LS | 1 | 0 |  | 0
Special Structures
18.28 | Fender System | LS | 1 | 0 |  | 0
18.29 | Fender System Access | LS | 1 | 0 |  | 0
18.3 | Special Structures | LS | 1 | 0 |  | 0
18.31 | Other Structures | LS | 1 | 0 |  | 0
Ancillary Structures Report
18.32 | Condition Evaluation of Signal and Sign Structures, and High Mast Light Poles | EA structure | 0 | 0 | 0 | 0
18.33 | Condition Evaluation of Signal and Sign Structures, and High Mast Light Poles (No As built or Design Plans Available) | EA structure | 0 | 0 | 0 | 0
18.34 | Analytical Evaluation of Signal and Sign Structures, and High Mast Light Poles | EA structure | 0 | 0 | 0 | 0
18.35 | Ancillary Structures Report | LS | 1 | 0 |  | 0
18. Structures - Miscellaneous Total |  |  |  |  | 0 | 0

## Signing & Marking Guidelines
SIGNING AND PAVEMENT MARKING GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical traffic projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
A "Lower Range" roadway project may fall in the "Middle Range" for Signing and Pavement Marking projects and vice versa. See the project ranges below. The project ranges should be used only for Reference & Master Design Files and Quantities from Analysis. All other tasks should be defined on task by task basis and should not necessarily use the Project Ranges.
Lower Range
1. Two-Lane Arterial and Collector Roadways
2. New Construction & Reconstruction Projects on Limited Access Roadways with Interchange Spacing > 3 miles
3. Resurfacing Projects on Limited Access Roadways with Minor Signing Improvements
Middle Range
1. Multi-Lane Arterial and Collector Roadways
2. New Construction & Reconstruction Projects on Limited Access Roadways with Interchange Spacing between 2 and 3 miles
3. Stand-alone Rural Interchange Improvements
Upper Range
1. New Construction & Reconstruction Projects on Limited Access Roadways with Interchange Spacing < 2 miles
2. Stand-alone Urban Interchange Improvements

## 19. Signing & Marking Analysis
| Estimator: |  | 19. Signing and Pavement Marking Analysis | [7 empty] | How to Use This Form
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
What is the overall project complexity? (See S&PM Guidelines)
ITS02-001 | 19.1 | Traffic Data Analysis | LS | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 19.1 | [5 empty] | 2 | 4 | 6
ITS02-002 | 19.2 | No Passing Zone Study | Field Work (Staff-Days) | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.2 | [8 empty] | 8
|  |  | Analysis (Miles) | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 4 | 6 | 8
|  |  | Report | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 12 | 20 | 28
| 19.3 | Signing and Pavement Marking Master Design File Setup & Maintenance | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.3 |  | 30 | 40 | 50
ITS02-003 | 19.4 | Signing and Pavement Marking Master Design File | Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.4 |  | 40 | 90 | 140
|  |  | Signalized Intersection | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 8 | 12
|  |  | Vehicular Loops | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 12 | 20
|  |  | Colored Marking GIS File | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
ITS02-004 | 19.5 | Multi-Post Sign Support Calculations | EA | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.5 | [8 empty] | 3
ITS02-005 | 19.6 | Sign Panel Design Analysis | EA | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.6 | [8 empty] | 3
ITS02-006 | 19.7 | Sign Lighting/Electrical Calculations (only for special condictions) | EA | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.7 | [8 empty] | 2
| 19.8 | S&PM Quantities for EQ Report | Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.8 |  | 3 | 4 | 5 |  |  |  |  | 12 | 16 | 20
ITS02-008 | 19.9 | Project Cost | Engineer's Project Cost | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.9 |  | 2 | 5 | 8
|  |  | LRE Updates | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 4 | 6
ITS02-009 | 19.1 | Technical & Modified Special Provisions | EA | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.10 | [8 empty] | 6
ITS02-010 | 19.11 | Other Signing and Pavement Marking | LS |  |  | 0 | 0 | 0 | 0 |  |  | 19.11
| S&PM Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manger below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
ITS02-011 | 19.12 | Quality Assurance/Quality Control | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 19.12
| 19.13 | Supervision | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 19.13
| 19.14 | Technical Meetings (listed below) | Meetings | 0 |  | 0 | 0 | 0 | 0 |  |  | 19.14 | [8 empty] | 2
|  |  | Travel Time |  |  | 0 | 0 | 0 | 0
| 19.15 | Field Reviews (listed below) | LS |  |  | 0 | 0 | 0 | 0 |  |  | 19.15
| S&PM Nontechnical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
ITS02-024 | 19.16 | Coordination | LS | 1 | 3% | 0 | 0 | 0 | 0 |  |  | 19.16
| 19. S&PM Analysis Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
|  | Technical Meetings | # Meetings Designer | Travel Time (Hours) | # Meetings PM | Documentation
|  | Sign Panel Design | 0 | 0 | 0
|  | Queue Length Analysis | 0 | 0 | 0
|  | Local Governments (cities, counties) | 0 | 0 | 0
|  | Risk Register | 0 | 0 | 0
|  | Indpendent Project Cost | 0 | 0 | 0
|  | Other Meetings | 0 | 0 | 0
|  | Subtotal Technical Meetings | 0 | 0 | 0
|  | Progress Meetings (if required by FDOT) | 0 | 0
|  | Phase Review Meetings | 0 | 0
|  | Total Technical Meetings | 0 | 0
|  | Field Reviews | # of Staff | Site Time (per staff) | Travel Time (per staff) | Total Hours
|  | Field Review #1 | 0 | 0 | 0 | 0
|  | Field Review #2 | 0 | 0 | 0 | 0
|  | Field Review #3 | 0 | 0 | 0 | 0
|  | Field Review #4 | 0 | 0 | 0 | 0
|  | Plans-in-hand Field Review | 0 | 0 | 0 | 0
|  | Total Field Reviews |  |  |  | 0
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E12: Is Traffic Data Analysis required? Yes=1 No=0
Note on E13: Estimated # of (days x number of staff) to perform the field work. Examples: 2 staff x 0.5 day(s) = 1 4 staff x 2 days = 8
Note on E14: Length of project in miles to perform no passing zone study.
Note on E15: Is a No Passing Study Report required? Yes=1 No=0
Note on E16: Is Design File Setup required? Yes=1 No=0
Note on E17: Length of project in miles. The "Begin Project" and "End Project" mileposts are the basis for computing the project length. Add the toatl length of all ramps that are included in the project. Consider adding additional hours for side streets only when work along the side street is significant (more than just tying into existing roadway).
Note on E18: Estimated # of mid-block crossings or signalized intersections.
Note on E19: Estimated # intersections that include vehicular loops in the S&PM Plans.
Note on E20: Is GIS file for Colored Pavement Markings required? Yes=1 No=0
Note on E21: Estimated # of multi-sign post installations.
Note on E22: Estimated # of sign panels enetered into sign design software.
Note on E23: Estimated # of lighted signs installations.
Note on E24: Length of project in miles. The "Begin Project" and "End Project" mileposts are the basis for computing the project length. Add the total length of all ramps that are included in the project. Consider adding additional hours for side streets only when work along the side street is significant (more than just tying into existing roadway).
Note on E25: Estimated number of submittals of project cost.
Note on E26: Estimated number of LRE Updates: typically at Phase II, but sometimes for Phase I as well.
Note on E27: Estimated # of TSPs and MSPs.
Note on E30: Is QA/QC required? Yes=1 No=0
Note on F30: Enter % between 5% and 10%
Note on E31: Is Supervision required? Yes=1 No=0
Note on F31: % of technical subtotal.
Note on E32: Estimated # of meeting listed below
Note on F36: % of technical subtotal.

## 20. Signing & Marking Plans
| Estimator: |  | 20. Signing and Pavement Marking Plans Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task |  | Project Complexity |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
SPM02-001 | 20.1 | Key Sheet |  | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 20.1 | [8 empty] | 4
SPM02-002 |  | Signature Sheet |  | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
SPM02-003 | 20.2 | General Notes/Pay Item Notes |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 20.2 | [5 empty] | 6 | 9 | 12
SPM02-004 | 20.3 | Project Layout |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 20.3 | [8 empty] | 6
SPM02-005 | 20.4 | Plan Sheet | Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 20.4 |  | 2 | 4 | 6
SPM02-006 |  |  | Sig Intersection Mid-Block Xing | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
SPM02-007 |  |  | Interchange Roundabout | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
SPM02-008 |  |  | Rest Area Toll Facility | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
SPM02-009 | 20.5 | Special Details | Details | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 20.5 | [5 empty] | 2
SPM02-010 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 4
SPM02-011 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 6
SPM02-012 | 20.6 | Service Point Details | Service Point | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 20.6 | [5 empty] | 4
SPM02-013 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 8
SPM02-014 | 20.7 | Guide Sign Data | Sign Panel | 0 |  | 0 | 0 | 0 | 0 |  |  | 20.7 | [8 empty] | 2
SPM02-015 | 20.8 | Cross Sections (Sign Installations) | Multi-post signs | 0 |  | 0 | 0 | 0 | 0 |  |  | 20.8 | [8 empty] | 3
SPM02-016 |  |  | Overhead Sign Structures | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 6
SPM02-017 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 9
| S&PM Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
SPM02-018 | 20.9 | Quality Assurance/Quality Control | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 20.9
SPM02-019 | 20.1 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 20.1
| S&PM Plans Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E11: Is a Key sheet required? Yes=1 No=0
Note on E12: Is a signature sheet required? If Key Sheet is not required, then no hours will be given for the signature sheet. Yes=1 No=0
Note on E13: Is a general notes/pay item notes sheet required? Yes=1 No=0
Note on E14: Is a project layout sheet required? Should be used only when necessary (complex projects or multiple work location projects). Yes=1 No=0
Note on E15: Estimated number of sheets required for the S&PM plan.
Note on E16: Estimated # of mid-block crossings or signalized intersections to be shown on plan sheets.
Note on E17: Estimated # of interchanges or roundabouts to be shown on plan sheets.
Note on E18: Estimated # of rest areas or toll facilities to be shown on plan sheets.
Note on E19: Estimated # of simple details that that require no engineering and are common on all projects.
Note on E20: Estimated # Standard details that require some engineering and are site or project specific (e.g., gore markings, cross walk markings, pedestrian and bicycle markings, sign placement)l.
Note on E21: Estimated # of complex details that are highly unique or based on new technologies.
Note on E22: Estimated # of retrofit or modified service points to be shown in plans.
Note on E23: Estimated # of new service points to be shown in plans.
Note on E24: Estimated # of signs that must be imported from guide sign program.
Note on E25: Estimated # of multi-post signs that will be shown in the plans on a cross section when required by District.
Note on E26: Estimated # of single panel overhead structures that will be shown in the plans on a cross section. Includes creation of cross section.
Note on E27: Estimated # of multi-panel overhead structures that will be shown in the plans on a cross section. Includes creation of cross section.
Note on E29: Is QA/QC required for S&PM Plans? Yes=1 No=0
Note on F29: Enter % between 5% and 10%
Note on E30: Is Supervision required for S&PM Plans?? Yes=1 No=0
Note on F30: % of technical subtotal.

## Signalization Guidelines
SIGNALIZATION GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical traffic projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
A "Lower Range" roadway project may fall in the "Middle Range" for Lighting projects and vice versa. See the project ranges below. The project ranges should be used only for Reference & Master Design Files and Quantities from Analysis. All other tasks should be defined on task by task basis and should not necessarily use the Project Ranges.
Lower Range
1. Rural 2-Lane Project
2. Vehicular Loop Replacement
3. Flashing Beacon
4. Mid Block Traffic Signal
Middle Range
1. Rural Multi-Lane Highway
2. Urban Multi-Lane with minor R/W issues or Utility impacts
3. Urban 2-Lane with major R/W issues or Utility impacts.
Upper Range
1. Urban Multi-Lane with major R/W issues or Utility impacts
2. Single Point Urban Interchange

## 21. Signalization Analysis
| Estimator: |  | 21. Signalization Analysis | [7 empty] | How to Use This Form
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorial - A short webinar for the ITS Plans tab
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
ITS02-001 | 21.1 | Traffic Data Collection (No Analysis) | Crash Reports | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 21.1 | [8 empty] | 4
|  |  | 24 Hr. Machine Count | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
|  |  | 8 Hr. Turning Movement | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 12
|  |  | 7 Day Machine Count | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
|  |  | Speed, Delay, & Gap Studies | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 24
|  |  | Other |  |  | 0 | 0 | 0 | 0
ITS02-002 | 21.2 | Traffic Data Analysis | Intersection | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.2 | [5 empty] | 3 | 6 | 9
ITS02-003 | 21.3 | Signal Warrant Study | Intersection | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.3 | [5 empty] | 16 | 24 | 40
ITS02-004 | 21.4 | System Timings | Signalized Intersection | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.4 | [8 empty] | 2
| 21.5 | Master Design File Setup & Maintenance | Signalized Intersection | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.5 | [8 empty] | 4
|  |  | Interconnect Design | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
| 21.6 | Signalization Master Design File | Loops Only Intersection | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
ITS02-005 |  |  | Signalized Intersection | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 21.6 | [5 empty] | 20
|  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 34
|  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 48
|  |  | Interconnect Commun. (miles) | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 24
ITS02-006 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 32
| 21.7 | Overhead Street Name Sign Design | Street Names | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 21.7 | [5 empty] | 1
|  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 2
ITS02-007 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 3
ITS02-008 | 21.8 | Pole Elevation Analysis | Signalized Intersection | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.8 | [8 empty] | 1 | 1
ITS02-009 | 21.9 | Traffic Signal Operation Report | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.9 | [5 empty] | 20 | 30 | 40
| 21.1 | Signalization Quantities for EQ Report | Loops Only Intersection | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.1 | [8 empty] | 2
|  |  | Signalized Intersection | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4 |  |  | 16
|  |  | Interconnect (miles) | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
| 21.11 | Project Cost | Engineer's Project Cost | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.11 | [5 empty] | 2 | 5 | 8
|  |  | LRE Updates | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 2 | 4 | 6
| 21.12 | Technical & Modified Special Provisions | EA | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.12 | [8 empty] | 6
ITS02-010 | 21.13 | Other Signalization Tasks | LS |  |  | 0 | 0 | 0 | 0 |  |  | 21.13
| Signalization Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
ITS02-011 | 21.14 | Quality Assurance/Quality Control | LS | 1 | 5% | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manger below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346 | 21.14
| 21.15 | Supervision | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 21.15
| 21.16 | Technical Meetings (listed below) | Meetings | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.16 | [8 empty] | 2
|  |  | Travel Time |  |  | 0 | 0 | 0 | 0
| 21.17 | Field Reviews (listed below) | LS |  |  | 0 | 0 | 0 | 0 |  |  | 21.17
| Signalization Nontechnical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
ITS02-024 | 21.18 | Coordination | LS | 1 | 3% | 0 | 0 | 0 | 0 |  |  | 21.18
| 21. Signalization Analysis Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
|  | Technical Meetings | # Meetings Designer | # Meetings PM | Travel Time (Hours) | Documentation
|  | FDOT Traffic Operations | 0 | 0 | 0
|  | FDOT Traffic Design | 0 | 0 | 0
|  | Power Company (service point coordination) | 0 | 0 | 0
|  | Maintaining Agency (cities, counties) | 0 | 0 | 0
|  | Railroads | 0 | 0 | 0
|  | Risk Register | 0 | 0 | 0
|  | Indpendent Project Cost | 0 | 0 | 0
|  | Other Meetings | 0 | 0 | 0
|  | Subtotal Technical Meetings | 0 | 0 | 0
|  | Progress Meetings (if required by FDOT) | 0
|  | Phase Review Meetings | 0
|  | Total Technical Meetings | 0
|  | Field Reviews | # of Staff | Site Time (per staff) | Travel Time (per staff) | Total Hours
|  | Field Review #1 | 0 | 0 | 0 | 0
|  | Field Review #2 | 0 | 0 | 0 | 0
|  | Field Review #3 | 0 | 0 | 0 | 0
|  | Field Review #4 | 0 | 0 | 0 | 0
|  | Plans-in-hand Field Review | 0 | 0 | 0 | 0
|  | Total Field Reviews |  |  |  | 0
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E11: # of intersections.
Note on E12: # of approaches.
Note on E13: # of intersections. Hours based on one person.
Note on E14: # of approaches.
Note on E15: # of systems. Hours based on two people.
Note on E17: Estimated # of mid-block crossings or signalized intersections.
Note on E18: Estimated # of intersections included in study.
Note on E19: Estimated # of signalized intersections. Only use this when system timings are not provided by FDOT.
Note on E20: # of intersections.
Note on E21: Is Interconnect Design File required? Yes=1 No=0
Note on E22: Estimated # intersections requiring loop replacement
Note on E23: Estimated # of Simple complexity signalized intersections.
Note on E24: Estimated # of Standard complexity signalized intersections.
Note on E25: Estimated # of Complex signalized intersections.
Note on E26: Length of project corridor where driveways and side roads are typical.
Note on E27: Length of project corridor where driveways and side roads are numerous and R/W is tight.
Note on E28: Estimated # of street names that are a common layout, e.g., US 90, US 301, SR 20
Note on E29: Estimated # of street names that require a single line layout.
Note on E30: Estimated # of street names that require two line layout.
Note on E31: Estimated # of mid-block crossings or signalized intersections.
Note on E32: Is master Design File required? Yes=1 No=0
Note on E33: Estimated # intersections requiring loop replacement
Note on E34: Estimated # of mid-block crossings or signalized intersections.
Note on E35: Length of interconnect project.
Note on E36: Estimated number of submittals of project cost. Typically 1.
Note on E37: Estimated number of LRE Updates: typically at Phase II, but sometimes for Phase I as well.
Note on E38: Estimated # of TSPs and MSPs.
Note on E41: Is QA/QC required? Yes=1 No=0
Note on F41: Enter % between 5% and 10%
Note on E42: Is Supervision required? Yes=1 No=0
Note on F42: % of technical subtotal.
Note on E43: Estimated # of meeting listed below
Note on F47: % of technical subtotal.

## 22. Signalization Plans
| Estimator: |  | 22. Signalization Plans Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
What is the overall project complexity? (See Signalization Guidelines)
SIG02-001 | 22.1 | Key Sheet |  | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 22.1 | [8 empty] | 4
SIG02-002 |  | Signature Sheet |  | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
SIG02-003 | 22.2 | General Notes/Pay Item Notes |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 22.2 | [5 empty] | 6 | 9 | 12
SIG02-004 | 22.3 | Signalization Plan Sheets | Signalized Intersections | 0 |  | 0 | 0 | 0 | 0 |  |  | 22.3 |  | 2 | 4 | 6
SIG02-005 | 22.4 | Interconnect Plan Sheets | Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 22.4 |  | 2 | 4 | 6
SIG02-006 | 22.5 | Traffic Monitoring Site | Sites (Loop Detect.) | 0 |  | 0 | 0 | 0 | 0 |  |  | 22.5 | [8 empty] | 4
SIG02-007 |  |  | Sites (Other Detect.) | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
SIG02-008 | 22.6 | Guide Sign Data | Sign Panel | 0 |  | 0 | 0 | 0 | 0 |  |  | 22.6 | [8 empty] | 2
SIG02-009 | 22.7 | Special Details | Details | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 22.7 | [5 empty] | 1
SIG02-010 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 2
SIG02-011 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 4
SIG02-012 | 22.8 | Service Point Details | Service Point | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 22.8 | [5 empty] | 4
SIG02-013 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 8
SIG02-014 | 22.9 | Mast Arm / Monotube Data | Signal Arm | 0 | Single Mast Arm | 0 | 0 | 0 | 0 |  |  | 22.9 | [8 empty] | 1
SIG02-015 |  |  |  | 0 | Double Mast Arm | 0 | 0 | 0 | 0 | [11 empty] | 2
SIG02-016 | 22.1 | Strain Pole Schedule | Span | 0 |  | 0 | 0 | 0 | 0 |  |  | 22.1 | [8 empty] | 2
SIG02-017 | 22.11 | TTCP Signal | Intersections w/o ped signal | 0 |  | 0 | 0 | 0 | 0 |  |  | 22.11 |  | 16 | 16 | 24
SIG02-018 |  |  | Intersections with ped signal | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 24 | 32
SIG02-019 | 22.12 | Temporary Detection Sheet | Intersections | 0 |  | 0 | 0 | 0 | 0 |  |  | 22.12 | [8 empty] | 4
| Signalization Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
SIG02-020 | 22.13 | Quality Assurance/Quality Control | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 20.13
SIG02-021 | 22.14 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 20.14
| Signalization Plans Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E12: Is a Key sheet required? Yes=1 No=0
Note on E13: Is a signature sheet required? If Key Sheet is not required, then no hours will be given for the signature sheet. Yes=1 No=0
Note on E14: Is a general notes/pay item notes sheet required? Yes=1 No=0
Note on E15: Estimated # of intersections that require new or replacement signalization.
Note on E16: Estimated number of sheets for interconnect plans. Interconnect Plans are typically not necessary for low range projects.
Note on E17: Estimated # of sites with loop detecion.
Note on E18: Estimated # of sites with video or other type of detecion.
Note on E19: Estimated # of signs that must be imported from guide sign program.
Note on E20: Estimated # of details that require no engineering analysis (e.g., Ped Pole, VVH data/foundation, Department provided details).
Note on E21: Estimated # details require some engineering analysis (e.g.,signal/sign attachment detail, Communication or Wiring Diagram.
Note on E22: Estimated # of complex details that are highly unique or based on new technologies. Complex details are not typically required.
Note on E23: Estimated # of retrofit or modified service points to be shown in plans.
Note on E24: Estimated # of new service points to be shown in plans.
Note on E25: Estimated # of single mast arms.
Note on E26: Estimated # of double mast arms.
Note on E27: Estimated # of spans needed for project.
Note on E28: Estimated # of intersections that temporary signal installation - without pedestrian signals - is required.
Note on E29: Estimated # of intersections that temporary signal installation - with pedestrian signals - is required.
Note on E30: Estimated # of intersections that temporary detection is required.
Note on E32: Is QA/QC required for Signalization Plans? Yes=1 No=0
Note on F32: Enter % between 5% and 10%
Note on E33: Is Supervision required for Signalization Plans?? Yes=1 No=0
Note on F33: % of technical subtotal.

## Lighting Guidelines
LIGHTING GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical traffic projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
A "Lower Range" roadway project may fall in the "Middle Range" for Lighting projects and vice versa. See the project ranges below. The project ranges should be used only for Reference & Master Design Files and Quantities from Analysis. All other tasks should be defined on task by task basis and should not necessarily use the Project Ranges.
Lower Range
1. Rural Multi-Lane
2. Limited Access
Middle Range
1. Urban Multi-Lane
2. Complex Limited Access
3. Interchange Projects
Upper Range
1. Complex Interchange Projects
2. Stand-alone Corridor Lighting Projects

## 23. Lighting Analysis
| Estimator: |  | 23. Lighting Analysis | [7 empty] | How to Use This Form
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorial - A short webinar for the ITS Plans tab
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
ITS02-001 | 23.1 | Lighting Justification Report | LS | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 23.1 | [5 empty] | 24 | 32 | 40
ITS02-002 | 23.2 | Lighting Design Analysis Report (LDAR) | Corridor Lighting | 0 |  | 0 | 0 | 0 | 0 |  |  | 23.2 |  | 12 | 20 | 28 |  |  |  |  | 8
|  |  | Sig. Intersection Lighting | 0 | Simple | 0 | 0 | 0 | 0 |  |  |  |  | 4
|  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [5 empty] | 8
|  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [6 empty] | 12
|  |  | Interchanges | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 4 | 6 | 8
ITS02-003 | 23.3 | Voltage Drop Calculations | Circuit | 0 |  | 0 | 0 | 0 | 0 |  |  | 23.3 | [5 empty] | 1 | 2.5 | 4
ITS02-004 | 23.4 | DEP Coordination & Report (Sea Turtles) | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 23.4 | [5 empty] | 16 | 18 | 20
| 23.5 | Lighting Master Design File | Setup and Maintenance | 0 |  | 0 | 0 | 0 | 0 |  |  | 23.5 | [5 empty] | 16 | 28 | 40
ITS02-005 |  |  | Corridor Lighting | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 90 | 140
|  |  | Intersection Lighting | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 8 | 14 | 20
| 23.6 | Temporary Highway Lighting | Analysis | 0 |  | 0 | 0 | 0 | 0 |  |  | 23.6 | [5 empty] | 20 | 40 | 60
ITS02-007 |  |  | Design File | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 24 | 32 | 40
ITS02-008 | 23.7 | Design Documentation | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 23.7 |  | 8 | 16 | 24
ITS02-009 | 23.8 | Lighting Quantities for EQ Report | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 23.8 |  | 20 | 30 | 40
| 23.9 | Project Cost | Engineer's Project Cost | 0 |  | 0 | 0 | 0 | 0 |  |  | 23.9 |  | 2 | 4 | 6
|  |  | LRE Updates | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 4 | 6
| 23.1 | Technical & Modified Special Provisions | EA | 0 |  | 0 | 0 | 0 | 0 |  |  | 23.10 | [8 empty] | 6
| 23.11 | Other Lighting Analysis | LS |  |  | 0 | 0 | 0 | 0 |  |  | 23.11
| Lighting Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
ITS02-011 | 23.12 | Quality Assurance/Quality Control | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 21.12
| 23.13 | Supervision | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 21.13
| 23.14 | Technical Meetings (listed below) | Meetings | 0 |  | 0 | 0 | 0 | 0 |  |  | 21.14 | [8 empty] | 2
|  |  | Travel Time |  |  | 0 | 0 | 0 | 0
| 23.15 | Field Reviews (listed below) | LS |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manger below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346 | 21.15
| Lighting Nontechnical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
ITS02-024 | 23.16 | Coordination | LS | 1 | 3% | 0 | 0 | 0 | 0 |  |  | 21.16
| 23. Lighting Analysis Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
|  | Technical Meetings | # Meetings Designer | # Meetings PM | Travel Time (Hours) | Documentation
|  | FDOT Lighting Design | 0 | 0 | 0
|  | FDOT Traffic Design | 0 | 0 | 0
|  | Power Company (service point coordination) | 0 | 0 | 0
|  | Maintaining Agency (cities, counties) | 0 | 0 | 0
|  | Airport authority | 0 | 0 | 0
|  | FDEP Lighting (coast areas) | 0 | 0 | 0
|  | Engineer's Project Cost | 0 | 0 | 0
|  | Indpendent Project Cost | 0 | 0 | 0
|  | Other Meetings | 0 | 0 | 0
|  | Subtotal Technical Meetings | 0 | 0 | 0
|  | Progress Meetings (if required by FDOT) | 0
|  | Phase Review Meetings | 0
|  | Total Technical Meetings | 0
|  | Field Reviews | # of Staff | Site Time (per staff) | Travel Time (per staff) | Total Hours
|  | Field Review #1 | 0 | 0 | 0 | 0
|  | Field Review #2 | 0 | 0 | 0 | 0
|  | Field Review #3 | 0 | 0 | 0 | 0
|  | Field Review #4 | 0 | 0 | 0 | 0
|  | Plans-in-hand Field Review | 0 | 0 | 0 | 0
|  | Total Field Reviews |  |  |  | 0
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E11: Is a Lighting Justification Report required? Yes=1 No=0
Note on E12: Length of project to have corridor lighting.
Note on E13: Estimated # of simple mid-block crossings or signalized intersections.
Note on E14: Estimated # of standard mid-block crossings or signalized intersections.
Note on E15: Estimated # of complex mid-block crossings or signalized intersections.
Note on E16: Length of interchange ramps.
Note on E17: Estimated # of circuits. Typically four circuits per service point.
Note on E18: Is DEP Coordination & Report required? Yes=1 No=0
Note on E19: Is master Design File required? Yes=1 No=0
Note on E20: Length of project to be shown on plan sheets.
Note on E21: Estimated # of mid-block crossings or signalized intersections.
Note on E22: Is TTC Lighting analysis required? Yes=1 No=0
Note on E23: Is Design File required? Yes=1 No=0
Note on E24: Is Design File required? Yes=1 No=0
Note on E25: Are Signalization Quantities required? Yes=1 No=0
Note on E26: Estimated number of submittals of project costs. Typically 1.
Note on E27: Estimated number of LRE Updates: typically at Phase II, but sometimes for Phase I as well.
Note on E28: Estimated # of TSPs and MSPs.
Note on E31: Is QA/QC required? Yes=1 No=0
Note on F31: Enter % between 5% and 10%
Note on E32: Is Supervision required? Yes=1 No=0
Note on F32: % of technical subtotal.
Note on E33: Estimated # of meeting listed below
Note on F37: % of technical subtotal.

## 24. Lighting Plans
| Estimator: |  | 24. Lighting Plans Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
LTG02-001 | 24.1 | Key Sheet |  | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 24.1 | [8 empty] | 4
LTG02-002 |  | Signature Sheet |  | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
LTG02-003 | 24.2 | General Notes/Pay Item Notes |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 24.2 | [5 empty] | 6 | 9 | 12
LTG02-004 | 24.3 | Pole Data, Legend and Criteria | Poles | 0 |  | 0 | 0 | 0 | 0 |  |  | 24.3 | [8 empty] | 5 |  |  | 0.2
LTG02-005 | 24.4 | Project Layout |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 24.4 | [8 empty] | 6
LTG02-006 | 24.5 | Plan Sheets (Corridor Projects) | Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 24.5 | [8 empty] | 3
LTG02-007 |  | Plan Sheets (Isolated Loctions) | Intersections or Mid-Blocks | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
LTG02-008 |  |  | Interchanges or Rest Areas | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 24
LTG02-009 | 24.6 | Special Details | Details | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 24.6 | [5 empty] | 4
LTG02-010 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 8
LTG02-011 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 8 | 4
LTG02-012 | 24.7 | Service Point Details | Service Point | 0 | Simple | 0 | 0 | 0 | 0 |  |  | 24.7 | [5 empty] | 6
LTG02-013 |  |  |  | 0 | Standard | 0 | 0 | 0 | 0 | [9 empty] | 12
LTG02-014 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 16
LTG02-015 | 24.8 | Temporary Highway Lighting |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 24.8 | [5 empty] | 16 | 32 | 48
| Lighting Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
LTG02-016 | 24.9 | Quality Assurance/Quality Control | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 24.9
LTG02-017 | 24.1 | Supervision | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 24.1
| Lighting Plans Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E11: Is a Key sheet required? Yes=1 No=0
Note on E12: Is a signature sheet required? If Key Sheet is not required, then no hours will be given for the signature sheet. Yes=1 No=0
Note on E13: Is a general notes/pay item notes sheet required? Yes=1 No=0
Note on E14: Estimated # of poles to be placed in the Pole Data schedule.
Note on E15: Is a project layout sheet required? Should be used only when necessary (complex projects or multiple work location projects). Yes=1 No=0
Note on E16: Estimated number of sheets for Lighting Plans (Corridor Projects).
Note on E17: # of isolated areas (intersections, mid-block crossing, or similar) to receive new or retrofit lighting. These locations are not located within a corridor project.
Note on E18: # of interchanges or rest areas to receive new or retrofit lighting. If this is part of an interstate lighting project, subtract the limits of the interchange from the corridor project limits.
Note on E19: Estimated # of details that require no engineering analysis (minor details, manufacturer or FDOT provided details).
Note on E20: Estimated # of details that require engineering analysis and must be cretaed.
Note on E21: Estimated # of complex details (e.g., under deck lighting details or details based on new technologies) that required to be shown in plans.
Note on E22: Estimated # of retrofit or modified service points to be shown in plans.
Note on E23: Estimated # of new service points for conventional lighting to be shown in plans.
Note on E24: Estimated # of new service points for high mast lighting to be shown in plans.
Note on E25: Is temporary lighting required on project? Yes=1 No=0 Includes plans, notes and details. The requirements for Temporary Highway Lighting is unique and requires independent negotiations. Typically, this effort is between 16 to 48 hours to complete.
Note on E27: Is QA/QC required for Lighting Plans? Yes=1 No=0
Note on F27: Enter % between 5% and 10%
Note on E28: Is Supervision required for Lighting Plans?? Yes=1 No=0
Note on F28: % of technical subtotal.

## Landscape Guidelines
LANDSCAPE GUIDELINES
The following matrix was developed to determine the level of complexity of a Planting Plan.
Element | Complexity Guidance |  | Complexity | Rating | Comments |  | N/A | Simple | Standard | Complex
Planting Palette | Simple: | Palms/Trees Only | Simple | 1
| Standard: | Palms/Trees and shrubs
| Complex: | Specialized Designs (Urban Corridor, Complete Street, Scenic Interchange)
Roadway Type | Simple: | Existing Roadway | Standard | 2
| Standard: | Roadway Widening
| Complex: | Reconstruction or New Roadway Alignment
Roadway Elements | Simple: | Minor Intersections | Standard | 2
| Standard: | Standard intersections and Interchanges
| Complex: | Complex intersections and Multiple-Level Interchanges
Roadway Location (Context Classification) | Simple: | C1, C2 (rural) | Standard | 2
| Standard: | C2T, C3C, C3R (Suburban), Rural LA Facilities
| Complex: | C4, C5, C6 (Urban), Urban LA Facilities
Stakeholder Participation | Simple: | 1-3 Stakeholders | Standard | 2
| Standard: | 4-6 Stakeholders
| Complex: | 7+ Stakeholders or Public Workshop
Outdoor Advertising | Simple: | 1-3 Sign Faces | Simple | 1
| Standard: | 4-6 Sign Faces
| Complex: | 7+ Sign Faces
Total Points: |  |  |  | 10 | Planting Plan Complexity: | Mid
[5 empty] | Total Points 6 or less: | Low
[5 empty] | Total Points 7 to 12: | Mid
[5 empty] | Total Points 13 or more: | High

## 25. Landscape Analysis
| Estimator: |  | 25. Landscape Analysis Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
What is the complexity of the planting plan? (See Landscape Guidelines)
LND01-001 | 25.1 | Data Collection | LS | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 25.1 | [5 empty] | 8 | 24 | 40
LND01-002 | 25.2 | Outdoor Advertising Assessment | Sign Structure | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.2 | [8 empty] | 4
LND01-003 | 25.3 | Master Design File Setup (Base Files) | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.3 | [5 empty] | 16 | 28 | 40
LND01-004 | 25.4 | Site Inventory and Analysis | Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.4 |  | 8 | 32 | 56
LND01-005 |  |  | Area Projects Area (Acre) | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0.5 | 2 | 3
LND01-006 | 25.5 | Landscape Opportunity Plan | Mainline Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.5 | [5 empty] | 16 | 28 | 40
LND01-007 |  |  | Area Projects Area (Acre) | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 1 | 2 | 3
LND01-008 | 25.6 | Conceptual Planting Design | Report Preparation | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.6 |  | 16 | 28 | 40
LND01-009 |  |  | Mainline Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 40 | 60
LND01-010 |  |  | Area Projects Area (Acre) | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2 | 3
LND01-011 | 25.7 | Final Planting Design | Mainline Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.7 |  | 60 | 120 | 180
LND01-012 |  |  | Area Projects Area (Acre) | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 5 | 8
LND01-013 | 25.8 | Conceptual Irrigation Design | Feasibility Report | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.8 | [5 empty] | 16 | 24 | 32
LND01-014 |  |  | Mainline Length (Miles) | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 20 | 35 | 50
LND01-015 |  |  | Area Projects | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 1 | 2 | 3
LND01-016 | 25.9 | Final Irrigation Design | Mainline (per mile) | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.9 | [5 empty] | 50 | 100 | 150
LND01-017 |  |  | Area Projects | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 2 | 5 | 8
LND01-018 | 25.1 | Conceptual Hardscape Design | Report Preparation | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.1 | [5 empty] | 8 | 12 | 16
LND01-019 |  |  | LS | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 8 | 24 | 40
LND01-020 | 25.11 | Final Hardscape Design | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.11 | [5 empty] | 80 | 120 | 160
LND01-021 | 25.12 | Landscape Quantities for EQ Report | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.12 |  | 20 | 24 | 28
LND01-022 | 25.13 | Project Cost | Engineer's Project Cost | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.13 |  | 2 | 5 | 8
LND01-023 |  |  | LRE Updates | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 4 | 6
LND01-024 | 25.14 | Technical or Modified Special Provisions | TSPs & MSPs | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.14 | [8 empty] | 6
LND01-025 | 25.15 | Other Landscape Services | LS |  |  | 0 | 0 | 0 | 0 |  |  | 25.15
| Landscape Analysis Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
LND01-026 | 25.16 | Quality Assurance/Quality Control | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 25.16
LND01-027 | 25.17 | Supervision | LS | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 25.17
LND01-028 | 25.18 | Landscape Meetings (listed below) | Meetings | 0 |  | 0 | 0 | 0 | 0 |  |  | 25.18 | [8 empty] | 2
LND01-029 |  |  | Travel Time |  |  | 0 | 0 | 0 | 0
LND01-030 | 25.19 | Field Reviews (listed below) | LS |  |  | 0 | 0 | 0 | 0 |  |  | 25.19
| Landscape Analysis Non-Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0
LND01-031 | 25.2 | Coordination | LS | 1 | 3% | 0 | 0 | 0 | 0 |  |  | 25.2
| Landscape Analysis Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
|  | Technical Meetings | # Meetings Designer | Travel Time (Hours) | # Meetings PM | Documentation
|  | FDOT (kickoff, concept review) | 0 | 0 | 0
|  | Maintaining Agency (cities, counties) | 0 | 0 | 0
|  | Utility Owners | 0 | 0 | 0
|  | Local Agency for Tree Removal | 0 | 0 | 0
|  | Local Citizen Group(s) | 0 | 0 | 0
|  | Engineer's Project Cost | 0 | 0 | 0
|  | Indpendent Project Cost | 0 | 0 | 0
|  | Other Meetings | 0 | 0 | 0
|  | Subtotal Technical Meetings | 0 | 0 | 0
|  | Progress Meetings (if required by FDOT) | 0 | 0
|  | Phase Review Meetings | 0 | 0
|  | Total Landscape Meetings | 0 | 0
|  | Field Reviews | # of Staff | Site Time (per staff) | Travel Time (per staff) | Total Hours
|  | Field Review #1 | 0 | 0 | 0 | 0
|  | Field Review #2 | 0 | 0 | 0 | 0
|  | Field Review #3 | 0 | 0 | 0 | 0
|  | Field Review #4 | 0 | 0 | 0 | 0
|  | Plans-in-hand Field Review | 0 | 0 | 0 | 0
|  | Total Field Review Hours |  |  |  | 0
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E12: Is data collection required? Yes=1 No=0
Note on E13: Estimated # of Outdoor Advertising Sign Structures
Note on E14: Is design file setup required? Yes=1 No=0
Note on E15: Length of project where site inventory and analysis are to occur (miles).
Note on E16: Estimated total area in acres. Include all area within project limits. Do not deduct any unplantable areas.
Note on E17: Length of project where Landscape Opportunity Plan is developed (miles).
Note on E18: Area of project where Landscape Opportunity Plan is developed (acres).
Note on E19: Is a planting report required? Yes=1 No=0
Note on E20: Length of project where planting plans are to occur (miles).
Note on E21: Estimated total area in acres. Include all area within project limits. Do not deduct any unplantable areas.
Note on E22: Length of project where planting plans are to occur (miles).
Note on E23: Estimated total area in acres. Include all area within project limits. Do not deduct any unplantable areas.
Note on E24: Is a feasibility report required? Yes=1 No=0
Note on E25: Estimated total area to be irrigated.
Note on E26: Estimated total area in acres of project to be irrigated.
Note on E27: Estimated total area to be irrigated.
Note on E28: Estimated total area in acres of project to be irrigated.
Note on E29: Is report required? Yes=1 No=0
Note on E30: Is Hardscape Concept Design required? Yes=1 No=0
Note on E31: Is Final Hardscape Design required? Yes=1 No=0
Note on E32: Is an EQR required for the project? Yes=1 No=0
Note on E33: Estimated number of Engineer's Project Cost submittals.
Note on E34: Estimated number of LRE Updates: typically at Phase II, but sometimes for Phase I as well.
Note on E35: Estimated # of technical and modified special provisions.
Note on E38: Is QA/QC required for Landscape Plans? Yes=1 No=0
Note on F38: Enter % between 5% and 10%
Note on E39: Is Supervision required for Landscape Plans?? Yes=1 No=0
Note on E44: Is Coordination required? Yes=1 No=0
Note on F44: % of technical subtotal.
Note on E48: Total hours of travel time required for in person meetings.

## 26. Landscape Plans
| Estimator: |  | 26. Landscape Plans Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
What is the complexity of the planting plan? (See Landscape Guidelines)
LND02-001 | 26.1 | Key Sheet | LS | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 26.1 | [8 empty] | 4
LND02-002 |  | Signature Sheet | LS | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
LND02-003 | 26.2 | Plant Schedule (Sheet no longer produced) | [9 empty] | 26.2
LND02-004 | 26.3 | General Notes/Pay Item Notes | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 26.3 | [5 empty] | 6 | 9 | 12
LND02-005 | 26.4 | Planting Plans For Linear Areas | Linear Project Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 26.4 |  | 2 | 4 | 6
LND02-006 | 26.5 | Planting Plans for Non-Linear Areas (Stormwater Facilities, Rest Areas, Interchanges, & Toll Plazas) | Area Projects Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 26.5 |  | 2 | 4 | 6
LND02-007 | 26.6 | Planting Details | Details | 0 |  | 0 | 0 | 0 | 0 |  |  | 26.6 | [8 empty] | 4
LND02-008 | 26.7 | Irrigation Plans for Linear Areas | Linear Project Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 26.7 | [5 empty] | 2 | 4 | 6
LND02-009 | 26.8 | Irrigation Plans for Non-Linear Areas (Stormwater Facilities, Rest Areas, Interchanges, & Toll Plazas) | Area Projects Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 26.8 | [5 empty] | 2 | 4 | 6
LND02-010 | 26.9 | Irrigation Details | Details | 0 |  | 0 | 0 | 0 | 0 |  |  | 26.9 | [8 empty] | 4
LND02-011 | 26.1 | Hardscape Plans |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 26.1 | [5 empty] | 20 | 45 | 80
LND02-012 | 26.11 | Maintenance Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 26.11 | [5 empty] | 8 | 16 | 24
| Landscape Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
LND02-013 | 26.12 | Quality Assurance/Quality Control | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 26.12
LND02-014 | 26.13 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 26.13
| 26. Landscape Plans Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
`
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E12: Is a Key sheet required? Yes=1 No=0
Note on E13: Is a signature sheet required? If Key Sheet is not required, then no hours will be given for the signature sheet. Yes=1 No=0
Note on E15: Is a general notes/pay item notes sheet required? Yes=1 No=0
Note on E16: Estimated number of sheets for the Planting Plans (Linear Project).
Note on E17: Estimated number of sheets for the Planting Plans (Area Project).
Note on E18: Estimated # of planting details. This task includes any notes required.
Note on E19: Estimated number of sheets for the Irrigation Plans (Linear Project).
Note on E20: Estimated number of sheets for the Irrigation Plans (Area Project).
Note on E21: Estimated # of irrigation details. This task includes any notes required.
Note on E22: Are hardscape plans required for project? Yes=1 No=0
Note on E23: Is a maintenance plan required for the project? Yes=1 No=0
Note on E25: Is QA/QC required for Landscape Plans? Yes=1 No=0
Note on F25: Enter % between 5% and 10%
Note on E26: Is Supervision required for Landscape Plans?? Yes=1 No=0
Note on F26: % of technical subtotal.

## Survey Guidelines
GUIDELINES FOR SURVEY, PHOTOGRAMMETRY, MAPPING, AND TERRESTRIAL MOBILE LIDAR (Work Activities 27 – 30)
These four work activities are interrelated. Not all projects will require photogrammetry, mapping or terrestrial mobile LiDAR: the need or extent of any of these will have a direct relationship on the tasks included in the survey work activity.
All ranges shown in the Survey tasks are for 4-person crew days based on an 8 hour day. The ranges presented in the photogrammetry section represent the work effort that might be expected for individual tasks on typical mapping projects, including topographics, planimetrics, image processing, and fixed and rotary wing flight operations.
The staff hour ranges presented in this section represent the work effort that might be expected for individual tasks on typical roadway projects, ranging from a standard 2-lane resurfacing project (lower end of range) to a complicated reconstruction project (upper end of range). The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual survey tasks. Hours below or above the presented ranges may be applicable based on the constraints or requirements that are specific to the individual project. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
The following are general examples of the types of projects which would contain work effort from below the staff hour ranges contained in this handbook to above the ranges. This list is not inclusive, or always exact, but will provide the basis for beginning estimation and negotiation of staff hours for a project.
Survey Levels 1 through 4 are defined in FDOT Design Manual (FDM), Chapter 114.
Below to Lower End of Range Projects
· Urban and rural 2-lane resurfacing Level 1 survey.
· Rural 2-lane 3R (minor safety, earthwork, and utility involvement) Level 1 or 2.
· Rural 4-lane 3R (minor safety, earthwork, and utility involvement) Level 1 or 2
· Urban 3R (minor safety, earthwork, and utility involvement, primarily only milling and resurfacing) Level 1 or 2
· Multi-lane limited access resurfacing (minimal interchange involvement) Level 1 or 2
Lower End of Range Projects
· Rural 2-lane 3R (major safety, earthwork, and utility involvement) Level 2 or 3
· Rural 4-lane 3R (major safety, earthwork, and utility involvement) Level 2 or 3
· Urban 3R (major safety, earthwork, and utility involvement) Level 2 or 3
· Rural 2-lane to multi-lane widening/resurfacing (minor ROW, earthwork and utility impacts) Level 2 or 3
· Rural 2-lane new construction (new alignment, ROW, earthwork and utility impacts) (This is for full design survey and ROW) Level 4
· Rural 2-lane to urban multi-lane reconstruction (minor ROW and utility impacts, minimal intersection involvement) (This is for full design survey and ROW) Level 4
· Rural or urban 4-lane to 6-lane widening/resurfacing (widening in median, minor ROW, earthwork, and utility impacts, minimal intersection improvement) Level 3 or 4
· Rural 2-lane to 4-lane widening/resurfacing (major ROW, earthwork and utility impacts) Level 3 or 4 for full design model
· Multi-lane limited access resurfacing (minor safety, earthwork, and utility involvement, minimal intersection involvement) Level 2 or 3
· Rural 2-lane to urban multi-lane widening/resurfacing (utilizing existing pavement, minor cross slope correction, major ROW and utility impacts, intersection involvement) Level 3 or 4 for full design model
Middle of Range Projects
· Rural 2-lane to urban multi-lane reconstruction (major ROW and utility impacts, intersection involvement) (This is for full design survey and ROW) Level 4
· Rural multi-lane new construction (new alignment, ROW, earthwork and utility impacts, minimal intersection involvement) (This is for full design survey and ROW) Level 4
· Urban multi-lane new construction (new alignment, major ROW and utility impacts, intersection involvement) (This is for full design survey and ROW) Level 4
· Multi-lane limited access widening/resurfacing (minor ROW and utility impacts, interchange involvement) Level 3 or 4 for full design model (This is for full design survey and ROW)
· Multi-lane limited access reconstruction (minor ROW and utility impacts, interchange involvement) (This is for full design survey and ROW) Level 4
· Multi-lane limited access new construction (new alignment, minor ROW and utility impacts, minimal interchange involvement) (This is for full design survey and ROW) Level 4
Upper End to Above Range Projects
· Multi-lane widening, reconstruction or new alignment with major interchange involvement (major ROW and utility impacts,urban interchange involvement, major access management impacts) (This is for full design survey and ROW) Level 4
· Urban limited access (widening or reconstruction with multi-level interchanges) (This is for full design survey and ROW) Level 4
· Multi-lane limited access new construction (new alignment, major ROW and utility impacts, major interchange involvement) (This is for full design survey and ROW) Level 4

## 27. Survey
Estimator: | [9 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name | [6 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Field Crew Days/Unit | Crew Days | Field Support Hours / Crew Days | Field Support Hours | Office Support Hours / Crew Days | Office Support Hours | Comments
27.1 | Horizontal Project Control (HPC)
| 2-Lane Roadway | Mile |  |  | 0 |  | 0 |  | 0
| Multi-lane Roadway | Mile |  |  | 0 |  | 0 |  | 0
| Interstate | Mile |  |  | 0 |  | 0 |  | 0
27.2 | Vertical PC / Bench Line
| 2-Lane Roadway | Mile |  |  | 0 |  | 0 |  | 0
| Multi-lane Roadway | Mile |  |  | 0 |  | 0 |  | 0
| Interstate | Mile |  |  | 0 |  | 0 |  | 0
27.3 | Alignment and Existing R/W Lines
|  | Mile |  |  | 0 |  | 0 |  | 0
27.4 | Aerial Targets |  |  | Units/Day
| 2-Lane Roadway | EA |  |  | 0 |  | 0 |  | 0
| Multi-lane Roadway | EA |  |  | 0 |  | 0 |  | 0
| Interstate | EA |  |  | 0 |  | 0 |  | 0
27.5 | Reference Points | "A" |  | Units/Day
| 2-Lane Roadway | EA |  |  | 0 |  | 0 |  | 0
| Multi-lane Roadway | EA |  |  | 0 |  | 0 |  | 0
| Interstate | EA |  |  | 0 |  | 0 |  | 0
| Reference Points | "B" |  | Units/Day
| Non Alignment Points/Approximate | EA |  |  | 0 |  | 0 |  | 0
27.6 | Topography/DTM (3D)
|  | Mile |  |  | 0 |  | 0 |  | 0
27.7 | Planimetric (2D)
|  | Mile |  |  | 0 |  | 0 |  | 0
27.8 | Roadway Cross-Sections/Profiles
|  | Mile |  |  | 0 |  | 0 |  | 0
27.9 | Side Street Surveys
|  | Mile |  |  | 0 |  | 0 |  | 0
27.1 | Underground Utilities
| Designates | Mile/Site |  |  | 0 |  | 0 |  | 0
| Locates | Point |  |  | 0 |  | 0 |  | 0
| Survey |  | 0% | 0 | 0 |  | 0 |  | 0
27.11 | Outfall Survey
|  | Mile |  |  | 0 |  | 0 |  | 0
27.12 | Drainage Survey |  |  | Units/Day
|  | EA |  |  | 0 |  | 0 |  | 0
27.13 | Bridge Survey
| Minor / Major | EA |  |  | 0 |  | 0 |  | 0
27.14 | Channel Survey
|  | EA |  |  | 0 |  | 0 |  | 0
27.15 | Pond Site Survey
|  | EA |  |  | 0 |  | 0 |  | 0
27.16 | Mitigation Survey
|  | Mile |  |  | 0 |  | 0 |  | 0
27.17 | Jurisdiction Line Survey
|  | Mile |  |  | 0 |  | 0 |  | 0
27.18 | Geotechnical Support |  |  | Units/Day
|  | EA |  |  | 0 |  | 0 |  | 0
27.19 | Sectional / Grant Survey
|  | Corner |  |  | 0 |  | 0 |  | 0
|  | Mile |  |  | 0 |  | 0 |  | 0
27.2 | Subdivision Location
|  | Block |  |  | 0 |  | 0 |  | 0
27.21 | Maintained R/W
|  | Mile |  |  | 0 |  | 0 |  | 0
27.22 | Boundary Survey
|  | EA |  |  | 0 |  | 0 |  | 0
27.23 | Water Boundary Survey
|  | EA |  |  | 0 |  | 0 |  | 0
27.24 | R/W Staking / R/W Line
|  | EA |  |  | 0 |  | 0 |  | 0
|  | Mile |  |  | 0 |  | 0 |  | 0
27.25 | R/W Monumentation
|  | Point |  |  | 0 |  | 0 |  | 0
27.26 | Line Cutting
|  | Mile |  |  | 0
27.27 | Work Zone Safety
0
27.28 | Vegetation Survey
|  | LS | [6 empty] | 0
27.29 | Tree Survey
|  | LS | [6 empty] | 0
27.3 | Miscellaneous Surveys
[5 empty] | 0 |  | 0 |  | 0
Survey Subtotal |  |  |  | Crew Days | 0 | Field Support Hours | 0 | Office Support Hours | 0
27.31 | Supplemental Surveys | [8 empty] | THE % FOR SUPPLEMENTAL WILL BE DETERMINED AT NEGOTIATIONS. THIS ITEM CAN ONLY BE USED IF AUTHORIZED IN WRITING BY THE DISTRICT SURVEYOR
|  |  |  | 0 | 0 |  | 0 |  | 0
27.32 | Document Research | Units
0
27.33 | Field Reviews | Units
0
27.34 | Technical Meetings | LS
|  |  | 0 | [5 empty] | 0
27.35 | Quality Assurance / Quality Control | LS
[8 empty] | 5% | 0
27.36 | Supervision | LS
[8 empty] | 5% | 0
27.37 | Coordination | LS
[8 empty] | 3% | 0
27. Survey Total |  |  |  | Crew Days | 0 | Field Support Hours | 0 | Office Support Hours | 0
SPLS =
PLS =
Office Support =
[8 empty] | Total Hours = | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | PM Attendance at Meeting Required? |  |  | Number | Comments
Kickoff Meeting with FDOT |  | EA | 0 | 0 | 0 |  |  |  | 0
Baseline Approval Review |  | EA | 0 | 0 | 0 |  |  |  | 0
Network Control Review |  | EA | 0 | 0 | 0 |  |  |  | 0
Vertical Control Review |  | EA | 0 | 0 | 0 |  |  |  | 0
Local Governments (cities, counties) |  | EA | 0 | 0 | 0 |  |  |  | 0
Final Submittal Review |  | EA | 0 | 0 | 0 |  |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 | Subtotal PM Meetings |  |  | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | ** |  |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | ** |  |  | - -
Total Meetings |  |  |  |  | 0 | Total PM Mtgs (carries to Tab 3) |  |  | 0
[5 empty] | Carries to 27.34 |  |  |  | Carries to Tab 3
** Project Manager attendance at progress, phase and field review meetings are manually entered on General Task 3

## 28. Photogrammetry
Estimator: | [12 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name | [6 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hour / Unit | Hours | [5 empty] | Total Range | Comments | Comments
[5 empty] | PSM | Data Compiler | Map/Data Editor | Ortho Analyst | Lab Processor | Flight Crew
28.1 | Flight Preparation | Frame | 0 | 0 | [5 empty] | 0 | 0 |  | Flight crew only
|  | Frame | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.2 | Control Point Coordination
| Post ID | Point | 0 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | Point | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Complier only
28.3 | Mobilization
| Fixed Wing | Hour | 0 | 0 | [5 empty] | 0 | 0 |  | Flight crew only
| Rotary Wing | Hour | 0 | 0 | [5 empty] | 0 | 0 |  | Flight crew only
28.4 | Flight Operations
| Fixed Wing | Mile | 0 | 0 | [5 empty] | 0 | 0
| Rotary Wing | Mile | 0 | 0 | [5 empty] | 0 | 0
28.5 | Photo Products | Sheet | 0 | 0 |  |  |  |  | 0 |  | 0
28.6 | Lidar | Mile | 0 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | Mile | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
|  | Mile | 0 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
28.7 | Aerial Triangulation
| Field Control | Frame | 0 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | Frame | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
| With Aerial GPS Control | Frame | 0 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | Frame | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.8 | Surfaces
| Digital Elevation Model | Model | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
| Digital Terrain Model | Model | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.9 | Ortho Generation | Image | 0 | 0 |  |  |  | 0 |  |  | 0 |  | Ortho Analyst only
28.1 | Rectified Digital Imagery (Georeferenced) | Image | 0 | 0 |  |  |  | 0 |  |  | 0
28.11 | Mosaicking | Image | 0 | 0 |  |  |  | 0 |  |  | 0
28.12 | Sheet Clipping | Sheet | 0 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
|  | Sheet | 0 | 0 |  |  |  | 0 |  |  | 0 |  | Ortho Analyst only
28.13 | Topographics (3D) | Model | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.14 | Planimetrics (2D) | Model | 0 | 0 |  | 0 |  |  |  |  | 0
28.15 | Drainage Basin | Sheet | 0 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
|  | Sheet | 0 | 0 |  |  |  | 0 |  |  | 0 |  | Ortho Analyst only
28.16 | CADD Edit | LS | 25% |  |  | 0 | 0 | 0 | 0 |  | 0 |  | Enter in formula for CADD Edit
28.17 | Data Merging | Model | 0 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
|  | Model | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.18 | Miscellaneous | LS | 1 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | LS | 1 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
|  | LS | 1 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
|  | LS | 1 | 0 |  |  |  | 0 |  |  | 0 |  | Ortho Analyst only
|  | LS | 1 | 0 |  |  |  |  | 0 |  | 0 |  | Lab Processor only
|  | LS | 1 | 0 | [5 empty] | 0 | 0 |  | Flight Crew only
Photogrammetry Technical Subtotal | [10 empty] | 0
28.19 | Field Reviews | LS | 1 |  | 0 | [5 empty] | 0 |  | PSM only
|  | LS | 1 |  |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
28.2 | Technical Meetings | LS |  |  | 0 | [5 empty] | 0
28.21 | Quality Assurance/Quality Control | LS | 5% |  | 0 | [5 empty] | 0
28.22 | Supervision | LS | 5% |  | 0 | [5 empty] | 0
Photogrammetry Nontechnical Subtotal | [10 empty] | 0
28.23 | Coordination | LS | 0% |  | 0 | [5 empty] | 0
28. Photogrammetry Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Check = | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | PM Attendance at Meeting Required? |  |  |  |  | Number |  | Comments
Aerial Mapping Submittal Review |  | EA | 0 | 0 | 0 | [5 empty] | 0
Other Meetings |  | EA | 0 | 0 | 0 | [5 empty] | 0
Subtotal Technical Meetings |  |  |  |  | 0 | Subtotal PM Meetings |  |  |  |  | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | ** |  |  |  |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | ** |  |  |  |  | - -
Total Meetings |  |  |  |  | 0 | Total PM Mtgs (carries to Tab 3) |  |  |  |  | 0
[5 empty] | Carries to 28.20 | [5 empty] | Carries to Tab 3
** Project Manager attendance at progress, phase and field review meetings are manually entered on General Task 3

## 29. Mapping
| Estimator: |  | 29. Mapping Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
Master CADD File
MAP01-001 | 29.1 | Alignment | Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 29.1 | [5 empty] | 2 | 3 | 4
MAP01-002 | 29.2 | Section and 1/4 Section Lines | Section | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.2 | [6 empty] | 2 | 4
MAP01-003 | 29.3 | Subdivisions | Block | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.3 | [6 empty] | 4 | 12
MAP01-004 | 29.4 | Property Lines | Tract | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.4 | [6 empty] | 4 | 10
MAP01-005 | 29.5 | Existing R/W | Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.5 | [5 empty] | 8 | 16 | 24
MAP01-006 | 29.6 | Topography | Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.6 | [6 empty] | 2 | 4
MAP01-007 | 29.7 | Parent Tract Properties/Existing Easements | Parcel | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.7 | [5 empty] | 2 | 5 | 10
MAP01-008 | 29.8 | Proposed R/W Requirements | Parcel | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.8 | [6 empty] | 2 | 4
MAP01-009 | 29.9 | Limits of Construction | Length (Miles) | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.9 | [8 empty] | 2
MAP01-010 | 29.1 | Jurisdictional/Agency Lines | Linear Mile | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.1 | [5 empty] | 2 | 4 | 6
Sheet Files
MAP01-011 | 29.11 | Control Survey Cover Sheet | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.11 | [8 empty] | 8
MAP01-012 | 29.12 | Control Survey Key Sheet | Sheet (24" X 36") | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.12 | [5 empty] | 8 | 12 | 16
MAP01-013 | 29.13 | Control Survey Detail Sheet | Sheet (24" X 36") | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.13 | [5 empty] | 8 | 16 | 24
MAP01-014 | 29.14 | R/W Map Cover Sheet | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.14 | [8 empty] | 8
MAP01-015 | 29.15 | R/W Map Key Sheet | Sheet (24" X 36") | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.15 | [5 empty] | 2 | 12 | 24
MAP01-016 | 29.16 | R/W Map Detail Sheet | Sheet (24" X 36") | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.16 | [5 empty] | 4 | 18 | 32
MAP01-017 | 29.17 | Maintenance Map Cover Sheet | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.17 | [8 empty] | 8
MAP01-018 | 29.18 | Maintenance Map Key Sheet | Sheet (24" X 36") | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.18 | [5 empty] | 2 | 8 | 16
MAP01-019 | 29.19 | Maintenance Map Detail Sheet | Sheet (24" X 36") | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.19 | [5 empty] | 2 | 12 | 24
MAP01-020 | 29.2 | Reference Point Sheet | EA | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.2 | [8 empty] | 0.5
MAP01-021 | 29.21 | Project Control Sheet | Sheet (24" X 36") | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.21 | [5 empty] | 6 | 8 | 12
MAP01-022 | 29.22 | Table of Ownerships Sheet | Parcel | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.22 | [8 empty] | 4 |  |  | 0.2
Miscellaneous Surveys & Sketches
MAP01-023 | 29.23 | Parcel Sketches | Parcel | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.23 | [5 empty] | 4 | 10 | 16
MAP01-024 | 29.24 | TIITF Sketches | Parcel | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.24 | [5 empty] | 12 | 22 | 32
MAP01-025 | 29.25 | Other Specific Purpose Survey(s) | EA | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.25 | [5 empty] | 16 | 50 | 80
MAP01-026 | 29.26 | Boundary Survey(s) Map | EA | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.26 | [5 empty] | 16 | 50 | 80
MAP01-027 | 29.27 | R/W Monumentation Map | Sheet (24" X 36") | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.27 | [5 empty] | 8 | 20 | 32
MAP01-028 | 29.28 | Title Search Map | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.28 | [6 empty] | 2 | 4
MAP01-029 | 29.29 | Title Search Report | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.29 | [8 empty] | 2
MAP01-030 | 29.3 | Legal Descriptions | Parcel | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.3 | [6 empty] | 2 | 4
| Mapping Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
MAP01-031 | 29.31 | Quality Assurance/Quality Control | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 29.31
MAP01-032 | 29.32 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 29.32
MAP01-033 | 29.33 | Mapping Meetings (listed below) | Meetings | 0 |  | 0 | 0 | 0 | 0 |  |  | 29.33 | [8 empty] | 2
MAP01-034 |  |  | Travel Time |  |  | 0 | 0 | 0 | 0
MAP01-035 | 29.34 | Field Reviews (listed below) | LS |  |  | 0 | 0 | 0 | 0 |  |  | 29.34
| Mapping Non-Technical Subtotal |  |  |  |  | 0 | 0 | 0 | 0
MAP01-036 | 29.35 | Coordination | % | 1 | 3% | 0 | 0 | 0 | 0 |  |  | 29.35
MAP01-037 | 29.36 | Supplemental Mapping | LS |  |  | 0 | 0 | 0 | 0 |  |  | 29.36
| Mapping Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
|  | Technical Meetings | # Meetings Designer | Travel Time (Hours) | # Meetings PM | Documentation
|  | Local Governments (cities, counties, MPO) | 0 | 0 | 0
|  | 30/60/90/100% Comment Review Meetings | 0 | 0 | 0
|  | Utility Coordination | 0 | 0 | 0
|  | Other Meetings | 0 | 0 | 0
|  | Subtotal Technical Meetings | 0 | 0 | 0
|  | Progress Meetings (if required by FDOT) | 0 | 0
|  | Phase Review Meetings | 0 | 0
|  | Total Meetings | 0 | 0
|  | Field Reviews | # of Staff | Site Time (per staff) | Travel Time (per staff) | Total Hours
|  | Field Review #1 | 0 | 0 | 0 | 0
|  | Field Review #2 | 0 | 0 | 0 | 0
|  | Field Review #3 | 0 | 0 | 0 | 0
|  | Field Review #4 | 0 | 0 | 0 | 0
|  | Plans-in-hand Field Review | 0 | 0 | 0 | 0
|  | Total Field Review Hours |  |  |  | 0
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E12: Length in miles.
Note on E13: # of Sections
Note on E14: # of Blocks
Note on E15: # of Tracts
Note on E16: Length in miles. (project length includes side streets)
Note on E17: Length in miles.
Note on E18: # of Parcels
Note on E19: # of Parcels
Note on E20: Length in miles.
Note on E21: Length in Linear Mile. (linear mile is defined as the length of the actual lines being plotted, not the project length)
Note on E23: Is a Control Survey Cover Sheet required? Yes=1 No=0
Note on E24: # of Sheets (24" X 36")
Note on E25: # of Sheets (24" X 36")
Note on E26: Is a R/W Map Cover Sheet required? Yes=1 No=0
Note on E27: # of Sheets (24" X 36")
Note on E28: # of Sheets (24" X 36")
Note on E29: Is a Maintenance Map Cover Sheet required? Yes=1 No=0
Note on E30: # of Sheets (24" X 36")
Note on E31: # of Sheets (24" X 36")
Note on E32: # of Center Line Points
Note on E33: # of Sheets (24" X 36")
Note on E34: # of Parcels
Note on E36: # of Parcels
Note on E37: # of Parcels
Note on E38: # of Specific Purpose Surveys
Note on E39: # of Boundary Surveys
Note on E40: # of Sheets (24" X 36")
Note on E41: Is a Title Search Map required? Yes=1 No=0
Note on E42: Is a Title Search Report required? Yes=1 No=0
Note on E43: # of Parcels
Note on E45: Is QA/QC required? Yes=1 No=0
Note on F45: Enter % between 5% and 10%
Note on E46: Is Supervision required? Yes=1 No=0
Note on F46: % of technical subtotal.
Note on E47: Estimated # of meeting listed below
Note on E56: Total hours of travel time required for in person meetings.

## 30. Terrestrial Mobile LiDAR
Estimator: | [11 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name | [6 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hour / Unit | Hours |  |  |  |  | Total Range | Comments
[5 empty] | PSM | Senior LiDAR Technician | LiDAR Technician | LiDAR Operator | Field Technician
30.1 | Terrestrial Mobile LiDAR Mission Planning
|  | Scan Miles | 1 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Scan Miles | 1 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Scan Miles | 1 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.2 | Project Control Point Coordination
| 0 | Point | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Point | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Point | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.3 | Terrestrial Mobile LiDAR Mobilization
| 0 | Personnel | 1 | 0 |  |  |  | 0 |  | 0 | LiDAR Operator Only
|  | Personnel | 2 | 0 |  |  |  |  | 0 | 0 | Field Technician Only
30.4 | Terrestrial Mobile LiDAR Mission
| 0 | Scan Miles | 1 | 0 |  |  |  | 0 |  | 0 | LiDAR Sensor Operator
|  | Scan Miles | 1 | 0 | Number of Field Technician(s) = |  |  | 2 | 0 | 0 | 1-Technician to drive vehicle , 1-base station
30.5 | Terrestrial Mobile LiDAR Processing
| 0 | Scan Miles | 1 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Scan Miles | 1 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Scan Miles | 1 | 0 |  |  |  | 0 |  | 0 | LiDAR Operator
30.6 | Terrestrial Mobile Photography Processing
| 0 | Scan Miles | 1 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Scan Miles | 1 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Scan Miles | 1 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.7 | Transformation / Adjustment
| 0 | Scan Miles | 1 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Scan Miles | 1 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Scan Miles | 1 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.8 | Classification / Editing
| 0 | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.9 | Specific Surface Reporting
| 0 | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.1 | Topographic (3D) Mapping
| 0 | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.11 | Topographic (2D) Planimetric Mapping
| 0 | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.12 | CADD Edits
| 0 | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.13 | Data Merging
| 0 | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.14 | Miscellaneous
| Survey Report | LS | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | LS | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | LS | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Tech Only
|  | LS | 0 | 0 |  |  |  | 0 |  | 0 | LiDAR Operator Only
|  | LS | 0 | 0 |  |  |  |  | 0 | 0 | Field Technician Only
|  |  | Mobile Scan Technical Subtotal | [6 empty] | 0
30.15 | Field Reviews
|  | LS | 0 |  | 0 |  |  |  |  | 0
|  | LS | 0 |  |  | 0 |  |  |  | 0
30.16 | Technical Meetings
|  | LS | [7 empty] | 0 | From Meetings Table Below
30.17 | Quality Assurance / Quality Control
|  | LS | 0% | [6 empty] | 0
30.18 | Supervision
|  | LS | 0% | [6 empty] | 0
|  |  | Mobile Scan Nontechnical Subtotal | [6 empty] | 0
30.19 | Coordination
|  | LS | 0% | [6 empty] | 0
30. Terrestrial Mobile LiDAR Mapping Total | [9 empty] | 0
* The low end of the range is for rural 2-lane; medium range is for typical Multi-Lane; the high end of the range is for urban/interstate.
Technical Meetings |  |  | Units | No of Units | Hours/ Unit | Total Hours | Comments |  |  |  | PM Attendance at Meeting Required? | Number
Terrestrial Mobile LiDAR Mapping Submittal Review |  |  | EA | 0 | 0 | 0 | [5 empty] | 0
Other Meetings |  |  | EA | 0 | 0 | 0 | [5 empty] | 0
Subtotal Technical Meetings | [5 empty] | 0 | Subtotal PM Meetings |  |  |  |  | 0
Progress Meetings (if required by FDOT) |  |  | EA | 0 | 0 | 0 | ** |  |  |  |  | - -
Phase Review Meetings |  |  | EA | 0 | 0 | 0 | ** |  |  |  |  | - -
Total Meetings | [5 empty] | 0 | Total PM Mtgs (carries to Tab 3) |  |  |  |  | 0
[6 empty] | Carries to 30.16 |  |  |  |  | Carries to Tab 3
** Project Manager attendance at progress, phase and field review meetings are manually entered on General Task 3

## Architecture Guidelines
ARCHITECTURE GUIDELINES
The range of hours following each element of design is to be used as a guide to calculate the number of total hours required to perform that task, including design and drafting. The negotiator must use professional judgment based on the project scope to determine where each task would fall with in the range of hours. Each task must be judged based on its complexity. Various factors must be evaluated when considering the complexity of a project. Two of the primary considerations used to analyze projects are size and level of design effort.
Size factors to consider:
· Amount of information placed on each sheet
· Number of unique spaces to be designed
· Shape and massing of the structure
· Site constraints
· Number of stories
· Number of areas which require an enlarged floor plan
Level of design effort factors to consider:
· Shape and massing of the structure
· Level of interior and exterior finishes
· Soil conditions
· Access to utilities
· Structural system
· Communication requirements
· Number of dissimilar building components
· Amount of specialty equipment
The range of hours following each element of design is to be used as a guide to calculate the number of total hours required to perform that task, including design and drafting. The negotiator must use professional judgment based on the project scope to determine where each task would fall with in the range of hours. Each task must be judged based on its complexity and work effort.
The size of a building is not necessarily related to the complexity/work effort of its design. To determine the design complexity/work effort several factors must be considered.
1. Site Constraints: Limited R/W, topo, utilities placement, roadway geometry, and lane configurations, wind zones, flood zones, etc.
2. Familiarity: Whether or not a design Consultant is familiar with FDOT processes, building types, and use of generic plans.
3. Expandability: A requirement for future expandability may be a consideration in the initial design of the building.
4. Building Type: The function, size, utility requirements, operator space, location, etc. will affect the design.
5. Code requirements, Capacity ands Occupancy These requirements can have a profound effect on materials and systems
used in the design. Life Safety and other code requirements will have a direct influence on layout and size of space.
6. Location: The location of the building project can greatly affect elements such as utilities access and site access.
7. Sheet Production: The number of sheets will be determined by such elements as content of sheet, unique and special
purpose spaces, shape and mass of building(s), spaces requiring enlarged floor plans and details, interior finishes, structural
system, mechanical system, communications and data systems, and special equipment.
The following examples are used as a guide only. See the State's DMS Fee Curve Guidelines for a complete guide of complexity.
1. Considerably more than average complexity
Materials testing and research lab, Special purpose, Multiple use buildings.
2. More than average complexity
Vehicle Maintenance and Vehicle Maintenance Yard, Renovations, alterations, Large Toll Plaza, Weigh in Motion/Inspection Sta., Rest Area addition/redesign, Medium Toll Plaza, Small Toll Plaza, Rest Area interior modifications/refinish, Rest Area replacement
3. Repairs and Renovations
Miscellaneous Repairs and Renovations, Alterations to Office Space, Fire Code Corrective Work
4. Average Complexity
Office Space improvements, Medium Toll Plaza, WIM Sta., Rest Area replacement
5. Less than average complexity
Garage, Service, Repetitive Design, Open space office building
6. Considerably Less Than Average Complexity
Parking garage, warehouse, storage

## 31. Architecture Development
Estimator: | [11 empty] | Enter project name & description
999999-1-32-01
Representing |  |  | Print Name | [5 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task |  | Scale | Units | No of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
Architectural Plans
31.1 | Architectural Program Review/Verification |  |  | Text Pages | 0 | 0 | 0 | 0
31.2 | Key Sheet and Index of Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.3 | General Notes, Abbreviations, Symbols, and Legend |  |  | Sheet | 0 | 0 | 0 | 0
31.4 | Life Safety Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.5 | Site Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.6 | Floor Plans (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.7 | Floor Plans (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.8 | Exterior Elevations |  |  | Sheet | 0 | 0 | 0 | 0
31.9 | Roof Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.1 | Roof Details |  |  | Sheet | 0 | 0 | 0 | 0
31.11 | Interior Elevations |  |  | Sheet | 0 | 0 | 0 | 0
31.12 | Rest Room Plans (Enlarged) |  |  | Sheet | 0 | 0 | 0 | 0
31.13 | Rest Room Elevations |  |  | Sheet | 0 | 0 | 0 | 0
31.14 | Building Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.15 | Stair Section, Enlarged Stair Plan and Details |  |  | Sheet | 0 | 0 | 0 | 0
31.16 | Reflective Ceiling Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.17 | Room Finish Schedule or Finish Plan |  |  | Sheet | 0 | 0 | 0 | 0
31.18 | Door and Window Schedule |  |  | Sheet | 0 | 0 | 0 | 0
31.19 | Door Jamb Details and Window Details |  |  | Sheet | 0 | 0 | 0 | 0
31.2 | Exterior Wall Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.21 | Interior Wall Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.22 | Overhead Door Details |  |  | Sheet | 0 | 0 | 0 | 0
31.23 | Curtain Wall Details |  |  | Sheet | 0 | 0 | 0 | 0
31.24 | Fascia, Soffit and Parapet Details |  |  | Sheet | 0 | 0 | 0 | 0
31.25 | Signage Details |  |  | Sheet | 0 | 0 | 0 | 0
31.26 | Miscellaneous Details |  |  | Sheet | 0 | 0 | 0 | 0
31.27 | Repetitive Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.28 | Design Narrative Reports |  |  | LS | 0 | 0 |  | 0
31.29 | Permitting |  |  | LS | 0 | 0 |  | 0
31.3 | Other Pertinent Project Documentation |  |  | LS | 0 | 0 |  | 0
31.31 | Project Cost |  |  | LS | 0 | 0 |  | 0
31.32 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 0 | 0 |  | 0
Architectural Plans Technical Subtotal | [6 empty] | 0 | 0
31.33 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.34 | Technical Meetings | [7 empty] | See listing below
31.34.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.34.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.34.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.34.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.34.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.34.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.34.7 | Subtotal Technical Meetings | [6 empty] | 0
31.35 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.36 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.37 | Supervision |  |  | LS | % | 0% |  | 0
Architectural Plans Total | [6 empty] | 0 | 0
Structural Plans
31.38 | General Notes, Abbreviations, Symbols, and Legend |  |  | Sheet | 0 | 0 | 0 | 0
31.39 | Foundation Plans (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.4 | Foundation Plans (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.41 | Slab Plans (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.42 | Slab Plans (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.43 | Slab Placement Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.44 | Slab Placement Details |  |  | Sheet | 0 | 0 | 0 | 0
31.45 | Foundation Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.46 | Foundation Details |  |  | Sheet | 0 | 0 | 0 | 0
31.47 | Slab Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.48 | Slab Details |  |  | Sheet | 0 | 0 | 0 | 0
31.49 | Roof Framing Plans (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.5 | Roof Framing Plans (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.51 | Roof Loading Plans and Details |  |  | Sheet | 0 | 0 | 0 | 0
31.52 | Roof Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.53 | Roof Details |  |  | Sheet | 0 | 0 | 0 | 0
31.54 | Bearing Wall Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.55 | Bearing Wall Details |  |  | Sheet | 0 | 0 | 0 | 0
31.56 | Column Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.57 | Column Details |  |  | Sheet | 0 | 0 | 0 | 0
31.58 | Miscellaneous Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.59 | Repetitive Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.6 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.61 | Project Cost |  |  | LS | 1 | 0 |  | 0
31.62 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Structural Plans Technical Subtotal | [6 empty] | 0 | 0
31.63 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.64 | Technical Meetings | [7 empty] | See listing below
31.64.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.64.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.64.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.64.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.64.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.64.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.64.7 | Subtotal Technical Meetings | [6 empty] | 0
31.65 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.66 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.67 | Supervision |  |  | LS | % | 0% |  | 0
Structural Plans Total | [6 empty] | 0 | 0
Mechanical Plans
31.68 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  |  | Sheet | 0 | 0 | 0 | 0
31.69 | Plans (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.7 | Plans (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.71 | Details |  |  | Sheet | 0 | 0 | 0 | 0
31.72 | Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.73 | Piping Schematics |  |  | Sheet | 0 | 0 | 0 | 0
31.74 | Control Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.75 | Schedules |  |  | Sheet | 0 | 0 | 0 | 0
31.76 | HVAC Calculations |  |  | Sheet | 0 | 0 | 0 | 0
31.77 | Life Cycle Cost Analysis |  |  | Sheet | 0 | 0 | 0 | 0
31.78 | Repetitive Sheets |  |  | LS | 1 | 0 |  | 0
31.79 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.8 | Project Cost |  |  | LS | 1 | 0 |  | 0
31.81 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Mechanical Plans Technical Subtotal | [6 empty] | 0 | 0
31.82 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.83 | Technical Meetings | [7 empty] | See listing below
31.83.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.83.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.83.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.83.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.83.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.83.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.83.7 | Subtotal Technical Meetings | [6 empty] | 0
31.84 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.85 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.86 | Supervision |  |  | LS | % | 0% |  | 0
Mechanical Plans Total | [6 empty] | 0 | 0
Plumbing Plans
31.87 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  |  | Sheet | 0 | 0 | 0 | 0
31.88 | Plans (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.89 | Plans (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.9 | Isometrics (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.91 | Riser Diagrams |  |  | Sheet | 0 | 0 | 0 | 0
31.92 | Details |  |  | Sheet | 0 | 0 | 0 | 0
31.93 | Repetitive Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.94 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.95 | Project Cost |  |  | LS | 1 | 0 |  | 0
31.96 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Plumbing Plans Technical Subtotal | [6 empty] | 0 | 0
31.97 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.98 | Technical Meetings | [7 empty] | See listing below
31.98.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.98.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.98.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.98.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.98.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.98.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.98.7 | Subtotal Technical Meetings | [6 empty] | 0
31.99 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.1 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.101 | Supervision |  |  | LS | % | 0% |  | 0
Plumbing Plans Total | [6 empty] | 0 | 0
Fire Protection Plans
31.102 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  |  | Sheet | 0 | 0 | 0 | 0
31.103 | Fire Protection Plan |  |  | Sheet | 0 | 0 | 0 | 0
31.104 | Riser Diagram, Details, and Partial Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.105 | Hydraulic Calculation |  |  | Sheet | 0 | 0 | 0 | 0
31.106 | Repetitive Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.107 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.108 | Project Cost |  |  | LS | 1 | 0 |  | 0
31.109 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Fire Protection Plans Technical Subtotal | [6 empty] | 0 | 0
31.11 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.111 | Technical Meetings | [7 empty] | See listing below
31.111.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.111.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.111.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.111.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.111.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.111.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.111.7 | Subtotal Technical Meetings | [6 empty] | 0
31.112 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.113 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.114 | Supervision |  |  | LS | % | 0% |  | 0
Fire Protection Plans Total | [6 empty] | 0 | 0
Electrical Plans
31.115 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  |  | Sheet | 0 | 0 | 0 | 0
31.116 | Electrical Site Plan |  |  | Sheet | 0 | 0 | 0 | 0
31.117 | Lighting Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.118 | Lighting Fixtures Schedules |  |  | Sheet | 0 | 0 | 0 | 0
31.119 | Lighting Fixtures Details |  |  | Sheet | 0 | 0 | 0 | 0
31.12 | Lightning Protection Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.121 | Lightning Protection Details |  |  | Sheet | 0 | 0 | 0 | 0
31.122 | Power Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.123 | Power Distribution Riser Diagrams |  |  | Sheet | 0 | 0 | 0 | 0
31.124 | Panel Board Schedules |  |  | Sheet | 0 | 0 | 0 | 0
31.125 | Data Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.126 | Data Details |  |  | Sheet | 0 | 0 | 0 | 0
31.127 | Communication Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.128 | Communication Details |  |  | Sheet | 0 | 0 | 0 | 0
31.129 | Security Alarm System Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.13 | Miscellaneous Details |  |  | Sheet | 0 | 0 | 0 | 0
31.131 | Repetitive Sheets |  |  | LS | 1 | 0 |  | 0
31.132 | Energy Analysis |  |  | LS | 1 | 0 |  | 0
31.133 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.134 | Project Cost |  |  | LS | 1 | 0 |  | 0
31.135 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Electrical Plans Technical Subtotal | [6 empty] | 0 | 0
31.136 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.137 | Technical Meetings | [7 empty] | See listing below
31.137.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.137.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.137.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.137.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.137.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.137.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.137.7 | Subtotal Technical Meetings | [6 empty] | 0
31.138 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.139 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.14 | Supervision |  |  | LS | % | 0% |  | 0
Electrical Plans Total | [6 empty] | 0 | 0
Architecture Development Subtotal | [6 empty] | 0 | 0
31.141 | GBRS Certification |  |  | LS | 1 | 0 |  | 0
31.141.1 | GBRS Coordination Meetings |  |  | LS | 1 | 0 |  | 0
31.141.2 | GBRS Commissioning |  |  | LS | 1 | 0 |  | 0
31.141.3 | GBRS Green Credit |  |  | LS | 1 | 0 |  | 0
31.142 | Coordination |  |  | LS | % | 0% |  | 0
31.143 | Building Information Modeling (BIM) |  |  | Project | - - | - - | - - | - - | Using AutoCad Revit or a similar program for the production of construction documents does not cost the Client/Owner any additional design fee. However, the proportion of the fee is more front loaded because of the design process. The creation of the 3D model is part of the design and must be converted into 2D to print the construction documents. The additional use of the Virtual 3D model can provide additional advantages and services, but at an additional cost. Another very useful feature is the user's ability to visualize the spaces in 3D early on as part of the approval process.
31. Architecture Development Total | [6 empty] | 0 | 0
Total Technical Meetings (sum of meetings above) | [9 empty] | Comments | PM Attendance at Meeting Required? | Number
Meeting |  | Hours | [5 empty] | Total Meetings | Total Hours
|  | Architectural Plans | Structural Plans | Mechanical Plans | Plumbing Plans | Fire Protection Plans | Electrical Plans
FDOT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Local Governments (cities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Local Governments (counties) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Engineer's Project Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Independent Project Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Other Meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings | [7 empty] | 0 | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ** | - -
Phase Review Meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ** | - -
Total All Meetings | [7 empty] | 0 | 0 |  | Total PM Meetings (carries to Tab 3) | 0
Carries to Tab 3
** Project Manager attendance at progress, phase and field review meetings are manually entered on General Task 3

## 31T. Toll Facility Development
| Estimator: |  | 31T. Toll Facility Development Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District |  | Andra Diggs II, P.E., District Design Engineer, Florida's Turnpike Enterprise | [7 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
| NOTE: Signature Block is optional, per District preference |  |  | Helpful high level notes about toll site(s) scope can go here.
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
| CIVIL PLANS (SC_ Sheets Unless Noted Otherwise) | [9 empty] | 1. All items in RED font are for the user to edit cell. 2. Cells that are shaded in DARK GREY in collumn F contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | SITE CIVIL PLANS
RDY02-003 | 1 | Key Sheets | Master (TF) | 0 |  | 0 | 0 | 0 | 0 |  |  | 1 |  |  |  | 4
RDY02-004 |  |  | Toll Sites | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 4
|  |  | Building Types (A__) | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 4
RDY02-005 |  |  | Gantry Types (GS_) | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 4
RDY02-006 | 2 | Signature Sheet(s) | All Tolling Disciplines (TF) | 0 |  | 0 | 0 | 0 | 0 | Digital signature effort covered under Tab 3, Section 3.9. |  | 2 |  |  |  | 4
RDY02-006 | 3 | Toll Site Location Map | (TF) | 0 |  | 0 | 0 | 0 | 0 | Modify roadway project layout and adapt for Tolls - Identify Toll site gantries - Gantry Type, TEB/RTC, MP and Station. |  | 3 | 6 | 8 | 12
RDY02-006 | 4 | Civil General Notes and Legend |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 4 |  |  |  | 4
RDY02-006 | 5 | Overall Site Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 5 | 6 | 10 | 12
RDY02-003 | 6 | Enlarged Site Plan(s) | 1-3 Lane Sites | 0 |  | 0 | 0 | 0 | 0 |  |  | 6 | 12 | 12 | 16
RDY02-004 |  |  | 4+ Lanes (Wide Sites) | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 8 | 10 | 12
RDY02-003 | 7 | Grading Plan(s) | 1-3 Lane Sites | 0 |  | 0 | 0 | 0 | 0 |  |  | 7 | 16 | 18 | 20
RDY02-004 |  |  | 4+ Lanes (Wide Sites) | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 8 | 10 | 12
RDY02-006 | 8 | Grading Sections |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 10 | 12
RDY02-007 | 9 | Report of Core Borings |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 9 |  |  |  | 1
RDY02-008 | 10 | Civil Site Detail(s) |  | 0 |  | 0 | 0 | 0 | 0 | Includes bollards, barrier-sidewalk detail, and site concrete joint layouts; Includes toll site equipment slabs; When the toll loop pavement area is rigid concrete pavement, provide concrete joints with conduit stub-up locations. |  | 10 |  |  |  | 8
RDY02-007 | 11 | Other |  |  |  | 0 | 0 | 0 | 0 | Includes additional effort required to support work not covered by an existing defined task (i.e coordination, job specific task, special design effort, or express lanes development with the District) |  | 11 | 6 | 8 | 10
RDY02-003 | 12 | Estimated Quantities (EQ) Report | TEB Sites | 0 |  | 0 | 0 | 0 | 0 |  |  | 12 |  |  |  | 12
RDY02-004 |  |  | RTC Sites | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 16
RDY02-003 | 13 | Toll Siting Technical Memorandum (TSTM) | Report & Assembly | 0 |  | 0 | 0 | 0 | 0 |  |  | 13 |  |  |  | 72
|  |  | Future Toll Sites | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 16 | 24 | 32
RDY02-004 |  |  | Toll Sites | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 40 | 48 | 56
RDY02-008 | 14 | Project Cost |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 14 | 8 | 10 | 12
RDY02-008 | 15 | Modified Special Provisions/TSPs |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 15 |  |  |  | 12
| Site Civil Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
RDY02-031 | 16 | Quality Assurance/Quality Control | % | 1 | 7% | 0 | 0 | 0 | 0 |  |  | 16
RDY02-032 | 17 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 17
| Site Civil Plans Total |  |  |  |  | 0 | 0 | 0 | 0
| ARCHITECTURAL PLANS (AA_ Sheets) | [10 empty] | ARCHITECTURAL PLANS
RDY02-006 | 18 | General Notes, Abbreviations, Symbols, and Legend |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 18 |  |  |  | 4
RDY02-006 | 19 | Floor Plan and Life Safety Information |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 19 |  |  |  | 8
RDY02-006 | 20 | Reflected Ceiling Plan and Roof Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 20 |  |  |  | 8
RDY02-006 | 21 | Exterior Elevations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 21 |  |  |  | 8
RDY02-006 | 22 | Wall Sections |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 22 |  |  |  | 8
RDY02-006 | 23 | Door Details |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 23 |  |  |  | 6
RDY02-006 | 24 | Building Finish and Door Schedules |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 24 |  |  |  | 4
RDY02-006 | 25 | Other |  |  |  | 0 | 0 | 0 | 0 |  |  | 25
RDY02-006 | 26 | Permitting |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 26 | 40 | 60 | 80
RDY02-006 | 27 | Project Cost |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 27 |  |  |  | 6
RDY02-006 | 28 | Technical Special Provision Package |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 28 | 8 | 10 | 12
| Architectural Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
RDY02-031 | 29 | Quality Assurance/Quality Control | % | 1 | 7% | 0 | 0 | 0 | 0 |  |  | 29
RDY02-032 | 30 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 30
| Architectural Plans Total |  |  |  |  | 0 | 0 | 0 | 0
| STRUCTURAL PLANS (AS_ Sheets - Building Only) (See Tab 18 for Gantry Structural) | [10 empty] | STRUCTURAL PLANS
RDY02-006 | 31 | General Notes, Abbreviations, Symbols, and Legend |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 31 |  |  |  | 4
RDY02-006 | 32 | Floor Slab Plan and Foundation Sections |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 32 |  |  |  | 8
RDY02-006 | 33 | Roof Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 33 |  |  |  | 8
RDY02-006 | 34 | Exterior Elevations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 34 |  |  |  | 8
RDY02-006 | 35 | Section(s) & Detail(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 35 |  |  |  | 8
RDY02-006 | 36 | Structural Details for Equipment Frames |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 36 |  |  |  | 6
RDY02-006 | 37 | Other |  |  |  | 0 | 0 | 0 | 0 |  |  | 37
RDY02-006 | 38 | Structural Calculations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 38 |  |  |  | 40
RDY02-006 | 39 | Project Cost |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 39 |  |  |  | 6
RDY02-006 | 40 | Technical Special Provision Package |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 40 | 6 | 8 | 10
| Structural Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
RDY02-031 | 41 | Quality Assurance/Quality Control | % | 1 | 7% | 0 | 0 | 0 | 0 |  |  | 41
RDY02-032 | 42 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 42
| Structural Plans Total |  |  |  |  | 0 | 0 | 0 | 0
| MECHANICAL PLANS (AM_ Sheets) | [10 empty] | MECHANICAL PLANS
RDY02-006 | 43 | General Notes, Abbreviations, Symbols, Legend, and Code Data |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 43 |  |  |  | 4
RDY02-006 | 44 | Mechanical Floor Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 44 |  |  |  | 8
RDY02-006 | 45 | Mechanical Fuel Oil Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 45 |  |  |  | 8
RDY02-006 | 46 | Mechanical Equipment Details |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 46 |  |  |  | 6
RDY02-006 | 47 | AC Equipment Schedule |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 47 |  |  |  | 8
RDY02-006 | 48 | Other |  |  |  | 0 | 0 | 0 | 0 |  |  | 48
RDY02-006 | 49 | Mechanical Calculations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 49 |  |  |  | 40
RDY02-006 | 50 | Project Cost |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 50 |  |  |  | 6
RDY02-006 | 51 | Technical Special Provision Package |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 51 | 8 | 12 | 16
| Mechanical Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
RDY02-031 | 52 | Quality Assurance/Quality Control | % | 1 | 7% | 0 | 0 | 0 | 0 |  |  | 52
RDY02-032 | 53 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 53
| Mechanical Plans Total |  |  |  |  | 0 | 0 | 0 | 0
| ELECTRICAL PLANS (*E_ Sheets) | [10 empty] | ELECTRICAL PLANS
|  | SITE ELECTRICAL (SE_ Sheets) | [9 empty] | SITE ELECTRICAL
RDY02-006 | 54 | Electrical Symbols, Legend, and Abbreviations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 54 |  |  |  | 4
RDY02-006 | 55 | Electrical General Notes |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 55 |  |  |  | 4
RDY02-006 | 56 | Overall Electrical Site Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 56 |  |  |  | 8
RDY02-003 | 57 | Enlarged Electrical Site Plan(s) - TEB Sites | 1-3 Lane Sites | 0 |  | 0 | 0 | 0 | 0 |  |  | 57 | 10 | 12 | 16
RDY02-004 |  |  | 4+ Lanes (Wide Sites) | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 8 | 10 | 12
RDY02-006 | 58 | Lightning Protection Plan(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 58 |  |  |  | 8
RDY02-006 | 59 | Primary Service Routing Plan(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 59 |  |  |  | 12
RDY02-006 | 60 | Primary Service Routing Section(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 60 |  |  |  | 12
RDY02-006 | 61 | Electrical Site Detail(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 61 |  |  |  | 8
RDY02-006 | 62 | Roadside Tolling Cabinet (RTC) Electrical Site Plans | Enlarged Electrical Site Plan (E6/Loop) | 0 |  | 0 | 0 | 0 | 0 |  |  | 62 |  |  |  | 10
RDY02-006 |  |  | Enlarged Electrical Site Plan (Power) | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 10
RDY02-006 |  |  | Enlarged Electrical Site Plan (Data) | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 10
RDY02-006 |  |  | Riser Diagram(s) | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 |  |  | Electrical Schedule(s) | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 | 63 | Other |  |  |  | 0 | 0 | 0 | 0 |  |  | 63
|  | GANTRY ELECTRICAL (GE_ Sheets) | [9 empty] | GANTRY ELECTRICAL
RDY02-006 | 64 | Electrical Symbols, Legend, and Abbreviations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 64 |  |  |  | 4
RDY02-006 | 65 | Electrical General Notes |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 65 |  |  |  | 4
RDY02-006 | 66 | Non-Accessible Gantry | Electrical Plan(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 66 |  |  |  | 8
RDY02-006 |  |  | Electrical Details | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 6
RDY02-006 | 67 | Accessible Gantry | Electrical Plan(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 67 |  |  |  | 8
RDY02-006 |  |  | Enlarged Electrical Plan | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 |  |  | Electrical Details | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 6
RDY02-006 |  |  | Access Platform: Lighting Plan and Details | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 | 68 | Lightning Protection Details |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 68 |  |  |  | 6
RDY02-006 | 69 | Other |  |  |  | 0 | 0 | 0 | 0 |  |  | 69
|  | BUILDING ELECTRICAL (AE_ Sheets) | [9 empty] | BUILDING ELECTRICAL
RDY02-006 | 70 | Electrical Symbols, Legend, and Abbreviations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 70 |  |  |  | 4
RDY02-006 | 71 | Electrical General Notes |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 71 |  |  |  | 4
RDY02-006 | 72 | Power Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 72 |  |  |  | 12
RDY02-006 | 73 | Lighting Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 73 |  |  |  | 8
RDY02-006 | 74 | Lightning Protection Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 74 |  |  |  | 8
RDY02-006 | 75 | SCADA and Security System Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 75 |  |  |  | 8
RDY02-006 | 76 | Tolling Equipment Raceway Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 76 |  |  |  | 8
RDY02-006 | 77 | Interior Elevations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 77 |  |  |  | 8
RDY02-006 | 78 | Wall Mounted Wiring Details |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 78 |  |  |  | 6
RDY02-006 | 79 | Cable Tray Mounted Receptacles Details |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 79 |  |  |  | 8
RDY02-006 | 80 | Miscellaneous Electrical Details |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 80 |  |  |  | 6
RDY02-006 | 81 | Power Riser Diagram(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 81 |  |  |  | 8
RDY02-006 | 82 | Panel Schedules and Electrical Load Summary |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 82 |  |  |  | 12
RDY02-006 | 83 | SCADA System Notes and Block Diagram |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 83 |  |  |  | 6
RDY02-006 | 84 | Other |  |  |  | 0 | 0 | 0 | 0 |  |  | 84
|  | ELECTRICAL LUMP SUM ITEMS | [9 empty] | ELECTRICAL LUMP SUMS
RDY02-006 | 85 | Toll Siting Technical Memorandum - Utility Coordination |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 85 |  |  |  | 24
RDY02-006 | 86 | Electrical Calculations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 86 |  |  |  | 32
RDY02-006 | 87 | Project Cost |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 87 |  |  |  | 12
RDY02-006 | 88 | Technical Special Provision Package |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 88 | 32 | 36 | 40
| Electrical Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
RDY02-031 | 89 | Quality Assurance/Quality Control | % | 1 | 7% | 0 | 0 | 0 | 0 |  |  | 89
RDY02-032 | 90 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 90
| Electrical Plans Total |  |  |  |  | 0 | 0 | 0 | 0
| DEMOLITION PLANS (D_ Sheets) | [10 empty] | DEMOLITION PLANS
RDY02-006 | 91 | Key Sheet |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 91 |  |  |  | 4
RDY02-006 | 92 | General Notes and Legend |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 92 |  |  |  | 4
RDY02-006 | 93 | Abbreviations, Symbols, and Demolition Notes |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 93 |  |  |  | 6
RDY02-006 | 94 | Overall Site Demolition / Renovation Plan |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 94 | 8 | 16 | 24
RDY02-006 | 95 | Site Grading Plan(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 95 | 8 | 16 | 24
RDY02-006 | 96 | Site Demolition / Renovation Plan(s) (Phase 1 - #) | Civil | 0 |  | 0 | 0 | 0 | 0 |  |  | 96 |  |  |  | 8
RDY02-006 |  |  | Electrical | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 | 97 | Island / Lane Demolition / Renovation Plan(s) (Phase 1 - #) | Architectural | 0 |  | 0 | 0 | 0 | 0 |  |  | 97 |  |  |  | 8
RDY02-006 |  |  | Structural | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 |  |  | Mechanical / Plumbing | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 12
RDY02-006 |  |  | Electrical | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 | 98 | Canopy Demolition / Renovation Plan(s) (Phase 1 - #) | Architectural | 0 |  | 0 | 0 | 0 | 0 |  |  | 98 |  |  |  | 8
RDY02-006 |  |  | Structural | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 |  |  | Electrical | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 | 99 | Tunnel Demolition / Renovation Plan(s) (Phase 1 - #) | Structural | 0 |  | 0 | 0 | 0 | 0 |  |  | 99 |  |  |  | 8
RDY02-006 |  |  | Mechanical / Plumbing | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 |  |  | Electrical | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 8
RDY02-006 | 100 | Building Demolition / Renovation Floor Plan(s) | Architectural | 0 |  | 0 | 0 | 0 | 0 |  |  | 100 |  |  |  | 12
RDY02-006 |  |  | Structural | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 12
RDY02-006 |  |  | Mechanical / Plumbing | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 12
RDY02-006 |  |  | Electrical | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 12
RDY02-006 | 101 | Building Architectural Demolition / Renovation Elevation(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 101 |  |  |  | 12
RDY02-006 | 102 | Building Demolition / Renovation Detail(s) | Architectural | 0 |  | 0 | 0 | 0 | 0 |  |  | 102 |  |  |  | 12
RDY02-006 |  |  | Mechanical / Plumbing | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 12
RDY02-006 |  |  | Electrical | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 12
RDY02-006 | 103 | Power Riser Diagram(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 103 |  |  |  | 8
RDY02-006 | 104 | Electrical Panel Schedule(s) |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 104 |  |  |  | 8
RDY02-006 | 105 | Other |  |  |  | 0 | 0 | 0 | 0 |  |  | 105
RDY02-006 | 106 | Demolition Report |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 106 |  |  |  | 40
RDY02-006 | 107 | Structural Calculations |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 107 |  |  |  | 24
RDY02-006 | 108 | Project Cost |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 108 |  |  |  | 12
RDY02-006 | 109 | Technical Special Provision Package |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 109 | 12 | 16 | 24
| Demolition Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0
RDY02-031 | 110 | Quality Assurance/Quality Control | % | 1 | 7% | 0 | 0 | 0 | 0 |  |  | 110
RDY02-032 | 111 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 111
| Demolition Plans Total |  |  |  |  | 0 | 0 | 0 | 0
| Toll Facility Development Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
RDY01-046 | 112 | Tolls Design Meetings (listed below) | Meetings | 0 |  | 0 | 0 | 0 | 0 | Assumes 1 hour for each meeting - If no travel time is included, assume remote attendance. |  | 112 |  |  |  | 1
RDY01-047 |  |  | Travel Time |  |  | 0 | 0 | 0 | 0 | If meeting is to be led by the Tolling Consultant, add hours to "Travel Time" to cover agenda prep and meeting notes.
RDY01-048 | 113 | Field Reviews (listed below) | LS |  |  | 0 | 0 | 0 | 0 |  |  | 113
RDY02-032 | 114 | Coordination | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 114
| 31T. Toll Facility Development Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab.
|  | Technical Meetings | # Meetings Designer | Travel Time (Hours) | # Meetings PM | Documentation
|  | Tolls Kickoff | 0 | 0 | 0
|  | 45% MOT | 0 | 0 | 0
|  | Electrical Utility Coordination | 0 | 0 | 0
|  | Specification / Pay Item Coordination | 0 | 0 | 0
|  | Engineer's Project Cost | 0 | 0 | 0
|  | Independent Project Cost | 0 | 0 | 0
|  | Other Meetings | 0 | 0 | 0
|  | Subtotal Technical Meetings | 0 | 0 | 0
|  | Progress Meetings (if required by FDOT) | 0 | 0
|  | Phase Review Meetings | 0 | 0
|  | Total Tolls Design Meetings | 0 | 0
|  | Field Reviews | # of Staff | Site Time (per staff) | Travel Time (per staff) | Total Hours
|  | Field Review #1 (Discipline) | 0 | 0 | 0 | 0
|  | Field Review #2 (Discipline) | 0 | 0 | 0 | 0
|  | Field Review #3 (Discipline) | 0 | 0 | 0 | 0
|  | Field Review #4 (Discipline) | 0 | 0 | 0 | 0
|  | Field Review #5 (Discipline) | 0 | 0 | 0 | 0
|  | Plans-in-hand Field Review | 0 | 0 | 0 | 0
|  | Total Field Review Hours |  |  |  | 0
[5 empty] | # | Hours / # | Hours / # | Hours / # | Hours / #
|  |  |  | Sheets | 0 | 0 | 0 | 0 | 0
|  |  |  | Sites | 0 | 0 | 0 | 0 | 0
|  |  |  | Building Types | 0 | 0 | 0 | 0 | 0
|  |  |  | Gantry Types | 0 | 0 | 0 | 0 | 0
RDY02-006
RDY02-006
RDY02-006
RDY02-003
RDY02-004
RDY02-003
RDY02-004
RDY02-006
RDY02-007
RDY02-008
RDY02-007
RDY02-008
RDY02-003
RDY02-004
RDY02-008
RDY02-008
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E13: Is a Master Key Sheet required? Yes=1 No=0
Note on E14: Estimated # of toll sites in the project limits covered in the "SC_" sheets. References no. of toll sites
Note on E15: Estimated # of toll equipment building types in the project limits covered in the "AA_" sheets.
Note on E16: Estimated # of toll gantry types in the project limits covered in the "GS_" sheets.
Note on E17: # of expected sheets for signature (1-2 toll sites = 2, 3-4 toll sites = 4, 5+ toll sites = 6)
Note on E18: Estimated # of map sheets. 10-12 miles can be shown on a single sheet.
Note on F18: What is the complexity of the toll site?
Note on E19: 1 per toll site. References no. of toll sites
Note on E20: 1 per toll site. References no. of toll sites
Note on F20: What is the complexity of the toll site?
Note on E21: 1 for each site with 1-3 lanes.
Note on F21: What is the complexity of the toll site?
Note on E22: Toll sites with 4+ lanes, provide 2 sheets per site.
Note on F22: What is the complexity of the toll site?
Note on E23: 1 for each site with 1-3 lanes. References cell E22.
Note on F23: What is the complexity of the toll site?
Note on E24: Toll sites with 4+ lanes, provide 2 sheets per site.
Note on F24: What is the complexity of the toll site?
Note on E25: 1 per toll site. References no. of toll sites. Include cross sections at minimum (3) points of interest (building, maintenance pull-off area, and toll site equipment slabs).
Note on F25: What is the complexity of the toll site?
Note on E26: 1 per site when gantry upright is not near building foundation or equipment slab.
Note on E27: 2 per site. References no. of toll sites.
Note on E29: 1 for each TEB Site.
Note on E30: 1 for each RTC Site.
Note on E31: Is a TSTM required? Yes=1 No=0
Note on E32: # of Future Toll Sites.
Note on F32: What is the complexity of the toll site?
Note on E33: 1 per toll site. References no. of toll sites
Note on F33: What is the complexity of the toll site?
Note on E34: Is a project cost required? Yes=1 No=0
Note on F34: What is the complexity of the toll site?
Note on E35: Are TSPs / MSPs required? Yes=1 No=0
Note on E37: Is QA/QC required for Signalization Plans? Yes=1 No=0
Note on F37: Enter % between 5% and 10%
Note on E42: 1 per Toll Equipment Building type.
Note on E43: 1 per Toll Equipment Building type.
Note on E44: 1 per Toll Equipment Building type.
Note on E45: 1 per Toll Equipment Building type.
Note on E46: 1 per Toll Equipment Building type.
Note on E47: 1 per Toll Equipment Building type.
Note on E48: 1 per Toll Equipment Building type.
Note on E50: Is permitting required? Yes=1 No=0
Note on F50: What is the complexity of the permit effort?
Note on E51: Is a project cost required? Yes=1 No=0
Note on E52: Are Architectural TSP sections required? Yes=1 No=0
Note on F52: What is the complexity of the Architectural TSP sections?
Note on E54: Is QA/QC required for Signalization Plans? Yes=1 No=0
Note on F54: Enter % between 5% and 10%
Note on E59: 2 per Toll Equipment Building type.
Note on E60: 1 per Toll Equipment Building type.
Note on E61: 1 per Toll Equipment Building type.
Note on E62: 1 per Toll Equipment Building type.
Note on E63: 1 per Toll Equipment Building type.
Note on E64: 2 per Toll Equipment Building type.
Note on E66: Are structural calculations (non-gantry) required? Yes=1 No=0
Note on E67: Is a project cost required? Yes=1 No=0
Note on E68: Are Structural TSP sections (non-gantry) required? Yes=1 No=0
Note on F68: What is the complexity of the Structural TSP sections?
Note on E70: Is QA/QC required for Signalization Plans? Yes=1 No=0
Note on F70: Enter % between 5% and 10%
Note on E75: 1 per Toll Equipment Building type.
Note on E76: 1 per Toll Equipment Building type.
Note on E77: 1 per Toll Equipment Building type.
Note on E78: 2 per Toll Equipment Building type.
Note on E79: 1 per Toll Equipment Building type.
Note on E81: Are mechanical calculations required? Yes=1 No=0
Note on E82: Is a project cost required? Yes=1 No=0
Note on E83: Are Mechanical TSP sections required? Yes=1 No=0
Note on F83: What is the complexity of the Mechanical TSP sections?
Note on E85: Is QA/QC required for Signalization Plans? Yes=1 No=0
Note on F85: Enter % between 5% and 10%
Note on E91: 1 per site
Note on E92: 1 per site
Note on E93: 1 per site
Note on E94: 1 for each site with 1-3 lanes.
Note on F94: What is the complexity of the toll site?
Note on E95: Toll sites with 4+ lanes, provide 2 sheets per site.
Note on F95: What is the complexity of the toll site?
Note on E96: 1 per site
Note on E97: 1 per site
Note on E98: 1 per site if needed for roadway crossings.
Note on E99: 2 per ramp site min. 3 per mainline site min.
Note on E100: 1 per site
Note on E101: 1 per site
Note on E102: 1 per site
Note on E103: 2 per site
Note on E104: 1 per site
Note on E107: 1 per Gantry type.
Note on E108: 1 per Gantry type.
Note on E109: 1 per Gantry for approx. every 78 ft of span.
Note on E110: 5 per Gantry type.
Note on E111: 1 per Gantry per direction of travel.
Note on E112: 1 per Gantry type.
Note on E113: 6 per Gantry type.
Note on E114: 1 per Gantry type.
Note on E115: 1 per Gantry type.
Note on E118: 1 per Building type.
Note on E119: 1 per Building type.
Note on E120: 1 per Building type.
Note on E121: 1 per Building type.
Note on E122: 1 per Building type.
Note on E123: 1 per Building type.
Note on E124: 1 per Building type.
Note on E125: 3 per Building type.
Note on E126: 1 per Building type.
Note on E127: 1 per Building type.
Note on E128: 7 per Building type.
Note on E129: 1 per Building type.
Note on E130: 2 per Building type.
Note on E131: 2 per Building type.
Note on E134: Is a TSTM required? Yes=1 No=0
Note on E135: Are electrical calculations required? Yes=1 No=0
Note on E136: Is a project cost required? Yes=1 No=0
Note on E137: Are Electrical TSP sections required? Yes=1 No=0
Note on F137: What is the complexity of the Electrical TSP sections?
Note on E139: Is QA/QC required for Signalization Plans? Yes=1 No=0
Note on F139: Enter % between 5% and 10%
Note on E144: 1 per site.
Note on E145: 1 per site.
Note on E146: 1 per site.
Note on E147: 1 per site.
Note on F147: What is the complexity of the Site Demo?
Note on E148: 1 per site.
Note on F148: What is the complexity of the Site Demo grading?
Note on E149: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E150: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E151: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E152: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E153: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E154: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E155: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E156: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E157: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E158: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E159: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E160: As needed to coordinate with MOT phasing and demonstrate tolling demo/reno sequencing.
Note on E161: 1 per site. Not needed if full site demo.
Note on E162: 1 per site. Not needed if full site demo.
Note on E163: 1 per site. Not needed if full site demo.
Note on E164: 1 per site. Not needed if full site demo.
Note on E165: 1 per site. Not needed if full site demo.
Note on E166: 2 per site. Not needed if full site demo without phasing.
Note on E167: 2 per site. Not needed if full site demo.
Note on E168: 2 per site. Not needed if full site demo.
Note on E169: Required when existing building remains or phased demolition required.
Note on E170: Required when existing building remains or phased demolition required.
Note on E172: Is a Demolition Report required? Yes=1 No=0
Note on E173: Are structural calculations (non-gantry) required to support phased canopy removal? Yes=1 No=0
Note on E174: Is a project cost required? Yes=1 No=0
Note on E175: Are Demo TSP sections required? Yes=1 No=0
Note on F175: What is the complexity of the Demo TSP sections?
Note on E177: Is QA/QC required for Signalization Plans? Yes=1 No=0
Note on F177: Enter % between 5% and 10%
Note on E182: Estimated # of meetings listed below
Note on E189: Total hours of travel time required for in person meetings.

## Noise Guidelines
NOISE GUIDELINES
The staff hour ranges presented in this section represent the work effort that is expected for individual tasks related to modeling a typical roadway project. Noise analysis ranges are based on the number of noise receptors that have a potential to be impacted by the project. Number of noise receptors is a function of existing land use and roadway context classification.
Each alternative is considered a corridor and may be categorized at different ranges of complexity. Specific aspects of each individual project should be considered in negotiating hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
Lower End of Range Projects
Any corridor identified with a context classification of C1-Natural; C2-Rural of any length; or C3C-Surban Commercial with no residentials. Factors contributing to a lower classification include:
· Minimal noise sensitive uses in the corridor at a low density of development
· Few cross-roads, interchange ramps or other facilities that require additional modeling effort
· Minimal number of distinct traffic volumes needed to be entered into model
· Simple terrain and roadway cross-sections (minimal terrain or elevation changes that need to be coded in model)
· Minimal public involvement expected since likelihood of noise abatement is low
Middle of Range Projects
Any corridor identified with a context classification of C2T-Rural Town, C3R-Suburban Residential, C3C- Suburban Commercial, or C4-Urban General. Factors contributing to a lower classification include:
· length less or equal to 5 miles (greater length may justify “upper end” classification)
· moderate density and number of Noise Sensitive Areas (NSAs) proximate to corridor resulting in moderate number of receptors modeled:
o single family or low-level multi-family residential; mostly single-story properties
o churches, schools, outdoor uses (restaurant dining, etc.) or other sensitive receptors
o low to moderate number of outdoor “special land use” properties: parks, pools, etc.
o few building rows or coded barriers needed
· Some additional roadway links to be modeled (crossroads, turn lanes, interchange ramps, etc.) of a moderate level of complexity (few curves, few superelevated sections, etc.)
· Moderate numbers of roadway segments with distinct traffic volumes to be input.
· Relatively simple terrain and simple rural/suburban cross section to be included in model
· Moderate public involvement anticipated (potential for some abatement and outreach to a few communities)
Upper End of Range Projects
Any corridor identified with a context classification of C5-Urban Center or C6-Urban Core of any length; or
Any corridor greater than 5 miles identified with a context classification of C2T-Rural Town, 3CR-Suburban Residential, C3C- Suburban Commercial, T3 Suburban Zone, or C4-Urban General);
Factors contributing to an upper end classification include:
· large number of distinct NSAs proximate to corridor
· Density of NSAs is high resulting in large number of closely-spaced receptors, building rows in model, etc.:
o dense single family or multi-family residential; some or many multi-story properties
o many churches, schools, outdoor uses (restaurant dining, etc.) or other sensitive receptors
o Extensive outdoor “special land use” properties: parks, pools, etc.
o Numerous roadway links to be modeled (highway mainline, ramps, turn lanes, crossroads/overpass/underpass, etc.)
o Complex terrain and/or roadway cross section near NSAs that requires multiple features in model including terrain lines to define cut/fill, bridges, MSE walls, barrier walls, ditches, etc.
o Many traffic volumes to be input for many distinct segments of roadway
o Intensive public involvement anticipated (high likelihood of abatement and outreach to many people or to numerous distinct NSAs).

## 32. Noise Barrier Assessment
Estimator: | [7 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
32.1 | Noise Analysis | LS | 1 | 0 | 0
32.2 | Noise Barrier Evaluation | LS | 1 | 0 | 0
32.3 | Public Involvement | LS | 1 | 0 | 0
32.4 | Outdoor Advertising Identification | LS | 1 | 0 | 0
32.5 | Noise Study Report (NSR) Addendum | LS | 1 | 0 | 0
Noise Barrier Impact Design Assessment in the Design Phase Technical Subtotal |  |  |  |  | 0
32.6 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
32.7 | Quality Assurance/Quality Control | LS | % | 0% | 0
32.8 | Supervision | LS | % | 0% | 0
Noise Barrier Impact Design Assessment in the Design Phase Nontechnical Subtotal |  |  |  |  | 0
32.9 | Coordination | LS | % | 0% | 0
32. Noise Barrier Impact Design Assessment in the Design Phase Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours |  | PM Attendance at Meeting Required? | Number
Kickoff Meeting with FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Alternative Evaluation with FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Local Agency (cities, counties) |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 32.6 |  |  | Carries to Tab 3

## ITS Guidelines
ITS GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical traffic projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project.
A "Lower Range" roadway project may fall in the "Middle Range" for Lighting projects and vice versa. See the project ranges below. The project ranges should be used only for Reference & Master Design Files and Quantities from Analysis.
Lower Range
1. Adding very limited number of ITS devices.
2. Small extension of existing freeway management system.
3. Installation of isolated devices such as a CCTV camera, a DMS sign or RWIS site.
Middle Range
1. Small extension of existing freeway management system, communications architecture already determined.
2. Freeway management system with no communications hubs and all devices of a single type.
Upper Range
1. Complex urban freeway management system with a variety of different ITS of devices.
2. Lengthy rural freeway management system.
3. Freeway management system with numerous communications hubs and rings of devices.

## 33. ITS Analysis
Estimator: | [7 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
33.1 | ITS Analysis | Per Site | 0 | 0 | 0
33.2 | Communications Subsystem Analysis | LS | 1 | 0 | 0
33.3 | Grounding, Surge Suppression, and Lightning Protection Analysis | Per Site | 0 | 0 | 0
33.4 | Power Subsystem | LS | 1 | 0 | 0
33.5 | Voltage Drop Calculations | Per Site | 0 | 0 | 0
33.6 | Design Documentation | LS | 1 | 0 | 0
33.7 | Existing ITS System | LS | 1 | 0 | 0
33.8 | Queue Analysis | Per Site | 0 | 0 | 0
33.9 | Reference and Master ITS Design File | Per Site | 0 | 0 | 0
33.1 | Reference and Master Communications Design File | Per Mile | 0 | 0 | 0
33.11 | ITS Poles and Overhead Structures Elevation Analysis | Per Site | 0 | 0 | 0
33.12 | DMS Sign Panel Design Analysis | Per Site | 0 | 0 | 0
33.13 | ITS Quantities for EQ Report | ITS Installations | 0 | Calculated Hours | 0 |  |  |  | Yes | 24
|  |  |  | 0 |  |  |  |  | No | 2
33.14 | Project Cost | LS | 1 | 0 | 0
33.15 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
33.16 | Other ITS Analyses | LS | 1 | 0 | 0
Intelligent Transportation Systems Analysis Technical Subtotal |  |  |  |  | 0
33.17 | Field Reviews | LS | 1 | 0 | 0
33.18 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
33.19 | Quality Assurance/Quality Control | LS | % | 0% | 0
33.2 | Supervision | LS | % | 0% | 0
Intelligent Transportation Systems Analysis Nontechnical Subtotal |  |  |  |  | 0
33.21 | Coordination | LS | % | 0% | 0
33. Intelligent Transportation Systems Analysis Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
Kickoff Meeting with FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Local Governments (cities, counties, MPO) |  | EA | 0 | 0 | 0 |  |  | 0
Utility Owners |  | EA | 0 | 0 | 0 |  |  | 0
Field Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Engineer's Project Cost |  | EA | 0 | 0 | 0 |  |  | 0
Indpendent Project Cost |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 33.18 |  |  | Carries to Tab 3
Note on D22: Estimated # of ITS Installations (Poles, Base-Mounted Cabinet, DMS, HUB) for the project.
Note on E22: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on E23: Consider adding 4 hours to the calculated hours when required to include EQ Report with Phase II Submittal.

## 34. ITS Plans
| Estimator: |  | 34. ITS Plans Staff Hours | [6 empty] | Enter project name & description | How to Use This Form
999999-1-32-01
| Representing |  | Print Name | [6 empty] | Signature / Date | Video Tutorials - Short Webinars for each Staff Hour Form
| FDOT District | [9 empty] | Calculated hours represent the expected effort to complete each task based on project parameters and should be considered a starting point for staff hour negotiations. The Consultant and Department staff must jointly determine the appropriate staff hours to fully cover the effort.
Consultant Name
NOTE: Signature Block is optional, per District preference
| Task No. | Task | Project Parameter |  |  | Staff Hours |  |  |  | Documentation |  | Task | Project Complexity |  |  |  |  | Task Complexity |  |  | Basis |  |  | Other
|  |  | Description | Units | Complexity | Calculated | Department | Consultant | Negotiated | Provide documentation when negotiated hours differ from the calculated hours. |  |  | Below | Low | Mid | Upper | Above | Simple | Standard | Complex | Base 1 | Base 2 | Base 3 | N/A 1 | N/A 2 | N/A 3
ITS02-001 | 34.1 | Key Sheet | LS | 0 |  | 0 | 0 | 0 | 0 |  | 1. All items in RED font are for the user to edit cell. 2. All cells that are shaded in RED contain a drop down list for the user to make a selection. 3. Most "Project Parameter" cells will have a brief explanation of what should be inserted in the cell, this information is displayed by selecting a cell and hovering over that cell with your cursor. 4. All cells designed not to be edited by the user have been locked for the users convenience to avoid accidental edits of formulas, text, etc. If you recognize any errors in the locked cells, please contact the Staff Hour Forms Manager listed below. | 34.1 | [8 empty] | 4
ITS02-002 |  | Signature Sheet | LS | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 2
ITS02-003 | 34.2 | General Notes/Pay Item Notes | LS | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.2 | [5 empty] | 6 | 9 | 12
ITS02-004 | 34.3 | Project Layout | Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.3 | [8 empty] | 4
ITS02-005 | 34.4 | Communication Overview Sheet | ITS Site | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.4 | [8 empty] | 1
ITS02-006 | 34.5 | Typical & Special Details | Details | 0 | Standard | 0 | 0 | 0 | 0 |  |  | 34.5 | [8 empty] | 4
ITS02-007 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [11 empty] | 8
ITS02-008 | 34.6 | ITS & Communication Plan Sheet | Linear Project Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.6 |  | 4 | 6 | 8
ITS02-009 |  |  | ITS Installation | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 4
ITS02-010 | 34.7 | Maintenance of Communications Plan | Sheet(s) | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.7 | [8 empty] | 2
ITS02-011 | 34.8 | Fiber Optic Splice Diagrams | ITS Cabinet | 0 | Standard | 0 | 0 | 0 | 0 |  |  | 34.8 | [6 empty] | 2
ITS02-012 |  |  |  | 0 | Complex | 0 | 0 | 0 | 0 | [10 empty] | 4
ITS02-013 |  |  | Master ITS Hub Shelter | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 6
ITS02-014 | 34.9 | Grounding & Lightning Protection Plans | Site | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.9 | [8 empty] | 10
ITS02-015 | 34.1 | Cross Sections | Ground Mount ITS Site | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.1 | [8 empty] | 4
ITS02-016 |  |  | Cantilever ITS Site | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 8
ITS02-017 |  |  | Span Truss, MSE Wall, Bridge Mount, ITS Site | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 12
ITS02-018 | 34.11 | Hybrid & DMS Guide Sign Data | Sign Panel | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.11 | [8 empty] | 2
ITS02-019 | 34.12 | Service Point Details | ITS Cabinet | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.12 | [8 empty] | 6
ITS02-020 | 34.13 | Strain Pole Schedule | Strain Pole | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.13 | [8 empty] | 2
ITS02-021 | 34.14 | Temporary Traffic Control Plans | TTCP Notes | 0 |  | 0 | 0 | 0 | 0 |  |  | 34.14 | [8 empty] | 2
ITS02-022 |  |  | TTCP Detour Plan | 0 |  | 0 | 0 | 0 | 0 | [11 empty] | 6
| ITS Plans Technical Hours Subtotal |  |  |  |  | 0 | 0 | 0 | 0 |  | Please contact the Staff Hour Forms Manager below for further assistance. Mike Pennington, P.E. Project Management Support Engineer Mike.Pennington@dot.state.fl.us (850)414-4346
ITS02-023 | 34.15 | Quality Assurance/Quality Control | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 34.15
ITS02-024 | 34.16 | Supervision | % | 1 | 5% | 0 | 0 | 0 | 0 |  |  | 34.16
| ITS Plans Total |  |  |  |  | 0 | 0 | 0 | 0
Carries to Summary Tab
Note on G10: Calculated Staff Hours represent a recommended starting point for negotiations based on established guidelines.
Note on H10: FDOT recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on I10: Consultant recommended staff hours for the project. These hours may differ from the calculated staff hours recommended.
Note on J10: Final negotiated staff hours for the project.
Note on E11: Is a Key sheet required? Yes=1 No=0
Note on E12: Is a signature sheet required? If Key Sheet is not required, then no hours will be given for the signature sheet. Yes=1 No=0
Note on E13: Is a general notes/pay item notes sheet required? Yes=1 No=0
Note on E14: Estimated number of sheets for Project Layout Sheet.
Note on E15: Estimated # of ITS Sites. Use only when required by Department.
Note on E16: Estimated # of details that require minor or no engineering analysis (e.g., common details typically used in projects).
Note on E17: Estimated # details requiring engineering analysis (e.g., unique details that need to be created).
Note on E18: Estimated number of sheets for ITS & Communication Plan (Linear Project).
Note on E19: If the project is non-linear, what is the estimated # of ITS Installations?
Note on E20: Estimated number of sheets for Maintenance of Communications Plan.
Note on E21: Estimated # of ITS Cabinets requiring a standard diagram.
Note on E22: Estimated # of ITS Cabinets requiring a complex diagram (cross-connection/splice junction).
Note on E23: Estimated # of Master ITS Hub Shelters.
Note on E24: Estimated # of sites requiring grounding plans or lightning protection plans. Use this task when standard drawings and interim standards do not address the situation.
Note on E25: Estimated # of ground mount ITS sites.
Note on E26: Estimated # of cantilever mounted ITS sites.
Note on E27: Estimated # of full span truss mount ITS sites, MSE wall mount ITS sites, and bridge mount ITS sites.
Note on E28: Estimated # of Hybrid & DMS signs that must be imported from guide sign program.
Note on E29: Estimated # of ITS cabinets requiring service point details when standard plans are not applicable.
Note on E30: Estimated # of strain poles.
Note on E31: Are TTCP notes required? (Use only when not shown in Roadway TTCP) Yes=1 No=0
Note on E32: Estimated # TTCP detour plans required. (Use only when not shown in Roadway TTCP)
Note on E34: Is QA/QC required? Yes=1 No=0
Note on F34: Enter % between 5% and 10%
Note on E35: Is Supervision required? Yes=1 No=0
Note on F35: % of technical subtotal.

## Geotechnical Guidelines
GEOTECHNICAL GUIDELINES
The staff hour estimating form, basis and these accompanying instructions were developed to be consistent with the Geotechnical section of the Standard Scope of Service covering the typical range of geotechnical investigations anticipated on 80 percent of all highway projects. It is recognized that the Districts may need to vary the specific requirements of the scope for performance of geotechnical work to make them District or project specific. Where such variations occur, it is recommended that all changes to the Standard Scope be shown in italics to alert the user that the scope requirements have changed from the standard and that the range of staff hours shown in the basis may no longer be applicable to a specific task.
The ‘typical’ range of geotechnical investigations considered as applicable includes the following:
· Projects with geotechnical staffhours ranging from approx. 100 to 3,000;
· Projects that include commonly encountered soil and rock conditions, site investigation methods and geotechnical
design recommendations.
An example of a typical project would include evaluation of roadway subgrade or embankment stability/settlement related to sinkholes, soft clays, organic soils and/or high groundwater. A typical project would require geotechnical guidance for normal cut and fill. It may also require recommendations for realignment, surcharge, excavation and replacement, subgrade reinforcement using geosynthetics and/or underdrains. Examples of projects considered atypical and, therefore, may fall below the range are: RRR projects, minor intersection improvements, etc. Examples of projects considered atypical and, therefore, may fall above the range are: dealing with extensive waste phosphatic clays or design recommendations for soil improvement by lime/cement subgrade stabilization, deep dynamic compaction, vibroflotation, compaction grouting, pile reinforced embankments, etc.
The user must use experience and common sense in assessing where the specific project requirements may deviate from the typical project and some guidance is provided in the basis for each task. For instance, minimum hours listed are only applicable to typical projects. If needed, individual Structures Items can be used when negotiating Roadway projects, and individual Roadway Items can be used when negotiating Structures projects. If neither the Standard Scope nor the basis specifically include or describe an activity, type of analysis or geotechnical solution then it most likely is not covered within the typical staff hour ranges provided for guidance.
Although not specifically developed for Districtwide Geotechnical services, the staff hour estimating form, basis and these instructions may be used as a reference to such work if it falls within the typical range as defined above. Since analysis and reporting requirements for small geotechnical tasks may vary from the Standard Scope, the user should be cautious in applying the ranges shown in the basis to such work. The ranges were ‘proof tested’ against several typical projects from various Districts and found to result in reasonably consistent staff hour estimates compared to previously negotiated total staff hours. The form may be applicable to large projects over 3,000 staff hours but there is no comparative experience with a project of this size. Again the user should be cautious in applying the form, basis and instructions to very small or very large projects.
A number of tasks included in the staff hour estimating form are frequently requested of the geotechnical engineer by other design professionals. These tasks include Stormwater Volume Recovery Analysis and/or Background Seepage Analysis, Lateral Load Analysis, and Sheet Pile Wall Analysis. The user should determine if adequate hours for these activities are included in the relevant Drainage and Structures portions of the project to avoid repetition.
To use the form and instructions the user must have evaluated the project scope in addition to the likely subsurface conditions and foundation alternatives in sufficient detail to estimate the total number, type and depth of exploratory borings for Roadways and Structures as well as the relative complexity of the project. In general, simple straightforward projects will require lower staffhours, while conversely more complex projects will merit higher staffhours per unit within the ‘typical’ ranges listed on the estimating sheet for ‘lump sum’ items. When hours are determined ‘per item’ (such as per 100 LF of boring), and a range of hours is given to be multiplied by that item, it is intended that the higher end of the range be used for smaller projects, and vice versa.
Remember that this form is intended to estimate the TOTAL number of hours for each task including engineering or technician hours to perform the task, senior review hours and applicable clerical hours.

## 35. Geotechnical
Estimator: | [7 empty] | Enter project name & description
999999-1-32-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
Roadway
35.1 | Document Collection and Review | LS | 1 | 0 | 0
35.2 | Develop Detailed Boring Location Plan | LS | 1 | 0 | 0
35.3 | Stake Borings/Utility Clearance | Boring | 0 | 0 | 0
35.4 | Muck Probing | Crew Day | 0 | 0 | 0
35.5 | Coordinate and Develop MOT Plans for Field Investigation | EA | 0 | 0 | 0
35.6 | Drilling Access Permits | Location | 0 | 0 | 0
35.7 | Property Clearances | EA | 0 | 0 | 0
35.8 | Groundwater Monitoring | EA | 0 | 0 | 0
35.9 | LBR/Resilient Modulus Sampling | EA | 0 | 0 | 0
35.10 | Coordination of Field Work | 100 lf of boring | 0 | 0 | 0
35.11 | Soil and Rock Classification - Roadway | 100 lf of boring | 0 | 0 | 0
35.12 | Design LBR | LS | 1 | 0 | 0 | Only if LBR tests are required
35.13 | Laboratory Data | 100 lf of boring | 0 | 0 | 0
35.14 | Seasonal High Water Table | Boring | 0 | 0 | 0
35.15 | Parameters for Water Retention Areas | EA | 0 | 0 | 0
35.16 | Delineate Limits of Unsuitable Material | Cross-section | 0 | 0 | 0
35.17 | Electronic Files for Cross-Sections | 100 lf of boring | 0 | 0 | 0 | Duplication of Roadway Effort?
35.18 | Embankment Settlement and Stability | Embankment Boring | 0 | 0 | 0
35.19 | Monitor Existing Structures | LS | 1 | 0 | 0
35.20 | Stormwater Volume Recovery and/or Background Seepage Analysis | EA | 0 | 0 | 0 | Duplication of Drainage Effort?
35.21 | Geotechnical Recommendations | LS | 1 | 0 | 0
35.22 | Pavement Condition Survey and Pavement Evaluation Report | LS | 1 | 0 | 0
35.23 | Preliminary Roadway Report | LS | 1 | 0 | 0
35.24 | Final Report | EA | 0 | 0 | 0
35.25 | Auger Boring Drafting | 100 lf boring | 0 | 0 | 0
35.26 | SPT Boring Drafting | 100 lf boring | 0 | 0 | 0
Roadway Geotechnical Subtotal |  |  |  |  | 0
Structures
35.27 | Develop Detailed Boring Location Plan | LS | 1 | 0 | 0
35.28 | Stake Borings/Utility Clearance | Boring | 0 | 0 | 0
35.29 | Coordinate and Develop MOT Plans for Field Investigation | EA | 0 | 0 | 0
35.30 | Drilling Access Permits | Location | 0 | 0 | 0
35.31 | Property Clearances | EA | 0 | 0 | 0
35.32 | Collection of Corrosion Samples | EA | 0 | 0 | 0
35.33 | Coordination of Field Work | 100 lf of boring | 0 | 0 | 0
35.34 | Soil and Rock Classification - Structures | 100 lf of boring | 0 | 0 | 0
35.35 | Tabulation of Laboratory Data | 100 lf of boring | 0 | 0 | 0
35.36 | Estimate Design Groundwater Level for Structures | EA | 0 | 0 | 0
35.37 | Selection of Foundation Alternatives (BDR) | Bridge boring | 0 | 0 | 0
35.38 | Detailed Analysis of Selected Foundation Alternate(s) | Bridge boring | 0 | 0 | 0 | See Basis for reducing by 35.35
35.39 | Bridge Construction and Testing Recommendations | Bridge boring | 0 | 0 | 0
35.40 | Lateral Load Analysis (Optional) | Bridge boring | 0 | 0 | 0 | Duplication of Structural Effort?
35.41 | Walls | Wall Boring | 0 | 0 | 0
35.42 | Sheet Pile Wall Analysis (Optional) | Wall Boring | 0 | 0 | 0 | Duplication of Structural Effort?
35.43 | Design Soil Parameters for Signs, Signals, High Mast Lights, and Strain Poles and Geotechnical Recommendations | Boring | 0 | 0 | 0
35.44 | Box Culvert Analysis | EA | 0 | 0 | 0
35.45 | Preliminary Report - BDR | EA | 0 | 0 | 0
35.46 | Final Report - Bridge and Associated Walls | EA | 0 | 0 | 0
35.47 | Final Reports - Signs, Signals, Box Culvert, Walls and High Mast Lights | EA | 0 | 0 | 0
35.48 | SPT Boring Drafting | 100 lf of boring | 0 | 0 | 0
35.49 | Other Geotechnical | LS | 1 | 0 | 0
Structural Geotechnical Subtotal |  |  |  |  | 0
Geotechnical Technical Subtotal |  |  |  |  | 0
35.50 | Technical Special Provisions and Modified Special Provisions | EA | 0 | 0 | 0
35.51 | Field Reviews | LS | 1 | 0 | 0
35.52 | Technical Meetings | LS | 1 | 0 | 0 | Meetings listed below
35.53 | Quality Assurance/Quality Control | LS | % | 0% | 0
35.54 | Supervision | LS | % | 0% | 0
Geotechnical Nontechnical Subtotal |  |  |  |  | 0
35.55 | Coordination | LS | % | 0% | 0
35. Geotechnical Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
Kickoff Meeting with FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Boring Layout Approval |  | EA | 0 | 0 | 0 |  |  | 0
Attend in BDR Review Meeting |  | EA | 0 | 0 | 0 |  |  | 0
30/60/90% Submittal Review |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 35.52 |  |  | Carries to Tab 3