## Tab
CONSULTANT/ Firm Name:
Surveyor in Charge:
Contract No.:
Authorization No.:
FM No.:
Database No.:
Project Description/Limits:
Based on a | 4 | man | 8 | Hour day F.C.
NTP DATE:
Invoice period: from
Invoice period: to
rev. 9-14

## RIGHT OF WAY MAP
PERCENTAGE OF RIGHT OF WAY MAP WORK COMPLETE FORM
0
FIRM NAME
0
SURVEYOR IN CHARGE
SURVEYOR IN CHARGE SIGNATURE
INVOICING PERIOD DATES: | 0 | to | 0 |  | NTP DATE: | 0
FINANCIAL PROJECT # : | 0 |  |  |  | DATABASE # : | 0
PROJECT LIMITS: | 0
PERCENTAGE COMPLETE
WORK ITEMS | CONTRACT HOURS | TOTAL HOURS USED | PERCENT OF TASK RIGHT OF WAY MAP | NOTES:
COVER SHEET | 2 | 1 | 50%
KEY SHEET(S) | 2 | 1 | 50%
DETAIL SHEET(S) | 2 | 1 | 50%
TABLE OF OWNERSHIPS SHEET(S) | 2 | 1 | 50%
LEGAL DESCRIPITIONS | 2 | 1 | 50%
QA/QC | 2 | 1 | 50%
TOTAL | 12 | 6 | TOTAL RIGHT OF WAY MAP PERCENT: |  |  | 50%
I APPROVE / DISAPPROVE THE PERCENTAGE OF WORK COMPLETED.
SIGNATURE: |  |  |  | DATE:
District Right of Way Surveyor
Rev. 9-14
27