## Index
Department of Management Services, Division of State Technology
PROJECT RISK & COMPLEXITY ASSESSMENT TOOL
Risk & Complexity Assessment Model for State Information Technology Projects
Purpose: In order to determine the level of risk associated with the undertaking of a project effort, this worksheet presents a series of risk and complexity questions. Each question has a weighted value. Once the assessment is complete, the project is classified into one of four project categories from low risk/low complexity to high risk/high complexity. Based on the project’s risk and complexity categorization, project management best practice risk mitigation strategies become required. Mitigation strategies include the mandatory creation of certain project management artifacts, status reporting, governance oversight, scope/schedule/budget accuracy thresholds, and independent verification and validation (IV&V) support.
Form Title: DMS Project Risk & Complexity Assessment Tool
Form Number: DMS-F-0505A
Effective Date: 07/15 (incorporated into Rule 60GG-1, F.A.C.)
Scope: All state government information technology work efforts (projects) conducted for the State of Florida.
"Project" as defined in Florida Statues means an endeavor that has a defined start and end point; is undertaken to create or modify a unique product, service, or result; and has specific objectives that, when attained, signify completion.
Authority: Section 282.0051, Florida Statutes
INDEX
Tab |  | Description
Summary & Instructions |  | Instructions for completing assessments. Activates and summarizes assessment scoring.
Risk - Pre-Select |  | Questions and scoring criteria to determine Risk score for the Pre-Select Phase.
Complexity - Pre-Select |  | Questions and scoring criteria to determine Complexity score for the Pre-Select Phase.
Risk - Initiation |  | Questions and scoring criteria to determine Risk score for the Initiation Phase.
Complexity - Initiation |  | Questions and scoring criteria to determine Complexity score for the Initiation Phase.
Risk - Planning |  | Questions and scoring criteria to determine Risk score for the Planning Phase.
Complexity - Planning |  | Questions and scoring criteria to determine Complexity score for the Planning Phase.
Risk - Execution |  | Questions and scoring criteria to determine Risk score for the Execution Phase.
Project Category Lookup |  | Project Risk & Complexity Category Lookup table, based on Risk & Complexity scores.
REVISION HISTORY
Version | Date | Initials & Comments
1 | 2019-07-10 | AMN- Initial version of DMS Risk and Complexity Assessment
1.1 | 2019-07-15 | AMN- Updates after internal review

## Process Flow (hidden)
RISK & COMPLEXITY ASSESSMENT PROCESS FLOW
Legend:
AST - Agency for State Technology
PM - Project Manager

## Changes from 4-22 Version (hidden)
Rule Chapter 74-1, F.A.C
Changes to AST Risk & Complexity Assessment Workbook (Posted to AST Website on 4/22/2015)
Question No.
Changes
Seq. | Tab Name | From | To | Description of Change
1 | Risk Pre-Charter | 2) | NA | Deleted Question #2.
2 | Risk Pre-Charter | 3) | 2) | Renumbered question.
3 | Risk Pre-Charter | 4) | NA | Deleted Question #4.
4 | Risk Pre-Charter | 4) | 3) | Renumbered question.
5 | Risk Pre-Charter | 6) | 4) | Renumbered question.
6 | Risk Pre-Charter |  |  | Revised question to address projects executed within the past two years (changed from five years).
7 | Risk Pre-Charter |  |  | Changed scoring weight from 5 to 10 points.
8 | Risk Pre-Charter | NA | 5) | Added new Question #5. Scoring weight: 15 points.
9 | Risk Pre-Charter | 7) | 6) | Renumbered question.
10 | Risk Pre-Charter |  |  | Changed scoring weight from 5 to 10 points.
11 | Risk Pre-Charter | 8) | 7) | Renumbered question.
12 | Risk Pre-Charter |  |  | Changed scoring weight from 5 to 10 points.
13 | Risk Pre-Charter | 9) | 8) | Renumbered question.
14 | Risk Pre-Charter |  |  | Changed scoring weight from 10 to 5 points.
15 | Risk Pre-Charter | 10) | 9) | Renumbered question.
16 | Risk Pre-Charter |  |  | Changed scoring weight from 10 to 5 points.
17 | Risk Pre-Charter | 11) | 10) | Renumbered question.
18 | Risk Pre-Charter |  |  | Changed scoring weight from 10 to 5 points.
19 | Risk Pre-Charter | 12) | 11) | Renumbered question.
20 | Risk Pre-Charter |  |  | Changed scoring weight from 10 to 5 points.
21 | Risk Pre-Charter | 13) | 12) | Renumbered question.
22 | Risk Pre-Charter |  |  | Added answer “c” to previous Yes/No answer set.
23 | Risk Pre-Charter |  |  | Changed scoring weight from 10 to 15 points.
24 | Complexity Pre-Charter | 2) | NA | Renumbered question.
25 | Complexity Pre-Charter |  |  | Revised question wording for clarity.
26 | Complexity Pre-Charter |  |  | Changed answers from Yes/No to current answer set.
27 | Complexity Pre-Charter |  |  | Changed scoring weight from 10 to 15 points.
28 | Complexity Pre-Charter | 3) | NA | Deleted Question #3.
29 | Complexity Pre-Charter | 4) | 3) | Renumbered question.
30 | Complexity Pre-Charter |  |  | Changed scoring weight from 15 to 5 points.
31 | Complexity Pre-Charter | 5) | 4) | Renumbered question.
32 | Complexity Pre-Charter | 6) | 5) | Renumbered question.
33 | Complexity Pre-Charter | 7) | 6) | Renumbered question.
34 | Complexity Pre-Charter |  |  | Changed scoring weight from 5 to 15 points.
35 | Complexity Pre-Charter | 8) | 7) | Renumbered question.
36 | Complexity Pre-Charter |  |  | Changed scoring weight from 10 to 15 points.
37 | Complexity Pre-Charter | 9) | 8) | Renumbered question.
38 | Complexity Pre-Charter | 10) | 9) | Renumbered question.
39 | Complexity Pre-Charter | 11) | 10) | Renumbered question.
40 | Complexity Pre-Charter | 12) | 11) | Renumbered question.
41 | Complexity Pre-Charter | 13) | 12) | Renumbered question.
42 | Complexity Pre-Charter | 14) | 13) | Renumbered question.
43 | Risk Initiation Gate | 3) | NA | Deleted Question #3.
44 | Risk Initiation Gate | 4) | 3) | Renumbered question.
45 | Risk Initiation Gate | 5) | 4) | Renumbered question.
46 | Risk Initiation Gate | 6) | 5) | Renumbered question.
47 | Risk Initiation Gate | 7) | 6) | Renumbered question.
48 | Risk Initiation Gate | 8) | 7) | Renumbered question.
49 | Risk Initiation Gate |  |  | Changed previous answer set to Yes/No answer set.
50 | Risk Initiation Gate |  |  | Changed scoring weight from 5 to 20 points.
51 | Risk Initiation Gate | 9) | NA | Deleted Question #9.
52 | Risk Initiation Gate | 10) | 8) | Renumbered question.
53 | Risk Initiation Gate |  |  | Changed scoring weight from 15 to 5 points.
54 | Risk Initiation Gate | 11) | 9) | Renumbered question.
55 | Risk Initiation Gate | 12) | 10) | Renumbered question.
56 | Risk Initiation Gate | 13) | 11) | Renumbered question.
57 | Risk Initiation Gate | 14) | 12) | Renumbered question.
58 | Risk Initiation Gate |  |  | Changed scoring weight from 15 to 10 points.
59 | Risk Initiation Gate | 15) | 13) | Renumbered question.
60 | Risk Initiation Gate |  |  | Changed scoring weight from 15 to 20 points.
61 | Risk Initiation Gate | 16) | 14) | Renumbered question.
62 | Risk Initiation Gate |  |  | Changed scoring weight from 5 to 10 points.
63 | Risk Initiation Gate | 17) | 15) | Renumbered question.
64 | Risk Initiation Gate | 18) | 16) | Renumbered question.
65 | Risk Initiation Gate | 19) | 17) | Renumbered question.
66 | Risk Initiation Gate | 20) | 18) | Renumbered question.
67 | Risk Initiation Gate | 21) | 19) | Renumbered question.
68 | Risk Initiation Gate | 22) | 20) | Renumbered question.
69 | Risk Initiation Gate | 23) | 21) | Renumbered question.
70 | Complexity Initiation Gate | 1) | NA | Changed scoring weight from 15 to 20 points.
71 | Complexity Initiation Gate | 2) | NA | Changed scoring weight from 10 to 20 points.
72 | Complexity Initiation Gate | 3) a) | NA | Changed scoring weight from 4 to 5 points.
73 | Complexity Initiation Gate | 3) b) | NA | Changed scoring weight from 4 to 5 points.
74 | Complexity Initiation Gate | 4) | NA | No change.
75 | Complexity Initiation Gate | 5) | NA | Changed scoring weight from 25 to 20 points.
76 | Complexity Initiation Gate | 6) | NA | No change.
77 | Complexity Initiation Gate | 7) | NA | No change.
78 | Complexity Initiation Gate | 8) | NA | No change.
79 | Complexity Initiation Gate | 9) | NA | No change.
80 | Complexity Initiation Gate | 10) | NA | No change.
81 | Complexity Initiation Gate | 11) | NA | No change.
82 | Complexity Initiation Gate | 12) a) | NA | Deleted Question #12a.
83 | Complexity Initiation Gate | 12) b) | 12) a) | Renumbered question.
84 | Complexity Initiation Gate |  |  | Changed scoring weight from 6 to 10 points.
85 | Complexity Initiation Gate | 12) c) | 12) b) | Renumbered question.
86 | Complexity Initiation Gate |  |  | Changed scoring weight from 6 to 10 points.
87 | Complexity Initiation Gate | 13) | NA | No change.
88 | Complexity Initiation Gate | 14) | NA | Changed scoring weight from 10 to 15 points.
89 | Complexity Initiation Gate | 15) | NA | Deleted Question #15.
90 | Complexity Initiation Gate | 16) | 15) | Renumbered question.
91 | Risk Planning Gate | 1) a) | NA | Changed scoring weight from 10 to 5 points.
92 | Risk Planning Gate | 1) b) | NA | Changed scoring weight from 8 to 5 points.
93 | Risk Planning Gate | 2) | NA | Edited question for clarity.
94 | Risk Planning Gate | 3) | NA | Edited question for clarity.
95 | Risk Planning Gate | 4) a) | NA | Changed scoring weight from 20 to 10 points.
96 | Risk Planning Gate | 4) b) | NA | Changed scoring weight from 20 to 10 points.
97 | Risk Planning Gate | 5) | NA | Changed previous answer set to Yes/No answer set.
98 | Risk Planning Gate |  |  | Changed scoring weight from 6 to 9 points.
99 | Risk Planning Gate | 6) | NA | Changed previous answer set to Yes/No answer set.
100 | Risk Planning Gate |  |  | Changed scoring weight from 15 to 10 points.
101 | Risk Planning Gate | 7) | NA | Deleted Question #7.
102 | Risk Planning Gate | 8) | 7) | Renumbered question.
103 | Risk Planning Gate |  |  | Edited question for clarity.
104 | Risk Planning Gate |  |  | Changed scoring weight from 6 to 10 points.
105 | Risk Planning Gate | 9) | NA | Deleted Question #9.
106 | Risk Planning Gate | 10) | NA | Deleted Question #10.
107 | Risk Planning Gate | 11) | 8) | Renumbered question.
108 | Risk Planning Gate |  |  | Added answer “c” to previous answer set.
109 | Risk Planning Gate | 12) | 9) | Renumbered question.
110 | Risk Planning Gate |  |  | Changed previous answer set to Yes/No answer set.
111 | Risk Planning Gate | 13) | 10) | Renumbered question.
112 | Risk Planning Gate | 14) a) | 11) a) | Renumbered question.
113 | Risk Planning Gate |  |  | Changed scoring weight from 15 to 10 points.
114 | Risk Planning Gate | 14) b) | 11) b) | Renumbered question.
115 | Risk Planning Gate |  |  | Edited question for clarity.
116 | Risk Planning Gate |  |  | Changed scoring weight from 6 to 5 points.
117 | Risk Planning Gate | 15) | NA | Deleted Question #15.
118 | Risk Planning Gate | NA | 12) | Added new Question #12. Scoring weight: 10 points.
119 | Risk Planning Gate | NA | 13) | Added new Question #13. Scoring weight: 10 points.
120 | Risk Planning Gate | NA | 14) | Added new Question #14. Scoring weight: 10 points.
121 | Risk Planning Gate | NA | 15) | Added new Question #15. Scoring weight: 10 points.
122 | Risk Planning Gate | NA | 16) | Added new Question #16. Scoring weight: 10 points.
123 | Risk Planning Gate | NA | 17) | Added new Question #17. Scoring weight: 10 points.
124 | Risk Planning Gate | NA | 18) | Added new Question #18. Scoring weight: 10 points.
125 | Complexity Planning Gate | 1) a) | NA | No change.
126 | Complexity Planning Gate | 1) b) | NA | No change.
127 | Complexity Planning Gate | 1) c) | NA | No change.
128 | Complexity Planning Gate | 2) | NA | Edited question for clarity.
129 | Complexity Planning Gate |  |  | Changed scoring weight from 10 to 5 points.
130 | Complexity Planning Gate | 3) | NA | Added answer “c” to the answer set.
131 | Complexity Planning Gate | 4) | NA | Changed previous answer set to Yes/No answer set.
132 | Complexity Planning Gate |  |  | Changed scoring weight from 10 to 5 points.
133 | Complexity Planning Gate | 5) | NA | Edited d. answer.
134 | Complexity Planning Gate |  |  | Added PMBOK® definition of Work Package.
135 | Complexity Planning Gate |  |  | Changed scoring weight from 7 to 15 points.
136 | Complexity Planning Gate | 6) | NA | Changed answers from Yes/No to current answer set.
137 | Complexity Planning Gate | 7) | NA | Deleted Question #7.
138 | Complexity Planning Gate | 8) | 7) | Renumbered question.
139 | Complexity Planning Gate |  |  | Edited question: replaced “Initiation” with “Planning”.
140 | Complexity Planning Gate |  |  | Changed previous answer set to Yes/No answer set.
141 | Complexity Planning Gate | 9) | 8) | Renumbered question.
142 | Complexity Planning Gate |  |  | Changed answers from Yes/No to current answer set.
143 | Complexity Planning Gate |  |  | Changed scoring weight from 10 to 15 points.
144 | Complexity Planning Gate | 10) | 9) | Renumbered question.
145 | Complexity Planning Gate |  |  | Changed answers from Yes/No to current answer set.
146 | Complexity Planning Gate |  |  | Changed scoring weight from 10 to 15 points.
147 | Complexity Planning Gate | 11) | 10) | Renumbered question.
148 | Complexity Planning Gate |  |  | Changed scoring weight from 10 to 15 points.
149 | Complexity Planning Gate | 12) | 11) | Renumbered question.
150 | Complexity Planning Gate |  |  | Changed scoring weight from 20 to 10 points.
151 | Complexity Planning Gate | 13) | 12) | Renumbered question.
152 | Complexity Planning Gate |  |  | Edited question for clarity.
153 | Complexity Planning Gate |  |  | Changed scoring weight from 20 to 15 points.
154 | Complexity Planning Gate | 14) | NA | No change.
155 | Complexity Planning Gate | 15) | NA | Edited question. Added clarification comments.
156 | Complexity Planning Gate |  |  | Changed scoring weight from 8 to 15 points.
157 | Risk Event-Driven | 1) | NA | Changed scoring weight from 10 to 15 points.
158 | Risk Event-Driven | 2) | NA | No change.
159 | Risk Event-Driven | 3) | NA | No change.
160 | Risk Event-Driven | 4) | NA | No change.
161 | Risk Event-Driven | 5) | NA | Edited question: added the word “scope.”
162 | Risk Event-Driven | 6) | NA | No change.
163 | Risk Event-Driven | 7) | NA | No change.
164 | Risk Event-Driven | 8) a) | NA | No change.
165 | Risk Event-Driven | 8) b) | NA | No change.
166 | Risk Event-Driven | 8) c) | NA | No change.

## Summary
PROJECT RISK & COMPLEXITY ASSESSMENT SUMMARY | [5 empty] | Form Title: DMS Project Risk & Complexity Assessment Tool
AGENCY: |  | <Department Name> |  |  |  | Form Number: DMS-F-0505A
PROJECT: |  | <Project Name> |  |  |  | Effective Date: 07/15 (incorporated into Rule 60GG-1, F.A.C.)
Activate Assessment? |  |  |  |  | PROJECT CATEGORY
No | 1) PRE-CHARTER PHASE
p | Pre-Charter Risk Score |  | Not Scored
Select Yes / No | Pre-Charter Complexity Score |  | Not Scored
| PROJECT CATEGORY |  |  | Not Scored
Activate Assessment? |  |  |  |  | PROJECT CATEGORY
No | 2) INITIATION PHASE
p | Initiation Risk Score |  | Not Scored
Select Yes / No | Initiation Complexity Score |  | Not Scored
| PROJECT CATEGORY |  |  | Not Scored
Activate Assessment? |  |  |  |  | PROJECT CATEGORY
No | 3) PLANNING PHASE
p | Planning Risk Score |  | Not Scored
Select Yes / No | Planning Complexity Score |  | Not Scored
Used for Event-Driven Complexity score also.
| PROJECT CATEGORY |  |  | Not Scored
Activate Assessment? |  |  |  |  | PROJECT CATEGORY
No | 4) EVENT-DRIVEN ASSESSMENT
p | Event-Driven Risk Score |  | Not Scored
Select Yes / No | Event-Driven Complexity Score |  | Not Scored
Carried forward from Planning Complexity score.
| PROJECT CATEGORY |  |  | Not Scored
OVERALL PROJECT RISK & COMPLEXITY ASSESSMENT |  |  |  |  | OVERALL PROJECT CATEGORY
| Overall Risk Score |  | Not Scored
| Overall Complexity Score |  | Not Scored
| PROJECT CATEGORY |  |  | Not Scored
SCORING EXPLANATION
These assessments align projects by risk and complexity levels into one (1) of four (4) Risk and Complexity (R&C) Categories, which determine the amount of project management control required. The diagram below indicates the distribution of risk and complexity levels into the R&C Category:
• Category 4 represents High Risk and High Complexity projects.
• Category 3 represents High Risk and Medium Complexity projects, High Risk and Low Complexity projects, or Medium Risk and High Complexity projects.
• Category 2 represents Medium Risk and Medium Complexity projects, Medium Risk and Low Complexity projects, or Low Risk and High Complexity projects.
• Category 1 represents Low Risk and Medium Complexity projects or Low Risk and Low Complexity projects.
Each assessment is scored in range from 100 to 500, with 100 being the lowest possible score (corresponding to the lowest possible risk or complexity score, and 500 being the highest possible score (corresponding to the highest possible risk or complexity score). Scores for each assessment are rolled up cumulatively into an overall Risk & Complexity score, which in turn corresponds to the Project Risk & Complexity Category as indicated in the table above.
1) Activate an Assessment:
• Select "Yes" or "No" from the "Activate Assessment" drop-down list.
• "Yes" activates the assessment.
• "No" deactivates the assessment.
NOTES:
• Make sure that the current assessment is activated and assessments for all previous project phases are activated. Start with the Pre-Charter Assessment and proceed toward the current project phase. Do not activate assessments for future project phases.
• Questions in activated assessments that are left blank will default to their highest possible score, which will count toward the overall (cumulative) score and corresponding project category.
• Questions in deactivated assessments will not be scored and will not count toward the overall (cumulative) score and corresponding project category.
INSTRUCTIONS
2) Once an assessment is activated, answer its questions by selecting one response for each question from the drop-down list in the box located directly to the right of each question.
NOTES:
• Do not leave any questions blank. Questions left blank will default to their highest possible score.
• If a question is not applicable, select "NA" from the drop-down list. The "NA" response option is available for all questions.
3) Assessment scores and their corresponding Project Risk & Complexity Category are automatically calculated and tabulated in the "Summary" tab.
NOTES:
• Upon proceeding to the next project phase, or when performing an Event-Driven Risk & Complexity Assessment, make sure that the assessments from all previous project phases are activated.

## Risk_Pre_Charter
IT Risk Questions - Pre-Charter Phase | Comments |  | Proportional Weight | Risk Rank | SELECT ANSWER | Weighted Score
The Pre-Charter Risk Assessment is performed at the beginning of the Initiation Phase of the project. During this assessment, the Agency will review priorities and business need, assess the project and analyze factors that can impact project success. The resulting project category will establish the project management control requirements to be applied during the project Initiation phase. Select one response for each question listed below. Do not leave any questions blank. If a question is not applicable, select "NA" from the drop-down list. | Form Title: DMS Project Risk & Complexity Assessment Tool Form Number: DMS-F-0505A Effective Date: 07/15 (incorporated into Rule 60GG-1, F.A.C.)
1) What is the estimated total project cost? |  | 35 | 35
a. > $5,000,000 |  |  |  | 3.8462 | E | 26.9231
b. $1,000,001 to $5,000,000 |  |  |  | 3.0769 |  | Low
c. $500,001 to $1,000,000 |  |  |  | 2.3077
d. $250,000 to $500,000 |  |  |  | 1.5385
e. < $250,000 |  |  |  | 0.76923
2) How was the basis of estimate determined? |  | 5 | 5
a. Other methodology |  |  |  | 3.8462 | D | 3.8462
b. Consulting professional or agency judgment |  |  |  | 3.0769 |  | Low
c. Comparative (analogous) project evaluation |  |  |  | 1.5385
d. Based on the sum of estimates of each WBS element (top down or bottom up) |  |  |  | 0.76923
3) How important is the project to meeting the agency's Strategic Goals and Objectives as set forth in the agency's Long Range Program Plan (LRPP)? |  | 5 | 5
a. The project is critical to meeting Agency's Strategic Goals and Objectives. |  |  |  | 3.8462 | C | 3.8462
b. The project is important to meeting Agency's Strategic Goals and Objectives. |  |  |  | 2.3077 |  | Low
c. The project has little or no direct impact on Agency's Strategic Goals and Objectives. |  |  |  | 0.76923
4) Has the agency successfully executed projects with similar scope, schedule, and/or cost within the past two years? |  | 10 | 10
a. No |  |  |  | 3.8462 | B | 7.6923
b. Yes |  |  |  | 0.76923 |  | Low
5) What is the level of project management maturity within your organization? |  | 15 | 15
a. Not mature--mostly ad hoc project management processes |  |  |  | 3.8462 | D | 11.5385
b. Somewhat mature--an even mix of ad hoc and established, best-practice project management processes |  |  |  | 3.0769 |  | Low
c. Moderately mature--using established, best-practice project management processes, but not always consistently |  |  |  | 1.5385
d. Mature--using established, best-practice project management processes consistently |  |  |  | 0.76923
6) Does the project impact mission-critical supporting business processes? |  | 10 | 10
a. Yes |  |  |  | 3.8462 | B | 7.6923
b. No |  |  |  | 0.76923 |  | Low
7) What is the potential organizational impact to State agencies with proceeding with this project? |  | 10 | 10
a. Requires re-engineering of organizations and processes affecting multiple agencies |  |  |  | 3.8462 | C | 7.6923
b. Requires re-engineering of organizations and processes within our agency only |  |  |  | 2.3077 |  | Low
c. Requires no re-engineering of organizations and processes |  |  |  | 0.76923
8) How critical is the project to meeting externally generated mandates (Executive, Legislative, or Judicial)? |  | 10 | 10
a. The project is mandatory for accomplishment of external mandates. |  |  |  | 3.8462 | B | 7.6923
b. The project has little or no direct impact on accomplishment of external mandates. |  |  |  | 0.76923 |  | Low
9) What is the level of certainty in the estimated scope of the project? |  | 5 | 5
a. Low – Scope could change (increase or decrease). |  |  |  | 3.8462 | B | 3.8462
b. High – Scope is clearly fixed and will not change. |  |  |  | 0.76923 |  | Low
10) What is the level of certainty in the estimated cost of the project? |  | 5 | 5
a. Low – Cost estimate is not supported by experience or comparative analysis. |  |  |  | 3.8462 | C | 3.8462
b. Medium – Cost estimate is based on a comparative analysis of multiple similar projects. |  |  |  | 2.3077 |  | Low
c. High – Cost estimate based on hands-on experience and similar projects under similar conditions. |  |  |  | 0.76923
11) What is the level of certainty in the estimated duration of the project? |  | 5 | 5
a. Low – Duration estimate is not supported by experience or comparative analysis. |  |  |  | 3.8462 | C | 3.8462
b. Medium – Duration estimate is based on a comparative analysis of multiple similar projects. |  |  |  | 2.3077 |  | Low
c. High – Duration estimate based on hands-on experience and similar projects under similar conditions. |  |  |  | 0.76923
12) If the project plans to use GAA funding, do project funds cross fiscal year budgets? |  | 15 | 15
a. Yes |  |  |  | 3.8462 | C | 11.5385
b. No |  |  |  | 2.3077 |  | Low
c. This project does not plan to use GAA funding |  |  |  | 0.76923
| Sum of Weights | 130 |  |  | Score | 100
|  |  | 130 |  | Not Scored | Not Scored | Score
[7 empty] | VALUES | DESC. | POSITION
|  |  | 130 |  |  |  | 100 | Lower Limit
[7 empty] | 0 | Input Value | 4
[7 empty] | 500 | Upper Limit
3.8462
0.76923
High Risk: 368 - 500
Medium Risk: 234 - 367
Low Risk: 100 - 233
RED FLAG SETTING
LOW RISK
HIGH RISK
MEDIUM RISK

## Complexity_Pre_Charter
IT Complexity Questions - Pre-Charter Phase | Comments |  | Proportional Weight | Complexity Rank | SELECT ANSWER | Weighted Score
The Pre-Charter Complexity Assessment is performed at the beginning of the Initiation Phase of the project. Complexity is a risk modifier in that it can exacerbate or mitigate the impact of Risk on the successful completion of the project. The resulting project category will establish the project management control requirements to be applied during the project Initiation phase. Select one response for each question listed below. Do not leave any questions blank. If a question is not applicable, select "NA" from the drop-down list. | Form Title: DMS Project Risk & Complexity Assessment Tool Form Number: DMS-F-0505A Effective Date: 07/15 (incorporated into Rule 60GG-1, F.A.C.)
1) Are agency business processes directly impacted by the project? |  | 10 | 10
Business processes that are “directly impacted” by the project are specific business processes that are measurably effected by the project. Some projects, such as upgrading personal computers, may not have any business processes directly impacted by the project, only those that are indirectly impacted.
a. Yes |  |  |  | 2.7027 | B | 5.4054
b. No |  |  |  | 0.54054 |  | Low
2) Are there interrelated projects that are dependent upon this project, or upon which this project depends (either for inputs, outputs, or resources)? |  | 15 | 15
a. This project is dependent on one or more other projects, AND one or more other projects are dependent on this project. |  |  |  | 2.7027 | D | 8.1081
b. This project is dependent on one or more other projects. |  |  |  | 2.1622 |  | Low
c. One or more other projects are dependent on this project. |  |  |  | 1.0811
d. This project has no interdependencies. |  |  |  | 0.54054
3) Are the organizational structure and functional responsibilities clearly defined for this project? |  | 5 | 5
a. Organizational structure and functional responsibilities are not defined. |  |  |  | 2.7027 | B | 2.7027
b. Organizational structure and functional responsibilities are defined. |  |  |  | 0.54054 |  | Low
4) What role does the agency's IT department play in this project? |  | 10 | 10
• Participates in project governance • Provides project management • Ensures clear scope and requirements definition • Provides subject matter expertise in technical areas
a. None of the above, or only one of the above |  |  |  | 2.7027 | D | 5.4054
b. Two of the above |  |  |  | 2.1622 |  | Low
c. Three of the above |  |  |  | 1.0811
d. All of the above |  |  |  | 0.54054
5) Will this project drive a need for organizational change management? |  | 15 | 15
a. Yes |  |  |  | 2.7027 | B | 8.1081
b. No |  |  |  | 0.54054 |  | Low
6) Who are the primary customers for the potential solution? |  | 15 | 15
a. The public |  |  |  | 2.7027 | C | 8.1081
b. Employees at multiple agencies |  |  |  | 1.6216 |  | Low
c. Employees at our agency only |  |  |  | 0.54054
7) Are multiple project procurements required? |  | 15 | 15
a. Yes |  |  |  | 2.7027 | B | 8.1081
b. No |  |  |  | 0.54054 |  | Low
8) How much of the Agency's business is being reengineered as part of the project? |  | 20 | 20
a. > 75% of Agency business processes are being reengineered. |  |  |  | 2.7027 | E | 10.8108
b. 51 - 75% of Agency business processes are being reengineered. |  |  |  | 2.1622 |  | Low
c. 26 - 50% of Agency business processes are being reengineered. |  |  |  | 1.6216
d. 0 - 25% of Agency business processes are being reengineered. |  |  |  | 1.0811
e. No business process reengineering |  |  |  | 0.54054
9) Are Subject Matter Experts available to participate in the definition of project requirements and scope? |  | 20 | 20
a. No |  |  |  | 2.7027 | B | 10.8108
b. Yes |  |  |  | 0.54054 |  | Low
10) Are the operating procedures and business process diagrams that define and illustrate the work currently accomplished (by the effort under consideration) accurate and up-to-date? |  | 15 | 15
a. Procedures and process flow diagrams do not exist. |  |  |  | 2.7027 | C | 8.1081
b. Procedures and process flow diagrams are partially documented. |  |  |  | 1.6216 |  | Low
c. All procedures and process flow diagrams are up to date and validated. |  |  |  | 0.54054
11) Is documentation for the existing system (as it relates to this project) kept up-to-date with system design documents, specifications, and Operations & Maintenance guides? |  | 15 | 15
a. No |  |  |  | 2.7027 | B | 8.1081
b. Yes |  |  |  | 0.54054 |  | Low
12) For the existing system (as it relates to this project), is trained staff available to interpret system behavior? |  | 15 | 15
a. No |  |  |  | 2.7027 | B | 8.1081
b. Yes |  |  |  | 0.54054 |  | Low
13) Will the project involve protected data (Employee, Recipient, etc.)? |  | 15 | 15
a. Yes |  |  |  | 2.7027 | B | 8.1081
b. No |  |  |  | 0.54054 |  | Low
| Sum of Weights | 185 |  |  | Score | 100
|  |  | 185 |  | Not Scored | Not Scored | Score
[7 empty] | VALUES | DESC. | POSITION
|  |  | 185 |  |  |  | 100 | Lower Limit
[7 empty] | 0 | Input Value | 4
[7 empty] | 500 | Upper Limit
2.7027
0.54054
High Complexity: 368 - 500
Medium Complexity: 234 - 367
| Low Complexity: 100 - 233 | [5 empty] | Pre-Charter Phase Project Category
[7 empty] | VALUES | DESC. | POSITION
| PRE-CHARTER PHASE CATEGORY |  |  |  | Not Scored | Not Scored | 1 | Lower Limit
[7 empty] | 0 | Input Value | 4
| NOTIFY GOVERNANCE? |  |  |  | NOTIFY | NOTIFY | 4 | Upper Limit
LOW COMPLEXITY
HIGH COMPLEXITY
MEDIUM COMPLEXITY

## Risk_Initiation_Gate
IT Risk Questions - Project Initiation | Comments |  | Proportional Weight | Risk Rank | SELECT ANSWER | Weighted Score
The Initiation Phase Gate Risk Assessment is performed at the end of the Initiation Phase following completion of initial project documentation. During this assessment, the Agency will review Initiation documents and the Pre-Charter R&C Assessment. This assessment will confirm or adjust the project's risk & complexity level and the resulting project category, examine the effectiveness of Initiation phase activities, and establish requirements for the project Planning Phase. Select one response for each question listed below. Do not leave any questions blank. If a question is not applicable, select "NA" from the drop-down list. | Form Title: DMS Project Risk & Complexity Assessment Tool Form Number: DMS-F-0505A Effective Date: 07/15 (incorporated into Rule 60GG-1, F.A.C.)
1) What level of confidence does the Project Management Team have in the estimated cost of the project? |  | 25 | 25
a. Confidence in estimated project expenditures is less than or equal to 85%. |  |  |  | 1.5152 | C | 7.5758
b. Confidence in estimated project expenditures is greater than 85% and less than or equal to 95%. |  |  |  | 0.90909 |  | Low
c. Confidence in estimated project expenditures is greater than 95% and less than or equal to 100%. |  |  |  | 0.30303
2) Is this project critical to support the primary functions for which the requesting agency is responsible? |  | 20 | 20
a. Directly involves the effectiveness and efficiency of the agency's primary functions. |  |  |  | 1.5152 | C | 6.0606
b. Contributes to enabling the agency's primary functions. |  |  |  | 0.90909 |  | Low
c. Indirectly impacts, or has minimal impact, to the agency's primary functions. |  |  |  | 0.30303
3) Is this project dependent on the deliverable(s) from another project, organization, or agency? |  | 15 | 15
a. A project deliverable from another project, organization, or Agency is required. |  |  |  | 1.5152 | D | 4.5455
b. The project will utilize other project deliverables. |  |  |  | 1.2121 |  | Low
c. Other deliverables will enhance the project. |  |  |  | 0.60606
d. No other deliverables are required. |  |  |  | 0.30303
4) Is the project dependent on limited resources controlled by an external entity? |  | 15 | 15
a. Project requires external resources. |  |  |  | 1.5152 | B | 4.5455
b. Project requires no external resources. |  |  |  | 0.30303 |  | Low
5) Does the project sponsor have direct authority over all the resources needed for the project (including funding, equipment, facilities, and human resources)? |  | 15 | 15
a. The project sponsor has authority over none of the resources needed for the project. |  |  |  | 1.5152 | D | 4.5455
b. The project sponsor has authority over some of the resources needed for the project. |  |  |  | 1.2121 |  | Low
c. The project sponsor has authority over most of the resources needed for the project. |  |  |  | 0.60606
d. The project sponsor has authority over all of the resources needed for the project. |  |  |  | 0.30303
6) How will failure of the project impact the stakeholders? |  | 15 | 15
a. Impact of project failure on stakeholders is high. |  |  |  | 1.5152 | C | 4.5455
b. Impact of project failure on stakeholders is between high and moderate. |  |  |  | 0.90909 |  | Low
c. Impact of project failure on stakeholders is between moderate and minimal. |  |  |  | 0.30303
7) Does the project impact the state at an enterprise level? |  | 20 | 20
a. Yes |  |  |  | 1.5152 | B | 6.0606
b. No |  |  |  | 0.30303 |  | Low
8) What is the level of assurance that stakeholders will deliver resources as promised? |  | 5 | 5
a. Minimal - there is no history that stakeholders have delivered promised resources in the past. |  |  |  | 1.5152 | B | 1.5152
b. High - stakeholders have a proven history of delivering all promised resources on time. |  |  |  | 0.30303 |  | Low
9) Are there any projected changes of critical or key stakeholders over the life of the project? |  | 5 | 5
"Critical Stakeholders” are those essential stakeholders that must be involved with the project in order to achieve success, e.g., the project sponsor. “Key Stakeholders” are those vital stakeholders that need to be involved with the project, but their turnover is not directly tied to project success, e.g., a member of an executive steering committee.
a. Yes, change of critical stakeholders is anticipated. |  |  |  | 1.5152 | C | 1.5152
b. Yes, change of key stakeholders is anticipated. |  |  |  | 0.90909 |  | Low
c. No |  |  |  | 0.30303
10) Is the agency project manager assigned to this project certified by PMI® (PgMP®, PMP®, CAPM®, Agile Certified Practitioner®, etc.)? |  | 10 | 10
a. No |  |  |  | 1.5152 | B | 3.0303
b. Yes |  |  |  | 0.30303 |  | Low
11) Does the agency have the necessary knowledge, skills, and abilities to staff the project team with in-house resources? |  | 10 | 10
a. No |  |  |  | 1.5152 | C | 3.0303
b. Some, but not all [reword] |  |  |  | 0.90909 |  | Low
c. Yes |  |  |  | 0.30303
12) Do business users and subject matter experts have sufficient skills and experience given the size and complexity of the project? |  | 10 | 10
a. Business users and subject matter experts have never attempted a project of this size and complexity. |  |  |  | 1.5152 | C | 3.0303
b. Business users and subject matter experts have skills and experience from previous projects, but not from projects of similar size and complexity. |  |  |  | 0.90909 |  | Low
c. Business users and subject matter experts have extensive skills and experience from a previous project of similar size and complexity. |  |  |  | 0.30303
13) Does the assigned project manager have the specific experience (proven ability) to successfully execute a project of this scope and complexity? |  | 20 | 20
a. PM has never participated in a project of this scope and complexity. |  |  |  | 1.5152 | C | 6.0606
b. PM managed a similar project but with smaller scope and complexity. |  |  |  | 0.90909 |  | Low
c. PM has managed a project of this scope and complexity. |  |  |  | 0.30303
14) What percent of the project team has experience with the selected development methodology or selected implementation approach for the project? |  | 10 | 10
a. < 50 % |  |  |  | 1.5152 | C | 3.0303
b. 50 – 75 % |  |  |  | 0.90909 |  | Low
c. 76 – 100 % |  |  |  | 0.30303
15) What percent of the agency's IT leadership has experience with the development methodology or selected implementation approach for the project? |  | 5 | 5
a. < 50 % |  |  |  | 1.5152 | C | 1.5152
b. 50 – 75 % |  |  |  | 0.90909 |  | Low
c. 76 – 100 % |  |  |  | 0.30303
16) How clearly defined and understood are the goals and objectives of this project by a majority of the project team and stakeholders? |  | 25 | 25
a. The goals and objectives of this project are vague and open to interpretation. |  |  |  | 1.5152 | B | 7.5758
b. The goals and objectives of this project are well defined and understood. |  |  |  | 0.30303 |  | Low
17) Is the boundary between what is in the project scope and what is not in the project scope clearly documented? |  | 25 | 25
a. No |  |  |  | 1.5152 | B | 7.5758
b. Yes |  |  |  | 0.30303 |  | Low
18) Has the project charter been reviewed and approved by all key stakeholders, including the project sponsor? |  | 15 | 15
a. No |  |  |  | 1.5152 | B | 4.5455
b. Yes |  |  |  | 0.30303 |  | Low
19) How was the estimated completion date for this project determined? |  | 15 | 15
a. Completion date has not yet been determined or estimated. |  |  |  | 1.5152 | C | 4.5455
b. Completion date is driven by the need to meet a defined time constraint. |  |  |  | 0.90909 |  | Low
c. There is no mandated time constraint. The schedule will be developed based on scope of work and resource availability. |  |  |  | 0.30303
20) What is the estimated budget for this project? |  | 25 | 25
a. Greater than $1 million |  |  |  | 1.5152 | C | 7.5758
b. Between $250,000 and $1 million |  |  |  | 0.90909 |  | Low
c. Less than $250,000 |  |  |  | 0.30303
21) Are there multiple agencies engaged as participants in this project? |  | 25 | 25
a. Yes |  |  |  | 1.5152 | B | 7.5758
b. No |  |  |  | 0.30303 |  | Low
| Sum of Weights | 330 |  |  | Score | 100
|  |  | 330 |  | Not Scored | Not Scored | Score
[7 empty] | VALUES | DESC. | POSITION
|  |  | 330 |  |  |  | 100 | Lower Limit
[7 empty] | 0 | Input Value | 4
[7 empty] | 500 | Upper Limit
1.5152
0.30303
| Risk Pre-Charter Score |  |  | Not Scored
| Plus: Risk Initiation Score |  |  | Not Scored
| Cumulative Risk Score |  |  |  | 0 | 0
| Average Risk Score |  |  |  | 0 | 0
| High Risk: 368 - 500 |  | 368 - 500
| Medium Risk: 234 - 367 |  | 234 - 367
| Low Risk: 100 - 233 |  | 100 - 233
RED FLAG SETTING
LOW RISK
HIGH RISK
MEDIUM RISK

## Complexity_Initiation_Gate
IT Complexity Questions - Project Initiation | Comments |  | Proportional Weight | Complexity Rank | SELECT ANSWER | Weighted Score
The Initiation Phase Gate Complexity Assessment is performed at the end of the Initiation Phase following completion of initial project documentation. Complexity is a risk modifier in that it can exacerbate or mitigate the impact of Risk on the successful completion of the project. This assessment will confirm or adjust the project's risk & complexity level and the resulting project category, examine the effectiveness of Initiation phase activities, and establish requirements for the project Planning Phase. Select one response for each question listed below. Do not leave any questions blank. If a question is not applicable, select "NA" from the drop-down list. | Form Title: DMS Project Risk & Complexity Assessment Tool Form Number: DMS-F-0505A Effective Date: 07/15 (incorporated into Rule 60GG-1, F.A.C.)
1) What is the level of new technology or infrastructure impact required by the project? |  | 20 | 20
a. Requires significant level of new technologies or changes to critical systems. |  |  |  | 2.1739 | C | 8.6957
b. Requires moderate level of new technologies or changes to critical systems. |  |  |  | 1.3043 |  | Low
c. Requires minimal-to-no new technologies or changes to critical systems. |  |  |  | 0.43478
2) What is the expected duration of the time period between the acceptance of the Project Charter to the end of Execution Phase? |  | 20 | 20
a. > 24 months |  |  |  | 2.1739 | D | 8.6957
b. 13-24 months |  |  |  | 1.7391 |  | Low
c. 6-12 months |  |  |  | 0.86957
d. < 6 months |  |  |  | 0.43478
3) Amount of resources being managed:
a) How many physical project team locations have to be managed? |  | 5 | 5
a. > 4 |  |  |  | 2.1739 | C | 2.1739
b. 1 - 4 |  |  |  | 1.3043 |  | Low
c. 1 |  |  |  | 0.43478
b) How many physical locations are associated with the solution implementation? |  | 5 | 5
a. > 25 |  |  |  | 2.1739 | D | 2.1739
b. 6 - 25 |  |  |  | 1.7391 |  | Low
c. 2 - 5 |  |  |  | 0.86957
d. 1 |  |  |  | 0.43478
4) How many end users are going to be using the delivered product(s)? |  | 15 | 15
a. > 200 |  |  |  | 2.1739 | D | 6.5217
b. 100 - 200 |  |  |  | 1.7391 |  | Low
c. 25 - 99 |  |  |  | 0.86957
d. < 25 |  |  |  | 0.43478
5) How clearly defined are the project's major milestones and deliverables? |  | 20 | 20
a. Major milestones and deliverables are not defined and scheduled. |  |  |  | 2.1739 | B | 8.6957
b. Major milestones and deliverables are defined in detail with logical sequence and included in the schedule. |  |  |  | 0.43478 |  | Low
6) How many vendors are involved with this project (for applications, infrastructure, network, etc.)? |  | 15 | 15
a. More than one vendor |  |  |  | 2.1739 | C | 6.5217
b. One vendor |  |  |  | 1.3043 |  | Low
c. No vendors |  |  |  | 0.43478
7) How many constraints have been identified that influence the selection of a specific solution to resolve the business problem? |  | 10 | 10
Constraints can include but are not limited to time, funding, personnel, facilities, and management limitations.
a. 1 or more |  |  |  | 2.1739 | B | 4.3478
b. None |  |  |  | 0.43478 |  | Low
8) Are there any open issues relating to the integration with other projects that could impact the completion of key milestones? |  | 15 | 15
a. Integration issues have been identified that will impact the project schedule, and there is no contingency plan in place to avoid adverse impact. |  |  |  | 2.1739 | C | 6.5217
b. Integration issues have been defined in Issue tracking that could impact the project milestones, but contingency plans have been implemented to keep the project on schedule. |  |  |  | 1.3043 |  | Low
c. All dependencies and integration requirements are on-schedule, and there are no anticipated impacts. This information is verified on a regular basis via status and project communications. |  |  |  | 0.43478
9) Does this project require data conversion? |  | 20 | 20
a. Yes |  |  |  | 2.1739 | B | 8.6957
b. No |  |  |  | 0.43478 |  | Low
10) What percentage of human resources (business and IT) assigned to the project are also shared resources with other agency operations and/or projects or from other agencies? |  | 15 | 15
Percentage of human resources = (# project team members shared) / (total project team).
a. 81 - 100% |  |  |  | 2.1739 | D | 6.5217
b. 51 - 80% |  |  |  | 1.7391 |  | Low
c. 21 - 50% |  |  |  | 0.86957
d. 0 - 20% |  |  |  | 0.43478
11) How many primary stakeholders are there? |  | 10 | 10
a. > 5 |  |  |  | 2.1739 | B | 4.3478
b. 1 - 5 |  |  |  | 0.43478 |  | Low
12) Does the Project Sponsor:
a) Have an understanding of IT project management? |  | 10 | 10
a. No |  |  |  | 2.1739 | B | 4.3478
b. Yes |  |  |  | 0.43478 |  | Low
b) Have experience in the business or functional domain? |  | 10 | 10
a. No |  |  |  | 2.1739 | B | 4.3478
b. Yes |  |  |  | 0.43478 |  | Low
13) What is the Project Manager's authority over the project? |  | 15 | 15
Authority is defined as the formal and legitimate control specified in a charter that gives a project manager power to act in the name of the sponsor or on behalf of the organization on matters pertaining to project integration, cost, schedule, scope, risk, human resources, procurements, quality, and communications.
a. Little authority |  |  |  | 2.1739 | C | 6.5217
b. Some authority |  |  |  | 1.3043 |  | Low
c. Complete authority |  |  |  | 0.43478
14) Is the schedule end date fixed (by legislative mandate, contract end date, vendor support expiration, etc.)? |  | 15 | 15
a. Yes |  |  |  | 2.1739 | B | 6.5217
b. No |  |  |  | 0.43478 |  | Low
15) Is there more than one funding source for this project? |  | 10 | 10
a. Yes |  |  |  | 2.1739 | B | 4.3478
b. No |  |  |  | 0.43478 |  | Low
| Sum of Weights | 230 |  |  | Score | 100
|  |  | 230 |  | Not Scored | Not Scored | Score
[7 empty] | VALUES | DESC. | POSITION
|  |  | 230 |  |  |  | 100 | Lower Limit
[7 empty] | 0 | Input Value | 4
[7 empty] | 500 | Upper Limit
2.1739
0.43478
| Complexity Pre-Charter Score |  |  | Not Scored
| Plus: Complexity Initiation Score |  |  | Not Scored
| Cumulative Complexity Score |  |  |  | 0 | 0
| Average Complexity Score |  |  |  | 0 | 0
| High Complexity: 368 - 500 | [5 empty] | Initiation Phase Project Category
| Medium Complexity: 234 - 367 | [5 empty] | VALUES | DESC. | POSITION
| Low Complexity: 100 - 233 | [5 empty] | 1 | Lower Limit
[7 empty] | 0 | Input Value | 4
| INITIATION PHASE CATEGORY |  |  |  | Not Scored | Not Scored | 4 | Upper Limit
LOW COMPLEXITY
HIGH COMPLEXITY
MEDIUM COMPLEXITY

## Risk_Planning_Gate
IT Risk Questions - Project Planning | Comments |  | Proportional Weight | Risk Rank | SELECT ANSWER | Weighted Score
The Planning Phase Gate Risk Assessment is performed at the end of the Planning Phase. During this assessment, the Agency will review planning documents and previous R&C Assessments. This assessment will confirm or adjust the risk & complexity level and the resulting project category, examine the effectiveness of Planning phase activities, and establish requirements for the project Execution and Monitoring and Control phases. Select one response for each question listed below. Do not leave any questions blank. If a question is not applicable, select "NA" from the drop-down list. | Form Title: DMS Project Risk & Complexity Assessment Tool Form Number: DMS-F-0505A Effective Date: 07/15 (incorporated into Rule 60GG-1, F.A.C.)
1) Data Dependency:
a) Is the project dependent on data from other sources? |  | 5 | 5
a. Yes |  |  |  | 2.6316 | B | 2.6316
b. No |  |  |  | 0.52632 |  | Low
b) Is the project dependent on data that is currently not available? |  | 5 | 5
a. Yes |  |  |  | 2.6316 | B | 2.6316
b. No |  |  |  | 0.52632 |  | Low
2) Is the project going to be reliant on a sole vendor? |  | 10 | 10
a. Yes |  |  |  | 2.6316 | B | 5.2632
b. No |  |  |  | 0.52632 |  | Low
3) Will the primary solutions vendor support the technical solution after project completion? |  | 10 | 10
a. No |  |  |  | 2.6316 | B | 5.2632
b. Yes |  |  |  | 0.52632 |  | Low
4) End user anticipated involvement:
a) What is the anticipated involvement of End Users with System Requirements and Design? |  | 10 | 10
a. Minimal or no user involvement in System Requirements and Design. |  |  |  | 2.6316 | D | 5.2632
b. Play minor roles in System Requirements and Design. |  |  |  | 2.1053 |  | Low
c. Highly involved in System Requirements and Design. |  |  |  | 1.0526
d. End user involvement is not required for System Requirements and Design. |  |  |  | 0.52632
b) What is the anticipated involvement of End Users with User Acceptance Testing? |  | 10 | 10
a. Minimal or no end user involvement with user acceptance testing. |  |  |  | 2.6316 | D | 5.2632
b. Play minor roles with testing. |  |  |  | 2.1053 |  | Low
c. Highly involved with testing. |  |  |  | 1.0526
d. End user does not interact with the system. |  |  |  | 0.52632
5) Are exit criteria established for each project phase? |  | 9 | 9
a. No |  |  |  | 2.6316 | B | 4.7368
b. Yes |  |  |  | 0.52632 |  | Low
6) Does the project schedule incorporate incremental and comprehensive stakeholder reviews of project deliverables? |  | 10 | 10
a. No |  |  |  | 2.6316 | B | 5.2632
b. Yes |  |  |  | 0.52632 |  | Low
7) Are acceptence criteria identified for all deliverables? |  | 10 | 10
a. No |  |  |  | 2.6316 | B | 5.2632
b. Yes |  |  |  | 0.52632 |  | Low
8) If a vendor implementation is required, has the vendor successfully implemented the selected solution in another organization? |  | 6 | 6
a. Vendor has never implemented the selected solution. |  |  |  | 2.6316 | C | 3.1579
b. Vendor has provided more than one reference indicating that they have successfully implemented the selected solution. |  |  |  | 1.5789 |  | Low
c. A vendor is not required for implementation. |  |  |  | 0.52632
9) Is there contingency built into the project schedule to accommodate the mitigation of schedule risks? |  | 10 | 10
a. No |  |  |  | 2.6316 | B | 5.2632
b. Yes |  |  |  | 0.52632 |  | Low
10) Are appropriate sourcing lead times built into the schedule? |  | 10 | 10
Examples of sourcing lead times include the lead times for procurements and Requests for Service.
a. Sourcing lead times are not built into the schedule. |  |  |  | 2.6316 | B | 5.2632
b. Sourcing lead times are estimated and scheduled. |  |  |  | 0.52632 |  | Low
11) Change management process:
a) Does the project's governance process include a defined change management process to handle changing requirements? |  | 10 | 10
a. No |  |  |  | 2.6316 | B | 5.2632
b. Yes |  |  |  | 0.52632 |  | Low
b) Does the project have routine change management meetings? |  | 5 | 5
a. No |  |  |  | 2.6316 | B | 2.6316
b. Yes |  |  |  | 0.52632 |  | Low
12) Are quality assurance methods defined? |  | 10 | 10
a. No |  |  |  | 2.6316 | B | 5.2632
b. Yes |  |  |  | 0.52632 |  | Low
13) Have appropriate SMEs been engaged to support the project (legal, procurement, security, budget, technology, business, etc)? |  | 10 | 10
a. No |  |  |  | 2.6316 | C | 5.2632
b. Some input is still needed |  |  |  | 1.5789 |  | Low
c. Yes |  |  |  | 0.52632
14) Is there a documented timeline for the next phase of the project? |  | 10 | 10
a. Project schedule is not yet developed |  |  |  | 2.6316 | D | 5.2632
b. Project schedule has been completed at the milestone level |  |  |  | 2.1053 |  | Low
c. Detailed project schedule is complete, but not yet baselined |  |  |  | 1.0526
d. Detailed project schedule is complete and baselined |  |  |  | 0.52632
15) Are all necessary resources (equipment, software, office space, etc.) for the next phase of the project readily available? |  | 10 | 10
a. No |  |  |  | 2.6316 | B | 5.2632
b. Yes |  |  |  | 0.52632 |  | Low
16) Does the Organizational Change Management Plan address impacts to the business? |  | 10 | 10
a. No |  |  |  | 2.6316 | B | 5.2632
b. Yes |  |  |  | 0.52632 |  | Low
17) Have the costs associated with the organizational changes been identified and budgeted? |  | 10 | 10
a. No |  |  |  | 2.6316 | C | 5.2632
b. Yes |  |  |  | 1.5789 |  | Low
c. Not applicable |  |  |  | 0.52632
18) Does the Project Plan clearly identify Integration requirements with other systems or dependencies on other projects that are outside the direct control of the project team? |  | 10 | 10
a. No |  |  |  | 2.6316 | B | 5.2632
b. Yes |  |  |  | 0.52632 |  | Low
| Sum of Weights | 190 |  |  | Score | 100
|  |  | 190 |  | Not Scored | Not Scored | Score
[7 empty] | VALUES | DESC. | POSITION
|  |  | 190 |  |  |  | 100 | Lower Limit
[7 empty] | 0 | Input Value | 4
[7 empty] | 500 | Upper Limit
2.6316
0.52632
| Risk Pre-Charter Score |  |  | Not Scored
| Plus: Risk Initiation Score |  |  | Not Scored
| Plus: Risk Planning Score |  |  | Not Scored
| Cumulative Risk Score |  |  |  | 0 | 0
| Average Risk Score |  |  |  | 0 | 0
| High Risk: 368 - 500 |  | 368 - 500
| Medium Risk: 234 - 367 |  | 234 - 367
| Low Risk: 100 - 233 |  | 100 - 233
RED FLAG SETTING
LOW RISK
HIGH RISK
MEDIUM RISK

## Complexity_Planning_Gate
IT Complexity Questions - Project Planning | Comments |  | Proportional Weight | Complexity Rank | SELECT ANSWER | Weighted Score
The Planning Phase Gate Complexity Assessment is performed at the end of the Planning Phase. Complexity is a risk modifier in that it can exacerbate or mitigate the impact of Risk on the successful completion of the project. This assessment will confirm or adjust the risk & complexity level and the resulting project category, examine the effectiveness of Planning phase activities, and establish requirements for the project Execution and Monitoring and Control phases. Select one response for each question listed below. Do not leave any questions blank. If a question is not applicable, select "NA" from the drop-down list. | Form Title: DMS Project Risk & Complexity Assessment Tool Form Number: DMS-F-0505A Effective Date: 07/15 (incorporated into Rule 60GG-1, F.A.C.)
1) In order to meet requirements, will the project solution drive a need for:
a) An increased level of testing from original projections? |  | 5 | 5
a. Yes |  |  |  | 2.7624 | B | 2.7624
b. No |  |  |  | 0.55249 |  | Low
b) Less flexibility in the project schedule? |  | 5 | 5
a. Yes |  |  |  | 2.7624 | B | 2.7624
b. No |  |  |  | 0.55249 |  | Low
c) More rigid development and internal project processes? |  | 5 | 5
a. Yes |  |  |  | 2.7624 | B | 2.7624
b. No |  |  |  | 0.55249 |  | Low
2) Has the complexity of the project required additional efforts to monitor scope / schedule / cost or quality parameters? |  | 5 | 5
a. Yes |  |  |  | 2.7624 | B | 2.7624
b. No |  |  |  | 0.55249 |  | Low
3) How many stakeholders need separate or unique communications? |  | 8 | 8
Unique communications refers to any individual or tailored communications with any individual stakeholder or group of stakeholders.
a. Four or more |  |  |  | 2.7624 | C | 4.4199
b. One to three |  |  |  | 1.6575 |  | Low
c. None |  |  |  | 0.55249
4) Are there clear lines of authority and accountability for tasks and deliverables within the project team? |  | 5 | 5
Clear lines of authority and accountability are those that are apparent, easily perceived, and free from confusion, doubt, or ambiguity.
a. No |  |  |  | 2.7624 | B | 2.7624
b. Yes |  |  |  | 0.55249 |  | Low
5) How many work packages are associated with the project? |  | 15 | 15
The work defined at the lowest level of the Work Breakdown Structure for which cost and duration can be estimated and managed. (PMBOK®, 5th Edition)
a. > 200 |  |  |  | 2.7624 | D | 8.2873
b. 101 - 200 |  |  |  | 2.2099 |  | Low
c. 51 - 100 |  |  |  | 1.105
d. 1 - 50 |  |  |  | 0.55249
6) Regarding the system development lifecycle methodology selected for the project, does the project staff have experience with the selected methodology? |  | 15 | 15
A “system development methodology” in software engineering is a framework that is used to develop an information system. Common methodologies include Agile, Waterfall, Spiral Development, Prototyping, Incremental, Rapid Application Development, etc.
a. The project staff requires training for the selected methodology. |  |  |  | 2.7624 | C | 8.2873
b. The project staff has knowledge of, but limited experience with, the selected methodology. |  |  |  | 1.6575 |  | Low
c. The project staff has extensive experience with the selected methodology. |  |  |  | 0.55249
7) Are there any new requirements determined after Project Planning that will drive a need for additional funding? |  | 10 | 10
a. Yes |  |  |  | 2.7624 | B | 5.5249
b. No |  |  |  | 0.55249 |  | Low
8) Does the project team require any additional training in order to be effective on the project (for technical, functional, or business skills)? |  | 15 | 15
a. All require training |  |  |  | 2.7624 | D | 8.2873
b. Most require training |  |  |  | 2.2099 |  | Low
c. Some require training |  |  |  | 1.105
d. None require training |  |  |  | 0.55249
9) Do the project team members have experience with an IT project of this magnitude and scope? |  | 15 | 15
a. None have experience |  |  |  | 2.7624 | D | 8.2873
b. Some have experience |  |  |  | 2.2099 |  | Low
c. Most have experience |  |  |  | 1.105
d. All have experience |  |  |  | 0.55249
10) Do the project team members have experience working together as a project team? |  | 15 | 15
a. No team members have experience working together as a project team. |  |  |  | 2.7624 | C | 8.2873
b. Some team members have experience working together as a project team. |  |  |  | 1.6575 |  | Low
c. All team members have experience working together as a project team. |  |  |  | 0.55249
11) Is the size of the project team appropriate for the size and complexity of the project effort? |  | 10 | 10
a. No |  |  |  | 2.7624 | B | 5.5249
b. Yes |  |  |  | 0.55249 |  | Low
12) What is the size of the project team? |  | 15 | 15
a. > 20 project team members |  |  |  | 2.7624 | C | 8.2873
b. Between 5 and 20 project team members |  |  |  | 1.6575 |  | Low
c. < 5 project team members |  |  |  | 0.55249
13) Are appropriately skilled resources available for the next phase of the project? |  | 15 | 15
a. Resources are not available for all roles. Significant preemption for other support activities is anticipated, and/or a high turnover is anticipated. |  |  |  | 2.7624 | B | 8.2873
b. Resources are available. Minimal turnover or preemption for other support activities is expected. |  |  |  | 0.55249 |  | Low
14) What percentage of the project team members are co-located? |  | 8 | 8
a. < 25% of team is in the same location. |  |  |  | 2.7624 | D | 4.4199
b. 25 - 49% of team is in the same location. |  |  |  | 2.2099 |  | Low
c. 50 - 90% of team is in the same location. |  |  |  | 1.105
d. > 90% of team is in the same location. |  |  |  | 0.55249
15) How would you evaluate the complexity of the business processes impacted by the project? |  | 15 | 15
Consider the number of inputs that the business processes require, the number of steps within those processes, the number of people involved in those processes, and the number of outputs that the processes are expected to produce.
a. High complexity |  |  |  | 2.7624 | C | 8.2873
b. Moderate complexity |  |  |  | 1.6575 |  | Low
c. Minimal complexity |  |  |  | 0.55249
| Sum of Weights | 181 |  |  | Score | 100
|  |  | 181 |  | Not Scored | Not Scored | Score
[7 empty] | VALUES | DESC. | POSITION
|  |  | 181 |  |  |  | 100 | Lower Limit
[7 empty] | 0 | Input Value | 4
[7 empty] | 500 | Upper Limit
2.7624
0.55249
| Complexity Pre-Charter Score |  |  | Not Scored
| Plus: Complexity Initiation Score |  |  | Not Scored
| Plus: Complexity Planning Score |  |  | Not Scored
| Cumulative Complexity Score |  |  |  | 0 | 0
| Average Complexity Score |  |  |  | 0 | 0
| High Complexity: 368 - 500 | [5 empty] | Planning Phase Project Category
| Medium Complexity: 234 - 367 | [5 empty] | VALUES | DESC. | POSITION
| Low Complexity: 100 - 233 | [5 empty] | 1 | Lower Limit
[7 empty] | 0 | Input Value | 4
| PLANNING PHASE CATEGORY |  |  |  | Not Scored | Not Scored | 4 | Upper Limit
LOW COMPLEXITY
HIGH COMPLEXITY
MEDIUM COMPLEXITY

## Risk_Event-Driven
IT Risk Questions - Event-Driven Assessment | Comments |  | Proportional Weight | Risk Rank | SELECT ANSWER | Weighted Score
The Event-Driven Risk Assessment is performed if the project experiences a significant change, or cumulative changes (in cost, schedule, or scope), from the project baseline. During this assessment, the Agency will review project change control request(s), Initiation and Planning documents, and previous R&C assessments. This assessment will confirm or adjust the project's risk & complexity level and the resulting project category, and determine if review and amendment to project management baselines are needed. Select one response for each question listed below. Do not leave any questions blank. If a question is not applicable, select "NA" from the drop-down list. | Form Title: DMS Project Risk & Complexity Assessment Tool Form Number: DMS-F-0505A Effective Date: 07/15 (incorporated into Rule 60GG-1, F.A.C.)
1) To what degree are stakeholders impacting the schedule by not providing timely decisions? |  | 15 | 15
a. Time required for critical decisions exceeds available schedule. |  |  |  | 3.125 | B | 9.375
b. Critical decisions are resolved within available schedule. |  |  |  | 0.625 |  | Low
2) Has an assumption used for planning and management of the project been proven invalid? |  | 15 | 15
a. Yes, and there is an impact to the project. |  |  |  | 3.125 | C | 9.375
b. Yes, but there minimal-to-no impact to the project. |  |  |  | 1.875 |  | Low
c. No |  |  |  | 0.625
3) Is the project making progress in its current phase? |  | 20 | 20
a. Progress is behind schedule by 10% or more. |  |  |  | 3.125 | B | 12.5
b. Progress is on or ahead of schedule. |  |  |  | 0.625 |  | Low
4) Is the project being managed in compliance with the project management plan? |  | 15 | 15
a. No, or the project management plan was inadequate. |  |  |  | 3.125 | B | 9.375
b. Yes |  |  |  | 0.625 |  | Low
5) Has requirements elaboration resulted in a requirements variance sufficient to force changes to project schedule, scope, or cost? |  | 20 | 20
a. Yes |  |  |  | 3.125 | B | 12.5
b. No |  |  |  | 0.625 |  | Low
6) Has project testing criteria and methodology been verified and validated? |  | 15 | 15
a. No |  |  |  | 3.125 | B | 9.375
b. Yes |  |  |  | 0.625 |  | Low
7) Is the project team effectively executing the project through well defined, repeatable processes? |  | 15 | 15
a. No |  |  |  | 3.125 | B | 9.375
b. Yes |  |  |  | 0.625 |  | Low
8) Will the project require:
a) An increased level of testing from projections? |  | 15 | 15
a. Yes |  |  |  | 3.125 | B | 9.375
b. No |  |  |  | 0.625 |  | Low
b) An increase in the duration of the project schedule? |  | 15 | 15
a. Yes |  |  |  | 3.125 | B | 9.375
b. No |  |  |  | 0.625 |  | Low
c) An increase in the project's baselined cost? |  | 15 | 15
a. Yes |  |  |  | 3.125 | B | 9.375
b. No |  |  |  | 0.625 |  | Low
| Sum of Weights | 160 |  |  | Score | 100
|  |  | 160 |  | Not Scored | Not Scored | Score
[7 empty] | VALUES | DESC. | POSITION
|  |  | 160 |  |  |  | 100 | Lower Limit
[7 empty] | 0 | Input Value | 4
[7 empty] | 500 | Upper Limit
3.125
0.625
Event-Driven Project Category
| Risk Pre-Charter Score |  |  | Not Scored |  |  | VALUES | DESC. | POSITION
| Plus: Risk Initiation Score |  |  | Not Scored |  |  | 1 | Lower Limit
| Plus: Risk Planning Score |  |  | Not Scored |  |  | 0 | Input Value | 4
| Plus: Risk Event-Driven Score |  |  | Not Scored |  |  | 4 | Upper Limit
| Score from Complexity_Planning |  |  |  | 0 | 0
| Event Driven Risk Score |  |  |  | 0 | 0
| Cumulative Risk Score |  |  |  | 0 | 0
High Risk: 368 - 500
Medium Risk: 234 - 367
Low Risk: 100 - 233
RED FLAG SETTING
| Planning Complexity Completed? |  |  |  | NO | NO
| Planning Complexity Rating |  |  |  | Low_Complexity | Low_Complexity
Defaults to High_Complexity if Planning Complexity is not completed for the Event-Driven Assessment.
| EVENT-DRIVEN CATEGORY |  |  |  | Not Scored | Not Scored
LOW RISK
HIGH RISK
MEDIUM RISK

## Project Category Lookup Table (hidden)
RISK & COMPLEXITY ASSESSMENT - PROJECT CATEGORY LOOKUP TABLE |  |  |  | Form Title: DST Project Risk & Complexity Assessment Tool
Risk | High_Complexity | Medium_Complexity | Low_Complexity | Form Number: DST-F-0505A
High_Risk | 4 | 3 | 3 | Effective Date: 07/15 (incorporated into Rule 74-1.002, F.A.C.)
Medium_Risk | 3 | 2 | 2
Low_Risk | 2 | 1 | 1
RISK & COMPLEXITY ASSESSMENT - PROJECT CATEGORY SCORING BY PHASE
Pre-Charter |  |  | Not Scored
Initiation |  |  | Not Scored
Planning |  |  | Not Scored
Event-Driven |  | Low_Complexity | Not Scored

## L_DEPT (hidden)
AGENCY / DEPARTMENT
<Department Name>
AHCA | Agency for Health Care Administration
APD | Agency for Persons with Disabilities
CITRUS | Department of Citrus
DACS | Department of Agriculture & Consumer Services
DBPR | Department of Business & Professional Regulation
DCF | Department of Children & Families
DEM | Department of Emergency Management
DEP | Department of Environmental Protection
DEO | Department of Economic Opportunity
DFS | Department of Financial Services
DJJ | Department of Juvenile Justice
DMA | Department of Military Affairs
DMS | Department of Management Services
DOC | Department of Corrections
DOE | Florida Department of Education
DOH | Florida Department of Health
DOR | Florida Department of Revenue
DOS | Florida Department of State
DOT | Florida Department of Transportation
DVA | Florida Department of Veterans' Affairs
ELC | Early Learning Coalition
FL | Florida Lottery
FDEA | Florida Department of Elder Affairs
FDLE | Florida Department of Law Enforcement
HSMV | Department of Highway Safety & Motor Vehicles
OFR | Office of Financial Regulation
OIR | Office of Insurance Regulation
INSERT ROWS ABOVE THIS LINE TO UPDATE DROP-DOWN LIST

## L_Answer Select (hidden)
A
B
C
D
E
NA
INSERT ROWS ABOVE THIS LINE TO UPDATE DROP-DOWN LIST
A
B
C
D
NA
INSERT ROWS ABOVE THIS LINE TO UPDATE DROP-DOWN LIST
A
B
C
NA
INSERT ROWS ABOVE THIS LINE TO UPDATE DROP-DOWN LIST
A
B
NA
INSERT ROWS ABOVE THIS LINE TO UPDATE DROP-DOWN LIST
Yes
No
INSERT ROWS ABOVE THIS LINE TO UPDATE DROP-DOWN LIST