## Project Information
Stakeholder Analysis Communication Plan
Rule Chapter 60GG-1 does not require the use of a Stakeholder Analysis Communication Plan template. This is an FDOT Recommended tool to assist with the requirements noted below for the Communication Plan and Project Charter. However, if you choose to use this template, please reference this document as appropriate in the Project Management Plan.
| Section: | 60GG-1.003 Initiation | Risk & Complexity Category |  |  |  | Project Information
| Documentation or Activity: | [5 empty] | Project
| Project Charter |  | 4 | 3 | 2 | 1 | Project Manager
| No. | Requirements |  |  |  |  | Risk & Complexity Category
| 003.4.12 | The Project Charter identifies the project stakeholders. | Required | Required | Required | Required | Project Sponsor
Last Updated (Date)
| Section: | 60GG-1.004 Planning | Risk & Complexity Category |  |  |  | Update Log | Purpose of the update
Documentation or Activity:
| Communication Plan |  | 4 | 3 | 2 | 1
| No. | Requirements
| 004.9.1 | The Communications Plan documents the project information requirements of stakeholders. | Required | Required | Required | Required
| 004.9.2 | The Communications Plan documents, in detail, what information will be collected and reported. | Required | Required | Required | Required
| 004.9.3 | The Communications Plan documents, in detail, when information will be collected and reported. | Required | Required | Required | Required
| 004.9.4 | The Communications Plan documents, in detail, how information will be collected and reported. | Required | Required | Required | Required
| 004.9.5 | The Communication Plan documents the responsibility for (1) meeting summaries, (2) project status reports, (3) project governance meetings, and (4) stakeholder communications (including reporting variances in schedule, cost, or scope and emerging risks or issues). | Required | Required
| 004.9.6 | The Communication Plan documents the frequency for (1) meeting summaries, (2) project status reports, (3) project governance meetings, and (4) stakeholder communications (including reporting variances in schedule, cost, or scope and emerging risks or issues). | Required | Required
| 004.9.7 | The Communication Plan documents the format for (1) meeting summaries, (2) project status reports, (3) project governance meetings, and (4) stakeholder communications (including reporting variances in schedule, cost, or scope and emerging risks or issues). | Required | Required
| 004.9.8 | The Communication Plan documents the distribution method for (1) meeting summaries, (2) project status reports, (3) project governance meetings, and (4) stakeholder communications (including reporting variances in schedule, cost, or scope and emerging risks or issues). | Required | Required
| 004.9.9 | The Communication Plan documents the location of the project repository. | Required | Required
| 004.9.10 | The Communication Plan documents the Decision Tracking process. | Required | Required
| 004.9.11 | The Communication Plan documents the Action Item Tracking process. | Required | Required
Instructions
1 | Enter your Project Name on the Header of each tab.
2 | Fill out the Project Information beginning on Row 3 above.
3 | Enter all stakeholders on the project in Column A. Stakeholders to be considered are the Legislature, Governor's Office, FDOT Executive Leadership, and the citizens of Florida.
4 | On a scale of 1-10 (with 10 being the most), enter the stakeholder's interest in this project. FDOT Recommendation: Do not assign a value of "5". Instead, use a value of "4.9" or "5.1". See step 6 in the Instructions below for further clarification.
5 | On a scale of 1-10 (with 10 being the most), enter the stakeholder's influence on this project. FDOT Recommendation: Do not assign a value of "5". Instead, use a value of "4.9" or "5.1". See step 6 in the Instructions below for further clarification.
6 | As each stakeholder is assigned a number for interest and influence, a plot (or dot) will show up on the graph to the right of the stakeholder list. The graph is divided into four (4) quadrants (Q1, Q2, Q3, Q4). Depending on where the plot falls on the graph, the stakeholder will fall into one of those quadrants.
7 | Each quadrant is represented in the Communication Plan. Enter the types of communications (Communication Activity) that will be relevant for each stakeholder quadrant. At a minimum, Rule Chapter 60GG-1, F.A.C. requires the following types: meeting summaries, project status reports, project governance meetings, and stakeholder communications (including reporting variances in schedule, cost, or scope and emerging risks or issues). As part of the template, these four requirements have been entered under Q1. However, you may move these around as appropriate.
8 | For each Communication Activity listed, fill out the remaining fields (How will communicate (Medium/Format/Distribution Method), When, How Often (Frequency), Responsibility (Who)). A Notes column has also been added if necessary.
9 | As updates to any tab are made, create a line on the update log beginning on Row 11 above.
10 | If this template does not fit the needs of the project, specifically document in the Project Management Plan (PMP) that deviation from this template is necessary. Any altered, added or removed sections to the template must be approved by the signatories listed on the PMP template. Note: Any modifications to the approved template must still meet the requirements of Rule Chapter 60GG-1, Florida Administrative Code (F.A.C.).
Definitions
Influence |  | Measures the stakehodler's degree of ability to help or have impact on the project
Interest |  | Measures the stakeholder's degree of support or opposition to the project's goals and objectives
Stakeholder |  | A person, group, organization, or state agency involved in or affected by a course of action as defined in Section 282.0041(21), Florida Statute (F.S.)

## Stakeholder Analysis
Rank on a scale of 1 - 10
Stakeholder Name | Interest | Influence | Contact Information
Governor's Office | 1 | 10
Legislature | 1 | 10
FDOT Secretary | 2 | 10
Chief of Transportation Technology | 4 | 10
Chief Information Officer | 4 | 9
Application Services Manager | 10 | 9
CPM Section Manager | 10 | 8
Project Manager | 10 | 7
Project Team | 10 | 6
Application Services Section Managers | 6 | 4
FDOT Rule 60GG-1 Expert | 10 | 4
Subject Matter Experts (SMEs) | 6 | 3
Citizens of Florida | 1 | 1
Legend:
Influence measures their degree of ability to help or have impact on your project
Interest measures their degree of support or opposition to your goals and objectives
|  |  |  | Q1 | Manage Closely | Fully engaged, detailed information, involve in governace and decision-making, consult regularly
|  |  |  | Q2 | Keep Satisfied | Engage and consult on area of interest; otherwise, provide high-level communication
|  |  |  | Q3 | Keep Informed | Involve, inform and consult them in their area of interest; use as a potential supporter/goodwill ambassador
|  |  |  | Q4 | Monitor | Check to see if their position has moved; otherwise, inform them through general communication, such as newsletters or website.
Q1
Q2
Q3
Q4

## Communication Plan
Quadrant | Communication Activity (What) | How will communicate (Medium/Format/Distribution Method) | When, How Often (Frequency) | Responsibility (Who) | Notes
Q1 | Meeting Minutes/Summaries | email/SharePoint | Weekly | Jr. Project Manager
| Project Status Report | email | Bi-Weekly | Project Manager
| Team Meeting/Project Governance Meeting | In-person/Conference Call | Weekly | Project Manager
| Stakeholder Communications (including variances in schedule, cost, scope, emerging risks and issues) | email | Bi-Weekly | Project Manager
Q2 | Status Updates | email/SharePoint | Upon Request/As needed | Project Manager
Q3 | Subject Matter Meetings | In-person/Conference Call | Upon Request/As needed | Project Manager
| Status Updates | email/SharePoint | Upon Request/As needed | Project Manager
Q4 | Subject Matter Meetings | In-person/Conference Call | Upon Request/As needed | Project Manager
| Status Updates | email/SharePoint | Upon Request/As needed | Project Manager