## Plan
4 Year Acquisition Plan for Asset Maintenance
Updated 9/3/2025
District | County(ies) | Description (including types of assets) | Calendar Year of Projected Procurement | Current Contract Information (Note * = possible renewal of existing contract) |  |  |  | Upcoming Contract Information
|  |  |  | Contract # | Contract Term (Yrs) | Contract Begin | Contract End | New Contract # | Advertisement Dates
Calendar Year 2025
5 | Osceola & Orange | State Primary Roads | 2025 | E5X47-R0 * To Be Renewed | 3.2521 | 2022-07-01 | 2025-09-30 | E5X47-R1 | N/A
5 | Orange & Osceola | I-4 | 2025 | E5X88-R0 * To Be Renewed | 3.2521 | 2022-07-01 | 2025-09-30 | E5X88-R1 | N/A
5 | Brevard | I-95 | 2025 | E5X11-R0 * To Be Renewed | 3.3342 | 2022-07-01 | 2025-10-30 | E5X11-R1 | N/A
5 | Brevard | State Primary Roads | 2025 | E5X12-R0 * To Be Renewed | 3.3342 | 2022-07-01 | 2025-10-30 | E5X12-R1 | N/A
5 | Volusia & Flagler | I-95 | 2025 | E5X37-R0 * To Be Renewed | 3.5014 | 2022-07-01 | 2025-12-30 | E5X37-R1 | N/A
Turnpike | Citrus, Hernando, Hillsborough, Pasco, Polk | Toll Roads, Toll Facilities | 2025 | E8T73-R0 * | 2.9973 | 2023-01-01 | 2025-12-30 | E8T73-R1 | N/A
5 | Seminole & Volusia | I-4 | 2025 | E5X90-R0 * To Be Renewed | 3.7507 | 2022-07-01 | 2026-03-31 | E5X90-R1 | N/A
Calendar Year 2026
2 | Clay | State Primary Roads | 2026 | E2Y86-R0 * | 7.0027 | 2019-06-29 | 2026-06-28
2 | Nassau | State Primary Roads | 2026 | E2Y74-R0 * | 7.0027 | 2019-06-30 | 2026-06-29
6 | Miami-Dade | I-95, I-75, I-195, SR 826, SR 856, SR 970 & SR 913 | 2026 | E6N37-R0 * | 5 | 2021-08-01 | 2026-07-31
1 | Collier | State Primary Roads | 2026 | E1S36-R0 * | 6.9973 | 2019-10-01 | 2026-09-28
4 | Martin, St. Lucie, Palm Beach & Broward | US1 and A1A Roadway | 2026 | E4T63-R0 * | 7.0027 | 2019-11-01 | 2026-10-31
Turnpike | Osceola, Orange, Lake, Sumter, Seminole | Toll Roads, Toll Facilities | 2026 | E8R87-R0 * | 7 | 2019-12-01 | 2026-11-29
Calendar Year 2027
1 | Polk | I-4 & State Primary Roads in NE Polk County | 2027 | E1T20-R0 * | 6.9973 | 2020-07-01 | 2027-06-29
2 | Alachua | I-75, Rest Areas | 2027 | E20V9 | 5 | 2022-07-01 | 2027-06-30
3 | Bay & Calhoun | All State Roads and associated facilities | 2027 | E3V71 | 5 | 2022-07-01 | 2027-06-30
7 | Hillsborough, Hernando, Pasco Cou | I-75, Rest Areas | 2027 | E7N65-R0 * | 6 | 2021-07-01 | 2027-06-30
2 | Madison | State Primary Roads | 2027 | E2R44-R1 | 7 | 2020-10-01 | 2027-09-30
2 | Putnam | State Primary Roads | 2027 | E2Z80-R0 * | 7 | 2020-10-01 | 2027-09-30
1 | Districtwide | Structure (Bridge and Non-Bridge) Inspection and Maintenance | 2027 | E1U99 | 4.9973 | 2022-11-01 | 2027-10-30
4 | Martin, St. Lucie, Palm Beach & Broward | US 1 and A1A Structures (bridge and non-bridge) | 2027 | E4T64-R0 * | 8 | 2019-11-01 | 2027-10-30
7 | Districtwide | Structures (Bridge and Non-Bridge) Inspection and Maintenance | 2027 | E7P33 | 5 | 2022-11-01 | 2027-10-31
Turnpike | Palm Beach, Martin, St. Lucie, Indian River, Okeechobee, Osceola | Toll Roads, Toll Facilities | 2027 | E8S48-R0 * | 6.9973 | 2020-12-01 | 2027-11-29
1 | Charlottee | State Primary Roads | 2027 | E1T80-R0 * | 6.9973 | 2021-01-01 | 2027-12-30
3 | Escambia | All State Roads, Structures (bridge and non-bridge) | 2027 | E3W02 | 4.9973 | 2023-01-01 | 2027-12-30
3 | Districtwide | Rest Areas, Welcome Centers, and WIMs | 2027 | E3V79 | 5 | 2023-01-01 | 2027-12-31
5 | Districtwide | Rest Areas | 2027 | E5X59 | 5.5041 | 2022-07-01 | 2027-12-31
5 | Lake, Seminole & Orange | Wekiva Parkway | 2027 | E5X89 | 5.5041 | 2022-07-01 | 2027-12-31
7 | Pinellas | State Primary Roads | 2027 | E7I95-R1 | 6.9973 | 2021-01-06 | 2028-01-04
4 | Palm Beach | I-95, Roads, Structures (Bridge and non-bridge) | 2027 | E4U23-R0 * | 6.9973 | 2021-01-30 | 2028-01-28
6 | Districtwide | Movable Bridge Inspection & Maintenance | 2027 | E6N26-R0 * | 7 | 2021-02-01 | 2028-01-31
Calendar Year 2028
2 | Duval | State Primary Roads | 2028 | E2V97-R0* | 10 | 2018-06-01 | 2028-05-30
2 | Duval, Nassau & St. Johns | I-95, SR 202, SR 9B | 2028 | E2X03-R0* | 10 | 2018-06-27 | 2028-06-25
5 | Sumter | I-75, | 2028 | E5V46-R0* | 7 | 2021-07-01 | 2028-06-30
5 | Marion & Sumter | All State Roads | 2028 | E5V71-R0* | 7 | 2021-07-01 | 2028-06-30
7 | Hillsborough | Skyway Bridge | 2028 | E7P34 | 6 | 2022-07-01 | 2028-06-30
4 | Martin | State Primary Roads | 2028 | E4V95 | 6 | 2022-10-24 | 2028-10-23
1 | Sarasota | State Primary Roads | 2028 | E1U59-R0* | 6 | 2022-01-01 | 2028-12-29
4 | Broward | I-95, I-595, & I-75 | 2028 | E4V24-R0* | 6 | 2022-01-01 | 2028-12-31
5 | Flagler & Volusia | State Primary Roads | 2028 | E5U63-R0* | 10 | 2019-01-01 | 2028-12-31
Calendar Year 2029
3 | Franklin, Gulf, Jefferson, Liberty, & Wakulla | State Primary Roads | 2029 | E3O40-R1 | 7 | 2022-07-01 | 2029-06-30
2 | Districtwide | Welcome Centers, Rest Areas, WIMs | 2029 | E20V8 | 7 | 2022-08-11 | 2029-08-10
2 | Baker, Columbia, Hamilton, Madison, & Suwannee | I-10, I-75 | 2029 | E20W0 | 7 | 2022-11-01 | 2029-10-31
4 | Broward & Palm Beach | US 27, Wayside Parks | 2029 | E4V94 | 7 | 2022-11-12 | 2029-11-11
7 | Citrus | State Primary Roads | 2029 | E7M59-R0 | 10 | 2020-01-01 | 2029-12-31

## Line Chart
Procurements Actions
January - June 2025 | 8
July - December 2025 | 4
January - June 2026 | 5
July - December 2026 | 1
January - June 2027 | 10
July - December 2027 | 8
January - June 2028 | 6
July - December 2028 | 3

## Bar Chart
AM Acquisition Plan for 2025
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February
Current Contract #
E8V22 | bar: November to April
E6M77 | bar: January to June
E7M98 | bar: January to June
E3R56 | bar: February to July
E5X47 | bar: March to August
E5X88 | bar: March to August
E5X11 | bar: April to September
E5X12 | bar: April to September
E5X37 | bar: July to December
E4R18 | bar: July to December
E8T73 | bar: July to December
E5X90 | bar: September to February
AM Acquistion Plan for 2026
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February
Current Contract #
E2Y86 | bar: January to June; November
E2Y74 | bar: January to June
E6N37 | bar: February to July
E1S36 | bar: April to September
E4T63 | bar: May to October
E8R87 | bar: June to November
AM Acquistion Plan for 2027
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February
Current Contract #
E1T20 | bar: January to June
E20V9 | bar: January to June
E3V71 | bar: January to June
E7N65 | bar: January to June
E2R44 | bar: April to September
E2Z80 | bar: April to September
E1U99 | bar: May to October
E4T64 | bar: May to October
E7P33 | bar: May to October
E8S48 | bar: June to November
E1T80 | bar: July to December
E3W02 | bar: July to December
E3V79 | bar: July to December
E5X59 | bar: July to December
E5X89 | bar: July to December
E7I95 | bar: August to January
E4U23 | bar: August to January
E6N26 | bar: August to January
AM Acquistion Plan for 2028
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February
Current Contract #
E2V97 | bar: December to May
E2X03 | bar: January to June
E5V46 | bar: January to June
E5V71 | bar: January to June
E7P34 | bar: January to June
E4V95 | bar: May to October
E1U59 | bar: July to December
E4V24 | bar: July to December
E5U63 | bar: July to December
All Years Combined
| November: 2025; January: 2026 | [10 empty] | 2027 | [11 empty] | 2028
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February
Current Contract #
E8V22 | bar: November to April
E6M77 | bar: January to June
E7M98 | bar: January to June
E3R56 | bar: February to July
E5X47 | bar: March to August
E5X88 | bar: March to August
E5X11 | bar: April to September
E5X12 | bar: April to September
E5X37 | bar: July to December
E4R18 | bar: July to December
E8T73 | bar: July to December
E5X90 | bar: September to February
E2Y86 | bar: January to June; November
E2Y74 | bar: January to June
E6N37 | bar: February to July
E1S36 | bar: April to September
E4T63 | bar: May to October
E8R87 | bar: June to November
E1T20 | bar: January to June
E20V9 | bar: January to June
E3V71 | bar: January to June
E7N65 | bar: January to June
E2R44 | bar: April to September
E2Z80 | bar: April to September
E1U99 | bar: May to October
E4T64 | bar: May to October
E7P33 | bar: May to October
E8S48 | bar: June to November
E1T80 | bar: July to December
E3W02 | bar: July to December
E3V79 | bar: July to December
E5X59 | bar: July to December
E5X89 | bar: July to December
E7I95 | bar: August to January
E4U23 | bar: August to January
E6N26 | bar: August to January
E2V97 | bar: December to May
E2X03 | bar: January to June
E5V46 | bar: January to June
E5V71 | bar: January to June
E7P34 | bar: January to June
E4V95 | bar: May to October
E1U59 | bar: July to December
E4V24 | bar: July to December
E5U63 | bar: July to December