## Slide 1: Girder Strengthening using CFRP Wrap
SR-404 over Banana River

## Slide 2: Bridge Location

## Slide 3: Bridge Information
Parallel Bridges 700082 & 700148
  Built in 1971
  Span Length 43-ft
  7 spans

## Slide 4: Repair Locations

## Slide 5: Issue discovered during bridge inspection
Bridge # 700082
2011
Minor cracks were documented
2013
In-place spall
2015
In-place spall
Repair Design started
Notes: Location 1
Removing spall/loose concrete revealed corroded strands
AASHTO Type II at end of beam
3 strands corroded; 24 strands total

## Slide 6: Issue discovered during bridge inspection
2010
Spall was patched
Bridge # 700082
2015
Patch failed
Strand with 100% section loss
Notes: Location 2
Removing spall/loose concrete revealed corroded strands
AASHTO Type II at end of beam
3 strands corroded; 24 strands total

## Slide 7: Issue discovered during bridge inspection
Bridge # 700148
2015
In-place spall documented
Notes: Location 3
Removing spall/loose concrete revealed corroded strands
AASHTO Type II at end of beam
2 strands corroded; 24 strands total

## Slide 8: Repair Design
CFRP was selected as the repair method
Consultant developed repair plans
  Structure 700082, 3 strands at each location
  Structure 700148, 2 strands
  Surface Preparation Details
  CFRP Repair Details
  Time: 2 months

## Slide 9: Repair Design
Design Assumed Strands will not be repaired
CFRP Designed to restore beam to original moment and shear capacity
Load Rating Check
Procedure:
  Remove loose material
  Clean surface and steel
  Repair concrete
  CFRP installation
Notes: CFRP installation process included: Primer/saturant application (CFRP resin), CFRP application (wet lay-up), protective UV coating.

## Slide 10: CFRP Repair Detail

## Slide 11: CFRP Repair Detail

## Slide 12: Construction
Construction:
  Time: 1 week
  Cost: $15,051
    Including personnel and equipment
Construction was performed by in-house Heavy Bridge Crew
Construction time: 5 days
Notes: Construction team included: in-house crew, EOR on site during initial CFRP installation, safety personnel

## Slide 13: Construction

## Slide 14: Construction

## Slide 17: Benefits
Time:
  Reduced by avoiding contract development.
Life-Cycle:
  corrosion resistance.
Economical Benefit
  Low installation cost
  Fast turn around