## SUE Matrix
FPID: | 417540-6-52-01 | Description: | SR 29 |  | This matrix was created by Faller, Davis & Associates to assist the UAO's in identifying conflicts between the UAO's facilities and proposed roadway construction. Faller, Davis & Associates accepts no liability for conflicts overlooked for this report. Each UAO or designee is responsible to perform a detailed and comprehensive plans review for conflict analysis.
Phase #: | II | Plans Date: | 2024-06-08
Preparer: | Stephen Slinn
Date: | 2024-08-05
Conflict # | Utility Agency/ Owner (UAO) | Station/Offset | Facility Description (Material, Type, Number, Size) | Conflict Description (Possible or Actual) | VVH (Y/N) | Test Hole VVH # | Suggested Conflict Resolution | Resolved Status
LP1 |  | 2086+17, 46' LT, |  | Light Pole 1 - Exploratory | Y
LP2 |  | 2087+53, 45' RT. |  | Light Pole 2 - Exploratory | Y
LP3 |  | 2089+15, 51' LT. |  | Light Pole 3 - Exploratory | Y
LP4 |  | 2090+82, 47' RT. |  | Light Pole 4 - Exploratory | Y
LP5 |  | 2092+43, 58' LT. |  | Light Pole 5 - Exploratory | Y
LP6 |  | 2094+50, 69' RT. |  | Light Pole 6 - Exploratory | Y
LP7 |  | 2094+50, 69' LT. |  | Light Pole 7 - Exploratory | Y
LP8 |  | 2096+55, 62' RT. |  | Light Pole 8 - Exploratory | Y
LP9 |  | 2096+58, 60' LT. |  | Light Pole 9 - Exploratory | Y
LP10 |  | 2098+74, 85' RT. |  | Light Pole 10 - Exploratory | Y
LP11 |  | 2098+77, 49' LT. |  | Light Pole 11 - Exploratory | Y
LP12 |  | 2099+73, 136' RT. |  | Light Pole 12 - Exploratory | Y
LP13 |  | 2099+99, 62' LT. |  | Light Pole 13 - Exploratory | Y
LP14 |  | 2101+46, 129' RT. |  | Light Pole 14 - Exploratory | Y
LP15 |  | 2101+30, 61' LT. |  | Light Pole 15 - Exploratory | Y
LP16 |  | 2102+89, 75' RT. |  | Light Pole 16 - Exploratory | Y
LP17 |  | 2102+61, 31' LT. |  | Light Pole 17 - Exploratory | Y
LP18 |  | 2105+27, 72' RT. |  | Light Pole 18 - Exploratory | Y
LP19 |  | 2105+29, 66' LT. |  | Light Pole 19 - Exploratory | Y
LP20 |  | 802+66, 46' LT. |  | Light Pole 20 - Exploratory | Y
LP21 |  | 2100+90, 172' LT. |  | Light Pole 21 - Exploratory | Y
LP22 |  | 401+47, 41' LT. |  | Light Pole 22 - Exploratory | Y
LP23 |  | 403+01, 38' RT. |  | Light Pole 23 - Exploratory | Y
LP98 |  | 2234+55, 72' RT. |  | Light Pole 98 - Exploratory | Y
LP99 |  | 2235+75, 69' LT. |  | Light Pole 99 - Exploratory | Y
LP100 |  | 2236+95, 72' RT. |  | Light Pole 100 - Exploratory | Y
LP111 |  | 2238+15, 70' LT. |  | Light Pole 111 - Exploratory | Y
LP113 |  | 2240+55, 73' LT. |  | Light Pole 113 - Exploratory | Y
LP114 |  | 2239+35, 72' RT. |  | Light Pole 114 - Exploratory | Y
LP115 |  | 2242+95, 76' LT. |  | Light Pole 115 - Exploratory | Y
LP116 |  | 2241+75, 72' RT. |  | Light Pole 116 - Exploratory | Y
LP117 |  | 2245+35, 77' LT. |  | Light Pole 117 - Exploratory | Y
LP118 |  | 2244+15, 74' RT. |  | Light Pole 118 - Exploratory | Y
LP119 |  | 2247+75, 76' LT. |  | Light Pole 119 - Exploratory | Y
LP120 |  | 2246+55, 74' RT. |  | Light Pole 120 - Exploratory | Y
LP121 |  | 2250+15, 77' LT. |  | Light Pole 121 - Exploratory | Y
LP122 |  | 2248+95, 74' RT. |  | Light Pole 122 - Exploratory | Y
LP123 |  | 2252+55, 77' LT. |  | Light Pole 123 - Exploratory | Y
LP124 |  | 2251+35, 74' RT. |  | Light Pole 124 - Exploratory | Y
LP125 |  | 2254+95, 77' LT. |  | Light Pole 125 - Exploratory | Y
LP126 |  | 2253+75, 75' RT. |  | Light Pole 126 - Exploratory | Y
LP127 |  | 2257+35, 73' LT. |  | Light Pole 127 - Exploratory | Y
LP128 |  | 2256+15, 74' RT. |  | Light Pole 128 - Exploratory | Y
1 | Comcast | 2086+92, 30' LT | BTV | In proposed sidewalk and proposed paved shoulder | Y |  | relocate/adjust
2 | Immokalee | 2088+34, 87' LT | Water Main | In conflict with proposed side drain | Y |  | relocate/adjust
3 | Summit | 2088+38, 83' LT | BFOC | Possible conflict due to construction of side drain | Y
4 | Centurylink | 2088+38, 95' LT | BFOT | Possible conflict due to construction of side drain | Y
5 | Summit | 2088+70, 84' LT | BFOC | Possible conflict due to construction of side drain | Y
6 | Immokalee | 2088+70, 87' LT | Water Main | In conflict with proposed side drain | Y |  | relocate/adjust
7 | Centurylink | 2088+70, 94' LT | BFOT | Possible conflict due to construction of side drain | Y
8 | Exploratory | 2094+00, 65' RT | Multipole sign | Possible conflict with signage - Exploratory | Y
9 | Immokalee | 2094+15, 86' LT | WM | Possible conflict due to construction of side drain | Y
10 | Centurylink | 2094+15, 92' LT | BFOT | Possible conflict due to construction of side drain | Y
11 | Immokalee | 2094+55, 85' LT | WM | Possible conflict due to construction of side drain | Y
12 | Centurylink | 2094+55, 92' LT | BFOT | Possible conflict due to construction of side drain | Y
13 | Immokalee | 2095+23, 45' LT | Water Main | In proposed sidewalk, proposed paved shoulder, and proposed widening | Y |  | vertically adjust
14 | Immokalee | 2095+23, 50' RT | Water Main | In proposed sidewalk, proposed paved shoulder, and proposed widening | Y |  | vertically adjust
15 | Centurylink | 2097+10, 93' LT | BFOT | In conflict with proposed drainage ditch | Y
16 | Centurylink | 2097+10, 80' LT | BFOT | In conflict with proposed drainage ditch | Y
17 | Summit | 2097+10, 78' LT | BFOC | In conflict with proposed drainage ditch | Y
18 | Centurylink | 2097+10, 74' LT | BFOC | In conflict with proposed drainage ditch | Y
19 | Immokalee | 2097+10, 71' LT | SS | In conflict with proposed drainage ditch | Y
20 | Centurylink | 2099+05, 94' LT | BFOT | In conflict with proposed drainage ditch | Y
21 | Centurylink | 2099+05, 79' LT | BFOC | In conflict with proposed drainage ditch | Y
22 | Centurylink | 2099+05, 78' LT | BFOC | In conflict with proposed drainage ditch | Y
23 | Summit | 2099+05, 75' LT | BFOC | In conflict with proposed drainage ditch | Y
24 | Immokalee | 2099+05, 72' LT | SS | In conflict with proposed drainage ditch | Y
25 | Teco | 2099+05, 64' LT | 8" Gas Main | In conflict with proposed drainage ditch | Y
26 | Centurylink | 2099+05, 56' LT | BT | In conflict with proposed drainage ditch | Y
27 | Centurylink | 2099+05, 44' LT | BT | In conflict with proposed drainage ditch | Y
28 | Centurylink | 2099+98, 79' LT | BFOC | In conflict with proposed drainage structure | Y
29 | Centurylink | 2100+80, 40' LT | BT | Conflict with drainage culvert | Y
30 | Summit | 2100+80, 82' LT | BFOC | Conflict with drainage culvert | Y
31 | Centurylink | 2100+80, 81' LT | BFOC | Conflict with drainage culvert | Y
32 | Centurylink | 2101+10, 81' LT | BFOC | Conflict with drainage structure | Y
33 | Centurylink | 2101+10, 92' LT | BFOT | Conflict with drainage culvert | Y
34 | Centurylink | 2101+17, 79' LT | BFOC | In conflict with proposed drainage culvert | Y
35 | Unknown | 2101+20, 45' LT | BE | Conflict with drainage structure | Y
36 | Centurylink | 2101+20, 45' LT | BT | Conflict with drainage structure | Y
37 | Centurylink | 2101+50, 79' LT | BFOC | In conflict with proposed drainage structure | Y
38 | Centurylink | 2101+50, 74' LT | BFOC | In conflict with proposed drainage structure | Y
39 | Centurylink | 2102+04, 91' LT | BFOT | In conflict with proposed drainage ditch | Y
40 | Centurylink | 2102+04, 79' LT | BFOC | In conflict with proposed drainage ditch | Y
41 | Centurylink | 2102+04, 73' LT | BFOC | In conflict with proposed drainage ditch | Y
42 | Summit | 2102+04, 70' LT | BFOC | In conflict with proposed drainage ditch | Y
43 | Immokalee | 2102+04, 65' LT | SS | In conflict with proposed drainage ditch | Y
44 | Teco | 2102+04, 56' LT | Gas Main | In conflict with proposed drainage ditch | Y
45 | Centurylink | 2102+04, 43' LT | BT | In conflict with proposed drainage ditch | Y
46 | Centurylink | 2102+04, 40' LT | BT | In conflict with proposed drainage ditch | Y
47 | Centurylink | 2103+37, 42' LT | BT | In conflict with proposed drainage inlet | Y
48 | Centurylink | 2103+37, 38' LT | BT | In conflict with proposed drainage inlet | Y
49 | Centurylink | 2103+80, 40' LT | BT | Conflict with drainage culvert | Y
50 | Centurylink | 2104+02, 93' LT | BFOT | In conflict with proposed drainage ditch | Y
51 | Centurylink | 2104+02, 79' LT | BFOC | In conflict with proposed drainage ditch | Y
52 | Centurylink | 2104+02, 73' LT | BFOC | In conflict with proposed drainage ditch | Y
53 | Summit | 2104+02, 67' LT | BFOC | In conflict with proposed drainage ditch | Y
54 | Immokalee | 2104+02, 64' LT | SS | In conflict with proposed drainage ditch | Y
55 | Teco | 2104+02, 55' LT | 8" Gas Main | In conflict with proposed drainage ditch | Y
56 | Centurylink | 2104+02, 42' LT | BT | In conflict with proposed drainage ditch | Y
57 | Centurylink | 2104+02, 39' LT | BT | In conflict with proposed drainage ditch | Y
58 | Teco | 2104+79, 54' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y |  | vertically adjust
59 | Summit | 2106+20, 54' LT | BFOC | In conflict with proposed drainage culvert | Y
60 | Teco | 2106+00, 63' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y
61 | Exploratory | 2106+50, 60' LT | Multipole sign | Possible conflict with signage - Exploratory | Y
62 | Centurylink | 2107+07, 40' LT | BT | Conflict with drainage culvert | Y
63 | Centurylink | 2107+07, 42' LT | BT | Conflict with drainage culvert | Y
64 | Summit | 2107+07, 58' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
65 | Teco | 2107+07, 53' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y |  | relocate/adjust
66 | Summit | 2108+52, 57' LT | BFOC | In conflict with proposed drainage culvert | Y
67 | Centurylink | 2108+52, 69' LT | BFOC | In conflict with proposed drainage culvert | Y
68 | Summit | 2110+08, 60' LT | BFOC | Conflict with drainage structure | Y
69 | Centurylink | 2110+08, 71' LT | BFOC | Conflict with drainage structure | Y
70 | Summit | 2110+80, 61' LT | BFOC | Conflict with drainage structure | Y
71 | Centurylink | 2110+80, 80' LT | BFOC | Conflict with drainage structure | Y
72 | Centurylink | 2111+80, 63' LT | BFOC | Conflict with drainage culvert | Y
73 | Calumet | 2112+62, 93' RT | GM | Conflict with drainage structure | Y
74 | Summit | 2112+92, 64' LT | BFOC | In conflict with proposed drainage culvert | Y
75 | Summit | 2114+04, 64' LT | BFOC | In conflict with proposed drainage culvert | Y
76 | Centurylink | 2114+15, 92' LT | BT | Possible conflict due to construction of side drain | Y
77 | Calumet | 2113+06, 93' RT | GM | Conflict with drainage structure | Y
78 | Calumet | 2114+22, 92' RT | GM | Conflict with drainage structure | Y
79 | Centurylink | 2114+60, 92' LT | BT | Possible conflict due to construction of side drain | Y
80 | Centurylink | 2114+90, 92' LT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
81 | Centurylink | 2114+90, 80' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
82 | Centurylink | 2114+90, 77' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
83 | Summit | 2114+90, 63' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
84 | Calumet | 2128+38, 90' RT | GM | Conflict with drainage structure | Y
85 | Centurylink | 2129+00, 30' RT | BT | In conflict with proposed drainage pond | Y
86 | Centurylink | 2129+00, 35' RT | BT | In conflict with proposed drainage pond | Y
87 | Centurylink | 2131+00, 28' RT | BT | In conflict with proposed drainage pond | Y
88 | Centurylink | 2131+00, 35' RT | BT | In conflict with proposed drainage pond | Y
89 | Centurylink | 2133+20, 63' LT | BFOC | Possible conflict due to construction of drainage structure | Y
90 | Centurylink | 2133+20, 61' LT | BT | Possible conflict due to construction of drainage structure | Y
91 | Centurylink | 2133+20, 23' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
92 | Teco | 2133+20, 21' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y |  | relocate/adjust
93 | Centurylink | 2133+20, 14' RT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
94 | Centurylink | 2133+20, 38' RT | BT | Possible conflict due to construction of drainage structure | Y
95 | Centurylink | 2135+00, 29' RT | BT | In conflict with proposed drainage pond | Y
96 | Centurylink | 2135+00, 35' RT | BT | In conflict with proposed drainage pond | Y
97 | Calumet | 2135+95, 103' RT | GM | Conflict with drainage structure | Y
98 | Calumet | 2139+63, 91' RT | GM | Conflict with drainage structure | Y
99 | Calumet | 2140+09, 91' RT | GM | Conflict with drainage structure | Y
100 | Centurylink | 2170+71, 93' LT | BT | In conflict with proposed side drain | Y |  | relocate/adjust
101 | Centurylink | 2170+83, 91' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
102 | Centurylink | 2171+12, 91' LT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
103 | Centurylink | 2173+00, 72' LT | BFOC | Possible conflict due to construction of drainage structure | Y
104 | Summit | 2173+00, 61' LT | BFOC | Conflict with drainage structure | Y
105 | Summit | 2174+00, 60' LT | GM | Conflict with drainage structure | Y
106 | Centurylink | 2174+00, 70' LT | GM | Conflict with drainage structure | Y
107 | Summit | 2175+03, 48' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
108 | Teco | 2175+03, 27' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y |  | relocate/adjust
109 | Centurylink | 2175+03, 15' RT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
110 | Centurylink | 2175+03, 35' RT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
111 | Centurylink | 2175+03, 79' LT | BT | Conflict with drainage culvert | Y
112 | Centurylink | 2175+03, 68' LT | BFOC | Conflict with drainage culvert | Y
113 | Calumet | 2175+03, 87' RT | GM | In conflict with proposed drainage culvert | Y
114 | Centurylink | 2178+07, 93' LT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
115 | Centurylink | 2178+07, 83' LT | BT | In conflict with proposed drainage culvert | Y
116 | Centurylink | 2178+13, 93' LT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
117 | Centurylink | 2178+47, 92' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
118 | LCEC | 2178+52, 92' LT | BE | In conflict with proposed drainage culvert | Y |  | relocate/adjust
119 | Centurylink | 2178+53, 83' LT | BT | Possible conflict due to construction of drainage structure | Y
120 | Centurylink | 2178+58, 92' LT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
121 | Teco | 2179+99, 26' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y |  | relocate/adjust
122 | Centurylink | 2179+99, 29' RT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
123 | Centurylink | 2179+99, 36' RT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
124 | Centurylink | 2180+00, 68' LT | BFOC | Possible conflict due to construction of drainage structure | Y
125 | Calumet | 2180+00, 88' RT | GM | Conflict with drainage structure | Y
126 | Centurylink | 2188+00, 69' LT | BFOC | Possible conflict due to construction of drainage structure | Y
127 | Summit | 2188+65, 80' LT | BFOC | Possible conflict due to construction of drainage structure | Y
128 | Centurylink | 2188+70, 87' LT | BT | Conflict with side drain | Y
129 | Centurylink | 2188+74, 68' LT | BFOC | Possible conflict due to construction of drainage structure | Y
130 | Summit | 2189+24, 79' LT | BFOC | Possible conflict due to construction of drainage structure | Y
131 | Centurylink | 2189+31, 86' LT | BT | In conflict with proposed drainage structure | Y |  | relocate/adjust
132 | Centurylink | 2199+00, 70' LT | BT | Possible conflict due to construction of drainage structure | Y
133 | Centurylink | 2199+56, 89' LT | BT | Possible conflict due to construction of drainage structure | Y
134 | Centurylink | 2200+12, 92' LT | BT | Possible conflict due to construction of drainage structure | Y
135 | Centurylink | 2200+75, 66' LT | BT | Possible conflict due to construction of drainage structure | Y
136 | Centurylink | 2202+54, 66' LT | BT | Possible conflict due to construction of drainage structure | Y
137 | Centurylink | 2202+84, 66' LT | BT | Possible conflict due to construction of drainage structure | Y
138 | Centurylink | 2202+86, 60' LT | BT | In conflict with proposed drainage structure | Y |  | relocate/adjust
139 | Centurylink | 2212+40, 54' LT | BT | Possible conflict due to construction of drainage structure | Y
140 | Summit | 2212+40, 63' LT | BFOC | Conflict with drainage structure | Y
141 | Summit | 2212+99, 62' LT | BFOC | In shared use path and proposed drainage culvert | Y |  | relocate/adjust
142 | Summit | 2213+05, 53' LT | BFOC | Possible conflict due to construction of drainage structure | Y
143 | Summit | 2215+20, 64' LT | BFOC | Conflict with drainage structure | Y
144 | Centurylink | 2215+20, 52' LT | BT | Conflict with drainage structure | Y
145 | Summit | 2217+05, 64' LT | BFOC | In conflict with proposed drainage culvert | Y
146 | Centurylink | 2217+05, 51' LT | BT | In conflict with proposed drainage culvert | Y
147 | Summit | 2218+00, 64' LT | BFOC | Conflict with drainage structure | Y
148 | Centurylink | 2218+00, 50' LT | BT | Conflict with drainage structure | Y
149 | Centurylink | 2118+96, 51' LT | BT | In conflict with proposed drainage culvert | Y
150 | Centurylink | 2118+96, 48' LT | BT | In conflict with proposed drainage culvert | Y
151 | Centurylink | 2219+43, 42' LT | BT | In conflict with proposed drainage culvert | Y
152 | Centurylink | 2219+43, 43' LT | BT | In conflict with proposed drainage culvert | Y
153 | Centurylink | 2219+43, 41' LT | BFOC | In conflict with proposed drainage culvert | Y
154 | Summit | 2219+44, 59' LT | BFOC | In conflict with proposed drainage culvert | Y
155 | Summit | 2219+84, 49' LT | BFOC | In conflict with proposed drainage culvert | Y
156 | Centurylink | 2219+84, 42' LT | BT | In conflict with proposed drainage culvert | Y
157 | Summit | 2221+00, 47' LT | BFOC | In conflict with proposed drainage culvert | Y
158 | Centurylink | 2221+00, 40' LT | BT | In conflict with proposed drainage culvert | Y
159 | Centurylink | 2221+70, 92' RT | BFOC | Conflict with drainage culvert | Y
160 | Crown Castle | 2222+08, 58' LT | BFOC | In shared use path and proposed guardrail | Y |  | relocate/adjust
161 | Crown Castle | 2222+28, 71' RT | BFOC | In shared use path and proposed drainage culvert | Y |  | relocate/adjust
162 | Summit | 2222+62, 42' LT | BFOC | In conflict with proposed drainage structure | Y
163 | Centurylink | 2222+62, 39' LT | BT | In conflict with proposed drainage structure | Y
164 | Summit | 2223+91, 44' LT | BFOC | In conflict with proposed drainage structure | Y
165 | Centurylink | 2223+91, 42' LT | BT | In conflict with proposed drainage structure | Y
166 | Summit | 2225+20, 44' LT | BFOC | In conflict with proposed drainage structure | Y
167 | Centurylink | 2225+20, 42' LT | BT | In conflict with proposed drainage structure | Y
168 | Summit | 2226+56, 46' LT | BFOC | In conflict with proposed drainage structure | Y
169 | Centurylink | 2226+56, 43' LT | BT | In conflict with proposed drainage structure | Y
170 | Summit | 2227+92, 44' LT | BFOC | In conflict with proposed drainage structure | Y
171 | Centurylink | 2227+92, 42' LT | BT | In conflict with proposed drainage structure | Y
172 | Summit | 2229+28, 41' LT | BFOC | In conflict with proposed drainage structure | Y
173 | Centurylink | 2229+28, 39' LT | BT | In conflict with proposed drainage structure | Y
174 | Summit | 2230+60, 40' LT | BFOC | In conflict with proposed drainage structure | Y
175 | Centurylink | 2230+60, 38' LT | BT | In conflict with proposed drainage structure | Y
176 | Summit | 2232+01, 39' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
177 | Centurylink | 2232+01, 37' LT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
178 | Centurylink | 2232+01, 36' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
179 | Centurylink | 2232+01, 33' LT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
180 | Teco | 2232+01, 32' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y |  | relocate/adjust
181 | Centurylink | 2232+01, 29' LT | BFOC | In conflict with proposed drainage culvert | Y |  | relocate/adjust
182 | Centurylink | 2232+01, 24' LT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
183 | Centurylink | 2232+01, 29' RT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
184 | Centurylink | 2232+01, 35' RT | BT | In conflict with proposed drainage culvert | Y |  | relocate/adjust
185 | Summit | 2233+18, 40' LT | BFOC | In proposed shoulders | Y |  | relocate/adjust
186 | Centurylink | 2233+18, 38' LT | BT | In proposed shoulders | Y |  | relocate/adjust
187 | Centurylink | 2235+00, 64' LT | BFOC | In conflict with proposed drainage ditch | Y
188 | Centurylink | 2235+98, 96' RT | BT | In conflict with proposed drainage ditch | Y
189 | Centurylink | 2235+98, 99' RT | BFOC | In conflict with proposed drainage ditch | Y
190 | Calumet | 2236+00, 87' RT | GM | In conflict with proposed drainage ditch | Y
191 | Centurylink | 2236+00, 89' RT | BT | In conflict with proposed drainage ditch | Y
192 | Centurylink | 2236+00, 93' RT | BFOC | In conflict with proposed drainage ditch | Y
193 | Summit | 2237+00, 67' LT | BFOC | In conflict with proposed drainage ditch | Y |  | relocate/adjust
194 | Calumet | 2238+00, 87' RT | GM | In conflict with proposed drainage ditch | Y
195 | Centurylink | 2238+00, 89' RT | BT | In conflict with proposed drainage ditch | Y
196 | Centurylink | 2238+00, 93' RT | BFOC | In conflict with proposed drainage ditch | Y
197 | Summit | 2239+00, 68' LT | BFOC | In conflict with proposed drainage ditch | Y
198 | Calumet | 2240+11, 88' RT | GM | Possible conflict due to construction of cross drain | Y
199 | Centurylink | 2240+11, 90' RT | BT | Possible conflict due to construction of cross drain | Y
200 | Centurylink | 2240+11, 94' RT | BFOT | Possible conflict due to construction of cross drain | Y
201 | Summit | 2241+00, 70' LT | BFOC | In conflict with proposed drainage ditch | Y
202 | Calumet | 2242+00, 87' RT | GM | In conflict with proposed drainage ditch | Y
203 | Centurylink | 2242+00, 89' RT | BT | In conflict with proposed drainage ditch | Y
204 | Centurylink | 2242+00, 93' RT | BFOC | In conflict with proposed drainage ditch | Y
205 | Summit | 2243+00, 72' LT | BFOC | In conflict with proposed drainage ditch | Y
206 | Calumet | 2244+00, 84' RT | GM | In conflict with proposed drainage ditch | Y
207 | Centurylink | 2244+00, 84' RT | BT | In conflict with proposed drainage ditch | Y
208 | Centurylink | 2244+00, 88' RT | BFOC | In conflict with proposed drainage ditch | Y
209 | Summit | 2245+00, 73' LT | BFOC | In conflict with proposed drainage ditch | Y
210 | Centurylink | 2246+00, 83' RT | BT | In conflict with proposed drainage ditch | Y
211 | Centurylink | 2246+00, 87' RT | BFOC | In conflict with proposed drainage ditch | Y
212 | Calumet | 2246+00, 87' RT | GM | In conflict with proposed drainage ditch | Y
213 | Centurylink | 2246+98, 56' LT | BT | In conflict with proposed guardrail | Y |  | relocate/adjust
214 | Summit | 2247+00, 74' LT | BFOC | In conflict with proposed drainage ditch | Y
215 | Centurylink | 2247+51, 58' LT | BT | In conflict with proposed guardrail | Y |  | relocate/adjust
216 | Centurylink | 2247+52, 59' LT | BT | In conflict with proposed guardrail | Y |  | relocate/adjust
217 | Centurylink | 2247+52, 58' LT | BFOT | In conflict with proposed guardrail | Y |  | relocate/adjust
218 | Centurylink | 2248+00, 84' RT | BFOT | In conflict with proposed drainage ditch | Y
219 | Centurylink | 2248+00, 81' RT | BT | In conflict with proposed drainage ditch | Y
220 | Calumet | 2248+00, 82' RT | GM | In conflict with proposed drainage ditch | Y
221 | Summit | 2249+00, 74' LT | BFOC | In conflict with proposed drainage ditch | Y
222 | Exploratory | 2249+12, 78' LT | Multipole sign | Possible conflict with signage - Exploratory | Y
223 | Centurylink | 2250+00, 77' RT | BT | In conflict with proposed drainage ditch | Y
224 | Centurylink | 2250+00, 82' RT | BFOT | In conflict with proposed drainage ditch | Y
225 | Calumet | 2250+00, 84' RT | GM | In conflict with proposed drainage ditch | Y
226 | Summit | 2251+00, 73' LT | BFOC | In conflict with proposed drainage ditch | Y
227 | Centurylink | 2252+00, 77' RT | BT | In conflict with proposed drainage ditch | Y
228 | Centurylink | 2252+00, 82' RT | BFOC | In conflict with proposed drainage ditch | Y
229 | Calumet | 2252+00, 84' RT | GM | In conflict with proposed drainage ditch | Y
230 | Summit | 2253+00, 74' LT | BFOC | In conflict with proposed drainage ditch | Y
231 | Centurylink | 2254+00, 77' RT | BT | In conflict with proposed drainage ditch | Y
232 | Centurylink | 2254+00, 82' RT | BFOT | In conflict with proposed drainage ditch | Y
233 | Calumet | 2254+00, 84' RT | GM | In conflict with proposed drainage ditch | Y
234 | Summit | 2255+00, 73' LT | BFOC | In conflict with proposed drainage ditch | Y
235 | Centurylink | 2256+00, 76' RT | BT | Conflict with cross drain | Y
236 | Centurylink | 2256+00, 82' RT | BFOT | Conflict with cross drain | Y
237 | Calumet | 2256+00, 84' RT | GM | Conflict with cross drain | Y
238 | Summit | 2257+00, 73' LT | BFOC | In conflict with proposed drainage ditch | Y
239 | Centurylink | 2257+22, 77' RT | BT | Possible conflict due to construction of cross drain | Y
240 | Centurylink | 2257+22, 83' RT | BFOT | Possible conflict due to construction of cross drain | Y
241 | Calumet | 2257+22, 85' RT | GM | Possible conflict due to construction of cross drain | Y
242 | Immokalee | 191+87, 40' RT | Sanitary Sewer | In proposed sidewalk | Y |  | relocate/adjust
243 | Calumet | 191+98, 42' RT | GM | In proposed sidewalk | Y
244 | Teco | 2097+00, 55' LT | 8" Gas Main | In proposed sidewalk | Y
245 | Teco | 2109+50, 51' LT | 8" Gas Main | Possible conflict with roadway items | Y
246 | Teco | 2110+08, 52' LT | 8" Gas Main | Possible conflict with roadway items | Y
247 | Teco | 2110+80, 52' LT | 8" Gas Main | Possible conflict with roadway items | Y
248 | Teco | 2111+80, 50' LT | 8" Gas Main | Possible conflict with roadway items | Y
249 | Teco | 2114+00, 48' LT | 8" Gas Main | Possible conflict with roadway items | Y
250 | Teco | 2117+89, 49' LT | 8" Gas Main | Possible conflict with roadway items | Y
251 | Teco | 2173+00, 31' LT | 8" Gas Main | Possible conflict with roadway items | Y
252 | Teco | 2174+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y
253 | Teco | 2177+50, 26' LT | 8" Gas Main | Possible conflict with roadway items | Y
254 | Teco | 2188+00, 26' LT | 8" Gas Main | Possible conflict with roadway items | Y
255 | Teco | 2188+74, 26' LT | 8" Gas Main | Possible conflict with roadway items | Y
256 | Teco | 2199+00, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y
257 | Teco | 2200+65, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y
258 | Teco | 2202+87, 35' LT | 8" Gas Main | Possible conflict with roadway items | Y
259 | Teco | 2212+40, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y
260 | Teco | 2212+88, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y
261 | Teco | 2215+25, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y
262 | Teco | 2217+00, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y
263 | Teco | 2218+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y
264 | Teco | 2219+28, 35' LT | 8" Gas Main | Possible conflict with roadway items | Y
265 | Teco | 2219+82, 36' LT | 8" Gas Main | Possible conflict with roadway items | Y
266 | Teco | 2220+00, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y
267 | Teco | 2222+00, 39' LT | 8" Gas Main | Possible conflict with roadway items | Y
268 | Teco | 2224+00, 38' LT | 8" Gas Main | Possible conflict with roadway items | Y
269 | Teco | 2225+20, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y
270 | Teco | 2226+58, 39' LT | 8" Gas Main | Possible conflict with roadway items | Y
271 | Centurylink | 2226+58, 40' LT | BT | Possible conflict with roadway items | Y
272 | Teco | 2228+00, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y
273 | Teco | 2229+30, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y
274 | Teco | 2230+65, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y
275 | Teco | 2233+40, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y
276 | Teco | 2235+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y
277 | Teco | 2237+00, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y
278 | Teco | 2239+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y
279 | Teco | 2241+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y
280 | Teco | 2243+00, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y
281 | Teco | 2245+00, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y
282 | Teco | 2247+00, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y
283 | Teco | 2249+00, 35' LT | 8" Gas Main | Possible conflict with roadway items | Y
284 | Teco | 2251+00, 36' LT | 8" Gas Main | Possible conflict with roadway items | Y
285 | Teco | 2253+00, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y
286 | Teco | 2255+00, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y
287 | Teco | 2257+00, 39' LT | 8" Gas Main | Possible conflict with roadway items | Y

## Conflict Matrix
FPID: | 417540-6-52-01 | Description: | SR 29 |  | This matrix was created by Faller, Davis & Associates to assist the UAO's in identifying conflicts between the UAO's facilities and proposed roadway construction. Faller, Davis & Associates accepts no liability for conflicts overlooked for this report. Each UAO or designee is responsible to perform a detailed and comprehensive plans review for conflict analysis.
Phase #: | IIIR | Plans Date: | 2025-12-10
Preparer: | James Thorpe
Date: | 2025-12-10
Conflict # | Utility Agency/ Owner (UAO) | Station/Offset | Facility Description (Material, Type, Number, Size) | Conflict Description (Possible or Actual) | VVH (Y/N) | Test Hole VVH # | Suggested Conflict Resolution | Resolved Status
LP1 |  | 2086+17, 46' LT, |  | Light Pole 1 - Exploratory | Y | LP-1 | Design change/No Conflict
LP2 |  | 2087+53, 45' RT. |  | Light Pole 2 - Exploratory | Y | LP-2 | Design change/No Conflict
LP3 |  | 2089+15, 51' LT. |  | Light Pole 3 - Exploratory | Y | LP-3 | Design change/No Conflict
LP4 |  | 2090+82, 47' RT. |  | Light Pole 4 - Exploratory | Y | LP-4 | Design change/No Conflict
LP5 |  | 2092+43, 58' LT. |  | Light Pole 5 - Exploratory | Y | LP-5 | Design change/No Conflict
LP6 |  | 2094+50, 69' RT. |  | Light Pole 6 - Exploratory | Y | LP-6 | Design change/No Conflict
LP7 |  | 2094+50, 69' LT. |  | Light Pole 7 - Exploratory | Y | LP-7 | Design change/No Conflict
LP8 |  | 2096+55, 62' RT. |  | Light Pole 8 - Exploratory | Y | LP-8 | Design change/No Conflict
LP9 |  | 2096+58, 60' LT. |  | Light Pole 9 - Exploratory | Y | LP-9 | Design change/No Conflict
LP10 |  | 2098+74, 85' RT. |  | Light Pole 10 - Exploratory | Y | LP-10 | Design change/No Conflict
LP11 |  | 2098+77, 49' LT. |  | Light Pole 11 - Exploratory | Y | LP-11 | Design change/No Conflict
LP12 |  | 2099+73, 136' RT. |  | Light Pole 12 - Exploratory | Y | LP-12 | Design change/No Conflict
LP13 |  | 2099+99, 62' LT. |  | Light Pole 13 - Exploratory | Y | LP-13 | Design change/No Conflict
LP14 |  | 2101+46, 129' RT. |  | Light Pole 14 - Exploratory | Y | LP-14 | Design change/No Conflict
LP15 |  | 2101+30, 61' LT. |  | Light Pole 15 - Exploratory | Y | LP-15 | Design change/No Conflict
LP16 |  | 2102+89, 75' RT. |  | Light Pole 16 - Exploratory | Y | LP-16 | Design change/No Conflict
LP17 |  | 2102+61, 31' LT. |  | Light Pole 17 - Exploratory | Y | LP-17 | Design change/No Conflict
LP18 |  | 2105+27, 72' RT. |  | Light Pole 18 - Exploratory | Y | LP-18 | Design change/No Conflict
LP19 |  | 2105+29, 66' LT. |  | Light Pole 19 - Exploratory | Y | LP-19 | Design change/No Conflict
LP20 |  | 802+66, 46' LT. |  | Light Pole 20 - Exploratory | Y | LP-20 | Design change/No Conflict
LP21 |  | 2100+90, 172' LT. |  | Light Pole 21 - Exploratory | Y | LP-21 | Design change/No Conflict
LP22 |  | 401+47, 41' LT. |  | Light Pole 22 - Exploratory | Y | LP-22 | Design change/No Conflict
LP23 |  | 403+01, 38' RT. |  | Light Pole 23 - Exploratory | Y | LP-23 | Design change/No Conflict
LP98 |  | 2234+55, 72' RT. |  | Light Pole 98 - Exploratory | Y | LP-98 | Design change/No Conflict
LP99 |  | 2235+75, 69' LT. |  | Light Pole 99 - Exploratory | Y | LP-99 | Design change/No Conflict
LP100 |  | 2236+95, 72' RT. |  | Light Pole 100 - Exploratory | Y | LP-100 | Design change/No Conflict
LP111 |  | 2238+15, 70' LT. |  | Light Pole 111 - Exploratory | Y | LP-111 | Design change/No Conflict
LP113 |  | 2240+55, 73' LT. |  | Light Pole 113 - Exploratory | Y | LP-113 | Design change/No Conflict
LP114 |  | 2239+35, 72' RT. |  | Light Pole 114 - Exploratory | Y | LP-114 | Design change/No Conflict
LP115 |  | 2242+95, 76' LT. |  | Light Pole 115 - Exploratory | Y | LP-115 | Design change/No Conflict
LP116 |  | 2241+75, 72' RT. |  | Light Pole 116 - Exploratory | Y | LP-116 | Design change/No Conflict
LP117 |  | 2245+35, 77' LT. |  | Light Pole 117 - Exploratory | Y | LP-117 | Design change/No Conflict
LP118 |  | 2244+15, 74' RT. |  | Light Pole 118 - Exploratory | Y | LP-118 | Design change/No Conflict
LP119 |  | 2247+75, 76' LT. |  | Light Pole 119 - Exploratory | Y | LP-119 | Design change/No Conflict
LP120 |  | 2246+55, 74' RT. |  | Light Pole 120 - Exploratory | Y | LP-120 | Design change/No Conflict
LP121 |  | 2250+15, 77' LT. |  | Light Pole 121 - Exploratory | Y | LP-121 | Design change/No Conflict
LP122 |  | 2248+95, 74' RT. |  | Light Pole 122 - Exploratory | Y | LP-122 | Design change/No Conflict
LP123 |  | 2252+55, 77' LT. |  | Light Pole 123 - Exploratory | Y | LP-123 | Design change/No Conflict
LP124 |  | 2251+35, 74' RT. |  | Light Pole 124 - Exploratory | Y | LP-124 | Design change/No Conflict
LP125 |  | 2254+95, 77' LT. |  | Light Pole 125 - Exploratory | Y | LP-125 | Design change/No Conflict
LP126 |  | 2253+75, 75' RT. |  | Light Pole 126 - Exploratory | Y | LP-126 | Design change/No Conflict
LP 127 |  | 2257+35, 73' LT. | 8" Steel Gas Main | Light Pole 127 - gas line is shown in ORD but VVHs are all three exploratory to 8'. (Our foundation will be 10.5' deep here.) | N | LP-127
LP128 |  | 2256+15, 74' RT. |  | Light Pole 128 - Exploratory | Y | LP-128 | Design change/No Conflict
1 | Comcast | 2086+92, 30' LT | BTV | In proposed sidewalk and proposed paved shoulder | Y | 1-1A | No conflict/Design change
2 | Immokalee | 2088+34, 87' LT | Water Main | In conflict with proposed side drain | Y | 1-2A | No conflict/design change
3 | Summit | 2088+38, 83' LT | BFOC | Possible conflict due to construction of side drain | Y | 1-3A | No conflict/design change
4 | Centurylink | 2088+38, 95' LT | BFOT | Possible conflict due to construction of side drain | Y | 1-4A | No conflict/design change
5 | Summit | 2088+70, 84' LT | BFOC | Possible conflict due to construction of side drain | Y | 1-5A | No conflict/design change
6 | Immokalee | 2088+70, 87' LT | Water Main | In conflict with proposed side drain | Y | 1-6A | No conflict/design change
7 | Centurylink | 2088+70, 94' LT | BFOT | Possible conflict due to construction of side drain | Y | 1-7A | No conflict/design change
8 | Exploratory | 2094+00, 65' RT | Multipole sign | Possible conflict with signage - Exploratory | Y |  | No conflict/Design change
9 | Immokalee | 2094+15, 86' LT | WM | Possible conflict due to construction of side drain | Y | 1-9A | No conflict/design change
10 | Centurylink | 2094+15, 92' LT | BFOT | Possible conflict due to construction of side drain | Y | 1-10A | No conflict/design change
11 | Immokalee | 2094+55, 85' LT | WM | Possible conflict due to construction of side drain | Y | 1-11A | No conflict/design change
12 | Centurylink | 2094+55, 92' LT | BFOT | Possible conflict due to construction of side drain | Y | 1-12A | No conflict/design change
13 | Immokalee | 2095+23, 45' LT | Water Main | In proposed sidewalk, proposed paved shoulder, and proposed widening | Y | 1-13A | No conflict/Design change
14 | Immokalee | 2095+23, 50' RT | Water Main | In proposed sidewalk, proposed paved shoulder, and proposed widening | Y | 1-14A | No conflict/Design change
15 | Centurylink | 2097+10, 93' LT | BFOT | In conflict with proposed drainage ditch | Y | 1-15A | No conflict/design change
16 | Centurylink | 2097+10, 80' LT | BFOT | In conflict with proposed drainage ditch | Y | 1-16A | No conflict/design change
17 | Summit | 2097+10, 78' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-17A | No conflict/design change
18 | Centurylink | 2097+10, 74' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-18A | No conflict/design change
19 | Immokalee | 2097+10, 71' LT | SS | In conflict with proposed drainage ditch | Y | 1-19A | No conflict/design change
20 | Centurylink | 2099+05, 94' LT | BFOT | In conflict with proposed drainage ditch | Y | 1-20A | No conflict/design change
21 | Centurylink | 2099+05, 79' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-21A | No conflict/design change
22 | Centurylink | 2099+05, 78' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-22A | No conflict/design change
23 | Summit | 2099+05, 75' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-23A | No conflict/design change
24 | Immokalee | 2099+05, 72' LT | SS | In conflict with proposed drainage ditch | Y | 1-24A | No conflict/design change
25 | TECO Peoples Gas | 2099+05, 64' LT | 8" Gas Main | In conflict with proposed drainage ditch | Y | 1-25A | No conflict/design change
26 | Centurylink | 2099+05, 56' LT | BT | In conflict with proposed drainage ditch | Y | 1-26A | No conflict/design change
27 | Centurylink | 2099+05, 44' LT | BT | In conflict with proposed drainage ditch | Y | 1-27A | No conflict/design change
28 | Centurylink | 2099+98, 79' LT | BFOC | In conflict with proposed drainage structure | y | 1-28A | No conflict/design change
29 | Centurylink | 2100+80, 40' LT | BT | Conflict with drainage culvert | Y | 1-29A | No conflict/design change
30 | Centurylink | 2100+80, 82' LT | BT | Conflict with drainage culvert | Y | 1-31 | To be removed
31 | Centurylink | 2100+80, 81' LT | BT | Conflict with drainage culvert | Y | 1-31A | To be removed
32 | Centurylink | 2101+10, 81' LT | BT | Conflict with drainage structure | Y | 1-32 | To be removed
33 | Centurylink | 2101+10, 92' LT | BFOT | Conflict with drainage culvert | Y | 1-33 | To be removed
34 | Centurylink | 2101+17, 79' LT | BT | In conflict with proposed drainage culvert | Y | 1-34 | To be removed
35 | LCEC | 2101+20, 45' LT | BE | Conflict with drainage structure | Y | 1-35 | No conflict/design change
36 | Centurylink | 2101+20, 45' LT | BT | Conflict with drainage structure | Y | 1-36 | To be removed
37 | Centurylink | 2101+50, 79' LT | BT | In conflict with proposed drainage structure | Y | 1-37 | No conflict/design change
38 | Centurylink | 2101+50, 74' LT | BFOC | In conflict with proposed drainage structure | Y | 1-38 | No conflict/design change
39 | Centurylink | 2102+04, 91' LT | BFOT | In conflict with proposed drainage ditch | Y | 1-39 | No conflict/design change
40 | Centurylink | 2102+04, 79' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-40 | No conflict/design change
41 | Centurylink | 2102+04, 73' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-41 | No conflict/design change
42 | Summit | 2102+04, 70' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-42 | No conflict/design change
43 | Immokalee | 2102+04, 65' LT | SS | In conflict with proposed drainage ditch | Y | 1-43 | No conflict/design change
44 | TECO Peoples Gas | 2102+04, 56' LT | Gas Main | In conflict with proposed drainage ditch | Y | 1-44 | No conflict/design change
45 | Centurylink | 2102+04, 43' LT | BT | In conflict with proposed drainage ditch | Y | 1-45 | No conflict/design change
46 | Centurylink | 2102+04, 40' LT | BT | In conflict with proposed drainage ditch | Y | 1-46 | No conflict/design change
47 | Centurylink | 2103+37, 42' LT | BT | In conflict with proposed drainage inlet | Y | 1-47 | No conflict/design change
48 | Centurylink | 2103+37, 38' LT | BT | In conflict with proposed drainage inlet | Y | 1-48 | No conflict/design change
49 | Centurylink | 2103+80, 40' LT | BT | Conflict with drainage culvert | Y | 1-49 | To be removed
50 | Centurylink | 2104+02, 93' LT | BFOT | In conflict with proposed drainage ditch | Y | 1-50 | No conflict/design change
51 | Centurylink | 2104+02, 79' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-51 | No conflict/design change
52 | Centurylink | 2104+02, 73' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-52 | No conflict/design change
53 | Summit | 2104+02, 67' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-53 | No conflict/design change
54 | Immokalee | 2104+02, 64' LT | SS | In conflict with proposed drainage ditch | Y | 1-54 | No conflict/design change
55 | TECO Peoples Gas | 2104+02, 55' LT | 8" Gas Main | In conflict with proposed drainage ditch | Y | 1-55 | No conflict/design change
56 | Centurylink | 2104+02, 42' LT | BT | In conflict with proposed drainage ditch | Y | 1-56 | No conflict/design change
57 | Centurylink | 2104+02, 39' LT | BT | In conflict with proposed drainage ditch/drainage culvert | Y | 1-57 | To be removed
58 | TECO Peoples Gas | 2104+79, 54' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y | 1-58 | Protect in Place
59 | Summit | 2106+20, 54' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-59 | No conflict/design change
60 | TECO Peoples Gas | 2106+00, 63' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y | 1-60 | No conflict/design change
61 | Exploratory | 2106+50, 60' LT | Multipole sign | Possible conflict with signage - Exploratory | Y |  | No conflict/design change
62 | Centurylink | 2107+07, 40' LT | BT | Conflict with drainage culvert | Y | 1-62 | No conflict/design change
63 | Centurylink | 2107+07, 42' LT | BT | Conflict with drainage culvert | Y | 1-63 | To be removed
64 | Summit | 2107+07, 58' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-64 | No conflict/design change
65 | TECO Peoples Gas | 2107+07, 53' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y | 1-65 | Protect in Place
66 | Summit | 2108+52, 57' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-66 | No conflict/design change
67 | Centurylink | 2108+52, 69' LT | BT | In conflict with proposed drainage culvert | Y | 1-67 | No conflict/design change
68 | Summit | 2110+08, 60' LT | BFOC | Conflict with drainage structure | Y | 1-68 | No conflict/design change
69 | Centurylink | 2110+08, 71' LT | BFOC | Conflict with drainage structure | Y | 1-69 | No conflict/design change
70 | Centurylink | 2110+80, 61' LT | BT | Conflict with drainage structure | Y | 1-70 | To be removed
71 | Centurylink | 2110+80, 80' LT | BT | Conflict with drainage structure | Y | 1-71 | No conflict/design change
72 | Centurylink | 2111+80, 63' LT | BT | Conflict with drainage culvert | Y | 1-72 | To be removed
73 | Calumet | 2112+62, 93' RT | PET | Conflict with drainage structure | Y | 1-73 | No conflict/design change
74 | Summit | 2112+92, 64' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-74 | Relocate/adjust
75 | Summit | 2114+04, 64' LT | BFOC | In conflict with proposed drainage structure | Y | 1-75 | Relocate/adjust
76 | Centurylink | 2114+15, 92' LT | BFOT | Possible conflict due to construction of side drain | Y | 1-76 | No conflict/design change
77 | Calumet | 2113+06, 93' RT | PET | Conflict with drainage structure | Y | 1-77 | No conflict/design change
78 | Calumet | 2114+22, 92' RT | PET | Conflict with drainage structure | Y | 1-78 | No conflict/design change
79 | Centurylink | 2114+60, 92' LT | BFOT | Possible conflict due to construction of side drain | Y | 1-79 | No conflict/design change
80 | Centurylink | 2114+90, 92' LT | BFOT | In conflict with proposed drainage culvert | Y | 1-80 | To be removed
81 | Centurylink | 2114+90, 80' LT | BT | In conflict with proposed drainage culvert | Y | 1-81 | To be removed
82 | Centurylink | 2114+90, 77' LT | BT | In conflict with proposed drainage culvert | Y | 1-82 | To be removed
83 | Summit | 2114+90, 63' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-83 | Relocate/adjust
84 | Calumet | 2128+38, 90' RT | PET | Conflict with drainage structure | Y | 1-84 | Relocate/adjust
85 | Centurylink | 2129+00, 30' RT | BT | In conflict with proposed drainage pond | Y | 1-85 | To be removed
86 | Centurylink | 2129+00, 35' RT | BT | In conflict with proposed drainage pond | Y | 1-86 | To be removed
87 | Centurylink | 2131+00, 28' RT | BT | In conflict with proposed drainage pond | Y | 1-87 | To be removed
88 | Centurylink | 2131+00, 35' RT | BT | In conflict with proposed drainage pond | Y | 1-88 | To be removed
89 | Centurylink | 2133+20, 63' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-89 | To be removed
90 | Centurylink | 2133+20, 61' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-90 | To be removed
91 | Centurylink | 2133+20, 23' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-91 | To be removed
92 | TECO Peoples Gas | 2133+20, 21' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y | 1-92 | Relocate/adjust
93 | Centurylink | 2133+20, 14' RT | BT | In conflict with proposed drainage culvert | Y | 1-93 | To be removed
94 | Centurylink | 2133+20, 38' RT | BT | Possible conflict due to construction of drainage structure | Y | 1-94 | To be removed
95 | Centurylink | 2135+00, 29' RT | BT | In conflict with proposed drainage pond | Y | 1-95 | To be removed
96 | Centurylink | 2135+00, 35' RT | BT | In conflict with proposed drainage pond | Y | 1-96 | To be removed
97 | Calumet | 2135+95, 103' RT | PET | In conflict with proposed drainage pond | Y | 1-97 | To be removed
98 | Calumet | 2139+63, 91' RT | PET | In conflict with proposed drainage culvert | Y | 1-98 | See FPID: 417540-5-52-01
99 | Calumet | 2140+09, 91' RT | PET | In conflict with proposed drainage culvert | Y | 1-99 | See FPID: 417540-5-52-01
100 | Centurylink | 2170+71, 93' LT | BFOT | In conflict with proposed side drain | Y | 1-100 | To be removed
101 | Centurylink | 2170+83, 91' LT | BFOC | In conflict with proposed side drain | Y | 1-101 | To be removed
102 | Centurylink | 2171+12, 91' LT | BT | In conflict with proposed side drain | Y | 1-102 | To be removed
103 | Centurylink | 2173+00, 72' LT | BFOC | Possible conflict due to construction of drainage structure | Y | 1-103 | Protect in Place
104 | Summit | 2173+00, 61' LT | BFOC | Conflict with drainage structure | Y | 1-104 | No conflict/design change
105 | Summit | 2174+00, 60' LT | BFOC | Conflict with drainage structure | Y | 1-105 | No conflict/design change
106 | Centurylink | 2174+00, 70' LT | BT | Conflict with drainage structure | Y | 1-106 | To be removed
107 | Summit | 2175+03, 48' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-107 | No conflict/design change
108 | TECO Peoples Gas | 2175+03, 27' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y | 1-108 | No conflict/design change
109 | Centurylink | 2175+03, 15' RT | BT | In conflict with proposed drainage culvert | Y | 1-109 | To be removed
110 | Centurylink | 2175+03, 35' RT | BT | In conflict with proposed drainage culvert | Y | 1-110 | To be removed
111 | Centurylink | 2175+03, 79' LT | BT | Conflict with drainage culvert | Y | 1-111 | To be removed
112 | Centurylink | 2175+03, 68' LT | BFOC | Conflict with drainage culvert | Y | 1-112 | To be removed
113 | Calumet | 2175+03, 87' RT | PET | In conflict with proposed drainage culvert | Y | 1-113 | No conflict/design change
114 | Centurylink | 2178+07, 93' LT | BFOT | In conflict with proposed drainage culvert | Y | 1-114 | To be removed
115 | Centurylink | 2178+07, 83' LT | BFOT | In conflict with proposed drainage culvert | Y | 1-115 | No conflict/design change
116 | Centurylink | 2178+13, 93' LT | BT | In conflict with proposed drainage culvert | Y | 1-116 | To be removed
117 | Centurylink | 2178+47, 92' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-117 | To be removed
118 | LCEC | 2178+52, 92' LT | BE | In conflict with proposed drainage culvert | Y | 1-118 | Relocate/adjust
119 | Centurylink | 2178+53, 83' LT | BFOT | Possible conflict due to construction of drainage structure | Y | 1-119 | To be removed
120 | Centurylink | 2178+58, 92' LT | BFOT | In conflict with proposed drainage culvert | Y | 1-120 | To be removed
121 | TECO Peoples Gas | 2179+99, 26' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y | 1-121 | Relocate/adjust
122 | Centurylink | 2179+99, 29' RT | BT | In conflict with proposed drainage culvert | Y | 1-122 | To be removed
123 | Centurylink | 2179+99, 36' RT | BT | In conflict with proposed drainage culvert | Y | 1-123 | To be removed
124 | Centurylink | 2180+00, 68' LT | BFOC | Possible conflict due to construction of drainage structure | Y | 1-124 | No conflict/design change
125 | Calumet | 2180+00, 88' RT | PET | Conflict with drainage structure | Y | 1-125 | Relocate/adjust
126 | Centurylink | 2188+00, 69' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-126 | No conflict/design change
127 | Summit | 2188+65, 80' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-127 | No conflict/design change
128 | Centurylink | 2188+70, 87' LT | BT | Conflict with side drain | Y | 1-128 | No conflict/design change
129 | Centurylink | 2188+74, 68' LT | BFOT | Possible conflict due to construction of drainage structure | Y | 1-129 | No conflict/design change
130 | Summit | 2189+24, 79' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-130 | No conflict/design change
131 | Centurylink | 2189+31, 86' LT | BT | In conflict with proposed drainage structure | Y | 1-131 | No conflict/design change
132 | Centurylink | 2199+00, 70' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-132 | No conflict/design change
133 | Centurylink | 2199+56, 89' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-133 | No conflict/design change
134 | Centurylink | 2200+12, 92' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-134 | No conflict/design change
135 | Centurylink | 2200+75, 66' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-135 | No conflict/design change
136 | Centurylink | 2202+54, 66' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-136 | To be removed
137 | Centurylink | 2202+84, 66' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-137 | To be removed
138 | Centurylink | 2202+86, 60' LT | BT | In conflict with proposed drainage structure | Y | 1-138 | To be removed
139 | Centurylink | 2212+40, 54' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-139 | No conflict/design change
140 | Centurylink | 2212+40, 63' LT | BFOT | Conflict with drainage culvert | Y | 1-140 | To be removed
141 | Centurylink | 2212+99, 62' LT | BFOT | In shared use path and proposed drainage culvert | Y | 1-141 | To be removed
142 | Summit | 2213+05, 53' LT | BT | Possible conflict due to construction of drainage structure | Y | 1-142 | No conflict/design change
143 | Summit | 2215+20, 64' LT | BFOC | Conflict with drainage structure | Y | 1-143 | No conflict/design change
144 | Centurylink | 2215+20, 52' LT | BT | Conflict with drainage structure | Y | 1-144 | No conflict/design change
145 | Summit | 2217+05, 64' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-145 | No conflict/design change
146 | Centurylink | 2217+05, 51' LT | BT | In conflict with proposed drainage culvert | Y | 1-146 | No conflict/design change
147 | Summit | 2218+00, 64' LT | BFOC | Conflict with drainage structure | Y | 1-147 | No conflict/design change
148 | Centurylink | 2218+00, 50' LT | BT | Conflict with drainage structure | Y | 1-148 | No conflict/design change
149 | Centurylink | 2118+96, 51' LT | BT | In conflict with proposed drainage culvert | Y | 1-149 | No conflict/design change
150 | Centurylink | 2118+96, 48' LT | BT | In conflict with proposed drainage culvert | Y | 1-150 | No conflict/design change
151 | Centurylink | 2219+43, 42' LT | BT | In conflict with proposed drainage culvert | Y | 1-151 | No conflict/design change
152 | Centurylink | 2219+43, 43' LT | BT | In conflict with proposed drainage culvert | Y | 1-152 | No conflict/design change
153 | Centurylink | 2219+43, 41' LT | BT | In conflict with proposed drainage culvert | Y | 1-153 | No conflict/design change
154 | Summit | 2219+44, 59' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-154 | No conflict/design change
155 | Summit | 2219+84, 49' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-155 | No conflict/design change
156 | Centurylink | 2219+84, 42' LT | BT | In conflict with proposed drainage culvert | Y | 1-156 | No conflict/design change
157 | Summit | 2221+00, 47' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-157 | No conflict/design change
158 | Centurylink | 2221+00, 40' LT | BT | In conflict with proposed drainage culvert | Y | 1-158 | No conflict/design change
159 | Centurylink | 2221+70, 92' RT | BFOC | Conflict with drainage culvert | Y | 1-159 | No conflict/design change
160 | Crown Castle | 2222+08, 58' LT | BFOC | In shared use path and proposed guardrail | Y | 1-160 | Relocate/adjust
161 | Crown Castle | 2222+28, 71' RT | BFOC | In shared use path and proposed drainage culvert | Y | 1-161 | No conflict/design change
162 | Summit | 2222+62, 42' LT | BFOC | In conflict with proposed drainage structure | Y | 1-162 | No conflict/design change
163 | Centurylink | 2222+62, 39' LT | BT | In conflict with proposed drainage structure | Y | 1-163 | No conflict/design change
164 | Summit | 2223+91, 44' LT | BFOC | In conflict with proposed drainage structure | Y | 1-164 | No conflict/design change
165 | Centurylink | 2223+91, 42' LT | BT | In conflict with proposed drainage structure | Y | 1-165 | No conflict/design change
166 | Summit | 2225+20, 44' LT | BFOC | In conflict with proposed drainage structure | Y | 1-166 | No conflict/design change
167 | Centurylink | 2225+20, 42' LT | BT | In conflict with proposed drainage structure | Y | 1-167 | To be removed
168 | Centurylink | 2226+56, 46' LT | BFOT | In conflict with proposed drainage structure | Y | 1-168 | To be removed
169 | Centurylink | 2226+56, 43' LT | BT | In conflict with proposed drainage structure | Y | 1-169 | To be removed
170 | Summit | 2227+92, 44' LT | BFOC | In conflict with proposed drainage structure | Y | 1-170 | No conflict/design change
171 | Centurylink | 2227+92, 42' LT | BT | In conflict with proposed drainage structure | Y | 1-171 | To be removed
172 | Summit | 2229+28, 41' LT | BFOC | In conflict with proposed drainage structure | Y | 1-172 | No conflict/design change
173 | Centurylink | 2229+28, 39' LT | BFOT | In conflict with proposed drainage structure | Y | 1-173 | To be removed
174 | Summit | 2230+60, 40' LT | BFOC | In conflict with proposed drainage structure | Y | 1-174 | No conflict/design change
175 | Centurylink | 2230+60, 38' LT | BT | In conflict with proposed drainage structure | Y | 1-175 | No conflict/design change
176 | Summit | 2232+01, 39' LT | BFOC | In conflict with proposed drainage culvert | Y | 1-176 | Relocate/adjust
177 | Centurylink | 2232+01, 37' LT | BFOT | In conflict with proposed drainage culvert | Y | 1-177 | To be removed
178 | Centurylink | 2232+01, 36' LT | BT | In conflict with proposed drainage culvert | Y | 1-178 | To be removed
179 | Centurylink | 2232+01, 33' LT | BT | In conflict with proposed drainage culvert | Y | 1-179 | To be removed
180 | TECO Peoples Gas | 2232+01, 32' LT | 8" Gas Main | In conflict with proposed drainage culvert | Y | 1-180 | Protect in Place
181 | Centurylink | 2232+01, 29' LT | BT | In conflict with proposed drainage culvert | Y | 1-181A | To be removed
182 | Centurylink | 2232+01, 24' LT | BT | In conflict with proposed drainage culvert | Y | 1-182 | To be removed
183 | Centurylink | 2232+01, 29' RT | BT | In conflict with proposed drainage culvert | Y | 1-183 | To be removed
184 | Centurylink | 2232+01, 35' RT | BT | In conflict with proposed drainage culvert | Y | 1-184 | To be removed
185 | Summit | 2233+18, 40' LT | BFOC | In proposed shoulders | Y | 1-185 | See Conflict #382
186 | Centurylink | 2233+18, 38' LT | BT | In proposed shoulders | Y | 1-186 | See Conflict #398
187 | Centurylink | 2235+00, 64' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-187 | No conflict/design change
188 | Centurylink | 2235+98, 96' RT | BT | In conflict with proposed drainage ditch | Y | 1-188 | No conflict/design change
189 | Centurylink | 2235+98, 99' RT | BFOC | In conflict with proposed drainage ditch | Y | 1-189 | No conflict/design change
190 | Calumet | 2236+00, 87' RT | PET | In conflict with proposed drainage ditch | Y | 1-190 | No conflict/design change
191 | Centurylink | 2236+00, 89' RT | BT | In conflict with proposed drainage ditch | Y | 1-191 | No conflict/design change
192 | Centurylink | 2236+00, 93' RT | BFOC | In conflict with proposed drainage ditch | Y | 1-192 | No conflict/design change
193 | Summit | 2237+00, 67' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-193 | No conflict/design change
194 | Calumet | 2238+00, 87' RT | PET | In conflict with proposed drainage ditch | Y | 1-194 | No conflict/design change
195 | Centurylink | 2238+00, 89' RT | BT | In conflict with proposed drainage ditch | Y | 1-195 | No conflict/design change
196 | Centurylink | 2238+00, 93' RT | BFOC | In conflict with proposed drainage ditch | Y | 1-196 | No conflict/design change
197 | Summit | 2239+00, 68' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-197 | No conflict/design change
198 | Calumet | 2240+11, 88' RT | PET | Possible conflict due to construction of cross drain | Y | 1-198 | Protect in Place
199 | Centurylink | 2240+11, 90' RT | BT | Possible conflict due to construction of cross drain | Y | 1-199 | No conflict/design change
200 | Centurylink | 2240+11, 94' RT | BFOT | Possible conflict due to construction of cross drain | Y | 1-200 | No conflict/design change
201 | Summit | 2241+00, 70' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-201 | No conflict/design change
202 | Calumet | 2242+00, 87' RT | PET | In conflict with proposed drainage ditch | Y | 1-202 | No conflict/design change
203 | Centurylink | 2242+00, 89' RT | BT | In conflict with proposed drainage ditch | Y | 1-203 | No conflict/design change
204 | Centurylink | 2242+00, 93' RT | BFOC | In conflict with proposed drainage ditch | Y | 1-204 | No conflict/design change
205 | Summit | 2243+00, 72' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-205 | No conflict/design change
206 | Calumet | 2244+00, 84' RT | PET | In conflict with proposed drainage ditch | Y | 1-206 | No conflict/design change
207 | Centurylink | 2244+00, 84' RT | BT | In conflict with proposed drainage ditch | Y | 1-207 | No conflict/design change
208 | Centurylink | 2244+00, 88' RT | BFOC | In conflict with proposed drainage ditch | Y | 1-208 | No conflict/design change
209 | Summit | 2245+00, 73' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-209 | No conflict/design change
210 | Centurylink | 2246+00, 83' RT | BT | In conflict with proposed drainage ditch | Y | 1-210 | No conflict/design change
211 | Centurylink | 2246+00, 87' RT | BFOC | In conflict with proposed drainage ditch | Y | 1-211 | No conflict/design change
212 | Calumet | 2246+00, 87' RT | PET | In conflict with proposed drainage ditch | Y | 1-212 | No conflict/design change
213 | Centurylink | 2246+98, 56' LT | BT | In conflict with proposed guardrail | Y | 1-214 | No conflict
214 | Summit | 2247+00, 74' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-214A | No conflict/design change
215 | Centurylink | 2247+51, 58' LT | BT | In conflict with proposed guardrail | Y | 1-215 | No conflict
216 | Centurylink | 2247+52, 59' LT | BT | In conflict with proposed guardrail | Y | 1-216 | No conflict
217 | Centurylink | 2247+52, 58' LT | BFOT | In conflict with proposed guardrail | Y | 1-217 | No conflict
218 | Centurylink | 2248+00, 84' RT | BFOT | In conflict with proposed drainage ditch | Y | 1-218 | No conflict/design change
219 | Centurylink | 2248+00, 81' RT | BT | In conflict with proposed drainage ditch | Y | 1-219 | No conflict/design change
220 | Calumet | 2248+00, 82' RT | PET | In conflict with proposed drainage ditch | Y | 1-220 | No conflict/design change
221 | Summit | 2249+00, 74' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-221 | No conflict/design change
222 | Exploratory | 2249+12, 78' LT | Multipole sign | Possible conflict with signage - Exploratory | Y | 1-222 | No conflict
223 | Centurylink | 2250+00, 77' RT | BT | In conflict with proposed drainage ditch | Y | 1-223 | No conflict/design change
224 | Centurylink | 2250+00, 82' RT | BFOT | In conflict with proposed drainage ditch | Y | 1-224 | No conflict/design change
225 | Calumet | 2250+00, 84' RT | PET | In conflict with proposed drainage ditch | Y | 1-225 | No conflict/design change
226 | Summit | 2251+00, 73' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-226 | No conflict/design change
227 | Centurylink | 2252+00, 77' RT | BT | In conflict with proposed drainage ditch | Y | 1-227 | No conflict/design change
228 | Centurylink | 2252+00, 82' RT | BFOC | In conflict with proposed drainage ditch | Y | 1-228 | No conflict/design change
229 | Calumet | 2252+00, 84' RT | PET | In conflict with proposed drainage ditch | Y | 1-229 | No conflict/design change
230 | Summit | 2253+00, 74' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-230 | No conflict/design change
231 | Centurylink | 2254+00, 77' RT | BT | In conflict with proposed drainage ditch | Y | 1-231 | No conflict/design change
232 | Centurylink | 2254+00, 82' RT | BFOT | In conflict with proposed drainage ditch | Y | 1-232 | No conflict/design change
233 | Calumet | 2254+00, 84' RT | PET | In conflict with proposed drainage ditch | Y | 1-233 | No conflict/design change
234 | Summit | 2255+00, 73' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-234 | No conflict/design change
235 | Centurylink | 2256+00, 76' RT | BT | Conflict with cross drain | Y | 1-235 | No conflict/design change
236 | Centurylink | 2256+00, 82' RT | BFOT | Conflict with cross drain | Y | 1-236 | No conflict/design change
237 | Calumet | 2256+00, 84' RT | PET | Conflict with cross drain | Y | 1-237 | Protect in Place
238 | Summit | 2257+00, 73' LT | BFOC | In conflict with proposed drainage ditch | Y | 1-238 | No conflict/design change
239 | Centurylink | 2257+22, 77' RT | BT | Possible conflict due to construction of cross drain | Y | 1-239 | No conflict/design change
240 | Centurylink | 2257+22, 83' RT | BFOT | Possible conflict due to construction of cross drain | Y | 1-240 | No conflict/design change
241 | Calumet | 2257+22, 85' RT | PET | Possible conflict due to construction of cross drain | Y | 1-241 | Protect in Place
242 | Immokalee | 191+87, 40' RT | Sanitary Sewer | In proposed sidewalk | Y | 1-242 | Relocate/adjust
243 | Calumet | 191+98, 42' RT | PET | In proposed sidewalk | Y | 1-243 | No Conflict
244 | TECO Peoples Gas | 2097+00, 55' LT | 8" Gas Main | In proposed sidewalk | Y | 1-244 | No Conflict
245 | TECO Peoples Gas | 2109+50, 51' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-245 | No Conflict
246 | TECO Peoples Gas | 2110+08, 52' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-246 | No Conflict
247 | TECO Peoples Gas | 2110+80, 52' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-247 | No Conflict
248 | TECO Peoples Gas | 2111+80, 50' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-248 | No Conflict
249 | TECO Peoples Gas | 2114+00, 48' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-249 | No Conflict
250 | TECO Peoples Gas | 2117+89, 49' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-250 | No Conflict
251 | TECO Peoples Gas | 2173+00, 31' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-251 | See Conflict #368
252 | TECO Peoples Gas | 2174+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-252 | See Conflict #368
253 | TECO Peoples Gas | 2177+50, 26' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-253 | See Conflict #368
254 | TECO Peoples Gas | 2188+00, 26' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-254 | See Conflict #368
255 | TECO Peoples Gas | 2188+74, 26' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-255 | See Conflict #368
256 | TECO Peoples Gas | 2199+00, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-256 | See Conflict #368
257 | TECO Peoples Gas | 2200+65, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-257 | See Conflict #368
258 | TECO Peoples Gas | 2202+87, 35' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-258 | See Conflict #368
259 | TECO Peoples Gas | 2212+40, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-259 | See Conflict #368
260 | TECO Peoples Gas | 2212+88, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-260 | See Conflict #368
261 | TECO Peoples Gas | 2215+25, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-261 | See Conflict #368
262 | TECO Peoples Gas | 2217+00, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-262 | See Conflict #368
263 | TECO Peoples Gas | 2218+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-263 | See Conflict #368
264 | TECO Peoples Gas | 2219+28, 35' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-264 | See Conflict #368
265 | TECO Peoples Gas | 2219+82, 36' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-265 | See Conflict #368
266 | TECO Peoples Gas | 2220+00, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-266A | See Conflict #368
267 | TECO Peoples Gas | 2222+00, 39' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-267 | See Conflict #368
268 | TECO Peoples Gas | 2224+00, 38' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-268 | See Conflict #368
269 | TECO Peoples Gas | 2225+20, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-269 | See Conflict #368
270 | TECO Peoples Gas | 2226+58, 39' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-270 | See Conflict #368
271 | Centurylink | 2226+58, 40' LT | BT | Possible conflict with roadway items | Y | 1-271 | See Conflict #398
272 | TECO Peoples Gas | 2228+00, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-272 | See Conflict #368
273 | TECO Peoples Gas | 2229+30, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-273 | See Conflict #368
274 | TECO Peoples Gas | 2230+65, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-274 | See Conflict #368
275 | TECO Peoples Gas | 2233+40, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-275 | See Conflict #368
276 | TECO Peoples Gas | 2235+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-276 | See Conflict #367
277 | TECO Peoples Gas | 2237+00, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-277 | See Conflict #367
278 | TECO Peoples Gas | 2239+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-278 | No conflict
279 | TECO Peoples Gas | 2241+00, 32' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-279 | No conflict
280 | TECO Peoples Gas | 2243+00, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-280 | No conflict
281 | TECO Peoples Gas | 2245+00, 33' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-281 | No conflict
282 | TECO Peoples Gas | 2247+00, 34' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-282 | No conflict
283 | TECO Peoples Gas | 2249+00, 35' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-283 | No conflict
284 | TECO Peoples Gas | 2251+00, 36' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-284 | No conflict
285 | TECO Peoples Gas | 2253+00, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-285 | No conflict
286 | TECO Peoples Gas | 2255+00, 37' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-286 | No conflict
287 | TECO Peoples Gas | 2257+00, 39' LT | 8" Gas Main | Possible conflict with roadway items | Y | 1-287 | No conflict
288 | Centurylink | 2098+91, 39' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
289 | Centurylink | 2099+30, 43' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
290 | LCEC | 2100+15, 89' LT | BE | Possible conflict with proposed drainage culvert | N |  | To be removed
291 | Centurylink | 2100+33, 43' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
33A | Immokalee | 2101+13, 89' LT | Water Main | Possible conflict with proposed drainage culvert | Y | 1-33A | To be removed
292 | Centurylink | 2101+35, 80' LT | BT | Possible conflict with proposed drainage structure | N |  | To be removed
292A | Centurylink | 2215+91, 62' LT | BFOT | Possible conflict with proposed drainage structure | N |  | To be removed
293 | Centurylink | 2101+35, 76' LT | BT | Possible conflict with proposed drainage structure | N |  | To be removed
294 | Centurylink | 2101+56, 38' LT | BT | Possible conflict with proposed drainage structure | N |  | To be removed
294A | Centurylink | 2218+99, 49' LT | BT | Possible conflict with proposed drainage structure | N |  | To be removed
295 | Centurylink | 2101+70, 38' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
295A | Centurylink | 2221+58, 43' LT | BFOT | Possible conflict with proposed drainage culvert | N |  | To be removed
295B | Centurylink | 2226+09, 42' LT | BFOT | Possible conflict with proposed drainage culvert | N |  | To be removed
295C | Centurylink | 2227+21, 40' LT | BFOT | Possible conflict with proposed drainage culvert | N |  | To be removed
295D | Centurylink | 2227+94, 45' LT | BT | Possible conflict with proposed drainage structure | N |  | To be removed
296E | TECO Peoples Gas | 2227+94, 41' LT | 8" Gas Main | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
296 | Centurylink | 2104+24, 40' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
297 | Centurylink | 2104+46, 40 'LT | BT | Possible conflict with proposed drainage structure | N |  | To be removed
298 | Centurylink | 2104+46, 42' LT | BT | Possible conflict with proposed drainage structure | N |  | To be removed
299 | TECO Peoples Gas | 2104+91, 55' LT | 8" Gas Main | Possible conflict with proposed drainage culvert | N |  | To be removed
300 | TECO Peoples Gas | 2104+98, 55 'LT | 8" Gas Main | Possible conflict with proposed drainage structure | N |  | To be removed
301 | Centurylink | 2106+79, 60' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
62-A | Centurylink | 2107+07, 39' LT | BT | Possible conflict with proposed drainage culvert | Y | 1-62A | To be removed
64-A | Centurylink | 2107+07, 60' LT | BT | Possible conflict with proposed drainage structure | Y | 1-64A | To be removed
68-A | Centurylink | 2110+07, 59' LT | BT | Possible conflict with proposed drainage structure | Y | 1-68A | To be removed
302 | Summit | 2111+48, 61' LT | BFOC | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
303 | Centurylink | 2111+48, 62' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
303A | Immokalee | 2113+03, 61' LT | Water Main | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
303B | Immokalee | 2113+07, 64' LT | Water Main | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
304 | Summit | 2113+69, 61' LT | BFOC | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
305 | Centurylink | 2114+04, 64' LT | BT | Possible conflict with proposed drainage structure | N |  | To be removed
83-A | Centurylink | 2114+89, 63' LT | BT | Conflict with proposed drainage structure | Y | 1-83A | To be removed
305A | Centurylink | 2116+31, 92' LT | BFOT | Possible conflict with proposed drainage structure | N |  | To be removed
305B | Centurylink | 2116+82, 92' LT | BFOT | Possible conflict with proposed drainage structure | N |  | To be removed
306 | Calumet | 2105+83, 89' RT | PET | Possible conflict with proposed drainage culvert | N |  | To be removed
307 | Calumet | 2109+94, 90' RT | PET | Possible conflict with proposed drainage structure | N |  | To be removed
308 | Calumet | 2112+05, 91' RT | PET | Possible conflict with proposed drainage structure | N |  | To be removed
308A | Immokalee | 2113+07, 84' RT | Water Main | Possible conflict with proposed drainage culvert | N |  | Protect in Place
308B | Calumet | 2117+29, 91' RT | PET | Possible conflict with proposed drainage structure | N |  | To be removed
309 | Calumet | 2119+04, 90' RT | PET | Possible conflict with proposed drainage structure | N |  | To be removed
310 | Centurylink | 2119+91, 94' LT | BFOT | Possible conflict with proposed drainage structure | N |  | To be removed
311 | Centurylink | 2119+91, 80' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
312 | Centurylink | 2119+91, 73' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
313 | Centurylink | 2119+91, 63' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
314 | Summit | 2119+91, 51' LT | BFOC | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
315 | TECO Peoples Gas | 2119+91, 43' LT | 8" Gas Main | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
316 | Centurylink | 2119+91, 13' RT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
317 | Centurylink | 2119+91, 34' RT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
318 | Calumet | 2119+91, 90' RT | PET | Possible conflict with proposed drainage structure | N |  | To be removed
318A | Comcast | 2128+77, 104' RT | OT | Possible conflict with proposed pond | N |  | To be removed
318B | LCEC | 2128+80, 103' RT | OE | Possible conflict with proposed pond | N |  | To be removed
318C | LCEC | 2130+84, 102' RT | OE | Possible conflict with proposed pond | N |  | To be removed
318D | Comcast | 2132+95, 102' RT | OT | Possible conflict with proposed pond | N |  | To be removed
318E | LCEC | 2132+99, 104' RT | OE | Possible conflict with proposed pond | N |  | To be removed
318F | Centurylink | 2133+20, 44' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
318G | TECO Peoples Gas | 2133+20, 38' LT | 8" Gas Main | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
318H | Summit | 2133+20, 36' LT | BFOC | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
318I | Centurylink | 2133+20, 14' RT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
318J | Centurylink | 2133+20, 16' RT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
318K | LCEC | 2135+89, 103' RT | OE | Possible conflict with proposed pond | N |  | To be removed
101A | Centurylink | 2170+84, 93' LT | BT | Conflict with proposed side drain | Y | 1-101A | To be removed
319 | Centurylink | 2175+03, 15' RT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
320 | TECO Peoples Gas | 2175+03, 30' LT | 8" Gas Main | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
321 | Summit | 2175+03, 38' LT | BFOC | Possible conflict with proposed drainage culvert | N |  | Relocate/adjust
322 | Centurylink | 2175+03, 48' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
323 | Centurylink | 2175+03, 78' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
323A | TECO Peoples Gas | 2178+60, 92' LT | 8" Gas Main | Possible conflict with proposed side drain | N |  | To be removed
324 | Centurylink | 2180+00, 65' LT | BFOT | Possible conflict with proposed drainage culvert | N |  | To be removed
137A | Centurylink | 2202+82, 61' LT | BT | Possible conflict with proposed side drain | Y | 1-137A | To be removed
325 | Centurylink | 2211+75, 57' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
326 | Centurylink | 2213+43, 64' LT | BFOT | Possible conflict with proposed drainage culvert | N |  | To be removed
327 | Centurylink | 2215+25, 63' LT | BFOT | Possible conflict with proposed drainage culvert | N |  | To be removed
328 | Centurylink | 2218+00, 65' LT | BFOT | Possible conflict with proposed drainage culvert | N |  | To be removed
329 | Centurylink | 2218+79, 57' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
330 | Centurylink | 2221+19, 46' LT | BT | Possible conflict with proposed drainage culvert | N |  | To be removed
331 | TECO Peoples Gas | 2240+11, 62' LT | 8" Gas Main | Possible conflict with proposed drainage culvert | N |  | Protect in Place
332 | Centurylink | 2210+10, 64' LT | BT | Possible conflict with proposed drainage culvert | N |  | Nonconflict/design change
333 | LCEC | 2100+08, 105' RT | OE/Power Pole | Power pole in new roadway | N |  | Relocate
334 | LCEC | 2101+15, 105' RT | OE/Power Pole/Service | Power pole in new sidewalk | N |  | Relocate
335 | Comcast | 2101+15, 105' RT | OT/Service box | Service box in new sidewalk | N |  | Relocate
336 | LCEC | 2103+85, 105' RT | OE/Power Pole | Power pole in new ditch | N |  | Relocate
337 | Comcast | 2103+85, 105' RT | OT/Service box | Service box in new ditch | N |  | Relocate
338 | LCEC | 2128+80, 101' RT | OE/Power Pole | Power pole in new pond | N |  | Relocate
339 | Comcast | 2128+80, 101' RT | OTV/Power Pole | Power pole in new pond | N |  | Relocate
340 | LCEC | 2132+95, 104' RT | OE/Power Pole | Power pole in new pond | N |  | Relocate
341 | Comcast | 2132+95, 104' RT | OTV/Power Pole | Power pole in new pond | N |  | Relocate
342 | LCEC | 2135+85, 103' RT | OE/Power Pole | Power pole in new pond | N |  | Relocate
343 | Comcast | 2135+85, 103' RT | OTV | LCEC power pole in new pond | N |  | Relocate
344 | LCEC | 2172+65, 0' RT | OE | OE across raised roadway | N |  | To be raised
345 | LCEC | 2178+75, 0' RT | OE | OE across raised roadway | N |  | To be raised
346 | LCEC | 2191+83, 0' RT | OE | OE across raised roadway | N |  | To be raised
347 | LCEC | 2202+40, 0' RT | OE | OE across raised roadway | N |  | To be raised
348 | FPL Transmission | 2220+75, 0' RT | OE | OE across raised roadway | N |  | Check vertical clearance
349 | FPL Transmission | 2221+05, 0' RT | OE | OE across raised roadway | N |  | Check vertical clearance
350 | FPL Transmission | 2221+40, 0' RT | OE | OE across raised roadway | N |  | Check vertical clearance
351 | FPL Transmission | 2223+83, 0' RT | OE | OE across raised roadway | N |  | Check vertical clearance
352 | FPL Transmission | 2224+08, 0' RT | OE | OE across raised roadway | N |  | Check vertical clearance
353 | LCEC | 2233+15, 0' RT | OE | OE across raised roadway | N |  | To be raised
354 | Immokalee Sewer | 2099+43, 73' LT | Manhole | Regraded | N |  | Adjust manhole top vertically
355 | Immokalee Sewer | New Market Rd | Manhole | Regraded | N |  | Adjust manhole top vertically
356 | Immokalee Sewer | 2099+70, 68' LT | Manhole | Regraded | N |  | Adjust manhole top vertically
357 | Immokalee Water | 2099+85, 96' LT | Valve box | Regraded | N |  | Adjust valve box vertically
358 | Immokalee Water | 2100+25, 90' LT | Valve boxes | New sidewalk | N |  | Adjust valve boxes vertically
359 | Immokalee Water | 2101+38, 88' LT | Fire hydrant | Regraded | N |  | Adjust
360 | Immokalee Sewer | 2104+08, 64' LT | Manhole | Regraded | N |  | Adjust manhole top vertically
361 | Immokalee Water | 2106+20, 88' LT | Fire hydrant | Regraded | N |  | Adjust, min. 4' from SUP
362 | Immokalee Water | 2107+70, 81' LT | Valve box | New SUP | N |  | Adjust valve box vertically
363 | Immokalee Water | 2111+23, 87' LT | Fire hydrant | Regraded | N |  | Adjust, min. 4' from SUP
364 | Immokalee Water | 2113+05, 83' LT | Valve box | New SUP | N |  | Adjust valve box vertically
365 | Immokalee Water | 2113+05, 99' RT | Vault | Regraded | N |  | Adjust vault vertically
366 | TECO Peoples Gas-Peoples Gas | 2217+70, 34' LT | Vault | In new pavement | N |  | Relocate
367 | TECO Peoples Gas-Peoples Gas | 2234+00 to 2237+00, 49' LT | 8" steel GM | Below new guardrail | Y | 1-276 | Relocate
368 | TECO Peoples Gas-Peoples Gas | 2159+03 to 2234+00 LT | 8" steel GM | Under new pavement | N |  | Relocate?
369 | Centurylink | 2104+60 to 2120+35 LT/RT | 2-BT (one in service, one out of service), pedestals, etc. | Under new pavement | N |  | To be removed
370 | Centurylink | 2159+03 to 2240+00 RT | 2-BT (one in service, one out of service), pedestals, etc. | Under new pavement | N |  | To be removed
371 | Centurylink | 2107+35, 90' LT | BFOT pedestals | Regraded | N |  | Adjust
372 | Centurylink | 2119+70, 94' LT | BFOT vault | Regraded | N |  | Adjust
373 | Centurylink | 2170+85, 95' LT | BFOT vault | Regraded | N |  | Adjust
374 | Centurylink | 2177+85, 78' LT | BFOT,BT vaults, pedestals, etc. | Regraded | N |  | Adjust
375 | Centurylink | 2189+30, 71' LT | BFOT vault, pedestal | Regraded | N |  | Adjust, min. 4' from SUP
376 | Centurylink | 2199+00, 74' LT | BFOT vault, pedestal | in SUP | N |  | Relocate/adjust, min. 4' from SUP
377 | Centurylink | 2202+40, 44' LT | BFOT vault, pedestal | edge of paved shoulder | N |  | Relocate
378 | Centurylink | 2212+20, 46' LT | BFOT vault, pedestal | edge of paved shoulder | N |  | Relocate
379 | Centurylink | 2220+40 to 2229+00, 50' LT | BFOT | Below new guardrail | N |  | To be removed
380 | Summit | 2170+00 to 2207+00 LT | BFOC | Under new pavement | N |  | Relocate?
381 | Summit | 2214+25, 52' LT | BFOC vault | Regraded | N |  | Adjust
382 | Summit | 2216+00 to 2234+00 LT | BFOC | Under new pavement | N |  | Relocate?
383 | Summit | 2234+00 to 2235+00, 48' LT | BFOC | Below new guardrail | N |  | Locate and protect
384 | Summit | 2238+00 to 2244+00, 48' LT | BFOC | Below new guardrail | N |  | No Conflict
385 | Summit | 2244+25, 63' LT | BFOC vault | Regraded | N |  | Adjust
386 | Summit | 2254+30, 66' LT | BFOC vault | Regraded | N |  | Adjust
387 | Centurylink | 2113+00, 77' LT | BT vault | In new SUP | N |  | Adjust
388 | Centurylink | 2117+10, 76' LT | BT vault | In new SUP | N |  | Adjust
389 | Centurylink | 2159+20, 58' LT | BT vault | Regraded | N |  | Adjust
390 | Centurylink | 2170+60, 72' LT | BT vault | Regraded | N |  | Adjust
391 | Centurylink | 2170+70, 58' LT | BT vault | Adjacent to new driveway | N |  | Relocate
392 | Centurylink | 2178+55, 72' LT | BT vault | Adjacent to new SUP | N |  | Relocate/adjust, min. 4' from SUP
393 | Centurylink | 2179+40, 80' LT | BT pedestal | In new SUP | N |  | Relocate/min. 4' from SUP
394 | Centurylink | 2187+75, 83' LT | BT vault/pedestal | In new SUP | N |  | Relocate/min. 4' from SUP
395 | Centurylink | 2202+83, 48' LT | BT vault/pedestal | Adjacent to new driveway | N |  | Relocate
396 | Centurylink | 2211+42, 55' LT | BT vault/pedestal | Regraded | N |  | Adjust
397 | Centurylink | 2220+40 to 2222+00, 50' LT | BT | Below new guardrail | N |  | To be removed
398 | Centurylink | 2222+00 to 2244+00, 50' LT | BT | Under new pavement/guardrail | N |  | To be removed
399 | Centurylink | 2100+05, 97' LT | BFOT | Temporay strain pole (TTCP Phase IA/IB) | N |  | To be removed
400 | Centurylink | 2101+66, 45' LT | BT | Temporay strain pole (TTCP Phase IIA) | N |  | To be removed
401 | Summit | 2255+00, 81' RT | BFOC | Possible conflict with relocated multipost sign | N |  | To be removed
402 | Centurylink | 2255+00, 86' RT | BT | Possible conflict with relocated multipost sign | N |  | To be removed
403 | FDOT | 2255+00, 62' RT | BE | Possible conflict with relocated multipost sign | N |  | Adjust/Locate and protect
404 | Calumet | 2255+00, 90' RT | PET | Possible conflict with relocated multipost sign | N |  | Adjust/Locate and protect
LP1 |  | 2092+66, 53' RT. |  |  | N
LP2 |  | 2094+60, 48' LT. |  |  | N
LP3 |  | 2096+55, 48' RT. |  |  | N
LP4 |  | 2098+73, 76' RT. |  |  | N
LP5 | TECO Peoples Gas | 2098+78, 61' LT. | 8" Steel Gas Main | Light Pole 5 - 2' space between edge of shaft foundation and edge of pipe. (Pole is 30' south of VVH 1-25A) | Y | 1-25A
LP6 |  | 2099+71, 127' RT. |  |  | N
LP7 | Century Link, Buried Telephone | 2099+91, 76' LT. |  | Light Pole 7 - 2' space between edge of shaft foundation and buried telephone line. (Pole is 90' north of VVH 1-21A) | Y | 1-21A
LP7 | Century Link, Buried Telephone | 2099+91, 76' LT. |  | Light Pole 7 - 2' space between edge of shaft foundation and buried telephone line. (Pole is 90' north of VVH 1-22A) | Y | 1-22A
LP8 |  | 2101+27, 143' RT. |  |  | N
LP9 | TECO Peoples Gas | 2101+38, 62' LT. | 8" PVC Sanitary Sewer | Light Pole 9 - 3' space between edge of shaft foundation and edge of pipe. (Pole is 65' south of VVH 1-43) | Y | 1-43
LP9 | TECO Peoples Gas | 2101+38, 62' LT. | 8" Steel Gas Main | Light Pole 9 - 3' space between edge of shaft foundation and edge of pipe. (Pole is 65' south of VVH 1-44) | Y | 1-44
LP10 | Century Link, Buried Telephone | 2102+65, 44' LT. | 1" BFOC | Light Pole 10' - 1' space between edge of shaft foundation and fiber optic cable. (Pole is 72' south of VVH 1-47) | Y | 1-47
LP11 |  | 2102+89, 75' RT. |  | Light Pole 16 - Exploratory | Y | LP-16
LP12 |  | 2105+47, 72' RT. |  |  | N
LP13 |  | 2105+50, 66' LT. |  |  | N
LP14 |  | 803+21, 43' LT. |  |  | N
LP15 |  | 2101+03, 181' LT. |  |  | N
LP16 |  | 401+06, 36' LT. |  |  | N
LP17 |  | 403+20, 38' RT. |  | Light Pole 23 - Exploratory | Y | LP-23
405 | FDOT | 2093+69, 39' RT. | BE | Possible conflict with proposed multipost sign | N |  | Adjust/Locate and protect
406 | TECO Peoples Gas | 2107+34, 54' LT | 8" Gas Main | Possible conflict with proposed multipost sign | N |  | Locate and protect
407 | Centurylink | 2107+34, 59' LT | BT | Possible conflict with proposed multipost sign | N |  | To be removed
408 | Summit | 2107+34, 60' LT | BFOC | Possible conflict with proposed multipost sign | N |  | To be removed
409 | Centurylink | 2107+34, 68' LT | BT | Possible conflict with proposed multipost sign | N |  | To be removed

## Matrix Guide
FPID: | 1 | Description: | 2 |  |  | This matrix was created by _______3___________ to assist the UAO's in identifying conflicts between the UAO's facilities and proposed roadway construction. __________________ accepts no liability for conflicts overlooked for this report. Each UAO or designee is responsible to perform a detailed and comprehensive plans review for conflict analysis.
Phase #: | 4 | Plans Date: | 5
Preparer: | 6
Date: | 7
Conflict # | Utility Agency/ Owner (UAO) | Station | Offset (From C/L) | Facility Description (Material, Type, Number, Size) | Conflict Description (Possible or Actual) | VVH (Y/N) | Test Hole VVH # | Suggested Conflict Resolution | Resolved Status
8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Consider using the form from the beginning of a project as a tool for monitoring areas of concern with UAO facilities. That is the reason for the Phase Number space. The form is set up to: 1. Print the header information on each page. 2. The cells where the conflicts are listed are set to word wrap automatically. 3. The footer is set to number the pages 1 of ??.
1 | Project number.
2 | Project description.
3 | Disclaimer that the reviewer and their firm is not responsible for any missed conflicts. The blanks are for the name of the design firm.
4 | Phase that the plans represent.
5 | The date should be on the plans Key Sheet. The phase and plans date should keep everyone working on the same plans.
6 | That would be you, the person that wrote the conflict matrix.
7 | The date the matrix was completed.
8 | For ease of discussion the conflicts are numbered, plan sheet numbers are not used because they change from Phase to Phase which has caused confusion in the past.
9 | Owner of the underground line.
10 | The standard reference used on FDOT plans is the Centerline of Construction, it is used for all components of the proposed roadway construction.
11 | Offset from the Centerline of Construction
12 | Describe the facility. What is it? Water main? Force main? Cable? Conduit? Overhead electric? Overhead cable? Manhole? Handhold? What's the size? How many? What's it made of?
13 | What is it the facility perceived to be in conflict with? It a possible conflict or actually in conflict with proposed work. Consider the trench and hole size required to place pipe and drainage structures. Don't forget aerial facilities when there are signals and large signs in the project.
14 | SUE work can be used to if a conflict is considered a possibility. This entry area is a tool to determine areas where test holes should be taken for confirmation or exclusion of a conflict.
15 | Entry area for the test hole number. Test holes should be numbered consecutively to avoid confusion.
16 | What can be done to remove the conflict? Don't forget to consult with the Designer for alternatives to the proposed construction.
17 | Examples of entries could be "Cleared…addressed by a utility work schedule", "Pending...utility work schedule forthcoming", "No Conflict". It's suggested to keep the entries determined as "No Conflict" in the matrix so other reviewers will know a perceived conflict has been noted and determined to not be an issue.