## WPII Project Team Availability
Florida Department of Transportation - Work Program Integration Initiative (WPII)
Project Team Member Schedule Availability (DDI Phases)
Project Role | Name (will be deleted for ITN) | Project Track | Est. WPII Administrative Time (A) | Est. WPII Deliverable / Work Time (B) | Est. Weekly Total Availability (A+B) | % of 40-HR Standard
Statewide Remediation Program Manager | Sara Dugger | Statewide Remediation | 4 | 16 | 20 | 50%
Technical Business Analyst/Liaison | Patricia Atchley | Statewide Remediation | 2 | 38 | 40 | 100%
Technical Track Lead | Brian Tippel | Technical | 10 | 30 | 40 | 100%
Technical Architect | Matt Ferris | Technical | 2 | 18 | 20 | 50%
Data Management Team Member | Tamil Dhanabalan | Technical | 2 | 38 | 40 | 100%
Data Management Team Member | Jay Jagatheesan | Technical | 2 | 38 | 40 | 100%
Data Management Team Member | Sara Close | Technical | 2 | 38 | 0 | 0%
Project Manager | Danielle Kosberg | PMO | 10 | 30 | 40 | 100%
PMO Project Coordinator | Manny Hernandez | PMO | 5 | 35 | 40 | 100%
PMO Project Coordinator | Regina Richardson | PMO | 10 | 30 | 40 | 100%
PMO Project Coordinator (Future Role) | Future Role | PMO | - | - | - | -
Project Administrator | Heather DeFrancisco | PMO | 35 | 5 | 40 | 100%
Finance Manager | David Perrin | PMO | - | - | 30 | 75%
Contract & Budget Manager | Alan Busenbark | PMO | - | - | 10 | 25%
OCM Track Lead (Future Role) | Future Role | OCM | - | - | - | -
Project Communications Lead (Future Role) | Future Role | OCM | - | - | - | -
OCM Change Impact Assessment Lead (Future Role) | Future Role | OCM | - | - | - | -
OCM Change Impact Assessment Lead (Future Role) | Future Role | OCM | - | - | - | -
Path Forward Track Lead | Paul Baker | Path Forward | - | - | 10 | 25%
Business Process Standardization Manager/Business Track Lead | Greg Patterson | Business Track | 6 | 18 | 24 | 60%
Develop the Work Program Solutions Lead | Anna Suhrweir | Business Track | 1 | 29 | 30 | 75%
Manage Funds Lead/Specialist (Future Role) | Deena Shealy | Business Track | - | - | - | -
Manage Project Portfolio Lead/Specialist (Future Role | Kendra Sheffield | Business Track | - | - | - | -
Manage Project Development to Close Out Lead/Specialist | Karen Corman | Business Track | 3 | 15 | 18 | 45%
Manage Project Development to Close Out Lead/Specialist (Future Role) | Tim Olssen | Business Track | - | - | - | -
Forcast Cash Flow Lead/Specialist (Future Role) | Cheri Jenkins | Business Track | - | - | - | -
Forcast Cash Flow Lead/Specialist (Future Role) | Christa Dismuke | Business Track | - | - | - | -
Forcast Cash Flow Lead/Specialist (Future Role) | Gwendowlyn Jones-Battles | Business Track | - | - | - | -
Forcast Cash Flow Lead/Specialist (Future Role) | David James | Business Track | - | - | - | -
Forcast Cash Flow Lead/Specialist (Future Role) | Future Role | Business Track | - | - | - | -
Manage Agency Performance Lead/Specialist (Future Role) | Fred Grant | Business Track | - | - | - | -
Manage Federal Programs Lead/Specialist | David Williams | Business Track | 1 | 31 | 32 | 80%
Manage Federal Programs Lead/Specialist (Future Role) | Sean McAuliffe | Business Track | - | - | - | -
Manage Budget Lead/Specialist (Future Role) | Mechelle Marcum | Business Track | - | - | - | -
Senior Business Process Lead | Drew Evers | Business Track | 4 | 36 | 40 | 100%
Senior Business Process Lead | Michael Stephens | Business Track | 1 | 39 | 40 | 100%
Senior Business Process Lead | Linda Glass-Johnson | Business Track | 1 | 39 | 40 | 100%
Senior Business Process Lead | Mina Nofallah | Business Track | 1 | 39 | 40 | 100%
Deliver the Work Program Solutions Lead | Lisa Evans | Business Track | 5 | 23 | 28 | 70%
Manage Contractual Commitment to Close Lead/Specialist | Josephine Jones | Business Track | 1 | 29 | 30 | 75%
Perform General Accounting Lead/Specialist (Future Role) | Tim Hsieh | Business Track | - | - | - | -
Perform General Accounting Lead/Specialist (Future Role) | Future Role | Business Track | - | - | - | -
Perform Project Cost Accounting Lead/Specialist Future Role) | Jason Adank | Business Track | - | - | - | -
Perform Project Cost Accounting Lead/Specialist (Future Role) | Future Role | Business Track | - | - | - | -
Columns:
Project Role - WPII project position function or role
Project Track - Business, OCM, Technical, Statewide Remediation, Contracts, or Procurement, or support groups: PMO, IV&V, etc.
Est. WPII Administrative Time - An integer amount in hours available (max) to work on all WPII Administrative-only activities per week.
Est, WPII Deliverable / Work Time - An integer amount in hours available (max) to work on WPII deliverable and project work activities per week.
Est. Weekly Total Availability - An integer amount in hours available (max) to work on all WPII activities per week, incl. WPII administrative tasks
% of 40-Hr Standard - Calculated percentage of Availability based on a 40-hour week