## Slide 1
Florida Department of Transportation
FINANCIAL PROJECT IDENTIFICATION NUMBERS:
447555-1, 447555-2, 453333-3 (Go Together) 453333-2, 453333-1, and 453333-4 Martin and Okeechobee Counties
STATE ROAD (SR) 710
PROJECTS UPDATE
APRIL 21, 2025 – POLICY BOARD MEETING
Martin Metropolitan Planning Organization

## Slide 2
Agenda
2
Corridor Overview
Project Goals
Existing Conditions
Proposed Improvements by Segment
  Challenges
  Key Stakeholder
  Coordination
  Project Schedule
Notes: Corridor Overview (common)
Existing Conditions
Project Goals
FPID Number 1 -

## Slide 3
FDOT Compass
3
Transportation Project Development Process
Right-Of-Way
Appraisal
Negotiations
Acquisition
Design
Detailed design
Construction Plans
Cost Estimates
Permits
Planning
Existing Conditions
Needs Assessment
Work Program
PD&E
Purpose & Need
Alternatives Analysis
Environmental Studies
Documentation
We Are Here
Construction
Build and Deliver

## Slide 4
4
Traffic and Safety
Traffic Volumes
Truck % : 8% to 18%
Level of Service Target C (Outside Urbanized Area)
Currently exceeds target
 | 2023
Peak Hour | 790
AADT | 9,400
Crashes
Crash Analysis
139 crashes (2019 – 2023)
  High crashes of 34 in 2021 and 2023
  7 fatal crashes, 38 injury crashes (9 serious)
  5 fatal involved trucks, 3 were head-on
  ABOVE IS FOR –2 ONLY, GODFREY TO UPDATE TO ADD IN -1
Fatal Crash Locations

## Slide 5
5
Proposed Goals
INCREASE CAPACITY
  From 2-lane undivided to a 4-lane divided facility
PROVIDE SAFETY
  Address Safety Concerns
LOWER FATALITY RATE
  Eliminate fatalities (Target Zero) along SR 710
IMPROVE INTERSECTION
  Intersection realignment between Martin Highway and SE 126th Boulevard which will include adding a traffic signal
ACCOMMODATE TRAFFIC
  Intersection design will accommodate heavy truck traffic
Proposed Improvements:
  Enhance mobility, safety, emergency access, and truck movement
  Enhance Strategic Intermodal System (SIS) connectivity in the region
  Connect SR 70 and Port of Palm Beachs

## Slide 6
SR 710 from west of SE 126th Boulevard to Van Buren Avenue
Approximately 17.7 miles
Okeechobee and Martin Counties
Broken out into 4 segments
Corridor Overview
1
Realignment of SW Martin Hwy/CR 714 to Intersect with SE 126th Blvd and SR 710. Add Lanes & Reconstruct SR 710 from West of SE 126th Blvd to Okeechobee/Martin County Line – Okeechobee County
2
Add Lanes & Reconstruct SR 710 from Okeechobee /
Martin County Line to FPL Access Rd – Martin County
3
Add Lanes & Construct SR 710 from FPL Access Rd to Allapattah Rd – Martin County
4
Add Lanes & Construct SR 710 from CR 609/Allapattah Rd to Van Buren Ave – Martin County
MAP LEGEND
Lake Okeechobee
6

## Slide 7
7
Looking Back
Stakeholder Challenges
Right-of-way Impact Cost
High Construction Cost
High Utility Relocation Cost
Major Challenges
2011
2021
2024
FDOT Completed PD&E Study
Safety Study
Design commence for all segments

## Slide 8
8
Realignment of SW Martin Hwy/CR 714 to Intersect with SE 126th Blvd and SR 710
1
Financial Project Identification Number (FPID) #: 447555-1 and -2
Realignment of SW Martin Hwy/CR 714 to Intersect with SE 126th Blvd and SR 710
Add Signal
Realignment of SW Martin Hwy/CR 714 to Intersect with SE 126th Blvd and SR 710
Add Lanes & Reconstruct SR 710 from West of SE 126th Blvd to Okeechobee/Martin County Line – Okeechobee County
FPID #: 453333-3
SR 710 from west of SE 126th Blvd to E of CR 714/SW Martin Hwy
Notes: The purple portion highlighted on the screen covers FPID’s 447555-1, -2 & 453333-3 within both Okeechobee and Martin Counties. The proposed improvements include Realignment of SW Martin Hwy/CR 714 to Intersect with SE 126th Blvd and SR 710. Add Lanes & Reconstruct SR 710 from West of SE 126th Blvd to Okeechobee/Martin County Line

## Slide 9
9
9
Corridor Schedule for Segment
* Construction Letting is currently funded for fiscal year 2030.
4th Quarter
2025
Design Starts
Initial Plans
June
2024
PD&E Study for I-95 Widening from South of High Meadow Avenue to SR-70/Okeechobee Road | FM No. 422681-5-22-02 / 422681-6-22-02 | Ad No. 25442/43
2nd Quarter
2026
4th Quarter
2028
Public Information Meeting
Final Plans
3rd Quarter 2029*
Construction
Letting
Project schedule is subject to change.
1
Realignment of SW Martin Hwy/CR 714
to Intersect with SE 126th Blvd and SR 710
4th Quarter
2026
Right-of-Way
Starts
* Construction is currently funded for fiscal year 2030
Notes: These Design Segments are currently ongoing
Right-of-Way is scheduled for 2026
Utility Relocation is scheduled for 2029
Construction is scheduled for FY 2030

## Slide 10
FPID: 453333-2
SR 710 from Okeechobee/Martin County Line to FPL Access Rd
9.771 miles
10
SR 710 from CR 714 to Martin FPL Power Plan Rd
2
Notes: We going to focus on the -2 segment. _2 extends from Okeechobee/Martin County Line to FPL Access Rd within Martin County

## Slide 11
11
Existing Conditions
GAS MAIN
GAS MAIN
FPL DISTRIBUTION (To be replaced with new transmission poles)
FPL TRANSMISSION
Fiber
SR 710/SW Warfield Blvd is an existing two-lane (one lane in each direction), undivided, east/west roadway
Posted speed limit: 60 mph
Functional classification: Rural Principal Arterial

## Slide 12
South Florida Water Management District (SFWMD)
  Joint Agency Meeting to discuss permit criteria
FEC Railway
  Met to discuss impacts of future rail improvements
CSX Transportation
  Met to discuss right-of-way impacts
FPL Transmission
  Disposition of easement and potential impacts
Martin County
  Construction & Maintenance Agreement
12
Key Stakeholder Coordination

## Slide 13
13
PD&E Typical Section
Eastbound
Westbound
65 MPH/4-lane Divided/SIS Rural Principal Arterial
  C-2 Context Classification
  Class 3 Access
Shared Use Path (SUP) and Interceptor Ditch
40 FT
12’
SHLD.
(4’ PAVED)
SUP
& INTERCEPTOR DITCH
RELOCATION EASEMENT
MEDIAN
BORDER
50’
EXIST EASEMENT
100 FT
40 FT
40’
50’
EXIST EASEMENT
12’ SHLD.
(5’ PAVED)
VARIES 100’ – 200’
CSX R/W
LANES
(2) 12’
LANES
(2) 12’
BORDER
40’
12’ SHLD.
(5’ PAVED)
1
3
2
2
3
1
CHALLENGES
FPL Transmission Relocation
  Time consuming process
  Escalated costs
Right-of Way Needs
  276.560 ac
  3 Business Relocations
3
Notes: Big picture; FDOT R/W290

## Slide 14
Eastbound
Proposed Typical Section
Convert Exist 2-lane 2-way to New EB Roadway
Avoid reconstruction
Reduce new Impervious Area
Keep Exist Cross Drains
Dry Swale in FDOT R/W
Avoid FPL Relocation
1
2
3
Westbound
2
1
40 FT
12’
SHLD.
(4’ PAVED)
INTERCEPTOR DITCH
(2) 12’
MEDIAN
BORDER
50’
EXIST EASEMENT
40’
40’
50’
EXIST EASEMENT
12’ SHLD.
(5’ PAVED)
VARIES 100’ – 200’
CSX R/W
LANES
(2) 12’
LANES
BORDER
5’ -40’
12’ SHLD.
(5’ PAVED)
25’ – 30’
REFINEMENTS
3
BENEFITS
Avoid FPL relocation
No business relocations anticipated
Reduce construction costs
Reduce stormwater treatment
Reduce wetland impacts
20’
SUP
Notes: Reduced FDOT 196’

## Slide 15
15
Proposed Typical Section
NEW FDOT R/W
CSX R/W OF INTEREST TO FDOT
INTERCEPTOR DITCH CONSTRUCTION AND MAINTENANCE EASEMENT
FPL EASEMENT (Subordination of FPL Transmission to FDOT)
EXISTING FDOT R/W
Stakeholder coordination
    High construction costs
    Construction & Maintenance Agreements:
      Interceptor ditch
      Shared use path
      Frontage road
Challenges:
Notes: Four Lanes Divided Roadway (Two Lanes in each direction)​
65 mph Design Speed​
Strategic Intermodal System (SIS)​
Rural Principal Arterial​
C-2 Context Classification

## Slide 16
* Construction Letting is currently funded for fiscal year 2030.
PD&E Study for I-95 Widening from South of High Meadow Avenue to SR-70/Okeechobee Road | FM No. 422681-5-22-02 / 422681-6-22-02 | Ad No. 25442/43
3rd Quarter 2030*
Construction Letting
* Construction is currently not funded
Project schedule is subject to change.
Corridor Schedule for Segment
2
2nd Quarter
2030
Final Plans
3rd Quarter
2029
2nd Public Info Meeting
4th Quarter
2028
Utility Relocation Starts
1st Quarter
2027
Right-of-Way Starts
4th Quarter
2026
1st Public Info Meeting
4th Quarter
2025
Initial Plans
June
2024
Design Starts
SR 710 from CR 714 to FPL Access Rd
Notes: 2 public meetings: before R/W and after R/W: combine between -1 and -2
Utility relocation starts

## Slide 17
17
SR 710 from FPL Access Rd to Allapattah Rd
3
FPID: 453333-1
SR 710 from FPL Access Rd to Allapattah Rd
5.201 miles
Notes: We going to focus on the -2 segment. _2 extends from Okeechobee/Martin County Line to FPL Access Rd within Martin County

## Slide 18
18
18
* Construction Letting is currently funded for fiscal year 2030.
4th Quarter
2025
Design Starts
Initial Plans
May
2024
PD&E Study for I-95 Widening from South of High Meadow Avenue to SR-70/Okeechobee Road | FM No. 422681-5-22-02 / 422681-6-22-02 | Ad No. 25442/43
4th Quarter
2026
3rd Quarter
2030
Public Information Meeting
Final Plans
1st Quarter 2031*
Construction
Letting
Project schedule is subject to change.
3
1st Quarter
2027
Right-of-Way
Starts
Corridor Schedule for Segment
* Construction is currently not funded
SR 710 from FPL Access Rd to Allapattah Rd
Notes: Appraisal date?

## Slide 19
19
SR 710 from CR 609/Allapattah Rd to Van Buren Ave
4
FPID: 453333-4
SR 710 from CR 609/Allapattah Rd to Van Buren
0.770 miles
Notes: We going to focus on the -2 segment. _2 extends from Okeechobee/Martin County Line to FPL Access Rd within Martin County

## Slide 20
20
20
* Construction Letting is currently funded for fiscal year 2030.
4th Quarter
2025
Design Starts
Initial Plans
May
2024
PD&E Study for I-95 Widening from South of High Meadow Avenue to SR-70/Okeechobee Road | FM No. 422681-5-22-02 / 422681-6-22-02 | Ad No. 25442/43
1st Quarter
2027
3rd Quarter
2027
Public Information Meeting
Final Plans
July 2029*
Construction
Letting
Project schedule is subject to change.
4
1st Quarter
2027
Right-of-Way
Starts
Corridor Schedule for Segment
* Construction is currently not funded
SR 710 from CR 609/Allapattah Rd to Van Buren Ave
Notes: Appraisal date?

## Slide 21
21
National Distracted Driving Awareness Month

## Slide 22
Robert Lopes, P.E.
Florida Department of Transportation (FDOT) Project Manager
FDOT District Four
3400 West Commercial Boulevard
Fort Lauderdale, FL 33309
robert.lopes@dot.state.fl.us
(954) 777-4425
22
Contact Information
Scan the QR Code to visit the project website at
https://www.d4fdot.com/tcfdot/sr_710_projects.asp for more information about this project or to sign up to be on the mailing list.

## Slide 23
23
Questions / Comments

## Slide 24
24
Proposed Typical Section
NEW FDOT R/W
CSX R/W OF INTEREST TO FDOT
INTERCEPTOR DITCH CONSTRUCTION AND MAINTENANCE EASEMENT
FPL EASEMENT (Subordination of FPL Transmission to FDOT)
EXISTING FDOT R/W
Stakeholder coordination
    High construction costs
    Construction & Maintenance Agreements:
      Interceptor ditch
      Shared use path
      Frontage road
Challenges:
Notes: Four Lanes Divided Roadway (Two Lanes in each direction)​
65 mph Design Speed​
Strategic Intermodal System (SIS)​
Rural Principal Arterial​
C-2 Context Classification