0081002

All Jobs


PROSECUTION AND PROGRESS
(REV 4-2-19)

Subarticle 8-10.2 is deleted and the following substituted:

8-10.2 Amount of Liquidated Damages: Applicable liquidated damages are the amounts established in the following schedule:

Original Contract Amount
Daily Charge Per Calendar Day
$50,000 and under
$1,015
Over $50,000 but less than $250,000
$1,045
$250,000 but less than $500,000
$1,170
$500,000 but less than $2,500,000
$1,690
$2,500,000 but less than $5,000,000
$2,579
$5,000,000 but less than $10,000,000
$3,756
$10,000,000 but less than $15,000,000
$4,344
$15,000,000 but less than $20,000,000
$5,574
$20,000,000 and over
 $10,203 plus 0.00005 of any
amount over $20 million (Round to nearest whole dollar)
