## Title
FDOT STAFF HOUR ESTIMATION
WORKSHEET PACKAGE
July 2019

## Disclaimer
FDOT Staff Hour Worksheet Package
The staff hour ranges presented on the following sheets represent the work effort that may be expected for each specific task on typical projects. These hourly ranges vary from a simple project (lower end of range) to a complicated project (upper end of range). The ranges represent neither the minimum nor maximum hours that may be negotiated for a particular task on a project. Hours below or above these ranges may be applicable based upon constraints and requirements that are specific to the project.

## Spreadsheet instructions
Subconsultant Instructions for Submittal of Staffhours for a Technical Proposal
1 | In spreadsheet tab "Project Information" - add as much information as possible; minimum data is FPID, Federal Aid No., Project Name, name of consultant and county name.
2 | In spreadsheet tab "Staff Hour Summary--Grand Total" - add staff classifications in columns C through N, row 10 (for example Project Manager, Chief Engineer, Landscape Architect, Technician, etc.)
3 | In tab "Summary" - enter name of firm in cell C4.
4 | Complete appropriate staff hour sheets for work being performed in individual discipline sheets (tabs 3 through 36). Add name of estimator to the top of each sheet.
5 | In tab "Staff Hour Summary - Firm" - enter distribution of hours by classification for each task in rows 64 through 98.
Subconsultant Instructions for Submittal of Staffhours for a Fee Proposal
1 | Complete the information in Steps 1 - 5 above.
2 | In tab "Fee Sheet - Sub" - enter rates for employee classifications in row 9; subconsultants project number in cell O4; and name of estimator in cell O6.
3 | Also in "Fee Sheet - Sub" - enter Overhead Rate in cell N49, Operating Margin in N50, and FCCM in N51.
4 | Add an EXPENSE sheet to this workbook (this sheet is not included in spreadsheet). Reference expense amount into "Fee Sheet - Sub" cell N52.
Prime Consultant Instructions for Submittal of Staffhours for a Technical Proposal
1 | In spreadsheet tab "Project Information" - add as much information as possible; minimum data is FPID, Federal Aid No., Project Name, name of consultant and county name.
2 | In tab "Staff Hour Summary--Grand Total" - add staff classifications in columns C through N, row 10 (for example Project Manager, Chief Engineer, Landscape Architect, Technician, etc.). After classifications are added for prime, add in all other classifications from Subconsultants. Additional columns may be required if over 12 classifications are used.
3 | In tab "Summary" - enter name of prime firm in cell C4. Add names of subconsultants. Add hours from each subconsultant in respective disciplines.
4 | Complete appropriate staff hour sheets for work being performed in individual discipline sheets (tabe 3 through 36). Add name of estimator to the top of each sheet.
5 | In tab "Staff Hour Summary - Firm" - enter distribution of hours by classification for each task in rows 64 through 98.
6 | In tab "Staff Hour Summary -- Grand Total" - enter distribution of hours by classification for each task in rows 65 through 99. Use distributions provided by subconsultants for tasks being done solely by subconsultant. For tasks with both prime and subconsultant hours - use either a blended percent distribution or just the primes distribution.
Prime Consultant Instructions for Submittal of Staffhours for a Fee Proposal
1 | Complete the information in Steps 1 - 6 above.
2 | In tab "Fee Sheet - Prime" - enter rates for employee classifications in row 9; prime consultant project number in cell O4; and name of estimator in cell O6. Also add fees for each subconsultant in cells Q55-Q66.
3 | Also in "Fee Sheet - Prime" - enter Overhead Rate in cell N49, Operating Margin in N50, and FCCM in N51.
4 | Add an EXPENSE sheet to this workbook. Reference expense amount into "Fee Sheet - Prime" cell N52.
5 | Add subconsultant staff hours to "CITS".
Spreadsheets to be Submitted with Technical Proposals
1 | Requirements will vary by District. A typical submittal would be the "Summary", "Staff Hour Summary -- Grand Total" and "Staff Hour Summary-Firm" completed by the prime consultant along with the "Staff Hour Summary - Firm" completed by each subconsultant.

## Project Information
Financial Project Identification Number: | 999999-1-52-01 |  |  |  |  | Federal Aid Project Identification Number: |  |  |  |  | 54321
Name of Prime / Subconsultant: | Enter name of prime or subconsultant | [8 empty] | County: | enter name of county
Project Description: | Enter project name & description
Begin Milepost: |  |  | End Milepost: |  |  |  | Project Length: |  |  | Miles
Number of Lanes: |  |  | Typical Section: |  |  |  | (Urban / Rural / Int.) |  |  | Lane Configuration: |  | (Divided / Undivided)
Project Type: |  | (Minor / Major) |  | Access Management Classification: | [5 empty] | Roadway Classification: |  | (NHS/FIHS/Off Sys.)
CAP Level: |  |  |  | TTCP Level: |  |  |  |  | Survey Level:
Design Variations: | 1. |  |  |  | Design Exceptions: |  |  | 1.
| 2. | [6 empty] | 2.
| 3. | [6 empty] | 3.
| 4. | [6 empty] | 4.
| 5. | [6 empty] | 5.
Proposed Design Contract Time: |  | months/days |  |  |  | Date of Negotiation: |  |  | Context Classification:
Project Activity: | Estimated By: | [6 empty] | Negotiated By: (name - firm)
| Consultant |  |  |  | FDOT |  |  | Consultant |  |  | FDOT
3. Project Common & Project General Tasks | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
4. Roadway Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
5. Roadway Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
6a. Drainage Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
6b. Drainage Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
7. Utilities | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
8. Environmental Permits and Env. Clearances | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
9. Structures Summary | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
10. Structures - Bridge Development Report | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
11. Structures - Temporary Bridge | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
12. Structures - Short Span Concrete | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
13. Structures - Medium Span Concrete | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
14. Structures - Structural Steel | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
15. Structures - Segmental Concrete | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
16. Structures - Movable Span | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
17. Structures - Retaining Walls | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
18. Structures - Miscellaneous | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
19. Signing and Pavement Marking Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
20. Signing and Pavement Marking Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
21. Signalization Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
22. Signalization Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
23. Lighting Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
24. Lighting Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
25. Landscape Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
26. Landscape Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
27. Survey | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
28. Photogrammetry | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
29. Mapping | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
30. Terrestrial Mobile LiDAR | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
31. Architecture Development | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
32. Noise Barriers Impact Design Assessment | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
33. Intelligent Transportation Systems Analysis | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
34. Intelligent Transportation Systems Plans | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
35. Geotechnical | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office
36. 3D Modeling | Enter name & firm |  |  |  | Enter name & office |  |  | Enter name & firm |  |  | Enter name & office

## Summary
Name of Consultant: |  | Enter name of prime or subconsultant | [8 empty] | Enter project name & description
999999-1-52-01
Project Staff Hours
Activity No. | Activity | Enter Firm Name | Enter Name Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6 | Sub 7 | Sub 8 | Sub 9 | Sub 10 | Sub 11 | Sub 12 | Total Hours
3 | Project Common and General Tasks | 0 | [12 empty] | 0
4 | Roadway Analysis | 0 | [12 empty] | 0
5 | Roadway Plans | 0 | [12 empty] | 0
6a | Drainage Analysis | 0 | [12 empty] | 0
6b | Drainage Plans | 0 | [12 empty] | 0
7 | Utilities | 0 | [12 empty] | 0
8 | Env. Permits and Env. Clearances | 0 | [12 empty] | 0
9 | Structures - Summary, Misc. Tasks, Dwgs. | 0 | [12 empty] | 0
10 | BDR | 0 | [12 empty] | 0
11 | Temporary Bridge | 0 | [12 empty] | 0
12 | Short Span Concrete Bridge | 0 | [12 empty] | 0
13 | Medium Span Concrete Bridge | 0 | [12 empty] | 0
14 | Structural Steel Bridge | 0 | [12 empty] | 0
15 | Segmental Concrete Bridge | 0 | [12 empty] | 0
16 | Movable Span | 0 | [12 empty] | 0
17 | Retaining Walls | 0 | [12 empty] | 0
18 | Miscellaneous Structures | 0 | [12 empty] | 0
19 | Signing & Pavement Marking Analysis | 0 | [12 empty] | 0
20 | Signing & Pavement Marking Plans | 0 | [12 empty] | 0
21 | Signalization Analysis | 0 | [12 empty] | 0
22 | Signalization Plans | 0 | [12 empty] | 0
23 | Lighting Analysis | 0 | [12 empty] | 0
24 | Lighting Plans | 0 | [12 empty] | 0
25 | Landscape Analysis | 0 | [12 empty] | 0
26 | Landscape Plans | 0 | [12 empty] | 0
27 | Survey - Field and Office Support | 0 | [12 empty] | 0
28 | Photogrammetry | 0 | [12 empty] | 0
29 | Mapping | 0 | [12 empty] | 0
30 | Terrestrial Mobile LiDAR | 0 | [12 empty] | 0
31 | Architecture Development | 0 | [12 empty] | 0
32 | Noise Barriers Impact Design Assessment | 0 | [12 empty] | 0
33 | ITS Analysis | 0 | [12 empty] | 0
34 | ITS Plans | 0 | [12 empty] | 0 | check
35 | Geotechnical | 0 | [12 empty] | 0
36 | 3D Modeling | 0 | [12 empty] | 0
Project Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Survey Field Crew Days | 0 | [12 empty] | 0
Notes: | 1. Staff hours for prime consultant come directly from each discipline's worksheet.
2. Staff hours for subconsultants are to be entered manually into columns D through O.
3. For workbooks prepared by subconsultants, their project hours will be totaled in column C.

## Staff Hour Summary--Grand Total
ESTIMATE OF WORK EFFORT FOR TECHNICAL PROPOSALS - GRAND TOTAL
Financial Project Number: | 999999-1-52-01 | [10 empty] | Project Name: | Enter project name & description
FAP Number: | 54321 | [7 empty] | Date: | 2019-08-26 |  | Name of Consultant: | Enter name of prime or subconsultant
WORK ACTIVITY | Hours from "Summary" sheet
[7 empty] | EMPLOYEE CLASSIFICATION | [6 empty] | TOTAL
[14 empty] | STAFF HOURS |  | ON CADD
| Grand Total | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | RANGE
| Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  |  | PERCENT
3. Project General and Project Common Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Roadway Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. Roadway Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6a. Drainage Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6b. Drainage Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. Environmental Permits and Env. Clearances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. Structures - Bridge Development Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11. Structures - Temporary Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12. Structures - Short Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13. Structures - Medium Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14. Structures - Structural Steel Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15. Structures - Segmental Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16. Structures - Movable Span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17. Structures - Retaining Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18. Structures - Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19. Signing & Pavement Marking Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20. Signing & Pavement Marking Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21. Signalization Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22. Signalization Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23. Lighting Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24. Lighting Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25. Landscape Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26. Landscape Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27. Survey (Field & Office Support) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28. Photogrammetry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29. Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30. Terrestrial Mobile LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31. Architecture Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32. Noise Barriers Impact Design Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33. Intelligent Transportation Systems Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34. Intelligent Transportation Systems Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35. Geotechnical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36. 3D Modeling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Field Survey Estimate:
Notes: | [8 empty] | 0 | 4-person crew days |  | (Prime Consultant) |  | 0 | 0
1. This worksheet provides the distribution of the grand total staff hours for a project.
2. Percentages for staff hour distribution by classification are entered below in rows 65 to 99 of this sheet.
3. Total Staff Hours (column O) may not match staff hours from Summary worksheet (column B) due to rounding. Staff hours calculated for employee classifications are to be adjusted so totals in columns B and O match.
4. Formulas under "Total Staff Hours Range" (columns O & P) may be adjusted to provide desired range.
5. This spreadsheet to be provided in Technical Proposals for Districts that require a breakdown of hours by classification.
ESTIMATE OF WORK EFFORT FOR TECHNICAL PROPOSALS - GRAND TOTAL
Financial Project Number: | 999999-1-52-01 | [11 empty] | Project Name: | Enter project name & description
FAP Number: | 54321 | [7 empty] | Date: | 2019-08-26 |  |  | Name of Consultant: | Enter name of prime or subconsultant
Staff Hour Distribution Percentages - Grand Total
| Hours from "Summary" sheet Grand Total | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | Total
3. Project General and Project Common Tasks | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4. Roadway Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5. Roadway Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6a. Drainage Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6b. Drainage Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7. Utilities | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8. Environmental Permits and Env. Clearances | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10. Structures - Bridge Development Report | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11. Structures - Temporary Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12. Structures - Short Span Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13. Structures - Medium Span Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14. Structures - Structural Steel Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15. Structures - Segmental Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16. Structures - Movable Span | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17. Structures - Retaining Walls | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18. Structures - Miscellaneous | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
19. Signing & Pavement Marking Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
20. Signing & Pavement Marking Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
21. Signalization Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
22. Signalization Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
23. Lighting Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
24. Lighting Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
25. Landscape Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
26. Landscape Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
27. Survey (Field & Office Support) | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
28. Photogrammetry | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
29. Mapping | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30. Terrestrial Mobile LiDAR | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31. Architecture Development | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
32. Noise Barriers Impact Design Assessment | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
33. Intelligent Transportation Systems Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
34. Intelligent Transportation Systems Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
35. Geotechnical | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
36. 3D Modeling | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Note: | This spreadsheet to be used in Technical Proposal for Districts requiring the Grand Total hours be provided along with percentage distribution by classification.

## Staff Hour Summary - Firm
ESTIMATE OF WORK EFFORT FOR TECHNICAL PROPOSALS - FIRM TOTAL
Financial Project Number: | 999999-1-52-01 | [11 empty] | Project Name: | Enter project name & description
FAP Number: | 54321 | [7 empty] | Date: | 2019-08-26 |  |  | Name of Consultant: | Enter name of prime or subconsultant
Hours from "Summary" sheet
WORK | [6 empty] | EMPLOYEE CLASSIFICATION | [6 empty] | TOTAL
ACTIVITY | [13 empty] | STAFF HOURS |  | ON CADD
| Firm Total | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | RANGE
| Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  |  | PERCENT
3. Project General and Project Common Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Roadway Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. Roadway Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6a. Drainage Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6b. Drainage Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. Environmental Permits,and Env. Clearances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. Structures - Bridge Development Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11. Structures - Temporary Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12. Structures - Short Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13. Structures - Medium Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14. Structures - Structural Steel Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15. Structures - Segmental Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16. Structures - Movable Span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17. Structures - Retaining Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18. Structures - Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19. Signing & Pavement Marking Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20. Signing & Pavement Marking Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21. Signalization Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22. Signalization Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23. Lighting Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24. Lighting Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25. Landscape Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26. Landscape Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27. Survey (Field & Office Support) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28. Photogrammetry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29. Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30. Terrestrial Mobile LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31. Architecture Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32. Noise Barriers Impact Design Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33. Intelligent Transportation Systems Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34. Intelligent Transportation Systems Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35. Geotechnical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36. 3D Modeling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Field Survey Estimate:
Notes: | [8 empty] | 0 | 4-person crew days |  | FIRM TOTAL |  | 0 | 0
1. This worksheet provides the distribution of a firm's total staff hours for a project.
2. Percentages for staff hour distribution by classification are entered below in rows 64 to 98 of this sheet.
3. Total Staff Hours (column O) may not match staff hours from Summary worksheet (column B) due to rounding. Staff hours calculated for employee classifications are to be adjusted so totals in columns B and O match.
4. Formulas under "Total Staff Hours Range" (columns O & P) may be adjusted to provide desired range.
ESTIMATE OF WORK EFFORT FOR TECHNICAL PROPOSALS - FIRM TOTAL
Financial Project Number: | 999999-1-52-01 | [11 empty] | Project Name: | Enter project name & description
FAP Number: | 54321 | [7 empty] | Date: | 2019-08-26 |  |  | Name of Consultant: | Enter name of prime or subconsultant
Staff Hour Distribution Percentages - Firm Total
| Hours from "Summary" sheet Firm Total | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | Total
3. Project General and Project Common Tasks | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4. Roadway Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5. Roadway Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6a. Drainage Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6b. Drainage Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7. Utilities | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8. Environmental Permits,and Env. Clearances | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10. Structures - Bridge Development Report | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11. Structures - Temporary Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12. Structures - Short Span Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13. Structures - Medium Span Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14. Structures - Structural Steel Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15. Structures - Segmental Concrete Bridge | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16. Structures - Movable Span | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17. Structures - Retaining Walls | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18. Structures - Miscellaneous | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
19. Signing & Pavement Marking Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
20. Signing & Pavement Marking Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
21. Signalization Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
22. Signalization Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
23. Lighting Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
24. Lighting Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
25. Landscape Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
26. Landscape Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
27. Survey (Field & Office Support) | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
28. Photogrammetry | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
29. Mapping | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30. Terrestrial Mobile LiDAR | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31. Architecture Development | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
32. Noise Barriers Impact Design Assessment | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
33. Intelligent Transportation Systems Analysis | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
34. Intelligent Transportation Systems Plans | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
35. Geotechnical | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
36. 3D Modeling | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Fee Sheet - Prime
ESTIMATE OF WORK EFFORT AND COST - PRIME CONSULTANT
Name of Project: | Enter project name & description | [11 empty] | Consultant Name: | Enter name of prime or subconsultant
County: | enter name of county | [11 empty] | Consultant No.: | enter consultants proj. number
FPN: | 999999-1-52-01 | [11 empty] | Date: | 2019-08-26
FAP No.: | 54321 | [11 empty] | Estimator: | insert name
Staff Classification | Total Staff Hours From "SH Summary - Firm" | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | SH | Salary | Average
[14 empty] | By | Cost By | Rate Per
|  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Activity | Activity | Task
3. Project General and Project Common Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
4. Roadway Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
5. Roadway Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6a. Drainage Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6b. Drainage Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
7. Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
8. Environmental Permits,and Env. Clearances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
10. Structures - Bridge Development Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
11. Structures - Temporary Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
12. Structures - Short Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
13. Structures - Medium Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
14. Structures - Structural Steel Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
15. Structures - Segmental Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
16. Structures - Movable Span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
17. Structures - Retaining Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
18. Structures - Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
19. Signing & Pavement Marking Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
20. Signing & Pavement Marking Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
21. Signalization Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
22. Signalization Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
23. Lighting Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
24. Lighting Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
25. Landscape Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
26. Landscape Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
27. Survey (Field & Office Support) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
28. Photogrammetry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
29. Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30. Terrestrial Mobile LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
31. Architecture Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
32. Noise Barriers Impact Design Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
33. Intelligent Transportation Systems Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
34. Intelligent Transportation Systems Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
35. Geotechnical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
36. 3D Modeling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Staff Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Staff Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
[14 empty] | Check = | 0
[6 empty] | Survey Field Days by Subconsultant |  |  |  | SALARY RELATED COSTS: | [5 empty] | 0
[6 empty] | 4 - Person Crew: |  |  |  | OVERHEAD: |  |  | 0% |  |  | 0
[10 empty] | OPERATING MARGIN: |  |  | 0% |  |  | 0
| Notes: | [8 empty] | FCCM (Facilities Capital Cost Money): |  |  | 0% |  |  | 0
| 1. This sheet to be used by Prime Consultant to calculate the Grand Total fee. | [8 empty] | EXPENSES: |  |  | 0% |  |  | 0
| 2. Manually enter fee from each subconsultant. Unused subconsultant rows may be hidden. | [8 empty] | Survey (Field - if by Prime) |  | 0 | 4-person crew days @ | 0 | / day | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Subconsultant: | Enter Name Sub 1 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 2 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 3 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 4 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 5 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 6 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 7 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 8 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 9 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 10 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 11 |  |  |  |  | 0
[10 empty] | Subconsultant: | Sub 12 |  |  |  |  | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Geotechnical Field and Lab Testing | [5 empty] | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Optional Services | [5 empty] | 0
[10 empty] | GRAND TOTAL ESTIMATED FEE: | [5 empty] | 0

## Fee Sheet - Sub
ESTIMATE OF WORK EFFORT AND COST - SUBCONSULTANT
Name of Project: | Enter project name & description | [11 empty] | Consultant Name: | Enter name of prime or subconsultant
County: | enter name of county | [11 empty] | Consultant No.: | enter consultants proj. number
FPN: | 999999-1-52-01 | [11 empty] | Date: | 2019-08-26
FAP No.: | 54321 | [11 empty] | Estimator: | insert name
Staff Classification | Total Staff Hours From "SH Summary - Firm" | Project Manager | Staff Classi- fication 2 | Staff Classi- fication 3 | Staff Classi- fication 4 | Staff Classi- fication 5 | Staff Classi- fication 6 | Staff Classi- fication 7 | Staff Classi- fication 8 | Staff Classi- fication 9 | Staff Classi- fication 10 | Staff Classi- fication 11 | Staff Classi- fication 12 | SH | Salary | Average
[14 empty] | By | Cost By | Rate Per
|  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Activity | Activity | Task
3. Project General and Project Common Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
4. Roadway Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
5. Roadway Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6a. Drainage Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
6b. Drainage Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
7. Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
8. Environmental Permits,and Env. Clearances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
9. Structures - Misc. Tasks, Dwgs, Non-Tech. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
10. Structures - Bridge Development Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
11. Structures - Temporary Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
12. Structures - Short Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
13. Structures - Medium Span Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
14. Structures - Structural Steel Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
15. Structures - Segmental Concrete Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
16. Structures - Movable Span | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
17. Structures - Retaining Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
18. Structures - Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
19. Signing & Pavement Marking Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
20. Signing & Pavement Marking Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
21. Signalization Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
22. Signalization Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
23. Lighting Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
24. Lighting Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
25. Landscape Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
26. Landscape Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
27. Survey (Field & Office Support) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
28. Photogrammetry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
29. Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30. Terrestrial Mobile LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
31. Architecture Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
32. Noise Barriers Impact Design Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
33. Intelligent Transportation Systems Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
34. Intelligent Transportation Systems Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
35. Geotechnical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
36. 3D Modeling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Staff Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Staff Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
[14 empty] | Check = | 0
[10 empty] | SALARY RELATED COSTS: | [5 empty] | 0
[10 empty] | OVERHEAD: |  |  | 0% |  |  | 0
[10 empty] | OPERATING MARGIN: |  |  | 0% |  |  | 0
| Notes: | [8 empty] | FCCM (Facilities Capital Cost Money): |  |  | 0% |  |  | 0
| 1. This sheet to be used by Subconsultant to calculate its fee. | [8 empty] | EXPENSES: |  |  | 0% |  |  | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Survey (Field) |  | 0 | 4-person crew days @ | 0 | / day | 0
[10 empty] | Geotechnical Field and Lab Testing | [5 empty] | 0
[10 empty] | SUBTOTAL ESTIMATED FEE: | [5 empty] | 0
[10 empty] | Optional Services | [5 empty] | 0
[10 empty] | GRAND TOTAL ESTIMATED FEE: | [5 empty] | 0

## 3. Project General Tasks
Estimator: | [5 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
3.1 | Public Involvement
3.1.1 | Community Awareness Plan | LS | 1 | 0 | 0
3.1.2 | Notifications | LS | 1 | 0 | 0
3.1.3 | Preparing Mailing Lists | LS | 1 | 0 | 0
3.1.4 | Median Modification Letters | LS | 1 | 0 | 0
3.1.5 | Driveway Modification Letters | LS | 1 | 0 | 0
3.1.6 | Newsletters | LS | 1 | 0 | 0
3.1.7 | Renderings and Fly Throughs | LS | 1 | 0 | 0
3.1.8 | PowerPoint Presentation | LS | 1 | 0 | 0
3.1.9 | Public Meeting Preparations | LS | 1 | 0 | 0
3.1.10 | Public Meeting Attendance/Followup | LS | 1 | 0 | 0
3.1.11 | Other Agency Meetings | LS | 1 | 0 | 0
3.1.12 | Web Site | LS | 1 | 0 | 0
3.1 Public Involvement Subtotal |  |  |  |  | 0
3.2 | Joint Project Agreements | EA | 0 | 0 | 0
3.3 | Specifications Package Preparation | LS | 1 | 0 | 0
3.4 | Contract Maintenance and Project Documentation | LS | 1 | 0 | 0
3.5 | Value Engineering (Multi-Discipline Team) Review | LS | 1 | 0 | 0
3.6 | Prime Consultant Project Manager Meetings | LS | 1 | 0 | 0 | See listing below
3.7 | Plans Update | LS | 1 | 0 | 0
3.8 | Post Design Services | LS | 1 | 0 | 0
3.9 | Digital Delivery | LS | 1 | 0 | 0
3.1 | Risk Assessment Workshop | LS | 1 | 0 | 0
3.11 | Railroad, Transit, and/or Airport Coordination | LS | 1 | 0 | 0
3.11.1 | Aeronautical Evaluation | LS | 1 | 0 | 0
3.12 | Landscape and Existing Vegetation Coordination | LS | 1 | 0 | 0
3.13 | Other Project General Tasks | LS | 1 | 0 | 0
3. Project Common and Project General Tasks Total |  |  |  |  | 0
3.6 - List of Project Manager Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments
Roadway Analysis |  | EA | 0 | 0 | 0
Drainage |  | EA | 0 | 0 | 0
Utilities |  | EA | 0 | 0 | 0
Environmental |  | EA | 0 | 0 | 0
Structures |  | EA | 0 | 0 | 0
Signing & Pavement Marking |  | EA | 0 | 0 | 0
Signalization |  | EA | 0 | 0 | 0
Lighting |  | EA | 0 | 0 | 0
Landscape Architecture |  | EA | 0 | 0 | 0
Survey |  | EA | 0 | 0 | 0
Photogrammetry |  | EA | 0 | 0 | 0
ROW & Mapping |  | EA | 0 | 0 | 0
Terrestrial Mobile LiDAR |  | EA | 0 | 0 | 0
Architecture |  | EA | 0 | 0 | 0
Noise Barriers |  | EA | 0 | 0 | 0
ITS Analysis |  | EA | 0 | 0 | 0
Geotechnical |  | EA | 0 | 0 | 0
Progress Meetings |  | EA | 0 | 0 | 0
Phase Reviews |  | EA | 0 | 0 | 0
Field Reviews |  | EA | 0 | 0 | 0
Total Project Manager Meetings |  |  | 0 |  | 0 | Total PM Meeting Hours carries to Task 3.6 above
Notes:
1. If the hours per meeting vary in length (hours) enter the average in the hour/unit column.
2. Do not double count agency meetings between permitting agencies.
3. Project manager meetings are calculated in each discipline sheet and brought forward to Column D, except for Photogrammetry.

## Selective C&G Guidelines
SELECTIVE CLEARING AND GRUBBING GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on projects that require selective clearing and grubbing. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
Lower Range
1. Complexity of ROW Adjacent to Site: No existing vegetation |  |  | 6. Number of Species to Eradicate/Remove: 1 to 3 Species
2. Roadway Type: Existing roadway. |  |  | 7. Number of Methods of Eradication/Removal: 1 Method
3. Roadway Elements: Minor intersections. |  |  | 8. Sensitive Sites: None.
4. Utility Coordination: Minimum. |  |  | 9. Tree Relocation: Minor < 10 units
5. Size of Site: Under 5 acres |  |  | 10. Other Considerations
Middle Range
1. Complexity of ROW Adjacent to Site: Minor screening or buffering impacts |  |  | 6. Number of Species to Eradicate/Remove: 4 to 6 Species
2. Roadway Type: Roadway widening. |  |  | 7. Number of Methods of Eradication/Removal: 2 Methods
3. Roadway Elements: Major Intersections, Standard interchanges. |  |  | 8. Sensitive Sites: Part of the site is sensitive.
4. Utility Coordination: Moderate. |  |  | 9. Tree Relocation: Moderate 10 - 20 units
5. Size of Site: 5-25 acres. |  |  | 10. Other Considerations
Upper Range
1. Complexity of ROW: Significant screening or buffering impacts. Commitments and/or Stakeholders involved. |  |  | 6. Number of Species to Eradicate/Remove: 7+ Species
2. Roadway Type: New roadway alignment. |  |  | 7. Number of Methods of Eradication/Removal: 3+ Methods
3. Roadway Elements: Multiple-level interchanges. |  |  | 8. Sensitive Sites: A majority of the site is sensitive and/or Environmental permits.
4. Utility Coordination: Extensive. |  |  | 9. Tree Relocation: Major or complex > 20 units
5. Size of Site: 25+ acres. |  |  | 10. Other Considerations
The following matrix for the Task 4 and 5, Roadway Analysis, work activities was developed as part of the Staff Hour Basis to help Consultant and FDOT project managers determine the overall level of complexity of a project with respect to the selective clearing and grubbing component. The Consultants and the Department will use the matrix (see below) to determine the appropriate level of complexity, based on the project scope, for each Task element. The Consulants and the Department will then use the negotiated level of complexity (Lower, Middle, or Upper) results to determine where, in each defined staff hour range, the level of design effort should fall.
STAFF-HOUR RANGE FOR SELECTIVE CLEARING AND GRUBBING ANALYSIS
PROJECT SCOPE | LOWER | MIDDLE | UPPER | RATING | COMMENTS
Complexity of ROW | No screening or buffering impacts | Minor screening or buffering impacts | Significant screening or buffering impacts, Commitments/Stakeholders involved
| j k l | m n o | p q r
Roadway Type | Existing Roadway | Roadway Widening | New Roadway Alignment
| j k l | m n o | p q r
Roadway Elements | Minor Intersections | Standard intersections and Interchanges | Complex intersections and Multiple-Level Interchanges
| j k l | m n o | p q r
Utility Coordination | Minimum | Moderate | Extensive
| j k l | m n o | p q r
Size of Site (Entire project limits) | Small (Under 5 acre) | Medium (5-25 acres) | Large (over 25 acres)
| j k l | m n o | p q r
Number of Species to Eradicate/Preserve | 1-3 Plant Species | 4-6 Plant Species | 7+ Plant Species
| j k l | m n o | p q r
Number of Methods of Eradication/Removal/Preservation | 1 Method | 2 Methods | 3+ Methods
| j k l | m n o | p q r
Sensitive Sites (Wetlands, Submerged, Dune, Sensitive Vegetation, Environmental Permits Requried) | No sensitive sites present | Part of the project site is sensitive | A large majority of the project site is sensitive
| j k l | m n o | p q r
Tree/Palm Relocation | < 10 Trees Relocated | 10 - 20 Trees Relocated | >20 Relocated
| j k l | m n o | p q r
Other Considerations (Explain)
| j k l | m n o | p q r
Adjacent Property Screening Concerns | None | Limited | Extensive
| j k l | m n o | p q r
Total Points |  |  |  | 0
STAFF-HOUR RANGES
Lower Range - Total Points <30
Middle Range - Total Points 30-50
Upper Range - Total Points >50

## Tree Disposition Guidelines
TREE DISPOSITION PLAN GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on projects that require creation of the Tree Disposition Plans. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
Note: 'Tree' refers to both Trees and Palms
Lower Range
1. Number of Existing Tree Relocates (Naturally Occuring): None
2. Number of Existing Landscape Material to be Relocated: None
3. Number of Trees Root Pruned: None
4. Size of Site (Entire project limits): Under 5 acres
5. Number of Tree Preservation Areas: 1-3 areas
6. Number of Trees Inventoried and Preserved: 0-10
7. Other Considerations
Middle Range
1. Number of Existing Tree Relocates (Naturally Occuring Trees): 0-5
2. Number of Existing Landscape Material to be Relocated: 0-5
3. Number of Trees Root Pruned: 0-5
4. Size of Site (Entire project limits): 5-25 acres
5. Number of Tree Preservation Areas: 4-6 areas
6. Number of Trees Inventoried and Preserved: 10-20
7. Other Considerations
Upper Range
1. Number of Existing Tree Relocates (Naturally Occuring): 6+
2. Number of Existing Landscape Material to be Relocated: 6+
3. Number of Trees Root Pruned: 6+
4. Size of Site (Entire project limits): over 25 acres
5. Number of Tree Preservation Areas: 7+
6. Number of Trees Inventoried and Preserved:20+
7. Other Considerations
The following matrix for the Task 4 and 5, Roadway Analysis, work activities was developed as part of the Staff Hour Basis to help Consultant and FDOT project managers determine the overall level of complexity of a project with respect to the tree disposition plan component. The Consultants and the Department will use the matrix (see below) to determine the appropriate level of complexity, based on the project scope, for each Task element. The Consulants and the Department will then use the negotiated level of complexity (Lower, Middle, or Upper) results to determine where, in each defined staff hour range, the level of design effort should fall.
STAFF-HOUR RANGE FOR SELECTIVE CLEARING AND GRUBBING ANALYSIS
PROJECT SCOPE | LOWER | MIDDLE | UPPER | RATING | COMMENTS
Number of Existing Tree Relocates (Naturally Occuring) | None | 0-5 | 6+
| j k l | m n o | p q r
Number of Existing Landscape Material to be Relocated | None | 0-5 | 6+
| j k l | m n o | p q r
Number of Trees Root Pruned | None | 0-5 | 6+
| j k l | m n o | p q r
Size of Site (Entire project limits) | Small (Under 5 acre) | Medium (5-25 acres) | Large (over 25 acres)
| j k l | m n o | p q r
Number of Tree Preservation Areas | 1-3 Areas | 4-6 Areas | 7+ Areas
| j k l | m n o | p q r
Number of Trees Inventoried and Preserved | 0-10 | 10- 20 | 20 +
| j k l | m n o | p q r
Other Considerations (Explain)
| j k l | m n o | p q r
Total Points |  |  |  | 0
STAFF-HOUR RANGES
Lower Range - Total Points <20
Middle Range - Total Points 20-30
Upper Range - Total Points >30

## Roadway Guidelines
ROADWAY GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical roadway projects, ranging from a standard two-lane rural resurfacing project (lower end of range) to a rural two-lane to four-lane reconstruction project or a multi-lane rural widening project (middle of the range) to a complicated rural or urban reconstruction project or a multi-lane urban widening project (upper end of range). The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiating hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
The following are general examples of the types of projects which would contain work efforts from below the staff hour ranges contained in this handbook to above the ranges. The work efforts for smaller stand-alone projects such as intersection improvements, railroad grade crossing improvements, traffic monitoring sites, sidewalk improvements, etc need to be evaluated not only considering the length of the improvements, but also on the complexity of the specific design features, including drainage, permitting, utilities, signal structures and right-of-way constraints. These factors can result in hours below, within or above the presented ranges being applicable. This list is not all inclusive, or always exact, but will provide the basis for beginning estimation and negotiation of staff hours for a project.
Below Range Projects
· Rural 2-lane resurfacing (with no 3R improvements)
· Safety (Minor Safety Improvements, no ROW impacts)
Lower End of Range Projects
· Rural 2-lane 3R (Minor safety, earthwork and utility involvement)
· Rural 4-Lane 3R (Minor safety, earthwork and utility involvement)
· Urban 3R (Minor safety, earthwork and utility involvement, primarily only milling & resurfacing)
· Multi-Lane limited access resurfacing (no 3R improvements and minimal interchange involvement)
Middle of Range Projects
· Rural 2-Lane 3R (Major safety, earthwork and utility involvement)
· Rural 4-Lane 3R (Major safety, earthwork and utility involvement)
· Urban 3R (Major safety, earthwork and utility involvement)
· Rural 2-Lane to Multi-Lane Widening/Resurfacing (Minor ROW, earthwork and utility impacts)
· Rural 2-Lane New Construction (New alignment, ROW, earthwork and utility impacts)
· Rural 2-Lane to Urban Multi-Lane Reconstruction (Minor ROW and utility impacts, minimal intersection involvement)
· Rural or Urban 4-Lane to 6-Lane Widening/Resurfacing (Widening in median, minor ROW earthwork and utility impacts, minimal
intersection involvement)
· Rural Multi-Lane New Construction (New alignment, ROW, earthwork and utility impacts, minimal intersection involvement)
· Multi-Lane Limited Access Resurfacing (Minor safety, earthwork and utility involvement, minimal interchange involvement)
· Multi-Lane Limited Access Widening/Resurfacing (Minor safety, earthwork and utility involvement, minimal interchange involvement)
Upper End of Range
· Rural 2-Lane to 4-Lane Widening/Resurfacing (Major ROW, earthwork and utility impacts)
· Rural 2-Lane to Urban Multi-Lane Reconstruction (Major ROW and utility impacts, intersection involvement)
· Rural 2-Lane to Urban Multi-Lane Widening/Resurfacing (Utilizing existing pavement, minor cross-slope correction, major ROW and
utility impacts, intersection involvement)
· Multi-Lane Limited Access Resurfacing (Major safety, earthwork and utility involvement)
· Urban Multi-Lane New Construction (New alignment, major ROW and utility impacts, intersection involvement)
· Multi-Lane Limited Access Widening/Resurfacing (Minor ROW and utility impacts, interchange involvement)
· Multi-Lane Limited Access Reconstruction (Minor ROW and utility impacts, interchange involvement)
· Multi-Lane Limited Access New Construction (New alignment, minor ROW and utility impacts, minimal interchange involvement)
Above Range
· Multi-Lane Widening/Resurfacing, Reconstruction or New Alignment with Major Interchange Involvement (Major ROW and utility
impacts, urban interchange involvement, major access management impacts)
· Urban Limited Access (Widening/resurfacing or reconstruction with multi-level interchanges)
· Multi-Lane Limited Access New Construction (New alignment, major ROW and utility impacts, major interchange involvement)

## 4. Roadway Analysis
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
4.1 | Typical Section Package | LS | 1 | 0 | 0
4.2 | Pavement Type Selection Report | LS | 1 | 0 | 0
4.3 | Pavement Design Package | LS | 1 | 0 | 0
4.4 | Cross-Slope Correction | LS | 1 | 0 | 0
4.5 | Horizontal /Vertical Master Design Files | LS | 1 | 0 | 0
4.6 | Access Management | LS | 1 | 0 | 0
4.7 | Roundabout Evaluation | LS | 1 | 0 | 0
4.8 | Roundabout Final Design Analysis | LS | 1 | 0 | 0
4.9 | Cross Section Design Files | LS | 1 | 0 | 0
4.10 | Temporary Traffic Control Plan Analysis | LS | 1 | 0 | 0
4.11 | Master TTCP Design Files | LS | 1 | 0 | 0
4.12a | Selective Clearing and Grubbing of Existing VegetationField Assessment | LS | 1 | 0 | 0
4.12b | Selective Clearing and Grubbing Site Inventory of Existing Vegetation and Cross-Discipline Coordination (OPTIONAL SERVICES) | LS | 1 | 0 | 0
4.12c | Selective Clearing and Grubbing- Existing Vegetation Maintenance Report | LS | 1 | 0 | 0
4.13 | Tree Dispostion Plan | LS | 1 | 0 | 0
4.14 | Design Variations and Exceptions | LS | 1 | 0 | 0
4.15 | Design Report | LS | 1 | 0 | 0
4.16 | Quantities | LS | 1 | 0 | 0
4.17 | Cost Estimate | LS | 1 | 0 | 0
4.18 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
4.19 | Other Roadway Analyses | LS | 1 | 0 | 0
Roadway Analysis Technical Subtotal |  |  |  |  | 0
4.2 | Field Reviews | LS | 1 | 0 | 0
4.21 | Monitor Existing Structures | LS | 1 | 0 | 0
4.22 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
4.23 | Quality Assurance/Quality Control | LS | % | 0% | 0
4.24 | Independent Peer Review | LS | % | 0% | 0
4.25 | Supervision | LS | % | 0% | 0
Roadway Analysis Nontechnical Subtotal |  |  |  |  | 0
4.26 | Coordination | LS | % | 0% | 0
4. Roadway Analysis Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
Typical Section |  | EA | 0 | 0 | 0 |  |  | 0
Pavement |  | EA | 0 | 0 | 0 |  |  | 0
Access Management |  | EA | 0 | 0 | 0 |  |  | 0
15% Line and Grade |  | EA | 0 | 0 | 0 |  |  | 0
Driveways |  | EA | 0 | 0 | 0 |  |  | 0
Local Governments (cities, counties, MPO) |  | EA | 0 | 0 | 0 |  |  | 0 | yes
Work Zone Traffic Control |  | EA | 0 | 0 | 0 |  |  | 0 | no
30/60/90/100% Comment Review Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 | Total Project Manager Meetings (carries to Tab 3) |  | 0
[5 empty] | Carries to 4.17 |  |  | Carries to Tab 3

## 5. Roadway Plans
Estimator: | [6 empty] | Enter project name & description
999999-1-52-01
Representing |  |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Scale | Units | No. of Units or Sheet | Hours/ Unit or Sheet | Total Hours | Comments
5.1 | Key Sheet |  | Sheet | 0 | 0 | 0
5.2 | Summary of Pay Items Including Quantity Input |  | Sheet | 0 | 0 | 0
5.3 | Typical Section Sheets
5.3.1 | Typical Sections |  | EA | 0 | 0 | 0
5.3.2 | Typical Section Details |  | EA | 0 | 0 | 0
5.4 | General Notes/Pay Item Notes |  | Sheet | 0 | 0 | 0
5.5 | Summary of Quantities Sheets |  | Sheet | 0 | 0 | 0
5.6 | Project Layout |  | Sheet | 0 | 0 | 0
5.7 | Plan/Profile Sheet |  | Sheet | 0 | 0 | 0
5.8 | Profile Sheet |  | Sheet | 0 | 0 | 0
5.9 | Plan Sheet |  | Sheet | 0 | 0 | 0
5.1 | Special Profile |  | Sheet | 0 | 0 | 0
5.11 | Back-of-Sidewalk Profile Sheet |  | Sheet | 0 | 0 | 0
5.12 | Interchange Layout Sheet |  | Sheet | 0 | 0 | 0
5.13 | Ramp Terminal Details (Plan View) |  | Sheet | 0 | 0 | 0
5.14 | Intersection Layout Details |  | Sheet | 0 | 0 | 0
5.15 | Special Details |  | EA | 0 | 0 | 0
5.16 | Cross-Section Pattern Sheet(s) |  | Sheet | 0 | 0 | 0
5.17 | Roadway Soil Survey Sheet(s) |  | Sheet | 0 | 0 | 0
5.18 | Cross Sections |  | EA | 0 | 0 | 0
5.19 | Temporary Traffic Control Plan Sheets |  | Sheet | 0 | 0 | 0
5.2 | Temporary Traffic Control Cross Section Sheets |  | EA | 0 | 0 | 0
5.21 | Temporary Traffic Control Detail Sheets |  | Sheet | 0 | 0 | 0
5.22 | Utility Adjustment Sheets |  | Sheet | 0 | 0 | 0
5.23 | Selective Clearing and Grubbing Sheet(s)
5.23.1 | Selective Clearing and Grubbing |  | Sheet | 0 | 0 | 0
5.23.2 | Selective Clearing and Grubbing Details |  | Sheet | 0 | 0 | 0
5.24 | Tree Disposition Sheet(s)
5.24.1 | Tree Disposition Plan Sheet(s) |  | Sheet | 0 | 0 | 0
5.24.2 | Tree Disposition Plan Tables and Schedules |  | Sheet | 0 | 0 | 0
5.25 | Project Control Sheet(s) |  | Sheet | 0 | 0 | 0
5.26 | Environmental Detail Sheets |  | Sheet | 0 | 0 | 0
5.27 | Utility Verification Sheet(s) (SUE Data) |  | Sheet | 0 | 0 | 0
Roadway Plans Technical Subtotal | [5 empty] | 0
5.28 | Quality Assurance/Quality Control |  | LS | % | 0% | 0
5.29 | Supervision |  | LS | % | 0% | 0
5. Roadway Plans Total | [5 empty] | 0

## 6a. Drainage Analysis
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
6a.1 | Drainage Map Hydrology | Per Map | 0 | 0 | 0
6a.2 | Base Clearance Calculations | Per Location | 0 | 0 | 0
6a.3 | Pond Siting Analysis and Report | Per Basin | 0 | 0 | 0
6a.4 | Design of Cross Drains | EA | 0 | 0 | 0
6a.5 | Design of Ditches | Per Ditch Mile | 0 | 0 | 0
6a.6 | Design of Stormwater Management Facility (Offsite or Infield Pond) | EA | 0 | 0 | 0
6a.7 | Design of Stormwater Management Facility (Roadside Treatment Swales and Linear Ponds) | Per Cell | 0 | 0 | 0
6a.8 | Design of Floodplain Compensation | Per Floodplain Basin | 0 | 0 | 0
6a.9 | Design of Storm Drains | EA | 0 | 0 | 0
6a.10 | Optional Culvert Material | EA | 0 | 0 | 0
6a.11 | French Drain Systems | Per Cell | 0 | 0 | 0
6a.11.a | Existing French Drain Systems | Per Cell | 0 | 0 | 0
6a.12 | Drainage Wells | EA | 0 | 0 | 0
6a.13 | Drainage Design Documentation Report | LS | 1 | 0 | 0
6a.14 | Bridge Hydraulic Report | EA | 0 | 0 | 0
6a.15 | Temporary Drainage Analysis | LS | 1 | 0 | 0
6a.16 | Cost Estimate | LS | 1 | 0 | 0
6a.17 | Technical Special Provisions / Modified Special Provisions | LS | 1 | 0 | 0
6a.18 | Hydroplaning Analysis | LS | 1 | 0 | 0
6a.19 | Existing Permit Analysis | LS | 1 | 0 | 0
6a.20 | Other Drainage Analysis | LS | 1 | 0 | 0
6a.21 | Noise Barrier Evaluation | LS | 1 | 0 | 0
Drainage Analysis Technical Subtotal |  |  |  |  | 0
6a.22 | Field Reviews | LS | 1 | 0 | 0
6a.23 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
6a.24 | Environmental Look-Around (ELA) Meeting | LS | 1 | 0 | 0
6a.25 | Quality Assurance/Quality Control | LS | % | 0% | 0
6a.26 | Independent Peer Review | LS | % | 0% | 0
6a.27 | Supervision | LS | % | 0% | 0
Drainage Analysis Nontechnical Subtotal |  |  |  |  | 0
6a.28 | Coordination | LS | % | 0% | 0
6a. Drainage Analysis Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
Base Clearance Water Elevation |  | EA | 0 | 0 | 0 |  |  | 0
Pond Siting |  | EA | 0 | 0 | 0 |  |  | 0
Agency |  | EA | 0 | 0 | 0 |  |  | 0
Local Governments (cities, counties) |  | EA | 0 | 0 | 0 |  |  | 0
FDOT Drainage |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  |  | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 | Total Project Manager Meetings (carries to Tab 3) |  | 0
[5 empty] | Carries to 6.19 |  |  | Carries to Tab 3

## 6b. Drainage Plans
Estimator: | [6 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Scale | Units | No. of Units or Sheet | Hours/ Unit or Sheet | Total Hours | Comments
6b.1 | Drainage Map (Including Interchanges) |  | Sheet | 0 | 0 | 0
6b.2 | Bridge Hydraulics Recommendation Sheets |  | Sheet | 0 | 0 | 0
6b.3 | Summary of Drainage Structures |  | Sheet | 0 | 0 | 0
6b.4 | Optional Pipe/Culvert Material |  | Sheet | 0 | 0 | 0
6b.5 | Drainage Structure Sheet(s) (Per Structure) |  | EA | 0 | 0 | 0
6b.6 | Miscellaneous Drainage Detail Sheets |  | Sheet | 0 | 0 | 0
6b.7 | Lateral Ditch Plan/Profile |  | Sheet | 0 | 0 | 0
6b.8 | Lateral Ditch Cross Sections |  | EA | 0 | 0 | 0
6b.9 | Retention/Detention Ponds Detail Sheet(s) |  | Sheet | 0 | 0 | 0
6b.10 | Retention Pond Cross Sections |  | EA | 0 | 0 | 0
6b.11 | Erosion Control Plan Sheet(s) |  | Sheet | 0 | 0 | 0
6b.12 | SWPPP Sheet(s) |  | Sheet | 0 | 0 | 0
Drainage Plans Technical Subtotal | [5 empty] | 0
6b.13 | Quality Assurance/Quality Control |  | LS | % | 0% | 0
6b.14 | Supervision |  | LS | % | 0% | 0
6. Drainage Plans Total | [5 empty] | 0

## Utility Guidelines
UTILITY GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual tasks on typical roadway projects, ranging from a standard 2-lane rural resurfacing project (lower end of range) to a complicated urban reconstruction project (upper end of range). The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual utility tasks. Hours below or above the presented ranges may be applicable based on the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiating hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
Any Verified Vertical Elevation and Horizontal Locaiton (Vvh; SUE) information is addressed in the Survey activity.
The following are general examples of the types of projects which would contain work effort from below the staff hour ranges contained in this handbook to above the ranges. This list is not inclusive, or always exact, but will provide the basis for beginning estimation and negotiation of staff hours for a project.
Low Range Projects
· Rural 2-lane resurfacing (with no 3R improvements).
· Sidewalk project with no utility involvement.
· Minor bridge repair projects (painting or caulking) with no utility involvement.
· Multi-lane limited access resurfacing (no interchange involvement).
· Rural 3R (minor safety improvements)
· Rural Signalization
· Multi-lane limited access resurfacing (safety, earthwork, and minor intersection involvement).
· Intersection improvements without lane additions or signalization
Middle of Range Projects
· Rural 3R (major safety, minor earthwork, realigning ditches).
· Urban 3R (safety, no change to profile grade line, utility exception granted).
· Highway lighting (FDOT Installed).
· Rural widening/resurfacing (minor ROW and earthwork).
· Urban Signalization with utility impact.
· Intersection improvements with lane additions and signalization.
Upper End of Range
· Urban 3R (major safety, extensive above ground feature relocation).
· Rural 2-lane new construction (new alignment, ROW, and earthwork).
· Rural 2-lane to urban multi-lane reconstruction (ROW and intersection involvement).
· Rural or urban 4-lane to 6-lane widening/resurfacing (widening in median, minor ROW, earthwork, and intersection involvement).
· Urban Multi-intersection Signalization with utility impact.
· Rural multi-lane new construction (new alignment, ROW, earthwork and intersection involvement).
· Rural 2-lane to 4-lane (major ROW and earthwork).
· Multi-lane limited access reconstruction (ROW and interchange involvement).
· Multi-lane rural limited access new construction (new alignment, ROW and interchange construction).
· Urban multi-lane new construction (new alignment, ROW and intersection construction).
· Multi-lane limited access, urban reconstruction or new alignment with major interchange involvement (major ROW and interchange
construction, major access management impacts).
· Multi-lane Urban limited access new construction (new alignment, major ROW and, major interchange involvement).

## 7. Utilities
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours |  | Comments
7.1 | Utility Kickoff Meeting | LS | 1 | 0 | 0 | Meeting is listed below
7.2 | Identify Existing Utility Agency Owner(s) | LS | 1 | 0 | 0
7.3 | Make Utility Contacts | LS | 1 | 0 | 0
7.4 | Exception Processing | LS | 1 | 0 | 0
7.5 | Preliminary Utility Meeting | LS | 1 | 0 | 0 | Meeting is listed below
7.6 | Individual/Field Meetings | LS | 1 | 0 | 0 | Meetings are listed below
7.7 | Collect and Review Plans and Data from UAO(s) | LS | 1 | 0 | 0
7.8 | Subordination of Easements Coordination | LS | 1 | 0 | 0
7.9 | Utility Design Meeting | LS | 1 | 0 | 0 | Meeting is listed below
7.1 | Review Utility Markups & Work Schedules, and Processing of Schedules & Agreements | LS | 1 | 0 | 0
7.11 | Utility Coordination/Followup | LS | 1 | 0 | 0
7.12 | Utility Constructability Review | LS | 1 | 0 | 0
7.13 | Additional Utility Services | LS | 1 | 0 | 0
7.14 | Processing Utility Work by Highway Contractor (UWHC) | LS | 1 | 0 | 0
7.15 | Contract Plans to UAO(s) | LS | 1 | 0 | 0
7.16 | Certification/Close-Out | LS | 1 | 0 | 0
7.17 | Other Utilities | LS | 1 | 0 | 0
7. Utilities Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
Kickoff (see 7.1) |  | EA | 0 | 0 | 0 |  |  | 0
Preliminary Meeting (see 7.5) |  | EA | 0 | 0 | 0 |  |  | 0
Individual UAO Meetings (see 7.6) |  | EA | 0 | 0 | 0 |  |  | 0
Field Meetings (see 7.6) |  | EA | 0 | 0 | 0 |  |  | 0
Design Meeting (see 7.9) |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings (this is automatically added into Utilities Total (cell F27)) |  | EA | 0 | 0 | 0 |  |  | 0
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
Carries to Tab 3

## Environmental Permit Guidelines
ENVIRONMENTAL PERMITS and ENVIRONMENTAL CLEARANCES GUIDELINES
An effective permitting program is based on a commitment to close coordination and documentation among the CONSULTANT, the Department’s District Permit Coordinator, the Department's Environmental Management Office, the Department’s Project Manager, and regulatory agencies. The CONSULTANT shall meet with the District Permit Coordinator and the Department’s Project Manager prior to developing and submitting all permit application packages to ensure District policies regarding acquisition of environmental permits have been adequately addressed. The Consultant shall meet with the Permit Coordinator and the Environmental Management Office to determine the level of work required for reevaluations and environmental clearances. The CONSULTANT shall proceed with the development and submittal of permit application packages and acquisition of permits based upon the general guidelines provided by the DEPARTMENT. The Environmental Permits Task is generally considered complete once all applicable environmental permits have been obtained.
The CONSULTANT, the Department's Permit Coordinator and the Department's Environmental Management Office will fully review the project's PD&E documents to determine any special requirements or commitments. The Department's staff and the CONSULTANT will also review the regulating agencies requirements for any species issues to fully understand surveying and permitting.
Below is a brief description of a typical low-range project, a typical mid-range project, and a typical high-range project, with examples of each. Some projects, even typical ones, may not fall neatly into one of these categories. Thus, the descriptions and lists below should be used only as a general guide and should never be used in lieu of close coordination among the CONSULTANT, the Department’s District Permit Coordinator, the Department's Environmental Management Office and the Department’s Project Manager.
Typical Low-Range Project- A low-range project will typically not include additional travel lanes, but may include minor wetland or surface water impacts not requiring mitigation. Low-range projects do not typically require authorization for use of Sovereign Submerged Lands and have no involvement with Threatened or Endangered Species. Examples of typical low-range projects may include permitting for:
· Minor intersection improvements
· Culvert extensions
· Bridge replacement (in-kind or rehabilitation)
· Shoulder widening
· Rehabilitation, Resurfacing, and Restoration
· Sidewalks
Permits may be issued from the following agencies:
· DEP/WMD (General Permit)
· USACE (Nationwide)
· USCG (Advanced Approval)
· EPA and/or DEP [National Pollutant Discharge Elimination System (NPDES) Construction General Permit]
· DEP (Coastal Construction Control Line (CCCL) permit)
· Local Government
Typical Mid-range Project - A mid-range project will typically include additional travel lanes, may include wetland or surface water impacts of less than one half acre and may require mitigation. Mid-range projects may require authorization for use of Sovereign Submerged Lands and may have involvement with Threatened or Endangered Species. Examples of typical mid-range projects may include permitting for:
· Multi-lane reconstruction
· Add lane and resurfacing
· Bridge widening or replacement (not in-kind)
· Minor activities waterward of the Coastal Construction Control Line (CCCL)
· Minor activities within Water Management District or local drainage district lands
· Trails
Permits may be issued from the following agencies:
· DEP/WMD (Individual Permit)
· WMD Right of Way Occupancy Permit
· USACE (Nationwide, or Letter of Permission)
· USCG (bridge permit issued by USCG District)
· EPA and/or FDEP [National Pollutant Discharge Elimination System (NPDES) Construction General Permit]
· Department of Environmental Protection (CCCL permit)
· Local Government
· Local Water Control District Right of Way Occupancy Permit
· FDEP Class V deep well permit
Typical High-Range Project – A high-range project will typically include additional travel lanes, wetland or surface water impacts of one half acre or greater, and require mitigation. High-range projects may require authorization for use of Sovereign Submerged Lands and may have involvement with Threatened or Endangered Species. Examples of typical high-range projects may include permitting for:
· New road construction
· New bridge construction
· Multi-lane reconstruction
· Adding lanes and resurfacing
· Bridge widening or replacement (not in-kind)
· Major activities waterward of the CCCL
Permits may be issued from the following agencies:
· DEP/WMD (Individual Permit)
· WMD Right of Way Occupancy Permit
· USACE (Individual Permit or Regional General Permit)
· USCG (bridge permit issued by USCG Headquarters, Washington, D.C.)
· EPA and/or DEP [National Pollutant Discharge Elimination System (NPDES) Construction General Permit]
· DEP (CCCL permit)
· Local Government
· Local Water Control District Right of Way Occupancy Permit
· DEP Class V Deep Well Permit

## 8. Env. Permits and Clearances
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
Environmental Permits and Environmental Clearances
8.1 | Preliminary Project Research | LS | 1 | 0 | 0
Permits
8.2 | Field Work
8.2.1 | Pond Site Alternatives | per pond site | 0 | 0 | 0
8.2.2 | Establish Wetland Jurisdictional Lines and Assessments | LS | 1 | 0 | 0
8.2.3 | Species Surveys | LS | 1 | 0 | 0
8.3 | Agency Verification of Wetland Data | LS | 1 | 0 | 0
8.4 | Complete And Submit All Required Permit Applications
8.4.1 | Complete and Submit All Required Wetland Permit Applications | LS | 1 | 0 | 0
8.4.2 | Complete and Submit All Required Species Permit Applications | LS | 1 | 0 | 0
8.5 | Coordinate and Review Dredge and Fill Sketches | LS | 1 | 0 | 0
8.6 | Prepare USCG Permit Application | LS | 1 | 0 | 0
8.7 | Prepare Water Management District or Local Water Control District Right of Way Occupancy Permit Application | LS | 1 | 0 | 0
8.8 | Prepare Coastal Construction Control Line (CCCL) Permit Application | LS | 1 | 0 | 0
8.9 | Prepare USACE Section 408 Application to Alter a Civil Works Project | LS | 1 | 0 | 0
8.10 | Compensatory Mitigation Plan | LS | 1 | 0 | 0
8.11 | Mitigation Coordination and Meetings | LS | 1 | 0 | 0
8.12 | Other Environmental Permits | LS | 1 | 0 | 0
Environmental Clearances/Reevaluations
8.13 | Technical support to Department for Environmental Clearances and Reevaluations (use when consultant provides technical support only)
8.13.1 | NEPA or SEIR Reevaluation | LS | 1 | 0 | 0
8.13.2 | Archaeological and Historical Resources | LS | 1 | 0 | 0
8.13.3 | Wetland Impact Analysis | LS | 1 | 0 | 0
8.13.4 | Essential Fish Habitat Impact Analysis | LS | 1 | 0 | 0
8.13.5 | Protected Speices and Habitat Impact Analysis | LS | 1 | 0 | 0
8.14 | Preparation of Environmental Clearances and Reevaluations (use when consultant prepares all documents associated with reevaluation)
8.14.1 | NEPA or SEIR Reevaluation | LS | 1 | 0 | 0
8.14.2 | Archaeological and Historical Resources | LS | 1 | 0 | 0
8.14.3 | Wetland Impact Analysis | LS | 1 | 0 | 0
8.14.4 | Essential Fish Habitat Impact Analysis | LS | 1 | 0 | 0
8.14.5 | Protected Species and Habitat Impact Analysis | LS | 1 | 0 | 0
8.15 | Contamination Impact Analysis | LS | 1 | 0 | 0
8.16 | Asbestos Survey | LS | 1 | 0 | 0
Environmental Permits and Environmental Clearances/Reevaluations Technical Subtotal |  |  |  |  | 0
8.17 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
8.18 | Quality Assurance/Quality Control | LS | % | 0% | 0
8.19 | Supervision | LS | % | 0% | 0
Environmental Permits and Environmental Clearances Nontechnical Subtotal |  |  |  |  | 0
8.20 | Coordination | LS | % | 0% | 0
8. Environmental Permits and Environmental Clearances Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
WMD |  | EA | 0 | 0 | 0 |  |  | 0
NMFS |  | EA | 0 | 0 | 0 |  |  | 0
USACE |  | EA | 0 | 0 | 0 |  |  | 0
USCG |  | EA | 0 | 0 | 0 |  |  | 0
USFWS |  | EA | 0 | 0 | 0 |  |  | 0
FFWCC |  | EA | 0 | 0 | 0 |  |  | 0
FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 |  | PM attendance at Progress Meetings is manually entered on General Task 3 | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 |  | PM attendance at Phase Review Meetings is manually entered on General Task 3 | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 8.18 |  |  | Carries to Tab 3

## Structures-Guidelines
STRUCTURES GUIDELINES
The staff hour workbook for structural design efforts, the staff hour worksheets, and the typical ranges and descriptions of each task were developed by a committee consisting of individuals from the FDOT and the consulting industry.
It is intended that individuals negotiating work efforts for both the FDOT and the Consultant be experienced structural engineers knowledgeable of the work effort to complete each task. The worksheets are intended to guide negotiators who have hands on experience designing multiple similar projects.
These worksheets are intended to accommodate approximately 90% of the structures being designed. Staff hour ranges are for new, replacement and widened bridges, rural and urban grade separation, interchange bridges, typical trestle and high level water crossings, retaining walls, box culverts, overhead signs, and other miscellaneous structures. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual task. Specific aspects of each individual project should be considered in negotiating hours for each individual task.
Worksheets and ranges have not been developed for rehabilitation or repair projects or exceptionally complex projects (Skyway) or tunnels. It is anticipated that approximately 10% of structure task efforts will fall outside the ranges, either above or below the maximum and minimum values given, respectively.
Activity worksheets have been developed for the different work elements and bridge structure types normally encountered within FDOT projects. Only the Activity worksheets required should be included in the final workbook. Where more than one bridge is included within the project, individual worksheets shall be replicated for each bridge, such as Activity 10 BDR and other bridge task sheets as required. Each of these worksheets will have to be individually linked to the Activity 9 Structures Summary worksheet. It is the Consultant's responsibility to ensure the accuracy of the formulas.
There are many cases where individual tasks included within these activity worksheets are not required. In such cases, the number of units shall be indicated as zero. Individual line items shall not be deleted, nor inserted.
The following Activity worksheets are provided:
· Activity 9 is a summary of the General Tasks, Bridge Development Report, Bridge Design and Production, Retaining Wall Design and Production and Miscellaneous Structure Design and Production activities within the project. The general tasks address the technical tasks associated with the development of the project-based key sheet/index of drawings, general notes, cost estimates and Technical Special Provisions. This worksheet also addresses non-technical tasks such as field reviews, technical meetings and coordination. This Activity worksheet also addresses Quality Assurance/Quality Control, Independent Peer Review and Supervision activities.
Activity 10 addresses Bridge Development Report tasks. The staff hour ranges were developed for general geometric requirements, statical systems, superstructures alternates, substructure alternatives, foundation alternates, vessel collision, scour, precast bridge options, moveable spans, temporary traffic control, constructability requirements, bridge security, retaining wall, quantities, cost estimates and aesthetics consideration. Report preparation including conclusions and recommendations, development of exhibits and supporting documentation are to be included. The option to include Preliminary Plans is also available.
· Activity 11 addresses Temporary Bridge tasks. The staff hour ranges were developed for an ACROW bridge superstructure with layout of substructure and possibly special design of substructure for longer spans or taller substructures than allowed by the Standard Drawings.
· Activity 12 addresses Short Span Concrete bridge tasks. The staff hour ranges were developed for precast and cast-in-place slab type bridges, inverted T and other slab type bridges. Use either Cast-in-Place Bridge or Prestressed Slab Unit Bridge depending on the anticipated structure type.
· Activity 13 addresses Medium Span Concrete bridge tasks. The staff hour ranges were developed for precast, prestressed concrete beam bridges designed as simply supported or continuous over intermediate supports. Use either Simple Span Concrete Design or Continuous Concrete Girder Design depending on the anticipated structure type, unless both systems are used in the same bridge.
· Activity 14 addresses Structural Steel bridge tasks. The staff hour ranges were developed for all steel girder superstructure types, including steel plates, standard rolled shapes, box girders, simple and continuous configurations. The forms were not intended to cover steel frames or trusses. Use either Structural Steel Plate Girder Design or Structural Steel Box Girder Design depending on the anticipated structure type.
· Activity 15 addresses Segmental Concrete bridge tasks. The staff hour ranges were developed for precast, cast-in-place, span-by-span, balanced cantilever, single or multi-celled box, multiple box.
· Activity 16 addresses Bascule bridge tasks. The staff hour ranges were developed for the bascule pier, rest pier, movable span, electrical, mechanical & control house. The worksheet does not cover approach spans. Account for approach spans by adding worksheets for Activity 12, 13, 14 or 15, as applicable. The following task clarifications are provided for Activity 16:
Task 16.23 Stringer Design: This task is only used if deck stringers are anticipated in the design as is typical for steel grid deck bridges where the deck spans transversely between stringers. If a deck system that spans longitudinally between floorbeams is used, this task is not used.
Task 16.27 Sidewalk Bracket Design: This task only used on bridges with sidewalks.
Task 16.28 Roadway Bracket Design: This task is used when cantilever brackets are used to support the deck outside of the main girders as is the most common case.
Task 16.31 Trunnion Girder Design: This task only used for Hopkins (cantilever) trunnion arrangements.
Task 16.39 Bascule GP&E: This task is only used if the bridge length prohibits providing a scale for the overall bridge GP&E that is appropriate for detailing of the movable span (clearances, subcable location, etc.)
Task 16.49 Trunnion Girder: This task only used for Hopkins (cantilever) trunnion arrangements.
Task 16.50 Cylinder Girder: This task only used for hydraulic cylinder driven bascule bridges incorporating independent cylinder girders.
Task 16.55 Pedestrian Rail and Support Details: Use only if bridge has a pedestrian rail.
Task 16.56 Curb and Sidewalk Details: Use only if bridge has a raised curb or sidewalk decking that differs from the roadway deck.
Task 16.64, 16.65, 16.66, 16.67: Mechanical Drive Design: Use tasks 16.64, 16.65, 16.66, & 16.67 for bridges utilizing an electric motor or hydraulic motor drive train with a rack and pinion. If a hydraulic motor is used use these tasks with Task 16.68, Hydraulic Drive Design.
Task 16.68 Hydraulic Drive Design: Use if hydraulic cylinder or hydraulic motor drive is employed in the design. If a hydraulic motor drive is employed, use this task with appropriate tasks from 16.64, 16.65, 16.66, & 16.67.
Task 16.89 PLC Logic: Use only for bridges with Programmable Logic Controllers.
· Activity 17 addresses Retaining Wall tasks. The staff hour ranges were developed for permanent and temporary proprietary walls, cast-in-place retaining walls and other retaining walls.
· Activity 18 addresses Miscellaneous structure tasks. The staff hour ranges were developed for concrete box culverts, strain poles, mast arms, overhead and cantilever sign structures, high mast light foundations, noise barrier walls and special structures.

## 9. Structures Summary
Estimator: | [10 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | Design and Production Staffhours |  |  |  | Comments
|  |  | No. of Units | Hours per Unit | No. of Sheets | Total
General Drawings
9.1 | Key Sheet and Index of Drawings | Sheet | 0 | 0 | 0 | 0
9.2 | Project Layout | Sheet | 0 | 0 | 0 | 0
9.3 | General Notes and Bid Item Notes | Sheet | 0 | 0 | 0 | 0
9.4 | Miscellaneous Common Details | Sheet | 0 | 0 | 0 | 0
9.5 | Incorporate Report of Core Borings | Sheet | 0 | 0 | 0 | 0
9.6 | Standard Plans- Bridges | LS | 1 | 0 |  | 0
9.7 | Existing Bridge Plans | LS | 1 | 0 |  | 0
9.8 | Assemble Plan Summary Boxes and Quantities | LS | 1 | 0 |  | 0
9.9 | Cost Estimate | LS | 1 | 0 |  | 0
9.10' | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 |  | 0
Structures - Summary and Miscellaneous Tasks and Drawings Subtotal |  |  |  |  | 0 | 0
Task No. | Task | Total | Task 10 | Task 11 | Task 12 | Task 13 | Task 14 | Task 15 | Task 16 | Task 17 | Task 18
10-16 | Bridge 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-16 | Bridge 2 | 0
10-16 | Bridge 3 | 0
10-16 | Bridge 4 | 0
10-16 | Bridge 5 | 0
10-16 | Bridge 6 | 0
10-16 | Bridge 7 | 0
10-16 | Bridge 8 | 0
10-16 | Bridge 9 | 0
10-16 | Bridge 10 | 0
17 | Retaining Walls | 0 | [7 empty] | 0
18 | Miscellaneous Structures | 0 | [8 empty] | 0
Structures Technical Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task No. | Task | Units | No. of Units | Hours per Unit | Total | Comments
9.11 | Field Reviews | LS | 1 | 0 | 0
9.12 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
9.13 | Quality Assurance/Quality Control | LS | % | 0% | 0
9.14 | Independent Peer Review | LS | 1 | 0 | 0
9.15 | Supervision | LS | % | 0% | 0
Structures Nontechnical Subtotal |  |  |  |  | 0
9.16 | Coordination | LS | 1 | 0 | 0
9. Structures - Summary and Miscellaneous Tasks and Drawings Nontechnical and Coordination Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments |  |  |  | PM Attendance at Meeting Required? | Number
BDR Coordination/Review |  | EA | 0 | 0 | 0 | [5 empty] | 0
90/100% Comment Review |  | EA | 0 | 0 | 0 | [5 empty] | 0
Aesthetics Coordination |  | EA | 0 | 0 | 0 | [5 empty] | 0
Regulatory Agency |  | EA | 0 | 0 | 0 | [5 empty] | 0
Local Governments (cities, counties) |  | EA | 0 | 0 | 0 | [5 empty] | 0
Utility Companies |  | EA | 0 | 0 | 0 | [5 empty] | 0
Other Meetings |  | EA | 0 | 0 | 0 | [5 empty] | 0
Subtotal Technical Meetings |  |  |  |  | 0 | [5 empty] | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  |  |  |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  |  |  |  | - -
Total Meetings |  |  |  |  | 0 | Total Project Manager Meetings (carries to Tab 3) |  |  |  |  | 0
[5 empty] | Carries to 9.11 | [5 empty] | Carries to Tab 3

## 10. Structures-BDR
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Requirement
10.1 | Bridge Geometry | LS | 1 | 0 |  | 0
10.2 | Ship Impact Data Collection | LS | 1 | 0 |  | 0
10.3 | Ship Impact Criteria | EA | 0 | 0 |  | 0
Superstructure Alternatives
10.4 | Short Span Concrete Bridge | EA ALT | 0 | 0 |  | 0
10.5 | Medium Span Concrete Bridge | EA ALT | 0 | 0 |  | 0
10.6 | Long Span Concrete Bridge | EA ALT | 0 | 0 |  | 0
10.7 | Structural Steel Bridge | EA ALT | 0 | 0 |  | 0
Foundation & Substructure Alternatives
10.8 | Pier/Bent | EA Type | 0 | 0 |  | 0
10.9 | Shallow Foundations / GRS Abutments | EA Type | 0 | 0 |  | 0
10.1 | Deep Foundations | EA Foundation Evaluated | 0 | 0 |  | 0
Movable Span
10.11 | Data Collection and Design Criteria | LS | 1 | 0 |  | 0
10.12 | Movable Span Geometrics and Clearances | LS | 1 | 0 |  | 0
10.13 | Deck System Evaluation | LS | 1 | 0 |  | 0
10.14 | Framing Plan Development | LS | 1 | 0 |  | 0
10.15 | Main Girder Preliminary Design | LS | 1 | 0 |  | 0
10.16 | Conceptual Span Balance/Counterweight | LS | 1 | 0 |  | 0
10.17 | Support System Development | LS | 1 | 0 |  | 0
10.18 | Drive Power Calculations | LS | 1 | 0 |  | 0
10.19 | Drive System Development | LS | 1 | 0 |  | 0
10.2 | Power and Control Development | LS | 1 | 0 |  | 0
10.21 | Conceptual Pier Design | LS | 1 | 0 |  | 0
10.22 | Foundation Analysis (FL PIER) | LS | 1 | 0 |  | 0
10.23 | Tender Visibility Study | LS | 1 | 0 |  | 0
Other BDR Issues
10.24 | Aesthetics | LS | 1 | 0 |  | 0
10.25 | TTCP/Staged Construction Requirements | LS | 1 | 0 |  | 0
10.26 | Constructibility Requirements | LS | 1 | 0 |  | 0
10.27 | Load Rating for damaged/widened structures | EA Unit | 1 | 0 |  | 0
10.28 | Quantity and Cost Estimates | EA ALT | 0 | 0 |  | 0
10.29 | Quantity and Cost Estimates - Movable Span | LS | 1 | 0 |  | 0
10.3 | Wall Type Justification | LS | 1 | 0 |  | 0
Report Preparation
10.31 | Exhibits | EA SHEET | 0 | 0 |  | 0
10.32 | Exhibits - Movable Span | EA SHEET | 0 | 0 |  | 0
10.33 | Report Preparation | LS | 1 | 0 |  | 0
10.34 | Report Preparation - Movable Span | LS | 1 | 0 |  | 0
10.35 | BDR Submittal Package | LS | 1 | 0 |  | 0
10. Structures - Bridge Development Report Total | [5 empty] | 0
When ONLY 30% plans are final deliverable, use Task Nos. as shown for applicable bridge types for project Activities 12 thru 16. Staffhours to be negotiated and scaled appropriately.

## 11. Temporary Bridge
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans [Tasks under Activity 11 are for Prefabricated Temporary Bridges only]
11.1 | Overall Bridge Final Geometry | LS | 1 | 0 |  | 0
11.2 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
11.3 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
End Bent Design and Plans
11.4 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
11.5 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Intermediate Bent Design and Plans
11.6 | Intermediate Bent Structural Design | EA Design | 0 | 0 |  | 0
11.7 | Intermediate Bent Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
11.8 | Foundation Layout | EA | 0 | 0 |  | 0
11. Temporary Bridge Total |  |  |  |  | 0 | 0

## 12. Short Span Concrete
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans
12.1 | Overall Bridge Final Geometry | LS | 1 | 0 |  | 0
12.2 | Expansion/Contraction Analysis | EA Unit | 0 | 0 |  | 0
12.3 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
12.4 | Construction Staging | Sheet | 0 | 0 | 0 | 0
12.5 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0 | 0
12.6 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
End Bent Design and Plans
12.7 | End Bent Geometry | EA End Bent | 0 | 0 |  | 0
12.8 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
12.9 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
12.1 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Intermediate Bent Design and Plans
12.11 | Bent Geometry | EA Bent | 0 | 0 |  | 0
12.12 | Bent Stability Analysis | EA Analysis | 0 | 0 |  | 0
12.13 | Bent Structural Design | EA Design | 0 | 0 |  | 0
12.14 | Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
12.15 | Bent Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
12.16 | Foundation Layout | Sheet | 0 | 0 | 0 | 0
Miscellaneous Superstructure Design and Plans
12.17 | Finish Grade Elevation Calculation | LS | 1 | 0 |  | 0
12.18 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
Cast-in-Place Slab Bridges
12.19 | Bridge Deck Design | EA Unit | 0 | 0 |  | 0
12.2 | Superstructure Plan | Sheet | 0 | 0 | 0 | 0
12.21 | Superstructure Sections and Details | Sheet | 0 | 0 | 0 | 0
Prestressed Slab Unit Bridges
12.22 | Prestressed Slab Unit Design | EA Design | 0 | 0 |  | 0
12.23 | Prestressed Slab Unit Layout | Sheet | 0 | 0 | 0 | 0
12.24 | Prestressed Slab Unit Details and Schedule | Sheet | 0 | 0 | 0 | 0
12.25 | Deck Topping Reinforcing Layout | Sheet | 0 | 0 | 0 | 0
12.26 | Superstructure Sections and Details | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar List
12.27 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Load Rating
12.28 | Load Ratings | EA Unit | 0 | 0 |  | 0
12. Structures - Short Span Concrete Bridge Total |  |  |  |  | 0 | 0

## 13. Medium Span Concrete
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans
13.1 | Overall Bridge Final Geometry | LS | 1 | 0 |  | 0
13.2 | Expansion/Contraction Analysis | EA Unit | 0 | 0 |  | 0
13.3 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
13.4 | Construction Staging | Sheet | 0 | 0 | 0 | 0
13.5 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0 | 0
13.6 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
End Bent Design and Plans
13.7 | End Bent Geometry | EA End Bent | 0 | 0 |  | 0
13.8 | Wingwall Design and Geometry | EA End Bent | 0 | 0 |  | 0
13.9 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
13.1 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
13.11 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Intermediate Bent Design and Plans
13.12 | Bent Geometry | EA Bent | 0 | 0 |  | 0
13.13 | Bent Stability Analysis | EA Design | 0 | 0 |  | 0
13.14 | Bent Structural Design | EA Design | 0 | 0 |  | 0
13.15 | Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
13.16 | Bent Details | Sheet | 0 | 0 | 0 | 0
Pier Design and Plans
13.17 | Pier Geometry | EA Pier | 0 | 0 |  | 0
13.18 | Pier Stability Analysis | EA Design | 0 | 0 |  | 0
13.19 | Pier Structural Design | EA Design | 0 | 0 |  | 0
13.2 | Pier Plan and Elevation | Sheet | 0 | 0 | 0 | 0
13.21 | Pier Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
13.22 | Foundation Layout | Sheet | 0 | 0 | 0 | 0
Superstructure Deck Design and Plans
13.23 | Finish Grade Elevation (FGE) Calculation | LS | 1 | 0 |  | 0
13.24 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
13.25 | Bridge Deck Design | EA Section | 0 | 0 |  | 0
13.26 | Bridge Deck Reinforcing and Concrete Quantities | EA Unit | 0 | 0 |  | 0
13.27 | Diaphragm Design | EA Section | 0 | 0 |  | 0
13.28 | Superstructure Plan | Sheet | 0 | 0 | 0 | 0
13.29 | Superstructure Section | Sheet | 0 | 0 | 0 | 0
13.3 | Miscellaneous Superstructure Details | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar Lists
13.31 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Continuous Concrete Girder Design
13.32 | Section Properties | LS | 1 | 0 |  | 0
13.33 | Material Properties | LS | 1 | 0 |  | 0
13.34 | Construction Sequence | EA Unit | 0 | 0 |  | 0
13.35 | Tendon Layouts | EA Unit | 0 | 0 |  | 0
13.36 | Live Load Analysis | EA Unit | 0 | 0 |  | 0
13.37 | Temperature Gradient | EA Unit | 0 | 0 |  | 0
13.38 | Time Dependent Analysis | EA Unit | 0 | 0 |  | 0
13.39 | Stress Summary | EA Unit | 0 | 0 |  | 0
13.4 | Ultimate Moments | EA Unit | 0 | 0 |  | 0
13.41 | Ultimate Shear | EA Unit | 0 | 0 |  | 0
13.42 | Construction Loading | EA Unit | 0 | 0 |  | 0
13.43 | Framing Plan | Sheet | 0 | 0 | 0 | 0
13.44 | Girder Elevation, including Grouting Plan and Vent Locations | Sheet | 0 | 0 | 0 | 0
13.45 | Girder Details | Sheet | 0 | 0 | 0 | 0
13.46 | Erection Sequence | Sheet | 0 | 0 | 0 | 0
13.47 | Splice Details | Sheet | 0 | 0 | 0 | 0
13.48 | Girder Deflections and Camber | Sheet | 0 | 0 | 0 | 0
Simple Span Concrete Design
13.49 | Prestressed Beam | EA Design | 0 | 0 |  | 0
13.5 | Prestressed Beam Schedules | Sheet | 0 | 0 | 0 | 0
13.51 | Framing Plan | Sheet | 0 | 0 | 0 | 0
Beam Stability
13.52 | Beam/girder stability | EA Unit | 0 | 0 |  | 0
Bearing
13.53 | Bearing pad and bearing plate design | Type/ Span | 0 | 0 |  | 0
13.54 | Bearing pad and bearing plate details | Sheet | 0 | 0 | 0 | 0
Load Rating
13.55 | Load Ratings | Per Beam | 0 | 0 |  | 0
13. Structures - Medium Span Concrete Bridge Total |  |  |  |  | 0 | 0

## 14. Structures-Structural Steel
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans
14.1 | Overall Bridge Final Geometry | LS | 1 | 0 |  | 0
14.2 | Expansion/Contraction Analysis | EA Unit | 0 | 0 |  | 0
14.3 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
14.4 | Construction Staging | Sheet | 0 | 0 | 0 | 0
14.5 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0 | 0
14.6 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
End Bent Design and Plans
14.7 | End Bent Geometry | EA Bent | 0 | 0 |  | 0
14.8 | Wingwall Design and Geometry | EA Bent | 0 | 0 |  | 0
14.9 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
14.1 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
14.11 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Intermediate Bent Design and Plans
14.12 | Bent Geometry | EA bent | 0 | 0 |  | 0
14.13 | Bent Stability Analysis | EA design | 0 | 0 |  | 0
14.14 | Bent Structural Design | EA design | 0 | 0 |  | 0
14.15 | Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
14.16 | Bent Details | Sheet | 0 | 0 | 0 | 0
Pier Design and Plans
14.17 | Pier Geometry | EA pier | 0 | 0 |  | 0
14.18 | Pier Stability Analysis | EA design | 0 | 0 |  | 0
14.19 | Pier Structural Design | EA design | 0 | 0 |  | 0
14.2 | Pier Plan and Elevation | Sheet | 0 | 0 | 0 | 0
14.21 | Pier Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
14.22 | Foundation Layout | Sheet | 0 | 0 | 0 | 0
Superstructure Deck Design and Plans
14.23 | Finish Grade Elevation (FGE) Calculation | LS | 1 | 0 |  | 0
14.24 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
14.25 | Bridge Deck Design | EA section | 0 | 0 |  | 0
14.26 | Bridge Deck Reinforcing and Concrete Quantities | EA Unit | 0 | 0 |  | 0
14.27 | Superstructure Plan | Sheet | 0 | 0 | 0 | 0
14.28 | Superstructure Section | Sheet | 0 | 0 | 0 | 0
14.29 | Miscellaneous Bridge Deck Details | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar Lists
14.3 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Structural Steel Plate Girder Design
14.31 | Unit Modeling | EA Unit | 0 | 0 |  | 0
14.32 | Section Design | EA Unit | 0 | 0 |  | 0
14.33 | Stiffener Design and Locations | EA Unit | 0 | 0 |  | 0
14.34 | Cross-Frame Design | EA Unit | 0 | 0 |  | 0
14.35 | Connections | EA Unit | 0 | 0 |  | 0
14.36 | Bearing Assembly Design and Detailing (with Jacking Analysis) | EA Unit | 0 | 0 |  | 0
14.37 | Splice Design | EA Unit | 0 | 0 |  | 0
14.38 | Shear Stud Connectors | EA Unit | 0 | 0 |  | 0
14.39 | Deflection Analysis | EA Unit | 0 | 0 |  | 0
14.4 | Framing Plan | Sheet | 0 | 0 | 0 | 0
14.41 | Girder Elevation | Sheet | 0 | 0 | 0 | 0
14.42 | Structural Steel Details | Sheet | 0 | 0 | 0 | 0
14.43 | Splice Details | Sheet | 0 | 0 | 0 | 0
14.44 | Girder Deflections and Camber | Sheet | 0 | 0 | 0 | 0
Structural Steel Box Girder Design
14.45 | Unit Modeling | EA Unit | 0 | 0 |  | 0
14.46 | Section Design | EA Unit | 0 | 0 |  | 0
14.47 | Stiffener Design and Locations | EA Unit | 0 | 0 |  | 0
14.48 | Interior Cross-Frame Design | EA Unit | 0 | 0 |  | 0
14.49 | Exterior Cross-Frame Design | EA Unit | 0 | 0 |  | 0
14.5 | Connections | EA Unit | 0 | 0 |  | 0
14.51 | Bearing Assembly Design and Detailing (with Jacking Analysis) | EA Unit | 0 | 0 |  | 0
14.52 | Splice Design | EA Unit | 0 | 0 |  | 0
14.53 | Shear Stud Connectors | EA Unit | 0 | 0 |  | 0
14.54 | Deflection Analysis | EA Unit | 0 | 0 |  | 0
14.55 | Framing Plan | Sheet | 0 | 0 | 0 | 0
14.56 | Girder Elevation | Sheet | 0 | 0 | 0 | 0
14.57 | Structural Steel Details | Sheet | 0 | 0 | 0 | 0
14.58 | Splice Details | Sheet | 0 | 0 | 0 | 0
14.59 | Girder Deflections and Camber | Sheet | 0 | 0 | 0 | 0
Erection Scheme
14.6 | Erection scheme analysis | EA Critical Stage | 0 | 0 |  | 0
14.61 | Erection scheme | Sheet | 0 | 0 | 0 | 0
Load Rating
14.62 | Load Rating | EA Unit | 0 | 0 |  | 0
14. Structures - Structural Steel Bridge Total |  |  |  |  | 0 | 0

## 15.Str.-Segmental Concrete
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Layout Design and Plans
15.1 | Final Bridge Geometry | LS | 1 | 0 |  | 0
15.2 | Casting Geometry Calculation | LS | 1 | 0 |  | 0
15.3 | Finish Grade Geometry Calculation | LS | 1 | 0 |  | 0
15.4 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
15.5 | Construction Schedule | LS | 1 | 0 |  | 0
15.6 | General Plan and Elevation | Sheet | 0 | 0 | 0 | 0
15.7 | Approach Slab Plan and Details | Sheet | 0 | 0 | 0 | 0
15.8 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
15.9 | Existing Bridge Plans | LS | 1 | 0 |  | 0
End Bent Design and Plans
15.1 | End Bent Geometry | EA Bent | 0 | 0 |  | 0
15.11 | Wingwall Geometry and Design | EA Bent | 0 | 0 |  | 0
15.12 | End Bent Structural Design | EA Design | 0 | 0 |  | 0
15.13 | End Bent Plan and Elevation | Sheet | 0 | 0 | 0 | 0
15.14 | End Bent Details | Sheet | 0 | 0 | 0 | 0
Pier Design and Plans
15.15 | Pier Geometry | EA Pier | 0 | 0 |  | 0
15.16 | Pier Stability Analysis | EA Analysis | 0 | 0 |  | 0
15.17 | Pier Construction Loads | EA Design | 0 | 0 |  | 0
15.18 | Pier Structural Design | EA Design | 0 | 0 |  | 0
15.19 | Pier Plan and Elevation | Sheet | 0 | 0 | 0 | 0
15.2 | Pier Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Substructure Design and Plans
15.21 | Foundation Layout | Sheet | 0 | 0 | 0 | 0
Longitudinal Analysis
15.22 | Section Properties | LS | 1 | 0 |  | 0
15.23 | Material Properties | LS | 1 | 0 |  | 0
15.24 | Superimposed Dead Loads | LS | 1 | 0 |  | 0
15.25 | Construction Sequence | EA Unit | 0 | 0 |  | 0
15.26 | Tendon Layouts | EA Unit | 0 | 0 |  | 0
15.27 | Live Load Analysis | EA Unit | 0 | 0 |  | 0
15.28 | Temperature Gradient | EA Unit | 0 | 0 |  | 0
15.29 | Time Dependent Analysis | EA Unit | 0 | 0 |  | 0
15.3 | Stress Summary | EA Unit | 0 | 0 |  | 0
15.31 | Ultimate Moments | EA Unit | 0 | 0 |  | 0
15.32 | Ultimate Shear | EA Unit | 0 | 0 |  | 0
15.33 | Construction Loading | EA Unit | 0 | 0 |  | 0
Transverse Analysis
15.34 | Time Dependent Analysis | EA Typ. Section | 0 | 0 |  | 0
15.35 | Live Load Analysis | EA Typ. Section | 0 | 0 |  | 0
15.36 | Temperature Gradient | EA Typ. Section | 0 | 0 |  | 0
15.37 | Stress Summary | EA Typ. Section | 0 | 0 |  | 0
15.38 | Ultimate Moments | EA Typ. Section | 0 | 0 |  | 0
15.39 | Construction Loading | EA Typ. Section | 0 | 0 |  | 0
Superstructure Design
15.4 | Typical Segment | LS | 1 | 0 |  | 0
15.41 | Pier Segment | EA Type | 0 | 0 |  | 0
15.42 | Expansion Joint Segment | EA Type | 0 | 0 |  | 0
15.43 | Blister Details | EA Type | 0 | 0 |  | 0
15.44 | Deviator Blocks | EA Type | 0 | 0 |  | 0
15.45 | Bearings | LS | 1 | 0 |  | 0
15.46 | Expansion Joints | EA Design | 0 | 0 |  | 0
15.47 | Special Analysis | EA Case | 0 | 0 |  | 0
Superstructure Plans
15.48 | Typical Sections | Sheet | 0 | 0 | 0 | 0
15.49 | Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
15.5 | Segment Layout/Designations | Sheet | 0 | 0 | 0 | 0
15.51 | Typical Segments | Sheet | 0 | 0 | 0 | 0
15.52 | Variable Depth Segments | Sheet | 0 | 0 | 0 | 0
15.53 | Pier Segments | Sheet | 0 | 0 | 0 | 0
15.54 | Expansion Joint Segments | Sheet | 0 | 0 | 0 | 0
15.55 | CIP Closure Joint Details | Sheet | 0 | 0 | 0 | 0
15.56 | Casting Geometry | Sheet | 0 | 0 | 0 | 0
15.57 | Integrated 3-D Drawings | Sheet | 0 | 0 | 0 | 0
Post-Tensioning Details
15.58 | Bulkhead Details | Sheet | 0 | 0 | 0 | 0
15.59 | Transverse Tendon Layout | Sheet | 0 | 0 | 0 | 0
15.6 | Longitudinal Tendon Layout | Sheet | 0 | 0 | 0 | 0
15.61 | Temporary Post-Tensioning | Sheet | 0 | 0 | 0 | 0
15.62 | Quantities and Stressing Schedule | Sheet | 0 | 0 | 0 | 0
15.63 | Future Post-Tensioning | Sheet | 0 | 0 | 0 | 0
15.64 | Anchorage Blisters | Sheet | 0 | 0 | 0 | 0
15.65 | Deviation Blocks | Sheet | 0 | 0 | 0 | 0
15.66 | PT Grouting Plan Details | Sheet | 0 | 0 | 0 | 0
Miscellaneous Details
15.67 | Erection Sequence and Details | Sheet | 0 | 0 | 0 | 0
15.68 | Access Opening Details | Sheet | 0 | 0 | 0 | 0
15.69 | Bearings | Sheet | 0 | 0 | 0 | 0
15.7 | Expansion Joints | Sheet | 0 | 0 | 0 | 0
15.71 | Vermin Screen Details | Sheet | 0 | 0 | 0 | 0
15.72 | Railing Details | Sheet | 0 | 0 | 0 | 0
15.73 | Lighting and Luminaries | Sheet | 0 | 0 | 0 | 0
15.74 | Architectural Details | Sheet | 0 | 0 | 0 | 0
15.75 | Special Systems | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar Lists
15.76 | Preparation of Reinforcing Bar Lists | Sheet | 0 | 0 | 0 | 0
Load Rating
15.77 | Load Ratings (LRFR) | EA Unit | 0 | 0 |  | 0
| 15. Structures - Segmental Concrete Bridge Total |  |  |  | 0 | 0

## 16. Structures-Movable Span
Estimator: | [6 empty] | Enter project name & description
Bridge Identifier (Number or Name): | [6 empty] | 999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
Final Design Bascule Pier
16.1 | Pier Deck | LS | 1 | 0 |  | 0
16.2 | Leaf/Pier Clearance Diagrams | EA Diagram | 0 | 0 |  | 0
16.3 | Load Shoe Columns | LS | 1 | 0 |  | 0
16.4 | Trunnion Columns | LS | 1 | 0 |  | 0
16.5 | Foundations | LS | 1 | 0 |  | 0
16.6 | Footing | LS | 1 | 0 |  | 0
16.7 | Seal | LS | 1 | 0 |  | 0
16.8 | Back Wall (Approach Span Bearings) Closed Piers Only | LS | 1 | 0 |  | 0
16.9 | Bascule Pier Deck Elevations | EA Pier | 0 | 0 |  | 0
Bascule Pier Dimensions - Detailing
16.1 | Pier Plan Views | Sheet | 0 | 0 | 0 | 0
16.11 | Pier Elevation Views | Sheet | 0 | 0 | 0 | 0
16.12 | Pier Sections | Sheet | 0 | 0 | 0 | 0
Bascule Pier Reinforcing Details
16.13 | Pier Reinforcing | Sheet | 0 | 0 | 0 | 0
Bascule Pier Miscellaneous Details
16.14 | Pier Barrier Details | Sheet | 0 | 0 | 0 | 0
16.15 | Stair Details | Sheet | 0 | 0 | 0 | 0
16.16 | Handrail Details | Sheet | 0 | 0 | 0 | 0
16.17 | Ladder and Hatch Details | Sheet | 0 | 0 | 0 | 0
16.18 | Pier Equipment | Sheet | 0 | 0 | 0 | 0
16.19 | Bascule Pier Notes and Summary of Quantities | Sheet | 0 | 0 | 0 | 0
16.2 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
Bascule Leaf Design
16.21 | Deck Design | LS | 1 | 0 |  | 0
16.22 | Sidewalk Design | LS | 1 | 0 |  | 0
16.23 | Stringer Design | LS | 1 | 0 |  | 0
16.24 | Typical Floorbeam Design | LS | 1 | 0 |  | 0
16.25 | End Floorbeam Design | LS | 1 | 0 |  | 0
16.26 | Deep Floorbeam Design | LS | 1 | 0 |  | 0
16.27 | Sidewalk Bracket Design | LS | 1 | 0 |  | 0
16.28 | Roadway Bracket Design | LS | 1 | 0 |  | 0
16.29 | Main Girder Influence Lines | LS | 1 | 0 |  | 0
16.3 | Main Girder Design | LS | 1 | 0 |  | 0
16.31 | Trunnion Girder Design | LS | 1 | 0 |  | 0
16.32 | Main Girder Camber Data | LS | 1 | 0 |  | 0
16.33 | Leaf Lateral Bracing Design | LS | 1 | 0 |  | 0
16.34 | Counterweight Design | LS | 1 | 0 |  | 0
16.35 | Live Load Shoe Design | LS | 1 | 0 |  | 0
16.36 | Barrier Design | LS | 1 | 0 |  | 0
16.37 | Deck Elevations | LS | 1 | 0 |  | 0
16.38 | Balance Calculations | LS | 1 | 0 |  | 0
Bascule Leaf Detailing
16.39 | Bascule GP&E | Sheet | 0 | 0 | 0 | 0
16.4 | Bascule Leaf Notes | Sheet | 0 | 0 | 0 | 0
16.41 | Framing Plan | Sheet | 0 | 0 | 0 | 0
16.42 | Flooring Plan and Details | Sheet | 0 | 0 | 0 | 0
16.43 | Typical Section and Finish Grade Elevations | Sheet | 0 | 0 | 0 | 0
16.44 | Girder Elevation | Sheet | 0 | 0 | 0 | 0
16.45 | Girder Details | Sheet | 0 | 0 | 0 | 0
16.46 | Camber Layout | Sheet | 0 | 0 | 0 | 0
16.47 | Floor Beams | Sheet | 0 | 0 | 0 | 0
16.48 | Counterweight Girder/Box | Sheet | 0 | 0 | 0 | 0
16.49 | Trunnion Girder | Sheet | 0 | 0 | 0 | 0
16.5 | Cylinder Girder | Sheet | 0 | 0 | 0 | 0
16.51 | Lateral Bracing Details | Sheet | 0 | 0 | 0 | 0
16.52 | Counterweight Bracing Details | Sheet | 0 | 0 | 0 | 0
16.53 | Joint Details | Sheet | 0 | 0 | 0 | 0
16.54 | Traffic Barrier Details | Sheet | 0 | 0 | 0 | 0
16.55 | Pedestrian Rail and Support Details | Sheet | 0 | 0 | 0 | 0
16.56 | Curb and Sidewalk Details | Sheet | 0 | 0 | 0 | 0
16.57 | Barrier and Sidewalk Bracket Details | Sheet | 0 | 0 | 0 | 0
16.58 | Counterweight Details | Sheet | 0 | 0 | 0 | 0
16.59 | Stress Table or Influence Lines | Sheet | 0 | 0 | 0 | 0
Mechanical Design
16.6 | Final Power Requirements | LS | 1 | 0 |  | 0
16.61 | Trunnion Assembly | LS | 1 | 0 |  | 0
16.62 | Span Locks | LS | 1 | 0 |  | 0
16.63 | Sump Pumps | LS | 1 | 0 |  | 0
Mechanical Drive Design
16.64 | Drive Shafts, Couplings, Keys, Bearings and Supports | LS | 1 | 0 |  | 0
16.65 | Rack & Pinion, Bearings and Supports | LS | 1 | 0 |  | 0
16.66 | Drive Train | LS | 1 | 0 |  | 0
16.67 | Motor Brakes & Machinery Brakes | LS | 1 | 0 |  | 0
Hydraulic Drive Design
16.68 | Hydraulic Drive | LS | 1 | 0 |  | 0
Machinery Detailing
16.69 | Machinery Layout | Sheet | 0 | 0 | 0 | 0
16.7 | Machinery Elevation | Sheet | 0 | 0 | 0 | 0
16.71 | Machinery Section | Sheet | 0 | 0 | 0 | 0
16.72 | Trunnion Assembly | Sheet | 0 | 0 | 0 | 0
16.73 | Drive Details | Sheet | 0 | 0 | 0 | 0
16.74 | Span Locks | Sheet | 0 | 0 | 0 | 0
Electrical Design
16.75 | Load Analysis | LS | 1 | 0 |  | 0
16.76 | Power Distribution | LS | 1 | 0 |  | 0
16.77 | Drive Equipment | LS | 1 | 0 |  | 0
16.78 | Bridge Controls | LS | 1 | 0 |  | 0
16.79 | Grounding | LS | 1 | 0 |  | 0
16.8 | Lightning and Surge Suppression | LS | 1 | 0 |  | 0
16.81 | Pier Lighting | LS | 1 | 0 |  | 0
Electrical Detailing
16.82 | Electrical Plan and Elevation | Sheet | 0 | 0 | 0 | 0
16.83 | Electrical Symbols and Abbreviations | Sheet | 0 | 0 | 0 | 0
16.84 | Single/Three Line Diagram | Sheet | 0 | 0 | 0 | 0
16.85 | Panelboard and Light Fixture Schedules | Sheet | 0 | 0 | 0 | 0
16.86 | Wire and Conduit Schedules and Diagrams | Sheet | 0 | 0 | 0 | 0
16.87 | Control Desk/Panel Layout | Sheet | 0 | 0 | 0 | 0
16.88 | Control Schematics | Sheet | 0 | 0 | 0 | 0
16.89 | PLC Logic | Sheet | 0 | 0 | 0 | 0
16.9 | Communication System | Sheet | 0 | 0 | 0 | 0
16.91 | Navigation Lighting Details | Sheet | 0 | 0 | 0 | 0
16.92 | Pedestrian Gate, Traffic Gate and Barrier Details | Sheet | 0 | 0 | 0 | 0
16.93 | Submarine Cable | Sheet | 0 | 0 | 0 | 0
16.94 | Miscellaneous Details | Sheet | 0 | 0 | 0 | 0
Control House
16.95 | Architectural Design | LS | 1 | 0 |  | 0
16.96 | Architectural Details | Sheet | 0 | 0 | 0 | 0
16.97 | Structural Design | LS | 1 | 0 |  | 0
16.98 | Structural Details | Sheet | 0 | 0 | 0 | 0
16.99 | HVAC/Plumbing Design | LS | 1 | 0 |  | 0
16.1 | HVAC/Plumbing/Electrical Cables | Sheet | 0 | 0 | 0 | 0
Reinforcing Bar Lists
16.101 | Preparation of Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Load Rating
16.102 | Load Ratings | LS | 1 | 0 |  | 0
16. Structures - Movable Span Total |  |  |  |  | 0 | 0

## 17. Str-Retaining Walls
Estimator: | [6 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
General Requirements
17.1 | Key Sheet | Sheet | 0 | 0 | 0 | 0
17.2 | Horizontal Wall Geometry | Per Wall | 0 | 0 |  | 0
Permanent Proprietary Walls
17.3 | Vertical Wall Geometry | Per Wall | 0 | 0 |  | 0
17.4 | Semi-Standard Drawings | Sheet | 0 | 0 | 0 | 0
17.5 | Wall Plan and Elevations (Control Drawings) | Sheet | 0 | 0 | 0 | 0
17.6 | Details | Sheet | 0 | 0 | 0 | 0
Temporary Proprietary Walls
17.7 | Vertical Wall Geometry | Per Wall | 0 | 0 |  | 0
17.8 | Semi-Standard Drawings | Sheet | 0 | 0 | 0 | 0
17.9 | Wall Plan and Elevations (Control Drawings) | Sheet | 0 | 0 | 0 | 0
17.1 | Details | Sheet | 0 | 0 | 0 | 0
Cast-in-Place Retaining Walls
17.11 | Design | EA Design | 0 | 0 |  | 0
17.12 | Vertical Wall Geometry | EA Wall | 0 | 0 |  | 0
17.13 | General Notes | Sheet | 0 | 0 | 0 | 0
17.14 | Wall Plan and Elevations (Control Drawings) | Sheet | 0 | 0 | 0 | 0
17.15 | Sections and Details | Sheet | 0 | 0 | 0 | 0
17.16 | Reinforcing Bar List | Sheet | 0 | 0 | 0 | 0
Other Retaining Walls and Bulkheads
17.17 | Design | EA Design | 0 | 0 |  | 0
17.18 | Vertical Wall Geometry | EA Wall | 0 | 0 |  | 0
17.19 | General Notes, Tables and Misc. Details | Sheet | 0 | 0 | 0 | 0
17.2 | Wall Plan and Elevations | Sheet | 0 | 0 | 0 | 0
17.21 | Details | Sheet | 0 | 0 | 0 | 0
17. Structures - Retaining Walls Total |  |  |  |  | 0 | 0

## 18. Structures-Miscellaneous
Estimator: | [6 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Unit | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
Concrete Box Culvert
18.1 | Concrete Box Culverts | EA | 0 | 0 |  | 0
18.2 | Concrete Box Culverts Extensions | EA Extension | 0 | 0 |  | 0
18.3 | Concrete Box Culvert Data Table Plan Sheets | Sheet | 0 | 0 | 0 | 0
18.4 | Concrete Box Culvert Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
Strain Poles
18.5 | Steel Strain Poles | Initial Config | 0 | 0 |  | 0
|  | EA Add'l Config | 0 | 0 |  | 0
18.6 | Concrete Strain Poles | Initial Config | 0 | 0 |  | 0
|  | EA Add'l Config | 0 | 0 |  | 0
18.7 | Strain Pole Data Table Plan Sheets | Sheet | 0 | 0 | 0 | 0
18.8 | Strain Pole Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
Mast Arms
18.9 | Mast Arms | EA Design | 0 | 0 |  | 0
18.1 | Mast Arms Data Table Plan Sheets | Sheet | 0 | 0 | 0 | 0
18.11 | Mast Arm Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
Overhead/Cantilever Sign Structures
18.12 | Cantilever Sign Structures | EA Design | 0 | 0 |  | 0
18.13 | Overhead Span Sign Structures | EA Design | 0 | 0 |  | 0
18.14 | Special (Long Span) Overhead Span Sign Structures | EA Design | 0 | 0 |  | 0
18.15 | Monotube Overhead Sign Structure | EA Design | 0 | 0 |  | 0
18.16 | Bridge Mounted Signs (Attached to Superstr.) | EA Design | 0 | 0 |  | 0
18.17 | Overhead and Cantilever Sign Structures Data Table Plan Sheets | Sheet | 0 | 0 | 0 | 0
18.18 | Overhead and Cantilever Sign Structures Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
High Mast Lighting
18.19 | Non-Standard High Mast Lighting Structures | EA Design | 0 | 0 |  | 0
18.2 | High Mast Lighting Special Details Plan Sheets | Sheet | 0 | 0 | 0 | 0
Noise Barrier Walls (Ground Mount)
18.21 | Horizontal Wall Geometry | EA Wall | 0 | 0 |  | 0
18.22 | Vertical Wall Geometry | EA Wall | 0 | 0 |  | 0
18.23 | Summary of Quantities - Aesthetic Requirements | Sheet | 0 | 0 | 0 | 0
18.24 | Control Drawings | Sheet | 0 | 0 | 0 | 0
18.25 | Design of Noise Barrier Walls Covered by Standards | EA Design | 0 | 0 |  | 0
18.26 | Design of Noise Barrier Walls Not Covered by Standards | EA Design | 0 | 0 |  | 0
18.27 | Aesthetic Details | LS | 1 | 0 |  | 0
Special Structures
18.28 | Fender System | LS | 1 | 0 |  | 0
18.29 | Fender System Access | LS | 1 | 0 |  | 0
18.3 | Special Structures | LS | 1 | 0 |  | 0
18.31 | Other Structures | LS | 1 | 0 |  | 0
Ancillary Structures Report
18.32 | Condition Evaluation of Signal and Sign Structures, and High Mast Light Poles | EA structure | 0 | 0 | 0 | 0
18.33 | Condition Evaluation of Signal and Sign Structures, and High Mast Light Poles (No As built or Design Plans Available) | EA structure | 0 | 0 | 0 | 0
18.34 | Analytical Evaluation of Signal and Sign Structures, and High Mast Light Poles | EA structure | 0 | 0 | 0 | 0
18.35 | Ancillary Structures Report | LS | 1 | 0 |  | 0
18. Structures - Miscellaneous Total |  |  |  |  | 0 | 0

## Signing & Marking Guidelines
SIGNING AND PAVEMENT MARKING GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical traffic projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
A "Lower Range" roadway project may fall in the "Middle Range" for Signing and Pavement Marking projects and vice versa. See the project ranges below. The project ranges should be used only for Reference & Master Design Files and Quantities from Analysis. All other tasks should be defined on task by task basis and should not necessarily use the Project Ranges.
Lower Range
1. Rural projects (minimal intersection involvement)
2. Limited Access with interchange spacing greater than 3 miles
3. Intersection Improvements (up to two auxiliary lanes) or minor roadway improvements
4. Limited Access resurfacing - Striping and minor signing
Middle Range
1. Limited Access with interchange spacing between 2 and 3 miles
2. Intersection Improvements (three to six auxiliary lanes)
3. Interchange Improvements (rural diamond)
4. Multi-Lane with less than three signals per mile
Upper Range
1. Multi-Lane with three signals or more per mile
2. Limited Access with interchange spacing less than two miles
3. Major Intersection Improvements (seven or more auxiliary lanes)
4. Interchange Improvements (loop ramps or urban diamond)
("Limited Access with Interchange Spacing" applies to Widening, New Construction and /or Major Signing)
("Auxiliary lanes" applies to the total exclusive turn lanes for the entire intersection.)

## 19. Signing & Marking Analysis
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
19.1 | Traffic Data Analysis | LS | 1 | 0 | 0
19.2 | No Passing Zone Study | LS | 1 | 0 | 0
19.3 | Reference and Master Design File | LS | 1 | 0 | 0
19.4 | Multi-Post Sign Support Calculations | EA | 1 | 0 | 0
19.5 | Sign Panel Design Analysis | EA | 1 | 0 | 0
19.6 | Sign Lighting/Electrical Calculations | EA | 1 | 0 | 0
19.7 | Quantities | LS | 1 | 0 | 0
19.8 | Cost Estimate | LS | 1 | 0 | 0
19.9 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
19.1 | Other Signing and Pavement Marking | LS | 1 | 0 | 0
Signing and Pavement Marking Analysis Technical Subtotal |  |  |  |  | 0
19.11 | Field Reviews | LS | 1 | 0 | 0
19.12 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
19.13 | Quality Assurance/Quality Control | LS | % | 0% | 0
19.14 | Independent Peer Review | LS | % | 0% | 0
19.15 | Supervision | LS | % | 0% | 0
Signing and Pavement Marking Analysis Nontechnical Subtotal |  |  |  |  | 0
19.16 | Coordination | LS | % | 0% | 0
19. Signing and Pavement Marking Analysis Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
Sign Panel Design |  | EA | 0 | 0 | 0 |  |  | 0
Queue Length Analysis |  | EA | 0 | 0 | 0 |  |  | 0
Local Governments (cities, counties) |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 19.12 |  |  | Carries to Tab 3

## 20. Signing & Marking Plans
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name | [5 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Scale | Units | No of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
20.1 | Key Sheet |  | Sheet | 0 | 0 | 0 | 0
20.2 | Summary of Pay Items Including Input |  | LS | 1 | 0 |  | 0
20.3 | Tabulation of Quantities |  | Sheet | 0 | 0 | 0 | 0
20.4 | General Notes/Pay Item Notes |  | Sheet | 0 | 0 | 0 | 0
20.5 | Project Layout |  | Sheet | 0 | 0 | 0 | 0
20.6 | Plan Sheet |  | Sheet | 0 | 0 | 0 | 0
20.7 | Typical Details |  | EA | 0 | 0 |  | 0
20.8 | Guide Sign Worksheet(s) |  | EA | 0 | 0 |  | 0
20.9 | Traffic Monitoring Site |  | EA | 0 | 0 |  | 0
20.1 | Cross Sections |  | EA | 0 | 0 |  | 0
20.11 | Special Service Point Details |  | EA | 0 | 0 |  | 0
20.12 | Special Details |  | LS | 1 | 0 |  | 0
20.13 | Interim Standards |  | LS | 1 | 0 |  | 0
Signing and Pavement Marking Plans Technical Subtotal | [5 empty] | 0 | 0
20.14 | Quality Assurance/Quality Control |  | LS | % | 0% |  | 0
20.15 | Supervision |  | LS | % | 0% |  | 0
20. Signing and Pavement Marking Plans Total | [5 empty] | 0 | 0

## Signalization Guidelines
SIGNALIZATION GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical traffic projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
A "Lower Range" roadway project may fall in the "Middle Range" for Lighting projects and vice versa. See the project ranges below. The project ranges should be used only for Reference & Master Design Files and Quantities from Analysis. All other tasks should be defined on task by task basis and should not necessarily use the Project Ranges.
Lower Range
1. Rural 2-Lane Project
2. Vehicular Loop Replacement
3. Flashing Beacon
4. Mid Block Traffic Signal
Middle Range
1. Rural Multi-Lane Highway
2. Urban Multi-Lane with minor R/W issues or Utility impacts
3. Urban 2-Lane with major R/W issues or Utility impacts.
Upper Range
1. Urban Multi-Lane with major R/W issues or Utility impacts
2. Single Point Urban Interchange

## 21. Signalization Analysis
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
21.1 | Traffic Data Collection | LS | 1 | 0 | 0
21.2 | Traffic Data Analysis | PI | 0 | 0 | 0
21.3 | Signal Warrant Study | LS | 1 | 0 | 0
21.4 | System Timings | LS | 1 | 0 | 0
21.5 | Reference and Master Signalization Design File | PI | 0 | 0 | 0
21.6 | Reference and Master Interconnect Communication Design File | LS | 1 | 0 | 0
21.7 | Overhead Street Name Sign Design | EA | 0 | 0 | 0
21.8 | Pole Elevation Analysis | LS | 1 | 0 | 0
21.9 | Traffic Signal Operation Report | LS | 1 | 0 | 0
21.1 | Quantities | LS | 1 | 0 | 0
21.11 | Cost Estimate | LS | 1 | 0 | 0
21.12 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
21.13 | Other Signalization Analysis | LS | 1 | 0 | 0
Signalization Analysis Technical Subtotal |  |  |  |  | 0
21.14 | Field Reviews | LS | 1 | 0 | 0
21.15 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
21.16 | Quality Assurance/Quality Control | LS | % | 0% | 0
21.17 | Independent Peer Review | LS | % | 0% | 0
21.18 | Supervision | LS | % | 0% | 0
Signalization Analysis Nontechnical Subtotal |  |  |  |  | 0
21.19 | Coordination | LS | % | 0% | 0
21. Signalization Analysis Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
FDOT Traffic Operations |  | EA | 0 | 0 | 0 |  |  | 0
FDOT Traffic Design |  | EA | 0 | 0 | 0 |  |  | 0
Power Company (service point coordination) |  | EA | 0 | 0 | 0 |  |  | 0
Maintaining Agency (cities, counties) |  | EA | 0 | 0 | 0 |  |  | 0
Railroads |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 21.15 |  |  | Carries to Tab 3

## 22. Signalization Plans
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name | [5 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Scale | Units | No of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
22.1 | Key Sheet |  | Sheet | 0 | 0 | 0 | 0
22.2 | Summary of Pay Items Including Designer Interface Input |  | Sheet | 0 | 0 | 0 | 0
22.3 | Tabulation of Quantities |  | Sheet | 0 | 0 | 0 | 0
22.4 | General Notes/Pay Item Notes |  | Sheet | 0 | 0 | 0 | 0
22.5 | Plan Sheet |  | Sheet | 0 | 0 | 0 | 0
22.6 | Interconnect Plans |  | Sheet | 0 | 0 | 0 | 0
22.7 | Traffic Monitoring Site |  | EA | 0 | 0 |  | 0
22.8 | Guide Sign Worksheet |  | EA | 0 | 0 |  | 0
22.9 | Special Details |  | Sheet | 0 | 0 | 0 | 0
22.1 | Special Service Point Details |  | EA | 0 | 0 |  | 0
22.11 | Mast Arm/Monotube Tabulation Sheet |  | PI | 0 | 0 |  | 0
22.12 | Strain Pole Schedule |  | PI | 0 | 0 |  | 0
22.13 | TTCP Signal |  | EA | 0 | 0 |  | 0
22.14 | Temporary Detection Sheet |  | PI | 0 | 0 |  | 0
22.15 | Utility Conflict Sheet |  | Sheet | 0 | 0 | 0 | 0
22.16 | Interim Standards |  | LS | 1 | 0 |  | 0
Signalization Plans Technical Subtotal | [5 empty] | 0 | 0
22.17 | Quality Assurance/Quality Control |  | LS | % | 0% |  | 0
22.18 | Supervision |  | LS | % | 0% |  | 0
22. Signalization Plans Total | [5 empty] | 0 | 0

## Lighting Guidelines
LIGHTING GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical traffic projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
A "Lower Range" roadway project may fall in the "Middle Range" for Lighting projects and vice versa. See the project ranges below. The project ranges should be used only for Reference & Master Design Files and Quantities from Analysis. All other tasks should be defined on task by task basis and should not necessarily use the Project Ranges.
Lower Range
1. Rural Multi-Lane
2. Limited Access
Middle Range
1. Urban Multi-Lane
2. Complex Limited Access
3. Interchange Projects
Upper Range
1. Complex Interchange Projects
2. Stand-alone Corridor Lighting Projects

## 23. Lighting Analysis
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
23.1 | Lighting Justification Report | LS | 1 | 0 | 0
23.2 | Lighting Design Analysis Report | LS | 1 | 0 | 0
23.3 | Voltage Drop Calculations | EA | 0 | 0 | 0
23.4 | FDEP Coordination and Report | LS | 1 | 0 | 0
23.5 | Reference and Master Design Files | LS | 1 | 0 | 0
23.6 | Temporary Lighting | LS | 1 | 0 | 0
23.7 | Design Documentation | LS | 1 | 0 | 0
23.8 | Quantities | LS | 1 | 0 | 0
23.9' | Cost Estimate | LS | 1 | 0 | 0
23.1 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
23.11 | Other Lighting Analysis | LS | 1 | 0 | 0
Lighting Analysis Technical Subtotal |  |  |  |  | 0
23.12 | Field Reviews | LS | 1 | 0 | 0
23.13 | Technical Meetings | LS | 1 | 0 | 0
23.14 | Quality Assurance/Quality Control | LS | % | 0% | 0
23.15 | Independent Peer Review | LS | % | 0% | 0
23.16 | Supervision | LS | % | 0% | 0
Lighting Analysis Nontechnical Subtotal |  |  |  |  | 0
23.17 | Coordination | LS | % | 0% | 0
23. Lighting Analysis Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
FDOT Lighting Design |  | EA | 0 | 0 | 0 |  |  | 0
FDOT Traffic Design |  | EA | 0 | 0 | 0 |  |  | 0
Power Company (service point coordination) |  | EA | 0 | 0 | 0 |  |  | 0
Maintaining Agency (cities, counties) |  | EA | 0 | 0 | 0 |  |  | 0
Airport authority |  | EA | 0 | 0 | 0 |  |  | 0
FDEP Lighting (coast areas) |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 23.14 |  |  | Carries to Tab 3

## 24. Lighting Plans
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name | [5 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Scale | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
24.1 | Key Sheet |  | Sheet | 0 | 0 | 0 | 0
24.2 | Summary of Pay Items Including Designer Interface Input |  | Sheet | 0 | 0 | 0 | 0
24.3 | Tabulation of Quantities |  | Sheet | 0 | 0 | 0 | 0
24.4 | General Notes/Pay Item Notes |  | Sheet | 0 | 0 | 0 | 0
24.5 | Pole Data, Legend and Criteria |  | Sheet | 0 | 0 | 0 | 0
24.6 | Service Point Details |  | Sheet | 0 | 0 | 0 | 0
24.7 | Project Layout |  | Sheet | 0 | 0 | 0 | 0
24.8 | Plan Sheet |  | Sheet | 0 | 0 | 0 | 0
24.9 | Special Details |  | Sheet | 0 | 0 | 0 | 0
24.1 | Temporary Lighting Data and Details |  | Sheet | 0 | 0 | 0 | 0
24.11 | Temporary Traffic Control Plan Sheets |  | Sheet | 0 | 0 | 0 | 0
24.12 | Interim Standards |  | LS | 1 | 0 |  | 0
Lighting Plans Technical Subtotal | [5 empty] | 0 | 0
24.13 | Quality Assurance/Quality Control |  | LS | % | 0% |  | 0
24.14 | Supervision |  | LS | % | 0% |  | 0
24. Lighting Plans Total | [5 empty] | 0 | 0

## Landscape Guidelines
LANDSCAPE GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on landscaping projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
Lower Range
1. Complexity of Landscape Design: Minimum Quantities |  |  | 6. Outdoor Advertising: 1 to 3 Sign Faces
2. Roadway Type: Existing roadway. |  |  | 7. Stakeholder Participation: 1 to 3 stakeholder meetings
3. Roadway Elements: Minor intersections. |  |  | 8. Irrigation System: Simple System, potable supply. Existing water/power source
4. Roadway Location: Rural. |  |  | 9. Hardscape Development: Simple surfaces, catalog items.
5. Utility Coordination: Minimum. |  |  | 10. Base Files: Complete and current CADD files available
Middle Range
1. Complexity of Landscape Design: Moderate Quantities |  |  | 6. Outdoor Advertising: 4 to 6 Sign Faces
2. Roadway Type: Roadway widening. |  |  | 7. Stakeholder Participation: 4 to 6 stakeholder meetings
3. Roadway Elements: Standard interchanges. |  |  | 8. Irrigation System: Moderate complexity, wells, multiple mainlines. Proposed water/power source
4. Roadway Location: Suburban. |  |  | 9. Hardscape Development: Moderate patterns, special elements.
5. Utility Coordination: Moderate (Suburban). |  |  | 10. Base Files: Partial CADD files available
Upper Range
1. Complexity of Landscape Design: Large Quantities |  |  | 6. Outdoor Advertising: 7+ Sign Faces
2. Roadway Type: New roadway alignment. |  |  | 7. Stakeholder Participation: Public workshops
3. Roadway Elements: Multiple-level interchanges. |  |  | 8. Irrigation System: Complex system. multiple water/power sources and system types
4. Roadway Location: Urban. |  |  | 9. Hardscape Development: Custom vertical elements, walls, structures.
5. Utility Coordination: Extensive (urban). |  |  | 10. Base Files: No useable CADD files
The following matrix for the Task 25, Landscape Architecture Analysis, work activities was developed as part of the Staff Hour Basis to help Consultant and FDOT landscape architects determine the overall level of complexity of a project with respect to the landscape component. The Consultants and the Department will use the matrix (see below) to determine the appropriate level of complexity, based on the project scope, for each Task element. The Consulants and the Department will then use the negotiated level of complexity (Lower, Middle, or Upper) results to determine where, in each defined staff hour range, the level of design effort should fall.
STAFF-HOUR RANGE FOR LANDSCAPE ANALYSIS
PROJECT SCOPE | LOWER | MIDDLE | UPPER | RATING | COMMENTS
Complexity of Landscape Design | Minimum Qtys | Moderate Qtys | Large Qtys
| j k l | m n o | p q r
Roadway Type | Existing Roadway | Roadway Widening | New Roadway Alignment
| j k l | m n o | p q r
Roadway Elements | Minor Intersections | Standard Interchanges | Multiple-Level Interchanges
| j k l | m n o | p q r
Roadway Location | Rural | Suburban | Urban
| j k l | m n o | p q r
Utility Coordination | Minimum (Rural) | Moderate (Suburban) | Extensive (Urban)
| j k l | m n o | p q r
Outdoor Advertising | 1-3 Sign Faces | 4-6 Sign Faces | 7+ Sign Faces
| j k l | m n o | p q r
Stakeholder Participation | 1-3 Stakeholder Meetings | 4-6 Stakeholder Meetings | Public Workshops
| j k l | m n o | p q r
Irrigation System | Simple System, potable supply Existing water/power source | Moderate complexity, wells, multiple mainlines, proposed water/power source | Complex System, Multiple water/power source and system types
| j k l | m n o | p q r
Hardscape Development | Simple surfaces, catalog items | Moderate patterns, special elements | Custom vertical elements, walls, structures
| j k l | m n o | p q r
Other Considerations (Explain) Base Files | Complete and current CADD files available | Partial CADD files available | No Usable CADD Files
| j k l | m n o | p q r
Total Points |  |  |  | 0
STAFF-HOUR RANGES
Lower Range - Total Points <30
Middle Range - Total Points 30-50
Upper Range - Total Points >50

## 25. Landscape Analysis
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Units | Total Hours | Comments
25.1 | Data Collection | LS | 1 | 0 | 0
25.2 | Site Inventory and Analysis
25.2a | Selective Clearing and Grubbing Site Inventory | LS | 1 | 0 | 0
25.2b | Inventory and Analysis | LS | 1 | 0 | 0
25.2c | Vegetation Disposition Plan
25.2c1 | Vegetation Disposition Plan- Mainline | Per mainline mile | 0 | 0 | 0
25.2c2 | Vegetation Disposition Plan- Interchange | Per interchange | 0 | 0 | 0
25.3 | Planting Design
25.3a | Conceptual Planting Design
25.3a1 | Report Preparation | LS | 1 | 0 | 0
25.3a2 | Mainline | Per mainline mile | 0 | 0 | 0
25.3a3 | Interchanges, Intersections, and Rest Areas | EA | 0 | 0 | 0
25.3a4 | Toll Plazas | EA | 0 | 0 | 0
25.3b | Final Planting Design
25.3b1 | Master Design File Creation | LS | 1 | 0 | 0
25.3b2 | Mainline | Per mainline mile | 0 | 0 | 0
25.3b3 | Interchanges, Intersections, and Rest Areas | EA | 0 | 0 | 0
25.3b4 | Toll Plazas | EA | 0 | 0 | 0
25.4 | Irrigation Design
25.4a | Conceptual Irrigation Design
25..4a1 | Feasibility Report | LS | 1 | 0 | 0
25..4a2 | Mainline | Per mainline mile | 0 | 0 | 0
25..4a3 | Interchanges, Intersections, and Rest Areas | EA | 0 | 0 | 0
25..4a4 | Toll Plazas | EA | 0 | 0 | 0
25.4b | Final irrigation Design
25.4b1 | Mainline | Per mainline mile | 0 | 0 | 0
25.4b2 | Interchanges, Intersections, and Rest Areas | EA | 0 | 0 | 0
25.4b3 | Toll Plazas | EA | 0 | 0 | 0
25.5 | Hardscape Design
25.5a | Conceptual Hardscape Design | Per mainline mile | 0 | 0 | 0
26.5b | Final Hardscape Design | Per mainline mile | 0 | 0 | 0
25.6 | Roll Plots | EA | 0 | 0 | 0
25.7 | Cost Estimates | LS | 1 | 0 | 0
25.8 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
25.9 | Inspection Services | LS | 1 | 0 | 0
25.1 | Other Landscape Services | LS | 1 | 0 | 0
25.11 | Outdoor Advertising | EA | 0 | 0 | 0
Landscape Analysis Technical Subtotal |  |  |  |  | 0
25.12 | Field Reviews | LS | 1 | 0 | 0
25.13 | Technical Meetings / Public Meetings | LS | 1 | 0 | 0 | Meetings are listed below
25.14 | Quality Assurance/Quality Control | LS | % | 0% | 0
25.15 | Independent Peer Review | LS | % | 0% | 0
25.16 | Supervision | LS | % | 0% | 0
Landscape Analysis Nontechnical Subtotal |  |  |  |  | 0
25.17 | Project Coordination | LS | % | 0% | 0
25.18 | Interdisciplinary Coordination | LS | % | 0% | 0
25. Landscape Analysis Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
FDOT (kickoff, concept review) |  | EA | 0 | 0 | 0 |  |  | 0
Maintaining Agency (cities, counties) |  | EA | 0 | 0 | 0 |  |  | 0
Utility Owners |  | EA | 0 | 0 | 0 |  |  | 0
Local Agency for Tree Removal |  | EA | 0 | 0 | 0 |  |  | 0
Local Citizen Group(s) |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 25.12 |  |  | Carries to Tab 3

## 26. Landscape Plans
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name | [5 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Scale | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
26.1 | Key Sheet |  | Sheet | 0 | 0 | 0 | 0
26.2 | Tabulation of Quantities and Plant Schedule |  | Sheet | 0 | 0 | 0 | 0
26.3 | General Notes |  | Sheet | 0 | 0 | 0 | 0
26.4 | Tree and Vegetation Protection and Relocation Plans and Tree Disposition Plans |  | Sheet | 0 | 0 | 0 | 0
26.5 | Planting Plans For Linear Roadway Projects |  | Sheet | 0 | 0 | 0 | 0
26.6 | Planting Plans (Interchanges and Toll Plazas) |  | Sheet | 0 | 0 | 0 | 0
26.7 | Planting Details and Notes |  | Sheet | 0 | 0 | 0 | 0
26.8 | Irrigation Plans for Linear Roadway Project |  | Sheet | 0 | 0 | 0 | 0
26.9 | Irrigation Plans for Interchange and Toll Plazas |  | Sheet | 0 | 0 | 0 | 0
26.1 | Irrigation Details and Notes |  | Sheet | 0 | 0 | 0 | 0
26.11 | Hardscape Plans |  | Sheet | 0 | 0 | 0 | 0
26.12 | Hardscape Details and Notes |  | Sheet | 0 | 0 | 0 | 0
26.13 | Maintenance Plan |  | Sheet | 0 | 0 | 0 | 0
Landscape Plans Technical Hours Subtotal | [5 empty] | 0 | 0
26.14 | Quality Assurance/Quality Control |  | LS | % | 0% |  | 0
26.15 | Supervision |  | LS | % | 0% |  | 0
26. Landscape Plans Total | [5 empty] | 0 | 0

## Survey Guidelines
GUIDELINES FOR SURVEY, PHOTOGRAMMETRY, MAPPING, AND TERESTRIAL MOBILE LIDAR (Work Activities 27 – 30)
These four work activities are interrelated. Not all projects will require photogrammetry, mapping or terrestrial mobile LiDAR: the need or extent of any of these will have a direct relationship on the tasks included in the survey work activity.
All ranges shown in the Survey tasks are for 4-person crew days based on an 8 hour day. The ranges presented in the photogrammetry section represent the work effort that might be expected for individual tasks on typical mapping projects, including topographics, planimetrics, image processing, and fixed and rotary wing flight operations.
The staff hour ranges presented in this section represent the work effort that might be expected for individual tasks on typical roadway projects, ranging from a standard 2-lane resurfacing project (lower end of range) to a complicated reconstruction project (upper end of range). The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual survey tasks. Hours below or above the presented ranges may be applicable based on the constraints or requirements that are specific to the individual project. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
The following are general examples of the types of projects which would contain work effort from below the staff hour ranges contained in this handbook to above the ranges. This list is not inclusive, or always exact, but will provide the basis for beginning estimation and negotiation of staff hours for a project.
Survey Levels 1 through 4 are defined in FDOT Design Manual (FDM), Chapters 114, 210, 211, and 260.
Below to Lower End of Range Projects
· Urban and rural 2-lane resurfacing Level 1 survey.
· Rural 2-lane 3R (minor safety, earthwork, and utility involvement) Level 1 or 2.
· Rural 4-lane 3R (minor safety, earthwork, and utility involvement) Level 1 or 2
· Urban 3R (minor safety, earthwork, and utility involvement, primarily only milling and resurfacing) Level 1 or 2
· Multi-lane limited access resurfacing (minimal interchange involvement) Level 1 or 2
Lower End of Range Projects
· Rural 2-lane 3R (major safety, earthwork, and utility involvement) Level 2 or 3
· Rural 4-lane 3R (major safety, earthwork, and utility involvement) Level 2 or 3
· Urban 3R (major safety, earthwork, and utility involvement) Level 2 or 3
· Rural 2-lane to multi-lane widening/resurfacing (minor ROW, earthwork and utility impacts) Level 2 or 3
· Rural 2-lane new construction (new alignment, ROW, earthwork and utility impacts) (This is for full design survey and ROW) Level 4
· Rural 2-lane to urban multi-lane reconstruction (minor ROW and utility impacts, minimal intersection involvement) (This is for full design survey and ROW) Level 4
· Rural or urban 4-lane to 6-lane widening/resurfacing (widening in median, minor ROW, earthwork, and utility impacts, minimal intersection improvement) Level 3 or 4
· Rural 2-lane to 4-lane widening/resurfacing (major ROW, earthwork and utility impacts) Level 3 or 4 for full design model
· Multi-lane limited access resurfacing (minor safety, earthwork, and utility involvement, minimal intersection involvement) Level 2 or 3
· Rural 2-lane to urban multi-lane widening/resurfacing (utilizing existing pavement, minor cross slope correction, major ROW and utility impacts, intersection involvement) Level 3 or 4 for full design model
Middle of Range Projects
· Rural 2-lane to urban multi-lane reconstruction (major ROW and utility impacts, intersection involvement) (This is for full design survey and ROW) Level 4
· Rural multi-lane new construction (new alignment, ROW, earthwork and utility impacts, minimal intersection involvement) (This is for full design survey and ROW) Level 4
· Urban multi-lane new construction (new alignment, major ROW and utility impacts, intersection involvement) (This is for full design survey and ROW) Level 4
· Multi-lane limited access widening/resurfacing (minor ROW and utility impacts, interchange involvement) Level 3 or 4 for full design model (This is for full design survey and ROW)
· Multi-lane limited access reconstruction (minor ROW and utility impacts, interchange involvement) (This is for full design survey and ROW) Level 4
· Multi-lane limited access new construction (new alignment, minor ROW and utility impacts, minimal interchange involvement) (This is for full design survey and ROW) Level 4
Upper End to Above Range Projects
· Multi-lane widening, reconstruction or new alignment with major interchange involvement (major ROW and utility impacts,urban interchange involvement, major access management impacts) (This is for full design survey and ROW) Level 4
· Urban limited access (widening or reconstruction with multi-level interchanges) (This is for full design survey and ROW) Level 4
· Multi-lane limited access new construction (new alignment, major ROW and utility impacts, major interchange involvement) (This is for full design survey and ROW) Level 4

## 27. Survey
Estimator: | [9 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name | [6 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Field Crew Days/Unit | Crew Days | Field Support Hours / Crew Days | Field Support Hours | Office Support Hours / Crew Days | Office Support Hours | Comments
27.1 | Horizontal Project Control (HPC)
| 2-Lane Roadway | Mile |  |  | 0 |  | 0 |  | 0
| Multi-lane Roadway | Mile |  |  | 0 |  | 0 |  | 0
| Interstate | Mile |  |  | 0 |  | 0 |  | 0
27.2 | Vertical PC / Bench Line
| 2-Lane Roadway | Mile |  |  | 0 |  | 0 |  | 0
| Multi-lane Roadway | Mile |  |  | 0 |  | 0 |  | 0
| Interstate | Mile |  |  | 0 |  | 0 |  | 0
27.3 | Alignment and Existing R/W Lines
|  | Mile |  |  | 0 |  | 0 |  | 0
27.4 | Aerial Targets |  |  | Units/Day
| 2-Lane Roadway | EA |  |  | 0 |  | 0 |  | 0
| Multi-lane Roadway | EA |  |  | 0 |  | 0 |  | 0
| Interstate | EA |  |  | 0 |  | 0 |  | 0
27.5 | Reference Points | "A" |  | Units/Day
| 2-Lane Roadway | EA |  |  | 0 |  | 0 |  | 0
| Multi-lane Roadway | EA |  |  | 0 |  | 0 |  | 0
| Interstate | EA |  |  | 0 |  | 0 |  | 0
| Reference Points | "B" |  | Units/Day
| Non Alignment Points/Approximate | EA |  |  | 0 |  | 0 |  | 0
27.6 | Topography/DTM (3D)
|  | Mile |  |  | 0 |  | 0 |  | 0
27.7 | Planimetric (2D)
|  | Mile |  |  | 0 |  | 0 |  | 0
27.8 | Roadway Cross-Sections/Profiles
|  | Mile |  |  | 0 |  | 0 |  | 0
27.9 | Side Street Surveys
|  | Mile |  |  | 0 |  | 0 |  | 0
27.1 | Underground Utilities
| Designates | Mile/Site |  |  | 0 |  | 0 |  | 0
| Locates | Point |  |  | 0 |  | 0 |  | 0
| Survey |  | 0% | 0 | 0 |  | 0 |  | 0
27.11 | Outfall Survey
|  | Mile |  |  | 0 |  | 0 |  | 0
27.12 | Drainage Survey |  |  | Units/Day
|  | EA |  |  | 0 |  | 0 |  | 0
27.13 | Bridge Survey
| Minor / Major | EA |  |  | 0 |  | 0 |  | 0
27.14 | Channel Survey
|  | EA |  |  | 0 |  | 0 |  | 0
27.15 | Pond Site Survey
|  | EA |  |  | 0 |  | 0 |  | 0
27.16 | Mitigation Survey
|  | Mile |  |  | 0 |  | 0 |  | 0
27.17 | Jurisdiction Line Survey
|  | Mile |  |  | 0 |  | 0 |  | 0
27.18 | Geotechnical Support |  |  | Units/Day
|  | EA |  |  | 0 |  | 0 |  | 0
27.19 | Sectional / Grant Survey
|  | Corner |  |  | 0 |  | 0 |  | 0
|  | Mile |  |  | 0 |  | 0 |  | 0
27.2 | Subdivision Location
|  | Block |  |  | 0 |  | 0 |  | 0
27.21 | Maintained R/W
|  | Mile |  |  | 0 |  | 0 |  | 0
27.22 | Boundary Survey
|  | EA |  |  | 0 |  | 0 |  | 0
27.23 | Water Boundary Survey
|  | EA |  |  | 0 |  | 0 |  | 0
27.24 | R/W Staking / R/W Line
|  | EA |  |  | 0 |  | 0 |  | 0
|  | Mile |  |  | 0 |  | 0 |  | 0
27.25 | R/W Monumentation
|  | Point |  |  | 0 |  | 0 |  | 0
27.26 | Line Cutting
|  | Mile |  |  | 0
27.27 | Work Zone Safety
0
27.28 | Vegetation Survey
|  | LS | [6 empty] | 0
27.29 | Tree Survey
|  | LS | [6 empty] | 0
27.3 | Miscellaneous Surveys
[5 empty] | 0 |  | 0 |  | 0
Survey Subtotal |  |  |  | Crew Days | 0 | Field Support Hours | 0 | Office Support Hours | 0
27.31 | Supplemental Surveys | [8 empty] | THE % FOR SUPPLEMENTAL WILL BE DETERMINED AT NEGOTIATIONS. THIS ITEM CAN ONLY BE USED IF AUTHORIZED IN WRITING BY THE DISTRICT SURVEYOR
|  |  |  | 0 | 0 |  | 0 |  | 0
27.32 | Document Research | Units
0
27.33 | Field Reviews | Units
0
27.34 | Technical Meetings | LS
|  |  | 0 | [5 empty] | 0
27.35 | Quality Assurance / Quality Control | LS
[8 empty] | 5% | 0
27.36 | Supervision | LS
[8 empty] | 5% | 0
27.37 | Coordination | LS
[8 empty] | 3% | 0
27. Survey Total |  |  |  | Crew Days | 0 | Field Support Hours | 0 | Office Support Hours | 0
SPLS =
PLS =
Office Support =
[8 empty] | Total Hours = | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | PM Attendance at Meeting Required? |  |  | Number | Comments
Kickoff Meeting with FDOT |  | EA | 0 | 0 | 0 |  |  |  | 0
Baseline Approval Review |  | EA | 0 | 0 | 0 |  |  |  | 0
Network Control Review |  | EA | 0 | 0 | 0 |  |  |  | 0
Vertical Control Review |  | EA | 0 | 0 | 0 |  |  |  | 0
Local Governments (cities, counties) |  | EA | 0 | 0 | 0 |  |  |  | 0
Final Submittal Review |  | EA | 0 | 0 | 0 |  |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 | Subtotal PM Meetings |  |  | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | ** |  |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | ** |  |  | - -
Total Meetings |  |  |  |  | 0 | Total PM Mtgs (carries to Tab 3) |  |  | 0
[5 empty] | Carries to 27.32 |  |  |  | Carries to Tab 3
** Project Manager attendance at progress, phase and field review meetings are manually entered on General Task 3

## 28. Photogrammetry
Estimator: | [12 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name | [6 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hour / Unit | Hours | [5 empty] | Total Range | Comments | Comments
[5 empty] | PSM | Data Compiler | Map/Data Editor | Ortho Analyst | Lab Processor | Flight Crew
28.1 | Flight Preparation | Frame | 0 | 0 | [5 empty] | 0 | 0 |  | Flight crew only
|  | Frame | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.2 | Control Point Coordination
| Post ID | Point | 0 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | Point | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Complier only
28.3 | Mobilization
| Fixed Wing | Hour | 0 | 0 | [5 empty] | 0 | 0 |  | Flight crew only
| Rotary Wing | Hour | 0 | 0 | [5 empty] | 0 | 0 |  | Flight crew only
28.4 | Flight Operations
| Fixed Wing | Mile | 0 | 0 | [5 empty] | 0 | 0
| Rotary Wing | Mile | 0 | 0 | [5 empty] | 0 | 0
28.5 | Film Processing | Frame | 0 | [5 empty] | 0 |  | 0
28.6 | Photo Products | Sheet | 0 | 0 |  |  |  |  | 0 |  | 0
28.7 | Scanning | Frame | 0 | 0 |  |  |  | 0 |  |  | 0 |  | Ortho Analyst only
|  | Frame | 0 | 0 |  |  |  |  | 0 |  | 0 |  | Lab Processor only
28.8 | Lidar | Mile | 0 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | Mile | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
|  | Mile | 0 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
28.9 | Aerial Triangulation
| Field Control | Frame | 0 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | Frame | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
| With Aerial GPS Control | Frame | 0 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | Frame | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.1 | Surfaces
| Digital Elevation Model | Model | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
| Digital Terrain Model | Model | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.11 | Ortho Generation | Image | 0 | 0 |  |  |  | 0 |  |  | 0 |  | Ortho Analyst only
28.12 | Rectified Digital Imagery (Georeferenced) | Image | 0 | 0 |  |  |  | 0 |  |  | 0
28.13 | Mosaicking | Image | 0 | 0 |  |  |  | 0 |  |  | 0
28.14 | Sheet Clipping | Sheet | 0 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
|  | Sheet | 0 | 0 |  |  |  | 0 |  |  | 0 |  | Ortho Analyst only
28.15 | Topographics (3D) | Model | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.16 | Planimetrics (2D) | Model | 0 | 0 |  | 0 |  |  |  |  | 0
28.17 | Drainage Basin | Sheet | 0 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
|  | Sheet | 0 | 0 |  |  |  | 0 |  |  | 0 |  | Ortho Analyst only
28.18 | CADD Edit | LS | 25% |  |  | 0 | 0 | 0 | 0 |  | 0 |  | Enter in formula for CADD Edit
28.19 | Data Merging | Model | 0 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
|  | Model | 0 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
28.2 | Miscellaneous | LS | 1 | 0 | 0 | [5 empty] | 0 |  | PSM only
|  | LS | 1 | 0 |  | 0 |  |  |  |  | 0 |  | Compiler only
|  | LS | 1 | 0 |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
|  | LS | 1 | 0 |  |  |  | 0 |  |  | 0 |  | Ortho Analyst only
|  | LS | 1 | 0 |  |  |  |  | 0 |  | 0 |  | Lab Processor only
|  | LS | 1 | 0 | [5 empty] | 0 | 0 |  | Flight Crew only
Photogrammetry Technical Subtotal | [10 empty] | 0
28.21 | Field Reviews | LS | 1 |  | 0 | [5 empty] | 0 |  | PSM only
|  | LS | 1 |  |  |  | 0 |  |  |  | 0 |  | Map/Data Editor only
28.22 | Technical Meetings | LS |  |  | 0 | [5 empty] | 0
28.23 | Quality Assurance/Quality Control | LS | 5% |  | 0 | [5 empty] | 0
28.24 | Supervision | LS | 5% |  | 0 | [5 empty] | 0
Photogrammetry Nontechnical Subtotal | [10 empty] | 0
28.25 | Coordination | LS | 0% |  | 0 | [5 empty] | 0
28. Photogrammetry Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Check = | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | PM Attendance at Meeting Required? |  |  |  |  | Number |  | Comments
Aerial Mapping Submittal Review |  | EA | 0 | 0 | 0 | [5 empty] | 0
Other Meetings |  | EA | 0 | 0 | 0 | [5 empty] | 0
Subtotal Technical Meetings |  |  |  |  | 0 | Subtotal PM Meetings |  |  |  |  | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | ** |  |  |  |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | ** |  |  |  |  | - -
Total Meetings |  |  |  |  | 0 | Total PM Mtgs (carries to Tab 3) |  |  |  |  | 0
[5 empty] | Carries to 28.22 | [5 empty] | Carries to Tab 3
** Project Manager attendance at progress, phase and field review meetings are manually entered on General Task 3

## 29. Mapping
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
Master CADD File
29.1 | Alignment | Mile | 0 | 0 |  | 0
29.2 | Section and 1/4 Section Lines | Section | 0 | 0 |  | 0
29.3 | Subdivisions / Property Lines | EA | 0 | 0 |  | 0
29.4 | Existing R/W | Mile | 0 | 0 |  | 0
29.5 | Topography | Mile | 0 | 0 |  | 0
29.6 | Parent Tract Properties/Existing Easements | Parcel | 0 | 0 |  | 0
29.7 | Proposed R/W Requirements | Parcel | 0 | 0 |  | 0
29.8 | Limits of Construction | Mile | 0 | 0 |  | 0
29.9 | Jurisdictional/Agency Lines | Linear Mile | 0 | 0 |  | 0
Sheet Files
29.1 | Control Survey Cover Sheet | Sheet | 0 | 0 |  | 0
29.11 | Control Survey Key Sheet | Sheet | 0 | 0 |  | 0
29.12 | Control Survey Detail Sheet | Sheet | 0 | 0 |  | 0
29.13 | R/W Map Cover Sheet | Sheet | 0 | 0 |  | 0
29.14 | R/W Map Key Sheet | Sheet | 0 | 0 |  | 0
29.15 | R/W Map Detail Sheet | Sheet | 0 | 0 |  | 0
29.16 | Maintenance Map Cover Sheet | Sheet | 0 | 0 |  | 0
29.17 | Maintenance Map Key Sheet | Sheet | 0 | 0 |  | 0
29.18 | Maintenance Map Detail Sheet | Sheet | 0 | 0 |  | 0
29.19 | Reference Point Sheet | Sheet | 0 | 0 |  | 0
29.2 | Project Control Sheet | Sheet | 0 | 0 |  | 0
29.21 | Table of Ownerships Sheet | Sheet | 0 | 0 |  | 0
Miscellaneous
29.22 | Parcel Sketches | Parcel | 0 | 0 |  | 0
29.23 | TIITF Sketches | Parcel | 0 | 0 |  | 0
29.24 | Other Specific Purpose Survey Map | EA | 0 | 0 |  | 0
29.25 | Boundary Survey(s) Map | EA | 0 | 0 |  | 0
29.26 | R/W Monumentation Map | Sheet | 0 | 0 |  | 0
29.27 | Title Search Map | LS | 1 | 0 |  | 0
29.28 | Title Search Report | LS | 1 | 0 |  | 0
29.29 | Legal Descriptions | Parcel | 0 | 0 |  | 0
29.3 | Final Maps/Plans Comparison | Sheet | 0 | 0 |  | 0
Mapping Technical Subtotal |  |  |  |  | 0 | 0
29.31 | Field Reviews | EA | 1 | 0 |  | 0
29.32 | Technical Meetings | LS | 1 | 0 |  | 0
29.33 | Quality Assurance/Quality Control | EA | % | 0% |  | 0
29.34 | Supervision | EA | % | 0% |  | 0
Mapping Nontechnical Subtotal | [5 empty] | 0
29.35 | Coordination | LS | % | 0% |  | 0
29.36 | Supplemental Mapping | LA | % | 0% |  | 0
29. Mapping Total |  |  |  |  | 0 | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | PM Attendance at Meeting Required? | Comments | Number of Required PM Meetings?
Kickoff meeting |  | EA | 0 | 0 | 0 |  |  | 0
Control map review |  | EA | 0 | 0 | 0 |  |  | 0
45/60/90/final map review |  | EA | 0 | 0 | 0 |  |  | 0
Other meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 | Subtotal Project Manager Meetings |  | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 | Total Project Manager Meetings (carries to Tab 3) |  | 0
[5 empty] | Carries to 29.32 |  |  | Carries to Tab 3

## 30. Terrestrial Mobile LiDAR
Estimator: | [11 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name | [6 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No. of Units | Hour / Unit | Hours |  |  |  |  | Total Range | Comments
[5 empty] | PSM | Senior LiDAR Technician | LiDAR Technician | LiDAR Operator | Field Technician
30.1 | Terrestrial Mobile LiDAR Mission Planning
| Choose Range Category | Scan Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Scan Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Scan Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.2 | Project Control Point Coordination
| Choose Range Category | Point | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Point | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Point | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.3 | Terrestrial Mobile LiDAR Mobilization
| Choose Range Category | Personnel | 1 | 0 |  |  |  | 0 |  | 0 | LiDAR Operator Only
|  | Personnel | 2 | 0 |  |  |  |  | 0 | 0 | Field Technician Only
30.4 | Terrestrial Mobile LiDAR Mission
| Choose Range Category | Scan Miles | 0 | 0 |  |  |  | 0 |  | 0 | LiDAR Sensor Operator
|  | Scan Miles | 0 | 0 | Number of Field Technician(s) = |  |  | 2 | 0 | 0 | 1-Technician to drive vehicle , 1-base station
30.5 | Terrestrial Mobile LiDAR Processing
| Choose Range Category | Scan Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Scan Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Scan Miles | 0 | 0 |  |  |  | 0 |  | 0 | LiDAR Operator
30.6 | Terrestrial Mobile Photography Processing
| Choose Range Category | Scan Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Scan Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Scan Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.7 | Transformation / Adjustment
| Choose Range Category | Scan Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Scan Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Scan Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.8 | Classification / Editing
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.9 | Specific Surface Reporting
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.1 | Topographic (3D) Mapping
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.11 | Topographic (2D) Planimetric Mapping
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.12 | CADD Edits
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.13 | Data Merging
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only
30.14 | Miscellaneous
| Survey Report | LS | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only
|  | LS | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | LS | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Tech Only
|  | LS | 0 | 0 |  |  |  | 0 |  | 0 | LiDAR Operator Only
|  | LS | 0 | 0 |  |  |  |  | 0 | 0 | Field Technician Only
|  |  | Mobile Scan Technical Subtotal | [6 empty] | 0
30.15 | Field Reviews
|  | LS | 0 |  | 0 |  |  |  |  | 0
|  | LS | 0 |  |  | 0 |  |  |  | 0
30.16 | Technical Meetings
|  | LS | [7 empty] | 0 | From Meetings Table Below
30.17 | Quality Assurance / Quality Control
|  | LS | 0% | [6 empty] | 0
30.18 | Supervision
|  | LS | 0% | [6 empty] | 0
|  |  | Mobile Scan Nontechnical Subtotal | [6 empty] | 0
30.19 | Coordination
|  | LS | 0% | [6 empty] | 0
30. Terrestrial Mobile LiDAR Mapping Total | [9 empty] | 0
* The low end of the range is for rural 2-lane; medium range is for typical Multi-Lane; the high end of the range is for urban/interstate.
Technical Meetings |  |  | Units | No of Units | Hours/ Unit | Total Hours | Comments |  |  |  | PM Attendance at Meeting Required? | Number
Terrestrial Mobile LiDAR Mapping Submittal Review |  |  | EA | 0 | 0 | 0 | [5 empty] | 0
Other Meetings |  |  | EA | 0 | 0 | 0 | [5 empty] | 0
Subtotal Technical Meetings | [5 empty] | 0 | Subtotal PM Meetings |  |  |  |  | 0
Progress Meetings (if required by FDOT) |  |  | EA | 0 | 0 | 0 | ** |  |  |  |  | - -
Phase Review Meetings |  |  | EA | 0 | 0 | 0 | ** |  |  |  |  | - -
Total Meetings | [5 empty] | 0 | Total PM Mtgs (carries to Tab 3) |  |  |  |  | 0
[6 empty] | Carries to 30.16 |  |  |  |  | Carries to Tab 3
** Project Manager attendance at progress, phase and field review meetings are manually entered on General Task 3

## Architecture Guidelines
ARCHITECTURE GUIDELINES
The range of hours following each element of design is to be used as a guide to calculate the number of total hours required to perform that task, including design and drafting. The negotiator must use professional judgment based on the project scope to determine where each task would fall with in the range of hours. Each task must be judged based on its complexity. Various factors must be evaluated when considering the complexity of a project. Two of the primary considerations used to analyze projects are size and level of design effort.
Size factors to consider:
· Amount of information placed on each sheet
· Number of unique spaces to be designed
· Shape and massing of the structure
· Site constraints
· Number of stories
· Number of areas which require an enlarged floor plan
Level of design effort factors to consider:
· Shape and massing of the structure
· Level of interior and exterior finishes
· Soil conditions
· Access to utilities
· Structural system
· Communication requirements
· Number of dissimilar building components
· Amount of specialty equipment
The range of hours following each element of design is to be used as a guide to calculate the number of total hours required to perform that task, including design and drafting. The negotiator must use professional judgment based on the project scope to determine where each task would fall with in the range of hours. Each task must be judged based on its complexity and work effort.
The size of a building is not necessarily related to the complexity/work effort of its design. To determine the design complexity/work effort several factors must be considered.
1. Site Constraints: Limited R/W, topo, utilities placement, roadway geometry, and lane configurations, wind zones, flood zones, etc.
2. Familiarity: Whether or not a design Consultant is familiar with FDOT processes, building types, and use of generic plans.
3. Expandability: A requirement for future expandability may be a consideration in the initial design of the building.
4. Building Type: The function, size, utility requirements, operator space, location, etc. will affect the design.
5. Code requirements, Capacity ands Occupancy These requirements can have a profound effect on materials and systems
used in the design. Life Safety and other code requirements will have a direct influence on layout and size of space.
6. Location: The location of the building project can greatly affect elements such as utilities access and site access.
7. Sheet Production: The number of sheets will be determined by such elements as content of sheet, unique and special
purpose spaces, shape and mass of building(s), spaces requiring enlarged floor plans and details, interior finishes, structural
system, mechanical system, communications and data systems, and special equipment.
The following examples are used as a guide only. See the State's DMS Fee Curve Guidelines for a complete guide of complexity.
1. Considerably more than average complexity
Materials testing and research lab, Special purpose, Multiple use buildings.
5%
2. More than average complexity
Vehicle Maintenance and Vehicle Maintenance Yard, Renovations, alterations, Large Toll Plaza, Weigh in Motion/Inspection Sta., Rest Area addition/redesign, Medium Toll Plaza, Small Toll Plaza, Rest Area interior modifications/refinish, Rest Area replacement
3. Average Complexity
Office Space improvements, Medium Toll Plaza, WIM Sta., Rest Area replacement
90%
4. Less than average complexity
Garage, Service, Repetitive Design, Open space office building
5%
5. Considerably Less Than Average Complexity
Parking garage, warehouse, storage

## 31. Architecture Development
Estimator: | [11 empty] | Enter project name & description
999999-1-52-01
Representing |  |  | Print Name | [5 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task |  | Scale | Units | No of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
Architectural Plans
31.1 | Architectural Program Review/Verification |  |  | Text Pages | 0 | 0 | 0 | 0
31.2 | Key Sheet and Index of Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.3 | General Notes, Abbreviations, Symbols, and Legend |  |  | Sheet | 0 | 0 | 0 | 0
31.4 | Life Safety Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.5 | Site Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.6 | Floor Plan(s) (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.7 | Floor Plan(s) (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.8 | Exterior Elevation(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.9 | Roof Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.1 | Roof Details |  |  | Sheet | 0 | 0 | 0 | 0
31.11 | Interior Elevation(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.12 | Rest Room Plan(s) (Enlarged) |  |  | Sheet | 0 | 0 | 0 | 0
31.13 | Rest Room Elevation(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.14 | Building Section(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.15 | Stair Section, Enlarged Stair Plan and Details |  |  | Sheet | 0 | 0 | 0 | 0
31.16 | Reflective Ceiling Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.17 | Room Finish Schedule or Finish Plan |  |  | Sheet | 0 | 0 | 0 | 0
31.18 | Door and Window Schedule |  |  | Sheet | 0 | 0 | 0 | 0
31.19 | Door Jamb Detail(s) and Window Details |  |  | Sheet | 0 | 0 | 0 | 0
31.2 | Exterior Wall Section(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.21 | Interior Wall Section(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.22 | Overhead Door Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.23 | Curtain Wall Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.24 | Fascia, Soffit and Parapet Details |  |  | Sheet | 0 | 0 | 0 | 0
31.25 | Signage Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.26 | Miscellaneous Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.27 | Repetitive Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.28 | Design Narrative Reports |  |  | LS | 0 | 0 |  | 0
31.29 | Permitting |  |  | LS | 0 | 0 |  | 0
31.3 | Other Pertinent Project Documentation |  |  | LS | 0 | 0 |  | 0
31.31 | Cost Estimate |  |  | LS | 0 | 0 |  | 0
31.32 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 0 | 0 |  | 0
Architectural Plans Technical Subtotal | [6 empty] | 0 | 0
31.33 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.34 | Technical Meetings | [7 empty] | See listing below
31.34.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.34.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.34.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.34.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.34.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.34.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.34.7 | Subtotal Technical Meetings | [6 empty] | 0
31.35 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.36 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.37 | Supervision |  |  | LS | % | 0% |  | 0
Architectural Plans Total | [6 empty] | 0 | 0
Structural Plans
31.38 | General Notes, Abbreviations, Symbols, and Legend |  |  | Sheet | 0 | 0 | 0 | 0
31.39 | Foundation Plan(s) (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.4 | Foundation Plan(s) (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.41 | Slab Plan(s) (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.42 | Slab Plan(s) (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.43 | Slab Placement Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.44 | Slab Placement Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.45 | Foundation Section(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.46 | Foundation Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.47 | Slab Section(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.48 | Slab Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.49 | Roof Framing Plan(s) (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.5 | Roof Framing Plan(s) (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.51 | Roof Loading Plan(s) and Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.52 | Roof Section(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.53 | Roof Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.54 | Bearing Wall Section(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.55 | Bearing Wall Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.56 | Column Section(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.57 | Column Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.58 | Miscellaneous Sections |  |  | Sheet | 0 | 0 | 0 | 0
31.59 | Repetitive Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.6 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.61 | Cost Estimate |  |  | LS | 1 | 0 |  | 0
31.62 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Structural Plans Technical Subtotal | [6 empty] | 0 | 0
31.63 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.64 | Technical Meetings | [7 empty] | See listing below
31.64.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.64.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.64.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.64.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.64.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.64.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.64.7 | Subtotal Technical Meetings | [6 empty] | 0
31.65 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.66 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.67 | Supervision |  |  | LS | % | 0% |  | 0
Structural Plans Total | [6 empty] | 0 | 0
Mechanical Plans
31.68 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  |  | Sheet | 0 | 0 | 0 | 0
31.69 | Plan(s) (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.7 | Plan(s) (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.71 | Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.72 | Section(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.73 | Piping Schematic(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.74 | Control Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.75 | Schedule(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.76 | HVAC Calculations |  |  | Sheet | 0 | 0 | 0 | 0
31.77 | Life Cycle Cost Analysis |  |  | Sheet | 0 | 0 | 0 | 0
31.78 | Repetitive Sheets |  |  | LS | 1 | 0 |  | 0
31.79 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.8 | Cost Estimate |  |  | LS | 1 | 0 |  | 0
31.81 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Mechanical Plans Technical Subtotal | [6 empty] | 0 | 0
31.82 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.83 | Technical Meetings | [7 empty] | See listing below
31.83.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.83.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.83.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.83.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.83.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.83.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.83.7 | Subtotal Technical Meetings | [6 empty] | 0
31.84 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.85 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.86 | Supervision |  |  | LS | % | 0% |  | 0
Mechanical Plans Total | [6 empty] | 0 | 0
Plumbing Plans
31.87 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  |  | Sheet | 0 | 0 | 0 | 0
31.88 | Plan(s) (Small Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.89 | Plan(s) (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.9 | Isometric(s) (Large Scale) |  |  | Sheet | 0 | 0 | 0 | 0
31.91 | Riser Diagram(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.92 | Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.93 | Repetitive Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.94 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.95 | Cost Estimate |  |  | LS | 1 | 0 |  | 0
31.96 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Plumbing Plans Technical Subtotal | [6 empty] | 0 | 0
31.97 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.98 | Technical Meetings | [7 empty] | See listing below
31.98.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.98.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.98.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.98.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.98.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.98.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.98.7 | Subtotal Technical Meetings | [6 empty] | 0
31.99 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.1 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.101 | Supervision |  |  | LS | % | 0% |  | 0
Plumbing Plans Total | [6 empty] | 0 | 0
Fire Protection Plans
31.102 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  |  | Sheet | 0 | 0 | 0 | 0
31.103 | Fire Protection Plan |  |  | Sheet | 0 | 0 | 0 | 0
31.104 | Riser Diagram, Details, and Partial Plans |  |  | Sheet | 0 | 0 | 0 | 0
31.105 | Hydraulic Calculation |  |  | Sheet | 0 | 0 | 0 | 0
31.106 | Repetitive Sheets |  |  | Sheet | 0 | 0 | 0 | 0
31.107 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.108 | Cost Estimate |  |  | LS | 1 | 0 |  | 0
31.109 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Fire Protection Plans Technical Subtotal | [6 empty] | 0 | 0
31.11 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.111 | Technical Meetings | [7 empty] | See listing below
31.111.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.111.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.111.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.111.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.111.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.111.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.111.7 | Subtotal Technical Meetings | [6 empty] | 0
31.112 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.113 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.114 | Supervision |  |  | LS | % | 0% |  | 0
Fire Protection Plans Total | [6 empty] | 0 | 0
Electrical Plans
31.115 | General Notes, Abbreviations, Symbols, Legend, and Code Issues |  |  | Sheet | 0 | 0 | 0 | 0
31.116 | Electrical Site Plan |  |  | Sheet | 0 | 0 | 0 | 0
31.117 | Lighting Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.118 | Lighting Fixtures Schedule(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.119 | Lighting Fixtures Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.12 | Lightning Protection Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.121 | Lightning Protection Details |  |  | Sheet | 0 | 0 | 0 | 0
31.122 | Power Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.123 | Power Distribution Riser Diagram(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.124 | Panel Board Schedule(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.125 | Data Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.126 | Data Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.127 | Communication Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.128 | Communication Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.129 | Security Alarm System Plan(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.13 | Miscellaneous Detail(s) |  |  | Sheet | 0 | 0 | 0 | 0
31.131 | Repetitive Sheets |  |  | LS | 1 | 0 |  | 0
31.132 | Energy Analysis |  |  | LS | 1 | 0 |  | 0
31.133 | Other Pertinent Project Documentation |  |  | LS | 1 | 0 |  | 0
31.134 | Cost Estimate |  |  | LS | 1 | 0 |  | 0
31.135 | Technical Special Provisions and Modified Special Provisions Packages |  |  | LS | 1 | 0 |  | 0
Electrical Plans Technical Subtotal | [6 empty] | 0 | 0
31.136 | Field Reviews |  |  | LS | 1 | 0 |  | 0
31.137 | Technical Meetings | [7 empty] | See listing below
31.137.1 | FDOT |  |  | EA | 0 | 0 |  | 0
31.137.2 | Local Governments (cities) |  |  | EA | 0 | 0 |  | 0
31.137.3 | Local Governments (counties) |  |  | EA | 0 | 0 |  | 0
31.137.4 | Other Meetings |  |  | EA | 0 | 0 |  | 0
31.137.5 | Progress Meetings |  |  | EA | 0 | 0 |  | 0
31.137.6 | Phase Review Meetings |  |  | EA | 0 | 0 |  | 0
31.137.7 | Subtotal Technical Meetings | [6 empty] | 0
31.138 | Quality Assurance/Quality Control |  |  | LS | % | 0% |  | 0
31.139 | Independent Peer Review |  |  | LS | % | 0% |  | 0
31.14 | Supervision |  |  | LS | % | 0% |  | 0
Electrical Plans Total | [6 empty] | 0 | 0
Architecture Development Subtotal | [6 empty] | 0 | 0
31.141 | LEED Certification |  |  | LS | 1 | 0 |  | 0
31.142 | Coordination |  |  | LS | % | 0% |  | 0
31.143 | Building Information Modeling (BIM) |  |  | Project | - - | - - | - - | - - | Using AutoCad Revit or a similar program for the production of construction documents does not cost the Client/Owner any additional design fee. However, the proportion of the fee is more front loaded because of the design process. The creation of the 3D model is part of the design and must be converted into 2D to print the construction documents. The additional use of the Virtual 3D model can provide additional advantages and services, but at an additional cost. Another very useful feature is the user's ability to visualize the spaces in 3D early on as part of the approval process.
31. Architecture Development Total | [6 empty] | 0 | 0
Total Technical Meetings (sum of meetings above) | [9 empty] | Comments | PM Attendance at Meeting Required? | Number
Meeting |  | Hours | [5 empty] | Total Meetings | Total Hours
|  | Architectural Plans | Structural Plans | Mechanical Plans | Plumbing Plans | Fire Protection Plans | Electrical Plans
FDOT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Local Governments (cities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Local Governments (counties) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Other Meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings | [7 empty] | 0 | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ** | - -
Phase Review Meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ** | - -
Total All Meetings | [7 empty] | 0 | 0 |  | Total PM Meetings (carries to Tab 3) | 0
Carries to Tab 3
** Project Manager attendance at progress, phase and field review meetings are manually entered on General Task 3

## 32. Noise Barrier Assessment
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
32.1 | Noise Analysis | LS | 1 | 0 | 0
32.2 | Noise Barrier Evaluation | LS | 1 | 0 | 0
32.3 | Public Involvement | LS | 1 | 0 | 0
32.4 | Outdoor Advertising Identification | LS | 1 | 0 | 0
32.5 | Noise Study Report (NSR) Addendum | LS | 1 | 0 | 0
Noise Barrier Impact Design Assessment in the Design Phase Technical Subtotal |  |  |  |  | 0
32.6 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
32.7 | Quality Assurance/Quality Control | LS | % | 0% | 0
32.8 | Supervision | LS | % | 0% | 0
Noise Barrier Impact Design Assessment in the Design Phase Nontechnical Subtotal |  |  |  |  | 0
32.9 | Coordination | LS | % | 0% | 0
32. Noise Barrier Impact Design Assessment in the Design Phase Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours |  | PM Attendance at Meeting Required? | Number
Kickoff Meeting with FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Alternative Evaluation with FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Local Agency (cities, counties) |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 32.6 |  |  | Carries to Tab 3

## ITS Guidelines
ITS GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical traffic projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project.
A "Lower Range" roadway project may fall in the "Middle Range" for Lighting projects and vice versa. See the project ranges below. The project ranges should be used only for Reference & Master Design Files and Quantities from Analysis.
Lower Range
1. Adding very limited number of ITS devices.
2. Small extension of existing freeway management system.
3. Installation of isolated devices such as a CCTV camera, a DMS sign or RWIS site.
Middle Range
1. Small extension of existing freeway management system, communications architecture already determined.
2. Freeway management system with no communications hubs and all devices of a single type.
Upper Range
1. Complex urban freeway management system with a variety of different ITS of devices.
2. Lengthy rural freeway management system.
3. Freeway management system with numerous communications hubs and rings of devices.

## 33. ITS Analysis
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
33.1 | ITS Analysis | LS | 1 | 0 | 0
33.2 | Communications Plan Analysis | LS | 1 | 0 | 0
33.3 | Lightning Protection Analysis | Per Site | 0 | 0 | 0
33.4 | Power Subsystem | LS | 1 | 0 | 0
33.5 | Voltage Drop Calculations | LS | 1 | 0 | 0
33.6 | Design Documentation | LS | 1 | 0 | 0
33.7 | Existing ITS System | LS | 1 | 0 | 0
33.8 | Queue Analysis | PI | 0 | 0 | 0
33.9 | Reference and Master ITS Design File | PI | 0 | 0 | 0
33.1 | Reference and Master Communications Design File | PI | 0 | 0 | 0
33.11 | Pole Elevation Analysis | LS | 1 | 0 | 0
33.12 | Sign Panel Design Analysis | LS | 1 | 0 | 0
33.13 | Quantities | Sheet | 0 | 0 | 0
33.14 | Cost Estimate | LS | 1 | 0 | 0
33.15 | Technical Special Provisions and Modified Special Provisions | LS | 1 | 0 | 0
33.16 | Other ITS Analyses | LS | 1 | 0 | 0
Intelligent Transportation Systems Analysis Technical Subtotal |  |  |  |  | 0
33.17 | Field Reviews | LS | 1 | 0 | 0
33.18 | Technical Meetings | LS | 1 | 0 | 0 | Meetings are listed below
33.19 | Quality Assurance/Quality Control | LS | % | 0% | 0
33.2 | Supervision | LS | % | 0% | 0
Intelligent Transportation Systems Analysis Nontechnical Subtotal |  |  |  |  | 0
33.21 | Coordination | LS | % | 0% | 0
33. Intelligent Transportation Systems Analysis Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
Kickoff Meeting with FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Local Governments (cities, counties, MPO) |  | EA | 0 | 0 | 0 |  |  | 0
Utility Owners |  | EA | 0 | 0 | 0 |  |  | 0
Field Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 33.18 |  |  | Carries to Tab 3

## 34. ITS Plans
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name | [5 empty] | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Scale | Units | No. of Units | Hours/ Unit | No. of Sheets | Total Hours | Comments
34.1 | Key Sheet |  | Sheet | 0 | 0 | 0 | 0
34.2 | Summary of Pay Items-including Designer Interface Input |  | Sheet | 0 | 0 | 0 | 0
34.3 | Tabulation of Quantities |  | Sheet | 0 | 0 | 0 | 0
34.4 | General Notes/Pay Item Notes |  | Sheet | 0 | 0 | 0 | 0
34.5 | Project Layout |  | Sheet | 0 | 0 | 0 | 0
34.6 | Typical and Special Details |  | Sheet | 0 | 0 | 0 | 0
34.7 | Plan Sheet |  | Sheet | 0 | 0 | 0 | 0
34.8 | ITS Communications Plans |  | Sheet | 0 | 0 | 0 | 0
34.9 | Fiber Optic Splice Diagrams |  | Sheet | 0 | 0 | 0 | 0
34.1 | Lightning Protection Plans |  | Sheet | 0 | 0 | 0 | 0
34.11 | Cross Sections |  | Sheet | 0 | 0 | 0 | 0
34.12 | Guide Sign Worksheet(s) |  | Sheet | 0 | 0 | 0 | 0
34.13 | Special Service Point Details |  | Sheet | 0 | 0 | 0 | 0
34.14 | Strain Pole Schedule |  | Sheet | 0 | 0 | 0 | 0
34.15 | Overhead/Cantilever Sign Structure |  | Sheet | 0 | 0 | 0 | 0
34.16 | Other Overhead Sign Structures (Long Span, Monotube, etc.) |  | Sheet | 0 | 0 | 0 | 0
34.17 | Temporary Traffic Control Plans |  | Sheet | 0 | 0 | 0 | 0
34.18 | Interim Standards |  | Sheet | 0 | 0 | 0 | 0
34.19 | GIS Data and Asset Management Requirements |  | LS | 1 | 0 | 0 | 0
Intelligent Transportation System Plans Technical Subtotal | [5 empty] | 0 | 0
34.2 | Quality Assurance/Quality Control |  | LS | % | 0% |  | 0
34.21 | Supervision |  | LS | % | 0% |  | 0
34. Intelligent Transportation System Plans Total | [5 empty] | 0 | 0

## Geotechnical Guidelines
GEOTECHNICAL GUIDELINES
The staff hour estimating form, basis and these accompanying instructions were developed to be consistent with the Geotechnical section of the Standard Scope of Service covering the typical range of geotechnical investigations anticipated on 80 percent of all highway projects. It is recognized that the Districts may need to vary the specific requirements of the scope for performance of geotechnical work to make them District or project specific. Where such variations occur, it is recommended that all changes to the Standard Scope be shown in italics to alert the user that the scope requirements have changed from the standard and that the range of staff hours shown in the basis may no longer be applicable to a specific task.
The ‘typical’ range of geotechnical investigations considered as applicable includes the following:
· Projects with geotechnical staffhours ranging from approx. 100 to 3,000;
· Projects that include commonly encountered soil and rock conditions, site investigation methods and geotechnical
design recommendations.
An example of a typical project would include evaluation of roadway subgrade or embankment stability/settlement related to sinkholes, soft clays, organic soils and/or high groundwater. A typical project would require geotechnical guidance for normal cut and fill. It may also require recommendations for realignment, surcharge, excavation and replacement, subgrade reinforcement using geosynthetics and/or underdrains. Examples of projects considered atypical and, therefore, may fall below the range are: RRR projects, minor intersection improvements, etc. Examples of projects considered atypical and, therefore, may fall above the range are: dealing with extensive waste phosphatic clays or design recommendations for soil improvement by lime/cement subgrade stabilization, deep dynamic compaction, vibroflotation, compaction grouting, pile reinforced embankments, etc.
The user must use experience and common sense in assessing where the specific project requirements may deviate from the typical project and some guidance is provided in the basis for each task. For instance, minimum hours listed are only applicable to typical projects. If needed, individual Structures Items can be used when negotiating Roadway projects, and individual Roadway Items can be used when negotiating Structures projects. If neither the Standard Scope nor the basis specifically include or describe an activity, type of analysis or geotechnical solution then it most likely is not covered within the typical staff hour ranges provided for guidance.
Although not specifically developed for Districtwide Geotechnical services, the staff hour estimating form, basis and these instructions may be used as a reference to such work if it falls within the typical range as defined above. Since analysis and reporting requirements for small geotechnical tasks may vary from the Standard Scope, the user should be cautious in applying the ranges shown in the basis to such work. The ranges were ‘proof tested’ against several typical projects from various Districts and found to result in reasonably consistent staff hour estimates compared to previously negotiated total staff hours. The form may be applicable to large projects over 3,000 staff hours but there is no comparative experience with a project of this size. Again the user should be cautious in applying the form, basis and instructions to very small or very large projects.
A number of tasks included in the staff hour estimating form are frequently requested of the geotechnical engineer by other design professionals. These tasks include Stormwater Volume Recovery Analysis and/or Background Seepage Analysis, Lateral Load Analysis, and Sheet Pile Wall Analysis. The user should determine if adequate hours for these activities are included in the relevant Drainage and Structures portions of the project to avoid repetition.
To use the form and instructions the user must have evaluated the project scope in addition to the likely subsurface conditions and foundation alternatives in sufficient detail to estimate the total number, type and depth of exploratory borings for Roadways and Structures as well as the relative complexity of the project. In general, simple straightforward projects will require lower staffhours, while conversely more complex projects will merit higher staffhours per unit within the ‘typical’ ranges listed on the estimating sheet for ‘lump sum’ items. When hours are determined ‘per item’ (such as per 100 LF of boring), and a range of hours is given to be multiplied by that item, it is intended that the higher end of the range be used for smaller projects, and vice versa.
Remember that this form is intended to estimate the TOTAL number of hours for each task including engineering or technician hours to perform the task, senior review hours and applicable clerical hours.

## 35. Geotechnical
Estimator: | [7 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
Roadway
35.1 | Document Collection and Review | LS | 1 | 0 | 0
35.2 | Develop Detailed Boring Location Plan | LS | 1 | 0 | 0
35.3 | Stake Borings/Utility Clearance | Boring | 0 | 0 | 0
35.4 | Muck Probing | Crew Day | 0 | 0 | 0
35.5 | Coordinate and Develop MOT Plans for Field Investigation | EA | 0 | 0 | 0
35.6 | Drilling Access Permits | Location | 0 | 0 | 0
35.7 | Property Clearances | EA | 0 | 0 | 0
35.8 | Groundwater Monitoring | EA | 0 | 0 | 0
35.9 | LBR/Resilient Modulus Sampling | EA | 0 | 0 | 0
35.10 | Coordination of Field Work | 100 lf of boring | 0 | 0 | 0
35.11 | Soil and Rock Classification - Roadway | 100 lf of boring | 0 | 0 | 0
35.12 | Design LBR | LS | 1 | 0 | 0 | Only if LBR tests are required
35.13 | Laboratory Data | 100 lf of boring | 0 | 0 | 0
35.14 | Seasonal High Water Table | Boring | 0 | 0 | 0
35.15 | Parameters for Water Retention Areas | EA | 0 | 0 | 0
35.16 | Delineate Limits of Unsuitable Material | Cross-section | 0 | 0 | 0
35.17 | Electronic Files for Cross-Sections | 100 lf of boring | 0 | 0 | 0 | Duplication of Roadway Effort?
35.18 | Embankment Settlement and Stability | Embankment Boring | 0 | 0 | 0
35.19 | Monitor Existing Structures | LS | 1 | 0 | 0
35.20 | Stormwater Volume Recovery and/or Background Seepage Analysis | EA | 0 | 0 | 0 | Duplication of Drainage Effort?
35.21 | Geotechnical Recommendations | LS | 1 | 0 | 0
35.22 | Pavement Condition Survey and Pavement Evaluation Report | LS | 1 | 0 | 0
35.23 | Preliminary Roadway Report | LS | 1 | 0 | 0
35.24 | Final Report | EA | 0 | 0 | 0
35.25 | Auger Boring Drafting | 100 lf boring | 0 | 0 | 0
35.26 | SPT Boring Drafting | 100 lf boring | 0 | 0 | 0
Roadway Geotechnical Subtotal |  |  |  |  | 0
Structures
35.27 | Develop Detailed Boring Location Plan | LS | 1 | 0 | 0
35.28 | Stake Borings/Utility Clearance | Boring | 0 | 0 | 0
35.29 | Coordinate and Develop MOT Plans for Field Investigation | EA | 0 | 0 | 0
35.30 | Drilling Access Permits | Location | 0 | 0 | 0
35.31 | Property Clearances | EA | 0 | 0 | 0
35.32 | Collection of Corrosion Samples | EA | 0 | 0 | 0
35.33 | Coordination of Field Work | 100 lf of boring | 0 | 0 | 0
35.34 | Soil and Rock Classification - Structures | 100 lf of boring | 0 | 0 | 0
35.35 | Tabulation of Laboratory Data | 100 lf of boring | 0 | 0 | 0
35.36 | Estimate Design Groundwater Level for Structures | EA | 0 | 0 | 0
35.37 | Selection of Foundation Alternatives (BDR) | Bridge boring | 0 | 0 | 0
35.38 | Detailed Analysis of Selected Foundation Alternate(s) | Bridge boring | 0 | 0 | 0 | See Basis for reducing by 35.35
35.39 | Bridge Construction and Testing Recommendations | Bridge boring | 0 | 0 | 0
35.40 | Lateral Load Analysis (Optional) | Bridge boring | 0 | 0 | 0 | Duplication of Structural Effort?
35.41 | Walls | Wall Boring | 0 | 0 | 0
35.42 | Sheet Pile Wall Analysis (Optional) | Wall Boring | 0 | 0 | 0 | Duplication of Structural Effort?
35.43 | Design Soil Parameters for Signs, Signals, High Mast Lights, and Strain Poles and Geotechnical Recommendations | Boring | 0 | 0 | 0
35.44 | Box Culvert Analysis | EA | 0 | 0 | 0
35.45 | Preliminary Report - BDR | EA | 0 | 0 | 0
35.46 | Final Report - Bridge and Associated Walls | EA | 0 | 0 | 0
35.47 | Final Reports - Signs, Signals, Box Culvert, Walls and High Mast Lights | EA | 0 | 0 | 0
35.48 | SPT Boring Drafting | 100 lf of boring | 0 | 0 | 0
35.49 | Other Geotechnical | LS | 1 | 0 | 0
Structural Geotechnical Subtotal |  |  |  |  | 0
Geotechnical Technical Subtotal |  |  |  |  | 0
35.50 | Technical Special Provisions and Modified Special Provisions | EA | 0 | 0 | 0
35.51 | Field Reviews | LS | 1 | 0 | 0
35.52 | Technical Meetings | LS | 1 | 0 | 0 | Meetings listed below
35.53 | Quality Assurance/Quality Control | LS | % | 0% | 0
35.54 | Supervision | LS | % | 0% | 0
Geotechnical Nontechnical Subtotal |  |  |  |  | 0
35.55 | Coordination | LS | % | 0% | 0
35. Geotechnical Total |  |  |  |  | 0
Technical Meetings |  | Units | No of Units | Hours/ Unit | Total Hours | Comments | PM Attendance at Meeting Required? | Number
Kickoff Meeting with FDOT |  | EA | 0 | 0 | 0 |  |  | 0
Boring Layout Approval |  | EA | 0 | 0 | 0 |  |  | 0
Attend in BDR Review Meeting |  | EA | 0 | 0 | 0 |  |  | 0
30/60/90% Submittal Review |  | EA | 0 | 0 | 0 |  |  | 0
Other Meetings |  | EA | 0 | 0 | 0 |  |  | 0
Subtotal Technical Meetings |  |  |  |  | 0 |  | Subtotal Project Manager Meetings | 0
Progress Meetings (if required by FDOT) |  | EA | 0 | 0 | 0 | PM attendance at Progress Meetings is manually entered on General Task 3 |  | - -
Phase Review Meetings |  | EA | 0 | 0 | 0 | PM attendance at Phase Review Meetings is manually entered on General Task 3 |  | - -
Total Meetings |  |  |  |  | 0 |  | Total Project Manager Meetings (carries to Tab 3) | 0
[5 empty] | Carries to 33.18 |  |  | Carries to Tab 3

## 3D Modeling Guidelines
3D MODELING GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual tasks related to modeling a typical roadway project. It is understood that range classification of modeling effort may differ from those used on typical roadway tasks as described in the Roadway Guidelines section of this document. Modeling ranges are based on the number of typical sections (templates) applied on a corridor (Alignment) and the number of variations of edge conditions (i.e. tie-down conditions outside of the curb and gutter or shoulder edge) Each alignment is considered a corridor and may be categorized at different ranges of complexity. Areas outside of the practical application of corridors with the use of templates (roundabouts, intersection grading, curb ramps, turnouts, gore areas, ponds, etc.) are to be quantified independently. These ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiating hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
The following are general examples of corridor descriptions and the applicable range as outlined in this handbook. The work effort for independently modeled elements such as gore areas, pond sites, floodplain compensation sites, intersection plateauing, cross overs, curb ramps, turnouts, bridges and roundabouts will be quantified under separate tasks. This list is not all inclusive, or always exact, but will provide the basis for beginning estimation and negotiation of staff hours required to model a corridor.
Lower End of Range Corridors
Any corridor identified with a context classification of C1-Natural or C2-Rural. Consist of a single typical section with up to two end conditions.
Middle of Range Corridors
Any corridor identified with a context classification of C2T-Rural Town, 3CR-Suburban Residential, C3C- Suburban Commercial, T3 Suburban Zone, or C4-Urban General) Consist of a two typical sections with up to two end conditions per typical.
Upper End of Range Corridors
Any corridor identified with a context classification of C5-Urban Center or C6-Urban Core. Consist of two or more typical section with more than two end conditions each typical.
3D MODELING PHASE GUIDELINES
PHASE I Phase I complete model to include existing features (pavement, shoulder, sidewalk, curb/gutter, utilities-if required per scope, drainage - if required per scope) and proposed corridor(s). Since drainage is not normally determined at Phase I open drainage swales would not be included in the effort to model a Phase I complete corridor. Phase I does not included proposed utility modeling or areas of detail modeling such as crossovers, intersection grading, driveways, roundabouts, or side road connections.
PHASE II Modification of Phase I model to include the addition of proposed drainage, proposed utilities, ponds, floodplain compensation sites, retaining walls, barrier walls, guardrail terminals, cross overs, gore areas, side street connections, roundabouts, driveways and curb ramps.
90%PHASE III Modification of Phase II model to further refine areas of transition between templates, detailed grading areas, Bridge approaches and end bents, median noses, shoulder transition areas, retaining walls, barrier walls and guardrail. Includes all effort to update the model in order to accurately reflect changes made based on Phase II review comments.
100%PHASE IV Includes all effort necessary to update the model to comply with changes based on Phase III review comments and to accurately generate, export and otherwise prepare the Final 3D deliverable files as described in the FDOT CADD Manual. This effort includes preparation of all AMG-####.dwg/DGN and XML files as described in the FDOT CADD Manual section 5.10.4.2
1. Model Development - Whoever develops the model will need good engineering judgement and 3D modeling experience.
a. Model may tell you that your initial alignment, profiles and typical sections will not work.
b. A skilled designer/engineer recommended.
i. Must be able to “make” and “defend” engineering design decisions.
ii. It is easier to “design-by-model”, then try and “model-your-design”.
iii. A skilled engineer will make critical design decisions and “design-by-model” (e.g. change profiles on the fly, or add/remove/relocate alignments as needed
c. Some FDOT PMs request distribution of staff hours to give more hours to “Engineering Intern” positions (e.g. Phase III/II/I).
i. Modeling activities/tasks should be given to a skilled designer/engineer.
ii. A skilled designer/engineer needs to make model assumptions (e.g. model-controlling features)
d. If any changes occur that affects a model-controlled feature (e.g. scope change), the model may need to be heavily modified, or redone completely.
i. Adding widening and/or sidewalks to a project, is not as simple as “moving or adding lines” anymore.
2. Multiple Disciple Coordination - If you have projects that requires multiple disciplines (e.g. Drainage/Bridge/Signals etc.)
a. These staff need to be involved in the early (Phase I) modeling effort. Need “Staff Hours” to get these disciplines on board early.
b. Most of their design work is reflected in the modeling effort.
c. Cannot approach 3D modeling the same way as a non-modeling project
i. Work is organized differently and all disciplines need to collaborate and make decisions together early.
1. No more “Here is my stuff… You match me” or “What does my component have to do with yours?”
2. Coordinate/collaborate required at every step for successful design integration.
3. Initial Model - What you think will work for initial concept, will get vetted by a well-developed 3D model.
a. 3D modeling is iterative. The model tends to dictate changes in initial alignments, profiles, and typical sections.
4. Additional Controls - When 3D modeling, you will realize that you need more alignments and profiles than 2D design.
a. Staff hours estimate needs to reflect the additional horizontal/vertical controls needed.

## 36. 3D Modeling
Estimator: | [6 empty] | Enter project name & description
999999-1-52-01
Representing |  | Print Name |  |  |  | Signature / Date
FDOT District
Consultant Name
NOTE: Signature Block is optional, per District preference
Task No. | Task | Units | No of Units | Hours/ Unit | Total Hours | Comments
36.1 | Phase I 3D Design Model | Alignment / Corridor Mile | 0 | 0 | 0
36.2 | Phase II 3D Design Model | Alignment / Corridor Mile | 0 | 0 | 0
36.3 | Phase III 3D Design Model | Alignment / Corridor Mile | 0 | 0 | 0
36.4 | Final 3D Design Model | Alignment / Corridor Mile | 0 | 0 | 0
36.5 | Cross Section Design Files | LS | 1 | 0 | 0
36.6 | Template and Assembly Development (Optional) | LS | 1 | 0 | 0
3D Modeling Technical Subtotal |  |  |  |  | 0
36.7 | Quality Assurance/Quality Control | LS | % | 0% | 0
36.8 | Supervision | LS | % | 0% | 0
36.9 | Coordination | LS | % | 0% | 0
3D Modeling Total |  |  |  |  | 0