## Version
Document Control Panel
Project Name: | < required >
Project Description: | < required >
Project Manager Name: | < required >
Agency/Firm: | < optional>
Topic | Name | Date
Created by:
Reviewed by:
Modified by:
Form FM-SE-22B Requirements Traceability Verification Matrix. Effective 9/4/2019

## Guide
Requirements Traceability Verification Matrix Guide
1. Introduction
In this Requirements Traceability Verification Matrix (RTVM) there are five tabs: Version, Guide, Acronyms, Instructions and RTVM. The tabs are intended to be self-explanatory. Complete the Version tab as needed. Add to the Acronyms tab any new acronyms you put into the RTVM, especially when they refer to Detailed Requirement Source Documents (Column F in the RTVM tab). The Instructions tab has explantions of what goes into each column of the RTVM. These explations can also be found in the RTVM column headings that appear in pop-up windows as you drag the mouse across the column headings. The RTVM tab has four rows of example material (rows 7-10) that accompany this RTVM Guide.
After the Concept of Operations (ConOps) and Project Systems Engineering Management Plan (PSEMP) are developed, the next systems engineering task is to develop System Requirements. The User Needs and high-level requirements identified in the ConOps and PSEMP feed into the development of detailed system requirements. The Detailed Requirements need to be unambiguous, and, once applied later in the project, need to be thoroughly tested to ensure all elements of the system do what they are supposed to do. The requirements need to specifically identify what, how well, and under what conditions a product will achieve a given purpose.
There are three key systems engineering activities to do in the System Requirements stage:​
· Develop a Requirements Traceability Verification Test Matrix (RTVM)
· Create a System Verification Plan​
· Create a System Acceptance Plan.
1.1 RTVM
The first of the three key activities to do in system requirements is an RTVM, which will accompany the requirements documents. The RTVM, at minimum, is a table with a column containing each detailed requirement and a corresponding column for how that requirement will be tested and verified. Use the FDOT Systems Engineering RTVM Template, described in this Guide, to fill out the RTVM. Also use the Systems Verification Plan Template to fill out the Verification Test Cases that will be identified in the RTVM.
1.1.1 Requirements
The systems engineering approach uses general, abstract, functional and high-level language but with enough specificity to bound subsequent desired technology choices to those that will meet User Needs and system requirements. Requirements may initially be high-level and tell of generic project functions. Detailed requirements will follow from User Needs and high-level requirements.​
Requirements stipulate the specifications the system will meet but not define how the design will meet those specifications. This allows the developers to use their expertise in designing the system and to use the latest technology. Systems engineering specifically focuses on requirements and not technologies, at this stage, and thwarts efforts to use particular, pre-chosen or vendor-specific technologies, in favor of the latest ones available that meet the requirements.​ The systems engineering process puts off technology decisions by specifying requirements prior to design. Due to the changing nature of technology, it is important to make technology decisions as close to system implementation as possible. The systems engineering process helps to ensure this by developing the design to meet User Needs and system requirements. ​
Managing requirements includes key crosscutting activities with stakeholders, such as:​
· Eliciting requirements from stakeholders ​
· Analysis of requirements to get them all ​
· Documenting requirements for traceability and configuration management​
· Validation of requirements, so that they are necessary, clear, consistent, accurate, complete, and verifiable.​
​Good systems engineering practice involves analyzing the requirements to make sure they are achievable, necessary, and independent of technology. Requirements should be approved by the users and stakeholders of the proposed system. High-level requirements developed for this project’s PSEMP and detailed requirements from an RTVM developed for a similar project will very likely be of use. It is not necessary to quote FDOT specifications in an RTVM. A brief summary along with the referenced document and section number are sufficient.
1.1.2 Traceability
Traceability links together the entire systems engineering process as a crosscutting activity.​​ Systems requirements trace back to User Needs identified in the ConOps and forward to Verification Test Cases, also in the RTVM, which are used in the implementation and testing stages later in the testing process.​ Every requirement must relate back to at least one user need and there should not be requirements that do not trace back to a user need. ​
​Keep in mind that the system engineering documents produced at each step of the process must be living documents. In order to have complete traceability, the previous systems engineering documents must be updated to be consistent with the current step’s documentation throughout the system lifecycle. Traceability is documented through consistent configuration management throughout the project lifecycle. ​
Traceability is intended to create linkages between User Needs, project requirements, and verification of the tests of these requirements. Traceability should ensure that:
· All User Needs are addressed by a requirement
· All Detailed Requirements are verified
· All project requirements in the RFP and all other system requirements are tested
· No test is left out or forgotten.
1.1.3 Verification
In the RTVM, verification involves defining and using Verification Test Cases which are developed in the System Verification Plan. The Verification Test Case number is identified in the RTVM. The System Verification Plan Template explains how to fill out the Verification Test Case Table.
The first element of the Verification Test Cases, as laid out in the System Verification Plan, are the Verification Test Methods. The Verification Test Methods are Analysis, Approved Products List (APL), Construction Engineering and Inspection (CEI) Checklist, Deliverable, Demonstration, Inspection and Testing. These generic test methods are explained in the System Verification Plan Template.
Additional columns in the RTVM include space for the initials of those performing and reviewing the verification tests.
1.1.4 Matrix
Filling out the RTVM matrix is described in Sections 2 and 3 of this Guide.
1.2 System Verification Plan
The RTVM, just examined, is accompanied by a System Verification Plan, the second systems requirements activity. As the requirements are finalized, create a System Verification Plan to describe how the Verification Test Cases of requirements will be tested. Use the FDOT System Verification Plan Template to complete this plan. Details of the System Verification Plan may be transferred into the Request for Proposal (RFP) for a contractor to perform. Also, the System Verification Plan and System Acceptance Plan may be developed by a contractor, as determined in the PSEMP.
1.3 System Acceptance Plan
When completing the System Verification Plan Template, organize a System Acceptance Plan, the third systems requirements activity, to describe how to accomplish the acceptance testing of the system or include the system acceptance criteria in the System Verification Plan. The System Verification Plan and System Acceptance Plan may be one document, especially for a low-risk project. Details of the System Acceptance Plan may be built into the RFP for a contractor to perform. Also, the System Verification Plan and System Acceptance Plan may be developed by a contractor, based on the RFP and as defined in the PSEMP.
2. RTVM Template
The RTVM is a document that links User Needs with Detailed Requirements and the System Verification process. The purpose of the RTVM is to ensure that all requirements are associated with User Needs and that all the Detailed Requirements defined for a system are verified through testing or observation. The RTVM is a tool for the verification team to ensure that all detailed requirements are included and none are left out during system development and testing. Detailed requirements should trace forward to tests and backwards to the User Needs. Detailed requirements are linked to User Needs with no user need going unaddressed.
The spreadsheet template for the RTVM is available in the RTVM tab. The RTVM has columns, or fields, for:
· User Need Identification Number
· User Needs
· Detailed Requirements Identification Number
· Detailed Requirements
· Document Section
· Detailed Requirements Source
· Verification Test Case ID from the Systems Verification Plan to ensure that requirements are met
· Degree of compliance (Yes, No, Partial or Not Applicable)
· Notes, comments and the date of review
· Signature of responsible persons.
An example of RTVM entries are shown below in the RTVM tab in this file..
The idea of the RTVM is to list all project requirements with a Verification Test Case. Later the reviewer(s) will perform the test, verify degree of compliance and initial the verification on the right.
The top five lines in the table are for task and project identification.
Line six, the column headers, shows the titles of the fields to fill out. Line six is organized into three sections, denoted by the header color:
· ​From the left, with a light blue highlighted header, are the User Need ID and User Need Summary (Columns A and B). ​
· Next, with the dark blue header, are the Detailed Requirement Summary, Document Section and Source Document columns (Columns C-F). ​
· ​After that, with the green header, comes the Verification columns for the Verification Test Cases, Compliance, Notes/Comments/date and sign offs by the contractor’s reviewer and the FDOT reviewer (Columns G-K). ​
2.1 User Needs
User Needs and their ID numbers (UNxxx) are listed in the ConOps. They are created and agreed upon by the project stakeholders to meet the project’s goals. User needs should be referenced accordingly in the RTVM along with the User Need ID number. Stakeholders are responsible for the list of User Needs, and developers of the RTVM who believe the project has additional User Needs should confer with stakeholders to have them added to the ConOps.
2.2 Detailed Requirements
2.2.1 Detailed Requirement Summary
Create a Detailed requirement ID for each Detailed Requirement. A Detailed Requirement specifies what an intended system should do or how it should perform. Requirements are generally written as a verb and a noun. Detailed requirements that meet User Needs come from the sources that FDOT uses as part of its Standard Specifications, District ITS Facilities Management, Software Architecture, RFP, etc. Give only enough detail to identify the requirement. Do not quote specifications from the source document.
2.2.2 Document Section and Source Document
List next the Document Section and Source Document. The Source Document and Document Sections columns should direct the preparer of the Systems Verification Plan and Systems Verification Test Case Table sufficiently to determine the complete test for the detailed requirement.
In the Document Section column (Column E) enter the section of the document cited. The Detailed Requirement Source Document (Column F) can come from a number of sources. Enter the source document from RFP, ITS FM, FDOT Standard Specifications, Software Architecture and so forth. Put the reference in the Detailed Requirement Summary in Column F and enter any acronym or abbreviation used in the Acronyms tab. The following discusses several Source Documents often used in an RTVM.
Request for Proposal (RFP)
RFP requirements are derived from the project plans and Minimum Technical Requirements (MTR) and Technical Special Provisions (TSP) and identify details needed for:
· Project Requirements and Provisions for Work - submittals, permits, meetings and progress reports, quality management plans, testing
· Design and Construction Criteria - utility coordination, design documentation, calculations, and computations, traffic control plans, signing and pavement marking plans, and ITS Plans and Designs for installation of equipment, ITS testing and acceptance, applicable versions of FDOT Standard Specifications, Design Manual, Design Standards and so forth.
Software Architecture
Software requirements are derived from the Transportation Management Center (TMC) operator needs and equipment interactions, the SunGuide software needs, and other system needs, such as Florida 511 system requirements. Changes to SunGuide software are also subject to the SunGuide change management process.
District ITS Facilities Management
Detailed Requirements can come from the FDOT District Geographic Information System (GIS) Facilities Management database for field equipment. These Detailed Requirements should include needed minimum equipment attributes and MTR or TSP requirements, as appropriate, from the District’s database.
FDOT Standard Specifications
These requirements come from the version(s) of FDOT Standard Specifications that will apply to the procurement contract. In developing the requirements, designers should review the equipment needs of the project with the FDOT Standard Specifications. The equipment, installation, testing, and warranty requirements should be listed, as needed in the Systems Verification Plan Test Cases, as appropriate.
Non-Standard Requirements
Non-standard requirements need to be specified sufficiently to identify what the system will do or be without a reference to a standard. This may especially be needed when a new technology system is required (e.g. for a connected vehicle (CV) requirement).
2.3 Verification
2.3.1 Verification Test Case ID
Verification Test Cases are developed in the System Verification Plan, Verification Test Case Table. Enter the Verification Test Case ID (TCxxx) from the Test Case Table.
2.3.2 Compliance
The Compliance column has a drop-down list button from which to choose whether the verification was in compliance (Yes or No), partially in compliance (Partial) or if compliance is not applicable (NA).
2.3.3 Comments
Notes/Comments/Date allow the reviewer to further qualify their review and to note the date.
2.3.4 Initials
The last two columns are for initialing the identity of the reviewer. The FDOT reviewer may be the project CEI.
Form FM-SE-22A Requirements Traceability Verification Matrix Guide. Effective 9/4/2019

## Acronyms
Acronyms | (These acronyms apply to the Guide tab. Add any that apply to the project RTVM, especially Source Documents (Column F))
APL | Approved Products List
CEI | Construction Engineering and Inspection
ConOps | Concept of Operations
CV | Connected Vehicle
FDOT | Florida Department of Transportation
GIS | Geographic Information System
ITS | Intelligent Transportation Systems
ITS FM | ITS Facilities Management
MTR | Minimum Technical Requirements
PSEMP | Project Systems Engineering Management Plan
RFP | Request for Proposals
RTVM | Requirements Traceability Verification Test Matrix
TMC | Transportation Management Center
TSP | Technical Special Provisions
Form FM-SE-22B System Validation Plan Template. Effective 9/4/2019

## Instructions
Instructions for Completing this Document
1 | Complete the Project Name, Project Description fields, and Project Manager fields
2 | For RTVM columns refer to the following:
A | User Need ID: A unique User Need (UN) ID number (UNXXX) identifies the UN from a tabular list in the ConOps.
B | User Need Summary: Enter a description of the User Need defined in the ConOps.
C | Detailed Requirement ID: A unique Detailed Requirement (DR) ID number (DRXXX) identifies the DR that addresses the User Need in the ConOps.
D | Detailed Requirement Summary: Enter a description of the detailed (functional or non-functional) requirement defined by a source document in Column E that addresses the User Need listed in Column A and B.
E | Document Section: Enter the Section of the document cited in Column F.
F | Detailed Requirement Source Document: Enter the source document, such as RFP, ITS FM, FDOT Standard Specifications, Software Architecture and so on.
G | Verification Test Case ID: Verification test cases are developed in the System Verification Plan, Verification Test Case Table. Enter the Test Case ID from the Test Case Table.
H | Compliance (Y/N/Partial/NA): Use the button on the right of the entry box to confirm whether the verification test done in Column F for Column D is compliant, non-compliant, partially compliant, or if the test is not applicable.
I | Notes/Comments/Date: Populate this column with additional observations about the test and the date.
J | Reviewer Initials: The person performing the test will enter his/her initials in this column.
K | FDOT Initials: The person confirming the test for FDOT will enter his/her initials in this column.
Form FM-SE-22B System Validation Plan Template. Effective 9/4/2019

## RTVM
REQUIREMENTS TRACEABILITY VERIFICATION MATRIX
Project Name: | < required >
Project Description: | < required >
Project Manager Name: | < required >
Agency/Firm: | < optional>
User Need ID | User Need Summary | Detailed Requirement ID | Detailed Requirement Summary | Document Section | DR Source Document | Verification Test Case ID | Compliance (Y/N/Partial/NA) | Notes/Comments/Date | Reviewer Initials | FDOT Initials
UN009 | Continuous electrical power and communications | DR001 | Install power service assembly | 639-3 | FDOT Standard Specs | TC015 | Yes | APL PRODUCTS USED | HAS
UN019 | Performance measures and system validation | DR002 | Send traffic measures of effectiveness (MOEs) to Regional Traffic Management Center (RTMC) Master Server and save for MOE report | Q - Testing | RFP | TC007 | Partially | APL PRODUCTS USED | HAS
UN002 | Closed-circuit television (CCTV) system oversight of highway and interchanges | DR003 | Furnish and install CCTV camera at locations shown in plans | 682-1 | FDOT Standard Specs | TC001 | Yes | APL PRODUCTS USED | HAS
UN003 | Microwave vehicle detection system (MVDS) system for real-time data | DR004 | Furnish and install microwave vehicle detection system at locations shown in plans | 660-2.2.1 | FDOT Standard Specs | TC002 | Yes | APL PRODUCTS USED | HAS
DR005
DR006
DR007
DR008
DR009
Form FM-SE-22B Requirements Traceability Verification Matrix. Effective 9/4/2019
Example: Lines 7-15
Note on K1: Steven Petty: I repositioned this title so that it wasn't cut off.
Note on A6: User Need ID: A unique User Need (UN) ID number (Unxxx) identifies the UN from a tabular list in the ConOps.
Note on B6: User Need Summary: Enter a description of the User Need defined in the ConOps.
Note on C6: Detailed Requirement ID: A unique Detailed Requirement (DR) ID number (DRxxx) identifies the DR that addresses the User Need in the ConOps.
Note on D6: Detailed Requirement Summary: Enter a description of the detailed (functional or non-functional) requirement defined by a source document in column E that addresses the User Need listed in Column A and B.
Note on E6: Document Section: Enter the Section of the document cited in Column F.
Note on F6: Detailed Requirement Source Document: Enter the source document, such as RFP, ITS FM, FDOT Standard Specifications, Software Architecture and so on.
Note on G6: Test Case ID: Test cases are developed in the System Verification Plan, Test Case Table. Enter the Test Case ID from the Test Case Table.
Note on H6: Compliance (Y/N/Partial/NA): Use the button on the right of the entry box to confirm whether the verification test done in Column F for Column D is compliant, non-compliant, partially compliant or if the test is not applicable (NA).
Note on I6: Notes/Comments: Populate this column with additional observations about the test and the date.
Note on J6: Contractor Initials: The person performing the test will enter their initials in this column.
Note on K6: FDOT Initials: The person confirming the test for FDOT will enter their initials in this column.