## ICE Guidelines
INTERSECTION CONTROL EVALUATION GUIDELINES
The staff hour ranges presented in this section represent the work effort that might be expected for individual design tasks on typical traffic projects. The ranges represent neither the minimum nor maximum hours that might be negotiated on a project for individual design tasks. Hours below or above the presented ranges may be applicable based upon the constraints or requirements that are specific to the individual project. Specific aspects of each individual project should be considered in negotiation hours for each individual task. Whenever possible, examples of individual tasks will be included to provide guidance in determining what types of effort are associated with each individual task.
A "Lower Range" roadway project may fall in the "Middle Range" for ICE projects and vice versa. See the project ranges below. The project ranges should be used only for Reference & Master Design Files and Quantities from Analysis. All other tasks should be defined on task by task basis and should not necessarily use the Project Ranges.
Lower Range
Stage 1: Screening (without DTOE or DDE approval)
Stage 1: Screening (with single selected control strategy w/ no-build)
Stage 1: Screening (with multiple suggested control strategies)
Middle Range
Stage 1: Screening (with additional data collection)
Stage 2: Preliminary Control Strategy Assessment (with single concept w/ no-build, cost, ROW, and environmental analysis)
Stage 2: Preliminary Control Strategy Assessment (with single concept w/ no-build, and additional data)
Upper Range
Stage 2: Preliminary Control Strategy Assessment (with multiple concepts and additional data)
Stage 2: Preliminary Control Strategy Assessment (with multiple concepts and public, local, road user engagement)
Stage 3: Detailed Control Strategy Assessment (with public outreach, development, costs, and environmental analysis - single w/ no-build)
Stage 3: Detailed Control Strategy Assessment (with public outreach, development, costs, and environmental analysis - multiple)
Stage 3: Detailed Control Strategy Assessment (revise design)

## ICE Analysis
Intersection Control Evaluation Analysis | [6 empty] | Min Totals | Max Totals
Task No. | New Task No. | Task | Units | Staff Hour Range | Basis for Staff Hour Range
0.1 | 0.1 | Traffic Data Collection | LS | See Basis for Staff Hour Range | This includes all efforts required to identify and document the project location, basic roadway characteristics, control and design vehicles, design and target speeds, peak hour volumes for design and opening years, growth rate, crash data collection/summarization, environmental data, multimodal use(s), and roadway context classifications. This effort is comprised of a desktop analysis (10 - 16 hours/intersection) as well as peak hour turning movement counts utilizing two people. (20 - 30 hours/intersection, plus 10 hours per additional person) |  | 30 | 56
Stage 1
0.2 | 1 | CAP-X Analysis | LS | See Basis for Staff Hour Range | Includes all efforts required for AM & PM Cap-X analysis. Input data from Task 0.1 into the FDOT CAP-X spreadsheet tool, select alternatives, and populating the lane input tab to aid in identifying various traffic control strategies. CAP-X rankings obtained from the CAP-X analysis spreadsheet will be input into ICE form. (2 - 6 hours per control strategy) | Assume One Control Strategy | 2 | 6 | Assume One Complex Control Strategy
0.3 | 1.1 | SPICE Analysis | LS | See Basis for Staff Hour Range | Includes all efforts required for SPICE analysis. Input data from Task 0.1 into the FDOT SPICE tool to analyze the safety aspect of viable alternatives, while applying engineering judgement in evaluating these aspects. (2 - 4 hours per control strategy) |  | 2 | 4
0.4 | 1.2 | Stage 1 Justification | LS | See Basis for Staff Hour Range | Includes all efforts required to complete the Stage 1 justification and package together the submittal. Input data from Tasks 0.1, 1.0, and 1.1 into the Stage 1 ICE form for DTOE and DDE concurrence and approval. Attach supporting documentation, including CAP-X and SPICE analysis spreadsheet output sheets and supporting data. Should the submittal be approved and signed, do not proceed to next Task. (2 - 4 hours per control strategy) |  | 2 | 4
0.5 | 1.3 | Stage 1 Comments and Edits | LS | See Basis for Staff Hour Range | Includes all efforts required to address all comments and feedback, and finalize the submittal. This task shall include minor changes to any Stage 1 tasks to finalize packet for DTOE or DDE approval. In the event of major changes, Stage 1 analysis should potentially be re-done. (0 - 4 hours per Stage 1 ICE Package) |  | 0 | 4
New | 1.4 | Quality Assurance / Quality Control / Supervision |  |  | Includes all efforts required to produce and implement a QA/QC plan. Includes review of ICE deliverable, verification that comments were addressed, etc. (4 - 10 hours per Stage 1 ICE Package) |  | 4 | 10
Stage 2 | [5 empty] | Stage 1 Total | 40 | 84
0.5 | 2 | Preliminary Conceptual Designs | LS | See Basis for Staff Hour Range | See ICE Plans tab for estimating hours to develop concept plans.
0.61 | 2.1 | Operational Analysis | LS | See Basis for Staff Hour Range | Includes all efforts in analyzing the Level of Service (LOS) and Total Delay from the AM/PM peaks of opening and design year operations for each selected control strategy. TMC's and growth trends from Task 0.1 should be utilized as well as modeling software such as Synchro, SIDRA, and HCS7. (2 - 6 hours per analysis) | 8 Analysis | 16 | 72 | 12 Analysis
0.62 | 2.2 | Safety Analysis | LS | See Basis for Staff Hour Range | Includes all efforts in re-analyzing the safety performance for the narrowed down selected control strategies by updating the Stage 1 SPICE tool from Task 1.2 to Stage 2. (1 - 2 hours per analysis) | 2 Analysis | 2 | 6 | 3 Analysis
0.63 | 2.3 | Cost Estimate | LS | See Basis for Staff Hour Range | Includes the creation of high-level engineers design, right-of-way, and construction costs for each selected control strategy where a concept was developed. (2 - 6 hours per control strategy) | 2 Analysis | 4 | 18 | 3 Analysis
0.64 | 2.4 | Benefit-Cost Analysis | LS | See Basis for Staff Hour Range | Includes all efforts required to evaluate the Delay, Safety, and Overall Benefit-Cost ratio of each control strategy by inputting data from the Cost Estimate analysis into the ICE Tool. Demand counts from Task 0.1, Delay output from Task 2.1, SPICE output from Task 2.2, and Cost parameters from Task 2.3 are input into the ICE Tool spreadsheet. The spreadsheet then outputs Net Present Value of Costs and Benefits. (2 to 5 hours per control strategy) | 2 Control Strategies | 4 | 16 | 3 Control Strategies
0.65 | 2.5 | Environmental, Utility, and Right-of-Way Impact Analysis | LS | See Basis for Staff Hour Range | Includes all efforts required to evaluate and summarize any impacts of the proposed control strategy to the surrounding environment or adjacent properties. A broad overview summary of the impacts the of the proposed control strategy while focusing on social, natural, or physical environment impacts which may preclude the advancement of a particular alternative control strategy. (1 - 5 hours per control strategy) | 2 Control Strategies | 2 | 16 | 3 Control Strategies
0.66 | 2.6 | Multimodal Accommodation Analysis | LS | See Basis for Staff Hour Range | Includes all efforts required to evaluate and summarize any multimodal accommodations have for each proposed control strategy. A broad overview summary of the pedestrian and bicycle activity levels, accommodations, transit services near the intersection, and freight needs. (1 - 5 hours per control strategy) | 2 Control Strategies | 2 | 16 | 3 Control Strategies
New | 2.7 | Agency Coordination and Public Input |  |  | Includes all efforts required to coordinate meetings with agency staff and public. Should coordination need to occur, each meeting is allotted 8 hours for a maximum of two meetings. (0 - 16 hours per evaluation) |  | 0 | 16
0.67 | 2.8 | Stage 2 Justification | LS | See Basis for Staff Hour Range | Includes all efforts required to complete the Stage 2 justification. Input the findings from all previous tasks into the Stage 2 ICE form for DTOE and DDE concurrence and approval. Provide brief justification as to why each control strategy is viable or not. Attach supporting documentation and data. (2 - 5 hours per control strategy) | 2 Control Strategies | 2 | 16 | 3 Control Strategies
0.41 | 2.9 | Stage 2 Comments and Edits | LS | See Basis for Staff Hour Range | Includes all efforts required to complete and wrap up all District comments and feedback, and finalize the submittal. This task shall include minor changes (including concept re-design) to all Stage 2 tasks to finalize packet for DTOE and DDE approval. In the event of major changes, Stage 2 analysis should be re-done. (5 - 20 hours per Stage 2 ICE Package) |  | 4 | 20
New | 2.91 | Quality Assurance / Quality Control / Supervision |  |  | Includes all efforts required to produce and implement a QA/QC plan. Includes review of ICE deliverable, verification that comments were addressed, etc. (2 - 8 hours per Stage 2 ICE Package) |  | 4 | 10
Stage 3 | [5 empty] | Stage 2 Total | 64 | 256
0.7 | 3 | Detailed Control Strategy Assessment | LS | See Basis for Staff Hour Range | All efforts required to conduct a more detailed assessment of remaining viable control strategies. This may involve the collection of additional data, further public outreach, developing more detailed designs, conducting more detailed operational analysis, more detailed cost estimates, further environmental analysis, and any other activities necessary to identify the preferred control strategy. (This task is scope specific with no staff hour range. Staff hours will be developed on an individual case-by-case basis based on the level of outstanding issues from proposed strategies.)
0.8 | 3.1 | Stage 3 Justification | LS | See Basis for Staff Hour Range | Includes all efforts required to complete the Stage 3 justification. Input data from additional analysis into the ICE forms for DTOE and DDE concurrence and approval. Provide brief justification as to why each control strategy was re-analyzed and why it is viable or not. Attach supporting documentation and data. (0 - 5 hours per intersection)
0.41 | 3.2 | Stage 3 Comments and Edits | LS | See Basis for Staff Hour Range | Includes all efforts required to complete and wrap up all District comments and feedback, and finalize the submittal. This task shall include minor changes (not including concept re-design) to all Stage 3 tasks to finalize packet for DTOE or DDE approval. (5 hours per Stage 2 ICE Package)
New | 3.21 | Quality Assurance / Quality Control / Supervision |  |  | Includes all efforts required to produce and implement a QA/QC plan. Includes review of ICE deliverable, verification that comments were addressed, etc. (2 - 8 hours per Stage 3 ICE Package)
Note: Task No. column will be removed once all the comments are closed. | [5 empty] | Range is based on complexity of study
[6 empty] | Total | 104 | 340
[6 empty] | Average | 222

## ICE Plans
Intersection Control Evaluation Plans
Task No. | Task | Units | Staff Hour Range | Basis for Staff Hour Range
0.01 | No-Build Plan Sheet | Sheet | 4 to 10 | Includes work for developing existing conditions (no-build) plan sheet of the study location. Consists of background aerial, right-of-way boundaries, and labeling. Part of Stage II analysis concept plan creation. | Assume No Build + One Control Strategy | 24 | 50 | Assume No Build + Two Control Strategies
0.02 | Concept Plan Sheet | Sheet | 10 to 20 | Includes work for developing concept plan sheet for each proposed alternative. Consists of background aerial, right-of-way boundaries, labeling, and shaded concept of proposed alternative. Based on the number and complexity of alternatives proposed. Part of Stage II analysis concept plan creation. Note: these hours are for typical alternative intersections. However, if new alternative intersections are introduced, the hours may need to be adjusted accordingly.
0.03 | Concept Re-Design | Sheet | See Basis for Staff Hour Range | Includes all changes major and minor to initial concept based on findings from Stage II analysis. Use 2 - 15 hours per alternative based on number of alternatives being re-designed and their complexity. Part of Stage III analysis concept plan re-design.